GEF-6 Project Identification Form (PIF)

Project Type: Medium-sized Project

Type of Trust Fund: GEF Trust Fund

For more information about GEF, visit TheGEF.org

PART I: PROJECT INFORMATION

| Project Title: | Integration of Natural Capital Accounting in public and private sector policy and decision-making for sustainable landscapes (former title: Integrating Natural Capital and Sustainable Rice Production in Thailand – ‘NCSRP project’) |  |  |  |
| --- | --- | --- | --- | --- |
| Country(ies): | Thailand | GEF Project ID: |  | 9542 |
| GEF Agency(ies): | UNEP | GEF Agency Project ID: |  | 01438 |
| Other Executing Partner(s): | Ministry of Natural Resources and Environment (MoNRE), Ministry of Agriculture and Cooperatives (MoAC) | Submission Date: |  | 7 July 2016 15 August 2016 28 August 2016 11 Nov 2016 18 Jan 2017 |
| GEF Focal Area(s): | Biodiversity | Project Duration (Months) |  | 54 |
| Integrated Approach Pilot | IAP-Cities IAP-Commodities IAP-Food Security |  | Corporate Program: SGP |  |
| Name of parent program: |  | Agency Fee ($) |  | 190,000 |

A. indicative Focal Area  Strategy Framework and Other Program Strategies

| ### Objectives/Programs (Focal Areas, Integrated Approach Pilot, Corporate Programs) | ### Trust Fund | ### (in $) |  |
| --- | --- | --- | --- |
|  |  | ### GEF Project Financing | ### Co-financing |
| BD-4 Program 10 | GEFTF | 2,000,000 | 8,150,000 |
| Total Project Cost |  | 2,000,000 | 8,150,000 |

B. indicative Project description summary

| ### Project Objective: To alleviate threats to biodiversity and ecosystem services in critical production landscapes in Thailand by integrating values of forests and other Natural Capital into policies and operations of key economic sectors |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| ### Project Components | ### Finan-cing Type | ### Project Outcomes | ### Project Outputs | ### Trust Fund | ### (in $) |  |
|  |  |  |  |  | ### GEF Project Financing | ### Co- financing |
| 1. Policies and market incentives in support of integrating Natural Capital into key economic sectors (agriculture, tourism, water services) | TA | 1.1 Three national economic sectors are aware of their impact and dependency on NC, and enabled to integrate NCA in policies, plans and budgets, 1.2 Increased national/provincial budgets and institutional capacity benefitting biodiversity conservation and ecosystem services in support of NC-dependent sectors. Reduction in NC & biodiversity- harmful financial incentives Increase in fiscal measures and/or budgets benefitting NC | 1.1.1 Assessment of the status of provision of ecosystem services, highlighting dependencies and values with 3 economic sectors and their role in a national transformation towards a Green Economy. 1.1.2. National - sector roundtables and 3 sector reviews to highlight ecological footprints, corporate/ investment risks related to NC, and identification of entry points and opportunities for mainstreaming NC values into sectoral policies. 1.1.3. Targeted 3 national sector policies or plans adopted /modified that promote and incentivize actions to ensure sustainable management of critical NC through valuation and/or accounting. 1.2.1. Development of a national Natural Capital Account that highlights the contribution of NC to key economic sectors. 1.2.2. Establishment of institutional mechanism and enhanced capacity for NC responsive Government’s budgeting, and fiscal policy processes. | GEFTF | 590,290 | 3,500,000 |
| 2. Integration of Natural Capital Accounting into government development plans and operations of targeted economic sectors at landscape level. | TA | 2.1. Enhanced incorporation of the value of NC including biodiversity, in provincial government plans and corporate decision making, leading to increased investments in NC Two provincial development or investment plans adapted protecting or restoring NC including BD Integration of NC values, corporate risks and protection into at least four (4) new company sustainability/business plans and/or transactions of financial institutions Critical ecosystem services and NC protected or restored in at least 40,000 ha in two land & seascape(s) as against baseline 5% increase in financing for NC and biodiversity management in two selected provinces and/or land/seascapes Management effectiveness of 1 PA enhanced through improved bufferzone & landscape/seascape NC utilisation, policy and financing | 2.1.1 Adoption of or amendments to two provincial development or investment plans based on NCA, and enhanced multi-agency collaboration to ensure integration of NC in investment decisions and operations of key sectors at landscape level. 2.1.2. Integration of NC values in four corporate risk analyses, sustainability/business plans and sustainability reporting of the private sector and financial institutions to – minimize negative impacts to biodiversity and other critical.NC 2.1.3 Public-private partnership, NC responsive budgets and market-based mechanisms applied to two priority land/seascapes, one PA and two sectors - protecting or restoring critical ES (determined by NCA) | GEFTF | 750,892 | 2,410,000 |
| 3. Dissemination of information, awareness raising and networking for mainstreaming of NCA | TA | 3.1 M&E providing the quantitative benchmarks on BD, NC values and adoption of NCA practises through project investments. 3.2. Partnerships, knowledge and acceptance of NCA built, and best practices widely communicated for upscaling. | 3.1.1. Sector-specific M&E tracking and impact monitoring system developed and capacity built on quantification of benefits to NC (incl.BD & ecosystem services); including changes in sectoral plans, budgets and operations that adopted NCA and preservation of ES. 3.1.2 Project M&E system generating information on project progress, impact and management performance. 3.2.1. Development and implementation of a communication outreach and engagement strategy for sectorwide adoption of NCA, based on results of M&E and best practise. 3.2.2. Establishment of a mechanism and online knowledge sharing platforms to facilitate networking among policy makers, practitioners and corporate sector in Thailand, to exchange their knowledge and experiences in mainstreaming NCA into sectoral planning processes and business/financial sector operations. | GEFTF | 477,000 | 1,500,000 |
| Subtotal |  |  |  |  | 1,818,182 | 7,410,000 |
| Project Management Cost (PMC) |  |  |  |  | 181,818 | 740,000 |
| Total Project Cost |  |  |  |  | 2,000,000 | 8,150,000 |

C. Indicative sources of  Co-financing for the project by name and by type, if available

| Sources of Co-financing | Name of Co-financier | Type of Co-financing | Amount ($) |
| --- | --- | --- | --- |
| Recipient Government | Office of Natural Resources and Environmental Policy and Planning | Unknown | 7,500,000 |
| Recipient Government | Rice Department, Ministry of Agriculture and Cooperatives (MOAC) | Unknown | 500,000 |
| GEF Agency | UNEP (e.g. Sustainable Rice Platform. TEEB, SEEA, Regional Office) | In-kind | 150,000 |
| Total Co-financing |  |  | 8,150,000 |

D. Indicative Trust Fund  Resources Requested by Agency(ies),  Country(ies) and the Programming of Funds

| GEF Agency | Trust Fund | Country/ Regional/ Global | Focal Area | Programming of Funds | (in $) |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | GEF Project Financing (a) | Agency Fee (b) | Total (c)=a+b |
| UNEP | GEFTF | Thailand | Biodiversity |  | 2,000,000 | 190,000 | 2,190,000 |
| Total GEF Resources |  |  |  |  | 2,000,000 | 190,000 | 2,190,000 |

E.  Project preparation grant (ppg)

Is Project Preparation Grant requested? Yes    No  If no, skip item E.

PPG  Amount requested by agency(ies), Trust Fund,  country(ies) and the Programming  of funds

| Project Preparation Grant amount requested: $50,000 PPG Agency Fee: $4,750 |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| GEF Agency | Trust Fund | Country/ Regional/Global | Focal Area | Programming of Funds | (in $) |  |  |
|  |  |  |  |  | PPG (a) | Agency Fee (b) | Total c = a + b |
| UNEP | GEF TF | Thailand | Biodiversity |  | 50,000 | 4,750 | 54,750 |
| Total PPG Amount |  |  |  |  | 50,000 | 4,750 | 54,750 |

F.  Project’s Target Contributions to Global Environmental Benefits

Provide the expected project targets as appropriate.

| Corporate Results | Replenishment Targets | Project Targets |
| --- | --- | --- |
| Maintain globally significant biodiversity and the ecosystem goods and services that it provides to society | Improved management of landscapes and seascapes covering 300 million hectares | 40,000 hectares |

part ii:  project JustiFication

1. Project Description.

1.1. Global environmental and/or adaptation problems, root causes and barriers that need to be addressed

    - Global environmental problems and threats:

Background and GEB:  Thailand is one of the most biodiverse countries in Southeast Asia, and located within two major biogeographical regions – the Indochinese region in the north and the Sundiac region in the south. With 15 mountain ranges, its various watersheds and main river basins connected to the Mekong River, the Gulf of Thailand and Andaman Sea form a juncture of distribution for various plant species, such as temperate plant species and sub-alpine flora species from China and the Himalayas, tropical plant species from Indo-China and tropical species from other parts of Asia. In consequence, this area is one of the most biodiverse in the world. Thailand contains around 15,000 plant species, representing 8% of the world’s total. Forest area covers at least 33% of the country’s total area, with at least 18% comprised of conserved forests. According to WWF-Thailand, Thailand hosts numerous protected areas covering 20% of the territorial area including 26 marine national parks, 13 wetlands of international importance, 2 natural world heritage sites, and 4 biosphere reserves.

Threatened species in Thailand are numerous, consisting of 121 mammals, 184 birds, 33 reptiles, 5 amphibians, 218 fishes and no fewer than 1,131 plant species. The numbers of wild elephants are estimated at between 1975 and 2380; wild buffalo numbers remain between 50 and 70, and tigers between 200 and 500, while guars and bantengs remain at around 200. The kouprey, eld’s deer and java rhino have not been reported in the wild for a long time; the number of Irrawaddy dolphins is plummeting too. Some freshwater fish species have become extinct and there are more than 20 endangered species listed. Thailand’s unique biodiversity is supported by a large variety of ecosystems, landscapes and habitats, most of which are also greatly threatened by human activity. In 1961, Thailand had a lush forest covering 53.35% of the country; however, by 2009, terrestrial forest cover had decreased to 32.1%. Thailand is also an agrobiodiversity sanctuary for world rice landraces. However, farmer preference to grow high-yielding varieties rather than indigenous varieties is causing rapid genetic erosion.

Thailand’s unique coastal and marine biodiversity remains highly threatened by impacts of economic development, brackish water shrimp farming, construction of residential areas and industrial estates. Factories conversion and reclamation perhaps best exemplified by the rapid losses in mangrove forest cover and habitat quality. Beaches and reefs have been heavily impacted all over the country due to massive tourism development, settlements and port activities. At present, only a few undisturbed beach forests remain, most located in the national marine parks. A survey undertaken in 2006 revealed that only 40% of the seagrass bed in the Gulf of Thailand was in good condition, while this figure was only 20% in the Andaman Sea. Suratthani province has the largest area of coral reefs, equivalent to 25% of the national total. However, a survey conducted in 2007 indicated that only 5% of coral reefs in the Suratthani are considered in good condition, 24% in fair condition, 52% in poor condition and 13% in very poor condition.

Economic vulnerability of key sectors due to loss of Natural Capital (NC): NC - the stock of natural ecosystems such as forests, wetlands or agro-production systems, yields a flow of ecosystem services that provide the foundation for our economy and human well-being. Yet growing demand for food, energy and other natural resources has led to ecosystem degradation and biodiversity loss at an alarming rate; with causal factors well documented in the Millennium Ecosystem Assessment (MA). Although The Economics of Ecosystems and Biodiversity (TEEB 2010) highlighted the multi-trillion dollar annual contribution of natural capital to the global economy, the top global 100 environmental externalities are costing the global economy approximately USD 4.7 trillion a year through impacts of air pollution, climate change and particularly through loss of natural capital (Trucost). These studies led to increased recognition within the corporate sector of the economic values of biodiversity and ecosystem services, their dependencies on them, and moreover, the need to incorporate those values into their own corporate and financial sector operations as well as into public polices and national accounting systems.

Key economic sectors in Thailand such as agriculture, tourism and water services sectors depend on multiple ecosystem services and benefits provided by the NC contained in natural and production landscapes. Some of the well-known dependencies of agroecosystems include those related to hydrologic services, pollination, soil structure and fertility enhancement- all critical to sustaining agricultural production in Thailand and hence highlighting the need for a landscape approach. The diversity of ecosystem services and disservices to and from agroecosystems is summarized in the Figure below, which highlights the dependencies of agroecosystems on ecosystem services such as hydrology, pollination, soil structure and soil fertility- all critical to sustaining agricultural production and hence highlighting the need for the landscape approach. Conversely, poor management of agricultural ecosystems can impact adversely upon the flows of ecosystems and disservices from production landscapes to surrounding areas, including subsequently affecting other economic sectors such as water services and tourism that also depend on ecosystem services provided by healthy NC in production landscapes. As an example, the intensification of rice production in Thailand has led to serious degradation of the many ecosystem services delivered to other sectors, e.g. in preserving biodiversity, providing freshwater, through regulating functions, or through the aesthetic and recreational value of rice landscapes for eco-tourism.

Ecosystem services and disservices to and from agricultural production systems

The (irrigated) agriculture sector exhibits strong ecosystem services impacts as well as dependencies on healthy forested watersheds to guarantee a steady supply of water resources for production. Those linkages are presently not incorporated in market mechanisms or payment for ecosystem services, nor adequately embedded in sustainable landscape management practices in Thailand. Building a stronger economic case between the production sector and the ecosystems and services on which it depends or which they impact should be incorporated in corporate risk management strategies as well as NC-based landscape management principles and practices.

Though food production is the most important provisioning ecosystem service delivered by production landscapes such as rice, it is important to understand the other two categories of ecosystem services, and the tradeoffs among them. Berg et al. (2012) point out that future production systems should be optimized not purely to maximize productivity, but should instead be designed to sustain (rather than maximize) productivity while also delivering a variety of interlinked ecosystem services, or ‘bundles’ of services, such as in-field fish production, pollination, water provision, regulation and purification, genetic diversity, pest control, nutrient cycling and natural hazard regulation.

In many cases, the benefits of such ecosystem services may be felt far outside the perimeter of the farm or landscape, and may even accrue to other actors or economic sectors such as tourism, water and public health. In view of these complex linkages and inter-relationships, it is essential to understand the overall impacts and distributional effects of land use decisions on the status of biodiversity and ecosystem services, in order to (a) achieve sustainable management of natural capital at the landscape level, and (b) to catalyze appropriate policy changes (e.g. to promote sustainable food production systems, sustainable management of land and water resources, and adoption of landscape level planning, taking into account forest habitat connectivity, land fragmentation, and other factors).

Whilst natural forests account for about one-third of the land area of Thailand, forest loss remains a major challenge due to population pressure and demand for land for industrial crop production, tourism infrastructure and urban expansion. As a result, the country’s forest areas declined significantly over the past 40 years, from 221,707 sq km in 1973 to 163,393 sq km in 2013. Deforestation in upstream watersheds changes hydrological regimes and water supply, which can lead to floods and drought, as well as rising underground water tables in downstream agricultural or urban areas. Sectors such as urban and industrial water supply, agriculture – specifically irrigated rice, but also tourism, are critically dependent on healthy (forested) watersheds including stable and adequate water availability; it is therefore in the interests of these nationally-important economic sectors to maintain the quantity and quality of natural capital such as forest ecosystem services. Healthy (forested) landscapes also play an essential role in supporting a diversity of flora and fauna and deliver other critical ecosystem services such as aesthetic and recreational services and values. Extensive loss of forest cover as well as forest degradation in Thailand have contributed to seasonal floods (as were experienced in late 2011) as well as  increasing water scarcity during seasonal droughts (as experienced in 2015 and 2016). The economic loss in Thailand caused by deforestation is significant. The Thailand Development Research Institute (TDRI, 2006) analysed the value of forests, including the loss of use and non‐use values. Based on detailed analysis of the Khao Yai National Park, the total value of deforestation is approximately USD 2.13 billion per year when extrapolated to the total of 4.08 million hectares deforested (national desired forest area minus remaining forest area).

In addition to forest ecosystems, marine and coastal ecosystems in Thailand have also been in continuing decline. Fishery-based industries and tourism depend on healthy NC including the ecosystem services provided by reefs, mangroves and seagrass meadows. As mentioned previously, these ecosystems are under threat from a broad range of disturbances contributing to declines in fish and shellfish production and reduced revenues for local communities. A study conducted in Surat Thani Province estimated the value of the welfare impacts of mangrove deforestation on coastal, mangrove-dependent fisheries as $33–$110 per hectare deforested.

In 2011, Thailand witnessed its worst flooding in half a century, leaving severe impairments to the country’s economy, industrial sector, and society. Both natural and manmade factors contributed to the crisis, including deforestation and watershed degradation, as well as inadequate coordination of river basin management. The resulting inability to effectively manage discharge led to inundation of 9,065,200 hectares of land (18% of the country), and the flooding was ranked as the world’s fourth costliest disaster as of 2011 (Geo-Informatics and Space Technology Development Agency). The flooding impacted a total of 4,039,459 households; 2,329 houses were completely destroyed and 96,833 partially damaged; with a total death toll of 657 people. The Word Bank estimated damages to have reached USD 48 billion. Economic recovery remains fragile due to the impact on confidence of investors and insurance companies. Tourism suffered losses estimated at USD 123.6 million and a fall of 3.2 million tourists.

Impact of selected economic sectors to natural capital, ecosystem services and biodiversity: The project will focus on three sectors: tourism, agriculture/rice, and water services. Thailand’s tourism industry plays a key role in the national economy, contributing 44% of GDP and providing an important source of foreign exchange revenue. Tourism is a prime beneficiary of cultural services provided by ecosystems (e.g. recreation, scenic and spiritual values of the land and waters) but also provisioning services due to the dependency and high water use of the hotel and tourism sector. Tourism in Thailand has shown an increasing trend of 15.9 million, 19.2 m, 22.3 m and 26.5 m visitors in 2010, 2011, 2012 and 2013, respectively. However, as mentioned earlier, this rapid and often uncontrolled growth of tourism has led to severe impacts on biodiversity and ecosystems, particularly in coastal tourist destinations. This is especially evident in destinations such as Koh Chang (Trat), Koh Samet (Rayong), Pattaya (Chonburi), Cha-am (Petchaburi), Hua Hin (Prachaub Kirikhan), Koh Samui (Surat Thani), Patong (Phuket), Koh Phi-Phi (Krabi) which are now densely urbanized and have lost much of their original pristine natural beauty. Over-exploitation of coastal tourism destinations beyond the ecosystem carrying capacity (especially with regard to water resources and waste treatment) has imposed intolerable pressures on natural capital, with serious long-term ecosystem impacts. Much of the negative development in some of the islands has taken place in Protected Area or protected forest (watersheds). Unmanaged, illegal and inadequately regulated construction in these sites has led to over-commercialization of fragile coastal ecosystems, resulting in impacts such as algal blooms, habitat loss for marine and coastal species (e.g. sea turtles, dugong, whales, coral reefs) and loss of natural beach vegetation. This continuing loss of ecosystem services is compounded by weak regulation; for example, conservation areas and agricultural land (e.g. Agricultural Land Reform areas) have been illegally appropriated by investors for commercial development of resorts and recreation estates. The resulting degradation and fragmentation of ecosystems frequently translates into permanent loss of livelihoods for fishers and farmers, flooding or prolonged drought due to lack of surface water resources, as well as degradation of the quality of the tourist destinations themselves.

Thailand is also a major global agriculture producer and exporter of crops, including rice, brackish water shrimp, tropical fruits, natural rubber, palm oil, cassava and maize. The related areas of production have expanded due to enhanced market access, widespread introduction of contract farming, and government subsidies. Rice dominates many of Thailand’s rural landscapes; however, intensification of production has led to serious impacts on ecosystem services delivered by these landscapes, e.g. in preserving biodiversity, providing freshwater, through regulating functions, or through the amenity value of rice landscapes for eco-tourism. Degradation in either the quality or quantity of NC including of their ecosystem services provided, either within or arising from production landscapes, such as water resources for irrigated rice production, carries significant implications for quality of life and well-being of farming communities, e.g. due to floods, drought, pests and diseases. Conventional farming practices, e.g. burning harvesting waste, inefficient irrigation, and excessive use of chemical inputs not only increase costs, but also contribute to a negative GHG balance. Introduction of ecologically friendly practices such as applying the Sustainable Rice Standards facilitated through this project can support the twin goals of climate change  mitigation as well as reducing the impact of the rice sector on downstream ecosystem services.

Threats to NC, biodiversity and ecosystem services in the three suggested provinces: The project will target two of the three provinces listed below, Chiang Rai, Chonburi and Trat, as provisionally proposed by the GoT. These have their own specific baseline situation related to status and problems of forests, biodiversity conservation, as well as key NC-dependent sectors. The final selection of the targeted provinces and land/sea scapes will be done during the PPG.

In 2014, Chiang Rai province had 480,116 hectares of forests, compared with 510,146 million hectares in 2004, a decline of 6% over 10 years, largely attributed to development for tourism and commerce, as well as huge swathes of forests and scrubland converted to agriculture. Chiang Rai is rich in biodiversity, however it also harbors at least 18 global and national threatened species and one endemic species (Banded Slender Skink - Lygosoma haroldyoungi), including mammals: Common Otter (Lutra lutra)-NT, Assamese Macaque (Macaca assamensis)-NT, Tiger (Panthera tigris) –EN, White Handed Gibbon (Hylobates lar) –EN, Asiatic Black Bear (Ursus thibetanus)-VU, Hog badger (Arctonyx collaris) –NT, and Sumatran Serow (Capricornis sumatraensis); birds: Sarus crane (Grus antigone) and White-shouldered Ibis (Pseudibis davisoni), both extinct in the wild in Chiang Rai; Mrs. Hume’s Pheasant (Syrmaticus humiae)-NT, Blyth’s Kingfisher (Alcedo Hercules)-NT, Black-bellied Tern (Sterna acuticauda)-EN; Baer's Pochard (Aythya baeri)-CR, Black-headed Ibis (Threskiornis melanocephalus)–NT, Jerdon’s Bushchat (Saxicola jerdoni)–LC, Giant Nuthatch (Sitta magna)–EN; and Swan Goose (Anser cygnoides) –VU.

The province has four protected areas including the Nhong Bong Khai Non-hunting Area, a wetland supporting e.g. the migratory Baer's Pochard bird (Aythya baeri), listed as vulnerable; the Luang National Park, which harbours a population of tiger (Panthera tigris); the Khun Chae National Park, with e.g. significant species like Slow Loris, White Handed Gibbon (Hylobates lar), Leopard Cat (Prionailurus bengalensis), and Sumatran Serow (Capricornis sumatraensis); and the Lam Nam Kok National Park with rich Dipterocarp forests. This province has been suggested by the GoT specifically with regards the project target of linking biodiversity conservation and NC dependencies of the tourism, rice and water services sectors with well managed and fiscal/policy supported Sustainable Forest Management mechanisms. This will be reconfirmed or may be changed during the project preparation phase consultation process.

Chonburi province had 54,349 hectares forests in 2014, up 12.5% from 48,268 hectares in 2004 as a result of major replanting of wood and paper pulp plantations. The province has both upland and flat land areas, as well as a long coastline and 47 islands popular with the tourism sector, including 3 large ones: Khram Island (important for turtle nesting in Gulf of Thailand), Si Chang Island, and Larn Island. The province’s main environmental challenges include solid waste management, coastal degradation and water pollution.  In 2010, municipalities including Pattaya generated about 16,620 tons/day (representing 40% of municipal waste generated throughout the country); whilst coastal degradation has resulted from unfettered infrastructure development. Notwithstanding its heavy urban development, the province contains a number of diverse natural habitats important for maintaining threatened wildlife species (12 species listed on IUCN Red Data Book) and 4 endemic species: Slender-tailed Four-clawed Gecko (Gehyra angusticaudata), Western Four-clawed Gecko (Gehyra lacerate), Roule’s Legless Skink (Isopachys roulei)-DD; and the Triangle Blackhead (Sibynophis triangularis) –NT. Of the 12 threatened species highlights include: Irrawaddy dolphin (Orcaella brevirostris) –VU; Dugong (Dugong dugon) –VU;  Pileated gibbon (Hylobates pileatus)-EN; Hog deer (Hyelaphus porcinus)- EN,; Manchurian Reed Warbler (Acrocephalus tangorum) –VU; Island rat (Rattus remotus) – LC; Large Flying Fox (Pteropus vampyrus) –NT; Southeastern Leaf Turtle (Cyclemys atripons) –NA; Small Flying Fox (Pteropus hypomelanus)-LC; Lyle’s Flying Fox (Pteropus lylei) –NT; Southern Butterfly Lizard (Leiolepis belliana belliana)-NA; and Small spotted Coral Snake (Calliophis maculiceps) –LC.

Chonburi province has four protected areas and one National Park. Some of these protected areas such as the Khao Chao Bor Thong Waterfall National Park are key to protecting important forested catchment for water supply downstream, as well as providing a recreational function for the millions of tourists who visit the province annually. The Khao Kheow and Khao Chompoo Wildlife Sanctuary have good quality Tropical Moist Evergreen Forest (80% of the WS); fauna found here include Barking Deer, Leopard, and Leaf Monkeys. The park experiences continuing challenges with poaching, as well as in managing the increasing tourism pressure. Khao Kheow is well known as an Open Safari Park and is eastern Thailand's ecotourism hotspot. This province has been proposed by the GoT as the focus of a project to enhance protection of the remaining forest and coastal / marine resources, through linking ecosystem services, specifically water and recreational services, valuation and policies with the tourism and water services sectors.

Trat province, is bordered by Chantaburi province to the northwest, Cambodia to the east – including its proximity to  the biodiverse and famous Cardamon Mountains to the east, and the Gulf of Thailand to the south. It has some of the more intact forests remaining in Thailand, with over 31% of the province or 90,179 ha of mostly Moist Evergreen Tropical Forest (2015). The province of 286,600 hectares has over 55 islands, and has 41% under agricultural use. The mainland is mainly utilized for fruit farming (durian, rambutan, mangosteen, lonkong etc.) and other minor crops rather than rice farming or livestock. The province is also known for mining, including for precious stones. Fisheries and tourism are the main activities on the main islands such as Koh Chang, much of whose lowland coastal forests have been lost due to expansion  of hotels and tourism facilities. Nevertheless, Trat is a rather ‘green’ province compared to many areas of the country,due to its beautiful and abundant natural resources including pristine lowland and mangrove forests, important river systems and abundant reefs. The  designation of the province as a sustainable tourism destination by the National Tourism Authority of Thailand highlights its potential for linking sustainable tourism and fisheries development with protecting its natural capital, especially mangroves, reefs and forests, that are key to maintaining water resources. It has two National Parks. The Mu Koh Chang National Marine Park with an area of 65,000 hectares including more than 52 islands, was established in 1982 to protect its reef habitats, and is an IUCN Category II protected area. The Namtok Khlong Kaeo National Park (20,000 hectares) comprises several densely forested mountain ranges including Khaokaw, Tabard, Tachoat  and Kampang mountains, a watershed which also serves as the border between Thailand and Cambodia. Trat province is rich in biodiversity; however it also harbors at least 10 global and national threatened species and two endemic species, the Triangle Blackhead (Sibynophis triangularis) as well as the endemic Ko-Chang-frog (Rana kochang);  including the Tiger (Panthera tigris) – EN, Large Flying Fox (Pteropus vampyru) -VU, Northern Smooth-tailed Treeshrew (Dendrogale murina) –VU,  Small Flying Fox (Pteropus hypomelanus) – NT, Silvered Leaf Monkey (Semnopithecus germaini) – NT, Sumatran Serow (Capricornis sumatraensis), various species of Gibbon, Common Munjak, and Mouse Deer; Indochinese Water Dragon (Physignathus cocincinus) – EN, and Southeastern Leaf Turtle (Cyclemys atripons) – VU.

Prospects for NC and the landscape approach: Notwithstanding continuing wide-scale environmental degradation, Thailand derives large benefits from ecosystems. In view of the complex linkages and inter-relationships that govern the delivery of ecosystem services, it is essential to understand the overall impacts and distributional effects of key economic sectors and land use decisions on the status of biodiversity and ecosystem services, in order to (a) achieve sustainable management of natural capital at the landscape level, and (b) to catalyze appropriate policy changes (e.g. by promoting sustainable food production systems, sustainable management of land, forest and water resources, and adoption of landscape level planning, taking into account forest habitat connectivity, land fragmentation, and other factors).  In particular, the country recognizes the important environmental role performed by watersheds, river basins and coastal areas, as well as their significance in supporting livelihoods linked to fisheries, recreation and tourism, among many others. Likewise, the national government of Thailand recognizes that forest ecosystems ecological services that benefit agriculture, industries, water and power needs, yet has been struggling to mainstream this understanding into action in its key economic sectors, its related production landscapes and with responsible sector agencies such as tourism, rice and water services.

    - Root causes and fundamental barriers:

The proposed project will address three major barriers:

Barrier 1: Limited integration of NC into Thailand’s national policy, budgets and institutional mechanisms:

In Thailand, there is general awareness of an environmental role performed by watersheds, river basins and coastal areas and their significance for supporting people’s livelihoods with links to agriculture, fisheries, recreation and tourism, among others. Although the Government of Thailand recognizes forest ecosystems and their ecological services that benefit agriculture, industries, water and power needs, this general awareness has yet to be translated into policies and operations of key economic sectors and in managing production landscapes. This is partly due to limited availability of a strong evidence base highlighting inter-relationships, dependencies and potential impacts of economic sectors on NC provided by production landscapes. In general, natural capital values are not internalized into public and private sector decision making, policies and operations. There is a particular gap in credible information on natural capital values relating to non-market values of biodiversity and ecosystem services delivered by production landscapes. In terms of valuation, the most frequent subject for valuation studies in Thailand has been forest ecosystems, followed by wetlands, mangroves, coastal, and coral reef ecosystems. Provisioning services, especially food and raw material (timber and fuelwood) have been the most extensively valued, followed by cultural services (recreation and tourism). Relatively limited attention has been devoted to other key ecosystem services provided by production landscapes, such as water and pest regulation, soil erosion control, natural hazards regulation, water purification and pollination- all important aspects to be considered in sustainable landscape management. It should also be noted that despite the predominance of rice-based landscapes across Thailand, existing studies have not focused on those landscapes. Within the past decade, economic valuations in Thailand have been funded by agencies such as the Department of Marine and Coastal Resources (DMCR) and the Department of National Parks, Wildlife, and Plant Conservation (DNP). This clearly indicates that the initial efforts made in Thailand in valuing natural capital have been limited to departments dealing with environmental issues and natural resource management, without active engagement of other Ministries and Departments responsible for sectoral issues, such as agriculture, tourism and infrastructure development. As a result, stakeholders and experts from key economic sectors have neither been engaged in, nor even informed of the outcomes of valuation studies and their implications for sectoral planning processes and operations.

A further challenge is presented in the limited availability of policy-focused ecosystem assessments and valuation studies for specific landscapes aimed at informing development and policy planning processes through scenario analyses for different land-use options. As a result, there is limited awareness and experience in Thailand in applying such tools in generating policy-relevant information and recommendations and to also influence development and sectoral planning processes. In this regard, targeted capacity building and technical support are required to enable practitioners in Thailand to utilize a wide range of integrated ecosystem services-based assessments and modeling programmes to map the quantity and values of ecosystem services and conduct scenario analysis to assist decision makers, including Integrated Valuation of Ecosystem Services and Ecosystem Services and Tradeoffs (InVEST), Artificial Intelligence for Ecosystem Services (ARIES), and Multi-scale Integrated Models of Ecosystem Services (MIMES).

Furthermore, the absence of systematic approaches to monitor natural capital and its contribution to key economic sectors, particularly the system of national accounts that integrates natural capital values has prevented national budgeting processes to reflect dependencies and impacts of economic sectors on natural capital. Thailand has made some efforts in these areas, including a 2010 study by Thailand’s National Economic and Social Development Board (NESDB), which attempted to identify approaches for integrating biodiversity values into the national economic policy and master plan by studying the application of the UN-System of Environmental-Economic Accounting (SEEA) 2003 method to embed natural capital into the National Account. The study’s scope included input-output table accounts for water, forestry, minerals, and energy. However, the study was hampered by a limited understanding of the UN-SEEA 2003 methodology, while inconsistencies in the use of existing indicators led to shortcomings in data compilation. The study concluded that (a) in order to integrate natural capital into Thailand’s National Account, short and long term capacity-building is needed to raise understanding and competence in applying the SEEA framework; and (b) a national inter-agency committee is required, empowered by legal mandate to facilitate and ensure inter-ministerial cooperation and regulatory coherence. NESDB has expressed interest in participating in the application of SEEA 2012 as a means of driving the country’s Green Economy Policy as part of the 11th National Economic and Social Development Plan (NESDP). However, limited progress has been made to date, and new institutional arrangements are urgently needed to facilitate sharing of information provided by natural capital accounting across ministries, allowing a coherent budgeting/planning process.

Barrier 2: Insufficient capacity and expertise in integrating NC into operations of private sector and financial institutions:

A second major challenge faced relates to the integration of natural capital considerations into operations of private sector companies in key economic sectors in Thailand, including financial institutions. The private and financial sectors in Thailand have developed their own approaches to incorporate biodiversity and ecosystem protection measures into their operations and risk analysis processes; however, these are driven mainly by their reporting and CSR obligations, with only a secondary focus on incorporating the concept of natural capital and ecosystem services-based approaches in core operations. As a result, the extent of mainstreaming of natural capital into corporate or financial institutions in Thailand remains limited. Transforming the operations of the private sector and financial institutions to minimize potential negative impacts of their operations on natural capital will require a broader and more comprehensive approach to fully integrate natural capital values and considerations into corporate risk analysis frameworks, core business models and investment decisions. Insufficient awareness of the linkages and dependencies of production and service sectors on NC, NC-associated investment risks, as well as limited (narrow) understanding within industry sectors of the concept of biodiversity and ecosystem services and their valuation (especially non-market values) is another key challenge that will be addressed through the proposed project.

Furthermore, limited focus placed on landscape-level management of ecosystem services and biodiversity, particularly in relation to forest and land connectivity, ecological quality of habitats, and the dependencies of economic sectors on natural capital, as well as general lack of appropriate market structures or incentives that support and promote the NC-based approaches into economic sectors and in managing production landscapes is another key barrier to be addressed. In the absence of market structures or economic incentives to support farmers or land owners to maintain and enrich biodiversity resources in production landscapes, farmers and land owners are perversely incentivized instead to invest in intensive high-input unsustainable production systems that deliver only short-term economic returns at the cost of irreversible loss of genetic diversity, degraded natural habitats and biodiversity. The absence of financial or other incentives for adoption of sustainable best practice at farm level and sustainable management of natural capital in production landscapes is exacerbated by lack of awareness and aversion to risk by small, resource-poor smallholders. In this regard, there is a need to promote wide-scale adoption of sustainable agriculture / best practices that incorporate natural capital considerations. Such adoption will enhance standards of management of agricultural production landscapes and surrounding forested watersheds, while reducing their environmental footprint.

Barrier 3: Lack of partnerships, awareness and acceptance of NC among key stakeholders:

In Thailand, scientific knowledge and information on NC exists only within scientific circle; there is no effective mechanism to share and disseminate such knowledge and information among policy-makers and practitioners in both public and private sectors. There is a clear need to establish a knowledge learning network that can foster partnerships and facilitate networking among policy-makers and practitioners, and through which globally-recognized best practice can be integrated into sectoral planning processes. Furthermore, there is no national monitoring system in place to tracking implementation of NC-based planning and financing within public and private sector entities, as well as their impacts. It is also imperative to establish a system to monitor - with objectively verifiable data, the successful incorporation and benefits generated to NC including biodiversity through sector transformation and sustainable management of landscapes, such as promoted through the project on sustainable rice standards. The barriers above have allowed continuing and rapid loss of NC in Thailand. Examples include loss of indigenous flora and fauna within agricultural production landscapes; ongoing diminution in water regulating services provided by forested watersheds, leading to seasonal floods and droughts; and a continuing drop in demersal fish populations due to degradation of reefs and other nearshore habitats. Habitat degradation has also led to loss in eco-tourism opportunities and values. In the absence of market structures or economic incentives to support farmers or land owners to maintain and enrich biodiversity resources in production landscapes, farmers and land owners are perversely incentivized instead to invest in intensive high-input unsustainable production systems that deliver only short-term economic returns at the cost of irreversible loss of genetic diversity, degraded natural habitats and biodiversity.

# 1.2. Baseline scenario and any associated baseline projects

# Natural capital including their ecosystem services and biodiversity, provided by major forested and production landscapes in Thailand are under increasing pressure from economic development in sectors, such as agriculture, tourism and infrastructure development. Intensification of rice production in Thailand has resulted in serious degradation of many ecosystem services delivered at landscape level. The impacts of such continuing declines are often felt beyond the farm boundary itself, affecting watersheds servicing downstream and urban areas, soil conservation and erosion prevention, as well as recreational values for tourism. Furthermore, forest encroachment, infrastructure development and upstream development activities can adversely  impact on remaining forests, biodiversity and landscape-level ecosystem services, in turn affecting the sustainability of other sectors Addressing these challenges requires heightened recognition within economic sectors regarding their dependencies on natural capital, along with  increased public and private investment in conserving the biodiversity and ecosystem services provided by landscapes (i.e. beyond protected areas), through application of tools and incentive schemes to internalize the market and non-market values of ecosystem services. Although few actual on-the-ground investments and programmes exist to support such sector and landscape linkages, several policies and initiatives have been introduced that offer a firm foundation for implementation of the proposed project, as summarized below.

Legal mechanisms, institutions and public policies: Thailand has two legal mechanisms enabling the integration of biodiversity and ecosystem service values into their enforcement procedures, (i) the ‘Enhancement and Conservation of the National Environmental Quality Act’, B.E. 2535 (ECNEQ 1992), as well as (ii) the requirement to conduct E.I.A on certain categories of development and investments. Under the first Act, the official model being used is to calculate the cost of forest degradation and forest loss, either terrestrial or mangrove forest within any protected area or national reserve forest. The relevant forest authorities must refer to their respective jurisdictions under the Forest Act 1941, National Reserve Forest Act 1964, National Parks Act 1962, or the Wildlife Preservation and Conservation Act 1992, depending on the legal status of the forest land. As these legal provisions refer to changes in ecosystem services resulting from encroachment of forest land, authorities need access to grounded data to enter into a mathematical model that can assess an economic cost resulting from such losses. These pricings can then be used by the courts in dealing with illegal encroachment cases. However, the ECNEQ Act of 1992, while giving the provisions for the designation and conservation of environmentally protected areas, does not always apply to broader management of production landscapes that do not fall under the categories of protected areas, limiting its ability to influence decisions and policies relating to mainstream economic sectors, such as infrastructure, tourism and agriculture.

The second legal mechanism – the requirement to conduct an Environmental Impact Assessment (EIA) on certain categories of new project developments - is intended to optimize cost-benefit trade-offs resulting from human interventions for development. This legal mechanism is key to integration of biodiversity and ES values into decision-making for development projects. Current EIA requirements and methodology are comprehensive, and are supported by an effective process for developing and approving assessment reports. The scope of EIA requirements includes biotic and abiotic resources, human use value, and quality of life value. Costs and benefits resulting from the intervention must be calculated, and recommendations made for mitigation of potential impacts, or alternative interventions. However, most EIA reports currently only incorporate market values of biodiversity and ecosystem services, without considering non-market values, which often represent the main ecosystem services and critical NC that are perceived relevant to local communities and the public. In the baseline scenario, the capabilities of EIA licensees and appraisers are limited in terms of an understanding of the concepts of non-market values of biodiversity and ecosystem services and to highlight potential implications of proposed development projects, including those relating to infrastructure and tourism development. The proposed GEF project aims to fill this gap by contributing to further enhancement of EIA procedures to reflect non-market values, by developing decision support tools and a knowledge base for EIA assessors and appraisers, and by facilitating adoption of GIS technologies, coupled with models of bio-physical changes and their values.

In the tourism sector, various government programs and budget allocations have been introduced to promote sustainable tourism, including the Thailand National Tourism Development Plan (2012-2016) which aims to boost the sector’s competitiveness. The Tourism Authority of Thailand’s 2016 marketing plan focuses on promoting Thailand as a “Quality Leisure Destination”, emphasizing a shift in focus from volume to high quality tourism, and on the need to reduce social, cultural and environmental impacts. Related to the management of forests and forestland, which falls under the responsibility of MONRE, the 11th National Economic and Social Development Plan (2012-2016) specifies that at least 19 percent of total area is to be targeted for conservation, with forest reserves to be expanded to 40%. The Plan also emphasizes efforts to restore forest and conservation areas and curb encroachment. Moreover, the Plan aims to improve water management to alleviate water shortages, prevent and mitigate floods, and expand irrigation for crop lands. Recognizing forest loss and degradation forest as major causes of flooding, the Cabinet adopted the Master Plan on Water Resources Management (2013-2017). Under the Plan, one workplan focuses on flood water retention and runoff prevention restoration and conservation initiatives, and to develop a land use plan. Together, these plans and strategies provide a strong foundation for the proposed GEF-supported intervention to support and enable policy-makers and practitioners involved in tourism and other key economic sectors to better appreciate and address the dependencies of those sectors on ecosystem services, the value of critical natural capital and its long-term benefits and sector contributions.

Natural capital valuation and accounting: Efforts have been made in Thailand to apply the UN-SEEA 2003 methods, led by the National Economic and Social Development Board (NESDB). Moreover, NESDB has expressed interest in the SEEA 2012 as a means of driving the country’s Green Economy Policy as part of the 11th National Economic and Social Development Plan (NESDP). However, there is strong need to build capacity in relation to the principles of SEEA 2012, and to strengthen institutional framework and establish an effective Secretariat mechanism to coordinate inter-ministerial cooperation to support these efforts. In view of this, NESDB expressed its interest in participating in the proposed GEF project to enable them to address these capacity needs, and to ensure that information provided via NC accounting feeds into the Government’s budget planning processes and influences decision-making and sector policies. NESDB also recognizes the need for upgrading systems for data collection and integration, along with attendant technical and implementation capacity. Without the further interventions proposed under the GEF project, efforts to apply SEEA into Thailand’s national account will not be sustained nor funded via the government’s regular budget.

Clarifying the values of the stream of ecosystem services and their benefits over a specific time period is essential to gain a full appreciation of the long-term impacts of specific policy choices. In Thailand, efforts have been made in advancing the field of natural capital valuation, providing a basis for natural capital accounting, and for guiding decision-making processes in both public and private sectors. A study conducted by Emerton (2013) forecasted ecosystem service values of NC and seven selected ecosystem services (harvested products, watershed protection, carbon sequestration, water quality and flow, coastal protection and coastal tourism) over a 25-year timeframe, with and without a suite of green economic growth policies. The findings showed that green economic growth policies have the potential to enhance the net present value of ecosystem services from natural forests, freshwater wetlands, mangroves and coral reefs by USD 2.06 billion, an increase of 7.8 % over a BAU economic growth scenario. Strong interest and efforts of the Government of Thailand in this field of work is also evident in the establishment of the National Working Group on TEEB, with the aim to enhance understanding and promote incorporation of TEEB into national and departmental policies and regulatory provisions. Furthermore, some existing strategies and policies introduced by the Government, such as the 11th National Economic and Social Development Plan provide a strong foundation for the proposed GEF intervention. The 11th Plan includes the principles of the Green Economy and acknowledges the value of market-based instruments such as PES, as well as the initiative of the Biodiversity-Based Economy Development Office on the development of models and standards for eco-friendly production and greening the tourism sector, in this field of work and efforts in integrating natural capital into economic sectors.

Private sector baseline initiatives: The private and financial sectors in Thailand have developed their own approaches to incorporate biodiversity and ecosystem protection measures into their operations and risk analysis processes. For example, the Thai Pat Institute together with the Thai Listed Companies Association provide training for companies in Thailand under the Global Reporting Initiative (GRI) on corporate sustainability performance ranking – including on impacts or dependencies on biodiversity and their performance indicators.. However, despite the utility and relevance of the GRI and the Equator Principles (EP), these frameworks do not specifically incorporate the concept of NC and ecosystem services-based approaches. As a result, the mainstreaming of NC into corporate or financial institutions in Thailand remains limited in extent. So far, the focus has been on CSR yet proper reference to specific biodiversity and ecosystem services dependencies and linkages of three corporate sectors involved appears to be relatively superficial. Moreover, the government and Thai banks have yet to adopt existing international standards provided under the EPs. Further efforts are needed in introducing financial incentive schemes that promote biodiversity-friendly practices in selected sectors, with linkages to corporate performance. Examples include biodiversity offsetting, loan criteria for biodiversity conservation, and sustainable supply chain initiatives. The Stock Exchange of Thailand (SET) is a member of the Sustainable Stock Exchanges Initiative, a global initiative aimed at exploring how national exchanges can work together with investors, regulators, and companies to enhance corporate transparency, and ultimately performance, on environmental, social and corporate governance (ESG) issues. The Initiative also encourages responsible long-term approaches to investment. The SET hosted a regional dialogue for South East Asia on 18 May, 2015.

# Sustainable agriculture initiatives:

# The country’s 1st Biennial Update Report (BUR1, 2015) mentions the following additional domestic mitigation measures being undertaken for the agriculture sector, particularly for rice production: “In anticipation to potential climate variability especially prolong period of drought, the Rice Department (RD) has been conducting research into Alternate Wetting and Drying (AWD) cultivation practice that would use less water than traditional continuous flooding, and as such would benefit downstream sectors such as eco-tourism, and particularly water services sector for e.g. urban and industrial use. The results so far have been encouraging. RD has been able to achieve 20-50% reduction in water usage depending on soil type and condition as well as weather condition. The AWD cultivation practice could have significant potential in Thailand given the very large area and production of irrigated rice in Thailand, as well as enhance resilience toward possible prolonged period of drought, as experienced over the last years. However full deployment of this technology which will have significant benefits to other NC and ecosystem services & NC-dependent sectors, is hampered by the lack of central government policies, focused investment programs as well as the budgets, aiming at replication throughout Thailand.. Furthermore, the Ministry has also been promoting the use of precise fertilizer practice, which depending on the type of soil, crop, and stage of crop growth, suitable type and quantity of fertilizer as well as how to apply the fertilizer would be provided to the farmers.

# 1.3. Proposed alternative scenario, with a brief description of expected outcomes and components of the project

The Objective of the project is “To alleviate threats to biodiversity, ecosystem services, and to support low carbon growth in critical production landscapes in Thailand, by integrating values of forests and other natural capital into policies and operations of key economic sectors”. In close collaboration with project partners, the project aims to work towards the development and application of innovative policies and tools to support mainstreaming of market and non-market values of NC, their biodiversity, as well as their ecosystem services in key economic sectors, including agriculture, water services and tourism.  The project targets public policy (sectoral and economic development) as well as the role and responsibilities of the private sector and financial institutions. The project’s three components are:

Component 1: Policies and market incentives in support of integrating Natural Capital into key economic sectors (including agriculture, tourism, water services)

Outcome 1.1: Three national NC-dependent economic sectors are aware of their impact and dependency on NC, and enabled to integrate NCA in their policies, plans and budgets,

Outcome 1.2: Increased national/provincial budgets and institutional capacity benefitting forests, biodiversity conservation and ecosystem services in support of   NC-dependent sectors.

This component seeks to provide a firm grounding for integrating NC values and objectives into national accounting system, green budgets, and policies and plans for three economic sectors key to the economy of Thailand (agriculture/rice production, tourism and water services). To provide an authoritative basis for policy recommendations, the project will conduct a comprehensive policy-oriented assessment of NC, and ecosystem services and their values (Output 1.1.1), highlighting the role of the three sectors to the national transformation towards a Green Economy, through commitments such as food security, biodiversity and forest conservation, preservation of water resources as well as maintaining the quality of tourism destinations and services. It will also focus on assessing inter-dependencies with these three sectors, highlighting the adverse environmental implications and potential consequences of policy failures. Specifically, the national level assessment will include identification of biophysical natural capital assets and their interdependencies with agriculture – specifically rice, tourism, and water services, clarifying inter-sectoral relationships, and valuation of the assets and the assessment of their contribution to the Green Economy. The assessment will look at the impacts of economic development path on the key biophysical natural capital assets identified, and associated risks for priority sectors given likely changes in the flows of ecosystem services on which they depend. Sector roundtables and reviews will be conducted (Output 1.1.2) to assess the ecological footprint of the three sectors and to quantify corporate/investment risks related to NC, using tools such as the Natural Capital Protocol (to be adapted to Thailand and specific sectors), spatial mapping, GIS-based valuation and modeling tools to undertake scenario analysis, for example, of different development directions and land-use options. The sector reviews will also identify entry points and opportunities for mainstreaming NC values into sectoral policies. As part of the sector round tables the project will work on the improvement and strengthened institutionalization of the formally required EIA procedures in development projects, corporate investments and government programs that incorporate both market and non-market values of ecosystem services. The adoption of Strategic Environmental Assessments (SEA) will be considered if these fit and benefit existing government procedures. In this process, capacity will be developed of practitioners and policy-makers in applying ecosystem service-based tools, including natural capital valuation and accounting, and particularly, data interpretation and integration into policy-making processes, corporate risk analyses and investment decisions (part of 1.1.2). Based on the assessment findings (under Output 1.1.1), the project will present options under Output 1.1.3 to enhance national ecological infrastructure and investment plans – preferable at landscape-level, as well as sectoral policies by promoting and incentivizing actions (e.g. sustainable agriculture/rice production, sustainable tourism, sustainable water resource management, eco-infrastructure etc.) leading to sustainable management of critical NC and ecosystem services at a landscape level. Also included in this component will be the development of principles, technical guidelines and facilitation for enhancing national ecological infrastructure, leading to at least three sectoral policies that promote and incentivize actions to ensure sustainable management of critical NC – specifically in forests, protected areas, watersheds and (near-) coastal ecosystems.

Subsequently, Outcome 1.2 will include the development of policy and institutional mechanisms to ensure that NC account feeds into the Government’s budgeting processes and fiscal measures, leading to agreements among relevant ministries towards increased budget allocation for protection and sustenance of critical NC. Integration of NC in budgeting processes as well as NC-supportive fiscal measures will be implemented in close coordination with the UNDP Biofin Initiative, and with the active engagement with the Ministry of Finance, Bureau of the Budget, the Office of the National Economic and Social Development Board, as well as National Statistics Bureau and the Office for Agricultural Economics. NC accounting will be implemented and institutional arrangements made to ensure that a National Natural Capital Account is used (Output 1.2.1) to inform government, sectoral and budget planning processes towards increased allocations as well as supportive fiscal measures,  to protecting NC as well as transformation of NC-dependent sectors towards enhanced environmental sustainability and risk reduction. As mentioned earlier, the UN-SEEA 2012 framework will be followed to integrate the country’s statistics on the environment and its relationship with the economy, including the economy’s impacts on the environment and vice versa. This will enable the derivation of a coherent set of indicators and descriptive statistics from the accounts that can serve to inform a wide range of economic development pathways and sectoral policies, including, but not limited to, green economy/green growth, natural resource management and sustainable development. As part of the effort on NC accounting, depending on the needs identified, the SEEA-Experimental Ecosystem Accounting (EEA) may be implemented to include ecosystem services in its framework. A strong focus will be placed on compiling information to be integrated within the national account, focusing on the tourism, water services, and agricultural sectors. Moreover, the project may draw on the knowledge and experiences accumulated under the UNEP-TEEB initiative, working with UN Statistics Division and the Secretariat of the Convention on Biological Diversity (CBD) in promoting SEEA-EEA, and approaches to assess the environmental sustainability of agricultural production at the product/commodity level, including metrics for assessment of externalities and impacts to ecosystems services such as water and biodiversity arising from agriculture. The project will also seek partnerships with the Natural Capital Coalition (formerly TEEB for Business), which is currently developing a Natural Capital Protocol targeting private sector companies; this aims to provide global and sectoral guidance on qualitative, quantitative and monetary valuation of Natural Capital impacts and dependencies and when to apply which level of assessment. The project will utilize tools and guidance developed under this initiative; this might include the Guideline of Corporate Ecosystem Review and Valuation (CERV), which ECO-BEST in 2015 adapted and interpreted for the Thai context, using the two global guidelines from the World Resources Institute and the World Business Council for Sustainable Development. These guidelines are intended to assist enterprises in mitigating potential risks in integrating ecosystem services into corporate operational strategies and CSR programs. Output 1.2.2 will firstly enable institutional development and human capacity building for Government offices, at both provincial and sectoral levels, focusing upon the principles of NC valuation as well as financial incentive schemes and available economic instruments. Secondly, it will work with national government towards establishing a system for increasing NC responsive budget allocations and other fiscal measures benefitting NC. One possible option to be considered is to calculate part of the government budgets allocations to provinces based on ‘their performance’ in maintaining, restoring or protecting NC, whilst those same provinces would be free in deciding how to spend those extra funds, including to non NC investments such as e.g. towards education, infrastructure etc. This would provide a better incentive to local governments to ‘go green’. Whilst Component 1 establishes the capacity, national systems, plans towards NC responsive policies, sector transformation, and adoption of a landscape-basis for private and public investments, Component 2 is specifically aimed at the actual operationalization, budget allocations and on-the-ground landscape and sector activities towards mainstreaming NC and BD in operations and investments.

Component 2: Integration of Natural Capital Accounting into government development plans and operations of key economic sectors (agriculture, tourism, water services) at landscape level

Outcome 2.1: Enhanced incorporation of the value of NC including biodiversity in provincial government plans and corporate decision making, leading to increased investments in NC.

This component will address constraints and enable implementation related to integrating NC into sector operations through three types of outputs: the first (2.1.1) is to establish the provincial government platform, partnership and operational plans to translate and apply the NC policies and budget/fiscal measures of Component 1 to the provincial level (2 out of the 3 proposed provinces will be chosen during the PPG); the second (2.1.2) is to assist companies and government sector agencies integrating NC values in corporate risk analysis, sustainability/business plans and reporting, as well as NC-responsive investment decisions and market-based instruments with financial institutions; and the third type of output (2.1.3) applying these at landscape level with on-the-ground demonstration of protecting, restoring or investing in NC through public-private partnership and corporate operations key to protecting biodiversity and ecosystem services and strengthening environmental resilience of the selected landscapes, contributing to the NC within all selected sectors.

This component presents the integrated project approach under the targeted BD strategic programs 9 and 10 in validating and promoting innovation, technology transfer and supportive policies as well as incentive mechanisms for the three targeted sectors. The component will contribute to restoration and sustainable management of Natural Capital in the targeted landscapes and sectors.

Three provinces (Chiang Rai, Chonburi and Trat) have been proposed by the GoT on the basis of the significance to agriculture, (sustainable-)tourism and water services - including for rice production, to the respective provincial economies, and the urgent need to enhance protection of biodiversity and ecosystem services at landscape level. The project will focus on two distinct landscapes (2.1.3) – to be deliniated in two provinces, representing various ecosystems, HCVF, watersheds, and the key targeted BD/ES, as well as different sectors’ dependencies and/or impacts. Final selection of the provinces and landscapes will be made during the PPG, based on inclusive stakeholder consultations, assured local government buy-in, and identification of their respective linkages with critical NC and government development plans. Site selection criteria will aim to maximize targeted GEB outcomes such as biodiversity conservation, maintaining key ecosystem services key for the three sectors. Annex 1 provides a description of the selected provinces, their BD and NC values, as well as key challenges and opportunities.

Targeted landscapes: The project will invest in the protection of biodiversity, NC and sustainable use principles into the management of a  minimum of two landscapes, based on the enabling environment established under Component 1 as well as the provincial plans and corporate mechanisms and agreements of outputs  2.1.1 and 2.1.2  Interventions in Landscapes One and Two (2.1.3) will target coastal land/seascapes with a total area of at least 40,000 ha, where NC-based sector transformation and public-private partnership will be applied to protecting and restoring critical coastal resources such as mangroves, shallow reefs/seagrass meadows, river estuaria, as well as forested watersheds considered key to tourism and water supply (to e.g. irrigated agriculture), as well as protection against coastal flooding. It will also work with one PA – to be selected during the PPG, where management effectiveness will be enhanced through mechanisms such as improved bufferzone and landscape management based on agreed local policies, plans and financing with sectors active in the landscape towards the protection of NC and biodiversity.

In addition to maintaining ecosystems services key to sustaining strategic national economic sectors, the project will conserve globally significant biodiversity through forest conservation and management – enabled through public-private partnership and increased investment directed at the NC objectives under this project, including the protection of threatened or endemic species. Some of the key targeted species are threatened and included in the IUCN Red List as well as the Thai Red Data listing (see Annex 1 for details) including: 2 Critically Endangered (CR) species; 9 Endangered (EN) species, including: Indochinese Tiger, Pileated Gibbon, White-handed Gibbon, Hog Deer, Greater Adjutant, Giant Nuthatch, and Black-bellied Tern and Indochinese Waterdragon; 11 Near-Threatened species (NT) – including Silvered Leaf Monkey; and 11 species stated as Vulnerable (VU).

In order to provide a strong basis and agreement for the on-the-ground sustainable landscapes work (e.g. output 2.1.3), Component 2 will begin with the drafting and negotiation of national / provincial legislative processes – under Output 2.1.1, supporting  adoption or amendments of at least two provincial development or investment plans and enhanced multi-agency collaboration to ensure integration of NC in investment decisions and operations of key sectors at landscape level (e.g. financial & fiscal incentives, market-based instruments). For the agriculture sector, reviews and assessments will be conducted by drawing on the analytical frameworks and approaches adopted by the global UNEP ‘TEEB for Agriculture & Food’ study, which aims to provide comprehensive assessments of the ‘eco-agri-food systems’ complex and to demonstrate that the economic environment in which farmers operate is distorted by significant externalities, both negative and positive, and a lack of awareness of dependency on natural capital.

Output 2.1.2 will assist selected provincial and corporate partners to integrate NC values into risk analysis, sustainability/business and development plans using methods and guidelines developed by various partners including UNEP/FI and the Natural Capital Declaration. Financial incentives will be designed to contribute to enhancement of NC, including protection of biodiversity as well as sustainable forest management practices in the targeted landscapes of Output 2.1.3 e.g. in key river catchments and eco-tourism destinations. Moreover, the activity will stimulate active corporate sector engagements through creating tangible incentives for the partner companies. Building on sector-level agreements forged, policies established and capacity built under Component 1, this activity will support NC-based sector transformation and apply NC values to two ES-dependent sectors in the coastal land- and seascape(s) of 40,000 ha, protecting or restoring critical coastal mangroves, seagrass, coral reef habitats and forested watersheds (Output 2.1.2). For example, this may involve working with tourism operators, hotels and investment companies to partner with the government and invest in restoration and conservation of key inland watersheds to reduce floods in the coastal plains, protecting reefs from impacts of the expanding tourism industry (e.g. through the UNEP Green Fins programs), working with the fisheries sector and local investors to restore mangroves and estuarine swamps, and other related work on coastal and marine NC.  It additionally could also involve agreements with national and local government as well as investments by the rice sector towards sustainable management of forested watershed – on which the sector depends for water supply.

This component will build a strong economic case for incorporating NC-values in policies and regulations governing the agriculture sector, in order to  incentivize preservation of particularly the water resources from healthy (production) landscapes on which the sector depends. The internalization of NC-based farm and landscape management principles will be incorporated in corporate risk management strategies as well as NC-based landscape management principles and practices. Finally, Component 2 will raise awareness and appreciation of the NC-based linkages among various key economic sectors and the importance of agricultural production landscapes (as exemplified by rice) in delivering important ecosystem benefits beyond primary food production to other economic sectors, especially to the tourism and water sectors. It will also promote the appreciation of the multi-functionality of production landscapes, e.g. as watersheds for downstream urban areas, in regulating water flows and quality and in their cultural, aesthetic and recreational values.

The public-private partnership established and best practices gained under Component 2 will be sustained and replicated in other landscapes and programs enabled through the national sector policies established (1.1.3),  the national budgets made available (1.2.2), as well as the provincial investment plans developed and agreed with local and national governments (2.1.1). Additionally, monitoring activities under Component 3 will validate the positive benefits of sustainable landscape management, the level of incorporating the value and objectives of NC in sectors, as well as strengthen and expand the partnerships. Component 3 will also capture and disseminate best practice gained under Component 2 on mainstreaming NC values into sectoral planning processes and business/financial sector operations. This will build a better business case for sustained national and sector growth by transitioning to a green economy for both the public as well as private sector.

Component 3 : Dissemination of information, awareness raising and networking for mainstreaming NCA

Outcome 3.1: M&E providing the quantitative benchmarks on BD,  NC values and adoption of NCA practises through project investments.

Outcome 3.2: Partnerships, knowledge and acceptance of NCA built, and best practices widely communicated for upscaling.

Convenient access to timely and relevant information on NC and ecosystem services will be important to support the development of key skills and competencies among responsible personnel in both public and private sector organizations. This component will draw lessons from the first two components to catalyze scale-up and integration of the concept of NC in both public and private sectors, e.g. through both tracking of adoption of NC-based plans, budgets and practices, as well as the dissemination of best practices. Output 3.1.1 will establish the capacity and M&E system providing quantitative benchmarks on the level of adoption of NCA; as well as the level of benefitting biodiversity and NC objectives and targets through sustainable landscape management in the two targeted landscapes. Specifically, it will quantify and monitor NC results delivered as against the targets and indicators agreed under Component 1.1 (linked to Thailand’s adoption of SEEA, in collaboration with Thailand’s National Statistics Bureau and the Office for Agricultural Economics). It will also track changes in sectoral plans, budgets and operations that support NC.

Under Output 3.2.1, dissemination of information will be conducted via a communication, outreach and engagement strategy based on the results of the M&E and ‘best practice’ information generated by the project under Comp 1 and 2, by incorporating an open-access knowledge base to fulfill two functions: (1) support the project’s capacity-building and training activities – specifically on mainstreaming the use of NCA; and (2) provide a portal to connect researchers, government planners and policymakers, as well as  corporate sector practitioners in a network or Community of Practice to exchange their knowledge and experiences in mainstreaming NC values into sectoral planning processes and business/financial sector operations.

The project will facilitate networking among policy-makers and corporate partners in Thailand as part of Output 3.2.2 to exchange their knowledge and experiences in mainstreaming NC values into sectoral planning processes and business/financial sector operations. This process could involve the Sustainable Stock Exchanges Initiative, Chamber of Commerce Thailand, CSR Club Thai Listed Companies Association, National Rice Department, or e.g. the Tourism Association of Thailand. Key approach is to communicate and build a broader public-private partnership in Thailand towards transitioning to a Green Economy based on a proven and positive business case for both the government as well as private sector, that by targeting, incorporating, and subsidizing NC conservation and restoration the country’s economy will grow and/or be sustained.

The online knowledge will be developed and maintained to support and promote networking and exchange of experiences and success stories (Output 3.2.2). These activities will help enhance understanding and support among policymakers, practitioners and the broader stakeholder community for the principles underpinning NC/ecosystem services and their practical implementation, and thus facilitate mainstreaming of natural capital values into sectoral planning processes and business/financial sector operations.

An additional essential output would be the establishment of a full project M&E system to measure impact, progress and management performance of the project (Output 3.1.2).

# 1.4. Incremental/additional cost reasoning and expected contributions from the baseline, the GEFTF, LDCF / SCCF and co-financing

# The financial resources provided by the GEFTF will serve to enhance the resilience of landscapes and their contributions to key economic sectors targeted by the project, and mainstream the incorporation of the principles and planning tools based on NC valuation and accounting into public policy and core strategies of private sector actors. The project design is grounded in the full recognition of the dependencies of key economic sectors in Thailand, particularly agriculture/rice, tourism and water sector on the Natural Capital provided by healthy sea- and landscapes. The project also recognizes the impacts of activities of one sector on the provision of ecosystem services affecting other sectors that also depend on those services (e.g. impacts of agricultural production on watersheds servicing downstream and urban areas, soil conservation and erosion prevention and recreational values for tourism). Addressing these dependencies and interrelationships among economic sectors requires a landscape-wide approach, through coordinated efforts at sector level. It also requires increased investments in management of biodiversity and ecosystem services provided by landscapes (i.e. beyond protected areas), through application of innovative tools and incentive schemes to internalize the market and non-market values of ecosystem services into sectoral planning processes and private sector operations.

# GEF support for this project will leverage the opportunities identified in the baseline scenario and bring together providers and beneficiaries of ecosystem services via national and provincial policy mechanisms and demonstration activities for selected landscapes. This approach will ensure a coherent cross-sectoral approach to sustainable management of biodiversity and ecosystem services at landscape level. By promoting the application of market-based instruments such as PES, the project will also contribute to sustainable forest management through increased investments in forest conservation and restoration. For the agriculture sector, the project will ensure a balanced development trajectory that contributes to food self-sufficiency, protects biodiversity and ecosystem services provided by production landscapes, while minimizing resource use and enhancing farmer livelihoods.

# As embedded in the project design, the GEF incremental support will mobilize additional funding to ensure policies, plans, programmes and investments of key economic sectors are based on credible information produced via Natural Capital valuation and accounting as well as other planning tools. GEF support will also encourage investments by both public and private sectors towards sustainable management of critical Natural Capital provided by production landscapes as well as sustainable forest management in the surrounding areas.

# Given the highly favorable baseline situation and potential for scale-up, the incremental GEFTF investment is expected to generate significant global environmental benefits well beyond the direct scope of the project itself.

# 1.5. Global environmental benefits (GEFTF, NPIF) and/or adaptation benefits (LDCF/SCCF)

# The project is expected to generate the following global environmental benefits, and which will be reassessed during the project preparation phase based on better field delineation, baseline data and identification of the specific sectors and landscapes.

# Biodiversity FA:

Biodiversity and ecosystem services of watershed forests and other NC  recognised, valued and incorporated in policies, financing and sector practices in at least 40,000 ha of  landscape(s) as well as seascape, including forested watershed, and associated mangrove, seagrass and coral habitats.

The project will deliver important incremental benefits in terms of the protection of threatened or endemic species. The trageted ares include the endemic Triangle Blackhead (Sibynophis triangularis) as well as the endemic Ko-Chang-frog (Rana  kochang). Most of selected key species are threatened and included in the IUCN Red List as well as the Thai Red Data listing (see Annex 1 for details): 2 Critically Endangered (CR) species; 9 Endangered (EN) species, including: Indochinese Tiger, Pileated Gibbon, White-handed Gibbon, Hog Deer, Indochinese Water Dragon, Greater Adjutant, Giant Nuthatch, and Black-bellied Tern; 11 Near-Threatened species (NT) such as e.g the Silvered Leaf Monkey; 11 Vulnerable (VU) species; and 3 species with Data Deficient but known as overexploited.

Management effectiveness scores of one PA improved by PY 4 (as measured through GEF TT) through corporate sector partnership, change process, investments, supportive land-use policy, and monitoring.

At least two corporate agencies adopt tools such as the Natural Capital Protocol, leading to quantified assessment, the incorporation in business planning, setting related strategic targets, as well as operations related to ecosystem services provided by NC (dependencies, impacts and costs). The related GEB will be further specified and quantified during the project preparation phase  based on full delineation of the selected targeted areas, sectors, as well as comprehensive baseline assessments.

Corporate financial benefits invested, paid or donated towards NC & forest resources protection and restoration – benefitting biodiversity, increasing by an average >5% p.a.  over the project’s life. ,

# Cross-cutting enabling GEB:

Through the development of an enhanced knowledge base relating to the status of NC for production landscapes and improved information on linkages with, and contributions to key economic sectors, the project will facilitate improved decision-making to minimize adverse impacts of key sectors on ecosystem service provision at two levels. Firstly, at provincial and landscape levels, the project will allow provincial and local stakeholders to systematically define environmental and economic trade-offs associated with development measures, and incorporate ecosystem service-related opportunities and risks into the their planning and development of provincial or landscape strategies. The project will formulate sustainable development plans for the three pilot provinces, whereby local stakeholders can negotiate mutual long-term benefits while minimizing risks and conserving natural ecosystems, including biodiversity. Secondly, for the corporate sector, the project will support initiatives by leading enterprises to integrate the value of ecosystem services and biodiversity into their own operations and activities. Such initiatives will contribute not only to long-term business sustainability but also to the standard of the company’s sustainability reporting. Ultimately, participating companies will be able to clearly define their operations as contributing to long-term operational and corporate sustainability, offering competitive advantage through growth, innovation and new market opportunities, while strengthening stakeholder relations and the company’s long-term license to operate. Together these public and private initiatives will help boost the contribution of sustainable forest ecosystem services to the economy, at both national and local levels.

The project will lead to enhanced protection, restoration, and sustainable management of forested landscapes as well as seascapes. Additionally, integration of the NC concept and approaches into business models, risk analyses and decision-making processes within government, private sector entities and financial institutions will positively affect their operations in the targeted minimum of  40,000 hectares of land- and seascapesscapes –, within the two selected and involving one Protected Area. The support provided by the project to the application of market-based instruments and fiscal measures will address key operational challenges through credible assessment and monitoring of environmental and social benefits gained through the schemes, and equitable distribution of such benefits to service providers, including local community groups and indigenous people.

# 1.6. Innovativeness, sustainability and potential for scaling up

# Innovativeness: The project is innovative as it aims to operationalize the concept of natural capital and ecosystem-based approaches at the landscape level, and promote integration of values of services/benefits obtained from multiple ecosystem services into decision making and operations of key economic sectors (including agriculture, tourism and water resources). By applying ecosystem-based approaches and emphasizing landscape connectivity, the project will foster partnerships among multiple departments within central and local government as well as the private sector.

# The project will also focus on designing and testing innovative policy and market-based mechanisms (including a PWS scheme that contributes to sustainable forest management) to create additional value-added at landscape/watershed level. The design and implementation of such instruments will be supported by a robust information base made available through policy-specific NC valuation and decision support systems, drawing on cutting-edge technologies and approaches. Moreover, it is anticipated that over the project’s duration, awareness-raising activities will contribute to increased awareness and investments by key economic sectors on the sustainable management of NC at the landscape level, leading to heightened consumer consciousness and willingness to pay for sustainably produced food, as well as for sustainable tourism services and products.

# Sustainability: The sustainability of the project will be ensured through institutionalization of mechanisms to support integration of NC-based approaches within key economic sectors (e.g. establishment of institutional mechanisms around Thailand’s NC accounting and its integration into budgeting processes, institutionalization of EIA procedures that incorporate ES values, enhancing policy and regulatory frameworks that support the application of PES). These mechanisms will help ensure ongoing efforts and post-project impacts. Establishing channels for farmers and rural communities to derive direct and immediate economic benefits from adoption of sustainable rice and NC-based sustainable best practices will create an intrinsic incentive structure financed through the market. Once market linkages are established and supported by the overall policy environment, such structures are well-positioned to be inherently sustainable over the longer term.

Scaling up: The project aims to strengthen Thailand’s public and private administration systems in order to incorporate biodiversity and NC valuation into their respective decision-making structures and reporting systems. The support from GEF would allow Thailand to directly access global-level expertise and experience to implement the UN SEEA 12 framework and adapt to the Thai context. GEF financing will function as a catalyst to drive political commitment to driving change among existing public sector agencies, both in term of enforcement of existing legal and regulatory provisions and in developing innovation financial instruments to incentivize biodiversity conservation. From a global perspective, the project will enhance Thailand’s capability to implement the NBSAP, which directly serves its obligations under the CBD. In particular, GEF funding will expedite Thailand’s capability to accomplish the Aichi Target 3 and Target 20.

The project’s management by the Office of Natural Resources and Environmental Policy and Planning ONEP, under the Ministry of Natural Resources and Environment, Thailand also contributes to wider policy goals. Since ONEP serves as the national Secretariat/focal point for natural resources and environmental policy and planning in Thailand, enhancement of ONEP’s own capacity will make a major and direct contribution to other related areas of policy and planning processes in the longer term. Under the project, opportunities for exchange of knowledge and experience with other government agencies as well as with international experts, project partners and other stakeholders will yield significant benefits in broadening interest and upscaling successful initiatives that conserve and sustain biodiversity within agricultural landscapes. As ONEP also serves as Thailand’s national biodiversity focal agency within ASEAN, the project’s outcomes, accomplishments and lessons learned will also be reported and disseminated via relevant ASEAN and other regional and institutional fora.

# To maximize project impact and the potential for scaling up, the final selection of project provinces and investment landscapes will be made during the project preparation phase, based on extensive stakeholder consultations including an assessment of willingness and capacity to implement the project approach. Increasing awareness with specifically the targeted private sector will expand market opportunities and create further economies of scale. In order to maximize the dissemination and wider replication of best practice (Comp 3.2), to unlock the potential of new market opportunities, private sector partnerships will be explored and established during the project’s duration. Embedding and linking the project’s field-level activities with the process of policy development will contribute to an enabling policy, regulatory and institutional framework that further contributes to the sustainability of project outcomes.

2. Stakeholders. Will project design include the participation of relevant stakeholders from civil society and indigenous people?  (yes  /no )

In view of the multi-disciplinary nature of the project, the complex institutional interrelationships and socio-economic implications and the policy-landscape nexus, it will be critically important to engage and secure the commitment of a broad range of stakeholders during the project’s design and preparation. Selected key partners and initiatives and their roles in the project are described below.

| Stakeholder | Role and Involvement in the Project |
| --- | --- |
| Ministry of Natural Resources and Environment (MoNRE) | MoNRE is responsible for environmental protection and restoration, particularly the protection of natural resources, including forests, water, oceans and minerals. The Ministry’s Office of Natural Resources and Environmental Policy and Planning (ONEP) will serve as the lead project Executing Agency, in collaboration with the Rice Department (RD) of MOAC, and will be responsible for overall project management. ONEP is also the CBD national focal point, responsible for coordinating implementation of the Convention in Thailand. In addition to ONEP, the Royal Forest Department (responsible for managing national reserve forests, buffer zone areas and community forests), Department of National Parks, Wildlife and Plant Conservation (responsible for managing protected areas in land use planning), the Department of Water Resources (responsible for overseeing management of water resources including rainwater, surface water, groundwater, and seawater in river basins), the Department of Groundwater Resources (mandated to oversee development and management of integrated groundwater resources), and the Department of Marine and Coastal Resources (responsible for formulating policies and plans for conservation and restoration of marine and coastal resources) of MoNRE will contribute to the assessments and policy mainstreaming work. |
| Ministry of Agriculture and Cooperatives (MOAC) | MOAC is responsible for administering national agricultural policy, water resources, irrigation, promotion and development of farmers and cooperative systems. Synergies will also be ensured with ongoing research and extension activities undertaken by their Rice Department related to sustainable rice systems and practises. In addition, the Land Development Department (LDD) of MOAC will also be involved in the project, in keeping with its mandate on land development and through the provision of updated spatial data. The Royal Irrigation Department (responsible for overseeing implementation of water management for agriculture), and the Office of Agricultural Economics (with its role in providing statistical data related to agriculture) will also provide technical support to the project under Component 1. |
| Office of National Economic and Social Development Board (NESDB) | NESDB is the national economic planning agency responsible for providing strategic guidance to line ministries on development priorities, through its five-year National Economic and Social Development Plans. NESDB is responsible for analyzing budget proposals and making decisions on budget allocation, and maintains an economic intelligence database, particularly for monitoring and analyzing national and sectoral performance and GDP; it will therefore play a key role in promoting coordination among sectoral agencies and introducing natural capital accounting into relevant line Ministries. |
| Biodiversity-Based Economic Development Organization (BEDO) | BEDO, an agency established under MoNRE, is mandated to promote Thailand’s efforts to manage biodiversity resources and their utilization for economic purposes, leading to job creation, income and opportunities for local communities. As an agency focusing on supporting the private sector and introducing market-based instruments, BEDO’s participation in this project is therefore important to effective delivery of project outputs and outcomes. |
| Ministry of Finance (MOF) | The MOF is responsible for public finance, taxation, the Treasury, government properties, operations of government monopolies, and revenue-generating State enterprises. In particular, the Fiscal Policy Office is responsible for formulating and implementing economic, monetary, and fiscal and taxation policies. It also undertakes macro-economic analysis, and is therefore a key agency for the development of natural capital accounting, budget allocation and promotion of investment towards sustainable management of natural capital. |
| Ministry of Information and communication Technology (MICT) | MICT, particularly through the National Statistical Office (NSO) acts as a statistical information center for the country and manages data produced by the NSO as well as other government agencies. TNSO, together with NESDB, will play an active role in undertaking activities to develop the national natural capital account, building on the country’s earlier efforts on UN-SEEA. |
| Ministry of Tourism and Sports (MoTS) | MoTS is responsible for promoting the tourist industry, and in particular, the Department of Tourism (DOT) is mandated to promote and develop sustainable tourism in tourism service system and tourism sites, through research and analysis of statistical data and developing roadmaps and plans for tourism development. In addition, the Tourism Authority of Thailand (TAT) is responsible for the promotion of tourism in Thailand; TAT undertakes studies to prepare development plans for tourist destinations and supports capacity development for tourism industry personnel. These two agencies are key stakeholders to be invited particularly for activities under Component 1, focusing on natural capital mainstreaming into sector policies and programmes. |
| Ministry of Interior (MOI) | The responsibilities of the MOI include local administrations, land management and public works. In particular, the Department of Local Administration and the Department of Provincial Administration, responsible for supporting local governments through provision of guidance on local development plans, as well as personnel, finance and administration of local government organizations. In the proposed project, these departments will play a key role in implementation of activities focused on influencing provincial development or investment plans. |
| Provincial authorities | Provincial authorities in selected pilot sites are responsible for integrating sectoral development plans of relevant ministries into provincial plans, and therefore will play a key role in the project, especially in activities to drive adoption or amendment of provincial development or investment plans to promote natural capital mainstreaming. |
| National-level committees | The project will engage with several national-level committees responsible for thematic areas directly relevant to the project, such as the National Committee on Biological Diversity (NCBD), and the National Working Group on the Economics of Ecosystems and Biodiversity (TEEB) which will provide technical inputs and access to relevant expertise. |
| Financial institutions and industry associations | Selected key financial institutions, such as the Bank for Agriculture and Agricultural Co-operatives (BAAC), Office of Insurance Commission (OIC), Federation of Thai Industries (FTI) and Thai Chamber of Commerce (TCC) will be actively engaged in the implementation of activities aiming to influence approaches to corporate risk analysis and operations of private sector and financial institutions. |
| Academic institutions | Universities with strong expertise in the fields of resource economics, assessment and scenario analysis will contribute technically to the analytical and capacity building work to be conducted under the project. The selected institutions would include: Kasetsart University’s Faculty of Forestry (GIS, modeling and evaluation of biodiversity at species and ecosystem levels), Sukhothai Thammathirat Open University (economic valuation of ecosystems and biodiversity), and Naresuan University’s Faculty of Forestry (scenario analysis and modeling). Furthermore, universities including Burapha University, Chonburi and Mae Fah Luang University, Chiang Rai, located within or close to the target provinces will be invited to serve as technical hubs in their respective regions. Given that each selected province is recognized as strategically important for national economic development, these universities will support the project by providing insights into local socio-economic-political environments for implementation, and as disseminators of the project’s results at provincial level. |
| Civil society organizations | At all stages from PPG and throughout implementation, the project will engage with and involve key social and environmental CSOs with relevant expertise and mandate, including locally-based grass-roots organizations (CBOs), social enterprises, business associations and advocacy groups with international affiliations. The following is a non-exhaustive list: Mae Fah Luang Foundation Under Royal Patronage, World Wildlife Fund Thailand, Population and Community Development Association (PDA), IUCN, Kenan Institute Asia, Seub Nakhasathien Foundation, Thailand Environment Institute; Stockholm Environment Institute Asia, Good Environmental Governance Network, Thailand Business Council for Sustainable Development Network, Stock Exchange of Thailand, Federation of Thai Industries, Alliance for Water Stewardship, Chaipattana Foundation, Green World Foundation, Thai PatInstitute, CSR Club of Thai Listed Companies Association Network, Securities and Exchange Commission (SEC) and the ASEAN CSR Network. |
| International networks and initiatives | The project will be implemented with technical support and networks provided through selected international initiatives, such as the Sustainable Rice Platform (a global multi-stakeholder initiative with 50 institutional members), the UNEP Finance Initiative/Natural Capital Declaration (an initiative that promotes the integration of natural capital into mainstream financial system and financial institutions’ operations, products and decisions), and TEEB (which provides capacity development and technical support on valuation of ecosystem services and natural capital accounting as well as economic instruments and incentives). |

3. Gender Considerations. Are gender considerations taken into account? (yes  /no ).

Research indicates that sustainable production practices in the targeted sectors may have significant long-term gender impacts. For example, in Thailand’s rice sector, the labor input of women into rice farming represents approximately 40% of the total labor force. Women’s share of landholdings is almost 30%.. The project preparation phase will conduct a gender gap survey and analysis in order to incorporate a gender perspective in project interventions and provide an impartial platform to address gender concerns. Such data will enhance the project’s effectiveness in understanding, promoting and incorporating gender equality and its contribution to sustainable development. Additionally, specific logframe indicators and targets will be set related to gender equality or inclusiveness, as well as explicit budget allocations to enable meaningful M&E through collection of gender-disaggregated data. The project preparation phase will also engage first-hand women’s voices by employing community-level participatory research involving women’s groups to target opportunities specifically related to women’s roles in the targeted sectors, related to their role and dependencies in production, finance and decision making. Selection and design of technological and institutional interventions will be undertaken in close collaboration with local women’s organizations. UNEP has recently adopted the Gender Marker and Guidelines which will ensure that project design meets the gender requirements of GEF as well UNEP.

# 4 Risks. Indicate risks, including climate change, potential social and environmental risks that might prevent the project objectives from being achieved, and, if possible, propose measures that address these risks to be further developed during the project design (table format acceptable).

Table 1: project risks and mitigation strategies

| # Risk | # Rating | # Mitigation Strategy |
| --- | --- | --- |
| # Government budgetary constraints at national and local level | # M | # Initial assessments of the feasibility of budgetary and implementation provisions have been conducted jointly with the executing partners. During the project preparation phase, commitments on budgetary support and cofinancing will be formalized during the project preparation phase. Furthermore, the project will continue to seek cofinancing through private sector partnerships and other sources throughout the project’s duration. |
| # Limited capacity of local/national institutions to implement project activities. | # M | # The project will ensure full support throughout the implementation phase though support via the Executing Agency, including activities for targeted capacity-building, in order to specifically prepare local and national institutions for their respective roles and responsibilities. This targeted capacity-building support will also aim at addressing specific challenges due to weak understanding within national governmental institutions and other stakeholders of the concepts and approaches relating to ecosystem management and Natural Capital (particularly through Outputs 2.2.3). Implementation will additionally be supported by a range of local and international institutional centers of excellence such as universities and research institutions as well as UNEP’s Regional Offices for Asia and the Pacific, and around the world. |
| # Weak coordination and partnerships among different ministries, provincial governments and private sector | # M | # The implementation of Natural Capital accounting, as well as integration of Natural Capital into economic sectors requires active involvement of a wide range of stakeholders including private sector actors, as well as close coordination among all relevant ministries and provincial governments. In view of this, the project will ensure that all key stakeholders are involved from the initial stages of project planning and implementation, by building upon and strengthening existing coordination mechanisms (e.g. coordination mechanisms relating NBSAP and BIOFIN). Furthermore, project output 1.1.2 specifically aims at establishing institutional mechanisms to ensure strong cross-sectoral coordination and collaboration. |
| # Low level of participation and support from stakeholders | # L | # The risk is considered low due to pre-existing engagement and excellent working relationships among all partners. The project will mitigate this risk by employing a participatory and consultative approach to build consensus and enhance local ownership. This latter is especially important at provincial level, and is a key to project success. A clear emphasis on economic benefits to e.g. the local farmer community or local tourism businesses will also serve to mitigate any risk of inadequate stakeholder support. |
| # Impact of climate change on production landscapes and stakeholder’ decision-making | # L | # Climate change impacts impose additional pressures on vulnerable and risk-averse farmers, potentially diminishing their readiness to participate in any innovative activity in the targeted landscapes. The project will mitigate this risk through a comprehensive awareness-building program targeting local government and participating communities. |

# 5. Coordination. Outline the coordination with other relevant GEF-financed and other initiatives.

The project will maximize synergies and complementarities with other major recently-completed and ongoing initiatives in Thailand. The EU, Thailand and Germany co-funded the recently-completed project on Enhancing Economics of Biodiversity and Ecosystem Services in Thailand and South-east Asia (ECO-BEST). ECO-BEST (2011-2015) project pioneered the introduction of TEEB concepts to policymakers and planning agencies concerned with biodiversity in protected areas in Thailand. Initial capacity-building efforts and networks established among experts and policymakers will be utilized in implementing this GEF project. The ‘TEEB for Agriculture & Food’ study is conducting sectoral analyses (including for rice) to highlight the diverse benefits to humans of appropriately managed rice production systems (in terms of the provisioning of food, water quality and quantity, raw materials and climate change mitigation). The findings of the study will inform this GEF project. The methodological approaches used to account for the externalities of eco-agri-food systems can be adjusted to the project approach of conducting landscape level analyses of different production systems within different socio-economic contexts for policy reform.

Furthermore, Thailand has implemented several other initiatives to institutionalize biodiversity non-market values in specific thematic or geographic situations. These include the Biodiversity-Based Economy Development Organization (BEDO) project on PES for elephant conservation in Ang Lue Nai Wildlife Sanctuary, the GEF-funded UNDP-DNP CATSPA Project for strengthening financial management of five of Thailand’s protected areas, the GEF-funded UNDP-PCD CBFCM Project to develop PES schemes in four pilot catchments, and the USAID-WinRock LEAD Project for paying carbon stock to those who maintain forest areas in Mea Sa Watershed Area. Among the above projects at least one site of the CATSPA project in Inthanon National Park, the CBFCM in Koh Tao (Surat Thani) and both of the ECO-BEST pilot sites are landscapes with significant potential for agriculture and eco-tourism beyond the boundaries of the respective protected areas. The Early Warning System Model for Decision Support System for Flash Flood and Landslide Warning System in an Upper Watershed: A Case Study at Mae Wang Watershed, Chiang Mai Province (Junkhiew et.al, 2013) offers a further example. Tools and methodologies applied under the above-mentioned projects will provide a robust basis for further upscaling efforts proposed under this GEF project in designing and introducing innovative and effective economic instruments.

The Rice Department works closely in partnership with the Sustainable Rice Platform (of which it is a founding governmental member) in field testing and validating the recently-launched SRP Standard on Sustainable Rice Cultivation. The Standard, together with its associated Performance Indicators provide an essential underpinning for the proposed GEF project in terms of developing sustainable best practice recommendations tailored to Thailand’s specific production contexts. The project will also work together with the GIZ-implemented Better Rice in Asia (BRIA) project in this regard.

The project will also link with the “Mapping the Natural Capital of Dawna-Tenasserim Landscape” project hosted by WWF Thailand, launched in 2012 to use INVEST for evaluating trade-offs in ecosystem services. The initiative involved collaboration with Naresuan University’s Faculty of Forestry on scenario analysis and the use of ARIES and INVEST in modeling water quantity and quality for the Klong Tha Dee sub-river basin, Nakorn Si Thammarat. The acquired data helped shape recommendations for changes in water regulation. The National Parks and Protected Areas Innovation Institute (NPII) have also applied INVEST to evaluate ecosystem services delivered by Mae Wong National Park in 2012-14. The experiences gained through the application of tools such as ARIES and INVEST and lessons learned will be reflected in the selection of tools and methodologies for this project.

Internationally, GIZ has developed the Manual on Integrating Ecosystem Services into Development Planning: A Stepwise Approach for Practitioners as a guidance document based on the TEEB approach (2012). The manual aims to assist government officers serving in both development and conservation authorities in working together with other stakeholders such as academics, NGOs, community leaders and the private sector to recognise the linkages between nature and development, consider trade-offs associated with development plans and incorporate ecosystem service-related opportunities and risks into their respective development strategies. This manual was adopted and promoted by the CBD Secretariat, ASEAN Center for Biodiversity and other international development agencies, including the global ValuES project supported by the German Government. This guidance document, as well as other publications and methodologies developed under previous initiatives and partners, will be fully utilized in implementing the current project.

6. Consistency with National Priorities. Is the project consistent with the National strategies and plans or reports and assessments under relevant conventions? (yes  /no ).  If yes, which ones and how:  NAPAs, NAPs, ASGM NAPs, MIAs, NBSAPs, NCs, TNAs, NCSAs, NIPs, PRSPs, NPFE, BURs, etc.

The project is consistent with Thailand’s policies and priorities with regard to NC and its obligations under the CBD, in particular in its direct contribution towards attaining Aichi Biodiversity Targets 2 and 3, which include the integration of biodiversity values into national and local development planning processes, as well as into national accounting and reporting systems, and the development and application of positive incentives for the conservation and sustainable use of biodiversity. The Thailand’s National Biodiversity Strategies and Action Plans (NBSAP) for 2015-2021 also contain strategies and action plans related to the integration of biodiversity that are relevant to the focus of the project. In particular, strategy 1 on “Integration of biodiversity values and management with participation from all levels and the strategy 2 on “Conservation and restoration of biodiversity”, and strategy 3 have the direct, strong relevance. Furthermore, the 11th National Economic and Social Development Plan (NESDP), covering the period 2012-2016, highlights the importance of sustainable management of natural resources and the environment, while ensuring food and energy security. The Plan itself adheres to the philosophy of the Sufficiency Economy advocated by His Majesty the King. At the local level, Thailand has developed a set of provincial development plans, many of which refer to the importance of understanding the value of forests, sustaining the ecological base and promoting sustainable use of biodiversity. However, in practice the majority of these plans prioritize promotion of plantations, large-scale development projects and tourism development.

The INDC submitted October 2015 includes targets related to adaptation measures and NC in reference to water resources management, safeguarding food security, promoting sustainable agriculture & Good Agricultural Practices (GAP), and safeguarding biodiversity. Furthermore, the GoT has established additional policies related specifically to forest management, including the National Forest Policy (1985), National Forestry Development Plan (1997), as well as a Resolution adopted by the Cabinet in 1989 to ban commercial logging in all natural forests nationwide. Existing laws on forest management include the Forest Act (1941) which regulates forestry activities and protects forest lands, and the National Forest Reserve Act (1964), which serves as an overarching legislative framework for the regulation of forest areas in the country.  These laws, policies, governance mechanisms and initiatives offer a strong foundation for the proposed GEF-supported intervention, and the integration of Natural Capital values in managing production landscapes. The proposed project would also complement and add value to the GoT’s proactive measures on forest restoration and rehabilitation in major river basins.

In addition to the above, the proposed project contributes to Thailand’s efforts towards the 2030 Agenda for Sustainable Development including Sustainable Development Goals (SDGs), which were adopted by world leaders in 2015 as an overarching development framework for eradicating poverty and achieving sustainable development. In particular, the project contributes directly towards the attainment of SDG 2 (Food Security and Sustainable Agriculture), SDG 6 (Sustainable Management of Water), SDG 8 (Inclusive and Sustainable Economic Growth), SDG 12 (Sustainable Consumption and Production), and SDG 15(Sustainable Use of Terrestrial Ecosystems and Forest Management).

7. Knowledge Management

The project’s communications, outreach and engagement strategy will capture best practice generated by the project and make this information available for dissemination to other corporate, public or smallholders in the targeted provinces and nationally through the evolving partnership.

Furthermore, the project will draw on knowledge, expertise, and networks associated with various existing initiatives managed by UNEP, such as TEEB (particularly relating to its work with the UN Statistics Division and the CBD Secretariat in promoting SEEA-EEA, as well as the ‘TEEB for Agriculture & Food’ initiative), UNEP-FI’s Natural Capital Declaration and Natural Capital Coalition  (formerly ‘TEEB for Business’), and the work relating to assessments of biodiversity and ecosystem services facilitated under the Intergovernmental Platform on Biodiversity and Ecosystem Services (IPBES) and the Sub-global Assessments (SGA) Network- a network of practitioners and policy-makers involved in undertaking ecosystem services assessments. Opportunities will be provided for policy-makers and experts involved in the project to participate in networking and capacity building opportunities provided under these initiatives, and to share knowledge and experiences gained through the project in related fora. At the same time, the project will benefit significantly from international and regional expertise available through these major initiatives, through provision of technical support and involvement of selected experts from those networks.

iii:  approval/endorsement by gef operational focal point(s) and GEF agency(ies)

A. Record of Endorsement of GEF Operational Focal Point (s) on Behalf of the Government(s):

| Name | Position | Ministry | Date (MM/dd/yyyy) |
| --- | --- | --- | --- |
| Dr Kasemsun Chinnavaso | Permanent Secretary & GEF OFP | Ministry of Natural Resources and Environment | 12 April 2016 |

B. GEF Agency(ies) Certification

This request has been prepared in accordance with GEF policies and procedures and meets the GEF criteria for project identification and preparation under GEF-6.

| Agency Coordinator, Agency name | Signature | Date (MM/dd/yyyy) | Project Contact Person | Telephone | Email |
| --- | --- | --- | --- | --- | --- |
| Brennan Van Dyke, Director, UNEP-GEF Coordination Office |  | January 18, 2017 | Max Zieren, Task Manager Asia | +66-2-288-210 | max.zieren@unep.org |

Annex 1: Characteristics of proposed target provinces

| # Province | # Bio-physical settings | # Challenges and Potential |
| --- | --- | --- |
| Chiang Rai | - Surrounded by forested mountain ranges, paddy rice is grown in the Kok River valley - Headwaters are mainly located in the province, and offers strong potential for promoting sustainable forest management and integrated water resources & catchment management. - Rice is grown mainly for sub-sistence or household consumption, with limited market surplus. - Rich and diverse upland forest ecosystems, rich in biodiversity, and ecosystem services to downstream beneficiaries: - The province is 1,167,800 hectares large with 480,116 hectares of forests in 2014, and deforestation rate of 6% over 10 years (2004 – 2014). , - The province harbors at least 18 global and national threatened spcies and one endemic species (Banded Slender Skink - Lygosoma haroldyoungi), including mammals: Common Otter (Lutra lutra)-NT, Assamese Macaque (Macaca assamensis)-NT, Tiger (Panthera tigris) –EN, White Handed Gibbon (Hylobates lar) –EN, Asiatic Black Bear (Ursus thibetanus)-VU, Hog badger (Arctonyx collaris) –NT, and Sumatran Serow (Capricornis sumatraensis) VU; birds: Sarus crane (Grus antigone) and White-shouldered Ibis (Pseudibis davisoni), both extinct in the wild in Chiang Rai; Mrs.Hume’s Pheasant (Syrmaticus humiae)-NT, Blyth’s Kingfisher (Alcedo Hercules)-NT, Black-bellied Tern (Sterna acuticauda)-EN; Baer's Pochard (Aythya baeri)-CR, Black-headed Ibis (Threskiornis melanocephalus)–NT, Jerdon’s Bushchat (Saxicola jerdoni)–LC, Giant Nuthatch (Sitta magna)–EN; and Swan Goose (Anser cygnoides) –VU. - The province has four protected areas including the Nhong Bong Khai Non-hunting Area, a wetland supporting e.g. the migratory Baer's Pochard bird (Aythya baeri), listed as vulnerable; the Luang National Park, which harbours a population of tiger (Panthera tigris); the Khun Chae National Park, with e.g. significant species like Slow Loris, White Handed Gibbon (Hylobates lar), Leopard Cat (Prionailurus bengalensis), and Sumatran Serow (Capricornis sumatraensis); and the Lam Nam Kok National Park with rich Dipterocarp forests. | - Deforestation in key watersheds and quality of tourism recreational sites. Water supply for urban and irrigated rice use increasingly challenged. - To be impacted by macro-infrastructure development (ADB supported Greater Mekong Subregion - Economic Development Corridor). Roads, railways and industrial development will significantly change current land use patterns. - Strong interest among foreign investors in the province. - Good potential for linking rice cultivation, sustainable management of watershed and water resources management, and introduction of sustainable rice cultivation practices. - High potential for mass and eco-tourism. - High potential for, and strong local government commitment to, improving forest protection and management through SFM practices, which will generate both BD and SFM GEB. - This province has been proposed by the GoT as a focus for efforts to link biodiversity conservation and NC inter-dependencies of the tourism, rice and water services sectors with well managed and fiscal/policy-supported Sustainable Forest Management mechanisms. |
| Chonburi | - Flat land with isolated forested areas in the central region, including several wetlands, and a long coastline with 47 islands popular with the tourism sector, including 3 big ones: Khram Island (important for turtle nesting in Gulf of Thailand), Si Chang Island, and Larn Island. - Chonburi is 436,000 ha large with 54,349 hectares classified as forests in 2014, with an increase of 12.5% over the 10 years (20014 -2014) due to reforestation and etsblishment of treecrop plantations. Notwithstanding its heavy urban development, the province contains a number of diverse natural habitats important for maintaining threatened wildlife species (12 species listed on IUCN Red DataBook) and 4 endeminc species: Slender-tailed Four-clawed Gecko (Gehyra angusticaudata), Western Four-clawed Gecko (Gehyra lacerate), Roule’s Legless Skink (Isopachys roulei)-DD; and the Triangle Blackhead (Sibynophis triangularis) –NT. Of the 12 threatened species highlights include: Irrawaddy dolphin (Irrawaddy dolphin) –VU; Dugong (Dugong dugon) –VU; Pileated Gibbon (Hylobates pileatus)-EN; Hog deer (Hyelaphus porcinus)- EN,; Manchurian Reed Warbler (Acrocephalus tangorum) –VU; Island rat (Rattus remotus) – LC; Large Flying Fox (Pteropus vampyrus) –NT; Southeastern Leaf Turtle (Cyclemys atripons) –NA; Small Flying Fox (Pteropus hypomelanus)-LC; Lyle’s Flying Fox (Pteropus lylei) –NT; Southern Butterfly Lizard (Leiolepis belliana belliana)-NA; and Small spotted Coral Snake (Calliophis maculiceps) –LC. Chonburi province has four protected areas and one National Park, yet none of global significance to biodiversity conservation (as if classified as MAB or WHS). Yet protected areas such as the Khao Chao Bor Thong Waterfall National Park are key to protecting important forested catchment for watersupply downstream, as well as recreational functions for the millions of tourists visiting the province annually. The Khao Kheow and Khao Chompoo Wildlife Sanctuary have good quality Tropical Moist Evergreen Forest (80% of the WS) and key fauna found here include Barking Deer, Leopard, and Leaf Monkeys. The park experiences challenges with wildlife poaching, as well as on managing the increasing tourism pressures. Khao Kheow is well known as an Open Safari Park and eastern Thailand's ecotourism hotspot. | Major competition for water resources (agriculture, tourism, industry, golf courses). Coastal tourism and industrial development have led to significant environmental degradadtion, pollution of coastal waters as well as challenges with solid waste management; these have negatively impacted the agricultural sector, especially as a result of competition for land and labor. Maintaining production levels and area of rice cultivation is challenged by urban / industrial development and other crops with higher returns and lower labor requirements (e.g. oil palm, sugar cane, rubber). Expansion of infrastructure development (e.g. road and water storage) is possible. High potential for mass tourism, but low potential for eco-and agro-tourism. NC-dependent beneficiaries of ecosystem services are abundantly found in this province in the industrial, tourism and water services sectors. This province has been proposed by the GoT to focus efforts to enhance protection of remaining forest, coastal and marine resources, through making the case as well as establishing sector policies and fiscal measures to protect biodiversity, water and recreational services through collaboration with the tourism and water services sectors. |
| Trat | - Trat is the easternmost province along the Thai coast. It has borders with Chanthaburi Province to the northwest, Cambodia to the east, and the Gulf of Thailand to the south. - The province of 2,866 sq.km.(286,600 hectares) includes 41% under agricultural. The land is mainly utilized for fruit farming (Durian, Rambutan, Mangosteen, Lonkong etc.) and other smaller crops rather than rice farming or livestock (2011). - It has 90,179 hectares classified as forest in 2015 which represents 31.46% of the provincial area, which is high by average Thai statistics. Some key species endangered (Thai Red Data list) include: Indochinese Water Dragon (Physignathus cocincinus) as Endangered (EN); the Large Flying Fox (Pteropus vampyru), Northern Smooth-tailed Treeshrew (Dendrogale murina) and Southeastern Leaf Turtle (Cyclemys atripons) - all three listed as Vulnerable (VU); the Small Flying Fox (Pteropus hypomelanus) and Silvered Leaf Monkey (Semnopithecus germaini) listed as Near threatened (NT). There are also the endemic Triangle Blackhead (Sibynophis triangularis) as well as the endemic Ko-Chang-frog (Rana kochang). - Trat province has led the country on mangrove restoration projects, including through its Prednai community project, which restored 1,850 hectares of mangroves, mainly with the purpose to enhance coastal protection against impacts of tropical storms. This model is now being replicated through seven Community Learning Centers in six Thambons as part of US $150,000 Mangroves for the Future project implemented by RECOFTC and partners. Trat also implemented a Mangrove Demonstration project under the former UNEP/GEF (ID# 885) ‘Reversing Environmental Degradation Trends in the South China Sea and Gulf of Thailand’, project. - Trat has two National Parks: the first, the Mu Koh Chang National Marine Park has an area of 650 square kilometers (65,000 hectares), including more than 52 islands. The most notable island within the archipelago is Koh Chang, which is also a quickly developing tourism area. Established in 1982, specifically to protect its reef habitats, it is an IUCN Category II protected area. Koh Chang island has steep hills covered for approximately 75 % with dense tropical rain forest, which is considered one of the country’s best-preserved examples of this type of forest. The protected bays and estuaries around the villages Baan Khlong Prao, Baan Khlong Son, Baan Salak Khok and Baan Salak Phet also have extensive mangrove areas that also rank among the best-preserved in Thailand. Although little has been published regarding its biodiversity, an endemic amphibian, the Rana kochang (Ko-Chang-frog), lives exclusively on the island. Additionally, at least 29 different species of (terrestrial) mammals, 61 types of bird and 42 reptile and amphibian species are found in the area. The second protected area in Trat province, the Namtok Khlong Kaeo National Park (20,000 hectares) is situated inn Khao Saming and Bor Rai districts. The NP comprises several densely forested mountain ranges including Khaokaw, Tabard, Tachoat and Kampang mountains, which also serve as the border between Thailand and Cambodia. The highest peak is Khao Tabath at 836 metres above sea level. The majority of the forest area is classed as Moist Evergreen Forest, including valuable species of Dipterocarpaceae, Marlabar ironwood, Sterculiaceae, Meliaceae, Lagerstromeae, plus many palm species such as rattan, fishtail palm, and areca. The area has some important species such as Tiger (Panthera tigris), Sumatran Serow (Capricornis sumatraensis), Gibbon, Common Munjak, Mouse Deer, Squirrels, Pangolin, Palm Civet, Wild Boar, and (Malayan Sun-?)Bear. | - Main environment issues in Trat Province are waste management, water pollution and coastal erosion. - Trat has strong significance and potential as a pilot site for the GEF project, given the abundance and health of its natural resources such as forests, rivers and reefs. The province has a vibrant agricultural sector, yet also has a growing potential for (sustainable) tourism, as confirmed by the designation of Trat by the Tourism Authority of Thailand for what it refers to as ‘low-carbon holidays’. The province will use Mak Island as a model to enhance the concept of a low-carbon destination that can be adopted by other islands such as the much larger Koh Chang Island. Mak Island, part of the Koh Chang cluster of islands, has been selected as Thailand’s first low-carbon holiday island. Proposed low-carbon projects for Koh Chang include restoring mangroves though tree planting campaigns – replicated as well to other locations, promoting cycling, establishing sailboat and yachting routes, and promoting consumption of locally produced seafood and farm produce, in order to reduce fuel use on transport of goods. This concept needs further elaboration to also include responsible management of the forested watershed to reduce floods in tourism areas, to maintain natural beauty for recreation, to introduce ‘green fins’ in the scuba industry, to reduce waste from the hotel and tourism sector, and other ‘green’ approaches.. |

ibid.

Berg, H., Berg, C, and Thanh Tam Nguyen.  2012. Integrated Rice-Fish Farming: Safeguarding Biodiversity and Ecosystem Services for Sustainable Food Production in the Mekong Delta. J. Sus. Ag, 36: 8, 2012.

Sathirathai, 1998 cited in Barbier, 2000.

The three provinces where the pilot landscapes will be selected within are provisional and will be confirmed at PPG stage.

Accessible at: http://infofile.pcd.go.th/law/1_En_NEQA1992.pdf?CFID=4577293&CFTOKEN=94543183 .

Initiated as a technical research, and gradually developed for court cases by Dr. Pongsak Withawatchutikul and team at DNP. Principles and model can be downloaded at www.dnp.go.th/fca16/file/4stu89xq4s6insl.doc and its analyze paper can be downloaded at www.elib.coj.go.th/Ebook/data/judge_report/jrp2556_11_53.

http://d2ouvy59p0dg6k.cloudfront.net/downloads/report_economic_analysis_of_ecosystemservicesnov2013.pdf

A scenario that depicts what will happen if the region’s PA system is expanded and re-categorized to include a more representative range of critical ecosystems and management systems, and also if renewed efforts are made to better fund and conserve ecosystems and biodiversity outside these protected areas.

Thai Pat Institute and the CSR Club of Thai Listed Companies Association work with the Securities and Exchange Commission (SEC) and the ASEAN CSR Network to support corporate compliance with the Global Reporting Initiatives (GRI). Performance indicators EN11 to EN15 require companies to report on information on location and size of land owned in protected areas or areas of high biodiversity (EN11 core), descriptions of significant impacts of activities, products, and services habitats protected or restored (EN12 core), habitats protected or restored (EN13 additional), strategies for managing impacts on biodiversity (EN14 additional) and number of IUCN Red List species and national conservation list species (EN15 additional).

http://www.ifc.org/wps/wcm/connect/region__ext_content/regions

By 2020, at the latest, incentives, including subsidies, harmful to biodiversity are eliminated, phased out or reformed in order to minimize or avoid negative impacts, while positive incentives for conservation and sustainable use of biodiversity are developed and applied, consistent with the CBD and other relevant international obligations, taking into account national socio-economic situation.

By 2020, at the latest, the mobilization of financial resources for effectively implementing the Strategic Plan for Biodiversity 2011-2020 from all sources, and in accordance with the consolidated and agreed process in the Strategy for Resource Mobilization, should increase substantially from current levels.

Mae Fah Luang Foundation Under Royal Patronage: http://www.maefahluang.org

World Wildlife Fund Thailand: http://www.panda.org

Population and Community Development Association: http://www.pda.or.h/en

IUCN: http://www.iucn.org/asia/thailand/countries/thailand

Kenan Institute Asia

Seub Nakhasathien Foundation: http://www.sueb.or.th

Thailand Environment Institute: http://www.tei.or.th/

Stockholm Environment Institute Asia Center: https://www.sei-international.org/asia/

Thailand Business Council for Sustainable Development Network: http://www.tei.or.th/tbcsd/

Stock Exchange of Thailand: http://www.set.or.th

Federation of Thai Industries: http://www.fti.or.th

Alliance for Water Stewardship: http: http://www.allianceforwaterstewardship.org

Chaipattana Foundation: http://www.chaipat.or.th/chaipat_english/

Green World Foundation: http://www.greenworld.or.th

IRRI household survey, 2010

EU-Thai-German Project, ECO-BEST, by Piyathip Eawpanich 2015 (GIZ Bangkok)

Available at www.eweb.bedo.or.th (Thai only)

Available at www.th.undp.org.

Available at www.undp.org

Available at www.lowemissionsasia.org

Thai Journal of Forestry, 2013. Volume 32 Number 1 January-April 2013. Published by Forestry Research Center, Kasetsart University. Bangkok 10900.

http://www.thainaturalcapital.org/index.php?action=nature

EU-Thai-German co-financed ECO-BEST Project, GIZ Bangkok  (2015).

https://www.cbd.int/doc/case-studies/inc/giz-2012-en-integr-ecosys-serv-in-dev-planning.pdf