Project Identification Form (PIF)

Project Type: Full-sized Project

Type of Trust Fund: GEF Trust Fund

For more information about GEF, visit www.TheGEF.org

`

PART I: Project Identification

| Project Title: | Conservation and Sustainable Management of Turkey’s Steppe Ecosystems |  |  |
| --- | --- | --- | --- |
| Country(ies): | Turkey | GEF Project ID: | 5657 |
| GEF Agency(ies): | FAO | GEF Agency Project ID: | 626050 |
| Other Executing Partner(s): | - Ministry of Forestry and Water Affairs (MFWA); General Directorate of Nature Conservation and National Parks -Ministry of Food, Agriculture and Livestock (MFAL); General Directorate of Plant Production | Submission Date: | April 14, 2014 |
| GEF Focal Area (s): | Biodiversity | Project Duration (months): | 36 months |
| Name of parent program (if applicable): - For SFM/REDD+ - For SGP - For PPP |  | Agency Fee ($): | 221,233 |

- Focal Area  strategy Framework:

| ### Focal Area Objectives | Trust Fund | Indicative Grant Amount ($) | ### Indicative Co-Financing ($) |
| --- | --- | --- | --- |
| BD-1: Improve sustainability of Protected Area systems | GEF TF | 1,051,948 | 4,000,000 |
| BD-2: Mainstream biodiversity conservation and sustainable use into production landscapes, seascapes and sectors. | GEF TF | 1,276,819 | 4,730,000 |
| Total project costs |  | 2,328,767 | 8,730,000 |

- Project framework

| Project Objective: The conservation of Turkey’s steppe biological diversity through a landscape approach that simultaneously strengthens the protected area estate and mainstreams biodiversity conservation objectives and practices into the production landscapes. |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Project Component | Grant Type | Expected Outcomes | ### Expected Outputs |  | ### Trust Fund | ### Indicative Grant Amount ($) | Indicative Co-financing ### ($) |
| 1. Increasing the effectiveness of PA System in Turkey for the effective conservation of steppe biodiversity | TA | 1.Representation of the various steppe ecosystems and threatened steppe species in PA system under various management regimes improved. Indicators - New steppe protected area established in Karacadağ (Karacadag- Sanliurfa Province) protecting 10,000 ha of key steppe habitats and species, including: wild wheat (triticum dicoccoides), wild pea (Cicer echinospermum), sociable lapwing (Vanellus gregarious) and great bustard (Otis tarda), Anatolian leopard (Panthera pardus tulliana) -Enhanced management effectiveness of the 20,000 ha. of the existing Kızılkuyu Wildlife Development Area (WDA) and newly established Karacadag | 1.1. Surveys and analysis for establishment of new PA conducted and completed. i) baseline analysis to identify the area (10.000 ha) of new PA; (ii) ecosystem services assessment; (iii) socio-economic impact analysis, a biodiversity monitoring program, and financial sustainability plan; and (iv) analysis of legal and administrative requirements to establish a new PA; (v) community based management plan for the future Karacadağ steppe PA (vi) biodiversity conservation priorities and monitoring plan. 1.2 Updated WDA management plan w/ focus on steppe biodiversity through: (i) targeted biodiversity surveys; (ii) biodiversity-based training needs assessment of WDA staff; (iii) biodiversity monitoring program; (iv) assessment of ecosystem services in Kızılkuyu steppe; (v) a visitor management program for the WDA. 1.3 (i) Joint biodiversity conservation action plan for the two PA includes: biodiversity hot spot areas within each PA and in the Anatolia steppe landscape around them; hotspot maps; PA-based species and habitat conservation plans; Zoning plans to provide for connectivity and (ii) installation of infrastructure and equipment required for effective management. |  | GEFTF | 750,000 | 3,100,000 |
| 2. Mainstreaming steppe biodiversity conservation into production landscapes | TA | 2. Reconciliation of land use activities with steppe biodiversity conservation in sensitive buffer zones around Karacadağ Indicators -Biodiversity/steppe ecosystem vitality objectives and targets mainstreamed into agriculture and pasture land use practice across at least 50,000 ha. steppe area (declared as buffer zone) around Karacadağ Protected Area, as measured by the GEF tracking tool - At least 400 natural resource management professionalsand farmers trained in biodiversity main-streaming practices relevant to their areas of expertise (farming, pasture land) - FAO Voluntary Guidelines on Land Tenure with biodiversity conservation criteria mainstreamed applied across at least 20,000 hectares of leased pasture and croplands; - Application of Save and Grow sustainable crop production intensification methods across at least 5,000 ha; and application of Global Agenda for Sustainable Livestock methods for improved management of at least 10,000 ha of pasture lands. | 2.1. Designation of a buffer zone around the Karacadağ Protected Area. 2.2 At least 3 community based agricultural and pasture landuse plan(s) (pasture land, ecotourism and crop land management plans) for the buffer zones to secure production activities for local livelihoods while conserving steppe biodversity. 2.3. Biodiversity main-streaming training program developed and implemented for MFAL and farmer organizations. 2.4 Pilot land tenure/ land use licensing process with biodiversity conservation objectives and practices mainstreamed. |  | GEFTF | 611,553 | 2,200,000 |
| 3. Enabling environment for effective conservation of steppe biodiversity across the steppe landscapes. | TA | 3. Steppe ecosystems (landscapes) more effectively managed by a strengthened national and local PAs institutions and stakeholders leading to reduced threats to steppe ecosystems Indicators -Improved management of 2,229,000 ha steppe areas in the Southeastern Anatolian Region. -Improved capacity of at least 750 staff and farmers from pilot area and central government level on steppe landscape scale conservation via the protected area estate and biodiversity mainstreaming into production landscapes. # -Steppe ecosystem fragmentation and disturbance in pilot province reduced by at least 20% as measured by Green Steppe scorecard. At least 1 new institutional mechanism for partner-ing among government and civil society organizations to mainstream biodiversity into agri-cultural land manage-ment operational at provincial level. | 3.1. A national long-term landscape-based strategy for steppe ecosystem and steppe biodiversity conservation in the protected area and productive landscape estates defining priority areas for conservation and connectivity and the range of specific uses and management regimes appropriate to different site types. 3.2. New partnerships among government, universities and CSOs to provide improved access to biodiversity information and expertise to steppe land management professionals at national, provincial and local levels. 3.3 Landscape-based steppe biodiversity conservation training program developed and implemented for GDNCNP and MFAL to enable landscape approach combining both PA estate and productive landscape in steppe biodiversity conservation. 3.4 Inter-institutional coordination mechanisms among key stakeholders (MFWA, MFAL, Agricultural Research Institute, CSOs, Regional University) developed. 3.5. Official “Green Steppe” scorecard for certification of advanced ecosystem based steppe lands management. 3.6 Legal definition of natural steppe lands elaborated to support more robust steppe conservation action. |  | GEFTF | 752,214 | 2,600,000 |
| 4. Dissemination of information and best practicies, monitoring and evaluation | TA | 4. The evaluation of the progress made to achieve the project objectives and otcomes are evaluated and the lessons learned and future implementations are facilitated | 4.1 Final evaluation conducted. 4.2 Project-related “best-practices” and “lessons-learned” published. |  | GEFTF | 100,000 | 255,000 |
| Sub-Total |  |  |  |  |  | 2,213,767 | 8,155,000 |
| Project management Cost (PMC) |  |  |  |  |  | 115,000 | 575,000 |
| Total project costs |  |  |  |  |  | 2,328,767 | 8,730,000 |

- Indicative Co-financing for the project by source and by name if available, ($)

| Sources of Co-financing | Name of Co-financier | Type of Co-financing | Amount ($) |
| --- | --- | --- | --- |
| National Government | Ministry of Forestry and Water Affairs | In-kind | 2,500,000 |
| National Government | Ministry of Forestry and Water Affairs | Grant | 3,230,000 |
| National Government | Ministry of Food, Agriculture and Livestock | In-kind | 1,000,000 |
| National Government | Ministry of Food, Agriculture and Livestock | Grant | 1,500,000 |
| GEF Agency | FAO | In-kind | 150,000 |
| GEF Agency | FAO | Grant | 350,000 |
| Total Co-financing |  |  | 8,730,000 |

- Indicative Trust Fund Resources Requested by Agency, Focal Area(s) and Country

| GEF Agency | Type of Trust Funds | Focal Area | Country Name/ Global | Grant Amount ($) (a) | Agency Fee ($) (b) | Total ($) c=a+b |
| --- | --- | --- | --- | --- | --- | --- |
| FAO | GEF TF | BD | Turkey | 2,328,767 | 221,233 | 2,550,000 |
| Total Grant Resources |  |  |  | 2,328,767 | 221,233 | 2,550,000 |

- Project preparation Grant (PPG)

|  | Amount Requested ($) | Agency Fee for PPG ($) |
| --- | --- | --- |
| No PPG required |  |  |
| (Upto) $50k for projects up to & including $ 1 million |  |  |
| (Upto) $100k for projects up to & including $ 3 million | $91,324 | $8,676 |
| (Upto) $150k for projects up to & including $ 6 million |  |  |
| (Upto) $200k for projects up to & including $ 10 million |  |  |
| (Upto) $300k for projects above $ 10 million |  |  |

| Type of Trust Funds | GEF Agency | Focal Area | Country Name/ Global | PPG ($) (a) | Agency Fee ($) (b) | Total ($) c=a+b |
| --- | --- | --- | --- | --- | --- | --- |
| GEF TF | FAO | BD | Turkey | 91,324 | 8,676 | 100,000 |
| Total Grant Resources |  |  |  | 91,324 | 8,676 | 100,000 |

part ii:  project JustiFication

- Project Overview

A.1.	Project description. Briefly describe the project, including: 1) the global environmental problems, root causes and barriers that need to be addressed; 2) baseline scenario and any associates baseline projects; 3) the proposed alternative scenario, with a brief description of expected outcomes and components and the project; 4) incremental cost reasoning and expected global benefits (GEFTF, NPTF) and adaptation benefits (LDCF/SCCF); 6) innovativeness, sustainability and potential for scaling up.

# Global environmental problems, root causes and barriers

# Turkey has a total land area of 779,452 km2 and is surrounded by seas on three sides: the Black Sea, the Marmara, the Aegean and the Mediterranean. It is one of the biodiversity rich countries in the world while possessing vital resources for people’s food security. Therefore, it is the challenge of Turkey both to protect and use this important wealth rationally for the welfare of the future generations. Due to its three biogeographic regions and their transition zones, and because of its climatic and geographical features changing within short intervals of space due to its position as a bridge between two continents, Turkey has acquired the character of a small continent from the point of biological diversity. Turkey has forest, mountain, steppe, wetland, coastal and marine ecosystems and different forms and combinations of these systems. The ecosystem mosaic of several different ecological characteristics provides nesting and breeding areas for thousands of fauna and flora species and their populations. Another factor that increases this wealth is that two of the four migratory routes of the West Palearctic Region pass above Turkey. This makes it an important place as a feeding and breeding area for birds. Invertebrates constitute the largest number among the identified living species. The total number of invertebrate species in Turkey is estimated at 19,000, of which nearly 4,000 species/subspecies are endemic. The total number of vertebrate species identified to date is about 1,500.

In Turkey, steppes and grasslands, defined as areas covered with herbaceous plants, are currently about 32 million ha of  land surface. Only 6% are protected, and 44% are still natural (see Table 1). The steppe ecosystems in Turkey are prevalent especially in Central Anatolia, in the high mountain floors of the Aegean and Mediterranean Regions and in a major part of Eastern Anatolia. There is no legal definition for steppes in Turkey, and they are considered as part of ranges, pastures, meadows, and grasslands.  All steppe lands in Turkey are owned by the state, but certain utilisation rights delegated to local people and local administrations.

Table 1. Category of steppe ecosystems of Turkey, their size and land use type

| Category of Steppe | Area (ha) | Key BD Areas (%) | Protected Areas (%) | Arable (%) | Agric (%) | Pasture (%) | Permanent crops (%) | Natural (%) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Mountain Steppes |  |  |  |  |  |  |  |  |
| Mid-Anatolia mountain | 8,362,018 | 13 | 0.7 | 27 | 23 | 1 | 0.9 | 48.7 |
| Central Eastern Anatolia Mountain | 2,788,501 | 28 | 0.0 | 11 | 17 | 1 | 0.6 | 70.0 |
| Eastern Anatolia Mountain | 5,181,794 | 27 | 2.2 | 13 | 16 | 2 | 0.1 | 69.2 |
| Eastern Anatolia High Mountain | 1,567,547 | 34 | 3.2 | 2 | 7 | 1 | 0.0 | 90.5 |
| South Eastern Anatolia Mountain | 1,223,513 | 28 | 0.0 | 36 | 19 | 23 | 2.8 | 19.0 |
| Plain Steppe |  |  |  |  |  |  |  |  |
| Mid-Anatolia Plain Steppe | 7,821,932 | 14 | 6.2 | 47 | 22 | 5 | 1.6 | 24.7 |
| South Eastern Anatolia Plain | 2,532,580 | 37 | 0.8 | 56 | 12 | 7 | 7.0 | 18.6 |
| Eastern Anatolia Plain Steppe | 1,425,703 | 23 | 0.9 | 43 | 20 | 6 | 0.2 | 31.2 |
| North Eastern Anatolia High Plain | 193,541 | 21 | 0.0 | 58 | 11 | 16 | 0.1 | 16.0 |
| Thrace Plain Steppe | 714,202 | 5 | 0.0 | 67 | 15 | 8 | 0.1 | 11.0 |
| Salt steppes |  |  |  |  |  |  |  |  |
| Mid-Anatolia Salt Steppe | 317,156 | 85 | 59.1 | 16 | 7 | 10 | 0.6 | 66.9 |
| Eastern Anatolia Salt Steppe | 154,309 | 41 | 1.8 | 23 | 15 | 1 | 0.0 | 61.4 |
| Total | 32,282,794 | 30 | 6 | 33 | 15 | 7 | 1 | 44 |

# Figure 1. Distribution of the steppes in Turkey

# (Key Biodiversity Areas of Turkey by Doğa Derneği)

# The plains in Southeastern Turkey contain one of the largest pristine steppe habitats in Turkey. The steppes in this region range from Graminae dominated grasslands to semi-deserts along the Syrian border. At least two thirds of these natural steppes are now converted to agricultural land. The remaining steppes cover the relatively flat stony hills that are not suitable for agriculture and thus are used as pastures by nomads.

These remaining steppes lie within two large Key Biodiversity Areas (KBA) documented by Doga Dernegi in 2006, namely Akçale Steppes and Ceylanpınar. These areas are partly protected through national legislation. For example, the Kızılkuyu Wildlife Developmet Area lies within the Akçakale steppes which are now part of the Tek Tek Mountains National Park. Ceylanpınar shelters the main part of the world population of critically endangered sociable lapwing (Vanellus gregarius) during migration. The Akçakale steppe KBA contains the last remaining well preserved and rich steppe lands in Turkey and Europe. The SE Anatolian Plain’s dominant vegetation cover was once steppe in the lowlands and oak woodland in the uplands and today it is a mixture of grassland and agriculture where tree cover having been extensively destroyed.

# All steppe areas are owned by the state (treasury) but local people and local administrations have certain utilization rights on these areas. However, due to lack of clear management guidance and control, these lands are subject to inappropriate and overuse by local people. It can also be concluded that these lands are subject to tragedy of common which causes in practice several conflicts between local users as well as between local groups and government agencies.

# In Turkey, steppe ecosystems are particularly highly threatened by unsustainable human activities. The largest loss in steppe biodiversity occurs in key ecosystem services, steppe species and its habitats.. The major cause of this is that steppe areas mainly occur in flat plains and  close to settlement areas. The main threat to steppe vegetation in Turkey is the ongoing expansion of agricultural development, resulting in: conversion of steppe to arable lands; increased settlement; increased use of pesticides and fertilizers; afforestation; and over-grazing.

# The most significant cumulative impact of these threats is: (i) the increased fragmentation of steppe habitats; (ii) reduction in the effectiveness of the steppe natural areas as buffer against climate change impacts; (iii) reduction in the capacity of the steppe to provide key ecosystem services, notably potable water, productive soils for agriculture and agro-biodiversity; (iv) the ongoing loss of threatened floral habitats and associated species; (v) incremental loss of habitat for breeding and migrating faunal species such as the goittered gazelle ( Gazelle subgutturosa) ; and (vi) increased severe soil erosion. Despite these developmental pressures, approximately 25 percent of the Anatolian steppes still remain in largely native condition, particularly in the mountainous regions, and are considered as global priorities for conservation action.

Kızılkuyu and Karacadağ of Southern Anatolia have special importance in terms of arid and semi-arid steppe ecosystems. Kızılkuyu and Karacadağ are located in Şanlıurfa-Diyarbakır and Adıyaman Provinces. These areas are undamaged steppe areas of Turkey that are rich in vegetative cover and fauna.

Figure 2. Location of the Kızılkuyu Wildlife Development Area and Karacadağ

Some of the globally threatened species found in Kızılkuyu include the sociable lapwing (Vanellus gregarious) and great bustard (Otis tarda). The sociable lapwing, which is a critically endangered (CR) species, passes through Turkey during its fall and spring migration period and Kızılkuyu is the one of the most important stopover sites during its migration. The great bustard (Otis tarda) is a globally threatened species assessed as Vulnerable (VU) by IUCN and as endangered (EN) according to the Red Bird List of Turkey. A flagship species for steppe habitats, it is under threat because of habitat loss and illegal hunting. The Kızılkuyu area is also an important place for the great bustard as a wintering ground.

Other globally threatened animal species found in the Kızılkuyu area are the goittered gazelle (Gazella subgutturosa), the pin-tailed sand grouse (Pterocles alchata), the cream-colored courser (Cursorius cursor), and Montagu's harrier (Circus pygargus). The main problems for the species and steppe habitat in the proposed project site and its surrounding are: (i) illegal hunting (especially for goittered gazelle and great bustard); (ii) overgrazing, (iii) industrial waste, especially unrefined industrial waters, (iv) lack of water resources for animals and extension of the agricultural areas.

Existing WDA and proposed protected area are not connected each other, for example, through buffer zones or ecological corridors. However, it is possible to establish a corridor between two protected areas in terms of local ecological, social and economical factors. Accordingly, this area is included in potential areas for the Natura 2000 Program.

In this context, the Government of Turkey (GoT) notes the need (i) to conserve steppe habitats, (ii) to protect the areas together with species action plans including relevant capacity development and awareness raising tools (iii) support co-management approaches and (iv) develop a common understanding towards the management of steppe habitats. From this perspective, the project will support the Government of Turkey’s efforts to reduce and manage the threats in the project and replication areas and increase the capacity and awareness for related stakeholders.

Among the key barriers to the achievement of effectively managed steppe protected areas are the following:

Barrier #1: Insufficient representation of Turkey’s steppe ecosystems within the PA system:

In Turkey, currently there are about 32 million ha. steppes areas of which only 6% are protected and legally covered by protected areas. But inside a few PA, different non-steppe ecosystems occupy most of their areas. Less than 1% of the national protected area system can be counted as “steppe protected areas”. Still total protected surface of Turkey is 7,24 % and also the average should be increased in order to represent all habitats in Turkey. This tiny representation of steppe system in Turkey’s PA system is a significant barrier to sufficient conservation of steppe biodiversity within Turkey PA system. The existing steppe protected area (SPA) apart from the small overall steppe area protected, suffers from other shortcomings as well: other SPA exist in forest areas, but their size is much smaller. In short, the existing SPA system does not adequately represent all the geographic zones in Turkey’s steppe areas.

While expanding the SPA network is an established government priority, the baseline approach to this expansion is oriented towards the traditional environment and conservation sector, lacks innovation, and is not carefully prioritized. Steppe ecological and representation gaps are not critically assessed prior to expansion decisions. A significant factor contributing to this barrier is the difficulty of accessing accurate data on steppe ecosystems in the Iranian-Turanian bio-geographical region where steppe systems occur. None of the SPA is designed to conserve landscape scale processes and none of them are managed with strategic approaches. There has never been a full-fledged strategic assessment and gap analysis of the steppe ecosystems covered by the existing PA system. Furthermore, the management processes, the strengths and the weaknesses of the management of the steppe ecosystems are not assessed comprehensively, and the measure to eliminate the threats to the steppes are not taken effectively. Other important specially managed area designations, such as military reserves and wildlife development areas are not considered as part of the SPA network and thus not included in the analysis of coverage and gaps and potential synergies.

Barrier #2: Limited operational implementation for individual Steppe Protected Area (SPA) management practices on the ground.

Although tools for systematic area-based planning, plans and co-management approaches themselves have proliferated world-wide and have been already undertaken in Turkey, these have yet to lead to changes in land use, land management practices and land management planning approaches on the ground. This is currently hampered by the tendency of the research biologists interested in planning to work in isolation. Putting conservation plans into practice requires close involvement from the outset with implementing agencies and other stakeholders, but it also needs biological analyses to be integrated with research on the economic and social consequences of conservation and management of the PAs. There is however no national or local level coordination of the management and development of a management plan of PAs, and the PA system in the steppes is currently inadequate. In addition, protected areas are planned and managed in isolation from the surrounding landscapes and there is no cooperation between conservation agencies, development sectors and land-use planning authorities at national and local levels.

The ecological integrity of some steppe habitats that have been, or are currently, under unsustainable land use management regimes are increasingly degrading due to lack of management plans and management strategies for area and key species. Currently the participation of local people in planning and implementation of programs on conservation or management of Kızılkuyu Wildlife Development Area and Karacadağ is limited. Women are largely absent in decision making process. Generally, not only management plans but also sub-programs to support site management as visitor management program, ecosystem valuation and monitoring programs are absent in the site level. Beside the plans and programs, there is no action plans to conserve key species because of limited experience and interest of protected areas staff.

Due to a lack of involvement of local stakeholders in conservation and sustainable management of steppe ecosystems activities and projects, the steppe PAs are poorly oriented to contribute to or support socio-economic development priorities of local people. PA staff has limited experience in participatory PA management, planning, public involvement and resolving conflicts of interests with resource users. There is also not a common culture of co-management of protected areas, and enforcement activities often result in the aggravation of conflicts with local people. The collaboration and cooperation between national and local PA authorities in the management of PAs in the steppe biome, although highly variable in time and space, is often characterized by a number of inefficiencies and lost opportunities. There is no consolidated database and environmental information system for the steppe habitats not only at the site level but also national level.

Planning and site management include knowledge, experience, work on close cooperation and participation. And also it needs special budget, special site management plans, sub-programs and monitoring systems and adequately trained field staff. There are many gaps to support site management practices in Kızılkuyu and Karacadağ. As a result, key steppe habitats and key steppe species are under threat by uncontrolled utilizations.

Generally, existing planning and management processes in Turkey do not support cooperation and co-ordination.  For this reason, there is minimal cooperation and co-ordination between conservation agencies and other related agencies at national and site level.  The productive landscape context of most SPA is a critical element in the long-term viability and effectiveness of any SPA. Cooperation across sectors is critical to any landscape-scale vision of steppe conservation, as well as to effective monitoring and enforcement work and proactive, prevention-oriented efforts. In the absence of such a cooperative framework, their ability to mitigate primary threats to globally significant steppe biological diversity is compromised significantly.

- Barrier #3: Minimal experience among key government and civil society stakeholders and capacity for sustainable management of steppes.

The overall capacity (planning, management, human resources, skills, knowledge, and equipment) of the national and local PA authorities to manage proactively or respond to key threats and challenges facing existing steppe PAs is generally limited. Two thirds of the total steppe areas are located in the southern and eastern Anatolia and are managed by Van-Erzurum and Malatya Regional Directorate under General Directorate of Nature Conservation and National Parks. At the time of their establishment, these areas were not created for the purposes of steppe conservation hence they provide little no special management attention to the steppe areas within their borders. As a result, traditionally there has been minimal focus on developing expertise in steppe ecosystem dynamics and how to manage a PA to sustain natural steppe ecological processes.

Capacity barriers include information deficiencies and absence of know-how to address specific threats (farming, fragmentation, overgrazing or others). There are a number of key knowledge gaps to support operational decision-making in steppe PAs. Steppe protected areas management requires some specialized expertise in the technical areas and new, more “fluid” perspectives in the management area.  Among Turkey’s PA staff, there is a low level of competence and qualification in steppe conservation issues and management challenges. For example, management requirements for different steppe habitats under different management regimes, cost-effective restoration and rehabilitation measures for different steppe vegetation types and habitat requirements for key floral and faunal species.  Protected areas staff and local people officials have minimal knowledge of the substantial body of experience managing and conserving close cooperation with all and to solve problems together.

Besides the lack of experience and knowledge, the number of staff assigned to protected areas is inadequate to support effective management of the protected areas and its values. When the number of staff is low, the responsibility and workload increases and effectiveness decreases. The high workload prevents staff to dedicate time for learning and adopting new and better PA management experiences and practices.  This is exacerbated by poorly developed mechanisms for exchanging information and experiences among protected areas in Turkey. Language barriers contribute to preventing staff from accessing new lines of thought, management practices and conservation methods available in the international arena.

Regarding data availability, in most protected areas in Turkey, especially steppe habitats, there is a paucity of data and information on priority species numbers, distribution and status, local resource use, and trends regarding current and emerging threats. This lack of basic, reliable information available for decision-makers is a significant barrier that hampers the planning, development and effective management of the steppe protected areas system.

There is very limited experience for co-management of protected areas in Turkey. Due to a lack of involvement of local stakeholders in PA activities and projects, the protected areas are poorly oriented to contribute to or support socio-economic development priorities of local people. For this reason enforcement activities often result in the aggravation of conflicts with local people. PA staff has limited experience in participatory PA management, public involvement and resolving conflicts of interests with resource users.  There are few if any effective co-management and enforcement models.  Turkey’s protected areas system is inexperienced in facilitating local stakeholders, which is a serious barrier to improving steppe protected areas effectiveness.  In some protected areas, the local people have the right to utilize biological resources inside the protected areas multiple use zones.  To ensure that this is done sustainably, the protected area must be able to engage local stakeholders effectively to develop local grazing management practices that ensure this outcome.  Inadequate data and untrained staff hamper the development of effective management prescriptions, such as the optimal timing of visitors or best grazing management practices. There are few coordinated strategies for, and limited coordinated implementation of, the effective conservation of steppe species of concern, notably migrating faunal species.

# On the other hand, there is no common defintion of steppe ecosystems in Turkey. The steppe ecosystems are considered as  pasture lands in Turkey due to the lack of a legal definition of natural steppe ecosystems. This hampers the identification natural steppe ecosystems and the planning of effective steppe conservation measures.

Pasture/grazing land management authority and steppe biodiersity conservation authority are different and their management objectives are totally different from each other. According to the existing definition and understanding, steppe habitats should be grazed by animals and used by nomadic and other stakeholders for agricultural activites as well as industrial development.  Because of lack of the general conservation strategy and unknown hot spot areas for steppe habitats and species, development activities are hampering the conservation activities. This is also a significant barrier to SPA expansion in Turkey.

The baseline scenario and associated baseline projects

The main authority of management of the protected areas and protection of the biodiversity in Turkey is the Ministry of Forestry and Water Affairs (MFWA). The history of Turkey’s protected areas goes back to the 1950s when first national park of Turkey (Yozgat Çamlığı National Park) was declared in 1958. Following this, efforts towards the conservation of biodiversity have been continuing in a more systematic way, especially after 1990’s with the emergence of concepts such as Important Bird Areas, Important Plant Areas, Important Turtle Nesting Areas, and Key Biodiversity Areas. The gap analysis approach, which emerged in late 1990’s and gradually evolved to Systematic Conservation Planning (SCP), also developed rapidly in Turkey. Since then, works on prioritization for nature conservation have been continuing region by region. In 2000, the GEF-II Biodiversity project changed the management and planning approaches of Turkey’s PA Management System. During the last ten years, the General Directorate of Nature Conservation and National Parks (GDNCNP), the General Directorate of Forestry (GDF), civil society organizations (CSOs and universities, with some support from the private sector, have conducted protected area studies in different regions and different ecosystems. To date, 7.632 million ha of land have been declared as protected areas including national parks, nature parks, nature protection areas, natural parks, wildlife development areas, wetland sites, special protected regions, natural sit areas etc. Those areas generally represent forests, wetlands, mountains and a small part of steppe ecosystems. On the other hand, the mountains steppes are managed and planned by General Directorate of Forestry in the forest areas because these steppes are within the forest regime and upper part of the mountain peaks.

The Ministry of Food Agriculture and Livestock (MFAL) is the primary authority responsible for steppe ecosystems in Turkey. The meadows and pastures in the country are managed by MFAL in accordance with the Pasture Law of 1998, which is the main instrument for their protection. However, if meadow and pasture lands are declared as a protected area such as a National Park, a Wildlife Development Area, a Nature Park, or a Nature Reserve, they need to be managed in close cooperation by the Ministry of Forestry and Water Affairs (MFWA) and MFAL in accordance with both the Pasture and National Parks Laws. Both the Pasture Law and the National Parks Law support the management and conservation of those areas and both Ministries should work close cooperation to implement their responsibilities under their own laws.

The baseline projects are drawn from the established work programs of the two ministries that will implement the GEF project, namely MFWA and MFAL. The following programs constitute the baseline program/project situation in Turkey in conservation of steppe ecosystems:

Enhancing of National Protected Areas System Project (2013-2015). This baseline program will directly contribute to the enabling environment. These activities are not directly related with steppes but it will focus on nature conservation and biodiversity within all ecosystems. The objectives/goals of this program are: (i) preparation a national strategy and action plan for protected areas, including strategies, policies and management objectives for both existing and new protected areas, (ii) raising awareness on protected areas and biodiversity conservation, and (iii) increasing the effectiveness of current protected areas management system. This project is supported by national budget of Turkey and it will be an umbrella that will provide guidance and will present a series initiatives supporting common framework to effective management of the protected areas both existing and new ones for all kind of ecosystems of Turkey.

# Strengthening the national nature protection system for implementation of Natura 2000 requirements project (2013-2015): This project is directly related with biodiversity conservation and strengthening of the institutional and technical capacity related with Natura 2000. Under this project, the technical structure for Natura 2000 will be established and potential areas to be protected will be identified.

- National Park Program:  This regular program focuses on planning and management of the protected areas in Turkey. The results of the program are used to assess the effectiveness of the protected areas and conserving biodiversity in the country.

Developing Production Grass -Pasture and Fodder Plants Production Project: The aim of the project is to decrease the pressure on meadows and, pastures; increase the grass pasture and fodder plants production.

Meadow registration and monitoring system (MER-BİS):  The main objectives of the program are: conservation and sustainability of soil and water, avoidance of erosion, reduction of the negative effects of agricultural practices and support conservation of land. The program offers direct benefits to the farmers according to their field practices. With the program, good agricultural practices are implemented and environmental friendly agricultural techniques and studies are supported.

Developing Meadow Services Project: The budget is spent for restoration, rehabilitation and management of the meadows in Turkey. Total budget for Diyarbakır-Şanlıurfa-Adıyaman Provinces are 8,357,770TL.

Conservation Program on the Agricultural Lands for Environment (ÇATAK Project): Conservation and sustainability of the soil and water, avoidance of erosion, increase of the negative effects of the agricultural practices and support conservation of lands are main objectives of the program. The program offers direct benefit for the farmers according to the field practices. With the program good agricultural practices are implements and environmental friendly agricultural techniques and studies are supports.

Table 2. Baseline activities and preliminary co-financing

| Baseline project Co-funders | Name of Co-financier | Brief Description of Co-funded Baseline Project Activities | Type of co-financing | Amount ($) |
| --- | --- | --- | --- | --- |
| National Government | The Ministry of Forestry and Water Affairs (MFWA) | - Enhancing existing protected areas systems - National protected areas strategy and action plan - National ecotourism strategy and action plan | Grant | 1,500,000 |
| National Government | MFWA | - National Parks Project | Grant | 1,730,000 |
| National Government | MFWA | - MFWA staff, office, transport services and procurement of facilities | In-kind | 2,500,000 |
| National Government | The Ministry of Food, Agriculture and Livestock (MFAL) | - Protection, restoration, rehabilitation and the sustainable use of grasslands, pastures and meadows, -Decreasing the uncontrolled implementation and control the overgrazing activities - Registration and monitoring of ranges, pastures and grasslands | Grant | 1,500,000 |
| National Government | MFAL | MFWA staff, office, transport services and procurement of facilities | In-kind | 1,000,000 |
| Total |  |  |  | 8,230,000 |

The proposed alternative scenario, with a brief description of expected outcomes and components and the project

All recent exercises in identifying and prioritizing sites in Turkey point to the fact that the current coverage of protected areas is inadequate. At the same time, during the past decade a number of researchers demonstrated that steppe habitats are proportionally less protected in the existing system. Not only coverage, but also representation of these ecosystems is insufficient. Moreover, the research findings also indicate that 44% of Turkey steppe habitats are still natural. This provides a unique opportunity to designate new natural steppe protected areas to strenghten the existing protected area system and its  representation within the system.

The project will target representation of the various steppe ecosystems and threatened steppe species in PA system under various management regimes. Two priority sites have been selected according to the resource values, species, and their threat status under the National Red List of Turkey and global IUCN categories. The first priority site is Kızılkuyu, which is an existing wildlife development area, and the second priority site which will be implemented as a replication area is Karacadağ.

The project objective is : The conservation of Turkey’s steppe biological diversity through a landscape approach that simultaneously strengthens the protected area estate and mainstreams biodiversity conservation objectives and practices into the production landscapes.

The project will achieve this objective through the following three components:

Component 1.	Incorporating steppe ecosystems into the PA system of Turkey for effective conservation of their biodiversity.

This component will aim to address the first barrier of insufficient representation of Turkey’s steppe ecosystems within the PA system.

The Government of Turkey has committed to expand the national PA network up to 10% by 2015 within the national strategy and policy document. Protected areas established for different purposes to date have reached 7,3 million hectares in total, corresponding to some 7.24 % of the country’s surface area. However, the existing protected areas do not adequately represent the components of biological diversity that the country has, including the steppe and marine ecosystems in particular. Protected area management is still evolving and improving in Turkey. Under the baseline situation, operational management capacities and site level operations are limited. Management plans for the existing protected areas, not only steppes but also other ecosystem types, are developed by outside actors. Besides the planning process, establishing a new protected area process is also carried out individually without stakeholder participation. Analysis of the baseline situation, management planning and establishing processes typically don’t include participatory approaches and landscape-level conservation planning.

Another important gap related with site management is land-use guidelines and sub-management programs. Currently, after preparing long term management plans for protected areas, land-use guidelines and sub-programs are not usually prepared for planners and managers. Therefore, the management plan ends up being a framework document that doesn’t include any details that would allow managers to implement it on the ground. Appropriate sub-programs and plans should be developed that include how the area should be managed in order to achieve the desired objectives for biodiversity protection and that provide information on the requirements for maintaining ecological integrity and viable populations of species in different types of ecosystems across the landscape.

Under component 1, the project will carry out the following activities:

- Carry out the necessary surveys and analysis required for the establishment of a new Steppe Protected Area in Karacadağ. Activities include (i) carrying out  baseline analysis to identify the area (in 10.000 ha) that would fall under the protected area status; (ii) assessing of ecosystem services; (iii) socio-economic impact analysis of the establishment of the new area, a biodiversity monitoring program, and financial sustainability plan; and (iv) carrying out legal and administrative analysis to identify the requirements to establish a new protected area in Karacadağ; (v) preparing first management plan for the future Karacadağ steppe protected area, including financial plan.

- Enhancing management effectiveness of the Kizilkuyu Wildlife Development Area (WDA), by: (i) updating the management plan’s focus on steppe biodiversity through targeted biodiversity surveys; (ii) conducting a biodiversity-based training needs assessment of WDA staff; (ii) elaborating a biodiversity monitoring program; (iii) carrying out an assessment of ecosystem services in Kızılkuyu steppe protected area; (iv) developing a visitor management program for the Kızılkuyu WDA; and (iv) Evaluating management effectiveness of Kızılkuyu WDA with the Management Effectiveness Tracking Tool (METT) to monitor of progress, identify key management issues, and appropriate follow-up steps  in the area.

- Joint biodiversity conservation action plan between the two PA identifying biodiversity hot spot areas within each PA and in the landscape around them and connecting them across the Anatolia steppe ecosystem;  and mapping these hotspots for use in more detailed planning under Component 3. This will include priority species and habitat conservation plans that will look not only at species and habitats within the protected areas but also as this biodiversity inter-relates with the landscape surrounding the each PA.  Work will also include management and zoning plans to provide for connectivity and installation of infrastructure and equipment required for effective management.

Component 2. 	Mainstreaming steppe biodiversity conservation into production landscapes.

This component addresses the second barrier discussed above, namely the limited operational implementation for individual Steppe Protected Area-SPA management practices on the ground, with a particular focus on mainstreaming  biodiversity conservation into production landscapes.

Developing a stronger sub-system of steppe protected area that protects a representative cross-section of steppe ecosystems will be difficult without concerned effort to generate the information, institutional and human capacity needed to support such a process.  In the baseline situation, the GDNCNP, Department for National Parks and Department for Wildlife Development will face capacity constraints in achieving this Government commitment and will require assistance from other non-profit CSO and academic stakeholders to continue down this path to designate new steppe PA consultations and planning documentation.

In order to support site level operationalization of steppe ecosystem conservation and sustainable use, the project will focus its efforts on reconciling land use activities with steppe biodiversity conservation in sensitive buffer zones, by implementing the following activities:

- Designation of a buffer zone around the Karacadağ  Protected Area

- At least 3 community based agricultural and pasture landuse plan(s) (pasture land and crop land management plans) for the buffer zone to Karacadag PA and for lands around Kızılkuyu WDA to secure production activities for local livelihoods while conserving steppe biodversity. The project will provide support to stakeholder working groups to prepare and implement key land use plans that include sustainable agriculture methods and practices with biodiversity conservation objectives mainstreamed into these approaches.

- Biodiversity main-streaming training program developed and implemented for MFAL and farmer organizations and farmers themselves. Providing training to local stakeholders on good agricultural practices and controlled the graizing delivered Implementing pilot demonstrations activities on sustainable use of pasture and arable lands to support biodiversity protection while maintaining household’s livelihoods,

- Pilot land tenure/ land use licensing process with biodiversity conservation objectives and practices mainstreamed.

- Establishing adaptive management system with inherent monitoring program for more effective steppe protected area management in Karacadağ and Kızılkuyu steppe protected areas

- Enhancing visitor experience and knowledge on steppe biodiversity by setting up visitor infrastructures as entrance points, sign and information boards and publications

Component 3. 	Enabling environment  for effective conservation of steppe biodiversity across the steppe landscape.

This component addresses the third barrier of minimal experience among key government and civil society stakeholders and capacity for sustainable management of steppe. In the baseline situation, protected areas are managed by government institutions in central and local levels. The partnerships with other agencies and stakeholders are limited, and inadequate partnership with existing stakeholders is hampering conservation effectiveness.  No official guidelines and related tools are available to catalyze the protected area system’s ability to form effective partnerships for conservation across Turkey.

In the baseline situation, improving management and field conservation capacity will be a struggle for most protected areas in Turkey. None of the protected areas have a long-term strategic management plan developed in participation with local stakeholders. The main reason for this is lack of staff capacity to engagement of the stakeholders.

MFWA policy calls for every staff member to participate in an in-service training program each year, but in the baseline scenario, steppe protected areas are not able to afford this.  There is no specialized national system for training of steppe protected area staff and no regular training planned.  Protected area staff at the central and site level are invited occasionally to participate in various conferences and workshops.  Due to absence of special experts and regular program for steppes, existing capacity doesn’t increase regularly.

For this reason, it is crucially important to prepare a steppe landscape biodiversity conservation strategy as a long-term framework to strength its management and representation in the existing PA system. To date, no gap analysis has been done at a national, system-wide level of the steppe region in terms of species, plant and animal habitats. In the baseline situation, PA system will continue to suffer from gaps in its coverage of the range of habitats and ecosystems and gaps in its management capacity.

However in a baseline situation, the MFWA will be unable to develop and apply a long-term strategy for expanding and improving the effectiveness of the steppe PA network because the system-wide perspective of the protected area system historically has been biased towards forest and mountain systems in terms of prioritization, equipment and methodologies and developing staff capacity. In the baseline situation, this is likely to be continued. Traditionally in Turkey as in many other countries, steppe lands have been recognized for their agricultural values only. Only recently steppe areas have been the subject of increased attention of public, with stakeholders and especially CSOs and academician taking up the issue in the agenda.

On the other hand, the main treats to protected areas come from the  neighboring areas, especially from adjacent areas where inappropriate and unsustainable land use practices are taking place. However, protected areas in the country are mainly designated and managed without buffer zones as there is no buffer zone provisions in relevant legislative and administrative arrangements. In addition, protected areas staff capacity on integrated and participatory management of protected areas in connection with buffer zones is limited.

In order to strengthen the institutional capacity for effective management of the steppe protected areas, and mainstreaming steppe biodiversity conservation into production landscapes the project will;

- Develop a long-term framework for steppe strategy, A long-term landscape-based PA expansion strategy for the second stage of expansion strategy (i.e. until 2023) and focusing on steppe ecosystem and steppe biodiversity conservation in the protected area and productive landscape estates defining priority areas for conservation and connectivity and the range of specific uses and management regimes appropriate to different site types. This will include identifying biodiversity hot spot areas in the Anatolia steppe ecosystem (Turkeys’ steppes) and mapping them for ease of information access.

- New partnerships among government, universities and CSOs to provide improved access to biodiversity information and expertise to steppe land management professionals at national, provincial and local levels. This will include undertaking a gap analysis and institutional mapping exercises in relevant government departments to improve the conservation of steppe ecosystems.

- Prepare an implement a steppe biodiversity conservation mainstreaming training program for GDNCNP and MFAL to enable landscape approach combining both PA estate and productive landscape in steppe biodiversity conservation. This capacity building program and guidelines for the dissemination of know-how on steppe protected area planning, management and buffer zone management in order to (i) develop capacity of PA agency staff at various levels, as well as local people and associations involved in PA planning and co-management; (ii) enhance conservation-related knowledge and capacities among non-PA actors across the broader steppe ecosystem landscape, (iii) establish local offices with relevant capacity to effectively manage the steppe protected areas and its buffer zone.

- Develop/strengthen the existing inter-institutional coordination mechanisms among key stakeholders (MFWA, MFAL, Agricultural Research Institute, National and Regional CSOs, Regional University).

- Official “Green Steppe” scorecard for certification of advanced ecosystem based steppe lands management.

- Legal definition of natural steppe lands elaborated to support more robust steppe conservation action.

Component 4:  Dissemination of information and best practicies,  monitoring and evaluation

Work under this component will ensure the project’s adaptive management approache culminates in a terminal evaluation of the progress made to achieve the project objectives and otcomes.  It will also ensure that the project’s good practice and lessons learned and shared to inform future biodiversity conservation investements in Turkey and worldwide.

Incremental cost reasoning and expected contributions from the baseline, the GEFTF, LDCF/SCCF and co-financing

The Government of Turkey has been active for decades investing in addressing several protected areas management issues; more recently it also started to support new approaches and tools. The MFWA has been carrying out conservation activities within protected areas as well as in production landscapes, in coordination and collaboration with other institutions. These activities vary from planning and management to implementation on the ground for protected areas, species, habitats and other biodiversity elements in different scales (i.e. local scale to national scale, trans-boundary areas). However, Turkey has very little experience on conservation of steppe biodiversity and changing life style, abandonment of rural areas, intensification of agricultural activities, over use of water resources (e.g. for household, agricultural purposes and energy production) is increasing the threats on steppe biodiversity. It is very critical for GDNCNP to adapt itself into changing conditions, create collaborations and partnerships with relevant institutions. This project will help GDNCNP improve its current capacity in main themes: institutional capacity to adapt changing conditions, and background for conservation of steppe biodiversity.

These themes can be explained in more detail as follows;

- Steppe protected area representation will increase both in coverage in number. Currently its only  6% are protected of total surface of steppes in Turkey and there are only two protected areas especially formed for conservation of steppe biodiversity,

- Currently GDNCNP has limited capacity in identification, planning and management of the steppe biodiversity. Throughout this project the capacity of GDNCNP on these topics will increase,

- At the moment there are two major institutions responsible for maintaining, overseeing protecting and managing steppe biodiversity. Conservation of steppe biodiversity is under the jurisdiction of General Directorate of National Parks and Nature Conservation (GDNCNP) of Ministry of Forestry and Water Affairs (MFWA) and sustainable management of steppe resources is under the jurisdiction of Ministry of Food Agriculture and Livestock (MFAL). Although, it is crucial for these two institutions to collaborate to protect the steppe biodiversity, currently there are a few examples of this collaboration, and there are no formal procedures or mechanisms established for collaboration. Consequently, improving the collaborative environment between MFAL and GDNCNP, which will be supported by this project, is critically important.

The MFWA, through General Directorate of Nature Conservation and National Parks, completed a set of pilot projects on conservation biodiversity and effective management of natural resources. The GEF-II Biodiversity and Natural Resources Management Project was completed for four sites which represent four different habitat types. The Conservation and Sustainable Development of Biological diversity and Natural Resources in Yıldız Mountains project is also completed. The MFWA is currently implementing the “Strengthening the National Nature Protection System for Implementation of Natura 2000 Requirements” project” and the “National Biodiversity Strategy and Action Plan (for the period 2008-2017)” which supports the conservation and effective management of existing resources. The proposed project will build on the experience of MFWA in the implementation of these projects.

The proposed project will build on the experience and lessons learned of the GEF-II/Biodiversity and Natural Resource Management Project, GEF/Enhancing Effectiveness of Forest Protected Areas in Küre Mountains, EU/ Conservation of Biodiversity and Natural Resources and Sustainable Development in Yıldız Mountains project that created the acceptance of the need for improved protected areas management systems.  The results achieved by those projects, such as increased capacity of protected areas management, improved public awareness of steppe habitats conservation and strengthened policy/institutional framework, created an understanding within provincial and local government of the need for greatly improved management systems. The proposed project will build on this awareness to expand the coverage of the PA system and mainstream biodiversity conservation into production landscapes.

Global benefits (GEFTF, NPTF) and adaptation benefits (LDCF/SCCF)

The project is expected to contribute to achieve multiple global environmental benefits (GEB) including: (i) conservation of globally important biodiversity adapted to protected areas system; (ii) increased number of hectares in the key steppe area where external inputs are replaced with a biodiversity-rich solution in this globally important ecosystem; (iii) globally applicable, community-based conservation models and tools that support local people – as well as the scientific and national protected areas management authority – to conserve key steppe biodiversity to design as a protected area and to prepare participatory planning of the pilot site, increase knowledge, and improve key steppe species conservation; (iv) biodiversity conservation by increasing and managing available habitat for globally threatened species in Anatolia steppes and reducing unsustainable practices such as overgrazing.

This project will focus on improving the sustainability of protected area system and mainstream biodiversity conservation and sustainable natural resource use in the production landscapes as an integrated strategic response to the threats described above. Ultimately, both mainstreaming and protected area approaches will be needed to conserve Turkey’s steppe ecosystems and achieve sustainable livelihood in Turkey. This project’s long term solutions will foster sustainability and long-term conservation of steppe ecosystems by developing the national steppe strategy document and will guide strengthening and expanding existing PA in priority steppe areas. Also it will improve steppe area conservation through co-management approaches that strengthen the linkages between protected areas managers and other stakeholders.

The global environmental benefits expected to be achieved with the incremental GEF support are shown in the following table.

Table 3. Summary of expected GEB

| Current Practices | Improved practices introduced by project | Selected Global Benefits |
| --- | --- | --- |
| # Protected areas: Insufficient representation of steppe ecosystems into the PA system Limited operational implementations and management practices Pressure on steppe ecosystem Lack of involvement of local stakeholders for conservation of biodiversity Minimal experience among key stakeholders for sustainable management of steppe | Sustainable steppe management practices Mitigation of the threats on steppe areas, developments of conservation practices towards steppe biodiversity elements and guidelines Establishing adaptive management system with inherent monitoring program Reconciliation of land use activities with steppe biodiversity conservation in sensitive buffer zones. Mainstreaming biodiversity conservation into the cropland and pastureland management practices in buffer zones Reducing threats acting on steppe biodiversity. Improving local livelihood through income generating activities Improving pasture management: Reduced over grazing and/or rotational grazing to reduce pressure on vegetative cover | Increased the SPA’s number and protected surface in Turkey By 2016, an additional 10,000 ha added to national system. Improved management of 20,000 ha existing steppe protected area biodiversity conservation mainstreamed into the at least 50,000 ha of steppe lands outside the protected area estate. The model for strengthening of management effectiveness and species protection action plans of steppe protected areas and steppe species will be incorporated in the existing system. Long-term framework strategy for steppe ecosystem and steppe biodiversity in Turkey will be completed Improved or no negative change in the status and condition of globally significant steppe habitats and species, including: wild wheat (triticum dicoccoides), wild pea (Cicer echinospermum), sociable lapwing (CR- Vanellus gregarious) and great bustard (VU-Otis tarda), goittered gazelle (VU- Gazella subgutturosa); Anatolian leopard (EN- Panthera pardus tulliana). Contribution to CBD PoWPA (expansion of PAs, integration of PAs in wider landscapes, and community engagement schemes). |

Innovativeness, sustainability and potential for scaling up.

The project is designed to apply innovative tools for steppe ecosystem biodiversity conservation in Turkey’s PA and agriculture land estates.  One such innovative tool is a ‘Green Steppe” scorecard that the project will enable stakeholders to develop and to pilot under this project as a way to certify, advanced ecosystem-based steppe lands management. In Turkey, as in many countries, it is innovative to plan strategically to conserve biodiversity in both protected areas and in the larger productive landscape in which the protected areas exist.

The sustainability of a protected area system requires that each protected area site is effectively governed and managed according to its specific demands. Some areas will require a low level of management activity while others may require a greater management effort to achieve their conservation objectives. In some instances the most efficient way to improve the system’s sustainability will be to focus on improved site level management for each protected area within the system. With the project, site level management approaches and participatory techniques will be carried out. Landscape-level and ecosystem based participatory conservation planning and management will be developed by stakeholders for Karacadağ steppe ecosystem and species protection action plan for focal steppe species in Kızılkuyu Wildlife Development Area will be developed. On the other hand, community based agricultural and pasture land use plan(s) for the buffer zones to secure production activities will prepare with the participatory and ecosystem based management and planning approaches.  These innovative approaches will be scaled up through a paradigm shift of Turkey’s protected areas managers, staff, local people and other stakeholders that will (i) support the creation and effective management of new protected areas that extends the coverage of threatened species in protected area systems and improves the coverage of their spatial range, (ii) build capacity of natural resource and/or protected areas managers to support and create cooperation and collaboration with related stakeholders who benefit natural resources  (iii) support policies and national strategy for steppe ecosystems that support protection systems.

A.2 Stakeholders. Identify key stakeholders (including civil society organizations, indigenous people, gender groups, and other as relevant) and describe how they will be engaged in project preparation.

The MFWA (General Directorate of Nature Conservation and National Parks- GDNCNP) and the MFAL (General Directorate of Plant Production-GDPP) are the two lead executing partners. These two key stakeholders will be responsible from the coordination of both preparing and implementing processes of the project. Other stakeholders will be included in the preparation of the project document, which will provide guidance on steppe conservation and utilization. FAO has already established a team for this project to oversee project preparation and ensure full participation of stakeholders during this process. The coordination team will ensure that all relevant stakeholders are consulted and involved in the development of the project proposal.

Besides these two ministries, many National CSOs are working on biological diversity, especially on identification and management of biodiversity within forests, wetlands and steppes. Universities, such as the Harran University, civil societies and CSOs, the Nature Conservation Centre (DKM), WWF-Turkey, Doğa Derneği and the Chamber of Agricultural Engineers will be included to assist the project preparation and oversight as needed. On the other hand, many of the scientists are working on steppe ecosystem in Turkey from Botanical, Ecological and Agricultural Departments in different institutions. They are also key stakeholders to prepare the project.

The project will also include Kızılkuyu and Karacadağ settlements in the surrounding areas so all the local residents are the main stakeholders for preparation and implementation of the project. Consultation with stakeholders will be made on regular manner. At least two workshops with stakeholders will be organized during the project preparation stage to consult, generate information, validate the approach and develop stakeholders’ partnership strategy for implementation of the project. In addition, separate consultations and discussions will be organized with stakeholders to develop a co-financing plan and ensure its implementation.

At national level, a Project Steering Committee (PSC) for the overall and inter-agency coordination of project implementation will be established and chaired by  (MFWA) with the participation of MFAL, the Ministry of Development provincial level representative, National CSO and FAO.

Beside the steering committee there will be a National Project Implementation Unit at the national level. The National Level Implementation Unit will consist of full time staff from MFWA and part time staff from MFAL. The experts and project secretariat will work with this unit and close cooperation with field level unit. The project will be executed by the provincial directorates of the MFWA and the MFAL at the field level. The executing partners will work closely with a wide range of stakeholders, including village cooperatives, village leaders, private farmers, shepherds, the private sector, universities, research institutions, civil society organizations, local communities and residents. A project implementation unit in the field level will be established. The unit will include the representatives of local staff of relevant government agencies, local farmer organizations and CSOs as mentioned above. The experts who will be hired by the project will work with field unit to implement project activities.

An independent advisory unit will also be established at national level for providing the project management with technical and scientific advises and inputs. The unit will compose the representatives of national and local level universities, research organizations, and CSOs.

A.3 Risks. Indicate risks, including climate change risks, potential social and environmental risks that might prevent the project objectives from being achieved, and, if possible, propose measures that address these risks to be further developed during the project design (Table format acceptable).

Table 4. Risk matrix

| Risk Type | Probability | Mitigation |
| --- | --- | --- |
| Poor project coordination | High | Close and collaborative cooperation between many institutional stakeholders (particularly the MFWA and the MFAL) will be essential for the project to achieve its stated goal and objectives. This is mitigated to some extent by the positive experience of collaboration of the project management team and further through the structure of it, project management and project steering committee for project management |
| Low capacity of local and national institutions | Medium | National institutions capacity and technical expertise in MFWA/MFAL staff at various levels are weak. To mitigate this risk, the project will support the institutional framework and technical capacity development at national and local levels, a capacity building program and training at central and local levels.. |
| Climate change | Low | Climatic changes will require evolving research on the best approach for the newly proposed technologies. The MFAL and the MFWA, with the support of FAO technical expertise, are in a good position to adopt forthcoming research results. On the other hand, climatic changes can also increase political support for the project. |
| Low ownership and lack of sustainability of new technologies and techniques | Low | Lack of ownership and subsequent lack of sustainability of new technologies promoted under the project could cause difficulties in achieving desired adoption levels. This will be mitigated through the above mentioned capacity building program and through an awareness campaign targeted at project beneficiaries. This capacity building program will involve tools, such as economic models and plans, economic analysis that clearly show that there is an economic and social benefit to the adoption of these technologies (win-win). |
| Loss of income for local people | Medium | Because of the establishment of a new Steppe Protected Area, there will be some limitation for local people who are living in and around the area. The income level could decrease based on limitations and conservation statues of the protected area. This situation will be mitigated through the creation a new job opportunities. Some of the local people will be able to find job in community based sustainable tourism activities including local guides and they will be able to sell their local handcraft and dairy products to the visitors. Additionally, the project will provide support to local area attractions through awareness raising, promotion, visitor facilities and marketing activities which will ultimately contribute to provide alternative income for the local people. The nationwide ÇATAK Program will cover the lost incomes of local people, which originates from the introduction of conservation measures in private lands. |

A.4 Coordination. Outline the coordination with other relevant GEF financed and other initiatives.

The proposed project will be coordinated with and benefit from the pipeline FAO/GEF project on sustainable land management and climate friendly agriculture in Turkey, which is aiming, among others, rehabilitation of degraded dry lands including pastures and mainstreaming biodiversity conservation into production landscapes in Konya Closed Basin. Specifically, (i) preparation of pilot integrated SLM and biodiversity conservation land use plan,(ii) certification of forest and rangeland landscapes by internationally recognized environmental standards that incorporate biodiversity considerations, (iii) establishment of biodiversity monitoring system, and (vi) quantification of ecosystem services values in pilot areas of KCB, and (v) relevant enabling environment activities, will be the main outcomes that will be coordinated with proposed project.

The project will also be aligned with on-going FAO GEF project on Alignment of Turkey's National Action Plan with UNCCD 10-Year Strategy and Reporting Process. Special attention will be given to mainstreaming biodiversity conservation into land use strategic planning process and to the monitoring system to be establish for UNCCD reporting.

The Project should also benefit from the methods for integration of biodiversity conservation into forest landscape management developed under the ongoing UNDP/GEF project on Integrated Approach to Management of Forests in Turkey, with demonstration in high conservation value forests in the Mediterranean region project. This project promoted an integrated approach at the landscape level to the management of high conservation value forests in the Mediterranean region to secure, among others, biodiversity mainstreaming.

National Basin Management Strategy of Turkey (NBMS) will be the national strategy with which the present proposal will coordinate. The results and the recommendations of NBMS will lead the proposed project to identify the participatory measures that would maximize social economic benefits and build capacity among key stakeholders – including local governments, communities and private sector as part of the process of building resilience of the rural economy and ensuring the sustainability of the natural resource base.

The Project will also benefit from the ‘Strengthening Protected Area Network of Turkey: Catalyzing Sustainability of Marine and Coastal Protected Areas’, another GEF funded project, which will be completed by 2014. Although the project is about marine ecosystems, general project framework is very similar and concentrated on improving the effectiveness of the marine protected areas. Know-how of the Marine Protected Area project will be unique asset for institutional capacity building, governance issues, developing a collaborative working environment, during the implementation of the steppe project. And finally, FAO will work closely with CITES and the IUCN Cat Specialist Group to contribute information generated on the Anatolian leopard under this project and to benefit from CITES and IUCN expertise in this area.

- Description of the consistency of the project with:

B.1 National strategies and plans or reports and assessments under the relevant conventions, if applicable, i.e. NAPAS, NAPs, NBSAPs, national communications, TNAs, NCSAs, NIPs, PRSPs, Biennial Update Reports, etc.

The proposed project is consistent with the various strategies, programs and action plans published by the Government of Turkey (GoT) pursuant to its commitments under the relevant international environment and nature conservation conventions, as well as with the relevant national development plans and strategies adopted by the GoT. With respect to the environmental conventions, i.e. the Convention on Biological Diversity (CBD), the proposed project is fully consistent with and will contribute significantly to implementation of the following strategies, programs and action plans:

The National Biodiversity Strategy and Action Plan ( 2007) is developed by GoT institutions pursuant to the CBD. One of its strategic objectives is “to protect steppe biological diversity, to ensure the sustainable use of its components, as well as to ensure the fair and equitable sharing of the benefits from the utilization of genetic resources; and to combat against the loss of steppe biological diversity and the social-economic results of that”. And the strategy calls for identifying the state of the existing species in steppe ecosystems, mapping and determining of the threats. The proposed project will contribute specific responses addressed in the National Action Plan, including;

- The education of people specialized at taxonomy, ecology and genetic areas to be able to build up a steppe biological diversity inventory with the cooperation of education and research institutions, and the organization of those people so that a systematized work can be done,

- The identification of steppe areas and the special areas which have special importance for biological diversity and/or are especially under threat in steppes and mapping them by using GIS,

- The identification of the status of existing species in steppe ecosystems, the determination of the threats to the existing species and habitats, and an update of the red lists of the endangered species.

The proposed project will directly support to the implementation of these objectives by preparing and developing a national strategy that incorporates steppe biodiversity conservation considerations into actions, tools and guidelines to manage of steppe ecosystem and realizing the actions under the objective.

Furthermore, the project will directly address one of the cross-cutting issues requiring capacity development, namely national thematic assessment identified in Turkey’s National Capacity Self-Assessment (NCSA) under the Rio Conventions (2011).  The NCSA was financed by Global Environment Facility (GEF) through the United Nations Environment Program (UNEP)  to assess  the existing national capacity, identify and prioritize the capacity needs and reveal the cross-cutting issues and synergy areas among three Rio conventions (UNCBD, UNFCCC, UNCCD) to be implemented in Turkey.

The National Capacity Action Plan has been prepared by the Turkey’s National Capacity Self-Assessment (NCSA) project for the three Rio Conventions (UNFCCC, UNCBD, UNCCD) in order to be implemented effectively. The National Capacity Action Plan includes the activities to be carried out in the synergy areas that cover all three conventions, the current capacity in terms of time, human resources and finance.

Under the national thematic assessment “ 5.2.3. Assessment of National Capacity and Identification of Needs” refer that “With regard to legislation, gap was indentified in some issues while lack of implementation and sanctions was identified in some issues. The principal issues which have legislative gaps are biosafety, use of genetic resources, benefit-sharing, alien species, microorganisms, steppe protected areas and coastal-marine protected areas. The issues where lack of adaptation, implementation and sanction are observed intensify in objectives on planning and sustainable use.”

With respect to GoT National development plans, the project will directly contribute to the Ninth Development Plan of Turkey (2007-2013). Under the strategic objective 4,”Protection and management of rural environment”, protection and management of rural environment and sustainable management of natural resources are a priority for the country’s overall economic development. The other important measure under the Development Plan is “to provide sustainable utilization of natural resources” .One of the main priority under the measure of the Development Plan is to promote strategic management of the country’s steppe ecosystems and its flora and fauna species.

The project will clearly support implementation of the GoT’s National Rural Development Plan (2009-2013), which targets the conservation of agricultural areas, pastures and forests, wetland, steppe ecosystem including flora and fauna resources in areas that will be integrated into forest regimes. The Rural Development Plan underscores the relationship between rural poverty and natural resource degradation, recognizing a significant increase in recent years in erosion and degradation of land and water resources in the country, in many cases due to improper farming techniques and increasing climate variability (droughts, floods and landslides). To mitigate these processes, the Plan gives priority to strategies, measures and activities that address management of steppe ecosystems.

B.2 GEF focal area and/or fund(s) strategies, eligibility criteria and priorities

The proposed project is a single focal area project and in line with the Biodiversity Conservation (BD-1 and BD 2) Focal Areas. The proposed project will contribute to the improvement of effectiveness of existing steppe protected areas as well as development of new steppe protected areas under the BD -1, outcome 1.1 The project will also contribute to the mainstreaming biodiversity conservation and sustainable utilization into the steppe production landscapes (BD 2, outcome 2.1) and its incorporation in policy and regulatory framework at national level (BD-2, outcome 2.2).

The proposed project is also in line with the Aichi Targets adopted at the 10th Conference of the Parties of the CBD, and the Nagoya Protocols. Most directly it will contribute to Aichi Target 1 on making people aware of the values of biodiversity and the steps they can take to conserve and use them sustainably; and to Target 4, on Governments, business and stakeholders at all levels have taken steps to achieve or have implemented plans for sustainable production and consumption and have kept the impacts of use of natural resources well within safe ecological limits. The project will also contribute to Target 14, on ecosystems that provide essential services, including services related to water, and contribute to health, livelihoods and well-being, are restored and safeguarded, taking into account the needs of women, indigenous and local communities, and the poor and vulnerable and Target 19, knowledge, the science base and technologies relating to biodiversity, its values, functioning, status and trends, and the consequences of its loss, are improved, widely shared and transferred, and applied.

B.3 The GEF Agency’s comparative advantage for implementing the project

FAO’s primary comparative advantage for biodiversity conservation is in the productive landscape under the GEF’s BD-2 objective. However, FAO has deep experience in biodiversity conservation overall and in biodiversity conservation in the protected area estate through its technical divisions focussing on forests, fisheries, land and water. The proposed project will benefit from FAO’s extensive work on conservation and management of natural resources specifically conservation of agrobiodiversity within the ecosystem and land management context. Regarding biodiversity conservation and mainstreaming biodiversity conservation into the production landscapes, FAO has gained a rich base of best practices and lessons learned from a diversity of ecosystems and contexts by implementing hundreds of projects and programs. FAO supports member countries on the promotion of the ecosystem approach in agriculture through developing tools, methodologies and providing training, information and advisory services for institutional strengthening, policy reform and national programming. FAO is the leading agency in gathering and disseminating data and information related to agro biodiversity and genetic resources, which are built upon scientific knowledge, local experience and farmer innovation, which are available through FAO’s web sites and information systems such as FAOSTAT, TERRASTAT, LRIS, and GTOS. FAO is also a leading partner in several international initiatives, such as the International Treaty on Plant Genetic Resources for Food and Agriculture and the International Plant Protection Convention, The Commission on Genetic Resources for Food and Agriculture (CGRFA), and the World Overview of Conservation Approaches and Technologies (WOCAT).

FAO has been providing technical support member countries for the establishment and management of protected areas and conservation of biodiversity and wildlife resources. At national level, FAO supported the national park establishment in Kure Mountain area through “National Parks and Protected Areas, Biodiversity Conservation and Rural Development” in 1998-2000 which established a baseline for the recently completed GEF project on the same area. FAO/GEF SLM project in Konya closed basin (including pasture management component and biodiversity conservation) will be operational this year. FAO is also supporting Turkey to align its national UNCCD NAP with UNCCD 10 years strategy including all aspects of land management, monitoring and reporting. Together with UNEP, FAO is supporting the development of new GEF project on “Mainstreaming Biodiversity Conservation and Sustainable Use for Improved Human Nutrition and Wellbeing” which is aiming strengthening the conservation and sustainable management of agricultural biodiversity through mainstreaming into national and global nutrition, food, and livelihood security strategies and programmes.  At regional level, FAO is providing support for the conservation of biodiversity resources through supporting the countries to improve their enabling environment for the protected areas and mainstreaming biodiversity conservation into the agricultural production systems. FAO is supporting several land and biodiversity conservation projects through FAO Turkey Partnership Program, which includes (i) conservation of globally important Agricultural Heritage Systems (GIHAS) in Turkey and Azerbaijan, (ii) conservation agriculture and organic farming in Turkey and Central Asia; and (iii) pasture management in Central Asian countries.  At global level, FAO the proposed project will benefit from FAO’s extensive work on conservation and management of natural resources within the ecosystem context worldwide. FAO is currently implementing 19 GEF country projects in all continents, as well as two regional projects on biodiversity conservation by consolidating the network of protected areas in the South Pacific Islands (Project No. 3819, “PAS: Forestry and Protected Area Management” in Fiji, Samoa, Vanuatu and Niue) and in Africa (Project No. 3984 “SPWA-BD: Development of a Trans-frontier Conservation Area Linking Forest Reserves and Protected Areas in Ghana and Cote d'Ivoire”).

The FAO office in Ankara is well equipped with a multi-disciplinary team, including crop, land and water, livestock and forestry specialists, as well as project management and administration. The local office is also supported by technical back stopping and administrative support from the Regional Office, including specialists in environmental services, bio-energy, forestry, rangelands management, and crop production.

part iii:  approval/endorsement by gef operational focal point(s) and GEF agency(ies)

- Record of Endorsement of GEF Operational Focal Point (S) on Behalf of the Government(S): (Please attach the Operational Focal Points endorsement letter(s) with this template. For SGP, use this OFP endorsement letter).

| Name | Position | Ministry | Date (MM/DD/YYYY) |
| --- | --- | --- | --- |
| Prof. Dr. Lütfi AKCA | Undersecretary, GEF Operational Focal Point | Ministry of Forests and Water Affairs | 04/03/2014 |

B.  GEF Agency(ies) Certification

| This request has been prepared in accordance with GEF/LDCF/SCCF/NPIF policies and procedures and meets the GEF/LDCF/SCCF/NPIF criteria for project identification and preparation. |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Agency Coordinator, Agency name | Signature | Date (MM/DD/YYYY) | Project Contact Person | Telephone | Email Address |
| Gustavo Merino Director Investment Centre Division Technical Cooperation Department FAO Viale delle Terme di Caracalla (00153) Rome, Italy |  | April 17, 2014 | Ekrem Yazici Forestry Officer FAO SEC Ankara, Turkey | + 90 312 3079518 | Ekrem.Yazici@fao.org |
| Jeffrey Griffin Environment Officer/OiC day-to-day matters GEF Unit Email: jeffrey.griffin@fao.org Tel: +3906 5705 5680 |  |  |  |  |  |

TA includes capacity building and research and development.

These are the Euro-Siberian, Mediterranean and Iranian-Turanian