Document of

The World Bank

FOR OFFICIAL USE ONLY

Report No: PP2290

Project Paper

ON A

PROPOSED grant

In the AMOUNT OF US $3.0 MILLION

TO THE

SOCIALIST REPUBLIC OF VIETNAM

FOR A

STRENGTHENING PARTNERSHIPS to protect endangered wildlife in vietnam PROJECT

December 11, 2017

This document has a restricted distribution and may be used by recipients only in the performance of their official duties. Its contents may not otherwise be disclosed without World Bank authorization..

CURRENCY EQUIVALENTS

(Exchange Rate Effective on September 27, 2017)

1,000 Vietnamese Dong = 0.044 United States Dollars

1.00 United States Dollars = 22,729 Vietnamese Dong

FISCAL YEAR

| January 1 | – | December 31 |
| --- | --- | --- |

ABBREVIATIONS AND ACRONYMS

| APEC | Asia-Pacific Economic Cooperation |
| --- | --- |
| ARREST | Asia’s Regional Response to Endangered Species Trafficking Program |
| ASEAN-WEN | ASEAN Wildlife Enforcement Network |
| BD | Biodiversity |
| CBD | Convention on Biological Diversity |
| CCPE | Central Committee of Propaganda and Education |
| CITES | Convention on International Trade in Endangered Species of Wild Fauna and Flora |
| CPF | the World Bank Group Country Partnership Framework |
| DA | Designated Account |
| DARD | Departments of Agriculture and Rural Development |
| DFID | Department for International Development of the U.K. |
| DONRE | Departments of Natural Resources and Environment |
| EA | Environmental Assessment |
| EM | Ethnic Minority |
| FM | Financial Management |
| FPD | Forest Protection Department |
| GDP | Gross Domestic Product |
| GEF | Global Environment Facility |
| GIG | Governance and Inclusive Growth |
| GIZ | German Society for International Cooperation |
| GNI | Gross National Income |
| GoV | Government of Vietnam |
| GWP | Global Partnership on Wildlife Conservation and Crime Prevention for Sustainable Development |
| ICCWC | International Consortium of Combating Wildlife Crime |
| IPF | Investment Project Financing |
| ISDS | Integrated Safeguards Data Sheet |
| KBA | Key Biodiversity Area |
| M&E | Monitoring and Evaluation |
| MARD | Ministry of Agriculture and Rural Development |
| MOF | Ministry of Finance |
| MOJ | Ministry of Justice |
| MONRE | Ministry of Natural Resources and Environment |
| MOT | Ministry of Tourism |
| MOU | Memorandum of Understanding |
| MPS | Ministry of Public Safety |
| NBSAP | National Biodiversity Strategy and Action Plan |
| NGO | Non-governmental Organization |
| ODA | Official Development Assistance |
| PA | Protected Area |
| PAMB | Protected Area Management Board |
| PCRA | Procurement Capacity and Risk Assessment |
| PDO | Project Development Objective |
| PMU | Project Management Unit |
| POM | Project Operations Manual |
| PPC | Provincial People’s Committee |
| PPSD | Project Procurement Strategy Document |
| PSC | Project Steering Committee |
| SEDP SEDS | Socio-Economic Development Plan Socio-Economic Development Strategy |
| SMART | Spatial Monitoring and Reporting Tool |
| STEP | Systematic Tracking of Exchanges in Procurement |
| TA | Technical Assistance |
| TOR | Terms of Reference |
| USAID | U.S. Agency for International Development |
| USD | United States Dollar |
| VEA | Vietnam Environment Administration |
| WEN | Wildlife Enforcement Network |
| WLC | Wildlife Consumption in Vietnam Project |

| Regional Vice President: |  | Victoria Kwakwa |
| --- | --- | --- |
| Country Director: |  | Ousmane Dione |
| Global Practice Senior Director: |  | Karin Kemper |
| Practice Manager: |  | Christophe Crepin |
| Task Team Leader: |  | Thu Thi Le Nguyen |

VIETNAM

STRENGTHENING PARTNERSHIPS TO PROTECT ENDANGERED

WILDLIFE IN VIETNAM PROJECT

TABLE OF Contents

Page

I.	STRATEGIC CONTEXT	1

A.	Country Context	1

B.	Sectoral and Institutional Context	2

C.	Higher Level Objectives to which the Project Contributes	6

II.	PROJECT DEVELOPMENT OBJECTIVE	7

A.	Project Development Objective	7

B.	Project Beneficiaries	7

C.	PDO Level Results Indicators	8

III.	PROJECT DESCRIPTION	8

A.	Project Components	8

B.	Project Cost and Financing	9

C.	Lessons Learned and Reflected in the Project Design	9

IV.	IMPLEMENTATION	11

V.	KEY RISKS AND MITIGATION MEASURES	13

VI.	APPRAISAL SUMMARY	14

A.	Technical	14

B.	Economic Analysis	15

C.	Procurement and Financial Management	16

D.	Environmental Safeguards	16

E.	Social Safeguards	17

F.	World Bank Grievance Redress	18

Annex 1: Results Framework and Monitoring	19

Annex 2: Detailed Project Description	25

Annex 3: Implementation Arrangements	31

Annex 4: Incremental Cost Analysis	37

Annex 5: Theory of Change	47

| APPRAISAL DATA SHEET |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Vietnam |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Strengthening Partnerships to Protect Endangered Wildlife in Vietnam (P162792) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PROJECT PAPER |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| . |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| EAST ASIA AND PACIFIC |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 0000009532 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Report No.: PP2290 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| . |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Basic Information |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Project ID |  |  |  |  |  |  |  | EA Category |  |  |  |  |  |  |  |  |  | Team Leader(s) |  |  |  |  |  |  |  |  |  |  |
| P162792 |  |  |  |  |  |  |  | C - Not Required |  |  |  |  |  |  |  |  |  | Thu Thi Le Nguyen |  |  |  |  |  |  |  |  |  |  |
| Financing Instrument |  |  |  |  |  |  |  | Fragile and/or Capacity Constraints [ ] |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Investment Project Financing |  |  |  |  |  |  |  | Financial Intermediaries [ ] |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  | Series of Projects [ ] |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Project Implementation Start Date |  |  |  |  |  |  |  | Project Implementation End Date |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 31-Jan-2018 |  |  |  |  |  |  |  | 31-May-2023 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Expected Effectiveness Date |  |  |  |  |  |  |  | Expected Closing Date |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 01-Jul-2018 |  |  |  |  |  |  |  | 31-May-2023 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Joint IFC |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| No |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Practice Manager/Manager |  |  |  |  | Senior Global Practice Director |  |  |  |  |  |  |  | Country Director |  |  |  |  |  |  |  | Regional Vice President |  |  |  |  |  |  |  |
| Christophe Crepin |  |  |  |  | Karin Erika Kemper |  |  |  |  |  |  |  | Ousmane Dione |  |  |  |  |  |  |  | Victoria Kwakwa |  |  |  |  |  |  |  |
| . |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Approval Authority |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Approval Authority |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| CD Decision |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| . |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Borrower: Socialist Republic of Vietnam |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Responsible Agency: Ministry of Natural Resources and Environment |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Contact: |  |  | Nhan Thi Thanh Hoang |  |  |  |  |  |  |  |  |  | Title: |  | Deputy Director, Biodiversity Conservation Department |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Telephone No.: |  |  | 84-902282326 |  |  |  |  |  |  |  |  |  | Email: |  | hoangnhan.bca@gmail.com |  |  |  |  |  |  |  |  |  |  |  |  |  |
| . |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Project Financing Data (in USD Million) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Total Project Cost: |  |  |  |  | 3.30 |  |  |  |  |  |  |  | Total Bank Financing: |  |  |  |  |  |  |  | 0.00 |  |  |  |  |  |  |  |
| Financing Gap: |  |  |  |  | 0.00 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| . |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Financing Source |  |  |  |  |  |  |  |  |  |  | Amount |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Global Environment Facility - IBRD as Implementing Agency Borrower |  |  |  |  |  |  |  |  |  |  | 3.00 0.30 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Total |  |  |  |  |  |  |  |  |  |  | 3.30 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| . |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Expected Disbursements (in USD Million) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Fiscal Year | 2019 |  |  | 2020 |  | 2021 |  |  | 2022 |  |  | 2023 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Annual | 0.5 |  |  | 0.5 |  | 0.7 |  |  | 1.0 |  |  | 0.3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Cumulative | 0.5 |  |  | 1.0 |  | 1.7 |  |  | 2.7 |  |  | 3.0 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| . |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Institutional Data |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Practice Area (Lead) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Environment & Natural Resources |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Contributing Practice Areas |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Proposed Development Objective(s) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| The Project Development Objective is to strengthen the legal and regulatory framework, and the related implementation capacity for the protection of threatened wildlife. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| . |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Components |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Component Name |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Cost (USD Millions) |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Component 1: Strengthening the legal and regulatory framework |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 0.85 |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Component 2: Enhancing capacity to effectively implement and enforce policies and regulations related to wildlife protection |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 1.15 |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Component 3: Promoting knowledge sharing and awareness raising |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 0.72 |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Component 4: Project Management and Monitoring and Evaluation |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 0.28 |  |  |  |  |  |  |  |  |  |  |  |  |  |
| . |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Compliance |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Policy |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Does the project depart from the CAS in content or in other significant respects? |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Yes |  | [ ] |  | No |  | [ X ] |
| . |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Does the project require any waivers of Bank policies? |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Yes |  | [ ] |  | No |  | [ X ] |
| Have these been approved by Bank management? |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Yes |  | [ ] |  | No |  | [ X ] |
| Does the project meet the Regional criteria for readiness for implementation? |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Yes |  | [ X ] |  | No |  | [ ] |
| . |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Safeguard Policies Triggered by the Project |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Yes |  |  |  |  |  | No |  |  |  |
| Environmental Assessment OP/BP 4.01 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | X |  |  |  |  |  |  |  |  |  |
| Natural Habitats OP/BP 4.04 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | X |  |  |  |
| Forests OP/BP 4.36 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | X |  |  |  |
| Pest Management OP 4.09 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | X |  |  |  |
| Physical Cultural Resources OP/BP 4.11 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | X |  |  |  |
| Indigenous Peoples OP/BP 4.10 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | X |  |  |  |
| Involuntary Resettlement OP/BP 4.12 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | X |  |  |  |
| Safety of Dams OP/BP 4.37 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | X |  |  |  |
| Projects on International Waterways OP/BP 7.50 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | X |  |  |  |
| Projects in Disputed Areas OP/BP 7.60 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | X |  |  |  |
| . |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Legal Covenants |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Name |  |  |  |  |  |  |  |  |  | Recurrent |  |  |  |  | Due Date |  |  |  |  |  |  |  | Frequency |  |  |  |  |  |
| Project Execution Generally |  |  |  |  |  |  |  |  |  | Yes |  |  |  |  | N/A |  |  |  |  |  |  |  | Recurrent |  |  |  |  |  |
| Description |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| The Recipient shall carry out the Project through MONRE, in accordance with the provisions set forth in Section 2.02 of the Grant Agreement (GA). |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Name |  |  |  |  |  |  |  |  |  | Recurrent |  |  |  |  | Due Date |  |  |  |  |  |  |  | Frequency |  |  |  |  |  |
| Institutional and Other Arrangements |  |  |  |  |  |  |  |  |  | Yes |  |  |  |  | N/A |  |  |  |  |  |  |  | Recurrent |  |  |  |  |  |
| Description |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| The Recipient shall, through MONRE, throughout the period of implementation of the Project, maintain institutional arrangements as set forth in Section 2.03 of the Grant Agreement. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Name |  |  |  |  |  |  |  |  |  | Recurrent |  |  |  |  | Due Date |  |  |  |  |  |  |  | Frequency |  |  |  |  |  |
| Project Operations Manual |  |  |  |  |  |  |  |  |  | Yes |  |  |  |  | N/A |  |  |  |  |  |  |  | Recurrent |  |  |  |  |  |
| Description |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| The Recipient shall adopt the Project Operations Manual (POM) acceptable to the World Bank, and carry out the Project in accordance with the provisions of the POM as set forth in Section 2.04 of the Grant Agreement. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Name |  |  |  |  |  |  |  |  |  | Recurrent |  |  |  |  | Due Date |  |  |  |  |  |  |  | Frequency |  |  |  |  |  |
| Safeguards |  |  |  |  |  |  |  |  |  | Yes |  |  |  |  | N/A |  |  |  |  |  |  |  | Recurrent |  |  |  |  |  |
| Description |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| The Recipient, through MONRE, shall ensure that all terms of reference for any technical assistance or studies carried out under the Project are consistent with, and pay due attention to, the World Bank’s Safeguards Policies. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Name |  |  |  |  |  |  |  |  |  | Recurrent |  |  |  |  | Due Date |  |  |  |  |  |  |  | Frequency |  |  |  |  |  |
| Donor Visibility and Visit |  |  |  |  |  |  |  |  |  | No |  |  |  |  | N/A |  |  |  |  |  |  |  | As appropriate |  |  |  |  |  |
| Description |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| The Recipient shall take or cause to be taken all such measures to identify publicly the Donor’s support for the Project and enable the representatives of the Donors to visit any part of the Recipient’s territory for purposes related to the Project as set forth in Section 2.06 of the Grant Agreement. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Name |  |  |  |  |  |  |  |  |  | Recurrent |  |  |  |  | Due Date |  |  |  |  |  |  |  | Frequency |  |  |  |  |  |
| Project Monitoring, Reporting and Evaluation |  |  |  |  |  |  |  |  |  | Yes |  |  |  |  | Once month after the end of semester |  |  |  |  |  |  |  | Every semester |  |  |  |  |  |
| Description |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| The Recipient shall monitor and evaluate the progress of the Project and prepare Project Reports as set forth in Section 2.07 of the Grant Agreement. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Name |  |  |  |  |  |  |  |  |  | Recurrent |  |  |  |  | Due Date |  |  |  |  |  |  |  | Frequency |  |  |  |  |  |
| Completion Report |  |  |  |  |  |  |  |  |  | No |  |  |  |  | November 30, 2023 |  |  |  |  |  |  |  | Once |  |  |  |  |  |
| Description |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| The Recipient shall prepare the Completion Report as set forth in Section 2.07 of the Grant Agreement. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Name |  |  |  |  |  |  |  |  |  | Recurrent |  |  |  |  | Due Date |  |  |  |  |  |  |  | Frequency |  |  |  |  |  |
| Financial Management |  |  |  |  |  |  |  |  |  | Yes |  |  |  |  | 45 days after the end of semester for IFRs; 6 months after the end of fiscal year for audits |  |  |  |  |  |  |  | Every semester for IFRs; annually for audits |  |  |  |  |  |
| Description |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| The Recipient shall ensure that, as set forth in Section 2.08 of the Grant Agreement, a financial management system is maintained; interim unaudited financial reports for the Project are prepared and furnished to the World Bank not later than forty-five (45) days after the end of each calendar semester, covering the semester; and its Financial Statements for the Project covering the period of one fiscal year of the Recipient are audited and furnished to the World Bank not later than six months after the end of such period. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Name |  |  |  |  |  |  |  |  |  | Recurrent |  |  |  |  | Due Date |  |  |  |  |  |  |  | Frequency |  |  |  |  |  |
| Procurement |  |  |  |  |  |  |  |  |  | Yes |  |  |  |  | May 31, 2023 |  |  |  |  |  |  |  | Recurrent |  |  |  |  |  |
| Description |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| All goods, non-consulting services and consulting services required for the Project and to be financed out of the proceeds of the Grant shall be procured in accordance with the requirements set forth or referred to in the “World Bank Procurement Regulations for IPF Borrowers” dated July 2016 and the provisions of the Recipient’s procurement plan for the Project, as the same may be updated from time to time in agreement with the World Bank. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Name |  |  |  |  |  |  |  |  |  | Recurrent |  |  |  |  | Due Date |  |  |  |  |  |  |  | Frequency |  |  |  |  |  |
| Eligible Expenditures |  |  |  |  |  |  |  |  |  | Yes |  |  |  |  | May 31, 2023 |  |  |  |  |  |  |  | Recurrent |  |  |  |  |  |
| Description of Covenant |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| The Recipient may withdraw the proceeds of the Grant as set forth in Section 3.01 of the Grant Agreement. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| . |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Conditions |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Source of Fund |  |  |  |  | Name |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Type |  |  |  |  |  |  |  |
| GEF |  |  |  |  | Countersignature of the Grant Agreement |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Withdrawal |  |  |  |  |  |  |  |
| Description of Condition |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Notwithstanding the provisions of Section 3.01 of this Agreement, no withdrawal shall be made for payments made prior to the date of countersignature of the Grant Agreement. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Team Composition |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Bank Staff |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Name |  |  |  |  | Role |  |  |  |  |  | Title |  |  |  |  |  | Specialization |  |  |  |  |  |  |  | Unit |  |  |  |
| Thu Thi Le Nguyen |  |  |  |  | Team Leader (ADM Responsible) |  |  |  |  |  | Environmental Specialist |  |  |  |  |  | Project coordination/ Environmental policy |  |  |  |  |  |  |  | GEN2B |  |  |  |
| Hoai Van Nguyen |  |  |  |  | Procurement Specialist (ADM Responsible) |  |  |  |  |  | Senior Procurement Specialist |  |  |  |  |  | Procurement |  |  |  |  |  |  |  | GGO08 |  |  |  |
| Ha Thuy Tran |  |  |  |  | Financial Management Specialist |  |  |  |  |  | Sr Financial Management Specialist |  |  |  |  |  | Financial Management |  |  |  |  |  |  |  | GGO20 |  |  |  |
| Thong Trung Le |  |  |  |  | Social Safeguards Specialist |  |  |  |  |  | Social Development Specialist |  |  |  |  |  | Social |  |  |  |  |  |  |  | GSU02 |  |  |  |
| Khang Van Pham |  |  |  |  | Environmental Safeguards Specialist |  |  |  |  |  | Consultant |  |  |  |  |  | Environmental Safeguards |  |  |  |  |  |  |  | GEN2B |  |  |  |
| Aristeidis I. Panou |  |  |  |  | Counsel |  |  |  |  |  | Counsel |  |  |  |  |  | Legal |  |  |  |  |  |  |  | LEGES |  |  |  |
| Keiko Ashida Tao |  |  |  |  | Team Member |  |  |  |  |  | Environmental Specialist |  |  |  |  |  | Natural Resource Management |  |  |  |  |  |  |  | GEN04 |  |  |  |
| Keith Symington |  |  |  |  | Team Member |  |  |  |  |  | Consultant |  |  |  |  |  | Biodiversity |  |  |  |  |  |  |  | GEN04 |  |  |  |
| Ngan Hong Nguyen |  |  |  |  | Team Member |  |  |  |  |  | Communications Officer |  |  |  |  |  | Communication |  |  |  |  |  |  |  | EAPEC |  |  |  |
| Dung Thuy Vu |  |  |  |  | Team Member |  |  |  |  |  | Team Assistant |  |  |  |  |  | Team Assistant |  |  |  |  |  |  |  | EACVF |  |  |  |
| Claudia Sobrevila |  |  |  |  | Team Member |  |  |  |  |  | Senior Environmental Specialist |  |  |  |  |  | Biodiversity |  |  |  |  |  |  |  | GEN04 |  |  |  |
| Elisson M. Wright |  |  |  |  | Team Member |  |  |  |  |  | Consultant |  |  |  |  |  | Wildlife Trafficking |  |  |  |  |  |  |  | GEN01 |  |  |  |
| Stephen Ling |  |  |  |  | Team Member |  |  |  |  |  | Lead Specialist |  |  |  |  |  | Biodiversity |  |  |  |  |  |  |  | GEN2B |  |  |  |
| Diji Chandrasekharan Behr |  |  |  |  | Team Member |  |  |  |  |  | Sr Natural Resources Econ. |  |  |  |  |  | Environmental Economics |  |  |  |  |  |  |  | GEN2B |  |  |  |
| Thu Ha Le |  |  |  |  | Counsel |  |  |  |  |  | Associate Counsel |  |  |  |  |  | Legal |  |  |  |  |  |  |  | LEGES |  |  |  |
| Douglas J. Graham |  |  |  |  | Peer Reviewer |  |  |  |  |  | Senior Environmental Specialist |  |  |  |  |  | Wildlife protection |  |  |  |  |  |  |  | GEN07 |  |  |  |
| George Henry Stirrett |  |  |  |  | Peer Reviewer |  |  |  |  |  | Environmental Specialist |  |  |  |  |  | Wildlife protection |  |  |  |  |  |  |  | GEN2A |  |  |  |
| Nigel Ross Hughes |  |  |  |  | Peer Reviewer |  |  |  |  |  | Sr Natural Resources Mgmt. Spec. |  |  |  |  |  | Wildlife protection |  |  |  |  |  |  |  | GEN01 |  |  |  |
| Extended Team |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Name |  |  |  |  | Title |  |  |  |  |  |  |  | Office Phone |  |  |  |  |  |  |  | Location |  |  |  |  |  |  |  |
| . |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Locations |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Country |  | First Administrative Division |  |  |  |  | Location |  |  |  |  |  |  | Planned |  |  | Actual |  |  |  | Comments |  |  |  |  |  |  |  |
| Vietnam |  |  |  |  |  |  |  |  |  |  |  |  |  | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| . |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

STRATEGIC CONTEXT

Country Context

- Vietnam is a lower middle income country with a gross national income (GNI) per capita of $1,980 (current US$) and a population of 94.4 million (2016). The country has achieved remarkable economic growth over the last 25 years, with the average gross domestic product (GDP) growth at 6.8 percent. Overall poverty rates have dropped markedly during this period, from 58 percent in 1993 to 12 percent in 2013. Vietnam aspires to modernity, industrialization, and a higher quality of life. Vietnam 2035: Toward Prosperity, Creativity, Equity, and Democracy, a joint initiative of the Government of Vietnam and the World Bank identifies that these aspirations stand on three pillars: balancing economic prosperity with environmental sustainability, promoting equity and social inclusion, and bolstering the state’s capacity and accountability.

- The rapid growth of Vietnam often overlooks the critical role played by the country’s biodiversity and natural assets in supporting economic development. Vietnam ranks 16th worldwide in terms of animal and plant species richness, endowed with a wide range of ecosystems including moist forests, dry forests, coral reefs, mangroves, freshwater lakes and lagoons. Its natural resources and ecosystems provide various kinds of benefits (i.e., ecosystem products and services, and non-material benefits) which are critical for many economic sectors such as agriculture, forestry, and fisheries (22 percent of GDP combined) and tourism (13.9 percent). Accounting for the environmental footprint of Vietnam’s rapid development would require adjusting gross national savings as a percentage of GDP downward from 35.5 percent to 15.2 percent, if depletion of natural assets were fully taken into account. The country’s growth to achieve those aspirations will be sustained only if it balances with environmental sustainability.

- The rural population, particularly the poor, are severely affected by a decline in the natural capital. Dependency of the rural poor on natural resources makes them more vulnerable to a decline in natural assets and environmental services than the urban poor. In general, natural resources and biodiversity accounts for over a third of the wealth of the poor, providing them with food, medicines, housing materials, and opportunities for income such as small-scale farms, livestock, and tourism. Biodiversity and beautiful terrestrial, coastal and island landscapes also underpin much of Vietnam’s rapidly expanding tourism industry in the rural areas. In total, approximately 25 million people in Vietnam derive 20-50 percent of their income from biodiversity. In addition to economic values, many plants and animals are considered culturally sacred and are objects of worship. Moreover, natural assets provide a wide range of critically important environmental services for the rural population. The terrestrial and coastal vegetation helps to regulate the local climate through surface energy fluxes, transpiration, and carbon storage. The key biodiversity areas (KBAs) contain more than one fifth (0.37 Gt) of the country’s total forest carbon stocks. Vegetation also filters air and water, prevents land degradation, and mitigates the effects of natural disasters such as landslides, floods, and typhoons. Mangrove forests along the coast act as “green shields”, reducing the strength of sea wave by 20-70 percent and providing natural defense to the coastal communities. Also, it has been estimated that mangroves save billions of Dongs in annual maintenance and repair costs of dykes.

- Recognizing these environmental and social impacts, Vietnam’s Socio-Economic Development Plan for 2016-2020 (SEDP) emphasizes the need to ensure environmental sustainability as an essential component for strong and sustainable economic growth. Such a sustainable, inclusive, and resilient growth path calls for strong policies and institutions to coordinate actions and investments that internalize environmental and climate costs, and more accessible data and information for decision making and monitoring progress. The Government of Vietnam (GoV) has established the protection of biodiversity and natural resources a priority task for the 2016-2020 period. The Ministry of Environment and Natural Resources (MONRE) and the Ministry of Agriculture and Rural Development (MARD) are two key agencies responsible to carry out this task.

Sectoral and Institutional Context

- It is widely recognized that the illegal exploitation, trade and consumption of wildlife has increased significantly in Vietnam as well as at the global level, resulting in dramatic declines in wildlife populations and near extinction of some species. Although the value of illegal trade remains uncertain, the global illegal wildlife trade is estimated to be worth between US$5-20 billion annually. Vietnam has been identified by Convention on International Trade in Endangered Species of Wild Fauna and Flora (CITES) as one of the countries of “primary concern” in the control of illegal trade and consumption of ivory as well as rhino horn. Vietnam is not only a destination of trade chains of wildlife sourced from other countries, but also considered a transit point of such trade chains. Between 2010 and 2014, 3,823 cases of wildlife crime were apprehended, involving more than 58,869 individuals. In 2010, the Forest Protection Department (FPD) confiscated over 34 tons of wildlife products from illegal traders, representing nearly 13,000 individual wild animals. Wildlife trade and consumption have led to widespread depletion of species from most forest areas in Vietnam, giving rise to the phenomenon of “empty forests” in which wildlife density is very low. Despite conservation efforts, Javan rhinos went extinct in Vietnam after the last individual was poached for its horn and found dead in Cat Tien National Park in 2010. In marine ecosystems, species including marine turtles, giant clams, and seahorses have also been seriously depleted largely by wildlife trade.

- Economic growth has also contributed to increased demand for luxury goods including highly-valued wildlife products used for ornaments, traditional medicine, and foods served in specialty restaurants. A survey on “Knowledge, Attitudes and Behavior on the Use of Wildlife Products in Hanoi” in 2014 shows that 25 percent of the respondents have used food and medicines from wild animals, and 10 percent have used ornaments derived from wildlife. The species most valued for such wildlife products include tiger, bear, pangolin, freshwater turtles, snakes, and monitor lizards that are hunted or farmed in Vietnam or sourced from other Asian countries, as well as rhino and other ungulate species for its horns that are sourced from Africa. There is increasing evidence that civil servants are a key consumer group of wildlife products in Vietnam, and they tend to have influential power over other groups in the society such as community leaders and business owners. There have been many communications and awareness raising efforts in recent years by various entities including MONRE, development partners, and international and local NGOs regarding the trade and use of wildlife products such as rhino horn and bear bile. These campaigns mainly targeted general consumers and the private sector without specific focus on civil servants as a target group.

- In response to these trends, the GoV has strengthened the policy and legal framework and prioritized actions to address wildlife protection in recent years. The Law on Biodiversity No. 20/2008/QH12 adopted on November 13, 2008 is the legislative framework for biodiversity protection in Vietnam and governs all biodiversity-related issues (i.e., ecosystems, species and genetic resources, as well as protected areas). In 2013, the GoV issued the National Biodiversity Strategy and Action Plan which prioritizes the protection of endangered species in support of the Law on Biodiversity, specifically focusing on management of endangered species and conservation measures. In the same year, the GoV adopted Decree 160/2013/ND-CP to stipulate the criteria for identification and management of endangered, rare, and precious species prioritized for protection and list those species. In 2015, the Penal Code was amended to increase the punishment to offences against regulations on management and protection of endangered animals to up to 15 years of imprisonment and include stricter criminal penalties to be applied for poaching and illegal wildlife trafficking. Moreover, Vietnam’s leadership sent a strong signal of their commitment to protect wildlife by hosting the Hanoi Conference on Illegal Wildlife Trade and burning confiscated ivory and rhino horns in November 2016. In the same year, the Directive No. 28/ CT-TTg of the Prime Minister was issued to mandate key ministries and agencies to carry out urgent solutions to prevent and fight against the illegal management and trade of wild animals. In total, 8 government decrees, 8 decisions, 12 ministerial circulars, and 5 major laws have been introduced or revised to protect wildlife since 2004.

- However, overlaps and inconsistencies among various laws and regulations have created serious implications to the protection of threatened species, particularly to the application of the Law on Biodiversity. Overlapping mandates and regulatory regimes exist particularly between MONRE and MARD. The former is charged with biodiversity conservation, wildlife management, and the conservation of endangered species prioritized for conservation and sustainable use of biodiversity resources. Decree No. 36/2017/ND-CP mandates MONRE with inventory, monitoring and evaluation related to biodiversity, and hence updating of the threatened species list (IUCN Red list). However, MARD is the responsible national agency for CITES in Vietnam. And Decree No. 28/2017/ND-CP charges MARD with inventory and monitoring in forest areas management of “lists of valuable, rare and endangered forestry plant and animal gene that could be exploited and used”. Protected areas within Vietnam’s terrestrial, inland water and marine ecosystems falls under the remit of MARD, while protected areas within wetland ecosystems are the responsibility of MONRE. Consequently, different management regimes are applicable to the same endangered species.

- In addition to overlapping roles and responsibilities, the effectiveness of enforcement operations is affected by insufficient coordination and information sharing within and between agencies. Besides MONRE and MARD, key enforcement agencies engaging in wildlife protection and trade at the central level in Vietnam include the Environmental Police under the Ministry of Public Security (MPS), Markets Control Department under the Ministry of Trade, Department of Customs under the Ministry of Finance (MOF), Ministry of Justice (MOJ), Supreme People’s Procuracy, and Supreme People’s Court. The Environmental Police is a statutory investigating body responsible for wildlife and forest crime and the lead agency tackling illegal domestic wildlife trade. The Department of Customs is responsible for, among others, identifying and seizing contraband smuggled into and out of Vietnam, including illicit wildlife and timber trafficking. This work is carried out in collaboration with the Border Guards in particular. The MOJ implements legal procedures at administrative levels, including legal dissemination and education. Importantly, MOJ oversees the revisions of the Penal Code as it is applied in wildlife species, including revising punitive measures. The Supreme People’s Procuracy is mandated with the prosecution of economic crimes including environmental crimes, while the Supreme People’s Court provides guidance to lower courts on the implementation of particular laws. At the provincial level, the Biodiversity Conservation Units have been established recently within the Departments of Natural Resources and Environment (DONREs) to strengthen wildlife conservation on the ground. Also, management of protected areas has become increasingly decentralized, with the responsibility for individual protected areas mandated to their respective Protected Area Management Board (PAMB). The PAMBs are administered by provincial People’s Committees and technically supported by MONRE and MARD. The Forest Protection Department (FPD) under MARD is the lead agency for forest protection and management, with a specific mandate on monitoring wildlife poaching and enforcing relevant laws. Functions are delivered locally by the approximately 13,000 FPD officers nationwide. The Departments of Agriculture and Rural Development (DARDs) are responsible for supervising the operation of the provincial FPD, and at a district level this role is undertaken by the District People’s Committee. These complex arrangements result in a lack of cohesion between the various systems, tools, and protocols applied in enforcing, investigating, and prosecuting wildlife protection and anti-crime measures. More collaboration among the enforcement agencies is necessary specifically in sharing information and updating regularly to each other on the status of enforcement and conservation operations and its effectiveness, and jointly reviewing and assessing individual cases.

- Also, there remain major challenges in the processing of cases, prosecution of documented offenses, and levying of appropriate penalties due to lack of adequate knowledge and clear guidance on the application of the key legislation related to the protection of threatened species. Across agencies, enforcement officers often lack knowledge and experience to apply the Biodiversity Law and Decree 160 on endangered species prioritized for protection consistently in field operations. Consequently, they tend to apply a more lenient, discretionary punishment regime such as Decree 32 instead. Also, enforcement officers often have limited knowledge of species under protection and experience in frontline investigation techniques. The lack of adequate knowledge and experience, hence proper collection and documentation of evidence, seriously impedes effective prosecution of individual cases. Additionally, due to deficiencies in the criminal code, punishments have mostly been administrative sanctions only and, consequently insufficient to provide incentives to reduce wildlife crime. The amendment of the Penal Code in 2017 with stricter penalties will change this over time, only if adequate training and support are provided to enforcement officers and judicial authorities.

- Clear technical and regulatory guidance is much needed not only for conservation and enforcement authorities, but also for the economic sector. For example, “wildlife conservation facilities” refer to a specific type of operation regulated under the Law on Biodiversity and aimed at the ex-situ protection of prioritized endangered species. These facilities are intended for conservation purposes only, including rescue, conservation breeding, re-introduction, relocation, pure genetic preservation of the endangered species. However, some facilities take advantage of legal loopholes and overlapping legislation and breed threatened species such as bears for commercial purposes. Operators of conservation facilities are not sufficiently regulated by a formalized process such as licensing in which they need to demonstrate their knowledge and capacity to adequately manage and conserve threatened species. This issue with wildlife conservation facilities is likely to exacerbate the illegal trade and consumption of threatened species in Vietnam. Another issue is that there have been no clear guidelines to integrate the protection of wildlife into the major economic sector such as tourism. Threatened species are often used to attract tourists. The facilities where those animals are kept and their health conditions are not always satisfactory. Tourists also consume or purchase illegal wildlife products as exotic experience or souvenir. Furthermore, wildlife crime has not been adequately addressed in the National Crime Prevention Strategy. Prevention of such crimes is as critical as law enforcement in order to reduce poaching, illicit wildlife trade and consumption of wildlife products.

- Recognizing the importance of strong partnerships across sectors and national borders in addressing wildlife trade issues, the GoV has joined international, regional and national efforts to strengthen collaboration on enforcement activities, information and knowledge sharing, and capacity building. The GoV organized the Biodiversity and Ecosystem Conservation Forum 2015 and 2016 to bring stakeholders together to complement each other and increase synergies. These evolving partnerships have been useful to deepen the dialogue on policy and technical aspects and joint actions of national agencies and development partners, the private sector, NGOs, and other stakeholders. Vietnam has made commitment to the international communities through its engagement in international and regional efforts including the Convention on Biological Diversity, CITES, London Declaration, Kasane Declaration on Wildlife and Wild Plant Trade, and Declaration on the 22nd Asia-Pacific Economic Cooperation (APEC) Economic Leaders’ Meeting including a provision for continued efforts against wildlife trafficking. Vietnam is a member of the ASEAN Wildlife Enforcement Network (ASEAN-WEN)—a regional inter-agency and inter-governmental initiative established to address illegal cross-border wildlife trade, share knowledge and facilitate the exchange of regional best practices. Vietnam’s engagement in the ASEAN-WEN is supported the country’s participation in the Asia’s Regional Response to Endangered Species Trafficking Program (ARREST) as a local partner, and development of the Vietnam Wildlife Enforcement Network (Vietnam-WEN) as a national inter-agency task force. In addition, Vietnam also established the National Biodiversity Steering Committee on implementation of the National Biodiversity Strategy and Action Plan (NBSAP), an inter-agency committee tasked with oversight of the biodiversity agenda and providing instructions and direction among relevant ministries on specific issues such as wildlife protection. The GoV signed a Memorandum of Understanding (MOU) with Laos on forest protection that encompasses both illegal logging and illicit products made from wild animals. The GoV also hosted the post-London High Level Summit in Hanoi in 2016 where more than 30 countries took stock of actions to address illegal wildlife trafficking.

Higher Level Objectives to which the Project Contributes

- By strengthening national capacity to protect biodiversity and ecosystems in Vietnam, the proposed Project contributes to achieving the World Bank’s twin goals to eliminate extreme poverty and boost shared prosperity in a sustainable manner. The Project also aligns with the World Bank Group Country Partnership Framework (CPF) for Vietnam for FY2018-2022 (Report No. 111771-VN). The latter supports the implementation of Vietnam’s Socio-Economic Development Strategy (SEDS) for 2011–2020. The proposed Project would address the Focus Area 3 of the CPF on ensuring environmental sustainability and resilience and would contribute to improve natural resources management through conservation of forests and biodiversity. The protection of biodiversity especially the ecosystems and threatened species is a critical task identified in the National Climate Change Strategy of Vietnam issued in 2011 and the National Determined Contributions (NDC) in 2016. The reduction of consumer demand of wildlife products aligns with greening life style and sustainable consumption as a key strategic task that contribute to the reduction of environmental footprint to direct the country toward a low carbon development pathway as stipulated in the National Green Growth Strategy for period 2011–2020.

- The Project has been developed under the “Global Partnership on Wildlife Conservation and Crime Prevention for Sustainable Development (GWP)”, a multi-agency program funded by the Global Environment Facility (GEF) and led by the World Bank, which aims at promoting wildlife conservation, wildlife crime prevention, and sustainable development to reduce impacts to known threatened species from poaching and illegal trade. The proposed Project is one of the 19 national projects under the GWP and will be coordinated systematically under the GWP through its coordination grant. The Project is consistent with the objectives of the GEF-6 Biodiversity Strategy and Programming Directions and will make a direct contribution to BD 2 - Program 3 on “Reducing Poaching and Illegal Trafficking of Threatened Species” by mainstreaming wildlife and biodiversity concerns across a wide range of government agencies and sectors, including agencies not traditionally concerned with wildlife and biodiversity issues. It will also benefit from lessons and insights of the broader global program. This Project will also contribute to the achievements of the CBD Aichi 2020 Biodiversity targets, particularly target 12: “By 2020 the extinction of known threatened species has been prevented and their conservation status, particularly of those most in decline, has been improved and sustained”.

- The proposed Project complements the associated parallel co-financing Saving Species Project (2016-2021) supported by the U.S. Agency for International Development (USAID) which will direct a significant portion of its $9.9 million budget to capacity building of law enforcement officers and the judiciary authorities, institutionalizing training in wildlife trafficking, and strengthening trans-boundary enforcement efforts through ASEAN-WEN. The proposed Project, on the other hand, will strategically focus on the issues with the legal and regulatory framework related to the application of the Law on Biodiversity, the National Crime Prevention Strategy, intra- and inter-agency coordination and information sharing to improve enforcement operations, international collaboration through the existing partnership forum and memorandums of understanding with key partners, and awareness raising regarding consumption of wildlife products for targeted audience at the central and provincial levels, with spillover effects on other groups such as the private sector and youth.

PROJECT DEVELOPMENT OBJECTIVE

Project Development Objective

- The Project Development Objective is to strengthen the legal and regulatory framework, and the related implementation capacity for the protection of threatened wildlife.

Project Beneficiaries

- Project direct beneficiaries are the Government of Vietnam and its various government agencies involved in wildlife protection. MONRE as well as MPS, MARD, MOJ, MOF Supreme People’s Procuracy, Supreme People’s Court, and the Ministry of Trade will benefit from clearer regulatory protocols and enhanced capacity for relevant officials and staff to perform their tasks related to wildlife protection.  These beneficiaries also extend to staff at the provincial departmental levels (e.g. PPCs, DONRE, DARD), involved in management and implementation of wildlife protection activities. Awareness raising under the Project will benefit mainly civil servants with spill-over effects on other groups of the society such as community leaders and business owners. The Project’ indirect beneficiaries include local people in or near the natural habitat who are typically kept poor by reduced environmental services and illegal activities that hinder fair development and progress. Ecosystem-level benefits will be achieved through enhancing the potential of forests to support greater numbers of prey species and thus restore functional forest ecosystems with top-order carnivores. It will also ensure species and their habitats are better managed and more resilient, thus creating the conditions for communities to continue to use nature as a social safety net, particularly as climate change uncertainty exacerbates already tenuous lives. By reducing wildlife crime locally, this Project will reduce insecurity in the society,  and create the infrastructure for effective law implementation, providing additional socio-economic benefits for communities. Given the growing reputational risk for Vietnam related to wildlife crime, this Project will provide important benefits for Vietnam’s international relations and also for international trade, tourism and the economy as a whole.

PDO Level Results Indicators

- The PDO level results indicators are set as follows:

  - Draft amendments to the laws and regulations on threatened wildlife protection submitted for approval to the competent authorities;

  - Enforcement and conservation officers with increased competency in the application of the laws and regulations on wildlife protection;

  - Enforcement and conservation agencies that deploy the Spatial Monitoring and Reporting Tool (SMART);

  - Share of government agencies participating in the Biodiversity Steering Committee that agree on joint work plans on wildlife protection; and

  - Share of central and local government staff reached by awareness raising campaigns.

PROJECT DESCRIPTION

Project Components

- The Project consists of four components:

Component 1: Strengthening the legal and regulatory framework.  This component provides support for: (a) drafting amendments to the articles of the Law on Biodiversity, Decree 160, and other key regulations relevant to the protection of prioritized endangered species; (b) development of a legal framework for the improved management and monitoring of ex-situ wildlife conservation facilities; (c) development and submission of recommendations on the implementation of the Law on Biodiversity in the tourism sector to integrate the protection of threatened species into tourism activities; and (d) incorporation of wildlife crime issues in the National Crime Prevention Strategy. This component aims to harmonize legal and regulatory instruments relevant to the protection of threatened wildlife in Vietnam, especially making clear the roles and responsibilities of the key agencies such as MONRE, MARD, DONRE, and DARD. Component 1 is based on the finding and recommendations from past assessments, including the Wildlife Consumption in Vietnam Project (WLC), the International Consortium of Combating Wildlife Crime (ICCWC), and the Governance and Inclusive Growth (GIG) project, all of which recommend to reduce overlaps and improve the legal environment for the protection of threatened species. This component will be led by MONRE and coordinated with MARD, MOJ, Ministry of Tourism (MOT), MPS and the Environmental Police.

Component 2: Enhancing capacity to effectively implement and enforce policies and regulations related to wildlife protection. This component will support (a) strengthening of the capacity in the application of the Biodiversity Law and Decree 160 for the field staff of key law enforcement agencies; (b) development of an information sharing mechanism on the protection and conservation of the prioritized endangered species; (c) development of conservation program for selected critically endangered species; and (d) institutional strengthening of the Biodiversity Steering Committee to enhance coordination of the enforcement and conservation operations among various agencies. MONRE will lead the component activities in coordination with  MPS, MARD, DONRE, PPCs, and MOJ. Specifically, the Project will support a training needs assessment and develop training programs to complement capacity building in law enforcement under the Saving Species Project and the Regional Wildlife Project, both supported by the USAID.

Component 3: Promoting knowledge sharing and awareness raising. This component aims at promoting knowledge sharing and awareness raising to contribute to reducing demand for wildlife consumption. The activities include (a) an expansion and facilitation of the Endangered Wildlife Partnership Forum; (b) knowledge exchange on policy development, conservation and enforcement capacity, and outreach related to the protection and management of threatened species; and (c) development and implementation of an awareness raising strategy on the consumption of threatened wildlife products for targeted audience at the central and provincial levels. MONRE and Central Party Committee on Propaganda and Education (CCPE) will lead this component, in collaboration with media, communication agencies and NGOs.

Component 4: Project Management and Monitoring and Evaluation (M&E). This component will provide support for MONRE in project management and implementation of the Project, including planning, coordination, technical inputs, financial management, procurement, environmental and social safeguards compliance, monitoring and evaluation, and reporting. A Project Management Unit (PMU) will be established within MONRE to be responsible for day-to-day project management. MONRE through the PMU will develop a project operational manual (POM) in form and substance acceptable to the Bank, setting forth guidelines and procedures for the implementation of the Project.

Project Cost and Financing

| Project Components | Project cost (US$ million) | Grant Financing | Counterpart fund |
| --- | --- | --- | --- |
| 1. Strengthening legal and regulatory framework 2. Enhancing capacity to effectively implement and enforce policies and regulation related wildlife protection 3. Promoting knowledge sharing and awareness raising 4. Project Management and Monitoring and Evaluation | 1.00 1.20 0.80 0.30 | 0.85 1.15 0.72 0.28 | 0.15 0.05 0.08 0.02 |
| Total | 3.30 | 3.00 | 0.30 |

Lessons Learned and Reflected in the Project Design

- The Project has been designed with consideration of past projects addressing illegal wildlife consumption and demand reduction at the national level, particularly through the Wildlife Consumption in Vietnam: Reforming Policies and Practices to Strengthen Biodiversity Conservation Project (WLC) (a GEF medium-sized project, June 2012‒May 2015). For example, combatting illegal wildlife trade requires political commitment and ownership of the management of the issue by the government. Mobilizing a range of partners in various relevant sectors to drive change within their areas, under the overall coordination of a specialized government agency, has proved to be an effective working structure for the wildlife consumption issue. The Biodiversity Conservation Agency (BCA) under MONRE was the lead agency under the WLC project and will be the implementing agency under the proposed Project. Key conservation and enforcement agencies and the private sector will be mobilized and involved in various activities proposed under the Project.

- Another lesson from the WLC project states that a follow-up project could consider strategic points of intervention for reducing the trade and consumption, key stakeholders to be targeted, and how to design interventions that address motivations and attitudes as a crucial aspect of the ‘knowledge attitudes practice’ theory of change. In addition, assessments carried out under the WLC project have shown that awareness campaign and communications on illegal consumption of wildlife products are effective to change the audiences’ behavior. Accordingly, the proposed Project will include civil servants among target audience as they have strong influential power with spill-over effects on other target groups in the society (the private sector, youth, community, etc.).

- Similarly, sustainability of actions to combat wildlife trade requires long-term commitment, support and resources of the government and coordinated efforts, likely best achieved through strong linkages with other established programs. Thus, the proposed Project will coordinate with other national projects under the GWP. This will facilitate information and knowledge sharing with other countries in Africa as well as Asia including Thailand, Indonesia and the Philippines. The Project activities are also designed to ensure synergy with the initiatives of the GoV, other development partners, NGOs including the ASIA-WEN, the Saving Species Project, etc.

- The WLC project demonstrated that a key determinant for success is close collaboration and partnership building across the various agencies and stakeholders, and confirmed MONRE’s suitability as a convening agency in implementing such an approach. Under the WLC, a Wildlife Partnership Forum led by the GoV was piloted as a networking platform for collaboration between government agencies and multi-sectoral stakeholders. As such, communication activities have directly reached audiences with the active support and cooperation from forum members such as the Central Youth Union, Central Committee of Propaganda and Education (CCPE), community-based organizations, local and international NGOs, and other relevant government ministries such as Ministry of Health, Ministry of Public Security, Ministry of Industry and Commerce. However, given the size of the WLC project, campaigns were only conducted in limited areas (e.g., new public health guidance and policies to raise awareness on wildlife consumption) and scale. The proposed Project will support the development and implementation of strategic work plans of the Forum to expand partnerships and collaboration in different sectors at the national and regional levels.

- Furthermore, the project activities, particularly for Components 1 and 2, have been developed with specific reference to the recommendations of the United Nations Office for Drugs and Crime ICCWC Toolkit released in 2015. These recommendations include: (i) improved guidance (and clearer definitions) in the Penal Code on levels and values associated with wildlife crimes (including violations of the Law on Biodiversity), thus a greater proportion of cases will be presented to the Procuracy for trial; (ii) better cohesion in targeting vulnerable species, trafficking routes and apprehending offenders; (iii) enhanced knowledge and awareness of wildlife crime issues and challenges among the Judiciary, Procuracy and other institutions involved in investigating wildlife cases, and (iv) improved competencies of enforcement agencies in crime scene management through directed training.

IMPLEMENTATION

    - Institutional and Implementation Arrangements

- Implementation arrangements of the proposed Project will build on the robust structure established under the WLC project.

- The Ministry of Natural Resources and Environment (MONRE) will be the implementing agency on behalf of the Recipient. MONRE will establish the Project Management Unit (PMU) and will be responsible for the overall implementation and management of the Project, including procurement, financial management, safeguards management, monitoring, and overall administration. MONRE will be the lead agency for the implementation of Component 1. MONRE will also lead the implementation of Component 2 in collaboration with MARD, MPS, DONRE, PPCs, and MOJ. MONRE and the Central Party Committee on Propaganda and Education (CCPE) will lead the implementation of Component 3.

- A Project Steering Committee (PSC) will be established to make decisions and provide guidance for the implementation of project activities, including approval of the annual work plans and budget revisions. The PSC will consist of high-ranking officials representing MONRE, MARD, MPS, MOF (Department of Customs), Ministry of Justice, CCPE and other relevant agencies. It is tentatively planned that MONRE’s Vice Minister will chair the PCS with the Deputy Director General of Vietnam Environment Administration (VEA) under MONRE as the vice chairperson. The PSC will meet regularly or on an ad-hoc basis as necessary.

- A Project Management Unit (PMU) will be established within VEA of MONRE. The PMU will comprise Project Director, Project Coordinator, Financial Management Officer, Procurement Officer, and Project Assistant. Project director will have overall responsibility of project management and daily operation of the project as well as coordination with all relevant stakeholders, ministries and agencies. The PMU will develop annual work plans, carry out activities as planned, coordinate with the lead and collaborating agencies as well as beneficiary agencies, supervise consultants and monitor activities, ensure the quality of deliverables, and prepare reports as described in the POM. The PMU will ensure that the Project is implemented in accordance with the project documents such as the Project Paper, Grant Agreement, Disbursement Letter, POM, Integrated Safeguards Data Sheet (ISDS), FM handbook, and procurement framework.

- Roles, functions, and responsibilities of the PMU and collaborating agencies (MONRE, MARD, MPS, MOJ, MOT, DONRE, DARD, PPCs, and CCPE) under the proposed Project will be detailed in the POM. Component 1 will be led by MONRE and implemented closely with MARD, MOJ, MOT, MPS and the Environmental Police. Component 2 will be led by MONRE in collaboration with the Ministry of Public Security (MPS), MARD, DONRE, PPCs, and MOJ. Component 3 will be led by MONRE and CCPE. Component 4 will be managed by MONRE, The Project will be implemented in accordance with Decree No 16 of the Government on management and use of official development assistance (ODA) and concessional loans of donors.

    - Coordination with other development partners’ support

- Coordination among various donors is critical as there are many donor-funded projects on wildlife protection and illegal trade in Vietnam. The main donors include: USAID, German Society for International Cooperation (GIZ), and the Department for International Development of the U.K. (DFID). The design and approach of the Project complement these programs, especially the USAID Saving Species project, Governance and Inclusive Growth (GIG) project, and their regional support on wildlife trade, which apply nearly US$20 million combined to wildlife protection in Vietnam. These projects are similarly framed around the three main pillars of legal harmonization, law enforcement, and demand reduction, with a strong emphasis on law enforcement. At an overarching level, the involvement of MARD as the main government partner in implementing and coordinating the Project activities will be critical for the Project to meet its objective, given the important role of MARD in the protection of wildlife (e.g., the lead agency for the national Wildlife Enforcement Network). Bilateral meetings and consultations were held with MARD and USAID specifically to discuss synergies between the on-going national and regional projects mentioned earlier and the proposed Project. Several key activities in which close coordination with MARD/USAID is expected, including the application of SMART tools, provision of training, and expansion and facilitation of the Endangered Wildlife Partnership Forum.

    - Results Monitoring and Evaluation

- Project monitoring and evaluation (M&E) and reporting are an integral part of the project design. The M&E system will be implemented and managed by MONRE through the PMU which will be responsible for gathering and analysis of data and information and preparation of regular progress reports. The PMU will engage with an M&E specialist who will support to carry out M&E activities during project implementation. Methodologies and result indicators are provided in the Results Framework and Monitoring (Annex 1) and included in the POM. Also, the Project will contribute to the GWP Core Indicators, specifically measuring the number of law enforcement and judicial activities and the number of people supported at program sites. The GWP Tracking Tool has been prepared and will be used to monitor the progress. The periodical progress reports contain implementation progress of the planned activities, data on the result indictors, and an assessment of risks and mitigation measures, which will be reviewed by the PSC and the Bank. MONRE will jointly conduct implementation support missions with the Bank to assess implementation progress on the ground. In-depth assessments will be conducted jointly by MONRE, the Bank, and other key stakeholders at mid-term to see if there is a need to adjust the Project, and at the end of the project for a terminal evaluation. These assessments will be compiled into a mid-term review report and a terminal evaluation report to be reviewed by the PSC and the Bank.

    - Sustainability

- Environmental sustainability is as an essential component for strong and sustainable economic growth recognized under the Vietnam’s Socio-Economic Development Plan for 2016-2020 (SEDP). In this context, the GoV is committed to addressing wildlife crime issues and has established biodiversity and natural resources protection as a priority task for the 2016-2020 period. MONRE and other key agencies such as MARD are mandated by specific legislation to address the protection of biodiversity and natural resources. Also, various donors and NGOs have been keen to provide support for reducing wildlife crimes in Vietnam and are likely to continue to do so.

- The proposed project activities were selected for the potential of making impacts on the protection and conservation of threatened species in Vietnam in a short- to medium-term. Once the project activities are proven to have impacts, it will have more potential for the Government to continue or expand the activities after the Project. A strengthened and improved legal and policy framework will bring long-term benefits and sustainability for the environment and society that extend far beyond the completion of the project. In addition, the project's multi-stakeholder approach, involving the participation of many government agencies in the implementation of relevant project components, contributes to the mainstreaming of conservation and biodiversity issues across many sectors and agencies. Mainstreaming these issues, increasing awareness, and strengthening policies, will make significant contributions to the sustainability of project outcomes and changing behavior for wildlife protection. The project design recognizes the importance of the public as well as civil servants to participate in biodiversity and wildlife protection is critical for long-term sustainability of controlling illegal trade and reducing demand for wildlife consumption. It has therefore incorporated a targeted intervention to raise awareness and education of civil servants, which has potential of greater spill-over impacts on the public at large.

KEY RISKS AND MITIGATION MEASURES

- The overall risk to PDO achievement is assessed as moderate. The key risks and issues that could affect achievement of the proposed project’s development objectives are described below.

- Political and governance risks are assessed as substantial. The GoV has demonstrated their commitment to the protection of threatened species, including combating against illegal wildlife trade. While there is a strong commitment at the highest level in the GoV, there is a risk that insufficient attention and commitment are secured at the provincial, district, and lower levels. This risk will be mitigated by implementing measures catered for civil servants to raise awareness on the consumption of threatened wildlife products. The strategy is to consider incentives for civil servants to stop wildlife consumption and become role models to the public, and education about potential punitive consequences of such crimes.

- Institutional capacity for implementation and sustainability risks is substantial. There is a risk that uneven implementation of participating agencies may delay the achievement of project development objectives. For the Project to be successful, at the strategic leadership level, a multi-agency Project Steering Committee is to provide guidance and overall coordination of different participating agencies. At the implementation level, MONRE will play a leadership role and facilitate the collaboration of project participating agencies, which was done well under the WLC Project. Close collaboration within MONRE’s different departments to facilitate project implementation is important to ensure the project activities are implemented without delay. In this effort, MONRE is holding a joint review with the Bank to address systematic issues within MONRE for ways to accelerate project implementation.

- Some activities such as support for incorporating wildlife crimes in the National Crime Prevention Strategy, training on subjects related to the application of the Penal Code, anti-poaching monitoring technology may qualify as support to criminal justice as defined in the Staff Guidance Note on World Bank Support for Criminal Justice Activities (the Guidance Note) issued in February 2012. Therefore, a risk assessment has been prepared in accordance with the Guidance Note and is available in the project files. In sum, it is confirmed that these interventions fall within the development purposes of the Bank and are grounded in an appropriate and objective economic rationale. Additionally, these interventions do not involve the Bank in the political affairs of Vietnam. The Project does not provide any direct support to criminal justice actions nor partisan politics. The main risks considered include: (a) being associated with abuses of authority; and (b) reputational risk from its support for the Environmental Police. The overall risk of political interference and of reputational risk is considered low, because of the small size of the Project and its support for the restricted and very specific activities. The grant agreement includes several covenants to mitigate these risks. The POM will further include detailed guidelines consistent with the provisions. Also, the Project will ensure the study will take into account international experiences and standards with support from the knowledge sharing from the Bank-led Global Wildlife Program.

Risks table

| Risk Categories | Rating |
| --- | --- |
| - Political and governance | Substantial |
| - Macroeconomic | Moderate |
| - Sector strategies and policies | Moderate |
| - Technical design of project or program | Moderate |
| - Institutional capacity for implementation and sustainability | Substantial |
| - Fiduciary | Moderate |
| - Environment and Social | Low |
| - Stakeholders | Moderate |
| Overall | Moderate |

APPRAISAL SUMMARY

Technical

- The proposed Project is one of the national projects under the GWP funded by the GEF, and consequently, its design is consistent with the technical approach of the GWP. The Project will also benefit from the GWP through its coordination grant to systematically coordinate with relevant GEF projects, exchange experiences, and ensure complementarity with other regional and global initiatives at the national level. The Project recognizes that CITES provides the international legal framework for regulating international trade in wildlife. The Project will be delivered within this legal framework and will contribute towards the full and effective implementation of relevant CITES Resolutions and Decisions on illegal trade in wildlife.

- The proposed Project follows the theory of change proposed by the GWP that prioritizes emergency short-term interventions through reducing poaching, trafficking, and demand and long-term interventions that reflect the real value of wildlife. Under the proposed Project, the former is addressed by reducing the complexity of and filling the gaps in the legal framework; providing capacity building to improve the effectiveness of conservation and law enforcement; awareness raising and education; and enhancing partnerships and collaboration across agencies, sectors, and national boundaries for sustainable management of threatened wildlife. These interventions are designed to act collectively to both increase the costs of participation in wildlife crimes, and increase equitable sharing of the benefits from protected wildlife resources under the framework of CITES and the national policy and regulatory framework. This approach is critical for creating the fundamental socio-economic conditions necessary for the long-term persistence of biodiversity, which is consistent with the objectives of the CBD. (See Annex 5)

Economic Analysis

- The Project will generate monetary and non-monetary benefits derived from the sustainable use of wildlife. As its support is mostly technical assistance, it is mostly non-quantifiable benefits, for example, in broad-based institutional strengthening and capacity development from the strengthened enabling environment and effective management, monitoring, and implementation of wildlife protection at the national and local levels (Components 1 and 2), as well as from raised awareness of civil servants with spill over impacts on the public about consumption of wildlife products (Component 3). Overall, reduction and deterrence of wildlife crimes would bring socioeconomic impact such as decreased corruption and insecurity. The legal markets would receive fair prices in the absence of increased supply from illegal trade. A decline in over-hunting of wildlife species would halt further degradation of ecosystems and natural resources. As natural resource stocks recover, communities would benefit from them in the form of food, building materials, medicines, and fuel. Their benefits would also include those from ecosystem services, including biogeochemical and nutrient cycles; energy production, natural pest control by predators in food webs, pollination by insects, bats, and birds; decomposition of biomass, wastes, and pollution; soil formation, retention, erosion prevention, and maintenance of soil fertility; and climate regulation. Additionally, the entire country would receive the non-material benefits including historical, cultural, spiritual, recreational, educational, and scientific benefits.

- In particular, the benefits from Component 1 would be further strengthening of legal and regulatory frameworks developed under the WLC project, with clear understanding of impact of the relevant decrees/regulations at both central and provincial level including Law on Biodiversity and Decree 160, concrete activities defined and assigned to various stakeholders for conservation of selected wildlife species, and improved data and information sharing on threatened species. The proposed activities under Component 2 would generate such benefits as a reduction in wildlife crime and smuggling as a result of improved interagency cooperation and coordination through NBSAP Steering Committee as a national biodiversity protection taskforce; strengthened capacity in implementation of wildlife regulations; increased awareness and control of the supply side of illegal wildlife products; and effective crime prevention and enforcement. Anticipated benefits from the proposed activities under Component 3 would be a reduction in demand for wildlife consumption, through increased understanding and awareness among target groups; and increased incentive for wildlife conservation among civil servants and citizens.

Procurement and Financial Management

- Procurement for the proposed Project shall be carried out in accordance with “The World Bank Procurement Regulations for IPF Borrowers: Procurement in Investment Project Financing” (Procurement Regulations) dated July 2016. As being required under the Procurement Regulation, a Project Procurement Strategy for Development (PPSD) and Procurement Plan have been prepared by the Recipient. PPSD helps the Recipient make decisions on fit-for-purpose procurement arrangements based on a robust analysis of their capacity, the market for the intended procurement scopes, and analysis of key risks. BCA under VEA of MONRE has become familiar with the World Bank procurement policies through past projects including the WLC project (GEF MSP, 2013-2015). Also, the “Guidelines on Preventing and Combating Fraud and Corruption in Projects Financed by IBRD Loans and IDA Credits and Grants, dated October 2006 and revised January 2011 and as of July 2016 (“Anti-Corruption Guidelines”) shall apply to the Project. More details are provided in Annex 3.

- An FM assessment was conducted during Project preparation and concluded that the FM risk is Moderate, given that VEA of MONRE, including its Chief Accountant, has accumulated experience in the implementation of a Bank project through the WLC project which completed in 2015. The FM role of VEA in MONRE is critical in monitoring fund flows and in meeting the financial reporting requirements. The risk will be mitigated through the establishment of a simple financial management system with designated staff being responsible for financial management of the grant. The Bank will also provide regular guidance to VEA staff. The review has concluded that the proposed Project and financial management arrangements will be adequate and acceptable provided that a number of FM actions will be implemented by the PMU, including (i) FM positions will be assigned and trained in specific guidelines and procedures for trust fund, procurement, financial management and disbursements; (ii) a simple Project accounting software which was already used in previous Project will be updated for the proposed Project and training is provided to the FM staff; and (iii) an FM chapter in the POM will be prepared and approved by the Bank. More details are provided in the Annex 3.

Environmental Safeguards

- The Project will provide technical assistance and capacity building to Vietnam in its efforts to protect the globally significant endangered species, including strengthening of the legal and regulatory framework for the protection of threatened species, law enforcement capacity and partnerships, and communication campaigns for awareness raising on the consumption of wildlife products. Specifically, the Project will provide training and equipment (e.g., SMART tools, GPS, computers, printers, etc.), support communications and awareness campaigns, support information management on selected endangered species (e.g., species profiles, populations and distribution, threats, protection status). It is anticipated that the Project will have positive environmental effects through these interventions. The Project will not support any civil works, and therefore the Project is envisaged not to cause any significant adverse environmental impacts.

- The Project triggers OP/BP 4.01 on Environmental Assessment given that there is a possibility that studies and technical assistance (TA) for enhancing legislation and institutions for improved protection of the threatened species may lead to the regulatory development or revision of certain provisions of existing legislation which may have safeguard implications in terms of the management of protected areas, including potential access restrictions. However, given the nature of activities and the potential environmental implications, which would be further downstream and may be outside the life of the project, the project’s environmental effects have been envisaged to be negligible. Thus, the Project is classified as Category C and environmental risk is considered low. Where the studies and TA are anticipated to involve environmental implications, an assessment of potential environmental impacts will be included in the TORs for the studies and TA. These TORs shall be reviewed and cleared by the Bank team.

Social Safeguards

- The Project will support the provision of TA to relevant Government agencies in Vietnam to enhance the protection of the globally significant endangered species. The Project will indirectly benefit local people living in or near natural habitats who have been affected negatively by reduced environmental services and illegal activities that often lead to insecurity of the area. However, there is a possibility that strengthening and amending the legal and regulatory framework to implement the Law on Biodiversity and other relevant legislation may affect the local ethnic minority (EM) people who engage in hunting, keeping, and using wildlife for their sustenance and way of life. It may also adversely affect the EM people’s participation and consultation process. During the project implementation, these issues should be carefully monitored. Therefore, the TORs for drafting amendments to the Law on Biodiversity and other key regulations will pay particular attention to these social issues and reflect the directions and principles of OP/BP 4.10 on Indigenous People. It will describe how the identified issues are addressed either through existing safeguard instruments or provisions in proposed policies and institutional set up.

- The Project will not support any activities involving involuntary resettlement. To ensure a more systematic approach that analysis of safeguard implications is well-integrated into each study and TA activity, all TORs will be reviewed and cleared by the Bank’s social safeguards specialist to ensure that the TORs reflect the directions and principles of OP/BP 4.12 on Involuntary Resettlement.

- Mainstreaming gender issues into project activities is of attention of the Project. Although both men and women deal with the wildlife trade, it is predominated by men. For example, the consumption of wildlife is highly gendered. Much of the consumption of wildlife for medicinal purposes is tied to culturally perceived masculinity and sexual prowess, along with male sociality and prestige (McElwee et al. 2012). On the other hand, women in rural areas tend to play key roles in protecting the environment and natural assets. For example, women and ethnic minorities represent around 90 percent of collectors of wild medicinal and aromatic plants in some province in northeastern Vietnam (TRAFFIC 2017). Therefore, mainstreaming gender issues into policy advice and then into policy design is to ensure that both women and men benefit from the changes these policies are intended to bring about. To this end, the Project will encourage both men and women’s participation, especially strengthen women’s roles and contribution in (i) providing advices, comments and feedbacks to the amendment of the Law on Biodiversity and other key regulations; (ii) exchanging and disseminating information and knowledge on policy development and enforcement capacity; and (iii) awareness raising and capacity building activities. Women’s Unions will be engaged to carry out information dissemination as part of outreach efforts to targeted stakeholders, especially the poor and ethnic minority women related to the protection and management of threatened species.

- MONRE will be the implementing agency which will be responsible for ensuring the Project’s compliance with the World Bank safeguards policies. MONRE has implemented the Bank-financed projects in the past and is familiar with the World Bank safeguard policies and the requirements.

World Bank Grievance Redress

- Communities and individuals who believe that they are adversely affected by a World Bank (WB) supported project may submit complaints to existing project-level grievance redress mechanisms or the WB’s Grievance Redress Service (GRS). The GRS ensures that complaints received are promptly reviewed in order to address project-related concerns. Project affected communities and individuals may submit their complaint to the WB’s independent Inspection Panel which determines whether harm occurred, or could occur, as a result of WB non-compliance with its policies and procedures. Complaints may be submitted at any time after concerns have been brought directly to the World Bank's attention, and Bank Management has been given an opportunity to respond. For information on how to submit complaints to the World Bank’s corporate Grievance Redress Service (GRS), please visit http://www.worldbank.org/GRS. For information on how to submit complaints to the World Bank Inspection Panel, please visit www.inspectionpanel.org.

| Annex 1: Results Framework and Monitoring |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| . |  |  |  |  |  |  |  |
| Country: Vietnam |  |  |  |  |  |  |  |
| Project Name: Strengthening Partnerships to Protect Endangered Wildlife in Vietnam (P162792) |  |  |  |  |  |  |  |
| . |  |  |  |  |  |  |  |
| Results Framework |  |  |  |  |  |  |  |
| . |  |  |  |  |  |  |  |
| Project Development Objectives |  |  |  |  |  |  |  |
| . |  |  |  |  |  |  |  |
| PDO Statement |  |  |  |  |  |  |  |
| The Project Development Objective is to strengthen the legal and regulatory framework, and the related implementation capacity for the protection of threatened wildlife. |  |  |  |  |  |  |  |
| These results are at | Project Level |  |  |  |  |  |  |
| . |  |  |  |  |  |  |  |
| Project Development Objective Indicators |  |  |  |  |  |  |  |
|  |  | Cumulative Target Values |  |  |  |  |  |
| Indicator Name | Baseline | YR1 | YR2 | YR3 | YR4 | YR5 | End Target |
| PDO1: Draft amendments to the law and regulations on threatened wildlife protection submitted for approval to the competent authorities (Number) | 0 | 0 | 0 | 1 | 3 | 5 | 5.00 |
| PDO2: Enforcement and conservation officers with increased competency in the application of laws and regulations on wildlife protection (Number) | 0 | 0 | 50 | 100 | 250 | 500 | 500 |
| PDO3: Enforcement and conservation agencies that deploy the SMART tool (Number) | 0 | 0 | 5 | 10 | 20 | 25 | 25 |
| PDO4: Share of government agencies participating in Biodiversity Steering Committee that agree on joint workplans on wildlife protection (percentage) | 0 | 0 | 50 | 60 | 70 | 90 | 90 |
| PDO5: Share of central and local government staff reached by awareness raising campaigns (percentage) | 0 | 0 | 0 | 10 | 25 | 50 | 50 |
| Intermediate Results Indicators |  |  |  |  |  |  |  |
| Indicator Name | Baseline | YR1 | YR2 | YR3 | YR4 | YR5 | End Target |
| IR1: Consultations with the constituencies on the proposed amendments to the law and regulations on threatened wildlife protection (Yes/No) | No | No | No | No | No | Yes | Yes |
| IR2: A legal framework developed for the management of ex-situ wildlife conservation facilities and submitted to the relevant authority for approval (Yes/No) | No | No | No | No | No | Yes | Yes |
| IR3: Recommendations on the implementation of the Law on Biodiversity in the tourism sector developed and submitted to the relevant authority (Yes/No) | No | No | No | No | No | Yes | Yes |
| IR4: Wildlife crime issues integrated into the National Crime Prevention Strategy (Yes/No) | No | No | No | No | Yes | Yes | Yes |
| IR5: A training needs assessment and training plan designed for the enforcement and implementation of the Law on Biodiversity and regulations (Yes/No) | No | No | Yes | Yes | Yes | Yes | Yes |
| IR6: People accessing the information sharing mechanism on the conservation of prioritized threatened species, and its share of women (Number/percentage) | 0 | 0 | 0 | 0 | 250 (30) | 500 (30) | 500 (30) |
| IR7: Memorandum of Understanding for collaboration with key stakeholders formalized (Number) | 0 | 0 | 0 | 1 | 2 | 3 | 3 |
| IR8: An awareness raising strategy targeting civil servants developed and implemented (Yes/No) | No | No | No | Yes | Yes | Yes | Yes |
| . |  |  |  |  |  |  |  |

| Indicator Description |  |  |  |  |
| --- | --- | --- | --- | --- |
| . |  |  |  |  |
| Project Development Objective Indicators |  |  |  |  |
| Indicator Name | Description (indicator definition etc.) | Frequency | Data Source / Methodology | Responsibility for Data Collection |
| PI1: Draft amendments to the laws and regulations on threatened wildlife protection submitted for approval to the competent authorities (Number) | This indicator will measure the number of laws and regulations including the Biodiversity Law and Decree 160, for which draft amendments are developed and submitted for approval to improve the effectiveness of these laws for protection of wildlife, for instance, to clarify the roles and responsibilities of different agencies and the gaps and overlaps among different laws and regulations. | Annual | MONRE’s official submission records, the National Assembly’s records | BCA, MONRE |
| PI2: Enforcement and conservation officers with increased competency in the application of the laws and regulations on wildlife protection (Number) | Training will target field enforcement and conservation officers across the agencies. Evaluation of trainees will be conducted after the training is provided in order to measure how many officers became competent in applying the Biodiversity Law, Decree 160, and other relevant regulations. | After training | Evaluation of trainees | Trainers, PMU |
| PI3: Enforcement and conservation agencies that deploy the SMART tool (Number) | This indicator captures the initial application of technical supporting tools to combat threatened wildlife violations | After each training session | Follow up surveys with the enforcement and conservation agencies | PMU |
| PI4: Share of government agencies participating in the Biodiversity Steering Committee that agree on joint work plans on wildlife protection (percentage) | Inter-agency coordination will be measured by percentage of the member agencies of the Biodiversity Steering Committee that agree on join work plans to share information and improve coordination on wildlife protection. | Annual | Meeting minutes; Annual reports | Biodiversity Steering Committee: PMU |
| PI5: Share of central and local government staff reached by awareness raising campaigns (percentage) | This captures the extent of awareness raising among civil servants at the central and local levels by taking samples from selected agencies. | Annual | Sample surveys | MONRE; Central Party Committee on Propaganda and Education; PMU |
| . |  |  |  |  |
| Intermediate Results Indicators |  |  |  |  |
| Indicator Name | Description (indicator definition etc.) | Frequency | Data Source / Methodology | Responsibility for Data Collection |
| IR1: Cross-sectoral constituencies participating in consultations on the proposed amendments to laws and regulations on threatened wildlife protection (Yes/No) | Consultations are a key step to develop draft amendments to laws and regulations. Consultations should have cross-sectoral participation from key agencies (MARD, MoJ, Supreme People’s Court, Supreme People’s Procuracy, MPS, Market Control, DARD, etc.), private sector, and communities including female constituencies. (Linked to PI1) | Annual | Consultant’s report | Consultant; PMU |
| IR2: A legal framework developed for the management of ex-situ wildlife conservation facilities and submitted to the relevant authority for approval (Yes/No) | Legal requirements that apply to conservation facilities, particularly breeding facilities and rescue centers, will fill the gap in the management and monitoring of those facilities (Linked to PI1) | Annual | Monitoring reports by the authorities in charge | DONRE, PMU |
| IR3: Recommendations on the implementation of the Law on Biodiversity in the tourism sector developed and submitted to the relevant authority (Yes/No) | Recommendations will clarify applicable laws and regulations and promote the protection of threatened species in tourism activities. (Linked to PI1) | Annual | Consultant’s report | Consultant; PMU |
| IR4: Wildlife crime issues integrated into the National Crime Prevention Strategy (Yes/No) | A component on preventing wildlife crimes in the National Crime Prevention Strategy developed and submitted for adoption by the MPS. (Linked to PI) | Annual | Consultant’s report | Consultant; PMU |
| IR5: A training needs assessment and training plan designed for the enforcement and implementation of the Law on Biodiversity and regulations (Yes/No) | A training needs assessment and plan will be designed in the application of the Biodiversity Law, Decree 160 and other regulations. (Linked to PI2) | Annual | Consultant’s report | Consultant; PMU |
| IR6: People accessing to the information sharing mechanism on the conservation of prioritized threatened species, and its share of women (Number/Percentage) | It aims to measure an increase in the number of people who access and share information on the threatened species, appropriate methodology of conservation and management to promote inter-agency coordination and to enhance the coordination among different agencies and increase the public interest. (Linked to PI2) | Annual | Statistics on website access; Questionnaire to website users | PMU/BCA |
| IR7: Memorandum of Understanding for collaboration with key stakeholders formalized (Number) | This is for active and enhanced collaboration among various national and international stakeholders, including social organizations, media, NGOs, government agencies, etc. (Linked to PI3) | Annual | MOUs signed | MONRE; PMU |
| IR8: An awareness raising strategy targeting civil servants developed and implemented (Yes/No) | An awareness raising strategy on the consumption of threatened wildlife products will primarily target civil servants in order to transform them into role models to the public. | Annual | Consultant’s report | Communications consultant; PMU |

Annex 2: Detailed Project Description

Vietnam: Strengthening Partnerships to Protect Endangered Wildlife in Vietnam

- The Project Development Objective is to strengthen the legal and regulatory framework, and the related implementation capacity for the protection of threatened wildlife. The PDO will be achieved through the following components and activities:

- Component 1: Strengthening the legal and regulatory framework.  The activities include (a) drafting amendments to the articles of the Law on Biodiversity, Decree 160, and other key regulations relevant to the protection of prioritized endangered species; (b) development of a legal framework for the improved management and monitoring of ex-situ wildlife conservation facilities; (c) development and submission of recommendations on the implementation of the Law on Biodiversity in the tourism sector to integrate the protection of threatened species into tourism activities; and (d) incorporation of wildlife crime issues in the National Crime Prevention Strategy. This component aims to harmonize legal and regulatory instruments relevant to the protection of threatened wildlife in Vietnam, especially making clear the roles and responsibilities of the key agencies such as MONRE, MARD, DONRE, and DARD. Component 1 is based on the finding and recommendations from past assessments, including the Wildlife Consumption in Vietnam Project (WLC), the International Consortium of Combating Wildlife Crime (ICCWC), and the Governance and Inclusive Growth (GIG) project, all of which recommend to reduce overlaps and provide an improved legal environment for the protection of threatened species. This component will be led by MONRE and implemented closely with MARD, MOJ, MOT, MPS, and the Environmental Police. The Project will provide support to:

- Draft amendments to the articles of the Law on Biodiversity, Decree 160, and other key regulations relevant to the protection of prioritized endangered species. This activity will contribute to the GoV’s current effort in improving the Law on Biodiversity and Decree 160 by reviewing, consulting, and drafting an amendment to the articles such as Articles 37 through 49 that are critical for the protection of prioritized endangered species. Based on the assessments conducted previously by the Government such as the Governance and Inclusive Growth (GIG), this activity will look at gaps and overlaps among the existing laws and regulations relevant to the in-situ protection of endangered terrestrial, aquatic, and marine species, trade, as well as breeding of those species. It will particularly clarify roles and responsibilities of different agencies to improve the effectiveness of the relevant laws and regulations. Lead agency: MONRE in collaboration with MARD and MOJ.

Outputs:  Draft amendments to the articles of the Law on Biodiversity, Decree 160, and other relevant regulations for submission by MONRE to the corresponding authorities.

- Develop a legal framework for the improved management and monitoring of ex-situ wildlife conservation facilities.  “Wildlife conservation facilities” refer to a specific type of operation regulated under the Law on Biodiversity and aimed at the ex-situ protection of prioritized endangered species. Currently there is no clear legal framework in Vietnam for wildlife conservation facilities to effectively protect and conserve wildlife ex-situ. There is confusion over the Law on Biodiversity in respect to farming of prioritized endangered species. Under the current Law on Biodiversity, there is in practice a difficulty in separating saving and breeding activities and facilities permitted to protect and reproduce endangered species. De-facto licenses/permits are granted for farming operations suspected for breeding endangered species, rare plants, fish and other sea mammals. It is a thriving industry in which wildlife caught from the natural habitat are bred in captivity and exported. The legal framework intends to guide facility managers and the enforcement authorities to improve ex-situ conservation of prioritized endangered species. The guidelines encompass, inter alia, inventory, facility standards, management and monitoring of breeding, and reporting responsibilities. Lead agency: MONRE.

Output:  Submission of a legal framework for the management of ex-situ wildlife conservation facilities to the relevant authority, in order to improve ex-situ conservation of prioritized endangered species.

- Develop and submit recommendations on the implementation of the Law on Biodiversity in the tourism sector to integrate the protection of threatened species into tourism activities. A study will look at the current issues in tourism activities, case studies highlighting good practices and business cases suitable in Vietnam, incentives for relevant authorities, business owners and operators, protected area managers, and tourists to promote the protection of threatened species in tourism activities. The recommendations will be submitted to the corresponding authorities (e.g., the Ministry of Tourism (MOT), MARD, PPCs) for adoption and implementation. These will also feed into the amendment of the articles of the Law on Biodiversity proposed under (a) above. Lead agency: MONRE in collaboration with the MOT, MARD, and PPCs.

Outputs:  Recommendations on the implementation of the Law on Biodiversity in the tourism sector to integrate the protection of threatened species into tourism activities.

- Incorporate wildlife crime issues in the National Crime Prevention Strategy. This activity will incorporate the issues of wildlife trade and consumption of threatened species into the National Crime Prevention Strategy. This activity will be led by the Ministry of Public Security (MPS). The Environmental Police (under MPS) is a statutory investigating body responsible for wildlife and forest crime. The Environmental Police’s overall responsibility is the enforcement of national policies aimed at preventing violations of the various laws. The component on preventing wildlife crimes in the Strategy will be disseminated to the enforcement officers through the training planned under Component 2. Lead agency: The MPS in collaboration with the Environmental Police.

Outputs:   A component on preventing wildlife crimes in the National Crime Prevention Strategy developed and submitted for adoption by the MPS.

- Component 2: Enhancing capacity to effectively implement and enforce policies and regulations related to the wildlife protection. This component will support (a) strengthening of the capacity for the application of the Biodiversity Law and Decree 160 for the field staff of key law enforcement agencies; (b) development of an information sharing mechanism on the protection and conservation of the prioritized endangered species; (c) development of conservation program for selected critically endangered species; and (d) institutional strengthening of the Biodiversity Steering Committee to enhance coordination of the enforcement and conservation operations among various agencies. The effectiveness of this component will be augmented by the improved regulatory framework (under Component 1), and an enhanced interagency coordination, especially at the local level. MONRE will lead the component activities in coordination with the Ministry of Public Security, MARD, DONRE, PPCs, and the Ministry of Justice. Especially, the Project will support a training needs assessment and develop training programs to complement capacity building in law enforcement under the Saving Species Project and the Regional Wildlife Project, both supported by the USAID. The Project will provide support to:

- Provide training in the application of the Biodiversity Law, Decree 160, and the Penal Code. A training needs assessment will be conducted to develop and prioritize training program including target provinces and protected areas to complement the Saving Species project supported by USAID. The targeted audience is field staff of the key law enforcement and conservation agencies. These agencies include DONRE, MARD Forest Protection Department, Provincial People’s Committee (PPCs), protected areas, and other enforcement authorities. Training subjects include the application of the Biodiversity Law, Decree 160, and Penal Code, reflecting the proposed amendments under Component 1 to test the effectiveness of such amendments on the ground; anti-poaching monitoring technology (i.e., the Spatial Monitoring and Reporting Tool (SMART) to monitor law enforcement); inter-agency communications in the enforcement operations at the local level to improving the flow of accurate information among conservation officers, enforcement officers, and prosecutors required for the application and enforcement of the Law on Biodiversity; and the development and application of valuation methodology with judiciary to standardize and adequately interpret and apply the Law on Biodiversity and relevant regulations across agencies. Lead agency: MONRE in collaboration with MPS, DONRE, MARD, PPCs, and MOJ.

Outputs: Training developed based on a training needs assessment and plan which complements the Saving Species project supported by USAID, and provided for DONRE, MARD Forest Protection Department, PPCs, conservation facilities, and protected area managers and staff, and other enforcement authorities.

- Develop an information sharing mechanism at the national level on the protection and conservation of the prioritized endangered species. This activity aims to promote scientifically sound conservation of endangered species prioritized under Decree 160 across the agencies. This is built on the web-based wildlife database and reporting system for the Hanoi area which was developed under the WLC project. The mechanism will include, inter alia, an up-to-date species list, a database on population and distribution, appropriate methodology of conservation and management, threats, trafficking cases (e.g., location), etc. For example, trafficking data is entered to the system by enforcement agencies and the data is integrated and accessible via MONRE web site. The database will be located at and maintained regularly by MONRE and will be openly accessible to promote inter-agency coordination and to increase the public interest. This will also be useful for the national reporting such as CBD and CITES reports and further improving the legal framework for the protection of threatened species. Lead agency: MONRE.

Outputs: Database and information sharing mechanism for improved and systematic threatened species monitoring and reporting.

- Develop a conservation program for selected critically endangered species and provide technical assistance to roll out the program. Based on the information collected and made available through the information sharing mechanism at MONRE above, a conservation program will be developed for the protection and conservation of selected critically endangered species. The program will be developed jointly with key enforcement and conservation agencies to promote effective protection and conservation of selected species across the agencies on the ground. The Project will also provide technical assistance such as dissemination, work plans, capacity building to roll out the program. Lead agency: MONRE.

Outputs: A conservation program for selected critically endangered species developed jointly with the relevant enforcement and management agencies and rolled out.

- Strengthen the institutional capacity of the Biodiversity Steering Committee to enhance coordination of the enforcement and conservation operations among various agencies. The National Biodiversity Steering Committee has been established to implement the National Biodiversity Strategy and Action Plan (NBSAP). The Committee is chaired by MONRE and is tasked with oversight of the biodiversity agenda and providing instructions and direction among relevant ministries on specific issues such as wildlife protection. This activity aims to enhance inter-agency coordination to improve the implementation of the Law on Biodiversity. It will support the development of join work plans including a coordination mechanism and regular information sharing on the status of the enforcement and conservation operations and its effectiveness. It will map and review the operations of different enforcement agencies with a view to improve accountability, inter-agency coordination, and effectiveness of the enforcement and conservation operations. Lead agency: MONRE.

Output: Joint work plans for the Biodiversity Steering Committee including a coordination mechanism and regular information sharing on the status of the enforcement and conservation operations and its effectiveness.

- Component 3: Promoting knowledge sharing and awareness raising. This component aims to improve knowledge sharing and awareness raising to reduce demand for wildlife consumption. The activities include (a) an expansion and facilitation of the Endangered Wildlife Partnership Forum; (b) knowledge exchanges on policy development, implementation and enforcement capacity, and outreach related to the protection and management of endangered species; and (c) development and implementation of an awareness raising strategy on the consumption of endangered wildlife products. MONRE and CCPE will lead this component, in cooperation with media/communication agencies, civil society organizations and NGOs. The Project will provide support to:

- Expand and facilitate the Endangered Wildlife Partnership Forum between various national and international stakeholders, including social organizations, media, NGOs, government agencies, etc. in order to increase synergies and collaboration on the ground. Development of joint work plans and a collaboration framework including stakeholder mapping and a resource mobilization strategy will be supported. The intended outcomes include active and enhanced coordination among the Forum member organizations, and facilitation of new partnerships between NGOs, government agencies, and the media through development. Lead agency: MONRE in collaboration with MARD.

Outputs:  A collaboration framework including stakeholder mapping, joint work plans, forum meetings and new MOUs among new partner organizations.

- Carry out knowledge exchange on policy development, conservation and enforcement capacity, and outreach related to the protection and management of endangered species. The activity will support knowledge exchange through the Endangered Wildlife Partnership Forum; and the Global Partnership on Wildlife Conservation and Crime Prevention for Sustainable Development Program (GWP), a multi-agency program funded by the GEF and led by the World Bank to support priority African and Asian countries; and existing bilateral and multilateral agreements on wildlife/biodiversity conservation. The modalities include workshops, just-in-time/action-oriented training in-person and remotely, field-based opportunities that promote south-south learning, and international/national events that allow for knowledge sharing, as linked to the GWP coordination grant. Lead agency: MONRE.

Outputs: Knowledge sharing events on policy development, implementation and enforcement capacity, and outreach related to the protection and management of endangered species.

- Develop and implement an awareness raising strategy on the consumption of threatened wildlife products. Studies suggest that civil servants are one of the major consumer groups of wildlife products in Vietnam. There have been various communications and awareness raising efforts targeting consumers and the private sector, while a focus on civil servants have not been paid due attention. Civil servants are considered a “low hanging fruits” group, as they are small in number, quite homogenous, can be reached easily through the Government communications systems, and is under greater public and media supervision. Civil servants also have strong influential power with spill over impacts onto other target groups in the society (the private sector, youth, community, etc.). The strategy will consider incentives for civil servants to stop wildlife consumption and become role models to the public; and educational information on wildlife crimes and potential punitive consequences of such crimes. This activity will build on lessons from the above-mentioned Global Partnership Program on Wildlife Conservation and Crime Prevention for Sustainable Development. Lead agency: The Party Central Commission on Propaganda and Education and (CCPE)

Outputs: An awareness raising strategy targeting civil servants developed, adopted, and implemented at the central and local levels.

- Component 4: Project Management and Monitoring and Evaluation (M&E). This component will provide support for MONRE in project management and implementation of the Project, including planning, coordination, technical inputs, financial management, procurement, environmental and social safeguards compliance, monitoring and evaluation, and reporting. A Project Management Unit will be established within MONRE to be responsible for day-to-day project management. MONRE through the PMU will develop a project operational manual (POM) in form and substance acceptable to the Bank, setting forth guidelines and procedures for the implementation of the Project. Results of the Project will contribute to the GWP Core Indicators to measure the number of law enforcement and judicial activities and the number of people supported at program sites.

Outputs: A POM, annual operation plans, procurement plan, quarterly and annual reports, unaudited financial reports, external audits, a mid-term evaluation repot, and the terminal evaluation report.

Annex 3: Implementation Arrangements

Vietnam: Strengthening Partnerships to Protect Endangered Wildlife in Vietnam (P162792)

  - Project Institutional and Implementation Arrangements

- The Project will be implemented in accordance Decree No 16 of the Government on management and use of official development assistance (ODA) and concessional loans of donors. Implementation arrangements of the proposed Project will build on the robust structure established under the Wildlife Consumption (WLC) project.

- The Ministry of Natural Resources and Environment (MONRE) will be the implementing agency on behalf of the Recipient. MONRE will establish the Project Management Unit (PMU) and will be responsible for the overall implementation and management of the Project, including procurement, financial management, safeguards management, monitoring, and overall administration. MONRE will be the lead agency for the implementation of Component 1. The Ministry of Public Security (MPS) will be the technical lead for Component 2 in collaboration with MONRE, MARD, and the Department of Customs. MONRE and the Central Party Committee on Communications and Education will lead the implementation of Component 3.

- A Project Steering Committee (PSC) will be established to make decisions and provide guidance for the implementation of project activities, including approval of the annual work plans and budget revisions. The PSC will consist of high-ranking members representing MONRE, MARD, MPS, MOF (Department of Customs), Ministry of Justice, CCPE and other relevant agencies. It is tentatively planned that MONRE’s Vice Minister will chair the PSC with the Deputy Director General of VEA under MONRE as the vice chairperson. The PSC will meet regularly or on an ad-hoc basis as necessary.

- A Project Management Unit (PMU) will be established within VEA of MONRE. The PMU will comprise Project Director, Project Coordinator, Accountant, Procurement Officer, and Project Assistant. Project director will have overall responsibility of project management and daily operation of the project as well as coordination with all relevant stakeholders, ministries and agencies. The PMU will develop annual work plans, carry out activities as planned, supervise consultants and monitor activities, ensure the quality of deliverables, and prepare reports as described in the POM. The PMU will ensure that the Project is implemented in accordance with the project documents such as the Project Paper, Grant Agreement, Disbursement Letter, POM, Integrated Safeguards Data Sheet (ISDS), FM handbook, and procurement framework. The specific responsibilities of the PMU include the following:

- Prepare annual work plans in coordination with MARD and other lead agencies;

- Act as the secretariat of the PSC to organized and support their functions;

- Translate their guidance into day-to-day project coordination and management;

- Provide technical support to MONRE, MARD, and other stakeholders in the implementation of activities to achieve the project objectives;

- Mobilize relevant stakeholders in support of the achievement of project objectives;

- Undertake project monitoring, budget management, quarterly planning (based on the annual work plans), and fulfilling reporting requirements to the PSC and the Bank.

- The roles, functions, and responsibilities of the PMU and participating agencies (MONRE, MARD, MPS, MOJ, CCPE and Customs Department) under the proposed Project will be detailed in the POM.

- Coordination among various donors is critical as there are many projects on wildlife protection and illegal trade in Vietnam. The main donors include: USAID, GIZ, and DFID. The design and approach of the Project is well aligned with these programs, especially the USAID Saving Species Project and Governance and Inclusive Growth project which, combined with their regional support on wildlife trade, applies nearly US$ 20 million to wildlife protection in Vietnam. These projects are complementary with a strong emphasis on law enforcement, thus indicating a strong need for close coordination in the implementation.  At an overarching level, the involvement of MARD as the main government partner for USAID will enhance the potential of the Project to meet its objective, given the importance of MARD (e.g. lead agency for the national Wildlife Enforcement Network as well as other vital roles) and that the Project’s overall impact will be intimately tied to successful implementation and support at MARD and other agencies.  The Project has identified several key activities under all three Components where coordination with USAID/MARD will be vital during implementation, including details related to the application of new tools, training materials, target participants etc.  Through such close coordination, the Project will ensure that it remains focused on outcomes relevant to MONRE’s mandate, including its mandate for threatened wildlife protection, while being value-adding to the collective effort from all donors, maintaining a shared overarching goal, mutual components and complimentary tactics, and avoiding duplication.

  - Financial Management

- Funds Flows and Disbursement Arrangements. The PIU will open a segregated Designated Account (DA) in USD at a commercial bank acceptable to the Bank to receive the Grant proceeds. The ceiling of the DA will be specified in the Disbursement Letter issued by the Bank.

- Disbursement Methods. The Project will use the following disbursement methods: Reimbursement, Advance, and Direct Payment as per the Bank’s disbursement guidelines.

- Reporting on Eligible Expenditures Paid from the Designated Account.  Withdrawal applications reporting eligible expenditures paid from the Designated Account will be with the following documentation:

- Withdrawal applications reporting eligible expenditures paid from the designated accounts will be with the following documentation: (a) List of payments against contracts, together with records evidencing eligible expenditures (e.g., copies of receipts, supplier invoices) for the contracts subject to the World Bank’s prior review as required in the Grant Agreement; and (b) Statement of Expenditure for all other expenditures/ contracts not subject to the World Bank’s prior review.

- The PIU will report on the use of the Grant from the DA on a quarterly basis.

- The Project will be financed at 100 percent by the grant, inclusive of taxes. Expenditures eligible for grant financing include goods, non-consulting services, consulting services, operating costs, and training and workshops. Counterpart funds of $0.3 million will be in-kind contribution to the revision of regulatory framework, coordination of the Biodiversity Steering Committee and the Endangered Wildlife Partnership Forum, and the project management and M&E activities.

- Accounting Arrangement. A simple financial management system will be established to: i) record all financial transactions of the Project; ii) produce periodic financial reports and ensure that all expenditures are duly authorized before payments. The current accounting software of Wildlife Consumption, namely Bravo, shall be upgraded to record Project accounting activities. Documentation and supporting documents shall be maintained at the PMU for subsequent review and audit. The Bank will provide further trainings and guidance to set up the recording format when Project starts.

- Report Arrangement. The financial reports are required to be submitted semi-annually with project progress report and procurement plan to the Task Team Leader in the World Bank. The reports comprise of: i) Statement of Sources and Uses of Funds by categories; ii) Uses of fund by project components compared with the plan; and iii) Statement of Designated Account. The format of the report shall be briefed to the designated accountant(s) when the Project starts.

- Audit Arrangement. Financial statements of the Project will be audited annually in accordance with International Auditing Standards and in compliance with the independent auditing regulations of Vietnam and terms of reference acceptable to the Bank. The audited financial statements and audit report must be submitted to the Bank within six months of the end of the fiscal year and end of the Project. The auditor who is acceptable to the Bank would express a single audit opinion covering the Project Accounts, the use of Statements of Expenditures and the Designated Account. A management letter addressing any internal control weaknesses of the implementing agency will also be provided by the auditor together with the audit opinion report.

  - Procurement

- Applicable Procurement Procedures. For contracts financed in whole or in part by the Grant, procurement would be carried out in accordance with “The World Bank Procurement Regulations for Investment Project Financing (IPF) Borrowers: Procurement in Investment Project Financing” (hereinafter referred to as “Procurement Regulations”) dated July 1, 2016; and the provisions stipulated in the Grant Agreement. Under the proposed Project, World Bank system, Systematic Tracking of Exchanges in Procurement (STEP), will be used. Procurement Plans will be prepared, cleared and updated through this system. All procurement transactions for the Project will also be conducted through the system. Thus, all the procurement activities under the proposed Project will be entered into, tracked and monitored online through the system.

- Procurement Capacity and Risk Assessment. Procurement Capacity and Risk Assessment (PCRA) for BCA has been conducted. It found that BCA has certain experience in conducting procurement in accordance with the Vietnam public procurement law and regulations and in implementing a number of the ODA funded projects including World Bank, Japan International Cooperation Agency, Asian Development Bank, and United Nations Development Programme. The BCA had also just recently successfully completed the WLC project. Nevertheless, the assessment revealed several potential risks that could cause implementation delay and/or non-compliance as follows: (i) lack of certain knowledge and experience of carrying out procurement activities in accordance with the Bank’s Procurement Regulations, rules and procedures particularly with respect to the new features allowed by the Procurement Framework; (ii) unreasonably lengthy internal procurement approval process under MONRE/VEA; and (iii) potential preference to use national procurement rules and procedures when they differ from Bank’s Procurement Regulations. The following measures are proposed to be implemented during project implementation to mitigate the risks identified above and to strengthen the procurement capacity of the BCA: (i) providing regular procurement training for BCA staff; (ii) assign qualified staff and/or hire individual procurement consultant to assist the BCA carrying out procurement activities under the Project; and (iii) carrying out regular implementation support missions and conduct annual procurement post review.

- Procurement Strategy. Based on the project requirements, operational context, economic aspects, technical solutions and market analysis, a Project Procurement Strategy Document (PPSD) has been developed for the Project by VEA with the support from the Bank team. The PPSD identified that the procurement activities under the Project mainly include consultancy services of small scale ranging from USD 20,000 to USD 200,000. The market research of the PPSD demonstrates that there are significant number of potential consultants (including firms and individual consultants) in the country for the services under the Project and given that the economy and efficiency are critical aspects of the project implementation the national market approach appears appropriate approach for procurement of all procurement packages under the Project. For all procurements, the Bank’s Sample and/or Standard Procurement Documents shall be used. The PPSD also indicates a number of potential risks that may affect the success of the procurement process such as (i) frequent changes and overlap in the policy regime of Vietnam; (ii) shortage of counterpart fund; (iii) weak experience and lengthy process of handling complaint; and (iv) desire of the consultants to win the contract at any cost that may negatively affect the quality of services provided and implementation progress. A number of risk mitigation measures as well as allocation of risks to the party that is in best position to take the risks are also proposed in the PPSD.

- Procurement Plan. Based on the PPSD, the initial procurement plan for the Project is being prepared by the PMU. The Project comprises of mainly consultant services of relatively small scale with risk rating of moderate. Thus, CQS has been proposed as the most common used selection method for those assignments. Not any large contract is foreseen at the project preparation stage; nevertheless, consultant selection method of QCBS, QBS, FBS, LCS with appropriate market approach can be used if in the future any large package is established. There is not either any contract being propose at this stage that need to be awarded on direct selection basis. Direct selection can only be used under certain circumstances with appropriate justifications. Procurement of works is not foreseen under the Project. There may be several small packages for procurement of goods that will be procured through national market approach. Request for Bids (RFB) will be used for procurement of goods and for efficiency, and contracts with cost less than US$ 100,000 can be procured using RFQ method. The Procurement Plans will be updated annually (or as needed) by the BCA to (a) reflect project implementation; (b) accommodate changes that should be made; and (c) add new packages as needed for the Project. All procurement plans, their updates or modifications shall be subject to Bank’s prior review and no-objection. The Bank shall arrange for the publication of the procurement plan and its updates on the Bank’s external website. The project Procurement Plan agreed with the Bank will identify prior review contracts according to the thresholds being set based on the performance and risk rating. Contracts not subject to prior review will be subject to post review. The Bank will carry out procurement post reviews on an annual basis with an initial sampling rate of 20 percent, which will be adjusted periodically during project implementation based on the performance of the Project.

  - Environmental and Social (including safeguards)

- Environment. The Project will provide technical assistance and capacity building to Vietnam in its efforts to protect the globally significant endangered species, including strengthening of legal and regulatory framework for threatened species protection, enforcement capacity and partnerships, and communication campaigns for behavior change and awareness raising on biodiversity conservation. Specifically, the Project will provide training and equipment (e.g. GPS, computers, printers, etc.), communication and awareness program and campaign, studies on selected threatened species (e.g., species profiles, populations and distribution, threats, protection status). It is anticipated that the Project will have positive environmental effects through improved policies, capacity and awareness to enhance wildlife protection. The Project will not support any civil works, and thus the Project is envisaged to not cause any significant adverse environmental effects.

- The Bank OP/BP 4.01 on environmental assessment is triggered as there is a possibility that studies and technical assistance (TA) activities supported by the Project might result to revisions and changes of existing policies governing protected areas (PAs) and threatened wildlife, among others, which may have safeguard implications further downstream in terms of the management of these PAs, including potential access restriction. However, given the nature of activities and the potential environmental implications, which would be further downstream and may be outside the life of the Project, the Project’s environmental effects have been envisaged to be negligible. Therefore, the Project is classified as Category C and environmental risk is considered low. It is recommended that where studies and TA activities are anticipated involving environmental implications, the TORs for these studies and TAs embed the directions and principles of the environmental safeguard policies, namely assessing environmental implications which needs to describe how the identified environmental implications will be addressed either through the existing environmental safeguard instruments of the Bank and the Government of Vietnam or provisions in proposed policies and institutional set-up. These TORs shall be reviewed by and have inputs from the Bank team.

- MONRE has implemented the Bank-financed projects and it is familiar with the Bank safeguard policy requirements. Nonetheless, safeguard refreshing is necessary for MONRE during project implementation.

- Social. The project support will be on provision of technical assistance to various relevant Government agencies in Vietnam to enhance the protection of the globally significant endangered species. The Project is also aimed benefiting local people living in or nearby the natural habitats who are kept poor by reduced environmental services and illegal activities that results in fair development and progress. However, there is a possibility that the policy and institutional studies and recommendations may lead to development or revision of certain provisions of existing policies that likely to affect the local ethnic minority (EM) people who are involving in hunting, keeping and using wildlife. Social issues to be considered during project implementation whether these recommendations to reform and implementation of Law on Biodiversity and other policies may likely to adversely affect the EM peoples’ livelihoods, participation and consultation process as well as gender mainstreaming in wildlife protection and management. Therefore, the TORs for these studies will embed the directions and principles of OP/BP 4.10 on Indigenous People and OP/BP 4.12 on Involuntary Resettlement. An analysis of potential issues related to EM and gender will be included in the TORs which will need to describe how the identified issues will be addressed either through existing safeguard instruments or provisions in proposed policies and institutional set up. The Project does not foresee to involve in involuntary resettlement. To ensure a more systematic approach that analysis of safeguard implications is well-integrated into each study and TA activity, any TOR should be reviewed by and have inputs from the Bank team.

- Mainstreaming gender issues into project activities is of special attention of the Project. Mainstreaming gender issues into policy advice and then into policy design is to ensure that both women and men benefit from the changes these policies are intended to bring about. To this end, the Project will encourage women’s participation, strengthen women’s roles and contribution in (i) providing advices, comments and feedbacks to the amendment of the Law on Biodiversity and other key regulations; (ii) exchanging and disseminating information and knowledge on policy development and enforcement capacity; (iii) awareness raising and capacity building activities. Women’s Unions will be engaged to carry out information dissemination as part of outreach efforts to targeted stakeholders, especially the poor and ethnic minority women related to the protection and management of threatened species.

  - Monitoring & Evaluation

- The Results Framework has been developed with a set of indicators, data source, responsibility, and frequency to monitor the progress toward the target. The Operational Manual will guide the monitoring and evaluation activities. The Annual Operating Plans will describe the actual plan for the monitoring and evaluation activities.

- Periodically reports will be prepared to evaluate the progress of the project implementation. In addition, a Steering Committee will be established to guide, monitor and ensure that the project is implemented effectively.

- Mid-term and final evaluation will be carried out jointly with the GoV, MONRE, and WB. The GoV will produce mid-term and final reports which will be shared with the WB.

Annex 4: Incremental Cost Analysis

Vietnam: Strengthening Partnerships to Protect Endangered Wildlife in Vietnam (P162792)

  - The global environmental problems, root causes and barriers that need to be addressed

- It is widely recognized that the illegal trade and consumption of wildlife has increased significantly in recent years, resulting in dramatic declines in wildlife populations. The illegal wildlife trade is global in scope, and estimated to be worth between $5-20 billion annually. Many species are being poached and extracted from their natural habitat, which affects environmental services provided to the human. This is reducing dramatically the ecosystem services provided by elephants, the grazing services provided by rhinos and giraffes, as well as the myriad services underpinned by the many other species being targeted. Unsustainable levels of illegal trade and consumption is multifaceted threats as it affects all regions, with species being slaughtered and traded within countries, across borders, and between regions.

- Besides the threat to biodiversity conservation within forests, wetlands, and protected areas, illegal wildlife trade and consumption also has serious negative impacts on economies and societies. The degradation of ecosystems and natural resources leads to communities’ loss of access to resources, lost revenue and income. When natural resources and wildlife are extracted illegally, it is effectively lost income- whether private, in the form of lost wages, or depressed prices in legal markets due to increased supply, or public, in the form of foregone taxes and royalties where legal markets exist. The Environmental Justice Foundation estimates that Guinea loses $105 million worth of fish to pirate fishing yearly. Crime affecting natural resources and the environment inflict damage on developing countries worth more than US$70 billion a year (World Bank 2014). Biodiversity accounts for over a third of the wealth of the poor, providing them food, medicines and opportunities for income. As the stock of biodiversity disappears, so too the investment opportunities that attract the private sector, particularly to engage in non-consumptive and consumptive uses such as tourism and sport hunting, a critical economic driver in many countries.

- Within this situation, Vietnam’s biodiversity is facing various threats, especially illegal hunting, trading and consumption. Moreover, Vietnam is considered a consumer market and transit point of trade chains of wildlife sourced from other countries. The rapid growth of Vietnam’s economy over the past 20 years has inflated demand for luxury goods, including high value wildlife products, which are most commonly consumed in specialty restaurants or used in traditional medicine.

- Research has shown that Vietnamese consumer markets are increasingly the destination for species such as tiger and bear, pangolin, freshwater turtles, snakes, and monitor lizards sourced from other Asian countries; while products like rhino horn and ungulate horns sourced in Africa are frequently traded to Vietnam for domestic consumers.

- Over-hunting and unsustainable levels of wildlife trade and consumption have led to widespread depletion of wildlife species from most forest areas in Vietnam, giving rise to the phenomenon of “empty forests”, in which wildlife density is very low.

- Although the Government of Vietnam has recently increased its efforts and commitment to combat illegal wildlife trade and reduce consumer demand for wildlife products, such as signing in London Declaration, Kasane Declaration on wildlife and wild plant trade, Declaration against wildlife trafficking in the 9th East Asia Summit and Declaration on the 22nd APEC Economic Leaders’ Meeting including a provision for continued efforts against wildlife trafficking; as well as issuing strengthened wildlife protection policies and action plans including Directive 03/CT-TTg) on prioritizing enforcement to combat illegal poaching and wildlife trafficking, demonstrating the government's recognition of the urgency of controlling and reducing illegal wildlife trade in Vietnam, Guideline 98-HD/BTGTW on enhancing communication to reduce wildlife consumption and trade, joining the ARREST program (Asia’s Regional Response to Endangered Species Trafficking) as a local partner, and developing the Vietnam-Wildlife Enforcement Network, current responses remain inadequate to keep pace with escalating trade and demand.

- Root causes and barriers that need to be addressed in Vietnam include the following:

- There are still flaws in the legal and policy framework that make enforcement efforts difficult. Although studies have identified inadequacies, gaps and overlaps in the current policies and legal frameworks, the development of recommended regulations and legal documents requires more time and resources to complete, especially in new areas such as management of wildlife conservation breeding facilities and re-introduction to the wild; management of commercial captive breeding facilities to ensure they do not bring negative impacts to conservation; mechanisms for long-term species-based conservation programs; and many others.

- Effective enforcement by well-resourced, well-trained, professional and merit-based state protected areas agencies is absent. These authorities legally own the wildlife resource but are frequently underfunded and under-capacitated, which means that there is little effective enforcement, and in some cases a de facto open access regime in which people are able to utilize the wildlife resource for subsistence, for criminal poaching purposes, or for elite recreational hunting, frequently on an unsustainable basis. Often this results in ‘frontier economy’ conditions, where prices are rising and markets expanding without corresponding development of institutional constraints through definitions of legal ownership and regulations on use. If wildlife is to be owned by the state and not the communities, tight and effective enforcement is essential in order to avoid the tragedy of the commons.

- Awareness and support from the community for wildlife protection is not yet adequate. In particular, the private sector is not yet seriously engaged in conservation issues, providing only limited support and not yet mainstreaming conservation issues into business codes of conduct. This leads to the lack of ownership by the communities and the private sector. Since wildlife is considered a state-owned resource, and since communities co-existing with wildlife typically bear the costs of loss of livestock, crops and life without gaining significant economic benefit from wildlife, the wildlife itself may have little or no net positive economic value to the community. What is lacking in most countries is a systematic dialogue on how to best ensure that communities benefit from land and natural resources, consistent with national priorities and legislation, in order to create the fundamental socio-economic conditions necessary for the long-term persistence of biodiversity in line with the objectives of the CBD.

- Inter-agency cooperation has not been well coordinated despite the creation of Vietnam-WEN, because its coordination role and capacity has not been promoted; and law enforcement capacity is limited compared to the sophistication of wildlife trade operations controlled by organized criminal syndicates. Capacity building training for law enforcement officers has not been focused and institutionalized, and there are low incentives to combat wildlife crime when considering the high occupational risks for enforcement officer versus the low salaries and benefits.

  - The baseline scenario or any associated baseline projects

- This proposed Project is designed to build on and scale up the work begun under the “Wildlife Consumption in Vietnam: Reforming policies and practices to strengthen biodiversity conservation” (WLC) project. The WLC project was funded by the Global Environment Facility via the World Bank, and implemented by the Ministry of Natural Resources and Environment (MONRE) from 2012 up to May 2015.

- It was the first project to attempt to make systematic efforts to address illegal wildlife consumption and demand reduction at a national level. It has also produced some important results, outcomes, and experience that have provided an important baseline for all future demand reduction efforts, and need to be further developed and expanded in order to secure long-term behavior change.

- The baseline scenario built on results from the WLC Project and other associated projects is grouped into three components as follows:

•	Strengthening policy and legal environment and data management to protect threatened species: An in-depth review of the weaknesses and limitations of the legal framework for wildlife protection was conducted under the WLC Project, which provided a comprehensive list of recommendations for policy revisions and amendments, which will become an important basis for all future efforts in strengthening the framework. Some key recommendations include further regulations to enable application of the Penal Code to Decree 160/2013/ND-CP, and regulations to specify and support the management of wildlife conservation breeding, develop a permit system and law enforcement and management monitoring system for the exploitation of species prioritized for protection (under Decree 160), review the implementation of the Law on Biodiversity to determine the contents in need of revision and amendment relating to rare and precious species prioritized for protection and many others. The development of these regulations is in urgent need of completion in the shortest time. This project proposal is designed to fulfill these needs to strengthen the wildlife protection legal system and comply with international conventions to which Vietnam is a party.

•	Enhancing national enforcement infrastructure to reduce and deter illegal trade of endangered species: A new directive was issued by the Prime Minister in February 2014 (Directive 03/CT-TTg) on prioritizing enforcement to combat illegal poaching and wildlife trafficking, demonstrating the government's recognition of the urgency of controlling and reducing illegal wildlife trade in Vietnam. Although law enforcement efforts have been enhanced recently, it has been insufficient to adequately respond to the rapid increase in wildlife violations in Vietnam. According to statistics from Vietnam's National Forest Protection Department, from 2010 to the end of October 2014, there were 3,823 cases of wildlife violations, involving more than 58,869 individual wild animals, of which 3,078 were rare, precious and endangered species. These figures represent only a small portion of the quantity of wildlife being consumed domestically or smuggled to other countries, as it is estimated that only between 5-10 percent of all illegal trade is intercepted by authorities. The application of criminal measures is also very limited and inadequate to deter violators, with cases being slow to process and having a very low rate of successful prosecution. According to National Forest Protection Department statistics, between 2011 and 2013, 1028 cases of serious violations of regulations on management and protection of forests and forest products were prosecuted, involving 1,233 criminal defendants; however, only 153 cases (15 percent) were actually bought to trial.

Under the scope of the WLC project, strengthening law enforcement capacity and effectiveness was targeted through various efforts including: supporting law enforcement agencies in organizing strategic enforcement campaigns against wildlife retail establishments; developing law enforcement support materials (law enforcement manual, species ID guide, WildScan phone application for species identification and reporting wildlife crime); and developing a database to track and record wildlife violations in Hanoi.  However, these efforts are still at the initial stage. They will support law enforcement efforts more effectively when they are further improved and scaled up to other areas beyond Hanoi, such as hotspots for wildlife poaching, and illegal trade and consumption.

•	Strengthening partnerships, and scaling and institutionalising behaviour change campaigns, to reduce demand for wildlife consumption: The WLC Project piloted a partnership approach, and developed the Wildlife Partnership Forum as a networking platform for collaboration between government agencies, offices and organizations, socio-political organizations, the private sector, and NGOs and international organizations. As such, communication activities have directly reached key target audiences with the active support and cooperation from forum members such as the Central Committee of Propaganda and Education, National Youth Union, relevant government ministries such as Ministry of Health, Ministry of Public Security, Ministry of Industry and Commerce, and others. The communication campaigns were developed based on the results of various scientific studies and surveys on wildlife consumption (Institute of Sociology survey under WLC project in 2014, TRAFFIC survey in 2007, ENV survey in 2010), and achieved some significant results. However, campaigns were only conducted in limited areas and scales. Cooperation from other key partners such as Ministry of Education and Training (to target students and children) and the private sector (to target businessmen) has not yet been activated. Most importantly, civil servants are one of the major consumer groups of wildlife products in Vietnam. But no campaigns are targeting this group.

- There are also many NGOs working on various aspects of the demand reduction issue in Vietnam, including ENV, TRAFFIC, WWF, Humane Society International, Animals Asia Foundation, Wildlife Conservation Society, etc., but these efforts have not been well linked despite BCA’s coordination efforts. Although these efforts have not yet resulted in any significant level of behavior change in Vietnam, it is certain that over time, education and public awareness raising activities play a very important role in the prevention and reduction of illegal wildlife trade and consumption. For example, in 2012, WildAid reported a 50-70 percent reduction in shark fin consumption in China, and a government ban on serving shark fin soup at state banquets, as key results of longstanding communication campaigns targeting this issue.

- Many programs promote community-based natural resource management (CBNRM), which has made significant gains in pointing to pathways out of rural poverty that effectively strengthen enforcement. Effective CBNRM efforts provide communities with a stake in the preservation of wildlife and their habitats through shared responsibilities for management and shared benefits from their sustainable use. Community-based enforcement is useful at addressing local resource issues, but for effective prosecution support is required from government authorities. To shift ownership to the communities, capacity development of communities, FPD and commune People’s Committees is required to enhance understanding and community empowerment.

  - The proposed alternative scenario, with a brief description of expected outcomes and components of the project

- The proposed Project is designed as one of the national projects under the ‘Global Partnership on Wildlife Conservation and Crime Prevention for Sustainable Development’, a global program coordinated by the World Bank Group to reduce impacts to known threatened species from poaching and illegal trade, and as such, the outcomes will support both the global and local contexts.

- To achieve this, the Project will apply a participatory and mainstreaming approach to reduce the threat of illegal poaching, trafficking and consumption, and protect globally significant species. As such, the Project has been designed so that a range of agencies will take on implementing roles for specific and relevant output within this Project, under the overall coordination of the Ministry of Natural Resources and Environment (MONRE). Agencies with implementing roles will include MONRE, Ministry of Agriculture and Rural Development, Ministry of Public Security, Ministry of Justice, Ministry of Health, Ministry of Education and Training, and Ministry of Finance. The project will focus on three main components:

(1) Strengthening the legal and regulatory framework to protect threatened species:

- This component aims to further improve the legal and regulatory framework to enable effective protection of threatened species and biodiversity, in conformity with Vietnam’s obligations to the Convention on Biological Diversity (CBD), the Convention on International Trade of Endangered Species (CITES), and national laws. Expected output will include the development of regulations to instruct the implementation of the Law on Biodiversity, especially in applying the Penal Code to Decree 160 and developing specific and technical guidelines to manage wildlife conservation facilities, review the implementation of Law on Biodiversity and recommend contents in need of revision and amendment relating to the conservation of rare and precious species prioritized for protection. These have been identified as the priority needs by the law and policy review conducted under the WLC Project.

- Long-term and specific national conservation programs for selected species under Decree 160 will be also developed, with initial focus on endemic primate and turtle species. The species conservation programs will also support the implementation of the NBSAP and Biodiversity Master Plan. Currently, national species conservation programs have only been developed for tiger and elephant species, but there are many other critically endangered species that are in urgent need of the support of a comprehensive conservation strategy, in particular the critically endangered and endemic primates and turtles. In addition, it is necessary to develop a database on rare and precious species prioritized for protection to support their management and conservation and periodically submit to the Government for approval the List of rare and precious species prioritized for protection.

(2) Enhancing capacity to effectively implement and enforce Vietnam’s laws and regulation related to wildlife protection:

- The challenges that law enforcement authorities face in managing illegal wildlife trade and consumption in Vietnam have been well documented in various studies, including in the legal review and consultation workshops carried out under the WLC Project. Some of the biggest challenges include the lack of capacity, equipment and training for law enforcement authorities, the lack of clear procedures and systems for handling evidence, the lack of prosecutions for criminal violations and inadequacy of punishments, and the lack of policy incentives for officials to implement the law fully and correctly. This component is designed to build on the baseline scenario established under the WLC Project and address these shortcomings. This component will be led by MONRE with MARD, Ministry of Public Security and Ministry of Justice also playing key implementing roles for particular output.

- In order to improve interagency cooperation and coordination for wildlife law enforcement, a national information sharing system will be developed in conformity with NBSAP requirements, including national monitoring and reporting measures, policing strategies, data collection, etc. There will be increased support for anti-smuggling enforcement authorities along Vietnam's borders, especially borders with Laos and China, with more resources, equipment, technology, the introduction of detection dogs to assist detection and investigations, training, and a sustained campaign to prevent corruption amongst border officials. The Biodiversity Steering Committee will also be strengthened and activated as a national taskforce for biodiversity protection, with the institutionalization of training programs, materials, tools and support for more effective investigations, patrolling, intelligence analysis, policing operations, etc.

- In order to improve the application of the national legal and regulatory framework in conformity with the CBD and CITES as an effective deterrent against biodiversity violations, training programs and materials for enforcement officers will be institutionalized. This will contribute to more effective prosecution of wildlife violations, including sentencing guidelines, applying sanctions to biodiversity and wildlife crime, and raising awareness of the seriousness of biodiversity crime.

(3) Improving knowledge sharing and awareness raising:

- Some of the key findings from the study on wildlife consumer behavior and attitudes, conducted under the WLC Project, included a general low awareness of the consequences of wildlife consumption, the significant potential for future growth in the rate of wildlife consumption for food, medicine and ornaments, but also an overall willingness for consumers to try alternative, non-wildlife products (especially relating to traditional medicine). Following these findings, this component will build on the experience of the awareness activities and partnerships developed under the WLC Project, as well as that of other NGOs and organizations working in demand reduction activities in Vietnam. This component aims to increase the support for and awareness of biodiversity and wildlife protection within key target audiences, especially civil servants.

- Partnerships between government agencies, NGOs, the private sector, and socio-political organizations will be strengthened and supported by further development of the Wildlife Partnership Forum (coordinated by MONRE) as the networking and coordination platform for wildlife protection efforts. The project will also promote initiatives on wildlife protection for various NGOs and socio-political organizations through small-scale projects.

- Regional cooperation in reduction of demand for wildlife products will be strengthened through active participation in the Endangered Wildlife Partnership Forum and increased regional cooperation among agencies and cross-section of stakeholders. Implementation of MOUs with neighboring countries will be strengthened relating to the management and control of wildlife poaching, transportation and trafficking, especially MOUs with Laos, Cambodia, Thailand and China.

  - Incremental cost reasoning and expected contributions from the baseline, the GEFTF, and co-financing

- Vietnam's policy and legal framework for the conservation and management of wildlife shows an overall direction that is consistent with the imperative of controlling illegal wildlife consumption and trade. The Government of Vietnam at a high level has demonstrated its commitment to addressing the issue by signing the London Declaration on Illegal Wildlife Trade in February 2014, by issuing the Prime Minister's Directive 03/QD-TTg (also in February 2014) and Kasane Declaration on illegal wildlife trade on March 2015, and by approving Vietnam's National Tiger Recovery Program for the period 2014-2022, which supports Vietnam's commitments to the Global Tiger Initiative. However, there is still a large gap between the overall legal framework and statements of political support, and the implementation of the regulations on the ground to result in effective control of illegal wildlife trade and real reduction in illegal wildlife consumption.

- The review of weaknesses and limitations in the policy and legal framework, which was conducted under the WLC Project and released in September 2014, highlighted the lack of specific technical guidelines and procedures and many gaps, loopholes, overlaps and inconsistencies, which are inhibiting the ability of law enforcement officials to do their jobs effectively. For example, the Law on Biodiversity was passed in 2008, but the first Decree to implement it (Decree 160/2013/ND-CP on Species Prioritized for Protection) only came into effect in January 2014, and further regulations are urgently needed in order to support its effective implementation and achieve the intended objective of conservation and sustainable use of wildlife. There is also a lack of knowledge, awareness, and confusion about policies and institutional structures, and a lack of best practices to make actual changes on the ground.

- The proposed Project will build on the existing baseline and systemic improvements created under the WLC Project, and incrementally apply technical assistance and expertise to make stronger inroads into the large problem of illegal wildlife trade and consumption. In the absence of this support, the momentum for change initiated under the WLC Project is likely to dissipate quickly and prematurely, before having the chance to amount to any significant results for wildlife protection and conservation on the ground. The baseline situation of unsustainable wildlife consumption and trade, consequently over-exploiting threatened species would then be expected to continue for many years, and likely result in the extirpation or extinction of some particularly vulnerable species, such as elephants, rhinos, bears, tigers, and pangolins. This scenario could be expected to occur not just in Vietnam, but potentially in neighboring countries and the countries of origin as well.

- Vietnam currently lacks the technical capacity to develop effective strategies and mobilize the cross-sectoral support that is necessary to address illegal wildlife consumption and trade. GEF support can add value by supporting the development of interagency approaches, helping Vietnam to identify effective approaches that have been applied elsewhere, and by helping Vietnam to monitor progress at national level and, hence, be able to better report on progress at international level, such as through CITES. The focus of project efforts will be on globally threatened species – both those sourced into wildlife trade from Vietnam, as well as species (and parts thereof) traded internationally (such as rhino horn, ivory, and tiger bone glue). This focus on global environmental benefits should complement GEF investments in other biodiversity conservation projects, including other wildlife poaching and trafficking projects and protected areas management projects in southern Africa and South and South-East Asia. It is expected that this project would provide learning and experiences that would be particularly valuable for application in efforts for regional cooperation with other wildlife source, transit and consumer countries in Asia, such as China and Thailand.

  - Global environmental benefits (GEFTF)

- Illegal wildlife trade and consumption is now widely recognized as a significant threat to biodiversity on a global scale to be tackled with urgency. It has particularly important implications for globally threatened species such as rhino, elephant, tiger, and pangolin. However, international concerns also extend beyond the environmental issues and threats to species and ecosystems, to include threats to transnational security posed by organized criminal syndicates, human health impacts posed by the spread of zoonotic diseases, and the threat to economies and sustainable development posed by the loss and destruction of natural resources and biodiversity.

- These concerns are reflected in various recent decisions by the Convention on Biodiversity, Convention on International Trade in Endangered Species of Wild Fauna and Flora (CITES), the United Nations General Assembly, INTERPOL, and others (UNEP, 2014). In February 2014, the London Declaration on Illegal Wildlife Trade was signed by more than 40 countries including Vietnam, committing to greater efforts and coordination to strengthen policies and enforcement, and reduce consumer demand for wildlife products. Since 2012, many countries have also destroyed stockpiles of confiscated ivory to publicly demonstrate their commitment to end illegal poaching and trafficking, including Gabon, Philippines, United States, China, France, Chad, Belgium, and Hong Kong Special Administrative Region of China. In this context, the proposed project aims to not only address the domestic challenges of illegal exploitation, trade and consumption of endangered species in Vietnam, but to also make an important contribution at the global level by reducing the impact of domestic trade and consumption on global biodiversity.

- This aim will be supported by the inclusion of the proposed project as a national project under the ‘Global Partnership on Wildlife Conservation and Crime Prevention for Sustainable Development (GWP)’, which will ensure linkages and coordination with similar projects in other countries across the world, and the sharing of experience and lessons learned to combat wildlife trafficking. For example, by strengthening legislation and law enforcement, and reducing demand for wildlife products in Vietnam, the proposed project can contribute to reducing the impact of poaching in other countries that would otherwise service the demand in Vietnam, such as poaching rhinos in African countries. This would reduce the negative effects on conservation efforts in those countries; the economic threats caused by degradation, loss of biodiversity, and negative impacts on the tourism industry; and the loss of livelihoods for local communities caused by lost access to natural resources. The proposed project will also contribute to strengthening the coordination and information sharing among agencies and countries, leading to reduction of the spread of organized transnational crimes and contributing to the restoration and enhancement of national and regional security. Due to the global nature of this issue, by tackling poaching, trafficking and consumer demand in order to support the needs of wildlife protection and conservation in Vietnam, the proposed project will also help to reduce the pressure on wildlife and biodiversity around the world.

- This project is consistent with the objectives of the GEF-6 Biodiversity Strategy and Programming Directions. The expected output and outcomes will make a direct and significant contribution to BD 2-Program 3 on "Reducing Poaching and Illegal Trafficking of Threatened Species", by mainstreaming wildlife and biodiversity concerns across a wide range of government agencies and sectors, including agencies not traditionally concerned with wildlife and biodiversity issues.

  - Innovation, sustainability and potential for scaling up

- Innovation: The proposed project will continue to develop the multi-stakeholder, partnership approach piloted under the WLC Project, to combat illegal wildlife trade and consumption in Vietnam. This approach has been incorporated into the overall project design, with output and outcomes that engage other agencies as responsible implementing partners, to mainstream the illegal wildlife trade issue across sectors. This design will also enable the development of national expertise across a range of government agencies. The proposed project is also tackling the three pillars of poaching, trafficking and demand reduction together, in recognition that the issue needs to be addressed holistically in order to make an impact. The project design also includes several innovative outputs that aim to incentivize biodiversity protection for both the general public and government officials. For example, an annual awards program that recognizes outstanding efforts of civilians and government officials in biodiversity protection; and a system that rewards and encourages excellent enforcement efforts that lead to successful arrests and prosecutions of biodiversity crime.

- Sustainability:  Environmental sustainability is as an essential component for strong and sustainable economic growth recognized under the Vietnam’s Socio-Economic Development Plan for 2016-2020 (SEDP). In this context, the GoV is committed to addressing wildlife crime issues and has established biodiversity and natural resources protection as a priority task for the 2016-2020 period. MONRE and other key agencies such as MARD are mandated by specific legislation to address the protection of biodiversity and natural resources. Also, various donors and NGOs have been keen to provide support for reducing wildlife crimes in Vietnam and are likely to continue to do so.

- The proposed project activities were selected for the potential of making impacts on the protection and conservation of threatened species in Vietnam in a short- to medium-term. Once the project activities have achieved the objectives and are proven to have impacts, it will have more potential for the Government to continue or expand the activities after the Project.

- The project will strengthen and improve the legal and regulatory framework for the management and protection of wildlife, aiming to enhance the transparency of the legislation system and simplify the implementation of regulations to enable more effective law enforcement on the ground. A strengthened and improved legal and policy framework will bring long-term benefits and sustainability for the environment and society that extend far beyond the completion of the project.

- In addition, the project's multi-stakeholder approach, involving the participation of many government agencies in the implementation of relevant project components, contributes to the mainstreaming of conservation and biodiversity issues across many sectors and agencies. Mainstreaming these issues, increasing awareness, and strengthening policies, will make significant contributions to the sustainability of project outcomes and changing behavior for wildlife protection.

- The project design recognizes the importance of the public as well as civil servants to participate in biodiversity and wildlife protection is critical for long-term sustainability of controlling illegal trade and reducing demand for wildlife consumption. It has therefore incorporated a targeted intervention to raise awareness and education of civil servants, which has potential of greater spill-over impacts on the public at large.

- Potential for scaling up: As this is just the second project to implement systematic efforts to address illegal wildlife trade and consumption at a national level in Vietnam, and it started from a low baseline, there is significant potential for scaling up outcomes and outputs. In general, aspects such as training, capacity building and education programs for enforcement and demand reduction can be expanded and strengthened. Through increased international cooperation, knowledge and lessons learned can continue to be applied and exchanged. The improved legal and framework will be important to develop and further expand conservation programs and implemented on the ground.

- The project will also test and implement several specific initiatives that have great potential for scaling up within Vietnam or replication elsewhere. For example, the project will target civil servants to be role model for the public, especially community leaders and youth, which could be expanded nationwide if it proves to be an effective approach to reduce demand and consumption of wildlife products.

Annex 5: Theory of Change

Vietnam: Strengthening Partnerships to Protect Endangered Wildlife in Vietnam (P162792)

- In order to have a significant impact on preventing the extinction of known threatened species by curtailing poaching and the illegal wildlife trade, and promoting the sustainable use of wildlife resources, the Global Partnership on Wildlife Conservation and Crime Prevention for Sustainable Development (GWP) was designed following a theory of change that would address key distortions and weaknesses across the illegal wildlife value chain. This theory of change prioritizes investments in emergency short-term interventions to combat wildlife crime, and in ensuring that the real value of wildlife is reflected in land use planning and incentives in the longer term. Thus, emergency interventions focus on reducing poaching, reducing trafficking and reducing illegal trade. Long-term intervention focus on promoting sustainability, community benefits, effective governance by communities including through land use zonation and natural resource rules and practices. These interventions are designed to act collectively to shift the cost-benefit calculus in relation to the participation by a wide range of actors across the illegal supply chain–both increasing the costs of participation in the illegal trade, and increasing and more equitably sharing the benefits of tightly enforced sustainable management and use of wildlife resources, under the framework of CITES and other multilateral environmental agreements. This builds on the current thinking of organizations involved in wildlife protection, and simultaneously seeks to promote innovative thinking on interventions to address the escalating challenges more effectively. The GWP aims to promote dialogue in the countries in which the child projects are taking place on how to best ensure that communities benefit from land and natural resources, consistent with national priorities and legislation, in order to create the fundamental socio-economic conditions necessary for the long-term persistence of biodiversity, which is consistent with the objectives of the CBD. The theory of change of the GWP can be summarized by a series of interventions along the value chain from source to transit to demand. Illegal wildlife trade will come to an end, if there is concerted effort to reduce poaching and empower local communities to be the stewards and beneficiaries of wildlife, combined with controlling crime and trafficking at higher levels, and reducing demand for illegal wildlife and at the same time promoting the legal trade to provide incentives for wildlife-based land use and protection by the local communities. These series of interventions should, in the long term, result in healthy wildlife populations sustainably management by the landholders and local communities on the ground for the benefit of those along the legal value chain of the products currently traded illegally.

- As one of the national projects under the GWP, the proposed Project follows the theory of change as depicted in Figure 1. The current situation of wildlife conservation and illegal wildlife trade in Vietnam is a major concern for the country as well as for the international community. It is widely recognized that the illegal exploitation, trade and consumption of wildlife has increased significantly in Vietnam as well as at the global level, resulting in dramatic declines in wildlife populations and near extinction of some species (e.g., black rhino). Vietnam has been identified by CITES as one of the countries of “primary concern” in the control of illegal trade and consumption of ivory as well as rhino horn. Vietnam is not only a destination of trade chains of wildlife sourced from other countries, but also considered a transit point of such trade chains. Wildlife trade and consumption have led to widespread depletion of species from most forest areas in Vietnam, giving rise to the phenomenon of “empty forests” in which wildlife density is very low. The economic growth has also contributed to increased demand for luxury goods including highly-valued wildlife products used for ornaments, traditional medicine, and foods served in specialty restaurants. In response to these trends, the Government of Vietnam has strengthened the policy and legal framework and prioritized actions to address wildlife protection in recent years. However, overlaps and inconsistencies among various laws and regulations have created serious implications to the protection of threatened species. In addition, the effectiveness of enforcement operations is affected by insufficient coordination and information sharing within and between agencies. Also, there remain major challenges in the processing of cases, prosecution of documented offenses, and levying of appropriate penalties due to lack of adequate knowledge and clear guidance on the application of the key legislation related to the protection of threatened species. Clear technical and regulatory guidance is much needed not only for enforcement authorities, but also for the private sector, in particular for wildlife conservation facilities which are intended for ex-situ conservation of threatened species.

Figure 1. Theory of Change

- Given the limited size and scope, the proposed Project will focus on the short-term interventions related to reducing poaching, trafficking, and illegal trade, which aim to build an enabling framework for increasing impacts on reducing poaching, trafficking, and demand for illegal wildlife products. These short-term interventions include reducing the complexity of and filling the gaps in the legal framework; building capacity to improve the effectiveness of conservation and law enforcement; awareness raising and education targeting civil servants for spill over impacts; and enhancing partnerships and collaboration across agencies, sectors, and national boundaries for sustainable management of threatened wildlife. These interventions lead to amended legal and regulatory framework which provides clear guidance for conservation and law enforcement; increased competency in the application of laws and regulations; and increased awareness to reduce consumption of illegal wildlife products. These will ultimately act collectively to both increase the costs of participation in wildlife crimes and increase equitable sharing of the benefits from natural assets under the national policy and regulatory framework and the framework of CITES. This approach is critical for creating the fundamental socio-economic conditions necessary for the long-term persistence of biodiversity, which is consistent with the objectives of the CBD.

- Reduce poaching in Vietnam: The Project aims at creating an enabling environment to address poaching of wildlife from three different angles: strengthening the legal and regulatory framework; building capacity in conservation and law enforcement, especially at the local level; and enhancing intra- and inter-agency coordination and information sharing. The GWP asserts that reducing poaching is urgently needed to ensure that viable populations of species are maintained. Reducing poaching will require enhancing anti-poaching tracking and intelligence operations, through the development, training and education of tactical tracker and intelligence units in all protected area landscapes where much important biodiversity and known threatened species are found. Criminals need to be punished and poaching needs to become very difficult and costly. While the larger associated  parallel co-financing from Saving Species project supported by USAID (US$9.9 million) will take up the capacity building in intelligence operations, the proposed Project will complement with a focus on improving the legal and regulatory framework and its application on law enforcement and conservation activities on the ground and enhancing anti-poaching tracking.

- Reduce trafficking along the supply chain: Reduce trafficking requires strengthening anti-smuggling, customs control and container customs search programs, and especially control of small airstrips, and boats in ports and where rivers enter the sea, along with the use of controlled deliveries and DNA and other isotope markers to identify the source of wildlife, the criminal networks and buyers. It also requires strengthened efforts against corruption at all levels, including in the military, the police, the wildlife enforcement communities and other governmental agencies, using trans-boundary criminal intelligence units and further improving training and organization of specialized, well-paid and strongly-mandated anti-poaching units working inside and outside protected areas with both intelligence and enforcement operations. Other interventions include strengthening international interagency collaboration to fight organized wildlife crime by supporting programs that target the enforcement along the entire supply chain. Again, the complementary Saving Species project will focus on these interventions to address trafficking. The proposed Project will concentrate its effort on supporting inter-agency coordination and information sharing as well as the international platform for collaboration to fight against illegal wildlife trafficking.

- Reduce demand in Consumer countries: This requires a combination of strict enforcement for those trafficking wildlife and wildlife products at the end of the value chain, and conducting targeted awareness raising campaigns among end-users across the world, but particularly in relation to rhino and elephant products in East and Southeast Asia, of the devastating impacts of their present demand. The campaigns would need to dissuade consumers from purchasing illegally traded wildlife. Such campaigns, though often expensive and time-consuming, can be successful, as demonstrated by the significant shift in consumer opinion in Asia on the shark fin trade. It is important to note that this intervention by itself has not been sufficient to stem illegal killing of sharks. Criminals will continue to kill wildlife and traffic in contraband as long as the potential profits remain so high. It is critical to engage individual consumers in key consuming nations such as Vietnam by educating them about the impacts of wildlife trafficking, on people as well as wildlife, and encouraging them to examine their purchasing patterns. It is also important to recognize the complexity of the supply-demand relationship, since effective anti-poaching work in some areas may curb overall supply and drive prices up, increasing the pay-off for remaining poachers, pointing to the centrality of simultaneous demand reduction in key markets. In spite of a recent market survey indicating reduced prices in ivory in China, support to demand reduction activities is still critical to drive down consumption of illegal wildlife products in China and other major consumer countries. As long as there is market demand for illegal wildlife products, and it is economically viable to trade such products (i.e., market participants realize greater rewards than their costs and perceived risks), poaching of threatened species will continue.

- Studies suggest that civil servants are one of the major consumer groups of wildlife products in Vietnam. There have been various communications and awareness raising efforts targeting consumers and the private sector, while a focus on civil servants have not been paid due attention. The proposed Project will target its awareness raising campaigns on civil servants who are small in number, quite homogenous, can be reached easily through the Government communications systems, and is under greater public and media supervision. Civil servants also have strong influential power with spill over impacts onto other target groups in the society (the private sector, youth, community, etc.). The campaign strategy will consider incentives for civil servants to stop wildlife consumption and become role models to the public as well as educational information on wildlife crimes and potential punitive consequences of such crimes.

CBD Strategy and Action Plan – Vietnam.

Drury, R (2011) Hungry for success: urban consumer demand for wild animal products in Vietnam. Conservation

and Society 9: 247–257. Shairp, Rachel and Verissimo, Diogo and Fraser, Iain and Challender, Daniel and MacMillan, Douglas C. (2016) Understanding Urban Demand for Wild Meat in Vietnam: Implications for

Conservation Actions. PloS One, 11 (1). pp. 1-14. ISSN 1932-6203.

There is an exception for six national parks of special importance and/or with interprovincial trans-boundaries, for which management responsibility remains entirely within MARD.

Decree 32 on the management of endangered, precious, and rare forest fauna and flora species.

Commercial breeding facilities are regulated under Decree 82 on the management of expert, import, re-export and introduction from the sea, transit, breeding, rearing and artificial propagation of endangered, precious and rare wild animals and plants.

SMART provides timely and accurate information on where, how and by whom poaching, illegal logging and other direct threats to biodiversity are occurring. It allows for the collection of up-to-date field and intelligence data, and enables rapid feedback and communication between protected area managers and frontline enforcement staff.

Piloted in 10 Protected Areas in 2013, SMART has been applied in 26 PAs as of 2016 and has demonstrably improved anti-poaching detection, as well as documentation of wildlife trade “hotspots”. The tool has proven to be relatively easy to use and inexpensive, and can be well integrated into patrolling plans. However, there is an urgent and timely need to continuing applying the tool in other PAs to maximize patrol effectiveness and monitor poaching networks at larger geographic scales.

These are defined by Decree 160. Initial assessments suggest focus may include terrestrial turtles, gaurus and Edward’s pheasant.

Rebecca Drury, Hungry for Success: Urban Consumer Demand for Wild Animal Products in Vietnam. Conservation and Society 9(3): 247-257, 2011