REQUEST FOR BIODIVERSITY enabling activity

Proposal for Funding Under the GEF Trust Fund

part i:  project IDentifiers

| EA Title: | National Biodiversity Planning to Support the implementation of the CBD 2011-2020 Strategic Plan in Zimbabwe |  |  |
| --- | --- | --- | --- |
| Country(ies): | Zimbabwe | GEF Project ID: | t.b.d. |
| GEF Agency(ies): | UNDP | GEF Agency Project ID: | 4845 |
| Other Executing Partner(s): | Ministry of Environment and Natural Resources Management | Submission Date: | February 3, 2012 |
| GEF Focal Area (s): | Biodiversity | Project Duration (Months) | 36 |
| Check if applicable: | NCSA NAPA | Agency Fee ($): | $22,000 |

- EA framework

### EA Objective: To integrate Zimbabwe’s obligations under the Convention on Biological Diversity (CBD) into its national development and sectoral planning frameworks through a renewed and participative ‘biodiversity planning’ and strategizing process, in a manner that is in line with the global guidance contained in the CBD’s Strategic Plan for 2011-2020.

| ### EA Component | ### Grant Type | ### Expected Outcomes | ### Expected Outputs | ### Grant Amount ### ($) | ### Confirmed Co-financing ### ($) |
| --- | --- | --- | --- | --- | --- |
| 1) Stocktaking and national target setting | TA | - By end of 2012, a multi-sectoral/multi-stakeholder working group is established and it completes the stock-taking exercise. - By October 2012, national targets in response to the global Aichi Targets are developed. | 1.1 Review and stocktaking of products and results from previous biodiversity planning processes at the national level are carried out in participative manner. 1.2 In response to the global Aichi Targets, national biodiversity targets are developed in a manner that is attuned to Zimbabwe’s reality. 1.3 The achievement of national targets, developed in line with the global Aichi Targets, is duly monitored during the project duration and beyond, and this is reported upon to the CBD through national reports and other means. 1.4 In an iterative manner, Zimbabwe taps into useful information on, and participates into, global networks and initiatives on biodiversity data and indicators (such as the Biodiversity Indicators Partnership, Global Biodiversity Information Facility and the World Conservation Monitoring Centre, the Global Environment Outlook portal, among other relevant ones). | 34,000 | 79,240 |
| 2) NBSAP update | TA | - By early 2014, Zimbabwe’s NBSAP is fully updated, and it is in line with the guidance in the CBD Strategic Plan (2011-2020) and has been submitted to the CBD COP | 2.1 A National Biodiversity Strategy and Action Plan (NBSAP) for Zimbabwe, anchored into national development frameworks, is revised and/ updated, in a manner that is participative, widely disseminated and fully integrates new aspects of the CBD strategic plan, such as: (i) mainstreaming; (ii) the valuing of ecosystem goods and services; and (iii) the incorporation of challenges and opportunities linked to ecosystem-based adaptation and resilience, including the integration of a climate-ready network of protected areas into climate resilience, mitigation and adaptation plans for the NBSAP. This will include, inter alia, the following strategic studies: - Ecosystem Valuation in Zimbabwe - Advances in Sectoral Mainstreaming of Biodiversity in Zimbabwe 2.2 The updated and fully endorsed NBSAP for Zimbabwe is submitted to the CBD within the deadline set by the COP. 2.3 Impacts of climate change impacts on biodiversity are identified and adaptation measures mainstreamed into NBSAP, through a strategic study with the following theme: - Exploring and costing options for Ecosystem-based adaptation to climate change through the development of a robust PoWPA Action Plan and a plan for sustainable land use in Zimbabwe | 100,000 | 115,240 |
| 3) National frameworks for NBSAP implementation, CDB reporting and exchange mechanisms |  | - By 2013, complete the updating and improvement of national clearinghouse mechanisms - By 2014, complete plan for implementing the NBSAP, including capacity, technology and finance needs assessment | 3.1 National framework for NBSAP implementation is in place and includes: (i) institutional leadership for implementation is established and strategic partnerships forged (nationally and internationally); (ii) a costed and prioritized Action Plan is appended to the NBS; (iii) needs assessments on capacity, technology and finance are carried out; and (iv) a strategy for resource mobilization for the implementation of the NBSAP is produced and includes a baseline assessment of existing biodiversity finance. 3.2 An effective, user-friendly and easily updatable country-driven CHM site is developed; it is linked up to the CBD’s global CHM networks and to other information and knowledge exchange network on biodiversity. 3.3. Immediate CBD reporting obligations are met by Zimbabwe in a timely manner, in particular the Fifth National Report to the CBD by 31 March 2014. | 68,000 | 75,240 |
| Subtotal |  |  |  | 202,000 | 269,720 |
| EA Management Cost |  |  |  | 18,000 | 64,280 |
| Total EA Cost |  |  |  | 220,000 | 334,000 |

a   List the $ by EA components.

- Co-financing for the EA by source and by name

| Sources of Co-financing | Name of Co-financier | Type of Co-financing | Amount ($) |
| --- | --- | --- | --- |
| National Government | Ministry of Environment and Natural Resources Management | In-Kind | 134,000 |
| GEF Agency | UNDP | Grant | 200,000 |
| Total Co-financing |  |  | 334,000 |

- Grant  Resources Requested by Agency, Focal Area and Country

| GEF Agency | Type of Trust Fund | Focal Area | Country Name/ Global | (in $) |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | Grant Amount (a) | Agency Fee (b) | Total c=a+b |
| UNDP | GEF TF | Biodiversity (Focal Area Set Aside) | Zimbabwe | 220,000 | 22,000 | 242,000 |
| Total Grant Resources |  |  |  | 220,000 | 22,000 | 242,000 |

- EA Management Cost

| ### Cost Items | ### [GEF only] Total Estimated Person Weeks/Months | ### Grant Amount ($) | ### Co-financing ($) | ### EA Total ($) |
| --- | --- | --- | --- | --- |
| ### Local consultants* | 0 | 0 | 58,032 | 58,032 |
| ### International consultants* | 0 | 0 | 0 | 0 |
| ### Office facilities, equipment, vehicles and communications* |  | 12,600 | 6,000 | 18,600 |
| ### Travel* |  |  | 0 | 0 |
| ### Others** | Bank charges, exchange rate fluctuations and miscellaneous expenses. | 2,400 | 248 | 2,648 |
|  | Audit | 3,000 | 0 | 3,000 |
| Total |  | 18,000 | 64,280 | 82,280 |

*   Details to be provided in Annex A.     ** Other items to be clearly specified.

Additional information for Table D, if applicable:

Refer to the Total Budget and Workplan in Annex C for a thorough break-down of above costs for executing the project on the ground. These costs will be shared by UNDP and the GEF in a balanced way. The co-financing will pay for: - $58k for the National Project Assistant over three years - $3k for security services - $3k for refurbishing office space availed by government in order to make premises functional and secure - $248k for miscellaneous expenses. The GEF is, in turn, requested to finance: - $9.6k for the acquisition of IT equipment for project staff and consultants. - $3k as a contribution to the costs of utility bills in government premises. - $3k for the project audit - $2.4k for bank charges, exchange rate fluctuations and miscellaneous expenses.

part ii:  Enabling Activity JustiFication

A. Enabling Activity Background and Context

Zimbabwe is endowed with a rich diversity of life forms. At species level, the country supports an estimated 4,440 vascular plant species, 214 of which are endemic, 672 bird species, 450 of which breed in Zimbabwe, though none are strictly endemic, 196 mammal species, 156 reptile species, 57 species of amphibians, 132 fish species and uncounted numbers of species in other groups. There are 5 main ecoregions within Zimbabwe, including the Kalahari, Central, Zambezi, Save Limpopo, and Eastern Highlands, ranging in altitude from 687 m to 1500 m, and in rainfall from 400 mm annually to 740 mm. Zimbabwe’s biodiversity has particular importance to subsistence and indigenous communities; of the more than 6000 plant species, about 500 are used for medicinal species, and about 500 are listed as under threat of extinction. In the past, Zimbabwe’s biodiversity has been central to its economy – nature-based tourism has been one of the most important sectors of the economy. Even though tourism rates have plummeted by more than 75% since 2000, tourism continues to be a main economic driver, second only to mining. With a population of 12.5 million, and with a Human Development Index of .14, Zimbabwe has been classified as the least developed country in the world. The life expectancy has dropped from 60 to 42 since 1990 (among the lowest in the world), and more than 70% of the country faces high to extreme food insecurity. Zimbabwe has faced an extended period of hyperinflation, political instability and drought. However, in November 2010, the IMF described the Zimbabwean economy as "completing its second year of buoyant economic growth after a decade of economic decline", citing efforts to strengthen policies as one of the main reasons for the economic growth. There are numerous threats to biodiversity in Zimbabwe. These include: - Deforestation and land degradation: Excessive harvesting for both domestic and commercial use, as well as conversion of forest areas to agricultural land, has resulted in deforestation in forest reserves. The opening up of forests for agricultural expansion is the major reason for loss of forest biodiversity and has resulted in a 12% increase of agricultural land. The growth of the tobacco industry has also increased the demand for fuel wood for tobacco curing. Rapid deforestation in communal areas and other human settlements has also led to a drastic drop in populations of the medicinal plant species. - Wildfires and arson: The frequent occurrence of wildfires throughout the country now stands out as one of the major threats to biodiversity. The problem is mainly pronounced during the dry season when the temperatures are high and the vegetation is flammable. The occurrence of wildfires has impacted negatively on the grazing land for both domestic and wildlife species. Fires have also destroyed large tracts of commercial timber especially in the Eastern Highlands of the country. As much as 1,000,000 ha of woodlands and forests, bushlands, grazing lands and arable lands have been affected in recent fires. - Loss of habitat: Human encroachment, fragmentation of ecosystems, logging, mining and agriculture pose threats to ecosystems in the wildlife estate. The loss of habitat (drying up of rivers and surface waters, degraded land) cover has impacted negatively on aquatic life, terrestrial biodiversity and productivity of both livestock and crops. - Mining and road construction: Mining activities have become a major threat to biodiversity. Open cast methods involve stripping large pieces of land to remove the soil, which disturbs the natural environment surrounding the mines. It removes vegetation and takes away land that could be used for agriculture. Road construction, which involves the opening up, of new land has also impacted negatively of biodiversity. Large tracts of land are opened in remote areas, which are hosts to various species of wildlife. This has resulted in the fragmentation of ecosystems and habitats, obstructing migratory routes to breeding and feeding grounds used by wildlife - Climate change: Although the impacts of climate change and biodiversity have not been fully studied in Zimbabwe, evidence on the ground shows a decline of agro-biodiversity species after droughts and floods. A number of crop species are known to be extinct due the devastating impacts of droughts and floods. The drying up of wetlands and other water bodies during the drought years has also had negative impacts on the aquatic biodiversity. - Invasive species: Invasive alien species (IAS) have affected native biodiversity in almost every type of ecosystem throughout the country. As one of the greatest drivers of biodiversity loss, they pose a threat to ecosystem integrity and function and therefore, to human well‐being. While only a small percentage of organisms transported to new environments become invasive, their negative impacts on food security, plant, animal and human health and economic development can be extensive and substantial. Invasive alien species also exacerbate poverty and threaten sustainable development through their impact on agriculture, forestry, fisheries, human health and on wild biodiversity, which if often a basis of livelihoods of people in Zimbabwe. A specific example of the threat to livelihoods from invasive species is the reported deaths of fish (a critical food source for many) from the proliferation of the water hyacinth in the Lake Chivero and other water bodies throughout the country. - Pollution: Pollution caused by wide scale application of pesticides and herbicides to protect crops and control pests, such as tsetse flies disrupt natural food chains and negatively impact biodiversity. Widespread use of pesticides is a threat to wildlife, ecosystem structure and function, and human health. Of great concern are the organ chlorine pesticides that are taken by living organisms from water. They are very stable in the environment, and because of their persistence they can accumulate in fish, birds and other animals in ascending trophic levels in food chain. Pollution of water is exacerbated by direct discharge of raw municipal sewerage into public streams, frequent sewer bursts in some urban centers and untreated effluent from industries and mining. One of the major pollution indicators is the proliferation of aquatic invasive alien species, such as water hyacinth, that results from excessive eutrophication. Agencies responsible for managing biodiversity The Government of Zimbabwe is responsible for managing biodiversity through the Ministry of Environment and Natural Resources Management. In addition, related agencies also have specific areas of biodiversity-related responsibilities at national levels (e.g., the Zimbabwe National Water Authority) and local levels (e.g., Local Environmental Action Planning committees). There is also a strong network of international NGOs within Zimbabwe, (e.g., IUCN, The Nature Conservancy, and African Wildlife Foundation among others) who contribute resources and expertise for managing biodiversity. Protected Areas Zimbabwe has 249 protected areas, covering 15% of the land area. In addition, another 17% of the land area is included in traditional conservancies, tribal, communal and private lands. The vast majority (about 60%) of Zimbabwe’s protected areas are in the northwest corner of the country along the border with Zambia and Botswana, and in the southeast corner (about 30%) bordering South Africa and Mozambique. There are a few scattered protected areas in the central part of the country. Some work has been completed on an ecological gap assessment in partnership with BirdLife International (i.e., a survey of important bird areas), and there has been tremendous progress in developing transboundary protected areas (there are 6 transfrontier conservation areas). However, much remains to be done to fully implement the CBD Programme of Work on Protected Areas (PoWPA), including the improvement of distribution and representativeness of protected areas across the country, the development of a sustainable finance plan and finance mechanisms, the assessment of management effectiveness, the development of management plans including for climate change adaptation and resilience, effective monitoring and research, and comprehensive capacity needs assessments for protected areas. Because of the substantial number and coverage of protected areas within Zimbabwe, and the urgent need to improve management, and the potential of these protected areas in enabling climate resilience and adaptation, this proposal emphasizes the development of a climate-resilient protected area network. Barriers to effective implementation of the CBD Strategic Plan: The barriers are essentially the same as those identified in the 4th National Report: - Limited implementation and enforcement of policies due to inadequate human and financial resources. - Weak environmental information management systems, particularly for protected areas - Lack of institutional coordination within government departments, inter‐ministerial agencies, combined with the absence of a decentralized institutional structure to manage natural resources, and with the absence of effective communication tools and mechanisms to reach multiple stakeholders and sectors - Low levels of scientific expertise in specialized area such as taxonomy, GIS, Remote sensing and ecological land classification. - Increased pressure on natural resources due to human activities and natural disasters, climate change, droughts and floods, pests - Limited appreciation of social and economic value of biodiversity at all levels, and traditional knowledge not well documented - Inadequate specialized skills in policy analysis and harmonization of legal instruments; - Inadequate skills of local communities in sustainable management and utilization of biological resources. One of the priorities emerging from the 4th National Report is the need to better mainstream biodiversity into natural resource sectors. In particular, the report identifies the need to mainstream biodiversity with the following sectors: wildlife-based land reform policy, forest-based land reform policy, national agricultural policy, national energy policy, water and sanitation policy, environmental education policy, and poverty reduction programs, among others. Although Zimbabwe has not adopted a Poverty Reduction Strategy Programme (PRSP) a number of projects highlight the need for crosscutting poverty reduction activities. One of the key initiatives on poverty reduction is the community based natural resource management concept where communities are encouraged to conserve, sustainably use and equitably share the benefits derived therein. A successful case is the CAMPFIRE programme under which the rural people are granted the authority to manage their wildlife and other natural resources for their own benefit. A major component of this proposal is seeking ways to mainstream biodiversity into poverty alleviation and development programs. - National Reporting to CBD. Reports; Date of Submission to CBD Secretariat; Current Status*; Comments. National Biodiversity Strategy and Action Plan; 05/22/2000; Submitted. Revision of NBSAP; Not submitted; Not yet started; Funding being applied for under this grant. 1st National Report; 02/10/1998; Submitted. 2nd National Report; 07/22/2003; Submitted. 3rd National Report; 10/18/2005; Submitted. 4th National Report; 12/16/2010; Submitted. - Capacity Needs Assessments carried out YES NO. Start Date (31-01-2003):; End Date (30-09-2005):. Please list all of the CBD Program of Work and cross-cutting themes that were addressed in the Biodiversity Enabling Activities Capacity Needs Assessments:; Dates. - Assess inventory, databases and monitoring programmes in the Natural Resources, Wildlife, Forestry and Agricultural Sectors needed for key species at the genetic, species and ecosystem levels.; 1998– 2000. - Assess the adequacy of programmes/institutions focusing on developing incentives and reward systems for the sustainable use of biodiversity.; 1998– 2000. - Assess the capacity in terms of skills, equipment, financial and other resources including competencies in taxonomy of institutions and other stakeholders involved in biodiversity inventory and monitoring.; 1998– 2000. - Assess the effectiveness of marketing systems and the adequacy of markets for biodiversity products and capacity needed in the private sector to enhance this effectiveness.; 1998– 2000. - Assess the capacity of mechanisms that promote access to genetic resources and review the mechanisms in place for promoting access to genetic resources and benefit sharing.; 1998– 2000. - Assess the capacity to build legislation and policies for access to genetic resources and benefit sharing.; 1998– 2000. - Cross-cutting capacity needs assessments for the implementation of the Rio Conventions See e.g. http://ncsa.undp.org/report_detail.cfm?ProjectId=241&statusId=1; 2003- 2009. Under the Fourth National Report to the CBD: - Agricultural Biodiversity - Forest Biodiversity - Access to Genetic Resources and Benefit-sharing - Biodiversity for Development - Invasive Alien Species - Protected Areas - Sustainable Use of Biodiversity - Inland waters; 2008-2010. 3) Clearing House Mechanism (CHM) established?; YES NO. CHM link(s):; N.A... Is the CHM website maintained up to date?; YES NO. How many people currently operate and maintain the national CHM?; N.A.. How many people visited the national CHM website in the past 12 months?; N.A.. Note: Zimbabwe intents to create an effective, user-friendly and easily updatable country-driven CHM site, one which is linked up to the CBD’s global CHM networks and to other information and knowledge exchange network on biodiversity..

B. Enabling Activity Goals and Objectives

The Baseline Project: The Current NBSAP and the new CBD Strategic Plan The new CBD Strategic Plan, adopted at CoP-10 in 2010 in Nagoya, clearly addresses the need for updating NBSAPs, stating in Target 17 that “By 2015, each Party has developed, adopted as a policy instrument, and has commenced implementing an effective, participatory and updated national biodiversity strategy and action plan.” The strategic plan also covers a range of issues that will need to be incorporated into the revised NBSAPs, including guidance to countries to: a) fully realise the value of biodiversity and ecosystem services, and incorporate these values into national and local development and poverty reduction strategies (Targets 1 and 2); b) increase the global terrestrial protected area estate from 12% to 17% and the marine estate from 6% to 10% (Target 11); c) restore and safeguard key ecosystem services, especially for water, health and livelihoods (Target 14); and d) strengthen ecosystem resilience to climate change and promote ecosystem-based approaches to climate change adaptation and mitigation (Target 15). The most recent NBSAP for Zimbabwe was completed in 2000. This version of the NBSAP does not include the following elements of the CBD Strategic Plan’s Aichi Targets: - A plan for integrating the value of biodiversity into national and local development and poverty reduction strategies and planning processes and are being incorporated into national accounting, as appropriate, and reporting systems (Target 2) – the 4th National Report highlighted the need to undertake this study, citing as an urgent priority the need to mainstream biodiversity programs into national development strategies and plans. Some work has been done on valuation in the outdated NBSAP (e.g., on non-commercial forestry values), but there are many major gaps in assessing the values of biodiversity. The NBSAP also recognized that the “limited appreciation of the importance and contribution of biodiversity to the national economy and to local communities by policy makers” was a major impediment. - A plan for creating incentives and removing harmful subsidies (Target 3) – the 4th National Report identified the lack of expertise in developing appropriate incentives and policies as a major barrier to implementing the Strategic Plan. The NBSAP identifies inadequate incentives for some local communities and individuals to undertake biodiversity conservation and sustainable use initiatives in both protected and non-protected areas as a priority barrier for implementing the Strategic Plan. - A plan for fully implementing the Programme of Work on Protected Areas, including increased protection and landscape/seascape connectivity (Target 11) – the existing NBSAP does not adequately address issues related to the establishment of an effective protected area network as outlined in Target 11, nor does it address the need to strengthen ecosystem resilience and the contribution of biodiversity to carbon stocks, including the restoration of at least 15 per cent of degraded ecosystems (Target 16). Both the NBSAP and the 4th National Report identify the need to better account for, manage and plan for climate resilience and adaptation as a major priority. - A plan for restoring and safeguarding ecosystems that provide essential services, including services related to water, and contribute to health, livelihoods and well-being (Target 14) – the issue of ecosystem-based livelihoods is critical in Zimbabwe, yet this issue is not adequately addressed in the existing NBSAP. - A plan to improve the status of biodiversity by safeguarding ecosystems, species and genetic diversity through strengthening ecosystem resilience to climate change (Target 16) and the development of a comprehensive plan for sustainable production. (Target 4) - A plan to enhance the benefits to all from biodiversity and ecosystem services through the operationalization of the Nagoya Protocol on Access and Benefit Sharing which is consistent with national lesgislation (Target 16) and to harmonize it with Zimbabwe’s Statutory Instrument 6 of 2009 on access to genetic resources - A plan for the mobilization of financial resources for effectively implementing the Strategic Plan for Biodiversity 2011-2020 from all sources (Target 20) – neither the 4th National Report nor the NBSAP adequately address the issue of sustainable finance, and the NBSAP identifies the “limited financial base and institutional capacity to facilitate the formulation, implementation and monitoring of biodiversity projects at the local level” as a major barrier to effective implementation of the Strategic Plan. Proposed Response and Rationale: The new generation of BD EA. This project seeks to fully incorporate the above issues into the NBSAP. This ‘new generation’ of NBSAP will help set a regional standard of excellence by creating a national road map for achieving the Aichi Targets. Special emphasis will be placed on mainstreaming biodiversity into development plans, incorporating protected area networks and sustainable production systems into ecosystem-based climate adaptation and resilience plans, and creating sustainable finance for biodiversity conservation through the full valuation of key ecosystem services. Alignment with Focal Area Outcome(s): BD5 Objective: Integrate CBD Obligations into National Planning Processes through Enabling Activities (herein serving as the ‘Project Development Goal’): Focal Area Outcome 5.1: Development and sectoral planning frameworks at country level integrate measurable biodiversity conservation and sustainable use targets. The Project Objective is: To integrate Zimbabwe’s obligations under the Convention on Biological Diversity (CBD) into its national development and sectoral planning frameworks through a renewed and participative ‘biodiversity planning’ and strategizing process, in a manner that is in line with the global guidance contained in the CBD’s Strategic Plan for 2011-2020. This will be achieved through the following Outcomes (corresponding to components described in detail below): - Outcome 1 – A participative stocktaking exercise on biodiversity planning takes place and national biodiversity targets are developed in response to the global Aichi Targets - Outcome 2 – The NBSAP is revised/updated and it fully integrates new aspects of the CBD strategic plan, such as mainstreaming and anchoring the implementation of the plan into national development frameworks, valuing ecosystem services and promoting ecosystem-based adaptation and resilience - Outcome 3 – National frameworks for resource mobilization, Convention reporting and exchange mechanisms are established and strengthened Refer to Part I, Table A and to the next section for more details. How the project plans to build national capacity Enabling Activities are considered foundation activities within the framework of the GEF. The ultimate goal of Biodiversity Enabling Activities is to build national capacity across the board for biodiversity management. The effective achievement of global biodiversity benefits depend on the development of national capacity for managing biodiversity. The more robust this capacity is in a given country, the more effective the national implementation of the CBD will be. This project will build national capacity in Zimbabwe in the following manner: Individual; Much of the work under this project will be carried out through working groups. This is an ideal forum for imparting knowledge among different individuals involved in biodiversity planning and in environmental matters in Zimbabwe in general. For many of the civil servants and NGO staff in Zimbabwe, the opportunity for working within a project like this is a form of training. Furthermore, consultation, participation and ownership are guiding principles of biodiversity planning processes. These are part and parcel of this proposal.. Organizational; UNDP’s approach to Biodiversity Enabling activities in GEF5 goes beyond the mere production of national reports and strategies to the CBD and the development of a website for the CHM. Rather, it is concerned about the developing a permanent framework for reporting to the CBD and for maintaining the CHM interesting and up to date. This implies institutionalizing the capacity for eventually achieving this with as little external assistance as possible. Given the ambitious targets of the CBD Strategic Plan (2011-2020), it is recognized that actions to engage external assistance and retain national are in the meanwhile needed. This will be availed through the project. In particular, the following activities are specially targeted at building organizational capacity: - Taking stock of the NBSAP and identifying barriers to its implementation - Setting targets and priorities - Developing implementation plans for the revised NBSAP - Assessing and strengthening capacity needs - Developing clearinghouse mechanisms - Developing a permanent framework for reporting to the CBD. Systemic; The approach that UNDP has developed for Biodiversity Enabling Activities in GEF5 is transformational with respect to systemic capacity elements (i.e. policy, economic, regulatory, and accountability frameworks within which organizations and individuals operate). The aim is to ensure that the objectives, targets and guidance from the CBD Strategic Plan (2011-2020) become fully anchored into national development frameworks. This will be achieved by the development of the following new aspects of the CBD strategic plan: (i) the valuing of ecosystem goods and services; (ii) mainstreaming; and (iii) the incorporation of challenges and opportunities linked to ecosystem-based adaptation and resilience. The knowledge developed through these activities will become part of Zimbabwe’s new NBSAP and will have a greater chance of influencing and even becoming policy. In particular, the following activities are specially targeted at building systemic capacity: - Assessing and integrating ecosystem services through economic valuation - Mainstreaming biodiversity into development policies, plans and practices and into sectoral plans and strategies - Incorporating climate change issues into NBSAPs - Integrating the NBSAP implementation plan with the CBD Programme of Work on Protected Areas implementation plan - Securing sustainable finance for NBSAP implementation - Monitoring and reporting on the status of biodiversity under climate change scenarios.

C. Describe the Enabling Activity and Institutional Framework for Project Implementation (discuss the work intended to be undertaken and the output expected from each activity as outlined in Table A ).

Detailed Description of Activities per Project Component / Outcome The description that follows has been organized in five modules (I -V), following the GEF’s guidance, but which for the sake of simplicity were grouped within the three already mentioned Components / Outcomes. The following are modules: Component; Outline of modules for NBSAP Revision and Related Activities; Indicative percentage of total GEF funding in the proposal. 1; I. Preparation; 7%. II. Setting national targets, principles, & main priorities of the strategy; 10%. 2; III. Strategy and action plan development; 50%. 3; IV. Development of Implementation plans and related activities; 17%. V. Institutional, monitoring, reporting and exchange; 17%. Component 1. Stocktaking and national target setting Key Outputs expected under this component includes the following: 1.1 Review and stocktaking of products and results from previous biodiversity planning processes at the national level are carried out in a participative manner. 1.2 In response to the global Aichi Targets, national biodiversity targets are developed in a manner that is attuned to Zimbabwe’s reality. 1.3 The achievement of national targets, developed in line with the global Aichi Targets, is duly monitored during the project duration and beyond, and this is reported upon to the CBD through the 5th national report, and through other means. 1.4 In an iterative manner, Zimbabwe taps into useful information on, and participates into, global networks and initiatives on biodiversity data and indicators (such as the Biodiversity Indicators Partnership , Global Biodiversity Information Facility and the World Conservation Monitoring Centre , the Global Environment Outlook portal , among other relevant ones). Key Outcomes: - By early 2012, a multi-sectoral/multi-stakeholder working group is established and it completes the stock-taking exercise. - By October 2012, national targets in response to the global Aichi Targets are developed. Key Products or publications resulting from activities: - Brief Review of the Biodiversity Planning Process in Zimbabwe - Biodiversity Targets for Zimbabwe: As part of national efforts to implement the CBD’s Strategic Plan for 2011-2020 Key Activities (I-II): - Preparing for the NBSAP revision - Taking stock of the NBSAP and identifying barriers to its implementation: This activity will focus on rapidly but accurately taking stock of existing plans, policies and practices, and of the root causes of biodiversity loss. Within country-specific contexts, the aim is not only to identify key threats, but to understand the drivers behind these threats, as well as the key aspects of the policy environment that are barriers and challenges to effective conservation/sustainable use. Based on existing studies and analyses, the emphasis of this activity will be on filling the key gaps in the existing NBSAP, understanding the primary drivers and root causes, and identifying the means of overcoming existing barriers and challenges. Besides initiating all key recruitments and procurement of goods and services, the Enabling Activity Coordinator will at this stage establish the National Target Setting and NBSAP Update Working Group. This group will congregate representatives from key stakeholder institutions and national specialists. It will and provide support to the project activities from beginning to end. More specifically, the Working Group (or several sub-working groups under it) will ensure the process of wide stakeholder engagement and provide technical and policy inputs to the NBSAP review process, including by providing data and information to and by commenting the key products emanating from the Enabling Activity. The Working Group will be an essential vehicle for ensuring that the Enabling Activity project is successful in building national capacity for biodiversity planning. - Stakeholder consultation and participation: This activity will focus on ensuring a robust consultative process that engages representatives from key sectors, administrative leaders, and traditionally under-represented groups. It will count on the support and inputs from the National expert Biodiversity Management and Consultation Processes and the Expert in Biodiversity Planning and Monitoring. The aim is to develop and sustain a participatory process in order to increase the likelihood of successful implementation of the NBSAP. This is especially important relative to the goals of mainstreaming biodiversity into national development plans, and promoting resilient landscapes that include production sectors. (Refer to Chapter ‘Stakeholder involvement in the implementation of the project’ further down for more information on the stakeholder engagement strategy.) - Setting targets - Setting targets and priorities: This activity focuses on setting specific, measurable, achievable and time-bound targets for the NBSAPs based on the global Aichi Targets, including targets on restoration of ecosystems, protected area coverage, overall biodiversity loss, and other aspects of the Strategic Plan. This activity, which is linked to priority setting among different aspects within the NBSAP, will be completed by CoP-11. The Expert in Biodiversity Planning and Monitoring will play a pivotal role in preparing the required document on national target-setting for the COP. The work performed within this activity will be important for shaping the work under Component 2 on the NBSAP update process. Component 2. NBSAP Update Key Outputs expected under this component includes the following: 2.1 A National Biodiversity Strategy and Action Plan (NBSAP) for Zimbabwe, anchored into national development frameworks, is revised and/ updated, in a manner that is participative, widely disseminated and fully integrates new aspects of the CBD strategic plan, such as: (i) mainstreaming; (ii) the valuing of ecosystem goods and services; and (iii) the incorporation of challenges and opportunities linked to ecosystem-based adaptation and resilience, including the integration of a climate-ready network of protected areas into climate resilience, mitigation and adaptation plans for the NBSAP. This will include, inter alia, the following strategic studies: - Ecosystem Valuation in Zimbabwe - Advances in Sectoral Mainstreaming of Biodiversity in Zimbabwe 2.2 The updated and fully endorsed NBSAPs for Zimbabwe is submitted to the CBD preferably within the deadline set by the COP. 2.3 Impacts of climate change impacts on biodiversity are identified and adaptation measures mainstreamed into NBSAP, through the following strategic study: - Exploring and costing options for Ecosystem-based adaptation to climate change through the development of a robust PoWPA Action Plan and a plan for sustainable land use in Zimbabwe Key Outcomes: - By early 2014, Zimbabwe’s NBSAP is fully updated, it is in line with the guidance in the CBD Strategic Plan (2011-2020) and has been submitted to the CBD COP Key Products or Publications resulting from activities - Second National Biodiversity Strategy and Action Plan for Zimbabwe - Sub-product 1: Study on Ecosystem Valuation in Zimbabwe - Sub-product 2: Study on Advances in Sectoral Mainstreaming of Biodiversity in Zimbabwe - Sub-product 3: Study on the Incorporation of Challenges and Opportunities linked to Ecosystem-Based Adaptation and Resilience within Zimbabwe’s protected area network In connection with the above outputs and deliverables, and as a result of the activities outlined below, Zimbabwe will strive to achieve the following outcomes vis-à-vis its CBD obligation and related processes: - By early 2014, Zimbabwe’s NBSAP is fully updated, is in line with the guidance in the CBD Strategic Plan (2011-2020) and has been submitted to the CBD COP. Key Activity (III) - Developing the NBSAP This step will seek to achieve the following: (i) Developing the strategy and actions to implement the agreed targets though national consultations; (ii) Application of the NBSAP to sub-national entities through sub-national and local consultations; and (iii) Sectoral integration including mainstreaming into development, poverty reduction and climate change plans through sectoral consultations. While the project will focus on updating all aspects of NBSAPs, it will place particular emphasis on those aspects that are both highlighted in the 2011-2020 CBD Strategic Plan. These include the following: - Assessing and integrating ecosystem services through economic valuation: The study on the Economics of Ecosystems and Biodiversity (TEEB) has drawn attention to the global economic benefits of biodiversity and ecosystem services and to the growing costs of biodiversity loss and degradation. However, Zimbabwe has not yet linked the value of biodiversity and ecosystem services to our own national development goals, including poverty eradication and sustainable livelihoods. Through this activity, Zimbabwe will be able to demonstrate the benefits and values of ecosystems and biodiversity at a national level, and better link ecosystems and priority sectors in national development plans, in order to guide allocation of resources. The aim is to strengthen the point that biodiversity not only underpins human well-being, but that biodiversity and associated ecosystem services can make a significant contribution to poverty reduction and economic development. By engaging national specialists and providing support from global specialists, hard economic data will be collected and processed at the country level to demonstrate the costs and benefits of investing in biodiversity management. Capacity to carry out the assessments and make important links to priority economic sectors will be simultaneously built within the country. The availability of essential data and the analysis will allow us to “make the case” for biodiversity and will facilitate the process of mainstreaming biodiversity into sectoral planning through concrete biodiversity valuation examples. - Specific steps in this process include: - Identify and assess the full range of values of key ecosystem services within the country, based on existing local, national, regional and global studies on the value of ecosystems and biodiversity, including: the national TEEB valuation results, the valuation of protected areas, any other national ecosystem services studies that have been conducted (e.g., water, carbon), and existing global and regional maps and overlays of key ecosystem services - Identify the implications of these services for different stakeholder groups within the country, including those who benefit from, and pay for, the maintenance of these ecosystem services, and those that degrade ecosystems through unsustainable use. - Estimate and demonstrate the value of key ecosystem services (using methods appropriate to each service), including the value of the ecosystem service in contributing to climate resilience, adaptation and mitigation; reducing poverty, and sustaining livelihoods. - Where appropriate, this activity will also identify potential means of capturing the value of targeted ecosystem services including through policies such as payments for ecosystem services and other positive incentives. The above sub-activity will involve a number of stakeholders in working groups who will discuss the above themes, avail data for national consultants to compile reports from. The production of a specific report (Study on Ecosystem Valuation in Zimbabwe) will be lead by an Output-based consultancy, whose TOR are described in Annex D. The mentioned study will be incorporated into Zimbabwe’s new NBSAP. - Mainstreaming biodiversity into development policies, plans and practices and into sectoral plans and strategies: Mainstreaming has been defined as the internalization of biodiversity conservation goals into economic and development sectors, policies and programs, such that they become an integral part of their functioning of these sectors. As a minimum, the following key stakeholders will be consulted in connection this sub-activity: Forestry Commission / Biodiversity Office, Forestry Commission (VEGRIS), Ministry of Water Resources Development and Management, Ministry of Environment & Natural Resources Management, Department of Livestock Production and Development, Min. Agriculture (DR&SS) National Herbarium & Botanic Gardens, Birdlife Zimbabwe, Environmental Management Agency, Parks & Wildlife Management Authority. - As part of this process, the project will focus on the following sectors: Agriculture Forestry Hunting Livestock Tourism Water - The Project will also focus on the following development areas / topics: Land-use management, including spatial and infrastructural development planning Development finance Poverty alleviation Rural development and livelihoods Food security Gender Traditional medicine - Specific steps in this process will include: - Forming partnerships between relevant stakeholders interested in biodiversity conservation issues and in development issues - Explicitly identifying key stakeholders’ interests, and desired outcomes - Identifying potential conflicts and trade-offs, and work towards mutually acceptable solutions, including strategies that serve mutually beneficial interests and achieve mutually beneficial outcomes - Embedding and institutionalizing these strategies in the institutions, policies, agreements, programs and mechanisms of each sector The above sub-activity will involve a number of stakeholders in working groups who will discuss the above themes, avail data for national consultants to compile reports from. The production of a specific report (Study on Study on Advances in Sectoral Mainstreaming of Biodiversity in Zimbabwe) will be lead by an Output-based consultancy, whose TOR are described in Annex D. The mentioned study will be incorporated into Zimbabwe’s new NBSAP. - Incorporating climate change issues into NBSAP: The previous NBSAP did not adequately address aspects of climate change. This activity will involve incorporating aspects of climate change into NBSAPs, including, for example: - identifying, protecting and appropriately managing areas important for carbon sequestration; - updating the country’s ecological gap assessment to include predicted future distribution of biodiversity under climate change scenarios; - assessing the impact of climate change on the functioning of ecosystem services, such as water, soil formation, carbon cycle, species refugia etc.; - identifying areas important for improving nature’s ability to adapt to climate change, such as altitudinal gradients and conservation corridors - identifying areas of particular importance for restoration in order to improve climate resilience, adaptation and mitigation; - explore the role of protected areas in incorporating climate change issues into NBSAP. The above sub-activity will involve a number of stakeholders in working groups who will discuss the above themes, avail data for national consultants to compile reports from. The production of a specific report relating to the last bullet (Study on the Incorporation of Challenges and Opportunities linked to Ecosystem-Based Adaptation and Resilience within Zimbabwe’s protected area network) will be lead by an Output-based consultancy, whose TOR are described in Annex D. The mentioned study will be incorporated into Zimbabwe’s new NBSAP. Component 3. National frameworks for NBSAP implementation, CDB reporting and exchange mechanisms Key outputs expected under this component includes the following: 3.1 National frameworks for NBSAP implementation is in place and includes: (i) institutional leadership for implementation is established and strategic partnerships forged (nationally and internationally); (ii) a costed and prioritized Action Plan is appended to the NBS; (iii) needs assessments on capacity, technology and finance are carried out; and (iv) a strategy for resource mobilization for the implementation of the NBSAP is produced and includes a baseline assessment of existing biodiversity finance. 3.2 An effective, user-friendly and easily updatable country-driven CHM site is developed; it is linked up to the CBD’s global CHM networks and to other information and knowledge exchange network on biodiversity. 3.3 Immediate CBD reporting obligations are met by Zimbabwe in a timely manner, in particular the Fifth National Report to the CBD by 31 March 2014. Key Products or publications (maybe combined into one): - Set of ‘straight-forward’ and feasible NBSAP implementation plans, which ensure the effective implementation of the Action Plan contained in the NBSAP - Fully functional CHM for Zimbabwe, based on best international practice on the matter In connection with the above outputs and deliverables, and as a result of the activities outlined below, Zimbabwe will strive to achieve the following outcomes vis-à-vis its CBD obligation and related processes: - By 2013, complete the updating and improvement of national clearinghouse mechanisms - By 2014, complete plan for implementing the NBSAP, including capacity, technology and finance needs assessment - Developing implementation plans This activity will focus on developing an overall plan for implementing the NBSAP. The Expert in Capacity building will play a key role in it, with assistance from the National Target Setting and NBSAP Update Working Group and the International NBSAP Advisor. The NBSAP implementation plan will include the following components: - Developing an overall implementation plan: The primary output of this activity is an overall implementation plan that delineates major steps, responsible parties, costs for main activities, expected outcomes and a timeline. - Integrating the NBSAP implementation plan with the CBD Programme of Work on Protected Areas implementation plan: Zimbabwe is in the process of finalizing its PoWPA implementation plan, and this step will ensure that our work on protected areas, including goals, objectives and next steps, are fully integrated into the NBSAP. Zimbabwe will place particular emphasis on those aspects of Target 11 from the CBD Strategic Plan, including the country’s plans for expanding protected areas, improving management effectiveness, sustainably financing protected areas, improving connectivity, and integrating protected areas into the wider landscape and seascape. The Strategic Study on the Incorporation of Challenges and Opportunities linked to Ecosystem-Based Adaptation and Resilience within Zimbabwe’s protected area network (under Component 2) will play a key role in providing the elements for the incorporation of a specific PoWPA Action Plan, with focus on ‘climate change & protected areas’ issues, into the NBSAP. - Securing sustainable finance for NBSAP implementation: Article 20 of the Convention mentions the need for Parties “to provide, in accordance with its capabilities, financial support and incentives in respect of those national activities which are intended to achieve the objectives of this Convention.” In the past few years, there has been a wide proliferation of innovative biodiversity finance mechanisms, such as payments for ecosystem services, conservation trust funds, biodiversity offsets and bio-carbon funding, among many others. Zimbabwe is still in the early stages of exploring these mechanisms. This activity will therefore focus on the following: - Identifying existing financial gaps for implementing the NBSAP - Identifying potential sources of revenue for filling these gaps - Assessing the feasibility for these revenue sources - Developing a detailed plan for operationalizing these revenue sources - Assessing and strengthening capacity needs: One of the primary areas of enabling activities is the assessment of capacity needs. The decisions at CoP-10 place new and ambitious demands on countries, including requirements to protect and sustainably manage their lands and water, to develop comprehensive plans that integrate climate change into their land use, development and sectoral plans and strategies, and to develop appropriate biodiversity and climate policies, laws and incentives. This activity will ensure that Zimbabwe develops a road map for strengthening these specific capacities. Building on existing capacity needs assessment, and using existing guidance, Zimbabwe will identify the following gaps, along with capacity-building strategies to fill those gaps. Based on the recent 4th National Report, those gaps are likely to include: - Limited implementation and enforcement of policies due to inadequate human and financial resources. - Weak environmental information management systems (e.g., protected areas). - Lack of institutional coordination within government departments, inter‐ministerial and across stakeholders. - Underdeveloped communication strategies and tools (ICT) in various sectors and stakeholders rendering communication at various levels and in particular local communities difficult. - Low levels of scientific expertise in specialized area such as taxonomy, GIS, Remote sensing and ecological land classification. - Increased pressure on natural resources due to human activities and natural disasters, climate change, droughts and floods, pests - Climate variability affecting ability of ecosystems to deliver goods & services - Traditional & local knowledge not documented - Limited appreciation of social and economic value of biodiversity at all levels - Inadequate specialized skills in policy analysis and harmonization of legal instruments; - Inadequate skills of local communities in sustainable management and utilization of biological resources; - Lack of decentralized institutional structures to manage natural resources - Limited resources to support the management of biological resources; - Lack of a sense of ownership among resource users affecting sustainable utilization; - Deficiencies in the legal, regulatory, and institutional framework. - Institutionalizing, monitoring and reporting - Monitoring and reporting on the status of biodiversity under climate change scenarios: Monitoring and reporting on the status of biodiversity is a key aspect of several Programmes of Work within the CBD. To date, efforts to monitor and report on the status of biodiversity have been sporadic and have typically not taken into full account the status and trends of biodiversity, the status of effective conservation, the contribution of ecosystem services (such as water and carbon), and the likely impacts of climate change on biodiversity and ecosystem services. Through this project, Zimbabwe will ensure that future monitoring and reporting on the status of biodiversity and ecosystem services is comprehensive, and fully incorporates climate change issues. The Expert in biodiversity Planning and Monitoring should prepare a robust framework that will allow Zimbabwe to carry out this sub-activity. The International NBSAP Advisor is also expected to assist with this from a technical point of view, based on guidance from the Ad hoc Technical Expert Group (AHTEG), under the purview of the CBD and UNFCCC conventions. - Developing clearinghouse mechanisms (CHM): Of the 90 countries that accessed funding under the Fourth National Report joint global project (UNDP-UNEP/GEF), only 44 had national CHM sites, and of those, 25 were kept up-to-date (data from 2010). At the same time that CHMs are largely out of date, reliance on digital information has increased exponentially. Zimbabwe is no exception. There is not currently a central clearinghouse for biodiversity information to share data either within or beyond the country’s borders. This is particularly important given the prominence of transboundary protected area and transfrontier conservation areas within Zimbabwe. This aspect of the project will help Zimbabwe develop an effective, user-friendly and easily-updatable CHM that will enable us to effectively share information nationally, regionally and globally. The project will also work in collaboration with the CHM of the Secretariat of the CBD, to ensure that lessons and information are disseminated globally. The Enabling Activity Coordinator will be primarily responsible for this activity. The International NBSAP Advisor can assist by helping the Coordinator tap into best international practices and examples on the matter. The National Target Setting and NBSAP Update Working Group can serve as a primary review forum for CHM content, though would be an element to add in their indicative TOR. - Developing a permanent framework for reporting to the CBD: Parties to the CBD committed to submitting a fifth national report by 2014. In this project, Zimbabwe will submit a 5th National Report that fully covers the NBSAPs, key changes in the status and trends in biodiversity status, threats and conservation, and will develop a long-term reporting framework that will enable us to better track changes over time. The Enabling Activity Coordinator will be primarily responsible for this activity. The International NBSAP Advisor can assist by reviewing the report for technical consistency, though would be an element to add in the Advisor’s in TOR. The National Target Setting and NBSAP Update Working Group can serve as a primary review forum for CHM content, though the group may need to be revived when the report is to be prepared. Collaboration and synergies with related initiatives There are a few projects under implementation in Zimbabwe that have relevance for the activities under this EA project. These are: - UNDP/GEF project – Coping with Drought and Climate Change (GEF Project ID 3156 – on-going) - WWF/IBRD/GEF project -- Hwange-Sanyati Biological Corridor (HSBC) Environment Management and Conservation Project (status under review) - Zimbabwe Big Cat Project - The Zambezi Heartland Project of the African Wildlife Foundation (AWF) - UNDP project: Strengthening national capacity for climate change in Zimbabwe - UNDP GEF Small Grants Programme The Enabling Activity Coordinator, the host institution and the UNDP Country Office will ensure that this Enabling Activity project can benefit from technical synergies, which will be fostered in the following manner: (1) Representatives and experts from the on-going biodiversity projects (HSBC, Zimbabwe Big Cat Project and the AWF one) will be invited to NBSAP workshops and to participate, where relevant, in specific working groups. The aim is to ensure that the knowledge on biodiversity that these projects have collected and are producing can be incorporated into the NBSAP. (2) The two climate change projects are particularly relevant to the work of incorporating climate change issues into NBSAP. The climate modelling and assumptions used in the Coping with Drought project, as well as the adaptation learning produced by the project will be particularly useful in that activity and in defining finding the relevant interface climate change-biodiversity that applies to Zimbabwe. As for UNDP capacity building project for climate change, the national negotiators and experts being trained will be invited to NBSAP workshops and to participate, where relevant, in specific working groups. Project implementation arrangement: The project will be implemented over a period of 3 years. The Ministry of Environment and Natural Resources Management (MENRM) is the government institution responsible for the implementation of the project and will act as the Executing Agency. UNDP is the Implementing Agency for the project and accountable to the GEF for the use of funds. The project is nationally executed (NEX), in line with the Standard Basic Assistance Agreement (SBAA, 1980) between the UNDP and the Government of Zimbabwe, and the Country Programme Action Plan (CPAP) for 2012-2015. The overall responsibility for the project implementation by MENRM implies the timely and verifiable attainment of project objectives and outcomes. MENRM/UNDP will provide support to, and inputs for, the implementation of all project activities. The MENRM will nominate a high level official who will serve as the National Project Director (NPD) for the project implementation. The NPD will chair the Project Steering Committee (PSC) and other relevant stakeholders, sectoral and working groups under the project, and be responsible for providing government oversight and guidance to the project implementation The NPD will not be paid from the project funds, but will represent a Government in kind contribution to the Project. The NPD will be technically supported by a project technical team as well as UNDP’s technical backstopping provided by the UNDP/GEF Regional Technical Advisor responsible for the project and the UNDP Environment Focal Point at the Country Office. Working closely with the MENRM, the UNDP Country Office (UNDP-CO) will be responsible for: (i) providing project assurance services to government (ii) recruitment of project staff and contracting of consultants and service providers; (iii) overseeing financial expenditures against project budgets approved by PSC; (iv) appointment of independent financial auditors and evaluators; and (iv) ensuring that all activities including procurement and financial services are carried out in strict compliance with UNDP/GEF procedures. A UNDP staff member will be assigned with the responsibility for the day-to-day management and control over project finance. A National Project Steering Committee (PSC) will be convened by the MENRM, and will serve as the project’s coordination and decision-making body (Project Board). The PSC will include representation of all the key project stakeholders. The PSC meetings will be chaired by the NPD. It will meet according to necessity, but not less than once in 6 months, to review project progress, approve project work plans and approve major project deliverables and any major changes to the project. The PSC is responsible for ensuring that the project remains on course to deliver products of the required quality to meet the outcomes defined in the project document. The day-to-day administration of the project will be carried out by a Project Coordinating Unit (PCU), comprising the National Enabling Activity Coordinator supported by a Project Assistant. Both will be located within the MENRM Biodiversity offices. The project staff will be recruited using standard UNDP recruitment procedures. The Enabling Activity Coordinator will liaise and work closely with all partner institutions to link the project with complementary national programs and initiatives. The Enabling Activity Coordinator is accountable to the MENRM, UNDP and the PSC for the quality, timeliness and effectiveness of the activities carried out, as well as for the use of funds. The Enabling Activity Coordinator will also be technically supported by contracted national and international consultants and service providers. Recruitment of specialist services for the project will be done by the Enabling Activity Coordinator, in consultation with the UNDP and the MENRM. Comparative advantage of UNDP in Zimbabwe with respect to this project: UNDP has historically been the largest GEF implementing agency in terms of assisting countries in undertaking biodiversity enabling activities, having assisted more than 100 countries with it through several projects. The GEF2 global project ‘Biodiversity Support Programme’ was jointly implemented with UNEP and has set the stage at the global level in the field of biodiversity planning among GEF eligible countries. Furthermore, UNDP assisted Zimbabwe in the preparation of its existing NBSAP, the second and third national reports. The Government of Zimbabwe has requested UNDP assistance in designing and implementing this project, due to UNDP’s track record in Africa. UNDP currently supports the development and implementation of GEF projects in numerous other contries throughout Southern Africa (e.g., Angola, Botswana, Namibia, Zambia, Mozambique, South Africa, among others). UNDP has an established national office in Harare with well-developed working relationships with the key stakeholders of the project. At least two professional staff are directly in charge of the Environment and Energy portfolio in the UNDP Country Office. The Office counts on support, operational and senior level staff, who ensure programmes are well run. The UNDP Country Office is currently in the process of Planning for a New UNDP/UNFPA Development Framework in Zimbabwe for the 2012- 2015 period. The project will also benefit from the presence of a UNDP/GEF Regional Technical Advisor dedicated to Biodiversity in Pretoria. UNDP also has extensive experience in integrated policy development, human resources development, institutional strengthening, and non-governmental and community participation. Project’s alignment with UNDP’s programme for Zimbabwe National Priority 4 and Outcome 4.1 of the Zimbabwe United Nations Development Framework (UNDAF 2012-2015) is on sound management of the environment, natural resources and land for promotion of sustainable development. The two impact indicators selected for measurement of UNDAF Outcome 4.1 and Millennium Development Goal 7 both relate to biodiversity i) ration of area protected to maintain biodiversity and (ii) proportion of land area covered by forest, which underscores the importance that Zimbabwe gives to issues of biodiversity. The UNDP Country Programme Action Plan (CPAP 2012-2015) under the CPAP Outcome: “Improved engagement and implementation of multilateral environment agreements” specifically mentions in Paragraph 4.38 that the UNDP will support the review and implementation of the national biodiversity strategy and action plan. Stakeholder involvement in the implementation of the project The stakeholder involvement element is embedded in the description of several activities within this proposal which will have a consultative and participatory character. A full stakeholder involvement plan will be developed in connection with the preparation of the UNDP Project Document that will operationalize this proposal at the level of UNDP, allowing Zimbabwe to access the funding. This plan will depart from the following indicative and non-exhaustive list: - Forestry Commission - National Biodiversity Forum - Ministry of Water Resources Development and Management - Ministry of Environment & Natural Resources Management - Department of Livestock Production and Development - Ministry of Agriculture - 5 Agricultural Research Stations under the Department of Research and Specialist Services - The National Herbarium & Botanic Gardens under DR& SS - Ministry of Higher Education - Ministry of Mines and Mineral Development - Ministry of Local Government - Ministry of Finance - Ministry of Economic Planning and Investment Promotion - Ministry of Tourism - Zimbabwe Tourism Authority - Environmental Management Agency - Rural District Councils - Parks & Wildlife Management Authority - Gene Bank of Zimbabwe - Birdlife Zimbabwe - IUCN - The Nature Conservancy - African Wildlife Foundation - COMMUTECH - ARIPO - WWF - ZERO- Environmental Regional Organisation - Environment Africa - Institute of Environmental Studies (IES) University of Zimbabwe - Community Management Programme for Indigenous Resources (CAMPFIRE) Association - Biotechnology Trust Zimbabwe More specifically, the participation of NGO and CSO stakeholders in the implementation of this project will be ensured at every stage. The government of Zimbabwe welcomes the efforts engendered by NGOs and CSOs active in the environment arena, noting that there is scope for strengthening current efforts. These organisations, either national or international, play an important advocacy and ‘watchdog’ role with respect to biodiversity. Many of them count on extensive networks of stakeholders and have produced research data that can help enrich the products that this project will be concerned with. These advantages will be explored in full during project implementation. In addition to NGOs and CSOs mentioned in the list further up, there are a number of smaller, community-based organisations (CBOs) that operate in Zimbabwe and one of them, Chibememe Earth Healing Association (CHIEHA) reached the finalist stage of the global UNDP Equator Initiative Prize. The CHIEHA representatives have participated in various national and international biodiversity forums and have represented indigenous groups at various global fora. The knowledge and experiences of such groups with global exposure will be tapped on in this project. The UNDP-GEF Small Grants Programme has been operational in Zimbabwe since the early ‘90s and has close partnerships with CBOs. The EA will depend on SGP to recommend CBOs with wide experience and good reputation to participate in this EA. The involvement of traditional leaders will be ensured as this has proved to be instrumental and effective in previous biodiversity initiatives such as the UNDP/GEF Traditional Medicinal Plants Project, WWF, CAMPFIRE, the UNDP/GEF Small Grants Programme and various CBNRM projects across the country including those supported by UNESCO and FAO. In addition to traditional leaders, the 57 rural district councils (RDCS) and technical staff of various Government Ministries stationed at district level are main stakeholders when it comes to formulation, monitoring and evaluation, approval of community initiatives as well as formulation of community by-laws. Their role will be to support and coordinate the implementation of the project at local level. Thus skills and experiences on effective engagement and participation of rural district councils, traditional leaders and communities in general abound in Zimbabwe and these will be utilised under this project. In the area of biodiversity, tourism operators and lodge owners largely constitute the private sector. Safari operators such as Malilangwe Trust and Matupula Safaris have experience working with rural communities in order to reduce pressure on the ecosystems from unsustainable agriculture. The Zimbabwe Tourism Authority (ZTA) responsible for regulating such operators will assist with identification of key private sector stakeholders. Private companies such as Nyaradzo Funeral Assurance and mining firms such as Mbada Diamonds that have strong corporate social responsibility policies and have worked with surrounding communities in implementing community environmental and infrastructure projects will be key partners in the implementation of this project. Gender marking Although women in Zimbabwe enjoy one of the highest literacy rates in Africa – as high as 80%, this has not translated into gender equality. Zimbabwe’s customary Family Code grants very few rights to women, and Zimbabwean women encounter significant discrimination in the matter of ownership rights, and women are often unable to secure bank loans without their husband’s consent. Yet, as the 4th National Report notes, women are the major custodians of biodiversity especially those residing in the rural areas. Understanding their roles in biodiversity conservation, use and management is a key strategy in the sustainable management of biodiversity. These considerations will be part and parcel of the updated NBSAP for Zimbabwe, stating e.g. with the stocktaking activity, which will highlight the lack of gender mainstreaming in previous biodiversity planning processes. During the project inception the mandatory UNDP gender marker will be applied. This requires that each project in UNDP's ATLAS system be rated for gender relevance. This will for example include a brief analysis of how the project plans to achieve its environmental objective by addressing the differences in the roles and needs of women and men. Furthermore, gender marking implies the production of the following data by the project's year 2 and by its end: - Total number of full-time project staff that are women - Total number of full-time project staff that are men - Total number of Project Board members that are women - Total number of project Board members that are men - The number jobs created by the project that are held by women - The number jobs created by the project that are held by men

D. Describe, if possible, the expected cost effectiveness of the project:

The proposed GEF project will ensure that a national strategy and action plan guide all stakeholders and partners in the conservation of biodiversity within Zimbabwe. This is one way of making optimal use of biodiversity planning resources. The project combines GEF funding with UNDP co-financing and a government investment in order to achieve the project objective. The government contribution to the project includes the staff time of a Project Director and of support staff at the MENRM a number of project activities, organization of and participation in Project Board meetings, plus other work related to reporting, work plan approvals, signing off on CDR reports, RDPs, reviewing APRs/PIRs. In addition, information and data will be collected and provided by the MENRM and other government agencies regularly over the 3 years of project duration. The cost-effectiveness of the proposed activities will further be ensured by combining government internal, national and international expertise in implementing similar projects. GEF funding of consultation costs will be kept to a minimum, as government can finance much of it from existing resources. The same applies to the national contribution to EA working groups. The government of Zimbabwe wishes the work on the new NBSAP to be transformational from a biodiversity planning point of view, in particular with respect to the mainstreaming and ecosystem valuation aspects. Hence, the GEF’s financing of specialized consultants and knowledge / capacity building within the framework of this project is essential to its success, to the extent that it finances the costs of going beyond what government would be able to do without foreign assistance. The GEF funding to the project will focus in overcoming this specific barrier. UNDP is well positioned to assist Zimbabwe source the necessary expertise for this EA project in a cost-effective manner. The project adopts the least-cost means of achieving the project’s objectives and follows the activity norms and cost benchmarks defined by GEF guidelines. It will be built upon the strong foundation of the previous developed NBSAP, Capacity Assessments and National Reports.

E. describe the budgeted M&E Plan:

Type of M&E activity; Responsible Parties; Budget US$ Excluding project team staff time; Time frame. Inception Meeting; Project Coordinator UNDP CO UNDP GEF; $5,000; Within first two months of project start up. Inception Report; Project Team UNDP CO; None; Immediately following IW. Measurement of Means of Verification for Project Purpose Indicators, Project Progress and Performance (measured on an annual basis); Oversight by Project Manager Project team; To be finalized during the inception phase and determined as part of the Annual Work Plan's preparation.; Annually prior to ARR/PIR and to the definition of annual work plans. Simplified Biodiversity Enabling Activities Annual Project Review / Project Implementation Report (APR/PIR); Project Team UNDP-CO UNDP-GEF; None; Annually. Quarterly progress reports; Project team; None; Quarterly. CDRs; Project Manager UNDP CO; None; Quarterly. Lessons Learned Log; Project Manager UNDP CO Programme Staff; None; Quarterly. Terminal Report; Project team UNDP CO local consultant; $1,000 for printing costs; At least one month before the end of the project. Lessons learned; Project team UNDP-GEF Regional Coordinating Unit (suggested formats for documenting best practices, etc.); To be determined as part of the Annual Work Plan's preparation.; Yearly. Audit; UNDP CO Project team; $2,000 in total To be included in the CO audit plan.; Yearly. TOTAL indicative COST Excluding project team staff time and UNDP staff and travel expenses; US$ 8,000. Note: These costs are part and parcel of the project’s budget, and not additional to it. They may be funded by GEF, UNDP or government funds.

F. Explain the Deviations from typical Cost Ranges (where applicable):

-- n/a--

part iii:  approval/endorsement by gef operational focal point(s) and GEF agency(ies)

A.   Record of Endorsement of GEF Operational Focal Point(s) on Behalf of the Government(s): (Please attach the country endorsement letter(s) with this template).

| Name | Position | Ministry | Date (Month, day, year) |
| --- | --- | --- | --- |
| Mr. Irvin Douglas. Kunene | Director of Environment | Ministry of Environment and Natural Resources Management | 11/04/2011 |

B. Convention Participation*

| Convention | Date of Ratification/ Accession (mm/dd/yy) | National Focal Point |
| --- | --- | --- |
| UNCBD | Party since 04/06/2001 | Mr. I.D. Kunene |
| UNFCCC | Party since 30/06/09 | Mr. I.D. Kunene |
| UNCCD | Party since 23/09/97 | Mr. I.D. Kunene |
| Stockholm Convention | Party since 23/05/01 | Mr. I.D. Kunene |

*To be filled for NCSA proposals only

B.  GEF Agency(ies) Certification

This request has been prepared in accordance with GEF policies and procedures and meets the standards of the GEF Project Review Criteria for Biodiversity Enabling Activity approval.

| Agency Coordinator, Agency name | Signature | Date (Month, day, year) | Project Contact Person | Telephone | E-mail Address |
| --- | --- | --- | --- | --- | --- |
| Yannick Glemarec, UNDP/GEF Executive Coordinator |  | February 3, 2012 | Alice Ruhweza, Regional Technical Advisor, EBD Africa. | +27-12-3548120 | alice.ruhweza@undp.org |

Annex A. Consultants to be hired for the Enabling Activity

| Position Titles | $ / Person Week GEF only | Estimated Person Weeks GEF only | Tasks to be Performed |
| --- | --- | --- | --- |
| For EA Management |  |  |  |
| Local |  |  |  |
| National Project Assistant (156 weeks, or 3 years financed by UNDP, @ $372 per week or $19,344 p.a.) | n.a. | n.a. | Objective: To perform as the UNDP/MENRM liaison person on administrative and finance matters for the project. - Assist in preparing for Board meetings and prepare and circulate minutes and any other documentation necessary for the meetings - Compile background material, working papers and statistical data for briefing sessions - Arrange programme visits and prepare reports including travel administration functions - Assist in preparing for training sessions - Prepare payment requests to UNDP including adequate supporting documentation and follow up on status - Draft routine correspondence and follow up and respond to queries on programme matters - Support with procurement of goods and services including contracts administration - Maintain an asset register for programme equipment - Collect, maintain and update data relevant to the programme - Maintain a consultants’ database for the programme. - Maintain programme files for technical and financial records and keep information and reference material in a manner which allows easy reference and retrieval. - Provide programme information and data as requested by audit and evaluation missions - Support with preparation of workplans, progress reports including financial reports and obtaining necessary approvals and authorisations. Required Skills and Experience Secondary Education preferably with specialized certification in Accounting and Finance. University degree in Public Administration, Business, Finance would be desirable. 5 years or more of relevant administrative or programme experience is required at the national or international level. Experience in office management, equipment, usage of computers and office software packages (E-mail/Internet, MS Word, Excel, Publisher etc; ) and knowledge of spreadsheet and database packages and in handling of web-based management systems. Knowledge and experience of Government and UNDP project administration procedures will be an asset. Experience in Biodiversity programming will be an added advantage. |
| For Technical Assistance |  |  |  |
| Local |  |  |  |
| Enabling Activity Coordinator (156 weeks, or 3 years financed by UNDP, @ $870 per week or $45,240 p.a.) | n.a. | n.a. | Objective: To lead the overall process of the stocktaking, stakeholder consultation, national target setting and the development of the NBSAP in Zimbabwe and be responsible for the timely drafting and finalization of the NBSAP, the maintenance of the CHM and the production of the 5th National Report to the CBD. The key tasks are: - Ensure that project Objective, Outcomes, Outputs and Activities are achieved in a timely and appropriate manner. - Serve as team leader for other consultants involved in the NBSAP and be overall responsible for the timely drafting of the document for submission to UNDP, the GEF and the CBD Secretariat; strictly adhering to the deadlines agreed to; and ensuring quality control. - Develop TORs for Consultants for technical services, consultants, experts, and specifications of materials as required by the project, in consultation with the Project Director/UNDP. - Facilitate, guide and monitor the work of consultants, and approve their deliverables in association with the Project Committee. - Ensure that the inception meeting results in a clear roadmap on the scope of services and project tasks to be accomplished under the guidance of the NBSAP Advisors, key national implementing partners and the UNDP technical staff. - Submit draft and revised versions of all studies and reports of the NBSAP activities to International NBSAP Advisor, key national implementing partners and consultants/service providers and to UNDP technical staff for review and support in finalization. - Play a pivotal role in developing the substantive and budgetary part of the project’s work plan and coordinating the input and outputs of all consultants, as well as overseeing the technical quality of deliverables. - Submit in a timely manner, work plans and budgets to the Steering Committee and to the UNDP Country Office for approval, as well as Financial Reports as required. - Ensure that implementation adheres to the approved work plans and that it reaches the desired results. - Identify implementation partners for the undertaking of the various activities and develop an overall implementation plan. - Play a leading role in keeping the CHM up-to-date. - Prepare the project’s monitoring reports, more precisely, the Abridged PIR, the Risk Log, the Terminal Report and the Lessons learned reporting. - Organize and be a key resource person in project related activities. These may include planning for meetings, local and national workshops, consultations, field trips, and other project related activities. - Establish and maintain linkages with national and international organizations and persons which/who can be of assistance to the objectives of the Project. - Provide timely reporting of project status as required by the Project Committee and the UNDP. - Maintain records of Project Committee meetings, decisions, actions etc. - Coordinate with other initiatives and programs whose outcomes and outputs are relevant to this project’s objectives. - Any other duties assigned by the Project Committee that have direct relevance to the project. Selection criteria: Should have a relevant university degree, preferably with specialization in environmental natural sciences, environmental planning, economics, social sciences, management, administration or related field, preferably with professional exposure to biodiversity conservation issues in Zimbabwe. Minimum of 10 years of experience, of which 5 should be at a senior/managerial level, or an advanced degree with 3 years managerial experience. Knowledge and understanding of the relevant UN Convention, environmental issues in Zimbabwe, good leadership, coordination, communication, and facilitation skills are essential. Proven track record of drafting relevant materials in the biodiversity/ecosystem management theme (publications, reports and related documentation). Proven ability to collect, verify and analyze information, and to finish and present work with a high degree of accuracy and technical quality. Ability to communicate effectively orally and in writing, in order to communicate complex, technical information to both technical and general audiences. Previous experience in the development of NBSAPs is a plus. |
| National expert Biodiversity Management and Consultation Processes | 1000 | 24 | Play a leading and resource person role vis-a-vis the National Target Setting and NBSAP Update Working Group and in a number of national sub-national consultation process for all relevant activities under the Enabling Activity project. - Develop planning methodologies and processes for the sub-national technical meetings and consultations - Review base documents for the inputs to the sub-national technical meetings and consultations - Work on the preparation of base documents for technical meetings. - Together with support from MoENRM technical staff review the consolidated results of the five regional consultations - Review the NBSAP update - Develop methodologies for the national validation of the national targets and draft NBSAP - Carry out consultations with provincial authorities and organize sub-national technical meetings and consultations and National Technical meetings. - Collect and consolidate information arising from the technical meetings. - Provide inputs for evaluation of institutional capabilities. - work with local experts and government authorities to collect available information on biodiversity. - Provide inputs to the development of the NBSAP implementation plans Contribution to the following deliverables: - Brief Review of the Biodiversity Planning Process in Zimbabwe - Biodiversity Targets for Zimbabwe: As part of national efforts to implement the CBD’s Strategic Plan for 2011-2020 - Second National Biodiversity Strategy and Action Plan for Zimbabwe - Sub-product 1: Study on Ecosystem Valuation in Zimbabwe - Sub-product 2: Study on Advances in Sectoral Mainstreaming of Biodiversity in Zimbabwe - Sub-product 3: Study on the Incorporation of Challenges and Opportunities linked to Ecosystem-Based Adaptation and Resilience in Zimbabwe - Set of ‘straight-forward’ and feasible NBSAP implementation plans, which ensure the effective implementation of the Action Plan contained in the NBSAP Qualifications and experience: Should have an advanced degree (MSc) in environmental or natural sciences, economics, social sciences, management, preferably with professional exposure to biodiversity conservation issues. Proven track record of drafting relevant materials in the biodiversity/ecosystem based adaptation areas (publications, reports and related documentation). Proven ability to collect, verify and analyze information, and to finish and present work with a high degree of accuracy and technical quality. Ability to communicate effectively orally and in writing, in order to communicate complex, technical information to both technical and general audiences. Knowledge and understanding of the relevant UN Convention, Previous experience in the development of NBSAPs. |
| Expert in Biodiversity Planning and Monitoring | 1000 | 9 | - Play a central role in the process of reviewing previous biodiversity planning processes in Zimbabwe, working in close collaboration with the National Target Setting and NBSAP Update Working Group. - Carry out a thorough analysis of the threats to biodiversity and the causes and consequences of the loss of biodiversity in the country. - Develop proposals for the national targets for Zimbabwe in line with Aichi global targets - With a view to validating and widely discussing national commitments with respect to implementing the CBD at the national level, carry out consultations on the proposals for the national targets, working with provincial representatives, government counterparts, NGOs, CBOs, experts from research and academia, plus other relevant stakeholder to define national objectives and priorities. - Work on the preparation of base documents for technical meetings. - Regarding the effects of climate change on the ecosystems and biodiversity, evaluate and mainstream the outcomes and results of Zimbabwe’s national communication to the UNFCCC into the work of target-setting, reviewing previous biodiversity planning processes and preparing the new NBSAP for Zimbabwe. - Collaborate in the preparation of the required documents for the revised NBSAP. - Design a monitoring system and report on the status of biodiversity on the basis of national targets. - Help shape the structure and priorities of Zimbabwe’s updated NBSAP in close collaboration with other NBSAP consultants and the Working Group. Key contribution to the following deliverables under Components 1 and 2: - Brief Review of the Biodiversity Planning Process in Zimbabwe - Biodiversity Targets for Zimbabwe: As part of national efforts to implement the CBD’s Strategic Plan for 2011-2020 - Second National Biodiversity Strategy and Action Plan for Zimbabwe |
| Expert in Capacity building | 1000 | 9 | To consolidate and prepare project components related to capacity building. - Consolidate and analyze information on the existing legal framework, the current institutional basis and operational procedures. - Prepare the base document for regional consultations regarding the national capacity elements of the NBSAP. - Define the main methodological approaches for capacity evaluations to be applied in various contexts of the NBSAP update process, including and in particular the NBSAP implementation plans. - Evaluate national and provincial institutional capacities to implement a harmonized legal and policy framework, as well as actions on the ground that protect, sustainably use and safeguard biodiversity. - Prepare a report identifying strengths and weaknesses of institutional capacities at various levels and among a wide range of relevant stakeholder for biodiversity management in Zimbabwe. - Play a significant part in the preparation of the implementation plans for the revised NBSAP. - Define straight-forward and costed priority actions to improve the capabilities of national and provincial authorities. - Propose amendments to the legal-institutional dimensions and carry out a gap analysis on the procedures required for effective institutional coordination at the local, regional and national levels. - Prepare a final document (see deliverables) containing a proposed plan of action for capacity building, including a definition of impact and performance indicators and overall costs. Key contribution to the following deliverables under Components 3: - Set of ‘straight-forward’ and feasible NBSAP implementation plans, which ensure the effective implementation of the Action Plan contained in the NBSAP |
| National Target Setting and NBSAP Update Working Group (as part of the government co-financing) | n.a. | n.a. | The National Target Setting and NBSAP Update Working Group will be an essential vehicle for ensuring that the Enabling Activity project is successful in building national capacity for biodiversity planning. group will congregate representatives from key stakeholder institutions and national specialists. It will and provide support to the project activities from beginning to end. More specifically, the Working Group (or several sub-working groups under it) will ensure the process of wide stakeholder engagement and provide technical and policy inputs to the NBSAP review process, including by providing data and information to and by commenting the key products emanating from the Enabling Activity. Iterative and collective contributions to the following deliverables: - Brief Review of the Biodiversity Planning Process in Zimbabwe - Biodiversity Targets for Zimbabwe: As part of national efforts to implement the CBD’s Strategic Plan for 2011-2020 - Second National Biodiversity Strategy and Action Plan for Zimbabwe - Sub-product 1: Study on Ecosystem Valuation in Zimbabwe - Sub-product 2: Study on Advances in Sectoral Mainstreaming of Biodiversity in Zimbabwe - Sub-product 3: Study on the Incorporation of Challenges and Opportunities linked to Ecosystem-Based Adaptation and Resilience within Zimbabwe’s protected area network - Set of ‘straight-forward’ and feasible NBSAP implementation plans, which ensure the effective implementation of the Action Plan contained in the NBSAP - Fully functional CHM for Zimbabwe, based on best international practice on the matter |
| International |  |  |  |
| International NBSAP Advisor | 3000 | 8 | Objective To provide technical leadership and support through advisory and capacity building services to the overall process of the stocktaking, stakeholder consultation, national target setting and the development of the NBSAP for Zimbabwe. The International NBSAP Advisor will be an experienced expatriate, with wide experience in biodiversity management, including in Africa. He/she will render services to the Enabling Activity Coordinator and the National Project Director as his/her main clients. The International NBSAP Advisor will be responsible for the technical quality control on the process of drafting and finalizing the NBSAP and a number of other related products. Key tasks are: - Provide technical support and advise of high technical quality to other consultants involved in the NBSAP. - Assist the Enabling Activity Coordinator in striking the right balance with respect to the scope of project, its duration and budget, and the tasks to be accomplished by the different project consultants and service providers. This will imply reviewing and revising TORs and supporting the Coordinator in recruitment of consultants and procurement of service providers upon demand. - Help consultants and working groups in preparing and submitting all studies and reports of the NBSAP activities to the Coordinator, key national implementing partners and UNDP technical staff, as per reporting timelines agreed upon or before the inception meeting. - Ensure that all Climate Change-related issues highlighted in the second National Communication to the UNFCCC that affect Biodiversity (Adaptation) or are affected by Biodiversity (Mitigation) are integrated and addressed in the final NBSAP. Guidance from the Ad hoc Technical Expert Group (AHTEG) will apply. - Ensure that all lessons learnt in the mainstreaming of biodiversity into the production sectors are incorporated into the NBSAP. - Identify implementation partners for the undertaking of the various activities and develop an overall implementation plan. - Submit a final draft to the Project Manager, incorporating stakeholder inputs and guidance provided. Contribution to the following deliverables: - Brief Review of the Biodiversity Planning Process in Zimbabwe - Biodiversity Targets for Zimbabwe: As part of national efforts to implement the CBD’s Strategic Plan for 2011-2020 - Second National Biodiversity Strategy and Action Plan for Zimbabwe - Sub-product 1: Study on Ecosystem Valuation in Zimbabwe - Sub-product 2: Study on Advances in Sectoral Mainstreaming of Biodiversity in Zimbabwe - Sub-product 3: Study on the Incorporation of Challenges and Opportunities linked to Ecosystem-Based Adaptation and Resilience within Zimbabwe’s protected area network - Set of ‘straight-forward’ and feasible NBSAP implementation plans, which ensure the effective implementation of the Action Plan contained in the NBSAP - Fully functional CHM for Zimbabwe, based on best international practice on the matter Selection criteria: should have an advanced degree (MSc) in environmental or natural sciences, preferably with exposure to biodiversity conservation issues at the international level. Proven track record of drafting relevant materials in the biodiversity/ecosystem based adaptation areas (publications, reports and related documentation). Proven ability to collect, verify and analyze information, and to finish and present work with a high degree of accuracy and technical quality. Ability to communicate effectively orally and in writing, in order to communicate complex, technical information to both technical and general audiences. Knowledge and understanding of the relevant UN Convention (CBD), Previous experience in the development of NBSAPs at international level is an advantage. |

Annex B. Chronogramme of activities

| Comp | Modules | Guiding activities under each module | 2012 |  |  |  | 2013 |  |  |  | 2014 |  |  |  | 2015 |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 |
| 1 | I. Preparation | 1. Rapid stocktaking and review of relevant plans, policies and reports |  |  | X | X |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | 2. Identification of stakeholders; consultations and awareness |  |  |  | X | X |  |  |  |  |  |  |  |  |  |  |  |
|  |  | 3. Rapid assessment of the causes and consequences of biodiversity loss highlighting the value of biodiversity and ecosystem services and their contribution to human well-being |  |  |  | X | X |  |  |  |  |  |  |  |  |  |  |  |
|  | II Setting national targets, principles, & main priorities of the strategy | 4. Setting national targets, principles, & main priorities of the strategy though national consultations |  |  |  | X | X | X |  |  |  |  |  |  |  |  |  |  |
| 2 | III. Strategy and action plan development | 5. Developing the strategy and actions to implement the agreed targets though national consultations |  |  |  | X | X | X |  |  |  |  |  |  |  |  |  |  |
|  |  | 6. Application of the NBSAP to sub-national entities through sub-national and local consultations |  |  |  |  |  | X | X |  |  |  |  |  |  |  |  |  |
|  |  | 7. Sectoral integration including mainstreaming into development, poverty reduction and climate change plans through sectoral consultations |  |  |  |  |  |  |  | X | X | X |  |  |  |  |  |  |
| 3 | IV. Development of Implementation plans and related activities | 8. Development of a plan for capacity development for NBSAP implementation. |  |  |  |  |  |  |  |  |  |  | X | X | X |  |  |  |
|  |  | 9. Technology needs assessment |  |  |  |  |  |  |  |  |  |  |  | X | X |  |  |  |
|  |  | 10. Development of a communication and outreach strategy for the NBSAP. |  |  |  |  |  |  |  |  |  |  |  |  | X | X |  |  |
|  |  | 11. Development of a plan for resource mobilization for NBSAP implementation |  |  |  |  |  |  |  |  |  |  |  | X | X |  |  |  |
|  | V. Institutional, monitoring, reporting and exchange | 12. Establishment/ strengthening of national coordination structures |  |  | X | X |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | 13. CHM development. |  |  |  |  |  |  |  |  |  |  |  |  | X | X | X | X |
|  |  | 14. Development of indicators and monitoring approach |  |  |  |  |  |  |  |  |  |  |  |  |  | X | X | X |
|  |  | 15. Fifth national reports |  |  |  |  |  |  |  |  |  |  |  |  |  |  | X | X |

Annex C. UNDP Total Budget and Workplan

| GEF Component (Outcome) /Atlas Activity | Resp.Party/ Impl. Agent | Fund ID | Donor Name | ERP / ATLAS Budget Code | Atlas Budget Description | TOTAL Amount (USD) | Amount Year 1 (USD) | Amount Year 2 (USD) | Amount Year 3 (USD) | Budget Notes |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Comp 1. Stocktaking and national target setting | NEX | 62000 | GEF-10003 | 71200 | International Consultants | 8,000 | 8,000 |  |  | a |
|  | NEX | 62000 | GEF-10003 | 71300 | Local Consultants | 8,000 | 8,000 |  |  | b |
|  | NEX | 62000 | GEF-10003 | 71600 | Travel | 8,000 | 8,000 |  |  | c |
|  | NEX | 61999 | GEF-10002 | 72099 | Contractual Services-Companies | 9,000 | 9,000 |  |  | d |
|  | NEX | 62000 | GEF-10003 | 72500 | Supplies | 1,000 | 1,000 |  |  | e |
|  | GEF Subtotal Atlas Activity 1 (Comp 1) |  |  |  |  | 34,000 | 34,000 | 0 | 0 |  |
|  | NEX | 04000 | UNDP TRAC - 00012 | 71400 | Contractual Services - Individ | 45,240 | 45,240 |  |  | f |
|  | TRAC Subtotal Atlas Activity 1 (Comp 1) |  |  |  |  | 45,240 | 45,240 | 0 | 0 |  |
| TOTAL ACTIVITY 1 (Comp 1) |  |  |  |  |  | 79,240 | 79,240 | 0 | 0 |  |
| Comp 2. NBSAP update | NEX | 62000 | GEF-10003 | 71200 | International Consultants | 8,000 |  | 8,000 |  | a |
|  | NEX | 62000 | GEF-10003 | 71300 | Local Consultants | 8,000 |  | 8,000 |  | b |
|  | NEX | 62000 | GEF-10003 | 71300 | Local Consultants | 9,000 |  | 9,000 |  | g |
|  | NEX | 62000 | GEF-10003 | 71600 | Travel | 8,000 |  | 8,000 |  | c |
|  | NEX | 62000 | GEF-10003 | 72100 | Contractual Services-Companies | 16,000 |  | 16,000 |  | h |
|  | NEX | 62000 | GEF-10003 | 72100 | Contractual Services-Companies | 48,000 |  | 48,000 |  | i |
|  | NEX | 62000 | GEF-10003 | 72500 | Supplies | 3,000 |  | 3,000 |  | e |
|  | GEF Subtotal Atlas Activity 2 (Comp 2) |  |  |  |  | 100,000 | 0 | 100,000 | 0 |  |
|  | NEX | 04000 | UNDP TRAC - 00012 | 71400 | Contractual Services - Individ | 45,240 |  | 45,240 |  | f |
|  | TRAC Subtotal Atlas Activity 2 (Comp 2) |  |  |  |  | 45,240 | 0 | 45,240 | 0 |  |
| TOTAL ACTIVITY 2 (Comp 2) |  |  |  |  |  | 145,240 | 0 | 145,240 | 0 |  |
| Comp 3. National frameworks for NBSAP implementation, CDB reporting and exchange mechanisms | NEX | 62000 | GEF-10003 | 71200 | International Consultants | 8,000 |  |  | 8,000 | a |
|  | NEX | 62000 | GEF-10003 | 71300 | Local Consultants | 8,000 |  |  | 8,000 | b |
|  | NEX | 62000 | GEF-10003 | 71300 | Local Consultants | 9,000 |  |  | 9,000 | j |
|  | NEX | 62000 | GEF-10003 | 71600 | Travel | 8,000 |  |  | 8,000 | c |
|  | NEX | 62000 | GEF-10003 | 72100 | Contractual Services-Companies | 10,000 |  |  | 10,000 | k |
|  | NEX | 62000 | GEF-10003 | 72500 | Supplies | 2,000 |  |  | 2,000 | e |
|  | NEX | 62000 | GEF-10003 | 74100 | Professional Services | 12,000 |  | 8,000 | 4,000 | l |
|  | NEX | 62000 | GEF-10003 | 74200 | Audio Visual&Print Prod Costs | 11,000 |  | 11,000 |  | m |
|  | GEF Subtotal Atlas Activity 3 (Comp 3) |  |  |  |  | 68,000 | 0 | 19,000 | 49,000 |  |
|  | NEX | 04000 | UNDP TRAC - 00012 | 71400 | Contractual Services - Individ | 45,240 |  |  | 45,240 | f |
|  | TRAC Subtotal Atlas Activity 3 (Comp 3) |  |  |  |  | 45,240 | 0 | 0 | 45,240 |  |
| TOTAL ACTIVITY 3 (Comp 3) |  |  |  |  |  | 113,240 | 0 | 19,000 | 94,240 |  |
| Project Mgt | NEX | 62000 | GEF-10003 | 72800 | Information Technology Equipmt | 9,600 | 9,600 |  |  | n |
|  | NEX | 62000 | GEF-10003 | 73100 | Rental & Maintenance-Premises | 3,000 | 1,000 | 1,000 | 1,000 | o |
|  | NEX | 62000 | GEF-10003 | 74100 | Professional Services | 3,000 | 1,000 | 1,000 | 1,000 | p |
|  | NEX | 62000 | GEF-10003 | 74500 | Miscellaneous Expenses | 2,400 | 800 | 800 | 800 | q |
|  | GEF Subtotal Atlas Activity 4 (Proj Mgt) |  |  |  |  | 18,000 | 12,400 | 2,800 | 2,800 |  |
|  | NEX | 04000 | UNDP TRAC - 00012 | 71400 | Contractual Services - Individ | 58,032 | 19,344 | 19,344 | 19,344 | r |
|  | NEX | 04000 | UNDP TRAC - 00012 | 72100 | Contractual Services-Companies | 3,000 | 1,000 | 1,000 | 1,000 | s |
|  | NEX | 04000 | UNDP TRAC - 00012 | 73200 | Premises Alterations | 3,000 | 3,000 |  |  | t |
|  | NEX | 04000 | UNDP TRAC - 00012 | 74500 | Miscellaneous Expenses | 248 |  | 200 | 48 | q |
|  | TRAC Subtotal Atlas Activity 4 (Proj Mgt) |  |  |  |  | 64,280 | 23,344 | 20,544 | 20,392 |  |
| TOTAL ACTIVITY 4 (Project Management) |  |  |  |  |  | 82,280 | 35,744 | 23,344 | 23,192 |  |
|  | SUB-TOTAL GEF |  |  |  |  | 220,000 | 46,400 | 121,800 | 51,800 |  |
|  | SUB-TOTAL UNDP TRAC |  |  |  |  | 200,000 | 68,584 | 65,784 | 65,632 |  |
|  | GRAND TOTAL (in cash) |  |  |  |  | 420,000 | 114,984 | 187,584 | 117,432 |  |

| Budget Notes |  |
| --- | --- |
| a | Int. Cons.: NBSAP Advisor (8 weeks @ $3000). Costs spread equally across components 1, 2 and 3. |
| b | Nat. Cons.: National expert Biodiversity management and consultation processes (24 weeks @ $1000). Costs equally spread across components 1, 2 and 3. |
| c | Travel in connection with project activities, including international travel to bring the Int. NBSAP Advisor to the the country. |
| d | Consultations and meetings in connection with the biodiversity planning stock-taking and target setting exercises. |
| e | Fuel and stationary in connection with project activities. |
| f | National Enabling Activity Coordinator (3 year assignment throughout the duration of the project @ 45,240 per annum). |
| g | Nat. Cons.: Expert in biodiversity planning and monitoring (9 weeks @ $1000). |
| h | Consultations and meetings in connection with the NBSAP update exercise. |
| i | Output-based consultancy with the following tree-fold objective: (A) To assess and capture the value of ecosystems’ goods and services based on at least two case studies of collective livelihoods in Zimbabwe, namely forestry and wildlife management (e.g. CAMPFIRE); (B) To develop the mainstreaming elements of Zimbabwe’s NBSAP, following the best international guidance and practice available on the matter; and (C) To ensure that Zimbabwe’s PoWPA Action Plan includes costed options for Ecosystem-based adaptation to climate change. Refer to Annex D for detailed TOR. |
| j | Nat. Cons.: Expert in Capacity building (9 weeks @ $1000). |
| k | Consultations and meetings in connection with the NBSAP implementation plans, CHM and 5NR. |
| l | Webdesign in connection with updating the CHM according to activities described in Component 3. |
| m | Printing of 2000 copies of the NBSAP and related reports. |
| n | Acquisition of Laptops (2@US$1400), software licenses (2@US$800), portable hard drive (2@US$200), printer (2@US$300), data projector (1@US$800) and mobile phone contracts (1@US$2000) and other peripherals (@US2000) for project staff, including a reserve computer that may be used by project consultants. |
| o | Contribution to the costs of utility bills in government premises |
| p | Project Audit |
| q | Bank charges, exchange rate fluctuations and miscellaneous expenses. |
| r | National Project Assistant (3 year assignment throughout the duration of the project @ 19,344 per annum). |
| s | Partial costs of security services for the project office (shared with UNDP). |
| t | Refurbishing office space availed by government in order to make premises functional and secure. |

Annex D. Technical Assistance Service Provision: TOR for launching a Request for Quotes

As per the Total Budget and Workplan (TBW) in Annex C of this proposal, one output-based consultancy is planned under the project. This Annex describes the work under each of them. The content herein will form the basis to prepare complete a Requests for Quotes for the mentioned consultancy.

The complete Requests for Quotes prepared by UNDP normally has the following structure:

i.	Instructions to Offerors

ii.	General Conditions of Contract

iii.	Terms of Reference (TOR)

iv.	Proposal Submission Form

v.	Price Schedule

In this annex, only the TOR are described. The remainder of the chapters of the Requests for Quotes will be completed before launching the tenders and after due validation by UNDP.

The complete TOR for Requests for Quotes will include the following headings:

(1) Summary

(2) Background

(3) Objective of the Consultancy

(4) Scope of Work

(4) Expected Results

(5) Duty station

(6) Requirements to the documents

(7) Responsibility

(8) Qualification requirements

(9) Available information

(10) Selection Process

Sections 1 through 7 are contained herein. Sections 8, 9 and 10 are to be completed before launching the tenders. The number of minimum mission days and schedule of payment are to be completed when composing the final documentation for the Request for Quotes.

TOR for the Output Based Consultancy to assist Zimbabwe in the preparation of Strategic Studies in connection with the updating of the National Biodiversity Strategy and Action Plan

(1) Summary

Zimbabwe is in the process of implementing a GEF biodiversity planning project (under the ‘Enabling Activities’ funding window). Its objective is to integrate the country’s obligations under the Convention on Biological Diversity (CBD) into its national development and sectoral planning frameworks through a renewed and participative ‘biodiversity planning’ and strategizing process, in a manner that is in line with the global guidance contained in the CBD’s Strategic Plan for 2011-2020.

The following key outcomes are sought as part of the project, each representing one Component of the project:

1) A participative stocktaking exercise on biodiversity planning takes place and national biodiversity targets are developed in response to the global Aichi Targets

2) Zimbabwe’s National Biodiversity Strategy and Action Plan (NBSAP) is revised/updated and it fully integrates new aspects of the CBD strategic plan, such as mainstreaming and anchoring the implementation of the plan into national development frameworks, valuing ecosystem services and promoting ecosystem-based adaptation and resilience. The development of the NBSAP will be supported by the development following key studies:

- Ecosystem Valuation in Zimbabwe

- Advances in Sectoral Mainstreaming of Biodiversity in Zimbabwe

- Exploring and costing options for Ecosystem-based adaptation to climate change through the development of a robust Action Plan for the Progamme of Work on Protected Areas (PoWPA) and a plan for sustainable land use in Zimbabwe.

3) National frameworks for resource mobilization, Convention reporting and exchange mechanisms, including the Clearing House Mechanism (CHM) of the CBD, are established and strengthened

The ultimate goal of the project is to build national capacity within the topic of biodiversity planning. This implies procuring knowledge and capacity building services that are usually not available within State Institutions, due to the specificity of the topics at hand and the technical requirements.

Parallel to the Enabling Activities project, which focuses inter alia on NBSAP review, Zimbabwe is in the process of finalizing its implementation plan for the CBD’s Progamme of Work on Protected Areas (PoWPA). These processes are related. A specific sub-activity in the Enabling Activity  Project under Component 3 will establish a link between the two processes and ensure that Zimbabwe’s work on protected areas, including goals, objectives and next steps, are fully integrated into the NBSAP – more specifically in the NBSAP’s implementation plans. In connection with it, Zimbabwe will place particular emphasis on those aspects of Target 11 from the CBD Strategic Plan, including the country’s plans for expanding protected areas, improving management effectiveness, sustainably financing protected areas, improving connectivity, and integrating protected areas into the wider landscape and seascape. The incorporation of climate change issues into the management of protected areas is however a more specific topic and requires a more focused work, which Zimbabwe wishes to pursue.

Also, the capacity to explore certain issues, such as ecosystem valuation and biodiversity mainstreaming, which are part of the work under Component 2, will require specialised expertise, which is not immediately available in Zimbabwe.

Three Strategic Studies are foreseen under Component 2 of the project, and which link the PoWPA work with the NBSAP with focus on climate change and resilience, and which deepens the mainstreaming and valuation elements of the NBSAP with a view to improving the quality of the final National Strategy. These Studies are:

- Sub-product 1: Study on Ecosystem Valuation in Zimbabwe

- Sub-product 2: Study on Advances in Sectoral Mainstreaming of Biodiversity in Zimbabwe

- Sub-product 3: Study on the Incorporation of Challenges and Opportunities linked to Ecosystem-Based Adaptation and Resilience within Zimbabwe’s protected area network

Hence, an international Request for Quotes is being launched in view of having services rendered by a group of specialised consultants within the following areas of expertise to lead the preparation of the mentioned studies:

- The interface between biodiversity & climate change

- Environmental economics, finance and biodiversity mainstreaming

- Ecosystems and protected area specialist

Services may combine national and international expertise and quotes for qualified companies should be presented as a package of services, including honoraries, travel expenses and admin costs.

(2) Background

- To be added when composing the final documentation for the Request for Quotes -

(3) Objective of the Consultancy

Provide knowledge and capacity building services to the government of Zimbabwe, as well as to other key stakeholder involved in the implementation of the Biodiversity Enabling Activities Project, with the following specific sub-objectives:

(A)	To assess and capture the value of ecosystems’ goods and services based on at least two case studies of collective livelihoods in Zimbabwe, namely forestry and wildlife management (e.g. CAMPFIRE);

(B)	To develop the mainstreaming elements of Zimbabwe’s NBSAP, following the best international guidance and practice available on the matter; and

(C)	To ensure that Zimbabwe’s PoWPA Action Plan includes costed options for Ecosystem-based adaptation to climate change.

Each of the sub-objectives above represent one ‘Block of Service’, which is explained in the section that follows.

As part of the process of developing specific inputs to Zimbabwe’s NBSAP, the Consultancy in question will be the main driving force in the preparation of the NBSAP’s Strategic Studies mentioned further up.

(4) Scope of Work

Block of Services (A) Ecosystem Valuation in Zimbabwe

- Become familiar with Zimbabwe’s previous biodiversity planning processes, including the key reports and strategies that were produced and other relevant reports focusing on the economic value of biodiversity for the economy

- Become acquainted with relevant guidance from the CBD COP and with other relevant publications on the matter of ecosystem valuation (e.g. the TEEB) and the context in Zimbabwe.

- Identify and assess the full range of values of key ecosystem services within the country, based on existing local, national, regional and global studies on the value of ecosystems and biodiversity, including: the valuation of protected areas, any other national ecosystem services studies that have been conducted (e.g., water, carbon, soil formation, wildlife refugia, etc.), and existing global and regional maps and overlays of key ecosystem services. This may also include comparing valuation studies from ecosystems in neighbouring countries.

- Identify the implications of these services for different stakeholder groups within the country, including those who benefit from, and pay for, the maintenance of these ecosystem services, and those that degrade ecosystems through unsustainable use.

- Understand the context of local communities involved in the CAMPFIRE programme (case study) -- which the rural people are granted the authority to manage their wildlife and other natural resources for their own benefit. Other similar examples from the Zimbabwe and in the SADAC region may also be drawn in.

- Estimate and demonstrate the value of key ecosystem services (using methods appropriate to each service), including the value of the ecosystem service in contributing to climate resilience, adaptation and mitigation; reducing poverty, and sustaining livelihoods. Draw on the case study and similar examples from the Zimbabwe and in the SADAC region as applicable.

- Identify mechanisms for incorporating these values into national accounting practices.

- Where appropriate, this activity will also identify potential means of capturing the value of targeted ecosystem services, including through policies such as payments for ecosystem services and other positive incentives.

- As a result of the above, prepare specific inputs for Zimbabwe’s set of biodiversity targets (in line with the global Aichi Targets) (due before Sep 2012), for the country’s new NBSAP (due by end 2013) and for its Fifth National Report to the CBD (due in March 2014).

- Develop a written report that summarizes all findings.

- Prepare a set of simple but strong key economic and political messages backed up by credible data from the results of the analysis to be included in the conclusion of the case study and other similar examples from the Zimbabwe and in the SADAC region as applicable.

- Presentation of case study findings on NBSAP updating events.

Block of Services (B) Advances in Sectoral Mainstreaming of Biodiversity in Zimbabwe

The project will focus on the following sectors in Zimbabwe with respect to mainstreaming: (i) Agriculture; (ii) Forestry; (iii) Hunting; (iv) Livestock; (v) Tourism; and (vi) Water.

The Project will also focus on the following development areas / topics: (a) Land-use management, including spatial and infrastructural development planning; (b) Development finance; (c) Poverty alleviation; (d) Rural development and livelihoods; (e) Food security; (f) Gender; and (g) Traditional medicine.

- With focus on threats to biodiversity and on benefits that biodiversity and ecosystem services can generate, establish a an analytical link between the selected economic sectors and development topics targeted for biodiversity mainstreaming in Zimbabwe NBSAP.

- “Map” in an analytical manner the relevant policies, interests of and stakes for productive sectors and development agendas linked to the selected development topics.

- Organise, in collaboration with the project team, a round table involving sectoral representatives and development practitioners to discuss threats to biodiversity deriving from economic activities and development policies and agendas, as well as the benefits that biodiversity and ecosystem services can generate for these sectors. The goal is to emphasise the role of Biodiversity for Development in Zimbabwe.

- Assist the project team in:

- Forming partnerships between relevant stakeholders interested in biodiversity conservation issues and in development issues

- Explicitly identifying key stakeholders’ interests, and desired outcomes

- Identifying potential conflicts and trade-offs, and work towards mutually acceptable solutions, including strategies that serve mutually beneficial interests and achieve mutually beneficial outcomes

- Embedding and institutionalizing these strategies in the institutions, policies, agreements, programs and mechanisms of each sector

- Develop a written report that summarizes all findings.

- Prepare a set of simple but strong key economic and political messages backed up by credible data from the results of the analysis to be included in the conclusion of the case study and other similar examples from the Zimbabwe and in the SADAC region as applicable.

- Presentation of case study findings on NBSAP updating events.

Relevant note for Block of Service B:

A set of capacity building modules on national biodiversity strategies and action plans, and other aspects of implementation of the Convention, is available at the CBD website. Module B-3 on mainstreaming biodiversity into sectoral and cross-sectoral strategies, plans and programmes has been updated in 2011. It focuses on the theme of biodiversity mainstreaming both into (i) national development and poverty reduction frameworks, as in production sectors. The guidance also suggests a number of tools that can be used for the purpose with examples and further guidance. The document is available in English, French and Spanish. Zimbabwe will seek inspiration from these materials in its mainstreaming activities in connection with the NBSAP update.

In addition, Biodiversity for Development is a joint initiative involving the CBD Secretariat and UNDP. The aim is to ensure that biodiversity conservation and sustainable use are integral to national and regional economic and social development policies, legal frameworks, development plans and implementation systems.

The CBD provides access to a number of guiding and training materials aimed at developing the capacity of Parties to more effectively assess the impact of different productive sectors on biodiversity and make a win-win link between these and the conservation and sustainable use of biodiversity. They can be explored by departing from the following sites: (1) www.cbd.int/impact and (2) www.cbd.int/development.

Block of Services (C) Exploring and costing options for Ecosystem-based adaptation to climate change through the development of a robust Action Plan for the Progamme of Work on Protected Areas (PoWPA) and a plan for sustainable land use in Zimbabwe

- Based on existing data (e.g. from the WCMC Protected Area Database) and fine resolution GIS modelling, identify potential areas important for carbon sequestration in Zimbabwe and make recommendations for their protection and management, which may be incorporated into the national target setting exercise (in line with the global Aichi Targets) and into the country’s revised NBSAP.

- Assess the extent to which the country’s ecological gap assessment included predicted future distribution of biodiversity under climate change scenarios, making specific recommendations for protected area and corridor expansion, recommendations that should be realistically incorporated into Zimbabwe’s national biodiversity targets and revised NBSAP.

- Assess the impact of climate change on the functioning of ecosystem services, such as water and nutrient recycling, in a geographically-based manner.

- Identify areas important for improving nature’s ability to adapt to climate change, such as altitudinal gradients and conservation corridors.

- Identify areas of particular importance for restoration in order to improve climate resilience, adaptation and mitigation.

- As a result of the above, prepare specific inputs for Zimbabwe’s set of biodiversity targets (in line with the global Aichi Targets) (due before Sep 2012), for the country’s new NBSAP (due by end 2013) and for its Fifth National Report to the CBD (due in March 2014).

- Develop a written report that summarizes all findings.

- Prepare a set of simple but strong key economic and political messages backed up by credible data from the results of the analysis to be included in the conclusion of the case study and other similar examples from the Zimbabwe and in the SADAC region as applicable.

- Presentation of case study findings on NBSAP updating events.

(4) Expected Results

The completion of the following NBSAP Sub-Products:

- Sub-product 1: Study on Ecosystem Valuation in Zimbabwe

- Sub-product 2: Study on Advances in Sectoral Mainstreaming of Biodiversity in Zimbabwe

- Sub-product 3: Study on the Incorporation of Challenges and Opportunities linked to Ecosystem-Based Adaptation and Resilience within Zimbabwe’s protected area network

Presentations and lectures in NBSAP events according to agreed schedule of services.

– Number of minimum mission days and schedule of payment to be completed when composing the final documentation for the Request for Quotes –

(5) Duty station:

- Harare, Zimbabwe, for the mission part*

- Home based, for the completion of certain reports

*Note: all travel expenses should be included into the breakdown of contract total amount by submission of financial proposal.

(6) Requirements to the documents

- Draft and final documents should be submitted in English in MS Word (2007 or later). Used font: Arial, size: 12;

- Presentational documents should be prepared in MS Power Point.

– May be complemented when composing the final documentation for the Request for Quotes –

(7) Responsibility

- Agrees the above results with the Enabling Activities Technical Coordinator, under the guidance from the International NBSAP Advisor;

- Ensures timely and quality execution of the Terms of Reference;

- Ensures unconditional implementation of requirements of the contract

(8) Qualification requirements

- As minimum 5 years of work experience (preferably more, given the complexity of the services in question) in the relevant field for the three blocks of services: (a) environmental or natural science, with a specialization in ecosystem based climate change adaptation and/or mitigation; (b) national biodiversity valuation studies, payment for ecosystem services, sectoral mainstreaming of biodiversity, policy development, national accounting practices and methods; (c) protected area management; (d) any other field relevant for the consultancy in question.

- Valid certificates and licenses for consulting services in the field of biodiversity and or development.

- Available qualified personnel with university degrees in the required field of expertise.

- Outline of proposed approaches for the three blocks of services.

- List of rendered consulting services for the past 3 years.

- Ability to submit the 2 reference letters confirming the successfully rendered services for the last 2 years.

- Ability to write hold the trainings in English is a requirement.

(9) Available information:

Complete Project Document for the UNDP/GEF PIMS 4870 “National Biodiversity Planning to Support the implementation of the CBD 2011-2020 Strategic Plan in Zimbabwe”

– Relevant hyperlink to the project document to be added when composing the final documentation for the Request for Quotes –

(10)  Selection Process

The selection of the company will follow an open competitive process in line with UNDP procurement standards. The successful company would be required to enter into a standard UNDP Institutional Contract. The contract will be awarded according to the cumulative analysis scheme: proposal with the overall highest score after adding the score of the technical proposal and the financial proposal will be chosen.

www.bipindicators.net

www.gbif.org

www.unep-wcmc.org

geodata.rrcap.unep.org

This is the cost associated with the unit executing the project on the ground and could be financed out of trust fund or co-financing sources.

Ministry of Environment & Natural Resources Management, Republic of Zimbabwe. 2010. Zimbabwe’s 4th National Report.

Gandiwa, E. 2011. Wildlife Tourism in Gonarezhou National Park, Southeast Zimbabwe. Journal of Sustainable Development in Africa, Volume 13, No.1.

http://www.cbd.int/doc/world/zw/zw-nbsap-01-en.pdf

The actual submission of the NBSAP to the CBD Secretariat is the responsibility of the government of Zimbabwe, not UNDP.

Petersen, C and B. Huntley. 2005. Mainstreaming Biodiversity in Productive Landscapes. Working Paper 20. Washington DC: GEF.

This specific process will involve the

With reference to the applicable procurement process for the type of services being sought and budget allocated to financing them.

www.teeb.org

See www.cbd.int/nbsap/training.