GEF-6 REQUEST FOR Chemicals and Wastes enabling activity

Proposal for Funding Under THE GEF Trust Fund

For more information about GEF, visit TheGEF.org

part i:  project IDentifiers

| Project Title: | Improve Mercury Management in India |  |  |
| --- | --- | --- | --- |
| Country(ies): | India | GEF Project ID: |  |
| GEF Agency(ies): |  | GEF Agency Project ID: | 5661 |
| Other Executing Partner(s): | Ministry of Environment, Forest and Climate Change | Submission Date: | 24 June 2015 |
| GEF Focal Area (s): |  | Project Duration (Months) | 24 |
| Type of Report: | Minamata Initial Assessment | Expected Report Submission to Convention | Sep 2017 |

- Project Framework*

| Project Objective: Strengthen India’s capacity to manage and monitor mercury use, import, export, stockpiles, emissions and releases throughout the country (with a particular focus on Annex A (Part I), Annex B and Annex D of the Minamata Convention) and enable India to take an informed decision on ratifying the Minamata Convention and to meet future obligations under the Convention. |  |  |  |  |
| --- | --- | --- | --- | --- |
| ### Project Component | ### Project Outcomes | ### Project Outputs | ### (in $) |  |
|  |  |  | ### GEF Project ### Financing | ### Confirmed Co-financing |
| 1. Assessment of institutional and national capacity to ratify and prepare for implementation of the Minamata Convention | 1.1 Institutional capacity to manage and monitor Mercury assessed. National capacity to undertake mercury inventories built so as to support national decision making on Mercury. 1.2 Policy and regulatory framework and institutional capacity to meet present/future obligations under the Minamata Convention assessed. 1.3 National Mercury profile developed. 1.4 Environmentally sound schemes to reduce Mercury use, emission and releases identified. 1.5 National Mercury action plan and Mercury mainstreaming roadmap developed and submitted for national adoption/approval. | 1.1.1 National Mercury coordination mechanism set up and institutional gaps identified. 1.1.2 Capacity building and training to undertake the Mercury inventory. 1.1.3 Awareness raising campaign/activities conducted on environmental and health impacts of Mercury targeting policy makers, implementing entities, private sector and population groups at risk. 1.2.1 Assessment report prepared identifying the legal, policy, regulatory, technical and financial needs and gaps that need to be addressed to meet the Minamata Convention obligations, decision mechanism established and recommended actions to address these needs and gaps agreed upon. 1.3.1 Mercury inventory conducted in relevant industrial sector and considering geographical distribution (Annex D of the Minamata Convention). 1.3.2 Mercury inventory conducted for other sources (Annex A Part I, Annex B of the Minamata Convention). 1.3.3 Assessment on mercury use for dental amalgam in dental health care facilities. 1.4.1 Formulation of project concepts for long-term Mercury reductions. 1.5.1 Priority sectors and activities identified. 1.5.2 National mercury action plan drafted. 1.5.3 Roadmap for the mainstreaming of Mercury priorities developed. | 910,000 | 0 |
| Subtotal |  |  | 910,000 | 0 |
| Project Management Cost (Including Direct Project Cost: US$9,000) |  |  | 90,000 | 0 |
| Total Project Cost |  |  | 1,000,000 | 0 |

*   List the $ by project components.  Please attach a detailed project budget table that supports all the project components in this table.

- Source of Co-financing for the Project by Name and by Type

| Sources of Co-financing | Name of Co-financier | Type of Co-financing | Amount ($) |
| --- | --- | --- | --- |
| N/A |  |  |  |
| Total Co-financing |  |  |  |

- GEF Financing  Resources Requested by Agency,  Country and Programming of Funds

| GEF Agency | Trust Fund | Country Name/Global | Programming of Funds | (in $) |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | GEF Project Financing (a) | Agency Fee a)/ (b)2 | Total c=a+b |
| UNDP | GEF TF | India | Chemicals and Wastes | 1,000,000 | 95,000 | 1,095,000 |
| Total Grant Resources |  |  |  | 1,000,000 | 95,000 | 1,095,000 |

a) Refer to the Fee Policy for GEF Partner Agencies

part ii:  Enabling Activity JustiFication

| A. Enabling Activity Background and Context (Provide brief information about projects implemented since a country became party to the convention and results achieved): | India is one of the large coal producing countries with total coal reserves as one fifth of the world. A study project entitled “Assessment of the Mercury Content in Coal fed to Power Plants and study of Mercury Emissions from the Sector in India” has been executed by Central Institute of Mining & Fuel Research (CIMFR) in partnership with MoEF&CC and UNEP. In India, coal is used primarily for thermal power generation and cement production apart from iron and steel sector and brick kiln sector. India does not mine Mercury, and all its domestic demands are met through imports. It imported approximately 165 tonnes of Mercury in 2012-13, out of which 45 tonnes were exported to other countries in the same year, which leads to a conclusion that 120 tonnes of Mercury is being used in the country for product manufacturing and consumption in various sectors. Mercury has been used in nearly 3,000 industrial applications. The Government has also taken a number of policy and regulatory actions to steadily reduce some of the use, emissions and releases of Mercury in the country. The Government of India became a signatory to the agreed text for the Minamata Convention on 30 September 2014. The Hazardous Waste (Management, Handling & Transboundary Movement) Rules (2008) classify Mercury and Mercury compounds as a hazardous waste if the concentration of the components is equal to, or more than 50 mg/kg. The Rules under Schedule I also identify that the production process of caustic soda and chlorine (when making use of the Mercury Cell Process) results in Mercury bearing sludge, which is considered hazardous waste. Under Schedule 8 of the Rules, Mercury and waste containing mercury and/or Mercury compounds are considered a hazardous waste which is regulated as per Hazardous Waste (Management, Handling & Transboundary Movement) Rules (2008). The Central Pollution Control Board (CPCB) has issued guidelines for the environmentally sound management of Mercury contained in fluorescent lamps (2008) and of Mercury containing products and wastes in health care facilities (2012). With regard to policy and regulation on Mercury, the Bureau of Indian Standards (BIS) has issued standards for the level of Mercury in fluorescent lamps, etc. Furthermore, standards have been set for emission of Mercury from Hazardous Waste incinerators, while guidelines have been prepared for the disposal of hazardous waste in secured landfills, wherein standards have been prescribed for Mercury containing wastes. The Government of India and its partners have also implemented/undertaken the following projects and initiatives: - In the Chlor-Alkali industry, 99% of producers originally using the Mercury cell process, are believed to have switched to state-of-the-art membrane cell technology (cleaner production), following recommendations made by the Charter on Corporate Responsibility for Environmental Protection (CREP) and as part of a voluntary programme (March, 2013) between the Government of India and the Chlor-Alkali Industry. As part of the National Clean Energy Fund (NCEF) Project, a study is underway for the remediation of a Mercury contaminated site located on the banks of the Rushikulya River in Ganjam, Odisha. - In the lighting manufacturing industry, for all types of energy-saving lamps, there has been a decline in Mercury content over time, thanks to technological advancement, the CPCB guidelines for the environmentally sound management of Mercury in the fluorescent lamp sector (2008) and voluntary actions from lighting manufacturers. - Energy Efficiency Service Limited (EESL), a public sector entity under the administrative control of Ministry of Power is implementing innovative programmes across India to realize the energy efficiency potential in home lighting and street lighting sectors. The Domestic Efficient Lighting Programme (DELP) started in Delhi on 1 June 2015 which would involve, in phases, door to door distribution of LED bulbs. Under this scheme, up to 4 high quality LED bulbs of 7 watt would be given at a cost of INR 93 each against a market price of INR 350-500. This will lead to reduction in use of Mercury in lighting sector and energy saving will be a co-benefit. - The Central Pollution Control Board (CPCB) has carried out a study on Mercury releases from coal based thermal power plants in Singrauli area in the state of Uttar Pradesh (UP). A study project entitled “Assessment of the Mercury Content in Coal fed to Power Plants and study of Mercury Emissions from the Sector in India” has been executed by Central Institute of Mining and Fuel Research (CIMFR) in partnership with MoEF&CC and UNEP. - In the health care sector, the following major initiatives have been undertaken: - The All India Institute of Medical Science (AIIMS) carried out a project on “Assessment of awareness of environmental Mercury pollution in health-care system: solutions and strategies for prevention”. - CPCB carried out an analysis of Mercury in wastewater generated by hospitals, wherein concentrations were indicated to be in the range of 1 µg/l to 4 µg/l, which is within stipulated standards. - CPCB published guidelines on ‘Environmentally Sound Management of Mercury Waste Generated From Health Care Facilities” - Guidelines were issued for the phase-out of Mercury containing Blood Pressure (BP) instruments and thermometers. Guidelines were issued to all Ministries/Central Government hospitals under the Ministry of Health and Family Welfare (MoHFW) for reducing environmental pollution due to Mercury pollution originating from hospitals and health centres. - The Clinical Establishment Act (2010) enacted by the Indian Parliament has already been adopted by 14 States/Union Territories so far. Under the Act, every hospital/health centre has to make use of Mercury-free Blood Pressure instruments and thermometers. As a result of this Act, the number of Mercury containing medical devices that is being purchased, has dropped significantly. - Under the UNDP GEF Global medical waste project (Demonstrating and Promoting Best Techniques and Practices for Reducing Healthcare Waste to Avoid Environmental Releases of Dioxins and Mercury: GEF ID 1802), India introduced the use of Mercury-free devices in model facilities and disseminated awareness-raising and educational materials related to Mercury. In Uttar Pradesh, King George’s Medical University hospital demonstrated best practices for the management of Mercury waste, including handling, clean-up and interim storage of Mercury and the promotion of Mercury-free alternative medical devices. - Dental Amalgam: A programme for the prevention of dental caries is part of the national oral health programme and included under school health programme activities which will also reduce amalgam filling and will lead to reduction of emission at cremation. Considering the fact that with its rapidly growing population, India will host the greatest increase in energy use in the world over the next decade, which is heavily reliant on coal-fired power stations and boilers. Mercury releases might significantly increase without significant actions and the introduction of best environment practices and best available techniques (BEP/BAT) and environmentally friendlier interventions are made to curtail potential Mercury releases. To date, India has not conducted an exhaustive inventory on Mercury import, export, use, stockpiles, emissions and releases. Even though Policy and Regulatory actions have been taken, most were mostly developed to counter Mercury emission and releases on a case-by-case basis. As such, there is a crucial need to undertake i) A holistic Mercury inventory; ii) Assess the Policy and Regulatory Framework pertaining to Mercury; iii) Prepare a Mercury Profile; iv) Propose short term and long term Mercury reduction interventions for emission and releases; and v) Identify National Priorities, Develop a National Action Plan and a Mercury Mainstreaming Roadmap. |
| --- | --- |
| B. Enabling Activity Goals, Objectives, and Activities (The proposal should briefly justify and describe the project framework. Identify also key stakeholders involved in the project including the private sector, civil society organizations, local and indigenous communities, and their respective roles, as applicable. Describe also how the gender dimensions are considered in project design and implementation): | The proposed EA and the project framework, including envisaged activities, are fully in line with the GEF Initial Guidelines for Enabling Activities for the Minamata Convention on Mercury (GEF/C.45/Inf.05). The Project’s objective is to strengthen India’s capacity to manage and monitor mercury use, import, export, stockpiles, emissions and releases throughout the country (with a particular focus on thermal power generation and cement production) and enable India to take an informed decision on ratifying the Minamata Convention and enabling it to meet future obligations under the Convention. Specifically, the project is organized according to the following framework (additional details on project activities and outputs are provided in Section C.): 1. Assessment of institutional capacity to manage and monitory Mercury. Build national capacity to undertake mercury inventories so as to support national decision making on Mercury, through: - Establishment of a national Mercury coordination and identification of institutional gaps. - Capacity building and training to undertake the mercury inventory. - Raising awareness on Mercury, specifically targeting policy makers, implementing entities, private sector and population groups at risk. 2. Undertake an assessment of legal, policy, regulatory, technical and financial needs and gaps that need to be addressed to meet Minamata Convention obligations, and agree upon recommended actions to address these needs and gaps. The legal and policy review will assess the following Minamata Convention provisions: - Article 3 (Mercury Supply Sources and Trade) - Article 4 (Mercury added products) - Article 5 (Manufacturing processes in which mercury or mercury compounds are used) Article 7 (Artisanal and small-scale gold mining - including legislation and policy to cover formalization, worker health and safety); - Article 8 - Emissions (specifically in regard to relevant national air pollution/emission standards and regulations); - Article 9 - Releases (specifically in regard to the ability to identify and categorize sources of releases). The policy and legislative assessment will be undertaken through a review of existing legislation on chemicals management and identification of the gaps prevalent in association to Mercury aspects. The project will make use of the guidelines currently prepared/under preparation by UN agencies. Given that environment related issues are both subjects covered under National level and State level regulations, the assessment would identify gaps at both levels. Furthermore, as part of this project component, institutional capacity of governmental institutions and agencies, national level and state level, will be assessed to determine the capacity that already exists and outstanding needs and gaps that need to be addressed for implementation of the Minamata Convention. The assessment will also review the systems needed to report to the Convention under Article 21. A Mercury Initial Assessment Report will be prepared that will provide an overview of the structures, institutions, legislation etc. already available to implement the Minamata Convention, as well as an overview of identified barriers (legal, policy, regulatory, technical, etc.) that need to be addressed to meet Minamata Convention obligations. The Mercury Initial Assessment Report will also include proposed actions and interventions to overcome identified barriers. 3. Develop a National Mercury profile The project component will conduct a Mercury inventory covering the entire country. In addition a detailed Mercury inventory will be conducted focusing on all five sectors as per Annex D of the proposed Minamata Convention on Mercury (including Mercury releases) (Annex A Part I and Annex B of Mercury compounds of the proposed Minamata Convention on Mercury.) By adapting internationally accepted methodologies to national/local context, the project will develop a detailed national mercury inventory, which will include: - Sectors that (a) use mercury and the amount used per year along with their industry structure and manufacturing/process details, and (b) emission and release of mercury including manufacturing process details. To the extent feasible, use and emission and release of mercury including those relating to mercury added products would be assessed; - Identify a) emission sources of mercury; and, b) release sources of mercury to land and water. - Stocks of mercury and/or mercury compounds and import and export procedures including an assessment of the storage conditions; - Supply of mercury, including sources such as imports, local production as well as recycling activities and quantities; - Trade in mercury and mercury containing compounds in terms of imports/exports. The findings of the assessment will be presented in the National Mercury profile. 4. Identify environmentally sound schemes to reduce Mercury use, emission and releases. The project will conduct pilot studies/assessments in major polluting sectors with the aim to identify (technology) interventions and formulate long-term project concepts to reduce emission and releases/phase-out of Mercury in these sectors. 5. Develop a national Mercury Action Plan and Mercury Mainstreaming Roadmap Making use of the various guidance documents prepared by UNITAR on priority setting in the area of chemicals management, the project will identify priority sector and activities. Based on the priorities selected, a national Mercury Action Plan will be drafted as well as a Roadmap for the Mainstreaming of Hg Priorities developed. The Mercury Action Plan will identify not only the priorities to be addressed, by which means and within which time-frame, but will also identify financial needs for implementation of the Minamata Convention, including resources from the GEF, national budget allocations, bilateral sources, private sector resources, among others. In turn the Roadmap for the Mainstreaming of Hg Priorities will have the objective to ensure that Mercury related priorities are taken up in national and local development plans, as well as sector strategies, to ultimately ensure that government budget allocations are secured/assured for implementation of Mercury related interventions/activities. The National Mercury Action Plan and Mercury Mainstreaming Roadmap will be submitted for national adoption/approval. |
|  | Key Stakeholders The key stakeholder involved in the project are mainly the following: Ministry of Environment, Forest and Climate Change (MoEF&CC) – Leads the development and improvement of the policy and regulatory framework pertaining to environmental protection, such as National Environmental Policies, Environmental Management Acts and its Regulations, programmes and projects. The Ministry also coordinates all Mercury related activities in India, with a dedicated focal point for implementation of the Minamata Convention and its provisions. Ministry of Commerce and Industry – Provides policies pertaining to the operations of non-ferrous, chlor-alkali, dental amalgam, Mercury-added products and cement manufacturers and coordinate policies on mercury-added products (import/export). Ministry of Power – Ensures that electricity systems function with reliability and productivity, and promotes innovation in the energy sector. Ministry of Finance – Determines opportunities for mainstreaming existing financial mechanisms that will support the sound management of chemicals including Mercury. Ministry of Coal – Formulates and administrates the rules and regulations and laws relating to mines. Responsible for survey and exploration of all minerals. Ministry of Health and Family Welfare – Develops, implements and monitors health policies, regulations and standardization. In addition, the Ministry registers medical devices and monitors companies that import, manufacture, distribute and/or store medical equipment and devices. State Government Institutions and Municipalities/City Councils – Regulate and supervise waste management in municipalities/districts/councils and are responsible for hazardous waste storage and disposal. Research institutes/Academia – Assist in monitoring Mercury and POPs in air, soil and water and support the development and implementation of policies to fulfill obligations under the Minamata Convention. These include the Central Pollution Control Board (CPCB), National Environmental Engineering Research Institute (NEERI), National Council for Cement and Building Materials (NCCBM), State Pollution Control Boards (SPCBs), Department of Dental & Oral Surgery Lady Hardinge Medical College (LHMC), Division of Agricultural Chemicals in Indian Agricultural Research Institute (IARI), India Institute of Toxicology Research (IITR), among others. Private Sector/industry associations – Involved in various important aspects of the proposed project: Private companies/industries responsible for the release of Mercury and production of Mercury containing wastes; Services providers involved in waste collection, disposal and treatment; Distributors and retailers of Mercury containing and Mercury-free consumer products; Laboratories for testing and certification; etc. These partners will assist in the planning of interventions for future technology transfer and demonstration of Mercury-free production methods to promote cleaner production in India’s industrial sector. Civil Society Organizations and Non-Governmental Organizations (CSOs/NGOs) – Engaged in information outreach to local communities at risk, the general public and decision makers on the environmental and health aspects and concerns of Mercury releases and accumulation in the environment. The MIA will pay particular attention to assessing national capacity to keep such risk groups safe. Awareness raising and training conducted as part of the MIA will be specifically tailored to also reach out to such risk groups. Recommendations on how to improve gender dimensions and gender mainstreaming related to Mercury, and priorities actions in this area will also be highlighted in the Mercury Profile as well as the Mercury Action Plan and Roadmap for the Mainstreaming of Hg Priorities. |
| C. Describe the Enabling Activity and Institutional Framework for Project Implementation (discuss the work intended to be undertaken and the output expected from each activity as outlined in Table A). | The project will be implemented through the National Implementation Modality (NIM) with the MoEF&CC as the execution agency, which will also assume the role as the chair of the National Project Steering Committee (NPSC). The Hazardous Substances Management (HSM) division of the Ministry will be the responsible unit for the implementation of the project and a Project Management Unit (PMU) with a National Project Director and project coordinator will be established within MoEF&CC to coordinate the implementation of day-to-day project activities and act as the secretariat of the NPSC. The NPSC will be established as an inter-ministerial Steering Group comprised of technical and policy experts from MoEF&CC, other relevant ministries, industrial association, academia and NGOs to provide overall guidance and coordination for the implementation of the project and relevant activities. A Project Expert team comprised of national and international consultants will be contracted to provide technical support for the project’s implementation. The team will be selected based on technical expertise to support appropriate policy and legal gap analysis, assist in development of the various project related assessments and reports and plan activities for institutional capacity development. 1. Build National capacity to support national decision making on Mercury and to undertake Mercury inventories A national decision-making structure on Mercury (“Mercury Coordination/Consultation Mechanism (MCM)”) will be established in line with national capacity and existing structures and practices present in the country and where feasible will build/expand on similar structures established in support of other chemicals-related MEAs. National capacity to undertake the Mercury Inventory will be built through training, which will be conducted and facilitated by the project’s international/national technical experts. Training will be provided on data collection methodologies, reliability, credibility, data analysis, etc. Training will be targeted towards a group of national technical experts who will conduct and develop the National Mercury Profile. Training will also include key government representatives who make up the Mercury Coordination/Consultation Mechanism and who require sufficient knowledge about conducting a Mercury Inventory to be able to ultimately review and comment on it. Finally, as part of this project component, the project will raise awareness on the risks of Mercury and Mercury-associated impacts on human health and the environment. Awareness raising activities and campaigns will be tailored to priority recipients (in line with national priorities and resource availability), which are expected to include policy makers, the general public, national and local implementing and enforcing entities, private sector partners and population groups at risk (at National as well as State level). 2. Undertake an assessment of legal, policy, regulatory, technical and financial needs and gaps that need to be addressed to meet Minamata Convention obligations, and agree upon recommended actions to address these needs and gaps The policy and legislative assessment will be undertaken through a review of existing legislation on chemicals management and Mercury in specific and identification of the gaps prevalent in association to Mercury aspects. The project will make use of the guidance developed/currently under preparation by UN agencies on how to conduct the policy and legislative assessment. Given that environment related issues are both subjects covered under National level and State level regulations, the assessment would identify barriers, gaps and needs at both levels. Specifically, the policy and legislative assessment will assess the country’s readiness and capacity to implement the following Minamata Convention provisions as per Articles 3,4,5,6,7,8 & 9. Furthermore, as part of this project component institutional capacity of governmental institutions and agencies, national level and state level, will be assessed to determine the capacity that already exists and outstanding needs and gaps that need to be addressed for the implementation of the Minamata Convention. The assessment will also review the systems needed to report to the Convention under Article 21. In summary this project component will: - Assess/review legislation and regulations pertaining to the governance of chemicals in general and Mercury in specific; identify gaps and barriers for meeting the Minamata Convention requirements; and make recommendations for proposed amendments. - Assess the capacities and roles of the key institutions currently having responsibilities related to the management of Mercury. These institutions will include (but not be limited to) those listed in section B above, including institutions at state level. Recommendations will be proposed for further capacity development. - Assess monitoring capacity (in terms of compliance and in terms monitoring Hg levels in various environmental media as well as biological samples) of state institutions and national and state laboratories. Recommendations will be made for further improvements. Based on the findings from the conducted assessments, a Mercury Initial Assessment Report will be prepared that will provide an overview of the structures, institutions, legislation etc. already available to implement the Minamata Convention, as well as an overview of identified barriers (legal, policy, regulatory, technical, etc.) that need to be addressed to meet Minamata Convention obligations. The Mercury Initial Assessment Report will also include proposed actions and interventions to overcome identified barriers. The Mercury Initial Assessment Report will provide the Government of the Republic of India with good insight in order to later on make an informed decision on ratifying the Convention. The Mercury Initial Assessment Report will be discussed and reviewed by the “Mercury Coordination Mechanism. “The results of these discussions will direct the work on Mercury inventory, the preparation of the National Mercury Profile and the development of the Mercury Action Plan as mentioned. 3. Develop a National Mercury profile The project component will conduct a high-level Mercury inventory covering use, import, export, stockpiles, emissions and releases of Mercury. In addition a detailed Mercury inventory will be conducted focusing on the two most polluting sectors (in terms of Mercury releases), which are expected to be the thermal power generation and cement production sectors. By adapting internationally accepted methodologies to national/local context, the project will develop a national mercury inventory as per Section B.3 above. The inventory will make use of the UNEP "Toolkit for identification and quantification of mercury releases" which is intended to assist countries to develop a national mercury release inventory. It provides a standardized methodology and accompanying database enabling the development of consistent national and regional mercury release inventories. Additionally, in order to conduct the part of the inventory related to stockpiles, guidance under preparation by UNIDO would be applied. Finally, a small subset of the Mercury Inventory will focus on an assessment of the practices surrounding the use and application of dental amalgam among dental health care professionals in India. The subject of the inventory will assess current awareness levels on the impacts of Mercury as a result of the application of dental amalgam, extent to which dental amalgam is used, current waste management practices, etc. Outcomes of this assessment are expected to raise more awareness on the issue but also shape future policies and guidelines for safe Mercury use among dental healthcare professionals and ultimately a move towards alternatives. After completion of the data gathering stage, a National Mercury Profile, including significant sources of emissions and releases, as well as inventories of Mercury and Mercury compounds, will be prepared for review, approval and adoption by the Minamata Convention Mechanism during a national stakeholder workshop. 4. Identify environmentally sound schemes to reduce Mercury use, emission and releases The project will conduct pilot studies/assessments in the major polluting sectors with the aim to identify (technology) interventions and formulate long-term project concepts to ultimately significantly reduce releases/phase-out of Mercury in the sectors. These assessments are expected to identify best practices to reduce and minimize Mercury releases. Furthermore, project concepts will identify various finance sources (including resources from the GEF, national budget allocations, bilateral sources, private sector resources, among else) with the expectation that when these finance sources are sequenced they would be sufficient to make the investments necessary to address the Mercury challenges faced by these sectors. 5. Develop a national Mercury Action Plan and Mercury Mainstreaming Roadmap Following the finalization of the project activities as envisaged under component 1 - 4 the national project team will prepare a National Action Plan. Based on the findings from the legal, policy, regulatory, technical and financial needs and gaps assessment as presented in the Mercury Initial Assessment Report and the result of the Mercury Inventory as presented in the Mercury Profile, making use of the various guidance documents prepared by UNITAR on priority setting in the area of chemicals management, the project will identify priority sector and activities. Based on the priorities selected, a national Mercury Action Plan will be drafted. Expert teams composed of national stakeholders and national and international experts will draft proposals for actions to be included in Mercury Action Plan on how to address the current gaps and barriers for implementation of the Minamata Convention. These proposals will also include an overview of the costs to stakeholders (national and state government, private sector, state and research institutions, etc.) in meeting the country’s obligations under the Minamata Convention. The Mercury Action Plan will identify not only the priorities to be addressed, propose interventions and a time-frame, but will also identify financial needs for implementation of the Minamata Convention, including resources from the GEF, national budget allocations, bilateral sources, private sector resources, among else. After the development of the draft Mercury Action Plan it will be reviewed by all project stakeholders and discussed during a national stakeholder workshop, which will then be submitted for national adoption/approval. Secondly, the project will also develop a Roadmap for the Mainstreaming of Mercury Priorities. The roadmap will lay-out a plan for the mainstreaming of the national priorities taken up in the Mercury Action Plan with the objective to ensure that Mercury related priorities are taken up in national and local development plans, as well as sector strategies, to ultimately ensure that government budget allocations are secured/assured for implementation of Mercury related interventions/activities. After its development, the Roadmap for the Mainstreaming of Mercury Priorities will be submitted for national adoption/approval. Annex I (attached separately) indicates a total estimation of the GEF grant budget breakdown. |
| D. Describe, if possible, the expected cost-effectiveness of the project: | The cost-effectiveness of the project will be assured through management of the project by creating synergies with other chemicals-related projects (e.g. POPs). The project will as much as possible engage national expert and industry association inputs to facilitate the collection of accurate information and to establish high-responsiveness and project ownership among stakeholders to keep a steady momentum in project implementation. An international technical advisor is expected to provide succinct, specific inputs where local expertise gaps exist. This will support developing local and national capacity to manage Mercury and will contribute to the cost effectiveness of the project through reduced consultancy fees and travel expenses. Awareness creation among the general public and specific target communities at risk will be optimized through building upon existing on-going activities and working with local CSOs/NGOs. As per the GEF guidelines, MIAs should normally not exceed USD$ 200,000. However, based on the fact that (i) India is a developing economy with a lot of emphasis on coal based thermal power and cement production; reductions achieved in India will in turn provide significant global and local benefits; ii) Mercury is widely used in industrial applications and health sector in India and has the potential to be managed systematically; iii) India has not conducted formal Mercury inventory work, the additional USD$ 800,000 would be justified to ensure that national and local stakeholders, industries included, are fully engaged and cooperate to prepare an accurate Mercury Initial Assessment Report, National Mercury Profile, Mercury Action Plan and Roadmap for the Mainstreaming of Mercury Priorities. Lessons learned and experience gained from these project activities can be replicated in other countries to effectively address Mercury issues. |
| E. describe the budgeted M&E Plan: | Project monitoring and evaluation will be conducted in accordance with established UNDP and GEF procedures and will be described in detail in the project’s Project Document. |
| F. Explain the Deviations from typical Cost Ranges (where applicable): | N/A |

part iii:  approval/endorsement by gef operational focal point(s) and GEF agency(ies)

A.   Record of Endorsement of GEF Operational Focal Point(s) on Behalf of the Government(s): (Please attach the Operational Focal Point endorsement letter(s) with this template).

| Name | Position | Ministry | Date (Month, day, year) |
| --- | --- | --- | --- |
| Mr. Susheel Kumar | GEF Operational Focal Point | Ministry of Environment, Forest & Climate Change | 05/18/2015 |

B. Convention Participation

| Convention | Date of Ratification/ Accession (mm/dd/yyyy) | National Focal Point |  |
| --- | --- | --- | --- |
| UNCBD | 05/19/1994 | Ministry of Environment, Forest & Climate Change |  |
| UNFCCC | 08/26/2002 | Ministry of Environment, Forest & Climate Change |  |
| UNCCD | 12/17/1996 | Ministry of Environment, Forest & Climate Change |  |
| Stockholm Convention | 05/14/2002 | Ministry of Environment, Forest & Climate Change |  |
|  | Date Signed (mm/dd/yyyy) | National Focal Point | Date of Notification under Article 7 to the Minamata Convention Secretariat |
| Minamata Convention | 30 September 2014 | Ministry of Environment, Forest & Climate Change |  |

C.  GEF Agency(ies) Certification

| This request has been prepared in accordance with GEF policies and procedures and meets the standards of the GEF Project Review Criteria for Chemicals and Wastes Enabling Activity approval in GEF 6. |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Agency Coordinator, Agency name | Signature | Date (Month, day, year) | Project Contact Person | Telephone | E-mail Address |
| Ms. Adriana Dinu UNDP-GEF Executive Coordinator |  | 6/24/2015 | Mr. Jacques Van Engel Director MPU-Chemicals | +1 (212) 906-5782 | jacques.van.engel@undp.org |

Project ID number will be assigned by GEFSEC and to be entered by Agency in subsequent document submission.

Co-financing for enabling activity is encouraged but not required.

This is the cost associated with the unit executing the project on the ground and could be financed out of trust fund or co-financing sources. For EAs within the ceiling, PMC could be up to 10% of the Subtotal GEF Project Financing.

From the presentation made by a representative of light manufacturing industry at UNEP Mercury workshop on 19 Sept 2014

http://www.cpcb.nic.in/Guidelines_for_ESM_%20MercuryW_fromHCFs.pdf

http://nrhm.gov.in/nhm/nrhm/guidelines/indian-public-health-standards.html

http://www.unep.org/chemicalsandwaste/Mercury/MercuryPublications/GuidanceTrainingMaterialToolkits/MercuryToolkit/tabid/4566/language/en-US/Default.aspx