GEGEF-6 REQUEST FOR chemicals and wastes enabling activity

Proposal for Funding Under the GEF Trust Fund

For more information about GEF, visit TheGEF.org

part i:  project IDentifiers

| Project Title: | Development of Minamata Initial Assessment and Updating of National Action Plan for Artisanal and Small Scale Gold Mining in Indonesia |  |  |
| --- | --- | --- | --- |
| Country(ies): | Indonesia | GEF Project ID: |  |
| GEF Agency(ies): | UNEP | GEF Agency Project ID: | 01470 |
| Other Executing Partner(s): | Ministry of Environment and Forestry | Submission Date: | December 1, 2016 |
| GEF Focal Area (s): | Chemicals and Wastes | Project Duration (Months) | 24 |
| Type of Report: | National Action Plan | Expected Report Submission to Convention | 24 months after receipt of the first cash advance by participating country. |

- Project Framework*

| ### Project Outcome: Minamata Initial Assessment and National Action Plan for the ASGM sector developed and endorsed by the national government and key stakeholders facilitating the ratification and early implementation of the Minamata Convention in Indonesia. |  |  |  |
| --- | --- | --- | --- |
| ### Project Objective: Ratification and early implementation of the Minamata Convention contributes to the protection of human health and the environment from the risks posed by unintentional and intentional emissions and releases, unsound use and management of mercury in Indonesia. |  |  |  |
| ### Project Components | ### Project Outputs | ### (in $) |  |
|  |  | ### GEF Project ### Financing | ### Confirmed Co-financing |
| ### Global technical support for NAP development | - Training and guidance provided to relevant national stakeholders in Indonesia to develop a MIA and develop and implement a NAP as per Annex C of the Minamata Convention | ### 71,800 |  |
| - Minamata Initial Assessment (MIA) and National Action Plan (NAP) development | - Identified and strengthened national coordination mechanisms and stakeholder advisory groups that will guide the project implementation - National institutional and regulatory framework and national capacities on mercury management assessed - National inventories of mercury sources and releases and strategy for the identification of mercury contaminated sites developed - Challenges, needs and opportunities to implement the Minamata Convention assessed and recommendations to ratify and implement the Minamata Convention developed - Draft NAP developed as per Annex C of the Minamata Convention | 513,364 | 0 |
| - MIA validation and NAP endorsement and submission to the Minamata Secretariat | - Technical support provided to participating country to facilitate the MIA validation and NAP endorsement and submission to the Minamata Secretariat. | 31,200 |  |
| Subtotal |  | 616,364 | 0 |
| Project Management Cost |  | 63,636 | 0 |
| Monitoring and Evaluation |  | 20,000 | 0 |
| Total Project Cost |  | 700,000 | 0 |

*   List the $ by project components.  Please attach a detailed project budget table that supports all the project components in this table.

- Source of Co-financing for the Project by Name and by Type

| Sources of Co-financing | Name of Co-financier | Type of Co-financing | Amount ($) |
| --- | --- | --- | --- |
| NA |  |  |  |
| Total Co-financing |  |  | 0 |

- GEF Financing  Resources Requested by Agency,  Country and Programming of Funds

| GEF Agency | Trust Fund | Country/ Regional/ Global | Focal Area | Programming of Funds | (in $) |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | GEF Project Financing (a) | Agency Fee (b)b) | Total (c)=a+b |
| UNEP | GEFTF | Indonesia | Chemicals and Wastes | Mercury | 700,000 | 66,500 | 766,500 |
| Total GEF Resources |  |  |  |  | 700,000 | 66,500 | 766,500 |

a) Refer to the Fee Policy for GEF Partner Agencies

part ii:  Enabling Activity JustiFication

- Enabling Activity Background and Context

The Mercury Convention was adopted in January 2013 and will come into force once the required number of countries ratifies the Convention. The Minamata Convention on Mercury identifies and describes in its Article 13 the financial mechanism to support Parties from developing countries and countries with economies in transition to implement the Convention.  It identifies two entities that will function as the Financial Mechanism: a) the Global Environment Facility Trust Fund; and b) A specific international Programme to support capacity-building and technical assistance. As such, the GEF Assembly, at its fifth meeting, held in May 2014, agreed to an allocation in its sixth replenishment of $141 million for work under the Convention, out of which $30 million to support enabling activities and promote their integration into national budgets and planning processes, national and sector policies and actions and global monitoring.

The revised GEF initial guidelines for enabling activities for the Minamata Convention on Mercury circulated to the GEF Council members in January 2014 presented in its section 1 the initial guidelines for the development of “Minamata Initial Assessment activities” (MIA) and in its section 2 the guidelines for the preparations of Artisanal and Small-Scale Gold Mining (ASGM) National Action Plans (NAPs) required under article 7. These guidelines were revised by the Intergovernmental Negotiating Committee 6 (INC 6) consistent with the resolution adopted by the Conference of Plenipotentiaries on the Minamata Convention on Mercury. The draft guidance was introduced to the INC 7 as an annex of the document UNEP(DTIE)/Hg/INC.7/17. It was agreed that the guidance in its current form would be used to assist countries in the preparation of their action plans in the period between the current session and the first meeting of the Conference of Parties. This project follows the guidelines introduced in the INC 7 and will seek for comments from Governments to improve the guidance with a view to presenting a revised version of it for consideration and possible adoption by the Conference of the Parties at its first meeting.

The project also contributes to the achievement of the expected accomplishment A under the UNEP biennial Programme of Work (PoW) 2016-2017 “countries increasingly have the necessary institutional capacity and policy instruments to manage chemicals and waste soundly, including the implementation of related provisions in the multilateral environmental agreements”. The MIA and NAP development contributes in particular to the PoW output 2 “secretariat support provided to the intergovernmental negotiating committee to prepare a global legally binding instrument on mercury (the Minamata Convention on Mercury) during the interim period, prior to its entry into force”. Through this project UNEP will provide national stakeholders with the policy and technical instruments needed to ratify the Minamata Convention and will strengthen the national institutional capacity to its early implementation. It will also apply and comment the NAP guidance as required by the INC 7. The outcomes of this project are also aligned with the objectives of the proposed PoW and budget for the biennium 2018-2019 approved by UNEA in 2016, expected accomplishment A, policies and legal, institutional and fiscal strategies and mechanisms for sound chemicals management developed or implemented in countries within the framework of relevant multilateral environmental agreements and the Strategic Approach to International Chemicals Management (SAICM).  The project will contribute to the indicator of achievement by increasing the number of countries that have used UNEP guidance in developing an Action Plan that promotes sound mercury management and implement the Minamata Convention.

Mercury pollution is a serious concern in East and Southeast Asia, accounting for about 50% of the global total anthropogenic mercury emissions to the atmosphere.  Indonesia has indicated that availability of data is a major challenge to design adequated strategies for mercury reduction. Indonesia will benefit from new and updated information about the mercury situation in the country and from increased capacity in managing the risks of mercury, in particular from the ASGM sector. Indonesia will also be in compliance with the article 7 of the Minamata Convention. The sharing of experiences and lessons learned throughout the project is also expected to be an important contribution to other similar countries within region.

SDGs in Indonesia

The NAP development and future implementation contribute to achieve the following Sustainable Development Goals in Indonesia:

- Sustainable Development Goal (2) ensures healthy lives and promotes well-being for all at all ages. The NAP has strategies to prevent the exposure of vulnerable populations to mercury emissions and releases from the ASGM sector and consequently contributes to reduce the number of deaths and illnesses from hazardous chemicals (target 3.9). Indirectly, the positive impacts over population’s health also contribute to the Sustainable Development Goal (1) - end poverty in all its forms everywhere. Many ASGM miners are trapped in a vicious cycle of poverty due, among others to the burden with the costs associated with the deterioration of the miner’s health (target 1.2);

- Sustainable Development Goal (8) promotes inclusive and sustainable economic growth, employment and decent work for all. The NAP will identify the steps needed to facilitate the formalization of the ASGM sector and will develop strategies to promote the reduction of emissions releases, and exposure to mercury in the ASGM sector. These measures will improve the working conditions of miners, in particular through the elimination of worst practices of mercury use in ASGM and a broader access to mercury-free methods (target 8.3, 8.4);

- The project will also indirectly contribute to achieve the Sustainable Development Goal (5) achieve gender equality and empower women and girls. This will be done through the collection of disaggregated data by sex, the participation of stakeholders from both sexes in the consultations and the inclusion of gender sensitive indicators in the project logical framework. As part of the NAP, strategies to prevent exposure of vulnerable populations, particularly children and women of child-bearing age, especially pregnant women, to mercury use in ASGM will be developed. This strategy will contribute to the development of national sound policies and enforceable legislation for the promotion of gender equality and the empowerment of all women and girls at all levels (target 5c);

- Sustainable Development Goal (6) – ensure availability and sustainable management of water and sanitation for all. The NAP will contribute in particular to achieve the target 6.3 improving water quality by reducing the release of hazardous chemicals in the ASGM areas;

- Sustainable Development Goal (12) – ensure sustainable consumption and production patterns. The project will directly contribute to achieve the target 12.4 under this goal that is to achieve the environmentally sound management of chemicals and all wastes throughout their life cycle, in accordance with agreed international frameworks, and significantly reduce their release to air, water and soil in order to minimize their adverse impacts on human health and the environment. The NAP contributes to the environmentally sound management of mercury through the early implementation of the Minamata Convention.

National background information:

Indonesia signed the Minamata Convention on 10 October 2013 during the Diplomatic Conference (Conference of Plenipotentiaries), held in Kumamoto, Japan. On 05 August 2016 Indonesia notified the Minamata Secretariat that artisanal and small-scale gold mining and processing is more than insignificant in the country.

Indonesia was among the six countries that participated in the Global Mercury Project (GMP), implemented from 2002 to 2007 by UNIDO. The overall goal of the project was to demonstrate ways of overcoming barriers to the adoption of best practices and pollution prevention measures that limit the mercury contamination of international waters from artisanal and small-scale gold mining (ASGM). The project in Indonesia managed three sites: Galangan, Katingan District, Central Kalimantan; Tanoyan, Bolaang Mongondow District, North Sulawesi;  and Sekonyer Area, Kotawaringin Barat District, Central Kalimantan.  Each site had different cultures, infrastructure, processing methods, understanding and knowledge of health awareness, government capacity, affluence and other unique set of issues.

1) Galangan, Katingan District, Central Kalimantan

Gold mining in Galangan has been going on for more than 20 years. The gold field is located approximately 1 km from the vast Katingan River covering over 200 km2 area and extremely degraded from deforestation, desertification and mercury contamination as a result of artisanal gold mining. An assessment derived from satellite imagery by Dr. Kevin Telmer (University of Victoria, Canada) reported that between 1999 to 2002 mining operation claimed a rate of growth 8 km2 per year and only 30% (2.4 km2) of that was mined effectively, leaving the remainder as overburden pilling. Mercury contamination in the study area stems from processing ore in the mining field of Galangan and from amalgam burning in township of Kereng Pangi. It was estimated that a total of 3,000 to 4,000 kg of mercury were released in the study area during 2006 from both mine-sites and gold shops. Since then a mix of awareness raising with technology intervention resulted in adoption of cleaner technology, as well as significant changes in attitude and behaviour of the target population.

- In March 2007 a draft local regulation on ASM management was developed by the local government including general definitions, the management of mercury in mining business, the management of mercury in the business of processing (extracting) and trading gold, coaching and monitoring, sanctions, transitional provisions and closing provision.

2) Tanoyan, Bolaang Mongondow District, North Sulawesi

Different from the gold mining and processing techniques applied by miners in Central Kalimantan, miners in North Suloawesi had transitioned to cyanidation technology since early 2000, but mercury was still widely used especially for the need for ‘quic cash.’ It took between one to three months to acquire enough ground ore to operate a cyanidation tank through an entire cycle and most miners did not have sufficient capital on hand to pay for day-to-day expenses. The GMP project estimated in its baseline that perhaps up to one-third of the gold yield in North Sulawesi was still obtained using mercury in the whole ore amalgamation process. In Bolaang Mongondow District itself, it was estimated that more than 3,000 kg of mercury was lost to the environment annually.

The GMP project organized awareness activities in the region on the health hazards of mercury exposure and contamination, including in non-mining population through fish consumption or exposure via other media. Technology introductions were limited to sluice box introduction as a means of replacing whole ore amalgamation as a means of ‘fast cash,’ and retorts to recapture mercury during amalgam burning.

3) Sekonyer Area, Kotawaringin Barat District, Central Kalimantan

- Rasau and Aspai are two remote mining camps along the west side of Sekonyer River and located directly across Tanjung Puting National Park. The park not only provides native habitat for the endangered orang utan (pogmo pigmaeus), but also other protected tropical flora and fauna species. Mining for gold along Sekonyer River has been going on for over 20 years. Miners have cleared forested area to dig deep pits on land as well as pumping sediment with dredges on the river, negatively impacting the river ecology and threatening the protected area. Occasionally miners have crossed over into the park to explore for new deposit. Options for livelihood for most people are limited to illegal mining (gold and zircon), illegal logging or poaching, continuing the cycle of poverty and degrading the forested area further. The National Institute of Minamata Disease, Japan, provided his assistance to analyse total mercury and methyl mercury on fish and human’s hair collected by Friend of the National Park Foundation (FNPF). The results confirmed high concentration of total mercury in a few fish species consumed by the locals and relatively higher total mercury concentration in mining community than those of other occupations. Mercury contamination stems from processing ore and amalgam burning which commonly conducted in the kitchens, living room or porches of the rig owners.

- The GMP project conducted numerous awareness-raising activities on the health hazards of mercury and alternative technologies to reduce exposure.

- Indonesia has also benefited from the GEF funded project “Removal of Barriers to the Introduction of Cleaner Artisanal Gold Mining and Extraction Technologies » (GEF ID 1223). This global project was implemented by UNDP.

ASGM in Indonesia is conducted in 184 sub-districts at 30 provinces throughout Indonesia. The national government implementation plan aim at eliminating mercury usage for gold processing involving 11 stakeholders from various institutions. The National Action Plan to eliminate mercury usage for gold processing in Indonesia plans to formalize the activity in 22 cities.

Table 1. Mercury consumption in ASGM in Indonesia and calculation of associated emissions

| Country | Quality of data | ASGM Hg use, t |  |  | Percentage of total Hg applied to concentrate amalgamation | Percentage of total Hg applied to whole ore amalgamation | Emission Factor b | Year of most recent data | Mean air emission, t |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | min | mean | max |  |  |  |  |  |
| Indonesia | 4 | 122.5 | 175.0 | 227.5 | 17 | 83 | 0.33 | 2008 | 58.333 |

Table 2: Three major sources of mercury emissions in Indonesia, according to the Technical Background Report for the Global mercury Assessment 2013. Data from 2010.

| Sector Code | Activity Code | Estimate (min) | Emission estimate (Kg) | Estimate (max) |
| --- | --- | --- | --- | --- |
| Artisanal and small-scale gold production |  | 40833.333 | 58333.333 | 75833.333 |
| Non-ferrous metal production - Large scale gold production | Production of gold from large-scale mining | 36.036 | 5148.000 | 13384.800 |
| Coal Combustion | Combustion of brown coal (subbituminous Coals) | 2470.464 | 3921.372 | 5607.562 |

# Coordination with other activities

The assessment developed by the Minister of Environment and the National Autonomous University of Indonesia in 2011 entitled "National Assessment of the Use of Mercury in Indonesia, Report for the year 2011" will be the baseline for this project component. This document will be updated and Indonesia will hace access to improved data on mercury sources and releases. The project will also build on the findings and outcomes of the Global Mercury Project in Indonesia and the GEF funded project (GEF ID 1223) “Removal of Barriers to the Introduction of Cleaner Artisanal Gold Mining and Extraction Technologies ».

Participation in trainings and other relevant meetings

Indonesia has also actively participated at the Intergovernmental Negotiating Committees (INCs). Indonesia has also participated in the South East Asian Sub-Regional Workshop in Support for the Ratification and Early Implementation of the Minamata Convention on Mercury from 19 to 21 March 2014 in Kuala Lumpur, Malaysia. Indonesia has also participated in the Asia and the Pacific Regional Workshop in Support for the Ratification and Effective Implementation of the Minamata Convention on Mercury from 17 to 18 March 2015 in Jakarta, Indonesia.

- Enabling Activity Goals, Objectives, and Activities

The goal of the MIA and NAP development is to contribute to the implementation of the Minamata Convention through the reduction of the risks posed by the unsound use, management and releases of mercury, in particular in the ASGM sectors.  This goal contributes to the GEF focal area strategy 1 of the chemicals waste area which is “Develop the enabling conditions, tools and environment to manage harmful chemicals and wastes ».

Project objective: Ratification and early implementation of the Minamata Convention contributes to the protection of human health and the environment from the risks posed by unintentional and intentional emissions and releases, unsound use and management of mercury in Indonesia.

Project Components and Activities: The national MIA and NAP development has three components, which consists of the activities indicated below. Each component includes information on project outputs and activities.

Component 1: Global technical support for MIA and NAP development

# This project component will strengthen information exchange between stakeholders regionally/globally. As part of this, Indonesia will receive additional training and support to develop its MIA and NAP. Indonesia will have access to technical expertise and tools to facilitate the development of the MIA and NAP and information exchange, developed within the framework of the UNEP Global Mercury Partnership. The technical expertise and tools provided will respond directly to country needs identified. With this additional support Indonesia will be able to obtain feedback and rapid response to its queries on the development of the MIA and NAP and will also make full use of the existing capacities and expertise in the region and globally. Lessons learned identified through this project, in particular during the final lessons learned workshop will also be made available. It will identify opportunities for regional/global cooperation and synergies between countries working on their MIAs and NAPs.

Expected Outputs and planned activities:

  - Training and guidance provided to relevant national stakeholders in Indonesia to develop a MIA and develop and implement a NAP as per Annex C of the Minamata Convention.

    - Development of a roster of experts and collection of tools and methodologies for MIA and NAP development;

    - Capacity building trainings and assistance with baseline inventories;

    - Knowledge management and information exchange through the Global Mercury Partnership website and/or Partners websites and tools;

    - Final national workshop to identify lessons learned and opportunities for future cooperation in the NAP implementation. A gender session will be included in the workshop agenda.

Component 2: Minamata Initial Assessment (MIA) and National Action Plan (NAP) development, validation and endorsement

The National Coordination Mechanism (NCM) will be identified under this component. The NCM will coordinate and guide the implementation of the project while strengthening the synergies between institutions on management of chemicals, including mercury. Sectors that will participate in this process as part of the National Coordination Mechanism include representatives from health, environment, labor, finance, economy, industry, mining and energy sectors.

# In addition, the NCM will identify a stakeholder advisory group (SAG), composed of stakeholders who possess relevant knowledge and information, and whose collaboration and cooperation will be needed for the successful formulation of the MIA and NAP. The SAG will include relevant members of civil society with experience and knowledge in the national mercury uses and releases. A gender specialist will be identified in the country to participate actively in the NCM for mercury. The NCM will engage with the SAG at regular intervals and during all phases of the MIA and NAP development and direct feedback on these documents will be provided through a mechanism to be agreed upon by the NCM. A list of suggested members of the NCM and of the SAG can be found at page 9-10 to the guidance document for NAP development. It will be complemented by relevant stakeholders of other sectors during the inception workshop. It is expected that these broader consultations will enhance stakeholder’s commitment to the development of the MIA and the NAP and gain political support for the ratification and early implementation of the Minamata Convention on Mercury.

After the establishment of the NCM and SAG the project will proceed with the assessment of national capacities on mercury management (technical, administrative, infrastructure and regulatory) taking into account the obligations under the Minamata Convention. This review and assessment will result in a preliminary identification of national needs and gaps for the ratification and early implementation of the Minamata Convention. The assessments produced under this component will provide Ministries with strong arguments for the ratification of the Minamata Convention and prioritization of mercury management on the national agenda. Once the Convention is ratified, this component outputs will be essential to comply with the reporting obligations of the Convention and to monitor its implementation. Gender issues and the interests of vulnerable populations will be fully taken into account in the assessments.

Considering the specific challenges of the ASGM sector, the national assessment will be complemented by a national overview of the ASGM sector including information on the following topics:

- Baseline estimates of mercury emissions and releases from the ASGM sector;

- Structure of the ASGM sector (i.e., single family miners, community mines, etc.);

- Policies surrounding ASGM at regional/local levels;

- Geographic distribution of ASGM;

- Economics, such mercury supply, use and demand. The project will search in particular for information about gender and children aspects of the ASGM economics;

- Size of the formal and informal ASGM economy;

- Information on mining practices, including information on ore bodies exploited, processes used, the amount of mercury used, the number of people directly involved in ASGM and indirectly exposed to mercury (disaggregated by sex and age);

- Information on gold processing practices/burn off of mercury in gold processing shops or community retorts;

- Known information on overall environmental impacts, contaminated sites, mercury releases in soil, air and water;

- Studies and other information on mercury exposure, through various media, and studies on impacts in ASGM communities and downstream communities. The project will search for known information desegregated by sex and age;

- Information about access to technical assistance for miners;

- Leadership and organization of ASGM at national and local levels;

- Experiences in addressing ASGM;

- Information gaps at the local and national scale that can be addressed.

# The project will search for known information desegregated by sex and age.

For the NAP development, Indonesia will apply the Artisanal Gold Council methodology to develop the inventory of mercury releases from the Artisanal and small-scale gold mining sector (Article 7).

For all the other sectors, Indonesia will develop a mercury inventory using the UNEP Toolkit for Identification and Quantification of Mercury Releases Level 2 that was revised in 2013. More specifically, the mercury toolkit will assist Indonesia to address: a) Mercury supply sources and trade (Article 3); (b) Mercury-added products (Article 4); (c) Manufacturing processes in which mercury or mercury compounds are used (Article 5); (d) Emissions (Article 8); and (f) Releases (Article 9).  It will also include a description of mercury storage conditions.

This project component will also analyse existing information on mercury contaminated sites and will formulate a strategy to identify and assess mercury contaminated sites, using a nationally agreed criteria.

Taking into consideration the national assessments developed, this project component will identify the challenges, needs and opportunities to implement the Minamata Convention on priority sectors. It will prepare a list of recommendations to implement the Minamata Convention on Mercury, taking into consideration the role of all key players and their responsibilities, in particular gender concerns and the special needs of vulnerable groups.

Finally, the draft MIA is developed. The draft NAP is also developed according to Annex C of the Minamata Convention.

Expected Outputs and planned activities:

  - Identified and strengthened national coordination mechanism and stakeholder advisory group that will guide the project implementation

    - Organize a National Inception Workshop to raise awareness and to define the scope and objective of the MIA and NAP processes, including:

- Develop ToR for the National Coordination Mechanism and Stakeholder Advisory Group;

- Develop a strategy for awareness raising aimed at national stakeholders throughout the project;

- Identify key stakeholders and assign roles.

    - Conduct a national assessment on existing sources of information (studies), compile and make them available.

  - National institutional and regulatory framework and national capacities on mercury management assessed.

    - Assess key national stakeholders, their roles in mercury management and institutional interest and capacities;

    - Analyse the regulatory framework, identify gaps and assess the regulatory reforms needed for the ratification and early implementation of the Minamata Convention in Indonesia.

  - National inventories of mercury sources and releases and strategy for the identification of mercury contaminated sites developed.

    - Develop a qualitative and quantitative inventory of all mercury sources, emissions and releases;

    - Develop a national strategy to identify and assess mercury-contaminated sites;

  - Challenges, needs and opportunities to implement the Minamata Convention assessed and recommendations to ratify and implement the Minamata Convention developed

    - Conduct a national and sectoral assessment on challenges and opportunities to implement the Convention in key priority sectors;

    - Develop a report on recommendations to ratify and implement the Minamata Convention on Mercury.

  - Draft NAP developed as per Annex C of the Minamata Convention.

    - Development of the national overview of the ASGM sector according to the NAP guidance by local teams;

    - Organize national workshops to develop the draft NAP and a roadmap for NAP endorsement and submission to the Minamata Secretariat.

Component 3: MIA validation and NAP endorsement and submission to the Minamata Secretariat

# This project component will build on the national consultations initiated in the activity 1.1.3 and support the participating country in the process of endorsement and official submission of the NAP to the Minamata Secretariat. Under Article 7 of the Minamata Convention, after developing its NAP, a country must “ submit its National Action Plan to the Secretariat no later than three years after entry into force of the Convention for it or three years after the notification to the Secretariat, whichever is later”. The final MIA will also be validated and will allow the National Government to ratify and early implement the Convention based on a sound national assessment of the mercury situation. Awareness raising and dissemination of key MIA outputs and the NAP for the ASGM sector will also be performed under this project component under activity 3.1.4.

  - Technical support provided to the participating countries to facilitate the MIA validation and NAP endorsement and submission to the Minamata Secretariat.

    - Draft and validate MIA Report;

    - Design and conduct national workshops targeting vulnerable groups and miners to complete the final NAPs and to expose the formulated NAPs on ASGM to public consultation and endorsement;

    - Design and conduct national workshops targeting appropriate national decision makers that are decisive to NAP endorsement and official submission to the Minamata Secretariat;

    - Develop a national MIA and NAP awareness raising and dissemination and outreach strategy.

Project Stakeholders:

At the international level, the project will include:

    - UNEP DTIE Chemicals: as an implementing Agency, UNEP will provide technical oversight and administrative support to the National Coordinating agency and the National Coordinator. UNEP will also provide the global perspective and experience from other countries.

    - UNEP Regional Office for Asia and Pacific (ROAP), which will identify opportunities for regional synergies and areas of cooperation. Some examples may include: coordination of regional information exchange and provision of documents and inventories from other countries in the region, identification of regional experts, etc

    - The Minamata Convention Secretariat will provide guidance materials and opportunities to exchange information and to understand the Minamata Convention from a regional and global perspective.

    - Joint Secretariats BRS will provide areas of cooperation and synergies with POPs related activities.  The project will also consider using the existing resources at the BRS Secretariat level, such as facilities to provide technical support (webinars) organization of training workshops, etc.

    - Others: such as the regional/national representation of WHO, to provide the human health dimension to the project, such as the identification of mercury related activities and human risk. It will also provide opportunities for cooperation by making available its mercury programme and suitable expertise on mercury and humans.

The international partners will provide ongoing support to the project.

The following table outlines key national stakeholders in Indonesia, together with their proposed respective roles within the project.  The following list of stakeholders, prepared in consultation with the national government, will be expanded during project implementation.

Table 3: Stakeholder Participation

| Name of stakeholder/Organization | Responsibility/expertise |
| --- | --- |
| Ministries and government agencies |  |
| Ministry of Environment and Forestry | Environmentally sound management of chemicals; Analysis of chemicals in environmental and biological environmental licensing; Management of household and hazardous waste; |
| Ministry of Health | Responsible for regulations and governance related to public health; In charge of public health centers; Responsible authority for health surveillance and mercury waste management in health centers; Risk assessments and mercury poisoning. |
| Ministry of Foreign Affairs | Negotiation processes for legally binding instruments; Signature and ratification monitoring of legally binding instruments. |
| Ministry of Energy and Mineral Resources | Regulates mining in Indonesia |
| Ministry of Finance | Regulates commercial and finance activities in the country. |
| General Secretariat for coordinating government | Planning measures at central government level |
| Academy | Consulting and expertise on topics of interest. |
| Miners/miner representatives | Provide realistic view of current practices and barriers to change. |
| Community leaders and local government from ASGM areas | Assist with development and implementation of the NAP within ASGM communities. |
| Indigenous groups | Represent the interests of indigenous populations in ASGM areas. |
| Technical expert in gold mining | Understanding of technical alternatives to mercury use; provide training opportunities. |
| Environmental and human health organizations | Activities aimed at reducing environmental impacts of ASGM and the risks of human exposure. |
| Representatives from large scale mining | Contribute to finding innovative solutions and providing insights on mining regulatory issues; Potential partner with small-scale miners on technical improvements to mining practice. |
| Police and Customs officials | Enforcement. |
| Gold buying agents, gold traders, mercury traders | Understanding of gold market dynamics, and barriers to formalization. |
| Waste management specialists | Expertise related to available mechanisms to handle mercury wastes generated by ASGM and how to clean/restore contaminated sites- |
| Financial/banking sector | Small and commercial-sized loans to miners to assist with financing transition towards better practices. |

Table 4: suggested national stakeholders for the national advisory groups

| ASGM Stakeholder Groups | Contribution to Development of NAPs |
| --- | --- |
| Miner organizations (e.g., cooperatives and/or associations) | Understand how to organize miners. |
| Miners/miner representatives | Provide realistic view of current practices and barriers to change. |
| Community leaders and local government from ASGM areas | Assist with development and implementation of plan within ASGM communities. |
| Indigenous groups | Represent vested interests in ASGM operations in indigenous areas. |
| Technical expert in gold mining | - Understanding of technical alternatives to mercury use; - Provide training opportunities. |
| Environmental and human health organizations | Represent vested interests in reducing environmental impacts of ASGM and the risks of exposure to the public. |
| Academic and research organizations | - Provide valuable information and conduct future research; - Provide training opportunities from ASGM specialists. |
| Legal professionals | Understand national legislation as it relates to ASGM including relevant regulation on mercury use and trade regulation. |
| Representatives from large scale mining | - Contribute to finding innovative solutions and provide insights on mining regulatory issues; - Potential partner with small scale miners on technical improvements to mining practice. |
| Police and Customs officials | Understand role of enforcement. |
| Gold buying agents, gold traders, mercury traders | - Provide insight into market dynamics, and barriers to formalization; - Important focal point for community health and emissions. |
| Waste management specialists | Provide insight into available mechanisms to handle mercury wastes generated by ASGM and how to clean/restore contaminated sites. |
| Financial/banking sector | Small and commercial-sized loans to miners to assist with financing transition towards better practices. |

Socioeconomic benefits including consideration of gender dimensions

This project aims at strengthened national capacity to manage mercury and chemicals in general. Therefore it is anticipated that the project will positively impact poor populations, who are disproportionately affected by the impacts of environmental and health hazards. This is particularly true in ASGM communities that are not only directly exposed to mercury from amalgamation processes but also indirectly through the air breathed and from the polluted water and food consumed in a daily basis. Although to date no biomonitoring has been undertaken in the ASGM community in Indonesia, bio-monitoring results from several ASGM countries worldwide have shown alarming concentrations of Mercury in hair, urine, mother’s milk, and blood of children, women and men.

This project can assist Indonesia to clearly identify areas of improvement, starting at the local, and community levels and complemented with national policies.  For example, through the inventory process, and the mapping of key mercury pollution sources, the project will define at-risk populations across Indonesia. Project activities will also involve consultation with at-risk communities with the aim of increasing understanding about the risks of mercury exposure. Project activities will ensure communities at risk with clear and accurate information to protect themselves. This is likely to involve, but not be limited to employees potentially at risk of mercury exposure, workers associations and medical associations, and poor communities living in close proximity to industry facilities and contaminated sites.

Regarding gender, in many ASGM areas women perform tasks where toxic exposure occurs since they do not require strength. These jobs include pouring the mercury into the ball-mills or mixing the mercury in panning, and burning the amalgam, often with their children or babies nearby. In some countries, women also carry the rocks from the mining sites to the processing plants. Moreover, with an estimated 4.5 million women working in artisanal mining, many of childbearing age, low-level exposure to infants during gestation and breast-feeding is a risk.  As a potent neurological toxicant that interferes with brain functions and the nervous system, mercury has been shown to be particularly harmful to neurological development of babies and young children.

The project will ensure that there are opportunities for women to contribute to, and benefit from, the project outcomes. Specifically the project executor will work with national coordinators to ensure women are well represented on national coordinating committees, and that consultation with at-risk communities targets both women and men. The project coordinator will also ensure that always when possible, data collected in the framework of this project will be disaggregated by sex and age. The NAP for the ASGM sector will fully incorporate the gender dimensions identified in the national overview of the ASGM sector and foster gender equality. A gender specialist will be identified in each country and will take part in the Stakeholder Advisory Group. A gender specialist will also be engaged by the Global Mercury Partnership to ensure gender considerations are fully taken into account during the project implementation.

Pregnant women, children and communities nearby mercury sources are more vulnerable to mercury exposure. Therefore this project will advocate for a national regulatory framework targeting the protection of these vulnerable groups. Through these vulnerable groups, the project will also sensitize the general population about the risks of mercury.

C. Describe the Enabling Activity and Institutional Framework for Project Implementation

For project activities, please section B

Implementing Agency (IA): this project will be implemented by UNEP and executed by Ministry of Environment and Forestry. As Implementing Agency, UNEP will be responsible for the overall project supervision, overseeing the project progress through the monitoring and evaluation of project activities and progress reports, including on technical issues. In close collaboration with the Executing Agency, UNEP will provide administrative support to the Executing Agency.

UNEP will support Execution of this project, as part of the Mercury Partnership Programme, and will provide assistance to signatories to the Minamata Convention such as organizing regional awareness raising/training workshops, reviewing technical products, sending technical experts to key meetings, etc.  Furthermore, through its Programme of work, UNEP will identify suitable Divisions and Branches that can provide additional support to Indonesia and complement project activities.

Executing Agency (EA): Ministry of Environment and Forestry will execute, manage and be responsible for the project and its activities on a day-to-day basis.  It will establish the necessary managerial and technical teams to execute the project. It will search for and hire any consultants necessary for technical activities and supervise their work. It will acquire equipment and monitor the project; in addition, it will organize independent audits in order to guarantee the proper use of GEF funds.  Financial transactions, audits and reports will be carried out in accordance with national regulations and UNEP procedures. Ministry of Environment and Forestry will provide regular administrative, progress and financial reports to UNEP Chemicals.

National Coordination Mechanism (NCM) will meet regularly during project implementation.  The Committee will include Key National Stakeholders and will evaluate the progress of the project and will take the necessary measures to guarantee the fulfillment of its goals and objectives.  The NCM will take decisions on the project in line with the project objectives and these decisions will be implemented by the Executing Agency. The National Coordination Mechanism will consult the stakeholder advisory group on a regular basis.

Stakeholder Advisory Group (SAG): This Group will include relevant stakeholders who possess relevant knowledge and information, and whose collaboration and cooperation will be needed for the successful formulation of the MIA and NAP and also for the implementation NAP. The National Coordination Mechanism will engage with the advisory group at regular intervals and during all phases of the MIA and NAP development and direct feedback on these documents will be provided through a mechanism to be agreed upon by the National Coordination Mechanisms.

Global Mercury Partnership (GMP): the partnership works closely with stakeholders to assist in the timely ratification and effective implementation of the Minamata Convention. Reducing Mercury in ASGM is one of the partnership areas and it has supported countries in its efforts to reduce mercury uses and releases in the ASGM sector; eliminate the worst practices in ASGM and explore innovative market-based approaches to enable the transition away from mercury. The partnership will ensure the participating country has access to all the expertise and experience of its members to implement the project.

Figure 1: Implementation arrangements

- Describe, if possible, the expected cost-effectiveness of the project:

The project will use the current capacity for chemicals management present in Indonesia, such as the existing infrastructure and coordination mechanism. The project will also consider any previous efforts to collect information on national mercury sources and releases and to improve the sound management of mercury and mercury waste.

The project will also take into account the expertise gathered by some countries in previous projects related to mercury waste management, and in turn, share the experiences and lessons learned with those countries that are at an early stage of strengthening capacities for mercury management. The project will coordinate closely with the Chemicals Division at UNEP and with the different mercury programmes and projects in place.

The integration of outcomes and deliverables of this project is also expected to provide significant input to the existing national framework for chemicals management in Indonesia. In this respect, enhanced capacities and knowledge on mercury and mercury waste will facilitate the development and/or update of current policies and enforcement practices in a more efficient and resource saving approach.

- describe the budgeted M&E Plan:

Day-to-day management and monitoring of the project activities will be the responsibility of the executing agency. Ministry of Environment and Forestry will submit half-yearly progress reports to the implementing agency at UNEP Chemicals. Ministry of Environment and Forestry will also be responsible for the issuing of legal documents such as agreements with the government and other institutions including recruitment of local staff or consultants and the execution of the activities according to the work plan and expected outcomes.

The half-yearly reports will include progress in implementation of the project, financial report, a work plan and expected expenditures for the next reporting period.  It will also identify obstacles occurred during implementation period.

An independent terminal evaluation (TE) will take place at the end of project implementation, latest 6 months after completion of the project. The Evaluation Office of UNEP will be responsible for the TE and liaise with the UNEP Task Manager at DTIE Chemicals Branch throughout the process. The TE will provide an independent assessment of project performance (in terms of relevance, effectiveness and efficiency), and determine the likelihood of impact and sustainability. It will have two primary purposes: (i) to provide evidence of results to meet accountability requirements, and (ii) to promote learning, feedback, and knowledge sharing through results and lessons learned among UNEP and executing partners – Ministry of Environment and Forestry in particular. The direct costs of the evaluation will be charged against the project evaluation budget. The TE report will be sent to project stakeholders for comments. Formal comments on the report will be shared by the Evaluation Office in an open and transparent manner. Project performance will be assessed against standard evaluation criteria using a six point rating scheme. The final determination of project ratings will be made by the Evaluation Office when the evaluation report is finalised. The evaluation report will be publically disclosed and will be followed by a recommendation compliance process.

Table 5. Monitoring and Evaluation Budget

| M&E activity | Purpose | Responsible Party | Budget (US$)*1 | Time-frame |
| --- | --- | --- | --- | --- |
| Inception workshop | Awareness raising, building stakeholder engagement, detailed work planning with key groups | Ministry of Environment and Forestry | 0 | Within two months of project start |
| Inception report | Provides implementation plan for progress monitoring | Ministry of Environment and Forestry | 0 | Immediately following Inception Workshop |
| Technical Progress reports | Describes progress against annual work plan for the reporting period and provides activities planned for the next period | Ministry of Environment and Forestry | 0 | Half-yearly |
| Financial Progress reports | Documents project expenditure according to established project budget and allocations | Ministry of Environment and Forestry | 0 | Quarterly |
| Project Review by National Coordination Committee | Assesses progress, effectiveness of operations and technical outputs; Recommends adaptation where necessary and confirms implementation plan. | Ministry of Environment and Forestry | 0 | Month 2, 12 and 23 |
| Terminal report | Reviews effectiveness against implementation plan. Highlights technical outputs. Identifies lessons learned and likely design approaches for future projects, assess the likelihood of achieving design outcomes. | Ministry of Environment and Forestry | 0 | At the end of project implementation |
| Independent Terminal evaluation | Reviews effectiveness, efficiency and timeliness of project implementation, coordination mechanisms and outputs. Identifies lessons learned and likely remedial actions for future projects. Highlights technical achievements and assesses against prevailing benchmarks | UNEP, Independent external consultant | 10,000 | At the end of project implementation |
| Independent Financial Audit | Reviews use of project funds against budget and assesses probity of expenditure and transactions | Ministry of Environment and Forestry | 10,000 | At the end of project implementation |
| Total indicative M&E cost*1 |  |  | 20,000 |  |

*The inception workshop is one activity of the project component 2. Monitoring and evaluation activities will be done back to back with the inception workshop and therefore the cost is zero. The project Review by the National Coordination Committee will be held back to back with technical meetings that will take place throughout the project implementation. Therefore the additional cost is zero.

F. Explain the Deviations from typical Cost Ranges (where applicable):

part iii:  approval/endorsement by gef operational focal point(s) and GEF agency(ies)

A.   Record of Endorsement of GEF Operational Focal Point(s) on Behalf of the Government(s): (Please attach the Operational Focal Point endorsement letter(s) with this template).

| Name | Position | Ministry | Date (Month, day, year) |
| --- | --- | --- | --- |
| Ibu Laksmi DHEWANTHI | Operational Focal Point | Ministry of Environment and Forestry | September, 09, 2016 |

B. Convention Participation

| Convention | Date of Ratification/ Accession (mm/dd/yyyy) | National Focal Point |  |
| --- | --- | --- | --- |
| Minamata convention | Date Signed 10/10/2013 | National Focal Point: Yunik Kuncaraning purwandari | Date of Notification under Article 7 to the Minamata Convention Secretariat 05/08/2016 |

C.  GEF Agency(ies) Certification

| This request has been prepared in accordance with GEF policies and procedures and meets the standards of the GEF Project Review Criteria for Chemicals and Wastes Enabling Activity approval in GEF 6. |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Agency Coordinator, Agency name | Signature | Date (Month, day, year) | Project Contact Person | Telephone | E-mail Address |
| Brennan Van Dyke Director, UNEP GEF Coordination Office |  | December 1, 2016 | Kevin Helps Senior Programme Officer DTIE, UNEP | +254-20-762-3140 | Kevin.Helps@unep.org |

Annexes:

- consultants to be hired for the Enabling Activity  with GEF Funding

- Ofp endorsement letters

- environmental and social safeguards

- acronyms and abbreviations

- supervision plan

- gef approved budget

annex B: ofp endorsement letter and notifications to the minamata secretariat

## Annex C: Environmental and Social Safeguards Checklist

As part of the GEFs evolving Fiduciary Standards that Implementing Agencies have to address ‘Environmental and Social Safeguards’.  To fill this checklist:

- STEP 1: Initially assess E&S Safeguards as part of PIF development. The checklist is to be submitted for the CRC.

- STEP 2 : Check list is reviewed during PPG project preparation phase and updated as required

- STEP 3 : Final check list submitted for PRC showing what activities are being undertaken to address issues identified

UNEP/GEF Environmental and Social Safeguards Checklist

| Project Title: | Development of Minamata Initial Assessment and Updating of National Action Plan for the Artisanal and Small Scale Gold Mining in Indonesia |  |  |
| --- | --- | --- | --- |
| GEF project ID and UNEP ID/IMIS Number |  | Version of checklist |  |
| Project status (preparation, implementation, MTE/MTR, TE) | Preparation/submission | Date of this version: | 23/03/2016 |
| Checklist prepared by (Name, Title, and Institution) | Kevin Helps – Senior Programme Officer GEF Operations - UNEP DTIE Chemicals |  |  |

In completing the checklist both short- and long-term impact shall be considered.

Section A: Project location

If negative impact is identified or anticipated the Comment/Explanation field needs to include: Project stage for addressing the issue; Responsibility for addressing the issue; Budget implications, and other comments.

|  | Yes/No/N.A. | Comment/explanation |
| --- | --- | --- |
| - Is the project area in or close to - |  |  |
| - densely populated area | N.A. | The project will assess the situation with regard to mercury in Indonesia. It will not take direct action on the ground but inventories prepared to address priority issues will take socio-economic and environmental considerations into account. |
| - cultural heritage site | N.A. |  |
| - protected area | N.A. |  |
| - wetland | N.A. |  |
| - mangrove | N.A. |  |
| - estuarine | N.A. |  |
| - buffer zone of protected area | N.A. |  |
| - special area for protection of biodiversity | N.A. |  |
| - Will project require temporary or permanent support facilities? | N.A. |  |
| If the project is anticipated to impact any of the above areas an Environmental Survey will be needed to determine if the project is in conflict with the protection of the area or if it will cause significant disturbance to the area. |  |  |

Section B: Environmental impacts

If negative impact is identified or anticipated the Comment/Explanation field needs to include: Project stage for addressing the issue; Responsibility for addressing the issue; Budget implications, and other comments.

|  | Yes/No/N.A. | Comment/explanation |
| --- | --- | --- |
| - Are ecosystems related to project fragile or degraded? | N.A. | The project will assess the situation with regard to mercury in Indonesia. It will not take direct action on the ground but assessments and mercury inventories will assist the country to identify priority issues in relation to human health and the environment, where socio-economic and environmental considerations will be identified |
| - Will project cause any loss of precious ecology, ecological, and economic functions due to construction of infrastructure? | No |  |
| - Will project cause impairment of ecological opportunities? | No |  |
| - Will project cause increase in peak and flood flows? (including from temporary or permanent waste waters) | No |  |
| - Will project cause air, soil or water pollution? | No |  |
| - Will project cause soil erosion and siltation? | No |  |
| - Will project cause increase waste production? | No |  |
| - Will project cause Hazardous Waste production? | No |  |
| - Will project cause threat to local ecosystems due to invasive species? | No |  |
| - Will project cause Greenhouse Gas Emissions? | No |  |
| - Other environmental issues, e.g. noise and traffic | No |  |
| Only if it can be carefully justified that any negative impact from the project can be avoided or mitigated satisfactorily both in the short and long-term, can the project go ahead. |  |  |

Section C: Social impacts

If negative impact is identified or anticipated the Comment/Explanation field needs to include: Project stage for addressing the issue; Responsibility for addressing the issue; Budget implications, and other comments.

|  | Yes/No/N.A. | Comment/explanation |
| --- | --- | --- |
| - Does the project respect internationally proclaimed human rights including dignity, cultural property and uniqueness and rights of indigenous people? | Yes | It will respect cultural aspects in Indonesia |
| - Are property rights on resources such as land tenure recognized by the existing laws in affected countries? | N.A. |  |
| - Will the project cause social problems and conflicts related to land tenure and access to resources? | N.A. |  |
| - Does the project incorporate measures to allow affected stakeholders’ information and consultation? | Yes | The project will form a National Coordinating Committee, including all relevant stakeholders. This group will assess project progress at the national level and will propose if necessary corrective actions. Additionally, the Project Implementing Agency will provide technical feedback as assistance to the participating country. |
| - Will the project affect the state of the targeted country’s (-ies’) institutional context? | Yes | A Mercury Management team will be established to deal with mercury within national chemicals efforts. In the medium to long-term it is expected that the national regulatory system will be revised to include provisions in compliance with the Minamata Convention. |
| - Will the project cause change to beneficial uses of land or resources? (incl. loss of downstream beneficial uses (water supply or fisheries)? | No |  |
| - Will the project cause technology or land use modification that may change present social and economic activities? | No | The project might identify actions to change current practices towards the sound management of mercury. |
| - Will the project cause dislocation or involuntary resettlement of people? | No |  |
| Will the project cause uncontrolled in-migration (short- and long-term) with opening of roads to areas and possible overloading of social infrastructure? | No |  |
| - Will the project cause increased local or regional unemployment? | No |  |
| - Does the project include measures to avoid forced or child labour? | No |  |
| - Does the project include measures to ensure a safe and healthy working environment for workers employed as part of the project? | No | Those doing the inventory on the field will use protective equipment to avoid contamination with those chemicals. |
| - Will the project cause impairment of recreational opportunities? | No |  |
| - Will the project cause impairment of indigenous people’s livelihoods or belief systems? | No |  |
| - Will the project cause disproportionate impact to women or other disadvantaged or vulnerable groups? | No |  |
| - Will the project involve and or be complicit in the alteration, damage or removal of any critical cultural heritage? | No |  |
| - Does the project include measures to avoid corruption? | Yes | Close supervision of the expenditures will be done at the national level by the EA and overall by UNEP as IA. Cash advances will be related to outputs and held until proper justification of the expenditures and budget plans are provided. |
| Only if it can be carefully justified that any negative impact from the project can be avoided or mitigated satisfactorily both in the short and long-term, can the project go ahead. |  |  |

Section D: Other considerations

If negative impact is identified or anticipated the Comment/Explanation field needs to include: Project stage for addressing the issue; Responsibility for addressing the issue; Budget implications, and other comments.

|  | Yes/No/N.A. | Comment/explanation |
| --- | --- | --- |
| - Does national regulation in affected country (-ies) require EIA and/or ESIA for this type of activity? | No |  |
| - Is there national capacity to ensure a sound implementation of EIA and/or SIA requirements present in affected country (-ies)? | N.A. |  |
| - Is the project addressing issues, which are already addressed by other alternative approaches and projects? | No |  |
| - Will the project components generate or contribute to cumulative or long-term environmental or social impacts? | No | No negative impacts |
| - Is it possible to isolate the impact from this project to monitor E&S impact? | N.A. |  |

ANNEX D: ACRONYMS AND ABBREVIATIONS

| ASGM | Artisanal and Small-Scale Gold Mining |
| --- | --- |
| ASM | Artisanal and Small-Scale Mining |
| BRS | Basel, Rotterdam and Stockholm Conventions |
| DTIE | Division of Technology Industry and Economics |
| EA | Executing Agency |
| FNPF | Friends of the National Park Foundation |
| GEF | Global Environment Facility |
| GEF SEC | Global Environment Facility Secretariat |
| GEF TF | Global Environment facility Trust Fund |
| GMP | Global Mercury Partnership |
| GMP | Global Mercury Project |
| IA | Implementing Agency |
| INC | Intergovernmental Negotiating Committee |
| M&E | Monitoring and Evaluation |
| MEAs | Multilateral Environmental Agreements |
| MIA | Minamata Initial Assessment |
| NA | Non applicable |
| NAP | National Action Plan |
| NCM | National Coordination Mechanism |
| NGOs | Non-governmental Organizations |
| OFP | Operational Focal Point |
| PMC | Project Management Cost |
| PoW | Programme of Work |
| PPG | Project Preparation Grant |
| PSC | Project Steering Committee |
| ROAP | Regional Office for Asia and Pacific |
| SAICM | Strategic Approach for International Chemicals Management |
| SAG | Stakeholder Advisory Group |
| SDGs | Sustainable Development Goals |
| TE | Terminal Evaluation |
| ToR | Terms of Reference |
| UN | United Nations |
| UNIDO | United Nations Industrial Development Organization |
| UNDP | United Nations Development Programme |
| UNEP | United Nations Environment Programme |
| WHO | World Health Organization |

Project ID number will be assigned by GEFSEC and to be entered by Agency in subsequent document submission.

Co-financing for enabling activity is encouraged but not required.

This is the cost associated with the unit executing the project on the ground and could be financed out of trust fund or co-financing sources. For EAs within the ceiling, PMC could be up to 10% of the Subtotal GEF Project Financing.

http://www.unep.org/PDF/PressReleases/GlobalMercuryAssessment2013.pdf

Brazil, Lao PDR, Indonesia, Sudan, Tanzania and Zimbabwe.

http://www.amap.no/documents/doc/technical-background-report-for-the-global-mercury-assessment-2013/848.

Class 1 = presence/absence, no quantitative information, error can be greater than 100% (25 countries); class 2 = some indication of quantity of Hg used, estimated average error 75% (20 countries); class 3 = quantitative data but not significantly updated within past five years, error 50%(17 countries); class 4 = recent quantitative data; error 30%; b emission factor for concentrate amalgamation = 0.75 (1/1.3); Emission factor for whole ore amalgamation = 0.25 (1/4).

http://www.amap.no/documents/doc/technical-background-report-for-the-global-mercury-assessment-2013/848

www.unep.org/chemicalsandwaste/NationalStrategicPlan/tabid/53985/Default.aspx.

http://www.who.int/ipcs/assessment/public_health/mercury_asgm.pdf

http://www.wecf.eu/english/articles/2013/10/minamata-sideevent.php

See Telmer and Veiga (2009)

See United States EPA (1997); Bose-O’Reilly et al. (2010)

GEF policies encompass all managed trust funds, namely: GEFTF, LDCF, and SCCF