Request for CEO endorsement/approval

Project Type:

the least developed countries Fund for climate change (LDCF)

# Submission Date: 06/15/2012

# Resubmission Date: 08/01/12

# Resubmission Date: 08/23/2012

| Expected Calendar (mm/dd/yy) |  |
| --- | --- |
| Milestones | Dates |
| Work Program (for FSP) |  |
| Agency Approval Date | 10/01/2012 |
| Implementation Start | 11/01/2012 |
| Mid-term Review (if planned) | 12/01/2014 |
| Project Closing Date | 12/01/2016 |

# part i: project Information

# GEFSEC Project ID: 4227

# gef agency Project ID: 548

# Country(ies): Afghanistan

# Project Title: Building adaptive capacity and resilience to climate change in Afghanistan

# GEF Agency(ies): , ,

Other Executing partner(s): National Environmental Protection Agency (NEPA)

# GEF Focal Area: Climate Change Adaptation

# A. Project framework

| Project Objective: to increase resilience of vulnerable communities and build capacity of local and national institutions to address climate change risk |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| ### Project Components | ### Indicate whether Investment, TA, or STAb | Expected Outcomes | ### Expected Outputs | ### LDCF Financinga |  | Co-financinga |  | Total ($) c = a+b |
|  |  |  |  | ### ($) a | ### % | ### ($) b | ### % |  |
| 1. Climate change risk assessment, monitoring and forecasting information. | STA | Increased capacity and knowledge base for assessment, monitoring and forecasting of climate change-induced risks to water in Afghanistan. | Improved tools to assess, monitor, predict and interpret climate change related risks and associated training course development and delivery. A model and standard operating procedures for a national early warning system (EWS) for the systematic collection, analysis, and distribution of information on climate change-induced risks to water resources at the national and community levels developed, and piloted in the four priority provinces. Technical and policy briefs for policy makers on climate change risks to water and other key sectors developed. | 929,379 | 17.2% | 1,200,000 | 8.3% | 2,129,379 |
| 2. Climate change adaptation and response strategies. | TA | Climate change risks integrated into relevant policies, plans and programmes. | Tools and methodology for identification, evaluation and mainstreaming of climate change adaptation measures in the water sector and other water related/ affected sectors developed. Tools and training material targeting the current inter–ministerial coordination mechanism for climate change risk and adaptation integration (the National Climate Change Committee, or NCCC) developed. Policy options to include climate change risk and adaptation measures for sectoral policies and plans (water, agriculture, and disaster and conflict prevention) developed and proposed. Capacities developed to implement the national climate change adaptation strategy and climate proofed sectoral plans. | 719,250 | 13.3% | 1,920,000 | 13.3% | 2,639,250 |
| 3. Practices for water resources and watershed management piloted and tested in selected project sites. | STA | Reduction of climate change vulnerability in the selected project sites through local institutional capacity building and concrete interventions for improved water use efficiency. | Pilot demonstrations to build resilience in the irrigated agricultural sector through cost efficient water infrastructure and irrigation technologies implemented in Badakhshan Province. Pilot demonstrations to build resilience in the dryland agricultural sector through drought-resilient crops, water harvesting and catchment restoration measures implemented in Balkh Province and Badakhshan Province. Pilot demonstrations to build resilience in rural peri-urban communities through restoration of aquatic zones implemented in Daykundi Province. Creation and institutional strengthening of water management associations by training members on integrated water resources management and ecosystem based adaptation in Bamyan District and other pilot areas. | 2,498,455 | 46.4% | 8,920,000 | 61.9% | 11,418,455 |
| 4. Adaptive learning and dissemination of lessons learned and best practices. | TA | Increased knowledge of good practices on increasing resilience to climate change-induced risks to water resources. | Project lessons captured in, and disseminated through a project specific web site, the Global Adaptation Network (GAN) and the Asia-Pacific Adaptation Network (APAN). ##### Project knowledge shared with other countries in the region facing similar climate-induced drought and flooding hazards. ##### Project knowledge for national flood and drought prevention incorporated into training approaches and materials. Awareness raising activities on climate change-induced risks to water resources and adaptation for local communities and key national policymakers delivered using appropriate means. ##### Resource mobilisation strategy developed for replication of project lessons and demonstrations in other locations of Afghanistan. | 707,516 | 13.1% | 1,300,000 | 9.0% | 2,007,516 |
| 5. Monitoring and evaluation |  |  |  | 135,500 | 2.5% | 0 | 0% | 135,500 |
| 6. Project management |  |  |  | 399,900 | 7.4% | 1,060,000 | 7.4% | 1,459,900 |
| Total Project Costs |  |  |  | 5,390,000 | 100 | 14,400,000 | 100% | 19,790,000 |

a    List the $ by project components. The percentage is the share of LDCF and Co-financing respectively to the total amount for the 
             component.

b   TA = Technical Assistance; STA = Scientific & Technical Analysis

# B. Sources of confirmed Co-financing for the project (expand the table line items as necessary)

| Name of Co-financier (source) | Classification | Type | Project | %* |
| --- | --- | --- | --- | --- |
| National Solidarity Programme (NSP) |  | Grant Parallel | 10,000,000 | 69% |
| National Area-Based Development Programme (NABDP) |  | Grant - Parallel | 2,400,000 | 17% |
| National Environmental Protection Agency (NEPA) |  | In-kind | 1,000,000 | 7% |
| Agro-Meteorology Programme (AgroMet) |  | Grant -Parallel | 600,000 | 4% |
| Rehabilitation of the Afghan Meteorological Authority (RAMA) |  | Grant-Parallel | 400,000 | 3% |
| Total Co-financing |  |  | 14,400,000 | 100% |

* Percentage of each co-financier’s contribution at CEO endorsement to total co-financing.

- confirmed financing plan summary for the project ($)

|  | Project Preparation Amount (a) | Project (b) | Total c = a + b | Agency Fee | For comparison: LDCF Grant and Co-financing at PIF |
| --- | --- | --- | --- | --- | --- |
| GEF financing | 100,000 | 5,390,000 | 5,490,000 | 549,000 | 4,900,000 |
| Co-financing | 109,000 | 14,400,000 | 14,509,000 |  | 16,000,000 |
| Total | 209,000 | 19,790,000 | 19,999,000 | 549,000 | 20,900,000 |

D.   For Multi agencies/countries (in $)1

| GEF Agency | Country Name | (in $) |  |  |
| --- | --- | --- | --- | --- |
|  |  | Project (a) | Agency Fee (b)2 | Total (c) c=a+b |
| Total LDCF Resources |  | 0 | 2 | 0 |

- No need to provide information for this table if it is a single country and/or single GEF Agency project.

- Relates to the project and any previous project preparation funding that have been provided and for which no Agency fee has been requested from Trustee.

# E. Project management Budget/cost

| ### Cost Items | ### Total Estimated person weeks/months | ### LDCF ($) | ### Co-financing ($) | ### Project total ($) |
| --- | --- | --- | --- | --- |
| ### Local consultants* | ### 444 | 143,900 | 50,000 | 193,900 |
| ### International consultants* | 0 | 0 | 0 | 0 |
| ### Office facilities, equipment, vehicles and communications* |  | 256,000 | 1,010,000 | 1,266,000 |
| Travel* |  |  |  |  |
| Total | 444 | 399,900 | 1,060,000 | 1,459,900 |

* Details to be provided in Annex C.

# f. Consultants working for technical assistance components:

| ### Component | ### Estimated person weeks | ### LDCF($) | ### Co-financing ($) | ### Project total ($) |
| --- | --- | --- | --- | --- |
| ### Local consultants* | 978 | 409,500 | 0 | 409,500 |
| ### International consultants* | 387.5 | 968,800 | 0 | 968,800 |
| ### Total | 1,365.5 | 1,378,300 | 0 | 1,378,300 |

* Details to be provided in Annex C.

g. describe the budgeted m&e plan:

The LDCF project monitoring and evaluation (M&E) will be conducted in accordance with established United Nations Environment Programme (UNEP) and GEF procedures for Full Scale Projects (FSPs) under the LDCF Portfolio Project the project progress will be monitored and evaluated based on the SMART indicators as contained in the LDCF project’s Results Framework (see Annex A of this document) for each expected output as well as mid-term and end-of-project targets. The logframe will be the main tool for assessing project implementation progress and whether results are being achieved. The means of verification are also included in the Results Framework. M&E-related costs are included in the LDCF project budget.

The M&E plan will be reviewed and revised as necessary during the LDCF project inception phase to ensure that stakeholders understand their roles and responsibilities. Day-to-day project monitoring will be the responsibility of the NPC and his/her team. The National Project Coordinator (NPC) will submit 6 monthly narrative progress reports and quarterly financial reports to UNEP. Other partners will be responsible for collecting specific information to track the indicators. It is also the responsibility of the NPC to inform UNEP and the Project Steering Committee (PSC) of any delays or difficulties faced during implementation so that the appropriate support or corrective measures can be adopted in a timely fashion.

The LDCF project will undertake a Baseline Assessment during the first three months of the project in order to ascertain the baseline conditions for indicators identified in the Project Results Framework (Annex A). This baseline will incorporate Vulnerability Reduction Assessments (VRAs) to determine the number of people vulnerable to climate change risks in the priority project areas.

A Project Inception Workshop will be held within the first 3 months of the start of project. This will involve those with assigned roles in the LDCF project management structure, UNEP representatives, regional technical policy and programme advisors where appropriate/feasible, and other stakeholders. This workshop will: i) assist stakeholders to fully understand their roles in the implementation of the project; ii) facilitate a review of the indicators, targets and their means of verification; iii) review, and where necessary revise the risks and assumptions; iv) permit the project stakeholders to agree upon and schedule the M&E workplan and budget; and v) allow stakeholders to review and comment upon the first year Annual Work Plan (AWP). An Inception Workshop Report will be prepared no more than 1 month after the Inception Workshop.

UNEP will develop a Supervision Plan during the LDCF project’s inception phase that will be distributed and presented to all stakeholders during the Inception Workshop. The emphasis of the Supervision Plan will be on outcome monitoring, learning and sustainability. Financial management and implementation monitoring, however, will not be neglected. Project risks and assumptions will be regularly monitored by UNEP. Key financial parameters will be monitored annually to ensure the cost-effective use of financial resources.

The LDCF project will undergo an independent Mid-Term Evaluation at the mid-point of project implementation. The Mid-Term Evaluation will determine progress being made toward the achievement of outcomes and will identify course correction if needed. It will: i) focus on the effectiveness, efficiency and timeliness of project implementation; ii) highlight issues requiring decisions and actions; and iii) present initial lessons learned about project design, implementation and management. Findings of this review will be incorporated as recommendations for enhanced implementation during the final half of the LDCF project’s term. The organization, terms of reference (ToRs) and timing of the Mid-Term Evaluation will be decided after consultation between the parties to the LDCF project document. The relevant GEF Focal Area Tracking Tools will also be completed during the Mid-Term Evaluation cycle.

An independent Final Evaluation will take place three months prior to the LDCF project end date in accordance with UNEP and GEF guidance. The Final Evaluation will focus on the delivery of the LDCF project’s results as initially planned (and as corrected after the Mid-Term Evaluation, if any such correction took place). The Final Evaluation will assess the impact and sustainability of results, including their contribution to capacity development and the achievement of adaptation benefits. The Final Evaluation should also provide recommendations for follow-up activities.

A key Annual Project Review/Project Implementation Review (PIR) will be prepared to monitor progress made since the start of the LDCF project, and in particular since the previous reporting period. The PIR will include, but will not be limited to, reporting on the following:

i) Progress made toward the LDCF project’s objective and outcomes – each with indicators, baseline data and end-of-project targets (cumulative);

ii) Project outputs delivered per project outcome (annual);

iii) Lesson learned/good practice;

iv) AWP and other expenditure reports; and

v) Project risks and adaptive management.

Periodic monitoring will be conducted through visits to the demonstration sites undertaken by relevant staff from UNEP and the NCCC/PSC. Visits will be jointly conducted based on the agreed schedule to assess project progress first hand.

As a result of a request for assistance in project execution from NEPA, the UNEP Department of Environmental Policy Implementation (DEPI) Post Conflict and Disaster Management Branch (PCDMB) will be directly involved in financial management and project execution within Afghanistan, in close partnership with the Executing Agency. Since all financial disbursements will be managed through the UNEP Integrated Management Information System (IMIS), external annual audits of finances will not be necessary. Quarterly IMIS reports will be generated to track project expenditures.

The comprehensive M&E plan for the project is included in Section 6 of the Project Document, while the M&E budget is included in Table 1 below

Table 1: Costed M&E plan.

| Type of M&E activity | Responsible Parties | Budget US$ | Time frame |
| --- | --- | --- | --- |
|  |  | Excluding project team staff time |  |
| Inception workshop and report | - NPC | Indicative cost: $12,100 | Within first two months of project start up |
|  | - NTAs (National Technical Advisor) |  |  |
|  | - SA (Senior Advisor) - UNEP Task Manager (TM) |  |  |
| Measurement of means of verification of project results | - UNEP TM, - SA, - NTAs - NPC will oversee | To be finalized in Inception Phase and Workshop. This incudes hiring of specific studies and institutions, and delegate responsibilities to relevant team members. | Start, mid and end of project (during evaluation cycle) and annually when required. |
| Measurement of means of verification for project progress on output and implementation | - UNEP TM, - NPC, - SA, - NTAs and - project team | To be determined as part of the AWP’s preparation. | Annually prior to PIR and to the definition of annual work plans |
| PIR | - NPC | None. Financial audit records to be provided from IMIS for PSC review | Annually |
|  | - NTAs - UNEP TM - UNEP FMO (Fund Management Officer) |  |  |
|  | - SA |  |  |
| Periodic status/ progress reports | - NPC | None | Quarterly |
|  | - SA |  |  |
|  | - NTAs - UNEP TM |  |  |
| Mid-term evaluation | - NPC | Indicative cost: $35,000 | At the mid-point of project implementation. |
|  | - SA |  |  |
|  | - External Consultant - UNEP TM |  |  |
| Final evaluation | - NPC | Indicative cost: $35,000 | At least three months before the end of project implementation |
|  | - NTAs |  |  |
|  | - SA |  |  |
|  | - External Consultant - UNEP TM - UNEP FMO |  |  |
| Project terminal report | - NPC | None | On completion of the terminal evaluation. |
|  | - NTAs |  |  |
|  | - SA - UNEP FMO - UNEP TM |  |  |
| Visits to demonstration sites | - UNEP TM - SA - NPC - NTA | For GEF supported projects, paid from IA fees and operational budget | Yearly |
|  | - NCCC/PSC representatives |  |  |
| Consultants | - International M&E Expert | International M&E Expert: $53,400 | During baseline assessment in inception phase, at the mid-point of project implementation and at least three months before the end of project implementation |
| TOTAL indicative COST |  |  | Estimated to cost $135,500 |
| Excluding project team staff time and UNEP staff and travel expenses |  |  |  |

# part ii: project justification

- describe the project rationale and the expected measurable adaptation benefits:

Afghanistan is experiencing an increase in the number and intensity of droughts, as well as more frequent flooding events as a result of increased climate variability and the melting of glaciers in the highland regions. The climate change induced problems facing Afghanistan are twofold. Firstly, under conditions of climate change, it is predicted that the incidence of extreme weather events and droughts will increase, as will climate change-linked disasters such as glacial lake outflows. These changes are likely to adversely affect natural ecosystems, agriculture and community livelihoods throughout the country. Secondly, national structures, including communities, district leaders, researchers and government agencies currently lack the capacity to plan for, overcome and withstand the anticipated climate change-related threats. This capacity deficit as well as underlying vulnerability to climate change impacts are exacerbated by the following non-climate change-driven causes: i) unsustainable use of natural resources; ii) high poverty levels; and iii) dependence on rain-fed agriculture; and v) a poorly developed policy environment. In addition, the National Adaptation Plan of Action (NAPA) highlights water as the primary concern. Therefore the project will respond to the climate change impacts and climate variability adversely impacting the water resources of Afghanistan. It will also implement activities to ensure that Afghanistan can withstand future climate change impacts through: i) demonstrating adaptation activities at the community level; ii) promoting research and generating appropriate data for climate change planning; iii) building capacity; and iv) promoting the development of pertinent policy.

Specific activities undertaken by the project include: i) building capacity within national and local structures to predict and respond to climate change-induced extreme weather events; ii) building national capacity to plan for the long-term effects of climate change; iii) integrating climate change adaptation into national policy and development plans; iv) improving local-, district- and national-level awareness of climate change risks and adaptation; v) implementing small-scale adaptation measures to demonstrate successful adaptation in several sites and at scales ranging from villages to small watersheds; and vi) developing a national climate change adaptation strategy. Full details of the proposed activities can be viewed in Section 3.2 of the project document.

Focusing on the water sector and water supplies to communities and agriculture, the project will pursue an innovative ecosystem management approach to adaptation in order to develop resilient human-inhabited ecosystems, enhancing the benefits provided by ecosystems and ensuring their resilience under conditions of climate change. Ecosystem management adaptation builds resilience in vulnerable and degraded ecosystems because of its multi-disciplinary approach and landscape-level adaptation focus. A primary focus of the ecosystem management adaptation process is the establishment and re-establishment of indigenous plant species with multiple benefits to local populations. This approach builds healthy, socially beneficial and well-managed ecosystems as natural infrastructure to increase the adaptive capacity of communities and areas to climate change impacts as well as to promote disaster risk reduction. Although the activities are site-specific, the adaptation benefits will accrue at multiple scales, including small highland water catchments to large downstream basins. Downstream benefits of the LDCF project interactions will ensure that the cost-effectiveness of the project interventions is maximised.

In addition to the promotion of ecosystem services for broad-scale benefits, the ecosystem management adaptation approach will improve the livelihoods of vulnerable populations. Direct benefits include the establishment (and re-establishment) of indigenous plant species with multiple uses to local populations, and improved agricultural yields through sustainable management of water supplies and other available resources. Local livelihoods will be further improved through the provision of ecosystem-based marketable products (e.g. fruit, wood, honey and medicinal herbs) and enhanced agricultural productivity

Through the achievement of the above activities, the project will alleviate critical barriers that exacerbate communities’ vulnerability to climate change, and that prevent effective adaptation at the local and national levels. By focusing on priorities identified in the NAPA, the LDCF project is responding to Afghanistan’s principal identified climate change adaptation priorities. These local-level interventions will ensure the development of capacity within communities and local authorities to adapt to climate change.

The LDCF project will also provide national benefits through interaction with relevant stakeholders, including government agencies, development partners, international research forums and relevant non-governmental organisations (NGOs). Local-level interventions will be analysed and lessons learned will be documented, which will enhance the national body of knowledge for climate change adaptation. In addition, critical shortcomings in the capacity of national agencies to plan for and respond to climate change impacts will be addressed through awareness-building, training, policy development and capacity-building. The multi-sectoral nature of climate change will be addressed by empowering the NCCC and the component agencies to integrate climate change adaptation into their sectoral plans. Furthermore, knowledge and information about climate impacts within Afghanistan will be gathered, and vulnerability maps prepared from these data to enable appropriate long-term climate change adaptation planning.

Linkages between the national interventions and the local level interventions will be established through knowledge transfer between different stakeholders. The learning-by-doing approach used for the interventions will help to generate information on appropriate methodologies for adaptation that can be mainstreamed at a national level. Furthermore, the establishment of a climate EWS through development of national agencies will be piloted within the priority provinces, allowing the process of EWS delivery to be tested and refined.

Overall, by implementing an adaptive learning approach throughout the project implementation and ensuring clear communication between multiple sectors (including NGOs, government agencies and ministries, local communities and international partners), the project will enhance the resilience of Afghanistan, and facilitate adaptation to climate change impacts at the local, provincial and national levels.

- Describe the consistency of the project with national/regional priorities/plans:

The Afghanistan National Development Strategy (ANDS) (2008-2013) is the principle guiding document for Afghanistan’s development over this period and into the future, and it clearly articulates the Government of the Islamic Republic of Afghanistan (GIRoA)’s national goals, namely: i) security; ii) governance, rule of law and human rights; and iii) economic and social development. The LDCF project interventions promote sustainable development and components of the interventions will assist the national government to achieve all three of the goals. The United Nations Development Assistance Framework (UNDAF) is the UN’s principle document governing their operations in the country, and it has been constructed in order to ensure compliance with the ANDS. The LDCF project has been designed to be aligned to both the UNDAF and the ANDS.

Amongst the top ANDS priorities are water management and agriculture, which are particularly threatened under conditions of climate change. The focus on agriculture led to the development of a new National Agriculture Development Framework (NADF) by the Ministry of Agriculture, Irrigation and Livestock (MAIL). The NADF is based on a core principle of natural resource management, upon which it bases the development strategy for agricultural production and productivity, with economic regeneration at the top of the “agriculture triangle”. Consequently, natural resource management is presented as a key national priority under the ANDS.

Section V of the ANDS addresses water availability and associated issues as a key national priority. This was reiterated through the NAPA process, which resulted in two priority projects being strongly related to water availability. Target 10 of the MDGs is to halve by 2020 the proportion of people without sustainable access to safe drinking water and to ensure environmental sustainability. Consequently, the LDCF project has a strong focus on ensuring increased water supply despite the predicted reduction in the availability of water throughout Afghanistan under conditions of climate change.

In addition to the water and agriculture sectors, Afghanistan has been focussing on strengthening environmental management within the country. It is signatory to several significant Multilaterals Environmental Agreements (MEAs), namely i) the Convention on the International Trade in Endangered Species (CITES); ii) the United Nations Framework Convention on Climate Change (UNFCCC); iii) the United Nations Convention on Biological Diversity (UNCBD); and iv) the United Nations Convention on Combatting Desertification (UNCCD). In addition, Afghanistan has either developed or is in the process of developing strategy and policy documents governing the maintenance of forests, rangeland, biodiversity and water. The LDCF project is designed to strengthen the environmental management framework by capacitating both the mandated agencies (NEPA and, to a lesser extent, MAIL) and communities to address environmental issues arising in conjunction with changing climate.

The national development agenda also includes a significant component on addressing shortcomings of both transport and energy infrastructure in order to promote market access and social uplift in all areas. The LDCF project will assist in the achievement of these goals by protecting these infrastructural improvements both within the identified priority sites, and in downstream areas, by reducing the impacts of climate change-induced extreme weather, flooding, erosion and droughts.

The LDCF project will assist in the implementation of the Strategic National Action Plan for Disaster Risk Reduction (SNAP) by facilitating the development of a national climate EWS, and by building capacity within the mandated Afghanistan National Disaster Management Authority (ANDMA).

The National Action Plan for Women’s Affairs (NAPWA) specifies a growing role and engagement of women in Afghanistan’s national affairs. This role is further reflected in the ANDS, which specifies that women should be engaged and promoted through education, training, economic empowerment and social uplift. The gender-disaggregation of indictors in the LDCF project and the specific focus on ensuring the inclusion of women in project activities will assist in addressing the gender focus of national development plans.

Finally, the LDCF will ensure that the gains in the above-mentioned fields are capitalised upon by establishing partnerships with donor organisations and regional networks to ensure the future integration of climate change-related issues into on-going project activities throughout Afghanistan. These networks will also facilitate the transfer of information between partners to enable a more focussed approach to addressing climate change within the region.

- describe the consistency of the project with LDCF eligibility criteria and priorities:

- The objective of the LDCF is to fund urgent and immediate adaptation needs in the Least Developed Countries as identified in their NAPAs. This project conforms to the LDCF’s eligibility criteria, namely: i) undertaking a country driven and participatory approach; ii) implementing the NAPA priorities; iii) supporting a “learning by doing” approach; iv) undertaking a multi-disciplinary approach; v) promoting gender equality; and vi) undertaking a complementary approach, as described below.

- Country driven and participatory approach: activities to be undertaken by the project were selected through numerous stakeholder consultations (see Section 2.3 of the Project Document) and are therefore in line with country priorities. More details on conformity with national priorities are provided in Section 2.5 of the Project Document.

- Implementing NAPA priorities: the project will address the high-priority adaptation projects identified during the Afghanistan NAPA process “Community-based watershed management” and “Improved water management and use efficiency”. It will also address identified additional priority projects, including “Improved terracing, agroforestry and agro-silvo pastoral systems” as well as several lower priority NAPA adaptation measures (“Climate-related research and early warning systems”, “Rangeland management” and “Improved food security”).

- Supporting a “learning by doing” approach: the project will support a “learning by doing” approach by building capacity at national and provincial levels. This will allow for the identification of additional vulnerable areas and relevant adaptation measures, which can be replicated in other areas of Afghanistan. The successful adaptation measures piloted by the project will be used to inform national and sub-national development plans and policies, and to build capacity within the identified communities to adapt to climate change conditions. Furthermore, the project is designed to complement other on-going and planned projects and programmes without duplicating them.

- Multi-disciplinary approach: as previously mentioned, the project includes three principle components: i) developing national capacity to monitor, assess and respond to the effects of climate change; ii) developing strategies for climate change adaptation and promoting their mainstreaming into national policy; and iii) demonstrating effective adaptation measures at the local scale. Within each component, the project will undertake a number of different activities (see Section 3.2 of the Project Document) to facilitate adaptation to climate change impacts on water and livelihoods. These activities will integrate interventions relevant to many different sectors of national policy and the economy.

- Gender equality: Gender equity in Afghanistan is a challenging subject given the historical role of women during the rule of the Taliban. The ANDS and the National Action Plan for the Women of Afghanistan both contain guidelines on gender mainstreaming, and these guidelines have been taken into account in the planning of all project activities. The project stipulates that at least 30% of the project activity participants should be women, and wherever possible it will engage with and promote women’s shuras and other gender-focussed groups.

- Complementary approach: In order to build upon existing plans and avoid duplication of efforts, the project will work in conjunction with relevant on-going projects in Afghanistan (see Section 2.8 of the project document). It will build upon the activities of the identified baseline projects, ensuring that they are able to continue under conditions of climate change, and will exchange information with other relevant projects to ensure that valuable lessons learned are disseminated as widely as possible.

- outline the coordination with other related initiatives:

Current GEF projects in Afghanistan include the preparation of the Initial National Communication to the UNFCCC (the INC), which has been presented to the UNFCCC by government in June 2012, and the preparation of the National Biodiversity Strategy and Action Plan (NBSAP), which will run through to the end of 2012. The LDCF project will integrate the knowledge from the INC programme, and will make use of the administrative and policy vehicle created by this project in the form of the NCCC. The GEF NBSAP project will focus on the development of a strategy, as well as the mainstreaming of biodiversity conservation within NEPA, MAIL and other ministries. Field projects for the NBSAP project will focus on the Shah Foladi National Reserve project in Bamyan Province. As such, there is great potential for synergy between the LDCF project and the communities in valley areas proximal to the reserve. The implementing agency (IA) for both of these projects is UNEP, and the Executing Agency (EA) is NEPA, which will ensure that there is no duplication of activities between the two projects, and that there is strong cross-pollination of concepts and exchange of lessons learned with respect to conservation protocols and community interactions. Finally, the LDCF project will be operating upon the priority activities identified during the NCSA/NAPA project funded by GEF and completed in 2005.

The project is receiving parallel co-financing from the National Solidarity Programme (NSP), which is funding complementary activities within the selected provinces and at a national level. The NSP is a very large scale programme funded by multiple donors, including the World Bank, the Afghanistan Reconstruction Trust Fund (ARTF, funded by 14 different nations), the Japanese Social Development Fund (JSDF), and a number of bilateral partners. It is implemented by the Ministry for Rural Reconstruction and Develoment (MRRD). The NSP is the primary vehicle for promoting rural development in Afghanistan, and it operates through the establishment and empowering of CDCs throughout the country. These CDCs prepare community development plans, and apply for funding of such activities through the NSP. Activities undertaken by CDCs include a number of infrastructural improvements such as provision of irrigation canals, access roads and bridges, water supply and sanitation improvements, and micro-hydro power (MHP) schemes. The NSP also provides education and livelihoods improvements, although these account for a small part of the budget. As of September 2011, the NSP had disbursed over $888 million to CDCs, and spent more than $1.2 billion. The NSP has committed $10 million for development activities in the selected districts of the priority provinces, and this baseline financing has been allocated for a number of activities (irrigation, agricultural expansion, MHP plants and infrastructural improvements) that will benefit directly from the additionality of the LDCF project’s activities. The NSP is also contributing to the PMC costs through the provision of project office space and operational team time in each of the target priority provinces. It is also interested in facilitating the uptake of knowledge generated through the LDCF project into normal NSP operations and national structures through which it operates.

The National Area-Based Development Programme (NABDP) is another permanent programme of the MRRD. Operating through seven regional offices, the NABDP focuses on establishing District Development Assemblies (DDAs) and training them in good governance practice and infrastructure project planning and implementation skills. This district-level governance is then used to provide service delivery and livelihood diversification through the productive infrastructure. The NABDP is currently in Phase II (1009 – 2014), facilitated by the United Nations Development Programme (UNDP) and funded by nine European countries to the amount of $294.7 million. The principle focus of the NABDP is on: i) local institution building in the form of DDAs to promote private-public partnerships; ii) developing rural infrastructure in the form of roads, bridges and other essential components; iii) natural resource management through community interaction; iv) rural energy development, particularly renewable rural energy in the form of MHP projects; and v) rural economic development to provide a conducive environment for rural enterprise initiatives.

Policy development is a very small part of the NABDP’s actions, but the programme has helped to develop the draft Renewable Energy Policy through the Energy for Rural Development in Afghanistan (ERDA) sub-project. The NABDP is also currently providing support to the change management process in the MRRD, and sits on the rural development cluster currently developing the National Priority Plans for rural Afghanistan. Although the policy component of the NABDP is a small part of its budget, it is nevertheless significant in terms of overall investment, since the project itself has secured over US$ 170 million since it started. Of the total amount invested through the NABDP, $2.4 million has been allocated for activities in the priority provinces in which the LDCF project will be operating, including development of MHP under the ERDA sub-project, and the policy component of NABDP activities. These components will benefit directly from the ecosystem management adaptation interventions undertaken by the LDCF project as illustrated in Section 3.3 of the project document. The NADBP has also expressed a specific desire to integrate successful practices piloted by the LDCF project into its standard operations, and to facilitate national uptake through the MRRD.

Another essential baseline partner for the LDCF project is the Agro-Meteorology (AgroMet) Program. This programme was initially operated by the United States Geological Survey (USGS) and focussed on the development of weather monitoring and agricultural prediction capabilities within MAIL. The World Meteorological Organisation (WMO) has agreed to provide extra funding to the project and extend the period from 2012 to 2015. The AgroMet programme aims to extend the meteorological data gathering capacity of national institutions and to provide infrastructure and training for a global climate change observation system. By developing synergies with baseline activities of the AgroMet programme, the LDCF project will assist in the provision of training for capacity building in data management and interpretation, climate impact modelling and development of vulnerability maps. Close interaction with the AgroMet programme will ensure complementarity and development of synergies to develop Afghanistan’s capacity to carry out climate change monitoring, modelling and prediction.

The WMO has also provided additional funding to the Afghanistan Meteorological Authority (AMA) through the Rehabilitation of the AMA (RAMA) project. This funding is provided in order to develop the baseline capacity and infrastructure of the AMA, and includes an integrated Messir system for the coordination of weather data, weather forecasting and data integration. The project also includes staff training in the usage of the system. The LDCF project will build upon this base by enhancing the capacity of the AMA to undertake long-term climatological modelling, and to assess climate vulnerability. In total, the two WMO projects are contributing $1 million in baseline co-finance to the LDCF project

The LDCF project will also be closely coordinated and linked to the following activities that are currently underway or have recently been completed in Afghanistan:

- The UNDP/UNEP Strengthened Approaches for the Integration of Sustainable Environmental Management in Afghanistan (SAISEM) programme is designed to promote and build institutional capacity of the Afghan government and communities for sustainable environment management, and to improve the capability of national and local governance bodies for natural resources and disaster management. The project has run beyond the original timeline, and is scheduled to reach completion in 2012, and is therefore not considered a suitable source of co-finance. However, the lessons learned from this project with respect to sustainable environmental management will be integrated into the local-level engagements undertaken by the LDCF project.

- The United States Agency for International Development (USAID)-funded $6.7 million Pastoral Engagement, Adaptation and Capacity Enhancement (PEACE) Project was initiated in 2006, and has been extended to run to the end of 2012. The project is aimed at promoting “the development of the livestock sector by supporting pastoral land tenure conflict resolution, [introducing] new technologies to improve rangeland management, livestock production, and marketing. This project also builds the capacity of government personnel responsible for planning and implementing livestock development and rangeland resource management.” The PEACE projected has found and is digitising a 25,000-specimen herbarium at the University of Kabul, and has produced field guides to rangeland vegetation that are essential sources of supplementary information for ecosystem management protocols (see Appendix 11 of the Project Document for a draft list of species with potential multiple benefits for ecosystem management adaptation). PEACE also has considerable experience in resolving resource disputes in rangeland areas through their “Peace Ambassador” programme.

- The Irrigation Restoration and Development Project (IRDP) is a joint World Bank and GIRoA-funded project that aims to restore and upgrade irrigation facilities throughout the country in line with national priorities. It has also received additional funding from the FAO to provide technical assistance to the Ministry of Energy and Water (MEW), building on the gains of the now-complete Emergency Irrigation Rehabilitation Project. Included in the project is a component to upgrade and provide hydro-meteorological services, which will be an essential component of the data exchange network.

- The National Emergency Rural Access Project (NERAP) is another World Bank-funded programme which aims to provide year-round access to basic services and facilities in certain rural areas of Afghanistan by 2013. This has been undertaken through the rehabilitation and maintenance of rural access infrastructure, particularly roads and culverts. This infrastructure is vulnerable to damage from climate change-induced extreme weather events, and it is hoped that the LDCF project will ensure additional protection for infrastructure improved through the action of NERAP in the priority provinces.

- The Regional Integrated Multi-hazard Early Warning System for Africa and Asia (RIMES) project was established in 2009, and has 13 member states, with 18 collaborating countries (of which Afghanistan is one). RIMES is a collaborative program that is designed to provide regional early warning systems and identify new and emerging technologies and research products for use in such systems. By sharing funding between member states, the costs of establishing such EWSs are reduced. Afghanistan’s current lack of technical capacity and infrastructure means that it has not been included as a member state, but the current RIMES project will enhance Afghanistan’s capacity. This project is planned to run over the period 2012 – 2016, coinciding with the implementation period of the LDCF project. The RIMES project focus is on building national structures for a regional EWS. In particular, RIMES will be constructing a training centre with necessary equipment and facilities for this regional early warning system, in conjunction with capacity building. Through close coordination with the RIMES project (as well as the baseline RAMA and AgroMet projects), the LDCF project will provide standard operating procedures (SOPs) for a national EWS, and trial on-the-ground structures and lines of communication for the EWS to ensure the functioning of the system. In addition, the LDCF project will enhance the knowledge base and information exchange structures leading to the provision of EWS services.

- The International Centre for Integrated Mountain Development (ICIMOD) is a regional intergovernmental learning and knowledge-sharing centre serving the eight regional member countries of the Hindu Kush - Afghanistan, Bhutan, Bangladesh, China, India, Myanmar, Nepal and Pakistan - and based in Kathmandu, Nepal. ICIMOD aims to assist mountain people to understand the changes affecting these mountain regions as a result of climate change and human interventions. It promotes adaption measures and helps facilitate the capitalisation on benefits of the changes. In addition, ICIMOD assists in dealing with transboundary issues associated with water and resource management. It is an essential partner for knowledge exchange and climate change adaptation information for the LDCF project; and

- The Regional Climate Change Adaptation Knowledge Platform for Asia and Asia Pacific Adaptation Network is another source of climate change adaptation information. Whilst the primary focus of the adaptation measures is for tropical south Asia, it is likely that interaction with this platform will facilitate the development of appropriate climate change adaptation responses for certain components of the LDCF project.

The LDCF project will interact with and benefit from several on-going national and international UNEP programmes:

- The Programme of Research on Climate Change Vulnerability, Impacts and Adaptation (PROVIA) is a recent initiative designed to promote cohesive global efforts in the fields of “vulnerability, impacts and adaptation” (VIA). In partnership with WMO, UNESCO and several other partner organisations, UNEP has embarked upon this joint programme to prioritise, accelerate, harmonise and communicate VIA research. The four principle functions and outputs of the programme are: i) coordinating and convening activities of the scientific community; ii) promoting a science-policy dialogue; iii) communicating within and outside the community; and iv) cultivating a new generation of VIA scientists. The strong overlap between the outputs of this programme and the goals of the LDCF project mean that PROVIA will be able to provide considerable input through the mobilisation of international expertise and techniques for Afghanistan. The interface between science and the policy component will be especially important during the process of development of the national climate change strategy.

- A GEF Capacity Development Programme for Implementation of Multilateral Environmental Agreements has recently been approved in Afghanistan, and will be implemented during the LDCF project implementation period. This project is designed to enhance the ability of NEPA to facilitate and manage Afghanistan’s obligations under the various MEAs to which the country is a signatory. Careful coordination between the LDCF project and the GEF project will ensure that training and capacity building within the two projects is complementary and synergistic.

Further details of stakeholder interaction are detailed in Section 2.6 of the project document.

- Describe Additional cost reasoning:

Climate change-induced damage to infrastructure, livelihoods and systems in Afghanistan are likely to increase over time. The project will contribute to the reduction of these impacts by implementing appropriate adaptation activities. These activities will ensure that the effects of the baseline projects are sustained and enhanced despite the effects of climate change. It is highly unlikely that the communities selected would be able to adapt unassisted to the threats posed to their livelihoods by increased climate variability. EWS and risk reduction measures implemented within the identified priority sites will contribute towards improving the local communities’ strategies for coping with climate variability, and will thereby enhance their resilience. In addition, the interventions selected will allow communities to maximise the use of potentially beneficial impacts of climate change where this occurs. Furthermore, the project will build capacity within the general public and within government structures to reduce the country’s vulnerability to climate change impacts.

Specifically, the project will strengthen national policy, regulatory and institutional structures at the national level for predicting the effects and managing climate change adaptation, and provide scientific tools for proper advance planning and response (Outcomes 1 and 2). In addition, the project will pilot measures to improve the resilience of communities, productive systems and ecosystems in rural and peri-urban areas to conditions of climate change (Outcome 3). Finally, the project will ensure that knowledge of the best practices derived from these demonstrations is disseminated to relevant communities, government officials and local and international partner organisations (Outcome 4). These aims will be achieved through the following components:

Component 1: Climate change risk assessment, monitoring and forecasting, and information.

At present, Afghanistan has limited capacity to gather climate data, to interpret and predict likely outcomes, and to assess the vulnerability of specific places and economic sectors to the negative effects of climate change. Whilst GCM outputs are available for the region and rough maps of current vulnerability have been prepared by agencies outside the government, there are no suitable structures or mechanisms within the Afghanistan government to capitalise on these resources. This means that the majority of national development policy documents do not take cognisance of the potential impacts of climate change, rendering the country highly vulnerable to its negative impacts.

The LDCF project will dedicate resources (US$ 929,379 of LDCF funding, US$ 1,200,000 of co-financing) to increase the national capacity and knowledge base to ensure that Afghanistan can monitor, assess and respond appropriately to climate change risks through the development of institutional capacity within national-level institutions and departments. This will be done through a process of: i) undertaking institutional gap analyses and needs assessments to identify capacity and technical shortfalls; ii) developing a strategic data-gathering and data-sharing network for exchange of climate information between all relevant partners; iii) developing strategic regional and international partnerships to facilitate capacity development and information exchange; iv) identifying appropriate tools and models for developing climate change adaptation planning products; v) implementing training courses in international best-practice methodologies for climate change modelling, seasonal forecasting and hydrological modelling; and vi) assisting in the development of climate change vulnerability maps. Although there is currently limited technical infrastructure for carrying out these activities, the development of strong partnerships with baseline projects (such as USGS AgroMet, AMA and ANDMA) that are enhancing such infrastructure will promote development and purchase of appropriate systems to enable the development of climate change products and knowledge. Component 1 will benefit from interaction with PROVIA, the UNEP-led multi-agency joint Programme on Research and Policy for VIA.

In addition, the LDCF project will build capacity for national government agencies to successfully undertake climate change risk assessments for the country. It will also build upon the RAMA baseline training and facilities to facilitate the establishment of a climate change EWS. This facilitation will produce standard operating procedures and assist in the delineation of appropriate risk-reporting structures for a national EWS. It will test these procedures by trialling the system in the four identified priority provinces. The LDCF will also produce policy briefs to facilitate the integration of the lessons learned from the project activities into national policy.

In the absence of the project interventions, Afghanistan will continue to lack the capacity to gather and process relevant climate data, and consequently climate change adaptation knowledge and tools will not be developed. The lack of national capacity to identify and implement adaptation measures will prevent the inclusion of climate change risks into national development policy, and the lack of proper climate monitoring will limit the ability of both national and international adaptation efforts. For a more detailed analysis of the baseline versus adaptation cost reasoning see table 5 in section 3.6 of the UNEP prodoc.

Component 2: Climate change adaptation and response strategies.

Presently, climate change risks are poorly understood in Afghanistan, and are not integrated into relevant national policies, plans and programmes. Furthermore, the multi-disciplinary coordination necessary for appropriate climate change adaptation is lacking between national government line ministries and agencies. Although the NCCC was established in 2009, it does not yet meet regularly, and has had limited success in integrating climate change science into national policies.

The LDCF project will allocate resources (US$ 719,250 of LDCF funding, US$ 1,920,000 of co-financing)  towards the development of an appropriate multi-disciplinary national climate change adaptation policy. To ensure the effectiveness of this policy, capacity will be built in relevant government bodies (NEPA, MAIL, MEW and MRRD) to promote integration of climate change adaptation policy into all relevant sectors of government in particular for water sector including through the promotion of a resilient IWRM (Integrated Water Resources Management) policy in the country.   Additionally, institutional and technical training will be provided on the implementation of climate proofed sectoral plans within the overarching climate change adaptation policy. Outcome 2 will also reinforce the functioning of the NCCC. An effective, formal coordinating committee is essential to ensure synergies in the multi-sectoral approach, and ultimately successful implementation of the policy. Formalisation of a coordinating body through the LDCF project will be simplified by the existence of committees such as the NCCC.

In the absence of the LDCF project interventions, the lack of an overarching climate change adaptation policy will persist, as will the lack of coordination between national government line ministries and agencies regarding climate change activities. Additionally, capacity in relevant government bodies to understand and integrate climate adaptation strategies into multi-sectoral plans will remain limited. For a more detailed analysis of the baseline versus adaptation cost reasoning, see table 5 in section 3.6 of the UNEP prodoc.

Component 3: Practices for water resources and watershed management piloted and tested in selected sites.

At present, communities, productive systems and ecosystems in and around rural and peri-urban areas are highly vulnerable to changes in timing and intensity of rainfall and other climate change-induced events. Reliance on ecosystem services combined with widespread ecosystem degradation means that adaptive capacity is low throughout Afghanistan. Poverty further exacerbates this low adaptive capacity. There has been some multilateral investment into national infrastructure (such as the implementation of large scale irrigation programmes), however, these infrastructure changes do not take the predicted impacts of climate change into account. These investments provide a foundation for the additional work of the LDCF project, despite the apparent the lack of planning and integration of climate change risks into national policies.

The project will allocate resources (US$ 2,498,455 of LDCF funding, US$ 8,920,000 of co-financing) to address climate changed-induced risks to communities, productive systems and ecosystems by trialling different ecosystem and water management approaches to adaptation. These include: i) efficient water infrastructure and irrigation technologies to build climate resilience in the irrigated agriculture sector; ii) drought-resilient crops, water harvesting and catchment restoration measures to build climate resilience in the dryland agricultural sector; and iii) capacity building in local communities to undertake integrated watershed management to build climate resilience in rural and peri-urban communities. Four priority provinces identified as being particularly vulnerable to the impacts of climate change will be targeted in this component. Adaptation interventions that promote sustainable water supplies for domestic and agricultural use will be piloted in rangelands, mountains, wetlands and peri-urban subsistence farmland. For example, check dams and the use of low-water-usage irrigation systems in Badakhshan Province will reduce water use, making communities and water management more resilient in times of drought. At present, fields are flood-irrigated by diversion of rivers, which is a highly inefficient use of water. In Balkh Province, drought-resilient crop species and cultivars will be promoted which will increase the resilience of agricultural productivity and complement the efficient water management interventions. Additional low cost and high-impact simple water management interventions will be trialled within local communities in order to establish cost-effective adaptation options under drought and low-water conditions. In Bamyan Province, integrated watershed management plans will be developed for the restoration of degraded aquatic zones, including restoration of degraded watershed areas with multiple-use indigenous species where appropriate. In Daykundi Province, degraded wetlands, riverbanks and catchment areas will be restored through reforestation, and low-cost water barriers and catchment structures will be constructed. These interventions will enhance water catchment areas and reduce the incidence of floods in peri-urban areas. This will build further climate resilience at intervention sites and further downstream.

It is expected that the interest and willingness of the local communities to participate actively in the adaptation measures will be further ensured if they are able to secure a better livelihood as part of the project’s adaptation measures. The outcome’s demonstration component is expected to provide significant and tangible benefits for communities, which is likely to result in replication in other areas experiencing similar impacts.

In the absence of the project interventions, the adaptive capacity of communities, productive systems and ecosystems will remain low. The capacity of provincial- and district-level stakeholders to plan for climate change adaptation will also remain low, and the knowledge of suitable approaches to climate change adaptation at a local level will not be developed. Levels of poverty and food insecurity will continue to increase as current community coping strategies are largely inappropriate, particularly given the predicted impacts of climate change. For a more detailed analysis of the baseline versus adaptation cost reasoning, see table 5 in section 3.6 of the UNEP prodoc.

Component 4: Adaptive learning and dissemination of lessons learned and best practices.

At present the lack of knowledge of techniques and methods to cope with the impacts of climate change is limiting the ability of the country to build climate resilience, particularly within rural communities. Some research is being conducted to identify best practices for agriculture under dryland conditions in Afghanistan (such as research through MAIL and ICARDA), however, these best practices have not been examined in the context of climate change.

To improve this situation, the project will dedicate resources (US$ 707,516 LDCF funding, US$ 1,300,000 co-financing) to raising public awareness through national campaigns targeting the general public (through radio, television, newspapers and pamphlets in local languages) and schools, including rural areas (through integration of climate change impact and adaptation lessons into school curricula). In addition to providing general background knowledge and understanding of climate change, specific focus will be given to simple activities that can be undertaken at a community level to enhance adaptive capacity and the assessment of their cost effectiveness so they can be replicated into other areas of the country. In order to raise the awareness of relevant government sectors such as officials at MAIL, MRRD, MEW and the Ministry for Urban Development (MUD), training tools for adaptation and flood/drought prevention will be incorporated into public service training programmes in Afghanistan.

Activities in Component 4 will also focus on the capture and dissemination of project lessons learned to relevant networks through distribution tools (such as GAN, APAN, Climate and Development Knowledge Network, Adaptation Learning Mechanism, WeAdapt), as well as regionally with bordering nations (Iran, Turkmenistan, Tajikistan, Uzbekistan, China and Pakistan). This will facilitate adaptive learning within Afghanistan and regionally, and strengthen national and international knowledge exchange structures.

In the absence of the project interventions, knowledge of effective adaptation to the impacts of climate change will remain limited, to the detriment of highly vulnerable communities, productive systems and ecosystems in and around rural and peri-urban areas. Additionally, the benefits of sharing lessons learned regionally and internationally will not be realised. For a more detailed analysis of the baseline versus adaptation cost reasoning, see table 5 in section 3.6 of the UNEP prodoc.

- indicate the risk that might prevent the project objective(s) from being achieved and outline risk mitigation measures:

The proposed project has strong support from both national and local government. However, the project does contain significant risks, due to the special nature of Afghanistan at present. In particular, the risk of political instability is very real. Sites have been selected bearing in mind the security risk, and at least one of the areas (Bamyan) has not experienced a security problem since the end of significant hostilities in 2002. It is possible that the national security situation will deteriorate subsequent to the withdrawal of US troops in 2014, although this likelihood of this and the potential impacts on project execution are difficult to estimate. Measures detailed below should help to reduce the impact of any such instability. Monitoring of the security risks will be a key task of the IA, and the possibility of extending the project for up to a year in response to a security-induced slowing of potential outputs.

Another potential risk to the project is the severe lack of technical expertise within the country. As a result of this general shortcoming, NEPA has requested that UNEP DEPI/PCDMB provide execution assistance. The assignment of permanent PCDMB staff to the Special Adviser (SA) role is anticipated to reduce the impact of this risk. Additional risks and countermeasures are tabulated in Table 4 below.

Table 2: Risk log for the project with proposed mitigation measures

| # | Description of the risk | Potential consequence | Mitigation measures / Management response | Type (Risk category) | Probability & impact (1-5) |
| --- | --- | --- | --- | --- | --- |
| 1 | Deterioration of security situation in project sites. | Increased restrictions on movements for UN experts. Reduced availability of international experts for short-term contracts. Higher costs towards increasing security measures for the project personnel Potential increase in the time taken to implement project | Preference has been given in site selection stable sites, and communities with a good working relationship with UNEP, NEPA and implementing organisations. Strong participatory stakeholder consultations have been undertaken to ensure reasonable expectations and to clarify roles/responsibilities. Continual engagement with local political structures (shuras, community leaders, CDCs) by the Executing Agency will enhance security and community ownership. Local authorities and community development organisations are given more project responsibility. There will be a stronger focus on permanent experts, NEPA national staff structures and permanent UNEP DEPI/PCDMB staff, using short-term experts to facilitate crucial undertakings, and to assist in the building of local capacity. Additional costs are requested to cover costs incurred by the need to increase security measures. A 10% increase of the total budget is requested with 68% going towards direct security costs, with the remainder being used to address inflated costs associated with mitigation of this risk. It is possible to extend the project duration in order to allow project activities to reach fruition despite political instability. | Political | P=4 I=4 |
| 2 | Extreme climate events such as floods and droughts could disrupt project activities and/or damage ecosystems and infrastructure. | Reduced effectiveness of project interventions. Potential damage to baseline project interventions. | Coordination will be undertaken with partners such as ANDMA for disaster response in order to ensure that disaster relief interventions are also directed towards demonstration sites impacted by extreme climatic events. Appropriate species will be used for project interventions in order to minimise the potential impacts in the medium and long-term. The piloting of an EWS for the project’s pilot sites should assist in reducing the impacts of extreme climatic events. Where damage occurs before ecosystem management adaptation approaches can reduce the impacts of extreme events, supplementary infrastructural approaches and planting will be undertaken. After suitable review, the project implementation period could be extended in order to facilitate the establishment of ecosystem management adaptation measures. | Environmental | P=2 I=4 |
| 3 | Frequent changes in membership of the steering committee and project management team (Staff turnover). | Changes in project-related government priorities. Poor institutional memory. Poor project coordination. | Deputies and alternative representatives within the institutions will be recommended at inception to ensure that sufficient membership continuity is available. PSC will make use of established government structures to capitalise on functioning systems. | Organisational | P=3 I=2 |
| 4 | Poor provincial responses to leadership role from NEPA. | Reduced project buy-in from key provincial stakeholders. Difficulty in coordinating local project activities. | Provincial authorities have been individually consulted during PPG phase, and have endorsed the LDCF project. The PSC will engage with relevant provincial authorities throughout the duration of the project. | Organisational | P=1, I=2 |
| 5 | Lack of political support of project implementation at project sites. | Difficulty for NEPA staff and project management to reach area. Reduced project management effectiveness. Possible prevention of local communities from undertaking interventions. | Regional technical advisors with good local connections will be assigned to ensure that political interference is minimised. Community participation will be maintained throughout the project duration to promote local project ownership. On the ground coordination will be undertaken in conjunction with local political structures to facilitate political buy-in. Comprehensive stakeholder engagement has been undertaken, and will be maintained throughout the project implementation. | Political | P=2 I=2 |
| 6 | Limited technical capacity to implement the project, particularly at the demonstration sites, or through failure to obtain a sufficiently qualified and dynamic project coordinator. | Local implementation hampered, resulting in project delays. Potential wastage of project investments due to poor implementation. Challenges in monitoring project implementation. Reduced project management effectiveness. | Key partners have been identified or are being identified in project sites to facilitate project implementation. Capacity will be built in key NEPA district officials to implement and monitor project activities. Regular technical oversight missions will be undertaken by UNEP DEPI/PCDMB staff. On-the-job training will be provided to project manager to enhance management and implementation capacity. Appropriate incentives will be provided to ensure the securing of the best local manager. Permanent UNEP DEPI/PCDMB staff will be assigned to the project to provide technical and operational assistance | Technical | P=4; I=4 |

This risk log will be updated annually by the National Project Coordinator (NPC) in cooperation with the SA (see Section 4 of the project document for further details about roles). The status of existing risks will be re-assessed, and emerging risks identified by the PSC that might affect project implementation will be included. Where necessitated by changing risk profiles, additional mitigation measures may have to be included during the annual review process.

- Explain how cost-effectiveness is reflected in the project design:

Costings for interventions in Bamyan, Badakhshan and Daykundi were undertaken by local officials, national consultants and CBNRM experts. Preliminary costings carried out for dryland agricultural improvements in Balkhwere carried out by ICARDA, and the projects were deemed cost effective. The effectiveness of the interventions in increasing resilience to climate change will be tested and measured during the course of the LDCF project (Outcome 4.1). This will involve undertaking an economic analysis and performing cost-benefit analyses to ascertain whether each activity is economically viable option given climate change. The most successful activities will be prioritised for upscaling to additional areas in Afghanistan, and details regarding their implementation and lessons learned from the project will be disseminated at workshops and training events to ensure their mainstreaming.

Cost effectiveness is further ensured by building upon the current baseline projects in the project areas, thereby ensuring the long-term viability of the developments under conditions of climate change. Investment of small amounts in climate-proofing the significant infrastructural investments in the area will reduce the impacts of cliamte change-induced extreme weather on such investments. The current baseline investment from the cofinance parnters (NSP and NABDP) in the priority provinces is $12.4 million for 2012 alone. In addition, by targeting upland areas and focussing at a watershed level, the ecosystem services protected by project interactions will result in significant downstream benefits, ensuring that not only local communities but all households dependent on regular water supplies from the watersheds will benefit from the LDCF project interactions. This ecosystem management approach to climate change adaptation ensures benefits are widespread, since the value of ecosystem services extends far beyond the local impact.

By providing technical training and financial support to community organisations and improving livelihoods through, for example, improved agricultural resilience, the LDCF project will engender ownership of the project and enhanced capacity within these communities. This reduces the overhead for monitoring and maintenance of the activities, and will promote sustainability of project gains beyond the project lifespan.

Building upon current national development programmes and enhancing capacity within the management structures mandated by government further demonstrates the cost effectiveness of the LDCF project.

# part iii: institutional coordination and support

# a. Project Implementation Arrangement:

Figure 1: The LDCF project management structure.

The LDCF project will be implemented over a four year period. Following the CEO endorsement, the LDCF project will start shortly after internalization, at which point the hiring process for project staff will begin.

UNEP will be the Implementing Agency (IA) for the LDCF project and will oversee the project and provide technical assistance. UNEP, as the GEF Implementing Agency and through the Task Manager (TM) based in UNEP DEPI/GEF Climate Change Adaptation Unit (CCAU), will be responsible for project supervision to ensure consistency with GEF and UNEP policies and procedures. The TM will formally participate in Project Steering Committee (PSC) meetings, the mid-term and final evaluations, the clearance of half-yearly and annual reports, and the technical review of project outputs.

NEPA will be the Executing Agency (EA) for the project. Through its letter dated 22 May 2012, (see Appendix 19 of the Project Document) NEPA has authorized UNEP DEPI/PCDMB to provide execution support to the project. UNEP DEPI/PCDMB will work closely with NEPA to ensure that national capacity is built to enable the execution of similar GEF/LDCF projects in the future. UNEP DEPI/PCDMB has a permanent office in-country, which will facilitate this execution support role.

UNEP will ensure adequate segregation of reporting between its IA and EA roles through internal agreements between the relevant branches.

The LDCF project implementation arrangements comprise the following:

- PSC to provide oversight and support to the project.

- Project Management Unit (PMU) to execute the project.

- National Project Coordinator (NPC) who heads the PMU.

- Senior Advisor (SA) who will provide day-to-day guidance to the project team on executing the project.

- Technical advisors.

- Provincial coordination teams.

- Administrative and financial assistant.

- Consultants (national and international).

The main role of the PSC will be to: i) guide and oversee the technical progress and performance of the LDCF project; ii) enhance and optimize the contributions of various partner organizations through coordination of all activities and inputs; and iii) consider and approve annual work and procurement plans and review project reports and deviations from the approved plans. All decisions taken by the PSC will be communicated to all parties concerned by the PMU. The PSC will include high level representatives from NEPA, MEW, AMA, UNEP DEPI/PCDMB, UNEP DEPI/GEF CCAU and priority provinces (Badakhshan, Balkh, Bamyan and Daykundi). It will be chaired by the NEPA Representative. The PSC will meet twice a year, with ad hoc meetings to be called when necessary, to discuss the project key performance indicators and provide future guidance. At the discretion of this initial committee, members of relevant implementing NGOs may be invited to sit on the PSC to ensure local ownership and guidance for the project. The secretarial role of the PSC will be filled by the NPC.

To ensure national ownership, the NPC will report annually to the Project Support Board (PSB). The PSB will comprise the NCCC, which is the government-mandated committee for oversight of climate change matters, with an additional UNEP DEPI/GEF CCAU representative. The NCCC was formed during the INC process, which is almost complete. Although it is a very young institution, it is the most appropriate government entity to supervise climate change policy and strategy, and will therefore be supported both in terms of finances and capacity-building throughout the duration of the LDCF project. Consequently, the PSB will provide guidance and feedback to the PSC regarding funding, implementation and policy recommendations. Where changes to the Results Framework or timeline are recommended by the PSC, or where the delivery of project outcomes is likely to be delayed or impaired, the PSC will notify UNEP DEPI/GEF CCAU and the PSB well in advance to allow for corrective action to be undertaken.

For the purpose of the execution of the project, a PMU will be established at NEPA that will support day-to-day project execution. The PMU will be accountable to UNEP DEPI/GEF CCAU for ensuring:

- the quality of the different outputs and outcomes of the LDCF project;

- the effective use of both international and national resources allocated to it;

- the timely availability of financing to support project implementation; and

- the proper coordination among all project stakeholders, in particular, national parties.

A full-time NPC will be hired for day-to-day management of the project. He/She will head the PMU and will be liaise with the Senior Advisor (SA) in terms of execution support. The NPC will report to the Head of NEPA and to the SA. The NPC will also provide significant technical input into the relevant technical components of the project, playing both an oversight role and a hands-on role through training, production of documents and facilitation of consultant activities relevant to the NPCs area of expertise. The management role of the NPC will be to ensure that the project is managed in a transparent and effective manner, and that it is in line with all budget and work plans in accordance with guidelines from both GEF and UNEP. The PSC will work closely with NEPA officials and national coordinators (including the NEPA GEF coordinator) to ensure that project implementation closely adheres with national priorities and is facilitated by extant government structures.

In order to address the lack of technical capacity, UNEP DEPI/PCDMB will assign a staff member to provide project oversight and assistance, designated as the SA. The role of the SA will be to provide day-to-day guidance to the NPC on the implementation of the LDCF project. This will include: i) providing advice on suitable methodologies and approaches for achieving project targets and objectives; ii) assisting in drafting ToRs for technical consultants and supervision of consultants’ work; iii) providing quality assurance and technical review of project outputs; iv) assisting in knowledge management and communications for awareness raising; and v) supervising and training of national technical advisors. Due to the complex nature of project and its interventions, it is anticipated that the SA will be assisted by a part-time Adaptation Specialist (international consultant). The Adaptation Specialist will provide specific support and advice on the highly technical ecological, water and agriculture-related aspects of the implementation of on-the-ground interventions. This support and advice will extend to measuring the cost effectiveness of the LDCF project interventions. The SA role will be part-time, with a larger commitment of time during the early stages of the project, and a decreasing time commitment as the project progresses. This reflects the building of capacity within the national structures.

Additional technical coordination and support will be provided by two national technical advisors (NTAs), each responsible for a portion of the LDCF technical work. The NTA positions will be full-time, and they will work closely with the NPC to assist in the management of the LDCF project activities. They will serve as liaisons between the NPC and other technical/administrative staff both within the CCU, and in the priority provinces. The responsibilities of the NTAs will depend upon their relevant expertise and capability, but it is anticipated that one NTA will be responsible for oversight of projects within Daykundi and Bamyan, whilst the second will focus on Badakhshan and Balkh. These positions will require regular travel to the provinces to interact with provincial NEPA staff and provide input to interventions being undertaken. In addition, the NTAs will provide technical guidance and backstopping of the role of the SA, and it is anticipated that they will take over the duties of the SA role as their capacity is enhanced throughout the project.

Budgetary disbursement will be managed by UNEP, to facilitate timely expenditure and disbursement, as well as promote transparency in expenditure. Financial reports will be prepared quarterly through the Integrated Management Information System (IMIS) through which UNEP tracks all internal expenditures, and will be made available to NEPA and other members of the PSC for review. Administrative support will be provided by an Administrative Assistant.

Additional project staff will include drivers and translators, since translation is a prerequisite for the operations of international staff within the country and UN DSS security rules requires transport with drivers for national staff. Specific technical support for specialised tasks that cannot be filled by government staff will be filled by consultants. International technical assistance will be sourced for those specialised tasks where insufficient capacity is available among government staff or national consultants. Such international consultants will be selected with the assistance of UNEP structures and in conjunction with the NPC. NEPA will commit staff and time for project implementation at the central office, as well as project officers in each of the provinces. In addition, it will contribute office space in the selected priority districts, and a vehicle at the central office. Other government agencies such as ANDMA, MEW and AMA will commit staff to contribute to project implementation for outputs relevant to their activities.

Meetings between the LDCF project and the baseline project managers (NSP, NABDP, RAMA and AgroMet) will be undertaken twice a year or more frequently if required. These meetings will involve project coordinators from the various programmes to ensure alignment of goals and prevent duplication of effort. The LDCF project is the first significant adaptation project to be implemented in Afghanistan. Strong coordination between other related national and local projects is required to maximise the value-added benefits of the LDCF project. As a result, a project managers’ coordination working group will be established to exchange lessons learned and coordinate efforts during the project implementation. This working group will comprise managers from other ongoing projects detailed in the Project Document, as well as new projects that may come online during the project duration.

Implementation of project demonstration activities within the identified priority areas will be undertaken by non-governmental partner agencies with proven track records of project implementation and strong community ties within the project sites.

part iv: explain the alignment of project design with the original PIF: 

The project follows and substantiates the rationale set out in the PIF. The four outcomes set out in the PIF have been retained, although some changes in the wording of the outcomes has been made in order to clarify the scope and boundaries of the project. The outputs have also been revised moderately during the PPG process to reflect priorities identified by national partners and concerns with the feasibility of some of the outputs as laid out in the PIF. The content remains the same, but the specific focus has shifted from a limited water-focus to a broader focus on water as a component of a functional landscape.

The distribution of funds has shifted from the original layout in the PIF, with a larger portion of the total amount being used for on-the-ground interventions. In addition, an application for an additional 10% ($490,000) for the budget has been made. This additional funding has been committed to security concerns, which is a necessary change in a potentially volatile nation such as Afghanistan. The additional security costs are integrated into the overall output costs in the CEO endorsement.

Table 3: A comparison of the outcomes and outputs in the original PIF and the revised wording in the project document.

| ### Original (PIF) |  | ### Revised (PD) |  |
| --- | --- | --- | --- |
| Outcomes | ### Outputs | Outcomes | ### Outputs |
| 1. Increased capacity and knowledge base for assessment monitoring and forecasting of CC to water related risks in Afghanistan. | 1.1 Capacity to assess, monitor, predict and interpret climate change – to-water related risks in Afghanistan (vulnerability maps produced for planning purposes). 1.2 A functional EWS system for the systematic collection, analysis, and distribution of information on CC –to – water related risks at the national and community levels in place. 1.3 Technical and policy briefs for policy makers on CC –to – water related risks. | 1. Increased capacity and knowledge base for assessment monitoring and forecasting of climate change-induced risks to water in Afghanistan. | 1.1 Improved tools to assess, monitor, predict and interpret climate change related risks and associated training course development and delivery. 1.2 A model and standard operating procedures for a national EWS system for the systematic collection, analysis, and distribution of information on climate change-induced risks to water resources at the national and community levels developed, and piloted in the four priority provinces. 1.3 Technical and policy briefs for policy makers on climate change risks to water and other key sectors developed. |
| 2. CC risks integrated into relevant policies, plans and programmes. | 2.1 Tools and methodology for identification, evaluation and mainstreaming of CC adaptation measures in water sector and other water related/ affected sectors. 2.2. Inter–ministerial coordination mechanism in place for CC risk integration. 2.3 CC risk and adaptation measures integrated into relevant existing sectoral policies and plans (water, agriculture, disaster and conflict prevention). 2.4 Capacities to implement the national CC adaptation strategy and climate proofed sectoral plans are developed. | 2. Climate change risks integrated into relevant policies, plans and programmes. | 2.1 Tools and methodology for identification, evaluation and mainstreaming of climate change adaptation measures in the water sector and other water related/ affected sectors developed. 2.2 Tools and training material targeting the current inter–ministerial coordination mechanism for climate change risk and adaptation integration (NCCC) developed. 2.3 Policy options to include climate change risk and adaptation measures for sectoral policies and plans (water, agriculture, and disaster and conflict prevention) developed and proposed. 2.4 Capacities developed to implement the national climate change adaptation strategy and climate proofed sectoral plans. |
| 3. Reduction of CC vulnerability in the selected project sites through use of appropriate technologies for improved water use efficiency and increased environmental resilience. | 3.1 Introduction and testing efficient water management technologies adapted to intensive and prolonged droughts (including drip irrigation, water storage systems, water canals and their use). 3.2 Introduction and testing agriculture management practices to reduce water needs adapted to intensive and prolonged droughts (including drought tolerant varieties, diversified crops, adapted cultivation practices, seed banks). 3.3 Introduction and testing watershed management practices adapted to intensive and prolonged droughts and intensive floods (including grazing management, terracing, planting of grass and trees, improvement of water canals). 3.4 Creation and institutional strengthening of water management associations including through training of the members on integrated water resources management. | 3. Reduction of climate change vulnerability in the selected project sites through local institutional capacity building and concrete interventions for improved water use efficiency. | 3.1 Pilot demonstrations to build resilience in the irrigated agricultural sector through cost efficient water infrastructure and irrigation technologies implemented in Badakhshan Province. 3.2 Pilot demonstrations to build resilience in the dryland agricultural sector through drought-resilient crops, water harvesting and catchment restoration measures implemented in Balkh Province and Badakhshan Province. 3.3 Pilot demonstrations to build resilience in rural peri-urban communities through restoration of aquatic zones implemented in Daykundi Province. 3.4 Creation and institutional strengthening of water management associations by training members on integrated water resources management and ecosystem based adaptation in Bamyan District and other pilot areas. |
| 4. Increased knowledge of good practices on increasing resilience to CC –to – water related risks. | 4.1 Project lessons captured in, and disseminated through a project specific web site and Global Adaptation Network (GAN). 4.2 Project knowledge shared with other countries in the region facing similar climate-induced drought and flooding hazards. 4.3 Project knowledge incorporated into national flood and drought prevention and public service training programmes in Afghanistan. 4.4 Raised awareness, using appropriate means, on CC –to – water related risks and adaptation for local communities and key national policymakers. 4.5 Resources mobilized for replication of the project lessons and demonstrations in other locations of Afghanistan. | #### 4. Increased knowledge of good practices on increasing resilience to climate change-induced risks to water resources. | 4.1 Project lessons captured in, and disseminated through a project specific web site, the Global Adaptation Network (GAN) and the Asia-Pacific Adaptation Network (APAN). ##### 4.2 Project knowledge shared with other countries in the region facing similar climate-induced drought and flooding hazards. ##### 4.3 Project knowledge for national flood and drought prevention incorporated into training approaches and materials. 4.4 Awareness raising activities on climate change-induced risks to water resources and adaptation for local communities and key national policymakers delivered using appropriate means. ##### 4.5 Resource mobilisation strategy developed for replication of project lessons and demonstrations in other locations of Afghanistan. |

# part v: Agency(ies) certification

| This request has been prepared in accordance with LDCF policies and procedures and meets the LDCF criteria for project endorsement. |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Agency Coordinator, Agency name | Signature | Date (Month, day, year) | Project Contact Person | Telephone | Email Address |
| Maryam Niamir Fuller Director GEF Coordination Office |  | 08/27/2012 | Ermira FIDA Portfolio Manager, UNEP-GEF Adaptation | +254-20 762 3113 | ermira.fida@unep.org |

# Annex A: Project Results Framework

|  |  | Indicator | Baseline | Targets | Source of verification | Risks /Assumptions |
| --- | --- | --- | --- | --- | --- | --- |
| Project Objective: “to increase resilience of vulnerable communities and build capacity of local and national institutions to address climate change risk”. |  | 1. The percentage change in vulnerability of men and women living in the identified priority sites to climate change risks on the availability of water for productive and domestic uses. | 1. The baseline will be determined in the identified priority sites during the inception phase through a VRA. | 1a. Mid-way through the project, a 20% increase in the VRA scores. 1b. By the end of the project, a 50% increase in the VRA scores. | 1. Gender-sensitive field surveys/VRA. | Risks: Deterioration of security situation in project sites. Assumption: Identified priority sites are best placed to demonstrate the benefits of measures to adapt to climate change. Local political interference in project implementation is minimal. Government and partners are committed to adaptation and climate risk action. |
|  |  | 2. Number of national and sectoral policy and strategy documents revised/or developed to include climate change. | 2. There is no national climate change policy, and sectoral policies and strategies do not make any significant mention of climate change | 2. By the end of the project, at least : - one national climate change policy developed; and - one sectoral policy or strategy document is revised. | 2. Revised policy/ strategy documents. |  |
|  |  | 3. Number of national and local experts trained to address climate change and integrate it into national planning | 3. There are currently no experts or staff trained to integrate climate change into national planning | 3. At least 1 member of staff in each relevant government agency (MRRD, MEW, NEPA, MAIL, ANDMA) trained | 3. Reports detailing training workshops including attendance sheet and/or certificates. Revised policy/strategy documents. |  |
| Component 1 Climate change risk assessment, monitoring and forecasting information. | Outcome 1 Increased capacity and knowledge base for assessment monitoring and forecasting of climate change-induced risks to water in Afghanistan. | 1. Number of climate change risk assessment training events undertaken, and number of staff from relevant agencies trained in the skills necessary for climate change risk assessments. | 1. No training in forecasting, analysis and climate risk response has been undertaken. | 1. By the end of project,: - At least one national training workshop and five regional training workshops have been completed. - A functioning unit within AMA or MAIL is capable of undertaking climate risk assessments (at least 5 individuals). | 1. ARP Reports detailing training workshops including attendance sheet and/or certificates. | Risk: Deterioration of security situation in project sites. Assumption: Availability of technical expertise and equipment. Targeted institutions are willing to participate in training. |
|  |  | 2. Number of staff from relevant agencies trained in specific skills needed for climate change EWS. | 2. None | 2. At least 2 representatives of the following agencies: AMA; ANDMA; MAIL and MEW trained in specific skills needed for a climate change EWS. | 2. ARP Reports detailing training workshops including attendance sheet and/or certificates. |  |
|  |  | 3. Vulnerability maps based on regional climate change models, spatial models and hydrological models produced. | 3. Vulnerability maps of climate change risks are not presently available. | 3. By the end of the project, at least 1 detailed vulnerability map produced for each of the four ecoregions in Afghanistan. | 3. ARP Vulnerability maps. |  |
|  |  | 4. Type, amount and quality of EWS equipment provided to communities in trial areas. | 4. None | 4. By the end of the project, all required equipment has been distributed to communities in trial areas. | 4. ARP Field visits (surveys/interviews) to the communities in trial areas. |  |
|  |  | 5. SOPs for EWS designed, tested, and integrated into ANDMA structures. | 5. No climate EWS exists in Afghanistan | 5a. Midway through the project, SOPs for an EWS developed. 5b. By the end of the project, a functioning EWS trialled in the priority project areas. | 5. ARP SOPs developed. Number of relevant staff trained. |  |
| Component 2 Climate change adaptation and response strategies. | Outcome 2 Climate change risks integrated into relevant policies, plans and programmes. | 1. Climate change adaptation toolkit developed . | 1. No climate change adaptation toolkit has been developed for Afghanistan. | 1. By the end of the project, a comprehensive adaptation toolkit developed. | 2. ARP The adaptation toolkit. | Risk: Deterioration of security situation in project sites. Assumption: Government commits itself to incorporate climate change adaptation into its policy documents as a matter of priority. |
|  |  | 2. Climate change adaptation policy for Afghanistan developed. | 2. No climate change policy has been developed for Afghanistan. | 2. By the end of the project, a climate change policy including adaptation and mitigation approaches developed. | 2. ARP Afghanistan climate change policy document. |  |
|  |  | 3. Relevant sectoral policy and strategy documents revised to include climate change. | 3. Sectoral policy and strategy do not make any significant mention of climate change. | 3. By the end of the project at least one sectoral policy or strategy document is revised. | 3. Revised policy/ strategy documents |  |
| Component 3 Practices for water resources and watershed management piloted and tested in selected project sites. | Outcome 3 Reduction of climate change vulnerability in the selected project sites through local institutional capacity building and concrete interventions for improved water use. | 1. Change in the number of households with access to efficient water management technologies (including drip irrigation, water storage systems and water canals) for flood and drought management (disaggregated by gender). | 1. The baseline will be determined in the identified priority sites through surveys in the project inception phase. | 1a. At least 424 households with access to AMIT, or an increase in at least 42 hectares of micro-irrigated areas. 1b. At least 10,500m3 increased water storage capacity in check dams. 1c. At least three water storage impoundment dams constructed. | 1. Gender-sensitive household surveys undertaken within identified priority sites. | Risks: Deterioration of security situation in project sites. Extreme climate events such as floods and droughts could disrupt project activities and/or damage ecosystems and infrastructure. Assumption: Identified priority sites are best placed to demonstrate the benefit of implemented climate change adaptation measures. Local political support for project implementation is strong. |
|  |  | 2. % change in the number of households and total agricultural area where agricultural management techniques adapted to intensive and prolonged droughts are practiced. Such activities include use of drought-tolerant crop varieties, diversification of crops, use of climate change-adapted cultivation practices and maintenance of seed banks. | 2. The baseline will be determined in the identified priority sites through surveys in the project inception phase. | 2a. At least 400 ha of agricultural land planted with drought-tolerant crop varieties for 3 successive seasons. 2b. At least 400 ha of micro-catchment techniques such as catchment ponds, contour bunds and strip-crops 2c. At least 200 ha of degraded watershed slops restored with multi-use tree species. | 2. Household/ agricultural area surveys undertaken within identified priority sites. | Risks: Deterioration of security situation in project sites. Extreme climate events such as floods and droughts could disrupt project activities and/or damage ecosystems and infrastructure. Assumption: Identified priority sites are best placed to demonstrate the benefit of implemented climate change adaptation measures. Local political support for project implementation is strong. |
|  |  | 3.1. Area (ha) of flood-mitigating infrastructure implemented in rural and peri-urban areas. 3.2. % survivorship of newly planted multiple-benefit tree and shrub species 24 months after planting date. | 3.1. 0 ha 3.2. NA | 3.1a. At least 120 ha newly planted with multiple-benefit species (to enhance ecosystem services such as water catchment, soil stabilisation, and flood protection). 3.1b. At least 140 hectares of low-cost water barriers and catchment structures for each of 3 villages (these targets are likely to be re-assessed in light of the baseline). 3.2. At least 80% survival for planted multiple-benefit tree and shrub species. | 3.1a. Field survey techniques, maps, GPS coordinates of areas rehabilitated. 3.2. Field survey techniques. | Risks: Deterioration of security situation in project sites. Extreme climate events such as floods and droughts could disrupt project activities and/or damage ecosystems and infrastructure. Assumption: Identified priority sites are best placed to demonstrate the benefit of implemented climate change adaptation measures. Local political support for project implementation is strong. |
| Component 4 Adaptive learning and dissemination of lessons learned and best practices. | Outcome 4 Increased knowledge of good practices on increasing resilience to climate change-induced risks to water resources. | 1. Number of knowledge products generated and disseminated. | 1. None | 1a. By the end of the project, lessons learned are distributed: - in hard copy (e.g. pamphlets, briefing notes, newsletters, booklets etc); - electronically via the project website and Global Adaptation Network (GAN); and - media (radio, TV). 1b. Mid-way through the project, a project website is operational and is regularly updated with project information. | 1. Project evaluation reports. ALM, GAN, and WeAdapt platform. Visit to project website. | Risk: Deterioration of security situation in project sites. Assumption: Identified priority sites are best placed to demonstrate benefit of implemented climate change adaptation measures. |
|  |  | 2. National policy workshop on climate change adaptation organised. | 2. No | 2. At least one national policy workshop on climate change adaptation organised. | 2. ARP Workshop report including attendance sheet. |  |
|  |  | 3. Number of public service training programmes in Afghanistan integrating knowledge generated from project lessons learned. | 3. None | 3. At least one public service training program in Afghanistan based on project lessons, generated. | 3. ARP Training tools with integrated knowledge from project lessons learned. |  |

Annex B: Responses to Project Reviews (from GEF Secretariat and GEF Agencies, Responses to Comments from the Convention Secretariat made at PIF)

# GEF SECRETARIAT REVIEW FOR LDCF/SCCF PROJECTS1

(For both FSPs and MSPs)

________________________________________________________________________________________________________________________

Type of Fund: Least Developed Countries Fund (LDCF)

Country/Region: Afghanistan

Project Title: Afghanistan: Building adaptive capacity and resilience to climate change in Afghanistan.

# GEFSEC Project ID: 4227

GEF Agency Project ID:

# GEF Agency: UNEP

Anticipated Project Financing ($): PPG: $0; GEF Project Allocation: $4,900,000; Co-financing: $16,000,000; Total Project Cost: $20,900,000

PIF Approval Date: Anticipated Work Program Inclusion:

Program Manager: Deborah Hines

GEF Agency Contact Person: Ermira FIDA

_________________________________________________________________________________________________________________________

| No of and question / comment as it appears in the review sheet | Secretariat Comment at PIF/ Work Program inclusion | Response to Secretariat Comment at PIF/ Work Program inclusion | Updated response to Secretariat Comment at PIF/ Work Program inclusion following production of the Project Document (Comments not addressed at the PIF stage, and now addressed in the Project Document, are underlined in the ‘Response to Secretariat Comment at PIF/ Work Program inclusion’ column) |
| --- | --- | --- | --- |
| 3. Does the Agency have a comparative advantage for the project? | UNEP has a comparative advantage for the capacity building, assessment, and knowledge management components. However, its comparative advantage for component 3 is not well documented. Further the PIF does not address UNEP's capacity in the water sector or its comparative advantage for national water subsector projects. Recommendation: The comparative advantage of UNEP should be reviewed and made clear, with specific attention given to its role in the water sector and specifically for component 3. UNEP would need to work closely with partners in country in the execution of water practices activities. These partnerships should be clearly detailed in the project document. Resource | The text concerning UNEP’s comparative advantage has been revised in order to reflect UNEP’s experience and role in water sector in particular and adaptation in general with a focus on Ecosystem Based Adaptation which is the UNEP’s flagship program. In response to the required clarification the section on comparative advantage has reviewed to read as follows: “UNEP’s work on climate change adaptation focuses on three main areas: (i) Science and Assessments, (ii) Knowledge and Policy Support, and (iii) Building the Resilience of Ecosystems for Adaptation. UNEP’s credibility as a capacity builder, ecosystem manager and knowledge mobilizer is built through the implementation of around 80 projects on adaptation at global, regional and national levels, spread worldwide. UNEP has shifted the focus of its adaptation work on Ecosystem-Based Adaptation (EBA) which is known as EBA Flagship Programme. This is an approach to work with nature to build resilience of vulnerable ecosystems and use ecosystem services for adaptation and disaster risk reduction. The activities proposed under this proposed project cut across above areas of UNEP’s work on climate change adaptation. The project is consistent with UNEP’s comparative advantage as identified through the GEF Council paper on the subject (C.31/5 ), which delineates UNEP’s comparative advantage in providing the GEF with a range of relevant experiences, proof of concept, testing of ideas, and the best available science and knowledge upon which it can base its investments as well GEF Council paper (C.28/18), which delineates UNEP’s comparative advantage areas including: (i) strengthening meteorological and climate early warning systems (i.e. addressed through component 1 of this project, which seeks to strengthen the capacity to analyze and predict climate change impacts) and (ii) developing and using climate information to effect changes in relevant sectoral policies based on climate science. This is addressed through components 2 and 3 and 4, which seek provisions of methods and tools to support decision making, addressing barriers to implementation, and testing and demonstrating innovative solutions, as well as building climate resilience through ecosystem based adaptation approach. The project contributes to the achievement of the three following outcomes of the UNEP’s Program of Work for 2010-2011 for Climate Change Adaptation: (a) the generation and mobilization of knowledge for adaptation including through impact and vulnerability assessment, the Global Adaptation Network and a World Research Programme on Impacts, Vulnerability and Adaptation; (b) support for capacity building, policy setting and planning; and (c) support for ecosystem-based adaptation. The project is also consistent with UNEP’s work in the water sector, built on the UNEP Water Policy and Strategy as well as the achievements from the EMINWA (Environmentally-sound Management of Inland Waters) program and other programs falling under the IWRM. Within this focal area, UNEP draws on its expertise in assessment and monitoring, generation and application of knowledge and approaches for the better management of water systems. As UNEP continues to move towards implementing its water mandates as defined by its Governing Council, its activities in this focal area take as reference ecosystem based approaches. This is the approach already being used by many other UNEP’s LDCF projects addressing water resources in the following countries: Djibouti, Comoros, the Gambia, Tanzania, Cambodia as well as non-LDCF ones such as Nile River Basin project, lake Fagubine (Mali) project, Sudan IWRM project GEF SIDS project etc. The project will benefit the UNEP presence in Afghanistan. The UNEP office in Afghanistan enjoys strong, productive working relationships with the project partners at local and national level in the country. The UNEP office is also implementing community based natural resource management interventions in different Afghan provinces. It has also provided support to the Afghan delegation on its preparation for CoP15. UNEP has been helping the Government of Afghanistan to deliver technical and support services to the poor more effectively. UNEP has provided technical and administrative support to Afghanistan to elaborate its Initial National Communication (INC), the National Adaptation Programme of Action (NAPA), and the National Capacity Self Assessment for Global Environment Management (NCSA) through a synergic approach. UNEP is working together with national partners to develop the capacity of local government and communities to develop and implement sustainable natural resource management plans in Afghanistan. In the area of disaster preparedness and management, UNEP is currently supporting the elaboration of a regional national disaster management strategy. UNEP has an ongoing environment portfolio managed by a dedicated unit in partnership with national partners and other UN agencies. UNEP’s strong relationship with Government’s counterpart provides a unique position to mainstream key issues, such as CC and water management, in national policies, strategies and plans. UNEP’s current work to strengthen local governance and service delivery offer other opportunities to promote key issues at provincial and district levels. UNEP will aslo work closely with international partners in country in the course of proejct implementation. These partnerships should be clearly defined during the PPG and detailed in the project document. The Government of Afghanistan has defined sustainable livelihoods as a top priority in ADNS. UNEP has been assisting the country to achieve this goal under the United Nations Development Assistance Framework (UNDAF). The proposed project is aligned with UNEP’s comparative advantage, as articulated in the GEF Council Paper C.31.5 “Comparative Advantages of GEF Agencies”, in the area of capacity building, providing technical and policy support as well as expertise in project design and implementation. UNEP’s strengths come from its mandate to manage environment for sustainable development and to strengthen national capacity for natural resource management. The proposed project will be linked to these ongoing programmes/projects of UNEP, thereby ensuring that the results of this project will be up-scaled and mainstreamed into national development processes. UNEP is, therefore, best-positioned to implement this adaptation project.” | Response 1: The partners with which UNEP will work closely for the implementation of the LDCF project are outlined in the Project Document in ‘Section 2.8: Linkages with other GEF and non-GEF interventions.’ Additional details of linkages between the LDCF project and existing projects are provided in ‘Appendix 10: Project linkages to be established and maintained by the LDCF project.’ Furthermore, coordination will be sought with regional and local partners to strengthen the LDCF project. The mechanism for control of this coordination is outlined in ‘Section 4: Institutional Framework and Implementation Arrangements’ as follows: “Strong coordination between other related national and local projects is required to maximise the value-added benefits of the LDCF project. As a result, a project managers’ coordination working group will be established to exchange lessons learned and coordinate efforts during the project implementation. This working group will comprise managers from other ongoing projects detailed in Section 2.8, as well as new projects that may come online during the project duration.” |
| 5. Will the project deliver tangible adaptation benefits? | Not clear. 5.1 Component 1 does not address the fact that this part of the country is a desert area...droughts are to be expected. Climate forecasts will forecast dry conditions. 5.2 Capacity development needs to address water subsector issues related to institutions, national assistance to localities, irrigation T/A investments, and aquifer investigations/management measures. Component 2 and 3 address adaptation planning so local farmers will better understand climate hazards. The value of this action is not clearly demonstrated for this desert area of the country. The adaptation benefits relate to increased capacity to assess, monitor and predict water related climate risks, and to ensure that these risks are integrated into relevant policies and programmes could be useful but it is not clear that the project will address this gap, or if it can given the current situation in Afghanistan. 5.3 In addition, the on the ground water and agriculture practices should generate benefits related to reduced vulnerability through the adoption of appropriate technologies. However, the distinction between the "development issue" and the "adaptation issue" is not well defined. Lessons should be disseminated and fed back into other adaptation efforts | 5.1 New and increased climate evidences collected recently by the national team show that north and northeast Afghanistan are expected to experience the greatest precipitation decrease (up to 2.0 mm/year) all over Afghanistan over the next 50 years. This is not a desert area. It is an area prone to droughts and floods. Following additional consultations among stakeholders held recently in the course of addressing the GEF sec comments to the PIF, the project demonstration activities are proposed to focus in the north and north east with the aim to undertake a participatory site selection during the PPG, subject of an in depth analysis and assessment. The PIF is now making reference to northern Afghanistan as most vulnerable including for new evidences of observed climate change and impacts which are inserted in the text. The following text is inserted in the section A to reflect the above: “The region of Northern Afghanistan is found to be very vulnerable as reported by NAPA and evidences including from outcomes of 50 years data record and modelled scenarios developed by CRU centre. This area is prone to droughts and floods and because of the high population density and reliance on crops and livestock it is highly affected from climate change and this would continue to be the case unless timely adaptation measures are implemented. An evidence of this are recent floods which occurred in this region in early May 2010 which have highly affected eight districts in the Northern region (Almar, Bilchiragh, Dawlatabad, Ghormach, Gurziwan. Khoja Sabz Posh, Maimana city, and Pashton Kot) with 80 percent of affected districts’ roads reported damaged and 19 people killed by floods. 1,800-2,500 families were reported affected in Jawzjan province and 550 families in Fayzabad district have been displaced by rising water to two locations (a bridge and a school). 2,000 families from Balkh province were evacuated because of the massive floods. About 356 households from Baghlan province were affected (185 of which had homes completely destroyed); Yangi Qala province reported 173 affected families in four villages; Flood killed 3 people, injured 10 people, and damaged 10 houses Badakhshan province .” Additional information is added to the subsection on Afghanistan context under section A in order to address the fact that the country is prone to droughts and part of it (southeast part) is a desert area. Information on the average of received precipitation as well as wet and dry seasons is provided. The following additional text has been inserted to the subsection Afghanistan context: “Afghanistan receives an average of 316 mm (12.4 in) of rainfall per year, or 26 mm (1.0 in) per month. In average there are 55 days per year with more than 0.1 mm (0.004 in) of rainfall (precipitation) or 5 days with a quantity of rain, sleet, snow etc. per month. The driest period occurs around September with an average of 1 mm (0.0 in) of rainfall (precipitation) across less than in 1 day. The wettest period occurs around March with an average of 91 mm (3.6 in) of rainfall (precipitation) across 10 days” The following additional text on information on the observed climate variability and change over the last 50 years has also been inserted to the subsection: Observed and expected climate changes and its impacts: “During the last 50 years the temperature is increased by approximately 0.8 – 1 °C and precipitation is decreased by approximately 90-100 mm. Greater temperature amplitudes are observed during the last 50 years in Afghanistan, with extreme temperatures exceeding by 30% long terms maximum and minimum temperatures. “ The text concerning climate impacts on droughts is enriched with more information on climate forecast / predictions including new evidences collected recently by the climate change team which highlights the expected increased duration and frequency of droughts. The text is modified to read as follows: “Droughts are becoming more extreme and intense due to a steady temperature increase and rainfall decrease in the country. A regular drought cycle of 15 years has been observed in Afghanistan during which one would expect 2-3 years of drought conditions. However, since 1960 the country has experienced droughts more often (1963-1964; 1966-1967; 1970-1972 and 1998-2006) with the drought of 1998-2006 marked as the longest and most severe one in Afghanistan’s climatic history. Both surface and groundwater resources have been severely affected by the droughts as well as uncoordinated and unmanaged extraction. Available information shows that functional irrigation systems are running at about 25 % efficiency against their potential of 40-60%. This has resulted in observed decreases in the crop and other agricultural production. Climate change predictions for Afghanistan indicate further increases yet in drought frequency and duration over the next 50 years, as well decrease of the overall precipitation patterns particularly in the north (northwest and northeast) Afghanistan. The net effects at horizon 2050 would be: (i) decrease in crops productivity (with a predicted 60% loss of overall farm production loss of fertile, pasture and arable land and associated increase in malnutrition in rural communities) (ii) increase in drought-related conflicts (i.e. water access, rights and management); and (iii) migration of farmers towards urban areas.” - Capacity development interventions cutting across Component 1, 2 and 3 do now clearly address water issues related to institutions, national assistance to localities including Early Warning Systems, irrigation T/A investments, and aquifer investigations/management measures etc. In addition, component 2 and 3 which address planning bring additional values for farmers who will benefit from EWS (comp 1) and adaptation practices to be introduced and tested through the project (comp 3). All adaptation benefits mentioned in Section A are clearly addressed throughout the component description. The text under component 1, 2 and 3 which is now modified to reflect all the above reads as follows: “Component 1: Climate Risk Assessment, Forecasting and Information. The objective of this component is to increase the capacity and knowledge base for assessment, monitoring and forecasting of climate change to-water related risks. More specifically, activities under this component will aim at building national-level scientific and technical capacity to assess, monitor and interpret water related climate change impacts and associated risk in Afghanistan, including through the production of vulnerability maps for planning purposes, risk maps for land use planning, as well as future climate scenarios to feed in the water planning process. Protocols and institutional mechanisms for the dissemination of climate-related information, including Early Warning Systems for floods, droughts and extreme weather temperatures, will be developed and tested. Technical capacity of water-related institutions at national and sub-national level to undertake: water-related assessments (groundwater monitoring, water quality monitoring, and irrigation systems rehabilitation) will also be strengthened under this component. Component 2: CC adaptation planning and response strategies. The objective of the activities under this component is to integrate climate change risks into key national and sub-national policies, plans and programmes that govern water resources management and mobilization, land use planning, agricultural policies and other water related/affected sectors. Based on the information obtained through the assessments and studies to be undertaken under component 1 as well as the available and relevant knowledge, activities under component 2 will aim at developing tools and methodology for identification and evaluation of climate change adaptation strategies, such as targeted technical policy briefs for decision-makers. This project will benefit from a range of innovative climate-based analytical tools, methodologies, and software such as GIS climate change models, time-series analysis for multi-variables (i.e. precipitation, temperature, cloud cover, etc.) and ad-hoc mapping software for Afghanistan.. Based on knowledge acquired, the project will also aim at achieving the revision of existing sectoral strategies (agriculture, disaster and conflict prevention) in order to make them resilient to predicted climate change and to promote sustainable adaptation options. The overall climate risk mainstreaming exercise will be supported by efforts to set up and strengthen an inter-ministerial coordination mechanism for climate change risk assessment and integration. This component will be implemented at national and provincial level with key sectoral ministries. Component 3: Practices for water resource and watershed management piloted and tested in selected project sites. The objective of the activities under this component is to reduce climate change vulnerability at local level through pilot demonstration and interventions in the project site (to be selected during the PPG phase) as a means for demonstrating the validity of adaptation options and further informing national policy making. This will be achieved through the introduction and testing of innovative water and crop management practices adapted to prolonged droughts and intensive floods such as: efficient water management technologies (including drip irrigation, water storage systems, water canals and their use, as well as water allocation mechanisms); water efficient agriculture practices (including drought tolerant varieties, adapted cultivation practices such as reduced or low-tillage, soil fertility management, anti-erosive measures) and integrated community watershed management systems (including community-based grazing management, terracing, planting of grass and trees, improvement of water canals). In addition, the early warning system designed through component 1 will be tested at local level. Water management associations consisting of community members will be set up and strengthened to facilitate long term water management in the face of climate change. This component will be developed and implemented in conjunction with ongoing projects and activities in the selected region so as to generate added development benefits and to create synergies and economies of scale. This component will be implemented at local level with specific sites to be selected during the PPG implementation phase based on a comprehensive diagnostic of vulnerability and ongoing activities in the region in order to ensure cost-effectiveness of the interventions. - The following additional text is inserted in adaptation alternative for Component 3 which deals with on-the –ground water and agriculture practices, under additional cost reasoning section to clearly state the distinction between the “development issue” and “adaptation issue”: “The concrete interventions including their cost estimate and specific site selection will be agreed by stakeholders during the PPG implementation phase. The interventions will be designed and built to withstand to the expected impacts of climate change so as to be adaptive compared to the baseline interventions. For example water storage systems and water canals will be properly designed and embedded to resist to episodes of greater temperature amplitudes, droughts and flooding. Or, the crops and tree species to be planted will be selected to tolerate more intense and frequent climate hazards. Early Warning Systems developed though Component 1 interventions will be tested in this Component. Community members will be heavily involved in the implementation of the interventions of this component. In addition, water management associations consisting of community members will be set up and strengthened to facilitate water management in long term in the face of climate change. The LDCF funds will also be used to train the communities on how to maintain the adaptation infrastructure piloted by this project. When the relevant national plans would be revised the associations will be trained to implement them and apply the set standards by them. The project will also work on raising awareness of communities dealing with reforestation activities on the benefits of reforestation and sustainable harvesting including carbon benefits. This will ensure community ownership of the project interventions. Starting from a piloting in selected sites, the project will generate a series of lessons learned and best practices, the latter of which can be scaled up through adoption and adaptation by NEPA, MAIL and MEW at local and national level for IWRM and policy development” | Response 2: Provinces for the project demonstration activities were selected during the PPG phase. The demonstration sites are outlined in the Project Document in ‘Section 2.3: Demonstration sites’ as follows: “Local community interventions will be undertaken in four provinces of Afghanistan: Bamyan, Balkh, Badakhshan and Daykundi.” The process of site selection is outlined in the project document in ‘Section 2.3.1: Site selection criteria’ as follows: “A shortlist of provinces was selected during the inception workshop held in Kabul on 13 April 2011. This meeting was attended by stakeholders from many provinces and from all relevant ministries. Site selection criteria were decided upon by the stakeholders, and included poverty, agricultural dependence, water shortage, population pressure, incidence of drought and climate hazards, public awareness and education, and human health. Final province selection was undertaken by NEPA officials facilitated by the UNEP country team, and included additional essential criteria such as security risks and feasibility of operations within the provinces.” An example of the site selection criteria is provided in the project document in ‘Appendix 8: Example scoring sheet for site selection within provinces.’ Response 3: The specific sites for implementation of activities under Component 3 are detailed in the project document in ‘Section 3.2: Project goal and objective, Component 3’. Further details of activities in project sites (as well as a background of the sites) are provided in ‘Appendix 27: Details regarding the demonstration sites’. See Response3. Response 4: The concrete interventions and specific sites for implementation of activities under Component 3 are detailed in the project document in ‘Section 3.2: Project goal and objective, Component 3.’ Further details of interventions in project sites (as well as a background of the sites) are provided in ‘Appendix 27: Details regarding the demonstration sites.’ Cost estimates for interventions are provided in the project document in ‘Section 3.2: Project goal and objective, Component 3.’ and additional cost details are provided in: i) ‘Appendix 1: Budget by project components and UNEP budget lines (GEF funds only – US$)’; ii) ‘Appendix 2: Co-financing by source and UNEP budget lines’; and iii) Appendices 13-16 which provide a breakdown of indicative costs of Component 3 activities and interventions. |
| 6. Is the adaptation benefit measurable? | 6.1 The delivery of tangible adaptation benefits by the project is not fully clear from the PIF. 6.2 In addition, it is unclear who will benefit from component 3. Please provide greater clarity on the tangible adaptation benefits, especially in relation to project components 1 and 3. 6.3 Even though at the PIF stage, the expected outputs can be more clearly explained and stated in the project framework. (For example, as an output - "capacity for interpretation of CC to water related risks" is not clear and not at the correct results level.) Recommendation: Clearly spell out the expected outputs of the project. As framed in the PIF, the outputs should be stated as measurable outputs, and the description of the components should contain sufficient information to understand what outputs will be generated and how they will contribute to the component objective | 6.1 Section E on Additional Cost Reasoning has been reviewed to provide more clear details of the interventions including for tangible adaptation benefits listed at the end of the Section A. See adaptation alternative sections for each component. In addition see reply to comment 5 above for further changes to the text on proposed interventions. 6.2 Local communities living in the project site which will be selected during the PPG phase will benefit from the pilot interventions to be undertaken in component 3. The additional following text is inserted in the subsection : proposed project interventions and justification for Component 3: to reflect the beneficiaries: “The objective of the activities under this component is to reduce climate change vulnerability at local level through pilot demonstration and interventions in the project site (to be selected during the PPG phase) as a means for demonstrating the validity of adaptation options and further informing national policy making.” Additional following text is also inserted in the adaptation alternative for Component 3 under the additional cost reasoning section: “In close coordination with NEPA, MAIL and MEW, and through a highly participative approach, the project will pilot interventions that would improve resilience to CC for water management in the project selected site which will be identified during the PPG phase.” - Expected outputs are clearly spelled out along the lines of component description as well as additional cost reasoning. Those sections are modified to clearly describe the expected results. The output : “capacity for interpretation of CC to water related risks” has merged to the first output which is reworded to read as follows: “Capacity to assess, monitor, predict and interpret climate change – to-water related risks in Afghanistan. (vulnerability maps produced for planning purposes)” In addition, an Early Warning System to inform end-users on expected extreme weather events will be delivered through output 2 of component 1. This output is reworded to read as follows: “A functional EWS system for the systematic collection, analysis, and distribution of information on CC –to – water related risks at the national and community levels in place” | See Response 3. See Response 3. See Response 3. |
| 7. Is the project design sound, its framework consistent & sufficiently clear (in particular for the outputs)? | 7.1 Under component 3 of the project, it is not clear what adaptation measures will be implemented in relation to ongoing agriculture activities. 7.2 In the document list of ongoing activities, the World Bank and ADB water sector projects are not listed nor is GEF IW project in the Sistan Basin of the country through UNDP. Recommendation: Please be clear as to which activities are currently under implementation in the country and how the project proposed to work with specific ongoing initiatives, and how adaptation actions would be integrated into the water sector. Specify who will provide the required technical expertise. Include clear argumentation on how this component will help the targeted farmer groups to adopt agricultural practices that are resilient to climate change, e.g. what climate resilient practices and measures they will be informed about. | 7.1 A rapid assessment made during the PIF formulation process shows that the majority of ongoing and relevant projects in Afghanistan by other institutions do not fully (and directly) consider climate change impacts and consequences in their planned activities. The proposed LDCF project will build upon them and play a role of coordination among these interventions to ensure that climate change is considered and appropriately included in these projects’ activities. However, additional information on the relevant ongoing activities / projects in Afghanistan including those in agriculture is inserted in the baseline subsection under Component 3 (section E: Additional Cost Reasoning). As explained in our response to comment 5.3 additional information is inserted in adaptation alternative section to show what adaptation measures / interventions would be undertaken through this component. The baseline and adaptation alternative for component 3 now read as follows: Component 3: Baseline- “In collaboration with international donors and development agencies, the Afghanistan Government has been implementing various water management practices such as the rehabilitation of irrigation systems to reduce the vulnerability of farmers to extreme weather events and, thereby, improve food security. However, existing water management practices do not consider CC related changes in river flows, changing rainfall intensities and prolonged dry spells etc. Water management practices in Afghanistan (management, planning, irrigation, watershed management) have not yet been adapted to account for CC threats. There is a general lack of awareness about community-based approaches to address CC risks. There are no agricultural practices deployed for farmers living in drought-prone areas to cope with climate changes in place. There exist water management projects under implementation which do not address climate risk. They include: (i) Capacity Building and Institutional Development Programme for Environmental Management in Afghanistan (UNEP), (ii) Emergency Irrigation Rehabilitation Project (FAO), (iii) River Basin Management (EC), (iv) AgroMet (USAID), (v) Emergency Irrigation Rehabilitation (World Bank), (vi) Initiating Participatory Forestry in Support of Sustainable Livelihoods in Afghanistan (FAO), (vii) Climate proofing of horticulture in Afghanistan (DfID), (viii) Strengthened Approach for the Integration of Sustainable Environmental Management into the ANDS/PRSP (UNEP/UNDP), and the (ix) PEACE project (USAID). Ensuring synergic linkages between them to avoid duplication, including climate factor into them and promoting lesson sharing must be sought. A framework of best practices needs to be developed and adopted as a comprehensive and ecologically sensitive resilience approach to CC risk. Without the project degradation and unsustainable use of the natural resources will continue as no approaches to cope exist so far. The development assistance will continue to lack the climate factor. The country’s vulnerability will be increased in association with deepening of the poverty of the most vulnerable communities” Adaptation alternative: “In close coordination with NEPA, MAIL and MEW, and through a highly participative approach, the project will pilot interventions that would improve resilience to CC for water management in the project selected site which will be identified during the PPG phase. More specifically the project will pilot innovative and diversified efficient water management technologies such as: drip irrigation, water storage systems, water canals and their use; water efficient agriculture practices such as: drought tolerant varieties, adapted cultivation practices and integrated community watershed management systems such as grazing management, terracing, planting of grass and trees, improvement of water canals. The concrete interventions including their cost estimate and specific site selection will be agreed by stakeholders during the PPG implementation phase. The interventions will be designed and built to withstand to the expected impacts of climate change so as to be adaptive compared to the baseline interventions. For example water storage systems and water canals will be properly designed and embedded to resist to episodes of greater temperature amplitudes, droughts and flooding. Or, the crops and tree species to be planted will be selected to tolerate more intense and frequent climate hazards. Early Warning Systems developed though Component 1 interventions will be tested in this Component. Community members will be heavily involved in the implementation of the interventions of this component. In addition, water management associations consisting of community members will be set up and strengthened to facilitate water management in long term in the face of climate change. The LDCF funds will also be used to train the communities on how to maintain the adaptation infrastructure piloted by this project. When the relevant national plans would be revised the associations will be trained to implement them and apply the set standards by them. The project will also work on raising awareness of communities dealing with reforestation activities on the benefits of reforestation and sustainable harvesting including carbon benefits. This will ensure community ownership of the project interventions. Starting from a piloting in selected sites, the project will generate a series of lessons learned and best practices, the latter of which can be scaled up through adoption and adaptation by NEPA, MAIL and MEW at local and national level for IWRM and policy development. In the absence of this project’s interventions, degradation of natural resources in particular water resources will continue leading to food insecurity, extreme poverty and conflicts” - Following the comment made by the reviewer another stock take of relevant ongoing activities was made by the formulation team and the status of the three projects ( ADB, WB and UNDP GEF one) was found to be follows: - ADBwater sector project - it is still a ‘paper’ project: no official start, neither implementation. - UNDP GEF - This project has been put on hold and practically not active due to political reasons (issue between Iran and Afghanistan for the Sistan basin management). This stand-off is expected to last for sometime (2-3 years). # WB Emergency Irrigation Rehabilitation - it is inserted in the table of ongoing relevant projects. Another stocktaking exercise will follow in the course of the PPG phase in order to set up a clear baseline of the ongoing activities/ projects. | See Response 3. See Response 4. Response 5: The baseline of ongoing activities/ projects is outlined in the project document in ‘Section 2.7 Baseline analysis and gaps’ which provides the details of baseline projects related to Components 1-4. |
| 9. Is the project consistent with the recipient country’s national priorities and policies? | The coordination mechanisms are not clearly identified in the PIF. The PIF identifies possible linkages with FAO, DFID and with other ongoing projects. However two of the FAO projects end in 2010. However, clear coordination mechanisms are not presented. Recommendations: The PIF should identify mechanisms for coordination, even if at the PIF stage it cannot provide the specific details of partnerships or concrete linkages | 9. A recent update from the respective projects (FAO and DFID) shows that the two projects will now end (postponed) for 2012 so the project would have time to build upon their results. Those changes have been reflected to the table of relevant ongoing projects. Through the Component 4 a donor and partner coordination mechanism for water-climate issues will be set up in Afghanistan so to better integrate ongoing and planned programs with this project activities in Afghanistan. This component will also– use project outcomes for informing donor policies as well, and also create a link to the interministerial forum so that lessons learned from the project interventions can be relayed back to the national-level decision-making. More details of this mechanism will be elaborated in the project document. | Response 6: Coordination will be sought with regional and local partners to strengthen the LDCF project. The mechanism for control of this coordination is outlined in the project document in ‘Section 4: Institutional Framework and Implementation Arrangements’ as follows: “Strong coordination between other related national and local projects is required to maximise the value-added benefits of the LDCF project. As a result, a project managers’ coordination working group will be established to exchange lessons learned and coordinate efforts during the project implementation. This working group will comprise managers from other ongoing projects detailed in Section 2.8, as well as new projects that may come online during the project duration.” |
| 10. Is the proposed project likely to be cost-effective? | The project is likely to be cost-effective as it will build upon ongoing related project results. However the cost effectiveness analysis must be fully developed in the project document. | A detailed cost effectiveness analysis would be addressed in the project document. | Response 7: Text on project cost-effectiveness is provided in the project document in ‘Section 7.3: Project cost effectiveness’. Furthermore, cost effective assessments will be conducted throughout the project period. This is outlined in the project document under ‘Section 3.2: Project goal and objective, Component 3.’ as follows: “By means of a learning-by-doing approach within the priority provinces, a number of different ecosystem management-based adaptation and enhanced agricultural and water management approaches will be undertaken. These approaches will be assessed throughout the project period to establish the most suitable and cost-effective methods of enhancing resilience despite increasing climate change-induced variability. The assessments will comprise cost-benefit analyses that will focus on quantifying improvements in yields, increases in associated income streams and input costs of the interventions. These assessments will provide data and information that will inform the national climate change adaptation agenda.” |
| 14. Is the value-added of LDCF/SCCF involvement in the project clearly demonstrated through additional cost reasoning? | The value-added of the LDCF resources to the project could be demonstrated more clearly by providing clearer additional cost reasoning. The additional cost must be clearly linked to the adaptation measures of the project. Recommendation: Please clarify and enhance the argument on the value-added of the LDCF involvement, especially in component 3 where the ratio of LDCF to funding is 1:5. | The adaptation argument for component 3 has been explained throughout the responses provided to the previous comments (6 and 7). The additional cost in component 3 will go for the additional cost of adaptation, i.e. to increase the resilience of development interventions. |  |

# Annex c: consultants to be hired for the project

No consultants are to be hired for the project management. This will be carried out by the PMU, with the assistance of the UNEP Senior Advisor.

| Local | $/ person months | Estimated person months | Tasks to be performed |
| --- | --- | --- | --- |
| 2 x National Technical Assistants | 2,100 | 48 (ea) | The National technical assistants will have the following responsibilities: - act as a liaison with provincial authorities and institutions; - oversee and manage project implementation, monitor work progress, and ensure timely delivery of outputs in provinces; - report to the NPC and SA regarding project progress. Reports should contain assessments of progress in implementing activities, including reasons for delays, if any, and recommendations on necessary improvements; - support the NPC in developing and facilitating implementation of a comprehensive monitoring and reporting system; - support in the preparation of detailed annual work plans and budgets for approval by PSC; - supervise, coordinate and facilitate the work of the technical staff in the provinces; - provide input to management and technical reports and other documents as described in the M&E plan for the overall project; - participate in the PSC meetings and coordinate project site visits; and - shadow the role of the SA in order to build take over the supervisory technical role in the later stages of the LDCF project. |
| Workshop facilitator | 1,500 | 9.8 | The national consultant (NC) will support the international consultant (IC) or other NCs in the organisation of training workshops by preparing materials and sharing information with participants. The NC will be required to facilitate workshops for: i) activity 1.1.4; ii) activity 2.3.4. and iii) activity 3.4.1. |
| Hydrological modelling specialist | 1,800 | 8.2 | The NC will work closely with IC to: - identify appropriate models and climate change vulnerability tools (activity 1.1.5); and - undertake hydrological modelling to assess climate change risks and produce vulnerability maps (activity 1.1.6). |
| Hydrological engineer | 1,575 | 6 | The NC will provide technical assistance in: - the design and construction of check dams and micro-irrigation improvements in Badakhshan (activity 3.1.1.1) |
| EWS/disaster management specialist | 1,700 | 6.8 | The NC will work closely with the IC to : - assess the current state of EW and reporting systems (activity 1.2.1); - examine options for climate EWS (activity 1.2.2); - develop model and SOPs for EWS (activity 1.2.3); and - support the provision of necessary infrastructure to communities in trial areas to facilitate EW delivery, and train communities, local officers and national officials to test EWS (activity 1.2.4). |
| Climate change adaptation specialist | 1,800 | 23.3 | The NC will: - prepare policy and technical briefs on climate change risks (activity 1.3.1); - support IC on policy makers climate change training course (activity 1.3.2); - evaluate the national climate change knowledge base and the effectiveness of integration into national policies (activity 2.2.1); - provide capacity building to the NCCC in the form of training and policy briefings (activity 2.2.2); - undertake a gap analysis of the national development plan and polices (activity 2.3.1); - develop an overarching climate change policy in conjunction with the IC and relevant stakeholder consultation (activity 2.3.3); - develop training tools for IWM (activity 3.4.2); - incorporate training tools in national public service training (activity 4.3.3); and - identify additional locations and interventions to achieve long-term adaptation goals (activity 4.5.2). |
| Policy adviser | 1,630 | 10.3 | The NC will work closely with IC to : - undertake dynamic systems modelling to investigate effects of climate change policy on national development priorities (activity 2.3.2); - develop an overarching climate change strategy for Afghanistan; and - promote integration of climate change into policies for all relevant sectors (activity 2.3.4). |
| Restoration ecologist | 1,800 | 9.3 | The NC will work closely with the IC to provide technical assistance to identify pilot activities that will reduce climate change vulnerability in the selected project sites through use of appropriate technologies for improved water use efficiency (output 3.1). |
| Socio-economist | 1,570 | 10.7 | The NC will : - identify and promote opportunities for alternative crops and agricultural practices (output 3.2); and - conduct socio-economic assessment at the local level for valuing ecosystems goods and service (output 3.3). |
| Ecosystem management specialist | 1,800 | 7 | The NC will provide technical assistance to: i) establish 200 ha of multiple benefit indigenous fruit and nut trees and rangeland species (output 3.2) ii) undertake a study to assess the value of various multiple-benefit plant species for the restoration of degraded ecosystems and provision of enhanced ecosystem services under conditions of climate change (output 3.3). |
| M&E Expert | 1,500 | 11.2 | The M&E Expert will: - determine the cost effectiveness of each proposed intervention (activity 4.3.1);and - undertake annual review of the project including IMIS data. |
| Climate change education specialist | 1,500 | 16.8 | The NC will assist the IC and NTAs to: - undertake a training needs assessment in climate change for relevant government bodies (activity 2.4.1); - provide training to build capacity in various sectors (activity 2.4.2); - develop training tools for IWM and ecosystem management at a local level (activity 3.4.2); - conduct training workshops on climate change risks and adaptation within local communities (activity 3.4.3); - formalize training tools for adaptation and flood/drought prevention (activity 4.3.2); - incorporate training tools into public service training (activity 4.3.3); and - develop climate change and adaptation lessons for integration into curricula and provide teacher training (activity 4.4.2) |
| Publicity expert | 1,500 | 7 | The NC will assist the LDCF by undertaking the following activities: - conduct national public awareness campaign on the risks of climate change and potential benefits of adaptation measures (activity 4.4.1); and - disseminate information about climate change and adaptation (activity 4.4.4). |

| International | $/person week | Estimated person weeks | Tasks to be performed |
| --- | --- | --- | --- |
| UNEP Senior Adviser | 2500 | 171 | This position is specifically requested by NEPA in order to facilitate the project implementation due to the lack of capacity within the country. The SA will fulfill the following functions: - provide quality assurance and undertake technical review of project outputs (e.g. studies and assessments); - assist in the drafting of TORs for technical consultancies; - supervise the work of consultants; - assist in monitoring the technical quality of project M&E systems (including AWPs, indicators and targets); - conduct the financial administrative reporting and the PIR; - provide advice on suitable approaches and methodologies for achieving project targets and objectives; - provide a technical supervisory function to the work carried out by national technical advisors, and consultants hired by the project; - develop strategic regional and international partnerships to facilitate capacity development and regular exchanges of data for climate change; - assist in knowledge management, communications and awareness raising; and - support development of relevant funding proposals (activity 4.5.3). |
| Institutional development specialist | 2500 | 10 | The consultant will: - undertake an institutional mapping exercise and training needs in assessment, monitoring, prediction and interpretation of climate change risks (activity 1.1.1); and - develop a strategic plan and data network for climate and information management and exchange (activity 1.1.2). |
| Climate change and water resource modeller | 2500 | 27 | The consultant will: - provide training on climate change, hydrological modelling (activity 1.1.4); - identify appropriate models and climate change vulnerability tools (activity 1.1.5); and - undertake hydrological modelling to assess climate change risks and produce vulnerability maps (activity 1.1.6). |
| EWS/disaster management specialist | 2500 | 8 | The consultant will: - examine options for climate change early warning systems (activity 1.2.2); and - develop model and SOPs for an EWS through stakeholder participation and expert analysis (activity 1.2.3). |
| Adaptation specialist | 2500 | 107 | The IC will play an integral role in the functioning of the project, due to the lack of national capacity with respect to climate change adaptation. The IC will work closely with the NC to: - produce technical briefs on climate change risks (activity 1.3.1); - provide technical assistance on the training on mainstreaming climate change adaptation (activity 1.3.2); - undertake a survey of tools and methodologies for identification, evaluation and mainstreaming of adaptation measures (activity 2.1.1) - develop a climate change toolkit (activity 2.1.2); - facilitate planting of drought resilient crop species and cultivars (output 3.2). - provide technical assistance in developing climate change policy (activity 2.3.3); - develop training tools for IWM and ecosystem management (activity 3.4.2); - formalize training tools for adaptation and flood/drought prevention (activity 4.3.2); - identify additional locations and interventions to achieve long-term adaptation goals(activity 4.5.2); and - support the provision of necessary infrastructure to communities in trial areas to facilitate EWS delivery, train communities and local officers in EWS procedures and test EWS (activity 1.2.4). |
| International negotiations specialist | 2500 | 5 | The consultant will provide training on international negotiations and funding applications to government officials (activity 2.2.3). |
| Dynamic systems modeller | 2500 | 12 | The consultant will undertake dynamic systems modelling to investigate effects of climate change policy on national development priorities (activity 2.3.2). |
| Restoration ecologist | 2500 | 12 | The NC will work closely with the IC to provide technical assistance to identify pilot activities that will reduce climate change vulnerability in the selected project sites through use of appropriate technologies for improved water use efficiency (output 3.1). |
| Ecosystem management | 2500 | 7 | The IC will work closely with NC to provide technical assistance for: i) establish 200 ha of multiple benefit indigenous fruit and nut trees and rangeland species (output 3.2); and ii) undertake studies to assess the value of various multiple-benefit plant species for the restoration of degraded water systems and catchment areas for enhanced water catchment and flood protection (output 3.3). |
| Carbon market expert | 2500 | 7 | The consultant will undertake feasibility studies to assess the potential of securing carbon funding (output 3.3). |
| M&E expert | 2500 | 21 | The consultant will undertake the following M&E tasks: - baseline assessment; - mid-term evaluation; and - final evaluation. |

# Annex d: status of implementation of project preparation activities and the use of funds

- explain if the ppg objective has been achieved through the ppg activities undertaken. The PPG objective was to compile the full project proposal by colecting data, developing an appropriate project baseline, developing a logframe, indicators, timelines and targets for the project. The PPG process was challenging due to two significant challenges: i) poor capacity of national consultants to carry out on-the-ground analyses and technical reviews, and ii) security challenges that prevented project staff from accessing certain areas. In the end, a baseline assessment was not undertaken, and has been delayed to the inception phase. However, extensive national consultation was undertaken through a well-attended planning workshop for relevant stakeholders, follow up meetings with government agencies and NGOs to determine needs, and through site visits by national consultants to priority districts identified during the planning workshop. Intervention locales were identified down to sub-district or village level in three of the four priority provinces (Bamyan, Daykundi and Badakhshan), whilst a relevant international executing partner was located for the final province, and interventions identified through consultation with relevant experts.The project document has been prepared, including roles and responsibilities of project stakeholders, M&E guidelines, a project logical framework, and details of interventions.

- describe findings that might affect the project design or any concerns on project implementation, if any. No additional risks were identified other than those in the risk table. However, during the PPG phase the preferred modality was changed in line with the request from the national partner to allow for UNEP DEPI/PCDMB to assist with project execution.

- provide detailed funding amount of the ppg activities and their implementation status in the table below:

| Project Preparation Activities Approved | Implementation Status | LDCF Amount ($) |  |  |  | Co-financing ($) |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | Amount Approved | Amount Spent To-date | Amount Committed | Uncommitted Amount* |  |
| 1. Technical Review and Feasibility |  | 37,710 | 37,710 | 0 | 0 | 40,000 |
| 2. Institutional arrangements, Monitoring and Evaluation |  | 27,590 | 27,590 | 0 | 0 | 29,000 |
| 3. Stakeholder Consultations |  | 25,540 | 25,540 | 0 | 0 | 30,000 |
| 4. Financial planning, co-financing and finalization of project document |  | 9,160 | 9,160 | 0 | 0 | 10,000 |
| Total |  | 100,000 | 100,000 | 0 | 0 | 109,000 |

* Uncommitted amount should be returned to the LDCF Trust Fund. Please indicate expected date of refund transaction to Trustee.

This template is for the use of LDCF Adaptation projects only.

NAPA of Afghanistan identifies water sector as a main concern which is reflected in the two priority projects identified in the NAPA: “1: Improved water management and use efficiency”; and “2: Community-based watershed management”.

http://gefonline.org/projectDetailsSQL.cfm?projID=3174

For additional information, see www.climateadapt.asia

VRA stands for Vulnerability Reduction Assessment. The VRA is a perception-based approach, to complement quantitative indicators that measure project results. See Droesch, A.C. Gaseb, N. Kurukulasuriya, P. Mershon, A. Moussa, K.M. Rankine, D. and Santos, A. 2008. A guide to the Vulnerability Reduction Assessment. United Nations Development Programme Community –Based Adaptation Programme.

An institutional mapping exercise and a training needs analysis in relevant government agencies to determine shortfalls in assessment, monitoring, prediction and interpretation of climate change risks as well gaps in EWS knowledge, practice and capacity will be undertaken as preliminary activities under outcome 1.

Type of required equipment to facilitate EWS delivery to communities will be developed during the development of the SOPs for the EWS.

Ad-hoc mapping software refers to high resolution satellite imagery of Afghanistan coupled with latest Global Climate Models (GCMs) and Local Climate Models (LCMs).