Project Identification Form (PIF)

Project Type:

Type of Trust Fund:

PART I: Project Identification

| Project Title: | Integrating Climate Change into Environment and Sustainable Land Management Practices |  |  |
| --- | --- | --- | --- |
| Country(ies): | Angola | GEF Project ID: |  |
| GEF Agency(ies): |  | GEF Agency Project ID: |  |
| Other Executing Partner(s): | Ministry of Enviroment | Submission Date: | 2012-12-20 |
| GEF Focal Area (s): |  | Project Duration (Months) | 36 |
| Name of parent program (if applicable): - For SFM/REDD+ |  | Agency Fee ($): | 419,540 |

A.  Focal AREA STRATEGY Framework:

| ### Focal Area Objectives | ### Expected FA Outcomes | ### Expected FA Outputs | ### Trust Fund | ### Indicative ### Grant Amount ### ($) | ### Indicative Co-financing ### ($) |
| --- | --- | --- | --- | --- | --- |
|  | Outcome 1.1: Mainstreamed adaptation in broader development frameworks at country level and in targeted vulnerable areas | Output 1.1.1: Adaptation measures and necessary budget allocations included in relevant frameworks |  | 550,000 | 4,000,000 |
|  | Outcome 2.2: Strengthened adaptive capacity to reduce risks to climate-induced economic losses | Output 2.2.1: Adaptive capacity of national and regional centers and networks strengthened to rapidly respond to extreme weather events |  | 1,050,000 | 4,000,000 |
|  | Outcome 3.1: Successful demonstration, deployment, and transfer of relevant adaptation technology in targeted areas | Output 3.1.1: Relevant adaptation technology transferred to targeted groupss |  | 2,600,000 | 10,000,000 |
|  | Others |  |  |  |  |
| Sub-Total |  |  |  | 4,200,000 | 18,000,000 |
| Project Management Cost |  |  |  | 216,210 | 1,995,000 |
| Total Project Cost |  |  |  | 4,416,210 | 19,995,000 |

- Project Framework

| ### Project Objective: Strengthening climate change into natinoal development activities and promoting adaptative measures and practices |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| ### Project Component | ### Grant Type | ### Expected Outcomes | ### Expected Outputs | ### Trust Fund |  | ### Indicative ### Grant Amount ($) | ### Indicative Cofinancing ### ($) |
| Governance, Capacity Building and Institutional Strengthening |  | Climate Change policy, strategy and legislation reviewed and revised to ensure applicability to various sectors Promotion of public consultation and participation in climate change and sustainable NR management | Introduction of climate policy, strategy and legislation Sectoral Climate Risk Assessment guidelines developed An operational training manual integrating climate change into EIA, climate proofing assessment tools and climate adaptation technologies (Risk to Resilience). Strenghtening institutional capacities of the Climate Risk Unit |  |  | 1,500,000 | 10,000,000 |
| Promoting climate adaptation measures into SLM practices in 4 demonstration sites, namely Namibe, Huambo, Kuando Kubango and Cabinda |  | Good SLM practices and technologies disseminated in the pilot demonstration sitesand adopted by relevant economic sectors Enhanced enabling enviroment in support of Climate Change Adaptation technology transfer Adoption of sustainable land mangament practices in the agro-forestry sector . | Demonstration of CC existing adaptation practice and technologies in the agro-forestry sector : natural regeneration technics, rangelands and agrosystems rehabilitation practices, wind breaks and dune stabilization methods, water efficiency and haversting techniques etc Increased collaboration between Forestry and Agriculture Departments on SLM and adaptation activities Dissemination of SLM good adaptation practices and technologies in agro forestry and land ecology and sensitization of 350 communties Commercialisation of adapted technologies by the government of Angola |  |  | 2,500,000 | 6,000,000 |
| Knowledge management through a coordination mechanism with other projects; and monitoring and evaluation |  | Lessons learnt are captured and appropriately disseminated M&E plans are implemented | Knowledge adaptation products Participation in adaptation practioneers events Monitoring and evaluation of the project |  |  | 200,000 | 2,000,000 |
| Sub-Total |  |  |  |  |  | 4,200,000 | 18,000,000 |
| Project Management Cost |  |  |  |  |  | 216,210 | 1,995,000 |
| Total Project Costs |  |  |  |  |  | 4,416,210 | 19,995,000 |

- Indicative Co-financing for the project by source and by name if available, ($)

| Sources of Cofinancing | Name of Cofinancier | Type of Cofinancing | Amount ($) |
| --- | --- | --- | --- |
|  | Government of Angola |  | 1,995,000 |
|  | AfDB |  | 18,000,000 |
| Total Cofinancing |  |  | 19,995,000 |

- GEF/LDCF/SCCF/NPIF  Resources Requested by Agency, Focal Area and Country1

| GEF Agency | Type of Trust Fund | Focal Area | Country Name/Global | Grant Amount (a) | Agency Fee (b)2 | Total c=a+b |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Angola | 4,416,210 | 419,540 | 4,835,750 |
|  |  |  |  |  |  | 0 |
|  |  |  |  |  |  | 0 |
|  |  |  |  |  |  | 0 |
|  |  |  |  |  |  | 0 |
|  |  |  |  |  |  | 0 |
|  |  |  |  |  |  | 0 |
|  |  |  |  |  |  | 0 |
|  |  |  |  |  |  | 0 |
|  |  |  |  |  |  | 0 |
| Total Grant Resources |  |  |  | 4,416,210 | 419,540 | 4,835,750 |

1  In case of a single focal area, single country, single GEF Agency project, and single trust fund project, no need to provide 
    information for this table

2   Please indicate fees related to this project.

part ii:  project JustiFication

- Description of the consistency of the project with:

A.1.1   the GEF focal area/LDCF/SCCF strategies /NPIF Initiative:

The project is consistent with the ‘’ GEF Strategy on Adaptation to Climate Change for the Least Developed Countries Fund (LDCF)’’, namely developing countries to become climate resilient by promoting both immediate and longer-term adaptation measures in development policies, plans, programs, projects and actions with an impact to reduce absolute economic losses at country level due to climate change, including variability. The project will contribute to the achievement of CCA objective 1: Reduce vulnerability to the adverse impacts of climate change, including variability, at local, national, regional and global level, CCA objective 2 : increase adaptive capacity to respond to the impacts of climate change , including variability , at local, national, regional and global level and their associated outcomes, and CCA objective 3: transfer and adoption of adaptation technology. In conformity with these strategies ,

A.1.2.   For projects funded from LDCF/SCCF:  the LDCF/SCCF eligibility criteria and               priorities:

Angola ratified the UNFCCC in 2000 and is classified among the non Annex 1 Parties and has developed and submitted their National Communication. Angola has also prepared and submitted its NAPA in 2011. Angola is therefore entitled to benefit from the SCCF fund for the implementation of priority measures identified in their respective climate change strategies and also eligible for funding from the LDCF. In implementing priority interventions identified in the NAPA and national communications, the project is consistent with the Conference of Parties (COP-9) and also satisfies criteria outlined in UNFCCC Decision 7/CP.7 and GEF/C.28 /18. The project concept has been developed ensuring a high degree of country ownership and conformity with their programs and policies. It focuses on adaptation, which is the priority of both SCCF and LDCF. It will pursue a holistic approach to addressing vulnerabilities in the agriculture and NR sectors and increasing resilience of ecosystems. The project will address several of the priority areas of the two Funds, in particular support to capacity building, including institutional capacity, food security, natural resource management, and support in implementation of Angola’s NAPA. Compliance with programme and LDCF/SCCF Fund Policies: the project complies and draws its focus from urgent needs identified in the NAPA and National Communications which are directly relevant for supporting national development goals. A.1.3 For projects funded from NPIF, relevant eligibility criteria and priorities of the Fund:

A.2.   national strategies and plans or reports and assessments under relevant conventions, if  applicable, i.e. NAPAS, NAPs, NBSAPs, national communications,  TNAs, NIPs, PRSPs, NPFE, etc.:

As mentioned in the NAPA of Angola, the agricultural sector is amongst the most vulnerable sectors to the impacts of climate change and weather extremes, not least because of its dependence upon natural resources such as water and ecosystem services. Water supply for agricultural production, for example, will be critical to sustain production and even more important to provide the increase in food production required to sustain Angola’s growing population. Transformational approaches are required in the management of natural resources, including new climate-smart agriculture policies, practices and tools, better use and monitoring of climate science and land ecology, information in assessing risks and vulnerability, and increased financing for food security. Planners and policy makers have a key role to play in creating a conducive policy environment and securing financing for such transformation. In the face of those impacts and their effects in the agricultural sector in general, the PIF proposes (i) to integrate climate change into the national decision-making and (ii) to demonstrate in site adaptation practices and technologies relevant to targeted vulnerable areas Alignments with NAPA priorities: The Angola NAPA’s Priority number 2 investment project is to ‘’Promote Sustainable Land Management to Increase Agriculture Yields’’ by: - Development of Techniques for different crops; - Promote cultivation techniques for increased water retention and erosion prevention; - Promote changes in agricultural practices for the conservation of soil humidity and nutrients, avoiding superficial draining and controlling erosion; - Improvement in the use and availability of water and soil erosion control; - Promote Rotation of cultures and changes in the periods of planting and harvesting; - Development of new varieties of plants and techniques to increase added value; - Drip irrigation and concentration of irrigation on growth periods; - Promote Integration between agriculture, livestock and forestry, and installation of wind breakers; - Promote Reforestation in arid and semi-arid zones; - Techniques to ensure food security and quality; - Development of Methods for fighting pests. The GEF project will respond by promoting the above mentioned techniques and activities in selected areas Angola’s Initial National Communication Plan states: ‘’Climate change makes existing vulnerabilities more severe and creates risks for a certain population‘s survival system. Extreme weather makes agriculture difficult, even though few people inhabit areas with extreme weather and those who do generally adapt their way of life accordingly. Climate variability is frequently a risk factor because a year without rain or too much rain in a certain period, without notice, will have an impact on production. Climate change could create other risks and could intensify existing natural challenges even more. The identified impacts refer to: - Hydrology (changes in river basins, with additional effects to neighboring countries) - Forests and agricultural systems (given the changes in precipitation and hydrology, which affect agricultural practices) - Soil erosion (due to higher precipitation levels) - Maritime coast currents and coastal erosion (due to the rise of the sea level as well as sedimentation and erosion alterations, if there are changes in hydrology) - Human settlements (due to temperature changes and the need to cool inhabited spaces; there is also the question of higher risks of flooding and erosion) When it comes to adaptation measures for the agriculture sector, the Plan prescribes: promoting action to sensitize all players in the agrarian development process to the need for a sustainable management of natural resources, specifically soil, water, forestry and biodiversity; creating pilot-projects for managing natural resources and, based on the experience gathered with such projects, formulating an environmental policy; afforestation and reforestation of areas close to communities, encouraging the creation of communal forests; revitalizing and diversifying the rural economy, contributing to the fight against hunger and poverty, improving living conditions for farming families and ensuring greater food security. The promotion of pilot dissemination areas in this projects is fully aligned with this National Communication Plan As for the National Action Plan for SLM (NAP) to combat desertification which is currently being developed and validated in Angola, Sustainable Land Management (SLM) is a key part of Angola’s NAP, which illustrates Government’s commitment to address the land degradation threat in the Namibe and Huila Provinces. The GEF Project (and the baseline) is fully aligned to the PRSP in Angola, whose overall objective is to consolidate peace and national unity by improving the living conditions of the Angolan people and encouraging the most vulnerable groups to actively participate in the economic and social development process. The PRSP identifies five main priority pillars, a) creation of a macro-economic framework conducive to growth and poverty reduction, b) development of the social sectors, c) rural development and mine-clearing operations throughout the country, d) rehabilitation of basic infrastructure, and e) institutional capacity building and improvement of governance. This project is consistent with the provisions of the PRSP. The project also addresses priorities of the NEPAD Environment Action Plan (EAP) and the Comprehensive African Agricultural Development Program (CAADP). Land Degradation, Drought, and Desertification are priority issues in the EAP. It also prioritizes additional elements like fresh water, climate and transboundary natural resources management.

- Project Overview:
B.1. Describe the baseline project and the problem that it seeks to  address:

The Problem: Angola faces a variety of environmental and social problems resulting from a legacy of an extended civil war, which has given rise to widespread poverty, unsustainable utilization of natural resources, weak regulatory and law enforcement frameworks. The recent development trends pose a threat to fish resources, over-exploitation of plant species, soil erosion, and pollution of soils, water and the atmosphere as well, as climate change vulnerability raises concerns about the inherent risks to environmental sustainability. Some of the challenges in the sector include i) inadequate human and institutional capacity for planning and implementation of environmental and natural resource policies; ii) environmental policies, strategies and laws that are out-dated and not responsive to the current challenges facing the sector; iii) weak enforcement of environmental laws; and iv) weak inter and intra-sectoral collaboration among the various institutions involved in natural resource management and environmental conservation. The proposed baseline intervention is aimed at supporting the Government’s efforts to address the identified constraints and challenges in the sector. The Baseline: The baseline was approved by the Bank’s Board of Directors in March 2009; the loan agreement signed in July 2009 and entered into force in December 2009. The project received its first disbursement on 14 January 2010. The project has three main components namely: i) Environmental Governance, Capacity Building and Institutional Strengthening; ii) Integrated Environmental Conservation and Natural Resource Management; and iii) Project Management. The total project loan is UA 12 million. The baseline project is addressing the above challenges in Environmental Governance, Capacity Building and Institutional Strengthening and Integrated Natural Resource Management and Environmental Conservation. The key performance indicators for the baseline project include i) implementation of revised environmental policies and strategies in selected sectors such as agriculture, water, fisheries, forestry and mining, ii) application of EIA guidelines to screen socio-economic interventions iii) reduction of deforestation from 0.8 to 0.3% in project areas iv) capacity built among key staff through training v) increased national environmental awareness vi) establishment of the National Biodiversity Institute vii) Establishment of a climate risk management unit. The baseline three (3) components are as follows: - Environmental Governance, Capacity Building and Institutional Strengthening (US 10 millions) – Description of Activities - Review and revise environmental policy, legislation and strategy - Implement revised environmental policy, legislation and strategy - Strengthen the regulatory framework and enforcement of environmental laws - Train 40 staff to postgraduate diploma/MSc level in biodiversity, natural resource management, environmental impact assessment, climate change and sustainable land management; 120 staff sent on short-term professional training courses; 50 staff trained in Bank’s languages; 200 inspectors trained in Environmental Impact Assessment procedures and reporting; 100 Technicians trained on environmental Impact Assessment (EIA) methodology and processes; and 40 judges refreshed on application and enforcement of environmental laws. - Develop sectoral EIA guidelines for relevant sectors including but not limited to Agriculture, Water, Forestry, Rural Development and Mining.) - Promote public consultation and participation in environmental conservation and sustainable natural resource management - Establish/ strengthen a Climate Risk Management Unit (CRMU), a National Biodiversity Institute (INABIO), the Environmental Training School and a UN Conventions Unit. - Integrated Natural Resource Management and Environmental (US 6m) – Description of Activities - Establish four (4) pilot sites in Namibe, Kuando-Kubango, Huambo and Cabinda to demonstrate and promote synergy and best practice in sustainable land-use management, biodiversity conservation, conservation adaptation to climate change and the use of environmental clean technologies - Undertake nationwide environmental awareness campaign - Organize 25 training courses/workshops to train project beneficiaries and local committees - Organize 5 training courses/workshops on environmental technologies and develop guidelines for the application of such technologies - Project Management (US$ 2m) – Description of Activities - Planning, management, coordination and implementation of project activities - Monitoring and evaluation - Provide technical assistance - Procurement of relevant office equipment, vehicles The baseline project is also premised on the Government’s commitment to implement the three Earth Summit Conventions; namely; the United Nations Convention on Biodiversity Conservation (UNCBD), the United Nations Convention on Combating Desertification (UNCCD), and the United Nations Framework Convention on Climate Change (UNFCCC). The Ministry of Environment (MINAMB), which is the lead institution in the implementation of the UN Conventions, has inadequate human and institutional capacity to plan, coordinate and execute the relevant project activities in support of the UN conventions. In order to operationalize activities relevant to the 3 conventions, the baseline project is establishing four (4) pilot sites in Namibe, Kuando-Kubango, Huambo and Cabinda to promote and pilot synergy and best practice in sustainable land-use management, biodiversity conservation, and the use of environmental clean technologies.

B. 2. incremental /Additional cost reasoning:  describe the incremental (GEF Trust Fund/NPIF) or additional (LDCF/SCCF) activities  requested for GEF/LDCF/SCCF/NPIF  financing and the associated global environmental benefits  (GEF Trust Fund/NPIF) or associated adaptation benefits (LDCF/SCCF) to be delivered by the project:

The current baseline consists of a weak enabling consideration of climate change in its interventions: - At the administrative and institutional level: weak integration of climate change adaptation considerations into development policies and strategies, weak NR policy, institutional, regulatory and incentive framework; a limited degree of cooperation and coordination of climate change between relevant institutions and agencies - At the project/ investment level : insufficient capacity and experience in sustainable natural resources management and adaptation approaches; inadequate funding; site specific and often uncoordinated interventions which focus on symptoms rather than on root causes; and supported by weak analytical underpinnings. As a result, current practices to NRM have so far not been able to substantively address the challenges including climate change; - At the pilot site level: The baseline is developing 4 agriculture natural resources pilot centers which put an accent on clean technologies. The GEF component will promote the testing of climate change adaptation technologies into the 4 demonstration centers. Without the GEF component, the baseline would thus see, with the added impact of climate change, a continued degradation and failure of productive and nonproductive land use systems with the resulting loss of ecosystem functions and increased poverty. With GEF support, the approach adopted for this project includes both the institutional capacity building interventions as well as community-based empowerment of local communities to enable them to play an active role in implementing environmental conservation, adaptation of their assets to the challenges of climate change through demonstration projects and sustainable management of the country’s natural resource base. The interventions at the institutional level are aimed at enhancing the capacity of MINAMB (Environment Ministry), MINAG (Agriculture and Rural Development Ministry) and other relevant stakeholders in the sector including water, fisheries, forestry and mining, NGOs, CBOs, research and academic institutions, private sector as well as provincial and local governments to plan and implement sustainable natural resource management (NRM) and environmental conservation interventions and enforcement of relevant legislation. At local level the project aims to demonstrate best practice in sustainable forest management and integrated natural resources management. The project will empower local communities through capacity building and dissemination of adaptation technologies and guidelines and will promote the adoption of technologies aimed at enhancing sustainable land management (SLM), climate change (CC) adaptation and biodiversity conservation. The proposed GEF project is targeted to be demonstrative, integrating substantial development interventions that are meant to be complementary to the baseline. Therefore, if for e.g. component 2 in the baseline is about the establishment of four hard investments infrastructures, the same component in the GEF project is meant to be a softer component and create a more enabling environment by making these infrastructures more resilient. In genera-the activities selected in the GEF are centered around soft activities namely policy reform, demonstration activities and capacity building, given that the baseline has a more investment-oriented approach to mainstreaming climate change in a given sector. GEF’s project is 3 components at three different levels : - Governance, Capacity Building and Institutional Strengthening This component aims at integrating climate change adaptation into decision making. Whereas in the baseline the equivalent component emphasises the environemental aspects, this component under GEF emphasises the climate change aspects (climate proofing, climate risk assessement, etc.). In order to induce a catalytic and transformational change the component will propose: The reinforcement of the Climate Risk Unit in order to strenghten their capacitiy in climate change coordination, budget allocations into climate change adaptation measures, and building of relevant climate change frameworks. The Climate Risk Unit will be supported to establish climate policies, to support the development of national sectoral strategies and integrate climate change aspects into legislation. At the investment level the unit will develop Climate Risk Assessment guidelines that will be tested. Capacity building: to the various stakeholders and actors in order to move from ‘’Risk to Resilience’’, as it is proven that when risk is reduced, it can make a substantive contribution towards adapting to the impacts of climate change. Therefore, capacity building in risk assessment, risk reduction, vulnerabilities assessment, and adaptation technologies are planned. - Promoting Climate Change adaptation measures into SLM practices in 4 demonstration sites This component is built upon the pilot centers of the baseline project (component 2) and will create a climate change demonstration platform for dissemination of technologies and practices. The demonstration will be on-site and in the 4 pilot centers: Namibe, Huambo, Kuando Kubango and Cabinda. The components seeks to move from a silos approach (agriculture, forestry, environment dept/ministries) to a integrated approach that increases the collaboration of the different departments and puts in place demonstration investment of CC adaptation practices and technologies in the agro-forestry sector: like natural regeneration techniques, rangelands and agro systems rehabilitation practices, wind breaks and dune stabilization methods, water efficiency and harvesting techniques. The component will also build a mapping tool that will identify vulnerable areas and potential investments and CC technologies that can be “extrapolated” to those areas. - Knowledge Management through a structured Coordination Mechanism and Monitoring and evaluation This component is linked to the baseline’s components 1 and 3. From GEF‘s component 2, lessons learnt in the techniques adapted to the national context – biophysical and social – will be disseminated among stakeholders and investors. National experts will participate in practitioners’ events in the region. Demonstration activities will be set up jointly between the different projects. The component will also provide resource for the implementation of an M&E framework that will be established at preparation stage.

B.3. 	Describe the socioeconomic benefits to be delivered by the Project at the national and local levels, including consideration of gender dimensions, and how these will support the achievement of global environment benefits (GEF Trust Fund/NPIF) or adaptation benefits (LDCF/SCCF). As a background information, read Mainstreaming Gender at the GEF."

The socio economic benefits are numerous and range from: Reduce economic impacts induced by a better consideration of climate change impact in investment decision – making; Employment will increase because of job creation in the AfDB pilot centers and GEF demonstration centers; The GEF project will be replicated in a number of other provinces with all its benefits; The communities will economically benefit from the demonstration centers both technically but also economically as these will be considered resource centers and visitors may pay visits for various reasons. At the long-run food security will be increased as a result of the dissemination of adaptation practices; The most vulnerable communities will be starting to adapt to climate change; The project will promote positive gender outcomes through a number of training courses and workshops designed to raise awareness and enhance knowledge and skills in sustainable natural resources management, adaptation to climate change and conservation practices. Women play a critical role in natural resources management and rely on these resources for their livelihoods. The participation of women in practice and technologies selection at the community level is also expected to be high as women dominate most of the activities targeted in the agro-forestry sector.

B.4	Indicate risks, including climate change risks that might prevent the project objectives from being achieved, and if possible, propose measures that address these risks to be further developed during the project design:

RISK DESCRIPTION; RATING; MITIGATION MEASURES. Adverse climatic variability and changes resulting in flash floods and prolonged drought undermine achievement of benefits; Medium; Awareness raising and promote climate resilience activities. Promote the use of early warning systems at the community level. Insufficient time dedicated by collaborating and partner organizations and agencies to successfully implement the project components; Low; During the project preparation phase, time availability and commitments will be discussed among the participating organizations and agencies to ensure that none is carrying a heavier burden that it can sustain, especially among the central Ministry of Environment and the provincial branches. Communities reluctant to participate in the project activities; Low; Engage community leaders and encourage platforms for information sharing and exhibition of good practices for communities to visually identify benefits. Inadequate participation by all stakeholder groups to identify and prioritize adaptation needs in a sufficiently objective manner; Medium; Careful attention will be given to ensuring the involvement of all relevant stakeholders at an early stage and throughout the project implementation process, This will facilitate consideration of all points of view and balanced objective prioritization. Limitations in adoption of sustainable land management practices; Medium; Promote platforms for ideas sharing and engage community leaders in community mobilization activities. Lack of technical capacity to effectively implement project activities; Low; Ensure knowledge transfer from technical assistance provided by identifying national counterparts.. Inherent administration issues; High; Adequate procurement and disbursement support stuff.

B.5. Identify key stakeholders involved in the project including the private sector, civil society organizations, local and indigenous communities, and their respective roles, as applicable:

The key stakeholders involved in the project are the local communities and the Government Departments and Agencies that deal with environmental management in Angola. The project will be implemented through the Ministry of Environment (the climate change unit is in the Ministry) working in close collaboration with the Ministry of Agriculture and Rural Development and other line Ministries involved in natural resources management. The communities play a role in project planning, implementation, monitoring and evaluation through established local committees. The strengthening of the Government Departments and Agencies through capacity building of the relevant staff serves the entire nation, providing leadership in safeguarding the environment and imparting the knowledge on local communities. The capacity building will also enable the Government to provide a suitable environment for the private sector to be able to support activities in sectors such as agriculture, fisheries and mining. Key Stakeholders include: - National government representatives, including resource managers and experts from agriculture, environment and climate change ministries or provincial departments - Agriculture and agro-industries processing workers/farmers represented by CSOs, NGOs, and trade unions. - Representatives from regional and provincial governments, in each of the three provinces. The details will depend, in part on the sites selected for pilot studies. - National scientists and experts in economics, natural and social sciences, climate and development experts, from universities and other research bodies in the region. - Inter-governmental organizations: NEPAD, SADC, FAO, UNDP and the WB - NGOs, CSOs and specific partners identified during the project preparation phase

B.6. Outline the coordination with other related initiatives:

There is a donor coordination framework in the natural resource and environmental sector in Angola. Meetings are held periodically where donors share knowledge and experience on their respective interventions in the sector. Some of the donor-funded activities in the environment and natural resource sector include; (i) the Fisheries Sector Support Project funded by the Bank; (ii) the National Biodiversity Project funded by GEF; iii) the Rehabilitation of National Parks and the Integration of Ex-Combatants Projects funded by GTZ/ German Government; iv) the Sanitation and Environmental Project funded by EU; v) the Public Hygiene and Environmental Sanitation Project funded by UNICEF; vi) the Sustainable Land Management Project funded by UNDP; and vii) the Water, Public Hygiene and Environmental Sanitation Project jointly funded by UNDP and the Spanish Government. The UNEP GEF program ‘’Addressing Urgent Coastal Adaptation Needs and Capacity Gaps in Angola’’ is of particular relevance to the AfDB project. The UNEP project will provide scientific and technical data to inform the natural resource management decisions and planning that this baseline project will undertake. As there are significant gaps in regards to accurate and reliable climate data, this project will ground the institutional interventions of the AfDB project with climate information, particularly in the pilot centres which are geographically common (Cabinda) between the two GEF projects (Component 2). Information gleaned from improved climate monitoring will support the baseline project in making institutional decisions. The UNEP project will therefore strengthen the adaptation component to the AfDB baseline and GEF project’s activities in the environmental sector which will in turn promote sustainability of the baseline interventions despite climate variability. UNDP "Promoting climate-resilient development and enhanced adaptive capacity to withstand disaster risks in Angolan's Cuvelai River Basin", Provincial Government of Cunene. This project aims to support adaptation of communities most vulnerable to hydro-meteorological disasters in the region. This will be done through enhancing human and institutional capacity for increased sustainable rural livelihoods among those communities, investments in a comprehensive early warning system, and enhanced knowledge and planning. Some of the expected outcomes and outputs include increased resilience of smallholder farmer communities through facilitating and improving access to climate-resilient seeds, a functional end-to-end Famine and Flood Early Warning System, an update of a Province-level Master Plan through mainstreaming climate resilience considerations, and development and dissemination of micro-seasonal maps of different climate-resilient crops to extension agents. Comprehensively, these activities have the potential to change agricultural practices and enhance resilience to climate change, as well as to lead to replication and scaling up. This project specifically focuses on support for NAPA priorities 7 (Create an early warning system for flooding and storms) and 13 (Climate monitoring and data management system). These two NAPA priorities are intricately linked (and have therefore been bundled together for the purpose of this project) since establishment of a comprehensive famine and flood early warning systems (FFEWS) – including downscaled seasonal forecast delivery systems – is one key component of a more broad-based climate monitoring and data management system, which also includes climate information dissemination and capacity-building. As the NAPA notes, there is “insufficient climate monitoring infrastructure in Angola and as a result, early warning is nearly impossible in the country.” Agricultural planning and extension is also made difficult due to the lack of appropriate seasonal forecasts and climate monitoring information; even if systems are established the data must be shared with key stakeholders at the local level to develop appropriate site-specific responses, such as distribution of flood-resistant seed varieties. This is a resourceful project that is not only complementary to AfDB’s GEF project but also instrumental in demonstrating the use of early warning systems /monitoring/ and consequential actions such as the use of these systems for agricultural -increased productivity – activities, such as flood resistant seed varieties. AfDB’s GEF product may research these seeds (properties) in the 4 resource centers (located in other provinces and not Cunene) and feed the knowledge to this project and vice versa through the coordinated mechanism. The Umbrella Program for National Communication to the UNFCCC (UNEP). The process of preparing national communications and strengthening the information base in national institutions on climate change provides a backdrop on which this project can build. It has created a basic level of understanding among national institutions on articulating climate change matters and this project can further collaborate with such national institutions to create strengthened networks that can implement this project (particularly components 1, Governance). Climate for Development in Africa Programme (ClimDev-Africa). AfDB ClimDev-Africa programme supports Africa's response to climate variability and change by building regional, sub-regional and national policy capacity. It will improve the quality and availability of information and analysis to decision-makers. The proposed project will coordinate with this intervention by ensuring that climate change adaptation initiatives are folded effectively in policy documents and will synergize activities by sharing information garnered through the implementation of Components 1, 2 and 3). Integrating and Up-Scaling Climate Resilience Through Soil Fertility Management into Agricultural and Agro pastoral Production Systems for Food Security in Key Productive and Vulnerable Areas Through the Farmers Field School approach(FAO). The project will be based in Angola’s Central Plateau and the project aims to enhance the resilience of small farmers in coping with declining ecosystems services due to increasing climate variability, droughts, and extreme events. Although this initiative will be conducted in the interior while our project will be based in Namibe, Huambo, Kuando Kubango and Cabinda, there are opportunities for engagement, the sharing of lessons learned, particularly in the areas of resilient agriculture, and of ecosystems protection. It is therefore suggested that this project sets up a coordination mechanism for joint capacity building activities for: i) planning complementary activities between the different projects; ii) documenting lessons learned and knowledge management (component 3); iii) exchange of piloting activities and learning while doing, particularly in the 4 pilot centres (component 2). C. DESCRIBE THE GEF AGENCY’S The implementation progress in the proposed project will be shared with other donors and ensure synergies with the relevant programmes. The project will be housed at the Ministry of Environment and therefore the project implementation team will be part of the Ministry structures and interact with other project implementation teams in the environment sector.

C.   describe the GEF agency’s comparative advantage to implement this project:

The AfDB has proven experience in preparing, financing, and managing investment projects with SLM components linked to climate change and is promoting the inclusion of integrated sustainable natural resources management and climate change in AfDB Country Strategy Papers (CSP). The Bank has financed successfully some 16 adaptation (and mitigation) projects in the agriculture and agro business sector, from the Niger basin to the PISEAU in Tunisia, and in Egypt, Malawi and Gambia. The experience developed in the implementation of Niger basin and other similar progammes will be applied in the project design. Knowledge products have also been produced as a result of earlier interventions and these can be adapted to the local situation in Angola to maximize the impact of the resources. In addition the AfDB is providing co-financing of the project through a loan to the Government of Angola. The co-financed activities are complementary in terms of location as well as knowledge generation. Finally, the AfDB is extremely aware that climate change can reverse the progress in Africa’s economic growth, poverty reduction, and gender equality. AfDB has undertaken a program to climate – proof the investment portfolio and to integrate climate change adaptation and mitigation into investment due diligence and project design. On April 29th, the Bank launched its Climate Risk Management and Adaptation Strategy outlining support in climate proofing investments; in policy, legal, and regulatory reforms, and in knowledge generation capacity building. The Bank is also supporting the Climate Information for African Development Program (ClimDev Africa) to generate useful information for national environmental policies.

C.1   Indicate the co-financing amount the GEF agency is bringing to the project:

The total co-financing from the African Development Bank is USD 18 million of which approximately USD 10 million is spent on investments and technical assistance in legislation, governance, capacity building and institutional strengthening activities while approximately USD 8 million is spent on investments in integrated natural resources conservation and management activities.

C.2 How does the project fit into the GEF agency’s program (reflected in documents such as UNDAF, CAS, etc.) and staff capacity in the country to follow up project implementation:

The AfDB’s Country Strategy Paper (CSP) for Angola identifies two pillars of support i) the reduction of poverty through improved social services delivery and increased access to production factors; and (ii) the creation of an adequate environment for private sector development. This project is a cross cutting project as it focuses on the environment and land as a productivity factor and on climate change and in the Climate Risk Management and Adaptation Strategy of AfDB and therefore the project is anchored in both pillars through its activities listed in previous sections. The CSP is fully aligned to the PRSP in Angola, whose overall objective is to consolidate peace and national unity by improving the living conditions of the Angolan people and encouraging the most vulnerable groups to actively participate in the economic and social development process. Both the regional resource center in South Africa and the Angola field office in Luanda have adequate staff capacity to contribute to the successful outcomes of this project. Both offices and their staff will be involved in the M & E and supervision of this project.

part iii:  approval/endorsement by gef operational focal point(s) and GEF agency(ies)

A.   Record of Endorsement of GEF Operational Focal Point (S) on Behalf of the Government(S): (Please attach the Operational Focal Point endorsement letter(s) with this template. For SGP, use this OFP endorsement letter).

| Name | Position | Ministry | Date (MM/dd/yyyy) |
| --- | --- | --- | --- |
| Carlos Avelino Manuel CADETE | Operational focal point- National Director of Statistics, planning and Studies Gabinet | Ministry of environment | 12/20/2012 |

B.  GEF Agency(ies) Certification

| This request has been prepared in accordance with GEF/LDCF/SCCF/NPIF policies and procedures and meets the GEF/LDCF/SCCF/NPIF criteria for project identification and preparation. |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Agency Coordinator, Agency name | Signature | Date (MM/dd/yyyy) | Project Contact Person | Telephone | Email Address |
| Ignacio Tourino Soto, AfDB |  | 21/20/2012 | MARTTIN, FELIX JAN BAPTIST | +216-71102510 | F.MARTTIN@AFDB.ORG |

It is very important to consult the PIF preparation guidelines when completing this template.

Project ID number will be assigned by GEFSEC.

Refer to the reference attached on the Focal Area Results Framework when filling up the table in item A.

GEF will finance management cost that is solely linked to GEF financing of the project. PMC should be charged proportionately   
     to focal areas based on focal area project grant amount.

Same as footnote #3.