PROJECT DOCUMENT

ON A

PROPOSED GRANT FROM THE

gloBal environment facility

IN THE AMOUNT OF US$ 2.4 MILLION

to THE

ARGENTINE Republic

FOR THE

Third National Communication to the United Nations Framework Convention on Climate Change Project

August 13, 2010

Sustainable Development Department

Argentina, Paraguay and Uruguay Country Management Unit

Latin America and the Caribbean Region

CURRENCY EQUIVALENTS

(Exchange Rate Effective 5 August 2010)

| Currency Unit | = | AR Peso |
| --- | --- | --- |
| AR$ 1.0 | = | US$ 0.25 |
| US$ 1.0 | = | AR$ 3.93 |

FISCAL YEAR

| January 1 | – | December 31 |
| --- | --- | --- |

ABBREVIATIONS AND ACRONYMS

ACF		Argentina Carbon Facility

AMBA	Metropolitan Area of Buenos Aires

AOP		Annual Operating Plan

APL		Adaptable Program Loan

AR4		Fourth Assessment Report

BP		Bank Policy

CARICOM	Caribbean Community and Common Market

CCD		Climate Change Directorate

CCFA		Climate Change Focal Area

CICC		Inter Ministerial Commission on Climate Change

CIMA	Research Center on the Sea and the Atmosphere (Centro de Investigaciones del Mar y la Atmósfera)

CPS		Country Partnership Strategy

CS		Civil Society

CNRS		National Center for Scientific Research of France

COFEMA	Federal Council of Environment (Consejo Federal de Medio Ambiente)

CONICET	National Center of Scientific and Technical Reasearch (Consejo Nacional de Investigaciones Científicas y Técnicas)

COP		Conference of the Parties

DA		Designated Account

DIGMA	General Directorate of International Environmental Affairs (Dirección General de Medio Ambiente)

DGTA	General Administration and Technical Directorate (Dirección General Técnico Administrativa)

DNA		Designated National Authority

DNRI 	National Directorate of International Relations (Dirección Nacional de Relaciones Internacionales)

DPCyC	Budget, Shopping and Procurement Directorate (Dirección de Presupuesto, Compras y Contrataciones)

EAs		Enabling Activities

ER 		Emission Reduction

FA		Financial Assistant

FAC		Financial and Administrative Coordinator

FB 		Fundación Bariloche

FCPF		Forest Carbon Partnership Facility

FM		Financial Management

FNC		First National Communication

FY 		Fiscal Year

GCC 		Global Climate Change

GEF 		Global Environment Facility

GHG 		Greenhouse gasses

GIS		Geographic Information System

GOA 		Government of Argentina

GPFMC	General Procurement and Financial Management Coordinator

HFC		Hydrofluorocarbon

IBRD 		International Bank for Reconstruction and Development

ICB 		International Competitive Bidding

IDB 		Interamerican Development Bank

INDEC	National Institute of Statistics and Censuses (Instituto Nacional de Estadísticas y Censos)

IPCC 		Intergovernmental Panel for Climate Change

ISDS		Integrated Safeguards Data Sheet

IUFR		Interim Unaudited Financial Report

JICA		Japan International Cooperation Agency

JGM 		Chief of the Cabinet of Ministers (Jefatura de Gabinete de Ministros)

KP 		Kyoto Protocol

LUCF		Land Use Change and Forestry

LULUCF	Land Use, Land-Use Change and Forestry

MC		Mitigation Coordinator

MAGyP	Ministry of Agriculture, Livestock and Fisheries (Ministerio de Agricultura, Ganadería y Pesca)

MRI		Meteorological Research Institute of Japan

MSW		Municipal Solid Waste

MTR 		Midterm Review

M&E		Monitoring and Evaluation

NC		National Communication

NCAR		National Center for Atmospheric Administration

NEA		Argentina North East (Noreste de Argentina)

NGO		Non Governmental Organization

NOA		Argentina North West (Noroeste de Argentina)

NOAA		National Oceanic and Atmospheric Administration

NPP		Nuclear Power Plant

OP		Operational Policy

PAD		Project Appraisal Document

PC		Procurement Coordinator

PCN		Project Concept Note

PDO		Project Development Objective

PERMER	Renewable Rural Energy in Rural Markets Project

PIC		Public Information Center

PID		Project Information Document

PIU		Project Implementation Unit

PFC		Perfluorocarbon

PROSAP	Provincial Agricultural Services Program (Programa de Servicios Agropecuarios Provinciales)

P&M		Policies and Measures

REDD		Reducing Emissions for Deforestation and Forest Degradation R-PP		Readiness Plan Proposal

RVP		Regional Vice-Presidency

SAyDS 	Secretariat of Environment and Sustainable Development (Secretaría de Ambiente y Desarrollo Sustentable)

SBD	Standard Bidding Documents

SC 		Steering Committee

SDN		Sustainable Development Network

SEPA	Procurement Plan Execution System (Sistema de Ejecución de Planes de Adquisiciones)

SIC 		Secretariat of Industry, Business and SMEs

SIIF		National Integrated Financial Management System

SRH 		Sub-Secretariat of Water Resources (Secretaría de Recursos Hídricos)

SNC 		Second National Communication

SPE 		Secretariat of Economic Policy (Secretaría de Política Económica)

SPPCTIP 	Secretariat of Planning and Policy in Science and Technology and Productive Innovation (Secretaria de Planificación y Política en Ciencia, Tecnología e Innovación Productiva)

ST 		Secretariat of Transport (Secretaría de Transporte)

TAC		Technical Advisory Committee

TNC 		Third National Communication

TOR 		Terms of Reference

UEPEX	Financial and administration system used by Argentinean Government units responsible for the administration of foreign loans

UN		United Nations

UNFCCC 	United Nations Framework Convention on Climate Change

WB 		World Bank

| Vice President: |  | Pamela Cox |
| --- | --- | --- |
| Country Director: |  | Penelope Brook |
| Sector Manager: |  | Karin Kemper |
| Sector Leader: |  | Michel Kerf |
| Task Team Leader: |  | Marcelo Acerbi |

ARGENTINE REPUBLIC

Third National Communication to the United Nations Framework Convention on Climate Change Project Contents

Page

I.	STRATEGIC CONTEXT AND RATIONALE	1

A.	Country and Sector Issues	1

B.	Rationale for Bank Involvement	3

C.	Higher Level Objectives to which the Project Contributes	7

II.	PROJECT DESCRIPTION	8

A.	Lending Instrument	8

B.	Project Development Objective and Key Indicators	9

C.	Project Components	9

D.	Alternatives Considered and Reasons for Rejection	14

III.	IMPLEMENTATION	14

A.	Partnership Arrangements	14

B.	Institutional and Implementation Arrangements	14

C.	Monitoring and Evaluation of Outcomes/Results	15

D.	Sustainability and Replicability	16

E.	Critical Risks and Possible Controversial Aspects	17

F.	Loan/credit Conditions and Covenants:	20

IV.	APPRAISAL SUMMARY	20

A.	Economic and Financial Analyses	20

B.	Technical	21

C.	Fiduciary	21

D.	Social	22

E.	Environment	22

F.	Safeguard Policies	23

G.	Policy Exceptions and Readiness	23

Annex 1: Country and Sector or Program Background	24

Annex 2: Major Related Projects Financed by the Bank and/or Other Agencies	36

Annex 3: Results Framework and Monitoring	41

Annex 4: Detailed Project Description	49

Annex 5: Project Costs (US$ Million)	67

Annex 6: Implementation Arrangements	68

Annex 7: Financial Management and Disbursement Arrangements	74

Annex 8: Procurement Arrangements	79

Annex 9: Economic and Financial Analysis	85

Annex 10: Safeguard Policy Issues	87

Annex 11: Project Processing	89

Annex 12: Documents in the Project File	90

Annex 13: Statement of Loans and Credits	91

Annex 14: Country at a Glance	94

Annex 15: Consultation Meetings - List of Institutions Represented in the TNC Preparation Process	97

Annex 16: Comparison between the Scope of the Second National Communication and the Proposed Project	99

Annex 17: Sectoral Programs under Development by the GOA Related with the Goals of the Third National Communication Project	102

Annex 18: Maps (to be completed)	113

ARGENTINE REPUBLIC

THIRD NATIONAL COMMUNICATION TO THE UNITED NATIONS

FRAMEWORK CONVENTION ON CLIMATE CHANGE PROJECT

PROJECT APPRAISAL DOCUMENT

LATIN AMERICA AND CARIBBEAN

LCSEN

| Date: August 5, 2010 | Team Leader: Marcelo H. Acerbi |
| --- | --- |
| Country Director: Penelope Brook Sector Director: Laura Tuck | Sectors: Environment Themes: Climate Change |
| Project ID: P116974 | Environmental screening category: C |
| Lending Instrument: Grant | Safeguard screening category: C |

| Project Financing Data |  |  |  |  |
| --- | --- | --- | --- | --- |
| [ ] Loan [ ] Credit [x] Grant [ ] Guarantee |  | [ ] Other: |  |  |
| For loans/credits/other: |  |  |  |  |
| Loan currency: United States Dollars |  |  |  |  |
| - Total Bank financing (US$m.): 2.4 |  |  |  |  |
| Proposed terms: GEF Grant |  |  |  |  |
| Financing Plan (US$m) |  |  |  |  |
| Source | Local |  | Foreign | Total |
| Recipient | 0.6 |  |  | 0.6 |
| Global Environment Facility (GEF) |  |  | 2.4 | 2.4 |
| Total: |  |  | 2.4 | 3.0 |
| - Recipient: The Argentine Republic |  |  |  |  |
| Responsible agency: Chief of the Cabinet of Ministers: - General Administration and Technical Directorate. Contact: Mr. German Arribas, General Technical Administrative Director (arribasg@jgm.gov.ar) - Secretariat of the Environment and Sustainable Development (SAyDS), Climate Change Directorate. Contact: Nazareno Castillo Marín, Climate Change Director (ncastillo@ambiente.gov.ar) |  |  |  |  |

| Estimated Disbursements APL-1 (Bank FY/US$m) |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| FY | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 |
| Annual |  | 0.2 | 1.7 | 0.5 |  |  |  |
| Cumulative |  | 0.2 | 1.9 | 2.4 |  |  |  |
| Project implementation period: 1 December 2010 - 30 November 2012 Expected effectiveness date: 1 December 2010 Expected closing date: 30 November 2012 |  |  |  |  |  |  |  |

| Does the Project depart from the CAS in content or other significant respects? (Ref. PAD I.C) | [ ] Yes [X] No |
| --- | --- |
| Does the Project require any exceptions from Bank policies? (Ref. PAD IV.G) Have these been approved by Bank management? Is approval for any policy exception sought from the Board? | [ ] Yes [X] No [ ] Yes [ ] No [ ] Yes [X] No |
| Does the Project include any critical risks rated “substantial” or “high”? (Ref. PAD III.E) | [X] Yes [ ] No |
| Does the Project meet the Regional criteria for readiness for implementation? (Ref. PAD IV.G) | [X] Yes [ ] No |

Project development objectives (Ref. PAD II.B) The PDO is to strengthen the information base and institutional capacity of the key organizations, members of the Project Steering Committee, to integrate climate change priorities into development strategies and relevant sector programs of the Argentine Republic by providing financial and technical support to prepare its Third National Communication (TNC) to the United Nations Framework Convention on Climate Change (UNFCCC).

Project Description (Ref. PAD II.C) The Project consists of the following components: Component 1: Harnessing National Potential for Climate Change Mitigation Sub-component 1: GHG Inventory and Development of Tools to Manage the GHG Emissions Database Sub-component 2: Actions to Enhance Climate Change Mitigation Sub-component 3: Mitigation Policies and Measures (P&M) Component 2: Strengthening National Adaptation Agenda Sub-component 1: Assessment of Impacts of and Vulnerability to Climate Change Sub-component 2: Actions to Improve Adaptation to Climate Change Sub-component 3: Adaptation Policies and Measures (P&M) Component 3: Institutional Strengthening, Capacity Building, and Information Management Sub-component 1: Definition of Technical and Institutional Framework for the TNC Sub-component 2: Institutional Strengthening and Capacity Building Sub-component 3: Development, Publication and Dissemination of the TNC Component 4: Project Management

Which safeguard policies are triggered, if any? (Ref. PAD IV.F) No safeguard policies are triggered.

Significant, non-standard conditions, if any: None.

Conditions of Loan Effectiveness: No effectiveness conditions. Main Loan Covenants: To be confirmed based on the Grant Agreement.

- STRATEGIC CONTEXT AND RATIONALE

- Country and Sector Issues

- During the years from 2004–2008, Argentina’s economy grew at an average annual rate of 8%. This economic expansion relied heavily on the use of natural resources for agricultural production, energy generation, and transportation of goods among other activities. Going forward, important decisions need to be made regarding the development path Argentina should follow. In the future, Argentina is increasingly likely to introduce environmental considerations and sustainable development concepts into its strategic sector development plans for each of the main economic sectors, which have not been fully considered in the past. A set of sector programs currently under development by different Governmental agencies suggests significant synergies with the goals of this Project. In that sense, the Ministry of Agriculture, Livestock and Fisheries (MAGyP, Secretariat of Energy and Secretariat of Environment and Sustainable Development (SAyDS), among others, are promoting different national programs that contribute to reduce the effects of climate change in the country. Details of these programs are described in Annex 17. They are initial efforts with potential for substantial mitigation and adaptation impacts. All the on-going activities and sectoral programs will contribute inputs to the TNC as lessons learned or opportunities to consider obstacles or barriers.

- The global path of CO2 emissions already surpasses the worst case scenario (SRES). Although there are uncertainties with regard to exact consequences, there is high confidence (IPCC 2007) that impacts from climate change, even under significantly more modest emission scenarios than the current trends predict, will affect the functioning and integrity of key ecosystems worldwide. While the impacts are being felt globally, the effects of climate change will likely impact Latin America and the Caribbean heavily. This is a region with substantial, but intrinsically fragile, natural capital, and where there are a number of climate sensitive regions (climate hotspots).

- Argentina has been identified as particularly vulnerable to the impacts of climate change. Significant vulnerabilities anticipated in the Second National Communication (SNC) for the period  up to 2040 include: (i) reduction of the water level in the La Plata Basin; (ii) increase in water stress in northern Argentina, and in parts of the western areas of the country; (iii) potential water crisis in Mendoza, San Juan and Comahue; (iv) intense precipitation and floods in zones already affected; (v) further glacier retreat with implications for hydro-power generation and agriculture; (vi) increased vulnerability of coastal areas to sea level rise (SNC, 2007). Recently, extreme land degradation processes as well as extreme summer storms in Buenos Aires city confirm the trend.

- Currently available projections on climate change impacts at the national level present clear signals. E.g., most of the existing models project increased precipitation in Eastern, and decreased precipitation in Southwestern Argentina. Large uncertainties still exist, however, on the quantification of such changes. National efforts and different international collaboration agreements, e.g. one between the Japan International Cooperation Agency (JICA), the University of Buenos Aires, and the Meteorological Research Institute of Japan (MRI), and another between the National Center for Scientific Research (CNRS) of France, the Consejo Nacional de Investigaciones Científicas y Técnicas (CONICET), and the University of Buenos Aires, will be able to provide high resolution climate modeling throughout the country.

- In this context, National Communications (NCs) are essential pieces of information to reach the ultimate goal of the UNFCCC. According to Article 4, paragraph 1, and Article 12, paragraph 1 of the UNFCCC, each Party shall communicate to the Conference of the Parties (COP), through the secretariat, the following elements of information: (a) a national inventory of anthropogenic emissions by sources and removals by sinks of all greenhouse gases not controlled by the Montreal Protocol, to the extent its capacities permit, using comparable methodologies to be promoted and agreed upon by the COP; (b) a general description of steps taken or envisaged by the Party to implement the Convention; and (c) any other information that the Party considers relevant to the achievement of the objective of the Convention and suitable for inclusion in its communication, including, if feasible, material relevant for calculations of global emission trends.

- As an immediate background, the Second National Communication for Argentina (SNC) has produced several results of significant importance for the development of the TNC. Revised emission inventories for the years 1990, 1994, 1997, and 2000 have been developed. The results obtained from these inventories establish a solid baseline that facilitates the updating of GHG emissions and the analysis of future trends. The SNC also provided guidelines for adaptation and mitigation, thus a first step towards a concrete strategy. These guidelines promote interactive participation with relevant stakeholders, the inclusion of adaptation to future climate, as well as the presentation of climate variability. Four systems were analyzed in great detail: agriculture, coastal areas, water resources, and energy. The mitigation plan helped identify mitigation opportunities focused on energy efficiency and savings, renewable energy, emission reductions (ER) in the transport sector, and carbon sequestration. These adaptation and mitigation assessments lay the groundwork for further analysis. The SNC resulted also in the development of a high resolution regional circulation model in the Research Center on the Sea and the Atmosphere (CIMA) that will be of use for further vulnerability assessments under the proposed TNC.

- Even though the SNC was a key in identifying priorities for interventions, the translation of these assessments into concrete sector P&M with a broader impact has yet to happen. Climate change P&M are yet to be integrated into sector development strategies and to be assessed in terms of their economic, environmental and social impacts. Annex 16 includes a table indicating the main conclusions/outputs from the SNC and how the TNC envisions building upon them. In addition, the climatic and hydrological changes observed over the last decades point to the urgent need for prompt action particularly in the field of adaptation. For example the trend in reduced stream flows in the rivers originating in the Andes Mountains has already caused hydropower generation losses of up to 40% in the provinces of Rio Negro and Neuquen.

- The proposed TNC would further the process initiated by the SNC taking advantage of the currently strong political momentum to advance promptly with the CC agenda. The TNC will represent a key tool for decision makers at all levels contributing to deepening the understanding of the needs for and consequences of the implementation of mitigation and adaptation P&M. It will demonstrate their potential contribution to the sustainable development of the different economic sectors in Argentina. This is particularly relevant considering Argentina’s economic growth over the last years and the need for an analytical base to integrate CC aspects into that process. Ultimately, the TNC will help integrate climate change considerations into GOA’s sector policies and programs and would strengthen GOA’s capacities in that process. The Secretariat of Environment and Sustainable Development (SAyDS) has actively invited other sectors (both public and private) and groups of stakeholders (including NGOs) to contribute to the preparation of the TNC, as well as to Argentina’s positions in the UNFCCC negotiations prior to the COP15. Relevant sectors have proven open to participating in these discussions, confirming a crucial interest by stakeholders to proceed towards nationally agreed climate change agenda. Annex 15 provides details on institutions represented in different meetings.

- Argentina’s institutional framework to deal with climate change related issues has improved considerably since 2002. The institutional framework for climate change issues has been significantly strengthened since the Secretariat of Environment and Sustainable Development (SAyDS) was appointed the focal point for the UNFCCC in 2008 and the subsequent creation of the Climate Change Unit (UCC) in order to implement the climate change related activities of the SAyDS. In 2007, the UCC was converted into a directorate (CCD), further reflecting the importance given to the CC agenda by GOA. With the transition of the SAyDS into the Chief of the Cabinet's line management, its involvement in the coordination of inter-sectoral policies including climate change has started to increase considerably. As a result of this tendency, during December 2009, the SAyDS led the process to create the Governamental Commitee on Climate Change. This Committee has an inter-secretarial character aimed at discussing and advising on sector issues and ensuring the involvement and coordination of climate change considerations across relevant Governmental Institutions. The Committee will play a key role in the Project benefitting from most of the proposed activities, and will thus be strengthened further as an institutional platform for the national climate change agenda.

- Rationale for Bank Involvement

- The Project is in line with the Country Partnership Strategy (CPS). The Project is aligned with core objectives of the World Bank Group Country Partnership Strategy (CPS) 2010–2012 (Report #48476-AR), discussed by the Executive Directors on June 9, 2009. The key objectives of the CPS’ sustained growth pillar include: (i) infrastructure development with a focus on expanding access of the poor to basic services (water supply and sanitation, and urban and regional transport), reducing vulnerability to urban flooding and drainage problems, and removing logistics and transportation bottlenecks including an improvement of the country’s road system through performance-based management contracts to facilitate the expansion of trade and growth; and (ii) rural development and the environment with a focus on promoting agricultural growth, reducing rural poverty, and improving environmental management – all of which stand out as critical and relatively unaddressed concerns. The Project would be complementary to these objectives by generating relevant data for planning in these vulnerable sectors and by strengthening the country’s capacity in assessing the climate change threat to the above mentioned sectors.

- Bank role. Since 1998, the Bank has been active in the climate change agenda in the Latin America and Caribbean region, where it has 22 IBRD financed projects, 24 GEF operations, 56 carbon finance projects and 22 analytical and advisory activities. The Bank has also been active in fostering national institutional capabilities to deal with the consequences of climate change, e.g. support to climate change offices, facilitation of technical cooperation with leading climate research institutes, support in strengthening capacity in climate modeling and in implementing CDM projects. In Argentina, the Bank has a wide project portfolio with strong climate change linkages. References for these projects have been included in Annex 2.

- The World Bank is playing a leading role in supporting the adaptation field in Latin America. The Bank has identified adaptation to climate change impacts the top priority in a regional climate change strategy (World Bank, 2009). It has also proposed an adaptation strategy emphasizing an ecosystem approach and addressing long-term trends rather than climate variability (World Bank, 2005). The LCR region has the largest portfolio of any development agency on adaptation (Colombia: Integrated National Adaptation Program, P083075; Dominica, St. Lucia and St. Vincent: Implementation of Adaptation Measures in Coastal Zones, P090731; Regional Andes Adaptation Program for Glacier Dependent Ecosystems, P098248; CARICOM: Mainstreaming Adaptation to Climate Change, P073389, Mexico: Adaptation to Climate Change Impacts in the Coastal Wetlands of the Gulf of Mexico P100438; and Central America: Addressing Impacts of Extreme Weather Events, P099457). The Project would benefit from extensive experience in World Bank-assisted activities that dwell on adaptation issues.

- In terms of mitigation, the Bank has implemented the Carbon Finance Assistance Program to help design and launch the Argentina Carbon Facility (ACF). This has promoted the participation of Argentina in the international carbon market and the creation of a CDM project pipeline in the country. To date, the ACF has received 264 project ideas and issued 52 letters of No Objection, after which these projects have to follow the workflow of the Argentine Designated National Authority (DNA) in order to receive a national approval. Moreover, Argentina has been included in the Bank’s Forest Carbon Partnership Facility (FCPF) that assists developing countries in their efforts to reduce emissions from deforestation and forest degradation (REDD) by providing value to standing forests. In the FCPF context, Argentina will prepare a REDD strategy and further benefit from carbon finance. At the moment of preparating the TNC, the country was elaborating the readiness preparation proposal in order to receive funding to develop a REDD strategy.

- In Argentina, the Bank has assisted the Government in developing its SNC. The cooperation with the Bank on the SNC provides a solid basis for further analysis aimed at deepening the conducted assessments and translating them into concrete actions. The Bank brings strong technical expertise based on its work on all the sectors covered by the TNC: water, tourism, ecosystems, agriculture, energy, waste, disaster risk management, climate modeling and knowledge management, etc.

- The TNC shall also benefit from the Bank’s manifold scientific cooperation agreements with; inter alia, the National Center for Atmospheric Research (NCAR) and the National Oceanic and Atmospheric Administration (NOAA). Through these agreements, the TNC could access state of the art support on climate modeling as an additional tool and on a needs basis to complement the work on regional modeling already initiated at the local level. The TNC will further benefit from the Bank’s analytical work such as the regional study on the social impacts of climate change and the Amazon Dieback Study: a key question for Argentina is how climate-induced changes in the Amazon basin will affect rainfall patterns in the La Plata Basin, as well as climate in the Pampa region of Argentina, the central agricultural zone of the country.

- The Bank also has a broad lending portfolio in Argentina with which the proposed Project would be coordinated (Annex 2 expands the potential for cooperation). Specifically, the TNC would generate valuable data for long term planning and defining responses to climate change impacts in the sectors covered by the following lending operations: (i) the Urban Flood Prevention and Drainage Project (APL2), (ii) the National Urban Solid Waste Management Project; (iii) the Second Provincial Agricultural Development Project and the (iv) Buenos Aires Infrastructure Sustainable Investment Development Project. The proposed Project will also be coordinated with already approved GEF Projects in Argentina, or those in the process of approval in sectors related to energy efficiency, conservation of ecosystems and biodiversity , transport and forest management, for example: (i) the Energy Efficiency Project; (ii) the Establishment of Incentives for the Conservation of Ecosystem Services of Global Significance Project. (iii) the Rural Corridors and Biodiversity Conservation Project; (iv) the Sustainable Forest Management in the Transboundary Gran Chaco Americano Ecosystem Project; and (v) the Regional Sustainable Transport and Air Quality Project.

- The coordination of the TNC with the sectors, in which the Bank is involved, as well as the identification of new priority intervention areas in the field of adaptation and mitigation through the TNC, would provide new opportunities for cooperation.

- Finally, the TNC will learn from the development of other NCs in the Region. The TNC of Mexico to the UN Framework Convention on Climate Change was prepared with participation of the Government, academia, the private sector and NGOs. A very important step in integrating the participation of different ministries for decision-making was the creation of the Inter Ministerial Commission on Climate Change (CICC).

- CICC resulted from an agreement between the participating ministries, and was in charge of coordinating the actions of the Federal Public Administration, according to their own attributions. These actions are related to the implementation of policies for greenhouse gas emissions mitigation and for adaptation to the effects of climate change. This agreement also aimed at identifying, promoting and evaluating projects for the reduction and capture of GHG emissions in Mexico, by using the provisions of the Kyoto Protocol (KP) as well as other instruments directed towards the same goal. The members of the Commission were the Ministries of Foreign Affairs; Social Development; Environment and Natural Resources; Energy; Economy; Agriculture, Rural Development, Fisheries and Food; and Communications and Transport. The Ministry of Treasury and Public Credit was a guest participant. The Commission could also request other dependencies and governmental entities to participate on an ad-hoc basis when needed.

Government Policies and Strategies

- The Project is in line with GOAaspirations on advancing with the national climate change agenda, and has a specific target of promoting identification and filling of policy and strategy gaps in relevant sectors.

- Argentina is introducing environmental considerations and sustainable development concepts into its strategic sectoral development plans for each of the main economic sectors, which have not been fully considered in the past (see a detailed list of relevant Government initiatives in Annex 17). There are incipient efforts with substantial potential for mitigation and adaptation impacts. The on-going activities and sectoral programs will contribute with inputs to the TNC as lessons learned or opportunities to consider obstacles or barriers.

- The main objective of the TNC is to design climate change P&M that could be integrated into sectoral development strategies and assessing their economic, environmental and social impacts. This will offer a scientific-based decision making tool not only for the Secretariat of Environment and Sustainable Development (SAyDS) but also for policy makers across the different areas of national, provincial and municipal governments.

- This Project proposal has been elaborated after an initial consultation process within and outside the SAyDS.  Among Government agencies that have participated in this process are the Secretariat of Energy, the Secretariat of Industry, the MAGyP, and the Subsecretariat of Water Resources. Together with these, SAyDS is leading the climate change dialogue with other agencies, or with climate change units in provinces, which represent a valuable platform for building on specific TNC topics. The TNC preparation has triggered creation of the Government Committee on Climate Change, an inter sectoral group which under the coordination of the SAyDS will be in charge of the climate change policy for the country. The Committee will also serve as the Steering Committee for this Project (see Annex 6 for more details).

- Higher Level Objectives to which the Project Contributes

Environmental Objectives of the GOA

- The GOA has made a commitment to convert sustainable development and care for the environment into a real public policy, seeking to include environmental dimensions at all levels of Governmental actions. In this way, the Government has been working on optimization of instruments such as territorial planning, adopting a system for environmental diagnostic and information, and civil participation to strengthen economic sustainability. Climate change is a key issue of national environmental policy, involving reduction of GHG emissions and adaptation. The first actions of this national strategy are promotion of renewable energy sources in order to increase their share in the energy mix, achievement of energy efficiency through specific programs, and preservation of native forests. Under this context, the proposed TNC is fully aligned with national environmental priorities, which include, among other activities, completion of a national GHG inventory aimed at strengthening the systems of environment diagnostic, as well as identification of adequate measures for mitigation and adaptation.

- The Project contributes to achieving the ultimate objective of the UNFCCC. The objective of the UN Framework Convention on Climate Change (UNFCCC), and of any related legal instruments that the COP may adopt, is to achieve stabilization of greenhouse gas concentrations in the atmosphere at a level that would prevent dangerous anthropogenic interference with the climate system. Such a level should be achieved within a timeframe sufficient to allow ecosystems to adapt naturally to climate change, to ensure that food production is not threatened, and to enable economic development to proceed in a sustainable manner.

- Argentina is an active player in the international climate change agenda. Argentina ratified the UNFCCC on March 11, 1994, and the KP in September 28, 2001. As part of the obligations assumed as a Party to the UNFCCC, the GOA submitted its First National Communication (FNC) in July 1997, and a revised one in October 1999. The SNC was submitted in December 2007 with the support of the World Bank and the GEF. During 2008, the GOA started the preparation of the TNC to the Parties of the UNFCCC through the continued help of the Bank/GEF. Argentina was actively involved in the pre-Copenhagen negotiations. Thereby, and post-COP15, Argentina has continued to hold its position to claim deeper GHG ER commitments by developed countries than those originally agreed under the KP. At the same time, Argentina is requesting economic, technological and scientific support to implement appropriate mitigation actions in developing countries. This position is being shared by the majority of the Latin American countries. The current administration of the Secretariat of Environment and Sustainable Development (SAyDS) is demonstrating a deep commitment to the climate change agenda, as well as related leadership capacity among the national public authorities. There is a strong will inside the SAyDS to lead the effort of integrating climate change mitigation and adaptation into sector strategies and to develop a national strategic CC framework.

- PROJECT DESCRIPTION

- Lending Instrument

- The Project would be financed by a Global Environment Facility (GEF Enabling Activity (EA) Grant with co-financing from the Secretariat of Environment and Sustainable Development (SAyDS).

- The type of project activity proposed, national communication (NC), has been agreed under the UNFCCC to be financed by the GEF. Article 4.3 of the UNFCCC specifies that the Annex II countries shall provide financial resources to meet “the agreed full costs” incurred by developing country Parties in complying with their NC obligations. As mentioned above, NCs are essential pieces of information to reach the ultimate goal of the UNFCCC by informing all Parties about the current situation and future actions of individual countries in relation to climate change, allowing the COP to better define objectives and the level of effort required to accomplish them. This fact shows the potential global environmental benefits of NCs. The GOA is currently reviewing the sector development strategic plans for each of the main economic sectors; a part of the committed co-financing of the Project relates with this ongoing work.

- The Project is in line with the GEF support to Enabling Activities (EAs) pertaining under the GEF Climate Change Focal Area (CCFA). Under the Climate Change Focal Area, the GEF finances eligible enabling, mitigation, and adaptation activities. In particular, and according to the CCFA Strategy and Strategic Programming for GEF-4, EAs will continue to be financed by the GEF, as NCs represent an obligation for non-Annex I Parties to the UNFCCC. The GEF will make "further arrangements necessary to ensure that adequate and timely support for third and subsequent NCs is made available to countries requiring it". The GEF-4 programming document also emphasizes the need to help these national communications to develop into strategic documents that identify and implement programs and activities at the national level, both in the fields of mitigation and adaptation. To accomplish this, deeper commitment to climate change would be required at the national level. The proposed Project, as well as the approach taken by the GOA, is in line with this objective by supporting the design of policies and measures (P&M) that would provide the strategic framework for identified adaptation and mitigation actions. The proposed Project would thus go beyond the achievements of the SNC assessments by integrating climate change into sectoral policies and development planning. Beyond the GEF support for TNC, the proposed Project activities are also complying with the GEF mitigation and adaptation mission.

- Project Development Objective and Key Indicators

- The PDO is to strengthen the information base and institutional capacity of the key organizations, members of the Project Steering Committee, to integrate climate change priorities into development strategies and relevant sector programs of the Argentine Republic by providing financial and technical support to prepare its TNC to the UNFCCC.

- The TNC aims at contributing to the development of a national climate change strategy especially for national level decision makers to achieve national development goals and show leadership in addressing climate change through voluntary action. The TNC also aims at benefitting decision makers at provincial and municipal levels as well as the general public.

Key performance indicators:

- Key performance indicators are the following:

- Climate change mitigation: Number of studies available to inform different institutions and sectors about feasible mitigation policies and measures and their potential prioritization to facilitate decision making.

- Climate change adaptation: Number of studies available to inform different institutions and sectors about feasible adaptation policies and measures and their potential prioritization to facilitate decision making.

- Capacity building: % of targeted institutions with improved capacity to take proposed mitigation and adaptation policies and measures forward, and % of targeted stakeholder groups that express increased awareness on climate change concerns.

- Project Components

- The Project has four main components described as follows (and as presented in the draft Grant Agreement):

Component 1: Harnessing National Potential for Climate Change Mitigation - Upgrade and development of the Recipient’s national inventory of greenhouse gas emissions (GHG), including the provision of support to strengthen the Recipient’s technical capacity for modeling, analyzing and projecting GHG emissions. - Carrying out of studies on mitigation potential in the Recipient’s main economic and GHG-emitting sectors, with an aim at identifying priority mitigation measures. - Enhancement of an enabling framework for the implementation of mitigation measures, including the design and delivery of a set of policies and mitigation measures aimed at integrating climate change into the Recipient’s development strategy and sector programs. Component 2: Strengthening National Adaptation Agenda A. Provision of support for the carrying out of socio-economic and climate- change modeling scenarios, targeted at identifying priority adaptation actions and expected impacts, costs and benefits (building upon the conclusions of the SNC, as applicable). B. Carrying out of studies to further develop priority adaptation actions necessary to strengthen the Recipient’s preparedness to climate- change impacts in areas identified as most vulnerable. C. Enhancement of an enabling framework for the implementation of adaptation measures, including the design and delivery of a set of policies and adaptation measures aimed at integrating climate change into the Recipient’s development strategy and sector programs. Component 3: Institutional Strengthening, Capacity Building, and Information Management - A. Provision of support to define the technical scope of activities to be carried out under the TNC, including the design of the institutional and coordination arrangements necessary to facilitate access to Project information and to secure stakeholders’ ownership and participation. - B. Strengthening of institutional capacity at the national, provincial and municipal levels, with regard to the integration of climate data into sector programs and strategies through, inter alia, the carrying out of workshops aimed at developing and disseminating Project-related information and materials, targeting the participation of key governmental agencies, scientific and technological institutions, and civil society. - C. Preparation and dissemination of the TNC, incorporating the conclusions and results reached through the carrying out of Project-supported studies and additional related information. Component 4: Project Management A. Provision of technical and operational assistance, as necessary, to support adequate Project management and coordination by the PIU and the Steering Committee, including carrying out Project audits.

- A detailed description of each component is included in Annex 4 and a brief description at sub-component level is added below.

Component 1: Harnessing National Potential for Climate Change Mitigation (GEF cost: US$ 0.53 million, total: US$ 0.67 million)

- The objective of this component is to update the country’s GHG emission inventory for each emitting sector, and assess and design potential mitigation measures. These objectives will be achieved through three sub-components.

- Sub-component 1.1: GHG Inventory and Development of Tools to Manage the GHG Emissions Database: Upgrade and development of the Recipient’s national inventory of greenhouse gas emissions (GHG), including provision of support to strengthen the Recipient’s technical capacity for modeling, analyzing and projecting GHG emissions.

- Sub-component 1.2: Actions to Enhance Climate Change Mitigation: Carrying out studies on mitigation potential in the Recipient’s main economic and GHG-emitting sectors, energy and transport, waste, agriculture, and forestry, with an aim at identifying priority mitigation measures. The supported studies will analyze the technical and economic aspects related to implementation of the identified mitigation actions in Argentina.

- Sub-component 1.3: Mitigation Policies and Measures (P&M): Enhancement of an enabling framework for the implementation of mitigation measures, including the design and delivery of a set of mitigation P&M aimed at integrating climate change into the Recipient’s development strategy and sector programs. This includes development of future GHG emission scenarios targeted at reducing emissions; analysis of the technical and economic, social, environmental, financial, and institutional, stakeholder-based aspects related with implementation of the identified mitigation actions in Argentina.

Component 2: Strengthening National Adaptation Agenda (GEF cost: US$ 0.93 million, total: US$ 1.16 million)

- The objective of this component is to assess the anticipated climate change impacts and to identify the most vulnerable sectors and areas in Argentina. Necessary priority adaptation actions including estimation of their sector-wide costs will be designed to strengthen adaptive capacity and climate resilience. Irreversibility, magnitude and immediacy will serve as initial criteria for choosing priority adaptation P&M. Additionally, enhancement of an enabling framework for implementation of adaptation measures, as well as integration of climate change into development strategies and sector programs will be supported.

- Sub-component 2.1: Assessment of Impacts of and Vulnerability to Climate Change: Production of current and planned socio-economic and climate change scenarios, targeted at identifying priority adaptation actions and expected impacts, costs and benefits relying on the state of the art climate models  and building upon the conclusions of the SNC and other assessments, as applicable.

- Sub-component 2.2: Actions to Improve Adaptation to Climate Change: Carrying out of studies to further develop priority adaptation actions necessary to strengthen the Recipient’s preparedness to climate change impacts in areas identified as most vulnerable, including technical and economic analysis of the proposed adaptation actions.

- Sub-component 2.3: Adaptation Policies and Measures (P&M): Enhancement of an enabling framework for the implementation of adaptation measures, including the design and delivery of a set of adaptation P&M aimed at integrating climate change into the Recipient’s development strategy and sector programs on the above named sectors, as well as on challenges and opportunities in labor sector and its adaptation to climate change. This will include technical, economic, environmental, social and financial analysis of the proposed adaptation actions.

Component 3: Institutional Strengthening, Capacity Building, and Information Management (GEF cost: US$ 0.87 million, total: US$ 1.09 million)

- The objective of this component is to prepare the detailed TORs of the studies, strengthen institutional capacity of the organizations members of the Project Steering Committee, and disseminate the TNC results to a broad audience. Dissemination efforts will be guided by a thorough communication strategy, and messages and communication channels will be tailored according to targeted diverse audiences.

- Sub-component 3.1: Definition of Technical and Institutional Framework for the TNC: Provision of support to define the technical scope of activities to be carried out under the TNC, including the detailed design of the institutional and coordination arrangements necessary to facilitate access to Project information and to secure stakeholders’ ownership and participation.

- Sub-component 3.2: Institutional Strengthening and Capacity Building: Strengthening of institutional capacity at the national, provincial and municipal levels, with regard to the integration of climate data into sector programs and strategies through, inter alia, organizing workshops for national, provincial and municipal agencies and legislators; teachers at high school and primary school levels; civil society (CS); and journalists aimed at developing and disseminating Project-related information and materials tailored to different interest groups.

- Sub-component 3.3: Development, Publication and Dissemination of the TNC. Preparation and dissemination of the TNC to all relevant stakeholders, incorporating the conclusions and results reached through the carrying out of the Project-supported studies and additional related information. Preliminary results will be discussed through different mechanisms such as workshops.

- Component 4: Project Management (GEF cost: US$ 0.11 million, total: US$ 0.13 million): Provision of technical and operational assistance, as necessary, to support adequate Project management and coordination by the PIU and the Steering Committee, including carrying out of Project audits.

- The head of the PIU will be the Secretariat of Environment and Sustainable Development (SAyDS)/the Chief of the Cabinet of Ministers (JGM). The Climate Change Directorate (CCD) will be in charge of the Project implementation, including the selection of consultants, review of the preliminary and final reports, coordination of workshops, etc. The General Administrative and Technical Directorate (DGTA) in JGM will be in charge of the fiduciary issues, as well as serve as the formal communication channel between the World Bank and the Executing Agency.

- Lessons from the SNC: Quality, National Ownership, and Development of Future Climate Scenarios. The SNC produced three key results that provide useful lessons for the future climate change planning: the GHG emissions inventories, the Adaptation Strategy, and the National Mitigation Plan including capacity building. The revised and new GHG inventories for years 1990, 1994, 1997 and 2000 were important to establish a baseline for the last decade of the 20th century. The TNC will determine new estimations, which will further facilitate analyzing of emission trends. The vulnerabilities identified by the SNC showed that the significant climatic changes over the last 40 years have resulted in sharpening agricultural and livestock sector frontiers to the north and west of the traditional agricultural area. This autonomous adaptation trend was economically successful in the short term, but according to climate Projections it could have significant environmental impacts during the coming decades.

- Participation and Consultation. Participation of stakeholders and decision makers in the development of policies and strategies is of critical importance, as this will ensure ownership of and commitment for the Project implementation phase. Since the Project will help develop cross-sector strategies and programs, joint participation from all relevant Governmental Agencies starting right at the Project inception will ensure proper implementation and adequate mainstreaming across relevant sectors. The Steering Committee will be the main instrument to ensure sector consultation and participation (see Annex 6 for more details on institutional arrangements).

- Coordination of Activities. Close coordination and supervision of the studies will be needed, in particular with relation to the vulnerability assessments implemented by local institutions to ensure approach-based coherence between the subsequent strategies. Development of local emission factors and carbon sequestration coefficients is important, as Argentina presents particularities which are not easy to standardize for general approaches. Use of regional circulation models is important to fine-tune vulnerability assessments of fragile and critical ecosystems, and define a set of response options. A strong consultative process with the general public will ensure that any voluntary commitments assumed or ratified will be endorsed as legitimate. Involvement of the provinces as well as private sector and CS is a key to achieve a strong climate change agenda and broad country-wide support. This will be achieved by means of a Steering Committee and participatory activities along Project implementation.

- Availability of Information. The TNC has included dissemination activities at national, provincial and municipal levels. The Project budget has been planned accordingly.

- Alternatives Considered and Reasons for Rejection

- Non-Government Execution. An alternative to the Project design was to reconsider that the executing entity could have been an NGO. This option was discarded, as the current technical and administrative capacity of the GOA was considered adequate to execute the Project. Furthermore, this will strengthen the national buy-in and facilitate the integration of the studies’ results into the relevant sector programs. The SAyDS is highly recognized among other Government Agencies for its technical leadership on climate change issues, and it has established solid coordination mechanisms.

- Focused geographical scope. Whereas the SNC focused on some key geographical areas (Del Plata Basin, Cuyo, Comahue/Patagonia and the Rio de la Plata coastal zone) when studying vulnerabilities to climate change, now it has been decided to include all ecosystems and provinces under the vulnerability analysis, given the expected challenges ahead with regard to CC impacts and the need to start an ambitious adaptation program across the country.

- Limited federal participation. In contrast with the SNC, it was decided that the Steering Committee should also include representatives of regional agencies like COFEMA, in order to strengthen their involvement. Regional participation at the implementation level will be crucial to ensure proper institutional ownership and first hand data and information sources for relevant decision making and long term planning.

- IMPLEMENTATION

- Partnership Arrangements

- Given the nature and objectives of the Project, effective partnerships are key to successful implementation. A partnership between SAyDS (CCD) and other government agencies started during project preparation by cretating the Steering Committee. This partnership will be consolidated during the implementation phase. More details are included in Annex 6.

- Institutional and Implementation Arrangements

- Implementation Period: The Grant is expected to become effective by December 2010 for a two-year period. The expected Project closing date is 30 November 2012.

- General Implementation Arrangements: The Chief of the Cabinet of Ministers (JGM) will be the Project Executing Agency. The Secretariat of Environment and Sustainable Development (SAyDS) under the JGM is the focal point for the Climate Change Convention, and it has the institutional mandate to prepare national communications. The Climate Change Directorate (CCD) in the SAyDS will lead the technical aspects of the Project. The General Administrative and Technical Directorate (DGTA) of the JGM will be in charge of the overall Project implementation and responsible for the Project procurement and Financial Management (FM) activities: comprising budgeting, accounting and reporting, including preparation of Interim Unaudited Financial Reports (IUFRs), provision of internal control, and taking care of the disbursements and the external audit process. Annex 6 provides detailed information (including a diagram) regarding the Project implementation arrangements. The management structure of the TNC will be constituted by a Steering Committee (SC) serving as a consulting organ, the Project Implementation Unit (PIU), and a Technical Advisory Committee (TAC).

- Steering Committee (SC): The SC became effective on December 22, 2009. It consists of representatives from relevant Governmental agencies and the Federal Council for the Environment (COFEMA). The president of the SC is the Secretary of Environment and Sustainable Development. The main responsibility of the SC is to assure political and strategic support for the TNC implementation. It will provide guidance on implementation and make high level recommendations regarding the Project’s development, technical aspects and management issues.

- The SC will assure national ownership of the results making sure they prove useful for the development of national policies. The SC will monitor the progress reports elaborated by the PIU, and provide guidance on the structure and contents of the Project documents. The SC will have access to budget execution of activities based on reports elaborated by the PIU for each SC meeting, or as requested.

- Project Implementation Unit: The PIU will carry out the Project implementation according to the established chronogram and assigned budget. The PIU will be formed within the JGM by the CCD/SAyDS and the DGTA. The CCD will be in charge of the technical coordination of the PIU. It will be conformed by thematic coordinators and technical-administrative support. Dirección General Técnico Administrativa (DGTA) from JGM will be in charge of FM and procurement in the Project. The DGTA will carry out all procurement and contracting of external consultants serving the PIU in accordance with the Bank procedures.

- Technical Advisory Committee: The TAC will support the PIU in technical and scientific issues during Project implementation. TAC will be integrated by scientific and technical institutions, NGOs, CS, trade unions and representatives from the private sector. They will be selected using a methodology to be approved immediately after Project approval following principles of representativeness and open participation.

- Monitoring and Evaluation of Outcomes/Results

- Monitoring and Evaluation: The Project will have a robust monitoring and evaluation (M&E) system. The PIU will be responsible for overall Project M&E. A detailed M&E system and guidelines will be included in the Operational Manual. A framework for outcome monitoring and evaluation is included in Annex 3.

- Project Reports: The Recipient will submit to the Bank semi-annual integrated Project progress reports demonstrating Project development and financial and technical performance indicators. The Bank will conduct visits to jointly review progress made with regard to objectives and performance indicators. Regular monitoring of Project activities will be a responsibility of the PIU.

- Mid Term Review (MTR): The Bank’s supervision team, together with a team of external reviewers and key stakeholders, will conduct a MTR of Project execution, not later than 12 months after the first disbursement. The external review will focus on: (i) progress in achieving outcomes, (ii) institutional arrangements for implementation, (iii) operational manual, and (iv) review of both the implementation plan and general Project operational manual. During the preparation of the MTR, the SC, together with the local executing agencies, will prepare the following information: (i) executive summary of the overall Project status, (ii) description of the overall components’ development and indicators; and (iii) description of the status of the different studies.

- Supervision: The Bank team will deploy a supervision team during Project implementation, which will draw on specialists from across the Bank or externally as required. The Bank, during supervision, will take advantage of potential synergies in terms of technical activities, and especially during TOR development. All TORs for the TNC studies will require the Bank’s review.

- Sustainability and Replicability

- Sustainability. The Project will promote integration of climate change concerns into sector policies and programs, including related capacity building, concrete proposals for policy changes, and promotion of cross-sectoral coordination. Active participation by all stakeholders in the formulation of mitigation and adaptation P&M will be facilitated to ensure ownership and sustainability.

- The SNC identified the generally high initial costs and the prevailing scarcity of public funding to other than social investment purposes as the main limiting factor for adoption of mitigation and adaptation measures in Argentina. To address this obstacle, the TNC will study mechanisms to remove identified implementation barriers, and include research and innovation on possible financing sources for the identified mitigation and adaptation P&M: the aim is also to propose P&M which would be revenue-generating to cover at least a part of their implementation costs. Additionally, many adaptation and mitigation measures provide win-wins and multiple benefits, such as economic savings, improvement of local environments, and avoidance of expensive corrective measures in the future.

- To promote widest possible use of the resulting climate change studies, the Project will develop a thorough communication strategy tailored to different stakeholder groups. Workshops and dissemination material will be offered to participants of governmental, scientific and technological institutions and CS, and a communication system designed towards provincial and municipal governments.

- As a Party to the UNFCCC, Argentina will continue to prepare NCs showing progress and showcasing policies oriented to comply with its objectives.

- Critical Risks and Possible Controversial Aspects

- Eight potential risks have been identified, which could potentially affect the effectiveness and sustainability of the Project, as well as feasible mitigation options respect to each risk.

| Risk | Mitigation Measure | Residual risk rating |
| --- | --- | --- |
| Project Risks. Institutional and coordination risk: the adaptation and mitigation agendas in Argentina involve a variety of sectors, institutions and provinces distributed throughout the country. There is a risk that studies and Project activities cannot be completed because of limited institutional support, lack of dissemination of results, and insufficient coordination of inputs. | Strong coordination and involvement of concerned institutions right from the beginning will be sought to ensure adequate assessments, continuous access to data and integration of the results into sector planning. The Project has already established a Steering Committee which includes a core group of representatives from the relevant Governmental agencies and the COFEMA, and research institutions, CS and private sector representatives form an advisory panel attached to the SC. The COFEMA will also be actively involved. In addition, the Project will develop a continuous and extensive consultation process throughout Project duration including key stakeholders and sectors. This process was already launched with two workshops in August 2009, in order to ensure early buy-in and involvement by stakeholders in the definition of assessments and in strengthening the strategic value of the Project. The Project will develop a communication strategy. It will involve several ministries (e.g. Ministry of Economy) and will seek to strengthen existing commissions as coordination platforms for the CC dialogue. | M |
| Limited implementation experience of the agency responsible for the technical implementation of the Project. | The CCD was established in 2007 and is a relatively young unit inside the SAyDS. However, it has technical personnel who have been working for a long time on issues related to climate change issues, and it enjoys good recognition among other Secretariats. | M |
| Political risk: Formulation of mitigation and adaptation P&M implies important risks due to conflicting interests between sectors. Though the TNC will not implement any concrete measures on the ground, the Project needs to consider the political risks related to the P&M to be designed. Additionally, the general elections in 2011 expose the Project to the possibility that conclusions and outcomes of the TNC could become politicized, thereby undermining their technical merits. | The Project has convened a Steering Committee for the TNC in order to strengthen political ownership at different decision making levels. Enhancing nation-wide understanding of linkages between the climate change agenda and national development goals must involve adequate representation of decision makers. Legislators will be invited to the TNC dissemination events. Early involvement of the main political parties also lowers the risk related with the upcoming elections. Institutional arrangements for the Project include a Technical Advisory Panel comprised of NGOs and scientific experts. Its role will be essential to ensure the technical quality of outcomes as well as transparency of the process. | L |
| Cost-overruns and a short implementation period: The Project involves a significant number of technically challenging studies, which are closely interlinked with each other. There is a substantial risk of related cost-overruns and possible need to extend the Project implementation period. | Project preparation has included a detailed planning exercise including a detailed budget elaborated following local costs and a timeline to ensure proper interlinkage between studies. Both have been included in the Operational Manual of the Project. | M |
| Limited robustness and completeness of GHG emissions and climate data: Possible risks for the proposed Project activities are associated with the robustness and completeness of the data required to carry out the different studies that will be part of the TNC. In addition, much of the data required is dispersed among different public and private institutions and often difficult to gather. | The CCD as the responsible entity for the technical implementation of the Project will coordinate with the relevant institutions to collect the necessary data. The CCD maintains good interaction with relevant Secretariats, and enjoys a good reputation in technical and institutional terms among them. Regarding scientific capacity, many of the scientists and researchers who worked on the SNC, will provide information and experience. The Bank is engaged in several cooperation agreements with some of the globally leading climate research institutions facilitating access to solid climate data and tools for the CCD. The Project will thus benefit from the access to advanced modeling tools and training opportunities in applying adequate climate models on a regional basis. The Project will also benefit from cooperation with several Bank operations in relevant sectors, which also facilitates access to data and results. | L |
| Financial Management Risks. General FM risks in public sector. | The FM risks will be mitigated by ensuring an adequate internal control framework which includes an integrated accounting system, formal written procedures, segregated designated account (DA), and an independent external auditor. Given all the contracts and payments will be handled by the DGTA-JGM, this internal control will be executed for them. Some of the measures will include: i) Enhanced FM supervision to ensure the continuous adequacy of FM arrangements, evaluate Project internal control and update assessed risk. At least one on-site visit integrating the Project team is planned for the first year; ii) Continuous support to AGN (Argentina Supreme Audit Institution) efforts to ensure timely audit compliance for the Project. Upon audit findings, follow up on the borrower action plans to address the auditors’ recommendations; and iii) Involving the Internal Audit Units to carry out review of Project financial transactions. | M |
| Procurement Risks : The key issues and risks concerning procurement have been identified and include: (a) the lack of experience at the DGTA in Bank-financed Projects, (b) the lack of DGTA’s staff direct involvement in management of procurement using Bank procedures; (c) the significant number of contracts to be carried out in a short time, though most of them are consulting services and thus simple. | The corrective measures that have been agreed are the following: i) staff in the procurement unit should participate in the Basic Procurement Training delivered by the Bank, either in the country or in any neighboring country, ii) the Project will implement the SEPA system, iii) before negotiations, a Project operational manual would be developed including the implementation arrangements and the procurement procedures, and iv) while the technical unit identifies the dimension and number of the firms interested in participating in the processes of consulting services under the Project, it should be considered the packing of contracts in accordance with the market size. | M |

The following risk rating applies: L = Low; M = Modest; S = Substantial; and H = High.

The average risk rate for the Project is Moderate.

- Loan/credit Conditions and Covenants:

- There are no planned Board conditions.

- Grant covenants: To be confirmed based on the Grant Agreement.

- Grant dated covenant: A specific budget line entry for the Project will be created in the annual budget for 2010 and maintained thereafter to keep track of the Project’s budget execution processed in the National Integrated Financial Management System (SIIF).

- APPRAISAL SUMMARY

- Economic and Financial Analyses

- This Project will be implemented during a time of global economic uncertainty and volatility, but this context is not expected to affect Project implementation. The Project will be funded by a GEF grant and in-kind counterpart contribution, and it will have a small budgetary impact.

- As the Project consists of studies, it is not possible to estimate its economic impacts at this point, but the TNC will include the financial and economic analysis of the proposed mitigation and adaptation P&M identified and designed through the financed studies, thus facilitating decision-making and expected prompt implementation (see Components 1 and 2, and Annex 4 for more detailed information). The TNC will also contribute to the challenging task of determining economic losses associated with climate change impacts in Argentina through provision of new data and analysis on the complex linkages between sectors.

- Technical

- The main technical challenges of this Project relate to the uncertainties inherent to the currently existing models used for down-scaling of climate change models, a highly necessary but yet not widely applied exercise. The studies conducted under the Project will, however, benefit from the similar modeling efforts carried out across Latin America and the Caribbean in a multiple Bank-assisted Projects.

- Estimations of costs of sector-wide measures to promote climate change mitigation and adaptation are also in their infancy, and will largely depend on international developments around the UNFCCC and related market processes.

- Fiduciary

- The JGM will be the Project Executing Agency. The General Administrative and Technical Directorate (DGTA) of the JGM will be in charge of the overall Project implementation and responsible for the Project procurement and FM activities: comprising budgeting, accounting and reporting, including preparation of IUFRs, provision of internal control, and taking care of the disbursements and the external audit process.

- Financial Management: A FM review of the adequacy of the FM arrangements for the Project was performed in line with the guidelines issued by the FM Board on November 3, 2005, as well as the Simplified FM Assessment for Small Grants (2009) to determine if the FM arrangements in place are acceptable to the Bank. A summary of the FM assessment is presented in Annex 7.

- Financial Management Risk: The FM arrangements for the proposed Project are sound. From the FM perspective, the Project risk is considered Moderate. A detailed risk analysis is provided on the Risk Section of Annex 7.

- The Technical and Administrative General Secretariat (DGTA) of the JGM will perform the Project FM activities comprising budgeting, accounting and reporting, and including preparation of semestral IUFR, ensuring an adequate internal control framework is in place, and taking care of the disbursements and the external audit process.

- Procurement: All the procurement arrangements and an 18-month procurement plan will be included in the Operational Manual. DGTA/JGM will be responsible to follow standard Bank procedures for all Project procurement, and will ensure enforcement in procurement by beneficiaries. Procurement will include consulting services, goods, and non-consulting services; more details are provided in Annex 8.

- A procurement plan has been prepared by the Recipient during the Project preparation period. In addition, the team has identified the best alternatives for the procurement process to facilitate a prompt start-up. In connection to these discussions, the GoA team started a market research (see www.ambiente.gob.ar) to determine the potential supply of qualified consultant services and experts to cover the Project needs. This exercise has served for the detailed elaboration of the procurement plan.

- The procurement process will be under the direct responsibility of Chief of the Cabinet (Jefatura de Gabinete). This will simplify internal procedures between SAyDS and JGM facilitating fast implementation.

- Social

- The Project is aimed at developing strategies and plans for both mitigation and adaptation. Therefore, community and stakeholder participation is critical to ensure implementation and sustainability. Approximately 10% of the total Project budget has been assigned to raising public awareness, and the TNC report itself is planned to be published and widely distributed.

- The Project Steering Committee will act to ensure participation of a wide range of stakeholders along the Project implementation. Public awareness activities, including seminars, workshops, and web-based discussion groups, will provide opportunities for public participation. Activities will also feature tailored messages targeted at specific audiences such as students, professionals and CS organizations, media personnel, and community leaders. The Project will develop a plan of public awareness and education aiming at, inter alia, providing information to stakeholders to serve their further action in the field of climate change. Informal meetings and discussions will be promoted between, among others, members of the private sector, NGOs, national and regional public servants, research institutions, and CS leaders to encourage exchange of information and collaboration.

- Related to the above, and given that the mitigation and adaptation measures to be identified along the Project implementation will target reducing vulnerability to climate change and increasing climate resilience of the most vulnerable parts of the population, special efforts need and shall be made to involve participation of these vulnerable groups and include their concerns into the design of evolving climate policies.

- Evaluation of social impacts of all the identified mitigation and adaptation measures will form an integral part of the Project execution, but it needs to be recognized that these evaluations will include a number of uncertainties relating with the inherently uncertain nature of climate and societal modeling.

- Environment

- The proposed Project is rated as Category C for environmental assessment purposes consistent with the provisions of OP 4.01. This Project will not have adverse environmental impacts, as no civil works or remediation activities will be financed under the Project. Finally, identified mitigation and adaptation measures will reduce vulnerability of ecosystems and population, as well as the national carbon footprint.

- All the proposed studies and outputs will follow and be consistent with the Bank’s safeguards policies.

- Safeguard Policies

| Safeguard Policies Triggered by the Project | Yes | No |
| --- | --- | --- |
| Environmental Assessment (OP/BP 4.01) | [ ] | [x] |
| Natural Habitats (OP/BP 4.04) | [ ] | [x] |
| Pest Management (OP 4.09) | [ ] | [x] |
| Cultural Property (OPN 11.03, being revised as OP 4.11) | [ ] | [x] |
| Involuntary Resettlement (OP/BP 4.12) | [ ] | [x] |
| Indigenous Peoples (OP/BP 4.10) | [ ] | [x] |
| Forests (OP/BP 4.36) | [ ] | [x] |
| Safety of Dams (OP/BP 4.37) | [ ] | [x] |
| Projects in Disputed Areas (OP/BP 7.60)* | [ ] | [x] |
| Projects on International Waterways (OP/BP 7.50) | [ ] | [x] |

- Policy Exceptions and Readiness

- The proposed Project does not require any exceptions from Bank policies and is deemed to be ready for implementation. An acceptable Operational Manual was presented to the Bank at negotiations. In terms of readiness for implementation, the Project complies with the following criteria: FM and procurement arrangements and measures are in place for Project implementation; appropriate core Project staff is available at JGM and SAyDS, counterpart funds are available as part of JGM budget; and results assessment arrangements completed (institutional M&E obligations and budget are assigned).

THIRD NATIONAL COMMUNICATION TO THE UNITED NATIONS FRAMEWORK CONVENTION ON CLIMATE CHANGE

Annex 1: Country and Sector or Program Background

## Country Economic Context

- 1.	Argentina’s economy has been growing at an average annual rate of 8% for the last 5 years. This economic expansion increasingly stresses the use of natural resources for agricultural production, energy generation, and transportation of goods, among other activities. As this process continues, important decisions need to be made in relation to the development path Argentina should follow. Under this new scenario of economic growth, Argentina is introducing environmental considerations and sustainable development concepts into its strategic sector development plans for each of the main economic sectors, which have not been fully considered in the past. A set of sector programs currently under development in the legal framework of different Secretariats of the Government allude to a significant synergy with the goals of this Project. In that sense, the MAGyP, Secretariat of Energy and Secretariat of Environment and Sustainable Development (SAyDS), among others, are promoting different national programs that contribute to mitigate effects of climate change in the country. Details of these programs are described in Annex 17. They are incipient efforts with potential to substantial mitigation and adaptation impacts. All the on-going activities and sectoral programs will contribute with inputs to the TNC as lessons learned or opportunities to consider obstacles or barriers.

## Sector Context

## Climate Change Scenario

- 2.	While Argentina emits only about 0.85% of the annual global greenhouse gases, it is the fourth largest greenhouse gas (GHG) emitter in Latin America. The GHG emissions corresponding to year 2000, and including the Land Use Change and Forestry (LUCF) sector, are 238,703 Gg of CO2 eq., slightly lower than those of 1997. However, if LUCF sector is excluded, the emissions of the year 2000 increased 4.1% above those of the year 1997. This difference is explained by the increase of the net sequestration of the LUCF sector between the named years. When the emissions, expressed in tons of CO2 eq., are disaggregated by gases (without considering the LUCF sector), the 45.5% of the total relates to CO2, 30.1% to CH4, and 23.9% N2O. According to the SNC, the most emitting sectors include energy (46.8%), agriculture and livestock (44.3%), and waste management (5.0%), the remaining 3.9% corresponding to Industrial Processes.

3.	As an immediate background, the SNC produced several significant results for the development of the TNC: Revised emission inventories for the years 1990, 1994, 1997, and 2000, which results  establish a solid baseline facilitating the updating of GHG emissions and analyzing of their future trends. The SNC also resulted in guidelines for adaptation and mitigation, which serve as a first step towards concrete, already more action-oriented strategies, and interactive participation with relevant stakeholders is promoted. Four sectors/areas were analyzed in great detail: agriculture, coastal zone management, water resources, and energy. The mitigation plan helped to identify mitigation opportunities focused on energy efficiency (under implementation of a GEF project) and savings, renewable energy, ERs in the transport sector (with the support of an on-going GEF project), and carbon sequestration (endorsing the World Bank Forest Carbon Partnership Strategy, FCPS). These adaptation and mitigation assessments lay the groundwork for further analysis and help to promote their translation into concrete actions. Further vulnerability assessments under the proposed TNC will build upon the work carried out during the SNC.

4.	For Argentina, as for the most countries in the region, climate change is most of all an adaptation issue. Climate change impacts are already being experienced in Argentina, and future climate change projections indicate new vulnerabilities and aggravation of current ones, and the country has started to implement some specific adaptation actions. Adaptation has mostly taken place in an autonomous, unplanned manner particularly in the agricultural sector, and besides short term economic benefits, it has caused environmental damages, which are expected to be aggravated by as climate impacts grow stronger as projected. Given the structure of Argentina's economy, a comprehensive analysis of the challenges imposed to the agricultural sector by evolving climate conditions will be a cornerstone of the TNC. The Fourth Assessment Report (AR4) of the Intergovernmental Panel on Climate Change (IPCC) already provides substantial insights into the dilemma faced by agriculture, but it does not provide assessments of particular regional challenges. This is where the TNC aims at informing the UNFCCC and drawing attention to national, sub-national and local problems faced by Argentina: its entire production belt will be affected by increases in soil temperatures and changes in rainfall patterns, including the occurrence of extreme weather events. These changes will be gradual and unidirectional, and the challenge for the GOA is to internalize future implications into current planning.

5.	Even though Argentina’s GHG emissions are relatively moderate in the global context, forceful mitigation actions are required from the global community in order to prevent dangerous anthropogenic interference with the climate system in accordance with the Climate Convention’s ultimate objective. Argentina has a considerable portfolio of on-going mitigation projects, but its GHG emissions have been growing continuously over the last years, and deforestation rates are significant, with estimates for annual deforestation being as high as 250,000 ha (Brown A. et al, 2005. La Sitacion Ambiental Argentina 2005. (Fundación Vida Silvestre Argentina. Buenos Aires, 587pp.) According to the Fundación Bariloche (FB), which developed the GHG emission inventory for the SNC, a GHG emissions growth of 184.6% is projected between 1990 and 2030. The major share of this growth is due to the energy sector (122%), which would represent 53% of the total GHG emissions. Consequently, the proposed TNC seeks to identify and support forceful mitigation actions in the energy sector. For example, Argentina is endowed with substantial wind energy potential, and the TNC can help with addressing some of the barriers that prevent unleashing this potential. At a wider scale, the TNC has the potential to define and recommend steps that the GOA can adopt today to position itself to adhere to a low carbon footprint development path.

- Climate Change and Sectors

6.	During the last 5 years, many sectors in Argentina have started to incorporate climate change issues in their agendas. The following paragraphs describe the main sectors and the elements from each sector which are closely related to the TNC.

7.	Energy. The main characteristic of the energy sector in Argentina is the high participation of natural gas in the energy mix. This fossil fuel provides half of the primary energy consumed nationally for electricity generation, residential consumption and light transport. Natural gas production in 2000 was enough for residential consumption and exporting to neighboring countries despite the decreasing level of exploration of new reserves since 1998. Furthermore, the internal supply of oil, discounting exports, is nearly 25,000 MTep, while of natural gas it reached 35,600 MTep in 2005, 28% higher than internal oil supply. Both fossil fuels have been increasing their participation in the energy supply, counting for almost 90% of it. The production of hydro-electric energy increased from 270 MTep in 1970 to 3,680 MTep in 2005, reaching 5.2% of the internal primary energy supply. Production of nuclear energy started in 1974 with the nuclear power plant (NPP) Atucha I, and followed by the NPP Embalse, whose share of the internal supply of the national energy mix is lower than that of the hydropower.

8.	Liquid and gaseous hydrocarbons are important in the Argentine energy supply. Private studies showed their net emissions increasing 43.57% during 1990–2005, being 47.82% of the total net emissions in 1990, and 49.76% in 2005, with peaks higher than 58% in 1999 and 2000. Climate impacts on the energy sector are diverse and evident both for supply and demand. Projected climate changes add benefits and disadvantages to the current, already complex setting. The energy scenario used for estimating the influence of climate change is propitious to rational use of resources, higher penetration of efficiency enforcement, and sectoral integration at regional and national levels.

9.	An increase of better quality energy sources is expected, including enlargement of the natural gas networks and the consequent substitution of liquefied petroleum gas and kerosene in electricity production. An increase is also estimated in the electricity consumption for air conditioning, potable water provision, wastewater treatment and public lighting. The estimated total demand will increase more than 4% annually until 2018, given a GDP elasticity of 0.90, and then decrease to a rate of around 3% annually. It is expected that in thirty seven years, the energy consumption will increase almost 3.5 times reaching 150,000 ktep (thousands of tons of oil equivalent).

10.	It is expected that 5% of the increase of the electricity consumption will be due to the agricultural sector, driven by an external demand growth and rather stable or slightly enhanced climate conditions for agriculture in the wet Pampa and its boundary areas in the southwest of Argentina. The additional demand will be covered by hydro-electric power plants, both national and bi-national, and eventually nuclear power. High power wind turbines are likely to be connected to the grid. Thermal centrals would cover the remainder of the demand, thus minimizing the use of diesel applications. By 2018, hydro generation could achieve approximately 25–40% of the electricity supply, according to the annual hydraulics of rivers. Part of this supply, nearly 20% between 2020–2040, would be affected by the reduction of flows in Comahue, Cuyo and del Plata Basins, and would be covered by other sources or enhanced rationality of energy use. The reduction of fuel consumption for heating, mainly related with natural gas, would probably be frustrated due to increasing gas availability and consequent use in new/other regions. The reduction of fuel consumption for heating, mainly natural gas, would be exceeded by the availability of this fuel in more regions.

11.	Given the strong linkage the energy sector has with climate change, and the importance it will have in supplying an increasing future demand, the TNC is aimed at specially benefiting its planning. The Project component 1 seeks to address this issue by financing a set of studies to identify priority mitigation measures.

12.	Industry. In 2000, emissions from industrial processes were 11.108 Gg CO2 equivalent, representing 4.7% of the total GHG emissions in Argentina, including LULUCF, and 3.9% excluding LULUCF. Methane emissions are exclusive of oil-chemistry industry, and represent 0.03% of the national GHG emissions. Nitrous oxide emissions form nitric acid production were 145.4 Gg CO2 eq. (0.47 Gg N2O), representing 0.22% of the national total. Combined emissions of HFCs, PFCs and SF6 were 1,323.5 Gg CO2 eq. CO2 emissions from iron, steel, cement, ammonia, urea, lime and aluminum industries represent the main contribution of this gas by sub-category, followed by the potential emissions from HFCs consumption.

13.	Private studies showed that growth of the industrial sector increased 94.54% between 1990–2005, equivalent to 4.25% annual growth, and mainly based on the growing oil-chemistry, metals (iron, steel and aluminum), cement and “F” gases (HFCs, PFCs and SF6) production. Their contribution to the total emissions is relatively low, but increased from 3.92% in 1990 to 5.52% in 2005.

14.	Given the strong linkage the industrial sector has with climate change, the TNC outputs of component 1 will benefit its planning by financing a set of studies to identify priority mitigation measures in the sector.

15.	Agriculture. This sector is of high relevance for the TNC, since it satisfies the internal demand and generates a quarter of the national exports, being the base of the manufacturing industry. The contribution of this sector to the GDP is around 6%; and taking into account primary agricultural, livestock and industrial production, supplies and services, the percentage increases to 32%.

16.	The structure of the agro-industrial portion of the GDP is composed by 50% of derivative products based on soy and sunflower oil, cereals, and forage, which has the highest participation of 40%, while food and beverages represent 28% and livestock 10%. The high productivity and quality products from the agricultural sector are key factors of the economic growth with an advantageous scenario of prices in the international market.

17.	Emissions from the agricultural sector derive from a) methane emissions related with rice production in wetlands; b) methane, carbon monoxide, nitrous oxides (N2O and NOx) emissions related with burnt waste crops; c) direct and indirect emissions of N2O related with applied nitrogen through synthetic fertilizers, biologic fixation of nitrogen, and land disposal of agricultural wastes. Private studies indicate that emissions from the sector increased 28.07% in 1990–2005, 1.56% annually, representing a significant participation in the total emissions. This participation has been fluctuating from 45.52% in 1990, to 42.25% in 2005; a decreasing trend was detected from 2000, when the highest peak of 49.44% was observed.

18.	The variation in the inter-annual precipitation has a high impact on the agricultural production during the drought period. To a lesser extent, abundant precipitation produces excessive runoff causing flooding of productive lands, and damage to infrastructure, security and health of urban population. Increasing precipitation and implementation of new technologies have set off a favorable price rate and the agricultural boundary expanding to the west, producing a new cultivated area that until 1960 was considered semi-arid. Further, continuous and repeated flooding has damaged several agricultural areas in the provinces of Santa Fe, Buenos Aires, and Corrientes. Other already occurring negative climatic changes-related impacts is the generalized increase of precipitations in the north of Argentina in Chaco and Formosa, part of Salta, and Santiago del Estero, and high variability of precipitation is producing an unfavorable situation for agriculture due to a high risk of drought. A desertification process could be induced in the north and north-west of Argentina, if the current values of the average precipitation and higher temperatures were stabilized. This, jointly with the current land use and deforestation patterns, the low agricultural aptitude of the soils poor in organic matter, would threaten the sustainability of the productive systems in an irreversible manner.

19.	Given the strong linkage the sector has with climate change, and the importance of maintaining and increasing agricultural supply, the TNC is aimed at benefiting agricultural planning processes. The Project component 2 will identify priority adaptation measures for the sector to strengthen its resilience to climate change impacts, and to integrate climate change into its development strategies and sector programs.

20.	Waste. Emissions from the waste sector include contributions from Municipal Solid Waste (MSW), and organic waste from urban and industrial wastewater plants. According to the National Institute of Statistics and Censuses (INDEC) in 2004, in 2001 the population of Argentina rose to 36,260,130 inhabitants, 94% living in 273 cities with more than 20,000 inhabitants. In most of these cities, MSWis discharged in open dumps or non controlled landfills, and the daily MSW production per capita is 0.7 kg. In 2000, only 14 (5%) of these cities had controlled landfills, representing 43.6% of the total urban population, with a final disposal of 7,084,000 Mg of MSW, approximately 76.5% of the total. Waste composition varies widely according to its relationship with economic status of the population.

21.	According to private studies, the waste sector increased its emissions during 1990–2005 by 109.95%, almost 4.75% annually. This caused a strong relative increase in the contribution of the sector from 4.33% at the beginning of the period to 6.79% in 2002, when the economic crisis affected the emissions due to other sectors.

22.	Given the strong linkage the sector has with climate change, and the importance of enhancing its services, the TNC is aimed at benefiting its planning. The Project component 1 seeks to address this issue by financing a set of studies to identify or to strengthen priority mitigation measures in the sector.

23.	Forestry. Land Use, Land-Use Change and Forestry (LULUCF) sector inventory of GHG is included in the First and SNC of the GOA to the UNFCCC. These reports use the IPCC guidelines (2003) methodology and comprise four subsectors: changes in biomass in forests and other woody biomass, conversion of forests and grasslands, abandonment of managed lands and changes of soil carbon content due to land use changes. Considering the first three subsectors, forestry plantations and abandoning of cultivated lands are the main sinks of atmospheric carbon.

24.	According to the data presented by SNC for 2000, the estimation on the total balance of LULUCF sector in Argentina has caused a net capture of atmospheric CO2 of 43,941 Gg CO2 per year. The subsectors results are shown in the following table:

| LULUCF sub-sector in Gg | CO2 capture | CO2 emissions |
| --- | --- | --- |
| Changes in forest and other woody biomass | -15.750 |  |
| Forest and grassland conversion |  | 9.249 |
| Abandonment of managed lands | -48.747 |  |
| Changes of soil carbon content |  | 11.308 |
| LULUCF capture and emissions | -64.498 | 20.557 |
| Net Land use change and forestry (LU-CF) | -43,941 |  |

25.	Related to trends of emissions and sequestration between 1990 and 2000, CO2 removal due to changes in forest and other woody biomass was lower in 1990 (-12462 Gg CO2), and then reach -15.750 Gg CO2 (1994 and 2000) and -15.209 Gg CO2 (1997). Emissions from conversion of land use increased during the period 1990–1997, from 8,642 Gg CO2 to 15,357 Gg CO2. Later in 2000, it resulted in 9,250 Gg CO2, similar to 1994; both years experienced similar level of deforestation: 269,000 and 267,000 ha in 1994 and 2000 respectively. Most of the emissions due to land conversion in 1997 were associated with forest clearances (335,000 ha). CO2 sequestration on abandoned lands increased during the period 1990–2000. The assumptions of the SNC are that there is abandoned managed land, 3,473,000; 5,600,000; 6,100,000; and 10,700,000 ha in 1990, 1994, 1997 and 2000 respectively. The high participation of this subsector in the CO2 capture is important when comparing the CO2 sequestration due to abandoned lands in the considered periods (-11,514; -29,079; -30,414; and -48,747 Gg CO2) with the increasing trend of total net removal by LULUCF as follow:

| Gg CO2/Year | 1990 | 1994 | 1997 | 2000 |
| --- | --- | --- | --- | --- |
| LULUCF | -15 | -34 | -29 | -43 |

26.	In any case, there are some important inconsistencies in those data. Some of the assumptions, such as the amount of hectares assigned in abandoned managed lands category, and the biomass/ha in different ecosystems, among others, are issues that probably need to be adjusted. The overall LULUCF results of the SNC are striking and contrasting in trends with a country where the deforestation rate is several fold of the global medium rate.

27.	A subsequent study was conducted (Gasparri et al. 2008) that allowed to clarify some of the inconsistencies and provided additional data to the SNC. The study estimated the emissions from deforestation in Northern Argentine forests. Between 1900 and 2005, approximately 30% of the forests were deforested, leading to carbon emissions of 0.945 Pg C. Estimated average annual carbon emissions between 1996 and 2005, mostly from deforestation of the Chaco dry forests, were 20,875 Gg C y-1.

28.	In contrast, National Inventory of Greenhouse Gases indicates emissions from biomass elimination of 2,527 Gg C y-1. The estimate was based on unrealistic values of Above Ground Biomass (AGB) per hectare, particularly for Chaco Forest (15-20 Mg ha-1, which is 17% of the AGB used in the new study) but also for Yungas Forest (80 Mg ha-1 that is 39% of the AGB) and Atlantic Forest (177 Mg ha-1 that is 67% of the AGB) and neglects belowground biomass.

29.	This difference between this studies and National GHG inventory that makes the net balance shift in the Argentinean silviculture and land-use sector, from a carbon sink to a source. Carbon emissions for 2000 were 20,271 Gg C y-1 showing that in Northern Argentina, deforestation is a major source of carbon at country level.

30.	As part of emerging readiness strategy for REDD+ in the country, in April 2010 the SAyDS submitted to the FCPFWorld Bank the Readiness Plan Proposal (R-PP), under which the country is designing a work program for defining a reference scenario for REDD+. As the first step of this program, a compressive diagnosis document containing data availability and gaps regarding emissions and removals in the forestry sector, was submitted inside the R-PP document.

31.	In particular, regarding the synergies of the FCPF and the TNC processes: (i) the TNC will review and update the inventories for the sector applying the IPCC LULUCF Good Practice Guidance (GPG); and (ii) the FCPF will take into account the forestry inventory in its work program for defining a reference scenario for REDD+, defining one consistent source of information and an update and review process as necessary.

32.	Given the strong linkage the sector has with climate change, and the importance it has and will have in carbon emissions and removals, the TNC is aimed at benefiting its planning. The Project component 1 will address this issue by financing a set of studies to identify priority mitigation measures in the sector, and link them with other on-going initiatives such as the World Bank FCPF and other REDD strategies related with Argentina.

33.	Transport. In Argentina, cars are the most commonly used mode of transport. Railway traffic represents less than 20% of the agricultural freight. Fluvial and maritime transport represents yet smaller fraction, but it is in expansion. A particular characteristic associated with the transport-related GHG emissions in Argentina is that a high percentage of cars use compressed natural gas. Passenger transport, according to private studies, show positive trends with variations between different transport modes: the number of passengers transported by land –sub railways, railways and buses– has increased during last years. Respect to aviation, the number of transported passengers showed contradictory trends depending on the kind of flights, as international service has increased in terms of both national and foreign flights, but domestic decreased. Railway travel has increased in absolute terms, but there are rail branches with decreasing passenger numbers.

34.	In Argentina, over 89% of the population lives in urban areas in centers of 2,000 or more inhabitants. Despite the high degree of urbanization, Argentina is still experiencing significant growth rates of urban population. Between 1980 and 1991, urban areas grew from 23.2 million to 28.4 million inhabitants, 1.9% per year. Today, 13 million people, almost 38% of the total population, are concentrated in the Metropolitan Area of Buenos Aires (AMBA). Population densities are high with nearly 14,800 people per km2 in the city of Buenos Aires, which population of 3 millions growing at a rate of 0.7% annually. Yet some of the suburban municipalities are growing at a ten times faster rate. Sound urban transport management is critical for meeting the growing transport needs of the fast growing and sprawling regions of Argentina.

35.	The impacts of increasing urban population, growing motorization, suburbanization, inadequate transport and traffic management, worsening congestion, and air pollution have already been evident in many metropolitan areas and medium size cities in Argentina. Bus transport is deteriorating, and suburban rail services have become overcrowded, unreliable and subject to growing criticism regarding traffic safety and quality of service. Traffic safety and personal security have become serious issues that impact cities’ transport systems. Because of these factors, and the 2001 economic crisis and subsequent reduction in investment, public transport has lost around 50% of its ridership since the early 90s, aggravating the problems of congestion and pollution in some areas, and those of poor access and mobility in others, especially in zones marked by poverty.

36.	As the proposed Project demonstrates, mitigation of transport-related GHG emissions is important aspect of integrating environmental concerns into sectoral policies, programs, and investments. By cross-sectoral and participative work, significant GHG ERs can be achieved in the long-run, while also ensuring meeting of other development goals.

37.	Natural Resources Conservation and Ecosystem Services. The temperature increase expected to be observed in the next decades will affect ecosystems in several regions of Argentina. It is probable that mountain systems are affected, and it is expected that wetlands and other ecosystems at the north of Argentina will suffer damage due to hydrological stress. Except of some publications suggesting territorial expansions of several species, there are no reports linking evolution of ecological systems to climate scenarios during the next decades. The exception is a recent thesis of University of Buenos Aires (Castillo Marín, 2006) that demonstrates that climate changes are expected to increase areas covered by woody vegetation, and that the most significant changes were to occur in the Arid Chaco.

38.	Given the strong linkage this sector has with climate change, and the importance nature conservation and provision of environmental services have in terms of climate resiliency, the TNC aims at benefiting its planning especially in terms of the analysis focusing on ecoregions.

39.	Health. Private and union insurances in Argentina have grown in number since 2002, achieving nearly 15 million in 2004. The higher proportion corresponds to the union insurances, which represent almost 70% of the total. However, 48% of the Argentine population does not have access to social coverage or medical plans. The lowest coverage (58.7%) corresponds to children between 0 to 4 years, the general coverage portion increasing as the age of population increases. The lack of medical assistance is partially covered by the GOA by providing a free service of wide coverage through the public hospitals. According to information published by INDEC in the Permanent Survey of Households, 84% of households have potable water provision systems with a high proportion (86%) with access to the public water supply. In contrast, only 47% of households access a safe discharge system for domestic effluents.

40.	Climate change is expanding the distribution of vectors of infectious tropical diseases such as dengue and the snail that disseminates the esquistosomiasis along the Paraná River. Until recently, the snails in Argentina are free of this disease, but the threat is approaching in the Paraná River at the north of Itaipú. Malaria is other disease that is expanding closer to Argentina from Paraguay.

41.	Given the strong linkage the health sector has with climate change, and the remarkable risk climate change is imposing to current health care systems, the TNC aims at benefiting health care planning by analyzing the vulnerability of different populations to climate a change impacts.

42.	Tourism. Tourism is the third highest external income generating sector of Argentina after vegetable oils and oil. The main destination sites are Buenos Aires, Iguazú Falls, Patagonia glaciers, Bariloche and Cuyo. In 2005, income from foreign tourism represented 8.2% of the exportations of the total goods and services in Argentina, with a value of $US3.819 million. During the last years, tourism has shown continuous expansion and contributed to job creation.

43.	Climate change will affect beaches and coastal urban areas due to increasing erosion and flooding. According to the projected climate scenarios, beaches that are limited by steeps, sand dunes or forests can gradually lose their extension, and eventually disappear causing a serious damage to tourism at the zone. A progressive trend of extending summer climate conditions during the first stage of the autumn (Bejarán and Barros, 1998) was observed during the last decades throughout Argentina. Moreover, the circulation conditions in the low layers of the atmosphere have shown a trend to a prevalence of summer characteristics on winter ones in spring and autumn. Projections of climate models show a similar trend for the rest of the century (Di Luca et al., 2006), furthering the projected temperature increase shown by all models and climate scenarios, which by themselves will contribute to extend the warm period of the year. The higher summer temperatures and extension of the warm period in the maritime coasts will contribute to increasing internal tourism to the beaches. Until now, the biggest tourist attraction of Patagonia, the Perito Moreno glacier, has not shown retrocession signals. Overall, it is difficult to estimate the reaction of the tourism demand caused by possible lost of these natural marvels.

44.	Taken the above described factors, the TNC aims at benefiting planning of the tourism sector. The Project will identify the vulnerability of the sector to climate change conditions, as well as related economic impacts at sub-national level.

45.	Urban areas. In urban areas of Argentina, various extreme events of precipitation have occurred since the beginning of the century with severe economical damage. Big areas were flooded in 2001 in the Pampa Region in the southern Salado Basin, and almost 2 million ha in Buenos Aires. A maximum historic record of precipitation in the city of Buenos Aires triggered collapse of urban functions and caused numerous victims (Cañada de Gómez, November 2000, Santa Fe city due to Salado del Norte swelling in May 2003). In 2006, several extreme precipitation events along the country were observed with torrents, flooding and sliding in the provinces of Chaco and Formosa (April and May), and in winter extended snowy surfaces in Neuquén and Tierra del Fuego affected by  unusual warming. The results of these events included production of freshets (riadas) that increased water volumes and triggered severe damage.

46.	Heat waves and urban warming cause health problems among the population of the big cities, and increase the electricity demand for refrigeration. Heat waves could become more recurrent and intense due to the air flow from the north (Rusticucci et al, 2003), where the projected warming is higher causing entrance of warmer air masses. In this respect, the northern region of Argentina will be the most affected, as well as the big urban areas in the centre of the country such as Córdoba, Rosario, Mendoza, and Buenos Aires. Vulnerability to erosion will be increased by urban expansion on coastal zones, which itself accelerates land degradation.

47.	The TNC will assess the vulnerability of Argentine cities to climate change, and review current climate related adaptation planning and management tools.

48.	Water Resources. An increase in water stress in the north and part of the west of the country, retrocession of snow precipitation in the Andes, crisis of water provision in Mendoza and San Juan, a decrease of the hydro-electric generation at Comahue, and a continuous retrocession of glaciers are expected phenomenon due to climate change.

49.	Glacier retreat is well documented through photos and on site research in the Continental South Ice that Argentina shares with Chile, where only one of the fifty glaciers is growing, one other (Perito Moreno) is in equilibrium, and 48 are in retreat. This phenomenon is also observed in Cuyo, and both cases are in accordance with the increasing level of zero grade isotherm. The increasing risk of water deficit in the Andean Piedemonte Oasis in the Cuyo region is evident: the negative trends observed since 1980 show an average decrease of 50–60% in the river flow until 2000. The Cuyo’s river hydrogram is changing not only by lower absolute flows and higher relative flows in winter and spring due to the increase of winter temperatures that raises the height of the zero grade isotherms and contributes to the melting of snow. At the north and centre of the country, due to higher temperatures, evaporation will increase but no major changes in precipitation are expected.

50.	Given the strong linkage this sector has with climate change, the TNC will assess climate change impacts on watersheds, especially in the Northern Argentina.

51.	Fisheries. Argentine fisheries produce approximately 1.2 million tons annually, mainly hake and squid. The production is concentrated in Buenos Aires and Patagonia. Fishing in rivers and lakes only represents 2% of the total production due to, among other reasons, water pollution.

52.	Along the coast there are concentrations of industries, business, ports, oil extraction, and tourist and recreational activities. Continuous expansion of these activities makes the coastal zone a dynamic area of the country. Climate change could affect the coastal zone through increasing ocean temperatures, changes in the marine currents circulation, and average sea level rise. By far, scientific information on sea level rise has only been published in average terms.

53.	The TNC will study impacts of climate change on marine and continental fishing resources.

54.	Employment. In 2006, according to the statistics of the Ministry of Labor (Encuesta de Indicadores Laborales), employment presented 48 months of continuous recovery: from the second quarter of 2002, approximately 3.190 million workers were included in the labor market. All sectors showed employment growth, and especially manufacturing industry, retail, services and construction. An adoption of mitigation measures in different sectors could have a direct impact in quality and quantity of employment opportunities.

55.	The TNC will assess linkages between impacts of climate change and related policy developments, including changes related with technology development and transfer, and employment patterns.

## Government policies and strategies

56.	A set of sectoral programs currently under development in the institutional framework of different Secretariats are in line with the goals of this Project. In particular, the Secretariats of Energy and the Secretariat of Environment and Sustainable Development (SAyDS), and the Ministry of Agriculture, amongst others, are promoting different national programs that provide synergy potential with the objectives of the TNC.

57.	The Ministry of Agriculture, Livestock and Fisheries (MAGyP) is promoting, since 2004, production of biofuels and bioethanol, emphasizing production and use of vegetable oils and animal fats for biofuels, and sugar cane, corn and sorghum for bioethanol. It also encourages development of sustainable production systems in degraded areas, promoting forestry practices and improvement of infrastructure of agricultural services in order to increase competitiveness, exportations and employment.

58.	The Secretariat of Energy promotes and encourages use of renewable energy sources and rational use of electricity through incentives to consumption reductions, as well as developing methodologies to enhance energy efficiency in buildings, and proper technologies for diverse regions of the country. It further promotes substitution of natural gas and conventional sources of electricity production for different applications, as well as auto-generation of electricity, with the aim of achieving an 8% contribution of renewable energy sources of the national electricity consumption in a period of 10 years. The Secretariat also stimulates development of technology, production, use and applications of hydrogen as fuel and energy vector.

59.	The Secretariat of Environment and Sustainable Development (SAyDS) has focused in sustainable development of PyMEs through soft credits to optimize and convert processes for achieving improvements in environmental performance. It is also the legal authority for determining minimal requirements on environmental protection in order to enhance, restore, conserve, develop and sustainably manage native forests and related environmental services. It further sets up sectoral priorities for activities prone to major environmental impacts, namely industries such as paper, sugar, citruses, oil, chemical, metal refinement, meat processing and tannery. The SAyDS implemented integral solutions for national-level solid waste management, and offers technical and financial assistance for conservation projects and sustainable development, promoting increase of forested areas, and thus helping rural communities to avoid uprooting.

60.	Other Governmental Agencies, such as the Secretariat of Public Works, the Ministry of Federal Planning, Public Investment and Services, the National Water Institute, and the Provincial Directorate of Public Sanitation and Hydraulic Works have implemented measures contributing to climate change mitigation and adaptation by reinforcing infrastructure and repairing zones devastated or degraded by climatic events.

61.	A table in Annex 17 details specific programs and policy strategies, related with the climate change agenda, which are currently under development by Argentine Governmental Agencies.

THIRD NATIONAL COMMUNICATION TO THE UNITED NATIONS FRAMEWORK CONVENTION ON CLIMATE CHANGE

Annex 2: Major Related Projects Financed by the Bank and/or Other Agencies

- The Bank has a significant environmental portfolio of climate-related interventions in Argentina, mostly related to environmental management. These have been summarized in the following table, together with projects financed by other agencies. In both cases, this annex details the coordination opportunities identified for each proposed or ongoing project in particular.

- Coordination opportunities will be identified and promoted jointly by the Government and the Bank. The PIU will be in charge of contacts with other projects. Coordination will involve a range of activities including tehnical meetings, access to information and other complementarities. Linking to this existing portfolio and laying foundations for future portfolio will be a useful function for the Project. On the mitigation side, the PERMER, energy efficiency, landfill/methane, and transport projects cover the bases well. The Sustainable Natural Resources Management, Urban Flood Prevention, and Rural Corridors projects provide a sound foundation for future adaptation work. As the analysis is undertaken in both adaptation and mitigation sub-disciplines, the GoA will be able to develop more ideas about where climate responses are needed and what projects might meet these needs. This Project will lead to thoughtful and timely responses to programming opportunities in the future.

- Conclusions and recommendations from the TNC could be reflected in new tasks. The Bank Sustainable Industrial Development Project will count with mitigation options to reduce the carbon footprint of the sector. In terms of adaptation, the Rural Corridors will count with information on adaptation under an ecoregional scale.

| Sector Issue | Project Name | Status | Implementation | Linkage and coordination with the TNC Project |
| --- | --- | --- | --- | --- |
| Transport, structural planning, infrastructure, modal integration | Loan No. 77940: Metropolitan Areas Urban Transport Project | Not effective yet | N.A. | This project will offer a platform to implement mitigation options proposed by TNC for the transport sector (air quality, change in transport modes, etc.). |
| Climate change, GHG ERs associated with transport, sustainable urban transport | GEF TF093048:AR-Sustainable Transport and Air Quality Program | Not effective yet | N.A. | Outputs of this project will contribute to strengthen mitigation actions proposed in TNC in transport sector with concrete examples related to air quality. |
| Agricultural productivity, capacity building, agribusiness systems | Loan No.75970: Second Provincial Agricultural Development Project | Ongoing | Moderately satisfactory | Results of this project will contribute to achieve emissions indicators and further understanding of feasibility of mitigation actions proposed for the agricultural sector in the TNC. Provincial Agricultural Services Program (PROSAP) could promote integration of pilot activities of mitigation measures proposed in the TNC. |
| Development of the Argentina Energy Efficiency Fund, pipeline of projects, efficient lighting, capacity building for project management | GEF TF No. 92377: Energy Efficiency Project | Ongoing | Satisfactory | Common activities will be jointly coordinated, given the strong linkage between this project and the TNC. |
| Biodiversity, conservation, institutionalizing safeguards for forestry, promoting private forestry, upgrading park management capacity | Loan No. 75200: AR: Sustainable Natural Resources Management Project (formerly Sustainable Forestry Development) | Ongoing | Satisfactory | This project sets up a proper framework to develop proposed mitigation options for forestry sector by the TNC (component 1, subcomponent 2). |
| Solid waste management, GHG mitigation, air quality, carbon finance possibilities | GEF TF No.90822: Salta Landfill Gas Capture Project | Ongoing | Satisfactory | This project contributes with a concrete example to be considered when assessing feasibility of achieving mitigation activities in waste sector proposed by the TNC. |
| Biodiversity, forestry practices, ecosystem services | GEF TF No. 90118: Biodiversity Conservation in Productive Forestry Landscapes Project | Ongoing | Moderately satisfactory | Activities of this project will create a framework to strengthen capacity building for mitigation and adaptation activities proposed for forestry sector by the TNC (component 1, subcomponent 2 and component 3). |
| Vulnerability, security of economic assets and persons, housing program, infrastructure, mitigation of flood risk | Loan No. 73620: Urban Flood Prevention and Drainage Project | Ongoing | Satisfactory | Some of the adaptation systems promoted through this project could be identified for the TNC to assess their effects and promote derived actions. |
| Solid waste management, GHG mitigation, technical assistance, public health, infrastructure, legal issues, recycling and waste minimization policies | Loan No. 73620: National Urban Waste Management Project | Ongoing | Satisfactory | This project will provide a clear demand of methane projects and will contribute to develop mitigation actions proposed in TNC. |
| MSW management improvement, carbon finance, community development | GEF TF No.54470: Olavarría Methane Capture Project | Ongoing | Satisfactory | This project contributes with a concrete example to be considered when assessing the feasibility of achieving mitigation activities in the waste sector proposed by the TNC. |
| Renewable energy supply, sustainable business in rural areas, reform of the electricity sector, expansion of private participation | GEF TF No. 20548: Renewable Energy in the Rural Market Project (PERMER) | Ongoing | Satisfactory | The experience achieved through this project in identification of technologies for rural areas could be intensified and expanded through the TNC, as it will propose mitigation actions in the energy sector related with renewable energy. |
| Biodiversity, protection of bio-carbon assets, development of strategy for eco-system based adaptation measures to climate change | GEF Rural Corridors and Biodiversity Project | Proposed | - | This project will provide an adaptation experience through rural corridors that would complement the TNC. The TNC could contribute to the promotion and implementation of new practices. |
| Improvement of the environmental compliance of medium and small enterprises, increasing competitiveness | Sustainable Industrial Development Project | Proposed | - | This project provides a tool that the TNC could develop to higher levels and synergize in order to implement mitigation options in the industrial sector. |
| Increased understanding of climate change related vulnerability of agriculture in the Latin America and the Caribbean region | Climate Change and Agricultural Vulnerability across Mega-environments in Latin America | Closed | - | This project studied the scope of climate change related vulnerability of agriculture in LAC; one of its identified mega-environments being favorable high-potential areas or "bread baskets" as found in Argentina. Vulnerability was studied in terms of agricultural productivity, livelihoods of rural households, natural resources and environmental quality to identify suitable adaptation strategies, e.g. research and extension systems and water management for each mega-environment. Related TNC studies shall contemplate these results.. |

Related Projects Financed by other Agencies

Most of the projects mentioned in the table below are just under proposal stage. However, it is probable that they would provide (i) opportunities to coordinate information and activities, and in the best scenario, (ii) timely results for direct benefit of the Project.

| National Projects |  |  |  |
| --- | --- | --- | --- |
| GEF ID | Project Name | Focal Area | Relation with TNC |
| 3862 | Strengthening Fisheries Governance to Protect Freshwater and Wetland Biodiversity (proposed, UNDP) | Biodiversity | Information provided through this project will be an input for vulnerability and CC impact studies on fisheries activities proposed in the TNC. |
| 3910 | Inter-jurisdictional System of Coastal-Marine Protected Areas (ISCMPA) (proposed, UNDP) | Biodiversity | Activities developed under this project constitute a proper framework for developing of specific studies of vulnerability of marine coastal regions and environmental services proposed in the TNC. |
| 124 | Renewable Energy in Rural Markets Project (ongoing, WB) | Climate Change | The experience achieved through this project in identification of technologies in rural areas could be intensified and expanded through the TNC as proposed mitigation actions in the energy sector on renewable energy. |
| 2625 | Energy Efficiency Project (ongoing, WB) | Climate Change | Capacity building acquired through this project will help to achieve mitigation actions in energy sector proposed in the TNC. Common activities will be jointly coordinated. |
| 2379 | Sustainable Management of Arid and Semi-arid Ecosystems to Combat Desertification in Patagonia (resubmission, UNDP) | Land Degradation | This project will contribute to remove barriers that prevent the adoption of sustainable land use management that the TNC could capitalize for identifying adaptation options and assess environmental services of this region. |
| 3623 | Establishment of Incentives for the Conservation of Ecosystem Services of Global Significance (proposed, UNEP) | Multi Focal Area | Expected outputs of this project could be recognized by the TNC to go further vulnerability studies and studies on climate change impacts on specific ecosystems. |

THIRD NATIONAL COMMUNICATION TO THE UNITED NATIONS FRAMEWORK CONVENTION ON CLIMATE CHANGE

Annex 3: Results Framework and Monitoring

| PDO | Project Outcome Indicators | Use of Project Outcome Information |
| --- | --- | --- |
| The PDO is to strengthen the information base and institutional capacity of the key organizations, members of the Project Steering Committee, to integrate climate change priorities into development strategies and relevant sector programs of the Argentine Republic by providing financial and technical support to prepare its TNCto the UNFCCC. | 1. Climate change mitigation: Number of studies available to inform different institutions and sectors about feasible mitigation P&M and their potential prioritization to facilitate decision making 2. Climate change adapation: Number of studies available to inform different institutions and sectors about feasible adaptation P&M and their potential prioritization to facilitate decision making 3. Capacity building: % of targeted institutions with improved capacity to take proposed mitigation and adaptation P&M forward, and % of targeted stakeholder groups that express increased awareness on climate change concerns | Project outcome information will be used to evaluate the overall impact of the conducted studies, training and information dissemination on climate change in the national mitigation and adaptation agenda. |
| Intermediate Outcomes | Intermediate Outcome Indicators | Use of Intermediate Outcome Monitoring |
| Component 1: Harnessing National Potential for Climate Change Mitigation Feasible proposals for P&M for climate change mitigation in targeted sectors (energy and transport, waste, agriculture and forestry) prepared, including design of regulatory frameworks, implementation strategies, and institutional arrangements addressing identified barriers to enforce the P&M. | 1. Number of processes aimed at strengthening or generating mitigation P&M triggered by information and awareness generated during Project implementation 2. The estimated GHG intensity of the proposed P&M for mitigation | Intermediate outcome monitoring will be used to assess usefulness of the TNC studies and other outputs aimed at preparing and feeding into feasible proposals for mitigation and adaptation P&M and their implementation. |
| Component 2: Strengthening National Adaptation Agenda Feasible proposals for P&M for climate change adaptation in targeted sectors (ecoregions and ecosystem services, agriculture, health, tourism, urban planning, energy, water resources management and fisheries) prepared, including design of regulatory frameworks, implementation strategies, and institutional arrangements addressing identified barriers to enforce P&M. | 1. Number of processes aimed at vulnerability reduction measures and adaptation policies triggered by information and awareness generated along the Project implementation 2. The estimated total cost-benefit of the proposed adaptation P&M |  |
| Component 3: Instititonal Strengthening, capacity Building, and Information Management Wide and instrumental involvement of relevant stakeholder groups achieved along the TNC activities. | % of targeted stakeholder groups that express increased awareness on climate change concerns |  |
| Component 4: Project Management Project management strengthened through close cross-cutting coordination among relevant sectors and institutions. | % of the planned studies initiated and delivered in a timely fashion |  |

Arrangements for Results Monitoring

|  |  | Target Values |  | Data Collection and Reporting |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Project Outcome Indicators | Baseline | YR1 | YR2 | Frequency and Reports | Data Collection Instruments | Responsibility for Data Collection |
| 1. Climate change mitigation: Number of studies available to inform different institutions and sectors about feasible mitigation policies and measures and their potential prioritization to facilitate decision making | On-going related sectoral activities and programs | Solid documentation of the magnitude and trends of GHG emissions from different emitting sectors in place | Potential mitigation actions identified for the 5 priority sectors; and 11 studies available to inform different institutions and sectors about feasible mitigation P&M and their potential prioritization to facilitate decision making | Quarterly and Annual Project Implementation Reports (PIRs) | PIRs and supervision mission reports | PIU |
| 2. Climate change adaptation: Number of studies available to inform different institutions and sectors about feasible adaptation policies and measures and their potential prioritization to facilitate decision making | On-going related sectoral activities and programs | Solid documentation of climate change impacts on eco-regions and the targeted sectors (environmental services, health, tourism, agriculture, energy, urban areas, fisheries, water resource management, and employment) in place | Potential adaptation actions identified for the 9 priority sectors; and 9 studies available to inform different institutions and sectors about feasible adaptation P&M and their potential prioritization to facilitate decision making | Quarterly and Annual PIRs | PIRs and supervision mission reports | PIU |
| 3. Capacity building: % of targeted institutions with improved capacity to take proposed mitigation and adaptation policies and measures forward, and % of targeted stakeholder groups that express increased awareness on climate change concerns | The survey used in conjunction with each TNC event will include questions on respondents’ capacity to take climate change considerations into account in their work prior to their involvement in the TNC activities | A thorough communication strategy developed tailor-made to different stakeholder groups | At least satisfactory percentage of the survey responses collected at the TNC events confirms increased perception of capacity to understand climate change considerations and address them by concrete measures | Quarterly and Annual PIRs | Paper surveys collected in conjunction with each TNC event; Steering and Advisory Committee meetings; PIRs and supervision mission reports | PIU |
| Intermediate Outcome Indicators |  |  |  |  |  |  |
| Component 1: Harnessing National Potential for Climate Change Mitigation |  |  |  |  |  |  |
| 1. Number of processes aimed at strengthening or generating mitigation policies triggered by information and awareness generated along the Project implementation | There is a number of ongoing mitigation related initiatives | Targeted sectors have access to mitigation-related information (e.g. updated and new GHG emission inventories). | Targeted sectors have access to feasible options, P&M for climate change mitigation. | Quarterly and Annual PIRs and supervision mission reports | Steering and Advisory Committee meetings; technical reports generated under component 1; PIRs and supervision mission reports | PIU |
| 2. The estimated GHG intensity of the proposed P&M for mitigation | To be generated through related TNC studies under component 1 | All the targeted sectors (energy and transport, waste, agriculture and forestry) have access to updated and new GHG emission inventories, which identify, inter alia, the emission intensity of each sector. | The proposed mitigation options identify potential reduction of GHG intensity. | Quarterly and Annual PIRs | Technical reports generated under the component 1; PIRs and supervision mission reports | PIU |
| Component 2: Strengthening the National Adaptation Agenda |  |  |  |  |  |  |
| 1. Number of processes aimed at vulnerability reduction measures and adaptation policies triggered by information and awareness generated along the Project implementation | There are some ongoing vulnerability reduction and adaptation related initiatives | Targeted sectors have access to new adaptation-related information: Regional Circulation Models (RCMs); climate change scenarios generated through various RCMs; and studies on impacts of past climate variability and change in the country. | Planned sectoral impact and vulnerability studies are ready and the targeted sectors have access to feasible options, P&M for climate change adaptation. | Quarterly and Annual PIRs | Steering and Advisory Committee meetings; technical reports generated under the component 2; PIRs and supervision mission reports | PIU |
| 2. The estimated total losses and benefits of the proposed adaptation options and P&M | To be extracted, if feasible, based on ongoing initiatives to be identified along the studies under component 2 | Technical reports with economic, social and environmental impact assessments of the implementation of the designed P&M are under preparation based on the TNC socio-economic baseline scenario. | The proposed adaptation P&M present an attractive cost-benefit ratio. | Quarterly and Annual PIRs | Technical reports generated under the component 2; PIRs and supervision mission reports | PIU |
| Component 3: Institutional Strengthening, Capacity Building, and Information Management |  |  |  |  |  |  |
| % of targeted stakeholder groups that express increased awareness on climate change concerns | The survey used in conjunction with each TNC event will include questions on the general awareness level of the respondents prior to their involvement with the TNC | At least satisfactory percentage of the survey responses collected at the TNC events confirms increased understanding on climate change. | 1. At least satisfactory percentage of the survey responses collected at the TNC events confirms increased understanding on climate change. 2. At least satisfactory amount of the registered teachers have approved the designed distance course on climate change. | Quarterly and Annual Project Implementation Reports (PIRs) | Paper surveys collected in conjunction with each TNC event; PIRs and supervision mission reports | PIU |
| Component 4: Project Management |  |  |  |  |  |  |
| % of the planned studies initiated and delivered in a timely fashion | None | All the scheduled studies are initiated in a timely fashion. | All the planned studies are delivered in a timely fashion. | Quarterly and Annual PIRs | PIRs and supervision mission reports | PIU |

Arrangements for Results Monitoring

Data Collection

- Project activities will be reported by the PIU. CCD will be responsible for compiling data and reporting to the Steering Committee (SC), and the DGTA further to the World Bank.

Semiannual Evaluations

- Semiannual discussions are planned to coincide with supervision missions to identify and discuss lessons learned during implementation with Project stakeholders and beneficiaries. The PIU will submit semiannual reports on lessons learned and plans for incorporating those lessons into future activities.

Mid Term Review

- The Bank’s supervision team, together with a team of external reviewers and key stakeholders, will conduct a midterm evaluation of the Project execution. It will be conducted no later than 12 months after the first disbursement. The external review will focus on: (i) progress in achieving Project outcomes; (ii) status of the institutional arrangements for Project implementation; and (iii) review of both the Project implementation plan and general Project operational manual. To prepare for the midterm review (MTR), the SC, together with the PIU, will compile a report containing the following information: (i) executive summary of the overall Project status; (ii) up-to-date description of the overall components’ development and indicators; (iii) detailed work plan for Project completion; and (iv) copies of SC meeting proceedings.

Final Evaluation

- A final evaluation will be conducted within 6 months after the Project has been completed. The key objectives of the final evaluation will be to: (i) assess attainment of the Project’s expected results; (ii) assess use of the Project results in designing a national climate change strategy and action plan; and (iii) assessing progress towards integrating climate change considerations into development strategies and relevant sector programs.

THIRD NATIONAL COMMUNICATION TO THE UNITED NATIONS FRAMEWORK CONVENTION ON CLIMATE CHANGE

Annex 4: Detailed Project Description

- The PDO is to strengthen the information base and institutional capacity of the key organizations, members of the Project Steering Committee, to integrate climate change priorities into development strategies and relevant sector programs of the Argentine Republic by providing financial and technical support to prepare its TNC (TNC) to the United Nations Framework Convention on Climate Change (UNFCCC).

- The TNC will lead to development of a National Climate Change Strategy especially for national level decision makers to achieve national development goals and show leadership in addressing climate change through voluntary action. The TNC also aims at benefitting decision makers at provincial and municipal levels as well as general public.

- The TNC will strengthen the information basis and institutional capacity of the GOA in designing sector P&M for climate change mitigation and adaptation, based on an updated emission inventory, further analysis of national mitigation potential, and vulnerability assessments, while fulfilling its obligations to the UNFCCC. The proposed Project would support integration of CC considerations into Argentina’s domestic sector strategies. The identified mitigation and adaptation actions would also include analysis of environmental, social and economic impacts of implementation of identified measures, as well as of possible synergies.

- Implementation of the Project outcomes by the country is expected to generate global environmental benefits through the reduction of GHG emission as a consequence of designing appropriate mitigation P&M as proposed under the Project. It would also benefit biodiversity and land conservation by reducing vulnerability of critical ecosystems through identified adaptation measures, and addressing land degradation based on detailed vulnerability assessments. In short term, the Project would enable the country to act proactively with the domestic climate change agenda, based on a national climate change strategy, to guide development in different sectors.

- The main objective, structure and components of the Project have been discussed with GOA representatives in detail, reaching a consensus during meetings organized with the Climate Change Directorate (CCD) of the Secretariat of Environment and Sustainable Development (SAyDS) since 2008. Initial meetings in 2008 and 2009 were held to promote involvement and capture preliminary ideas from other Governmental Agencies, scientific and technological institutions and non-governmental organizations for development of the Project Information Form, and the TNC. The Project structure is presented in the following graph:

- In the following Project description, the beginning of the first paragraph in cursive under each sub-component reflects the sub-component description in the Grant Agreement. Additionally, the deliverables of each sub-component are summarized in continuation.

Component 1: Harnessing National Potential for Climate Change Mitigation (GEF cost: USD 0.53 million, total: USD 0.67 million)

- The objective of this component is to update the country’s GHG emission inventory for each emitting sector, design tools and procedures to improve data collection and management, and assess and design potential mitigation P&M.

Sub-component 1: GHG Inventory and Development of Tools to Manage the GHG Emissions Database

- Upgrade and development of the Recipient’s national inventory of greenhouse gas emissions (GHG), including provision of support to strengthen the Recipient’s technical capacity for modeling, analyzing and projecting GHG emissions. Deliverables: New inventories based on the latest IPCC Guidelines for National Greenhouse Gas Inventories in accordance with available data and related UNFCCC definitions, and revision of the previous inventories (1994, 1996, and 2000); Inventories produced using other methodologies; New and reviewed emission factors; Carbon footprint of the main export products and by person; Emission indicators assigning responsibilities and response capacities; Mechanisms for public access to information; and Quality control and quality assurance procedures for the used information and data.

- Under this sub-component, the existing GHG emission inventories (1994, 1996, and 2000) will be updated, and new ones developed in accordance with available data and related UNFCCC definitions, and required technical capacities will be strengthened for modeling, analyzing and ing GHG emissions for each emitting sector. The updating will be based on most recent data from the relevant sectors and the latest IPCC Guidelines for National Greenhouse Gas Inventories will be used, as well as other methodologies such as adoption, as feasible, of the tier 3 approach to reduce uncertainty in the GHG estimates. Furthermore, previous GHG emission inventories will be reviewed in terms of understanding trends and drivers for changing emission patterns.

- The sub-component would support the following activities:

- Develop GHG emission inventory up to latest feasible year, including compilation, standardization and archiving of sector related GHG emission data; review previous inventories analyzing observed emission trends for each sector; and suggest how to systematize data gathering and management processes. Respect to the LULUCF sector in particular, the necessary stages will be evaluated in order to develop a systematic annual emission inventory, based on the second forestry inventory. The IPCC LULUCF Good Practice Guidance (GPG) will be adopted.

- Develop GHG emission inventory using different methodologies. Options to consider include: i) consumption based inventory starting from input-product matrices; ii) bottom-up approaches (full product cycle) for the agricultural, forestry and industry sectors. This activity would be fed by the following activity on emission factors; and iii) develop GHG emission inventories for each province.

- Elaborate and review emission factors (EFs), including: i) review of the EF database of the IPCC, and determine EF ranges for each sector; ii) compare EFs used in NCs of countries with similar emission patterns; iii) review local scientific literature with regard of new EFs; iv) analyze EFs that could serve as an indicator for measuring the impact of policy implementation on GHG emissions trend/path; v) study EFs that could be used for the estimation of the carbon footprint of persons or products.

- Based on results from (b) and (c) above, develop carbon footprint of main export products and by person. This activity will be based on the carbon calculator developed by the SAyDS to improve the formulas and include new sectors. The results will provide inputs for the activities conducted under the dissemination and communication component.

- Develop indicators to determine GHG emission patterns. This activity will elaborate emission indicators assigning responsibilities (e.g. historical emissions, emissions per capita, etc.) and response capacities.

- Establish mechanisms for public access to information;

- Establish quality control and quality assurance procedures for the used information and data;

- Strengthen capacity for developing emission inventories and analyzing generated data.

- By the end of the Project, an updated emission inventory will be available, providing a continuous basis for GHG emissions data by sector, location, as well as trends. Inventory managing tools will be in place, such as trained staff to develop and manage GHG emissions database.

Sub-component 2: Actions to Enhance Climate Change Mitigation

- Carrying out studies on mitigation potential in the Recipient’s main economic and GHG-emitting sectors, energy and transport, waste, agriculture, and forestry, with an aim at identifying priority mitigation measures. The supported studies will analyze the technical and economic aspects related to implementation of the identified mitigation actions in Argentina. Deliverables: Studies related with renewable energy; carbon capture and storage; bio-fuels and bio-mass; energy efficiency in public, residential and commercial buildings; mitigation options in the transport sector; labeling system for consumption and emissions of passenger and light duty vehicles; mitigation options in the industrial sector; mitigation actions in the waste/wastewater sector; mitigation options in the agricultural sector and a case study on mitigation actions in the sugar cane exploitation; and Assessment of mitigation potential of forestry sector.

- The objective of this component is to support mitigation potential studies in the main economic and GHG emitting sectors in Argentina in order to identify priority mitigation measures. The updated GHG inventories will guide this process by identifying detailed emission patterns and absolute emissions per emitting sector, emission intensity and emissions trends. The supported studies will analyze the technical, economic, social, environmental, financial and institutional (stakeholder) aspects required for implementation of the identified mitigation actions. Mitigation potential studies will focus on the sectors with the highest carbon footprint and a growing trend of emissions. This sub-component will build on previous assessments under the SNC, and consider encountered barriers that prevented previously identified mitigation measures from being implemented.

- Energy and Transport: The studies will analyze the mitigation potential of energy supply and demand. This activity will be coordinated with the adaptation studies under component 2 that will be looking at the impact of climate change on energy infrastructure and generation facilities:

- Renewable energy (RE): i) Identify development potential for renewable energies by region in a quantitative and qualitative manner; ii) Conduct technical and economic feasibility studies for integrating different RE technologies into the national interconnected grid; iii) Generate a map that allows identification of potential and barriers associated with development and use of renewable energies, for both integrated and isolated systems. The map would also support policy development in order to promote identified technologies in each region.

- Carbon capture and storage: Assess national potential for carbon capture and storage in geological formations of the country. The study will map potential geological sites considering proximity to CO2 sources, and analyze technical, economic, legal and environmental aspects of implementation of this technology.

- Bio-fuels and bio-mass: Study potential contribution of biomass and second and third generation biofuels to the primary energy supply, considering sustainability criteria, production cost, state of the art technologies, and applicability in Argentina.

- Energy efficiency in public, residential and commercial buildings: i) Assess technical, economic and regulatory aspects of mitigation options in buildings; ii) Evaluate potential for using RE in buildings as well as implementation barriers; iii) Review possibilities to adapt existing buildings with significant energy consumption in order to make them more energy efficient; iv) Examine technical and economic aspects of use of efficient heating devices (e.g. heat pumps) as well as district based heating systems; v) Design sustainable building construction plans considering modification of building codes.

- Mitigation options in the transport sector: i) Assess mitigation potential in long distance freight and passenger transport; ii) Evaluate mitigation potential of urban transport systems, including electrification of suburban trains. Both activities will analyze alternative transportation means, including multi-modal transport systems (e.g. by river in the case of freight transport, BRT for urban transport), estimate investment costs, barriers (technical, institutional, etc), and externalities.

- Labeling system for consumption and emissions of passenger and light duty vehicles: i) Elaborate labeling and certification system for consumption and emissions of passenger and light duty vehicles; ii) Test system by developing a pilot plan for most representative vehicles of each category.

- Mitigation options in the industrial sector: The objective is to develop a map  demonstrating the prevalent energy consumption patterns of the industrial sector: i) Generate energy consumption database with adequate data protection system as basis for development of EE policies for industrial sector; ii) Characterize industrial groups based on their energy consumption patterns, estimate GHG emissions of these groups, and identify mitigation measures and indicators (emissions/industry or product); iii) Assess potential for use of residual gases, cogeneration and industrial recycling; iv) Environmental accountability: impact of GHG emissions on the value of companies considering possible mitigation scenarios. This sub-activity will seek active participation of representatives from the industrial sector in order to guarantee adequate data provision, create relevant tools for industry sector, and at the same time protect the provided data.

- Waste: The supported studies will analyze mitigation options in the waste sector encompassing measures to reduce waste generation, treat generated waste in a sustainable manner, and reduce emissions caused by landfills.

- Mitigation actions in the waste/wastewater sector: i) Conduct technical and economic studies of mitigation actions based on standard cost per region and type of waste in order to determine its potential as energy resource; ii) Determine local emission factors disaggregating by type of waste; iii) Assess methane capture and energy generation potential and cost in landfills; iv) Develop mitigation studies for residential and industrial wastewater by province and municipality for the sectors proposed by the IPCC; v) Propose actions to improve data generation on a municipal and provincial level in order to enable systematized and transparent documentation.

- Agriculture: The studies will focus on identifying mitigation options in the agricultural sector, particularly enteric methane emissions from cattle in Argentina.

- Mitigation options in the agricultural sector: i) Determine the mitigation potential in the agricultural sector and identify key mitigation actions; ii) Assess technical and economical feasibility of key mitigation actions; iii) Identify main barriers for the implementation of these actions; iv) Evaluate direct seeding versus alternative agricultural practices and methods in relation to GHG emissions; v) Identify carbon footprint of main agricultural export products; vi) Characterize agricultural and livestock production systems estimating the GHG emissions associated with each one, and develop emission indicators (e.g. emissions per a planted ha or per produced ton).

- Case study: Mitigation actions in the sugar cane exploitation: i) Define geographic distribution of sugar cane waste by GIS; analyze its energy potential; and develop an inventory for agricultural soils by type of cultivation method; ii) Develop methodology to determine burnt sugar cane areas; and quantify emissions based on field data of burnt biomass with the help of data acquired through remote sensing techniques; iii) Establish baseline for burnt sugar cane waste (more than 80% of emissions in this category according to SNC); and define future strategy through implementation of monitoring and fire analysis system based on data acquired through remote sensing; iv) Generate cartography on periodic and spatial distribution of sugar cane fires on a departmental level for the northern part of the country.

- Forestry sector including afforestation, reforestation, deforestation and forest degradation:

- Assess mitigation potential of forestry sector for different regions of the country considering implementation of the national forestry law: i) Technical and economic aspects of mitigation actions in the forestry sector; ii) Assess reforestation and afforestation actions in semi-arid zones; iii) Design a fire prevention management plan; iv) Develop reforestation and afforestation strategies; v) Identify the forestry carbon footprint; vi) Identify measures to recuperate degraded forestry systems; vii) Evaluate potential compatibility between growth of forestry, agricultural and cattle sectors, and necessity to mitigate and to adapt in these sectors, including the development of indicators that connect agricultural activities with deforestation and associated emissions; viii) Disseminate the existing regional development opportunities within the framework of the UNFCCC; ix) Evaluate and propose actions that contribute to achievement of UNFCCC objectives; and x) Analyze potential use of “poda” waste in Patagonia`s forests and other relevant regions.

- As a result, development of mitigation measures with the highest or most feasible reduction potential is expected including identification of costs and benefits per measure.

Sub-component 3: Mitigation Policies and Measures (P&M)

- Enhancement of an enabling framework for the implementation of mitigation measures, including the design and delivery of a set of mitigation P&M aimed at integrating climate change into the Recipient’s development strategy and sector programs. This includes development of future GHG emission scenarios targeted at reducing emissions; analysis of the technical and economic, social, environmental, financial, and institutional, stakeholder-based aspects related with implementation of the identified mitigation actions in Argentina. The TNC aims at proposing P&M which would themselves be revenue-generating to cover at least a part of their implementation costs, and research and innovation will be provided on their possible financing sources. Further, possible synergy in terms of climate change adaptation will be targeted. Deliverables: Plausible P&M for mitigation of climate change, including design of regulatory frameworks, implementation strategies, and institutional arrangements; and Economic, social and environmental impact assessments of the implementation of the designed P&M on the socio-economic baseline scenario to be developed under sub-component 2.1.

- The objective of this component is to support the enhancement of an enabling framework for the implementation of mitigation measures, and to integrate climate change into development strategies and sectoral programs. Based on the GHG emission inventories, results of the mitigation potential studies, as well as sectorial development policies, and considering outcomes of the UNFCCC negotiations, this sub-component will support the development of future GHG emission scenarios, and identify and propose a set of P&M in order to reach these scenarios.

- As a part of these scenarios, this sub-component would also establish integrated energy scenarios up to 2020 and 2050 looking at different GHG ER regimes.

- To facilitate the implementation of the identified P&M, the Project will design (1) regulatory framework including evaluation of possible modifications to existing regulatory frameworks in the energy and transport sectors, (2) implementation strategies; (3) institutional arrangements; (4) strategies and courses of action to address identified barriers to enforce P&M laid out in the NCs.

- This component will also support the assessment of the economic, social and environmental impacts of implementation of the P&M based on a dynamic socio-economic baseline scenario developed under the Project.

- This component is expected to result in design of an agreement on supporting and integrated policies and implementation strategies. These would facilitate implementation of priority mitigation measures identified under sub-component 2, and strengthen their sustainability.

- The TNC aims at proposing P&M which would themselves be revenue-generating to cover at least a part of their implementation costs. Additionally, the TNC will provide research and innovation on possible financing sources for the identified mitigation P&M. Possible synergy in terms of climate change adaptation will also be targeted.

Component 2: Strengthening National Adaptation Agenda (GEF cost: USD 0.93 million, total: USD 1.16 million)

- The objective of this component is to assess the anticipated climate change impacts and the most vulnerable sectors and areas in Argentina, and to identify and design necessary priority adaptation actions, including estimation of their sector-wide costs, and to strengthen adaptive capacity and climate resilience, support enhancement of an enabling framework for implementation of adaptation measures, and integrate climate change into development strategies and sector programs.

Sub-component 1: Assessment of Impacts of and Vulnerability to Climate Change

- Production of current and planned socio-economic and climate change scenarios, targeted at identifying priority adaptation actions and expected impacts, costs and benefits relying on the state of the art climate models  and building upon the conclusions of the SNC and other assessments, as applicable. Deliverables: Study on characterization of current and planned socio-economic scenarios; evaluation of performance of General Circulation Models (GCMs) to represent current and past climate change scenarios in Argentina; Generation of Climate Change Scenarios through utilization of a variety of Regional Climate Models (RCMs); Study of impact of climate change and variability in the recent past, and its relation with frequency and intensity of heat waves and freezes; Study of impact of climate change and variability in the recent past, and its relation with frequency and intensity of extreme hydroclimatic events, including floods and drought and covering climate-change related fire propagation hazards; and Vulnerability and climate change impact studies on eco-regions and ecosystem services; agricultural sector; health sector; tourism; urban areas; energy sector; water resources management; and fisheries.

- The objective of this component is to further assess the anticipated climate change impacts and the most vulnerable sectors and areas in Argentina, relaying on the state of the art climate models as a basis to define priority adaptation measures and policies. The supported vulnerability and impact studies will build upon the results of the SNC and other assessments, and cover all eco-regions, sectors, and areas identified as particularly vulnerable.

Climate models for Scenario Development in Argentina:

- This activity will finance the following studies:

- Study on characterization of current and planned socio-economic scenarios.

- Evaluation of performance of General Circulation Models (GCMs) to represent current and past climate change scenarios in Argentina. The Regional Circulation Models (RCMs) need to match the outputs of the GCMs. The study will evaluate the performance of various GCMs in the region, counting on outputs from IPCC work and models such as Hadley Center, LMD (France) and Earth Simulator Model (Japan).

- Generation of Climate Change Scenarios through utilization of a variety of RCMs. The coarse resolution of GCMs does not allow for modeling local climate conditions, such as variations in areas prone to flooding, or climate conditions of coastal zones. RCMs allow for a better resolution of coastal and mountain zones, where a 50 km distance can entail a drastic change in climate. Combinations of RCMs can reduce uncertainty; the proposed combination would potentially include the following models: ETA, MRF, MCR, PRECIS, RECCM3, MM5 and WOLF. They can be used to study the impact of land use change in a regional climate.

- Study of impact of climate change and variability in the recent past, and its relation with frequency and intensity of heat waves and freezes. Climate variability refers to variations of mean climate conditions, while climate change can be identified by changes in its variability that persists during an extended period (decades or more). The frequency and intensity of extreme events, be they due to variability or climate change, need to be studied, since they both generate highly negative impacts. In addition, impacts of climate change and climate variability on the zero-degree isotherm in the Comahue region will be studied, given its significance for hydropower generation.

- Study of impact of climate change and variability in the recent past, and its relation with frequency and intensity of extreme hydroclimatic events, including floods and drought. This study will be similar in nature to the one detailed above. In addition, it will cover climate-change related fire propagation hazards.

Vulnerability and Climate Change Impact Studies:

- This activity will finance the following studies:

- Eco-regions and ecosystem services: The objective is to study vulnerability of ecosystems and ecosystem services provided by them. This activity will support the following tasks: i) Define key ecosystems for each eco-region; ii) Identify environmental services of these ecosystems that provide benefits to local and regional populations, such as watershed protection, and define which of these services need to be studied in more detail in view of the expected CC impacts; iii) Quantify economically these ecosystem services and evaluate how they will be affected by CC for different scenarios, including with and without adaptation and for different climate change scenarios; iv) Identify relevant biological climate change indicators for each eco-region; v) Create distribution models of species considering changing climatic variables; vi) Analyze the following variables: phenology, interaction between species, changes in populations, ecosystems and species with high rate of extinction; vii) Identify adaptation options including, among others, conservation and restoration activities for different climate change scenarios; viii) Study other indirect and associated impacts, such as progression of the agricultural frontier as of relevance for ecosystems.

- Agricultural sector: The objective is to identify vulnerability of the main productive activities to estimated climate change and climate variability and the social aspects related to these activities. The study will also consider implications of said impacts on the respective employment situation. This activity would place particular emphasis on the impact of climate change on small agricultural and livestock producers, including small rural farmers, family production and subsistence agriculture, as well as possible migrations due to CC impacts. Furthermore, the study will consider regions affected by decreased precipitation and glacier retreat, such as the Cuyo region. The following activities would be supported: i) identify particularly vulnerable regions and production systems to be studied. In this context, the climate change impacts on cattle raising activities of particular importance for regional economies and Argentina’s export sector will be identified and evaluated; ii) Study impacts of climate change , and particularly of the intensified occurrence of extreme weather events, such as droughts and frost, on agriculture and livestock as well as of hydrological changes with implications for agricultural activities (changes in precipitation patterns, glacier retreat, etc); iii) Assess climate change impacts on seeding and harvesting periods; iv) Recommend adaptation measures for different climate change scenarios and for different time horizons; v) Identify  impacts of the main transportation systems for distribution of agricultural products, as well as possible adaptation measures.

- Health sector: The objective of this study is to analyze the vulnerability of different populations to direct and indirect climate change impacts (direct ones being heat waves, extreme weather events, etc., and indirect ones including changes in distribution of pathogens and vectors that cause diseases, etc.). Activities to be supported include: i) Analyze direct and indirect climate change induced impacts on the health sector, and identifying of vulnerable populations; ii) identify new areas that might face occurrence of climate change related health issues based on future climate change scenarios; iii) Identify adaptation options encompassing monitoring, prevention and response measures.

- Tourism: The objective of this study is to identify vulnerability of the sector to future climate conditions and the economic impact that they will have on regional economies and on Argentina in its totality. The study will further consider implications of said impacts on the respective employment situation. The supported activities include: i) Define selection criteria for vulnerable tourist sites; ii) Select vulnerable tourist areas and identify climate change impacts on these sites for different climate change scenarios; iii) Identify and quantify economic and social impacts of climate change on the tourism sector; iv) Identify adaptation needs and options.

- Urban Areas: The objective of this study is to assess the vulnerability of Argentine cities to climate change scenarios and review current climate related adaptation planning and management tools. Specific objectives include: i) Diagnosis of the actual risks in cities facing challenging climatic conditions; ii) Identification and review of actual planning and risk management tools being in place to confront climate related risk. and possible lack thereof; iii) Elaboration of future urban scenarios in the face of climate change for different climate change impacts and response scenarios; iv) Propose adaptable urban planning and management options; and v) Evaluation of occurrence of inundations and other extreme climatic events, including consideration of possible migrations caused by CC impacts; vi) Identify impacts on urban transportation systems and the connections between cities in that regard.

- Energy sector: The objective of the study is to evaluate vulnerability of the energy sector in the face of CC considering regional aspects. The study will also consider implications of said impacts on the respective employment situation. Supported activities include: i) Quantification of  CC impacts in this sector and associated cost; ii) Assess climate change impacts on energy resources and energy infrastructure, including generation facilities; iii) Assess impact on energy demand caused by climate change for different climate change scenarios; iv) Assess potential changes in potential of renewable energies as a consequence of changing climate patterns.

- Water resources management: The objective of this study is to assess climate change impacts on watersheds, especially in the northern part of the country. Beyond studying changes in water flows, the study will also identify implications on a local micro level, and look in more detail into impacts on dams up and down-stream. The study will encompass the analysis of impacts on water resources especially in agricultural regions under irrigation.

- Fisheries: The objective is to study impacts of climate change on continental and marine fishing resources. The study will also consider implications of said impacts on the respective employment situation. In particular, the study would: i) Analyze climate change impacts on fisheries and distribution of species; ii) Study relations between different species in the context of climate change; iii) Evaluate impacts of sea surface temperature increase and ocean acidification; iv) Analyze climate change impacts on trophic food chains and  further on species of commercial importance.

Sub-component 2: Actions to Improve Adaptation to Climate Change

- Carrying out of studies to further develop priority adaptation actions necessary to strengthen the Recipient’s preparedness to climate change impacts in areas identified as most vulnerable, including technical and economic analysis of the proposed adaptation actions. Deliverables: Studies developing actions to improve adaptation to climate change on eco-regions and ecosystem services; agricultural sector; health sector; tourism; urban areas; energy sector; water resources management; and fisheries.

- The objective of this component is to further develop priority adaptation actions necessary to strengthen preparedness to climate change impacts in areas identified as the most vulnerable under sub-component 1 and the SNC. The supported studies will include the technical, environmental, social, financial, and economic analysis of the proposed adaptation actions, thus enabling their prompt implementation. The activities supported under this component are expected to result in identification of priority adaptation actions including their expected impacts, costs and benefits.

- All studies will evaluate the technical measures and necessary technologies in order to be prepared to confront the anticipated climate change impacts, promote adaptation, and reduce the identified vulnerabilities. This includes training needs, information disclosure and communication, good sector practices, legislation reform, etc. Additionally, the studies will estimate the costs derived from climate change impacts at a sector level, and the cost of the identified adaptation measures.

- Adaptation to climate change in each eco-region: The study will prioritize those eco-system services that generate crucial local and regional benefits, such as, basin protection, fiber protection, and food. The study has to identify, among others, conservation and restoration options for different climate change impact scenarios.

- Adaptation to climate change in the agricultural sector: The study will define adaptation measures for the most vulnerable activities and regions, in terms of their significance to regional economies and exports. The study should emphasize the main aspects considered in the vulnerability evaluations, and consider social aspects as well. The study will develop information on good practices for the agriculture and livestock sectors. This information should be focused on a sub-national level and with case studies that allow for replication and dissemination of sustainable practices.

- Adaptation in the health sector: Based on the vulnerability and adaptation study, this work will identify best practices to strengthen primary care, promote health practitioners’ training, and improve prevention management.

- Adaptation in the tourism sector: Based on the vulnerability and adaptation study, tourism alternatives minimizing impact on climate and maximizing climate resiliency will be identified.

- Adaptation in urban areas: The Project will analyze several options in more detail: i) Environmental urban planning; ii) Zoning tools and sustainable land use planning; iii) Best practices in the building sector depending on different regional climate change scenarios; green building options and energy efficient building practices will be included; (iv) Monitoring of critical flood risk areas.

- Adaptation in energy generation and demand: This study will provide options for adapting the current and future energy infrastructure to climate change impacts. The study will include technical and economic aspects of the analyzed options. In addition, the study will evaluate potential changes in energy demand due to different climate scenarios and offer options to adapt to altered energy demand patterns.

- Adaptation in the water resources sector: The objective of this study is to identify necessary technological alternatives for facing climate change impacts on river basins and the subsequent effects on regional economies. Other points that will be considered are: i) Analysis of early warning systems; ii) Municipal adaptation actions; iii) Collect different local experiences; iv) Generate information accessible for all actors, and design low cost communication measures that can be applied by municipalities with limited budget; v) Design of civil works to reduce impacts of flooding and inundations; and vi) Development of water storage systems anticipating changes in supply.

- Adaptation in the fishing sector: The objective of this study is to identify options in the fishing sector to mitigate impacts of climate change, and to reduce vulnerability.

- Challenges and Opportunities in labor sector and its adaptation to climate change: The objective of this study is to identify climate change impacts on employment patterns and design mitigation and response measures. Furthermore, internal migrations due to climate change will be considered. Activities that will be included are: i) Identify economic sectors that will receive the highest impact, considering the number of people affected; and ii) Propose adaptation measures for those impacts.

- A visual decision-making tool in terms of multi-layer maps will be created to support prioritization of different adaptation action: A map presenting the magnitude of expected climate change impacts will be overlaid with another map presenting concentrations of economic activities and/or poverty in the coming 30 years. Through such maps, benefits of different actions can be concretized related with, inter alia, the number and characteristics of their primary beneficiaries.

Sub-component 3: Adaptation Policies and Measures (P&M)

- Enhancement of an enabling framework for the implementation of adaptation measures, including the design and delivery of a set of adaptation P&M aimed at integrating climate change into the Recipient’s development strategy and sector programs on the above named sectors, as well as on challenges and opportunities in labor sector and its adaptation to climate change. This will include technical, economic, environmental, social and financial analysis of the proposed adaptation actions. The TNC aims at proposing P&M which would themselves be revenue-generating to cover at least a part of their implementation costs, and research and innovation will be provided on their possible financing sources. Further, possible synergy in terms of climate change mitigation will be targeted. Additional deliverables: Design of an agreement upon supporting an integrated set of policies; and Analysis of labor P&M by comparing international legislation with expected outcomes for the near future in Argentina, where conclusions will be based on socio-political analysis of future scenarios and statistical modeling.

- The objective of this component is to support the enhancement of an enabling framework r the implementation of adaptation measures, and to integrate climate change into development strategies and sectorial programs. The activities under this component will deliver a set of P&M to address adaptation in different economic sectors. These P&M will be based on the results of the studies on vulnerability, impacts, and adaptation options. The design of P&M will take into account sectorial development strategies or programs already in place, as well as the outcomes of the negotiations currently underway in the UNFCCC. The activities will also include assessment of economic, social and environmental impacts of implementation of the identified P&M on the socio-economic baseline scenarios. Socio-economic scenarios will serve as reference scenario for the studies on climate change vulnerability, impacts, and adaptation P&M. Activities for the elaboration of socio-economic scenarios include: (i) Identify and assess the information necessary to develop the socio-economic scenario; (ii) Standardize statistical information; (iii) Identify national and international driving forces for the evolution of different socio-economic sectors; and (iv) Project the evolution of the socio-economic baseline scenario.

- As a result of this component, the design of an agreement upon supporting an integrated set of policies is expected, what would facilitate implementation of priority adaptation and mitigation measures and strengthen their sustainability.

- In addition, labor P&M will be analyzed by comparing international legislation with expected outcomes for the near future in Argentina. Conclusions will be based on socio-political analysis of future scenarios and statistical modeling.

- The TNC aims at proposing P&M which would themselves be revenue-generating to cover at least a part of their implementation costs. Additionally, the TNC will provide research and innovation on possible financing sources for the identified adaptation P&M. Possible synergy in terms of climate change mitigation will also be targeted.

Component 3: Institutional Strengthening, Capacity Building, and Information Management (GEF cost: USD 0.87 million, total: USD 1.09 million)

- The objective of this component is to prepare the detailed TORs of the activities, strengthen institutional capacity and disseminate the TNC results to a broad audience. Dissemination efforts will be guided by a thorough communication strategy, and messages and communication channels will be tailored according to targeted diverse audiences.

Sub-component 1: Definition of Technical and Institutional Framework for the TNC

- Provision of support to define the technical scope of activities to be carried out under the TNC, including the detailed design of the institutional and coordination arrangements necessary to facilitate access to Project information and to secure stakeholders’ ownership and participation.

- The objective of this component is to fully detail the technical scope of the activities undertaken as part of the TNC, and design the institutional and coordination arrangements in order to facilitate access to information and commit Governmental Agencies to the development of the Project. In depth technical task descriptions and responsibilities, timeframes and required resources will be designed for each activity. Expected results from this component include the preparation of detailed TORs for the activities to be performed, as well as the institutional architecture for the management and implementation of the Project activities.

Sub-component 2: Institutional Strengthening and Capacity Building

- Strengthening of institutional capacity at the national, provincial and municipal levels, with regard to the integration of climate data into sector programs and strategies through, inter alia, organizing workshops for national, provincial and municipal agencies and legislators; teachers at high school and primary school levels; CS; and journalists aimed at developing and disseminating Project-related information and materials tailored to different interest groups. Other deliverables: Related distance course for teachers; Preparation of one educational textbook for primary and one for secondary school students; Transformation of the Carbon Market Simulation Game to web format; and Design of a Simulation Game on Adaptation.

- The objective of this component is to strengthen institutional capacity so that public institutions would be able to provide adequate information on climate change and variability, and would become motivated to work for integrating climate concerns into sectoral programs and strategies based on the results of the supported studies. This component will support participation of stakeholders in the elaboration of climate change P&M. To optimize the scarce resources and the dissemination efforts to be undertaken, a thorough communication strategy will be developed to plan what shall be communicated to whom, when and by what means to strive for impacts. Workshops with participants of governmental, scientific and technological institutions and CS will be held, dissemination material developed to target specific audiences, and a communication system designed for assisting provincial and municipal governments in integrating climate change issues into their development planning and programs.

Capacity Building Activities

- Organization of workshops for national, provincial and municipal agencies and legislators. The main objective of this activity is to promote inclusion of climate change, its associated impacts and response measures, in the political agenda at the national, provincial and municipal levels. Workshops are planned for this purpose contemplating feasible access to federal representation. The activity will help institutional strengthening and training of Governmental Agencies, providing them with a toolset and building their capacity to develop initiatives that incorporate Global Glimate Change (GCC). The specific objectives of this activity are:

- Promote inclusion of climate change in provincial and municipal management practices;

- Present partial results of the TNC;

- Provide knowledge and train government officials so that they can develop programs and projects relating with climate change;

- Show examples of public policy implementation that address challenges of climate change and share experiences; and

- Train government officials in information collection and management that will allow for an improvement in preparation of future NCs.

- Organization of workshops for teachers at high school and primary school levels. The main objective of these workshops is to disseminate climate change issues, key results of the TNC, and the carbon footprint concept in a targeted manner to different audiences. Key actors involved include the Institutos de Formación Docente. Workshops are planned for this purpose contemplating feasible access to federal representation. The specific objectives of this activity are:

- Provide information to teachers and professors on the issues of climate change, its impacts and adequate response actions so that they can act as information multipliers to children and young students, given the significant importance that climate change will have on future generations;

- Help students grasp dimensions of GCC impacts and help them identify climate conditions that will prevail in different regions of the country, so they can become progressively involved around the CC agenda; and

- Present partial results of the TNC.

- Organization of workshops for CS (CS). The main objective of these workshops will be to disseminate climate change issues, the results of the TNC and the carbon footprint concept. Workshops are planned for this purpose contemplating feasible access to federal representation. The specific objectives of this activity are:

- Provide CS representatives information to gain awareness of climate change, its associated impacts and response actions so that they can act as information multipliers across their networks.

- Support CS representatives to understand dimensions of GCC impacts and help them identify climate conditions that will prevail in different regions of the country, so they can become progressively involved around the CC agenda; and

- Present partial results of the TNC.

- Organization of workshops for journalists across the country. Climate change issues are becoming increasingly relevant in mass media coverage. The objective of this activity is to train journalists on climate change topics and present them the results of the TNC, so they can become multipliers of the information generated by the Project. Workshops are planned for this purpose contemplating feasible access to federal representation. By attending these workshops, journalists are expected to gain significant knowledge allowing for an adequate comprehension of climate change issues. It is expected that media will also help in making public the impacts of climate change and mitigation and adaptation measures proposed and/or adopted in the local, regional and national level.

- Distance course for teachers. Given the lack of knowledge detected among teacher with regards to climate change, and the impossibility of federal agencies of offering training courses on this topic, a distance course for primary and high school teachers will be developed and implemented.

- Preparation of two Educational Textbooks, one for primary school students and one for secondary school students. Many students have limited access to specific, tailored information about climate change, thus limiting their potential to become information multipliers themselves and to change their habits and behaviors. Sometimes also teachers lack enough of appropriate information about climate change to be able to work in classes. These textbooks will include topics on climate change including information provided by the TNC. The objective of this activity is to design and publish an educational tool that allows access to information on climate change for children, so it can be used in schools throughout the country.

- Transform the Carbon Market Simulation Game to web format. This activity will allow having an online version of the Carbon Market Simulation Game, which will allow the public to play it and have a better comprehension of this topic. Currently, this game can only be played with a server and the right software. By having an online version, this tool can be extended and the number of users can increase significantly by organizing training workshops.

- Design of a Simulation Game on Adaptation. The objective of this activity is to design a tool that can generate awareness on impacts of climate change and the need to implement adaptation measures, in a similar fashion to the Carbon Market Simulation Game.

Sub-component 3: Development, Publication and Dissemination of the TNC

- Preparation and dissemination of the TNC to all relevant stakeholders, incorporating the conclusions and results reached through the carrying out of the Project-supported studies and additional related information. Preliminary results will be discussed through different mechanisms such as workshops. Deliverables: Final report; Final report for decision makers; Organization of 6 workshops to communicate final results; Preparation of a media campaign; and Design of information management software.

- The objective of this component is to integrate the results of all the studies supported under this Project in the format of the TNC to publish and disseminate it. Specific reports on each activity carried out under the Project and relevant to policy makers will be developed. This component includes also a communication strategy to disseminate the generated data and the preliminary and final results along the Project duration to all relevant stakeholders. Partial Project results will be discussed during implementation through different mechanisms such as workshops.

- Final Report. The objective of the final report is to integrate all the studies that were undertaken into a single document. This report will be 200 pages in length, A4 size, and 5,000 copies will be printed.

- Final Report for Decision Makers. The objective of this publication is to let decision makers at the national, provincial and municipal levels know about the implications of climate change on the different regions of the country, as well as to have quick access to key TNC results relevant to policy making. The report will include around 20 pages, and 2,500 copies will be printed.

- Organization of workshops to communicate final results. The Federal Government will communicate the results of the Project to local governments in all regions of the country. Workshops will be hosted in the City of Buenos Aires, Patagonia, Centro, NOA, NEA and Cuyo.

- Preparation of a media campaign. A specific strategy will be defined for the development of a media campaign focused on the topic of climate change, and based on the results of the TNC studies. The objectives of this campaign are: (i) Help to install the climate change topic on society and make it a key environmental concern; (ii) Help to raise awareness and achieve related commitment from society; (iii) Contribute to modify habits to reduce GHG emissions from transport, energy consumption, waste generation, etc.; (iv) Help to shape behaviors as needed by the GCC challenge; and (v) Contribute to individuals raising awareness of their role in developing actions and initiatives on mitigation and adaptation to climate change. The campaign could include:

- TV ad (30-second) to be broadcast on Canal 7 and Canal Encuentro

- Audio book

- Radio ads, broadcast on Radio Nacional

- Educational video on climate change for CSOs, educational institutions, industrial chambers, etc.

- Design of information management software. This software will have a section on emissions and other on climate change scenarios. Both will include results of the TNC. The emissions section shall permit the user to obtain emissions volume by type of gas and sector, historical series, and projections. It will also provide information on emissions by region or province, and costs of impacts and mitigation potential. The climate change scenarios section will include the IPCC Distribution Center web page as a model, allowing the user obtain outputs from the models by selecting a place and a time window. It will also provide information on current climate. It will be hosted both by the SAyDS website and at the National Weather Service (Servicio Meteorologico Nacional) website. In addition, this information should be in GIS format, so users can overlap climate change layers with others, such as vulnerability indicators from the socio-economic study, land use and forests, desertification, etc. Develop software for GHG emissions data management. This activity will develop software for GHG emissions management, emissions projections and a GIS system for the spatial distribution of emission sources. The software would identify emissions by GHG type, sector, period, and location. For the latter, inputs will be provided through development of GHG emission inventories by province. The software should also enable rapid visualization of changes in emission patterns.

Component 4: Project Management (GEF cost: USD 0.11 million, total: USD 0.13 million)

- Provision of technical and operational assistance, as necessary, to support adequate Project management and coordination by the PIU and the Steering Committee, including carrying out Project audits.

- This component will finance needed staff resources and other operational expenditures in the Executing Agency to ensure smooth management of the Project. The Steering Committee meetings and representatives of other participating agencies, provinces or stakeholder groups will be assisted to facilitate Project coordination during implementation.

- The head of the PIU will be the Chief of the Cabinet of Ministers (JGM). The General Administrative and Technical Directorate (DGTA) of the JGM will be in charge of the overall Project implementation and the fiduciary issues. The Climate Change Directorate (CCD) will be in charge of the Project technical implementation, including participation in selection of consultants, review of the preliminary and final reports, coordination of workshops, etc.

THIRD NATIONAL COMMUNICATION TO THE UNITED NATIONS FRAMEWORK CONVENTION ON CLIMATE CHANGE

Annex 5: Project Costs (US$ Million)

| Project Cost By Component and/or Activity | Local | Other Foreign | GEF | Total |
| --- | --- | --- | --- | --- |
| Component 1: Harnessing National Potential for Cliamte Change Mitigation | 0.13 |  | 0.53 | 0.66 |
| Component 2: Strengthening National Adaptation Agenda | 0.23 |  | 0.93 | 1.16 |
| Component 3: Institutional Strengthening, Capacity Building and Information Management | 0.22 |  | 0.87 | 1.09 |
| Component 4: Project Management | 0.03 |  | 0.11 | 0.14 |
| Total Project Costs | 0.61 |  | 2.44 | 3.05 |

1Identifiable taxes and duties are US$m ___, and the total Project cost, net of taxes, is US$m___. Therefore, the share of Project cost net of taxes is ___ percent.

THIRD NATIONAL COMMUNICATION TO THE UNITED NATIONS FRAMEWORK CONVENTION ON CLIMATE CHANGE

Annex 6: Implementation Arrangements

- General Implementation Arrangements: The JGM will be the Project Executing Agency and lead the Project Implementation Unit (PIU). The Secretariat of Environment and Sustainable Development (SAyDS), and its Climate Change Directorate (CCD) under the JGM is the focal point for the Climate Change Convention, and it has the institutional mandate to prepare NCs. The CCD will lead the technical aspects of the Project. The Technical and Administrative General Secretariat (DGTA) of the JGM will be in charge of the overall Project implementation and responsible for the Project procurement and FM activities: comprising budgeting, accounting and reporting, including preparation of IUFRs, provision of internal control, and taking care of the disbursements and the external audit process.

- The management structure of the TNC will be constituted by a Steering Committee (SC), serving as a consulting organ, a (PIU), and a Technical Advisory Committee (TAC).

Steering Committee (SC)

- The Steering Committee for the Project has been approved during a meeting dated December 22, 2009. The Steering Committee belongs to the Government Committee on Climate Change, a governmental body recently created to deal with climate change issues.

- Structure. The Steering Committee will be constituted by representatives of the main Federal Authorities through the Federal Secretariats linked to this Project, and provinces through COFEMA. The President of the SC will be the Secretary of Environment and Sustainable Development. The following Governmental agencies will be members of the SC:

- Chief of the Cabinet of Ministers - SAyDS (President of the Steering Committee)

- Ministry of Foreign Affairs, International Trade and Worship  - DIGMA (IIRR)

- Ministry of Science and Technology - Secretariat of Planning and Policy in Science, Technology and Productive Innovation

- Ministry of Science and Technology - National Directorate of Foreign Affairs

- Ministry of Planning and Public Investment with representation from the Secretariat of Energy, Secretariat of Transport, and the Sub-Secretariat of Water Resources

- Ministry of Defense

- Ministry of Labor, Employment and Social Security

- Ministry of Social Development

- Ministry of Production with representation from the Secretariat of Industry, Commerce and PyMES

- Ministry of Economy - Secretariat of Economic Policy

- Federal Council of Environment (COFEMA)

- Ministry of Education

- Ministry of Agriculture, Livestock and Fisheries

- The SC will preserve its right to allow new participants of other agencies, institutions or persons, according to its specific requirements or demands. The SC members will assure the supply of information from the agencies and organisms they represent for the accomplishment of studies and activities.

- Function. The main responsibility of the SC is to assure political and strategic support for the TNC implementation. It will provide guidance on implementation and make high level recommendations regarding the Project’s development, technical aspects and management issues. The SC will assure national ownership of the results making sure they prove useful for the development of national policies. The SC will assess the progress reports elaborated by the PIU. The SC will track deadlines and budget execution of activities based on reports elaborated by the PIU for each SC meeting, or as requested.

- Operational procedures. Active SC members have been officially appointed by an authority (not lower than Secretary Level) of each respective agency. Appointed members are experts with a National Director level or higher. Acting members will replace other members in case of absence. These acting assignments will be designated by the titular member or a higher level authority. Acting members will not have lower than Director Level. The membership of the SC will not be paid or represent charges against grant proceeds.

- Call to SC meetings. The SC will celebrate meetings on a quarterly basis in order to assess the progress of the Project. The SC President will call to these meetings. Additionally, members will be able to request to the President to have extraordinary meetings out of the quarterly program. These extraordinary meetings will also be conveyed by the President. The PIU will be in charge of the meetings’ arrangements.

- Decision making process. The SC decisions will be made on the basis of consensus. In case consensus is not achieved, the SC will decide on simple majority of active members (or acting members only in case of absentees) present in the meeting. In case of a tie, the SC President will have double vote. All decisions and conclusions will be documented in meeting proceedings which will be signed by all the SC members that have attended the meetings.

- Recommendation making process: The PIU will send TORs to the SC members for review by email. The members will have 3 working days to provide comments on these TORs. If a comment can not be solved directly by the PIU, a SC meeting will be called upon to solve it. If 3 working days pass and no comments are received, the PIU will continue the respective procurement process according to its TORs. In case of no-objections to reports on background evaluations of consultants conducted by the PIU, the same procedure will apply.

Project Implementation Unit (PIU)

- Functions. The PIU will have the following specific functions:

- Carry out the general coordination of the Project (DGTA/JGM);

- Technical supervision of accomplishment of activities, goals and timeframe of the Project (CCD/SAyDS);

- Carry out, following the Bank’s rules, the process to select scientific institutions and consultants to develop the studies and activities which are part of the Project (CCD/SAyDS);

- Obtain the World Bank no objection to award contracts to institutions and consultants selected for each case, if applicable (DGTA/JGM);

- Act as a link between the different agencies and parties involved in the implementation of the Project (CCD/SAyDS);

- Prepare the TORs for the institutions and consultant experts which will develop different Project activities (CCD/SAyDS);

- Monitor the partial results and final reports of the implemented activities (CCD/SAyDS);

- Prepare progress reports to be submitted to consideration of the SC (CCD/SAyDS) and the World Bank (DGTA/JGM); and

- Conduct the FM and procurement for all contracts and acquisitions that PIU would require (DGTA/JGM).

- Communication between the World Bank and the PIU. The DGTA will be the formal communication channel between the World Bank and the Executive Agency.

- Structure. The PIU staff will cover the following key positions:

Technical staff (CCD/SAyDS)

•	Technical Coordinator (TC)

•	GHG Inventory Coordinator (IC)

- Mitigation Coordinator (MitC)

•	Models Coordinator (ModC)

- Impacts, Vulnerability and Adaptation Coordinator (AC)

•	Training, Outreach and Communications Coordinator (TOCC)

•	Technical-administrative Assistant (TA)

- Monitoring Coordinator (MonC)

Administrative and financial staff (DGTA)

•	General Coordinator (GC)

•	Financial and Administrative Coordinator (FAC)

•	Procurement Coordinator (PC)

•	Administrative and Financial Assistant (AFA)

- The PIU staff can belong to the CCD (SAyDS) and the DGTA, or be external to these Agencies. In this case, the positions will be hired under the Grant proceeds.

- Operation. The PIU will be established in the CDD and the DGTA, and will count with official servants and external experts. Selection and contracts of external consultants to the PIU, as well as procurement of goods and services will be carried out following the Bank’s rules and procedures.

Technical Advisory Committee (TAC)

- Function. The TAC will support the PIU in technical and scientific issues during Project implementation. TAC opinions will not be binding.

- Structure. TAC will comprise scientific and technical institutions, NGOs, CS, trade unions and representatives from the private sector. They will be selected using criteria to be approved immediately after Project approval following principles of representativeness and open participation. These institutions shall be enrolled in a registry maintained by the PIU.

- Operation. TAC will meet every three months. Meetings will be coordinated by the Technical Coordinator.

- The following diagram summarizes the Project management structure. The arrows in the diagram do not represent management lines; they only illustrate flows                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                             of technical, scientific and political information, and describe different levels of coordination.

Science & Tech

MRE

Planning and Public Investment

Economy

DIGMA

SE

SPE

SPPCTIP

DNRI

SC

Steering Committee

Presidency in the SAyDS, JGM

Technical Advisory Committee (TAC)

ST

SSRH

Production

SIC

ModC & AC

TOCC

TA & MonC

GC

FAC

TC

PIU

Project Implementation Unit-JGM

DGTA and

Climate Change Directorate (SAyDS)

Defense

Education

Labor

Ministries

Agriculture

Social Development

COFEMA

Technical staff

(CCD/SAyDS)

Administrative and financial staff (DGTA)

IC & MitC

PC

AFA

References:

SC: Steering Committee

COFEMA: Consejo Federal del Medio Ambiente

JGM: Jefatura de Gabinete de Ministros

SAyDS: Secretaria de Ambiente y Desarrollo Sustentable

MRE: Ministerio de Relaciones Exteriores

DIGMA: Dirección General de Medio Ambiente

SPPCTI: Secretaria de Políticas y Programas de Cientica, Tecnología e Innovación Productiva

DNRI: Dirección Nacional de Relaciones Insternacionales

SE: Secretaría de Energía

SSRH: Subsecretaria de Recursos Hídrigos

ST: Secretaria de Transporte

SIC: Secretaria de Industria, Comercio y PYMES

SPE: Secretaria de Politica Económica

PIU: Project Implementation Unit

Technical staff (CCD/SAyDS)

TC: Technical Coordinator

IC: GHG Inventory Coordinator

MitC: Mitigation Coordinator

ModC: Models Coordinator

AC: Impacts, Vulnerability and Adaptation Coordinator

TOCC: Training, Outreach and Communications Coordinator

TA: Technical-administrative Assistant

MonC: Monitoring Coordinator

Administrative and financial staff (DGTA)

GC: General Coordinator

FAC: Financial and Administrative Coordinator

PC: Procurement Coordinator

AFA: Administrative and Financial Assistant

THIRD NATIONAL COMMUNICATION TO THE UNITED NATIONS FRAMEWORK CONVENTION ON CLIMATE CHANGE

Annex 7: Financial Management and Disbursement Arrangements

#### Executive Summary and Conclusion of the Financial Management Review

1.	A Financial Management (FM) review of the adequacy of the current financial management arrangements for the Project was performed in line with the guidelines issued by the Financial Management (FM) Board on November 2005 and the Simplified Financial Management Assessment for Small Grants from 2009 to determine if the financial management arrangements are working adequately and are acceptable to the Bank.

2.	The conclusion of the assessment that the DGTA of the Chief of the Cabinet through the Project Implementation Unit has adequate FM arrangements in place. The Project specific arrangements along with the government-wide FM system in place, located at the DGTA meet the minimum Bank requirements.

#### Country Issues

3.	The 13 findings of the Argentina Country Financial Accountability Assessment (CFAA) are that the PFM systems are well designed and underpinned by a strong legal framework and the availability of human resources with sufficient technical skills. These systems enable control of the budgetary resources received by the Government from all sources. However, despite these achievements, the CFAA concludes that the country’s PFM performance is still operating below expectations. With regard to FM risk, the CFAA indicates that the PFM risk can be considered moderate at the National Public Administration (NPA) of which the MSN is part and social security institutions that are included in the SIDIF.

4.	The Argentina CPS (Report #48476-AR) for the period 2010-2012 discussed by the Executive Directors on June 9, 2009 includes improved fiduciary risk and portfolio monitoring as one of the key elements of the Bank strategy to strengthen the capacity of the Government to prepare, approve and implement investment projects in Argentina. The following measures will contribute to the Bank effort to meeting the objectives expressed in the CPS:

- Enhanced FM supervision to ensure the continuous adequacy of FM arrangements, evaluate Project internal control and update assessed risk. At least one on-site visit integrating the Project team is planned for the first year.

- Continuous support to AGN (Argentina Supreme Audit Institution) efforts to ensure timely audit compliance for the Project. Upon audit findings, follow up on the borrower action plans to address the auditors’ recommendations.

- Involving the Internal Audit Units to carry out review of Project financial transactions.

5.	Given that this operation does not present any complexity for FM no specific complementary measures on standard FM arrangements have been designed for this Project.

#### Executing Agency

6.	The Executing Agency will be the JGM. The PIU will be jointly conformed by the CCD (SAyDS) of the JGM in charge of technical implementation, and the Technical and Administrative General Secretariat (DGTA) of the JGM, which will be in charge of the overall Project implementation and responsible for the Project FM activities.

#### Strengths and Weaknesses

7.	Strengths: Expertise and experience of the PIU staff that carry out FM functions of existing projects.

8.	Weaknesses: There are no critical FM issues identified for this Project.

Risk Assessment and Mitigation

9.	The FM risk assessment process aims at identifying FM risks so as to take appropriate measures mitigating identified Project risks. This enables the Bank to make decisions on the appropriate level of supervision intensity allocating FM resources in a manner consistent with assessed risks. A detailed risk assessment is presented below:

Table A7-1

Risk Assessment and Mitigating Measures

| Risks | Risk Rating | Risk Mitigating Measures | Residual Risk Rating |
| --- | --- | --- | --- |
| Inherent Risk |  |  |  |
| - Country Level | Moderate |  | Moderate |
| - Entity Level | Moderate |  | Moderate |
| - Grant Level | Moderate |  | Moderate |
| Overall Inherent Risk Substantial |  |  |  |
| Control Risk |  |  |  |
| - Budgeting | Moderate | Integrated accounting system | Moderate |
| - Accounting | Moderate | Integrated accounting system | Moderate |
| - Internal Control | Moderate | Formal written procedures | Moderate |
| - Funds Flow | Moderate | Segregated designated account | Moderate |
| - Financial Reporting | Moderate | Integrated accounting system | Moderate |
| - Auditing | Moderate | Independent external auditor | Moderate |
| Overall Control Risk | Moderate |  |  |
| Overall FM Risk | Moderate |  |  |

#### Internal Control and Internal Audit

10.	The DGTA is subject to internal audit of the General Syndicate of the Nation (SIGEN) which is the Federal Government’s internal audit agency under the jurisdiction of the executive branch. SIGEN supervises and coordinates the actions of the Internal Audit Units (IAUs) in all agencies, approves their audit plans, conducts research and independent audits, systematizes the information from its own reports and those produced by the IAUs. If necessary, the internal audit reports on the Project performance will be reviewed during Project supervision.

External Audit Arrangements

11.	The Project annual financial statements will be audited under TOR, auditing standards and by auditor acceptable to the Bank. The audit report shall be submitted to the Bank within six months of each Fiscal Year (FY). Annual audit would cover all funding and expenditures reported in the Project financial statements. For audit purposes the FY will be the calendar year. Project has proposed that the Argentine Supreme Audit Institution, Auditoria General de la Nación (AGN) be the external auditor for the Project.

12.	The audit reports that will be required to be submitted are presented below:

Table A7-2

Audit Reports’ Schedule

| Audit Report | Due Date |
| --- | --- |
| 1) Project Specific Financial Statements | June 30 |
| 2) Special Opinions | June 30 |
| - SOE | June 30 |
| - Designated Account | June 30 |

#### Accounting and Reporting

13.	The Project will apply the Government system specially designed for the execution of multilateral financed operations, which is legally required (UEPEX). UEPEX is compliant with Bank requirements, provides a good ex-ante internal control framework and is in line and better integrated with the national budget execution process. The Bank has strongly recommended the adoption of UEPEX for the new operation.

14.	The Technical and Administrative General Secretariat of the JGM will be responsible, among the functions detailed in Annex 6, for keeping accounting records for Project activities and preparation of annual financial statements and semiannual Interim Unaudited Financial Reports (IUFRs for reporting purposes, as follows:

- Sources and uses of funds: sources and uses of funds, for each semester and cumulative (uses by category), uses of funds by component and beginning and ending cash balances.

- Physical progress: Allocated budget and financial execution compared to physical progress and results achieved.

15.	IUFRs will be solely used for reporting purposes and will be part of the progress reports submitted by the Project.

16.	Draft format of Annual and Interim Financial Statements will be prepared by the Project and reviewed by the Bank by Negotiations.

Disbursement Arrangements

17.	The following Disbursement Methods may be used under the Grant:

- Reimbursement

- Advance

- Direct Payment

18.	Grant proceeds to be withdrawn by the Technical and Administrative General Secretariat of the JGM using the advance method will be deposited into a Segregated Designated Account (DA) in US dollars. The DA will be held at Banco de la Nacion Argentina (BNA) as usual for the Bank operations with the National Government. The ceiling for advances to be made into the DA would be US$ 0.5 million, estimated sufficient for Project execution.

19.	Supporting documentation for documenting Project expenditures under advances and reimbursement method will be: Statements of Expenditures (SOEs). SOE limits will be set at US$ 0.4 million and will be presented to the Bank at least once every calendar quarter.

20.	All consolidated SOEs documentation will be the responsibility of the Technical and Administrative General Secretariat of the JGM and will be maintained for post-review and audit purposes for up to one year after the final withdrawal from the Grant account.

21.	The Technical and Administrative General Secretariat of the JGM will have access the Bank’s Client Connection webpage to facilitate periodically reconciliations among its own ledgers, bank statements and the Bank disbursement records.

22.	Grant proceeds will be disbursed against the following expenditure categories:

Table A7-4

Disbursements per Expenditure Category

[TO BE AGREED DURING NEGOTIATIONS]

| Category | Amount of the Grant Allocated (expressed in USD) | Percentage of Expenditures to be Financed ([inclusive of Taxes) |
| --- | --- | --- |
| (1) Goods | TBD | 100% |
| (2) Consultants’ services | TBD | 100% |
| (3) Non-consultant Services | TBD | 100% |
| (4) Training | TBD | 100% |
| (5) Operating Costs | TBD | 100% |
| TOTAL AMOUNT | 2,400,000 |  |

Supervision Plan

23.	The initial supervision planning is presented in the table below. The supervision scope will be adjusted by the assigned FMS according to the fiduciary performance and updated risk.

Table A7-5

Financial Management Supervision Plan

| Type | Timing | Mechanism | Objective |
| --- | --- | --- | --- |
| On-site Visit | General Supervision: Once a year. | Integrating supervision missions. | - Review FM performance. - Follow up on External Auditors - - Recommendations / raised issues. - Review control. - Update assigned risk. - Transactions review as needed |
| IUFRs Review | Semiannually | Over the IUFRs submitted to the Bank. | - Review IUFRs information consistency. - Raise issues disclosed in IUFRs. |
| Audit Review | Once a Year | Over the Audit Report submitted to the Bank | - Raise issues disclosed in Audit Report |

Action Plan

24.	FM actions to be completed by the Technical and Administrative General Secretariat of the JGM are reflected in the table below.

Table A7- 6

Financial Management Action Plan

| Action | Responsible Entity | Completion Date | Status |
| --- | --- | --- | --- |
| 1. Prepare the external auditing TOR to be approved by the Bank | Technical and Administrative General Secretariat of the Chief of the Cabinet’s PIU | By Negotiations | Pending |
| 2. IUFRs format approved by the Bank. | Technical and Administrative General Secretariat of the Chief of the Cabinet’s PIU | By Negotiations | Pending |
| 3. Set a separate budget line in the annual budget to keep track of Project financial execution | Technical and Administrative General Secretariat of the Chief of the Cabinet’s PIU | First year annual budget and thereafter | Legal dated covenant |

THIRD NATIONAL COMMUNICATION TO THE UNITED NATIONS FRAMEWORK CONVENTION ON CLIMATE CHANGE

Annex 8: Procurement Arrangements

A. General

- Procurement for the proposed Project would be carried out in accordance with the World Bank’s "Guidelines: Procurement under IBRD Loans and IDA Credits", dated May 2004 – Revised October 2006 – Revised May 2010; and "Guidelines: Selection and Employment of Consultants by World Bank Borrowers", dated May 2004 – Revised October 2006 – Revised May 2010, and the provisions stipulated in the Legal Agreement. The various items under different expenditure categories are described in general below. For each contract to be financed by the GEF Grant, the different procurement methods or consultant selection methods, the need for pre-qualification, estimated costs, prior review requirements, and timeframe are agreed between the Recipient and the Bank in the Procurement Plan. The Procurement Plan will be updated at least annually, or as required to reflect the actual Project implementation needs and improvements of institutional capacity.

- Implementation arrangements: The General Administrative and Technical Directorate (DGTA) and the CCD (CCD)  in JGM will be jointly in charge of the overall Project implementation through the PIU. The Directorate of Budget, Procurement and Contracting (DPCC) depends on the DGTA will be responsible for the procurement and FM activities.

- Procurement of Works: No civil works are expected under the Project.

- Procurement of Goods: Goods procured under this Project would include IT equipment and other small items. The use of ICB is not foreseen. The procurement will be done using the Bank’s SBD for all ICB and National SBD and standard Requests for Quotations agreed with the Bank. Contracts for goods estimated to cost less than US$100.000 per contract, may be procured using Shopping.

- Procurement of Non-Consulting Services: All contracts for services not related to consultant services, such as: printing services, organization of workshops and dissemination activities may be procured under the same methodologies and thresholds specified for goods.

- Selection of Consultants: Consultant services procured under this Grant are expected to include: i) under Component 1: studies to update an emission inventory for different sectors (rural and agriculture, industries, waste, energy), technical assistance for the elaboration of emission patterns indicators; ii) under Component 2: studies to asses environmental, social and economic impacts and vulnerability and adaptation in natural resources in different eco-regions and sectors; consultant service for the generation of Climate Change scenarios through the use of an ensemble of regional climate models; iii) under Component 3:  mitigation studies in specific sectors, technical assistance for the elaboration of manual for students and development of e-learning courses for teachers, consultant service to design of dissemination campaign and iv) under Component 4: individual consultants to prepare TOR for the services and project management.

- Short lists of consultants for services estimated to cost less than $500,000 equivalent per contract may be composed entirely of national consultants in accordance with the provisions of paragraph 2.7 of the Consultant Guidelines. Specialized advisory services would be provided by individual consultants selected by comparison of qualifications of at least three candidates, and hired in accordance with the provisions of paragraph 5.1 to 5.3 of the Consultant Guidelines.  Individual consultants may be selected sole-source with prior approval of the Bank in accordance with provisions of paragraphs 5.4 of the Consultants Guidelines.

- Operating Costs: To be procured using the DGTA administrative procedures, reviewed and found acceptable by the Bank. This includes office and administrative costs related to managing a project, travel expenses and per diem, either related to supervision activities.

- Training: The Project will finance expenditures (other than those for consultants service) incurred by the Recipient and/or staff at national and regional level, as approved by the Bank on the basis of an annual plan, to finance reasonable transportation costs, per-diem and training registration fees, which would be procured using the DGTA administrative procedures, reviewed and found acceptable by the Bank.

- The procurement procedures and SBDs to be used for each procurement method, as well as model contracts are presented in the Operational Manual.

B. Assessment of the Agency’s Capacity to Implement Procurement

- Procurement activities will be carried out by the Procurement Unit of the Directorate of Budget, Procurement and Contracting (DPCC) of DGTA. The project would have an Administrative Coordination in DGTA that would liaise with the technical unit of the CCD (CCD).

- An assessment of the capacity of the Recipient to implement procurement activities for the Project has been carried out by Ana María Grofsmacht on April 6, 2010. The assessment reviewed the organizational structure for implementing the Project and the coordination with the technical unit that would be participating in the Project implementation.

- The key issues and risks concerning procurement for implementation of the project have been identified and include:

(a) Legal Aspects: national procurement regulations are not totally consistent with Bank Guidelines. National Public Procurement is ruled by separate and incomplete statutes, which only cover procurement by the central administration and decentralized agencies of the executive branch:

•	Supreme Decree No.1.023/2001 and its subsequent modifications (enacted through Decrees Nos. 666/2003 and 204/2004) establish the principles for public procurement and rule the procurement of goods and services. The applicability and enforceability of this Decree is, however, limited, since not all the necessary regulations have been issued. Decree 436/2000, which regulated the procurement-related articles of National Account Law 23.354 of 1956, is still used, despite the fact that those articles were repealed by Decree No.1.023/2001.

•	Public Works Law 13.064 of 1947 (Ley de Obras Públicas) governs the specifics of procurement of civil works.

•	Law 22.460 of 1981 for the contracting and promotion of consulting services was partially repealed in 1994, and it is in practice ignored. Decree 2.345/2008 governs the hiring of individual consultants. Regulations concerning the hiring of individuals result in lengthy approval processes by Government authorities; that is why implementing agencies resort on procurement agents quite often.

•	In addition, Law 24.156 on FM and Control Systems of 1992 (Ley de Administración Financiera y de los Sistemas de Control) contains provisions related to procurement, particularly in respect to reference prices.

Government owned enterprises, the legislative and judicial branches of government, the provinces and the City of Buenos Aires have their own public procurement rules and regulations. Although not all provincial procurement regulations were assessed, practice has demonstrated that they are modeled along federal rules.

(b) Procurement Cycle Management. DPCC does have neither previous experience in Bank-financed procurement nor a procurement information system in place. However, DPCC prepares an Annual Procurement Planning with the requirement received from the technical units.

(c) Organization and Functions. DPCC is headed by a Director and has a Procurement Coordinator, who is responsible to manage the Procurement Unit.

(d) Support and Control Systems. DPCC has an internal audit and a legal department and an external audit under General National Audit (AGN) and SIGEN.

(e) Staffing. The Procurement Unit of the DPCC is staffed by 11 persons, under the supervision of the Procurement Coordinator. Staffing would be adequate, which smoothly handle current work-load.

(f) Country Environment - Portfolio performance: In general, procurement performance in Bank-financed projects in Argentina has been rated as “Satisfactory” during the last years; however, shortcomings were found in some projects. The most serious of them are: (a) agreements signed with NGOs that are not consistent with Bank standard contract forms, (b) un-accuracy of cost-estimates, (c) biased technical specifications, (d) indications of collusion in the preparation of short-lists and (e) requirement of compliance with ISO quality standards as a way to restrict participation of small ITC equipment producers. Delays in the processing of project procurement have also been identified as a problem is some projects. Lastly, the hiring of a high number of individual consultants was identified as a source of fiduciary risk. In order to add transparency to Bank operations and improve procurement performance, the GOA and the Bank developed and implemented the SEPA in 2007 and the set of procurement-related covenants spelled out in Section G was subsequently put in place.

(g) Control Environment: Control environment has somehow deteriorated in Argentina in recent years due to budget constraints and resignation of key members of control institutions.

- Based upon the above, the risk-mitigation measures that have been agreed are:

  - The grant agreement should include the Special Procurement Provisions listed in Section F.

  - The grant agreement should include the Covenants listed in Section G.

  - The staff in the procurement unit should participate in the Basic Procurement Training delivered by the Bank, either in the country or in any neighboring country.

  - Once the technical unit concludes the evaluation of the dimension and numbers of the firms interested in participating in the processes of consulting services under the project, as a result of advertise published in a web page (www.ambiente.gob.ar), the packaging of contracts should be reviewed in accordance with the market size.

The overall residual project risk for procurement is Substantial due to: i) DPCC’s lack of previous experience in Bank procurement, ii) the significant number of contracts to be carried out in a short time, though most of them are consulting services and thus simple and iii) country considerations.

C. Procurement Plan

- The Recipient has prepared a detailed Procurement Plan which confirms the readiness of the Project in terms of initiating procurement processes. During preparation, the Bank and the Recipient held several meetings to identify the best alternatives of procurement processes to facilitate a prompt start up of implementation. In addition, the Recipient made a market research to determine the potential supply of qualified consultant services and experts to cover Project needs. Although the evaluation of the research has not been finishing, more than 120 answers were received.

- The Procurement Plan for the first 18 months of the Project implementation has been agreed between the Recipient and the Project Team during Appraisal. This plan has identified about 50 procurement activities; most of them are hiring of consultant firms and individual consultants. In this initial plan, there are minor non-consulting services for workshops and dissemination activities.

- The Procurement Plan will be updated in agreement with the Project Team annually, or as required to reflect the actual Project implementation needs and improvements of institutional capacity.

- The Procurement Plan will be available in the SEPA web (www.iniciativasepa.org).

D. Frequency of Procurement Supervision

- In addition to the prior review supervision to be carried out from Bank offices, the capacity assessment of the DPCC has recommended one supervision missions to visit the field to carry out post review of procurement actions. The Bank’s expost review shall cover no less than 1 of 5 contracts signed.

E. Details of the Procurement Arrangements Involving International Competition

1. Goods and Non-Consulting Services

(a) List of contract packages to be procured following ICB: not foreseen.

(b) The first two (2) processes procured under each procurement method and all direct contracting will be subject to prior review by the Bank.

2. Consulting Services

(a) List of consulting assignments with short-list of international firms: not foreseen.

(b) Consultancy services estimated to cost above $200,000 per contract, the first three (3) contracts under each selection method and all single source selection of consultants (firms) will be subject to prior review by the Bank.

F.	Special Procurement Provisions

- The following shall apply to procurement under the Project:

General

- All procurement shall be done using SBD, standard requests for proposals, model bid evaluation forms, model proposal evaluation forms and contract forms previously agreed with the Bank. As for consultant services contracts, only the types of contracts listed in Section IV of the Consultant Guidelines may be used, and “Convenios” will not be permitted.

- Foreign and local contractors, service providers, consultants and suppliers shall not be required: (a) to register; (b) to establish residence in Argentina; or (c) to enter into association with other national or international bidders as a condition for submitting bids or proposals.

- The invitations to bid, bidding documents, minutes of bid opening, requests for expressions of interest and notifications of contract award of all processes aimed at the procurement of goods, works and services (including consultants’ services), as the case may be, shall be published in the web page of Oficina Nacional de Contrataciones in a manner acceptable to the Bank.

- The Recipient: (a) will feed the Bank publicly accessible Procurement Plans Execution System (SEPA) within 30 days of Loan Effectiveness with the information contained in the initial Procurement Plan, (b) will update the Procurement Plan at least every three months, or as required by the Bank, to reflect the actual Project implementation needs and progress, and shall supply the SEPA with the information contained in the updated Procurement Plan immediately thereafter.

- The Recipient will keep updated a list of contracts signed under the Project, and such list will be produced by the Recipient’s FM System known as UEPEX.

- Bidders and consultants shall not be allowed to review or make copies of others bidders’ bids or consultants’ proposals, as the case may be.

- Bidding documents for NCB shall include Anticorruption Clauses, including those that give the Bank audit rights over bidders, suppliers, contractors and consultants, acceptable to the Bank. These clauses shall be substantially identical to those pertaining to Bank SBD for ICB.

Goods, Non-Consultant Services and Works

- A two-envelop system of procurement will not be used for the procurement of goods, services (other than consultants services) or works.

- Contracts of goods, services –other than consulting services– and works shall not be awarded to the “most convenient” bid, but to the one that has been determined to be substantially responsive and the lowest evaluated bid, provided that further on, the bidder is determined to be qualified to perform the contract satisfactorily.

G.  Procurement-related Covenants

- In order to disseminate Project implementation requirements and procedures, and define roles, responsibilities, mechanisms, schedules and accountability arrangements, the Recipient will implement the Project following the stipulations of an Operational Manual (OM) acceptable to the Bank.  The OM will include, inter alia, the Project’s institutional arrangements and operational, accounting, procurement and disbursement procedures.

- The Executive Agency will operate and maintain a web page to disseminate its most significant Project information.

THIRD NATIONAL COMMUNICATION TO THE UNITED NATIONS FRAMEWORK CONVENTION ON CLIMATE CHANGE

Annex 9: Economic and Financial Analysis

Financial Issues

  - Argentina experienced mostly strong macroeconomic performance during the last 4 years. Consecutive years of rapid and pro-poor economic growth enabled poverty and unemployment be cut to pre-crisis levels at the end of the 90s. The economy benefited from a significant reduction of public debt following the 2005 sovereign debt restructuring. In 2008, however, the economy started to decelerate due to domestic and international factors. While the economy grew at a healthy rate of 7.0 percent in 2008, real GDP growth is projected to decline sharply due to weakening private demand both at domestically and externally.

  - This Project will be implemented during a time of economic uncertainty and volatility. Nevertheless, it is not expected that this context would affect Project implementation. The Grant Recipient will be the Argentine Republic, and the GOA, will implement the Project through the Secretariat of Environment and Sustainable Development (JGM). There are no fiscal constrains that would hamper the Grant passing to the national budget.

  - The Project will be funded by a GEF grant, and it will have a small (positive) budgetary impact. The national contribution will be in-kind, based on the costs involved in representatives from the PIU and from the Steering Committee (SC) preparing, guiding and monitoring the Project implementation. Office costs and other operating expenses are also covered by the national contribution.

- Economic Issues

  - As the Project consists of studies, it is not possible to estimate its economic impacts at this point, but the TNC will include the financial and economic analysis of the proposed mitigation and adaptation P&M identified and designed through the financed studies, thus facilitating decision-making and expected prompt implementation (see Components 1 and 2, and Annex 4 for more detailed information). The TNC will also contribute to the challenging task of determining economic losses associated with climate change impacts in Argentina through provision of new data and analysis on the complex linkages between sectors.

  - Costs of climate change impacts could be structured into two categories:

      - Related productivity losses: Weather changes affect temperature and hydrologic balance, and have influence on floods and economic activities such as agriculture and tourism. Argentina is one of the 14 countries of the world most affected by flooding events, reaching GDP losses greater than 1.1%. Impacts on agricultural production derived from climate change are difficult to ascertain, as production practices may help exacerbate or diminish climate impacts; soil salinization, and erosion are linked to poor irrigation and land management practices.

      - Economic costs associated with cleaner energy production and energy resulting from emission standards and regulation: High upfront costs and market and regulation barriers prevent investments in energy saving activities. Clean transport technologies involve higher costs than conventional ones, and they might not be recoverable in the short term without specific subsidies. While increasing frequency of storms causes flooding and damages physical assets, it can also deliver more freshwater as the storms move inland to replenish reservoirs including those for hydropower and recharge groundwater.

THIRD NATIONAL COMMUNICATION TO THE UNITED NATIONS FRAMEWORK CONVENTION ON CLIMATE CHANGE

Annex 10: Safeguard Policy Issues

- This Annex summarizes the key issues related with the Bank’s environmental and social safeguard policies triggered by the Project, and explains how these issues have been or are proposed to be addressed in this Project.

Environment

- The Project is a category C for environmental assessment purposes, consistent with the provisions of OP 4.01, because it does not create direct or induce indirect impacts on the environment. The Project implementation will not have an adverse environmental impact. No civil works or remediation activities are financed under the Project. Finally, identified mitigation and adaptation measures will reduce vulnerability of ecosystems and the national carbon footprint. The Project will not support engineering designs for physical works, but focus on designing of policy frameworks. No Project-specific designs or interventions would be financed, and instead technical assistance would be directed towards studies on vulnerabilities to climate change for different sectors. These results would then be used as inputs to later design work for specific interventions.

Social

- The Project is aimed at developing strategies and plans for both mitigation and adaptation; therefore, community and stakeholder participation is critical to ensure implementation and sustainability. Approximately 10% of the total Project budget has been assigned to raising public awareness. The GOA is also allocating significant funds for related education and general change in perception of the overall population. The Government has made plans to publish and distribute the TNC widely, further promoting communication and public awareness efforts. One of the Project objectives is to integrate climate change considerations into national planning. The Project will be coordinated by a Steering Committee, which will act to ensure participation by all stakeholders, and monitor the implementation. Public awareness activities, including seminars, workshops, and web-based discussion groups, will provide opportunities for wide public participation.

- Activities will also feature tailored messages targeted at specific audiences such as students, professionals, clubs, civil organizations, media personnel, community leaders, and others. The Project will develop a plan of public awareness and education for all. One of its objectives is to provide methodology and experience to NGOs for further action in the field of climate change. Project implementation also emphasizes participation through workshops and seminars. Informal meetings and discussions will be promoted between, among others, private sector and NGO representatives, national and regional public servants, academics, and CS leaders, to encourage exchange of information and collaboration. The TNC will involve participation of stakeholders from its inception to ensure an effective implementation at all levels of society.

- Finally, the measures identified to reduce vulnerability to climate change will benefit vulnerable populations helping them to cope with climate change impacts.

- All studies to be funded will mainstream the principles of Bank’s safeguards policies.

THIRD NATIONAL COMMUNICATION TO THE UNITED NATIONS FRAMEWORK CONVENTION ON CLIMATE CHANGE

Annex 11: Project Processing

|  | Planned | Actual |
| --- | --- | --- |
| PCN review | 05/28/2009 | 06/03/2009 |
| Initial PID to PIC |  |  |
| Initial ISDS to PIC |  | 06/30/2009 |
| Appraisal | 05/17-20/2010 | 05/17-20/2010 |
| Negotiations | 09/2010 |  |
| Board/RVP approval | 10/2010 |  |
| Planned date of effectiveness | 12/01/2010 |  |
| Planned date of mid-term review | 12/01/2011 |  |
| Planned closing date | 11/30/2012 |  |

Key institutions responsible for Project preparation:

Chief of the Cabinet of Ministers:

- General Administration and Technical Directorate. Contact: Mr. German Arribas, General Technical Administrative Director (arribasg@jgm.gov.ar)

- Secretariat of the Environment and Sustainable Development (SAyDS), CCD. Contact: Nazareno Castillo Marín. Climate Change Director (ncastillo@ambiente.gov.ar)

Bank staff and consultants who worked on the Project included:

| Name | Title | Unit |
| --- | --- | --- |
| Marcelo Acerbi | Environmental Specialist, TTL | LCSEN |
| Tuuli Bernardini | Climate Adaptation Specialist | LCSEN |
| Federico Scodelaro | Chemical Engineer, JPA | LCSEN |
| Seraphine Haeussling | Climate Change Consultant | LCSEN |
| Estela Santalla | Climate Change Consultant | LCSEN |
| Ana Grofsmacht | Procurement Analyst | LCSPR |
| Daniel Chalupowicz | Financial Management Analyst | LCSFM |
| Alejandro Alcala Gerez | Senior Counsel | LEGLA |
| Maria Emilia Sparks | Team Assistant | LCC7C |
| Sofia Alejandra García | Civil Engineer, JPA | LCSEN |
| Walter Vergara | Lead Chemical Engineer (Peer Reviewer) | ENV |
| Richard Hosier | Sr. Environmental Specialist (Peer Reviewer) | ENVGC |
| Richard Damania | Lead Environmental Economist (Peer Reviewer) | SASDI |

Bank funds expended to date on Project preparation: USD 22,457

Estimated supervision costs: USD 35,000

THIRD NATIONAL COMMUNICATION TO THE UNITED NATIONS FRAMEWORK CONVENTION ON CLIMATE CHANGE

Annex 12: Documents in the Project File

- World Bank. Integrated Safeguards Data Sheet. Argentina Third National Communication to the UNFCCC Project.

- GEF/World Bank. 2009. Project Identification Form. Argentina Third National Communication to the UNFCCC Project.

- Secretariat of Environment and Sustainable Development, Preparatory Workshops Reports. Third National Communication to the UNFCCC Project.

- Secretariat of Environment and Sustainable Development, Preparatory Workshops Reports. Second National Communication to the UNFCCC Project. Final Report.

List of reports prepared under the Second National Communication

- Jorge E. Roulette Foundation (Institute of Studies and Research in Environmental Sciences). 2007. Training Program.

- Girardín, O., 2007. Inventories. Bariloche Foundation. Final Report.

- Menendez, A. 2007. Vulnerability of the Coastal Zone. Torcuato Di Tella Foundation. Final Report.

- Nunez Mario 2007. Vulnerability of Buenos Aires Pampas. CIMA-CONICET-Hidroestructuras SA. Final Report.

- Magrin, G. 2007. Vulnerability of agriculture production in the Humid Pampas. Ecological Universal Foundation. Final Report.

- Garcia N, 2007. Vulnerability of Water Resources: Coastal and Mesopotamia. School of Engineering, Universidad del Litoral. Final Report.

- Barros, V.2007. Vulnerability of Patagonia and the Southern part of the Provinces of Buenos Aires and La Pampa. Torcuato Di Tella Foundation. Final Report.

- Lara, A. 2007. Social and Economics Impacts of Climate Change. Serman y Asociados. Final Report..

- Flory, L. 2007. Vulnerability of Energy Sector and Energy Infrastructure. 2007. SORS SA.

- Kullock, D.2007. National Adaptation Program and Regional Adaptation Planning. Torcuato Di Tella Foundation.

- Nunez, M.2007. Estimation of Regional Climate Scenarios from Regional Climate Models. CIMA-CONICET. Innova-T Foundation.

- Rosenfeld, E. et al. Energy Efficiency Measures. Institute of Habitat Studies. IDEHAB. School of Architecture and Urbanism .Universidad Nacional de La Plata. Final Report.

- Ravella, O. 2007. Transport Sector. Institute of Habitat Studies (IDEHAB). School of Architecture and Urbanism Department. Universidad Nacional de La Plata. Final Report.

- Moregues, J. 2007. Renewable Energy.  Moragues-Rapallini Consultantes. Final Report.

THIRD NATIONAL COMMUNICATION TO THE UNITED NATIONS FRAMEWORK CONVENTION ON CLIMATE CHANGE

Annex 13: Statement of Loans and Credits

|  |  |  | Original Amount in US$ Millions |  |  |  |  |  | Difference between expected and actual disbursements |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Project ID | FY | Purpose | IBRD | IDA | SF | GEF | Cancel. | Undisb. | Orig. | Frm. Rev’d |
| P117377 | 2010 | AR Prevention & Management of Influenza | 229.00 | 0.00 | 0.00 | 0.00 | 0.00 | 138.43 | 32.13 | 0.00 |
| P116989 | 2010 | AR-Road Safety | 30.00 | 0.00 | 0.00 | 0.00 | 0.00 | 30.00 | 0.00 | 0.00 |
| P095485 | 2010 | AR Metropolitan Areas Urban Transport | 150.00 | 0.00 | 0.00 | 0.00 | 0.00 | 150.00 | 0.00 | 0.00 |
| P113896 | 2010 | AR San Juan SWAP | 50.00 | 0.00 | 0.00 | 0.00 | 0.00 | 50.00 | 0.00 | 0.00 |
| P101171 | 2009 | AR SOC&FISC NTL ID SYS II | 20.00 | 0.00 | 0.00 | 0.00 | 0.00 | 17.03 | 5.35 | 0.00 |
| P105680 | 2009 | AR(APL1) Matanza-Riachuelo Development | 840.00 | 0.00 | 0.00 | 0.00 | 0.00 | 840.00 | 0.00 | 0.00 |
| P106684 | 2009 | AR 2nd Prov Agric Dev | 300.00 | 0.00 | 0.00 | 0.00 | 0.00 | 269.25 | 21.42 | 0.00 |
| P106752 | 2009 | AR Unleashing Productive Innovation | 150.00 | 0.00 | 0.00 | 0.00 | 0.00 | 137.16 | -12.47 | 0.00 |
| P110462 | 2009 | AR Mining Environmental Restoration Proj | 30.00 | 0.00 | 0.00 | 0.00 | 0.00 | 30.00 | 0.00 | 0.00 |
| P115183 | 2009 | AR Basic Protection Project | 450.00 | 0.00 | 0.00 | 0.00 | 0.00 | 4.58 | -42.62 | 0.00 |
| P100806 | 2008 | AR Sustainable Natural Res Mgt | 60.00 | 0.00 | 0.00 | 0.00 | 0.00 | 58.22 | 17.37 | 0.00 |
| P099051 | 2007 | AR- SANTA FE ROAD Infrastructure | 126.70 | 0.00 | 0.00 | 0.00 | 0.00 | 62.14 | 60.00 | 0.00 |
| P099585 | 2007 | AR-Cordoba-Road Infrastructure | 75.00 | 0.00 | 0.00 | 0.00 | 0.00 | 13.39 | 11.06 | 0.00 |
| P101170 | 2007 | AR 2nd State Modernization | 20.00 | 0.00 | 0.00 | 0.00 | 0.00 | 12.20 | 7.74 | 0.00 |
| P105288 | 2007 | AR APL2 Buenos Aires Infrastructure | 270.00 | 0.00 | 0.00 | 0.00 | 0.00 | 192.68 | 69.01 | 0.00 |
| P095569 | 2007 | AR APL2 National Highway Asset Mgt | 400.00 | 0.00 | 0.00 | 0.00 | 0.00 | 307.47 | 274.81 | 0.00 |
| P095515 | 2007 | AR (APL2) Prov Maternal-Child Health | 300.00 | 0.00 | 0.00 | 0.00 | 0.00 | 214.87 | 135.47 | 0.00 |
| P095514 | 2007 | AR Lifelong Learning Project | 200.00 | 0.00 | 0.00 | 0.00 | 0.00 | 146.63 | 18.30 | 0.00 |
| P090993 | 2007 | AR-Essential Public Health Functions | 220.00 | 0.00 | 0.00 | 0.00 | 0.00 | 93.56 | 46.89 | 0.00 |
| P070963 | 2006 | AR Rural Education Improvement Project | 150.00 | 0.00 | 0.00 | 0.00 | 0.00 | 93.82 | 93.82 | -56.03 |
| P070448 | 2006 | AR Subnational Gov Public Sec Modernizat | 40.00 | 0.00 | 0.00 | 0.00 | 0.00 | 34.71 | 33.11 | 0.00 |
| P060484 | 2006 | AR Basic Municipal Services Project | 110.00 | 0.00 | 0.00 | 0.00 | 0.00 | 96.20 | 66.15 | 0.00 |
| P089926 | 2006 | AR Solid Waste Management Project | 40.00 | 0.00 | 0.00 | 0.00 | 0.00 | 33.55 | 27.95 | 0.00 |
| P092836 | 2006 | AR Inst. Strengthening - ANSES II TA | 25.00 | 0.00 | 0.00 | 0.00 | 0.00 | 17.32 | 16.32 | 0.00 |
| P093491 | 2006 | AR (APL2)Urban Flood Prev.&Drainage | 70.00 | 0.00 | 0.00 | 0.00 | 0.00 | 57.58 | 57.75 | 0.00 |
| P088220 | 2005 | AR (APL1)Urban Flood Preven&Drainage | 130.00 | 0.00 | 0.00 | 0.00 | 0.00 | 91.93 | 88.89 | 0.00 |
| P088032 | 2005 | AR(CRL1)Buenos Aires Infrastr SIDP(1APL) | 200.00 | 0.00 | 0.00 | 0.00 | 0.00 | 5.36 | 5.36 | -13.49 |
| P070628 | 2005 | AR-Provincial Road InfrastructureProject | 325.00 | 0.00 | 0.00 | 0.00 | 0.00 | 230.94 | 45.84 | 0.00 |
| P071025 | 2004 | AR-Provincial Maternal-Child Hlth Inv Ln | 135.80 | 0.00 | 0.00 | 0.00 | 0.00 | 3.45 | 3.45 | 0.00 |
| P088153 | 2004 | AR National Highway Asset Management | 200.00 | 0.00 | 0.00 | 0.00 | 0.00 | 9.79 | 9.79 | 0.00 |
| P006043 | 1999 | AR RENEW.ENERGY R.MKTS | 80.00 | 0.00 | 0.00 | 0.00 | 0.00 | 50.36 | 0.49 | -0.93 |
| P006041 | 1998 | AR SMALL FARMER DV. | 120.00 | 0.00 | 0.00 | 0.00 | 0.00 | 27.13 | -17.87 | 9.63 |
| P039584 | 1997 | AR B.A.URB.TSP | 300.00 | 0.00 | 0.00 | 0.00 | 0.00 | 50.08 | -49.92 | -49.92 |
| P006010 | 1997 | AR PROV AG DEVT I | 162.00 | 0.00 | 0.00 | 0.00 | 0.00 | 8.31 | -28.60 | 8.40 |
|  |  | Total: | 6,008.50 | 0.00 | 0.00 | 0.00 | 0.00 | 3,578.14 | 996.99 | - 102.34 |

Argentina

STATEMENT OF IFC’s

Held and Disbursed Portfolio

In Millions of US Dollars

|  |  | Committed |  |  |  | Disbursed |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | IFC |  |  |  | IFC |  |  |  |
| FY Approval | Company | Loan | Equity | Quasi | Partic. | Loan | Equity | Quasi | Partic. |
| 2000 | ASF | 3.76 | 0.00 | 0.00 | 3.85 | 3.76 | 0.00 | 0.00 | 3.85 |
| 1998 | AUTCL | 4.28 | 0.00 | 0.00 | 0.00 | 4.28 | 0.00 | 0.00 | 0.00 |
| 2004 | Aceitera General | 50.00 | 0.00 | 20.00 | 30.00 | 50.00 | 0.00 | 20.00 | 30.00 |
| 2006 | Arcor | 70.00 | 0.00 | 0.00 | 210.00 | 70.00 | 0.00 | 0.00 | 210.00 |
| 2000 | BACS | 0.00 | 6.25 | 0.00 | 0.00 | 0.00 | 6.25 | 0.00 | 0.00 |
| 2006 | BACS | 50.00 | 0.00 | 0.00 | 0.00 | 13.25 | 0.00 | 0.00 | 0.00 |
| 1999 | Banco Galicia | 57.79 | 0.00 | 0.00 | 40.91 | 57.79 | 0.00 | 0.00 | 40.91 |
| 2005 | Banco Galicia | 40.00 | 0.00 | 0.00 | 0.00 | 5.00 | 0.00 | 0.00 | 0.00 |
| 1997 | Bunge-Ceval | 0.00 | 0.00 | 5.00 | 0.00 | 0.00 | 0.00 | 5.00 | 0.00 |
| 2006 | CAPSA | 50.00 | 0.00 | 0.00 | 20.00 | 50.00 | 0.00 | 0.00 | 20.00 |
| 1995 | CEPA | 3.00 | 0.00 | 0.00 | 1.20 | 3.00 | 0.00 | 0.00 | 1.20 |
| 1998 | F.V. S.A. | 1.50 | 0.00 | 4.00 | 0.00 | 1.50 | 0.00 | 4.00 | 0.00 |
|  | Grupo Galicia | 0.00 | 3.06 | 0.00 | 0.00 | 0.00 | 3.06 | 0.00 | 0.00 |
| 1998 | Hospital Privado | 8.40 | 0.00 | 0.00 | 0.00 | 8.40 | 0.00 | 0.00 | 0.00 |
| 1992 | Huantraico | 0.00 | 27.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 |
| 2004 | Jumbo Argentina | 0.00 | 39.12 | 0.00 | 0.00 | 0.00 | 39.12 | 0.00 | 0.00 |
|  | LD Manufacturing | 0.00 | 0.00 | 5.00 | 0.00 | 0.00 | 0.00 | 5.00 | 0.00 |
|  | Milkaut | 0.00 | 1.23 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 |
| 1997 | Milkaut | 5.33 | 0.00 | 9.44 | 1.44 | 5.33 | 0.00 | 9.44 | 1.44 |
| 1993 | Molinos | 0.00 | 2.00 | 0.00 | 0.00 | 0.00 | 2.00 | 0.00 | 0.00 |
| 1994 | Molinos | 0.00 | 0.57 | 0.00 | 0.00 | 0.00 | 0.57 | 0.00 | 0.00 |
| 1996 | Neuquen Basin | 0.00 | 26.40 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 |
| 1999 | Neuquen Basin | 0.00 | 5.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 |
| 2006 | Noble Argentina | 18.00 | 0.00 | 0.00 | 18.00 | 15.00 | 0.00 | 0.00 | 15.00 |
| 2005 | PAE - Argentine | 105.50 | 0.00 | 15.00 | 135.00 | 103.53 | 0.00 | 15.00 | 135.00 |
| 1998 | Patagonia | 1.76 | 0.00 | 1.00 | 0.00 | 1.76 | 0.00 | 1.00 | 0.00 |
| 1998 | Patagonia Fund | 0.00 | 8.54 | 0.00 | 0.00 | 0.00 | 1.65 | 0.00 | 0.00 |
| 1999 | S.A. San Miguel | 2.76 | 0.00 | 0.00 | 0.00 | 2.76 | 0.00 | 0.00 | 0.00 |
| 2005 | S.A. San Miguel | 20.62 | 0.00 | 0.00 | 10.00 | 17.29 | 0.00 | 0.00 | 8.33 |
| 1995 | SanCor | 8.70 | 0.00 | 19.89 | 0.00 | 8.70 | 0.00 | 19.89 | 0.00 |
|  | Socma | 7.00 | 0.00 | 0.00 | 0.00 | 7.00 | 0.00 | 0.00 | 0.00 |
| 1995 | Socma | 0.94 | 0.00 | 0.00 | 15.00 | 0.94 | 0.00 | 0.00 | 15.00 |
| 1997 | T6I | 3.33 | 0.00 | 5.00 | 3.75 | 3.33 | 0.00 | 5.00 | 3.75 |
| 1997 | Terminal 6 | 3.33 | 0.00 | 0.00 | 1.63 | 3.33 | 0.00 | 0.00 | 1.63 |
| 1995 | Terminales Port. | 0.50 | 0.00 | 0.00 | 0.00 | 0.50 | 0.00 | 0.00 | 0.00 |
| 2000 | Tower Fund | 0.00 | 0.85 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 |
| 1995 | Tower Fund Mgr | 0.00 | 0.05 | 0.00 | 0.00 | 0.00 | 0.05 | 0.00 | 0.00 |
| 1996 | Transconor | 4.20 | 0.00 | 0.00 | 157.58 | 4.20 | 0.00 | 0.00 | 157.58 |
| 2001 | USAL | 9.27 | 0.00 | 0.00 | 0.00 | 7.27 | 0.00 | 0.00 | 0.00 |
| 2005 | Vicentin | 20.00 | 0.00 | 15.00 | 0.00 | 0.00 | 0.00 | 15.00 | 0.00 |
| 1993 | Yacylec | 0.00 | 2.52 | 0.00 | 0.00 | 0.00 | 2.52 | 0.00 | 0.00 |
|  | Total portfolio: | 549.97 | 122.59 | 99.33 | 648.36 | 447.92 | 55.22 | 99.33 | 643.69 |

|  |  | Approvals Pending Commitment |  |  |  |
| --- | --- | --- | --- | --- | --- |
| FY Approval | Company | Loan | Equity | Quasi | Partic. |
| 2001 | ITBA | 0.01 | 0.00 | 0.00 | 0.00 |
| 2001 | Gasnor | 0.02 | 0.00 | 0.00 | 0.02 |
| 2006 | Arcor Swap | 0.00 | 0.00 | 0.00 | 0.00 |
| 2004 | Banco Rio TFF | 0.02 | 0.00 | 0.00 | 0.05 |
| 2005 | Vicentin Exp. | 0.00 | 0.00 | 0.00 | 0.05 |
|  | Total pending commitment: | 0.05 | 0.00 | 0.00 | 0.12 |

THIRD NATIONAL COMMUNICATION TO THE UNITED NATIONS FRAMEWORK CONVENTION ON CLIMATE CHANGE

Annex 14: Country at a Glance

THIRD NATIONAL COMMUNICATION TO THE UNITED NATIONS FRAMEWORK CONVENTION ON CLIMATE CHANGE

Annex 15: Consultation Meetings - List of Institutions Represented in the TNC Preparation Process

(Meetings coordinated by CCD during September 26, 27 and October 20, 2009)

- Chamber of Exporters of the Argentine Republic (Cámara de Exportadores de la República Argentina-CERA)

- Consultative Council of Civil Society, Chancellery. (Consejo Consultivo de la Sociedad Civil, Cancillería)

- Climatology, University of Buenos Aires.(Cátedra de Climatología, Universidad de Buenos Aires-UBA)

- National Center of Patagonia, National Center of Scientific and Technical Research (CONICET). (Centro Nacional Patagónico, Consejo Nacional de Investigaciones Científicas y Técnicas -CONICET)

- Argentine Center of Engineers.(Centro Argentino de Ingenieros)

- Center of Climate and Atmosphere Research, University of Buenos Aires. (Centro de Investigaciones del Clima y Atmósfera, Univerisdad de Buenos Aires)

- Trade and Sustainability ( Comercio y Sustentabilidad)

- Ituzaingó Ecological Commission (Comisión Ecológica Ituzaingó)

- National Atomic Energy Commission (Comisión Nacional de Energía Atómica)

- Argentine Business Council for Sustainable Development -Consejo Empresario Argentino para el Desarrollo Sostenible (CEADS)

- Regional Center of Scientific and Technological Research, CONICET. (Centro Regional de Investigaciones Científicas y Tecnológicas, CONICET)

- Secretariat of Environment and Sustainable Development (Secretaría de Ambiente y Desarrollo Sustentable)

- Agricultural Experimental Station, INTA Faimallá, Tucumán. (Estación Experimental Agrícola, INTA Famaillá, Tucumán)

- School of Agronomy, University of Buenos Aires. (Facultad de Agronomía, Universidad de Buenos Aires)

- School of Natural Sciences and Mathematics, University of Buenos Aires. (Facultad de Ciencias Exactas y Naturales,Universidad de Buenos Aires)

- School of Engineering,  University of Buenos Aires (Facultad de Ingeniería, Universidad de Buenos Aires)

- School of Engineering, National University of the Center of Buenos Aires Province. (Facultad de Ingeniería, Universidad Nacional del Centro de la provincia de Buenos Aires)

- School of Veterinary, University of Buenos Aires. (Facultad de Veterinaria, Universidad de Buenos Aires)

- FOROBA

- Bariloche Foundation. (Fundación Bariloche)

- Eco Andina Foundation. ( Fundación Eco Andina)

- UOCRA Foundation. ( Fundación UOCRA)

- Pro Yungas Foundation.( Fundación ProYungas)

- Arrayanes Group (Grupo Arrayanes)

- Health and Environment Group, UOCRA Foundation. (Grupo de Salud y Medio Ambiente, Fundación UOCRA)

- Institute of Snow, Glaciology and Environmental Sciences of Argentine. (Instituto Argentino de Nivología, Glaciología y Ciencias Ambientales- CONICET)

- National Institute of Water. (Instituto Nacional del Agua)

- Argentine Institute of Portland Cement.( Instituto Cemento Porland Argentino)

- National Institute of Agricultural Technology. (Instituto Nacional de Tecnología Agropecuaria)

- Ministry of Sciences and Technology, Secretariat of Planning and Policy in Sciences and Technology and Productive Innovation, National Department of International Relations. (Ministerio de Ciencia y Tecnología: Secretaria de Planeamiento y Políticas en Ciencia, Tecnología e Innovación Productiva, Dirección Nacional de Relaciones Internacionales)

- Ministry of Defense, National Weather Service. (Ministerio de Defensa, Servicio Meteorológico Nacional)

- Ministry of Economics, Secretariat of Economics Policy. (Ministerio de Economía, Secretaría de Política Económica)

- Ministry of Education.(Ministerio de Educación)

- Ministry of Foreign Affairs, International Trade and Religion.(Ministerio de Relaciones Exteriores, Comercio Internacional y Culto)

- Ministry of Health, Epidemiology Department.(Ministerio de Salud, Dirección de Epidemiologia)

- Ministry of Labor, Sub Secretariat of Employment. (Ministerio de Trabajo, Secretaria de Empleo)

- CLARIS LPB Project Hydroclimate and Society in La Plata Basin-EU FP7 Collaborative Project.

- Secretariat of Agriculture. (Secretaría de Agricultura)

- Secretariat of Energy. (Secretaría de Energía )

- Secretariat of Industry, Trade and Small and Medium Enterprises.(Secretaría de Industria, Comercio y PYMES)

- Secretariat of Labor Health and Environment, General Confederation of Workers of the Argentine Republic (Secretaría de Salud Laboral y Medio Ambiente, Confederación General de Trabajadores de la República Argentina )

- Secretariat of Transport. (Secretaría de Transporte)

- “Light and Force” Labor Union, General Confederation of Workers of the Argentine Republic. (Sindicato Luz y Fuerza, Confederación General de Trabajadores de la República Argentina.)

- Argetine Catholic University (Universidad Católica Argentina).

- Argentine Industrial Union.(Unión Industrial Argentina)

- Hydroclimate Research Unit, School of Engineering and Water Sciences, School of Engineering. National University of Litoral. (Unidad de investigación en Hidroclimatología, Universidad Nacional del Litoral)

- National University of Cuyo Region. (Universidad Nacional de Cuyo).

- National University of La Matanza. (Universidad Nacional de La Matanza).

- National University of Rio IV. (Universidad Nacional Río IV).

- National University of La Plata. (Universidad Nacional de La Plata)

- National University of General San Martin. (Universidad Nacional de General San Martín).

- National Technological University. (Universidad Tecnológica Nacional).

THIRD NATIONAL COMMUNICATION TO THE UNITED NATIONS FRAMEWORK CONVENTION ON CLIMATE CHANGE

Annex 16: Comparison between the Scope of the Second National Communication and the Proposed Project

- This annex compares the scope of the SNC with the proposed scope for this Project. The TNC will contribute new and more detailed data per relevant sectors based on the results of the SNC, which developed a GHG Inventory for 2000 and revised the inventories for 1990, 1994 and 1997.

- The TNC will be the framework to:

- Compile, standardize and record relevant data per sectors

- Determine local emission factors for the main economic activities in Argentina

- Develop methodologies to determine the carbon footprint of strategic products

- Develop proxy indicators to facilitate subsequent updating of the data

- Establish mechanisms to facilitate public disclosure and diffusion of the generated information

- Strengthen capacities to develop GHG inventories

- Establish procedures for quality control and processing of data and information

- The main outputs from the SNC and how the TNC envisions building on those are described in the following table:

| Issue | Outputs form the SNC | Contributions from the proposed Third National Communication |
| --- | --- | --- |
| Specific studies | - Energy efficiency measures - Mitigation of emissions in transport sector and through renewable energies - Mitigation through carbon capture - ERs of enteric methane | Advances in technical, economic, financial, social and environmental studies on supply and demand of energy, transport, fugitive emissions in gas and oil sectors, agriculture, industry, forestry and waste management in order to identify the most cost-efficient mitigation measures for the high-emitting sectors. |
| Climate model | A regional climate model | Assembling and downscaling of available models at national and subnational level, and introduction of temporal horizons. |
| Vulnerability | Development of a high resolution regional circulation model in the “Centro de Investigaciones de Mar y Atmósfera” (CIMA) that will be of used for further vulnerability assessments. | Spread out development of vulnerability studies to eco-regions, and identify critical ecosystem services and needs for natural resource management. Specific studies related to agricultural production systems (meat, dairy products, and fruits), health, urban areas, tourism, hydric resources and employment. Near future climate projections and related impact assessments for the 2020s and 2050s will be performed based on refining the model developed under the SNT. |
| Adaptation | Development of the National Program of Adaptation. Regional Plans of Adaptation were created but no specific adaptation actions have been implemented. Adaptation has mostly taken place in an autonomous, unplanned manner particularly in the agricultural sector. | Based on the National Program of Adaptation and Regional Plans of Adaptation, the TNC will develop a set of specific studies on topics such as early alert systems, technologies for adaptation in the agricultural sector, infrastructure to prevent urban flooding, land use planning, tourism, strengthening of public health systems, hydric resource management for energy and agricultural purposes, and proper mechanisms for necessary transition in the labor sector. These studies will contribute to development of adaptation measures and policies to help the country to cope with anticipated impacts of climate change. |
| Socio-economic scenario | A socioeconomic study | One of the main objectives to be achieved through the TNC is to determine national socio-economic scenarios in order to evaluate the impact of and vulnerability to the different CC scenarios based on climate models. For this purpose, the Project will focus in identification and assessment of information to elaborate a socio-economic scenario, standardization of statistics, to recognize internal and external strengths related with evolution of the socio-economic sectors, and to develop an economic reference scenario and its projection over time. |
| P&M | Identified priorities to translate the assessments into concrete sectoral actions. However, the integration of these actions into sectoral development strategies and assess their economic, environmental and social impacts remain pending. | The TNC will focus on designing P&M for adaptation based on: - Impact and vulnerability assessments and identified opportunities for adaptation - GHG inventories and identified opportunities for mitigation - Analysis of the integration of P&M and sectoral development strategies and programs - Analysis of the economic, social and environmental impacts of implementing the identified P&M on the socio-economic reference scenario. |
| Training | Implemented a training program for teachers including educational activities and publishing of manuals for pupils and teachers. | The TNC will emphasise strengthening of institutional capacities to promote information dissemination and application of results of the proposed studies. The following activities have been planned: - Promote wide participation of involved parties in the elaboration of CC related P&M - Coordination and organization of related workshops with participation of governmental agencies, scientific and technical institutions, teachers and CS. - Dissemination of documents prepared under the TNC. - Developing of mechanisms to assist provincial and municipal governments to facilitate the incorporation of CC in their programs and plans. - Training on technological needs assessment and climate observation systems. |

THIRD NATIONAL COMMUNICATION TO THE UNITED NATIONS FRAMEWORK CONVENTION

ON CLIMATE CHANGE

Annex 17: Sectoral Programs under Development by the GOA Related with the Goals
of the Third National Communication Project

| Agency | Law/Resolution | Title Plan/Program | Summary | Links to CC | Current status and link to TNC |
| --- | --- | --- | --- | --- | --- |
| Secretariat of Agriculture | National Law 26.093. Res 7/2010 | National Program of Biofuels | Promotes the production and sustainable use of biofuels, emphasizing the use of biofuels from vegetable oils and animal fats, and of bioethanol from sugar cane, corn and sorghum production. | Contributes to displacement of fossil fuels. | The GoA started implementation of replacement of fossil fuels in the Transport Sector in January 2010. Results of this policy will be the input for the development of new technologies and studies under a sustainable criteria proposed in TNC (Component 1, Subcomponent 2). |
|  |  | Assistance to Small Producers to Achieve Environmental Protection (CAPPCA) | Develops sustainable production systems in degraded areas and promotes sustainable forestry practices. Assistance proposed to 2,000 small producers. | Regenerates degraded areas through sustainable production systems and forestation. | Results of this program were published in http://www.MAGyP.gob.ar/SAGPyA/programas/CAPPCA/02-Resultados/index.php. GoA pretends to continue strengthening of human resources to promote sustainable forestry practices. TNC will contribute to extend this policy to a higher number of small producers as proposed in Component 1, Subcomponent 2, Agriculture and Forestry Sector. |
|  | Res. 246/2007 | National Cattle Plan | Improves the efficiency of the livestock production and the supply of meat to assure a suitable provision to internal and external market. | It should be studied if the promoted efficiency measures contribute to decrease GHG emissions. | TCN will contribute to identify the impact of climate change in livestock producers and the particularly vulnerable regions and production systems on cattle raising activities, of particular importance for regional economies and Argentina´s export sector. |
|  |  | Program of Provincial Agricultural Services PROSAP | Improves infrastructure and agricultural services in order to increase competitiveness in a framework of equity and sustainability, exports and employment. | It should be studied if the promoted measures contribute or could contribute to decrease GHG emissions. | This program is ongoing. Partial outcomes (http://www.prosap.gov.ar/) have demonstrated improvements in agricultural services administration, including incorporation of Quality systems in the sector. Activities proposed in TNC related to mitigation and adaptation agenda in the agriculture and forestry sector will contribute to keeping up the achieved performance and to advance on new capacity building. |
|  | Law 26432 (extent and reform of Law 25080/1998) | Investment in Cultured Forest | Promotes investments in new forestry enterprises and extending existing forests with an objective of increasing wood supply through forestation. | It should be studied if the promoted measures and forestation contribute or could contribute to decrease GHG emissions and/or improve carbon sequestration. | The law did not achieve the expected results and was extend for an additional period of 10 years. Activities proposed in TNC Component 1, Subcomponent 2 will contribute to improve technical and economic issues in forestry sector. |
| Secretariat of Energy | Decree 140/2007 | National Program for Rational and Efficient Use of Energy (PRONUREE) | The GoA launched in 2007 this national program as part of the energy sector strategy to counter supply/demand imbalance. The program aims to promote the rational and efficient use of energy and includes: - Energy efficiency in industries - Labelling of energy efficiency - Regulation framework - Public Lighting and Semaphorization | Actions proposed to save energy consumption acknowledge the connection between energy efficiency and sustainable development, including the reduction of GHG. | The program is ongoing through implementation of specific plans such as PIEEP (for industry), Replacement of Incandescent Lamps in residential users, Public Lighting and Semaphorization, Residential energy consumption. The expected results are the saving of energy consumption (http://energia3.mecon.gov.ar/contenidos/verpagina.php?idpagina=2842). TCN will contribute to the action plan proposed under this program in other sectors such as transport, buildings and other industrial sectors (see Component 1, Subcomponent 2, Mitigation options in the industrial sector) |
|  |  | Energy Saving and Efficiency Program (PAyEE) | The National Directorate of Promotion of the Subsecretary of Electric Energy (Secretariatof Energy) creates the PAEEE in order to develop methodologies for studies on energy efficiency in buildings, necessary regulations, proper technologies for each region of the country, as well as programmed experience to apply in different climate zones. GoA through the Secretariat of Energy launched in 2003 this first program that included a number of strategic areas including development of regulatory framework, institutional strengthening, economic incentives, financial mechanisms, energy efficiency research and development and information systems regarding energy efficiency technologies. This was followed by the Program for the Rational Use of Energy (PURE) launched in 2004. | This is a climate-friendly measure of energy efficiency. | The program is ongoing. The Secretary of Energy has conducted a Preliminar Diagnosis of Potential Energy Saving (http://energia3.mecon.gov.ar/contenidos/archivos/DIAGNOSTICO%20PRELIMINAR%20DE%20POTENCIALES%20PAEEP.pdf) that will be the input for the proposed actions of TCN described in Component 1, Subcomponent 2, paragraph 9, energy efficiency in residential and commercial buildings. There is also a GEF project linked to this program. |
|  |  | Project of Energy Efficiency in Argentina. GEF | The objective is to increase the efficiency in the use of energy by developing a sustainable and growing market for energy efficiency services and equipment in Argentina | The global objective of the project is to reduce GHG emissions by removing the regulatory, financing, and informational barriers that prevent activities and investments in energy efficiency and energy conservation. This is a climate-friendly measure of energy efficiency. |  |
|  |  | Program for Rational Use of Electricity (PUREE) | Promotes the rational use of electricity based on an incentive program. Contributes to solve occasional problems of supply and preserve natural renewable resources. The program encourages residential users to save energy so that it would be available for commercial, industrial and economic activities. | By reducing energy consumption and decreasing energy demand at the Electricity Wholesale Market, the program achieves GHG ERs. | The program is ongoing. The program incentivates the reduction of electricity consumption of residential users through bonifications and additional charges and is applied on all the companies responsible of the distribution of energy (Edenor, Edesur and Edelap). Bonifications or additional charges are calculated on kWh consumption and are accredited/charge on the energy invoices. GoA is applying this program since 2005 and is expected that continuous this policy. Studies proposed in TNC focused on technical, economic and regulatory aspects of effectiveness of mitigation options will emphasize the main objective of this program. |
|  |  | Program for Rational Use of Natural Gas (PURE) | This program was launched in 2004 by the GoA and is an incentive-based program. Electricity and natural gas users were required to save at least 5% in 2004 compared with their in 2003 level of consumption; any consumption above the quota was subject to penalties and actual savings were rewarded. Promotes saving of energy restraining constant increase of internal demand for natural gas in a framework of shortage of the resource. | Reducing consumption of natural gas GHG emissions are expected to decrease as well. | The program is ongoing. The impact has been limited, particularly in the residential sector. TCN will contribute through its Component 1 Subcomponent 2 Energy Sector, to generate a proper energy consumption database including industrial groups characterization based on their energy consumption patterns in order to optimize the natural gas consumption of the different sectors. |
|  |  | National Plan of Emissions Mitigation through Development of Renevable Energy | - Identify potential opportunities for GHG ERs through the use of renewable energy - Identify national and provincial governments that promote development of renewable energy production - Propose design options for promotion and increased the use of renewable energy sources | Closely related to CC as focused on GHG ERs. | See at “PRONUREE”. |
|  | National Law 25.019 Res. 333/2001 | National Regime for Wind and Solar Energy | Guarantees an extra AR$ 0.03 per kWh provided by wind and solar energy sources to the Electricity Wholesale Market or to a public service, and secures fiscal stability for 15 years. | The law represents an incentive to produce clean energy. Ultimate results will reduce GHG emissions from fossil fuels use. | The law is applied in all projects that generate energy through wind and solar resources. Actions planned in TCN related to the identification of potential and barriers associated with the development and use of RREE will contribute to reinforce the application of this law along the country. |
|  |  | Program for Increased Productive and Energy Efficiency of Small and Medium Sized Enterprises (SME) (PIEEP) | Improves competitiveness of SMEs promoting implementation of Energy, Production and Environmental Management practices. | The program focused in the promoting of energy efficiency in three industrial sectors: sugar, citric and milk production that at last with contribute to mitigate GEIs from these sectors. | The program has finished. Results of expected outcomes are published in http://energia3.mecon.gov.ar/contenidos/verpagina.php?idpagina=2518 TCN will contribute to extend the outcomes of this program in other industrial SME sectors of interest for the competitiveness improvement of the country by using the capacity building yet developed. |
|  |  | Program for Quality of Electrical Devices (PROCAE) | Focuses in reduction of electricity consumption through the use of efficient electrical devices. The Secretary of Energy is promoting a labeling program which in its first stage will force refrigerator manufacturers to exhibit the energy efficiency profile of each device. | This is a climate-friendly measure of energy efficiency. | The program focuses on its first stage in the labeling of energy efficiency of refrigeration products. TCN will contribute to extend this action plan to a wider range of industrial manufacturing. |
|  |  | Project of Renewable Energies in Rural Markets (PERMER) | Focuses on electricity supply for a significant number of people living in rural areas as well as for approximately 6,000 public institutions (schools, health services, police, etc.). | The project supplies renewable energy sources, including solar panels to small populations. | The project is ongoing. Activities have delivered electricity through descentralized system to rural schools and households in Chaco, Jujuy, Misiones, Neuquén, Salta, Santiago del Estero y Tucumán (http://energia.mecon.gov.ar/permer/Estado.html) . Expected results will contribute to identify barriers that prevent the development and use of RREE for both integrated and isolated system along the country and to advance in the support of policy development proposed in TNC. |
|  | Res. 459/2007 and Res. 121/2008 | Total Energy Program | This program was launched in July 2007 by the GoA through the Ministry of Federal Plannification, Public Investment and Services. The objective was to incentivate the replacement of natural gas and electricity consumptions by the use of renewable fuels in productive activities and electricity generation. | Implies displacement of fossil fuels since it is expected the reduction of 5 M cubic meters of natural gas. | The program was launched for a period of 90 days in a context of an energy deficit. |
|  | Law 26190/2006 | Promoting the use of RREE for electricity production | Achieves a 8% contribution of renewable energy sources of the national electricity consumption in the period of 10 years from the beginning of this regime. | The law has a national objective to increase participation of renewable energies in the electric matrix. | The law is under execution. Through the GENREN framework the national energy company ENARSA has received at January 2010 the proposal of 1,470 MW for electricity generation based on RREE, mainly wind energy. Activities proposed in TNC in Energy Sector will contribute to integrate different RE technologies in order to diversify the energy matrix of the country reinforcing the proposals of this national law. |
|  | Law 26123/2006 | Hydrogen Promotion | Promotes development of technology, production, use and applications of hydrogen as a fuel and energy vector. | Promotes the use of hydrogen as an energy source. |  |
| Secretariat of Environment and Sustainable Development (SAyDS) |  | Credits to SMEs for Environmental Reconversion | Promotes sustainable development of SMEs through soft credits aimed at solving current problems in industrial sectors and optimizing and converting processes to achieve improvements in environmental performance. | New technologies should contribute to decrease GHG. | The TNC will contribute with a menu of mitigation options for the sector. |
|  |  | Office of Credits and Certifications | Manages the financial programs the SAyDS provides for enterprises, including the emission certificates that allow access to credits. | New technologies should contribute to the decreasing GHG emissions. | The Office is not operative for financing of programs. There are no credits available for this purpose. |
|  | Law 26331. Decree 91/2009 | Forests Law | Establishes the minimal requirements of environmental protection for enhancement, restoration, conservation, development and sustainable management of native forests and their environmental services. This Law originated the “National Program of Native Forest Protection”. | Tends to achieve a sustainable management of native forest avoiding deforestation and assuring protection of indigenous communities. |  |
|  | Res. 177/2007, 303/2007 and 1639/2007; 1398/2008 | Environmental Secure | Determines the activities dangerous for environment, and which could be forced to contract an environmental insurance. | The instrument focuses on determining responsibilities for repairing possible damage to enhance prevention and mitigation. |  |
|  |  | National Plan of Industrial Reconversion (PNRI) | Sets up sectoral priorities to approach activities implying higher environmental impacts, such as paper manufacturing, production of sugar, citrics, oil, and chemicals, metal refinement, meat processing, and tannery. | The measures should include best available technologies for GHG mitigation. | The Plan in ongoing focusing on two most affected basins: Salí Dulce and Matanza-Riachuelo. The plan established national priorities in sugar cane, pulp and paper, citric, oil, chemistry, galvanoplasty, slaughter house and tanning activities. TCN will contribute to this program with specific actions as described in Component 1, Subcomponent 2, paragraph 9 Energy point g Mitigation options in the industrial sector paragraph 10 Waste point a Mitigation actions in the waste/wastewater sector and Component 3 Institutional Strengthening, Capacity Building and Information Management. |
|  |  | National Project for Integral Solid Waste Management (PNGIRSU) | Implements integral solutions for the management of solid waste through sustainable projects from a federal perspective. | Focuses in the elimination of open dumps and inappropriate measures of MSW and final disposal allowing GHG capture and enhancing capacity to develop energy projects based on landfill gas. |  |
|  |  | Social Program of Forests | Offers technical and financial assistance for restoring projects and sustainable development of native forests aimed at increasing the national forested areas and thus helping rural communities to avoid uprooting. | Promotes the sustainable use of forested area. |  |
|  |  | National Program against Desertification (PAN) | Aims at overcoming desertification and mitigating effects of drought to contribute to sustainable development of affected zones in order to improve quality of life of implied communities. | Desertification is one of the expected impacts of temperature increases together with associated decreasing of water provision, amongst others. |  |
|  | Res. ACUMAR 8/2007 |  | Represents a set of actions to preserve and repair the Matanza Riachuelo Basin, including approximately 22,000 square kilometers where drains 64 km of Matanza and Riachuelo rivers. | Manufacturing industries that discharge effluents on this basin do not apply proper systems for wastewater treatment, thus causing contamination and GHG emissions. |  |
| Secretariat of Public Works Ministry of Federal Planning, Public Investment and Service |  | Flooding Prevention and Urban Drainage Program | This program was lunch by the GoA through the Ministry of Federal Planification, Public Investment and Services through a BIRF loan (7382-AR) in 2007. It aimes at reducing vulnerability of participating provinces (Misiones, Corrientes, Santa Fe, Chaco, Entre Ríos) to flooding through strengthening their capacities to face emergencies caused by flooding, reduce risk of flooding, implement a housing program that will help less well off population to live in flooding areas, and strengthen protection against flooding in geographical areas with high economic activity and vulnerable to recurrent flooding. | The project seeks to decrease the vulnerability to CC. | TNC through Component 2, Subcomponents 1 and 2 (paragraph 28) will help to implement specific actions on the current program. |
|  |  | Federal Housing Plan (IRAM?) | Proposes construction of 120,000 housing units in a short time as long as the official plans related to IRAM standards are accomplished; training of personnel on control, management, and adaptation by the offering enterprises to assure construction under standards of energy efficiency. | Efficient construction will reduce the consumption of energy per household, and thus contribute to decreasing the use of fossil fuels and subsequent GHG emissions. |  |
|  |  | Emergency Program, 2nd Emendation | Focuses on protection and rehabilitation of urban infrastructure, and mitigates effects in agricultural zones. | This program is an adaptation measure, since it reinforces more resistant urban infrastructure in terms of increasing frequency of extreme climate events. |  |
|  |  | Plan for Hydrological Protection for Delta Islands | Focuses on generation of evacuation centers and transportation to continental areas facilitating moving of productive instalations. | In spite it is not a measure for solving the problem it is a tool for inhabitants to mitigate the adverse effects of flooding. |  |
|  | Decree 1381/2001 | Hydrological Infrastructure Trustee | Affects development of infrastructure of hydric works to repair productive soils, prevent flooding in rural areas, and protect road and railway infrastructure. It will be implemented under the Federal Plan of Flooding Control | Constitutes a tool for repairing degraded zones after extreme climate events. |  |
| National Water Institute |  | Hydrologic Alert System for del Plata Basin | This is a national program developed during the 1982-1983 flooding. The system provides forecasts of river level along the coast of del Plata basin and also for fluvial navigation. | This is a tool to improve management of climate phenomena oriented to support related decision making. | Activities proposed in TCN related to adaptation in urban areas (Component 2, Subcomponents 1 and 2 (paragraph 28) will strengthen the activity of this system on the most vulnerable areas. |
| Provincial Directorate of Public Sanitation and Hydrological Works (Buenos Aires) |  | Integral Master Plan of Salado Basin | GoA has launched this master plan in order to increase the capacity of the Salado river, to achieve the recovery of productive areas and promoting biodiversity. Focuses on mitigation of damage caused by flooding and drought, including periodical revision of future climate scenarios. | Activities proposed will improve the environmental of the basin, recovering biodiversity and natural resources from degraded areas. | The plan is in his third phase of implementation and it is expected the recovery of lands for agriculture, cattle and milk production. Under this context, TNC will assist in the actualization of the plan through the evaluation of vulnerability including social aspects, the development of good practices, options for conservation and restoration between others. |
| Subsecretariat of Hydrological Resources |  | National Federal Plan of Water Resources | The management of water resources pertains to each provincial jurisdiction, but it is coordinated through the Federal Water Council. This plan promotes planning, coordination and reduction of risk of conflicts under the plan. The plan includes “Tools for Management” and “Tools for Management of Climate Change”. | Prevention of flooding and draught, provision of safe water, threat of sustainability of water resource by contamination and overexploitation are the main goals of this plan that seeks to decrease the vulnerability to climate change. | Activities proposed in TNC will improve the actions proposed in this plan by prioritizing the eco-system services in crucial local and regional areas and by identifying technological alternatives for facing climate change impacts on river basins and on regional economies. |

THIRD NATIONAL COMMUNICATION TO THE UNITED NATIONS FRAMEWORK CONVENTION ON CLIMATE CHANGE

Annex 18: Maps (to be completed)

SRES (Standard Reference Emission Scenarios) were prepared by the IPCC in 2001.  The worst case scenario, A1FI, assumed business as usual and runaway expansion in the use of fossil fuels.

Further, a new generation of climate simulations is expected to be available by the World Climate Research Program (WCRP) at global scale during the TNC implementation period, thus contributing to more accurate climate projections on which to base decision-making on climate-related issues.

One of the main concerns when preparing this Communication and also for meeting further commitments to the UNFCCC was the generation of information and knowledge in Mexico, as well as capacity building on topics such as climate variability and climate change. In order to achieve this, first a survey was carried out to create a database of academic institutions, research and development centers, private manufacturing centers and other organizations that are working on climate change and climate variability. This database helped to identify the topics studied by each group and institution, document the financial sources in use, evaluate the research potential and limitations in the country, and define the research priorities for the following years. The database also included information about 74 graduate programs available in the country, which are related to the field of climate change. This information helped in the development of a National Climate Change Strategy. Also, as part of this national effort to support, promote and develop research activities in the field of climate change, a seminar on Research Priorities in Climate Change was held, where over 70 experts and government officials attended. The conclusions of this seminar were also included in the Communication. An environmental research fund (Fondo Sectorial de Investigación Ambiental) was created, which included, among other fields, funds for climate change research as a priority area. Finally, a series of prizes and awards were instituted, which included the National Energy Savings Award; the National Energy Savings Award for the Public Administration, and others. These awards serve to encourage climate change related projects and research.

The environmental priorities described above are from the report “Policy of State” from the Presidency of the Nation of Argentina. http://www.casarosada.gov.ar/index.php?option=com_content&task=view&id=24&Itemid=34#j

Based on national development priorities, the GOA has identified five key sectors on which the TNC will focus in terms of climate change mitigation. The Project will identify mitigation options for these sectors based on their technical and economic aspects, and further, propose mitigation policies and measures. These P&M, before becoming concrete proposals, will go through an evaluation of their social, economic, and environmental impacts. This process will serve prioritizing of mitigation action, including those that could be linked to the sectors with the lowest abatement cost.

* By supporting the proposed Project, the Bank does not intend to prejudice the final determination of the parties' claims on the disputed areas.

See footnote number 9.

As defined in the detailed M&E plan in the Operational Manual: e.g. convening sectoral or cross-sectoral meetings on specific climate-related policy issues; widening up sectoral representation in climate-related events; parliamentary discussion initiatives, etc.

As per assessment of the Project Steering Committee.

As defined in the detailed M&E plan in the Operational Manual: e.g. convening sectoral or cross-sectoral meetings on specific climate-related policy issues; widening up sectoral representation in climate-related events; parliamentary discussion initiatives, etc.

This includes, inter alia, economic, social, cultural and environmental aspects, as relevant for each sector.

As defined in the detailed M&E plan in the Operational Manual: 0-25% unsatisfactory; 25-50% moderate; 50-75% satisfactory, and 75-100% highly satisfactory.

As defined in the detailed M&E plan in the Operational Manual: e.g. convening sectoral or cross-sectoral meetings on specific climate-related policy issues; widening up sectoral representation in climate-related events; parliamentary discussion initiatives, etc.

As defined in the detailed M&E plan in the Operational Manual: e.g. convening sectoral or cross-sectoral meetings on specific climate-related policy issues; widening up sectoral representation in climate-related events; parliamentary discussion initiatives, etc.

This includes, inter alia, economic, social, cultural and environmental aspects, as relevant for each sector.

As defined in the detailed M&E plan in the Operational Manual: 0-25% unsatisfactory; 25-50% moderate; 50-75% satisfactory, and 75-100% highly satisfactory.

See footnote 22.

See footnote 22.

Based on national development priorities, the GOA has identified five key sectors on which the TNC will focus in terms of climate change mitigation. The Project will identify mitigation options for these sectors based on their technical and economic aspects, and further, propose mitigation policies and measures. These P&M, before becoming concrete proposals, will go through an evaluation of their social, economic, and environmental impacts. This process will serve prioritizing of mitigation action, including those that could be linked to the sectors with the lowest abatement cost.

The TOR for the Biofuels study will request to explore both the benefits and the costs in greater detail in the Argentinean context.

The TOR will emphasise focus on the efficiency of Government Buildings or Public Housing which are generally the two substantial elements of the building sector where a government can play a direct and significant role.

Although the description is mainly focused on estimations of burnt sugar cane biomass, it would also consider possibilities to avoid in-field burning through use of whole-cane, mechanized harvesting. In addition, it could explore the potential of co-generation of steam and electricity using sugar cane milling waste such as bagasse, leaves and stems.

There is an important ongoing IBRD cooperation with Argentina in the field of forestry management. Two important past Bank operations and a third on-going one have provided support for the country to develop its forest inventory and relevant data and information for forest management. Implementation of this Project will also coincide with the Readiness Preparation Proposal submitted to the FCPF by Argentina that will complement the necessary counterpart resources.

A possible selection criteria for the options to be developed into detailed P&M could be, among others, the criteria used by the Mexico Low Carbon Growth Study: 1) CO2 emissions reduction (ER) potential – in Mexico, the established ER threshold was 5 MtCO2 ER by 2030; 2) Low cost per reduced ton of CO2e: accept only interventions with positive economic and social rates of return with a given discount rate or cost of capital, and an abatement cost of USD 25 or less per ton of CO2e reduced were considered (“no-regret” interventions with positive net benefits); 3) Feasibility of implementation determined by sector experts who took into consideration technical potential, market development, and institutional needs, and by government officials who considered the political and institutional feasibility of scaling up interventions across the economy. Further, before adopting an intervention, public discussion with sector experts, government officials, private sector, and civil society would take place.

The World Bank has gained an ample experience in the region regarding climate change impacts in the agricultural sector, e.g. through the Climate Change and Agricultural Vulnerability across Mega-environments in Latin America Project.

For adaptation, uncertainty and the long time horizon of climate impacts suggest that priorities could be defined in terms of irreversibility, magnitude and immediacy of impacts. This would argue for giving precedence to issues such as (irreversible) land use changes, and the impacts on durable assets with long lives (e.g. infrastructure). These criteria will be taken into account when preparing the TORs for studies.

The Ministry of Economy, Secretariat of Economic Policy has accepted to be a member of the Steering Committee. The participation of this Secretariat is of special importance for the Project implementation and beyond in terms of potential adoption of key P&M proposals of the TNC, including budgetary implications. This Secretariat is in charge of coordinating design, elaboration and proposals of strategic guidelines for programming economic policy. It’s also in charge of policy, plan and programme related impact assessments in the Ministry.

Detailed description of th ese functions and the division of responsibilities will be included in the Operational Manual.

TAC members could play a key role in disseminating the TNC results through the institutions they represent.

To be confirmed with LOA

To be confirmed with LOA

CCD: Climate Change Direction

JGM: Chief of the Cabinet of Ministers

DPCC: Direction of Budget, Procurement and Contracts

AGN: Auditoría General de la Nación

SIGEN: Sindicatura General de la Nación

For example, the Operational Manual, Bidding Documents and Standard Request for Proposal, technical background, designs, terms of reference of the works to be executed with Project funds; agreements with third parties and progress and monitoring reports.