GEF-6 Request for One-step medium-sized project APPROVAL

Type of Trust Fund: GEF Trust Fund

For more information about GEF, visit TheGEF.org

PART I: Project Identification

| Project Title: | Promoting Climate-smart Livestock Management in the Dominican Republic |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Country(ies): | Dominican Republic |  | GEF Project ID: |  |  |  |
| GEF Agency(ies): | FAO |  | GEF Agency Project ID: |  |  | 645733 |
| Other Executing Partner(s): | Ministry of Environment and Natural Resources (MARENA); Ministry of Agriculture (DIGEGA – CONALECHE) |  | Submission Date: |  |  | 4 June 2018 |
| GEF Focal Area(s): | Climate Change |  | Project Duration (Months) |  |  | 36 |
| Integrated Approach Pilot | IAP-Cities IAP-Commodities IAP-Food Security |  |  |  |  |  |
| Name of Parent Program: | N/A | Agency Fee ($) |  |  | 146,356 |  |

A.  Focal AREA STRATEGY Framework and Program:

| ### Focal Area Objectives/programs | ### Focal Area Outcomes | ### Trust Fund | ### (in $) |  |
| --- | --- | --- | --- | --- |
|  |  |  | ### GEF Project Financing | ### Co-financing |
| CCM-2 Program 4 | Outcome A. Accelerated adoption of innovative technologies and management practices for GHG emission reduction and carbon sequestration. Outcome B. Policy, planning and regulatory frameworks foster accelerated low GHG development and emissions mitigation. | GEFTF | 1,540,586 | 8,141,408 |
| Total project cost |  |  | 1,540,586 | 8,141,408 |

- Project Framework

| ### Project Objective: To mitigate climate change and to restore degraded lands through the promotion of climate-smart practices in the livestock sector, whilst focusing on family farming. |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| ### Project Components/ ### Programs | ### Financing Type | ### Project Outcomes | ### Project Outputs | ### Trust Fund | ### (in $) |  |
|  |  |  |  |  | ### GEF Project Financing | ### Confirmed Co-financing |
| Component 1: Institutional and financial strengthening to support a low-emissions livestock development pathway | TA | Outcome 1.1: The national institutional capacity strengthened to support the implementation of a climate-smart livestock management strategy. Indicator 9 (CCM): Degree of support for low GHG development in the policy planning and regulatory framework Indicator 11 (CC): Strengthening of Financial and Market Mechanisms. | Output 1.1.1: A climate-smart livestock management (CSLM) strategy, designed, agreed and disseminated with public and private actors in the livestock sector of the Yuna Watershed. Output 1.1.2: Public-Private partnerships designed to: i) pilot incentives, financial and market instruments, ii) enhance watershed management; and iii) implement the CSLM strategy. Output 1.1.3: National and local public officials trained to effectively support the implementation of the CLSM strategy with a gender perspective Target: 6 national agencies and 6 local institutions Output 1.1.4: A national CSLM strategy based on the lessons learned from the pilot intervention in the Yuna river, defined and agreed among key stakeholders. | GEFTF | 191,206 | 54,628 |
|  |  | Outcome 1.2: Knowledge shared and dissemination of lessons learned to support the CSLM strategy dissemination. Indicator: Number of visits to the platform | Output 1.2.1: An operational technical platform for the livestock sector, which includes information on monitoring, evaluation, dissemination of experiences and lessons learned. |  |  |  |
| Component 2: Climate-smart livestock management in the field: Technology Transfer, Deployment and Validation of Practices | TA | Outcome 2.1: Farm-level technologies have been implemented, promoting sustainable and low-emission livestock production Indicator 1 (CCM): t CO2e directly and indirectly reduced or avoided Indicator 4 (CCM): Deployment of low GHG technologies and practices | Output 2.1.1: A CSLM strategy with a gender sensitive approach tested and implemented at farm level, incorporating mechanisms of financial incentives and market access. Targets: 3000 hectares, 500 family farmers in the Yuna Basin, Output 2.1.2: A capacity development program for dairy and beef producers to support the adoption of CSLM technologies and good practices at the farm level. Target: 3000 hectares,77,000 animals, 700 family farmers | GEFTF | 658,080 | 6,721,559 |
|  |  | Outcome 2.2: Field technical capacities have been improved to disseminate CSLM and low- emission production models in targeted areas. Indicator: 30 extension officers (25 men and 5 women) trained in the application of low emission practices | Output 2.2.1: An extension program with a gender sensitive approach strengthened to support the promotion and implementation of the CSLM strategy and low-emission livestock models. Output 2.2.2: Business Plans with a gender perspective, aimed at public programs or development/commercial banks, and certification schemes, to implement the CSLM Strategy |  |  |  |
| Component 3: Monitoring, Reporting and Verification of the Livestock sector | TA | Outcome 3.1: GHG emissions from the livestock sector integrated into the Monitoring, Reporting and Verification National System Indicator 10 (CCM) An MRV system for the livestock sector emissions installed and reporting verified data | Output 3.1.1: An MRV system for measuring emissions and reporting data for the livestock sector Output 3.1.2: Farm-level monitoring system to monitor GHG emissions, strategies, financing and land degradation | GEFTF | 375,053 | 1,061,160 |
| Component 4: Project Monitoring, Evaluation and Knowledge Management | TA | Outcome 4.1: Project implementation based on RBM and lessons learned/good practices documented and disseminated. Indicator: Number of the M&E system reports; number of regular meetings of the executive committee and advisory committee | Output 4.1.1: Project Monitoring & Evaluation Plan and system, in place Output 4.1.2: Project Mid-term review and Final Evaluation. Output 4.1.3: Dissemination and communication products Output 4.1.4: A Communication Strategy implemented, including project website | GEFTF | 176,193 | 30,000 |
| Subtotal |  |  |  |  | 1,400,533 | 7,867,347 |
| Project Management Cost (PMC) |  |  |  |  | 140,053 | 274,061 |
| Total GEF Project Financing |  |  |  |  | 1,540,586 | 8,141,408 |

- Sources of Co-financing for the project by name and by type

Please include confirmed co-financing letters for the project with this form.

| Sources of Co-financing | Name of Co-financier | Type of Co-financing | Amount ($) |  |
| --- | --- | --- | --- | --- |
| Recipient Government | Ministry of Environment and Natural Resources (MARENA) | Cash | 1,000,000 |  |
| Recipient Government | Ministry of Environment and Natural Resources (MARENA) | In-Kind | 98,550 |  |
| Recipient Government | Ministry of Agriculture | In-Kind | 156,460 |  |
| GEF Agency | FAO | In-Kind | 60,000 |  |
| Recipient Government | DIGEGA | In-Kind | 95,100 |  |
| Recipient Government | Banco Agricola | Cash | 5,142,857 |  |
| Recipient Government/Private | CONALECHE | Cash | 1,256,545 |  |
| Recipient Government/Private | CONALECHE | In-Kind | 132,176 |  |
| Recipient Government | IDIAF | In-Kind | 146,160 |  |
| Private Sector | FEGACIBAO | In-Kind | 53,560 |  |
| Total Co-financing |  |  |  | 8,141,408 |

- Trust Fund Resources Requested by Agency(IES),  Country(ies), Focal Area and Programming of Funds

| GEF Agency | Trust Fund | Country/ Regional/Global | Focal Area | Programming of Funds | (in $) |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | GEF Project Financing (a) | Agency Fee a) (b) | Total (c)=a+b |
| FAO | GEF TF | Dominican Republic | CCM | N/A | 1,540,586 | 146,356 | 1,686,942 |
| Total Grant Resources |  |  |  |  | 1,540,586 | 146,356 | 1,686,942 |

- Refer to the Fee Policy for GEF Partner Agencies.

- Project’s Target Contributions to Global Environmental Benefits

Provide the expected project targets as appropriate.

| Corporate Results | Replenishment Targets | Project Targets |
| --- | --- | --- |
| - Maintain globally significant biodiversity and the ecosystem goods and services that it provides to society | Improved management of landscapes and seascapes covering 300 million hectares | hectares |
| - Sustainable land management in production systems (agriculture, rangelands, and forest landscapes) | 120 million hectares under sustainable land management | hectares |
| - Promotion of collective management of transboundary water systems and implementation of the full range of policy, legal, and institutional reforms and investments contributing to sustainable use and maintenance of ecosystem services | Water-food-ecosystems security and conjunctive management of surface and groundwater in at least 10 freshwater basins; | Number of freshwater basins |
|  | 20% of globally over-exploited fisheries (by volume) moved to more sustainable levels | Percent of fisheries, by volume |
| - 4. Support to transformational shifts towards a low-emission and resilient development path | 750 million tons of CO2e mitigated (includes both direct and indirect) | 958,054 metric tons |
| - Increase in phase-out, disposal and reduction of releases of POPs, ODS, mercury and other chemicals of global concern | Disposal of 80,000 tons of POPs (PCB, obsolete pesticides) | metric tons |
|  | Reduction of 1000 tons of Mercury | metric tons |
|  | Phase-out of 303.44 tons of ODP (HCFC) | ODP tons |
| - Enhance capacity of countries to implement MEAs (multilateral environmental agreements) and mainstream into national and sub-national policy, planning financial and legal frameworks | Development and sectoral planning frameworks integrate measurable targets drawn from the MEAs in at least 10 countries | Number of Countries: |
|  | Functional environmental information systems are established to support decision-making in at least 10 countries | Number of Countries: |

- Does the project include a “non-grant” instrument?    No

(If non-grant instruments are used, provide an indicative calendar of expected reflows to your Agency and to the GEF/LDCF/SCCF/CBIT Trust Fund) in Annex B.

N/A

- Project preparation grant (ppg)

Is Project Preparation Grant requested? Yes    No  If no, skip item G.

PPG  Amount requested by agency(ies), Trust Fund,  country(ies) and the Programming  of funds*

| GEF Agency | Trust Fund | Country/ Regional/Global | Focal Area | Programming of Funds | (in $) |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | PPG (a) | Agency Fee (b) | Total c = a + b |
| FAO | GEF TF | Dominican Republic | Climate Change | N/A | 50,000 | 4,750 | 54,750 |
| Total PPG Amount |  |  |  |  | 50,000 | 4,750 | 54,750 |

part ii:  project JustiFication

- Project Description. Briefly describe: a) the global environmental and/or adaptation problems, root causes and barriers that need to be addressed; b) the baseline scenario or any associated baseline projects, c) the proposed alternative scenario, GEF focal area strategies, with a brief description of expected outcomes and components of the project, d) incremental/ additional cost reasoning and expected contributions from the baseline, the GEFTF, LDCF/SCCF, CBIT and co-financing; e) global environmental benefits (GEFTF), and adaptation benefits (LDCF/SCCF); and 6) innovation, sustainability and potential for scaling up.

## a. The global environmental and/or adaptation problems, root causes and barriers that need to be addressed

The agricultural sector is a traditional pillar of the Dominican economy contributing to food security, employment, hard currency generation, and the production of raw materials for other industries.   The sector is considered a driver for poverty reduction in rural zones of the country.  Based on the Dominican Central Bank and the World Bank, the agricultural sector (including livestock, forestry, fishing, and agriculture itself) accounts for 7.6% of GDP of which 3.9% relates to livestock activities, 3.6% to agriculture, and 0.03% to forestry.  The growth rate of this sector has fluctuated over the last 10 years (2002-2011) oscillating between 3.7% (Ministry of Agriculture 2012) and 7% as cited above.

Agricultural production exerts pressure on natural resources such as soil, water, forest and biodiversity.  In the Dominican Republic, this pressure is deeply affecting upstream basins. The poverty level in mountainous regions is 67% (population living below the poverty-line), indigence is 21%, illiteracy rate among indigent people is near 91.8% (91.2% of men and 92.3% of women.  The main source of income of this population is traditional and subsistence agriculture (mainly rain-fed crops, cattle breeding, and others), which is done on poor soils and with inappropriate techniques for crop production and cattle breeding.  It is well documented that the production model in upstream basins, based on cutting down and burning trees, contributes to deforestation, soil erosion, basin pollution, dam sedimentation and destruction of endemic species’ habitats.

Traditional bovine production has centered on the unregulated and extensive use of pastures, which translates into pasture degradation, soil compaction and erosion, especially considering that 67 % of cattle farms apply “open-pasture” techniques (IICA, 2006). The ongoing use of traditional production systems leads to low levels of productivity and efficiency related to the exploitation of productive resources such as: humans, natural (soil, water, and forest), markets and economies.  In that regard, it should be noted that productivity levels for dairy cattle (including double purpose) of 5.5 liters/cow/day (baseline PROLEFAM, 2014), while in beef daily weight gains are below 300 grams/day, translating into a fattening period greater than 48 months for a steer until slaughter.

While the economic growth of the sector is moderate (between 3.7% and 4.4% per annum) there is a lack of understanding of the quantity of soil or water resources needed to sustain it due to knowledge gaps.  In certain watersheds of the country where land use change has been documented, such as the Artibonite’s River Basin (GEF-PNUD, 2014) and the Plan Sierra for the northern part of the Yaque del Norte River, there is strong evidence of a transition from agriculture towards livestock. In different surveys done for those initiatives, the teams documented unreliable rainfall and an increasing demand for meat as drivers of change. Logically, farmers are mitigating risks with changes in their land-use patterns.

In addition to the environmental problems of a local nature described above, bovine production generates two other problems of global importance: it is an important source of greenhouse gases and causes land degradation. These problems are described below:

Greenhouse Gas Emissions (GHG) According to the latest National Greenhouse Gases Inventory (INGEI) based in 2010, the agricultural sector of the Dominican Republic  is responsible for 7 million tons of CO2eq per year, equivalent to 20% of total emissions. These emissions concern methane and other GHGs released during agricultural activities, including the raising of livestock and the cultivation of rice and other products. According to the Economic Development Plan Compatible with Climate Change (Plan DECCC, in Spanish) of the Dominican Republic, under the premises of a trend scenario, emissions from the sector are expected to increase by 20% in the next 20 years, equivalent to 9 million tons of CO2 eq. in 2030. Despite having a growth rate significantly slower than projected for other key sectors, the agricultural sector is projected to contribute 18% of total emissions in 2030 and would continue to be the third main source of GHG emissions in the country.

| Inefficient livestock production is the one of the main factors for the high methane emissions in the agricultural sector. Livestock produces a significant amount of methane due to enteric fermentation and manure management, which represent 82% of total agricultural emissions (INGEI, 2015 base 2010). Particularly, emissions for bovine cattle in the Dominican Republic are estimated at 5.7 million tons of CO2 eq/year.  According to data generated by FAO’s Global Livestock Environmental Assessment Model (GLEAM, 2017), GHG emissions vary by production system as follows: 73% (4.6 million tons of CO2 eq.) of total emissions come mixed cattle production systems, while the remaining 27% comes from livestock pasture systems.  In all systems, methane generated by enteric fermentation constitutes the main source of emissions:  between 73% and 88%.  In systems based on pasture, N2O emissions have a significant contribution of greenhouse gases: 20% and 16% of emissions from beef and dairy cattle, respectively.

Land Degradation The livestock sector is an important driver for land degradation. The unsustainable management of livestock production in large pasture areas of the country has caused continuous land degradation. Traditionally, herd management does not take into account the impact of animals on vegetation, land or soil. Limited pasture rotation and high carrying capacity have resulted in compaction, loss of fertility, and soil erosion. The practices also cause losses of organic matter in the soil and, therefore, the release of CO2 into the atmosphere. An indicator of this degradation is the increase of herbaceous and stoloniferous grasses (which are better adapted to such grazing conditions) and the lower frequency of bunch grasses, as well as a reduction in the number of species. It has been observed that such changes in botanical composition result in a 12% reduction of annual forage production.

Although land degradation rates and pasture have been reduced over the past 25 years, many of the activities that make up current production systems pose new environmental challenges that must be addressed in a sustainable development context. It is important to highlight that land degradation and the consequent loss of productivity of pastures and nutritional quality lead to loss of productivity in animal production. Loss in productivity not only erodes farmers' incomes but also contributes to higher GHG emissions per unit of product, given the inverse relationship between herd productivity and the intensity of GHG emissions (FAO, 2013).

Barriers that need to be addressed While numerous efforts have been made, there are multiple barriers that impede the livestock sector’s advance towards climate smart livestock management and reductions of carbon and water footprints, land conservation, as well as the protection of water resources and biodiversity. The main barriers to the sustainable management of the livestock sector can be summarized as: (i) Lack of integrated policies and weak coordination in the livestock sector - the climate change mitigation focus is missing, (ii) Lack of information regarding livestock sector, (iii) Limited knowledge management capacities at institutional level, (iv) Limited technical and management  capacities of producers, (v) Limited access to markets and financing for climate-smart investments. These barriers are better described below:

(i) Lack of integrated policies and weak coordination in the livestock sector - the climate change mitigation focus is missing

One of the most important barriers to the limited progress of the livestock sector towards sustainability, including climate change mitigation and land degradation, is the development of an integrated policy for the sector, based on consensual concepts among the key players. Although there are sectoral initiatives, these are not well coordinated between the ministries involved and other institutions of the public sector, producer and civil society organizations, academic and research organizations, and international cooperation institutions. .

MARENA and the Ministry of Agriculture currently do not have specific operational mechanisms to inter-relate climate change and livestock management issues. Neither protocols, nor tools – including logistics – are in place to facilitate this cooperation among ministries. Therefore, the production and environment sides remain as thematic silos with no cross-feeding in the field.  In addition, there is an absence of strategies and plans that foster collaboration among the ministries. Policies remain sectorial, and no cross-cutting policies dealing with climate change and environment are in place.

Furthermore, there is a lack of coordination between the ministries and the academia and the private sector. At present, no work plan is in place to address a short, medium and long-term strategy aimed at transforming livestock into a more sustainable and low-emission activity. The link between climate change research and livestock sector needs is weak at national level

This lack of coordination and consultation leads to duplication in some areas, while other problems are not addressed. In particular,  climate change mitigation has not been effectively addressed. It is also necessary to unify the criteria among key actors for an integrated development policy in the livestock sector, which should balance the social, economic and environmental pillars. This is currently lacking

(ii) Lack of information regarding livestock sector

The country has not conducted a livestock census since the 1980s, pointing to a notable gap in the comprehensive analysis of the sector. Land use change can generally be detected using GIS information. This observation draws attention to a clear trend in the transition from agriculture to livestock. Without the census, it is impossible to distinguish between areas of scrub used as pasture and other type of pastures, nor to distinguish between bovine and caprine pastures in the Dominican geographic systems. Although there is a pre-census process in progress, it is necessary to specify the geographical definition of grazing as land use. The scenario is further complicated by the tendency of designating any type of terrain as “scrubs” or “grassland”.

In the absence of reliable data on livestock, it is impossible to understand the trends in the livestock sector or make an assessment on the environmental impacts of the sector, neither an analysis of good practices to mitigate negative environmental impacts. Despite the estimates presented above, there is a considerable diversity of biophysical, socio-economic and demographic situations that characterize the livestock sector. This diversity of situations creates a gap in our understanding, which hinders the design and targeting of technical interventions and the development of financial mechanisms. Accounting and monitoring methodologies for carbon sequestration and GHG emissions have to be validated and adjusted to locally specific circumstances. These methodologies are essential to demonstrate the contributions of the sector to the achievement of the country's goals in reducing its GHG emissions. They are also necessary to implement innovative financing mechanisms based on good environmental management.

It is important to take into account that, in particular, there is limited data available regarding the involvement of women in cattle raising, considering that women are generally dedicated to the raising of small stock. Likewise, no specific studies have been carried out on the contribution and role of women in cattle raising at the national level. However, within the framework of the execution of the “PROLEFAM” family dairy project (2013-2015) executed by the National Council for the Regulation and Promotion of the Dairy Industry (CONALECHE) and the General Livestock Directorate (DIGEGA) of the Ministry of Agriculture, an analysis was made of the dairy sector in the provinces of Monte Plata, El Seibo, Hato Mayor and La Altagracia, where it was indicated that 5% of family farms are owned by women.

The existing capacities to estimate GHG emissions in the livestock sector consist of organizational structures and trained personnel to carry out GHG inventory, in addition to the collaboration among the institutions linked to the topic.

Regarding the level of governance, a Department of GHG Inventories belongs to the Directorate of Climate Change (MARENA). In addition, there is a Department of Risk and Climate Change in the Ministry of Agriculture, which has trained personnel. In the same way, the General Directorate of Livestock hosts a climate change focal point, who has been trained on GHG inventory work. In terms of personnel, in recent years 12 technicians have been trained from various institutions, with support from different initiatives, such as the CD REDD I and II of the Coalition for Rainforest Nations (CfRN). Also the Economic Development compatible with Climate Change (DECCC) Plan project, with the support of CfRN and GIZ.  Additionally, the REDD-Centro American Commission of Environment and Development (CCAD)-GIZ project trained on land use and land use change, and GHG inventories for the AFOLU sector, which includes the livestock area. The Report for Results-based REDD+ project is currently underway with the support of CfRN focusing on the development of national capacities in the field of REDD+. The FCPF Readiness Project provides extensive support in the establishment of a REDD+ environment in the country, which includes the assessment of livestock lands and the creation of an MRV system in the AFOLU sector.

(iii) Limited knowledge management capacities at the institutional level

At the central level, the government has made significant efforts to invest in the development of the sector. This is reflected in the baseline activities. However, there are certain needs to be strengthened.

- There are also a diversity of stakeholders with diverse interests and sectoral relationships. Within this complexity, there is ineffective coordination. The links between the Ministry of the Environment and Natural Resources (in-charge of policy and reporting to UNFCCC),  and the Ministry of Agriculture, the General Livestock Direction, and the Dominican Forestry and Agricultural Research Institute (IDIAF) are unclear.  Even though the institutional landscape has evolved in the last ten years, no agency handles complete information about its sector. The National Strategy for Strengthening Human Resources and Competencies to Advance in Green Development, Low Emissions and Weather Resistance (2012), highlighted that institutional capabilities for integrating climate change issues and sectorial strategies have to be strengthened. The MARENA and the Ministry of Agriculture would benefit from these  synergies, and these actions would lead to financial and technical efficiency.

(iv) Limited technical and management capacities of farmers

Good livestock practices have been studied in the Central America and Caribbean region, such as: breed improvement, appropriate use of vegetative cover, live fences, silvopastoral practices, and integration of other food sources. However, such practices are not adequately disseminated in the DR. The adoption rate among producers is about 21%, which is very low for an efficient technology transfer. The extension services provided by the Ministry of Agriculture and CONALECHE are very limited. Few  extentionists work in areas where livestock production takes place. Extension workers are neither up to-date nor trained in how to apply climate-smart livestock management practices.

(v) Limited access to markets and financing for climate-smart investments

The financial mechanisms of the livestock sector are inefficient. Due to limited technical and management capacities, the access of individual producers to cooperatives is limited. In many cases, business plans are based on erroneous assumptions about the producers’ capacities and access to markets. This entails a high rate of debt default, with serious consequences for producers and their families.. This high level of unpaid debt affects the overall effectiveness of CONALECHE portfolio and its reinvestment potential.

The livestock sector operates through credit programs managed by Banco Agrícola and CONALECHE. Additionally, some milk processing industries and savings cooperatives at the provincial and regional levels have specific credit programs to finance new technologies and improvements for livestock farmers. The Ministry of Agriculture also has a mechanism to mitigate the effects of climate disasters in the form of agricultural insurance.

As a Council whose purpose is to promote a national dairy policy, CONALECHE is chaired by the Ministry of Agriculture and is made up of the following institutions: Ministries of Public Health and Industry and Commerce, five producers federations, a producers cooperative, the most prominent milk processing company, representatives of medium- and small-scale dairy farming, the National Board of Cattle Ranchers, the Association of Milk Producers, the Dominican Agro-Business Board, Banco Agrícola and the Milk Importers.

CONALECHE receives its funding from the following sources: (a) a monthly contribution from the State from the proceeds of imports of dairy products; (b) a contribution from the producers for each liter of milk sold to the milk processing plants, manufacturers of cheese and other milk products; and, (c) a contribution from the processing plants for each liter of milk sold. Of all the proceeds CONALECHE receives, 50% is distributed in the form of loans to milk producers for the promotion and development of the national livestock sector, with soft rates and terms of up to twelve years. Additionally, 40% is destined to funding DIGEGA’s livestock and animal health extension programs; while the remaining 10% funds CONALECHE's administrative expenses the promotion of the consumption of milk and milk products.

The rate of past due and unpaid loans from the credit program averages 15%. CONALECHE also offers direct technical assistance on good manufacturing practices, quality and safety to dairy processing plants. Furthermore, it assists small dairy processors to obtain their sanitary registry, facilitating the commercialization of quality and innocuous dairy products. Currently, CONALECHE is coordinating actions to establish a registry of milk producers at the national level, information that will serve the present initiative in the Yuna basin to update the number of producers and, at the same time, to estimate and monitor the level of GHG emissions through the MRV system. This registry of dairy producers will contribute to closing the information gap identified as one of the barriers to the development of the livestock sector.

The lack of public-private partnerships (PPPs) is affecting the livestock sector, especially among family farmers.

PPPs would inject funds into the sector, under strict financial criteria and based on rigorous market studies. In addition, iinnovative mechanisms need to be developed in order to stimulate investment in climate-smart practices and technologies, for example, through incentive schemes for the provision of ecosystem services. This idea is further developed under Component 1.

The entities that are being considered to finance PPPs, with an aim to promote climate-smart livestock management, are those that process and market milk and meat at the national level. First, they would benefit from procuring products of better quality and at the same time, with a lower level of GHG emissions generated per unit of milk and meat marketed. They could encourage climate-smart livestock management, by paying differentiated prices to farms certified by the government as low in GHG emissions. Both, the MARENA and the Ministry of Agriculture, together with private companies (industries), can establish incentive mechanisms for providing ecosystem services, based on the good practices implemented by the farms to become climate-smart. Such initiatives could include planting trees, protecting riverbanks, managing solid waste (manure), improving productive efficiency, among others.

Project Intervention Area This project targets the Yuna Basin, which is  a priority watershed identified by the Ministry of the Environment and Natural Resources. It is one of the largest Dominican basins with an area of 5,498 km2, and a length of 201 Km and has 8 important tributaries: Yuna; Camú; Masipedro; Maimón; Chacuey; Cuaba; Blanco y Tireo.  Rainfall varies from 1700 mm/year to more than 2200mm/year in the Cordillera Central, the Dominican Republic’s central mountain range.  This rainfall pattern creates two high-water periods: one in the upstream zone south of Bonao, and one in the delta of the lower Yuna. The lower Yuna comprises the territories between several key rivers and Los Haitises or cockpit country (karst), where inundations are common from Nagua and Payabo rivers. The basin’s importance is related to its contribution to the preservation of numerous protected areas: Los Haitises; La Humeadora; Valle Nuevo; La Vega Vieja, Idelisa Bonnelly de Calventi, Scientific Reserve Las Neblinas; Ébano Verde Scientific Reserve; the Duarte Highway, Bao River and Mirador Del Valle. The basin also feeds three dams, (5.3 x 108 M3 of water, producing 43.000 KW) and houses a high diversity, with globally significant ecosystems in addition to food security and rural territorial development.

The estimated population in the basin territory reaches a total of 2,066,738 inhabitants, considering the municipalities that compose it, which represents 22.6% of the total population. According to the Atlas of Poverty in the Dominican Republic, at the provincial level, Monte Plata has the highest percentage of poor households with 70.1%, followed by Samaná, Sánchez Ramírez and Duarte with values between 40 and 50%. Monseñor Nouel, Hermanas Mirabal, Espaillat, La Vega and Santiago all show levels of poverty between 20 and 30% (Morillo, 2014). In general, UNDP Human Development Index (HDI, 2017) is categorized as a low average in most of the provinces of the basin.

According to the MARENA agrological classification in the Yuna river basin, existent soils range from Class I to Class VIII (Figure 5). Class VI soils occupy the largest area (36%) and are located towards the south of the basin, where the mountains predominate and the relief is more rugged. This is followed by Class II (15.7%), cultivable and flat topography, and Class V soils suitable for pastures and rice crops (14.2%). Soils Classes I, IV, and VI cover between 8 and 10%; while those of Class III cover the smallest area (4.7%).

According to data from the last land use and cover study (MARENA, 2012), the area occupied by the Yuna river basin has a forest cover of 1,612.09 km2, equivalent to 30.6% of the territory; agriculture covers 1,080.42 km2, equivalent to 20.5%, and lastly, pastures cover 842.66 km2 representing 16%. Rice and cocoa crops cover altogether 1,073.87 km2 corresponding to 24.4%. The reminder, 8.5% includes urban areas, dams, minor crops and areas with scarce vegetation. This distribution of land use and coverage reflects the essential characteristics of a basin with intensive agricultural use and a modest extension dedicated to grazing land for livestock production.

Pastures are highly dynamic. If the current values on grassland land cover are compared with the two previous estimated values from MARENA (1996 and 2003), it is evident that this land category is expanding. Between 1996 and 2012, it grew more than 200%, increasing from 600km2 to 1500 km2..

The Yuna river basin has an important livestock activity where small (˂20 heads of cattle) and medium (20-100 heads of cattle) producers converge, with low presence of large producers (˃100 head of cattle). Their production is based on grazing and semi-stable systems, as in much of the country. It is important to highlight that the producers that affect this basin are well organized in 15 associations and a federation (FEGACIBAO). This would facilitate the implementation of actions for transforming the basin into a pilot area, making it possible to develop a climate-smart livestock model with the potential to extend to other cattle- producing areas of the country.

The Yuna river basin concentrates around 16% of the area of land dedicated to cattle raising (FAO-EU Pre-census, 2015), which is why it is considered necessary to ensure that the livestock activity, especially in the upper and middle part of the basin, is developed under a model of sustainable livestock production.  This would contribute to conserve the natural resources of the basin, reducing erosion, protecting water sources and increasing forest cover, through the reforestation of zones that need restauration of ecosystem functions (water and soil protection) and the implementation of silvopastoral production systems integrating tree, forage and cattle management, as a strategy to reduce CO2 and mitigate the GHG emissions generated by livestock.

## b. Baseline Scenario

There are currently several initiatives at national level led by the Government of DR and carried out with technical and financial assistance from different international cooperation agencies. The following table highlights four initiatives and of relevance to this Project proposal:

| Project title / Institution | Implementation Period / Budget | Description | Relevance for the proposed project |
| --- | --- | --- | --- |
| Model to increase the productivity level and access to markets of family dairy producers in the Dominican Republic | 2013-2015 Ministry of Agriculture and CONALECHE (USD 200,000) FAO (USD 295,000) | General Objective: To strengthen the capacity of the National Council for the Regulation and Promotion of the Dairy Industry (CONALECHE), to improve the level of productivity and quality of the family dairy chain in the Dominican Republic. Specific Objectives: a. To strengthen the capacity of CONALECHE to create synergies between the public and private sectors and to establish strategic alliances between value chain actors. b. To improve the capacity of technical multipliers and leading producers of the MEGALECHE program and CONALECHE, on sustainable management of family dairy systems. c. To support three (3) model dairy family farms, as units for the transfer of technology and knowledge to family farmers (men and women). d. To support three (3) milk collection centers of family producers, on good practices of collection, storage and cooling of raw milk. e. To strengthen the technical capacity of provincial inspectors of the Ministry of Public Health and CONALECHE, for the implementation of normative and regulations on the safe handling of dairy products. | The project was executed in the provinces of Monte Plata (belonging to the Yuna basin), El Seibo, Hato Mayor and La Altagracia, in the Eastern region of the country. This project generated baseline studies at the family dairy farm level with a sample of 242 farms. Methodologies were developed for technology transfer in dairy farms and practices that contribute to reduce GHG emissions, such as: protein banks, silvopastoral systems, live fence management, introduction and management of pastures and forages with improved varieties, among other good practices for improving milk quality. The outcomes and lessons learned of this project will serve as inputs for the actions planned with this GEF initiative, related to sustainable livestock strategy, strengthening of technical capacities at the level of producers and extension agents. |
| Reducing Emissions from Deforestation and Forest Degradation (REDD +) - Forest Carbon Partnership Facility (FCPF) | 2015-2019 Ministry of Environment and Natural Resources (MARENA) The World Bank USD 3.8 million | The objective of this project is to promote the implementation of key preparation activities to develop a national REDD + strategy. Expected outcomes: 1) Strengthening the capacities of relevant actors. 2) Structuring and / or adapting the institutional, regulatory and technical framework in order to allow the implementation of national REDD+ strategy (ENREDD+) activities 3) Strategic and operational proposal for the compilation of national reports on CO2 emissions from deforestation and forest degradation in the Dominican Republic. 4) Proposed approach to design the participatory National Forest Monitoring System. 5) Development and adoption of monitoring protocols on vegetative cover and carbon content. 6) Identification of potential social, environmental and economic impacts caused by the implementation of ENREDD + projects. 7) Participatory building of a ENREDD+ strategy. | This project will generate a work plan for the initial design of an integrated MRV system to measure, prepare reports and verify changes in deforestation or forest degradation, as well as in forest improvement activities. This initial design will be done in a phase fashion. This WB-financed initiative includes technical support in the development of safeguards; consultancies of foreign scientists - who will validate the measurement methodology; develop context-based tools, baseline tests; and train personnel from public and private institutions to take samples and prepare reports. This is related to this GEF initiative – see Component 3, outputs 3.1.1 and 3.1.2 in Table B above. |
| Catalyzing a multi-sectoral program to support water and soil management in the face of the threat of climate change in the Dominican Republic | 2017-2018 Ministry of Agriculture and Ministry of Environment (MARN) FAO (USD 273,000) IICA (USD 50,000) | This project is executed in two priority basins: Yaque del Norte and Ozama-Isabela (the latter is linked to the Yuna basin). Expected project outcomes: (a) Having strengthened the watershed governance framework at the national level, in particular for the Ozama-Isabela basin. (b) Position the technical service of the National Soil Conservation Service, giving a clear operational strategy to this agency. (c) Channel the financing of sustainable soil and water management as well as sustainable livestock actions. | This project strengthens the technical capacities of the extension service of the Ministry of Agriculture and the General Directorate of Livestock, through the training of multipliers. Multipliers train technicians and producers in sustainable soil and water management practices with a watershed approach. Good practices for soil and water conservation in livestock and agricultural farms are identified and implemented at the field level. These strengthened capacities in soil and water conservation will support the actions proposed by this GEF-financed project. See Component 2 (outputs 2.1.1, 2.1.2 and 2.3.1.) in Table B above. |
| Strengthening the Livestock Value Chain of Dominican Republic | 2016–2020 Dominican Agribusiness Board (JAD) USDA – NCBA CLUSA (USD 21 million) | Project objectives: 1. To improve the productivity of the livestock value chain (meat and dairy) by: increasing the use of improved techniques and technologies; the improvement of farm management; the increase in the availability of improved inputs and the use of financial services; strengthening the capacities of government institutions and key groups, and increasing the leveraging of private sector resources. 2. Extend the trade of meat and dairy products by: adding value to post-production; to increase the adoption of established standards; increase access to markets; build the links between buyers and sellers; improve post-production infrastructure; increase the use and efficiency of post-production processes; improve policies and the regulatory framework; strengthen the capacity of key organizations in this business sector. | This project is implemented in 11 provinces, including three provinces of the Yuna basin. The main project actions are aimed at strengthening the dairy and meat value chain for exports, considering good practices and training of producers and extension technicians. The JAD-USDA project will include sustainable livestock management actions. The GEF-financed project will coordinate actions in the field through outputs 2.1.1 and 2.1.2. In addition, the JAD project will add more beneficiaries to the MRV system generated by the GEF project. Synergies will be further established in Project Year 1 (2018-9). |

In addition to these initiatives, there is a mechanism to mitigate the effects of climate disasters through agricultural insurance. The livestock insurance has the support of the best specialists in risk inspections and claim adjustments. In this way, quality service is provided in the ranch/farm where the producer has his/her livestock: cattle, pigs, and sheep. The animals must be individualized within the consigned field, but the producer can also agree with the insurance company on other animal individualization methods. This is the most complete insurance plan for animals with national coverage and covers the widest range of risks as well as the highest range of causes of loss are attributed to climate disasters. Additionally, this also covers salvage costs according to the insurance modalities chosen.

## c. The proposed alternative scenario, GEF focal area strategies, with a brief description of expected outcomes and components of the project

The Project Objective is to  mitigate climate change and to restore degraded lands through the promotion of climate-smart practices in the livestock sector, whilst focusing on family farming. The Project is aimed to support GHG emission reduction by implementing good livestock practices, improving productivity and increasing cost effectiveness. Likewise, the Project will support the strengthening of technical capacities in the Ministries of Environment and Agriculture to design and implement an MRV system in national reporting. In addition, technical assistance at field level will be provided to test and implement technologies and good practices which enable the development of a sustainable low-emissions livestock sector in project targeted areas. Soil and water recovery and biodiversity protection are expected project co-benefits.

The alternative scenario involves the development, introduction and upscaling of Climate-Smart Livestock Management (CSLM) on small-sized farms that are engaged in intensive livestock production on natural rangelands. Dominican Republic has 2.5 million heads of cattle, of which 50% correspond to cattle for dual purposes (milk and meat), 31% exclusively for meat and 19% just for milk (ECLAC, 2016). According to the Dominican Association of Farmers (ADHA, 2010), more than 80% of dairy farms in the Dominican Republic are family owned. They contribute more than 50% of the nationally produced milk and meat, and they occupy more than 50% of the land dedicated for cattle raising, approximately 600,000 Ha, thus having a significant impact on the generation of GHG emissions from livestock activity. The project is therefore focused on small-scale farmers. This intervention will lead to lower GHG emission intensities, reversal of land degradation and restoration of land and the decreased economic vulnerability of farmers.

According to FAO, CSLM is based on two basic principles: (i) increased efficiency in the use of resources, and (ii) increased resilience and risk management at farm and systemic levels. Through the application of these principles, CSLM contributes to improved productivity and climate change mitigation; as well as to national food security and broader development goals. FAO recent research and experience in other countries like Uruguay suggests that there are many low cost, high impact, simple to implement technologies and practices that can lead to CSLM. Typical examples of measures which allow increased productivity while lowering GHG emission intensities and land degradation are provided in Annex D regarding the overall introduction to the proposed farming system shift (CEO Endorsement request).

The project strategy to mainstream CSLM into the livestock sector in the Dominican Republic is based on 3 main pillars:

- Piloting, learning and building capacity at the local level: The Project will work with 500 selected small and medium farmers in selected sites, in the Yuna Basin, with high concentration of livestock production based on natural rangelands. Through a consultative co-innovation process with the farmers, the Project will support the adaptation and implementation of the technologies and practices, leading to the economic and environmental gains. The 500 reference farmers will adopt integrated pasture and livestock management approaches rather than focusing uniquely on ‘animal management’. The results of the implementation of these technologies and practices will be monitored and evaluated in detail, against a range of economic and environmental criteria.  Adoption rates, pathways of incremental changes in production practices and related constraints will be assessed with particular care to generate information and lessons learned in view of upscaling.

- Replication strategy at national level: from demonstrating effectiveness to achieving impact at scale. The fact that the adoption of CSLM practices increases the profitability of farms is at the core of this strategy. First, the project will build the foundation to mainstream CSLM in policies and institutional Programmes by facilitating the development of a national CSLM strategy with the involvement of key actors from public, private and academic sectors and farmers’ groups. Second, it will create opportunities for funding of CSLM initiatives through the development of a NAMA for the livestock sector with low GHG emissions. Third, the development of the institutional and individual capacity required to disseminate and extend the improved technologies and practices. Due to the fact that these practices are more profitable to farmers than current practices, the project will dedicate resources to their broad dissemination, through awareness raising, capacity development and extension work.

- Climate Change Mitigation effect: The mitigation effect will be achieved through a range of entry points, resulting in a reduction of emissions and carbon sequestration, as well as improvement of degraded pastures.

The following factors will contribute to a substantial reduction in emission intensities and overall emissions: (1) number of heads per farm will remain rather constant (in order to ensure adequate forage supply, number of head cannot increase), (2) the proposal reduces the breeding overhead and increases the overall efficiency indicators of the herd (pregnancy, age at first mating, age at slaughter, etc.); (3) no nitrogen fertilizers are used to foster above ground net primary productivity (ANPP) (legumes may be introduced in the sward); (4) digestibility of diet increases significantly (due to the demonstrated impact of the increase in ANPP and the use of strategic supplementation with concentrates), which reduces acetic acid formation in the rumen as a precursor of methane; (5) even if there is a rebound effect, the increase in productivity is much larger, which means more food is produced with less emissions; (6) carbon sequestration will compensate a portion of gross emissions, contributing to a reduction in net emissions. This carbon is stored in soils that will remain as rangelands, there is no risk of reversibility of the removals; (7) afforestation (average 2 ha, each) for shadow and shelter in every farm, will sequester carbon in woody biomass.

The project will intervene in a context of strong on-going land degradation. There is wide international scientific literature showing that when organic inputs to soils increase in such circumstances, organic matter increases and so does carbon. Monitoring, Reporting and Verification (MRV) of soil carbon is not easy in the short term. The on-farm monitoring system implemented under the project will increase the understanding through: sampling and modelling of the particulate soil organic matter fraction and the change in below ground biomass. Monitoring this variable will provide an important proxy to determine how management practices address the soil organic matter pool.

To address the barriers described in the Baseline sub-section (see above), the Project will be implemented through four components aiming at: (i) Improving inter-institutional and financial efficiency and capacity to promote efficient and low emissions of livestock; consolidate and interpret information, methodologies and lessons learned to producing practical recommendations and facilitating replication; (ii) Validate technologies to stimulate climate-smart and low-emission livestock production by using: a)scientific frameworks tested by applied science; b) GHG analysis in different livestock systems and contexts; (iii) Strengthen the Monitoring, Reporting and Verification system in the MARENA to interact with the livestock and agriculture sectors; and (iv) ensure project results-based management, including a monitoring and evaluation system, and a results-based communication strategy.

Component 1: Institutional and financial strengthening to support a low-emissions livestock development pathway

Component 1 aims to strengthen the capacity for rolling out and replicating the CSLM technologies and practices to be developed under Component 2. This includes the development of a National CSLM strategy with involvement of a wide range of actors to unify criteria on CSLM and mainstream CSLM into national and local development plans, sectoral policy and institutional Programmes. The barrier of limited finance will be addressed through the development of public-private partnerships (PPPs), opportunities to mobilize finance and create economic incentives for adoption of good practices. In addition, institutional capacities to support CSLM implementation will be strengthened through a capacity development program. A dedicated information system will be created in to document and disseminate lessons from CSLM national and international experiences. FAO Livestock networks (such as LEAP Partnership and the Global Agenda for Sustainable Livestock) will support South-South and Triangular cooperation. In this way, Component 1 will contribute to overcome Barrier #1 (Lack of consultation and integrated policy) and Barrier #3 (Limited knowledge management capacities in institutions).

Component 1 comprises of two Outcomes and three Outputs:

Outcome 1.1. : The national institutional capacity strengthened to support the implementation of a climate-smart livestock management

This outcome will establish a framework for the deployment of CSLM practices in the livestock sector. Outcome 1.1 will, first, analyze barriers, costs and identify funding sources. The project will facilitate the iterative process to prepare the national CSLM strategy. The process will be fully participatory and consultative, with a gender approach. The broad consultation process will facilitate the agreement of the main actors in the public, private and academic sectors on a set of unified and agreed upon CSLM criteria on which the strategy will be built. This process will facilitate the integration of the strategy in the sector policy, as well as in the institutional programs.

- Output 1.1.1. A CSLM Strategy, designed, agreed and disseminated with public and private actors in the livestock sector of the Yuna Watershed.

Main activities will  include: Technical support in the design of the strategy focusing on: (1) CSLM practices for GHG mitigation and restoration of degraded pastures; (2) Ecosystem services, resilience, and other co-benefits; (3) Market certification and value chains; (4) Communication and Dissemination; (5) Communication and outreach of the proposals through events and printed materials and facilitation of agreements.

- Output 1.1.2 Public-Private partnerships designed to: i) pilot incentives, financial and market instruments, ii) enhance watershed management; and iii) implement the CSLM strategy.

Main activities will be: (1) the analysis of existing financial instruments - including a gender gap assessment; (2) the development of a financial tool to support the implementation of CSLM  practices (Component 2); (3) the consultation of actors to promote public-private partnerships (PPPs) and better access to financing; and (4) the formulation of PPP agreements to use financial instruments and apply the CSLM strategy.

The project will promote the enhancement of watershed management through the following activities: i) Technology transfer of good agricultural practices (GAP) for GHG emission reduction, such as: tree planting of livestock areas at risk of erosion, reforestation of riverbanks, soil conservation and management of solid waste in livestock farms; ii) Training of technicians and producers on the conservation of natural resources in livestock farms; iii) Promotion of participatory processes to raise awareness among stakeholders of the livestock sector and other stakeholders on the importance of the management of natural resources in the basin and its impact to mitigate GHG emissions. Lessons learned from these interventions will feed the design of a national CLSM strategy (see output 1.1.4).

- Output 1.1.3: National and Local Public Officials Trained to effectively support the implementation of the CLSM Strategy with a gender perspective

Main activities include: (1) Workshops to enhance the understanding among institutions on climate-smart livestock concepts and the CSLM strategy; (2) Capacity needs assessment to integrate CSLM strategy into institutional policies and programs; (3) workshop to identify opportunities on how to integrate the CSLM strategy into policies and programs. Developing institutional action plans, accordingly; and (4) South-south exchange program visits to other countries with climate-smart livestock and MRV systems designed and co-financed by GEF: Ecuador and Uruguay

- Output 1.1.4: A national CSLM strategy based on the lessons learned from the pilot intervention    in the Yuna river, defined and agreed among key stakeholders.

This output will include the design and discussion of a roadmap to include the lessons learned from the pilot intervention, as well as a national strategy document that will be agreed among the ministries, private sector and key civil society stakeholders. The CSLM national strategy will be part of the project legacy for future scaling-up actions to be financed by the Government and/or the international cooperation.

Outcome 1.2 Knowledge shared and dissemination of lessons learned to support the CSLM strategy dissemination.

In response to the capacity gaps in the sector, a knowledge management platform for the livestock sector will make available the lessons learned, methodologies and results of projects relevant to livestock management, in exchange for knowledge related to climate change, in addition to technological innovations  and policy changes. This component requires the development of technical capacities within the General Directorate of Livestock and CONALECHE, while linking exchanges with the information system of the Ministry of the Environment (see component 3) and with other databases from universities and research centers.

- Output 1.2.1 An Operational Technical Platform for the Livestock Sector, which includes information on Monitoring, Evaluation, Dissemination of Experiences and Lessons Learned.

Key activities include: (1) Analysis and documentation of good CSLM practices, (2) Design and implementation of the technical platform, (3) Preparation of an inter-institutional protocol to ensure the operational capacity, operation, and maintenance of the system, (4) Workshops for the regional dissemination and validation of the platform, (5) Training of technicians in the system maintenance and operations.

The Department of GHG Inventories (Directorate of Climate Change, MARENA), the Risk Management and Climate Change Department (Ministry of Agriculture), and the Focal Point of Climate Change of the General Directorate of Livestock will be responsible for THE inter-ministerial coordination during project lifetime and after project closure.

With the purpose of contributing to consolidate the coordinated actions between both Ministries, within the strategy that will be designed to promote climate-smart livestock management- institutional roles will be clearly defined. Ministries will work with producers' organizations, academia and the private sector, in a coordinated manner, with the aim to promote a transformation of the traditional livestock production model towards a more sustainable model, low in emissions, and to contribute to the conservation of natural resources.

In addition, the project will be supported by the National Soil Conservation Service (SNCS) in matters of watershed management and natural resources. SNCS is part of a Collaboration Agreement between the Ministries of Agriculture, Environment, and the National Institute of Hydraulic Resources (INDRHI). SNCS’ main purpose is to reestablish a soil and water conservation structure at the national level with capacity to reach the users of arable land in the watersheds.

Component 2. Climate-smart livestock management in the field: Technology Transfer, Deployment and Validation of Practices

Through Component 2, the Project seeks to overcome Barrier #3 (Limited knowledge management capacities at the institutional level), Barrier #4 (Limited technical and managerial capacities of farmers) and Barrier #5 (Limited access to markets and financing for climate-smart investments). The Project will implement sustainable production models in approximately 5,000 hectares among the upper, middle and lower basins of the Yuna River. During project implementation (3 years), technical and financial support will be provided to small- and medium-scale farmers in the Yuna river basin with dairy, meat and dual purpose production systems. Component 2 seeks to generate GHG emission reductions and increase soil and biomass carbon sequestration in project pilot farms. Silvopastoril systems and CSLM practices will be promoted among family farmers, generating socio-economic benefits through productivity and profitability increases. Co-benefits will include: support to biological corridors, and enhanced natural resource management in the basin. Field experiences will feed the knowledge management system developed under Component 1. CSLM practices will include: breeding (artificial insemination), paddock rotation, grazing management, and increase in vegetative and tree cover, increase and use of forage from live fences, coverage to lower temperature and diversify income, protein banks, and integration of cutting grass, and protection of riverbanks with bamboo and species suitable for livestock. See Annex D of this CEO Endorsement Request for more details.

In addition to field activities, the project will strengthen institutional capacities to disseminate climate-smart livestock practices. Extension technicians will participate in a capacity development program. Selected farmers will have strengthened capacities to transform their former business models into climate-smart practices, and will receive support for developing and testing new business plans.

The project will train existing extension agents for the livestock sector (DIGEGA-MEGALECHE), and technicians from producers’ organizations (i.e. FEGACIBAO) and NGOs (from the livestock and environment sectors). The latter will contribute to strengthening field technical capacities in coordination with government extension agents (DIGEGA-MEGALECHE), with the aim to implement climate-smart livestock management, both in the Yuna basin and at national level. The project will also incorporate extension agents of the National Soil Conservation Service (Ministry of Agriculture).

Outcome 2.1 Farm-level Technologies have been implemented, promoting Sustainable and Low-Emission Livestock Production

To achieve this outcome, the following outputs are proposed:

- Output 2.1.1 A CSLM Strategy with a gender sensitive approach tested and implemented at farm level, incorporating Mechanisms of Financial Incentives and Market Access

500 producers will implement livestock practices through Output 2.1.1. To achieve this target, the following key activities are foreseen: (1) Validate criteria and selection process of the farms by the Ministry of Agriculture, CONALECHE and producer organizations; (2) Selection of the farms from the consultation process between the Ministry of Agriculture, CONALECHE and producer organizations; (3) Selection and training of extension technicians; (4) Implementing the participatory process and good practices at farm level: (5) Annual planning and evaluation workshops. The project will finance the implementation of good practices in selected pilot farms including planting material, acquisition of studs and genetic material, training, and extension and management.

- Output 2.1.2 A Capacity Development Program for Dairy and Beef Producers, to support the adoption of CSLM Technologies and Good Practices at the farm level

Through this output, 700 producers, including at least 70 women, will receive continuous training on CSLM practices and approaches through a combined training program. This includes annual evaluation and planning workshops, as well as field days organized in pilot farms on a rotating basis, to share experiences and encourage farmer-to-farmer extension. Field visits will be directed to farmers who are not part of the pilot farms, and will be organized in conjunction with producer organizations. This will increase the indirect coverage of the project.

Outcome 2.2 Field Technical Capacities have been improved to disseminate CSLM and Low-Emission Production Models in targeted areas

The actions considered to strengthen technical capacities will be oriented towards strengthening a multidisciplinary vision of public and private organizations’ human resources (Ministry of Agriculture, DIGEGA, CONALECHE, Universities, industries, producer associations). These enhanced technical capacities will support producers in developing business plans to be submitted to: i) public programs and/or commercial banks for funding; ii) certification schemes; iii) other financial tools identified by the CSLM strategy.

- Output 2.2.1: An Extension Program with a gender sensitive approach strengthened to support the Promotion and Implementation of the CSLM Strategy and Low-Emission Livestock Models.

Under this output, the capacities of 50 extension agents from different institutions will be strengthened. Activities include: design of the extension plan, recruitment of technical personnel among institutions in the basin; development and implementation of technically appropriate training plans on livestock and change parameters measuring in the farms and technical aspects management.

Project training programs will be developed by experts in different technical areas such as climate-smart livestock management, extension, gender, business plans development, and MRV, among others. These experts, together with academia and research centers, will conduct the trainings for extension agents; these, in turn, will be training the producers for the implementation of GAPs in climate-smart livestock management. The training programs, which should ensure the inclusion of the gender equality approach in their contents, will be officially handed to DIGEGA to incorporate into its training programs for technicians and producers.  In the same manner, the training programs will be shared with universities that teach agricultural and environmental sciences, in order to update and strengthen their curricula.

- Output 2.2.2: Business Plans with a gender perspective, aimed at public programs or development/commercial banks, and certification schemes, to implement the CSLM  Strategy

The project will support the drafting and implementation of 10 individual business plans or partnerships, including at least in two farms led by women. Farms/Example Associations will be selected and stratified by size. Activities will include: (1) analysis of business models applied by project beneficiary farms; (2) carry out market studies and certification analysis, as applicable; (3) Training farms and associations in how to develop a business plan and to apply for financing and/or certification schemes; (4) continuous advice on the implementation of business plans.

The business plans will target individual producers or associations of producers within the Yuna river basin, which are part of the 500 direct beneficiaries of the project. The selection of the beneficiaries will be conducted by an inter-institutional commission composed of the organizations that make up the project and with a representation of the producers. The commission, with the support of the Gender expert will define the selection criteria, ensuring compliance with the principles of social inclusion and gender equality and avoiding any type of discrimination or bias, including -but not limited to- sex, age, colour, ethnicity, language, religion, political affiliation, national or social origin, disability, economic position and sexual orientation.

Public-private partnerships will help to guarantee the viability and sustainability of the business plans. The business plans will be one of the ways in which the results of the PPPs -established to promote the transformation of traditional livestock towards a more sustainable activity- will be reflected at a practical level. Both the public-private partnerships and the business plans will form an integral part of climate-smart livestock management strategy, at the pilot level in the Yuna basin and eventually, when it is scaled up at the national level.

Component 3. Monitoring, Reporting and Verification (MRV) of the Livestock Sector

Component 3 will address Barrier #2 (Lack of information for livestock sector planning) and Barrier #3 (Limited knowledge management capacities at the institutional level). The integrated MRV System of the MARENA will be strengthened by including links and data, analysis and reports at the national level on GHG emissions from the livestock sector. In particular, a monitoring system will be developed and implemented in 30 pilot farms to assess the results of the CSLM strategies in terms of global environmental benefits (GHG emissions, carbon sequestration and land degradation), farm income and gender issues. The farm monitoring system will combine remote-sensing information with data derived from the sampling of soil, vegetation and manure. The results and lessons will be incorporated into the development of the national livestock MRV system. Component 3 is structured into one outcome and two outputs:

Outcome 3.1. GHG emissions from the Livestock Sector integrated into the Monitoring, Reporting and Verification (MRV) National System

- Output 3.1.1: An MRV system for Measuring Emissions and Reporting Data for the Livestock Sector

Activities will include: (1) the design of a proposal for the MRV system linked to the MARENA system, including operational protocols for data management and verification of information; (2) MRV system implementation; (3) a study on the GHG livestock-based emissions, based on the MRV methodology; and (4) training on sampling and reporting, which will be delivered to public and private institutions technical staff.

- Output 3.1.2 Farm-level Monitoring System to monitor GHG emissions, Strategies, Financing and Land Degradation.

Activities will include: (1) Establishing a GIS system that covers targeted and control farms, (2) Definition of protocols for sampling and data analysis, (3) Monitoring of variables by remote sensing, (4) Sampling and analysis of soil, manure and vegetation, (5) Analysis of CC mitigation  and land restoration indicators, (6) Monitoring of socio-economic and gender variables, and (6) Development and validation of online tools for land assessment and monitoring, process information and calculate GHG emissions at farm level.

Component 4. Project Monitoring, Evaluation and Knowledge Management

Under this Component, a Monitoring and Evaluation (M&E) system will be implemented with Results- Based Management, supporting the overcoming of all identified barriers. In addition, extension materials on climate-smart livestock practices will be developed and validated by farmers and extension workers in the pilot farms, as well as for replication activities. A communication strategy will be developed and implemented to ensure a fluid information flow and the dissemination of project outcomes and outputs among producers, extension agents and institutions nationwide. Lastly, the project will establish and maintain links with international networks on CSLM to share lessons and results, including FAO partnerships, and to benefit from international experiences in the field. Component 4 is structured into one outcome and four outputs:

Outcome 4.1: Project implementation based on RBM and lessons learned/good practices documented and disseminated

- Output 4.1.1 Project Monitoring & Evaluation Plan and system, in place

Under this output, a database tool will be developed to allow the monitoring and evaluation of the outcome, outputs and activities of the projects in accordance with GEF and FAO standards, including GEF tracking tools. The system is supported by periodic reports to the Project Steering Committee (PSC) to ensure transparency and the flow of information. Progress will be assessed at the monthly meetings of the Project Team and the semiannual meetings of the PSC to assess the problems and adapt the course of action to achieve expected outcomes, if necessary. Once the project starts, a grievance mechanism will be defined, a focal point will be designated and stakeholders will be contacted to ensure that people affected by the project can submit a complaint, in accordance with FAO's operational procedures. The Environmental and Social Risk Management Plan will be finalized at project inception and be monitored by the M&E Specialist/Assistant Coordinator, during project implementation

- Output 4.1.2 Project Mid-term review and Final Evaluation.

After 18 months of project execution, a mid-term review (MTR) will be carried out. Six months before the end of project implementation, the final evaluation of the project will be carried out. See more details under sub-section 12) below and in Section 3 of the FAO-GEF Project Document.

- Output 4.1.3 Dissemination and communication products

Under Component 2, the project, through its consultative and action research approach, will develop an affordable package of measures, practices and technologies that will be tested and refined in diverse socioeconomic and ecological conditions. This experience will be transformed into a set of products for use by extension agencies, which include information brochures, a technical manual and four videos where farmers can share their CSLM experiences. The Manual will be developed in Project Year 1 (PY1) and a preliminary version will be published for use in the pilot farms. This version will be revised during project implementation, and a final version will be published in PY3. The extension agents trained in CSLM (Output 2.1.1), will have a validated material available to disseminate the approach to new farms.

- Output 4.1.4 A Communication Strategy implemented, including project website

Under this output, a communication strategy will be developed and implemented to ensure a smooth flow of information with farmers, extension agents and institutional partners, in support of activities in components 1 (national strategy, public-private agreements) and component 2 (activities at farm level, field days). The strategy will ensure that information about project outcomes and lessons are disseminated to a broad audience through appropriate communication channels. Activities will include the preparation of communication materials such as posters and brochures, presence in local media (TV, AM radio, newspapers), as well as the configuration and maintenance of a project website and dedicated accounts of social networks throughout Project duration.

## d) Incremental/ additional cost reasoning and expected contributions from the baseline, the GEFTF, LDCF/SCCF, CBIT and co-financing

Total GEF contributions to the project amount to USD 1,540,586 to finance activities and provide strategic inputs to achieve Global Environmental Benefits in terms of reducing GHG emissions and carbon sequestration, as well as important environmental and socio-economic co-benefits. The GEF contributions are complemented by co-financing from national executing partners and FAO, amounting to USD 8,141,408.

39% of the requested GEF contribution will cover farm-level technologies, including: i) technical assistance of Consultants to implement technologies at the farm level (Animal Production / CSLM Specialist and Farm Management / Extension Specialist and National MRV Specialist); ii) Component 3 (MRV); iii) Contracts within output 2.1, and a portion of outcome 3.1; iv) planting materials and supplies. See more details of this contribution: i) Specific technical assistance to implement GAPs that promote climate smart livestock management encompass: the establishment of silvopastoral systems, protein banks, living fences, management of paddocks and manure,  genetics improvement techniques, and follow up to field activities; ii) Specific technical assistance to design an MRV system to estimate GHG emissions generated by cattle farms, including protocols, on site sampling, lab tests and follow up to field activities; iii) Procurement of planting materials (seeds and supplies) to implement silvopastoral systems in pilot farms; iv) Training sessions for producers to implement GAPs to promote CSLM, including workshop logistics (venues, meals, material reproduction, among others).

GEF incremental contributions and co-financing are detailed below by component:

Component 1: GEF incremental financing of USD 191,206 will support the development and validation processes of the national CSLM strategy, as well as the protocols and frameworks for public-private partnerships to support the financing of the strategy. In addition, GEF resources will cover the costs of the workshops for the creation of institutional capacity in order to integrate the strategy into policies and work programs at the institutional level. The GEF will cover the expenses of establishing a technical platform of knowledge management, and training officials for its operation and maintenance. Finally, expenses for visits to other countries for knowledge-sharing on climate-sustainable livestock will be included.

Co-financing for Component 1 (USD 54,628) is provided by the MARENA, DIGEGA, IDIAF, and FAO. The co-financing covers the use of facilities and logistics of local institutions for meetings on the strategy validation and dissemination, salaries of field extension technicians, technical salaries for participation in workshops and validation and dissemination meetings within the framework of activities planned.

Component 2: The incremental financing of the GEF amounts to USD 658,080. The funds will cover (i) field coordinator and experts, workshops, supplies and materials, to implement livestock strategies at farm level, (ii) the training program to producers and extension agents, and (iii) elaboration and monitoring of business plans.

Co-financing for Component 2 amounts to USD 6,721,559 and is provided by the MARENA, and the Ministry of Agriculture, FAO, DIGEGA, Banco Agrícola (Agricultural Bank), CONALECHE, IDIAF and FEGACIBAO. Banco Agrícola and CONALECHE will provide cash co-financing (USD 6,399,402) to finance technical assistance to 500 producers to adopt and implement good practices and technologies for low-emission livestock. They also provide financing for business plans and certification to access payment for environmental services (PSA) and incentives. CONALECHE will finance plans to associations, aimed at adding value to milk.

In-kind co-financing for Component 2 (USD 347,657) will cover salaries and use of utility vehicles of extension technicians and coordinators located in CONALECHE's decentralized offices and central office, the Ministry of Agriculture, and the National Soil and Water Conservation Service. IDIAF will cover salaries for 2 researchers and 2 bromatology laboratory technicians. The Ministry of Agriculture will cover salaries of animal reproduction laboratory technicians. The MARENA will cover facilities and salaries for technical staff of forest nurseries. In support of the field activities, FEGACIBAO will provide technical salaries for local organizations managers and producer beneficiaries from 15 associations, in addition to 100,000 forest seedlings for farm reforestation. Finally, premises, use of facilities and logistics will be provided for coordination meetings and trainings.

Component 3: GEF incremental financing amounts to USD 375,053. Consultants, materials for sampling and laboratory analysis, and equipment to implement the farm monitoring program will be covered. The funds will also cover the establishment of the MRV system at the national level for the livestock sector, and technical studies on sector emissions.

Co-financing for Component 3 amounts to USD 1,061,160. The MARENA cash contribution is aimed to specialized technical assistance for the design and implementation of the MRV system, including methodologies and protocols for collecting and processing GHG emissions information from livestock activity. The DIGEGA and the MEGALECHE program also support, in part, the collection of GHG emissions information at the level of pilot farms. Salaries for technicians from the MARENA (Climate Change Directorate and Dept. of Forest Resources) and climate change technicians from the Ministry of Agriculture and DIGEGA will be provided. Finally, premises and physical facilities are provided to organize meetings and workshops with technicians and experts hired to implement the MRV.

Component 4: GEF incremental financing for Component 4 of USD 176,193 will be used to develop and maintain the M&E system, launch and final workshops, mid-term review and final evaluation, in accordance with FAO and GEF standards. It will provide funds to produce the technical manual and audiovisual material on CSLM. Finally, the project funds will cover the production of communication materials and the establishment and maintenance of the project's website and social network channels.

Co-financing for Component 4 amounts to USD 30,000, contributed by FAO. This includes salaries of technical committee technicians and board of directors to support the definition of the plan and project monitoring system. In addition, it covers facilities for meetings to follow up on the project, and a communications consultant, who will support the implementation of the project communication strategy.

## e) Global environmental benefits (GEFTF), and adaptation benefits (LDCF/SCCF)

The project is expected to present the following environmental benefits:

| Global Environmental Benefits | Target | Comment |
| --- | --- | --- |
| GHG emission reduction | 42,153 tons CO2-eq per year (reduction equivalent to 22% of total emissions) EI reduction: 46.4% for dairy production systems Emission profile: N2O manure: 16.3% reduction N2O feed: 67.6% reduction CH4 enteric: 13.1% reduction CH4 manure: 16.4% reduction CO2 feed: 13.5% reduction | Calculated with FAO Global Livestock Environmental Assessment Model (GLEAM) EI: Emission intensity (kg CO2eq/kg of output (dairy) |
| Area under sustainable management | 5,000 ha | Area of Project direct beneficiaries. |
| Carbon sequestration | 5,750 (tons CO2 year) (5,000 ha) | Based on estimations of carbon sequestration by Henderson et al. (2015)1 and the project intervention area |
| Income increase | Dairy: additional US$ 6,858,190 (year) in Project area | Dairy farmers’ milk price (reference): R$ 0.365 |
| Productivity increase | 18,790 tons of milk/ year (+46.3%) 538 tons of meat /year (+34.3%) |  |

1Henderson et al. (2015): https://www.sciencedirect.com/science/article/pii/S0306919215001256#b0340

This project will use relevant information to promote good agricultural practices in terms of reducing GHG emissions, and diversification of production along with the actions undertaken in the field and based on information generated by other projects implemented by FAO (PROLEFAM) and currently being implemented by other organizations (PROGANA-JAD). This will be done through the implementation of technological packages on good livestock practices such as silvopastoral systems (integration of trees to livestock production for fodder, forestry and fruit trees), living fences (as a biological corridor and connectivity) , green fertilizers (reduces the use of mineral fertilizers), arboreal forage banks, among other sustainable practices. The project will be able to reduce 22% of emissions from livestock systems in the Dominican Republic (equivalent to 42,153 tons CO2-eq). This reduction is based on the management of N2O from fertilizers through the management of manure (16.3% reduction) and feeding (67.6% reduction), reduction of CH4 by enteric fermentation (13.1% reduction) and manure management (16.4% reduction), reduction of CO2 emissions related to feed production (13%) and 5,750 tons of CO2 per year by increasing the mass of trees, with a total reduction of 47,903 tons of CO2-eq/year. Regarding the conservation of ecosystems and the sustainability of productive systems, measures will be applied under the sustainable productive landscapes approach in 5,000 ha (3000 direct hectares + 2000 indirect hectares) covered by the project (including basic information and monitoring of certain species, economic value, education and awareness, replication of best practices and policies).

Co-benefits

Reduce Land Degradation. The project will be implemented in livestock production farms located in degraded and severely degraded lands. Current management practices aimed at maximizing herd size has worsened land degradation processes, including soil compaction and erosion. The Project will address this trend by implementing CSLM practices in 500 farms covering 5,000 hectares (3000 direct hectares + 2000 indirect hectares) (i.e. reduction in herd size while maintaining productivity, introduction of paddocks, and pasture improvement through paddocks). These practices will lead to an accumulation of soil organic carbon, improved soil biodiversity and the recovery of degraded areas. The Project will improve extension programs and will indirectly improve soil quality in grasslands.

Biodiversity. Grasslands in the project intervention area possess a rich biodiversity of species. The habitats are varied and interspersed, with a series of localized geographic features, each of which includes rocks, hills, small streams and rivers. In addition, grasslands serve as corridors for isolated protected habitats. There are also rich and diverse soil types. The Dominican grasslands have suffered a systematic deterioration, mainly due to unsustainable grazing practices (overgrazing) in pastures. This project aims to stop and reverse this, which helps considerably to stop the loss of biodiversity and recover it.

Climate Change Adaptation Project interventions will increase the adaptive capacity of small-scale farmers and improve ecosystem resilience in affected grasslands. This is due to the combined effects on soil health, water storage capacity, biodiversity and body resistance of animals, as well as better decisions and risk management.

## f) Innovation, sustainability and potential for scaling up.

Innovation: Climate-smart livestock is an innovative approach that has been promoted by FAO and other organizations in the last five years. The GEF and FAO partnership has already cooperated in this regard, and two other climate-smart livestock projects have been approved in the Latin America region (Uruguay and Ecuador). FAO has informed the Government of DR on these FAO-GEF initiatives. This is the first project in the Dominican Republic that explicitly focuses on the potential of climate change mitigation in the livestock sector. The project will make an important contribution in helping the country achieve the ambitious goal of curbing specific GHG emissions from livestock. Given the trends in global  consumption of livestock products it is a project that is of global relevance. The full CSLM approach is detailed in Section 1 of the FAO GEF Project Document.

Social sustainability:  The project will intervene in a selected pilot region, which has been selected given the importance of family farms in maintaining local livelihoods. At farm level, a participatory approach will be applied by including the capacities, goals and aspirations of producers (including women) and their families in the design of CSLM strategies. At the territorial level, the project will support social cohesion by strengthening local producer organizations. These provide important forums for mutual learning and the consultation of local farmers’ problems and concerns. Producer organizations will also facilitate technical and financial assistance, and dialogue with public sector institutions at higher levels.

At the national level, social sustainability will be strengthened by including the concerns of producers in the low-emission livestock national strategy. This will be ensured through the participation of farmers' associations in the development and validation strategy, and through specific measures to increase capacities.

Environmental sustainability: The Project intervention strategy will focus on improving the environmental performance of small and medium-sized farmers who manage an important part of the country's fragile pastures. Stopping and reversing land degradation in this area will not only generate the climate change global environmental benefits and improve soil resources, but will also have a positive impact on other environmental goods and services, such as biodiversity conservation, landscape integrity and water regulation.

The Project will systematically monitor the impacts of the transition of production systems on different environmental factors (soil, vegetation, water). The Project is aimed at improving the understanding of these transition processes. This, in turn, will lay the foundation for associated initiatives and farmers to draw lessons from experience and optimize their strategies to maximize environmental benefits, while improving productivity.

At national level, the Project will contribute to the environmental sustainability of the livestock sector through the development of the national CSLM strategy, and the improvement of institutional capacities of the main public and private institutions, and farmers’ associations.

Financial and economic sustainability. The project adopts a multilevel approach to capacity building in order to ensure the financial and economic sustainability of the interventions. The livestock strategies are developed according to the real economic situation of each farm, as well as the goals and aspirations of the producers and their families. It is very probable that the time invested by the producer will be widely compensated by the increase in income. Any additional investment costs identified in the farm strategy, if applicable, will be covered by the project (e.g.  improving water availability or conducting reforestation activities). Most of the technological options supported by the project require little investment by producers. In this way, the project will work with producers to overcome the widespread scepticism about possible improvements in production systems.

At the national level, the project will provide public and private sector institutions with options to improve the economic opportunities linked to climate-smart livestock production. In particular, PPPs and the MRV system will allow institutions to identify and access financing sources to continue implementing the CLSM national strategy, which will, in turn, boost the economic performance of low-emission livestock models.

Sustainability of capacity development. The project capacity development strategy is addressed to all key stakeholders at the local, regional and national levels. At the local level, sustainability will be guaranteed through the application of the co-innovation approach. Extension officials and producers will together develop a farm-based strategy, by assessing the productive system of each farm, and the family farmers’ goals and aspirations. Extension agent will assume the role of facilitators instead of simply being technical advisors. The co-management approach has proven to be very effective in unleashing long-term improvements. It will be reinforced by farmer-to-farmer learning, dedicated workshops and field days, which have also proven to be very effective.

At the regional and national levels, the capacity development sustainability will be achieved by systematically including farmers' associations in project activities. These associations have great potential to spread the Project vision. At the national level, the capacities of the relevant actors will be strengthened to implement the national low-emission livestock strategy through a capacity-building program carefully adapted to the needs and situation of each institution. In particular, the capacities will be installed in the key units of the MARENA that have the mandate to implement programs for sustainable livestock development and climate change.

Replication and scaling-up: the project has great potential for replication and scaling up. In the Dominican Republic, the area of pastures managed by cattle producers amounts to 724,123 hectares (MARENA, 2017). The Project will intervene directly in 3,000 hectares. The Project will have an indirect impact on additional 2,000 hectares - through a close alignment with other ongoing initiatives, as well as a close collaboration with farmers' associations.

The national CSLM strategy to be developed within the framework of this initiative will be integrating public and private actors of national relevance (government institutions, industries, associations and federations of producers, academia, research centers, and international cooperation agencies), in order to facilitate the transfer of lessons learned that result from this pilot experience in the Yuna basin.

The Project will strengthen the capacities of public and private institutions, especially DIGEGA’s Extension Service, in relation to the implementation of good agricultural practices (GAP) and technologies for climate-smart/low emission livestock management, articulated with the platform for the management and transfer of knowledge.  Project lessons learned will be multiplied among extension agents at the national level, thus guaranteeing specialized technical assistance in climate-smart/ low emissions livestock.

CONALECHE and Banco Agrícola as financial entities with national scope, will offer credit to producers at a national level that require financing to implement GAP and technologies for climate-smart livestock management.

The project will be linked to other initiatives that are ongoing, being formulated or under pipeline, national in scope, such as livestock NAMA, and other priority country watersheds, like the “Sustainable Watershed Management Program”-funded by the Word Bank and the Ministry of Economy, Planning and Development (MEPyD), which would be directly linked to the actions and results generated from this intervention.

Further expansion will be sought through a series of complementary measures. One possibility is to seek funding related to climate change mitigation through the mechanism of National Appropriate Mitigation Actions (NAMA) of the UNFCCC. The Project will work in 500 farms as the spearhead of a much more ambitious strategy to produce more meat and more milk without an emission increase. Technical change and net income increase will stimulate farmers’ adoption of CLSM practices and technologies in the wider landscape. Targeted farms are expected to become more sustainable due to this dual-purpose livestock approach (i.e. GHG emission reduction and income increase). The spill-over effect is expected to be high.

# 2. Child Project?  If this is a child project under a program, describe how the components contribute to the overall program impact.

Not applicable

# 3. Stakeholders. Will project design include the participation of relevant stakeholders from civil society organizations (yes  /no) and indigenous peoples (yes  /no)? If yes, elaborate on how the key stakeholders engagement is incorporated in the preparation and implementation of the project.

The following table illustrates the role of project stakeholders:

| Stakeholder | Mandate (related to the Project) | Role in the Project |
| --- | --- | --- |
| Ministry of Environment and Natural Resources (MARENA) | Public institution responsible for the formulation of national policies related to the environment and natural resources, and to guarantee the sustainable use and management of renewable natural resources and the environment. MARENA hosts the GEF Operational Focal Point and has a Directorate of Climate Change responsible for ensuring compliance and maintaining follow-up to the United Nations Framework Convention on Climate Change. MARENA is the UNFCCC Focal Point. | Project executing partner and leader of the implementation through the Directorate of Climate Change, which will coordinate actions with other public and private institutions. |
| Ministry of Agriculture | The Ministry’s Department of Risk Management and Climate Change is directly responsible, or in coordination with other entities, for climate change adaptation activities in the agricultural sector to support food security in the country. | Project executing partner. It will support livestock extension services, provide technical assistance on animal genetic improvement and upkeep MARENA in the implementation of the MRV system. Involved dependencies: General Directorate of Livestock (DIGEGA), CONALECHE, and VITROGAN. |
| General Directorate of Livestock (DIGEGA) | DIGEGA is a dependency of economic and hierarchical order, within the structure of the Ministry of Agriculture. DIGEGA has traditionally played a key role in the protection and development of the national livestock. DIGEGA hosts the MEGALECHE Extension Program, which aim is to promote the organization of producers in associations and cooperatives. MEGALECHE also supports an extension system, seeks to increase the country's milk production, and promotes milk quality improvement through the transfer of simple, practical and widely tested technologies. | Project partner. The MEGALECHE Program has field extension agents who will be giving technical assistance to farms and producers’ associations – the GEF project beneficiaries. MEGALECHE promotes the implementation of good practices and delivers training on sustainable livestock management and GHG emission reduction. |
| CONALECHE | CONALECHE elaborates and executes the dairy policy in order to promote self-sufficiency and to improve the sector’s productivity and competitiveness levels. CONALECHE is oriented to develop and organize the national dairy industry, encouraging the production, industrialization, commercialization and consumption of milk and its derivatives. | Executing partner. CONALECHE’s Credit Unit will be financing beneficiary farms on good practices. CONALECHE’s dairy technical unit will offer technical assistance to dairy processors to improve milk quality and efficiency. |
| FAO | FAO is the agency of the United Nations that leads the international effort to end hunger. Climate change is one of FAO's main institutional priorities, as reflected in its Climate Change Strategy. This CC strategy translates the fundamental role of FAO into strategic actions and priorities at the global, national, regional and local levels. The main objective is to help member countries meet their commitments to address climate change. | GEF Implementing Agency. FAO will also provide specialized technical assistance during project implementation, particularly on climate-smart livestock management and GHG livestock-based emission reduction. |
| Dominican Institute of Agricultural and Forestry Research (IDIAF) | The IDIAF is the public institution responsible for executing the agricultural and forestry research and validation policy in the Dominican Republic. | Project partner. IDIAF has livestock researchers with experience in sustainable livestock management and measurement of GHG emissions by livestock activity. IDIAF has an experimental livestock station in the Yuna basin (Duarte province) and a soil analysis and forage safety laboratory in Santo Domingo. IDIAF will provide technical assistance in the design and implementation of the MRV system, and will deliver trainings for producers. |
| Banco Agrícola | Financing productive activities of the agricultural and agro-business sectors. | Financing of good practices for sustainable livestock management. Participation in the design of the financial strategy to promote sustainable livestock in project influence area. |
| Educational institutions | The University Environmental Network (RAUDO) covers all academic centers in the country, including the Autonomous University of Santo Domingo (UASD), the Ibero-American University (UNIBE), the Technological Institute of Santo Domingo (INTEC), the Pedro Henríquez Ureña National University (UNPHU), APEC University (UNAPEC), the Pontifical Catholic University Madre y Maestra (PUCMM), and the Catholic University of Cibao (UCATECI). RAUDO promotes the multiplication of information on climate change in universities and the implementation of projects. | - Support for research studies and technical consultancies. -Support for the implementation knowledge management platform and sharing lessons learned on sustainable livestock, climate change and GHG emission reduction. -UCATECI has an agreement signed with the Ministry of Environment, to promote the recovery and conservation of the basins of the Yuna and Camú rivers. |
| NGOs and Civil Society Organizations | The non-governmental organizations of the livestock sector are integrated into the agricultural and livestock development of the country, through the Dominican Agribusiness Board (JAD), the Dominican Association of Farmers and Farmers (ADHA), the National Patronage of Ranchers, the Dominican Association of Producers of Milk (APROLECHE), Dominican Association of Meat Producers and five regional livestock federations: FEGASUR, FEDEGARE, FEDEGANORTE, FEGACIBAO and FEDEGANO. | Project beneficiaries. The Federation of Cattle Ranchers of the Central Cibao and the Northeast (FEGACIBAO) will be a Project partner during implementation. FEGACIBAO is present in the Yuna basin with 15 associations and more than 1500 dairy producers (women and men). These producers will the project direct beneficiaries, will implement CSLM practices at farm level, and will participate in capacity development activities on how to achieve low-emissions livestock management. FEGACIBAO has a meeting room and office in the Yuna basin (Duarte province). It will support the articulation with the associations and the selection of producers to implement sustainable livestock practices and provide training. The Livestock Board and the ADHA will support the link with meat producers and will involve them in the implementation of sustainable livestock practices and participation in training activities. . |
| Milk and meat processing industries. | The industry is organized through the Dominican Association of Dairy Industries (ADIL), the Association of Processors of dairy products and derivatives (ADOPROLAD) and the Association of Industrial Slaughterhouses. | Supporting the design and implementation of the financial strategy and incentives, to promote a sustainable and low- emission livestock path. |

Please see sub-section 1.3.4 Stakeholder engagement of the FAO GEF Project Document for further details.

# 4. Gender Equality and Women’s Empowerment. Are gender equality and women's empowerment taken into account (yes  /no)?  If yes, elaborate how it will be mainstreamed into project implementation and monitoring, taking into account the differences, needs, roles and priorities of women and men.

The Project will strengthen the integration of producers in the agriculture sector associations and directions. A special focus will be put on women’s empowerment, both in producer associations and public institutions. Women-led organizations will be prioritized when selecting local partners.

This Project proposal will ensure gender equality in all project activities to be implemented in the Yuna River basin. This means giving the same opportunities to men and women to develop their capacities, reach their productive potential, and identify effective means to cope with shortage periods due to extreme weather conditions. Given that women find greater barriers in their economic development (in particular, due to less access to land and/or production assets, credit, employment, training opportunities, etc.), this Project will implement actions to facilitate women’s participation in training, income generation activities, and job creation, as follows:

- A study will be carried out on the roles of women as agents of change for development of the livestock sector low-emissions strategy, in line with the INDC;

- Prioritize the initiatives of women's groups and associations, and direct women to leadership positions as much as possible;

- Identify and include opportunities to channel the economic empowerment of women, especially the most vulnerable, within the value chains in support of business plans;

- Prioritize decent permanent employment alternatives, and ensure that interested young women are included in production support initiatives;

- Facilitate training and income generation activities to improve nutritional status and food security;

- Carry out an integration process for young family farmers, according to their conditions and interests, promoting their improvement in courses and / or careers related to the sector, as well as their integration to national and regional initiatives, such as the Culture of Water Program from the National Institute of Hydraulic Resources (INDRHI).

- Under Component 2, Output 2.1.2, the project will launch a strategy to implement technologies at farm level that develop sustainable low-emission livestock with a gender approach, incorporating financial and market incentives. At least 10% of the beneficiary farms will be led by women;

- Likewise, Output 2.2.1 will develop an extension program with a gender focus that will promote and implement the low-emission livestock production strategy. At least 10% of the participants will be women.

Project activities coincide with the gender approach of the GEF-6 Climate Change Mitigation Focal Area. The Project recognizes gender differences and will determine the key actions to promote the role of women in project implementation. This has been reflected in the use of gender analysis as part of the socioeconomic assessment during project preparation, as well as the use of indicators disaggregated by gender when relevant. Lately, the Project offers an opportunity to evaluate the role of women in the deployment of low GHG technologies and options for climate change mitigation in the livestock sector. To ensure the follow-up and execution of the proposed actions for gender issues, a Gender Specialist will be contracted to supporting the design of the sustainable livestock financial strategy, selecting  beneficiaries for implementation of good practices and training, and designing business plans.

# 5. Benefits. Describe the socioeconomic benefits to be delivered by the project at the national and local levels. Do any of these benefits support the achievement of global environment benefits (GEF Trust Fund) and/or adaptation to climate change?

The project seeks to improve the levels of livestock production in the Dominican Republic, while seeking to reduce emissions from the livestock sector. Specifically, the project seeks to improve the income of 500 family farmers in the targeted area through productivity increases, better access to markets and financing sources to adopt CSLM technologies.

The proposed project is based on national and international experiences with a aiming to improve the economic situation of farmer families and natural resources through the analysis and redesign of production systems based on the application of process technologies for the management of herds and grasslands. These processes allow loading rates to be reduced. At the same time, most farms can improve the amount of forage (+ 40%), which improved key production parameters, such as the weight of weaning calves (+ 20%), meat production (+ 24%) and milk production (+ 20%), which will increase income. The costs of these practices are very low (less than 5 USD/cow/year). According to FAO’s experience, CLSM interventions have shown improvements in production levels and incomes from the first year. In addition, farms have reported workload decreases, indicating higher productivity and quality of life. These benefits usually provide an incentive for farmers to manage their pastures sustainably. The pressure on the pastures is reduced and the degradation processes in the pastures are reversed. Due to the restructuring of the herd, GHG emissions will be reduced considerably. The application of the low-emission livestock approach could lead to the disappearance of non-productive cows compared to a normal business scenario, with considerable economic and environmental benefits.

# 6. Risks. Indicate risks, including climate change, potential social and environmental future risks that might prevent the project objectives from being achieved, and if possible, propose measures that address these risks:

| Description of Risk | Probability of occurrence | Impact | Mitigation actions |  | Responsible Party |
| --- | --- | --- | --- | --- | --- |
| Climate Risk: Extreme weather events related to climate change and climate variability: 45% of the Northern and Eastern territory of the Yuna Camú basin is in a zone of moderate risk with respect to hurricanes and tropical storms | High | High | Design a monitoring system that can also be used as a basis for a basin-wide flood forecasting system, including the risk assessment of landslides. |  | National executing partner |
| Climate risk: The project target areas may experience droughts during project implementation. Climate models clearly point to a precipitation reduction in the Yuma Camú basin in the future. | Medium | High | The selection of sites in the project area in different agro-ecological zones will ensure that at least a good proportion of farmers can introduce and test technologies and practices, even if drought is experienced in one of the areas. |  | Project Coordination Unit. National Executing Partner(s) |
| Environmental risk: Temperature increase and rainfall reduction create propitious conditions for the increase of forest fires. | Medium | Medium | Forest fires in the Yuna basin can be controlled through management and surveillance measures, particularly wood burning within protected areas. To remove illegal burning in landfills, it would suffice to enforce the Environmental Management Standard for solid waste – which in Article 6.1.5 states: No person should cause or allow open burning of solid waste. |  | Ministry of Environment and Natural Resources (MARENA) |
| Landslide risks: The flood area of the Yuna Camú basin covers almost 30% of the basin: • high slopes that show drastic drops over short distances, such as the Camú River, which rises to more than 2,000 m.a.s.l and descends to 120 m.a.s.l in its 50 km route to the Yuna River; • the amount of water discharged in the Yuna River is substantial and flows speed is quite high, due to the basin’s dense hydrographic network; • Soils are mostly coarse, and thus, tend to remain humid or saturated – this affects their infiltration capacity during extreme weather events; • Flat topography (less than 3 m.a.s.l) and low soil permeability in the lower basin area, makes soils vulnerable to water force. | Medium | High | Design a monitoring system that can also be used as a basis for a basin-wide flood forecasting system, including the risk assessment of landslides. |  | Project Coordination Unit. National Executing Partner(s) |
| Geographical risk: The Yuna Camú Basin is crossed by three well-known geological faults: the North, the Hispaniola by the center, and the San Juan-Restoration to the South. This indicates a risk to geodynamic phenomena. | Medium | Low |  |  |  |
| Social risk: Lack of farmers’ interest and motivation to participate in the project | High | High | Participating producers with a genuine interest and motivation will be targeted during the selection process. In addition, the selection process is articulated with the associations of local producers that will support the deployment of field activities. The Project will implement tested measures and approaches that ensure the generation of producers’ economic and financial benefits. This socio-economic feature is expected to be a strong rationale for farmers to participate in proposed climate-smart livestock activities (learning, testing, and sharing). |  | Project Coordination Unit. National Executing Partner(s) |
| Social risk: Lack of interest project stakeholders in participating in the process of elaboration and validation of the Climate-Smart Livestock Management Strategy and capacity development activities. | Low | High | Most stakeholders and potential producers have participated in the project preparation phase and have endorsed the project’s approach. During project year 1, all key stakeholders from the agricultural sector of the Yuna river basin will be properly identified and included. A value chain approach will be applied. As well, these stakeholders will be included as part of project implementation, and systematic monitoring. |  | Project Coordination Unit. National Executing Partner(s) |
| Institutional risk: Low technical capacity of experts and institutions at national and local levels may slow the project progress down. | Low | Low | A capacity assessment was conducted during the Project formulation phase and this risk has been identified as ‘low’. Adequate national experts will be identified to support project implementation. In terms of institutional capacities, the project will support capacity development activities to mitigate this risk. |  | Project Coordination Unit |
| Health risk: Epidemic of animal diseases in the project area | Medium | Low | Project sites will be selected in different agro-ecological zones, to ensure that at least a good proportion of farmers can introduce and test technologies and practices, even if an epidemic is experienced in an area. |  | Project Coordination Unit. National Executing Partner |
| Health & Legal risks: Transmission of seed and seedling pests and/or diseases in the pilot farms. The project includes the provision of sowing material (seeds or seedlings) of local forage tree species | Moderate | Moderate | The Project Coordination Unit will: - Avoid undermining local seed & planting material production and supply systems through the use of seed voucher schemes, for instance • Ensure that the seeds and planting materials are from locally adapted crops and varieties that are accepted by farmers and consumers • Ensure that the seeds and planting materials are free from pests and diseases according to agreed norms, especially the IPPC (International Plant Protection Convention) • Request FAO Pesticides Division's (AGPMG) authorization for all procurement of seeds and planting materials. - Request clearance from AGPMC is required for chemical treatment of seeds and planting materials • Clarify that the seed or planting material can be legally used in the country to which it is being imported • Ensure, according to applicable national laws and/or regulations, that farmers’ rights to PGRFA and over associated traditional knowledge are respected in the access to PGRFA and the sharing of the benefits accruing from their use. This is part of FAO Environmental and Social Safeguards. | Project Coordinator. FAO Dominican Republic. National Executing partner. |  |

# 7.  Cost Effectiveness. Explain how cost-effectiveness is reflected in the project design:

FAO’s experience has demonstrated that CSLM technologies and practices can be very profitable. Most CLSM options require minor or no investments from farmers. On the other hand, productivity, net farm income, and farm labor efficiency can increase if CSLM practices are adopted. This win-win solution has made the CLSM approach very attractive to family farmers that have learned about it. The CSLM approach supports producers in carefully analyzing which options could better adapt to their farm contexts and their own capacities, including a gender perspective. Many of these practices have been successfully applied in previous FAO projects in Latin America, Asia and Africa. During project preparation, CLSM technologies and practices have been adapted to the context of family farming in the Dominican Republic. Project cost-efficient in the national context has been duly analyzed during project design. Field project costs are similar to previous FAO projects in the livestock sector.

# 8. Coordination. Outline the coordination with other relevant GEF-financed projects and other initiatives [not mentioned in 1]:

Currently, at the national level, several government-led initiatives are carried out with technical and financial assistance from different international cooperation agencies, which include:

- Project Integrated Management of Natural Resources and Resilient Agriculture in the Yaque del Norte and Ozama-Isabela Hydrographic Basins in the Dominican Republic for sustainable soil and water management in two priority basins of the country executed by the Ministry of Agriculture and the MARENA with support from FAO and the Inter-American Institute for Cooperation on Agriculture (IICA). The technical team that has participated in the formulation of the project is also made up of the National Institute of Hydraulic Resources (INDRHI), the National Institute of Drinking Water and Sewerage (INAPA) and the World Bank. The initiative has four components: i) Soil and Forest Conservation in the Upper Basin and Rural Environmental Sanitation and Pollution Control; ii) Improvement of Response Capacity to Extreme Climate Events; iii) Improvement of Productive Capacity and Connectivity with Markets; and iv) Strengthening the Watershed Governance Structures.

Activities carried out under these components will improve the adoption of sustainable production systems from an environmental perspective. Also, they will be oriented to capacity development to face the threat of adverse natural phenomena, to improve the link between markets and agricultural/livestock producers (including women). Finally, the aim will be to strengthen the governance, consensus and participation of the actors in the two basins.

- Project Restoration of the Yuna-Camú River Basin and its Coast in the Duarte, Sánchez Ramírez, Bonao, Samaná, Espaillat and Santiago Provinces resides in the sustainable natural resources management in order to ensure the natural foundations and contribute to the well-being of communities. The Project addresses the root causes of deforestation and the degradation of natural resources, considering the water retention capacity of forests and their contributions to climate change impacts and the fight against desertification.

This initiative is comprised of eight components. The following components can be considered as relevant to the sustainable livestock proposal: i) Ensure water retention capacity of the basin and preserve ecosystems that harbor terrestrial and coastal biodiversity through the establishment of forest, agroforestry and/or fruit plantations, and reforestation measures in deforested mountainous soils, agroforestry systems, and restoration of coastal ecosystems associated with the basin; ii) Construction of soil and water conservation works; prevention and mitigation before natural phenomena; iii) Acquisition of measuring equipment, instruments and technologies;, surveillance and control booths; reforestation tools; conservation practices; iv) Strengthen the management capacity and local governance for the basin management, developing communities with social, cultural value systems and favorable practices towards the environment; v) Develop institutional capacity for the conservation and management of natural resources, and reduce land use conflict, conservation of coastal zones and protected areas; vi) Guarantee project result execution and achievement through the supervision and inspection of works.

- Project Strengthening the Dominican Livestock Value Chain (PROGANA) to improve the dairy and meat chain for export to the United States, began in 2015 with funds from the United States Department of Agriculture (USDA) and has as main national partner the Dominican Agribusiness Board (JAD). This project is carried out in 11 livestock provinces of the country, including two provinces of the Yuna basin: Duarte and Monte Plata. The initiative has a budget of USD 21 million and a duration of 5 years. The main actions of this project are aimed at (i) strengthening the dairy and meat exports chain, considering good practices and training of producers and extension technicians, and (ii) expanding trade in dairy and meat products.

This proposal is incorporating sustainable livestock actions and at the same time incorporating project beneficiaries into the reporting system of livestock generated emissions. Some PROGANA activities worthy of mention and relevant to the present GHG reduction proposal are: i) Training in improved livestock production techniques; ii) Farm management training; iii) Improve the capacity of: Livestock extension services from the General Directorate of Livestock (DIGEGA) and the private sector; Farmer organizations, and Financial services by providing livestock loans and private and public investments; iv) Promote and improve policies and the regulatory framework.

At regional and global level, the project will develop collaboration mechanisms with the following climate-smart livestock initiatives. Specifically, information on good practices and technical staff visits and documentation of lessons learned will be exchanged:

- GEF Project #5724: Participatory Assessment of Land Degradation and Sustainable Land Management in Grassland and Pastoral Systems (Global)

- GEF Project # 4775: Promotion of Climate-smart Livestock Management Integrating Reversion of Land Degradation and Reduction of Desertification Risks in Vulnerable Provinces (Ecuador)

- GEF Project # 9153: Climate-smart Livestock Production and Land Restoration in the Uruguayan Rangelands (Uruguay)

9.  Institutional Arrangement. Describe the institutional arrangement for project implementation:

The Project Institutional Arrangements are detailed in Section 3 of the FAO GEF Project Document. A summary is presented below:

The MARENA, through the Directorate of Climate Change, will be responsible for the overall execution of the project and will act as National Operational Partner. The Ministry of Agriculture, DIGEGA through its MEGALECHE program, CONALECHE, IDIAF and FEGACIBAO will be national project partners.

Project governance will be carried through 3 levels as following:

i. Project Steering Committee (PSC): The PSC will be composed of the MARENA, the Ministry of Agriculture, and FAO. Its main function is to guide the implementation of the project, verify and approve the annual work plans, approve the financial and technical reports, and provide strategic guidance for the project.

ii. Project Advisory Committee (PAC): The PAC will advise on issues/problems that arise during the implementation of the project, provide timely technical assistance to the Project Coordination Unit and participate in meetings convened by the PSC. This committee will be composed of a representative of each implementing partner, namely, by the following institutions: MARENA, Climate Change Directorate; Ministry of Agriculture, Livestock General Directorate – MEGALECHE; CONALECHE; FEGACIBAO; Banco Agrícola, and FAO.

iii. Project Coordination Unit (PCU): The main function of the PCU, following the directives of the PSC, is to ensure the coordination and execution of the project through the effective implementation of Annual Work Plan(s) and Budget(s). The Project Team of will be made up of the Project General Coordinator (PGC), the Assistant Coordinator/M&E Expert, the Coordinators of Components 1, 2 and 3, and an Administrative-Financial Manager. The PCU will coordinate field activities with extension technicians of the MEGALECHE Program of the DIGEGA and field technicians of FEGACIBAO. The PCU will also coordinated the support of specialized technical assistance provided by the project partners (IDIAF) and others.

The Project General Coordinator (PCG) will be responsible for supervising and guiding the Project Coordination Unit (PCU). He/she will also be responsible for coordinating activities with all instances linked to the different components of the project, as well as with the partner institutions of the project. He will also be in charge of daily project management and technical supervision including: (i) coordinating and closely supervising the execution of project activities, (ii) day-to-day management, (iii) coordination with other related initiatives, (iv) ensure a high level of collaboration between participating institutions and organizations at the national, provincial and local levels; (v) monitor the progress of the project and ensure the timely delivery of inputs and outputs; (vi) implement and manage the project monitoring plan and its communication program.

The Administrative and Financial Manager will be responsible for the day-to-day financial management of the project, including lifting the contracts and acquiring other necessary supplies according to the approved Project Budget and Annual Work Plans. He/she will work in close consultation with the PGC and project implementing partners, particularly the FAO Representation in the Dominican Republic and the MARENA.

The Assistant Coordinator/M&E Expert will be operationally responsible for the timely delivery of the necessary inputs to produce results, reports, will organize annual project workshops and meetings to monitor the progress of the project, will monitor the environmental and social risk management plan, will prepare annual work plans and budgets, and will organize the logistics of the Mid-Term Review (MTR) and Final Evaluation (FE).

Decision-Making Mechanism of the Project

10. Knowledge Management. Outline the knowledge management approach for the project, including, if any, plans for the project to learn from other relevant projects and initiatives, to assess and document in a user-friendly form, and share these experiences and expertise with relevant stakeholders.

A communication strategy will be developed and implemented to ensure the fluid information exchange with producers, extension agents and institutional partners, in support of the activities of Component 1 (CLSM strategy), Component 2 (implementation of strategies at farm level, training, field visits), and Component 3 (MRV system). The communication strategy will work cross-sectionally to ensure that information on project results and lessons learned are disseminated to a broad audience through appropriate communication channels. Outputs and activities will include: information system for good CSLM practices, preparation of communication materials such as posters and brochures, presence in local media (TV, AM radio, newspapers), set-up and maintenance of a Project website and dedicated accounts of social networks throughout the project duration. FAO will provide a part-time Communications Specialist to support the implementation of the project communication and dissemination strategy.

At the regional and global levels, the project will support the publication of journal articles on project outcome, particularly concerning advanced on-farm GHG monitoring and implementation of low-emission livestock strategies. Project results will be presented at international conferences related to climate-smart agriculture. In addition, the project will facilitate the participation of project staff in events of international research networks and professionals. A series of webinars on low-emission livestock will be carried out through a regional association of networks to connect with colleagues from other countries in the region. FAO, through its Livestock Unit, will work to disseminate project results and lessons through Global Livestock Environmental Assessment Model (GLEAM), Livestock Environmental Assessment and Performance Partnership (LEAP), and other initiatives related to Climate-smart Agriculture (CSA). Worldwide dissemination will also be ensured through cooperation with the Climate and Clean Air Coalition.

# 11. Consistency with National Priorities. Is the project consistent with the National strategies and plans or reports and assessments under relevant conventions? (yes  /no ).  If yes, which ones and how:  NAPAs, NAPs, NBSAPs, ASGM NAPs, MIAs, NCs, TNAs, NCSA, NIPs, PRSPs, NPFE, BURs, INDCs, etc.

This project is aligned with the National Development Strategy, specifically with general objectives 4.1 and 4.3 on sustainable management of the environment and adequate adaptation to climate change respectively. Within these general objectives, the following specific objectives are considered:

- 4.1.1: Protect and sustainably use ecosystems goods and services, biodiversity and the national natural heritage, including marine resources. The following lines of action are considered within this specific objective: 4.1.1.6 Develop monitoring and evaluation systems, evaluating and systems to assess the state of the environment and natural resources at the national, regional and local levels, based on the consolidation of an Environmental Information System that includes the valuation of natural resources in national accounts. 4.1.1.8: Restore and preserve ecosystem services, with emphasis on river basins, as well as design and implement a payment for environmental services mechanism for the communities and productive unit.

- 4.1.2: Promote sustainable production and consumption. The following lines of action are considered within this specific objective: 4.1.2.1 Support the development and adoption of environmentally sustainable production and consumption technologies and practices, as well as the disincentive to the use of pollutants and mitigation of damages associated with highly polluting activities. .4.1.2.2: Strengthen intersectoral coordination and public-private collaboration in the promotion of sustainable consumption and production practices. 4.1.2.7: Develop incentives and market instruments to promote the adoption of cleaner production practices and consumption of goods and services generated under sustainable production.

- 4.3.1: Reduce vulnerability, advance in the adaptation of the effects of climate change and contribute to its mitigation. The following lines of action are considered within this specific objective: 4.3.1.2 Strengthen, in coordination with local governments, the system of prevention, reduction and control of anthropogenic impacts that increase the vulnerability of ecosystems to the effects of climate change .4.3.1.3: Encourage the development and transfer of technologies that help adapt forest and agricultural species to the effects of climate change.

In its National Action Program to Combat Desertification and to mitigate the Effects of Drought (PAN-LCD), the Government of Dominican Republic recognizes extensive livestock and overgrazing as causes of degradation of productive capacity of soils through processes of soil erosion and impoverishment. This initiative is relevant to PAN-LCD since its objective is to reduce GHG emissions generated by livestock production through the good management practices models for soil recovery in the Yuna basin.

The Project is also incorporated into the logical framework of the National Strategy for Climate Change Adaptation in the Agricultural Sector of the Dominican Republic, by being aligned with the totality of its results and with numerous of its corresponding activities:

Outcome 1: Planning and management instruments for climate change adaptation implemented in the agricultural sector in the Dominican Republic.

• Activity 1: Design planning and management instruments, in particular, design mechanisms to improve the consultation (inter and intra) between institutions and / or producer organizations

• Activity 2: Develop financial mechanisms for small and medium farmers, including designing methodologies to prioritize activities and / or allocate resources.

Outcome 2: Knowledge management system for climate change adaptation of the agricultural sector is created and functional.

• Activity 1: Develop and implement a specialized information platform on climate change in the agricultural sector. In particular, design and install a system or information platform to assess the impact of climate change in the agricultural sector.

Outcome 3: Authorities and productive actors with strengthened capacities on Climate Change Adaptation in the agricultural sector.

• Activity 3: Technical Assistance, where it is proposed to provide technical assistance for the application of good agricultural practices

• Activity 4: Monitoring the use of good practices

The project is consistent with Dominican Republic’s Intended Nationally Determined Contribution (INDC) to the UNFCCC submitted in 2015. According to the INDC, the country intends to reduce the base year emissions by 25% by 2030. Base year estimated emissions in 2010 are 3, 6 tCO2e per capita. The reduction target covers the Agriculture and LULUCF sector among others. The proposed project would not only contribute to the reduction of emission intensity for dairy production systems, but also improve carbon sequestration in 5,000 hectares, which is considered an important contribution to CO2 removal.

Lastly, this project is in accordance with the Nationally Appropriate Mitigation Actions (NAMA) concerning the pig farming sector in the Dominican Republic. This NAMA aims to reduce GHG emissions through anaerobic digestion in pig farms. The NAMA includes the installation of 1750 bio digesters. It is estimated that this activity can reduce 0.36 MtCO2e / year during its 5 years of duration.

The National Strategy to Strengthen Human Resources and the Competences to Advance towards a Green, Low Emission and Climate Resilient Development, (2012) highlights that one of the areas for the development of institutional capacities is the integration of topics related to climate change in sectoral strategies.

# 12. M&E Plan. Describe the budgeted monitoring and evaluation plan.

The monitoring and evaluation functions and responsibilities are summarized in the Table below. The monitoring and evaluation activities will be carried out through: (i) continuous monitoring and supervision visits by the project coordination unit (PCU); (ii) technical monitoring of the indicators to measure the global benefits by the PCU and the FAO Lead Technical Officer (LTO) in coordination with the partners; (iii) mid-term review and final evaluation (independent consultants and the FAO Evaluation Office); and (iv) monitoring and supervision missions (FAO). The project M&E activities are estimated at USD 150,288.

| M&E Activity | Responsible parties | Time frame/ | Budget |
| --- | --- | --- | --- |
|  |  | Periodicity |  |
| Inception workshop | General Project Coordinator (GPC) FAO Dominican Republic (FAODO) (Support from Lead Technical Officer -LTO and FAO-GEF Coordination Unit) | Within two months of project start up | USD 2,500 |
| Project Inception report | GPC, M&E and FAO Dominican Republic, con with clearance by LTO, and FAOR | Immediately after the workshop |  |
| Project level impact monitoring | GPC, project partners, local organizations | Continuous | USD 37,805 (5 % CGP+ 40% M&E and Coord.Assist) |
| Field level impact monitoring | GPC | Continuous | USD 16,768 (3 % GPC, 3% Technicians, 5% Farm-level monitoring system) |
| Supervision visits and rating of progress in PPRs and PIRs | GPC, FAO Sub-regional Office for Mesoamerica (SLM) and LTO, FAO-GEF Coordination Unit may participate in the visits if needed | Annual, or as needed | FAO visits will be borne by GEF agency fees |
|  |  |  | USD 7,681 (visits shall be borne by the project’s travel budget) |
| Project Progress Reports (PPRs) | GPC, with stakeholder contributions and other participating institutions | Six-monthly | USD 7,060 (3.5% of GPC & Assistant Coordinator) |
| Project Implementation Review (PIR) | Drafted by the GPC, with the supervision of the LTO and FAODO. Approved and submitted to GEF by the FAO-GEF Coordination Unit | Annual | FAO staff time financed though GEF agency fees. |
|  |  |  | PCU time covered by the project budget. |
| Co-financing reports | GPC with input from other co-financiers | Annual | USD 1,925 (1% of the Coordinator’s time and Fin.Manag.) |
| Technical reports | GPC, FAO (LTO, FAODO) | As needed |  |
| Mid-term review | FAODO, External consultant, in consultation with the project team, including the FAO-GEF Coordination Unit and others | Midway through the project implementation period | USD 15,000 for external consultancy |
| Mid-term workshop | CGP, FAODO (Support from LTO) | Immediately after Mid-term review | USD 2,500 |
| Final Evaluation (FE) | External consultant, FAO Office of Evaluation (OED) in consultation with the project team, including the FAO-GEF Coordination Unit and others | At the end of the project (to start at least 6 months before the completion date) | USD 50,000 for external consultancy. Staff time and travel costs will be financed by GEF agency fees. |
| Terminal Report | GPC; FAO (FAODO, LTO, FAO TCR Reporting Unit) | Two months prior to the end of the project | USD 6,550 |
| Terminal Workshop | GPC, FAO Dominican Republic (Support from LTO) | Immediately after the Final Evaluation | USD 2,500 |
| Total M&E budget |  |  | 150,288 |

part iii:  approval/endorsement by gef operational focal point(s) and GEF AGENCY (ies)

A.   Record of Endorsement of GEF Operational Focal Point (S) on Behalf of the Government(S): (Please attach the Operational Focal Point endorsement letter(s) with this template. For SGP, use this SGP OFP endorsement letter).

| Name | Position | Ministry | Date (MM/dd/yyyy) |
| --- | --- | --- | --- |
| Patricia Abreu | Deputy Minister for International Cooperation | Ministry of Environment and Natural Resources (MARENA) | 03/28/2018 |

B.  GEF Agency(ies) Certification

| This request has been prepared in accordance with GEF policies and procedures and meets the GEF criteria for a medium-sized project approval under GEF-6. |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Agency Coordinator, Agency name | Signature | Date (MM/dd/yyyy) | Project Contact Person | Telephone | Email Address |
| Alexander Jones, Director, Climate and Environment Division |  | 4 June 2018 | Carmelo Gallardo, FAO Representative | +1 8094736903 | Carmelo.Gallardo@fao.org |
| Jeffrey Griffin Senior Coordinator, GEF Unit, Climate and Environment Division |  |  |  |  |  |

- Additional GEF Project Agency Certification (Applicable only to newly accredited GEF Project Agencies) For newly accredited GEF Project Agencies, please download and fill up the required GEF Project Agency Certification of Ceiling Information Template to be attached as an annex to this project template.

ANNEX A:  PROJECT RESULTS FRAMEWORK (either copy and paste here the framework from the Agency document, or provide reference to the page in the project document where the framework could be found).

Please refer to the Appendix I of the FAO GEF Project Document, see pages 68-77

annex B:  calendar of expected reflows (if non-grant instrument is used)

Provide a calendar of expected reflows to the GEF/LDCF/SCCF/CBIT Trust Funds or to your Agency (and/or revolving fund that will be set up)

N/A

ANNEX C: DETAILED CARBON CALCULATION

Emissions from cattle production in Dominican Republic

Total emissions: Cattle sector produces about 6.3 million tons per year. Of which 31% and 69% is produced from dairy and beef sector, respectively.

Main sources of emissions:  Main source of emissions is from methane from enteric fermentation almost 84% while nitrous oxide from feed production and manure management contributes 11%. Emissions from CO2 associated with feed production, transport and processing and energy use are negligible.

Methodology: Both the baseline and mitigation scenarios were estimated based on the number of farms targeted by the project (500 farms in the Yuna basin) targeting 77,000 animals in total. Livestock GHG emissions were estimated based on FAO’s GLEAM model. GLEAM is a modelling framework that simulates the interaction of activities and processes involved in livestock production and the environment. The results include both direct (manure management and enteric methane) and indirect (feed production) sources of emissions related to dairy farming in Dominican Republic. Carbon sequestration potential was estimated based on the estimates proposed by Henderson et al. (2015) and the project area.

Figure 1: Key sources of emissions

Contribution to emissions by production system: 73% (4.6 million tons CO2 eq.) of the total emissions from cattle are produced from animals reared in mixed systems and the rest, 27% from grazing systems. Figure 2 illustrates the contribution of various sources of emissions to GHG emissions.

In all systems, methane from enteric fermentation is the dominant source of emissions; ranging from 73%-88%.  In grassland-based systems N2O emissions also contribute an important share of emissions: 20% and 16% of emissions from beef and dairy cattle reared on grassland based systems, respectively. These N2O emissions in grassland based systems is due to the large amount of manure that are deposited on pastures.

Figure 2: Contribution to GHG emissions by source within production system

Emission intensity (kg CO2 eq. /kg protein)

The cattle sector produces about 0.03 million tons of protein. At national level, the emission intensity from the cattle sector is on average 262 kg CO2 eq./kg protein.  Emission intensity of protein production from the beef and dairy sector is 121 kg CO2 eq./kg protein and 548 kg CO2 eq./kg protein, respectively.

Map: Cattle population in the Yuna Basin.

Mitigation scenario: The mitigation scenario presented in the document represents the adoption of sustainable agro-forestry (silvo-pastoral) practices in dairy farms and is an example of the possible interventions that can be applied in the project region.

The intervention would affect the productivity of the herd and the quality of the feed. The effects on reduced emissions are a result of the possible increment in forage quality, which would reduce enteric methane emissions and nitrogen excretion, combined with the reduction of the number of replacement animals required, thus reducing overall GHG emissions from the herd.

|  | Direct emissions |  |  | Indirect emissions |  | Total emissions |
| --- | --- | --- | --- | --- | --- | --- |
|  | N2O from manure management | CH4 from enteric fermentation | CH4 from manure management | CO2 from feed production | N2O from feed production |  |
|  | tonnes of CO2eq |  |  |  |  |  |
| Baseline | 13,234 | 139,027 | 3,974 | 10,462 | 29,094 | 195,790 |
| Mitigation | 11,075 | 120,755 | 3,321 | 9,051 | 9,436 | 153,638 |
| Emission reduction | -16% | -13% | -16% | -13% | -68% | -22% |

The application of improved practices to promote sustainable livestock can reduce total GHG emissions from 10 to 40% and increase herd productivity (milk and meat) from 10 to 70%, thus reducing both overall emissions and emission intensity by unit of product.

ANNEX D: Proposed good practices to promote sustainable livestock systems in the Yuna basin.

| Good Practice / Technology | Description of its use | Impacts |
| --- | --- | --- |
| Use of improved pasture varieties | - Improved varieties of pasture are used and adapted to the soil and climate conditions of the area. | - Increases the availability of fodder for cattle with higher nutritional content than natural grass. - Increases the production of milk and meat per cow and per land area. |
| Grazing with paddock rotation | - The frequency and the grazing period are adjusted according to the availability of pasture. - Improves efficiency in the use of grass and land surface. | Improve the quality and digestibility of forages; improve the performance of animal production. |
| Silvopastoral systems | - Integration, in the same land, of trees to the traditional livestock production (pastoral) for fodder, forestry and / or fruit purpose. | - It favors Carbon soil sequestration; improve the supply and quality of forage; improves animal production; reduces the exposure of animals to heat stress. - Increase forage production per unit area of land. - Farm income diversification (when using timber or fruit species). |
| Live fences (silvopastoral system arrangement) | - As a biological corridor and connectivity. It allows to integrate trees with different purposes (shade, wood, fruit, and fodder). - Improves the availability of fodder for livestock feed (when forage species are used). | - Improves soil conditions, especially when using legume species that fix nitrogen to the soil. - Increase forage production per land unit area. |
| Forage banks | - Improves soil conditions, especially when using legume species that fix nitrogen to the soil - Improves the availability of quality forages for livestock feed. | - It can reduce costs of feeding livestock, by reducing the consumption of concentrated feed and replacing forages with better nutritional composition than natural pastures. - Improves soil conditions, especially when using legume species that fix nitrogen to the soil. |
| Manure management | - Harnessing manure as a fertilizer for intensive-use cutting forages. | - Reduces the use of fertilizers of mineral-synthetic origin. -Improves soil conditions. - Increase forage production on the same surface. -Contributes to GHG emission reduction |
| Soil and water conservation in livestock farms | - Implementation of soil conservation practices, such as the use of live barriers (fodder, agricultural crops, and shrubs), dead barriers, and use of cover crops to prevent erosion. - Construction of water traps that facilitate water infiltration, and rainwater harvesting. - Reforestation of riverbanks located on livestock lands, using species of timber, fruit or fodder trees to reduce erosion of soils that affect the Yuna basin rivers. | - It favors soil carbon sequestration; improves crop yield and forage; increase feed supply and quality. |
| Genetic improvement of livestock. | - Adapted bovine breeds are used for the area climate conditions - The practices of artificial insemination and embryo transfer are used to achieve a more efficient improvement. | - It improves the adaptation of livestock to tropical climatic conditions -Improves the productive and economic efficiency of the farm. |

Project ID number will be assigned by GEFSEC and to be entered by Agency in subsequent document submissions.

When completing Table A, refer to the excerpts on GEF 6 Results Frameworks for GETF, LDCF and SCCF and CBIT programming directions.

Financing type can be either investment or technical assistance.

For the promotion and implementation of the approach to low-emission livestock production in Dominican Republic

For GEF Project Financing up to $2 million, PMC could be up to10% of the subtotal; above $2 million, PMC could be up to 5% of the subtotal.  PMC should be charged proportionately to focal areas based on focal area project financing amount in Table D below.

Provide those indicator values in this table to the extent applicable to your proposed project.  Progress in programming against these targets for the projects per the Corporate Results Framework in the GEF-6 Programming Directions, will be aggregated and reported during mid-term and at the conclusion of the replenishment period. There is no need to complete this table for climate adaptation projects financed solely through LDCF, SCCF and/or CBIT.

PPG of up to $50,000 is reimbursable to the country upon approval of the MSP.

PPG fee percentage follows the percentage of the Agency fee over the GEF Project Financing amount requested.

For biodiversity projects, in addition to explaining the project’s consistency with the biodiversity focal area strategy, objectives and programs, please also describe which Aichi Target(s) the project will directly contribute to achieving.

UN 2016 estimate

GIZ (2010) (GEF-UNDP, 2009, 2014) and World Bank (2016).

It is expected that with the development of this pilot initiative for the Yuna river basin, the information base and the application of appropriate methodologies to estimate GHG emissions from livestock will be strengthened and made accessible to all the country's producers.

Climate-smart Agriculture Sourcebook. FAO, 2013.

To this end, FAO and IICA are currently providing technical assistance to both Ministries through the Soil and Water Catalytic Project, to put the SNCS into full operation.

There are currently 228 technicians nationwide (52 technicians belong to the Yuna basin), who have already been trained by FAO and IICA (through the Soils and Water Catalytic Project) on soil and water conservation, agroforestry and sustainable livestock.

http://www.fao.org/gleam/it/

http://www.fao.org/partnerships/leap/en/

For regional and/or global projects in which participating countries are identified, OFP endorsement letters from these countries are    required even though there may not be a STAR allocation associated with the project.

GEF policies encompass all managed trust funds, namely: GEFTF, LDCF, SCCF, and CBIT