GEF-6 PROJECT IDENTIFICATION FORM (PIF)

PROJECT TYPE: Medium-sized Project

TYPE OF TRUST FUND: Capacity Building Initiative for Transparency

For more information about GEF, visit TheGEF.org

PART I: PROJECT INFORMATION

| Project Title: | Capacity-building program to comply with the Paris Agreement and implement its transparency requirements at the national level |  |  |  |
| --- | --- | --- | --- | --- |
| Country(ies): | Ethiopia. | GEF Project ID: |  | 9967 |
| GEF Agency(ies): | UNDP | GEF Agency Project ID: |  | 6208 |
| Other Executing Partner(s): | Ministry of Environment, Forest and Climate Change | Submission Date: |  | Re-Submission: March 8th,2018 1st Submission: December 21st, 2017 |
| GEF Focal Area(s): | Climate Change | Project Duration (Months) |  | 48 |
| Integrated Approach Pilot | IAP-Cities IAP-Commodities IAP-Food Security |  | Corporate Program: SGP |  |
| Name of parent program: | [if applicable] | Agency Fee ($) |  | 110,770 |

- INDICATIVE FOCAL AREA  STRATEGY FRAMEWORK AND OTHER PROGRAM STRATEGIES

| Objectives/Programs (Focal Areas, Integrated Approach Pilot, Corporate Programs) | Trust Fund | (in $) |  |
| --- | --- | --- | --- |
|  |  | GEF Project Financing | Co- financing |
| CBIT | CBIT | 1,166,000 | 192,000 |
| Total Project Cost |  | 1,166,000 | 192,000 |

- INDICATIVE PROJECT DESCRIPTION SUMMARY

| Project Objective: To enhance institutional and technical capacity related to climate transparency in Ethiopia |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Project Components | Financing Type | Project Outcomes | Project Outputs | Trust Fund | (in $) |  |
|  |  |  |  |  | GEF Project Financing | Co- financing |
| - Institutional capacity development. | TA | 1. Strengthened institutional capacity for transparency-related activities | 1.1. A permanent inter-ministerial body for high-level leadership and planning support instituted for periodic ENDC update in meeting Multilateral Agreements | CBIT | 75,000 | 10,000 |
|  |  |  | 1.2. Clearly defined roles and tasks of stakeholders for the implementation of the transparency requirements | CBIT | 85,000 | 18,000 |
|  |  |  | 1.3. National system | CBIT | 300,000 | 32,000 |

|  |  |  | for GHG emission inventory, and functional GHG database and information system established |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| - Technical capacity development tools, training and assistance. | TA | 2. Strengthened technical capacity for transparency-related activities, including tracking of progress towards attaining ENDC | 2.1. Guidelines on the formulation of GHG mitigation policy measures | CBIT | 100,000 | 19,000 |
|  |  |  | 2.2. Methods to quantify and integrate support needs into the public budget system and report on effective utilization of the support received | CBIT | 150,000 | 20,000 |
|  |  |  | 2.3. Experts, in key sectoral ministries, regional states and city administrations, fully conversant on the transparency framework | CBIT | 75,000 | 19,000 |
|  |  |  | 2.5 Data collection widened and improved to sustain the use of the 2006 IPCC Guidelines | CBIT | 125,000 | 10.000 |
|  |  |  | 2.6 Training on the use of 2006 IPCC Guidelines at relevant Ministries and universities carried out |  | 75.000 | 10.000 |
|  |  |  | 2.7 National universities engaged to support the Competent Authority in establishing QA/QC procedures and uncertainty analysis of the GHG inventory |  | 75.000 | 10.000 |
| Subtotal |  |  |  |  | 1.060,000 | 148,000 |
| Project Management Cost (PMC) |  |  |  | CBIT | 106,000 | 44,000 |
| Total Project Cost |  |  |  |  | 1,166,000 | 192,000 |

For multi-trust fund projects, provide the total amount of PMC in Table B, and indicate the split of PMC among the different trust funds here: (GEF)

- INDICATIVE SOURCES OF  CO-FINANCING FOR THE PROJECT BY NAME AND BY TYPE, IF AVAILABLE

| Sources of Co- financing | Name of Co-financier | Type of Co- financing | Amount ($) |
| --- | --- | --- | --- |
| Beneficiaries | The Ministry of Environment, Forest and Climate Change and sectoral ministries | In-kind | 142,000 |
| GEF Agency | United Nations Development Programme | Cash | 50,000 |
| Total Co-financing |  |  | 192,000 |

- INDICATIVE TRUST FUND  RESOURCES REQUESTED BY AGENCY(IES), COUNTRY(IES), FOCAL AREA AND THE

PROGRAMMING OF FUNDS a)

| GEF Agency | Trust Fund | Country/ Regional/ Global | Focal Area | Programming of Funds | (in $) |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | GEF Project Financing (a) | Agency Fee (b)b) | Total (c)=a+b |
| UNDP | CBIT | Ethiopia | Climate Change | (select as applicable) | 1,166,000 | 110,770 | 1,276,770 |
| Total GEF Resources |  |  |  |  | 1,166,000 | 110,770 | 1,276,770 |

.

- PROJECT PREPARATION GRANT (PPG)

Is Project Preparation Grant requested? Yes    No	If no, skip item E.

PPG AMOUNT REQUESTED BY AGENCY(IES), TRUST FUND, COUNTRY(IES) AND THE PROGRAMMING  OF FUNDS

| Project Preparation Grant amount requested: $50,000 PPG Agency Fee: 4,750 |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| GEF Agency | Trust Fund | Country/ Regional/Global | Focal Area | Programming of Funds | (in $) |  |  |
|  |  |  |  |  | PPG (a) | Agency Fee (b) | Total c = a + b |
| UNDP | CBIT | Government of Ethiopia | Climate Change | (select as applicable) | 50,000 | 4,750 | 54,750 |
| Total PPG Amount |  |  |  |  | 50,000 | 4,750 | 54,750 |

- Refer to the Fee Policy for GEF Partner Agencies.

- PROJECT’S TARGET CONTRIBUTIONS TO GLOBAL ENVIRONMENTAL BENEFITS

Provide the expected project targets as appropriate.

| Corporate Results | Replenishment Targets | Project Targets |
| --- | --- | --- |
| 1. Maintain globally significant biodiversity and the ecosystem goods and services that it provides to society | Improved management of landscapes and seascapes covering 300 million hectares | Hectares |
| 2. Sustainable land management in production systems (agriculture, rangelands, and forest landscapes) | 120 million hectares under sustainable land management | Hectares |
| 3. Promotion of collective management of transboundary water systems and implementation of the full range of policy, legal, and institutional reforms and investments contributing to sustainable use and maintenance of ecosystem services | Water-food-ecosystems security and conjunctive management of surface and groundwater in at least 10 freshwater basins; | Number of freshwater basins |
|  | 20% of globally over-exploited fisheries (by volume) moved to more sustainable levels | Percent of fisheries, by volume |
| 4. Support to transformational shifts towards a low-emission and resilient development path | 750 million tons of CO2e mitigated (include both direct and indirect) | metric tons |
| 5. Increase in phase-out, disposal and reduction of releases of POPs, ODS, mercury and other chemicals of global concern | Disposal of 80,000 tons of POPs (PCB, obsolete pesticides) | metric tons |
|  | Reduction of 1000 tons of Mercury | metric tons |
|  | Phase-out of 303.44 tons of ODP (HCFC) | ODP tons |
| 6. Enhance capacity of countries to implement MEAs (multilateral environmental agreements) and mainstream into national and sub-national policy, planning financial and legal frameworks | Development and sectoral planning frameworks integrate measurable targets drawn from the MEAs in at least 10 countries | Number of Countries:1 |
|  | Functional environmental information systems are established to support decision-making in at least 10 countries | Number of Countries:1 |

PART II:  PROJECT JUSTIFICATION

  - Project Description. Briefly describe: 1) the global environmental and/or adaptation problems, root causes and barriers that need to be addressed; 2) the baseline scenario or any associated baseline projects, 3) the proposed alternative scenario, GEF focal area strategies, with a brief description of expected outcomes and components of the project, 4) incremental/additional cost reasoning and expected contributions from the baseline, the GEFTF, LDCF, SCCF, CBIT and co-financing; 5) global environmental benefits (GEFTF) and/or adaptation benefits (LDCF/SCCF); and 6) innovation, sustainability and potential for scaling up.

- The global environmental problems, root causes and barriers

The Twenty-First Conference of the Parties to the UNFCCC adopted the Paris Agreement in 2015. The purpose of the Paris Agreement is to hold the global average temperature above that of the pre-industrial revolution level to well below 2 degrees and to continue mitigation actions until the temperature increase is reduced to 1.5 degrees. It envisages Parties achieving net-zero emissions of GHG after 2050, with developed country Parties leading. Accordingly, developed country Parties are required to set their respective economy-wide emission reduction targets with developing countries being initially allowed to set sectoral targets but to follow soon in setting economy-wide targets. To this effect, the Paris Agreement requires all countries to submit their respective nationally determined contributions at the latest when they become Parties to the Paris agreement. It also requires all Parties to submit their respective nationally determined contributions every 5 years while allowing them to adjust their respective nationally determined contributions to enhanced mitigation ambitions at any time. The Paris Agreement also expects all Parties to strive to formulate and submit their respective long-term low greenhouse gas development strategies. Article 5 encourages Parities to increase their respective forest cover as carbon sink.

The Paris Agreement puts adaptation on equal footing with mitigation. It specifies the global goal of adaptation by showing that reduced mitigation increases the need for adaptation. It also states that adaptation actions have to be country determined and that their implementation should be country driven. Nevertheless, it expects Parties to submit their adaptation plans and reports of the implementation of their respective adaption plans so that Parties can learn from one another. It also deals with loss and damage caused by extreme weather and slow onset events. It encourages Parties to support one another to minimize loss and damage.

Article 9 of the Paris Agreement requires developed country Parties to provide finance for adaptation and mitigation actions to be carried out by developing country Parties. It also encourages other Parties that can provide finance to do so. It emphasizes the need for providing finance to the least developed country Parties and to the small island developing state Parties. In particular, Paragraph 4 of article 9 of the Paris Agreement requires the provision of finance to be balanced between adaptation and mitigation. Paragraph 3 of article 9 encourages developed country Parties to keep increasing the financial resources that they provide to developing country parties.

The Paris Agreement requires financial and other types of support from developed country Parties to developing country Parties for technology development transfer for both adaptation and mitigation. It states that capacity- building in developing country Parities, especially in the least developed countries and small island developing states is essential for implementing the Paris Agreement. It also states that capacity-building must be country driven and that developed country Parties have the prime responsibility for supporting capacity-building in developing country Parties though all Parties should cooperate for the purpose.

Article 13 of the Paris Agreement requires transparency of action taken and support given to and received by Parties. The transparency system is envisaged to be compulsory for developed country Parties and facilitative for developing country Parties, including in capacity-building. It will stocktake on adaptation and mitigation actions and on the finance, technology and capacity-building given and used both for adaptation and mitigation actions.

The purpose of the framework for transparency of actions under the Paris Agreement is to provide a clear understanding of climate change action, including clarity and tracking of progress towards achieving nationally determined contributions, and adaptation actions, including lessons learned (good practices, priorities, needs and gaps) in order to inform the global stocktake. The purpose of the framework for transparency of support under the Paris Agreement is to provide clarity on support provided by developed country Parties and received by developing country Parties. To this effect, developing country Parties to the Paris Agreement, such as Ethiopia, are required to provide information on financial, technological, and capacity-building support needed, requested and received.

On the other hand, the Government of Ethiopia (GoE) does not have the proper technical, institutional and financial capacity to adhere to the transparency requirements on its own. Consequently, without support, it will continue facing significant barriers in addressing its current and emerging capacity gaps to comply with the Paris Agreement and to implement its transparency requirements at the national level.

- The baseline scenario and any associated baseline project:

The GoE is committed to making development towards a climate resilient green economy a national priority for two reasons: the GoE believes that a climate resilient green economy will be a critical enabler for i) its ambitious growth agenda by ensuring a sustainable use of resources and ii) making a substantial contribution to the global effort to tackle climate change through the reduction of its own emissions and through showcasing the successful climate proofing of its assets.

The GoE has ratified the UNFCCC in 1994, the Kyoto Protocol in 2005, the Doha Amendment to the Kyoto Protocol in 2015 and the Paris Agreement in 2017. It has also prepared and implemented a number of strategic measures and various projects aimed at building a climate resilient net-zero emitting economy by 2030. These include: the Climate Resilient Green Economy Strategy of Ethiopia (CRGE), the Sectoral Reduction Mechanism, Ethiopia’s Nationally Determined Contributions (E-NDC) and sectoral, regional and city administrations’ adaptation plans and various projects to contain the adverse impacts of climate change.

These strategies, programs, plans and projects are expected to have significant contributions to the national effort to comply with the Paris Agreement and implement its transparency requirements at the national level. However, their level of detail and comprehensiveness as well as the capacity needed for their implementation needs improvement. Therefore, to meet effectively the transparency requirements under the Paris Agreement, the GoE requires a) robust domestic institutions for transparency-related activities in line with national priorities, b) relevant tools, a training package and programs, c) needs-driven assistance and d) improving transparency over time. Without capacity- building support in these areas, the GoE will face significant barriers in complying with the Paris Agreement and implement its transparency requirements due to the following reasons:

- The CRGE requires the conversion of the Inter-Ministerial Committee, which proved effective in enhancing the status of the CRGE at the national, continental and international political landscapes, into a permanent body.. Lack of capacity to strengthen the existing system; including through the articulation of the required technical, policy and institutional foundations, is the main barrier that has delayed the establishment of a robust high-level inter-ministerial body that drives implementation, and promotes the participation of a broad set of stakeholders.

- The Proclamation for the ratification of the Paris Agreement has authorized the Ministry of Environment, Forest and Climate Change; herein after referred to as ''the Competent Authority'', to take actions necessary for the implementation of the Paris Agreement in cooperation with sectoral ministries, regional states, city administrations plus international institutions. This Proclamation is of a framework nature and that its implementation requires issuance of a subsidiary instrument. Moreover, the Sectoral Reduction Mechanism that was developed before the adoption of the Paris Agreement provides good perspectives but lacks comprehensiveness to serve as a vehicle for the delivery of the Paris Agreement and its transparency framework to the fullest. Therefore, effective coordination for the implementation of the transparency requirements in the context of the federal governance structure of Ethiopia; which consists of sectoral ministries, autonomous regional states and independent city administrations, will be challenging without informing and enabling sectors, regions and city administrations to discharge their respective roles and responsibilities in keeping with the transparency requirements specified under the Paris Agreement. Ethiopia has submitted its Initial National Communication (INC) in 2001 and Second National Communication (SNC) in 2016 to the UNFCCC. All sectors in the INC and SNC applied Tier 1 of the IPCC default values. The INC and SNNC used the 1996 IPCC Guidelines.  As it stands now, the Competent Authority does not have a well-established i) GHG inventory system, ii) GHG database and information system, iii) quality control (QC) and quality assurance (QA) system, iii) guidance document on determining sector specific national emission factors, base-year emissions, the most likely emission scenario and estimating GHG emission effects ex-post. Capacity is also lacking for the generation, archiving, analysis and sharing of quality GHG emission information and data for the formulation of BURs and NCs. The establishment and operationalization of a national system for GHG emission inventory, and a functional GHG database and information system creates an environment conducive for the preparation of the first BUR by 2020 and TNC by 2022. This would also allow the Competent Authority to adjust the E-NDC, raise the mitigation ambition of Ethiopia in accordance with the Paris Agreement and work towards the inclusion of the raised ambition into the post 2025 Ethiopia’s vision.

- The E-NDC sets out the objective of lifting Ethiopia to middle income status while reducing the sharp increase in GHG emissions and vulnerability to extreme weather events. The mitigation component of E-NDC has quantified GHG emission reduction targets while the climate resilient component enunciating a qualitative target on adaptation. According to E-NDC, in 2010, Ethiopia’s annual emission of greenhouse gases was estimated to be about 150 Mt of CO2e or 1.8 tons per capita. If development were to continue with business as usual, GHG emissions would grow to 400 Mt of CO2e or 3.0 tons per capita, in 2030, as estimated in the E-NDC. Therefore, 60 GHG emission abatement opportunities, distributed across seven sectors, are reaffirmed by the E-NDC for their potential to ensure that GHG emission levels in 2030 do not exceed 150 Mt of CO2e. However, the technical capacity to formulate the policy measures envisaged under the CRGE and E-NDC for the conversion of these GHG emission abatement opportunities into measurable, reportable and verifiable climate actions is at an early stage of development. As a result, reporting quantitative GHG emission mitigation information in conformity with the transparency requirements of the Paris Agreement cannot be done until such a time as these abatement opportunities are converted into implementable climate actions.

- The E-NDC, which covers both mitigation and adaptation, has defined the scope of climate finance as comprising both public and private sources and both grants and loans. The GoE has quantified its support needs to reduce its GHG emissions starting from the 2010 level. Accordingly, the estimated expenditure for the implementation of the mitigation component of E-NDC is around US$150 billion; around US$80 billion is capital investment and the remaining US$70 billion is operating and program expenses. Unlike the mitigation component, the GoE has not quantified the capital investment, operating and program expenses needed for the attainment of its national adaptation goal because its request submitted by E-NDC to does so has not been matched with support. There is limited experience to i) assess and quantify capacity-building support needs in monetary terms and ii) there is limited exposure to track the use of the support received for, and evaluate the effectiveness of expenditures on, climate change mitigation and adaptation actions because the existing public budget management system is not designed to deal with climate finance flows and expenditures.

- The knowledge base and capability of in-country experts regarding compliance with the Paris Agreement and particularly for the implementation of its transparency requirements at the national level is at an early stage of development. Many in-country experts are generally unfamiliar with transparency related activities and the requirements thereof. Although some are aware of the transparency requirements, there are many others that need to understand what transparency is all about and its potential values. There is an inadequate number of qualified experts that can plan, set targets and achieve the targets they set in conformity with the transparency requirements of the Paris Agreement.

Gaps and needs identified in the Second National Communication, submitted in May 2016, are among others:

- The data generating, gathering, archiving, and analyzing capability of the country is still inadequate and should be enhanced

- Relevant institutions such as the Ministry of Environment, Climate Change and Forest, the Ministry of Agriculture and natural Resource, the Ministry of Water, Irrigation and Electric city, the National Meteorological Agency and the Central Statistical Agency, need to be strengthened in terms of manpower training and facilities

- Skilled human resource development to handle climate change issues is a priority for Ethiopia. There is a need to develop and implement a training programme which contains both short-term and long-term training in among others GHG inventory, scenario development, mitigation analysis, V&A assessment, policy analysis

- Strengthening of the national focal institutions related to climate change.

- The proposed alternative scenario, GEF focal area strategies, with a brief description of expected outcomes and components of the project

This Project, “Capacity-Building Program to Comply with the Paris Agreement and Implement its Transparency Requirements at the National Level’’, has two components and two outcomes. It will be implemented through six outputs. The outputs elaborated herein below are aligned to Paragraph 18 of the Programming Directions for the CBIT which is to: a) strengthen national transparency related institutions to lead, plan, coordinate, implement, monitor, and evaluate policies, strategies, and programs to enhance transparency, including the identification and dissemination of good practices for institutional strengthening and national network of practitioners; b) support on how to integrate knowledge from transparency initiatives into national policy and decision-making; and (c) assist the deployment and enhancement of information and knowledge management structure to meet the needs of Article 13 of the Paris Agreement.

Further, information on project implementation and lessons learnt will be continuously shared with the UNDP/UNEP CBIT Global Coordination Platform, in order to make such information available to other Parties and initiatives while at the same time benefitting, through the platform, from other parties ‘experience.

Output 1.1: A permanent inter-ministerial body for high-level leadership and planning support instituted for periodic ENDC update in meeting Multilateral Agreements

An inter-ministerial approach was followed during the preparation of the CRGE. This Inter-Ministerial approach ‘‘… has proved instrumental to kick-start the CRGE–however, responsibility for further development and implementation of this crucial undertaking ought to be transformed into a permanent setting (CRGE, 2011). As it stands now, the said approach has not been yet transformed into a permanent body. To this effect, the Competent Authority will be supported to transform the Inter-Ministerial Committee into a permanent body for the provision of high-level leadership and planning support during the implementation of the Paris Agreement and its transparency requirements. For this to happen, a detailed background study will be undertaken on the tasks expected from the inter-ministerial body in strengthening coordination and instituting formal cooperation among government, civil society organizations (CSOs), the private sector and academia. The background study will be then used for the preparation of a draft public document that determines the structure, composition, tasks and modes of operations of the permanent inter-ministerial body. The adoption of this draft public document provides the Inter-Ministerial body the required legal status to become part of the national climate governance and to continue driving implementation, and promoting the participation of a broad set of stakeholders during and beyond the life span of this CBIT Project. Moreover, a series of national workshops will be convened to assess the draft public document and further articulate the tasks and responsibilities of the permanent inter-ministerial body in providing leadership and planning support across key emitting sectors and governance levels. The leadership and planning support that would come from this permanent body will help the Competent Authority to mobilize various actors and their activities for the common objectives of the transparency initiative. This will in turn strengthen transparency-related institutions to improve cooperation and collaboration among them so that any action taken by one provides an incentive for others to take complementary actions in their respective areas of engagement. The multi-stakeholder nature of the high-level body gives space for major stakeholders and thus leads to better understanding and consensus building in decision-making on matters related to transparency from the outset.

Output 1.2: Clearly defined roles and tasks of stakeholders for the implementation of the transparency requirements The Competent Authority will be supported to elaborate the roles and responsibilities of actors and stakeholders for the implementation of the transparency requirements of the Paris Agreement consistent with the federal governance structure of Ethiopia; which consists of nine autonomous regional states and two independent city administrations. This will be achieved through commissioning a study on who should do what, when and how so as to foster compliance with the Paris Agreement and implement its transparency requirements. The output of this study will serve as an input for the preparation of the subsidiary instrument specified under the Proclamation issued by the GoE for the ratification of the Paris Agreement. The said subsidiary instrument could be a guideline, a directive or another instrument that fosters coordination and partnerships towards reducing costs, boosting effectiveness and eliminating the risk of gaps or double-works during planning and implementation of the Paris Agreement and its transparency requirements. This subsidiary instrument should build on existing relevant works and emphasize on promoting compliance as non-compliance is most often a result of unawareness on the adverse impacts likely to ensue due to compliance failure. Stakeholders’ workshop will be convened, with approximately 30-50 participants, in order to solicit ideas and gather perspectives that help enhance the relevance and effectiveness of the sought subsidiary instrument. To this end, a background material and targeted discussion questions will be prepared to support engagement and the acquisition of feedback. Ultimately, the subsidiary document will be finalized and submitted to the Competent Authority or to the permanent inter-ministerial body for consideration, approval and guidance on future actions in facilitating the CBIT support to enable the country for measurable change in NDC tracking and reporting. The Ministry regularly organizes consultative dialogues to review the implementation of the national and sectoral adaptation and mitigation plans. This iterative process will ensure that national and sectoral adaptation and mitigation plans are regularly updated and implemented.

The Ministry of Environment, Forest and Climate Change is mandated for coordinating Climate Change in Ethiopia and it has also the mandate to follow implementation of all directive and ensuring and enforcing obligations set by the government of Ethiopia.

Output 1.3: National system for GHG emission inventory and functional GHG database and information system established

With the provision of needs-driven capacity-building support, a national system for GHG emission inventory and a functional GHG database and information system will be established, improved and maintained at the Competent Authority.

The establishment and operationalization of a national GHG emission inventory system will be facilitated through the provision of technical support on the collection of activity data, calculation of GHG emissions, assessment of uncertainties and implementation of QA/QC procedures so as to make certain the accuracy, completeness, consistency, transparency and reliability of an inventory and documentation of the inventory process.

This output will also include i) the establishment of a national team of experts, which will be drawn from key emission sectors, for undertaking and preparing a national GHG emission inventory report, ii) fostering linkage between the Competent Authority and the relevant sectoral ministries, national regional states and city administrations on data collection and processing and iii) procurement of state-of-the art equipment and tools for data collection and processing.

In addition, a functional GHG database and information system will be built, hosted and operated by the Ministry of Environment, Forest and Climate Change.  Such system, which will be fully electronic and automated, will facilitate enhanced exchanges among different data providers (line Ministries, private sector, districts and municipalities) and will be continuously updated with new data over each inventory cycle, with the expectations that through CBIT each new GHG inventory will be better than the previous one. All relevant stakeholders will be able to access such system virtually in order to check, review and improve data, as well as to revise calculations used for the elaboration of the inventory, thus creating an additional layer of quality assurance.

The GHG database and information system will also facilitate the storage of key documentation and data, data sources, methods, assumptions used. The establishment and operationalization of a functional GHG database and information system will then allow the Competent Authority to further engage other stakeholders in the MRV process thus strengthening Ethiopia’s capacities to fulfil its enhanced transparency framework.

Output 2.1: Guidelines on the formulation of GHG emission mitigation policy measures

The capacity of the Competent Authority to formulate guidelines for the preparation and implementation of GHG emission mitigation policy measures will be enhanced. The sought guideline will inform on how to set a mitigation goal, estimate baseline scenarios, define accounting methods, compute allowable emissions, track and report progress towards goal achievement, and on verification and reporting. The preparation of such a guideline helps the Competent Authority to prioritize the relevant policy measures that help convert the GHG emission abatement opportunities, specified under the E-NDC, into measurable, reportable and verifiable climate actions. The prioritized relevant policy measures by the Competent Authority would in turn constitute a suit of policy measures from which sectors, regions, and city administrations can choose and use for the preparation and implementation of their respective climate actions. These policy measures should stimulate investment in working towards a climate resilient net-zero emitting economy, and they can be sector specific, can be implemented at city, regional and federal levels and can be complemented by the private sector, civil society organizations and local community groups. The formulation and implementation of GHG emission mitigation policy measures helps to shift investment towards a resilient net-zero emitting economic growth and hence enhance the penetration of sector-specific low carbon technologies and good practices. The sought guideline should be simple, practical and internationally acceptable, and be accessible to the public. It will be also improved continually using lessons drawn during implementation and by taking into account new developments in the MRV field.

Output 2:2 Methods to quantify and integrate support needs into the public budget system and report on effective utilization of the support received

Capacity will be built on the quantification of the expenses needed for the attainment of the national adaptation goal in monetary terms and for the evaluation of the effectiveness of expenditures on, climate change mitigation and adaptation actions. This will be achieved through supporting the development of practical approaches and methods that inform climate and development planners on how to i) quantify support needs for building resilience to climate change and minimizing the cost of countering vulnerability in light of a changing climate, ii) integrate support needs for building a climate resilient net- zero emitting economy into the national budget management system and iii) track and report on effective utilization of the support received. For this scenario to happen, good practices will be gathered from a wide range of sources. The collection of these good practices inform the preparation of a draft document for discussion among planners, experts and decision makers on the quantification and integration of support needs into the public budget system and reporting on effective utilization of the support received, both for climate change mitigation and adaptation actions. Accordingly, a maximum of five workshops will be organized.

These workshops will examine the content of the draft discussion document and explore additional or new approaches and methods that help quantify support needs; track inflows and outflows of support; evaluate and report on the effective utilization of the support received. Consequently, a final document that contains methods on quantification and integration of support needs into the public budget system and reporting the effective utilization of the support received will be prepared and submitted to the Competent Authority or to the permanent inter-ministerial body for consideration, approval and guidance on future actions.

Output 2.3: Experts, in key sectoral ministries, regional states and city administrations, fully conversant on the transparency framework

The knowledge base and capability of in-country experts in key emission sectors on compliance with the Paris Agreement and implementation of its transparency requirements will be built. Output 2.3 will be in particular aimed at creating capacities in a broad range of stakeholders on NDCs, NDC tracking, NC/BUR reporting obligations and the establishment of the enhanced transparency framework.

Consequently, in-country experts in key sectoral ministries, regional states and city administrations will become familiar with and fully conversant on transparency related activities and the requirements thereof. For this to happen, needs-responsive knowledge and capability enhancement training packages will be prepared focused on the technical, policy, institutional and legal building blocks of the Paris Agreement and its transparency requirements. A phased training program will be then designed and implemented in order to enhance the capacity of experts that would ultimately become expert TOTs on transparency and related activities. The said trainings comprise lectures, interactive group discussions, case studies and other approaches that provide targeted training meant for adults. Ultimately, the TOT experts will train, interact, and provide follow up to other experts at sectors, regional states and city administrations. The TOTs will also be supported with pedagogic materials for their subsequent use. As a result, the GoE will have adequate number of qualified experts that can plan, set target and achieve the target they set on compliance with and implementation of the Paris Agreement.

Output 2.4. Data collection widened and improved to sustain the use of the 2006 IPCC Guidelines

Ethiopia, also being a LDC, has limited availability of updated and high-quality data to be used for the calculation of the GHG inventories. While output 1.3 will facilitate relevant stakeholders to provide sectorial data through the GHG database and information system, this output will be dedicated to support the enhancement of key data in the most relevant sectors, in particular AFOLU and energy. The PPG funding will be dedicated inter alia at developing an ad hoc review of data needs to decide and prioritize on the specific subsector where improvements of activity data will be instrumental to improve the quality of inventory, using the 2006 IPCC guidelines, and in tracking the NDCs.

Output 2.5 Training on the use of 2006 IPCC Guidelines at relevant Ministries and universities carried out

In an effort to enhance quality reporting, improving sustainability and building local capacities, designated experts from line ministries and partnering universities will be trained on the use of the 2006 IPCC guidelines for the preparation of the GHG inventory. More specifically, experts will be trained on the application of the new methodology, differences with the previously used revised 1996 guidelines, data needs and existing gaps. This output will be fully integrated with output 1.3, 2.5 and 2.6 and will allow Ethiopia to implement the 2006 IPCC guidelines in future inventories, starting from the ones to be submitted in the future Third National Communications and First BUR.

The PPG phase will also be partly dedicated at implementing an assessment of gaps, constraints and needs for the adoption of the 2006 IPCC Guidelines, which in turn will support the design and efficient implementation of this output, as well as related 2.4 and 2.6

Output 2.6 National universities engaged to support the Competent Authority in establishing QA/QC procedures and uncertainty analysis of the GHG inventory

Development of QA/QC procedures and how to undertake uncertainty analysis will be needed for a comprehensive improvement of the GHG inventory.

So far Ethiopia has had limited capacities to implement those processes with national experts, so the Competent Authority will work with national universities to create the proper capacities to implement QA/C and uncertainty analysis in the future cycles of GHG inventories, also in light of its transition to the use of the 2006 IPCC guidelines.

Such procedures are integral to improve the estimates of emissions and removals and the overall TACCC of the GHG inventory and will be implemented in close coordination to output 1.3, 2.5 and 2.6

- Incremental/additional cost reasoning and expected contributions from the baseline, the GEFTF, LDCF, SCCF, CBIT and co-financing

As a responsible member of the world, Ethiopia is aware of the important role that developing countries play in fighting climate change. Ethiopia’s ambition to become a “green economy front-runner” is an expression of its potential for and belief in a sustainable model of growth. Despite the challenges of being one of the world’s poorest countries, Ethiopia has dedicated significant resources to building a climate resilient green economy (e.g. investment in hydro power generation). To capture the full potential of the CRGE compatible with the transparency requirements, the GoE seeks and welcomes the support of the GEF-CBIT as it will help to achieve its ambitious climate change mitigation and adaptation goals as specified in its NDC.

As it stands now, there is discrepancy between the desired level of capacity and the existing capacity assets. Therefore, with the current scenario, the GoE will face significant barriers to address both its current and emerging capacity gaps. As a result, meeting the transparency requirements specified under the Paris Agreement will remain challenging and thus ensuring its compliance with the Paris Agreement will be compromised. The E-NDC has also shown that technical and financial assistance and institutional strengthening are key areas requiring support. Overall, without capacity building support:

- The establishment of the high-level body to drive the implementation and to promote the participation of a broad set of stakeholders through a robust horizontal and vertical coordination mechanism will be delayed because its establishment requires capacity which is not currently available. Spearheading the transparency initiative is particularly challenging as it crosses sectors and governance levels and also involves government agencies, smallholder farmers and pastoralists, the private sector and the civil society organizations. The achievement of this critical task requires capacity for the horizontal coordination of sector ministries and relevant agencies at the federal level. Although transparency related actions are first to be adopted at the federal level; their implementation involves regions, cities and local administrations. Therefore, capacity for vertical coordination is also needed to engage regions, cities and local administrations in transparency related activities.

- The preparation of policy measures for the conversion of the existing abatement opportunities into measurable, reportable and verifiable climate actions will not be fully materialized. As a result, the likelihood of promoting investment in climate actions and thus reporting GHG emission reduction, avoidance or removal in tones of CO2e is going to be difficult.

- The preparation and periodical reporting on national inventory of GHG emissions will remain difficult due to the lack of an integrated system for GHG inventory and monitoring GHG mitigation results and;ii) technical skills on gathering accurate activity data, determining coverage of key sources, adoption of sector specific national emission factors and absence of a plan to increase accuracy in measurement. Under such instances, it is unlikely for the GoE to prepare its first BUR and for that matter to develop and submit its future NCs and BURs in a manner that serves the decision-making needs both domestically and at the international level.

- Reporting on support needed, received and utilized in a concrete and timely way will remain difficult. As a result of this, the GoE will be deprived of inputs or experiences relevant for raising finance for increasing its adaptive capacity and reducing its cost of vulnerability to climate change impacts. It will be also deprived of inputs or experiences relevant for developing important links among sectors and actors at all governance levels to support future investment and barrier removal; and the acquisition of a broad picture of technology needs and penetration of resilient technologies throughout the priority sectors.

- It is unlikely to raise sufficient awareness and build the needed knowledge base and capability of in-country experts that are critically needed to foster the informed participation in, and the full implementation of, the transparency requirements under the Paris Agreement.

- Global environmental benefits (GEFTF) and/or adaptation benefits (LDCF/SCCF)

The implementation of this Project will have important contributions to the global fight against climate change. The main benefits at the global level are:

- Shifting investment towards a resilient net-zero emitting economic growth and enhanced penetration of sector- specific good practices and low carbon technologies.

- Limitation of net GHG emissions in 2030 to 145 Mt CO2e or lower as provided under the E-NDC. This would constitute a 255 MtCO2e reduction from the business-as-usual emissions (BAU) in 2030 or 64% reduction by 2030 from the BAU scenario.

- Reporting quantitative GHG mitigation information consistent with the transparency  requirements.

- Reporting quantitative adaptation information to inform and learn from other Parties.

- Reporting of accurate and consistent GHG emission information through TNC and the first BUR of Ethiopia.

- Innovation, sustainability and potential for scaling up

Innovation: The design and implementation of this CBIT fundamentally deviates from the BAU capacity-building activities that are most often once-off events, scant and uncoordinated. This Project thus aims to institutionalize capacity-building programs and to strengthen structures for the provision of capacity-building support for the engines of a climate resilient net-zero emitting economy. In particular, integration and implementation of transparency requirements into development activities, public budget allocation processes and education programs will foster compliance with the transparency requirements of the Paris Agreement now and well into the future. Overall, the project is designed to bring about:

- A transformative impact: the project will build capacity focusing on the triple capacity development pillars- systemic, organizational and individual levels. This will help to bring about a transformative change in achieving long-term programmatic outcomes consistent with the transparency requirements of the Paris Agreement and the vision of building a climate resilient middle income economy with net-zero growth in carbon emissions by 2030.

- An enabling environment: the implementation of the Project will create an enabling environment that will help public agencies, the private sector, community associations and civil society organizations to work with clear mandates which would also increase the confidence of investors in climate resilient economy and consumers of green goods and services.

- The GoE is committed to making development towards a climate resilient green economy a national priority. Moreover, the set of policy measures, guidelines, guidance documents and other products coming out of this Project will be submitted to the appropriate government organs, via the Competent Authority, with the objective of their contents being mainstreamed into relevant policies, legislation, institutional mandates and procedures, etc. As a result, the participating entities should continue their activities by using the products of this Project both during the current Growth and Transformation Plan (GTP) and its successors. The products of this Project can be also used by teaching institutions, research organizations and other training institutions. The Competent Authority will also ensure the full engagement of the participating entities in the process from the start so that the Project will be implemented with their full participation, including in decision making. These actions would also create a good potential for scaling up.

  - Stakeholders. Will project design include the participation of relevant stakeholders from civil society organizations (yes  /no     ) and indigenous peoples (yes  /no )? If yes, identify key stakeholders and briefly describe how they will be engaged in project preparation.

The key stakeholders and brief descriptions of their engagement in the project design and preparation are provided below:.

- The Competent Authority or the Ministry of Environment, Forest and Climate change, which is the focal institution for the UNFCCC, the Kyoto Protocol as amended and the Paris Agreement: coordinates and supervises the implementation of the transparency initiative. It will monitor climate actions so as to measure, report and verify outcomes, and provide appropriate access to information on actions and outcomes to the public. It will maintain close links with all regional states, city administrations, institutions of higher learning and relevant ministries including through the establishment of environmental/CRGE units within those ministries and other relevant agencies that do not already have them.

- The Ministry of Finance and Economic Cooperation (MoFEC): in collaboration with the Competent Authority, will solicit financial support from international sources and channel the available funds in the form of advance support or ex-post payment. The MoFEC will ensure transparency, objectivity, consistency, and professionalism in its operations to ensure compliance with international standards and the relevant domestic laws.

- Ministry of Health, Ministry of Agriculture and Natural Resources, Ministry of Livestock and Fishery, Ministry of Water, Irrigation and Energy, Ministry of Transport, Ministry of Industry, Ministry of Urban Development and Construction and National Meteorology Agency: will participate and encourage the participation of other entities in their respective sectors during the formulation and implementation of the transparency initiative. They are responsible for coordinating the implementation of sectoral or sub-sectoral resilient green economy activities, preparing and submitting monitoring reports as well as for designing, establishing and staffing their respective environmental units.

- National regional states and city administrations: in collaboration with the relevant federal level institutions, they are responsible for implementing the transparency initiative consistent with the CRGE and its E-NDC. Coordination at regional state and city administration levels will be under the responsibility of the respective environmental agencies of the national regional states and city administrations.

- The civil society organizations: engage in mobilization for implementation, awareness creation and contribution in consultation workshops. They will also bring the voice of local communities that are highly vulnerable and less able to respond to the adverse impacts of climate change. The participating civil society organizations include the i) Consortium for Climate Change-Ethiopia (CCC-E) which comprises 31 member NGOs, ii) Union of Ethiopian Women Charitable Association, which comprises a total of 63 member NGOs; of which 13 of the member NGOs are working on climate change and iii) Institute for Sustainable Development, which comprises 8 member NGOs that are committed to work on REDD+.

- The private sector: will engage in funding, mobilization for implementation, awareness creation, and participation in consultation workshops and implementation.

- Universities of respective regions to support the Competent Authority in establishing QA/QC procedures and uncertainty analysis of the GHG inventor with the 2006 guidelines

  - Gender Equality and Women’s Empowerment. Are issues on gender equality and women’s empowerment taken into account? (yes  /no	).  If yes, briefly describe how it will be mainstreamed into project preparation (e.g. gender analysis), taking into account the differences, needs, roles and priorities of women and men.

The ENDC states the commitment of Ethiopia to ensure the integration of actions that improve the status of women, the welfare children, care for the elderly, care for persons with disabilities and environmental refuges when measures to fight against climate change are being planned and implemented. Accordingly, the policy, strategy, programs and plans on gender equality and women’s empowerment issued by the GoE; including those relevant provisions contained under the Constitution of the Federal Democratic Republic of Ethiopia, will be used to do analysis and mainstream considerations of gender equality and women’s empowerment during the planning and implementation stages of the transparency related activities. To make this happen, a procedure or a protocol which takes into account the differences, needs, roles and priorities of women and men, will be prepared in an inclusive way, and will be implemented with informed involvement of women throughout the life cycle of this CBIT Project.

Moreover, this project will also take into account the GEF Gender Equality Action Plan (GEAP) and the recommendations included in the UNDP/UNEP GSP document Gender Responsive National Communications Toolkit, as Ethiopia considers CBIT to be a meaningful entry point for training, awareness-raising and capacity-building efforts to ensure women’s equal engagement in and benefit from climate change action.

4 Risks. Indicate risks, including climate change, potential social and environmental risks that might prevent the project objectives from being achieved, and, if possible, propose measures that address these risks to be further developed during the project design (table format acceptable).

The major risk that could hinder the successful implementation of the project and the response measures to minimize risks are:

- Unavailability of adequate number of qualified experts: The shortage of skilled human resource is likely to hinder compliance with the Paris Agreement and implementation of its transparency requirements at the national level. The Project addresses this barrier through the preparation of a needs driven training package and the implementation of programmatic capability enhancement training sessions, aimed not only at national authorities but also at universities and civil society who will be instrumental in supporting national efforts toward a enhanced transparency framework. The Competent Authority will also address such risk by identifying and harnessing existing capacities and skill sets in order to strengthen participation of national experts, whereas for cases where international consultants would be recruited they will be paired with local expert to facilitate knowledge transfers.

- Readiness to participate in GHG reporting: The business-as-usual behavior regarding GHG emission inventory and reporting could be shifted into climate-compatible behavior through the provision of targeted awareness raising and positive incentive measures.

- Financial risks: The Competent Authority in collaboration with the participating public agencies will request the allocation of public budget. It will also coordinate the efforts of the participating public agencies in identifying innovative financing options to close financial gaps.

- Institutional framework and governance risks: Besides the existing administrative structures and formal linkages established by the Competent Authority, a project management team as a separate unit in the Competent Authority, with a steering committee comprising representatives drawn from the participating key organizations, will be formed. A monitoring and evaluation guide will also be developed and used. A log frame along with work plan with identified timelines and deliverables will be used for the regular review of the progress by the Project Steering Committee.

- Socio-economic risks: The various actions under the project will identify and incorporate socio-economic risk abatement measures in accordance with the existing law. The existing law requires the undertaking of impact assessment prior to the adoption or implementation of any public or private development activities.

- Environmental risk during implementation: The Competent Authority will a) make sure that climate risk abatement measures are taken by public and private developers including through i) creating awareness on climate change related hazards, ii) improving early warning systems to minimize the cost of countering vulnerability and increase resilience to extreme weather events (drought, flood and diseases) by working together with the concerned public organizations, and c) requiring the preparation of a risk management system prior to granting a license to operate and renew licenses for public and private investors. data availability', with potential risk mitigation measures such as: (i) Build on the existing national data collection infrastructure;

- Data availability risk: While also focusing one of the outputs on improving data collection, the government will additionally: (i) Build whenever needed on the existing national data collection infrastructure; ii) organize training for all relevant M&E system users, including industrial data providers; (iii) provide flexibility to expand participation of data providers in order to cover new MRV tasks, (iv) provide continued support in data generation and sharing using M&E system, as appropriate.

- Coordination. Outline the coordination with other relevant GEF-financed and other initiatives.

PATPA is supporting the Ethiopian government in converting its NDCs into actions by identifying the link between NAMA and NDC and on how NAMAs can be used as one of the tools in achieving the objectives of the NDC.

Further, the Ministry of Agriculture and Natural Resources and the Ministry of Industry are developing their respective GHG emission database. The Project ‘’CCA Growth: Implementing Climate Resilient and Green Economy plans in highland areas in Ethiopia’’; which is financed by GEF and supported by UNDP, is ready for implementation. The Repi Waste-to-Energy Project is in its final stage of construction. The implementation of these projects in a complementary fashion helps to draw practical lessons relevant for the establishment of a national system for GHG emission inventory, database and information system in connection to land, industry and waste sectors. There could be also various initiatives that in one way or another contribute to the transparency initiative. Therefore, the design of this Project will take into account and include good practices and experiences of baseline initiatives with the aim of benefiting from synergistic relationships, avoiding duplication of efforts and leveraging baseline investments. To this end, the Competent Authority will foster formal coordination and cooperation between the participating entities including through tracking progress and raising awareness of the participating entities. In this regard, the first opportunity to promote coordination and collaboration is ensuring the participation of institutions and individuals involved in the implementation of baseline initiatives in the Project steering committee.

- Consistency with National Priorities. Is the project consistent with the National strategies and plans or reports and assessments under relevant conventions? (yes  /no	).  If yes, which ones and how:  NAPAs, NAPs, ASGM NAPs, MIAs, NBSAPs, NCs, TNAs, NCSAs, NIPs, PRSPs, NPFE, BURs, INDCs, etc.

The Project is consistent with and has been designed to serve as a vehicle for the delivery of: i) the UNFCCC, the Kyoto Protocol; as amended, ii) the Paris Agreement and iii) the CRGE Vision, the Green Economy Strategy, the Ethiopia’s Program of Adaptation to Climate Change (Climate Resilient Strategy) and E-NDC. This Project also fits well within the second five year Growth and Transformation Plan of Ethiopia (GTP). The GTP is directed towards achieving Ethiopia’s long-term vision and sustaining rapid and broad-based economic development.

- Knowledge Management. Outline the knowledge management approach for the project, including, if any, plans for the project to learn from other relevant projects and initiatives, to assess and document in a user- friendly form, and share these experiences and expertise with relevant stakeholders.

The Competent Authority will establish a team to better serve the participating entities and other stakeholders to effectively take part in the transparency initiative. The team will coordinate the exchange of knowledge and the learning and sharing of good practices. The participating entities under the transparency initiative will thus receive guidance and technical assistance from the team as follows:

- Guidelines and training materials: one key role of the team is to avail guidance and technical materials, prepare or facilitate the preparation of training materials and provide or facilitate the provision of training in various programmatic areas.

- Support: the support provided by the team will include establishing effective communication or providing technical support during the implementation stage, including in the identification of specialists for the transfer of green technologies and good practices.

- Innovative financing options: the team’s support will include the identification of domestic and international public and private financing options and sources.

- Knowledge and lessons learned: the support in this area will focus on the identification and dissemination of lessons learned and good practices obtained via various knowledge products to raise awareness and inform stakeholders and decision makers.

# PART III: APPROVAL/ENDORSEMENT BY GEF OPERATIONAL FOCAL POINT(S) AND GEF AGENCY(IES)

- RECORD OF ENDORSEMENT OF GEF OPERATIONAL FOCAL POINT (S) ON BEHALF OF THE GOVERNMENT(S):

(Please attach the Operational Focal Point endorsement letter(s) with this template)

| NAME | POSITION | MINISTRY | DATE (MM/dd/yyyy) |
| --- | --- | --- | --- |
| H.E. Mr. Kare Chawicha Debessa | State Minister, GEF Operational Focal Point | MINISTRY OF ENVIRONMENT, FOREST AND CLIMATE CHANGE | 02/28/2018 |

This request has been prepared in accordance with GEF policies and procedures and meets the GEF criteria for project identification and preparation under GEF-6.

GEF AGENCY(IES) CERTIFICATION

| Agency Coordinator, Agency name | Signature | Date (MM/dd/yyyy) | Project Contact Person | Telephone | Email |
| --- | --- | --- | --- | --- | --- |
| Adriana Dinu, UNDP GEF, Executive Coordinator |  | Re-Submission: 03/08/2018 | Damiano Borgogno | 0090 850 288 2629 | Damiano.borgogno@undp.org |

- ADDITIONAL GEF PROJECT AGENCY CERTIFICATION (APPLICABLE ONLY TO NEWLY ACCREDITED GEF PROJECT AGENCIES)

For newly accredited GEF Project Agencies, please download and fill up the required GEF Project Agency Certification of Ceiling Information Template to be attached as an annex to the PIF.

Project ID number will be assigned by GEFSEC and to be entered by Agency in subsequent document submissions.

When completing Table A, refer to the excerpts on GEF 6 Results Frameworks for GETF, LDCF and SCCF and CBIT guidelines.

Financing type can be either investment or technical assistance.

For GEF Project Financing up to $2 million, PMC could be up to10% of the subtotal;  above $2 million, PMC could be up to 5% of the subtotal. PMC should be charged proportionately to focal areas based on focal area project financing amount in Table D below.

PPG requested amount is determined by the size of the GEF Project Financing (PF) as follows: Up to $50k for PF up to$2m (for MSP); up to $100k for PF up to $3m; $150k for PF up to $6m; $200k for PF up to $10m; and $300k for PF above $10m. On an exceptional basis, PPG amount may differ upon detailed discussion and justification with the GEFSEC.

PPG fee percentage follows the percentage of the Agency fee over the GEF Project Financing amount requested.

Provide those indicator values in this table to the extent applicable to your proposed project.  Progress in programming against these targets for the projects per the Corporate Results Framework in the GEF-6 Programming Directions, will be aggregated and reported during mid-term and at the conclusion of the replenishment period. There is no need to complete this table for climate adaptation projects financed solely through LDCF, SCCF or CBIT.

For biodiversity projects, in addition to explaining the project’s consistency with the biodiversity focal area strategy, objectives and programs, please also describe which Aichi Target(s) the project will directly contribute to achieving.

For regional and/or global projects in which participating countries are identified, OFP endorsement letters from these countries are required 
  	even though there may not be a STAR allocation associated with the project.

GEF policies encompass all managed trust funds, namely: GEFTF, LDCF, SCCF and CBIT