Project Identification Form (PIF)

Project Type:

Type of Trust Fund:

PART I: Project Identification

| Project Title: | Sustainable Agricultural Livelihoods in Marginal Areas (SALMA) |  |  |
| --- | --- | --- | --- |
| Country(ies): | Lebanon | GEF Project ID: |  |
| GEF Agency(ies): |  | GEF Agency Project ID: | P131431 |
| Other Executing Partner(s): | GoL, Ministry of Agriculture | Submission Date: | 2012-09-05 |
| GEF Focal Area (s): |  | Project Duration (Months) | 60 |
| Name of parent program (if applicable): - For SFM/REDD+ |  | Agency Fee ($): | 714,763 |

A.  Focal AREA STRATEGY Framework:

| ### Focal Area Objectives | ### Expected FA Outcomes | ### Expected FA Outputs | ### Trust Fund | ### Indicative ### Grant Amount ### ($) | ### Indicative Co-financing ### ($) |
| --- | --- | --- | --- | --- | --- |
|  | Outcome 1.3: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas I | Output 1.3.1: Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability I |  | 5,700,000 | 22,000,000 |
|  | Outcome 2.3: Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level | Output 2.3.1: Targeted population groups participating in adaptation and risk reduction awareness activities |  | 1,107,272 | 4,100,000 |
|  | Others |  |  |  |  |
| Sub-Total |  |  |  | 6,807,272 | 26,100,000 |
| Project Management Cost |  |  |  | 340,363 |  |
| Total Project Cost |  |  |  | 7,147,635 | 26,100,000 |

- Project Framework

| ### Project Objective: The proposed project development objective (PDO) is to increase the growth and stability of on-farm income of small farmers in ecologically vulnerable remote hilly areas by: 1) Increasing access to reliable sources for supplementary irrigation using sustainable land and water development approaches; and 2) Enhancing reforestation and afforestation efforts by the GoL and local communities in targeted remote hilly areas. |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| ### Project Component | ### Grant Type | ### Expected Outcomes | ### Expected Outputs | ### Trust Fund |  | ### Indicative ### Grant Amount ($) | ### Indicative Cofinancing ### ($) |
| 1. Increasing rural incomes by expanding water storage in small reservoirs, supporting sustainable irrigation, and improving access to markets |  | (i) Increased value of crop production, particularly for small farmers; (ii) Increased production of fruits, vegetables and other high value crops (iii) Increased water storage capacity for irrigation uses; | (i) Construction of hill lakes and associated soil conservation works will increase the amount of water stored from seasonal springs and run-off during winter and spring, which will be available for supplementary irrigation by small farmers during the dry summer season; (ii) Beneficiaries of the hill lakes will be equiped with primarily gravity-based modern irrigation networks to allow efficient supplementary irrigation of high-value fruit and vegetable crops; |  |  | 2,200,000 | 16,000,000 |
| 2. Supporting reforestation and afforestation in upstream basins to enhance water management and reduce run-off |  | (iv) Enhanced protection of agricultural lands from soil erosion (v) Increased area under forest cover | (i) Reforestation and afforestation in the project areas to enhance watershed management and control soil erosion, focusing primarily on agro-forestry and non-wood products to provide additional sources of income for communities in the project areas; |  |  | 3,500,000 | 6,000,000 |
| 3. Technical assistance, capacity enhancement and project coordination |  | (vi) Enhanced Capacity in the MoA on environmental service requirements adapted to specific ecological zones of Lebanon. | (i) providing technical assistance and capacity enhancement to the MoA, particularly to better target its activities to benefit smaller farmers in remote hilly areas (ii) building the capacity of the MoA in areas related to Carbon Finance to allow the Ministry and local communities to benefit from novel sources of funding in support of national reforestation efforts. |  |  | 1,107,272 | 4,100,000 |
| Sub-Total |  |  |  |  |  | 6,807,272 | 26,100,000 |
| Project Management Cost |  |  |  |  |  | 340,363 |  |
| Total Project Costs |  |  |  |  |  | 7,147,635 | 26,100,000 |

- Indicative Co-financing for the project by source and by name if available, ($)

| Sources of Cofinancing | Name of Cofinancier | Type of Cofinancing | Amount ($) |
| --- | --- | --- | --- |
|  | Government of Lebanon |  | 1,500,000 |
|  | World Bank |  | 20,000,000 |
|  | IFAD |  | 4,600,000 |
| Total Cofinancing |  |  | 26,100,000 |

- GEF/LDCF/SCCF/NPIF  Resources Requested by Agency, Focal Area and Country1

| GEF Agency | Type of Trust Fund | Focal Area | Country Name/Global | Grant Amount (a) | Agency Fee (b)2 | Total c=a+b |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Lebanon | 7,147,635 | 714,763 | 7,862,398 |
|  |  |  |  |  |  | 0 |
|  |  |  |  |  |  | 0 |
|  |  |  |  |  |  | 0 |
|  |  |  |  |  |  | 0 |
|  |  |  |  |  |  | 0 |
|  |  |  |  |  |  | 0 |
|  |  |  |  |  |  | 0 |
|  |  |  |  |  |  | 0 |
|  |  |  |  |  |  | 0 |
| Total Grant Resources |  |  |  | 7,147,635 | 714,763 | 7,862,398 |

1  In case of a single focal area, single country, single GEF Agency project, and single trust fund project, no need to provide 
    information for this table

2   Please indicate fees related to this project.

part ii:  project JustiFication

- Description of the consistency of the project with:

A.1.1   the GEF focal area/LDCF/SCCF strategies /NPIF Initiative:

The project supports the fundamentals of the GEF adaptation strategy: “the strategic thrust of GEF-financed climate change activities is to support sustainable measures that minimize climate change damage by reducing the risk, or the adverse effects, of climate change. The GEF will finance agreed and eligible enabling, mitigation, and adaptation activities in eligible recipient countries.” In particular, the Strategy defines “adaptation activities as those that minimize the adverse affects of climate change.” The project is closely aligned with GEF SCCF adaptation strategy for 2010-2014 with the goal to support developing countries to increase resilience to climate change through both immediate and longer term adaptation measures in development policies, plans, projects and actions. Through the construction of hill lakes, the project will enhance the storage of run-off water and its availability during the dry and hot summer months. This will allow small farmers in poor and remote hilly areas to diversify their cropping pattern and sources of income by growing high-value fruit and vegetable crops through the use of supplemental irrigation. The accompanying afforestation and soil erosion works will protect exposed soils from erosion and reduce absolute losses due to climate change, including variability. The project will thus support adaptation practices to respond to climate change induced stresses in vulnerable ecosystems. The mountainous areas of Lebanon present an ecosystem under stress from increasing intense rainfall events coupled with lower total seasonal rainfall and higher summer temperatures, resulting in anticipated lower crop yields and incomes that would undermine livelihoods for remote rural populations in the poorest areas of Lebanon.

A.1.2.   For projects funded from LDCF/SCCF:  the LDCF/SCCF eligibility criteria and               priorities:

Lebanon meets the eligibility criteria for SCCF which covers “All developing countries that are parties to the United Nations Framework Convention on Climate Change (UNFCCC) are eligible to receive financial support for adaptation interventions to be integrated into development activities.” Lebanon ratified UNFCCC in 15‐12‐1994.

The project is in line with the purpose of the convention COP 7, which states that long term measures are eligible in the areas of (a) adaptation to climate changes and (c) sectors including agriculture and forestry. The planned activities address five of the nine programming priorities of the SCCF, i.e. (i) water resources management, (ii) land management, (iii) agriculture, (iv) fragile ecosystems including mountainous ecosystems and (v) supporting capacity building, including institutional capacity for preventive measures, planning, preparedness and management of disasters relating to climate change, including contingency planning in particular for droughts and floods in areas prone to extreme weather events. As such, activities are contributing to the focal areas CCA1 – Reducing Vulnerability through contributing to outcome 1.3 Diversified and strengthened livelihoods and sources of income for vulnerable people in target areas as well as CCA2 – Increasing Adaptive capacity through contributing to outcome 2.3 strengthened awareness and ownership of adaptation and climate risk reduction processes at the local level. A.1.3 For projects funded from NPIF, relevant eligibility criteria and priorities of the Fund: n/a

A.2.   national strategies and plans or reports and assessments under relevant conventions, if  applicable, i.e. NAPAS, NAPs, NBSAPs, national communications,  TNAs, NIPs, PRSPs, NPFE, etc.:

Lebanon, in its National Capacity Self Assessment (NCSA) for implementation of the Rio conventions, states that with regard to Lebanon progress in implementing the UNFCCC, it faces challenges due to “Human induced climate change will have a negative impact on soil productivity, which in turn will cause land degradation, desertification, soil erosion and reduced crop production. Projected temperature changes brought on by climate change will also negatively affect the forestry sector and supply of water resources. Thus any shift in Lebanon’s weather parameters brought on by climate change could lead to serious environmental, social and economic problems.” The project directly addresses this implementation requirement through addressing land degradation, soil erosion, adaptation requirements in the forestry sector and supply of water resources. Moreover, Lebanon’s Second National Communication to the UNFCCC highlights the importance of water harvesting as a key measure for CC adaptation of the agriculture sector and it specifically recommends that “water harvesting techniques should be promoted at all levels [sic,] and hill lakes and small water reservoirs at the farm level should be reinforced and subsidized by the government whenever there are opportunities to develop them.” The National Communication also recommends that “Irrigation systems that are water efficient such as drip irrigation, mini-sprinklers and sprinklers should be promoted.” The project’s activities in hill lake construction and associated modern irrigation systems fall squarely with these recommendations.

- Project Overview:
B.1. Describe the baseline project and the problem that it seeks to  address:

Agriculture plays a relatively minor role in the economy (contributing about 6% of GDP in 2004 and 8% of the effective labor force) but is particularly important in poor rural areas. The rural population accounts for only 13% of the total but a larger proportion is poor. Around 20 to 25% of the active population has some activity in agriculture (on a full time or part time basis, including seasonal family labor). In the poorest regions of the country such as in the South, Akkar (North Lebanon), and in the Baalbeck and Hermel area (Northern Bekaa), agriculture accounts for up to 80% of the local GDP. Farm households are diverse and typically engage in non-agricultural economic activities as well as in agriculture, although poorer rural households tend to rely more heavily on agriculture than better-off households. Only 14% of the land is arable due to the predominance of mountainous and upland terrain, of which 67% is actively farmed at present. Lebanon possesses relatively ample water resources compared to neighboring countries, with annual precipitation averaging 8.6 billion cubic meters (BCM). However, rainfall is concentrated during the winter months and irrigation is a key requirement for agricultural productivity given the Mediterranean climate and relative lack of rainfall during the long summer growing period. Around 20% of farm land is irrigated with production concentrated on high-value crops such as fruit trees, olive trees, and vegetables, while the non-irrigated land is planted to lower value rain-fed cereals, used for livestock grazing, or abandoned. Producers face a high cost structure due to the predominance of mountainous areas, a small domestic market and fragmented small holdings, and a high proportion of hired labor (around 30%), mostly foreign. Nevertheless, studies have shown that Lebanon has a comparative advantage in the production of high-value horticultural crops (fresh fruit and vegetables) and, due to geographic location, is in a position to export to high-income countries in the Middle East and Europe. However, lack of access to irrigation severely limits agricultural productivity and a shortage of irrigated land exacerbates poverty in rural areas since poor households tend to derive a larger portion of their household income from agriculture. This suggests that the development of agriculture, especially through the expansion of irrigation, would help improve income for the poorest rural households. The Ministry of Agriculture has already identified 100 potential sites to establish hill lakes to collect run-off and spring waters located in remote and ecologically sensitive areas to support poor farmers through access to supplemental irrigation. The IFAD-funded HASAD project will support the establishment of 7-8 hill lakes, whereas the IBRD-funded SALMA project will establish additional 14-15 hill lakes. Both projects will also support installation of modern irrigation equipment for the beneficiary small farmers. The HASAD project will establish Farmer Services Center in the project areas and beneficiaries from the two projects will be served by these. However, recent analysis of climate-change scenarios has provided evidence that these poor hilly areas of Lebanon are likely not only to receive less rainfall in the future, but also to receive it in fewer, more intense rainfall events. Hence, these poorer hilly regions of the country are expected to be exposed to a higher risk of drought and agricultural stress and a greater risk of run-off and soil erosion. Within this context, the IBRD-funded SALMA project will include a significant component for reforestation activities upstream from the proposed hill lakes to provide environmental services in the form of enhanced watershed management, reduced soil erosion and siltation

B. 2. incremental /Additional cost reasoning:  describe the incremental (GEF Trust Fund/NPIF) or additional (LDCF/SCCF) activities  requested for GEF/LDCF/SCCF/NPIF  financing and the associated global environmental benefits  (GEF Trust Fund/NPIF) or associated adaptation benefits (LDCF/SCCF) to be delivered by the project:

The IBRD-funded SALMA project will target three of the poorest regions of Lebanon: (i) Akkar-Danniyeh (North Lebanon); (ii) North Baalbek and Hermel (North Bekaa Valley); and (iii) South Litani below Lake Karaoun (South Lebanon). The largest component of IBRD funding will be used for the construction of 14 hill lakes and associated modern irrigation networks that would allow small farmers to expand the production of high-value fruit and vegetable crops using water harvested by the hill lakes for supplemental irrigation during the dry summer months. IBRD funding will also be used for the afforestation/reforestation of about 2000 ha focusing mainly on areas upstream from the hill lakes to enhance watershed management and reduce silting of the lakes. The requested 7.2 million USD in SCCF funding will be crucial to expand the area covered by afforestation beyond the immediate watershed areas of the hill lakes and possibly into other ecological zones with different CC sensitivity conditions. This would respond to the MoA clearly stated priority of expanding forest areas in all ecologically suitable zones in Lebanon. It would also be used to establish hill lakes in existing natural forest areas to irrigate newly established forest areas to ensure adequate growth of planted seedlings (which normally require 1-2 years of supplemental irrigation). The same lakes could also be used for the control of forest fires in areas with little access to water. SCCF funding will also be very important to build the capacity at MoA in the area of measuring and monitoring carbon sequestration as well as in providing the related laboratory equipment. This technical capacity will be instrumental to allow the MoA to benefit from future carbon finance opportunities that could provide increasingly important sources of revenues to sustain long-term afforestation/reforestation efforts. Thus, the GEF funding will not only enhance the IBRD and IFAD funding to strengthen the overall adaptive capacity of the poor communities in remote hilly areas in Lebanon, it will also provide additional critical support to expand and conserve overall forest and the country’s ability to contribute to CC mitigation and benefit from the anticipated expansion in carbon finance opportunities.

B.3. 	Describe the socioeconomic benefits to be delivered by the Project at the national and local levels, including consideration of gender dimensions, and how these will support the achievement of global environment benefits (GEF Trust Fund/NPIF) or adaptation benefits (LDCF/SCCF). As a background information, read Mainstreaming Gender at the GEF.":

The project will directly support enhancing long term livelihoods of poor rural communities in remote and marginal mountainous areas. The project will improve, diversify and stabilize the incomes generated from farming through improvement in agricultural productivity and crop mix as a result of access to reliable irrigation during the driest months of the year. As such, the project will support the resilience rural communities in some of the poorest and most ecologically fragile areas in Lebanon. The afforestation/reforestation activities will not only contribute to protecting the physical assets of the communities (agricultural soils, irrigation and drainage networks, roads, etc.), they will also generate income from the non-wood forest products. Revenues generated by forest products are particularly important for women who are mostly involved in these activities. Women will also benefit most from the shift in crop mix since fruit and vegetable production are particularly labor intensive activities, compared to traditional rainfed cereals production. Moreover, since a large number of men tend to seek seasonal construction work in nearby towns and cities, women are likely to benefit from the added income opportunities associated with the production of high-value summer vegetable and fruit crops. The processing and conservation of fruits and vegetables will also generate additional value-added for women and an expanded source of income for the entire household.

B.4	Indicate risks, including climate change risks that might prevent the project objectives from being achieved, and if possible, propose measures that address these risks to  be further developed during the project design:

Previous experience and lessons learned under the AIDP and from the on-going IFAD HASAD project, as well as the substantial experience of Green Plan (the implementing agency) in similar activities and the strong support from the Minister of Agriculture, limit the risks associated with project design and implementation. However, there are a number of project risks, including the procurement, financial management, and M&E capacity of the Green Plan. Risks will be addressed during project design and implementation as follows: - Fiduciary. During preparation the Bank team will ensure that project readiness requirements are met, including preparing the procurement plan and establishing a financial accounting system satisfactory to the Bank. Additional resources will also be provided during implementation. - Monitoring and Evaluation. Technical assistance is proposed for M&E system design and for surveys and impact assessments. Monitoring quality of construction will be assured through improving capacity of the Green Plan, particularly its regional offices. - Environmental Safeguards. An environmental specialist would be contracted with responsibility for environmental issues including safeguards. - Hill Lakes. There are risks related to selection of sites for hill lakes. Rigorous site selection criteria will be established and additional technical staff contracted and surveying equipment purchased to mitigate this risk. - Irrigation Systems. The current requirement for up-front financing by beneficiaries before reimbursement may limit the participation of poorer farmers. Conversely, if pre-financing is provided, there is a risk that the money will not be spent on the agreed works. Accordingly, possible pre-financing based on achievement of milestones or through a guarantee fund will be explored during preparation. - Forestry. Seedlings will be provided by the MoA and planting activities carried out by the municipalities under an agreement with the MoA. Reforestation activities will take place primarily on state-owned and municipal land. There are risks that inputs will not be forthcoming in a timely way, not all municipalities will place high priority on the task, and it will be difficult to agree on the land to be planted. There is also a risk that planted areas will not be managed effectively, resulting in low seedling survival rates. Management of tree plots for up to three years will need to be ensured during preparation. - Coordination Risks. There is a risk that component 2 implementation will be complicated by inadequate communication between the MoA and the MoE. Both agencies engage in reforestation activities and are promoting the National Reforestation Plan (NRP), but the division of resources is unclear. To mitigate this potential issue, a project steering committee including these ministries is proposed. - Partner risks. Several other agencies are implementing projects in forestry and hill lake construction (e.g. IFAD, USAID, UNDP and EU), with risks of overlap and different methodologies affecting implementation. In addition, the HASAD project is establishing Farmer Service Centers to provide associated extension and marketing support, which may not be delivered in a timely way. The Bank team will coordinate with key donors during design and implementation to minimize overlap and strengthen available synergies. - Climate change risk: Climate change induced intense rainfall in poor hilly areas leads to erosion and hill lakes are damaged and storage capacity lost, thus reducing adaptive capacity of farmers. The project will coordinate reforestation of the watershed with increase in storage capacity, thus increasing soil erosion protection and reducing the climate risk for farmers.

B.5. Identify key stakeholders involved in the project including the private sector, civil society  organizations, local and indigenous communities, and their respective roles, as applicable:

The major beneficiaries will be farmers and farmer cooperatives who will participate in the project through participatory planning of infrastructural works, contributing labor for construction and financially through cost-sharing for irrigation systems, and by contracting local contractors for small works. Other relevant stakeholders include municipalities, who will participate through provision of municipal land and in tree planting activities under an agreement with the MoA as is currently practiced. Local NGOs will also be contracted to manage the Farm Service Centers under the HASAD project

B.6. Outline the coordination with other related initiatives:

The Government of Lebanon (GoL) has requested an IBRD loan of $20m to support the Ministry of Agriculture in its efforts to enhance the sustainable development and resilience of the poorer hilly regions of the country as well as to contribute to the National Reforestation Plan which aims at reforesting 50,000 ha by 2020. The SCCF funds will be fully blended with this IBRD loan to improve the projects ability to enhance resilience to the projected adverse effects of climate change anticipated to further undermine the agricultural incomes of the farmers in these regions. They will also be used to complement the IFAD-funded Hilly Areas Sustainable Agricultural Development (HASAD) project, which became recently effective. The MoA has started the rehabilitation of 9 forestry nurseries and is developing 10 new forest centers in addition to equipping 34 existing ones to improve forest management and protection.

C.   describe the GEF agency’s comparative advantage to implement this project:

The World Bank has abundant experience in supporting water harvesting infrastructure for adaptation to rainfall variability through construction of small-scale lakes and reservoirs as well as the introduction of efficient modern irrigation systems. The World Bank has also extensive experience in reforestation projects as well as in sustainable land and water management operations. It can address multisectoral adaptation activities in an integrated way, while supporting capacity building for long term impact and country self sustainability. In Lebanon, the World Bank has a long experience in supporting investment projects in all sectors. This includes the Agriculture Infrastructure Development Project (AIDP) that closed in 2004, which included important components on the rehabilitation of hill lakes, soil erosion control and irrigation networks. The project team will include technical experts in agriculture, water resources management, reforestation, and climate change adaptation, in addition to operations experts. In addition to experts based at the World Bank HQ, the project team will also include procurement and financial management specialists based at the World Bank country office in Beirut which will also provide all the needed logistical and administrative support to the project team.

C.1   Indicate the co-financing amount the GEF agency is bringing to the project:

Total financing under the project amounts to 33.3m USD. The GEF amount is requested at 7.2 m USD, leveraging 20 million in IBRD co-financing and 6.1m USD in Government and IFAD co-financing. The resulting cofinancing ratio of GEF to other sources results in 1:4.5

C.2  How does the project fit into the GEF agency’s program (reflected in  documents such as UNDAF, CAS, etc.)  and staff capacity in the country to follow up project implementation:

The SALMA GEF blended project would contribute to the economic infrastructure area of engagement outlined in the Country Partnership Strategy (CPS) for FY11-14 and is aligned with the lessons learned in the FY08-09 Interim Strategy Note (ISN). Three aspects of economic infrastructure are addressed: agriculture, environment, and transportation. By directing resources to rural farmers the project will contribute to Strategic Goal 3.5 of the CPS, community driven development that will create jobs, income opportunities, and leverage local assets thereby increasing economic empowerment in communities and reducing regional disparities; and, Strategic Goal 4.2 of the CPS, improving living standards of the most poor and vulnerable parts of Lebanese society. Further, the project addresses two of three Millennium Development Goals (MDGs) that risk not being met by 2015: (i) halving extreme poverty; and, (ii) reversing environmental degradation. The project is also a priority for the GoL. On December 15, 2011, the Bank received an official letter from the Minister of Finance requesting financial assistance to support the Strategy of the Ministry of Agriculture to promote the agriculture Sector, particularly in the areas of natural resources development and agricultural infrastructure. On February 8, 2012, a World Bank Agriculture Sector mission met with H. E. the Minister of Agriculture to discuss the specifics of the request for financial assistance. A project focusing on establishment of hill lakes in remote areas and integrated activities related to construction of agricultural roads, upstream reforestation and/or agro-forestry, and promoting supplementary irrigation for the production of high value crops was agreed. On March 19, 2012, the Ministry of Finance officially requested an IBRD loan of US$20 million to finance a project covering the above-mentioned priority areas. A project identification mission visited Lebanon in July 2012 and conducted in-depth discussions with the team from the Ministry of Agriculture. Based on these discussions, a detailed outline was agreed on the proposed Sustainable Agricultural Livelihoods in Marginal Areas (SALMA).

part iii:  approval/endorsement by gef operational focal point(s) and GEF agency(ies)

A.   Record of Endorsement of GEF Operational Focal Point (S) on Behalf of the Government(S): (Please attach the Operational Focal Point endorsement letter(s) with this template. For SGP, use this OFP endorsement letter).

| Name | Position | Ministry | Date (MM/dd/yyyy) |
| --- | --- | --- | --- |
| H.E. Mr. Nazem EL-KHOURY | Minister | Ministry of Environment |  |

B.  GEF Agency(ies) Certification

| This request has been prepared in accordance with GEF/LDCF/SCCF/NPIF policies and procedures and meets the GEF/LDCF/SCCF/NPIF criteria for project identification and preparation. |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Agency Coordinator, Agency name | Signature | Date (MM/dd/yyyy) | Project Contact Person | Telephone | Email Address |
| Karin Shepardson, World Bank |  | 2012-09-05 | Song Li (Regional GEF coordinator MNA Region) | 202-473-3488 | sli@worldbank.org |

It is very important to consult the PIF preparation guidelines when completing this template.

Project ID number will be assigned by GEFSEC.

Refer to the reference attached on the Focal Area Results Framework when filling up the table in item A.

GEF will finance management cost that is solely linked to GEF financing of the project. PMC should be charged proportionately   
     to focal areas based on focal area project grant amount.

Same as footnote #3.