Project Identification Form (PIF)

Project Type:

Type of Trust Fund:

For more information about GEF, visit TheGEF.org

PART I: Project Information

| Project Title: | Community Resilience to Climate and Disaster Risk in Solomon Islands Project |  |  |
| --- | --- | --- | --- |
| Country(ies): | Solomon Islands | GEF Project ID: |  |
| GEF Agency(ies): |  | GEF Agency Project ID: | P112613 |
| Other Executing Partner(s): | Ministry of Environment, Climate Change, Disaster Management and Meteorology, Ministry of Development Planning and Aid Coordination, and Ministry of Provincial Government and Institutional Strengthening | Submission Date: | 2013-06-06 |
| GEF Focal Area (s): |  | Project Duration (Months) | 60 |
| Name of parent program (if applicable): - For SFM/REDD+ - For SGP - For PPP |  | Project Agency Fee ($): | 694,061 |

A.  indicative Focal AREA STRATEGY Framework:

| ### Focal Area Objectives | ### Trust Fund | ### Indicative ### Grant Amount ### ($) | ### Indicative Co-financing ### ($) |
| --- | --- | --- | --- |
|  |  | 1,100,000 | 1,280,000 |
|  |  | 450,000 | 1,330,000 |
|  |  | 5,755,900 | 4,738,000 |
| Total Project Cost |  | 7,305,900 | 7,348,000 |  |

- indicative Project description summary

| ### Project Objective: To increase the capacity of selected rural communities to manage natural hazards and climate change risks |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| ### Project Component | ### Grant Type | ### Expected Outcomes | ### Expected Outputs | ### Trust Fund | ### Indicative ### Grant Amount ($) | ### Indicative Cofinancing ### ($) |
| Integrate climate change adaptation and disaster risk reduction in policies and planning |  | Policies, development plans and budgets at national, provincial and community levels incorporate and support CCA and DRR measures | National and provincial policy makers, planners and budget officers embrace and support climate change adaptation and disaster risk reduction objectives The use of integrated V&A and Climate-DRR assessment process and methods is increased among Government officers, communities, NGOs field workers and other practitioners. Awareness, consultations and participation on CCA and DRR key issues are increased at national, provincial and community levels. |  | 700,000 | 650,000 |
| Strengthen climate and disaster risk knowledge and information |  | Capacity of government agencies and partners to generate and use data, information and modelling tools to support planning, implementation and monitoring of CCA and DRR strategies and actions is enhanced | On-line information sharing and use of ecological and socio-economic data to support planning and implementation of CCA and Climate- DRR measures is strengthened. Understanding and use of climate and disaster risk data and information by government agencies, NGOs and private sector is enhanced. Hazard mapping and weather forecasting improved |  | 450,000 | 1,330,000 |
| Community based climate change adaptation and disaster risk reduction investments |  | Vulnerability of selected communities against extreme events and climate change impact is reduced | Vulnerability and Adaptation (V&A) tools and Community Based Disaster Risk Management (CBDRM) tools are developed and formally applied in sub-projects 100 % of planned community based subprojects completed and maintained in targeted provinces. Sub-projects selected by the communities may include community shelters, improved water supply and storage system, cyclone strengthening of buildings frames and foundations, foundation raising for flood alleviation and shoreline protection systems. |  | 5,755,900 | 4,738,000 |
| Project management, M&E |  |  |  |  | 400,000 | 630,000 |
| Subtotal |  |  |  |  | 7,305,900 | 7,348,000 |
| Project Management Cost (PMC) |  |  |  |  |  |  |
| Total Project Cost |  |  |  |  | 7,305,900 | 7,348,000 |

- Indicative Co-financing for the project by source and by name if available, ($)

| Sources of Cofinancing | Name of Cofinancier | Type of Cofinancing | Amount ($) |
| --- | --- | --- | --- |
|  | Global Fund for Disaster Resilience and Recovery |  | 1,818,000 |
|  | Solomon Islands Government |  | 1,500,000 |
|  | The Japan Policy and Human Resources (PHRD) Fund |  | 2,730,000 |
|  | IDA |  | 1,300,000 |
| Total Cofinancing |  |  | 7,348,000 |

- indicative trust fund  Resources ($) Requested by Agency, Focal Area and Country1

| GEF Agency | Type of Trust Fund | Focal Area | Country Name/Global | Grant Amount ($) (a) | Agency Fee ($) (b)2 | Total ($) c=a+b |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Solomon Islands | 7,305,900 | 694,061 | 7,999,961 |
|  |  |  |  |  |  | 0 |
|  |  |  |  |  |  | 0 |
|  |  |  |  |  |  | 0 |
|  |  |  |  |  |  | 0 |
| Total Grant Resources |  |  |  | 7,305,900 | 694,061 | 7,999,961 |

1  In case of a single focal area, single country, single GEF Agency project, and single trust fund project, no need to provide information for   
    this table. PMC amount from Table B should be included proportionately to the focal area amount in this table.

2   Indicate fees related to this project.

- Project preparation grant (ppg)

Please check on the appropriate box for PPG as needed for the project according to the GEF Project Grant:

Amount                         Agency Fee

Requested ($)	      for PPG ($)

- No PPG required.                                           		       ___-- 0--________       _  --0--_______

- (upto) $50k for projects up to & including $1 million	       ___     ________      ___     _____

- (upto)$100k for projects up to & including $3 million      ___     ________      ___     _____

- (upto)$150k for projects up to & including $6 million      ___     ________      ___     _____

- (upto)$200k for projects up to & including $10 million   ___     ________      ___     _____

- (upto)$300k for projects above $10 million     	       ___     ________      ___     _____

PPG  Amount requested by agency(ies), focal area(s) and country(ies) for MFA and/or MTF roject only

| Trust Fund | GEF Agency | Focal Area | Country Name/ Global | (in $) |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | PPG (a) | Agency Fee (b) | Total c = a + b |
|  |  |  |  |  |  | 0 |
|  |  |  |  |  |  | 0 |
|  |  |  |  |  |  | 0 |
| Total PPG Amount |  |  |  | 0 | 0 | 0 |

MFA:  Multi-focal area projects;  MTF:  Multi-Trust Fund projects.

part ii:  project JustiFication

Project Overview
A.1. Project Description. Briefly describe the project, including ; 1) the global environmental problems, root causes and barriers that need to be addressed; 2) the baseline scenario and any associated baseline projects, 3) the proposed alternative scenario, with a brief description of expected outcomes and components of the project, 4) incremental/additional cost reasoning and expected contributions from the baseline , the GEFTF, LDCF/SCCF and co-financing; 5) global environmental benefits (GEFTF, NPIF) and/or adaptation benefits (LDCF/SCCF); 6) innovativeness, sustainability and potential for scaling up

# 1) Environmental Problems # Located east of Papua New Guinea, Solomon Islands has a very diverse population of 552,300 (World Bank 2011), a land mass of 28,000 sq km spread out over 1,000 islands and an Exclusive Economic Zone of 1.6 million sq km containing some of the richest tuna fish stocks in the Pacific region. The country’s biodiversity is of global significance. Its reefs contain one of the highest diversities of coral and fish found anywhere in the world placing the country in the coral triangle of the worlds most important marine biodiversity area. The country’s terrestrial biodiversity has been described as “globally outstanding” (Olsen and Dinnerstein, 1998) with its forests containing 4500 species of plants and is recognized as one of the world’s great centers of plant diversity. This rich globally significant biodiversity together with the population and economy of the country is now facing the threats of climate change. # The Solomon Islands National Adaptation Plan of Action (NAPA) has determined, through a broad national consultative process, that agriculture, human settlements, water and sanitation and human health are priority vulnerable sectors requiring urgent support to enhance resilience against the predicted impacts of climate change. The 84% of people living in rural areas (World Bank 2007) rely mainly on their traditional food production systems, traditional knowledge, and strong communal systems and on agriculture, fishing and small business activities to support livelihoods. The majority of rural dwellers reside on hilly and mountainous areas and along very low lying coastal areas with very high exposure to abnormal and extreme weather and climatic events. # 2) Baseline Scenario and Associated Baseline Projects # There is mounting evidence, supported by a number of assessments and surveys that a growing population of rural families and communities are struggling to cope with the effects of changing weather patterns, particularly heavy rainfall, extreme high tides exacerbated by sea level rise and periods of prolonged drought, on their food production systems and water catchments. The rapidly growing population (2.8% p.a., World Bank 2006) living on low lying islands and low coastal areas are now struggling to cope with abnormally high tides and intensifying storm surges never before experienced which is affecting food production and water quality. A number of global and regional climate models are predicting that this will increase and intensify over the coming years for this part of the world. Perennial flooding of inland areas and salt-water intrusion into low coastal areas due to flooding and king tides have caused the national government and communities to realize that water security is a serious and growing concern. # Over the past few years flooding, king tides, excessive rainfall and storm surges have rendered rural locations and communities as disaster areas with the frequency of calls for disaster relief assistance from the national government reaching levels never before experienced in the country since it attained political independence in 1978. A typical example is the flooding incident that occurred on west Guadalcanal in 2010 that devastated several villages and killing 9 people. The rainfall recorded at Honiara weather station during the night of the flooding was the highest daily rainfall ever recorded in 30 years (standing at 251.8mm). Unfortunately, despite the rising threats and increasing hardships and loss due to climate variability and climate change, national and provincial government sector plans and decision-making processes do not sufficiently reflect this challenge and the main attitude and approach to addressing climate related issues continue to be predominantly reactionary rather than anticipatory. # Climate Change Adaptation (CCA) and Disaster Risk Reduction (DRR) are treated at the policy, strategic and institutional levels as two separate but inter-related issues. This is creating a potential for mixed messages about climate change impacts, duplication of roles and inefficient use of resources to address priority needs, disjointed and separate knowledge bases, separate methodologies addressing the same challenge and unnecessary separation of funding mechanisms. The officers in the National Disaster Management Office and the Climate Change Division are pursuing different corporate agendas and fail to maximize the potential synergies that their lines of business offer. There is increasing national recognition of the need to align efforts and both the Climate Change Division and the National Disaster Management Office see the value of this. Support to amend legislation and transform existing structures will be required. # Although evidence of climate change related-impacts has been observed already and highlighted through the NAPA process, the lack of proper scientific research (specifically on climate change impacts) and baseline monitoring data and its analysis is an issue. Such scientific information is vital when planning adaptation options that are anticipatory and sustainable. High resolution model analysis is also necessary when doing specific analysis particularly given that Solomon Islands is scattered and diverse in its geographical make up. # Ongoing projects on Climate Change and Disaster Risk Management initiatives are currently underway in Solomon Islands and address partially some of the above mentioned issues. # In particular, the project will build on the pilot project funded by the Japanese Policy and Human Resources Development (PHRD) Fund for an amout of US$2,730,000 which has similar objectives and activities and will lay much of the ground work for CRISP implementation. The objectives of the PHRD Project are to: (i) integrate climate change adaptation and disaster risk reduction across the Recipient’s sectors; (ii) improve climate change adaptation and disaster risk reduction information and communications; and (iii) increase the resilience of rural communities to climate change and natural hazards. The project has four components: (A) Coordination between Climate Change Adaptation and Disaster Risk Reduction Institutions (B) Information and Communication (C) Pilot Investments and (D) Project Management, Monitoring and Evaluation. # GFDRR (EU-ACP) will provide co-financing to the CRISP for an amount of US$1.818,000. GFDRR activities will contribute to achieve the CRISP’s objectives, by funding additional community investments and strengthening the establishment of an early warning network for volcanic/seismic hazards (the needs for which were identified originally under the GFDRR Solomon Islands Country Assessment carried out in 2009). # The project will establish a strong partnership with the IDA funded Rural Development Program (RDP) and align with and wherever possible use the processes and procedures of the RDP for community led investments. The objective of the RDP is to raise the living standard of rural households by establishing improved mechanisms for the delivery of priority economic and social infrastructure and services by the public and the private sector. The project has a strong focus on delivery of community infrastructure and services which aims to increase access to and use of infrastructure and services in rural areas through participatory planning, budgeting and execution mechanisms at community and provincial level. The contribution of the RDP to the CRISP is estimated to amount 1,300,000 US$ (co-financing). # The project will also work closely with specific initiatives to ensure that collaboration, rather than duplication, is achieved, and to scale up community investments. These initiatives include: (i) the Pacific Catastrophe Risk Assessment and Financing Initiative (PCRAFI), which offers risk information methodologies and products that can be used directly during implementation of the CRISP, (ii) the Pacific Risk Resilience Programme (UNDP; AUSAID) which will Strengthen Disaster Risk Management and Climate Change Adaptation at the national, sub-national and local levels; and, (iii) various NGO initiatives and programs (e.g, Red Cross, Save the Children) which aims to strengthen disaster preparedness capacities of communities in various provinces of SI, promote Hazard Vulnerability Risk Assessment (HVCA) which leads to development and Implementation of Village Risk Reduction Plans, Simulation Exercises First Aid Training, and Formation of Disaster Risk Reduction Village Committee. # 3) Proposed Alternative Scenario # The proposed project would assist the government and people of Solomon Islands in addressing some of the NAPA priorities particularly as concerns human settlements, coastal infrastructure and water security. It would also support the process of planning, implementing and learning from adaptation strategies and actions that over time should help the country to deal with climate variability and change. The project will strengthen human resources, institutional and systemic capacity and pilot practical measures that would increase resilience to climate variability and change. This will be achieved through the proposed projects four components: # Component 1 - Integrate climate change adaptation and disaster risk reduction in policies and planning. # This component will support the integration of Climate Change Adaptation and Disaster Risk Reduction in policies, strategies, institutional arrangements and knowledge base at national and local levels. Particular attention will be given to the review of the current institutional arrangements with the aim of improving the link with national development planning. It will strengthen the capacity of government to include climate change considerations in development planing and sector investments and to use V&A and DRR tools. It will also provide training and support consultations and participation to raise awareness on climate change adaptation and disaster risk management and promote change in practices among government officials and stakeholders. # Component 2 - Strengthen climate and disaster risk knowledge and information. # This component will strengthen the capacity of government agencies and key partners to generate, understand and use data, information and modelling tools to support planning, implementation and monitoring of CCA and DRR strategies and actions. It will support information-sharing protocols and climate information networks; enhance data collection and provide training to use geophysical, ecological and socio-economic data and V&A and DRR approaches to support planning and implementation of CCA and Climate- DRR measures. This component will also support better hazard mapping and improved weather forecasting. # Component 3 - Community based climate change adaptation and disaster risk reduction investment # This component will support the implementation of provincial or community-level climate change adaptation and disaster risk reduction investment activities and engineering works to increase resilience of public infrastructure in targeted provinces. Possible investment funded by the project may include community shelters, improved water supply and storage systems, cyclone strengthening of buildings frames and foundations, foundation raising for flood alleviation and shoreline protection systems. # 4) Incremental Additional Cost Reasoning # The project contributes to existing and on-going policy and programmatic work that has been spearheaded by the government and supported by a range of development partners (incl. UNDP, WB through the PHRD project, AusAID, NGOs..),. The proposed project components propose to support this work and take it further with the additional funding available through the LCDF. Below is outlined how each component will benefit from the funds, showing the baseline and the post-project alternative. # Component 1 – Integration of climate change adaptation and disaster risk reduction in government policies and operations # Baseline: Currently two documents, the National Disaster Risk Management Plan (NDRMP) updated in 2010 and the National Climate Change Policy (2012 – 17) (NCCP) published in 2012, define the institutional structures and operational arrangements for managing climate change and natural disaster risks. # It is recognised that the NDRMP and NCCP Committee structures largely involve the same people, and that the focus of the hazards and risk reduction Committees under the NDRMP can also fully address the purposes of the NCCP after broadening their terms of reference and perhaps renaming the Committees. Also enabled in a legal sense, none of these Committees are operating in practice, and the various Ministries capacity to undertake analysis, planning and operations relating to climate change adaptation and risk reduction to natural hazards is very limited. # Short term policy advice is provided by PHRD/GFDRR to strengthen the policy framework on DRM and CCA, but a long term engagement is required to mainstream DRM/CCA in priority sector investments. # Adaptation alternative: Component 1 of CRISP will support the Solomon Island Government’s objective of getting the Committees and activities described in the NDRMP and the NCCP operating by: # (a) Appointing the NDC Risk Reduction Committee (probably to be renamed to reflect a wider climate change adaptation focus) as the CRISP’s Project Coordination Committee (PCC) with a significant part of its membership being Permanent Secretaries. This arrangement is specified under the Grant Agreement for the PHRD funds and will be carried over into the grant agreements for the GFDRR and GEF funds. # (b) Appointing a Policy/Operations Advisor who will work with MECDM and other key Ministries (primarily Ministry of Lands, Housing and Survey (MLHS), Ministry of Agriculture and Livestock (MAL), Ministry of Health and Medical Services (MHMS) and Provincial counterparts) to: # The project will further assist Ministries, primarily MECDM, MLHS, MAL and MHMS, to collect and analyse natural hazard risk and climate change information to aid policy development, priority planning for Ministry activities, and to provide resources and information that can be applied at Provincial, Ward and Village level for future donor funded, or self-directed Government or Community led investments and mitigation measures. Some of the outputs from this work will feed into the risk assessments done at Village level in develop sub-projects under the rural investments phase (Component 3) of the CRISP. # Component 2 – Strengthening climate and disaster risk information and communication # Baseline: Information that is relevant to disaster risk management and coping with the impacts of a changing climate is currently scattered across multiple agencies both within and external to the Solomon Islands Government. Organisations are reluctant to share the information they have with others and there is no formal protocol in place to guide how this might be achieved. GIS capacity exists within various ministries but it is not known if the data sets held by MLHS, MECDM, MoFT and MECDM are inter-operable or compatible with each other. In order to have a more thorough understanding of risk; of which areas and communities are most 'at risk', an enabling environment for combining information about physical vulnerability with information that reveals insights into social vulnerability must be created. Regional tools and data have been developed as part of the PCRAFI (Pacific Catastrophe Risk Assessment and Financing Initiatave) and are provided through SOPAC via that Pacific Risk Information web portal. While this data and tool exists, there would need to be additional training and engagement for them to be fully utilized by the stakeholders in the Solomon Islands and would not meet all the national needs for risk information and communication. # Looking specifically at the availability of risk information, there are significant limitations of existing data for climate related hazards and climate change impacts at the resolution needed to inform detailed planning. The communication of risk information should be supported by a combination of institutional and technical capacity; however there are limited resources available at the national and subnational levels to do either of these. Currently, risk relevant data is rarely used to inform planning decisions. # WB PHRD project in collaboration with EU supports the MECDM Climate Change Division in its effort of gathering risk information scattered across ministries. However a much more important and longer term engagement is needed to establish the foundation of a disaster risk information system and promote the effective use of risk information for planning decisions. # Adaptation alternative: This component will support the establishment of a national risk information platform and provide site-specific risk assessments and technical advice on adaptation options and risk reduction measures for community investments under component 3. # The design of the risk information system will be based on the following principles: # (a) Complement and strengthen existing capacities of respective agencies responsible for managing relevant geospatial data and risk information. # (b) Facilitate the exchange and sharing of climate and disaster risk information and other mapping data between ministries and regional organizations, and with beneficiaries through appropriate data governance arrangements. # (c) Build on and integrate data and information from relevant national and regional initiatives, such as PCRAFI, ClimSystems and the second national communication, the Pacific Australian Climate Change Science and Adaptation Planning Project (PACCSAP), the Solomon Islands DesInventar, the Honiara Urban Vulnerability Assessment, amongst others. # (a) Enable the development and production of easy-to-use risk information products, such as hazard and risk maps and decision support systems in support of national and provincial-level planning for climate and disaster resilient development, as well as disaster response and recovery planning # The project would support the establishment of a climate and disaster risk information system by: # (a) Undertaking a comprehensive needs and capacity assessment of the institutional arrangements, capacities and systems to capture, process, analyse and share geospatial data and risk information, as well as assessment of available geospatial data and other information sources to underpin risk identification. # (b) Facilitating the development of data governance arrangements in close interaction with the respective line ministries. This includes creating protocols and meta-data standards for sharing climate and disaster risk information and other mapping data, as well as establishing effective inter-agency working and data sharing arrangements. This work will build on that undertaken under the PHRD grant by extending the scope from MECDM to other Ministries. # (c) Providing appropriate computer hard- and software, mapping equipment for field data-capture and baseline data, such as recent satellite imagery of priority areas. # Component 3 – Climate change adaptation and disaster risk reduction investment activities # Baseline: Several projects, including the World Bank funded Rural Development project, develop a community driven approach to deliver small scale infrastructure investments, which provides to the communities direct control over key project decisions and the management of investment funds. However, the limited resources available and the lack of disaster risk information and awareness does not allow to take into account sufficiently the impact of natural hazards and climate change in decision making. # The NDMO and various NGOs (Act for Peace, Red Cross, World Vision, Oxfam, World Fish, Solomon Islands Development Trust, TNC etc..) have developed Community Based Disaster Risk Management (CBDRM) approach in their programs using various community participatory tools, processes and methodologies. These tools and processes provide guidance to communities for the development of their Community Based Disaster Risk Management Plan which includes the identification of key risks, strengthening preparedness and response mechanisms, and prioritizes risk reduction measures. However, very few plans and investments have been implemented so far. # Adaptation alternative: This component will support the development and implementation of community-based climate change adaptation and disaster risk reduction investments. It will expand the pilot investments to be implemented under the PHRD grant and other NGO initiatives; the investments will be carried out in close collaboration with the RDP. Vulnerability and Adaptation (V&A) tools developed in the Climate change Unit of MECDM and Community Based Disaster Risk Management (CBDRM) approaches will be applied to assist in investment sub-project identification and scoping. # Investments will be undertaken in two or more provinces. The rural investments proposed have not been identified in detail, but will be developed into sub-projects through the application of community-based disaster risk management (CBDRM) and vulnerability and adaptation (V&A) procedures applied in the target Provinces and villages. Sub-projects will be selected using a participatory community driven approach, which support community ownership and understanding of climate risks. # 5) Adaptation Benefits # Benefits will be achieved through strengthening the institutions responsible for disaster and climate work, improving alignement between DRM and CCA and mainstreming DRM and CCA in key sectors (eg. agriculture, water, rural development, roads/infrastructure etc). This will build institutional capacity, understanding and better inform decision-making related to climate adaptation and disaster risk through enabling access to climate data that is critical for informed decision-making by all stakeholders. # The second key adaptation benefit of the program will be the community level investments that will put communities in the decision-making seat regarding the climate and disaster resilience investment activities that each will undertake. Communities will benefit both from the direct investments that will increase the resilience of their livelihoods and communities, but also through the experience and skills they learn through the planning and exectution of the community-based investments. # 6) Innovativeness, Sustainability and Potential for Scaling up # The Solomon Islands Government is strongly committed to the project. It is already implementing an associated PHRD pilot project that is laying the ground work for the CRISP. Many of the initiatives related to capacity strengthening the CRISP proposes to support were initiated by the government, including the integration of climate change and disaster divisions into a single ministry, and the merging of policy into a single document. Regarding the community investments, SIG proposes to integrate these activities with existing structures established to implement the RDP, to support the institutionalization of standard procedures and increase the likelihoods of sustainability. The potential for scaling up is significant, with the use of government systems, the community assets could be pread through other provinces in which the Ministry has a strong presence.

# A.2. Stakeholders. Identify key stakeholders (including civil society organizations, indigenous people, gender groups, and others as relevant) and describe how they will be engaged in project preparation:

# The key stakeholders include the Government of Solomon Islands -the Ministry of Environment, Climate Change, Disaster Management and Meteorology specifically who will benefit from the institution building activities of Component 1, but including other ministires and division that will benefit from the climate and risk decision making information that will be developed in Component 2.  The second group of stakeholders to benefit will be the communities and civil society organisations that engage in the community investment for climate and disaster adaptation.  Direct benefits will be received through the building and maintenance of the investments, but extend to capacity building through the knowledge gained through the risk information developed and shared through component two.

# A.3 Risk. Indicate risks, including climate change, potential social and environmental risks that might prevent the project objectives from being achieved, and, if possible, propose measures that address these risks to be further developed during the project design (table format acceptable):

# The following risks and coinciding ratings and proposed mitigation measures have been considered for the project: # A) Political interference in the selection of sites for pilot investments (Rating M):The NAPA has already provided guidance on priority vulnerable areas. The project will use this as a starting point as well as selection criteria agreed with the project steering committee comprising technical experts. # B) There is potential that some of the project activities may duplicate existing initiatives and create confusion amongst government ministries and stakeholders (rating M): A careful analysis will be undertaken during project preparation to confirm the adaptation to climate change and disaster risk reduction initiatives being planned for implementation in the country with the aim of seeking complementarity and leveraging greater impacts. In light of this the project will work closely with the Rural Development Programme (RDP) to create compatible community based tools and to avoid replication at village levels. # C) There is limited technical capacity within the Ministry of Environment, Climate Change, Disaster Management and Meteorology to implement the project (rating H): A Project Management Unit (PMU) is currently being established under the PHRD grant to support the lack of capacity within the Ministry in terms of fiduciary management and project coordination. It is proposed that the CRISP will be supported by the same PMU. # D) There is insufficient data and information to support V&A work (rating M): The project will have a dedicated component to strengthen the capacity of government ministries and NGO to collect, analyze and use new and/or existing data. Community based V&A and DRR assessments will also contribute to generating field data and every effort will be made to utilize the rich collection of socio-economic data developed by the Statistics Division of the Ministry of Finance

# A.4. Coordination. Outline the coordination with other relevant GEF financed and other initiatives:

# The project is consistent with and supports the finding of the stock-take assessment funded by the Global Facility of Recovery and Reconstruction (GFDRR) that highlights country gaps and priority measures that would strengthen the country disaster risk management capacity.The proposed project will be coordinated alongside a number of other national projects addressing climate change, disaster risk reduction and the sectors identified in priority one of the NAPA (agriculture and food security, water resources management, coastal infrastructure and health and medical services). Coordination and collaboration with other projects and agencies will begin during the design stage of the project as well as during implementation and monitoring. The aim will be to ensure optimization of synergies and minimization of duplication. Opportunities will be sought and partnerships forged so that V&A and DRR tools can be used within the work of other projects. Other projects that will be directly related to this project include; GEF-Pacific Adaptation to Climate Change Project (PACCC) executed through SPREP and focusing on agriculture food security, Pacific Islands Climate Prediction Project (AusAID) to enhance seasonal climate services, Sea Level and Climate Monitoring Project – Phase IV (AusAID), Reducing vulnerability of Pacific States (EU), Coral Triangle Initiative (GEF, USAID, AusAID) focussing on the marine biodiversity and resource, Global Climate Change Alliance Initiative (EU), Small Grants Programme (GEF and NZAid) supporting community based conservation and livelihood initiatives, and the Rural Development Programme (World Bank, EC and AusAID) supporting agriculture development..

Description of the consistency of the project with:

# B.1 National strategies and plans or reports and assessments under relevant conventions, if applicable, i.e. NAPAs, NAPs, NBSAPs, national communications, TNAs, NCSAs, NIPs, PRSPs, NPFE, Biennial Update Reports, etc.: # The National Development Strategy (NDS) includes as national objective to “ effectively respond to climate change and manage the environment and risks of natural disasters” (sic) In addition, Cabinet endorsed: the NAPA in late 2008, the National Disaster Risk Management Plan (NDRMP) in 2010 and the National Climate Change Policy (NCCP) in 2012. The NDRMP and the NCCP both make specific and repeated reference to the need to align CCA and DRR efforts. # The Ministry of Environment, Climate Change, Disaster Management and Meteorology (MECDM) through its Climate Change Division and the National Disaster Management Office coordinates the implementation of the government policy on adaptation to climate change, key priority areas of NAPA, and disaster risk management and climate change adaptation strategies. MECDM in-partnership with the Ministry of Development Planning and Aid Coordination are capitalizing on monitoring and evaluation aspects of the Medium Term Development Strategy (MTDS) to mainstream policy issues of NAPA priority areas, and disaster risk reduction and climate change into the development planning process. The NAPA priority areas to which the project would contribute include water supply, awareness and information, coastal resilience, as possibly also agriculture, fisheries and marine resources, and food security. # It is envisaged that the proposed project will be critical to achieving the government’s objective of integrating disaster risk reduction and climate change adaptation into development planning and financial planning (budgetary) processes of the Government of Solomon Islands.

# B.2. GEF focal area and/or fund(s) strategies, eligibility criteria and priorities:

The project scope and intent conforms to the programming principles of the LDCF (UNFCCC Decision 7/CP.7 and GEF/C.28/18, May 12, 2006) and will target some of the priority vulnerabilities and capacity needs identified in the Solomon Islands NAPA of November 2008. The project focuses on Priority 1 of the NAPA which includes water and sanitation, human settlements and human health, education awareness and information. Components 1 and 2 of the project addresses institutional capacity needs, knowledge and information gaps and  mainstreaming  Climate Change Adaptation and Risk Reduction in national, provincial and community development plans and strategies. Component 3 will support the transition from vulnerability assessments to implementation of adaptation measures in priority sectors (water resources and coastal protection) included in Priority 1 of the NAPA and  is aligned with the scope of expected interventions articulated in the LDCF programming paper (Decision 5/CP.9).  The project is country-driven and will help to achieve Objectives 2 and 7 of the National Development Strategy 2011-2020. Objective 2 is “to support the vulnerable”, Objective 7 is to “effectively respond to climate change and manage the environment and risks of natural disasters” (sic).

The project will help the country build on the very limited baseline situation and help finance the additional costs of ensuring that climate change impacts are considered and addressed in national sustainable development planning and implementation processes and interventions. The detailed design will ensure that cost-effective measures are planned and implemented and sustainability ensured through strengthening the capacity of national institutions and communities. It will also complement a range of development programs and projects funded by the national government and donor partners such as the EC, AusAID, NZAid, UNDP, ADB and World Bank.

It recognizes that poverty and vulnerability to climate change impacts are intimately connected and its interventions will be holistic in scope and contribute to improving livelihoods and welfare and minimizing poverty while at the same time enhancing overall resilience to the predicted impacts of climate change. (GEF/C.28/18, 1(b), 29).

B.3 The GEF Agency’s comparative advantage for implementing this project:

The World Bank is well placed to be the GEF Implementing Agency for this project. Since becoming a Member of the World Bank in 1978 Solomon Islands and the Bank have developed a strong partnership in development financing and implementation. The Bank has extensive experience assisting Solomon Islands in a range of sectors including Rural Infrastructure, Education, Agriculture, Health and Institutional Strengthening. The Bank is currently co-funding a major rural development programme which will be closely linked to this proposed project. Communications and advisory support is expected to improve considerably with the recent establishment of a World Bank Country Office in Solomon Islands. In addition to its direct country experience the World Bank bring global and regional knowledge in addressing climate change adaptation and disaster risk management issues, experience in investment operations, convening power among development partners and ability to leverage co-financing.

part iii:  approval/endorsement by gef operational focal point(s) and GEF agency(ies)

A.   Record of Endorsement of GEF Operational Focal Point (S) on Behalf of the Government(S): (Please attach the Operational Focal Point endorsement letter(s) with this template. For SGP, use this OFP endorsement letter).

| Name | Position | Ministry | Date (MM/dd/yyyy) |
| --- | --- | --- | --- |
| Joe Horokou | Director of the Environment Division | MECDM |  |

B.  GEF Agency(ies) Certification

| This request has been prepared in accordance with GEF/LDCF/SCCF/NPIF policies and procedures and meets the GEF/LDCF/SCCF/NPIF criteria for project identification and preparation. |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Agency Coordinator, Agency name | Signature | Date (MM/dd/yyyy) | Project Contact Person | Telephone | Email Address |
| Karin Shepardson |  |  | Jiang Ru | +1-202-473-8677 | jru@worldbank.org |

Project ID number will be assigned by GEFSEC.

Refer to the reference attached on the Focal Area Results Framework and LDCF/SCCF Framework when completing Table A.

TA includes capacity building, and research and development.

To be calculated as percent of subtotal.

On an exceptional basis, PPG amount may differ upon detailed discussion and justification with the GEFSEC.

PPG fee percentage follows the percentage of the GEF Project Grant amount requested.

Part II should not be longer than 5 pages.