REQUEST FOR  enabling activity

Proposal for Funding Under the

# part i:  project IDentifiers

| EA Title: | Third National Communication to the UNFCCC |  |  |
| --- | --- | --- | --- |
| Country(ies): | Bangladesh | GEF Project ID: | 5189 |
| GEF Agency(ies): |  | GEF Agency Project ID: | 5170 |
| Other Executing Partner(s): | Ministry of Environment and Forests/Department of Environment | Submission Date: | 2013-02-28 |
| GEF Focal Area (s): |  | Project Duration (Months) | 36 |
| Check if applicable: | NCSA NAPA | Agency Fee ($): | 43,379 |

- EA framework

| ### EA Objective: To assist Bangladesh in the preparation of its Third National Communication (TNC) for the implementation of the obligations under the United Nation Framework Convention for Climate Change. |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| ### EA Component | ### Grant Type | ### Expected Outcomes | ### Expected Outputs | ### Grant Amount ### ($) | ### Confirmed Co-financing ### ($) |
| National circumstances |  | 1. National circumstances reviewed and updated and a chapter on National Circumstances prepared | 1.1. All available national and sectoral strategies, plans, programmes and studies relevant to the formulation of the TNC, including national development blueprints and poverty reduction strategy papers and strategies analyzed. 1.2. Information on geographical characteristics including climate, forests, land use and other environmental characteristics and information on population, economy and other services sector updated. 1.3. Information regarding specific needs and concern arising from the adverse impacts of climate change and the implementation of response strategies provided. | 20,000 |  |
| Green house gas (GHG) inventory |  | 2. GHG inventory reviewed, updated and the National GHG Emission Inventory for the year 2006-2010 prepared. | 2.1. Increased awareness among national institutions on methods of inventory preparation and needs for emission coefficients. 2.2.Local emission factors for agriculture sector assessed and updated. 2.3. National GHG Emission Inventory for the year 2006 and 2010 prepared, highlighting emission sources and sinks including key source analysis. 2.4. Development of Database Management system not only for GHGs but also for other gases. 2.5. Enhanced capacity to prepare future GHG Inventory. 2.6.National data collection capability enhanced and GHG Inventory management system designed. | 96,000 |  |
| Studies on vulnerability and impacts and programmes containing measures to facilitate adequate adaptation to climate change |  | 3.Programmes/action plan containing measures to facilitate adequate adaptation to climate change are carried out | 3.1.Information on key climate vulnerable sectors updated. 3.2. Improved scientific, technical and institutional capabilities for V&A assessments. 3.3. Establishment of long-term water supply analysis in the agricultural sector. 3.4. Improved planning of the most drought prone area of the country especially on the Barind tract. 3.5. Improved planning of urban and coastal areas considering the effects of climate changes (e.g. rise in sea level, storm surges, floods, etc.). 3.6. Programmes/measures to motivate studies on adaptation and barrier removal mechanisms in mainstreaming adaptation to climate change formulated. | 133,000 |  |
| Programmes containing measures to mitigate GHG emission |  | 4. Programmes containing measures to mitigate GHG emission are formulated. | 4.1.Based on the updated inventory data over the period 2006-2010 and recalculated emission data for the years 1990, 1994, 2001 and 2005, sub-sector mitigation strategy developed. 4.2. Current Government Policies analyzed and policies needed for implementation of recommended mitigation options suggested. 4.3. Mitigation measures for the LUCF sector and for CH4 in the agriculture sector formulated. 4.4. Mitigation measures in the energy sector developed. 4.5. Development of Baseline and mitigation scenarios for priority sectors completed. 4.6. Draft National Mitigation Strategy with relevant stakeholders shared and finalized. | 95,000 |  |
| Other information considered relevant towards achieving the objective of the UNFCCC and Constrains and gaps; related financial, technical & capacity needs. |  | 5. Other relevant information is described. (e.g. research programmes / systematic observation, technology transfer, education, training and public awareness, capacity building, information and networking). 6. Constraints and Gaps, Related Financial, Technical & capacity needs are assessed | 5.1. Increased integration of climate change issues into relevant social, economic and national environmental policies. 5.2.Increased awareness on climate change issues among general people. 5.3.Capacity building efforts enhanced and information exchange mechanisms among public and NGOs strengthened. 5.4. Technology,financial and capacity needs for mitigation and adaptation identified. 6.1. Constraints, gaps and needs, and activities for overcoming gaps, etc assessed. 6.1.Information on financial resources and technical support provided by the Government of Bangladesh and by the GEF, Annex II Parties or bilateral and multilateral institutions, for activities related to climate change documented. 6.2. A list of projects proposed for financing prepared. 6.3.Information on barriers to the implementation of adaptation measures collected and assessed. 6.4.Information on other relevant needs and/or areas for capacity building collected and analyzed. | 46,000 |  |
| Compilation, translation and edition of final report |  | 7. Stakeholder consultations, meetings organized, six draft chapter produced and peer reviewed of final TNC report produced. | 7.1 TNC is produced, edited, finalyzed, translated published, distributed among the stakeholders and uploaded in the website of the Ministry of Environment & Forests and Department of Environment. | 25,321 |  |
|  |  | . |  |  |  |
|  |  |  | . |  |  |
| Subtotal |  |  |  | 415,321 | 0 |
| EA Management Cost |  |  |  | 41,300 |  |
| Total EA Cost |  |  |  | 456621 | 0 |

a   List the $ by EA components.

- Co-financing for the EA by source and by name

| Sources of Co-financing | Name of Co-financier | Type of Cofinancing | Amount ($) |
| --- | --- | --- | --- |
| Total Co-financing |  |  | 0 |

- Grant  Resources Requested by Agency, Focal Area and Country

| GEF Agency | Type of Trust Fund | Focal Area | Country Name/Global | EA Amount (a) | Agency Fee (b)2 | Total (c)=(a)+(b) |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Bangladesh | 456,621 | 43,379 | 500,000 |
|  |  |  |  |  |  | 0 |
|  |  |  |  |  |  | 0 |
|  |  |  |  |  |  | 0 |
|  |  |  |  |  |  | 0 |
| Total Grant Resources |  |  |  | 456,621 | 43,379 | 500,000 |

- EA Management Cost

| ### Cost Items | ### Total Estimated Person Weeks/Months | ### Grant Amount ($) | ### Co-financing ($) | ### EA Total ($) |
| --- | --- | --- | --- | --- |
| ### Local consultants* | 178.50 | 36,400 |  | 36,400 |
| ### International consultants* | 4.00 | 4,900 |  | 4,900 |
| ### Office facilities, equipment, vehicles and communications* |  | 0 |  | 0 |
| ### Travel* |  |  |  | 0 |
| ### Others** |  |  |  | 0 |
|  |  |  |  | 0 |
|  |  |  |  | 0 |
| Total |  | 41,300 | 0 | 41,300 |

*   Details to be provided in Annex A.     **For Others, to be clearly specified by overwriting fields (1)-(3)

# Additional information for Table D, if applicable:

If costs for office facilities, equipment, vehicles and communications, travels are requesting for GEF financing, please provide justification here:  Various items for office facilities and equipment (Computers, Laptop, Printer, Photo copier, Fax and other furniture and accessories) need to be procured for the Project Team to perform official tasks. A car will be rented for official use and to supervise project activities, organize meetings, workshops and other project events throughout the country. Travels will also be arranged to visit project sites and to participate in the workshops and trainings which will be organized in different parts of the country and abroad.

(Details have been provided in Annex A).

# part ii:  Enabling Activity JustiFication

| A. Enabling Activity Background and Context (Provide brief information about projects implemented since a country became party to the convention and results achieved): | Bangladesh is a non-Annex-1 Country Party to the UNFCCC and ratified the Framework Convention in 1994. The GOB officially contributed to the pre-Convention negotiation processes, helped Kyoto Protocol (KP) to become a binding commitment to Annex-1 countries by endorsing it, and contributed to the Conference of Parties (COP) and the Meeting of the Parties (MOP). GOB representatives have been serving various official and technical bodies in various capacities, which include chairing the Least Developed Country (LDC) body on advancing adaptation, and other bodies such as the Consultative Group of Experts. A number of its nationals have contributed to the IPCC (especially in the Second, the Third and the Fourth Assessment Reports), advanced academic debates and methodologies on adaptation issues, developed a generic methodology to estimate GHG emission reduction from urban refuge management, and acted as resource persons/technical Committee Members for the relevant global institutions such as the UNFCCC Secretariat, UNEP, UNDP and the GEF. In this continuum of official as well as unofficial engagements/interactions, GOB has also reiterated the reasons for being so vulnerable to climate change in its Initial National Communication (INC), submitted in October 2002 and in the Second National Communication (SNC) which is yet to be submitted to the UNFCCC soon. In addition to the preparation of the INC with GEF & USA funding, the GOB carried out the National Adaptation Programme for Action (NAPA) with financial assistance from the GEF/ UNDP. The NAPA was submitted to the UNFCCC in November 2005. The Government of Bangladesh also produced the Bangladesh Climate Change Strategy and Action Plan (BCCSAP) in 2009. The BCCSAP is focused on medium and long-term actions (it lists 44 such actions) based on the six thematic pillars: food security, social protection and health; comprehensive disaster management; infrastructure; research and knowledge management; mitigation and low carbon development; and capacity building and institutional strengthening. Powerful ministries and departments, including Finance, Planning, Agriculture, Water Resources, Foreign Affairs, Local Government and the Prime Minister’s Office, were involved in the planning. The National Climate Self-Assessment (NCSA) programme has provided Bangladesh with the opportunity to identify priority capacity needs for effectively addressing the crosscutting global environmental issues. Through implementation of the abovementioned projects the institutional capacity has been built in the Department of Environment and other government, non-government, private and research organizations by providing training, policy inputs and suggestion on climate change related issues. The government officials, development planners, NGO workers and policy makers will be able to understand climate change issues easily and utilize the programmes containing measures to mitigate and facilitate efficient adaptation to the adverse impacts of climate change. It will be possible to develop projects addressing climate change mitigation and adaptation either at the sectoral or national level. The lives and properties of the people will ultimately be saved and the sufferings of the livelihood will be relieved and the general people of the country specially the women, children and the marginalized groups will be benefited from the project outputs. The projects have strengthened the technical and institutional capacity of the Government in mainstreaming climate change concerns into its sectoral and national development planning priorities. |
| --- | --- |
| B. Enabling Activity Goals and Objectives (The proposal should briefly justify the need for the project). | The proposed project will enable the Government of the People’s Republic of Bangladesh (GOB) to prepare and submit its Third National Communication (TNC) to the Conference of the Parties (CoP) of the United Nations Framework Convention on Climate Change (UNFCCC). The activities of the TNC formulation project are a continuation and an update of the work undertaken by Bangladesh in preparing its Initial and Second National Communication. Objectives: This project will facilitate the integration of climate change concerns (both mitigation and adaptation) into the national development policies and plans. ● Update data and information on climate change issues, ● Promote energy efficient pathways of growth and development, self-reliance, reduction of risks from climate related hazards, ● Prepare an updated GHG emission inventory for 2006-2010. ● The project will also highlight sectors/areas with the highest mitigation and adaptation potential. The project will furthermore: ● Enhance capacity within GOB institutions/agencies and NGOs. Relevant stakeholders of the private sector, civil society organizations, local and indigenous communities will be involved in the consultations/workshops/round tables to voice their concerns on climate change issues and other capacity building activities for professional advancements. ● Strengthen the coordination, networks and information flows between ministries, different levels of government and civil society to have a more efficient integration of climate change variables into poverty reduction and development strategies. ● Respond to the major constraints and gaps identified in the Second National Communication. |
| C. Describe the Enabling Activity and Institutional Framework for Project Implementation (discuss the work intended to be undertaken and the output expected from each activity as outlined in Table A ). | Activities for project implementation National Circumstances Data and information on National Circumstances provided in the SNC will be updated based on current realities. Review of the updated statistical information (as available) on geographical characteristics including climate, forests, land use and other environmental characteristics will be carried out. Information on population, economy and other services sector, national policies and development strategies of the country will be provided. Analysis of the links between poverty and climatic variability or between disaster and poverty in Bangladesh will also be done. A report (chapter) on National Circumstances of the TNC will be prepared based on the above activities. Greenhouse Gas Inventory It is envisaged that the Emission Inventory under the TNC will be conducted following the revised IPCC 1996 and 2006 Guidelines. It will also draw on the IPCC Good Practice Guidance and Uncertainty Management in National GHG Inventories, and the Good Practice Guidance on Land Use, Land-use Change and Forestry. The Inventory of the Third National Communication (TNC) of Bangladesh will be based on the 2006 IPCC Guidelines and the equations provided there will be used where available activity data permit. "In the cases where the 2006 IPCC Guidelines are identical to the revised 1996 IPCC Guidelines or where the data required are similar, the existing data can be used in the 2006 IPCC Guidelines without any modification or adjustment". According to the decision of COP, GWPs calculated in the Second Assessment Report (SAR, 1995) are to be used until the end of 2012. The revised 1996 IPCC Guidelines are based on the findings of SAR. Four major activity/sectors will be covered under the inventory, which include (a) energy (including biomass burning, transport sector, etc.), (b) IPPU (cement manufacturing, brick making industries, fertilizer, pulp and paper, rice parboiling, etc.), (c) AFOLU ruminant livestock, wet rice cultivation, grassland clearing/burning of agricultural residues, and livestock management, land-use change and forestry (change in forest cover and woody biomass, change in forest land-use etc.). (d) wastes & refuge management (fugitive methane from urban refuge, municipal wastewater treatment/management etc.), and all the major GHGs, excepting those included and reported under Montreal Protocol, will be covered in the inventory. More elaboration on calorific value of coal, breakdown of diesel into different uses, system loss of natural gas, activity data of biomass, CH4 and N2O emissions estimation will be provided as these were not elaborated in the GHG Inventory chapter of the SNC. A report (chapter) on Greenhouse Gas Inventory by sources and removals by sinks for the year 2006-2010 for Bangladesh will be prepared under the TNC. Mitigation Analysis The TNC will identify GHG emission mitigation measures which deal with the following potential aspects in energy sector: (i) energy conservation (human behavioural aspects, demand side management, measures directly saving energy use, etc.), (ii) energy efficiency (choice of efficient technologies, choice of efficient fuel for similar energy services, etc.), and (iii) renewable energy sources and services (solar homes, solar village, etc.). It is to be of special interest to assess comparative advantage/disadvantage of using diesel operated captive power generators for short-time users as compared to grid electric system. Transport sector mitigation measures will concentrate on the following: (i) move towards fuel-efficient technologies for similar transportation service (passenger kilometers), (ii) efficient fuel, and (iii) change in mode of transportation (e.g., shift in freight transportation from road to rail, promotion of mass transit system in urban transport mix, CNG buses instead of individual cars in common and high density routes, etc.). Mitigation is also possible in agricultural sector, which may deal with (i) manure management, and (ii) biomass burning. Irrigated areas have increased significantly in recent years. Therefore, it will be interesting to check whether wet rice production is producing more methane gas than ever before. Indication of increasing trend is given in the SNC. Regional values were used to determine the local emission factors. Modeling will be undertaken for mitigation assessment. Permanent conversion of agricultural land into urban areas will have to be evaluated in terms of emission sources. In the LULUCF sector, we may consider the following mitigation opportunities: (i) afforestation programme, (ii) replantation of already denuded designated forest areas, (iii) road side/embankment (line) forestry, and (iv) community afforestation (village/homestead, char lands, newly emerged coastal islands, coastal greenbelt, (v) REDD, etc. In recent years, Bangladesh has helped UNFCCC to devise a new methodology of estimating fugitive methane gas from urban refuge management. Since efficient management is possible through aerobic composting of bio-degradable refuge in urban areas, an effort will be made to estimate potential/actual mitigation of GHGs from such activities. In SNC, the mitigation exercise suffers from some incompleteness. First, mitigation has been analysed with respect to a baseline scenario only for energy-related activities and even then only for a set of chosen measures. How these have been chosen remains unclear. No baseline and mitigation scenario over time for non-energy activities have been constructed. This could perhaps be done at least for emission from future domestic rice output. There is another issue related to completeness. The mitigation measures give only partial effects of the measures, in relation to both energy/emission and their socio-economic impact. What should be attempted is the construction of energy and emission Input-Output tables and estimate the total emission reduction or increase due to mitigation measures throughout the economy from these tables. An economy-wide emission scenario gives better ideas of the effects of the mitigation measures by activity and indeed may suggest which measures would be more effective in aggregate (including both direct and indirect effects) than others. Besides, Cost benefit analysis of identified mitigation measures will be done, barriers to mitigation will be determined and policies regarding how to overcome them will also be formulated. Finally a report (chapter) on “Programmes containing measures to mitigate GHG emission” will be prepared. |
|  | Studies on vulnerability and impacts Bangladesh experiences tropical cyclones, storm surges, floods, riverbank erosion, droughts and many other natural disasters. The risk of climate change is accelerating the duration, magnitude and frequency of natural hazards and making communities more vulnerable. Natural hazards/disasters cause an immense effect on different sectors like agriculture, fisheries, livestock, forest and ecosystem, infrastructure etc. Climate change will further aggravate those effects. The vulnerability of these sectors is interdependent and ultimately impacts the livelihoods. To understand cumulative impact of climate change on different sectors and dependant livelihood, linkage between livelihood development and cross sectoral issues of climate change adaptation practices will be assessed. This will provide knowledge how the climate change impacts and adaptation practices can support the livelihood development in better way. In the SNC vulnerability analysis has been done. Yet the question as to what would happen to poverty, employment and gendered impact will be answered and elaborated in the TNC. The Bangladesh climate change adaptation strategy aims at ensuring the development targets related to food security, water security and livelihood security, and other socio economic aspects. However, it will also include climate resilient infrastructure development for promoting energy and water efficient agricultural production. Adaptation strategy to climate change should also ensure safeguarding of the ecosystem by protecting forestry and biodiversity and adopting low carbon development. Many projects are being implemented by GOB and NGOs in different areas of Bangladesh in the name of climate change adaptations. It is not well known whether funds of the projects are being properly utilized as well as vulnerable people are getting benefit from those projects. Often, performance of those projects is evaluated by the implementing agencies themselves. An independent socio-economic evaluation of the performance of those climate change adaptation projects will be done, which is very much crucial for development and implementation of adaptation projects in future. At the same time government adaptation policies and roles will also be reviewed. The people living in the coastal belt are facing severe cyclones and storm surges almost every year and every year they are losing their lives, property, crops, livestock and all their belongings. So, Integrated management programme of the coastal area will be formulated for coastal defense, proper land use, planning for adaptation for the future natural hazards and for attaining sustainable development. A country which aspires to be a middle-income nation in 10 years’ time and more or less eradicate poverty by that time must consider in all seriousness the possible impact that climate change may have on such goals. To understand these issues, at least a macroeconomic model of climate change impact will be constructed where the future macro variables could be estimated based on types of shock including those of mitigation and adaptation measures. This would have perhaps also given some idea of the deadweight loss due to climate change i.e., the loss that cannot be recouped under any measure. Without such estimates of financing need and the need of the specific technology, actual adaptation may become quite difficult. Though the general trends of climate variability is known and then impacts are experienced, but the detail micro-level analyses of climate variability for different months of the year and their Impacts on various sectors especially on water resources and agriculture has not yet been Performed which will be done in the TNC. |
|  | The future scenarios are available for winter and summer, which is not adequate to analyze the impacts on agriculture, So, the monthly scenarios will be developed under the TNC project. Other Relevant Information This component of the TNC will provide information on past and ongoing initiatives to integrate climate change in the national planning process, status of activities related to technology transfer, overview of climate change research and systematic observation, information on research programmes related to impact and adaptation, initiatives on climate change education, training and public awareness and finally the status of information and networking. Available documents and information from different public, private, local and international sources will be used in preparing this chapter of the TNC to enable the country towards achieving the objectives of the UNFCCC. Constraints and Gaps; Related Financial, Technical, & Capacity Needs This component will include a description on constraints and gaps, and related financial, technical and capacity needs, as well as proposed and /or implemented activities for overcoming the gaps and constraints, associated with the implementation of activities, measures and programmes envisaged under the convention, and with the preparation and improvement of Third National Communication. Institutional Framework for Project Implementation The project will be implemented by the Ministry of Environment and Forests (MOEF) through its technical wing, the Department of Environment (DOE).The DOE will provide office space and premises for meetings and conferences and assign a National Project Director as in-kind support of the government to supervise the officials and activities of the TNC project. The Project Manager/ National Project Coordinator (NPC) will facilitate and guide the processes of developing the TNC, while a Project Support Team will operate under the supervision of the NPD and National Steering Committee (NSC). A Core National Team (CNT) will also be formed to enable the Project Support Team to render specific services for the TNC preparation. The project will strive to create a technical advisory board to provide technical support to the national team, project coordinator for efficient and timely execution of the project activities. One Finance Assistant and one Programme Assistant will assist the Project Manager/NPC for implementing the project tasks.. As the Subsidiary Body for Implementation (SBI) stressed the importance of maintenance of the national technical teams which have implemented the tasks of the Second National Communication may be engaged to perform the tasks of the TNC. Additional Experts may be included in the national teams to conduct the activities of the components of the TNC more efficiently. Two or more DOE officials may be assigned with the national team on part time basis to collect activity data and prepare the GHG inventory to build the capacity of DoE for future GHG inventory preparation. The Core National Team will also arrange/facilitate capacity building activities under the project. UNDP Bangladesh Country Office will facilitate the implementation of the project on behalf of GEF and provide support services to the project in accordance with the UNDP procedures. These services may include sub-contract arrangements with individual experts/professionals (project support team members) and national institutions and procurement of goods and services as necessary. |
| D. Describe, if possible, the expected cost-effectiveness of the project: | Mainstreaming Gender in TNC Preparation Process Gender dimensions will be very much part of the project design and implementation as there is growing realization in Bangladesh women need to be meaningfully involved in such development efforts, not just as beneﬁciaries but also in the decision-making and planning process. Understanding how the different social roles and economic status of men and women affect, and are affected differently by climate change will improve actions taken to adapt to and to mitigate climate change. For this reason the EA components on, i) the national circumstances and ii) studies on vulnerability and impacts and programmes containing measures to facilitate adequate adaptation to climate change will consider this gender dimension in order to better understand how the different roles of men and women in Bangladesh’ social and economic circumstances may affect the country’s ability to deal with mitigating and adapting to climate change. Traditionally, mitigation actions have focused on reduction of industrial greenhouse gas emissions, but also include the practice of energy efﬁciency and the application of renewable energy in commercial and residential sectors. Such technology issues have generally been considered climate neutral, and the role of women in such climate change mitigation strategies has received little attention. But in reality, as climate change is partly the result of human behavior and affects all people, mitigation strategies must consider the gendered patterns of energy use in order to be effective. In this sense, the project will incorporate a gender perspective in the identification, description and preparation of mitigation actions when relevant. Additionally, efforts will be undertaken to maintain gender balance in engaging the core national team, National Steering committee and other Core Sectoral Working Groups of the Third National Communication. As the enabling activity of the TNC project will enhance national capacity building for climate change research, formulation of mitigation, adaptation and response strategies, preparation of the National Greenhouse Gas Inventory and implementation of the mitigation and adaptation policies and options, the requested fund will be applied in a cost effective way. The project activities will also be able to strengthen the technical and institutional capacity of the Government in mainstreaming climate change concerns into its sectoral and national development planning priorities which will ensure the cost-efficiency of the GEF Funds. |
| E. describe the budgeted M&E Plan: | Monitoring responsibilities and events A detailed schedule of project review meetings will be developed by the project management, in consultation with project implementation partners and stakeholder representatives and incorporated in the Project Inception Report. Such a schedule will include: (i) tentative time frames for Steering Committee Meetings, (or relevant advisory and/or coordination mechanisms) and (ii) project related Monitoring and Evaluation activities. Day to day monitoring of progress of implementation will be the responsibility of the Project Coordinator/Project Manager and the National Project Director (NPD) based on the project’s Annual Work Plan and its indicators. The project team will inform the UNDP-CO of any delays or difficulties faced during implementation so that the appropriate support or corrective measures Periodic monitoring of implementation progress will be undertaken by the UNDP-CO through Quarterly meetings with the project proponent, or more frequently as deemed necessary. This will allow parties to take stock and to troubleshoot any problems pertaining to the project in a timely fashion to ensure smooth implementation of project activities. Project Monitoring Reporting The Project Coordinator/Project Manager in conjunction with the UNDP- GEF extended team will be responsible for the preparation and submission of the following reports that form part of the monitoring process. (a) Inception Report (IR) A Project Inception Report will be prepared immediately following the Inception Workshop. It will include a detailed First Year Work Plan divided in quarterly timeframes detailing the activities and progress indicators that will guide implementation during the first year of the project. The report will also include the detailed project budget for the first full year of implementation, prepared on the basis of the Annual Work Plan, including any monitoring and evaluation requirements to effectively measure project performance during the targeted 12 month timeframe. The Inception Report will include a more detailed narrative on the institutional roles, responsibilities, coordinating actions and feedback mechanisms of project related partners. In addition, a section will be included on progress to date on project establishment and start-up activities and an update of any changed external conditions that may affect project implementation. When finalized the report will be circulated to project counterparts who will be given a period of one calendar month in which to respond with comments or queries. Prior to this circulation of the IR, the UNDP Country Office and UNDP-GEF’s Regional Coordinating Unit will review the document (b) Quarterly Progress Reports Short reports outlining main updates in project progress will be provided quarterly to the local UNDP Country Office and the UNDP-GEF regional office by the project team. (c) Annual Progress Reports/Project Implementation Reports: These reports will be prepared to monitor the progress made since project start and in particular for the previous reporting period. The APR/ PIR combines both UNDP and GEF reporting requirements. (d) Reports on Bi-annual monitoring through Status survey This report will provide information on the progress of preparing the national greenhouse gas (GHG) inventories, vulnerability and adaptation assessment, mitigation assessment, research and systematic observation, education, training and public awareness, technology transfer and capacity-building initiatives and activities, with a view to improving the accuracy, consistency |
|  | and transparency of information to be provided in the TNC. Monitoring through site visits: Project Board members as well as UNDP CO officials will conduct visits to project sites to ensure quality works and monitor timely progress of the project activities. End of Project: During the last three months, the project team will prepare the Project Terminal Report. This comprehensive report will summarize the results achieved (objectives, outcomes, outputs), lessons learned, problems met and areas where results may not have been achieved. It will also lay out recommendations for any further steps that may need to be taken to ensure sustainability and replicability of the project’s results. ###### Audit Clause: The Government will provide the UNDP Resident Representative with certified periodic financial statements, and with an annual audit of the financial statements relating to the status of UNDP (including GEF) funds according to the established procedures set out in the Programming and Finance manuals. The Audit will be conducted by the legally recognized auditor of the Government, or by a commercial auditor engaged by the Government. Learning and knowledge sharing: Results of the TNC project (reports, GHG Inventories and other documents) will be shared and disseminated among all relevant stakeholders of the country. The TNC will be uploaded in the website of the Ministry of Environment & Forests and Department of Environment. |
| F. Explain the Deviations from typical Cost Ranges (where applicable): | N/A |

part iii:  approval/endorsement by gef operational focal point(s) and GEF agency(ies)

# A.   Record of Endorsement of GEF Operational Focal Point(s) on Behalf of the Government(s): (Please attach the country endorsement letter(s) with this template).

| Name | Position | Ministry | Date (Month, day, year) |
| --- | --- | --- | --- |
| Mr. Mesbah ul Alam | Secretary and GEF Operational Focal Point, UNFCCC Focal Point | Ministry of Environment and forests | 01/08/2012 |

# B. Convention Participation

| Convention | Date of Ratification/ Accession (mm/dd/yy) | National Focal Point |
| --- | --- | --- |
| UNCBD |  |  |
| UNFCCC | 22 October 2001 | Mr. Mesbah Ul Alam, Secretary, Ministry of Environment and Forests (MOEF) |
| UNCCD |  |  |
| Stockholm Convention |  |  |

# B.  GEF Agency(ies) Certification

This request has been prepared in accordance with GEF policies and procedures and meets the standards of the GEF Project Review Criteria for Enabling Activity approval.

| Agency Coordinator, Agency name | Signature | Date (Month, day, year) | Project Contact Person | Telephone | E-mail Address |
| --- | --- | --- | --- | --- | --- |
| Adriana Dinu Officer in Charge UND/GEF |  | February, 28, 2013 | Yamil Bonduki Sr. Programme Manager | +1 212 906-6659 | Yamil.bonduki@undp.org |

# Annex A

# consultants to be hired for the Enabling Activity

| Position Titles | $/ Person Week | Estimated Person Weeks | Tasks to be Performed |
| --- | --- | --- | --- |
| For EA Management |  |  |  |
| Local |  |  |  |
| Project Manager | 250 | 90 | -Under the overall supervision of the National Project Director and UNDP Management, the Project Manager will be responsible for overall management of the project. -Supervise and coordinate the production of project outputs as per the project document; -Ensure the technical coordination of the project and the work related to legal and institutional aspects; -Mobilize all project inputs in accordance with UNDP procedures for nationally executed projects; -Finalize the ToR for the consultants and subcontractors; -Coordinate the recruitment and selection of project personnel; -Supervise and coordinate the work of all project staff, consultants and sub-contractors; -Work closely with UNDP Management and project partners to closely coordinate all the actors involved with achieving Project Outcomes, Outputs and Activities; -Supervise the work of all members of the PT; -Prepare and revise project work and financial plans, as required Government and UNDP; -Manage procurement of goods and services under UNDP guidelines and oversight of contracts; -Ensure proper management of funds consistent with UNDP requirements, and budget planning and control; -Arrange for audit of all project accounts for each fiscal year; -Prepare and ensure timely submission of quarterly financial consolidated reports-FACE, quarterly consolidated progress reports, annual progress report, mid-term reports, and other reports as may be required by UNDP; -Report progress of project to the Steering Committee. -Oversee the exchange and sharing of experiences and lessons learned with relevant projects nationally and internationally. -Preparing a detailed annual work plan for the project. -Undertaking any other activities that may be assigned by the Steering Committee. -Ensure participation of UNDP Managers meeting. -Compile six chapters of the TNC and write Draft TNC report and Executive Summary and also prepare the Project Completion Report. |
| Finance Assistant | 200 | 12.5 | -Responsible for the maintenance of overall aspects of the project accounts, books of accounts, budgeting, budget trickling, financial operations and reporting, auditing and payroll;; -Compile and/or prepare the documentation necessary for the procurement of services, goods and supplies under the project; -Organize seminars, training, and workshops for stakeholders; -Ensure timely disbursement of funds from the project bank account; - Maintain the project’s files and supporting documentations for payments; - Maintain the project’s disbursement ledger and journal; - Prepare financial reports; -Assist team members, experts and consultants on procurement, logistics, travel and financial and other operational matters; -Maintain Petty cash & replenish time to time. -Undertake other financial duties as requested by the PM |
| Programme Assistant | 150 | 76 | -Maintain files and records of the project; -Assist Project Coordinator in organizing training/ seminar/ workshop etc.; -Circulate all sorts of meeting notice, working paper of the meeting, minutes of the meeting, official letters; -Facilitate necessary correspondence with relevant stakeholders; -Assist in the preparation of documentation in advance of and following all meetings and capacity building and awareness-raising activities, -Purchase stationeries and the petty materials for the project office; -Provide logistic support to event management; - Support, as necessary, the organization of training for the project personnel. -Prepare, maintain and update information on the project web site; -Assist in the preparation of documents related to project activities; - Assist Project Coordinator and Project Director as and when required. |
| International |  |  |  |
| Travel Project coordinator | 980 | 5 | Assistance to workshops/ UNFCCC meetings |
| For Technical Assistance |  |  |  |
| Local |  |  |  |
| Consultant/Consulting Firm/Institutions to be hired for preparing the National Circumstances Chapter of the TNC | 375 | 40 | -Identify information needs and collect necessary updated data from relevant sources. -Analyze all available national and sectoral strategies, plans, programmes and studies relevant to the formulation of the TNC, including national development blueprints and poverty reduction strategy papers and strategies. -Update the information base on geographical characteristics including climate, forests, land use and other environmental characteristics. -Update information base on population, economy and other services sector which may affect country’s ability to deal with mitigating and adapting to climate change. -Analyze poverty-climate links. -Prepare a Draft National Circumstances chapter of the TNC based on outputs of the above Activities. |
| Consultant/Consulting Firm/Institutions to be hired for preparing the National GHG Inventory | 1,125 | 80 | -Mobilize a Core Inventory Team involving sector-specific experts. Develop a work programme for the GHG inventory preparation. -Stock taking of the work done so far (ALGAS, INC, SNC and other relevant reports). -Organize training & workshop on methane emission factor and inventory preparation. -Develop methane emission factor for cultivated rice fields (for Boro, Aus, Amon and other crops) and enteric fermentation of ruminant livestock (especially for cow, buffalo, goats, sheep etc.). -Procurement of activity data for the years 2006-2010 for all the sectors viz. : (a) Energy, (b) IPPU, (c) AFOLU, and (d) Waste Sector. Solvent may be included in the TNC, because paints and varnishes, refrigerants, etc. may have significant contribution. -Undertake necessary initiatives to include GHGs such as CO, NOx, NMVOC, and refrigerants & propellants like HFC, CFC, PFC and SF6 other than CO2, CH4 and N2O to see their extent of emission in Bangladesh. -Carry out a Key source analysis. -Provide elaboration on calorific value of coal, breakdown of diesel into different uses, system loss of natural gas, activity data of biomass,andCH4 and N2O emissions estimation. -Projections of emission up to 2050 in all sectors may be undertaken using appropriate models. -Increase awareness among national institutions on methods of inventory preparation and needs for emission coefficients. - Provide training of stakeholders on procurement and archiving of activity data. -Development of Database Management system not only for GHGs but also for other gases. -Prepare the Draft National Emission Inventory Report and share with relevant agencies and experts for their comments and reviews. -Preparation of the National GHG Emission Inventory for the year 2006 -2010 highlighting emission sources and sinks. -Finalize the Inventory report. |
| Consultant/ Consulting Firm/Institutions to be hired for conducting mitigation analysis and preparing A chapter on GHG emission mitigation | 1,000 | 85 | -Review UNCCCSP, ALGAS, INC, SNC and other available documents to evaluate mitigation from various activities/ sectors. -Based on the updated inventory data over the period 2006-2010 and recalculated emission data for the years 1990, 1994, 2001 and 2005, time series emissions to be found sub-sector-wise for determining correct mitigation strategy. -Generating more than one scenario baseline and other two with mitigation measures in different sectors. -Carrying out a cost analysis for all of them and calculate the GHG mitigation potential in Gg. -Collect information on the cost of mitigation measures, not only the cost for US$/ton Co2. -Current Government Policies to be analyzed and policies needed for implementation of recommended mitigation options to be suggested. -Barriers how to overcome them. -Measures to be suggested for formally strengthening of institutions for identifying and evaluating mitigation projects for implementation. -Mitigation measures for the LUCF sector and for CH4 in the agriculture sector formulated. -Mitigations by renewable energy technologies be emphasized and elaborated. - Clean coal technologies to be explained, identified for adoption. -Besides renewable energy, forestry and waste are potential sectors for mitigation option; these sectors to be elaborated. -Collect information on projects that are being implemented or proposed for implementation. -At least two specific projects from each sector to be selected and complete financial analysis to be given. -Explore measures in other sector besides the energy sector. -Baseline and mitigation scenario over time for non-energy activities have to be constructed. - Share the Draft National Mitigation Strategy with relevant stakeholders and finalize it. |
| Consultant/ Consulting Firm/Institutions to be hired for conducting Climate change vulnerability and adaptation assessments | 1,000 | 125 | -Estimate damages and losses caused by past weather events like floods, cyclones, storm surges, river bank erosion, droughts and water logging etc. -Correlation of diseases with weather phenomena and weather patterns. -Identify greater effect of cyclones, storm surges- effects on low relief coastal areas; populations on the coastal margin, hotels, tourist developments. -Conduct vulnerability study in terms of impact on growth, poverty reduction, livelihood, employment and women. -Conduct detailed studies on climate change impacts on water resources, agriculture, biodiversity, fisheries and urban areas. -Study of present field level adaptation practices for coping and enhancing resilience of local people, involved organizations (government and NGOs), and implementing area. -Bangladesh Government’s Trust fund and other climate change organizations funded projects are needed to be extensively studied. -Review government policies and roles for the field level adaptation practices. -Asses cross sectoral issues and linkage between livelihoods and disasters. -Conduct economic evaluation of implemented adaptation projects will be done. -Conduct detailed micro-level analyses of climate variability for different months of the year and their impacts on various sectors especially on water resources and agriculture. -The process of erosion and accretion in the coastal zone needs to be accurately determined. -To draw up a list of the barriers to the implementation of adaptation measures in communities or regions including political barriers, those of social organization, traditions, public and local policies. -Assess current institutional weaknesses including those in the policy regime, which act as barriers of mainstreaming adaptation, and devise mechanisms to overcome such identified barriers. -Construct at least a macroeconomic model of climate change impact where the future macro variables could be estimated based on types of shock including those of mitigation and adaptation measures. -Conduct calculation of adaptation cost. |
| Consultant/ Consulting firm/Institutions to be hired for preparing the chapter on Other information | 500 | 80 | -Inclusion of climate change issues into country’s national planning priorities, in social, economic and environmental policies, and in development activities. -Identify needs for research to adapt to and mitigate climate change and arrangement for sufficient training and education programmes for raising awareness among general public, professionals, member of non-governmental organizations, policy makers and students on climate change issues. -Undertake necessary initiatives for enough funds from the donor agencies for research to adapt to and mitigate climate change and systematic observation. -Conduct technology needs assessments to identify the institutional arrangements for the transfer of technologies, removing the barriers and to facilitate appropriate technologies to the stakeholders. -Provide information on capacity building efforts and exchange mechanisms. -Provide information on the effects and impacts of various climate change related intervention and policies by type of sector or activity. |
| Consultants/to compile, review translate and edit the final report | 500 | 49 | Compilation, translate, review, edit and peer review and proof read the final report |
|  |  |  | - |
| International |  |  |  |
|  |  |  | - |
|  |  |  | - |
|  |  |  | - |

# Annex B

# Operational Guidance to Focal Area Enabling Activities

# Biodiversity

- GEF/C.7/Inf.11, June 30, 1997, Revised Operational Criteria for Enabling Activities

- GEF/C.14/11, December 1999, An Interim Assessment of Biodiversity Enabling Activities

- October 2000, Revised Guidelines for Additional Funding of Biodiversity Enabling Activities (Expedited Procedures)

# Climate Change

- GEF/C.9/Inf.5, February 1997, Operational Guidelines for Expedited Financing of Initial Communications from Non-Annex 1 Parties

- October 1999, Guidelines for Expedited Financing of Climate Change Enabling Activities – Part II, Expedited Financing for (Interim) Measures for Capacity Building in Priority Areas

- GEF/C.15/Inf.12, April 7, 2000, Information Note on the Financing of Second National Communications to the UN Framework Convention on Climate Change

- GEF/C.22/Inf.15/Rev.1, November 30, 2007, Updated Operational Procedures for the Expedited Financing of National Communications from Non-Annex 1 Parties

# Persistent Organic Pollutants

- GEF/C.17/4, April 6, 2001,  Initial Guidelines for Enabling Activities for the Stockholm Convention on Persistent Organic Pollutants

- GEF/C.39/Inf.5, October 19, 2010, Guidelines for Reviewing and Updating the NIP under the Stockholm Convention on POPs

# Land Degradation

- (ICCD/CRIC(5)/Inf.3, December 23, 2005, National Reporting Process of Affected Country Parties: Explanatory Note and Help Guide

# National Capacity Self-Assessment (NCSA)

- Operational Guidelines for Expedited Funding of National Self Assessments of Capacity Building Needs, September 2001

- A Guide for Self-Assessment of Country Capacity Needs for Global Environmental Management, September 2001

# National Adaptation Plan of Action (NAPA)

- GEF/C.19/Inf.7, May 8, 2002, Notes on GEF Support for National Adaptation Plan of Action,

EA

1.0

Project ID number will be assigned by GEFSEC.

This is the cost associated with the unit executing the project on the ground and could be financed out of trust fund or co-financing sources.