[image: image1.jpg]


request for project preparation grant (PPG) 

Project Type:  FORMDROPDOWN 
  

the  FORMDROPDOWN 

    Submission date: June 11, 2008     
     Re-submission date: August 28, 2008 
GEFSEC Project ID: 3704       
GEF agency Project ID: 4047           
Country: Benin
Project Title: Integrated Adaptation Programme to Combat the Effects of Climate Change on Agricultural Production and Food Security in Benin 

GEF Agency(ies):  FORMDROPDOWN 
,
Other Executing partner(s): Ministry of Agriculture      
GEF Focal Area: Climate Change

GEF-4 Strategic program(S): Climate Change Adaptation
a.   Project preparation Timeframe  

	Start date 
	October 2008

	Completion date
	October 2009


b  project preparation activities 
Project formulation will be based on step-by-step project formulation guidance in UNDP’s Adaptation Policy Framework Document and UNDP’s guidelines for developing adaptation projects.  The project design will follow the adaptive capacity approach in formulating project interventions.
i) Justification

This LDCF project will promote key elements of a programmatic approach to enhance the resilience of food production systems and food unsecure communities to the harmful effects of climate change on agriculture in Benin. The end-product of the preparatory phase will be a GEF Brief and UNDP Project Document which will outline in detail the following:

· Clear description of baseline activities and relative sources of financing; 

· Explicit specification of all adaptation activities to be financed under the LDCF and their additionality rationale (why and how are they supposed to reduce vulnerability and/or increase adaptive capacity beyond what is already being done);

· Identification of targeted communities and sites for project specific intervention;

· Clear logframe including description of the goal, objective, outcomes, outputs;

· Description of a Monitoring and Evaluation system for the adaptation project including impact indicators at the objective, outcome and output levels;

· Public Involvement Plan for design, preparation, implementation, and M&E phases/components.

Each of the proposed activities outlined in the NAPA which underlies this proposal (see submitted PIF for details) will be evaluated on the basis of cost-effectiveness during the preparatory phase, and those deemed most aligned with the overall project objective and programmatic approach to adaptation in Benin will be selected for implementation. 
ii) Description of PPG activities

Activities undertaken during the preparatory phase will include the collection of baseline information, identifying and filling key gaps in information to strengthen the design of the project, gathering key data/information for the design of the approved outcomes and outputs, identifying and confirming the lead implementing partner and implementation arrangements for each component, developing indicators for monitoring and evaluation both at the outcome and output levels and identifying and securing partnerships and other sources of financing and co-financing. The PPG grant would finance the costs for national and international consultants who will provide, under the guidance of UNDP/BDP/EEG, technical input towards the project design as well as logistic support for the activities listed above and described in detail below.  

COMPONENT 1: Needs Assessments and technical feasibility of adaptation options and measures

Project formulation will be based on step-by-step project formulation guidance in UNDP’s Adaptation Policy Framework’s Document and UNDP/BDP/EEG’s guidelines for developing adaptation projects. The project design will follow the adaptive capacity approach in formulating specific activities. This approach will ensure that the implementation of the NAPA follow-up project is not undertaken in isolation but contributes to ongoing activities executed by the government of Benin and other donors already actively engaged in rural and agricultural development.

(a) Climate change risks assessment for the agriculture sector 

PPG resources will be used to undertake a rigorous and detailed review of the scientific literature (including NAPA and subsequent National Communications documents) on climate change impacts on rain-fed farming and animal breeding systems with a particular focus on the most vulnerable areas identified in the NAPA and considered for project implementation. Based on the existing information, the review will undertake an indepth problem (root-cause) analysis of vulnerability and will identify what the likely impacts are, where they are likely to occur, on what scale and the timing of expected impacts. It will include a robust and scientific-based explanation of how climate change and variability will affect agricultural production conditions and food securiy in Benin (climate change risks assessment). Among the priority issues to be looked at, the PPG will strive to dertermine the likely impacts of climate change on transboundary transhumance systems and corridors and their consequences on the sustainability of current rangelands management systems, risks of user conflicts over pastoral resources, etc. The preparatory phase in coordination with the second national communication, will leverage the knowledge and expertise available on this issue in national and regional centers of excellence, such as the CIRDES (http://www.cirdes.org) which has done extensive work in this area. 
Additionally, PPG resources will be used to review best practices and suited methodologies to assess the the costs of the likely impacts of climate change on the agriculture sector assuming no adaptation interventions are undertaken. More generally, the PPG work will take stock of the range of climate and socio-economic scenarios on which these impacts are projected.  The findings of this risks analysis will guide the identification and confirmation of the project adaptation responses and will inform the detailed outcomes and outputs that the project will deliver (see § d) below).

Stakeholder consultations and validation with relevant governmental and non-governmental agencies, as well as other bilateral donors, will supplement the findings of the review and inform the technical feasibility for the proposed project.

(b) Comprehensive baseline and problem analyses 

A detailed assessment will include an analysis of the agriculture sector as well as a  review of ongoing and planned Government and UNDP projects and programmes, policies, laws, executive regulations and decrees relevant to rural and agriculture development and clarify baseline (non-climate driven) development issues pertaining to agriculture sector resilience. A review of relevant national documents as well as PRSP, UNDAF, CPAP, etc should be undertaken to identify linkages of the proposed initiative to national priorities. The review will focus on strengths and weaknesses and gaps of the existing system (as well as proposed interventions) to overcome anticipated impacts on agro-pastoral communities. A particular emphasis will be put on assessing the climate change vulnerability and maladaptive potential of on-going and planned rural development plans (including municipalities, village and community level development plans) with regard to agriculture and food production.
The information collected in this exercise will contribute towards outlining a clear and detailed problem analysis (situation and root-cause analysis) including the non-climate as well as climate change drivers of the problem. This will then be elaborated into identification of barrier-removal solutions that can be built into the project design. 

(c) Review of best practices 

A review of lessons learnt, models of best practices and successful adaptation measures available in the sub-region and internationally will be carried out in order to properly inform the selection of cost-effective adaptation options and the design of the proposed project. The lessons and knowledge collected and processed by Global Adapatation Learning Networks (such as the UNDP ALM, NCSP V&A Resources Network, WeADAPT, AIACCC, etc.) such as bilateral discussion with specific country like Mali will be mobilized and integrated into the project’s technical approach. A strong emphasis will be given on  models of best practicess regarding agro-meterological assistance services and food crisis EWS, as priorities raised by the NAPA, for which Mali is one of the ground-breaking countries in West Africa. This shall enable the country to build a cost-effective agro-meteorological system that will help farmers to better manage climate risk on agriculture and food production.
(d) Capacity needs assessment and capacity building strategy
Following from the lessons review, a detailed capacity assessment will be conducted at the national and local levels. Capacity indicators will be developed and will be used to identify capacity gaps to be fulfilled and targets to be achieved by the end of the project. The UNDP Capacity Assessment Methodology and Indicators will be applied and a full-fledge capacity building strategy developed, outlining the priority CB measures and activities to be supported by the project. Successful CB models and training modules existing in other WA countries will serve as basis for building the project’s CB approach. Available lessons and models will be analysed and tailored to the needs of the Beninese institutions and stakeholders.
(e) Identification of specific regions and sites for intervention within the fours targeted areas
Based on the information in (a) and (b) and clearly defined criteria (including vulnerability to climate change including variability as a priority), a selection will be made of specific high priority areas that this project will focus on in each principal agro-ecological zones of Mali (Sahelian, Sudanese, Guinean, etc.). A full assessment of the location specific risks facing the selected community/ies will be undertaken to inform the project design. A participatory stakeholder approach to site selection and to develop interventions will be employed and outlined in the UNDP project document
(f) Clarifying Additionality of Proposed Outcomes and Interventions

The additionality of the proposed project will be clarified in the context of the proposed outcomes and outputs (which have been outlined in the PIF). Comprehensive explanation will be provided on how LDC Funding will be directed towards the additional cost of ensuring that baseline activities are transformed into one that incorporates climate change concerns (i.e. the adaptation scenario). Towards this end, a detailed assessment, including stakeholder consultations, will be undertaken of activities that are taking place or have taken place in different communities in the identified vulnerable areas of Benin that are of relevance to the proposed outcomes. Based on the in-depth climate risks assessment and economic analysis of the baseline and proposed project funded interventions, the additionality of the proposed interventions (with respect to address climate change pressures on rain-fed farmers’ and pastoral communities) will be established. The details on the baseline and additional activities will contribute towards clarifying how the baseline situation will be amended through the proposed project in order that risks associated with climate change, including variability are addressed.

The above review will also include an inventory of who is doing what (and at what scale) so that the project LDCF can be designed to build on ongoing and planned activities. This inventory, together with the main findings of the climate risks assessment (see § a)), will contribute towards explicitly confirming and describing the most urgent and appropriate adaptation responses which qualify under the additionality criterion. PPG resources will then be utilized to assess the technical feasibility of the identified project interventions, using cost/benefits analysis and robust feasibility criteria (e.g. likelihood of success, alignment with local capacities, scalability, etc.). Project responses to be assessed will include strategies and measures geared towards adjusting/modifying the institutional, policy and regulatory framework, building institutional and individual capacity and piloting on-the-ground climate risks actions in selected vulnerable areas.  

The review and stakeholder consultations will also facilitate discussions with other local and international institutions who may be pursuing similar objectives/outcomes and identify important partnerships including co-financing opportunities.  It will also facilitate discussions with other agencies such as Government of Denmark, GTZ, UNDP/DDC, FAO and others on potential partnerships whereby the comparative advantage of these agencies can be brought to bear on the design and implementation of this project.  
(g) Integration with National Development Plans and Policies

The project will integrate climate change concerns into relevant national agriculture development plans and policies and also be aligned with core UNDP activities in Benin. In order to identify linkages of climate change concerns into national development plans and policies, a review of relevant national development policies will be undertaken. Useful documents in this regards are (i) Poverty Reduction Strategy Paper (PRSP; (ii) National Millennium Development Report (National MDG Report) and (iii) UN Common Country Assessment (CCA). A review of the UN/UNDP programming documents such as the United Nation Development Assistance Framework (UNDAF) and UNDP Country Programme Document (CPD) or Common Country Framework (CCF) will also be undertaken in order to ensure that the project is anchored on relevant ongoing UN development programmes/projects. The UNDP Project document will output exactly how the proposed initiative is aligned with UNCT priorities for Benin.

COMPONENT 2: Project Development

The outputs of Component 1 will be used as technical input for the formulation of an UNDP Project Document for the proposed project. Technical assistance will be required by a national and international consultants who are experienced in (i) GEF project formulation; (ii) UNDP project implementation requirements; (iii) technically competent in climate change impacts on crop production, farming systems  and adaptation options; and (iv) familiar with the institutional setting in Benin.

(a) Defining the logical framework and work plan for the project

PPG resources will be utilized to outline a detailed logical framework with elaboration of the project goal, objective, outcomes, outputs and activities, objective and outcome specific impact indicators and a fully developed work plan, budget and time frame for implementation. 

(b) Definition of institutional arrangements, roles and responsibilities 

A detailed delivery strategy, with clearly identified roles and responsibilities of specific institutions for the overall management of the project will be specified. An in-depth analysis will be undertaken of the capacity of the Ministry of Agriculture and/or other appropriate local institutions that could implement the full size project.  Details on oversight of technical activities including requisite reporting procedures will be established. UNDP guidelines as articulated in the Results Based Management Framework will be followed in formulating these details. 

(c) Definition of a Monitoring and Evaluation Plan

A detailed M&E work plan and delivery strategy will be defined including clear identification of responsibilities and institutions, as well as an appropriate budget allocation (based on best practices, and UNDP guidelines). This will also reflect the requirements of the GEF M&E Policy and Adaptation M&E framework. The Monitoring Plan will include qualitative and quantitative indicators that will measure the state of adaptive capacity at various stages of project implementation. The M&E plan will include provisions for independent evaluation and provision to ensure learning of lessons from implementation.

(d) Identification of quantitative and qualitative indicators

Using a fully participatory stakeholder approach, resources will be used to define the monitoring and evaluation indicators (both qualitative and quantitative) for measuring and verifying the successful delivery of the Project Objective and Outcomes. Emphasis will also be given to those indicators that will ensure progress at various stages of project implementation. The M&E framework will be based on the guidance provided by the new GEF M&E framework for adaptation currently being drafted by UNDP and amended appropriately given the context of the proposed project. 

(e) Exit Strategy (Sustainability)

A detailed sustainability strategy will be defined in order to ensure that continuation of the outcomes promoted through this project, including replication, upon after completion of the project cycle.  
COMPONENT 3: Consultation with key stakeholders
PPG resources will be utilized to engage key stakeholders at the national/sub-national and community level during the project design phase. In alignment with the approved project objective, comprehensive stakeholder analysis will be conducted to determine stakeholder needs vis-à-vis adaptation to potential climate change impacts, barriers to adaptation, expertise that might be helpful in designing the implementing the project and those who may have been involved in similar initiatives or planning processes.  The following activities will be undertaken:

(a) Mobilize and engage stakeholders
Participatory development of a detailed delivery work-plan approved and endorsed by the key stakeholders. The successful completion of the preparatory phase will require the participation of a number of key stakeholders.  Sensitization activities and ppartnerships will be carried out with:
· National policy-makers and local councillors: in 2008, local elections will take place in Benin whcih will lead to the renewal of rural ‘’communes’’ and municipalities’ boards. A dedicated communcation and awareness-raising camapigns will be developed and conducted at both central and municipal levels in order to sensitize the political sphere to the threats posed by climate change on Benin’s food security,  to  the NAPA priorities and to  the project’s main objectives and strategy. 

· Public, private and international institutions that monitor and produce information related to climate change and agriculture development. A mechanism for sharing information on sustainable farming systems that effectively integrate CC risk management techniques and technical capacities of communities and relevant institutions will be designed during the preparatory phase; 

· A wide array of national agencies coordinated by the Ministry of Agriculture and agriculture extension services  NGOs, international technical cooperation bodies, and local communities, will be consulted in order to establish an effective framework for the proposed project;

A plan for project management and stakeholders’ involvement during the implementation phase of the FSP (Full Size Project) will be discussed and finalized during the preparatory phase. In this regard, a group of stakeholders not directly involved in the project will be among the project partners, NGOs, Civil society organizations, CBOs, Research, training and academic institutes, and Regional administrators. 

Standard UNDP reporting, monitoring and evaluation procedures will apply to this project and will be elaborated in the full Project Document through the normal preparatory phase process. 

(b) Determining priorities and forge expanded partnerships

Participatory negotiation with the local communities and stakeholders to determine priority adaptation needs and to address partnership requirements for support and co-funding at various levels and within various sectors including government, NGO, private sector and bilateral partnership arrangements. Public-private-institutional-community partnerships including media will be engaged under a defined communication strategy aimed at performing policy advocacy, and dissemination of lessons learned. 

(c) Community Mobilization

A detailed work plan based on a participatory stakeholder approach will be developed to mobilize local communities in implementing relevant components of the project. This may include community participation in tracking the delivery of specific project outcomes.  

COMPONENT 4: Develop a financial plan and co-funding scheme
(a) Negotiate with Government Counterpart 

Negotiate with the government to ensure full agreement with the Project Objective, Outcomes, Outputs including partnerships for support and co-funding.  

(b) Explore Multilateral and Bilateral funding opportunities 

Develop partnerships and co-funding opportunities at various levels with bilateral and multi-lateral funding institutions as well as networking at the global level.

(c) Obtain official endorsement letters and guarantees

Official endorsement letter with guarantee of co-financing will be collected from the Government and donors and submitted to the UNDP/BDP/EEG. 
iii) Outputs from Preparation Activities

The expected Outputs from the Preparation phase based on assessments undertaken under Components 1- 4 which will feed into the Project Document are:

· Summary of the relevant baseline development plans and investment programmes of the public and private sector in Benin focusing on food security and sustainable agriculture that describes possible inter-linkages and entry points for the proposed UNDP/BDP/EEG intervention;

· Review and summary of the existing policy and regulatory framework relevant for agriculture and rural development, improvement of farming systems, and droughts mitigation.

· Review, analysis and summary of the past project related activities of other donors and private sector in adaptation, food production and security in Benin and an updated report on the co-operation and co-financing possibilities in the frame of the envisaged UNDP/BDP/EEG project;

· Supporting reports to justify the proposed project interventions and to leverage financing for the proposed activities (this will include climate risks assessments and costing, pre-feasibility studies and cost/benefits analyses for pilots, draft business plans etc.)  

· A Project Logical Framework that includes description of the goal, objective, outcomes, outputs;

· M&E framework for the projects that focuses on adaptation to climate change including variability. This includes a list of proposed indicators and an associated monitoring and evaluation plan (with a clear definition of how these indicators would be measured and how verification data would be collected through the monitoring programmes). 

· A work plan with detailed roles and responsibilities for implementation; 

· A stakeholder participation plan, with a clear focus on rural community involvement; 

· Endorsement letters from the government and letters confirming co-financing commitments;

· Project Document as per GEF and UNDP requirements including completed UNDP checklist for preparing adaptation projects; and  

· Other reports from all project relevant stakeholder consultations.
	Project Preparation Activities
	 FORMDROPDOWN 

	Co-financing
	Total

	Component 1: Needs assessment and technical feasibility of adaptation options and measures
	40,000
	20,000
	60,000

	Component 2: Project Development
	15,000
	15,000
	30,000

	Component 3: Consultations with  key stakeholders
	20,000
	10,000
	30,000

	Component 4: Financial Plan and co-funding scheme
	5,000
	10,000
	 15,000

	PPG Management Budget Costs*
	0
	25,000
	25,000

	Total project preparation financing
	80,000
	80,000
	160,000


* NB: The PPG management budget covers in-country operational management costs and expenditures related to facilitation of PPG activities and delivery of PPG outcomes. No UNDP Implementing Agency Services costs will be charged to the PPG Management Budget. All such costs will be charged to the IA corresponding fees.

c. PPG Budget Requesting LDCF/SCCF Financing

	Cost Items
	Total Estimated Person weeks

(pw)
	 FORMDROPDOWN 
 

 
	Co-financing ($)
	Total ($)

	Local consultants
	49
	30,000
	19,000
	49,000

	International consultants
	14
	30,000
	5,000
	35,000

	Communications, technical workshops, travel
	
	20,000
	36,000
	56,000

	Management
	
	0
	20,000
	20,000

	Total  PPG Budget
	
	80,000
	80,000
	160,000


d.   GEF Agency(ies) Certification




	This request has been prepared in accordance with GEF policies and procedures and meets the LDCF/SCCF criteria for project identification and preparation.

	[image: image2.wmf] 

 


Yannick Glemarec

Executive Coordinator

UNDP/GEF
	Project Contact Person

Tom Twining-Ward, Regional Technical Advisor for Climate Change Adaptation, UNDP Regional Coordinating Centre, Dakar

(through Bo Lim, Principal Technical Advisor, UNDP/GEF)

	Date: June 11, 2008
	Tel. and E-mail: tom.twining-ward@undp.org


Annex A

Consultants financed by the PPG and co-financing
	Position Titles
	$/

person week


	Estimated PWs
	Tasks to be performed

	Local


	
	
	

	Agro-climatology and adaptation expert
	1000
	25
	Help coordinate all PPG activities and ensure the quality of outputs 
Lead negotiations and consultations with potential partners;

Based on existing regional models, and knowledge of climate in Benin, identify a range of climate scenarios, with particular reference to the agriculture sector

Undertake vulnerability and climate risks assessments

Refine system boundaries and project’s scope
Outline a detailed problem analysis (root-causes, barriers, etc)
Identify appropriate adaptation options and measures

Identify potential specific sites for intervention
Organize and facilitate a series of technical workshops and consultative workshops
Define roles and responsibilities and confirm suitable institutional/implementation arrangements 


	Agriculture and Sustainable Land Management specialist
	1000
	8
	Establish the baseline situation/scenario as regards on-going and planned investments in the agriculture sector

Identify additional investments required to adapt to climate change;

Support design of on-the-ground pilot adaptation measures and prepare pre-feasibility studies and costs/benefits analysis
Help build partnerships and mobilize resources



	Agriculture sector institutional expert 
	1000
	8
	Review and analyze existing policies and regulatory and institutional frameworks, including adaptation incentives and disincentives, barriers, etc…  

Conduct  institutional and individual capacity gaps and needs analysis; 

Design the project’s policy, institutional and capacity development strategy and action plan;

Propose suitable institutional/implementation arrangements;

Help build partnerships and mobilize resources;



	Participation Specialist
	1000
	4
	Conduct Stakeholders Analysis and develop Stakeholders Participation Plan, including community mobilization strategy

Help build partnerships and mobilize resources


	Knowledge management and M&E Specialist
	1000
	4
	Design Knowledge Management and M&E component (including learning mechanisms and impacts indicators)

Develop the project’s Replication and Exit Strategy (sustainability)

Help build partnerships and mobilize resources


	International

	
	
	

	Climate change risk management specialists
	2,500
	4
	Assist in selection of regional scenarios, vulnerability and climate risk assessment and help determine suited risks management responses

Estimate the cost of climate change impacts on the agriculture sector in absence of adaptation

Help prepare pre-feasibility studies and cost/benefits analysis for the risks management measures to be supported by the project
Support the design of EWS and agro-meteorological assistance services

Assist in clarifying additionality of proposed outcomes and activities

	GEF/LDCF climate change adaptation specialists
	2,500
	10
	Lead the consultants’ team and help scope PPG activities and work plan
Control quality of inputs and outputs of all consultants and subcontractors

Validate project’s problem and barrier analysis

Help determine the project’s system boundaries and scope

Define the logical framework, work plan and budget for the project

Clarify the additionality of proposed outcomes and activities

Investigate potential options for the project’s institutional and implementation arrangements

Develop the project’s sustainability strategy

Demonstrate cost-effectiveness of the project’s interventions

Propose  co-funding and financing plans

Stimulate partnerships and help mobilize resources

Develop the FSP brief and UNDP Prodoc




