Agency’s Project ID: 4017
GEFSEC Project ID:      
Country: Timor-Leste
Country Eligibility:i) LDC status; ii) Date of UNFCCC ratification: 25 August 2006
Project Title: National Adaptation Programme of Action to Climate Change (NAPA) Formulation Project
GEF Implementing Agency: UNDP
National Executing Agency: ): Secretariat of State for Environmental Coordination, Territorial Ordinance and Physical Development 

Duration: 18 months
GEF Focal Area: Climate Change Adaptation
GEF Operational Program: LDCF
GEF Strategic Priority: N/A for LDCF projects
Estimated Starting Date: October 2007
IA Fee: US$ 20,000
Record of  endorsement on behalf of the Government (Operational Focal Point):

	Mr. Carlos Ximenes
National Directorate of Environmental Services
	Date: June 4, 2007


CLIMATE CHANGE ENABLING ACTIVITY

PROPOSAL FOR gef FUNDING FOR National Adaptation Programs of Action by Least Developed Countries (NAPA)
Record of  endorsement on behalf of the Climate Change Focal Point):

	Mr. Carlos Conceição

	Date: (Month, day, year)


	This proposal has been prepared in accordance with GEF policies and procedures and meets the standards of the GEF Project Review Criteria for NAPA approval.



	[image: image1.jpg]


IA/ExA Coordinator 

John Hough
Officer-In-Charge
UNDP/GEF 
	Project Contact Person

Gernot Laganda, Regional Technical Advisor / UNDP Regional Centre Bangkok 
(through Bo Lim, Principal Technical Advisor, Capacity Development and Adaptation Cluster, UNDP/BDP/EEG)

	Date: September 13, 2007
	Tel. and email:+66 (0)2288 2644

gernot.laganda@undp.org

	Financing Plan (US$)

	GEF Project/Component

	Project
	200,000

	Sub-Total GEF
	200,000

	Co-financing

	GEF Agency
	     

	Gov’t Contribution
	20,000

	Others
	     

	Sub-Total Co-financing:
	20,000

	Total Project Financing:
	220,000


[image: image2.jpg]REPUBLIC DEMOCRATIC OF TIMOR - LESTE
SECRETARIAT OF STATE FOR ENVIRONMENTAL COORDINATION,
TERRITORIAL ORDENANCE, AND PHYSICAL DEVELOPMENT
NATIONAL DIRECTORATE OF ENVIRONMENTAL SERVICES
Palicio do Governo

Date: 4 June 2007

To

Resident Representative,
UNDP Timor-Leste,

UN House, Caicoli Street,
Dili

Timor-Leste

Dear Mr. Finn Reske-Nielsen,

Re: Preparation of a National Adaptation Programme of Action (NAPA) for Timor-
Leste

On behalf of the Government of Timor-Leste and, in my capacity as GEF Operational
Focal Point, I hereby endorse the request of funding for US $200,000 for the above
mentioned activity. to be presented through the United Nations Development Programme
(UNDP) to the Global Environment Facility.

By requesting this assistance, the Government of Timor-Leste expresses its interest in

receiving UNDP support for the preparation of its National Adaptation Programme of
Action. i

i

fonal Directorate of Environmental Services (NDES)

Secretariat of State for Environmental Coordination, Territorial Ordinance, and Physical
Development

Timor-Leste





TABLE OF CONTENT
ABBREVIATIONS………….……………………………………………………………………. 3

1.  BACKGROUND……………………………………………………………………………….. 5

2.  INSTITUTIONAL CONTEXT……………………………………………………………….. 9 

3.  OBJECTIVES AND LINKAGES TO ONGOING ACTIVITIES …………………………10

10a)
Objectives of the project……………………………………………………………...……

b) Linkages to ongoing activities…………………………………………………………….. 10

c) Current and previous related activities…………………………………………… ….……11 

d) Alignment with capacity assessments and UN Country Programming …………………..  11

4.  PROJECT ACTIVITIES AND OUTPUTS………………………………………………….12
12Output 1: Institutional structure for preparation of NAPA document established


14Output 2: Vulnerability to current climate variability assessed


15Output 3: Potential climate change adaptation measures formulated and prioritized


16Output 4: The National Adaptation Programme of Action Prepared and Endorsed


5.  Institutional arrangements for oversight and coordination …17 

185.1.  High level political oversight, coordination and policy integration


185.2.  Project management and operational coordination


185.3.  Coordination with climate change team for National Communication to the UNFCCC


185.4.  Coordination with other teams for preparation of national reports

8
6.  TIMETABLE …...……………………………………………………………………………. 19
7.  BUDGET ……………………………………………………………………………………... 20
22ANNEXES

2
22Annex I: Terms of References


26Annex II: Organizational Chart for the Timor-Leste NAPA Process

6



ABBREVIATIONS 

CARITAS

Catholic agency for overseas aid and development
CBNRM-ET
Community Based Natural Resources Management – East Timor

CBD

Convention on Biological Diversity

CDCU

Capacity Development and Coordination Unit
CIDA

Canadian International Development Agency
CSIRO

Commonwealth Scientific and Industrial Research Organization (Australia)
COP

Conference of the Parties

ENSO

El Nino/Southern Oscillation
FAO

Food and Agriculture Organization 

GEF

Global Environment Facility

GoTL

Government of Timor-Leste
HIV/AIDS

Human Immunodeficiency Virus/Acquired Immune Deficiency Syndrome

JICA

Japanese International Cooperation Agency 
LDC

Least Developed Country


MAFF

Ministry of Agriculture, Forestry and Fisheries 

MEA

Multilateral Environment Agreement

MFP

Ministry of Finance and Planning 
MNRMEP

Ministry of Natural Resources, Mineral and Energy Policy
MTC

Ministry of Transportation and Communications 
NAPA

National Adaptation Programme of Action
NBSAP

National Biodiversity Strategy and Action Plan

NCSA

National Capacity Self Assessment

NDP

National Development Plan

NDES

National Directorate of Environment Services
NDMO

National Disaster Management Office

NDRMC 

National Disaster Risk Management Committee
NEAP

National Environmental Action Plan
NFP

National Focal Point
NGO(s)

Non-Governmental Organization(s) 

NORAD

Norwegian Aid for Development
NPC

National Project Coordinator
PIU

Project Implementation Unit

PSC

Project Steering Committee
RDTL

República Democrática de Timor-Leste
SEP

Sectoral Expenditure Program
SIDS

Small Island Developing State
SIP

Sectoral Investment Program
SSECTOPD
Secretariat of State for Environmental Coordination, Territorial Ordinance and Physical Development

SWG

Sector Working Group

TB

Tuberculosis 
TOR 

Terms of Reference

TWG

Technical Working Group
UK

United Kingdom

UN

United Nations

UNCBD

United Nations Convention on Biological Diversity

UNCCD

United Nations Convention on Combating Desertification and Land Degradation

UNDP

United Nations Development Programme

UNFCCC

United Nations Framework Convention on Climate Change 
UNFPA

United Nations Population Fund

UNMIT

United Nations Integrated Mission in Timor-Leste
USAID

United States Agency for International Development 

WB

World Bank

WG

Working Group 

WSSD

World Summit on Sustainable Development
1. BACKGROUND 
1. On 20 May 2002, Timor-Leste became the newest, sovereign nation in the world. It includes the eastern end of the island of Timor, the enclave of Oecussi and the islands of Ataúro and Jaco. The area of Timor-Leste is approximately 14,874 km2. To the North lies the Banda Sea and to the South lies the Timor Sea. Timor-Leste has a spectacular topography, dominated by the central mountain range of Ramelau. The highest point, Mount Tatamailau is 2,963 m above sea level. Almost half the land has 40% or more slope. The topography, dominated by steep slopes, increases the risk of soil erosion. In addition, the rainfall pattern, with its long dry season and short, but intense rains, amplifies the erosion hazard, further increasing the vulnerability of its population, a majority of who depend on agriculture. 

2. Timor-Leste is among the poorest countries in the region. Currently, more than 70 percent of the 923,198 people in Timor-Leste live under the US$1 per-person per day; more than 40 percent live under the national poverty line of US$0.55 per-person per day.  70% of the people live in rural areas with small landholdings and livestock, in areas that are prone to flooding, soil erosion, and droughts. 64% of the population is food insecure and about 45 percent of children younger than five years old are underweight. With a rapid population growth of about 2.5 percent annually, or 5 percent in the post-independent period between 2001 and 2004, the challenge for sustainable development is greater.
  Timor-Leste has a lot to improve with its human resource development.  Half of the population is illiterate - adult literacy rate is 50.1%. Health standards are low and Life expectancy is only 55.5 years.  Maternal mortality rate is as high as 420 women for every 100,000 births.  Moreover, gender-based violence has been indicated as rampant, but many cases go unreported. Unemployment rate has reached 60 percent among the productive portions of the population. 

3. Timor-Leste is vulnerable to changes in climate, as evidenced by existing sensitivities to climate events (such as drought and food shortages in the western highlands, and floods in Suai, Same, Ainaro and Manatuto districts). Because of the lack of consistent climate data, however, it is a challenge to examine climate risk in Timor-Leste with accuracy. During the Portuguese period, several stations measured rainfall/climate data for varying periods from 1914 to 1975, but many of these records are incomplete and in the custody of the Government of Portugal
. It is unclear how much data was recorded during the period of Indonesian control until 1999 but again a lot of that data still remains with the Indonesian Government
. Since 1999 there have been no sufficient meteorological or hydrological services available in the country following the 1999 destruction of most infrastructure (including meteorological) by retreating Indonesian forces.
4. A study conducted by the University of Melbourne suggests that the impact of climate 
change on Timor-Leste is likely to involve changes in the length and intensity of the rainy seasons, to changes in the number and intensity of storms and other climatic events (for example, floods, fires), to changes in the maximum and minimum temperatures and to sea level rises. Given that the country already experiences damaging droughts and floods, which result in decreased agricultural production, damage to infrastructure and loss of life, the most serious implication of climate change for Timor-Leste is likely to be the increase in intensity and possibly frequency of extreme events in the future. A great concern is also the possible link between climate change and El Niño events, which may be more severe in the future as the Pacific shifts to a more El Niño-like pattern.

5. Agriculture is the most important sector of activity in Timor-Leste and will continue so for the foreseeable future
. It employs around three quarters of the current labour force. Assessments of the vulnerability and adaptive capacity of agricultural systems is therefore a priority, particularly given that this sector is more sensitive to climate than any other. The main crops produced are maize, rice, coffee, cassava, sweet potatoes, soybeans, candlenuts, vegetables (15 different types), fruits, vanilla and species, bananas, coconuts and palm nuts.

6. Maize is the most abundant and accessible food crop, making it the most important source of food security in Timor-Leste. In most places, maize is grown in shallow soils on steep slopes using shifting cultivation that results in deforestation. Because 1) maize production is not irrigated and relies on reliable and regular rainfall in the wet season, 2) soils are not particularly fertile, and 3) maize production occurs on steep slopes, it is vulnerable to drought and irregular rainfall. 

7. Rice is the second most important food crop in Timor-Leste. Areas that are able to produce at least one rice crop per year tend to experience more food security than those that cannot. Irrigation is a critical input for rice production. However, in most places there is insufficient water in the dry season, and no significant water storage systems, for there to be year-round irrigation of rice crops. The areas that produce a single crop each year, and which account for the bulk of rice production, may be sensitive to climate change, particularly if rainfall in the west season decreases. Rice crops in flood prone areas may experience reduced production due to flooding. 

8. Coffee is an important cash crop in Timor-Leste. It is an important factor in the livelihoods of many Timorese families. Coffee requires an average annual rainfall of some 2-3,000 mm per year, relative humidity of 70-90%, and a distinct dry season for flowering and ripening of berries. Climate change may result in changes in humidity at lower altitudes where coffee is grown, and an overall shifting upwards of the altitude band favorable for coffee production. Increased rainfall in the dry season may also have an adverse effect on flowering and ripening of berries.

9. A range of small scale and low cost adaptation options for farming systems could be potentially employed that could assist in retaining soil quality and moisture, diversifying food sources and ensuring more reliable food supply. An equally important adaptation option would be a climate monitoring, forecasting and early warning system. This will provide accurate information about future rainfall for more efficient use of seeds, labour, and other household resources in farming and food procurement. This system could also be used for early warning about hazards and preparation for flooding.    

10. Water is a critical resource in Timor-Leste. Water supply, and in particular lack of water in the dry season, is the most important environmental constraint on agricultural production. Farmers identify rainfall and water availability as the two principal environmental constraints on production. Climate change could result in an increased amount of rain received throughout the year. However, the wet season may be slightly drier and the dry season may be slightly wetter. Rainfall may come in the form of fewer but more intense events. El Nino events which result in delayed rain and less rain may become more severe. This has implications for drought, floods, and water quality. 

11. Timor-Leste is already vulnerable to drought due to both a relative lack of reliable rainfall, as well as minimal water resource infrastructure. This existing vulnerability is a good indicator of likely future vulnerability to changed rainfall patterns. The severity of floods and landslides is exacerbated by upland farming practices which cause deforestation and soil erosion. Because it may result in more frequent and more intense rainfall events, when coupled with existing processes that cause deforestation and soil erosion, climate change could result in increased flood damage and landslides. If climate change results in more intense rainfall, and land clearing continues unabated (which increases rates of erosion), then problems of water quality may worsen. Water supply problems may be solved by the construction of small dams to capture peak flows for later use and to minimize flooding while as promoting access to renewable and cheaper sources of energy especially in the rural areas provide an effective solution to cutting trees for fuelwood. Reforestation is another means of controlling soil erosion.

12. From a biodiversity perspective, the island of Timor has considerable significance, lying as it does in the “Wallace Zone”, where the Indo-Malaysian and Australasian flora and fauna overlap. Yet, while the biodiversity of Timor-Leste is large and unique, it is poorly studied and there is very limited baseline information. The country is known to have good quality, rare and possibly unique terrestrial, lake and marine ecosystems – these stem from the unique geological and meteorological conditions. A Norwegian/UNDP assessment conducted in 2001 considers that for birds, endemism in Timor-Leste may be the highest for the whole archipelago, and also quite high for terrestrial mammals. Based on some recent data they note that some 25 species of birds (out of a total of 224 species recorded) are endangered. Another recent study tentatively identified eight Important Bird Areas using globally recognized criteria. This indicates a high level of both ecosystem and species diversity. The marine biodiversity is also thought to be valuable. The marine and coastal ecosystems are in good condition and are thought to have healthy populations of several globally important species (for example, turtles). In addition, Timor-Leste contains many species of direct benefit to man, for medicinal and commercial uses. Little is known of Timor-Leste’s genetic biodiversity, although the probability that Timor Island is the center of origin of the sandalwood tree – an important commercial species – indicates that the island’s sandalwood, at least, may contain valuable genetic characteristics. The vulnerability and adaptive capacity of these systems to climate change need to be assessed

13. The coastal zone of Timor-Leste, stretching over 700 km, includes unique resources both on land and in the sea. This ecosystem is at present in a remarkably pristine condition. If utilized in a non-destructive and well-planned manner, it will provide great possibilities for economic development, while providing necessary products to sustain the coastal population. If not controlled, economic interests relating to the coastal zone, particularly oil exploration and tourism, will constitute significant threats to this unique resource. Climate change is likely to result in a rise in global average sea levels. The vulnerability of Timor-Leste’s coastal areas will be determined in part by the speed of this change. A rapid rise in sea level along the coastline may have a number of adverse effects. Increased shoreline erosion is possible. Infrastructure such as buildings and roads, and activities such as agriculture that are close to the shore may be impacted by shoreline retreat. Rising sea levels can also cause salt-water intrusion into freshwater aquifers, resulting in salinisation of water used for drinking and agriculture. 
14. In Timor-Leste, healthy reef and mangrove systems confer a high degree of adaptability to climate change with benefits for inshore fish stocks and coastal protection. Preserving the quality of Timor-Leste’s coastline through careful controls on development will be an important strategy.

15. Health standards in Timor-Leste are currently very low. Access to health facilities is difficult, especially in rural areas. For the country as a whole it takes on average a 70-minute
 walk to reach the nearest health facility and there are no guarantees that a doctor or nurse will be available as these personnel operate more than one health facility. Respiratory and diarrhea diseases are widespread, and malaria and dengue fever are endemic. TB continues to afflict people and leprosy remains a problem. HIV/AIDS is not yet widely prevalent, but few people are aware of the threat it poses and fewer still know how to prevent it. Under climate change scenarios, there is a medium to high confidence that the incidences of some of these diseases will rise – making Timor-Leste very vulnerable.

16. Timor-Leste is located in an area that is highly vulnerable to natural disasters. It is vulnerable to earthquakes and associated phenomena such as tsunamis due to its geographical location. It experiences the El Nino/Southern Oscillation (ENSO) related weather anomalies associated with droughts in the region occurring in cycles of every four – seven years. It is also prone to floods, landslides and erosion resulting from the combination of heavy monsoon rain, steep topography and widespread deforestation. Currently, the country lacks capacity to forecast potential threats of large scale disasters and has little preparedness to respond and cope with such disastrous events. As a newly independent country, Timor-Leste, is restrained by human and financial capacity, hence its ability to respond and cope with natural disaster is very limited and primordial. 
17. Further to this is the frequency of violent conflicts that have befallen the country. In 1999, following a ballot to vote on a referendum for independence from Indonesian occupation, the Indonesian military and pro-Indonesian East Timorese militia went on a rampage of destruction. The violence resulted in many deaths and massive destruction of buildings and other infrastructure. All government services collapsed, most government buildings were burned to the ground, over 80% of East Timor’s infrastructure was destroyed, and more than half the population of 800,000 was displaced. In 2006, a political and civil crisis led to the death of many people, burning and looting of public and private property and displacement of over 180,000 people. These conflicts have created widespread poverty and increased the vulnerability of East Timorese to climate change.
2.
INSTITUTIONAL CONTEXT 
18. Several Government departments have responsibilities for activities related to climate change in Timor-Leste. These include; the Secretariat of State for Environmental Coordination, Territorial Ordinance and Physical Development (SSECTOPD), the Ministry of Agriculture, Forestry and Fisheries (MAFF), the Ministry of Natural Resources, Minerals and Energy Policy (MNRMEP), the Ministry of Transport and Communication (MTC), and the Ministry of Interior.

19. The lead agency and coordinating body for all Multi-lateral Environmental Agreements (MEAs) is the National Directorate for Environmental Services (NDES). NDES falls under the Secretariat of State for Environmental Coordination, Territorial Ordinance and Physical Development (SSECTOPD). Under the National Development Plan (NDP), the NDES has been given a mission to ‘conserve and protect natural resources and environment in East Timor through sustainable development planning’. The mandates and responsibilities of the NDES include: protecting and enhancing the natural environment of Timor-Leste, raising community awareness about the importance of protecting the environment and behaving in ways that support such protection, working with other government departments and agencies in integrating environmental considerations into their policies, programs and projects, integrating environmental consideration into policies, programs and plans
, developing and implementing environmental legislations and regulations including environmental impact assessment  and pollution control, monitoring and evaluation of environmental quality and its sustainability, and completion of policies on important environmental matters, including water catchments management and coastal zone management.

20. The National Development Plan (NDP) assigns the Ministry of Agriculture, Forestry, and Fisheries (MAFF) as the Government agency with prime responsibility for the development of agriculture, forestry, and fisheries sub-sectors.  The vision, as laid down in the NDP, is to have by 2020 sustainable, competitive and prosperous agricultural, forestry and fisheries industries that support improved living standards for the Nation’s people. MAFF’s mission is to efficiently deliver to agricultural, forestry and fishing communities, services that support improved productivity, income earning potential and export and that, therefore, support improved social welfare in the rural areas of the Nation, taking account of MAFF’s human, capital and financial resources. 

21. The Ministry of Natural Resources, Mineral and Energy Policy (MNRMEP) is responsible for the development and management of natural resources, including minerals and energy sources for Timor-Leste. MNREP has a mission to: “Efficiently administer legislation relating to minerals, energy and extractive industries in a consistent, fair, transparent, timely and accurate fashion; and partner industry and provide leadership in achieving regulatory reform
”.

22. The Ministry of Transport and Communications houses the Division of Meteorology. The NDP mandates the department to advise the government on climate conditions and forests, monitor weather and seismographic data for advance alert hazards, provide atmospheric information and forecasts, and to provide timely alerts to the nation of potential natural disasters
.

23. The National Disaster Management Office (NDMO) is currently under the authority of the Minister of Interior. The institution has been given responsibility to monitor, analyze, and manage natural disasters and attempting to manage natural risks and vulnerabilities that are likely to impact on people of Timor-Leste. To effectively meet its objectives and responsibilities, NDMO has formulated a National Disaster Risk Management Plan in line with the Government Decree no. 3/2004. The plan is to be overseen by a multi-sectoral National Disaster Risk Management Committee (NDRMC) which is an inter-ministerial committee composed of the Ministry of Interior, the Ministry of Planning and Finance, the Ministry of Transport and Communication, the Ministry of Public works, the Ministry of Health, the Ministry of Defense and State Administration, the Ministry of Natural Resources, Minerals and Energy Policy, the Ministry of Development, Secretary of State for Environmental Coordination, Territorial Ordinance and Physical Development and other relevant ministries and agencies.

3.
OBJECTIVES AND LINKAGES TO ONGOING ACTIVITIES
a) Objectives of the project
24. The objective of this project is to develop a National Adaptation Programme of Action to Climate Change (NAPA) 
 document for Timor-Leste consistent with Decision 28/CP.7 

25. The Specific objectives are:

1. To set up Institutional structure for the preparation of the NAPA document
2. To conduct participatory assessment of vulnerability to current climate variability

3. To identify key climate change adaptation measures and develop proposals for priority
 activities to address the adverse effects of climate change

4. To prepare the NAPA document in the format established by the COP

5. To have the NAPA document endorsed by the national Parliament, Council of Ministers and the Prime Minister

6. To disseminate the final NAPA document to the public

b) Linkages to ongoing activities 
26. Timor-Leste became party to the UN convention on land degradation in August 2003. In 
2006, the country received funding from GEF and Norwegian Government to develop its first 
national report on land degradation and develop its human resource capabilities to develop future national reports. A draft report was presented to the Seventh Asia and Pacific Regional NFP Meeting, held in Bangkok on 7-11 August 2006. In 2007, the country will start to implement a project on sustainable land management with GEF funding. It will therefore, be able to develop its NAP on land degradation. The NAPA project will seek synergy from these two projects.

27. The country acceded to the UN Conventions on Biodiversity and Climate Change on 8 January 2007. As such, it has not prepared any national communication/report under UNFCCC and CBD. It has also not received GEF funding for the enabling activities in climate change, biodiversity, biosafety, POP’s etc. It is however, envisaged that the country will undertake some of these activities within the lifetime of the NAPA process and possible linkages and synergies with these activities will be identified.

c) Current and previous related activities
28. Participatory Rural Energy Development Project; a pilot project aimed at; providing access to renewable energy sources for the remote and ‘un-served’ villages in Timor-Leste; establishing institutional structures to support rural/renewable energy development; and Policy formulation. The project is implemented by GoTL with financial support from UNDP and UK:
29. Biogas for Energy project by CARITAS: Another participatory energy project utilizing biogas technology in energy provision for Guisso village and Laulara and Maubara sub-districts.

30. Seedling Production and reforestation project by MAFF: a reforestation project by the Ministry of Agriculture Forest and Fisheries

31. Community Based Natural Resource Management for Carbon Sequestration (CBNRM-ET) project by CARE: This is a reforestation project aimed at mitigating carbon emission in 12 villages of Timor-Leste by utilizing carbon sinks. 
d) Alignment with ongoing capacity assessment activities and UN Country Programming
32. National Capacity Self Assessment; a project aimed at identifying capacity constraints and determine actions to remove the constraints in implementation of MEA’s. The project is being implemented by GoTL with UNDP support and GEF funding. This assessment has concentrated on the three thematic areas of desertification/ land degradation, biodiversity and climate change, and placed particular emphasis on identifying cross-cutting issues and synergies. The NCSA process has contributed to creating a sustainable institutional system and process for continuous assessment and improvement of national capacities for sustainable environmental management. Stocktaking was concluded in April 2006, Thematic Assessments in May 2006, and the NCSA report compiled in October 2006. 
33. United Nations Development Assistance Framework; The first UNDAF for Timor-Leste was completed in 2002, and formed the umbrella for the post-independence programmes of all UN agencies, funds and programmes during the period of 2003-2005. The areas identified as priority for development assistance from the UN were: Income poverty and hunger, education and culture, health, gender, and environment and natural resources. More recently, the UN Country Team agreed to extend the UNDAF for another two years until 2007, in line with the extension of the Government of Timor-Leste's National Development Plan. This will closer align the development assistance and priorities of the UN system to supporting national initiatives, and enable an adaptation agenda to be firmly anchored within a strengthened policy context. 
4.
PROJECT ACTIVITIES AND OUTPUTS
Output 1.0: Institutional structure for preparation of NAPA document established 

Activity 1.1: Establish a national NAPA team and set up a Project Implementation Unit (PIU)
34. The national climate change focal point in collaboration with the Director, National Directorate of Environmental Services (NDES) will establish a management office within the NDES in the State Secretariat of Environmental Coordination, Territorial Ordinance and Physical Development (SSECTOPD). He will then request the Secretary of State to be the lead person for the NAPA team. The Secretary of State will, in an open and flexible process that will be inclusive and transparent, constitute the NAPA team. The Timor-Leste NAPA team will consist of senior representatives of relevant government agencies, academia, private sector, donor partners, and civil society organizations. The NAPA team will be responsible for preparing the NAPA and coordinating the implementation of NAPA activities.

35. The Secretary of State in his capacity as the lead person for the NAPA team and in consultation with other members of the NAPA team and UNDP will appoint a Project Director. The Project Director will supervise activities, ensure timely provision of Government inputs and be responsible to the Government and UNDP for the achievement of the results and outputs. He will formulate a Project Implementation Unit (PIU) including recruitment of project staff, and setting up the project office. Ideally, the PIU will consist of a National Project Coordinator (NPC) and a senior Advisor to work full time in the coordination and the implementation of the prescribed work plan. The advisor, who will be under the supervision of the NPC, will provide expert advice to the NPC and the NAPA team. The NPC will be under the direct supervision of the Project Director, but constantly liaise with UNDP for project support. 

Activity 1.2: Secure high level support from the Government and key stakeholders 

36. The Timor-Leste National Adaptation Programme of Action (NAPA) will only be effective if they are followed up. It will therefore, be important, from the very beginning and maintained over the life of the process, to obtain high level support from key stakeholders and more specifically senior Government officials
 and decision makers. The high-level support will ensure that key stakeholders are not only involved but are committed to the NAPA products, that NAPA are recognized as an integral part of national sustainable development, and that Project administration, management and coordination mechanisms function effectively. 

37. As an initial step to secure high-level support, a formal Inception event will be organized to raise awareness of the NAPA process, inform stakeholders of its aims and intentions,  endorse the NAPA team, and build support and buy-in from all sectors and stakeholders. At this event, the NAPA formulation project will be presented and promoted, comments and recommendations will be solicited particularly on the sectors that would be covered under the NAPA, and the linkages with ongoing and planned related initiatives in the country will be defined. Participants to be invited will include the Prime-Minister, the President, the Cabinet, regional administrators, other senior Government officials, UNMIT, donor organizations, national and international NGOs, academia, private organizations, communities, and the media. Facilitation of the workshop will be done by the LDC Experts Group with invitation from the NAPA team leader and PIU.

38. For the high-level support to be effective, it must be maintained over the life of the NAPA process and beyond. Since there are many topics competing for the attention of senior officials, strategic efforts will be needed to maintain their support. The NAPA team will need to develop appropriate strategies to address this issue.

Activity 1.3: Conduct awareness raising and consultation amongst stakeholders

39. A broad-based process will be developed and implemented to identify, involve and learn from all key stakeholders. Stakeholders in this broad sense include not only Governmental institutions and their members, but bilateral partners, NGOs, academics, local community leaders, etc. The consultations process will be undertaken at the district, regional, as well as at the national level. At each of these levels, consultations will be undertaken with decision-makers and policy-setters, as well as technical/ managerial level specialists. The stakeholder consultation process will also serve to strengthen linkages with key stakeholder bodies and individuals, raising their understanding on climate change issues and its adaptation, and to further heighten awareness of the NAPA process and its goals.

Activity 1.4: Assemble a multidisciplinary integrated assessment team 

40. The Timor-Leste NAPA team will establish a multidisciplinary team, hereafter referred to as Sector Working Groups (SWGs), entrusted with undertaking most of the tasks associated with preparing the NAPA. Each SWG will consist of at least one national expert from identified key sectors who will be engaged on a commissioned basis to undertake well defined assessments and analysis. The final set of sectors that will be covered will be determined during the inception workshop and will include food security and agriculture; water availability, quality and accessibility; forests, coastal ecosystems and biodiversity; human health; human settlement and infrastructure; and natural and human-induced disasters

41. Given that the assessments and analysis for various sectors will be done by different individuals and that their reporting format may vary, the PIU will develop TOR for each group specifying a consistent approach to the content and format for the reporting. The TOR will also include a timeline with key milestones and deadlines
42. The multidisciplinary team will be charged with

· Synthesizing available information on adverse effects of climate change and coping strategies;
· Conducting participatory assessment of vulnerability to current climate variability and extreme weather events and more specifically assess where climate change is causing increases in associated risks;
· Identify key climate change adaptation measures;
· Identify and prioritize country driven criteria for selecting priority activities to address needs arising from the adverse effects of climate change;
Output 2.0: Vulnerability to current climate variability assessed

Activity 2.1: Synthesize available information on adverse effects of climate change

43. This activity is to synthesize what is known about Timor-Leste’s vulnerability and adaptive capacity with regard to the potential impacts of climate change. Timor-Leste acceded to the UNFCCC in January 2007, and as such, certain climate change materials including National Communications and Country Reports, are yet to be prepared. Very little research in the field of climate change (per se) has been conducted. Information on the impacts of climate change on economic, social and ecological well being of communities in Timor-Leste is therefore, scanty. The following three reports have tried to address the climate change issues to varying degree:

· Proceedings from the 1st National Workshop on Climate Change, Dili, November 2003 (RDTL, UNDP, CARE, CIDA)

· Briefing to Government, Civil Society, and Donors on climate change in Timor-Leste (Jon Barnett, Suraje Dessai, and Roger Jones – The University of Melbourne)

· NCSA Situation Analysis and Thematic Assessment Report on Climate Change

44. Many documents, invaluable in assessing existing vulnerabilities, impacts to adverse effects of climate change, and existing copings strategies, do however exist. These include:

· National Development Plan 2002-2007

· Population census 2004

· Sector Investment Plans (all Government Ministries)

· Human Development Reports

· Poverty Maps

· Timor-Leste Millennium Development Goals

· United Nations Development Assistance Framework (2003-2007)

· MAFF Policy and Strategic Framework

· Environmental Assessment Reports
· Climatic data for the period 1914 – 2006 held by the Ministry of Agriculture Forestry and Fisheries; Ministry of Transport and Communication; and Governments of Portugal, Indonesia and Australia
45. The multidisciplinary team (each team working on its own sector of interest identified in the project inception), with guidance from an international consultant (Vulnerability and Adaption specialist), will review these documents and any other not listed to identify  presently observed and projected climatic hazards that threaten vulnerable groups. Coping strategies already put in place will also be identified. The hazards will be described according to their range of impacts, duration and spatial extent and frequency of occurrence. Trends in the incidence and severity of each hazard will also be noted. Other details to describe the climatic hazards may include:

· A narrative that describes the effects of the hazard. This will help support the NAPA; project profiles by indicating what are the main concerns with the hazard;
· Estimates of the range of impacts, including economic losses, loss of life, and social stress;
· The duration and spatial extent of the hazard. Noting if specific regions are at higher risk;
· The expected frequency of occurrence; 

· Trends in the hazard;
Activity 2.2: Assess in a participatory manner vulnerability to current climate variability

46. Given that very little information on vulnerability exists, the assessment process will be a most important step of the NAPA preparation and has to be as exhaustive as is possible. The key questions to be answered in this activity are: ‘Who or what is vulnerable, to what climatic threat, and to what extent?’. Based on information obtained in activity 2.1, an assessment methodology will be formulated to collect information from all 13 districts of Timor-Leste on vulnerability. The formulated methodology will include design of systematic procedures for data collection, collation, processing, verification and review. 
This activity will be carried out by the multidisciplinary team, but an international consultant (Vulnerability and Adaption specialist), will guide the team in developing the assessment methodology, identifying relevant key stakeholders, and in collecting and analyzing the data
47. Although assessment of vulnerabilities will be sector based, the formulated methodology will be uniform to all the sectors. The format for presenting collected information will also be uniform and will be designed at this stage paying attention to the TORs developed in activity 1.4.

The process of data collection and analysis will be a participatory one and will involve a broad-based stakeholder consultation. It will be important, at this stage, therefore, to relook at the identified  key stakeholders in each district and ensure that men and women at the grassroots-level are wholly involved.

Output 3.0: Potential climate change adaptation measures formulated and prioritized 

Activity 3.1: Formulate potential climate change adaptation measures

48. For each of the priority sectors identified and based on the outcomes of activities 2.1 and 2.2, the multidisciplinary team will identify adaptation needs and formulate potential adaptation measures to address the identified needs. These measures may include awareness raising, capacity building, and policy reforms which may be integrated into sectoral and other policies. The adaptation measures may be grouped according to whether they are sectoral (relating to specific adaptations for sectors that could be affected by climate change); multi-sectoral (relating to the management of natural resources that span sectors), or cross-sectoral (including education and training, public awareness campaigns, disaster risk management, research, and monitoring).

49. To ensure greater efficiency and enhance the impact of the identified measures, the multidisciplinary team, will ensure synergies within the sectors and with other environmental strategies especially those of the Rio Conventions. The formulated potential climate change adaptation measures will form a first draft of potential NAPA activities and will be shared with the NAPA team. The national NAPA team will then disseminate the draft and facilitate countrywide consultative meetings to solicit feedback from the people on the adaptations measures, more inputs and proposal ideas, comments and revisions.

Activity 3.2: Develop a prioritization criteria

50. The multidisciplinary team having been involved in assesing vulnerabilities to current climate variabilities and formulating potential climate change adaptation measures will, by this time, be having good knowledge of vulnerabilities to adverse effects of climate change in Timor-Leste. The team, therefore, will be charged with developing a framework of locally-driven criteria for selecting priority activities to address needs arising from the adverse effects of climate change. The criteria may be based on the level or degree of adverse effects of climate change; poverty reduction to enhance adaptive capacity; synergy with other multilateral environmental agreements; and cost-effectiveness. Other factors that may be considered in the formulation of the criteria include urgency of the adaptation needs; ease and practicability of the identified activity; relevancy to existing national strategies for sustainable development. The developed criteria will then be refined by the NAPA team and presented in a national workshop to relevant stakeholders for refining and endorsement.
Activity 3.3: Priotize key adaptation measures for inclusion in the NAPA document

51. From activity 3.1, a list of all probable climate change adaptation measures will have been identified. It will be impractical to include all the identified activities in the NAPA document. During this activity, the developed list will be subjected to a prioritization critiria formulated in activity 3.2 to select and identify priority activities for inclusion in the NAPA document. The output of this activity will be priority adaptation measures for inclusion in the NAPA document.
Output 4.0: The National Adaptation Programme of Action Prepared and Endorsed 

Activity 4.1: Prepare and Present the Adaptation Strategy and Action Plan

52. Once the prioritization process is completed, an adaptation strategy will be prepared with a combination of different measures and policies. The adaptation strategy will consist of a plan containing the collection of measures selected for implementation, a time frame and other operational modalities for implementation.

53. The NAPA team will then convene regional (there are 4 regions in Timor-Leste) stakeholders’ consultation workshop to present and review the adaptation strategy and action plans. The main purpose for the NAPA document will be to communicate priority activities to address urgent and immediate needs related to adaptation to the adverse effects of climate change. The document will be important to:
· The Timor-Leste Government (who will fund and implement most of the identified activities), 

· UNFCCC Secretariat and LDC Experts Group

· Multilateral and bilateral development partners (including GEF, UN agencies and international and national NGOs)

· Private developers 
· Media and 

· Communities

The document, therefore, has to be easy to understand, action-oriented and country driven and setting clear priorities for urgent and immediate adaptation activities as identified in the preceding activities.

54. While it is important to give detailed procedures for the NAPA preparation process, most people in Timor-Leste (especially government officials) get intimidated by voluminous reports. It is therefore, suggested to have the NAPA document in the form of two paper bound reports. The first report, to contain a short overview of the NAPA preparation process and elaborated details of adaptation strategy and action plans formulated in activity 4.1, will be a maximum of 20 pages. The second paper bound report will contain all the other required sections of the format established by the COP which include; introduction and setting, framework for adaptation programme, identification of key adaptation needs, a list of identified adaptation measures, criteria for selecting priority activities, and the NAPA preparation process.

Activity 4.2: Review and endorsement of the NAPA document

55. The NAPA document will be translated into Portuguese and Tetun and distributed to all relevant stakeholders who will be invited to a national stakeholders’ consultation workshop to review the document. The document will then be presented to the Council of Ministers, the National Parliament, and the Prime Minister for final endorsement.
Activity 4.3: Dissemination of the NAPA Document 

56. The endorsed NAPA document, in English, Portuguese, and Tetun, will be disseminated to the public through the media (electronic and print), awareness campaigns, local leaders including village heads, and academic institutions. The document will also be made available to the UNFCCC Secretariat.

5.      Institutional arrangements for oversight and coordination 
57. In the past, due to the unique circumstances of Timor-Leste, UNDP projects have been implemented through a combination of direct and agency execution arrangements. Given the extensive capacity building needs of the GoTL, capacity for national execution must be developed. UNDP is therefore assisting at both central and local levels to support Timor-Leste’s transition to fully carry out the national execution modality. As part of this process, the GoTL will be fully involved in the management of this NAPA Project through the NDES. Project execution will adhere to UNDP “Direct Execution” (DEX) requirements as per the standard UNDP DEX Guidelines. NDES 

5.1.  High level political oversight, coordination and policy integration

Also refer to activity 1.2;

58. NAPA Project Steering Committee (PSC):

The Programme Steering Committee (PSC) will be the overall governing body for the NAPA formulation process. It will provide policy level guidance, review project progress and project financial status and review/endorse budget revisions. It will also set major implementation directions, approve project work plans, and ensure that NAPA activities are aligned with and mainstreamed into broader national environmental management and sustainable development policies and programmes. It will comprise representatives from all key stakeholder institutions, and will be chaired by the Secretary of State for Environmental Coordination, Territorial Ordinance and Physical Development. Regular PSC meetings shall be held on a three-monthly basis until the completion of the project. Special sessions will be convened as required.

5.2.  Project management and operational coordination

Also refer to activity 1.1;
59. Programme Implementation Unit (PIU):

The Programme Implementation Unit (PIU) will serve as secretariat and support unit for the NAPA process. It will be housed within the NDES and headed by a National Programme Coordinator (NPC) who will be under the direct supervision of the National Director. The NPC (TOR attached) will be responsible for the day-to-day running of project activities.

5.3.  Coordination with climate change team for the country’s national communication to the UNFCCC
60. At present, Timor-Leste does not have a climate change team, it has also not produced a national communication to the UNFCCC before, but over the life of the project it is envisaged that, such a team will have been constituted and will regularly produce the national communication to the UNFCCC as required. In the meantime, the climate change focal point will be charged in ensuring coordination with the other conventions.

5.4.  Coordination with other teams for preparation of national reports

61. Timor-Leste in 2006 was able to produce its first national report to the UNCCD and as 

part of the process, the national focal points (UNFCCC, UNCBD and UNCCD) were trained on how to produce successive national reports. This project will take advantage of the training and the relationship developed during the process and will build on strengthening the capacity of the national focal points not just in producing substantive and timely reports but also on coordinating among themselves while producing the reports.

6.   TIMETABLE 

	
	
	Month

	
	Activities
	1
	2
	3
	4
	5
	6
	7
	8
	9
	10
	11
	12
	13
	14
	15
	16
	17
	18

	1.0
	Institutional structure for the preparation of the NAPA document established
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	

	1.1
	Establish a national NAPA team and set up a Project Implementation Unit (PIU)
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	

	1.2
	Secure high level support from the Government and key stakeholders
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	

	1.3
	Conduct awareness raising and consultation amongst stakeholders
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	

	1.4
	Assemble a multidisciplinary integrated assessment team
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	

	2.0
	vulnerability to current climate variability assessed
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	

	2.1
	Synthesize available information on adverse effects of climate change
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	

	2.2
	Assess in a participatory manner vulnerability to current climate variability
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	

	3.0
	Potential climate change adaptation measures formulated and prioritized
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	

	3.1
	Formulate potential climate change adaptation measures
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	

	3.2
	Develop a prioritazation criteria
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	

	3.3
	Priotize key adaptation measures for inclusion in the NAPA document
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	

	4.0
	The National Adaptation Programme of Action Prepared and Endorsed
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	

	4.1
	Prepare and Present the Adaptation Strategy and Action Plan
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	

	4.2
	Review and endorsement of the NAPA document
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	

	4.3
	Dissemination of the NAPA Document
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	


7.   BUDGET 
Budget Table (US $):
	ACTIVITY 
	STOCKTAKING 
	PROCESS: (ASSESSMENTS , CONSULTATIONS, WORKSHOPS , ETC.) 
	PRODUCT: ASSESSMENT REPORTS / STRATEGY AND ACTION PLAN 
	TOTAL 

	Assessment and prioritization 

	1) Information gathering and synthesis, assessment of vulnerability 
	
	
	
	

	i) Synthesis of available information on adverse effects of climate change and coping strategies 
	8,600
	2,200
	200
	11,000

	ii) Participatory assessment of vulnerability to current climate variability and extreme weather events, and associated risks 
	20,800
	3,800
	500
	25,100

	2) Identification of adaptation measures, and criteria for priority activities 
	
	
	
	

	i) Identification of past and current practices for adaptation to climate change and climate variability 
	
	10,000
	200
	10,200

	ii) Identification of key climate change adaptation measures 
	
	10,500
	200
	10,700

	iii) Identification and prioritization of criteria for selecting priority activities 
	
	800
	200
	1,000

	TOTAL (Assessment and prioritization) 
	
	
	
	58,000

	Development of proposals for priority activities 

	1) National/ sub-national consultative process for short listing potential activities 
	
	11,600
	3,000
	14,600

	2) Selection and identification of priority activities on the basis of agreed criteria 
	
	3,000
	1,000
	4,000

	3) Prepare profiles of priority activities in the prescribed format 
	
	2,000
	3,000
	5,000

	TOTAL (Development of proposals for priority activities)
	
	
	
	23,600

	
	
	
	
	

	Preparation , review and finalization of the NAPA 

	1) 
	Public review 
	
	3,000
	
	3,000

	2) 
	Final review by government and civil society representatives 
	
	11,600
	1,000
	12,600

	3) 
	Printing, publishing and translation of the final NAPA document 
	
	
	14,000
	14,000

	4) 
	Dissemination 
	
	2,100
	
	2,100

	TOTAL (Preparation, review and finalization of NAPA) 
	
	
	
	31,700

	Technical assistance 

	1) 
	Assistance requested from LDC expert group 
	
	17,000
	
	17,000

	2) 
	Other technical assistance 
	
	28,500
	
	28,500

	
	TOTAL (Technical assistance) 
	
	
	
	45,500

	Project coordination and management 

	TOTAL (Project coordination and management) 
	
	41,200
	
	41,200

	TOTAL 
	
	
	
	200,000


Budget Details:
	 Description/Activity
	1.1
	1.2
	1.3
	1.4
	2.1
	2.2
	3.1
	3.2
	3.3
	4.1
	4.2
	4.3
	Total 
	%

	PIU staff salaries
	1,100
	1,100
	1,100
	 
	2,200
	4,400
	2,200
	 
	2,200
	2,200
	2,200
	1,100
	19,800
	10

	National Consultants
	 
	 
	 
	 
	8,400
	16,800
	8,400
	 
	8,400
	8,400
	 
	 
	50,400
	25

	International consultants
	 
	9,000
	 
	 
	4,500
	9,000
	 
	 
	 
	9,000
	 
	 
	31,500
	16

	Travel 
	300
	8,500
	2,000
	 
	3,500
	6,000
	300
	 
	600
	3,000
	600
	1,000
	25,800
	13

	Workshops/meetings
	 
	5,500
	600
	 
	1,200
	2,400
	1,200
	600
	1,200
	2,000
	1,200
	1,000
	16,900
	8

	Communication 
	100
	100
	100
	 
	200
	400
	200
	 
	200
	200
	200
	100
	1,800
	1

	Equipment 
	10,000 
	10,000
	5

	Translations 
	 
	 
	 
	 
	500 
	1,000 
	100 
	100 
	100 
	3,000
	1,000
	 
	5,800
	3

	Printing 
	 
	 
	 
	 
	200 
	500 
	200 
	200 
	200 
	 
	 
	10,000
	11,300
	6

	Operation maintenance
	5,000
	5,000
	2

	Miscellaneous
	21,700
	21,700
	11

	 Total
	1,500
	24,200
	3,800
	0
	20,700
	40,500
	12,600
	900
	12,900
	27,800
	5,200
	49,900
	200,000
	100


ANNEXES

Annex I: Terms of References

1. National Project Director (NPD)

The National Programme Director will serve as the overall Government manager of the project. S/he will be a senior serving member of the GoTL and designated by the Secretary of State in SSECTOPD. Key responsibilities of the NPD are:
· To provide overall leadership and supervision to staff of the NAPA project.

· To serve as focal point for NAPA project interaction with Government institutions and other stakeholders (donors, NGOs, academic institutions and the private sector).

· To be responsible for provision of all project reporting, including progress reports, project accounts and budgets, project workplans, Terms of Reference, etc. as required by the GoTL and UNDP.

· To ensure achievement of the overall objectives and specific outputs of the Project, by utilizing programme resources (as provided by the GoTL, UNDP or other parties) in an efficient, effective and transparent manner.

· Act as secretary to the policy NAPA Project Steering Committee (PSC) with the support of the PIU.

· Act as NAPA Project Liaison between the GoTL and other stakeholders
Qualifications:
· A senior government officer at the Secretary of State level of one of the Executing Agencies (MDE and MPF);

· Strong knowledge of government policies and strategies;

· Strong understanding about global and national environmental issues; 

· Good interaction with line ministries and other stakeholders;

· Demonstrated strong leadership and partnership; and 

· Demonstrated ability to liaise and foster cooperation between agencies, including government, academic and NGOs

2. National Project Coordinator (NPC)
The National Project Coordinator (NPC) will be responsible for the overall implementation of programme activities under the direction of the NPD. S/he will be a full-time staff member preferably seconded to the NAPA Project from the Government for the duration of the process. S/he will head the Project Implementation Unit (PIU), and will be the primary focal person for support provided to the NAPA multidisciplinary Team. Key responsibilities of the NPC include:

· Managing and coordinating all day-to-day Project activities and coordinating the activities of the multidisciplinary team and short-term specialists

· Managing the PIU and overseeing the activities of all PIU staff.

· Producing all required Project reports (financial, progress and technical reports, workplans, terminal report etc.)

· Providing regular summary reports and updates to the NPD, as required.

· Preparing reports for PSC meetings, and acting as coordinator for PSC activities under the direction of the PSC Chair.
Qualifications:

· Timorese National with fluency of English and Portuguese is an asset;

· A advanced degree or higher (Masters or higher) in areas relevant to environment and development;

· Good knowledge of global and national environment issues;

· A minimum of 5 years of working experience in the area relevant to the Programme and demonstrating ability in managing the donor projects; and

· Demonstrated strong leadership, effective management skills, good coordination ability and team working spirit.
3. Multidisciplinary Team (Sectoral Working Groups)
The final set of sectors that will be covered will be determined during the inception workshop and will include food security and agriculture; water availability, quality and accessibility; forests, coastal ecosystems and biodiversity; human health; human settlement and infrastructure; and natural and human-induced disasters. Each SWG will consist of at least one national expert from identified key sectors who will be engaged on a commissioned basis to undertake well defined assessments and analysis. The major tasks of the SWGs will be to:
· Undertake a situation analysis of available information on adverse effects of climate change and coping strategies in Timor-Leste;
· Under the guidance of a international consultant on Vulnerability and Adaptation and the NPC, formulate an assessment methodology to collect information from all the 13 districts of Timor-Leste;

· Undertake in a participatory way Assessments of vulnerability to current climate variability and extreme weather events and more specifically assess where climate change is causing increases in associated risks;

· Collectively develop a country driven criteria for selecting priority activities to address needs arising from the adverse effects of climate change;

· Formulate key climate change adaptation measures for inclusion in Timor-Leste’s NAPA document. Paying particular attention to individual sectors, as well as an analysis of synergies, complementarities and cross-cutting issues amongst the sectors;
· Support and participate in the Stakeholder Consultation process to be undertaken, including providing briefings and presentations to stakeholders and preparing explanatory documents and summary assessments of vulnerabilities to climate change in their sectoral areas for circulation to interested parties.

Qualifications of national expert:

· Timorese National with fluency of English (Portuguese is an asset);

· A minimum bachelors degree in areas relevant to environment and development;

· Good knowledge of global and national environment issues;

· A minimum of 5 years of working experience in the area relevant to the Programme and demonstrating ability in managing the donor projects; and

· Demonstrated strong leadership, effective management skills, good coordination ability and team working spirit.

4. NAPA Programme Steering Committee (PSC)

The Programme Steering Committee (PSC) will be the overall governing body for the NAPA preparation process. It will comprise representatives from all key stakeholder institutions, and will be chaired by the Secretary of State for SSECTOPD. The PSC will assume an on-going coordinating role for assessing and improving capacities for managing the environment in Timor-Leste. Regular PSC meetings shall be held on a three-monthly basis until the completion of the project. Special sessions will be convened as required.

Responsibilities of the PSC will include:

· Provide high level orientation and guidance for the NAPA preparation process; 

· Ensure that the NAPA preparation programme develops in accordance with national development objectives, goals and polices;

· Overseeing all activities of the Programme, based on reports provided by the NPD and NPC;
· Serving as the primary GoTL inter-sectoral coordination body to ensure full support and cooperation from all stakeholder institutions;
· Provide overall guidance and coordination for the Programme implementation and make sure that the NAPA preparation process is progressing well according to the approved workplan;
· Ensure that the Programme performs within the framework of the NAPA preparation process Document and/or as revised by the inception report approved by the Programme Steering Committee;

· Review and endorse the annual Programme workplan, the corresponding budget, and the Financial Reports proposed by NAPA team for the NAPA preparation process and monitor its implementation; 

· Review and approve six-month and annual Programme progress report;

· Coordinate between different institutions linked with the Programme to ensure that all Programme activities are implemented efficiently and as planned;

· Determine actions, if any, to be undertaken to rectify the situation when expected outputs as determined in the workplan could not be met;
· Reviewing and approving all Programme outputs;

· Provide guidance and coordination to promote Programme sustainability.

Annex II: Organizational Chart for the Timor-Leste NAPA Process

[image: image3.png]/J?UF“]LL






NPD (at NDES) 





Secretary of State


SSECTOPD





MEA Secretariat 





SWG I


Food security and agriculture





UNDP/GEF





NAPA Project Implementation Unit (PIU)





NAPA TEAM





SWG IV


Human health





SWG III


Forests, coastal ecosystems and biodiversity





SWG V


Human settlement and infrastructure





SWG VI


Natural and human induced disasters





SWG II


Water Availability, quality and accessibility





NAPA Project Steering Committee (PSC)








� United Nations Population Fund (UNFPA), Census Timor-Leste 2004.  United Nations, Dili, 2004. 


� According to a World Meteorological Organization Mission to Timor-Leste Report (Dili, 29 Jan – 2 Feb 2007)


� According to a World Meteorological Organization Mission to Timor-Leste Report (Dili, 29 Jan – 2 Feb 2007)


� Climate Change in Timor-Leste: Science, Impacts, Policy and Planning. Briefing to Government, Civil Society, and Donors, República Democrática de Timor-Leste. December 2003, The University of Melbourne / CSIRO.


� Ministry of Agriculture, Forest and Fisheries Policy and Strategic Framework (2004)


� Human Development Report 2006 Timor-Leste


� Natural Resources and Environment, Priorities and Proposed Investment Program, 2005, p.16


� National Development Plan, p.212


� National Development Plan, pp. 309-310


� National adaptation programme of action will serve as simplified and direct channels of communication for information relating to the urgent and immediate adaptation needs of the LDCs.


� A country driven criteria for selecting priority activities will be identified and agreed during the NAPA preparation but in accordance with Paragraph 8 of the Annex to Decision 28/CP.7


� Preferably the existing Inter-Ministerial Working Group which consist of senior representatives from the office of the Prime Minister; Ministry of Planning and Finance; Ministry of Agriculture, Forest and Fisheries; Ministry of Natural Resources, Minerals and Energy Policy; Ministry of Development; Ministry of Foreign Affairs and Cooperation; Ministry of Transport and Communication; Ministry of Health; Ministry of Public Works; Ministry of Justice (Land and Property Unit); and the Ministry of Interior (Disaster Risk Management Office).





PAGE  
1

