[image: image2.jpg]


request for project preparation grant (PPG) 

Project Type:  FORMDROPDOWN 
  
the GEF Trust Fund
      Submission date:  10/10/2008
Resubmission date:  04/02/2009
GEF Project ID
: 3832
GEF Agency  Project ID: 4231
Country(ies): Egypt
Project Title: Improving The Energy Efficiency Of Lighting And Building Appliances
GEF Agency(ies):  FORMDROPDOWN 

Other Executing partner(s): Ministry Of Electricity And Energy
GEF Focal Area(s):  FORMDROPDOWN 


 FORMDROPDOWN 

GEF-4 Strategic program(s): SP#1: Promoting Energy Efficiency In Residential And Commercial Buildings
name of parent/program/umbrella project (if applicable):  
     
a.   Project preparation Timeframe 

	Start date of PPG
	April 09

	Completion date of PPG
	June 10


B. Past project preparation activities ($)  


	List of Past Project Preparation Activities
	Output of the Activities
	Project 

Preparation  Amount (a)
	Co-financing (b)
	Total

c = a + b

	     
	     
	     
	     
	     

	     
	     
	     
	     
	     

	     
	     
	     
	     
	     

	     
	     
	     
	     
	     

	     
	     
	     
	     
	     

	Total Project Preparation Financing 
	     
	     
	     


C.  proposed project preparation activities ($)

	Describe the PPG activities and justifications:  

1. An updated market study 

For CFL component: 

· an updated assessment of the market potential within the main targeted sectors; 
· an updated analysis of the key barriers to phasing out inefficient lighting; 
· an updated assessment of the local production capacities and supply characteristics. This will include collection of updated information on the current production capacities in Egypt and the characteristics of the products that are currently being produced. Similar data will be collected about main importers and assemblers of equipment. Further, an assessment will be made of the capacities of production facilities to manufacture more and better quality equipment. This will primarily take place via an analysis of production statistics and enquiries with manufacturers and other supply chain parties.
· EE lighting equipment sales and availability. Updated baseline data about the sales of lighting equipment (volume, types and characteristics of products, prices, availability) in various retail and distribution channels will be collected to build an accurate overview of the current market. This will be done by means of an analysis of sales statistics and enquiries with major suppliers, wholesale distributors and retailers of lighting equipment;

· Identification and evaluation of the feasibility of the possible distribution and financing mechanisms for accelerating the market transformation

For Standards and Labels of other Appliances

· an updated assessment of the level of implementation and enforcement of the standards and labels already developed and the barriers faced (including an assessment of and suggestions for the further development of the legal a regulatory framework together with an assessment and elaboration of the further capacity building and training needs); 
· by building on the review of the international “best practices” and a list of typical appliances selected for standards and labeling schemes in other countries after the most evident choices such as refrigerators/freezers, washing machines, AC-devices etc., review of the degree of saturation, energy consumption intensity, growth rates and potential savings and GHG reduction of possible new appliances for the S&L expansion plan 
· compilation of the required initial market information for the new appliances to be targeted, such as:
· type and categories of appliances produced domestically;

· key producers, their capacities and awareness, interest in and constraints to improve EE of their products;
· characteristics of imported appliances and their share in over-all market; 
· distribution network and chains and their marketing strategies; 
· major consumer groups, their awareness, interest in, ability and constraints to purchase EE products; 
· tracking product flows to show how standards and labels are likely to affect the production and flow of goods; 
· collect energy use data to show equipment energy consumption and ownership trends to allow initial estimates of the saving potential of various appliances proposed for an expanded S&L scheme 
· review of the existing testing facilities and elaboration of their further development needs with the associated assessment of the financing needs and possible financing arrangements.
2. Stakeholder consultations and engagement 

· stakeholder analysis (national and provincial government agencies, industrial and private sector, civil society and academic institutions), their interests, capacities, current and potential roles in project activities;

· stakeholder involvement strategy and plan, including the plan for the engagement and capacity building of the local manufacturers and other key supply side entities.

The public authorities related to this project will be consulted do discuss their views on the detailed objectives and arrangements of the project, to assess whether their involvement in its execution can be enlarged, to secure their commitment to critical outputs and to agree on the activities these government units will undertake as a part of the project, including cofinancing of the proposed activities These discussions are envisaged to consist primarily about bilateral consultations. 

The consultations with public authorities will be complemented by consultations with the market  parties and NGOs. These will include manufacturers and other suppliers, distributors and retailers of the targeted appliances so as get their views on the proposed project strategy and project activities as well as on the envisaged co-operation opportunities, including cofinancing. The primary mechanism for this is envisaged to be bilateral meetings, but small workshops can also be considered, if more appropriate and efficient

3.  Finalizing the project design and presentation
Finalized project document and CEO endorsement request of the project in accordance with the adopted UNDP and GEF formats, including: 

· an updated situation and baseline analysis;

· completed stakeholder analysis and stakeholder involvement plan  

· finalized project intervention and financing strategy and logframe for each project component with measurable indicators together with their baseline and target values;.

· an incremental cost analysis, including the description and more detailed calculation of  project’s direct and indirect national and global environmental benefits in accordance with the methodology adopted by the GEF; 

· finalized project budget and work plan both in the ATLAS format and as a total budget with confirmed cofinancing;

· completed risk assessment and risk mitigation strategy, including an assessment of the social, economic and financial sustainability of proposed project activities; 

· completed project management and implementation plan, including coordination with other relevant projects such as the UNIDO Industrial EE projects and the projects financed, among others, by the EU and GTZ;

· completed project monitoring and evaluation plan

· completed, draft Terms of References for the key positions;



	List of Proposed Project Preparation Activities
	Output of the PPG Activities
	Project 

Preparation Amount (a)
	Co-financing (b)
	Total

c = a + b

	CFL market study 
	Study
	20,000
	60,000
	80,000

	S&L market study
	Study
	30,000
	60,000
	90,000

	Stakeholder consultations and engagement
	Final project design
	10,000
	10,000
	20,000

	Finalisation of the project design and presentation
	Final project design
	40,000
	20,000
	60,000

	Total Project Preparation Financing 
	100,000
	150,000
	250,000


D.  Financing plan summary for project preparation grant: ($)

	
	Project Preparation 
	Agency Fee 

	GEF financing 
	100,000
	 10,000

	Co-financing 
	150,000
	

	Total
	250,000 
	10,000


E.  PPG  requested by agency(ies), focal area(s) and country(ies) 1
	    GEF Agency
	Focal Area
	Country Name/

Global
	(in $)

	
	
	
	PPG (a)
	Agency

Fee (b)
	Total

c = a + b

	 FORMDROPDOWN 

	 FORMDROPDOWN 

	Egypt
	100,000
	10,000
	110,000

	Total PPG Requested
	100,000
	10,000
	110,000


         1  No need to provide information for this table if it is a single focal area, single country and single GEF Agency project.
F.   PPG Budget Request

	Cost Items
	Total Estimated Person Weeks for GEF Grant (PW)


	GEF ($)
	Co-financing ($)
	Total ($)

	Local consultants *
	358 (GEF 98)
	49,000
	130,000
	179,000

	International consultants*
	16
	48,000
	     
	48,000

	Travel
	
	3,000
	5,000
	8,000

	Miscellaneous
	
	     
	15,000
	15,000

	Total  PPG Budget
	
	100,000
	150,000
	250,000


*  Annex A for Consultant cost details should be prepared first before completing this table.  See notes on Annex A for the 
     required detailed information.  This table is the sum of all local and international consultants presented in Annex A.

G.   GEF Agency(ies) Certification



	This request has been prepared in accordance with GEF policies and procedures and meets the GEF criteria for project identification and preparation.


	Agency Coordinator, Agency name
	Signature
	Date 

(Month, day, year)
	Project Contact Person
	Telephone
	Email Address

	John Hough, Deputy Executive Coordinator, Undp/Gef 


	[image: image1.png]/J?UF“]LL




	04/02/2009
	Vesa Rutanen
	+358 50 3209287
	vesa.rutanen@undp.org


Annex A

Consultants Financed by the Project Preparation Grant (PPG)

	Position / Titles
	$/

Person Week1 
	Estimated PWs2
	Tasks to be performed

	Local
	
	
	

	Senior Ee Lighting Expert
	500
	40
	Updated market analysis and needs assessment for the EE lighting component, stakeholder engagement and project stategy formulation in cooperation with the other consultants

	Senior S&L Expert
	500
	40
	Updated market analysis and needs assessment for the EE lighting component, stakeholder engagement and project stategy formulation in cooperation with the other consultants

	Other Short Term Expert
	500
	18
	Complementary short term assignment to defined in further detail during the PPG implementation

	International
	
	
	

	Project Formulation Expert
	3000
	10
	In cooperation with the other project consultants, finalization of the project intervention strategy and required project documentation (project document and the CEO endorsment request)

	EE Lighting Expert
	3000
	3
	Completed needs assessment and draft project intervention strategy for the EE lighting component + other required technical expertise support

	S&L Expert
	3000
	3
	Completed needs assessment and draft project intervention strategy for the S&L component + other required expertise support


1  Provide dollar amount per person week.
2   Provide person weeks needed to carry out the task and corresponds to the dollar amount per person week in the previous column.
�   Project ID number will be assigned by GEFSEC.  If PIF has already been submitted, please use the same ID number as PIF. 


� While not directly under any umbrella project, the EE lighting component will be closely co-ordinated and can be considered as a part of the UNDP-UNEP-GEF Global Market Transformation for Efficient Lighting project





PAGE  
1
PPG-December  08.doc


