GEF-6 REQUEST FOR PROJECT ENDORSEMENT/APPROVAL  
Project Type: Full-sized Project
Type of Trust Fund: Least Developed Countries Fund
For more information about GEF, visit TheGEF.org
[image: image4.jpg]gef



      




   
                       

part i: project information

	Project Title: Building Resilience of Health Systems in Asian LDCs to Climate Change

	Country(ies):
	Bangladesh, Cambodia, Lao PDR, Myanmar, Nepal, Timor-Leste
	GEF Project ID:

	6984

	GEF Agency(ies):
	UNDP        
	GEF Agency Project ID:
	5400

	Other Executing Partner(s):
	World Health Organization (WHO)
	Submission Date:
	29 Aug 2017
5 Oct 2017

	GEF Focal Area (s):
	Climate Change   
	Project Duration (Months)
	48

	Integrated Approach Pilot
	IAP-Cities  FORMCHECKBOX 
  IAP-Commodities  FORMCHECKBOX 
  IAP-Food Security  FORMCHECKBOX 

	Corporate Program: SGP  FORMCHECKBOX 
  

	Name of Parent Program
	N/A
	Agency Fee ($)
	     855,000


A. Focal Area  Strategy Framework and Other Program Strategies

	Focal Area Objectives/Programs
	Focal Area Outcomes
	Trust Fund
	(in $)

	
	
	
	GEF Project Financing
	Co-financing

	CCA-1 
	CCA-1: Reduce vulnerability of people, livelihoods, physical assets and natural systems
	LDCF
	3,179,704          
	9,343,400         

	CCA-2
	CCA-2: Strengthen institutional and technical capacities for effective CCA
	LDCF
	3,772,893               
	13,818,200          

	CCA-3
	CCA-3: Integrate CCA into relevant policies, plans and associated processes
	LDCF
	2,047,403          
	3,900,000     

	Total project costs
	
	9,000,000
	27,061,600


B. Project description summary 
	Project Objective: Increase the adaptive capacity of national health systems and institutions, and sub-national level actors, to respond to and manage long-term climate-sensitive health risks in six Asian LDCs.

	Project Components/
Programs
	Financing Type

	Project Outcomes
	Project Outputs
	Trust Fund
	(in $)

	
	
	
	
	
	GEF Project Financing
	Confirmed Co-financing

	 Policy frameworks and health standards incorporate climate change risks and adaptation
	TA
	Outcome 1: Institutional capacities are strengthened to effectively integrate climate risks and adaptation options in health sector planning and implementation   
	1.1 Integrated health national adaptation plan (H-NAP) is designed/updated to achieve the national health adaptation goals

1.2 Standard operating procedures developed for managing climate-sensitive health outcomes
1.3 Capacity building to support the implementation of standard operating procedures  
	LDCF
	1,907,403     
	3,500,000     

	 Information, integrated surveillance and early warning systems
	Inv
	Outcome 2: Effective decision-making for health interventions is enabled through generation of information and improved surveillance and/or early warning systems   
	2.1. Vulnerability assessment conducted for future health burdens considering development and climate change 

2.2. Integrated surveillance system strengthened of climate-sensitive health outcomes- 

2.3. Early warning system and response strengthened
	LDCF
	2,032,893     
	9,118,200     

	 Service delivery
	TA
	Outcome 3: Climate resilience is enhanced in health service delivery  
	3.1 Health care infrastructure strengthened to the impacts of climate change

3.2 Capacity of health personnel improved to identify and treat to climate-sensitive health issues 

3.3 Climate-sensitive disease control/water programmes strengthened 
	LDCF
	3,039,704     
	8,943,400    

	 Regional cooperation and knowledge management
	TA
	Outcome 4.1 Enhanced regional cooperation and knowledge exchange for promoting scale-up and replication of interventions

Outcome 4.2 HNAP are effectively integrated into ongoing NAP processes
	4.1.1
Regional experiences synthesized and shared among countries in the region and across different regions.
4.1.2
Definition of normative aspects related to climate-resilient health systems by developing regional-level guidelines, manuals, and other relevant technical documents (e.g. climate-resilient health care facilities (CR-HCFs) and climate resilient Water Safety Plans (CR-WSPs)), as required by countries;
4.2.1
Training and technical support for MOHs to conduct economic analyses to inform integration of health into adaptation planning and budgeting.

4.2.2
Training and tech support for designing/developing bankable projects to secure public or other finance
	LDCF
	1,600,000     
	4,300,000     

	Subtotal
	
	8,580,000
	25,861,600

	Project Management Cost (PMC)

	(select)
	420,000     
	1,200,000     

	Total project costs
	
	9,000,000
	27,061,600


C. confirmed sources of Co-financing for the project by name and by type
Please include evidence for co-financing for the project with this form.
	Sources of Co-financing 
	Name of Co-financier 
	Type of Cofinancing
	Amount ($) 

	Government
	Ministry of Health and Family Welfare (Bangladesh)
	In Kind/Grant
	5,300,000     

	Government
	Ministry of Health (Cambodia)
	Grant
	2,500,000

	Government
	Ministry of Health (Lao PDR)
	In Kind
	2,385,200

	Government
	Ministry of Health and Sports (Myanmar)
	In Kind
	3,000,000

	Government
	Ministry of Health (Nepal)
	In Kind
	3,300,000

	Government
	Ministério da Saúde (Timor-Leste)
	In Kind
	1,500,000

	IGO
	WHO
	In Kind/Grant
	9,076,400

	Total Co-financing
	
	
	27,061,600


D. Trust Fund  Resources Requested by Agency(ies),  Country(ies) and the Programming of Funds
	GEF Agency
	Trust Fund
	Country 

Name/Global
	Focal Area
	Programming of Funds
	(in $)

	
	
	
	
	
	GEF Project Financing (a)
	Agency Fee a)  (b)2
	Total
(c)=a+b

	UNDP
	LDCF
	Bangladesh, Cambodia, Lao PDR, Myanmar, Nepal, Timor-Leste   
	(select)  
	(select as applicable)
	9,000,000
	855,000
	9,855,000

	Total Grant Resources
	9,000,000
	855,000
	9,855,000


                          a ) Refer to the Fee Policy for GEF Partner Agencies

E. Project’s Target Contributions to Global Environmental Benefits

          Provide the expected project targets as appropriate. 
	Corporate Results
	Replenishment Targets
	Project Targets

	1. Maintain globally significant biodiversity and the ecosystem goods and services that it provides to society
	Improved management of landscapes and seascapes covering 300 million hectares 
	      hectares

	2. Sustainable land management in production systems (agriculture, rangelands, and forest landscapes)
	120 million hectares under sustainable land management
	      hectares   

	3. Promotion of collective management of transboundary water systems and implementation of the full range of policy, legal, and institutional reforms and investments contributing to sustainable use and maintenance of ecosystem services
	Water-food-ecosystems security and conjunctive management of surface and groundwater in at least 10 freshwater basins; 
	      Number of freshwater basins 

	
	20% of globally over-exploited fisheries (by volume) moved to more sustainable levels
	      Percent of fisheries, by volume 

	4. 4. Support to transformational shifts towards a low-emission and resilient development path
	750 million tons of CO2e  mitigated (include both direct and indirect)
	      metric tons

	5. Increase in phase-out, disposal and reduction of releases of POPs, ODS, mercury and other chemicals of global concern
	Disposal of 80,000 tons of POPs (PCB, obsolete pesticides) 
	      metric tons

	6. 
	Reduction of 1000 tons of Mercury
	      metric tons

	7. 
	Phase-out of 303.44 tons of ODP (HCFC)
	      ODP tons

	6. Enhance capacity of countries to implement MEAs (multilateral environmental agreements) and mainstream into national and sub-national policy, planning financial and legal frameworks 
	Development and sectoral planning frameworks integrate measurable targets drawn from the MEAs in at least 10 countries
	Number of Countries:     

	7. 
	Functional environmental information systems are established to support decision-making in at least 10 countries
	Number of Countries:     

	f.  Does the project include a “non-grant” instrument?    No                  

(If non-grant instruments are used, provide an indicative calendar of expected reflows to your Agency and to the GEF/LDCF/SCCF Trust Fund) in Annex D.



part ii:  project justification

A. describe any changes in alignment with the project design with the original pif
 
A.1. Project Description. Elaborate on: 1) the global environmental and/or adaptation problems, root causes and barriers that need to be addressed; 2) the baseline scenario or any associated baseline projects, 3) the proposed alternative scenario, GEF focal area
 strategies, with a brief description of expected outcomes and components of the project, 4) incremental/additional cost reasoning and expected contributions from the baseline, the GEFTF, LDCF, SCCF,  and co-financing; 5) global environmental benefits (GEFTF) and/or adaptation benefits (LDCF/SCCF); and 6) innovativeness, sustainability and potential for scaling up.  
1. Mortality and morbidity have fallen rapidly in Asia over the past 25 years, and there has been a marked transition from communicable to non-communicable diseases. The burden of disease from major infectious causes such as respiratory infections and diarrhea has fallen sharply, while that from cancer, cardiovascular and respiratory diseases has increased.  Although health indicators still lag behind those of industrialized countries, life expectancy has increased and infant mortality rates have fallen in the region. Consequently, the proportion of the population aged over 65 years is projected to increase to over 25% by 2050. 
2. While significant achievements have been made, this progress is at risk as the health of populations in Asia remains sensitive to climate variability and change and the capacity to prepare for and respond to these challenges is limited. The number of health professionals per capita is still low by global standards and less than 5% of GDP goes to health systems.
3. The Intergovernmental Panel on Climate Change (IPCC) 5th Assessment Report concluded that, in Asia heat waves will increase morbidity and mortality in vulnerable groups in urban areas; transmission of infectious disease will be affected due to changes in temperature and rainfall and nutritional status will be at risk from crop losses. Further, it noted that population groups most at risk from climate extremes are those living in low-lying coastal zones and flood plains; such areas are home to 50% of Asia’s urban population.  
4. This problem is exacerbated in Asian Least Developed Countries (LDCs), namely Bangladesh, Cambodia, Lao, Myanmar, Nepal, and Timor-Leste, where health systems often struggle to manage existing health risks, and capacity to adapt to additional climate change-related health risks is limited.  In these countries, annual average temperatures are projected to rise by 1.0 to 1.6°C by the year 2100 under a low emissions scenario and 3.6-6.0°C under a high emissions scenario. These changes lead to marked increases in heatwaves, and more modest increases in the risk of floods and droughts. 

5. These climatic changes lead to increased health risks, via direct and indirect pathways. Potential direct impacts include deaths and injuries from extreme events (heatwaves, storms and floods). Indirect effects include increased risks of infectious diseases (including water borne, food borne and vector borne infections); food insecurity and malnutrition; and diffuse health impacts from loss of livelihoods, conflicts over resources and migration.

Summary of climate change and health indicators

	
	Bangladesh
	Cambodia
	Lao PDR
	Myanmar
	Nepal
	Timor-Leste

	Temperature rise: 1990 – 2100 /°C (high emissions)
	4.8
	4.2
	4.5
	4.6
	6.0
	3.6

	Temperature rise 1990 – 2100 /°C (low emissions)
	1.4
	1.2
	1.4
	1.4
	1.6
	1.0

	Heat wave days /year (high emissions, 2100)
	300
	240
	170
	240
	245
	360

	Heat wave days /year (low emissions, 2100)
	120
	75
	50
	70
	65
	210

	Change in risk of flooding 1990 – 2100/days per year (high emissions)
	+10
	+10
	+7
	+7
	+6
	+5

	Consecutive days of drought (high emissions, 2100)
	85
	60
	65
	80
	104
	60

	Consecutive days of drought (low emissions, 2100)
	70
	57
	57
	72
	<90
	60

	People affected by sea level rise /thousands (high emissions, 2070–2100) 
	7,200 
	31
	-
	18,000
	-
	7.2

	People affected by sea level rise /thousands (low emissions, 2070–2100 ) 
	2,600
	9.8
	-
	15,000
	-
	6.5

	Population at risk of malaria /thousands (2070, high emissions)
	147,000 
	22,000
	1,900
	46,000
	n/a
	2,760

	Population at risk of malaria /thousands (2070, low emissions)
	117,000
	22,000
	1,600
	<46,000
	n/a
	2,760

	Heat related mortality/ per 100,000 people over age 65 (high emissions, 2080)
	30
	56
	72
	38
	53
	39

	Heat related mortality/ per 100,000 people over age 65 (low emissions, 2080)
	4
	4
	15
	12
	12
	5

	Nutritional impact /additional deaths per million people (2050)
	67
	59
	54
	87
	62
	n/a


6. The long-term solution for the governments of these Asian LDCs would be to have enhanced national health systems and institutions which are able to prepare effectively to climate change impacts on health in vulnerable population groups, with early warning measures in place to enable preventative measures to the extent possible, and adequate technical capacity of health systems that are able to respond to climate-related health issues. 
7. There are a number of barriers however that hinder the long-term solution in the context of these countries.  These barriers were expressed by each of the participating countries: 

· limited awareness of health risks of climate change; 
· insufficient integration of health into climate change adaptation plans and initiatives;
· poor coordination across ministries and departments;
· insufficient data and monitoring of climate-sensitive health outcomes; 
· limited technical capacity of public health staff; and
· limited human and financial resources to assess risks and to design, implement, and monitor adaptation.
8. Asian LDCs have limited technical capacity of health care systems and personnel to effectively integrate climate-related risks into policy, planning, and regulatory frameworks. In part because climate change is a relatively new concern, and in part because of the medium to long timeframes of projections and the indirect mechanisms linking climate change to major health outcomes, there is limited awareness across sectors of the health risks posed by climate change.  This lack of awareness hinders adequate consideration of climate change impacts on health into national and sub-national adaptation planning.  
9. Similarly, related data on health vulnerability due to climate impacts, that could inform planning, is limited and does not lead to effective early warning based on climate projections and geographic or social vulnerability.  Further, early warning systems managed by national meteorological organizations lack systematic coverage of observational data from regions and areas of the countries with high risks of climate-sensitive health outcomes. Climate data is not adequately disseminated or tailored to the needs of public health professionals to enable application to planning and preparedness measures.  
10. The project’s target countries face formidable development challenges with limited public resources.  As a result, health care facilities are ill-equipped to prepare for and respond to extreme weather and climate events, lacking information and cost-effective methods and technologies to provide adequate water and sanitation services during extreme events. 
11. The baseline without adaptation would mean that the significance of health risks from climate change would remain unrecognized, leading to insufficient integration of health into climate change adaptation plans and initiatives, poor coordination across ministries and departments; insufficient data and monitoring of climate-sensitive health outcomes; limited technical capacity of public health staff; and limited human and financial resources to assess risks and to design, implement, and monitor adaptation policy. 

12. Currently, national health systems and climate monitoring systems are not linked. Evidence-based interventions are available for all climate-sensitive health outcomes, although the extent of their implementation varies across countries. These interventions were designed without considering changing weather patterns with climate change, hence human health in Asian LDCs, continues to be at risk from extreme and/or erratic weather events.  
13. Below are short summaries of the related baseline for each of the participating countries.  This was compiled during the project development phase in consultation with national stakeholders.  It details the most critical climate health challenge faced by the countries as well as information about existing institutional and health system capacity.  For additional details, please see the country-specific documents provided as annexes.

Bangladesh

14. While health spending is only 2.8% of GDP, there have been substantial improvements in health indicators in recent decades.  Child malnutrition (stunting in children under 5 years) has fallen from around 70% in 1990 to 36% in 2015. Mortality from all causes has approximately halved from 10/1000 in 1990 to 5/1000 in 2015. About 60% of the population has access to improved sanitation, and 87% have improved water supplies. These percentages are similar in both urban and rural areas.

15. Climate change, however, puts at risk these fragile development gains. Bangladesh has a subtropical monsoon climate with moderately warm temperatures and high humidity. There are three distinct seasons: hot, humid summer (March to June); cool rainy monsoon (June to October); and a cool, dry winter (October to March). Most parts of the country receive more than 2000mm rain per year, and 80% (1600mm) falls during the monsoon season.4  With wide seasonal variations in rainfall, the country is highly vulnerable to natural disasters including inland and coastal inundation, storm surge, cyclones and tornados, drought, river erosion, sea level rise and salinity intrusion. Over the last decade, Bangladesh is experiencing changes to climate, recurrent flooding has become an increasing problem, with increased rainfall occurring in several districts. The number of cyclones and storm surges has also increased. While overall rainfall has increased, so has variability, meaning that some areas are experiencing more drought. Sea level rise from climate change is contaminating fresh water and soil. Temperatures are expected to continue to increase, with a further 0.4°C increase in mean temperature expected by 2030, with an overall increase in rainfall. 

16. The main health concerns in Bangladesh are water- and vector-borne disease, pneumonia, skin and eye diseases, malnutrition, and high maternal and infant mortality.
  Malaria, dengue and cholera are of particular note, with increased heat and rainfall related to climate change contributing to incidence. While mortality from communicable diseases has fallen rapidly, there have been notable increases in non-communicable diseases. 

17. The populations that are especially vulnerable to climate change in Bangladesh include those living in coastal regions or on small islands, those in mountainous regions, and those in megacities. The coastal zone of Bangladesh has over 35 million people who are exposed to cyclones, storm surges, rough seas, salinity intrusion and permanent inundation due to sea level rise. There are 72 offshore islands with an area of 4,200 square kilometres where over 3 million people are extremely vulnerable, due to coastal flood risks. Areas with poor health infrastructure, such as in remote villages, are the particularly vulnerable given their limited access to health services. Children and pregnant women are especially vulnerable, in particular to malnutrition and diarrhoeal disease. People with underlying chronic disease or who are elderly are also at increased risk, as are those who are less mobile.

18. The impacts on health from increasing extreme events include direct trauma from storms and flooding, increase in vector-borne disease from more favourable (warmer and wetter) conditions, loss of food crops and fishery resources, and mental health impacts associated with declining incomes as well loss as the damage to local lives and livelihoods from extreme events which may be immense. Overcrowding and poor quality buildings contribute to deaths and injuries during extreme events.
 

19. Water-borne diseases will remain a major public health problem in Bangladesh as the climate changes, and require improvement in water supply and sanitation management as well as protection of water resources. A comprehensive health vulnerability and adaptation assessment conducted in 2011 concluded there is a need to undertake capacity and preparedness assessment of the health care facilities and health professionals to identify the strengths, weaknesses, and gaps in responding to the rising threats of emerging and re-emerging infectious diseases and non-communicable diseases (including mental health) associated with climate change.
  There is a need for health professionals to be trained on climate change and its impact on human health. 
20. The Climate Change and Health Promotion Unit is responsible for coordinating work on climate change, but lacks adequately trained personnel.  Capacity building is needed both within the health sector as well as across sectors is needed for climate health sensitive planning.  For example, the vulnerability and adaptation assessment developed by the health sector was not mainstreamed into regular health planning, due to adequate lack of awareness and technical capacity.  

21. Reliable access to health services is also a concern.  Health-care facilities, especially in remote areas, are vulnerable to extreme weather events and become inoperable during those events, when they are most needed. Remote facilities often lack access to safe running water and sanitation, which are preventive for many climate-sensitive diseases. Remote health-care providers have limited skill to diagnosis and treat climate-sensitive diseases. Health staff do not have access to treatment guidelines and are not skilled in epidemic preparedness. Community members, especially vulnerable groups such as poorer people, women and children, often do not have the resources to access health care.
22. The UNDP ‘National Capacity Development for Implementing Rio Conventions through Environmental Governance’, project focused on developing institutional capacities for management of global environment, mainstreaming global environmental conventions into human resource development, and raising awareness of the linkages between the Rio Conventions and sustainable development. That project offers some lessons towards carrying out needs assessments and approaches for capacity building of government staff, upon which this project can build.
23. Further, there are a number of interventions planned or underway, which will contribute to this baseline:

· A climate resilient water, sanitation and hygiene (WASH) project, Building adaptation to climate change in health in least developed countries through resilient WASH, is being implemented by Department of Public Health Engineering (DPHE) with technical assistance from WHO Bangladesh.  The aim of that project is to reduce risks of climate-related disease and improved health protection for the poor through achieving i) coherent climate resilient international policy ii) climate resilient health promoting WASH policies defined, iii) climate resilient water safety plans.  
· The Health, Nutrition and Population Sector Program, funded by World Bank, intends to pilot adaptation measures in three specific geographical divisions that are particularly vulnerable to different climate threats: Barishal (coastal flooding), Rajshahi (drought) and Sirajgonj (flood) division.

· A project funded by the Bangladesh Climate Change Trust, Adaptation research in the context of climate change impact on health sector in Bangladesh, will generate evidence on climate change and health related diseases like malaria, dengue, diarrhoeal diseases and others. It will also follow up a school health intervention trial and community based water treatment plants. This project will continue until the end of 2018.
· WHO and the UK Department for International Development (DFID) will start developing the health component of the National Adaptation Plan (NAP) in 2017.  In the course of Health-NAP (H-NAP) development analysis of climate impacts, adaptive capacity of communities/institutions for each major vulnerable health sector considering geography will be evaluated.

· UNDP has submitted a proposal to the GCF, on behalf of the Government of Bangladesh, to support the NAP process.  This is expected to be approved in 2017. 
Cambodia

24. From a strategic health perspective, Cambodia has been undergoing an epidemiological transition from communicable to non-communicable disease, although communicable disease remains a major problem with high burdens of tuberculosis, acute respiratory and gastroenteric infections, as well as being prone to outbreaks of water-borne and vector-borne disease. Through its impact on food security, adequate safe water, vector-borne disease transmission and productivity of major industry, climate change makes poverty reduction more difficult and further threatens growing inequality.  The GDP per capita is USD 1158.70 and growing at around 7% per annum, health spending however is low by global standards at about 1.3% of GDP given the increased pressures on health spending expected with climate change.
25. Climate change in Cambodia may increase the risk of food insecurity through floods and droughts and facilitate transmission of food and waterborne pathogens that cause diarrhoeal disease. Young children are especially vulnerable to malnutrition and diarrhoeal disease.  Children who are poorly nourished through inadequate nutrition and/or recurrent diarrhoea are at increased risk of poor health outcomes if exposed to other climate-related diseases. Nearly 80% of all reported dengue cases in Cambodia occur in children aged 9 years or younger, with the highest incidence in infants aged under 1 year.

26. Differences in education, literacy, land ownership, and income between men and women in Cambodia mean that women are more vulnerable than men to the impacts of climate change. They have fewer assets and resources available to adapt to climate change, including in their capacity to respond to acute climate shocks.  Public awareness is needed, which is tailored to the needs of communities, is needed to ensure preventative measures are taken to the extent possible. 
27. Cambodia has two main seasons, a dry season from mid-November to April and a monsoon wet season from May to October, interrupted by a “mini-dry season” in July to August. Temperatures average 28°C, ranging from a high of maximum daily temperatures of 38°C in April to a low of minimum of 17°C in January. Average annual rainfall ranges from 1400mm in the central lowlands to 5000mm in coastal areas, which are also more prone to extreme storms. Flooding is common in the monsoon season, from local rains and rains falling upstream in the Mekong basin, destroying crops and household assets. 
 Cambodia is a low-income country with an estimated population of 15.6 million people with a median age of 24.9 years and nearly 80% of whom live in rural areas. Approximately 70% of employment is in agriculture, mostly non-irrigated, rain-fed rice production. 
28. Mean annual temperatures have increased 0.8°C since 1960, at a rate of 0.18C per decade, and the frequency of heatwaves has increased. Further temperature increases of between 0.7 and 2.7°C by the 2060s and 1.4 to 4.3°C by the 2090s, with 14-49% and 20-68% more days respectively to be considered hot in relation to current climate. Sea-levels will rise by up to 0.98m by 2100.10
29. A wide range of health outcomes are associated with weather and climate variability. The three areas of highest priority in Cambodia are vector-borne disease (malaria and dengue particularly), water-borne and food-borne, and the health impacts of extreme events.
,

· Vector-borne disease will most likely increase due to higher temperatures, changing precipitation, increasing urbanization and migration. Malaria is associated, for example, with increased rainfall. In addition to malaria and dengue which are currently important, Japanese encephalitis, chikungunya and Zika viruses are of concern.10 Greater surveillance, early warning, access to effective treatment and improved healthcare worker skills, and vector management is required. An increase in water storage in response to more variable rainfall will require implementation of vector-control measures.
· Major water-borne diseases in Cambodia include rotavirus, Escherichia coli, Shigella, cholera and typhoid. Many rural households do not have adequate latrines or waste disposal that may affect water quality of surface and ground water during heavy rain. Drought also is associated with water-borne diseases as a result of the shortage of water and poor sanitation practices. Infection may manifest as acute diarrhoeal disease or as chronic gastrointestinal infection contributing to malnutrition. Improved sanitation and water supplies are needed to reduce this climate change impact.

· Strong storm surges cause death, injuries, morbidity and mental health issues. Flooding has been recorded almost every five years, becoming more frequent in the last 10 years. Sea level rise is causing more severe and more frequent coastal inundation, especially during storms and typhoons. Extreme events amplify existing health problems of diarrhoeal and respiratory infections and vector-borne disease, while access to health care is limited. Increasing frequency of hot days may have direct impacts on the health of the mostly outdoor workforce population and also negatively affect productivity. Increased temperatures and altered precipitation (more variable rainfall increasing both flooding and drought risk) may increase the risk of diarrhoeal disease. Early warning and improved access to services would reduce impacts of flooding on the health of communities, and modified activities may be needed to reduce impacts of heat on worker health and productivity.

30. The Ministry of Health (MoH) is responsible for health system planning, development and service delivery.  Within the Ministry, the Directorate General for Health manages 24 provincial health departments. The provincial health departments encompass 81 health operational districts and operate the provincial hospitals. Each operational district covers 100,000–200,000 people and operates a referral hospital and health centers. Each health center covers 10,000–20,000 people. The health centers provide a minimum package of activities, mainly preventive and basic curative services, and the referral hospitals provide a complementary package of activities, mainly secondary care. Provincial and national hospitals provide the highest-level complementary package. National hospitals include general hospitals and specialist hospitals for pediatrics, maternal and child health, and tuberculosis. Less formal health posts provide services in remote areas.

31. MoH faces several capacity and finance gaps, and the urban–rural distribution of resources disproportionately favors urban areas. Government funding for health care is only 1.4% of GDP, and development assistance accounts for 15–20% of health expenditure. Out-of-pocket expenditure accounts for almost two-thirds of total health expenditure, and most of this is paid to private providers. The private sector is extensive and insufficiently regulated, but it provides the majority of curative care (the type of care most needed to treat climate-sensitive diseases). According to the 2014 Cambodian Demographic and Health Survey, only 22% of unwell or injured patients sought care first in the public sector, while 67% sought care for their last episode from private providers. Staffing and equipment capacity are limited.  MoH employs just under 20,000 staff, but it hopes to increase the public health workforce to 32,000 people by 2020. Diagnostic equipment such as magnetic resonance imaging and computed tomography is largely unavailable, and maintenance is an issue. The equipment that is available is concentrated in the private sector.

32. The GEF-funded, Strengthening Climate Information and Early Warning Systems in Cambodia to Support Climate Resilient Development and Adaptation to Climate Change, project is improving the climate-observing infrastructure and increasing capacity to use climate and environmental information to respond to climate hazards and plan adaptation to climate change.  There are opportunities to build on this work to include early warning for health.

33. Similarly, there are opportunities to build on the work of the Cambodia Climate Change Alliance Phase 2 (CCCA-2) project, Strengthening Country Capacity to Deal Effectively with Climate-sensitive Vector-borne and Waterborne Diseases and Reducing the Health Impacts of Disasters, which runs through 2018, as well as the Vulnerability and Impact Research Targeting Usability and Effectiveness (VIRTUE) project which aims to improve understanding of climate-sensitive risks to health in Cambodia and to facilitate effective health adaptation responses targeted at vulnerable groups. 

Lao PDR

34. In Lao PDR, malaria is endemic occurring mostly in highland forests of the south, and multidrug resistance is of growing concern. Dengue outbreaks can place a heavy burden on the health system with a lack of adequate surveillance, vector-control, diagnosis and effective treatment, communication and early warning. Chronic malnutrition affects around 44% of children aged under 5 years in Lao, often the result of a combination of insufficient quality food and diarrhoeal disease. Life expectancy in Lao PDR is low (64 and 67 years for men and women respectively) and child mortality is high (71.4 per 1000 aged < 5 years). Diseases related to lack of clean water and sanitation contribute substantially to health burden in Lao with about a quarter of the population lacking access to improved drinking water, and a similar proportion practice open defecation.  A majority of health services and hospital are also lacking water and sanitation facilities. 

35. Significant disparities exist between urban and rural areas remain related to access to health services.  Access to health care is difficult, especially for those in more isolated regions as there are few health centres. For instance, vaccine-preventable diseases such as measles, polio, diphtheria, rubella, tetanus and pertussis are diminishing but still of concern, with some geographic areas and ethnic groups poorly covered.  Poverty is associated with more isolated rural and highland areas in the eastern border regions in the south.
  People living in rural and highland areas are more likely to be poor. Through its impact on food security, adequate safe water, vector-borne disease transmission and productivity of major industry, climate change makes poverty reduction more difficult and threatens growing inequality.  
36. Lao PDR has two main seasons, a dry season from mid-October to April and a rainy monsoon season from May to mid-October. Climate varies across three climatic zones: montane temperate and subtropical (northern highlands) tropical monsoon (central highlands), and tropical lowland and floodplains along the Mekong river.  Temperatures in Lao have risen over recent decades and will continue to increase between 1.4°C and 4.3°C by 2100 based on low and high emissions data, and will most likely be higher in southern areas. Dry seasons are getting longer and rainy seasons shorter but more intense. Mean annual rainfall is expected to increase in eastern and southern areas by 10-30% during the wet season, including with an increase in extreme events and flooding. Mountain areas may become more vulnerable to flash floods.

37. A climate change and health vulnerability assessment (2010-2011) concluded that waterborne diseases, especially dysentery and typhoid, remain a significant source of morbidity, with the health burden expected to increase with climate change. Vector-borne diseases, particularly dengue, also are expected to increase. Limited data and information are available on who is most vulnerable and which geographical areas will be more affected, but it is likely to be the more isolated, poorer areas in mountain regions who are most at risk. 
38. There is capacity gap between assessing vulnerability and addressing climate change and health issues. A health system review in 2014, organized by WHO on behalf of the Asia Pacific Observatory on Health Systems and Policies, concluded that despite strong government commitments to health, as reflected by policy statements, decrees, national strategies and plans, and a comprehensive health reform strategy, there are gaps between policy intentions and effective implementation.  Cross-sectoral collaboration is weak and political commitments have not yet been translated into increased health spending. 
39. There are initiatives in development, related to supporting the NAP process, that can built upon to ensure that health is mainstreamed into adaptation planning.  The Strengthening the Capacities for Iterative National Adaptation Planning Process in the Lao People’s Democratic Republic project is a four-year project with the main objectives to strengthen institutional and technical capacities for effective climate change adaptation and to integrate climate change adaptation into relevant policies, plans and associated processes. The outcomes of the GEF, UNDP and Ministry of Natural Resources and Environment project are:

· to strengthen capacity and ownership of adaptation and climate risk reduction planning at the local level;

· to achieve adaptation benefits for food security and nutrition objectives of vulnerable populations, especially women, through improving land use practices and community support services;

· to strengthen the institutional, policy and fiscal framework for climate change adaptation.

Myanmar

40. Myanmar aims to reduce poverty and improve human development through accelerating growth and providing economic stability. There has been an overall decline in poverty related indicators in recent decades, including increasing gender equality in educational outcomes, increased participation of women in government employment, increased sanitation. Myanmar’s human development index, although improving, remains below average for countries in East Asia and the Pacific. Through its impact on food security, adequate safe water, vector-borne disease transmission and agricultural productivity, climate change makes poverty reduction more difficult and threatens growing inequality.  
41. Life expectancy in Myanmar has increased over recent years to 63.2 years and 67.1 years for males and females respectively in rural areas, and 64 years and 69 years in urban areas (2007 estimates).
 Infant mortality has almost halved, from 78 per 1000 in 1990 to 40 per 1000 in 2013. As per WHO/UNICEF Joint Monitoring Report of 2015, Myanmar has achieved 81% improved drinking water coverage and 80% of the population have access to improved. However, like in other developing countries, safety of drinking water and safely management of sanitation is an issue. Water and sanitation facilities in coastal areas are also at risk of extreme weather events. Malnutrition is prevalent, with stunting in approximately 40% of children under five years and underweight in approximately 30%.
 Maternal mortality is high with between 230 and 580 maternal deaths per 100,000 live births. Communicable diseases of note include diarrhoea, cholera, influenza, malaria, dengue, yellow fever and tuberculosis. Indoor air pollution is a contributor to the burden of heart disease, stroke, lung cancer and COPD, especially in women, and to deaths from lower respiratory infections in children. Public health expenditure has increased as a proportion of government spending from 15.6% in 2010 to 45.9% in 2014.

42. Myanmar has three seasons of hot, rainy and cool and is vulnerable to extreme weather events of cyclones, floods and droughts. Since the 1950s, average temperatures in Myanmar have increased an average of 0.08°C per decade, with greater increases in northern and central regions (up to 0.32°C per decade in Kayin State). Overall rainfall has increased, but decreases in some regions have been observed (e.g. Bago region).17 The duration of the monsoon season has decreased, with later onset and earlier departure. Extreme weather events have increased in frequency and severity, including severe storms and cyclones, floods and storm surges, intense rainfall, drought and extreme heat. Over the coming decades temperatures will continue to rise 1.4°C to 4.6°C by the end of the century, depending on emissions, and the number of “warm spell” days per year will increase from 10 (1990 baseline) to between 70 and 230 depending on emissions. Rainfall intensity is projected to increase beyond the range of historical variability under a high emissions scenario, and the length of “dry spells” could increase from 8 to 80 days, with increased interannual variability.

43. Current climate variability and change are already affecting communities and socioeconomic sectors in Myanmar.  Drought, associated with shortened monsoon season, is the most severe weather event affecting local communities and causing health impacts. Climate change projections suggest extreme events will increase in frequency and intensity, further heightening these risks. The main health risks in Myanmar associated with climate include limited clean drinking water and poor sanitation services. Food insecurity and malnutrition among children is widespread. The greatest concern regarding climate change impacts on human health in Myanmar is related to availability of freshwater sources. Increases in intense rain events and tropical storms will lead to increases in flooding and storm surges which results in freshwater sources being contaminated by rising floodwater levels, while rising sea levels will result in fresh groundwater resources being displaced with salt water. An increase in non-potable fresh water will result in communities without safe drinking water and increasing dehydration risks, further exacerbated by diarrheal diseases. In addition, increased frequency and severity of droughts will decrease water availability and water quality –for drinking, sanitation and hygiene purposes. Myanmar’s climate will consequently become more favorable to transmission of vector-borne, water- and food-borne disease. 
44. Myanmar relies on passive surveillance for communicable disease resulting in incomplete data and limited ability to respond proactively in epidemic prevention. Lack of meteorological data and capacity for analysis and information exchange limits planning, early warning and timely response to extreme events.
 Children are highly vulnerable to malnutrition associated with reduced food security and increased diarrhoeal disease. Women are more at risk due to poverty and lower literacy and educational attainment. Particular regions at risk include Central Dry Zone and flood risk areas.  Enhanced early warning and public awareness tailored to needs is required to enable better preparedness.
45. Further, health facilities are not able to respond effectively to extreme events and Myanmar has limited technical capacity and limited personnel to plan for and implement climate adaptation activities.  Training is needed for staff to able to identify and treat climate related illness.

46. Natural Disaster Plans are in preparation in different sectors and there is a Myanmar Action Plan on Disaster Risk Reduction (2009-15). The focus is on raising public awareness to bring about behaviour change to protect communities from climate-associated health risks such as heat exposure and water-borne disease, including an annual ‘National Sanitation Week’. Basic sanitation systems are provided to communities to reduce transmission.
47. There are a number of programmes and projects provided related support in Myanmar: 

· The World Bank flood and landslide recovery project aims to support recovery of flood affected areas in 2016 flood which can collaborate with climate sensitive communicable disease control projects, water safety plan development and nutrition activities. 

· Asian Development is Rural Development Department, Relief and Resettlement Department for community disaster resilience focuses on preparedness for various epidemics and is one of the entry points for community disaster resilience and EWARS and disaster preparedness, health emergency response activities can be linked with ADB support projects.
· UNDP is working with the Environmental Conservation Department and support for climate change and disaster risk reduction through forest sector and environmental conservation. UNDP is also leading agency for DRR working group in Myanmar and implementation of water safety plan and community based climate related health risk reduction projects.
· The WHO Country Office plays a crucial role in health system strengthening and implementation of health care services in Myanmar by providing technical assistance and financial assistance. WHO country office with MOH implemented water safety plans in rural and town water supply systems funded by DFAT (Australia).
Nepal
48. Nepal’s climate varies with altitude between subtropical to alpine over a very short distance (200km). Rainfall is generally higher in the east compared to the west, and temperatures are warmer in the southern lowland areas that are in the Himalayan region to the north. The four seasons in Nepal are pre-monsoon (March-May), monsoon (June-September), post-monsoon (October-November) and winter (December-February). Annual maximum temperatures occur May-June. The topographic variability within Nepal leads to considerable variability in rainfall and temperatures.
49. Temperatures in Nepal have been increasing in recent decades at a rate of approximately 0.37°C and 0.15°C per decade in annual maximum and minimum temperatures, with warming greatest in the mountain compared with the lowland regions.
 There are fewer cold days and more warmer days. Snowfall in highlands areas has been decreasing and glaciers are shrinking, reducing water available for drinking and irrigation, while there has been a trend overall for increasingly heavy precipitation.

50. Overall health outcomes are improving, with substantial reductions in child mortality and maternal mortality over the last few decades. Health inequities remain significant, with numerous barriers to accessing health services – financial, sociocultural, geographic and institutional. Rapid urbanization, shifting health patterns and natural disasters place additional pressures on the system in providing quality care.  Current lack of primary healthcare for most of the population contributes to Nepal’s vulnerability to climate change. Epidemics relating, such as cholera, gastroenteritis, diarrhoea, encephalitis, meningitis, typhoid, jaundice, malaria, dengue, chikungunya and scrub typhus are exacerbated with warmer temperatures and flooding during the monsoon season, as well as lack of clean water and sanitation. 
51. Changing weather patterns in Nepal are consistent with the increasing risk of these climate-sensitive diseases, particularly malaria, kala-azar (visceral leishmaniasis), Japanese encephalitis, and diarrheal diseases (including cholera). Increasing temperatures will put more communities and a greater number of people at risk if the diseases spread to new regions, extending, for example, their altitudinal reach. Changing settlement patterns related to changing climatic conditions can further increase risks, with crowding and lack of infrastructure in rapidly urbanizing areas. Weather-induced disasters, such as flooding, adversely affect public health through injury and trauma, transmission of disease, and damage to infrastructure. Declining crop yields associated with both increasing extreme events and changes to average temperatures and precipitation and seasonal timing would increase undernutrition. 
52. Population vulnerability in Nepal is associated with geography, local resources, infrastructure, and governance effectiveness including access to information for extreme events. Areas that are flood-prone, mountainous, water stressed and/or densely populated are especially vulnerable to changing climate, and geographical isolation compounds vulnerability to climate sensitive disease and diminishes capacity to respond to additional challenges of climate change. Population groups that are relatively more vulnerable than others, including children, women (especially pregnant women), those living in informal urban settlements or on environmentally exposed areas such as riverbanks, steep hills or plains, displaced people, those outside formal employment, older people, refugees and those in prison.
53. Nepal’s priorities regarding equal access to health care, if realized, will go some way to reduce exclusion and inequalities. Poverty reduction in Nepal has been slow and unequal among groups, with women remaining overrepresented among the poor.  The loss of lives and livelihoods associated with exposure to major extreme events, including the 2015 earthquake, slows poverty reduction and attainment of development goals. Climate change makes poverty reduction more difficult and threatens growing inequality, through its impact on food security, safe water, sanitation, vector-borne disease transmission and income from agriculture.  

54. A number of efforts are ongoing providing support to address climate change and health issues in Nepal:

· WHO is implementing programmes that support the Ministry of Health in integrated disease surveillance and control of communicable diseases. In 2016 the Government of Nepal expanded the early-warning alert and response system in 81 sites.

· WHO and the Ministry of Urban Development, with the support of a climate change resilience project funded by the United Kingdom Department for International Development, are working on water safety plans as part of the DFID-funded project Building Adaptation to Climate Change in Health in Least Developed Countries through resilient Water, Sanitation and Hygiene. 

· The Nepal UNDP Country office is implementing the following projects: Renewable Energy for Rural Livelihoods, a GEF small grant programme, Ecosystem-Based Adaptation in Mountain Ecosystems in Nepal, the Nepal Climate Change Support Programme, the Community-Based Flood and Glacial Lake Outburst Risk Reduction Project and the Comprehensive Disaster Risk Management Programme.
· Financed through Bundesministerium für Umwelt, Naturschutz, Bau und Reaktorsicherheit (BMUB), UNDP is supporting Nepal to integrate agriculture into the NAPs process (US$500,000)

Timor-Leste

55. As many as 60-70% of households in Timor-Leste are already moderately-to-severely food insecure, particularly between December and February – often termed the ‘hungry season’, when most farmers have exhausted their stock of cereals and are awaiting their next harvest
.  Children are particularly vulnerable, as 47% under the age of five suffer from chronic malnutrition
. Malnutrition weakens the immune system and can lead to a heightened risk of illness and disease. Chronic undernutrition in early childhood also results in diminished cognitive and physical development, which can put children at a disadvantage for the rest of their lives
. Research has shown that the effects of chronic malnutrition are irreversible if left untreated by the time a child reaches two or three years of age
.  
56. Agriculture production has not yielded enough, to meet what is required by the growing population
.  While there has been an overall increase in total food production since 2002, imports are still needed to supplement the shortfall
.  80% of the country’s poor and 90% of the rural poor depend on subsistence rain-fed agriculture for their livelihood. Unusual or extreme weather has been cited as the cause for low crop yields (i.e. 25% decrease in rice in 2009 and 20% decrease in maize in 2010)
. Climate change will continue to challenge food security with increasing temperatures and variability in rainfall. The impacts are likely to be particularly acute in the coastal regions where the sea surges, coastal inundation, prolonged submersions, erosion, and long term sea level rise undermine land productivity.  
57. Timor-Leste’s susceptibility to climate change impacts is high and it lacks coping and adaptive capacity. Timor-Leste is approaching malaria eradication, but climate change will most likely increase the risk of both dengue and malaria at least in the next few decades, while increases in major water and sanitation-related health problems, such as water-borne diseases, including diarrhoea and other parasitic and bacterial infections, are also very likely. Increasing variability in rainfall will have negative consequences for agriculture and food security. Climate change will aggravate vulnerability to natural hazards such as frequent tropical cyclones, floods, droughts, landslides, and coastal inundation, all of which have negative impacts on health through deaths, injuries and loss of livelihoods. 
58. Similarly, negative impacts on agriculture and fisheries will contribute to poorer nutritional outcomes for the population, and likely to disproportionately affect women and children, as will drought and flooding affecting water supply and quality and contributing to diarrhoeal disease. Dependence on imported foods is high, at about 30-40%, creating vulnerability to international food market volatility, while poorer households are not able to access imported food at all. Increasing extreme heat is likely to negatively affect health of older people, children, those who are socially isolated and those occupationally at risk. Particular villages (sucos) are also considered more vulnerable, especially those in the western region with water and agriculture as notable resources at risk.
59. Climate change, largely through its impact on income generating activities relating to agriculture, will make poverty alleviation more difficult. Other ways in which climate change may contribute to poverty is through increasing illness (through vector-borne disease and diarrhoea, as examples) and its sequelae of reduced worker productivity and increased time spent out of education.
60. The fifth assessment report (AR5) from the Intergovernmental Panel on Climate Change (IPCC) indicates that temperature in the Southeast Asia sub-region has been increasing at a rate of 0.14°C to 0.20°C per decade since the 1960s, and predicts increases from 0.8°C to 3.2°C by the end of this century. The report further highlights the positive trend in the occurrence of heavy (top 10% by rain amount) and light (bottom 5%) rain events, and the influence of climate change on several large-scale phenomena affecting the region
.  Temperature observations in Timor-Leste are consistent with the high end of the range of the IPCC AR5 temperature trend.  Rainfall observations are also consistent with the report; heavy rain events are more common, while the overall average annual rainfall has decreased.  
61. The northern region has distinct wet (four months, December to March) and dry seasons, and in the south the wet season is longer (7-9 months) with peaks in December and May.  Timor-Leste has rainfall that is highly variable from year to year, influenced by the El Niño Southern Oscillation. It is prone to both drought and extremely heavy rainfall, which leads to erosion and landslides in mountainous regions due to deforestation for cropping and stock. Timor-Leste also experiences frequent and significant flooding.
 Temperatures in Timor-Leste increased by 0.5-0.8°C to 2005, and will increase a further 1.5-1.8°C by 2041-60 (relative to 1981-2000), with more days of extreme heat. Rainfall will become more variable, with increased intensity and frequency of rainfall in the wet season and less rain in the dry. Cyclones are expected to be fewer but more intense. Sea levels will rise by 76cm by 2100.31,
 
62. There are a number of ongoing initiatives supporting climate-resilience and climate-informed planning in Timor-Leste.  Specific programmes and projects directed at climate variability and change are described below:
· WHO and MOH have implemented water quality and safety project funded by DFAT from 2012 – 2017. This project helped develop capacity of national teams and policies and guidelines on water, sanitation and environmental health. Several models for water safety plans are developed in five urban water supply systems.
· The Global Climate Change Alliance Support Programme to Timor-Leste seeks to improve the capacity of populations vulnerable to climate change risks to cope with climate change effects through the sustainable management of their natural resources and the improvement of their livelihood options. This will be achieved using local development mechanisms taking social inclusion and conflict management into account. The project has three expected results:

· Weather monitoring is made reliable in all 13 districts; climate effects on agricultural production and the environment are better known; the results of regular agro-meteorological analysis are made accessible to the rural producers; and the consequent findings support the definition of evidence-based national policies.

· Rural communities are able to identify adaptive responses to climate challenges; these responses are incorporated into suco (village) development plans in at least 50% of sub-districts identified as vulnerable to climate change risks, in a socially inclusive way.

· The resilience of rural communities living in at least 50% of sub-districts identified as vulnerable to climate change risks is enhanced through the restoration of their environment, the implementation of sustainable livelihood development activities, and improved social dialogue.

· Strengthening the Resilience of Small Scale Rural Infrastructure and Local Government Systems to Climatic Variability and Risk - this UNDP-supported project uses the existing UNDP Local Government Support Programme as an entry point to deliver concrete measures to significantly increase the resilience of critical rural infrastructure to climate related impacts in high risk districts and sub-districts. Critical small scale rural infrastructure is designed and implemented through participatory approaches and strengthened local governance systems, reflecting the needs of communities vulnerable to increasing climate risks.  The project takes a three pronged approach comprising the following specific outcomes:

· Systematic use of climate risk information, with a focus on rural water, and integration into development frameworks

· Inclusive planning and budgeting for reducing climate related risks at the district and sub-district levels

· Physical investment for reducing climate risks

· The Strengthening Community Resilience to Climate Induced Natural Disasters in the Dili to Ainaro Road Development Corridor project is a joint UNDP-World Bank program addressing the disaster related issues along the Dili-Ainaro road corridor and will showcase what can be done to minimize and prevent the impact of local disasters on large scale infrastructure and communities. The project seeks to reduce the risks that Timor-Leste faces from natural disasters and climate change and help minimize the losses that result to its infrastructure assets and livelihoods. The project’s three goals are to:

· Improve understanding of the natural disaster risks faced by the Dili-Ainaro corridor, and communicate those risks to strengthen evidence based planning and investment

· Develop national and sub-national capacity for managing disaster risks including mainstreaming DRM in national, sub-national and sectoral strategies

· Demonstrate effective risk management practices to make assets and livelihoods more disaster and climate resilient in the Dili-Ainaro corridor
63. The project will address specific barriers and root causes (both direct and indirect) that prevent the improvement of the adaptive capacity of the health sector to climate variation and change in Bangladesh, Cambodia, Lao PDR, Myanmar, Nepal, and Timor-Leste which are described in the Development Challenge section above. The project is designed as a multi-country approach for responding to climate change induced health risks in Asian LDCs, through the pursuit of four outcomes. Within each of these outcomes, the participating countries have defined a tailored set of activities to address country-specific climate health risks. 
64. While country contexts differ, participating countries share similar challenges for addressing climate change health risks.  These have been defined in detailed in the annexes national documents, however common key challenges and barriers can be summarized as 1) Insufficient capacity for climate change adaptation within the relevant government agencies 2) Limited surveillance data inhibiting prevention and response to epidemics 3) Limited ability to prevent and treat climate-sensitive diseases and remain operational during extreme weather events 4) Insufficient regional knowledge sharing and scale up of successful pilot projects. Each country has expressed the need for technical assistance on utilizing the newest methodological approaches, including, but not limited to diagnostic tools, as well as data collection, reporting, and training, to improve country capacity to cope with climate variability and change. 
65. For Outcomes 1-3 stakeholders further elaborated their individual logframes for the proposed LDCF project.  Budgets have been reallocated across Outputs 1-3 to reflect needs and estimated costs of interventions.
Outcome 1: Institutional capacities are strengthened to effectively integrate climate risks and adaptation options in health sector planning and implementation 

66. As participating countries have completed their NAPAs and are getting ready to start their NAP processes, it is critical to achieve the goals of healthy communities and ensure that the health sector is properly represented in this process. In this context, ministries of health in participating countries will be supported to incorporate climate risks and opportunities into national health plans, policies and programs.
67. Climate change and health was perceived by stakeholders as a relatively new area, where support was needed to collect data, document analyses and sensitize decision-makers to the related impacts and the need to mainstream health into adaptation planning.  Related Outputs were common, but specific activities under each Output differed – this is also the case for Outcomes 2 and 3.
	Outcome 1: Institutional Capacities are strengthened to effectively integrate climate risks and adaptation options in health sector planning and implementation

	Country
	Outputs
	Activities

	Bangladesh
	1.1 Integrated health national adaptation plan (H-NAP) is designed/updated to achieve the national health adaptation goals
	1.1.1. Review national health strategy, informed by vulnerability study and mapping of Output 2

	
	1.2 Standard operating procedures developed for managing climate-sensitive health outcomes


	1.2.1 Develop a Memorandum of understanding/SOPs to share information to support an effective early-warning response among the Ministry of Environment and Forest, the Ministry of Health and Family Welfare, the Ministry of Disaster and Relief, DPHE and the Meteorological Department. 

1.2.2 Conduct periodic meeting with the ministries and agencies, as mentioned above, to oversee the coordination and sharing of information among the Ministries.

1.2.3. Strengthen monitoring framework to support SOPs. The monitoring framework will be developed to track the extent of implementation of policy in relation to climate change and health. 

1.2.4. Necessary orientations/trainings will be provided to the health management information system staff of the Directorate General of Health Services.

	
	1.3 Capacity building to support the implementation of standard operating procedures  
	1.3.1. Build capacity of health professionals and multi-sectoral stakeholders through training needs assessments, development and conduct of training modules and courses.

1.3.2
Prepare short courses course curricula to be incorporated into medical education on climate change and health.
1.3.3
Provide technical assistance to the Climate Change and Health Promotion Unit for policy advocacy.

	Cambodia
	1.1 Integrated health national adaptation plan (H-NAP) is designed/updated to achieve the national health adaptation goals
	1.2.1 Expand and strengthen the Climate Change Technical Working Group, review of existing health strategy and plans 

	
	1.2 Standard operating procedures developed for managing climate-sensitive health outcomes
	1.2.1 Building on 1.1.1, update the group’s terms of reference, establishing internal and external communications plans, improving members’ knowledge of relationships between climate change and health, updating and developing budgets and implementation plans for the National Strategy for Climate Change Adaptation and Disaster Risk Reduction, and ensuring all ministries that impact health adaptation activities are members.

	
	1.3 Capacity building to support the implementation of standard operating procedures  
	1.3.1 Conduct a baseline assessment of  the knowledge of Ministry of Health and other key ministry staff at national and provincial levels regarding relationships between climate change and health, and climate-sensitive diseases. Enhance existing WHO training materials based on these findings, to address knowledge and capacity gaps in Ministry of Health and other key ministries.

1.3.2 Support the development of university curricula to incorporate climate change into public health and medical programmes. This may include materials for a “micro-module” in climate change and health that can be incorporated across different disciplines. This unit could also be used for training of various ministry staff in climate change and health as part of Activity 1.3.1.

	Lao PDR


	1.1 Integrated health national adaptation plan (H-NAP) is designed/updated to achieve the national health adaptation goals


	1.1.1: Develop a health-specific national adaptation plan, (H-NAP) including terms of reference (informed by vulnerability assessment of Output 2.1)

1.1.2: Organize a consultation meeting with stakeholders on development of the health-specific national adaptation plan

1.1.3: Organize an advocacy meeting for decision- and policy-makers on development of the health-specific national adaptation plan

	
	1.2 Standard operating procedures developed for managing climate-sensitive health outcomes


	1.2.1: Facilitate coordination between health and other sectors, namely environment, water, transport, agriculture, and meteorology. 
1.2.2: Review and update the memorandum of understanding between various ministries relating to development and sharing of data relating to climate change and health.

1.2.3 Climate-sensitive management and response plans are developed in selected provinces (Savannakhet and Seokong)

	
	1.3 Capacity building to support the implementation of standard operating procedures  
	1.3.1: Develop training and advocacy materials on CC&H risks for healthcare facility workers at ministerial level and managers attend advocacy meetings and training sessions. 
1.3.2: Conduct a community awareness assessment on climate change and health risks, to develop behaviour change communication materials,

1.3.3: Conduct climate change and health risk campaigns in two pilot communities in the selected provinces.

	Myanmar


	1.1 Integrated health national adaptation plan (H-NAP) is designed/updated to achieve the national health adaptation goals
	1.1.1 Establish technical working group for health-specific components of national adaptation plan development

1.1.2 Review of existing relevant documents and consultation meetings to identify entry points

1.1.3 Develop health-specific components of national adaptation plan in consultation with key stakeholders

	
	1.2 Standard operating procedures developed for managing climate-sensitive health outcomes


	1.2.1 Assess existing standard operating procedures and guidelines for control of climate-sensitive diseases, and identify gaps and capacity needs.

1.2.2 Develop standard operating procedures for managing climate-sensitive diseases

	
	1.3 Capacity building to support the implementation of standard operating procedures
	1.3.1 Design and implement state and regional awareness raising, and training-of-trainers courses to support standard operating procedures

	Nepal


	1.1 Integrated health national adaptation plan (H-NAP) is designed/updated to achieve the national health adaptation goals


	1.1.1: Operational research on climate-resilient health systems development for improved natural disaster preparedness health care facilities in five municipalities
1.1.2. Review and update as necessary HNAP informed by 1.1.1

	
	1.2 Standard operating procedures developed for managing climate-sensitive health outcomes


	1.2.1: Expand and strengthen the Climate Change Technical Working Group by updating the group’s terms of reference; establishing internal and external communication plans; improving working group members’, policy-makers’ and programme managers’ knowledge of relationships between climate change and health; and ensuring health is covered in all policies so that the health co-benefits of climate change mitigation and adaption can be augmented.

	
	1.3 Capacity building to support the implementation of standard operating procedures
	1.3.1 Conduct baseline assessment of national and subnational level (regions and districts) Ministry of Health and other key ministries’ staff knowledge of relationships between climate change and health and climate-sensitive diseases and risks. 
1.3.2. Based on the findings of assessment, factsheets and advocacy materials on climate change and health risks for policy-makers and programme managers will be developed, and advocacy meetings and training sessions will be organized. Post-training assessment will also be carried out.

1.3.3: Support the development and operation of a web portal for climate change and health.
1.3.4: Support the development or update of university, academy and training institution curricula to incorporate climate change and health risk management into health and medical sciences academic and training programmes for continued access to training

	Timor-Leste
	1.1 Integrated health national adaptation plan (H-NAP) is designed/updated to achieve the national health adaptation goals


	1.1.1 Develop Timor-Leste’s H-NAP.
1.1.2 Perform costing for the National Strategy for Environmental Health.
1.1.3 Incorporate climate-related risk factors into the diagnosis and treatment guidance for the four highest priority climate-sensitive diseases identified by the national vulnerability and adaptation assessment. This may include respiratory, airborne, waterborne, noncommunicable, or vector-borne diseases.

	
	1.2 Standard operating procedures developed for managing climate-sensitive health outcomes
	1.2.1: Develop a coordination mechanism for information and data sharing between the health sector and other relevant sectors, including environmental, water, agriculture, meteorological, disaster risk reduction, and WASH. Some data is currently shared with the MCIE Adaptation Thematic Working Group but there is no formal mechanism to share new data as they are collected.
1.2.2: Review and update MOU between various ministries relating to development and sharing of CC&H required data and joint planning to address health sector climate risks. 
1.2.3 Build statistical capacity within the MOH to determine the exposure-response relationship between climate and health. Strengthen capacity of MCIE Adaptation Thematic Working Group for data sharing, management, and analysis. This will include training to determine the exposure-response relationship between meteorological factors and climate-sensitive diseases as well as the provision of analysis software and computing equipment as necessary.

	
	1.3 Capacity building to support the implementation of standard operating procedures

 
	1.3.1: Integrate climate change and health into the MOH Environmental Health Working Group.
1.3.2: Develop and deliver training and advocacy materials on climate change and health. 


Outcome 2: Effective decision-making for health interventions is enabled through generation of information and improved surveillance and/or early warning systems

68. Outcome 2 focused on linking available information to support surveillance and early warning systems to inform preparedness and response measures.  Vulnerability assessments to address data gapa and to project health burdens under different scenarios of development and climate change. This will reflect legal, policy and socio-economic barriers for special vulnerable and marginalized populations such as persons with disabilities, the elderly, socially-discriminated, and ethnic minorities. 

	Outcome 2: Effective decision-making for health interventions is enabled through generation of information and improved surveillance and/or early warning systems

	Country
	Outputs
	Activities

	Bangladesh
	2.1. Vulnerability assessment conducted for future health burdens considering development and climate change 


	2.1.1
Conduct a national health vulnerability assessment to inform health policy and plans on climate change risk periodically.

2.1.2. Conduct geographical information system-based risk mapping for climate-sensitive diseases.

	
	2.2. Integrated surveillance system strengthened of climate-sensitive health outcomes 


	2.2.2 Develop guidelines and tools for climate-sensitive surveillance system.

2.2.3 Train health facility personnel in using health emergency plans related to integrated disease surveillance and early-warning systems for dealing with climate change-sensitive diseases.

	
	2.3. Early warning system and response strengthened
	2.3.1 Develop early-warning alert and response systems and upgrade disease surveillance system to include data on climatic variables such as water quality, weather and entomological surveillance to develop models for prediction, prevention and preparedness of epidemic control of selected climate-sensitive diseases in project areas.
2.3.2. Health emergency plans related to integrated surveillance systems and early warning system strengthened for use by the Healthcare facilities for effective health interventions through prevention, control and management of climate-sensitive health risks and diseases such as Zika, malaria, dengue and diarrhoea.

	Cambodia
	2.2. Integrated surveillance system strengthened of climate-sensitive health outcomes 


	2.2.1 Strengthen diarrheal disease surveillance by revising case definitions and eliminating potential duplicate indicators in the health management information system (based on the 10th revision of the International Statistical Classification of Diseases and Related Health Problems), zero reporting system, and maternal and child health surveillance system. 
2.2.2 Adapt existing trainings and train health-care providers on the new case definitions and reporting. 

2.2.3. Improve dengue sentinel surveillance diagnosis and reporting mechanisms, including revising case definitions to include adult cases, to reduce lead time in identifying epidemics and improve capacity for prevention and response. Improving diagnosis may include clinical review of the efficacy and cost-effectiveness of dipsticks for diagnosis for dengue and the electronic dissemination of treatment guidelines in Khmer and English.

2.2.4 Increase the scope of the dengue sentinel surveillance system to include four additional provincial or referral hospitals.

	
	2.3. Early warning system and response strengthened


	2.3.1 Develop dengue early-warning systems based on existing meteorological and surveillance data for dengue in high-incidence provinces to facilitate timely preventive measures and enable better preparedness by health-care facilities. 

2.3.2. Identify and communicate data gaps to relevant Ministries for planning and budgeting 

	Lao PDR
	2.1. Vulnerability assessment conducted for future health burdens considering development and climate change 


	2.1.1 Update the 2010 WHO and Lao Ministry of Health climate change and health vulnerability assessment.
2.1.2 Use the updated vulnerability assessment to inform development of health-specific national adaptation plan (Output 1.1)

	
	2.2. Integrated surveillance system strengthened of climate-sensitive health outcomes 
	2.2.1 Conduct workshop for integrating climate variables into the existing dengue surveillance system

2.2.2 Provide training for surveillance staff and supply new guideline for mosquito surveillance 
2.2.3 Implement mosquito surveillance in selected communities in a district of Savannakhet province, document progress for upscaling

	
	2.3. Early warning system and response strengthened


	2.3.1 Conduct a feasibility/needs assessment for developing a climate change and health database, including the capacity for an early-warning system
2.3.2 Utilize results and findings of the feasibility and needs assessment to inform health-specific adaptation plan (Output 1.1) and to establish early warning systems.  

2.3.3. Identify gaps and inform relevant Ministries to guide policies, awareness raising materials to support SOPs (Output 1) to detail implementation processes and resource mobilization activities.

	Myanmar
	2.1. Vulnerability assessment conducted for future health burdens considering development and climate change 
	2.1.1 Assess vulnerability of climate change-sensitive diseases and prioritize areas to inform surveillance and early warning system



	
	2.2. Integrated surveillance system strengthened of climate-sensitive health outcomes 
	2.2.2 Review existing disease surveillance system and integrate surveillance of climate-sensitive diseases and new emerging diseases into system
2.2.3 Develop guidelines and materials for integrated disease surveillance system
2.2.4 Train health staff on integrated disease surveillance system at subnational level

	
	2.3. Early warning system and response strengthened


	2.3.1 Assess existing early-warning alert and response system ensuring timely intervention and upgrade reporting and coordination mechanism as necessary
2.3.2 Develop guidelines for early-warning alert and response system and emergency health actions
2.3.3 Train health staff on emergency health actions after disasters and early-warning alert and response system

	Nepal
	2.1. Vulnerability assessment conducted for future health burdens considering development and climate change 


	2.1.1. Vulnerability assessments as necessary for climate-sensitive diseases and risks (scrub typhus, chikungunya fever and Zika). 

2.1.2. Policy and strategy suggestions for prevention, control and management 

	
	2.2. Integrated surveillance system strengthened of climate-sensitive health outcomes 
	2.2.1 Update disease surveillance systems integrating climatic variables, water quality and entomological surveillance data into the early-warning alert and response system for developing models for prediction, prevention and preparedness of epidemic control of selected climate-sensitive diseases in selected districts.

	Timor-Leste
	2.1. Vulnerability assessment conducted for future health burdens considering development and climate change 


	2.1.1 Perform a national V&A assessment of the health risks of climate change. The assessment will build on the existing vulnerability assessments performed in the agriculture, infrastructure, and natural disaster sectors, and will include maps of vulnerability to climate-sensitive health risks.
2.1.2 Perform district-level V&A assessments in the five most vulnerable districts identified by the national V&A.

	
	2.2. Integrated surveillance system strengthened of climate-sensitive health outcomes 
	2.2.1 Strengthen regional and national laboratory capacity to perform water quality testing.
2.2.3 Strengthen regional and national laboratory and healthcare facility capacity to diagnose waterborne, vector-borne, and non-communicable climate sensitive diseases.

	
	2.3. Early warning system and response strengthened 
	2.3.1: Identify top four priority diseases in the national V&A assessment and study the feasibility of an EWS for each disease.
2.3.2: Disseminate findings to stakeholders, including the Ministry of Health and coordinate future interventions.


Outcome 3: Climate resilience is enhanced in health service delivery
69. Currently, climate-sensitive disease’s plans and programmes and emergency preparedness and response plans for public health and disaster management do not include consideration of climate change. Demonstrating effective health adaptation requires substantial improvements to existing health delivery systems. Under this outcome, specific health outcome control programs will be strengthened and emergency preparedness and management will be improved. Further, interventions will also involve (where appropriate) climate-proofing of existing health care facilities, particularly those that are located in remote or vulnerable communities. Efforts will also be done to enhance coordination at the institutional level to ensure that the health sector maximizes synergies and promotes health co-benefits across health-determining sectors such as disaster risk management, energy, agriculture, housing, and water.
	Outcome 3: Climate resilience is enhanced in health service delivery

	Country
	Outputs
	Activities

	Bangladesh
	3.1 Health care infrastructure strengthened to the impacts of climate change
	3.1.1 Prepare plans for developing climate-resilient health-care centres (Green Hospitals) in project areas addressing water, sanitation and hygiene, Comprehensive Disaster Management Programme (CDMP) and solar energy requirements related to climate change.

3.1.2 Pilot implementation in three green health centres, incorporating new policies and procedures related to safe water, sanitation, hygiene, cleanliness, medical waste management and solar power.

3.1.3 Revise and update emergency risk management and response protocol.



	
	3.2 Capacity of health personnel improved to identify and treat to climate-sensitive health issues
	3.2.1: Revise, update or develop an emergency risk management and treatment protocol to incorporate climate change and health.

3.2.2: Develop professional capacity among health-care services providers to address the adverse impacts of climate variability. Short courses will be developed on risk management and training of trainers carried out. A number of short courses will be piloted at the national level and in the project areas.



	Cambodia


	3.1 Health care infrastructure strengthened to the impacts of climate change
	3.1.1 Pilot climate-proofing community water, sanitation and hygiene infrastructure in Ratanakiri, using rural water safety plans to prepare for flood, drought, increased pathogen load, and increased mosquito breeding in water collection and storage containers. Improve infrastructure as identified in safety plans to protect against climate-sensitive waterborne diseases and extreme weather events. 

3.1.2. Promote vector control for water collection and storage as necessary, using guppy fish and education to protect against climate-sensitive vector-borne diseases. Document and share pilot results to inform future scale-up. This activity will build on the recently completed WHO regional water safety planning project. Following the completion of the project, the Cambodian government has adopted a Water and Sanitation for Health Sector Strategic Plan and National Action Plan including guidelines and training manuals.

3.1.3 Assess and report on climate resilience of health-care facility infrastructure in Ratanakiri. Build on the rural water safety planning process to pilot improving water, sanitation and hygiene infrastructure in health-care facilities to ensure continued functionality during and after floods and droughts and resilience to climate-sensitive diseases. Document and share pilot results to inform future scale-up.

	
	3.2 Capacity of health personnel improved to identify and treat to climate-sensitive health issues
	3.2.1 Improve community and health-care provider knowledge of the prevention, recognition and management of climate-sensitive health risks associated with food-, water- and vector-borne diseases. 

	
	3.3 Climate-sensitive disease control/water programmes strengthened
	3.3.1. Conduct a behaviour change communication campaign in Ratanakiri that can serve as a model for scale-up in other provinces. Nationally, the project will develop a section of the Ministry of Health website to post the existing diagnosis and treatment guidelines for climate-sensitive diseases in Cambodia in Khmer and English.

	Lao PDR


	3.1 Health care infrastructure strengthened to the impacts of climate change
	3.1.1 Develop a climate-resilience water safety plan for two selected provinces (Savannakhet and Seokong); by adapting WHO guidance on climate-resilience water safety plan and providing training for provincial water supply team.

3.1.2 Review and finalize the drafted disaster risk management plan by conducting stakeholder and technical consultation/working group meetings.

3.1.3 Support implementation of climate-proofing of hospitals within selected provinces using WASH FIT and the Green Hospital Initiative by providing training, and developing monitoring methods through technical assistance.



	
	3.2 Capacity of health personnel improved to identify and treat to climate-sensitive health issues
	3.2.1 Adapt WHO training manual on climate change and health and conduct training of trainers with representatives from 17 provinces and the capital Vientiane.



	Myanmar


	3.2 Capacity of health personnel improved to identify and treat to climate-sensitive health issues


	3.2.1 Train basic health staff on initial management of heat-related disorders

3.2.2 Train hospital staff on clinical management of health-related disorders

	
	3.3 Climate-sensitive disease control/water programmes strengthened
	3.3.1 Prevention training for heat-related disorders in agricultural and industrial workers

3.3.2 Improve vector-borne disease control programmes, ensuring effective response for disasters and health impacts of climate change

3.3.3 Climate-resilient water safety plans in vulnerable townships

3.3.4 Assess nutritional status and identify most vulnerable states and regions to climate related impacts to nutrition

3.3.5 Develop and implement nutritional programmes in most vulnerable states and regions

3.3.6 Carry out integrated assessments of ambient air quality, climate change and related diseases patterns

3.3.7 Carry out water scarcity and health impact study in dry zone area

3.3.8 Implement climate-resilient water safety plans in vulnerable townships

3.3.9 Conduct advocacy meeting of decision-makers for climate-resilient infrastructure in vulnerable areas and communities

3.3.10 Develop information, education and communication materials for stakeholders and community within and outside health sector

3.3.11 Raise awareness among community, including schools on health impacts due to climate change 



	Nepal


	3.1 Health care infrastructure strengthened to the impacts of climate change
	3.1.1: Assess climate resilience of health facilities in different ecological regions.

3.1.2: Climate-proofing of health facilities piloted based on national guideline, in selected Terai, (lowland), hill and mountain regions

	
	3.2 Capacity of health personnel improved to identify and treat to climate-sensitive health issues 


	3.2.1: Orientation to health management personnel on climate resilient water safety plans.

3.2.2 Conduct training on climate change and health, including prevention, control, management and surveillance of climate-sensitive diseases and risks to health personnel in pilot districts.

	
	3.3. Climate-sensitive disease control/water programmes strengthened
	3.3.1: Implement climate-resilient water safety plans in selected districts of the Terai (lowland), hill and mountain regions.

	Timor-Leste


	3.1 Health care infrastructure strengthened to the impacts of climate change


	3.1.1: Assess the resilience of health facilities to extreme climate events such as floods, landsides, and droughts.

3.1.2: Create disaster management and response plans for health facilities.

3.1.3: Develop climate resilient health care facility standards for adequate water, sanitation, and waste management. 

3.1.4: Pilot climate-proofing improvements in the assessed facilities.



	
	3.2 Capacity of health personnel improved to identify and treat to climate-sensitive health issues 


	3.3.2: Train healthcare workers in five pilot municipalities identified as vulnerable in the national V&A assessment (Output 2.1)



	
	3.3 Climate-sensitive disease control/water programmes strengthened


	3.2.1: Incorporate climate-resilience into existing water safety plan materials. 

3.2.2: Build on the previous WSP project in Aileu, Dili, Liquica, Oecusse, and Manatuto to strengthen the capacity of local authority and water user committees to protecting water quality and availability from climate change impact. 

3.3.3: Pilot climate-proofing improvements in water supply in the pilot municipalities.3.3.1: Incorporate climate change adaptation into existing program materials  (e.g. Saude na Familia and SISCa programs)

3.3.3: Pilot disease prevention measures at the community level to promote prevention and treatment of climate sensitive diseases.


Outcome 4.1: Enhanced regional cooperation and knowledge exchange for promoting scale-up and replication of interventions (to be directly implemented by WHO)

70. This Outcome aims to address technical gaps for implementation of health adaptation to climate change at country level as well as knowledge management at the regional-level. The regional approach proposed allows for learning and exchange of lessons between countries which will explicitly be promoted as one of the project’s outcomes. Economies of scale will be considered as well as the avoidance of duplication in terms of the technical support provided, ensuring the most cost-effective solutions. 

	Outcome 4.1: Enhanced regional cooperation and knowledge exchange for promoting scale-up and replication of interventions (to be directly implemented by WHO)




	Outcome
	Outputs
	Activities

	Outcome 4.1: Enhanced regional cooperation and knowledge exchange for promoting scale-up and replication of interventions


	Regional experiences synthesized and shared among countries in the region and across different regions. 
	4.1.1 Definition of normative aspects related to climate-resilient health systems by developing regional-level guidelines, manuals, and other relevant technical documents (e.g. climate-resilient health care facilities (CR-HCFs) and climate resilient Water Safety Plans (CR-WSPs)), as required by countries;
4.1.2 Regional capacity-building events for different topics (on policy, science and implementation of interventions) and conferences;
4.1.3 Systematization of regional experiences and promotion of North-South and South-South cooperation and knowledge exchange (which may include virtual communities of practice and platforms)


Outcome 4.2: HNAP are effectively integrated into ongoing NAP processes (Implemented by UNDP)

71. Through this Outcome, UNDP will provide technical assistance to governments of the participating countries to effectively embed the H-NAP process (under Outcome 1) with the ongoing NAP processes in the countries. Specifically, support will focus on data collection and analyses to support technical officers and decision-makers to better quantify needs and costs related to climate change and health planning.  This will inform annual planning and budgeting processes to support adequate resource mobilization from public or other resources.  Activities will build on the support provided by the UNDP/LDCF Assisting LDCs with country-driven processes to advance National Adaptation Plans (NAPs) project as well as the UNDP/USAID Capacity Building Programme on the Economics of Climate Change Adaptation (ECCA).  The NAPs support project provided technical assistance to countries in advancing their NAP processes through per the LEG guidelines tailored to the country context. The ECCA programme provides technical training on economic analyses to build capacity of decision-makers on climate-informed and economically-efficient planning.  ECCA is now in its second phase; a course has been developed and is available through the Asian Institute of Technology (AIT).  Existing materials, tailored as needed to incorporate health, will be used to provide needed support to countries through in-country training and remote support.  Products from this Outcome will be shared with participating countries for knowledge exchange.

	Outcome 4.2: HNAP are effectively integrated into ongoing NAP processes 
(Implemented by UNDP)



	Outcome
	Outputs
	Activities

	Outcome 4.2: HNAP are effectively integrated into ongoing NAP processes (Implemented by UNDP)

	Enhanced technical capacity of MOH in understanding adaptation planning into budgeting.


	4.2.1 Training and technical support for MOHs to conduct economic analyses to inform integration of health into adaptation planning and budgeting.

4.2.2 Training and tech support for designing/developing bankable projects to secure public or other finance




72. Adaptation interventions promoted by the project will be mainstreamed into main policy instruments and legislative platforms to enable project results to be sustained beyond the lifetime of the project. Sustainability has been built into the project approach by emphasizing institutional and individual capacity development.
73. The focus on improved planning and decision-making on climate change and health as well as strengthened information management for adaptation will strengthen each countries capacity to plan for and implement health adaptation to climate change in the medium- to long-term. These outcomes thus inherently contribute to sustainability of project activities by mainstreaming climate change adaptation – including practical measures implemented in this project. The creation or updating of H-NAPS and integrating with the over-arching NAPs will ensure it is embedded within national policies, strategies and plans on an ongoing basis.

74. To support sustainability, the project design relies on the following elements which are included within the corresponding Outcomes:
· A commitment to long-term planning at all levels, from strategies (such as promotion of inter-sectoral decision-making through inter-sectoral fora), to policies (such as the development of the health component of National Adaptation Plans (H-NAPs)), to specific measures (such as pre-defined action plans for dealing with outbreaks of water-borne disease);

· Inclusion into budgetary allocations to establish continuous improvement and training;

· Institutionalizing knowledge through development and maintenance of best practice learning detailed in guidelines and operational procedures;

· Embedding and maintaining automated collection of comprehensive surveillance information, correlating climatic data to bench marks and institutional metrics;

· Building of multi-sectoral teams, to allow climate-change adaptation to be integrated into planning in a wide range of sectors; 

· Mainstreaming within the health community the connections of climate change and health within national medical/nurse universities and community awareness training programmes will support long term sustainability;

· Creation of standing Technical Working Groups within each country that will have sufficient capacity to advocate and focus cross sector coordination that will enhance the health-specific component of the national adaptation plan processes;

· Explicit consideration of costs and benefits, with endorsement of strategies, policies and measures only if they can be expected to provide overall net benefits to health, and sustainable development; 

· Commitment to continuous monitoring and regular evaluation of interventions over time; and 

· Inclusion of fund-raising amongst national and international agencies and donors as a core activity. 

75. Project resources will be used to systematically capture, analyze and disseminate experience and best practices, from early stages of engagement and policy-related work. Consequently, the investments in this project will help scale up this nationwide approach for regional benefits.
76. The project builds on developing or further developing a policy and institutional framework for building health resilience to climate change.  There is strong commitment from Governments to integrate health management policies and capacities to effectively adapt to climate change across cross-sectoral programmes. 
77. The project strategy and outputs will have long term impacts – for instance, through the national H-NAP the integration of climate change adaptation into national and local health planning and governance practices, including sharing of climate data to support integrated health care approaches.  Focus on enhancing the capacity of surveillance and early warning systems will all make major contributions towards enduring impacts that extend well beyond the project lifetime.

78. Regional South-to-South coordination to ensure sharing of resilient health actions, policies and plans through lessons learned will ultimately build capacity for each country to strengthen and facilitate the integration of dealing with cross-cutting issues within the respective government’s decision-making processes and development policies, plans and programmes. This is being done to ensure that issues such as Climate Change, Health, Environment, Disaster, Gender and Poverty and their opportunities are adequately integrated into the mainstream development process. Furthermore, the South to South collaboration on health is aimed to raise awareness around and build capacity in mainstreaming across sector and government agencies, particularly at the local levels. For example, enhanced surveillance and early warning systems will be developed by the project and the related lessons learned will be adopted and applied to future phases of health care adaptation to climate change. Guidelines and SOPs will be developed and shared between the participants to better understand and institutionalize the approaches used.
79. The total cost of the project is US$36,061,600.  This is financed through a GEF - LDCF grant of US$9,000,000 and co-financing of US$27,061,600.  UNDP, as the GEF Implementing Agency, is responsible for the execution of the GEF resources and the cash co-financing transferred to UNDP bank account only.   

	Country
	Co-financing source
	Co-financing type
	Co-financing amount
	Description
	Risks
	Risk Mitigation Measures

	Bangladesh
	Ministry of Health and Family Welfare, Government of Bangladesh


	In kind/Grant
	US$5,300,000
	In-kind, Bangladesh Climate Change Trust-funded Adaptation Research project, telecommunications, other administration, enhancement of capacity of key policy-makers and programme managers, model health facilities and diseases, Climate-resilient water safety plan implementation 
	Low
	Project Board Oversight to secure resources with Regional Project Manager (Review at Project Inception and at Mid-term)

	
	WHO CO
	In Kind/Grant
	US$700,000
	In-kind and grant co-financing related to activities on water surveillance, water safety plans and other capacity building activities. 
	Low
	Project Board Oversight to secure resources with Regional Project Manager (Review at Project Inception and at Mid-term)

	Cambodia
	MOH - Department of Preventative Medicine
	Grant
	US$2,500,000
	$1,500,000 - Cambodia Climate Change Alliance (CCCA) and ADB’s Strengthening Resilience to Climate Change in the Health Sector in the Greater Mekong Sub-region

$1,000,000 – malaria and dengue control programmes under the Ministry of the Health’s National Center for Parasitology, Entomology and Malaria Control (CNM)
	Low
	Project Board Oversight to secure resources with Regional Project Manager (Review at Project Inception and at Mid-term)

	Lao PDR
	Lao Government (MOH)
	In Kind
	US$2,385,200
	In kind support related to Minisry of Health and National Center for Environment and Water

	Low
	Project Board Oversight to secure resources with Regional Project Manager (Review at Project Inception and at Mid-term)

	
	WHO CO
	In Kind
	US$1,036,400
	Activity budget for strengthening national emergency response, disaster management, dengue surveillance and WASH capacity in the country
	Low
	Project Board Oversight to secure resources with Regional Project Manager (Review at Project Inception and at Mid-term)

	Myanmar
	Government 
	In Kind
	US$3,000,000
	In Kind support from the Ministry of Health and Sports
	Low
	Project Board Oversight to secure resources with Regional Project Manager (Review at Project Inception and at Mid-term)

	Nepal
	Government - MOH
	In Kind
	US$3,300,000
	In kind support related to enhancement of capacity of key policymakers and program managers, integration of H-NAP in NAP process, Climate resilient health service delivery, establishment of model health facilities and diseases surveillance 
	Low
	Project Board Oversight to secure resources with Regional Project Manager (Review at Project Inception and at Mid-term)

	
	WHO CO
	In Kind/Grant
	US$700,000
	In kind support related to integration of H-NAP in NAP process, enhancement of capacity of key policymakers and program managers, climate resilient water safety plans implementation and support for integrated diseases surveillance as per international health regulation 
	Low
	Project Board Oversight to secure resources with Regional Project Manager (Review at Project Inception and at Mid-term)

	Timor-Leste
	Ministério da Saúde
	In Kind
	US$1,500,000
	Government in kind contribution related to staff time and related equipment
	Low
	Project Board Oversight to secure resources with Regional Project Manager (Review at Project Inception and at Mid-term)

	
	WHO CO
	In Kind/Grant
	US$240,000
	Activity budget related to water safety plans, climate change and health programmes, medical waste management, and  dengue control
	Low
	Project Board Oversight to secure resources with Regional Project Manager (Review at Project Inception and at Mid-term)

	Regional 
	WHO
	Grant
	US$6,400,000
	Grants from climate change and health  projects that WHO is coordinating within the sub-regions and countries participating in this project. This includes surveillance systems for climate-sensitive diseases, such as malaria, dengue, malnutrition, and diarrhoeal diseases, and staff costs.
	Low
	Project Board Oversight to secure resources with Regional Project Manager (Review at Project Inception and at Mid-term)


80. Through close consultation with stakeholders and development partners, the project will ensure collaboration with ongoing and in-development projects at the national and regional levels.  These include the climate change and health related projects and NAPs support projects included in the baseline section, as well as new partnerships currently being explored.  For instance, UNDP has recently submitted a proposal (US$3million) on behalf of the Government of Bangladesh to the GCF for consideration, the US$3million proposal is to support the NAP process.  This project is expected to be approved in 2018.  Further, UNDP has begun discussions with the Global Fund’s Regional Artemisinin-resistance Initiative (RAI), launched in 2013 in response to the emergence of drug-resistant malaria in the Greater Mekong region.  This programme has recently been expanded with a second phase (US$242million) addressing case management through health volunteers and surveillance systems, specifically related to malaria.  Collaboration will ensure complementarity and maximization of combined resources for common countries, namely Cambodia, Myanmar and Lao PDR.

A.2. Child Project?  If this is a child project under a program, describe how the components contribute to the overall program impact.  

N/A
A.3.  Stakeholders. Identify key stakeholders and elaborate on how the key stakeholders engagement is incorporated in the preparation and implementation of the project.  Do they include civil society organizations (yes X /no FORMCHECKBOX 
)? and indigenous peoples (yes X /no FORMCHECKBOX 
)? 

81.      Continued engagement with stakeholders is a key element of this proposal, from project inception, through prioritization, development and implementation of activities, to evaluation, communication and feedback. While the stakeholders engaged in the project and their nature of involvement varies somewhat country to country, there are common themes across countries. Active engagement with groups that represent more vulnerable segments of the population is a priority, for example, with a focus especially on engaging women, as proposers of activities and as participants in project activities, and in monitoring and evaluation. This is done with a view to capitalize on the skills and knowledge of women and to build capacity for responding to climate change among women, as well as to ensure that existing gender inequalities are not exacerbated.
82. The stakeholder engagement process has so far included a multinational inception workshop, in-country consultations and follow-up interactions to define each country’s climate change challenges, capacity building gaps and barriers, project activities, and potential risks. These extensive bilateral consultations have involved central government agencies, nongovernment organizations, and relevant development partners, with additional relevant stakeholders identified in the process. The project will continue to engage with stakeholders through the governance structures put in place by the project, and through existing structures at national and subnational levels, including national departments and agencies, and provincial and community-level governance structures and organizations.
83. WHO is the Implementing Partner for the project in each country, UNDP will directly implement Outcome 4.2. WHO will engage the Ministries of Health as Responsible Parties for Outputs 1-3. The active engagement of the Ministry under a broader regional project ensures knowledge sharing across participating countries and supports the upscaling and replication of efforts.
	Country
	Stakeholder
	Relevant roles
	Outcomes

	Bangladesh
	1. Ministry of Health and Family Welfare + DGHS
	Responsible party for the project.  Working in collaboration with other agencies and to develop the strategy for mainstreaming and incorporation of the H-NAP into the national health policy 

Monitoring and implementation of the H-NAP with advocacy for resource allocation in climate vulnerable area in terms of medication and water supply intervention. 

Develop capacity of health workers in various subjects as outlined in the proposal
	Outcomes 1, 2, 3,4

	
	2. Ministry of Environment and Forest + DOE
	Technical support and coordination as focal ministry for climate change
	Outcome 4

	
	3. Department of Public Health Engineering of Ministry of Local Government and Rural Development DPHE
	DPHE to assist in the improvement of WASH in health care facilities. Standard operating procedures for water safety plan and sanitation 
	Outcome 3

	
	5. WHO
	Responsible for the implementation and management of the project; 

WHO to monitor implementation and to provide technical support
	Outcomes 1,2,3 

Outcome 4

	
	6. Institute of Epidemiology, Disease Control and Research IEDCR
	IEDCR and BCAS to support in developing and strengthening the climate-sensitive diseases surveillance system 
	Outcomes 2, 3

	
	7. Bangladesh Centre for Advance Studies BCAS
	CSO active on adaptation to climate change; they will provide technical support and knowledge of which stakeholders to engage
	Outcomes 1,2,3 

	
	8. Communities, including local government institutes
	Communities engaged in vulnerability assessments and to the extent possible in project implementation
	Outcomes 1,2,3 

	Cambodia
	1. Ministry of Health MOH
	Evaluation and identification of health care infrastructure needs and capacity of health personnel
	Outcome 1

	
	2. Preventive Medicine Department, MOH
	Developing of H-NAP, strategy for climate change and health, and strengthening of inter-sectoral coordination and data/information sharing among agencies.  Provide overall coordination, implementation and management of projects related to waterborne diseases, respiratory diseases and other climate-sensitive diseases including emergency preparedness and response
	Outcomes 1, 2, 3,4

	
	3. Communicable Disease Control Department, MOH
	Provides coordination, management and surveillance of projects related to waterborne diseases, respiratory diseases and climate-sensitive diseases.
	Outcome 2

	
	4. National Center for Parasitology, Entomology and Malaria Control, MOH
	Strengthening national institutional capacity, support for sustainability of the project such as development of training program for healthcare workers; and surveillance, control and prevention of vector borne diseases.
	Outcome 2

	
	5. National Institute of Public Health, MOH
	Strengthening of laboratory capacity 
	Outcome 2

	
	6. Department of Planning, MOH
	Coordination of Disaster Management Program and health systems
	Outcome 3

	
	7. Ministry of Environment
	Provide guidance on development of national action plan and strategy including advocacy support
	Outcome 1

	
	8. Ministry of Education
	Promoting health education and raising awareness on climate change resilience and adaptation to climate sensitive health outcomes among school children and parents
	Outcome 1

	
	9. Ministry of Water Resources and Meteorology
	Provide climatic data and information for early warning system development and analysis
	Outcomes 1, 2

	
	10. Non-governmental local and international organizations and community representatives
	Promoting public education and raising awareness on climate change resilience and adaptation to climate sensitive health outcomes
	Outcomes 1,2,3 



	
	11. Selected provincial health departments
	Implementation of surveillance system and capacity building in diagnostic, case management, prevention and public education of climate-sensitive diseases
	Outcomes 2,3

	
	12. WHO
	Responsible for the implementation and management of the project; 

WHO to monitor implementation and to provide technical support

Direct implementation of output 4.1.
	Outcomes 1,2,3 


	
	13.  Communities
	Communities engaged in vulnerability assessments and to the extent possible in project implementation
	Outcomes 1,2,3 

	Lao PDR
	1. Ministry of Natural Resource and Environment, Ministry of Health
	Developing H-NAP, strategy for climate change and health, and strengthening inter-sectoral coordination
	Outcomes 1,2,3,4

	
	2. National Center for Environmental health and Water Supply
	Strengthening national institutional capacity, long term support for sustainability of the project such as development of training program for public health and healthcare workers, and control and prevention of waterborne diseases
	Outcomes 1,2,3 

	
	3. Selected 2 provincial health departments, district health offices, provincial centers for environmental health and water supply
	Strengthening local early warning system, and integrated surveillance
	Outcomes 2,3

	
	4. Provincial hospitals
	Developing climate-sensitive health management and response plans and introducing Green Hospital Initiatives
	Outcome 3

	
	5. Non-governmental local and international organizations and community representatives
	Raising awareness on climate change resilience and adaptation to climate sensitive health outcomes
	Outcomes 1,2,3 

	
	6.  Communities
	Communities engaged in vulnerability assessments and to the extent possible in project implementation
	Outcomes 1,2,3 

	
	7. WHO
	Responsible for the implementation and management of the project; 

WHO to monitor implementation and to provide technical support

Direct implementation of output 4.1.
	Outcomes 1,2,3 



	Myanmar
	1 Ministry of Health
	Responsible party for the project, cooperate and collaborate with other Ministries
	Outcomes 1,2,3,4

	
	2 Ministry of Environmental Conservation and Forestry
	GEF country focal Ministry
	Outcome 1

	
	3 Ministry of Transport, Department of Meteorology
	Monitoring agency for the weather forecast and climate model
	Outcomes 1,2

	
	4 Department of Rural Development  
	Responsible Agency for rural water supply to reduce the water scarcity
	Outcome 3

	
	5 City Development Committee
	Agency for Urban Water supply
	Outcome 3

	
	6 Ministry of Agricultural and Irrigation
	Responsible agency for food security
	Outcome 1

	
	7 WHO  
	Responsible for the implementation and management of the project; 

WHO to monitor implementation and to provide technical support
	Outcomes 1,2,3 

	
	8 Communities
	Communities engaged in vulnerability assessments and to the extent possible in project implementation
	Outcomes 1,2,3 

	Nepal
	1 Ministry of Health and Population MoHP
	Responsible Party for the project, lead ministry on health in Nepal


	Outcomes 1,2,3,4

	
	2 Ministry of Urban Development MUD
	Government agency to implement some of the activities related to WASH
	Outcome 2

	
	3 Ministry of Science technology and Environment MoSTE
	For technical support and coordination as focal ministry for climate change
	Outcomes 1,2

	
	4 Research institutions/Academia 
	For capacity building and research activities
	Outcome 1,2

	
	5 NGOs, Civil Society organizations
	Partnership with government agencies for awareness programs and implementation of adaptation activities at the local level
	Outcomes 2,3

	
	6 Communities
	Communities engaged in vulnerability assessments and to the extent possible in project implementation
	Outcomes 1,2,3 

	
	7. WHO
	Responsible for the implementation and management of the project; 

WHO to monitor implementation and to provide technical support

Direct implementation of output 4.1.
	Outcomes 1,2,3 

	Timor-Leste
	1 Ministry of Health
	Lead ministry on health, responsible party for the project
	Outcomes 1,2,3,4  

	
	2 WHO
	Responsible for the implementation and management of the project; 

WHO to monitor implementation and to provide technical support

Direct implementation of output 4.1.
	Outcomes 1,2,3 Outcome 4

	
	3 Ministry of Education
	Implements relevant climate change adaptation activities 
	Outcomes 1, 2

	
	4 Secretary of State of Environment, Ministry of Economic & Development
	Involved in the advocacy and coordination
	Outcome 2

	
	5 Directorate of Meteorology, Ministry of Communication, Telecommunication & Transport
	Involved in coordination and implementation, providing data and information on climate and weather forecast.
	Outcomes 1,2

	
	6 Directorate of Water & Sanitation, Ministry of Infrastructure
	 Implements the water safety plans
	Outcome 3

	
	7 National NGOs NGO Forum, NGO Haburas, etc, 
	 May be engaged for pilot work under the project
	Outcome 3

	
	8 Member of parliaments, local authorities, religious groups and civil societies
	 Provide oversight and support for the local projects
	Outcomes 1,2,3 

	
	9 Communities
	Communities engaged in vulnerability assessments and to the extent possible in project implementation
	Outcomes 1,2,3 


A.4. Gender Equality and Women's Empowerment. Elaborate on how gender equality and women’s empowerment issues are mainstreamed into the project implementation and monitoring, taking into account the differences, needs, roles and priorities of women and men.  In addition, 1) did the project conduct a gender analysis during project preparation (yes X /no FORMCHECKBOX 
)?; 2) did the project incorporate a gender responsive project results framework, including sex-disaggregated indicators (yes X/no FORMCHECKBOX 
)?; and 3) what is the share of women and men direct beneficiaries (women 50%, men  50%)? 

84.   This project aligns with GEF policies on gender mainstreaming; the activities require the full participation of local community and local stakeholders throughout the project, including its development and implementation, and that this is also where the benefits will be realized. The project ensures local women’s participation in particular throughout the project cycle, including in the development of this proposal, which aligns with the UN’s System Wide Action Plan (UN-SWAP) where women’s empowerment is expected to be included in each of the following areas: accountability, results based management, oversight, human and financial resources, capacity, and coherence, knowledge and information management. Many of the activities involved in this project attend to the delivery of basic services to communities as a foundation for building broad level resilience to climate change. This aligns with Outcome 3 of the UNDP Strategic Plan (2014-2017) (Countries have strengthened institutions to progressively deliver universal access to basic services). The focus on inclusive and more sustainable economic development aligns with Outcome 1 (Growth is inclusive and sustainable, incorporating productive capacities that create employment and livelihoods for the poor and excluded), the local input from women and women’s groups aligns with Outcome 2 (Citizen expectations for voice, development, the rule of law and accountability are met by stronger systems of democratic governance). Ensuring women’s participation, access to services and inclusive economic development will promote gender equality, aligned with Outcome 4 (Faster progress is achieved in reducing gender inequality and promoting women’s empowerment).

85. The project recognises that gender affects vulnerability to climate-related diseases and intersects with and enhances adverse outcomes for people in other marginalised or especially exposed groups. This project will thus be designed with a strong emphasis on benefiting marginalized, excluded, and vulnerable community groups. It will ensure that vulnerability assessments take into account social and gender vulnerabilities, such as stigma, discrimination, and regulatory and legal barriers, which make certain populations particularly vulnerable to climate change and deter them from seeking relevant health services. Awareness campaigns will be designed to reach out to marginalized communities and most vulnerable groups such as women, youth, elderly and people with disabilities, enabling their engagement in discussions and decision-making. Further, particular attention will be given to ensure that the creation of national health standards and guidelines (component 1) consider the most vulnerable and excluded groups.

86. For example, in Bangladesh it is observed that women and children are more likely to be impacted during floods and cyclones in vulnerable coastal regions, be affected by diarrhoea and malnutrition, and to suffer psychosocial distress due to displacement following disaster. Bangladesh specifically aims in their Climate Strange Strategy and Action Plan (2009) to increase the resilience of women and other vulnerable groups to climate change through community level adaptation. Similarly, community level adaptation to diversify livelihoods and improve basic services and social protection is aimed primarily at women. In Bangladesh women are not only more vulnerable to climate-sensitive health risks than men, they are also more likely to carry the burden of healthcare for their families, and improved access to healthcare for women is a national priority. The projects within the program will promote active participation among women including gender-based stakeholder engagement, while monitoring and evaluation will include sex disaggregation. 

87. In Cambodia, women are more vulnerable to climate-sensitive health risks because of lower literacy, lower wages, and fewer assets including smaller land holdings. Woman are also more likely to be responsible for water collection and treatment. WASH interventions in Cambodia under this proposal are to be specifically implemented in a participatory manner, and the perspectives of women and girls will be included in key decisions on resource allocation, planning and monitoring. Data will be disaggregated by sex to ensure that the effects on women specifically can be considered. Women’s representatives are included in all stages of the project, including in final review.

88. In Lao, improving public health services, especially for women, is embedded in the Constitution. Women in Lao are closely linked to the agriculture industry and hold much of the responsibility for family nutrition, food and water security. They are also vulnerable to malnutrition, especially anaemia, and are sensitive to changes to nutrition brought about by drought and flooding. Engaging women in activities that improve food security through improved land use practices is thus a priority in Lao. The MoH works with Lao Women’s Union representatives in villages to improve WASH facilities and behaviors.

89. Women in Myanmar are vulnerable to poor health from malnutrition and diarrhoeal disease arising from food insecurity, limited clean water and poor sanitation. Improving the education of women and girls and increasing workforce participation in professional occupations are key priorities to reduce gender inequalities. Activities in Myanmar includes implementing climate change awareness campaigns on climate change aimed specifically at reaching women and other more vulnerable groups and specifically targets inclusive economic growth in their Framework for Economic and Social Reform. 
90. Undernutrition is also a concern for women in Nepal, and it is observed that women and children are at increased risk during disaster. Increasingly uncertain rainfall affects women and girls more as they are responsible for water collection, and have to walk further to find water when rainfall is low. Improving water security would thus have a particularly beneficial impact on women and girls in Nepal. Women and other vulnerable population groups are also expected to especially benefit from the implementation of early warning systems for climate-related extreme events.  Nepal has specifically targeted women stakeholders in their consultation process for this proposal, and monitoring and evaluation will seek women’s as well as men’s perspectives.
91. In Timor-Leste, women are at significant risk of malnutrition from declining food availability relating to climate, and the National Nutrition Strategy aims specifically to address this. Women are also more vulnerable, to vector-borne disease and to household air pollution.  Similarly to elsewhere, gender intersects with other markers of vulnerability such as poverty in particular, and women are also more likely than me to be poor. This project includes an emphasis on gender-based stakeholder engagement in Timor and participation in local activities to improve resilience to climate change. The National Nutrition Strategy, a key activity in building population resilience, focuses on women and their very young children.

A.5 Risk. Elaborate on indicated risks, including climate change, potential social and environmental risks that might prevent the project objectives from being achieved, and, if possible, the proposed measures that address these risks at the time of project implementation.(table format acceptable):
92. The UNDP environmental and social safeguard requirements have been followed in the development of this GEF/LDCF-financed project. During the project development stage, UNDP and WHO screened the project for social and environmental risks.  Risks identified at the pre-screening (PIF) stage were reviewed and their probability of occurrence and likely impact were estimated in order to rate each risk, and determine how they would be mitigated by the Project.
93. In accordance with the UNDP Social and Environmental Screening Procedure, the project has been categorized as low risk and – as outlined below – is not expected to have significant negative environmental or social impacts. Please see Annex 6 – the Social and Environmental Screening report - for details. Nevertheless, risk avoidance and risk minimization, mitigation and management mechanisms are integrated into the project design (see Table 7) and a Social and Environmental Management Checklist has been completed (Annex 6). 
94. Human Rights: In line with national law WHO and UNDP principles, the project design seeks to uphold the centrality of human rights to sustainable development, poverty alleviation and ensuring fair distribution of development opportunities and benefits. Thus, it will implement a human rights-based approach in its delivery of Health policies consistent to the laws within the nation. This will include maintaining and respecting the legal and traditional rights of local communities. 
95. Participation and inclusion: While developing the project interventions, WHO as Implementing Partner for the project will ensure a participatory process focusing on strengthening capacity of the duty bearers to meet their obligations to the project stakeholders at the national, sub-national and community levels.  They are consulted to ensure that they were adequately informed of the proposed initiative, and for their full and effective participation, as appropriate, in the design of interventions that are inclusive, to promote ownership and sustainability.  
96. Equality and non-discrimination: The project will not discriminate on the grounds of race, ethnicity, gender, age, language, disability, sexual orientation, religion, political or other opinion, national or social or geographical origin, property, birth or other status including as a member of a minority. WHO and UNDP will ensure the meaningful, effective and informed participation of stakeholders during implementation, monitoring and evaluation. Capacity building training will be tailored to women and men at all levels including the project management office.

97. Accountability and rule of law: will be upheld by following the clauses included in the agreement signed between UNDP and WHO regarding policies on monitoring, evaluation, audits and transparency in project implementation. The legal context is also defined in this agreement. 

98. Gender Equality and Women’s Empowerment: Gender indicators with gender disaggregated data are incorporated in the project's Results Framework for monitoring progress during implementation and evaluations. In terms of the UNDP Gender Marker, the project has been rated GEN 2. 
	Project Risks

	Description
	Type
	Probability (p) and Impact (I)
	Mitigation Measures
	Owner
	Status

	Risk 1: Technical capacity. Stakeholders do not distinguish vulnerability to climate change from baseline weaknesses in disease control practices and management of environmental determinant of health (especially related to food and water security)
	Operational
	P = 2, I = 3


	Integration of monitoring and evaluation systems with surveillance and early warning systems will support correlation of health metrics against climate change factors.  Maintain proactive awareness raising and communication programmes, coupled with technical training and application of health information and early warnings to help differentiating climate and non-climate drivers for the implementation of integrated adaptation interventions 
	MOH, WHO, Project manager
	No Change

	Risk 2: Turnover of government staff who will be engaged various project components and potentially negate benefits of training
	Operational
	P = 3, I = 2


	To reduce negative impacts of staff turnover, the project will appoint supporting project management unit staff to ensure continuity and smooth transition. The project will focus on institutionalization of all outputs and outcomes to ensure sustainability of project products and achievements through emphasis of a training-of-trainers approach to capacity building efforts and on development of detailed training material over heavy investments on individuals.
	MOH, WHO, Project manager
	No Change

	Risk 3: Poor inter-ministerial collaboration, considering cross-sectoral nature of health, to effectively integrate health into adaptation planning.  
	Organizational / Institutional
	P = 2, I = 4


	Cross sectoral technical advisory groups will be established in each of the participating countries.  The project will support inter-ministerial coordination through its activities, building to the extent possible on existing coordination mechanisms.  Further, a stakeholder engagement plan has been developed as part of project preparation activities.  The plan will be revisited and revised as needed during implementation to ensure it is comprehensive and inclusive given local contexts.  
	MOH, WHO, Project manager
	No Change

	Risk 4: Ensure that DDT and other environmentally harmful pesticides are recommended for newly developed mosquito control  
	Environmental
	P = 2, I = 1


	Review of newly developed guidelines and policies to ensure this is not implemented nor recommended as a means of control. 
	Project Manager
	No Change


A.6. Institutional Arrangement and Coordination. Describe the institutional arrangement for project implementation. Elaborate on the planned coordination with other relevant GEF-financed projects and other initiatives.

99.     The implementing partner for this project is WHO (Outcomes 1-4.1), and Outcome 4.2 will be directly implmented by UNDP.  The Implmenting parter is responsible and accountable for managing the project, including the monitoring and evaluation of of project interventions, achieving project outcomes, and for the effective use of UNDP resources.  
`
[image: image1]
100. The Project Board is responsible for making by consensus, management decisions when guidance is required by the Project Manager, including recommendation for UNDP/Implementing Partner approval of project plans and revisions.  In order to ensure UNDP’s ultimate accountability, Project Board decisions should be made in accordance with standards that shall ensure management and development results, best value for money, fairness, integrity, transparency and effective international competition.  In case a consensus cannot be reached within the Board, final decision shall rest with the UNDP Programme Manager.  The terms of reference for the Project Board are contained in Annex.  The Project Board is comprised of the following individuals:  Representatives of the Ministries of Health of the participating countries, UNDP and WHO.
101. Members of the Project Board will be reviewed and recommended for approval during the PAC International Project Board meeting.  Representatives of other stakeholders can be included in the Board as appropriate.  The Board contains three distinct roles, including: 

· UNDP will serve as the “Executive” representing the project ownership and interests of the GEF Council and will chair the Board.

· WHO will serve as the Senior Supplier, representing the executing agency, and the technical expertise to the project.  The Senior Supplier’s primary function within the Board is to provide guidance regarding the technical feasibility of the project: 
a. Make sure progress towards the outputs remains consistent from the supplier perspective; 

b. promote and maintain focus on the expected project outputs from the point of vide of supplier management; 

c. ensure that supplier resources required for the project are made available;

d. contribute supplier opinions on project board decisions on whether to implement recommendations on proposed changes;

e. arbitrate on, and ensure resolution of, any supplier priority or resource conflicts. 
102. Suppliers should also advise on the selection of strategy, design and methods to carry out project activities; ensure that any standards defined for the project are met and used to good effect; monitor potential changes and their impact on the quality of deliverables from a supplier perspective; monitor any risks in the implementation aspects of the project. 
103. The Senior Beneficiaries will be the Ministries of Health in the countries participating in this project. They will represent the interests of those who will ultimately benefit from the project. The Senior Beneficiary’s primary function within the Board is to ensure the realization of project results from the perspective of project beneficiaries. This role includes: i) ensuring the expected output and related activities of the project are well defined; ii) ensuring progress towards the outputs required by the beneficiaries remains consistent from beneficiaries; iii) promote and maintain focus on the expected project outputs; iv) prioritize and contribute beneficiaries’ opinions on Project Board decisions on whether to implement recommendations on proposed changes; v) resolve priority conflicts. The Senior Beneficiaries primary function within the Board is to ensure the realization of project results from the perspective of project beneficiaries. 

104. The Senior Technical Advisor (STA) for Climate Change Adaptation within the Global Environmental Finance Unit at UNDP will undertake the Project Assurance role in coordination with WHO. The STA can, if necessary and upon agreement with the UNDP CO delegate the same to designated representative at the UNDP CO. The STA supports the Project Board Executive by carrying out objective and independent project oversight and monitoring functions. The Project Manager and Project Assurance roles should never be held by the same individual for the same project.

105. Regional Project Manager (RPM) will be recruited by WHO, to be based at WHO Regional Offices (SEARO and WPRO) with the authority to run the project on a day-to-day basis on behalf of the Implementing Partner within the constraints laid down by the Board. The Project Manager’s prime responsibility is to ensure that the project produces the results specified in the project document, to the required standard of quality and within the specified constraints of time and cost.  Furthermore, there will be National Project Managers based at the WHO Country Offices, so as to coordinate activities and workplans within the country effort.  
Governance role for project target groups

106. On the Project Board, Beneficiaries will be represented by officers from the Ministries of Health.

Direct Project Costs

107. UNDP Direct Project Services will apply to Project Management Cost.  Direct Project Costs may apply to other Outputs at the written request for support to implementation from WHO or participating countries.

Agreement on the intellectual property rights and use of logo on the project’s deliverables and disclosure of information

108. In order to accord proper acknowledgement to the GEF for providing grant funding, the GEF logo will appear together with the UNDP and WHO logos on all promotional materials, other written materials like publications developed by the project, and project hardware.  Any citations on publications regarding projects funded by the GEF will also accord proper acknowledgement to the GEF. Information will be disclosed in accordance with relevant policies notably the UNDP Disclosure Policy
 and the GEF policy on public involvement.

Project Management 
109. Sucessful execution of the project will require the establishment of an efficient global management structure, complemented by efficient regional and national management structures. As Implementing Partner, WHO will implement the project per established UNDP guidelines related to agency-executed projects. Within WHO, WHO will execute the project and will manage disbursement of project resources to its regional and country offices and report back to UNDP on expenditures as well as key results on a quarterly and annual basis as per the terms of Executing Agency Agreement between UNDP and WHO (see Figure below). 
[image: image2.png]Jrioworriance





    Project Organization Chart at Regional Level

110. At the country level, techncial advisory groups made up of key stakeholders will provide technical guidance to project implementation and support cross-sectoral collaboration. The Ministry mandated to oversea health concerns in each of the participating countries is expected to chair the committee, and identify a key person or persons who will have primary project responsibility for country level project activities, and to support coordinattion of country level activities. 
Additional Information not well elaborated at PIF Stage:
A.7 Benefits. Describe the socioeconomic benefits to be delivered by the project at the national and local levels. How do these benefits translate in supporting the achievement of global environment benefits (GEF Trust Fund) or adaptation benefits (LDCF/SCCF)?

111. The proposed project contributes to three LDCF/SCCF adaptation benefits, namely: 

· CCA-1: Reduce vulnerability of people, livelihoods, physical assets and natural systems 

· CCA-2: Strengthen institutional and technical capacities for effective CCA 

· CCA-3: Integrate CCA into relevant policies, plans and associated processes 

112. Outcome 1 focuses on supporting countries to integrate health into adaptation planning and support to the HNAP process.  This includes support to the development and implementation of SOPs for cross-sectoral collaboration -  thereby facilitating the integration of climate change impacts on health into broader policy and planning.  Outcomes 2 and 4 contribute to, through support to collect and analyse the data necessary for informed planning.  This includes support to surveillance, early warning information and economic data and analyses – strengthening institutional and technical capacities for effective climate change adaptation.  And Outcome 3 supports the necessary investments to improve safety through investments in WASH and piloting measures for climate-resilient health facilities, as well as training for hospital or clinic personnel to identify and treat climate-related illnesses.  

113. The vulnerabilty assessments planned under the project, will inform activities across the Outcomes, from broad adaptation planning to training to hospital personnel.  Where special needs are identified, policy support will be provided through the project with suggestions on how to address certain circumstances, building on best practices where possible.  For instance, the proposed LDCF project can build on the successes UNDP’s South Asia HIV programme in Bangladesh and Nepal, namely community-led health service to marginalized groups.  The HIV programme focused mainly on the LGBT community and sex workers, who were often reluctant to seek medical care due to fear of discrimination or general mistreatment.  Best practices of the community-led services can be applied to other marginalized groups, vulnerable to climate change impacts on health, as appropriate in participating countries of the LDCF project, including for example: poor households, individuals with limited mobility (e.g. elderly or disabled), remote communities, minority groups and indigenous peoples.  Vulnerability assessments planned under the proposed project will help further identify groups and needed support.  

114. In combination, these investments will ensure that a) climate change impacts on health are integrated into planning, b) decision-makers have the data and analyses needed to make informed decisions related to planning, as well as early warning, and c) people in need of health services can rely on trained personnel and safe facilities for support.
A.8 Knowledge Management. Elaborate on the knowledge management approach for the project, including, if any, plans for the project to learn from other relevant projects and initiatives (e.g. participate in trainings, conferences, stakeholder exchanges, virtual networks, project twinning) and  plans for the project to assess and document in a user-friendly form (e.g. lessons learned briefs, engaging websites, guidebooks based on experience) and share these experiences and expertise (e.g. participate in community of practices, organize seminars, trainings and conferences) with relevant stakeholders. 

115. Results from the project will be disseminated within and beyond the project intervention zone through existing information sharing networks and forums. The project will identify and participate, as relevant and appropriate, in scientific, policy-based and/or any other networks, which may be of benefit to project.  The project will identify, analyze, and share lessons learned that might be beneficial in the design and implementation of similar future projects and disseminate these lessons widely.  There will be continuous information exchange between this project and other projects of similar focus in the same country(ies), region and globally.

116. A detailed plan for disseminating results will be developed within the first 2 months of project implementation, in consultation with relevant parties including the project management unit of UNDP’s Adaptation Learning Mechanism.
117. There will be a two-way flow of information between this project and other projects of a similar focus. This will be supported by knowledge management activities in Outcome 4.1, including the development and sharing of case studies, national and regional seminars / workshops and exchange visits, and information exchange via a project website and national/regional level workshops. 

B. Description of the consistency of the project with:

B.1 Consistency with National Priorities. Describe the consistency of the project with national strategies and plans or reports and assessements under relevant conventions such as NAPAs, NAPs, ASGM NAPs, MIAs, NBSAPs, NCs, TNAs, NCSAs, NIPs, PRSPs, NPFE, BURs, etc.:

118. The project is consistent with national strategies and plans in the six participating countries.

Bangladesh

119. The Government of Bangladesh has responded to the climate change vulnerability issue and developed two key policy documents, including the National Adaptation Programme of Action (NAPA) and the Bangladesh Climate Change Strategy and Action plan (BCCSAP). These documents highlight the role and efforts of the Bangladeshi Government and the political will to address health issues due to climate change. NAPA recommends initiation of surveillance of climate-sensitive diseases and vectors. BCCSAP highlights health concerns in the first of its six pillars.  
Cambodia

120. In Cambodia, the project will implement adaptation interventions consistent with the National Adaptation Programme of Action (2006), the Climate Change Strategy for Public Health (2012) and the National Climate Change Action Plan for Public Health (2014–2018). These emphasize institutional capacity and emergency preparedness for three key areas: vector-borne diseases; waterborne and foodborne diseases; and the health impacts of extreme weather events. A National Strategy for Climate Change Adaptation and Disaster Risk Reduction is under development. The project will ensure that health aspects of adaptation to climate change and disaster risk reduction are integrated, consistent with the Sendai Framework for Disaster Risk Reduction. 
121. The Cambodia Climate Change Alliance Phase 2 (CCCA-2) project, Strengthening Country Capacity to Deal Effectively with Climate-sensitive Vector-borne and Waterborne Diseases and Reducing the Health Impacts of Disasters, runs through 2018 and has a similar scope to the GEF project. The CCCA-2 project has the following aims:
· to improve understanding of health professionals regarding climate change and health risks – particularly those posed by vector-borne diseases, water-related diseases, and hydro-meteorological disasters such as droughts and floods – and to increase capacity to prevent, diagnose and manage these high-priority climate-sensitive diseases;
· to strengthen national institutional capacity to conduct integrated, climate-based, community, vector and epidemiological surveillance of climate-sensitive diseases;
· to enhance capacity of the health sector to reduce disaster risk, build resilience and manage the health impacts of disasters;
· to increase community and stakeholder awareness of the health risks posed by climate change on extreme weather events and vector-borne and water-related diseases, and to improve understanding and use of health-protective behaviours.
Lao PDR

122. The project is consistent with the Strategy on Climate Change (2010) and the Climate Change Action Plan for 2013–2020 which emphasize water and sanitation, communicable diseases, awareness-raising, and streamlining and strengthening existing programmes. The Action Plan focusses on four key initiatives: strengthening institutional and human resource capacities on climate change; enhancing adaptive capacity for coping with climate change; climate change mitigation; and strengthening education and improving public awareness of climate change. Two key areas of public health were highlighted: increased resilience of rural water supply systems to climate change, and improved public health services for climate change adaptation.
Myanmar

123. Public health is one of the eight themes identified under The National Adaptation Programme of Action (NAPA 2012). The other themes are agriculture, early warning systems, forest, water resources, coastal zone, energy, industry, and biodiversity. Within the public health theme, the following projects were ranked according to importance: 
· Adaptation to climate change through climate-resilient health facilities in the Rakhine State and Ayeyarwady Region.

· Integrating climate change adaptation strategies into the prevention of heat-related disorders in agricultural and industrial workers.

· Supporting Intensive Care Units in hospitals to treat heat-related disorders.

· Reducing the vulnerability of local communities to climate-induced water-related health hazards through the provision of safe water supplies and sanitary latrines.

· Climate change adaptation through establishing post-disaster rapid response networks to meet the immediate nutritional needs of disaster-affected communities.

· Adaptation to climate change through the construction of climate-resilient health facilities in Bago, Mandalay and Sagaing Regions.

· Integrating climate adaptation strategies into the prevention and control of diarrheal diseases.

· Integrating climate change adaptation strategies into the prevention and control of malaria and dengue hemorrhagic fever.

· Building the capacity of the health sector for determining the direct and indirect impacts of climate change on the transmission of current and emerging diseases.

· Adaptation to climate change through integrated plague and rodent control strategies
124. The National Climate Change Policy, Strategy and Action Plan (MCCSAP) is being developed by the Myanmar Consortium for Climate Change Adaptation programme and the Ministry of Natural Resources and Environmental Conservation (MONREC). The programme, which runs from 2013-17 is designed to increase awareness of climate change in Myanmar, to strengthen institutional capacity to develop policies address it, and to develop eco-system based adaptation practices.

125. The MCCSAP presents a roadmap to guide Myanmar’s strategic responses to address climate related risks and opportunities over the next 15 years and beyond. It aims to support key actors in their decision making at the national and local level to respond to the challenges and opportunities associated with climate change.
Nepal

126. Nepal has been party to the UNFCCC since 1992. It submitted its first communication report in 2004 in which public health was identified as high priority.  The objectives of the UNFCCC came into effect in Nepal 2005, and in 2014 Nepal submitted its second communication report, prioritizing public health and identifying extreme weather events (cold waves and heat waves), diarrhoeal and vector-borne diseases as major climate-sensitive risks. 
127. Nepal has in place several major policies and priorities that align with this proposal, starting with the Constitution of Nepal (2015) that embeds the right of people to live in a healthy and clean environment, the right to seek and have equal access to basic health and emergency care, and the right to clean water and sanitation.
128. The Climate Change Policy (2011) promotes adaptation and mitigation, through natural resources management and climate resilient infrastructure for socioeconomic development, and the formation of an intersectoral working group to integrate climate change in all policies. It highlights the need to develop forecasting and preventive actions for vector-borne and other climate-sensitive diseases, better preparedness for epidemics, increased public awareness and capacity building, with an emphasis on community level programmes.
129. Nepal’s National Adaptation Programme of Actions to Climate Change (NAPA 2010) names public health as one of the six core themes, along with agriculture and food, climate-induced disasters, urban settlement and infrastructure, forests and diversity, and water resources and energy, In particular the public health priorities identified are to gather and apply evidence to reduce health impacts, empower communities through education, invest in disease outbreak and emergency response, scale-up existing programmes on vector-, water-, and foodborne disease, and strengthening early warning and surveillance systems. 
130. Nepal has also developed a National Framework on Local Adaptation Plans of Action (2011) to identify climate vulnerable communities, appropriate agents for service delivery and monitoring and evaluation. It is intended that these local level plans influence national level planning. The National Adaptation Plan (2015) integrates climate change into all sector policies, strategies, plans and programmes, taking a medium term (2018-30) and longer term (to 2050) perspective and with consideration of the Sendai Framework for Disaster Reduction and Sustainable Development Goals.
Timor-Leste

131. Timor-Leste’s National Adaptation Programme of Action on Climate Change (2010) considers the vulnerability of key sectors, including health. Health-related risks are rated as a high priority (priority 3) in the NAPA, and the Ministry of Health is tasked with addressing specific vulnerabilities through a proposed USD1.7 million project. The project includes policy reform (review of standards, national health vulnerability assessment), awareness raising and demonstration, strengthening of early-warning systems, targeted disease prevention measures, and institutional and capacity development (train policy-makers and planners, establish an inter-ministerial mechanism, integrate climate and health linkages into the school curriculum). These activities have not been funded for implementation, and the GEF project will incorporate them into its project design. Timor-Leste’s Initial National Communication (2014) includes overall vulnerability assessments at village level. The health assessment is limited to likely impacts on vector-borne disease, and describes direct and indirect impacts from changing temperature and rainfall on malaria and dengue according to district. There are no other health impacts included.

132. The Initial National Communication for Timor-Leste highlights nutrition and hunger, which are a main climate health risk in the country.  Food security is climate sensitive and Timor-Leste will be exposed to increasingly extreme droughts and rainfall. The most recent National Nutrition Strategy (2014-2019) aims specifically to reduce maternal and childhood undernutrition, including through improved food security. There is also a National Action Plan for a Hunger and Malnutrition Free Timor-Leste (2014). This Plan does address climate change through one of its five pillars. Pillar 3 aims to ensure that all food systems are sustainable, which includes climate resilient agriculture and recognition of the need for cross-sectoral coherence and cooperation, including disaster risk reduction and management and strengthening early warning systems for climate change disasters.   
C.  Describe the budgeted m &e plan:       
133. The project results as outlined in the project results framework will be monitored annually and evaluated periodically during project implementation to ensure the project effectively achieves these results.  It will be monitored through the following M&E activities. The M&E budget is provided in the table below. The M&E framework set out in the Project Results Framework in Part 3 of this project document is aligned with the AMAT and UNDP M&E frameworks. 

134. Project-level monitoring and evaluation will be undertaken in compliance with UNDP requirements as outlined in the UNDP POPP and UNDP Evaluation Policy. While these UNDP requirements are not outlined in this project document, the UNDP Country Office will work with the relevant project stakeholders to ensure UNDP M&E requirements are met in a timely fashion and to high quality standards. Additional mandatory GEF-specific M&E requirements (as outlined below) will be undertaken in accordance with the GEF M&E policy and other relevant GEF policies
.  
135. In addition to these mandatory UNDP and GEF M&E requirements, other M&E activities deemed necessary to support project-level adaptive management will be agreed during the Project Inception Workshop and will be detailed in the Inception Report. This will include the exact role of project target groups and other stakeholders in project M&E activities including the GEF Operational Focal Point and national/regional institutes assigned to undertake project monitoring. The GEF Operational Focal Point will strive to ensure consistency in the approach taken to the GEF-specific M&E requirements (notably the GEF Tracking Tools) across all GEF-financed projects in the country. This could be achieved for example by using one national institute to complete the GEF Tracking Tools for all GEF-financed projects in the country, including projects supported by other GEF Agencies.
    

M&E Oversight and monitoring responsibilities

136. Project Manager: The Project Manager is responsible for day-to-day project management and regular monitoring of project results and risks, including social and environmental risks. The Project Manager will ensure that all project staff maintain a high level of transparency, responsibility and accountability in M&E and reporting of project results. The Project Manager will inform the Project Board, the UNDP Country Office and the UNDP-GEF RTA of any delays or difficulties as they arise during implementation so that appropriate support and corrective measures can be adopted. 

137. The Project Manager will develop annual work plans based on the multi-year work plan included in Annex A, including annual output targets to support the efficient implementation of the project. The Project Manager will ensure that the standard UNDP and GEF M&E requirements are fulfilled to the highest quality. This includes, but is not limited to, ensuring the results framework indicators are monitored annually in time for evidence-based reporting in the GEF PIR, and that the monitoring of risks and the various plans/strategies developed to support project implementation (e.g. gender strategy, KM strategy etc..) occur on a regular basis.  

138. Project Board:  The Project Board will take corrective action as needed to ensure the project achieves the desired results. The Project Board will hold project reviews to assess the performance of the project and appraise the Annual Work Plan for the following year. In the project’s final year, the Project Board will hold an end-of-project review to capture lessons learned and discuss opportunities for scaling up and to highlight project results and lessons learned with relevant audiences. This final review meeting will also discuss the findings outlined in the project terminal evaluation report and the management response.

139. Project Implementing Partner:  The Implementing Partner is responsible for providing any and all required information and data necessary for timely, comprehensive and evidence-based project reporting, including results and financial data, as necessary and appropriate. The Implementing Partner will strive to ensure project-level M&E is undertaken by national institutes, and is aligned with national systems so that the data used by and generated by the project supports national systems. 

UNDP-GEF:

140.   The UNDP-GEF Regional Technical Advisor will support the Project Manager as needed, including through annual supervision missions. The annual supervision missions will take place according to the schedule outlined in the annual work plan. Supervision mission reports will be circulated to the project team and Project Board within one month of the mission.  The UNDP-GEF Regional Technical Advisor will initiate and organize key GEF M&E activities including the annual GEF PIR, the independent mid-term review and the independent terminal evaluation. The UNDP-GEF Regional Technical Advisor will also ensure that the standard UNDP and GEF M&E requirements are fulfilled to the highest quality.  

141. The UNDP-GEF Regional Technical Advisor is responsible for complying with all UNDP project-level M&E requirements as outlined in the UNDP POPP. This includes ensuring the UNDP Quality Assurance Assessment during implementation is undertaken annually; that annual targets at the output level are developed, and monitored and reported using UNDP corporate systems; the regular updating of the ATLAS risk log; and, the updating of the UNDP gender marker on an annual basis based on gender mainstreaming progress reported in the GEF PIR and the UNDP ROAR. Any quality concerns flagged during these M&E activities (e.g. annual GEF PIR quality assessment ratings) must be addressed by the UNDP Country Office and the Project Manager.  

142. The UNDP-GEF Regional Technical Advisor will retain all M&E records for this project for up to seven years after project financial closure in order to support ex-post evaluations undertaken by the UNDP Independent Evaluation Office (IEO) and/or the GEF Independent Evaluation Office (IEO).  

143. Additional M&E and implementation quality assurance and troubleshooting support will be provided by the UNDP-GEF Headquarters and the UNDP-GEF Directorate as needed.  

Audit

144. The project will be audited according to UNDP Financial Regulations and Rules and applicable audit policies for agency-implemented projects.

Additional GEF monitoring and reporting requirements

Inception Workshop and Report

145. A Project Inception Workshop will be held within the first two months of project start after the project document has been signed by all relevant parties to, amongst others:

· Re-orient project stakeholders to the project strategy and discuss any changes in the overall context that influence project strategy and implementation;

· Discuss the roles and responsibilities of the project team, including reporting and communication lines and conflict resolution mechanisms; 

· Review the project results framework and finalize the indicators, means of verification and monitoring plan; 

· Discuss reporting, monitoring and evaluation roles and finalize the M&E budget; identify national/regional institutes to be involved in project-level M&E; discuss the role of the GEF OFP in M&E;

· Update and review responsibilities for monitoring the various project plans and strategies, including the risk log; knowledge management strategy, and other relevant strategies;

· Review financial reporting procedures and mandatory requirements, and agree on the arrangements for audits 

· Plan and schedule Project Board meeting and finalize first year annual work plan

146. The Project Manager will prepare the inception report no later than one month after the Inception Workshop.  The inception report must be cleared by UNDP-GEF RTA and will be approved by the Project Board.    

GEF Project Implementation Report (PIR)

147. WHO Country Offices in consultation with Responsible Parties, and the UNDP-GEF Regional Technical Advisor will provide objective input to the annual GEF PIR covering the reporting period July (previous year) to June (current year) for each year of project implementation.  The WHO Country Offices in consultation with Responsible Parties will develop the PIR and submit these to the Project Management Unit, who will then compile the individual reports in one overall project PIR, to be finalized by WHO in consultation with UNDP-GEF and will coordinate with the GEF Operational Focal point and other stakeholders. 

148. The Project Manager will ensure that the indicators included in the project results framework are monitored annually in advance of the PIR submission deadline so that progress can be reported in the PIR.  Any environmental and social risks and related management plans will be monitored regularly, and progress will be reported in the PIR.

149. The PIR submitted to the GEF will be shared with the Project Board.  UNDP-GEF and WHO will coordinate the input of the GEF OFP and other stakeholders to the PIR as appropriate.  The quality rating of the previous year’s PIR will be used to inform the preparation of subsequent PIR.

GEF Focal Area Tracking Tools:  

150. The following GEF Tracking Tool(s) will be used to monitor global environmental benefit results:

The baseline/CEO Endorsement GEF Focal Area Tracking Tool(s) – submitted in Annex D to this project document – will be updated by the Project Manager/Team and shared with the mid-term review consultants and terminal evaluation consultants (not the evaluation consultants hired to undertake the MTR or the TE) before the required review/evaluation missions take place. The updated GEF Tracking Tool(s) will be submitted to the GEF along with the completed Mid-term Review report and Terminal Evaluation report.

Independent Mid-term Review (MTR)

151. An independent Mid-Term Evaluation of the project will be conducted after completion of the first two years. The Mid-Term Evaluation will determine progress being made toward the achievement of outcomes and will identify course correction if needed.  It will focus on the effectiveness, efficiency and timeliness of project implementation; will highlight issues requiring decisions and actions; and will present initial lessons learned about project design, implementation and management.  Findings of this review will be incorporated as recommendations for enhanced implementation during the final half of the project’s term.  The organization, terms of reference and timing of the mid-term evaluation will be decided after consultation between the parties to the project document.  The Terms of Reference for this Mid-term evaluation will be prepared by the WHO based on guidance from UNDP-GEF, and in line with UNEG Guidelines. The management response and the evaluation will be uploaded to UNDP corporate systems, in particular the UNDP Evaluation Office Evaluation Resource Center (ERC).  The relevant GEF Focal Area Tracking Tools will also be completed during the mid-term evaluation cycle.

Terminal Evaluation (TE)

152. An independent terminal evaluation (TE) will take place upon completion of all major project ouputs and activities.  The terminal evaluation process will begin three months before operational closure of the project allowing the evaluation mission to proceed while the project team to reach conclusions on key aspects such as project sustainability.  The project manager will remain on contract until the TE report and management response have been finalized.  The terms of reference, the evaluation process and the final TE report will follow the standard templates and guidance prepared by UNDP IEO for GEF-financed projects available at the UNDP Evaluation Resource Center.  As noted in this guidance, the evaluation will be “independent, impartial and rigorous”.  The consultants that will be hired to undertake the assignment will be independent from organizations involved in designing, executing or advising on the project to be evaluated.  The GEF Operational Focal Point and other stakeholders will be involved and consulted during the terminal evaluation process.  Additional quality assurance support is available from the UNDP-GEF Directorate.  The final TE report will be cleared by the UNDP-GEF Regional Technical Advisor, and will be approved by the Project Board.  The TE report will be publicly available in English and the corresponding management response to the UNDP Evaluation Resource Centre (ERC).  Once uploaded to the ERC, the UNDP IEO will undertake a quality assessment and validate the findings and ratings in the TE report, and rate the quality of the TE report.  The UNDP IEO assessment report will be sent to the GEF IEO along with the project terminal evaluation report.   

Final Report

153. The project’s terminal PIR along with the terminal evaluation (TE) report and corresponding management response will serve as the final project report package.  The final project report package shall be discussed with the Project Board during an end-of-project review meeting to discuss lessons learned and opportunities for scaling up.

Mandatory GEF M&E Requirements and M&E Budget

154. The indicative monitoring and evaluation plan and corresponding budgets is provided in Table below. Costs for M&E will be incorporated into Outcomes 1-3.

	GEF M&E requirements


	Primary responsibility
	Indicative costs to be charged to the Project Budget
  (USD)
	Time frame

	
	
	GEF grant
	Co-financing
	

	Inception Workshop 
	Project Manager/ PMU

WHO 
	USD 20,000
	None
	Within two months of project document signature 

	Inception Report
	Project Manager/ PMU

WHO
	None
	None
	Within two weeks of inception workshop

	Standard Monitoring and reporting requirements as outlined in the UNDP POPP
	Project Manager/ PMU 

WHO
	None
	None
	Quarterly, annually

	Monitoring of indicators in project results framework 
	Project Manager and

WHO 
	None 
	None
	Annually 

	GEF Project Implementation Report (PIR) 
	Project Manager/ PMU

WHO
	None
	None
	Annually 

	Monitoring of environmental and social risks, and corresponding management plans as relevant
	Project Manager/ PMU


	None
	None
	On-going

	Addressing environmental and social grievances
	Project Manager/ PMU
	None 
	None
	As needed

	Project Board meetings 
	Project Board, WHO,

UNDP-GEF 
	20000 USD per meeting

= 60000 USD
	None
	Meeting annually

	Supervision missions
	Project Manager/ PMU
	None

	None
	Annually

	Oversight missions
	Project Manager/ PMU
	None
	None
	Troubleshooting as needed

	GEF Secretariat learning missions/site visits 
	WHO, PMU and UNDP-GEF team
	None
	None
	To be determined.

	Mid-term GEF Tracking Tool 
	PMU

Project Manager

WHO
	None
	None
	Before mid-term review mission takes place.

	Independent Mid-term Review (MTR)  
	WHO, PMU and UNDP-GEF team
	30,000 USD
	None
	Between 2nd and 3rd PIR.  

	Final GEF Tracking Tool to be updated by MOH
	Project Manager 
	None
	None
	Before terminal evaluation mission takes place

	Independent Terminal Evaluation (TE) included in UNDP evaluation plan
	WHO, PMU and UNDP-GEF team
	100,000 USD
	None
	At least three months before operational closure

	TOTAL indicative COST 

Excluding project team staff time, and UNDP staff and travel expenses 
	210,000 USD
	None
	


PART iII:  certification by gef partner agency(ies)

A. GEF Agency(ies) certification
	This request has been prepared in accordance with GEF policies
 and procedures and meets the GEF criteria for CEO endorsement under GEF-6.


	Agency Coordinator, Agency Name
	Signature
	Date
(MM/dd/yyyy) 
	Project Contact Person
	Telephone
	Email Address

	Ms. Adriana Dinu

Executive Coordinator, UNDP- Global Environmental Finance     
	[image: image3.jpg]



	10/05/2017     
	 Ms. Mariana Simões 
	+66924764223     
	mariana.simoes@undp.org     


B. GEF_CEOENDR_60
ANNEX A:  PROJECT RESULTS FRAMEWORK (either copy and paste here the framework from the Agency document, or provide reference to the page in the project document where the framework could be found).

	Applicable Outputs from the 2014 – 2017 UNDP Strategic Plan:
	Output 1.4:  Scaled up action on climate change adaptation and mitigation cross sectors which is funded and implemented.

	Applicable Output Indicators from the UNDP Strategic Plan Integrated Results and Resources Framework:  
	Output 1.4 indicator 1.4.1:  a) Extent to which climate finance is being accessed b) Extent to which there is a system in place to access, deliver, monitor, report on and verify climate finance.

	Project Strategy
	Objective and Outcome Indicators


	Baseline
 


	Mid – Term Target
	Final Target
	Assumptions



	Project Objective: 

Increase the adaptive capacity of national health systems and institutions, and sub-national level actors, to respond to and manage long-term climate-sensitive health risks in six Asian LDCs.
	National H-NAP for long term planning and capacity development is created and budgeted.

(AMAT 3.2 Indicator 12) 

(Output 1.4 – UNDP strategic plan)
	H-NAP has not been developed and/or implemented.

(Note: Cambodia and Nepal have approved H-NAP – funding and implementation planning has not yet been incorporated.  Bangladesh has DFID HNAP development project – early stages)
	Draft H-NAP has been developed (Bangladesh, Lao PDR, Myanmar, and Timor-Leste).
	H-NAP is finalized/updated in 6 countries as the long-term plan for health adaptation to climate change and MOH is part of TWG with mandate to address cross-cutting climate change adaptation.
	With support provided through outcome 4.2, countries are able to identify and quantify possible socio-economic impacts related to health and climate change 

	Outcome 1: Institutional Capacities are strengthened to effectively integrate climate risks and adaptation options in health sector planning and implementation.
	Development of National Standards or guidelines for climate change and health systems 

	National standards, guidelines and SOPs are not available relating CC and Health


	Draft standards or guidelines are developed and disseminated for review


	Final standards and guidelines are developed.
	Technical capacity of staff to understand and implement the requirements within their current programmes and develop new programmes with funding appropriately. 

	Outcome 2: Effective decision making for health interventions is enabled through generation of information and improved surveillance and/or early warning systems
	Vulnerability and adaptation assessments (V+A) conducted for current and future health risks.

(AMAT 2.1 Indicator 6)
	V+A has not been completed, or existing V+A is outdated or not comprehensive.
	Gender-disaggregated health vulnerability and adaptation assessments conducted or updated in 2 countries.
	Gender-disaggregated health vulnerability and adaptation assessments completed or updated in 6 countries.
	Technical capacity to carry out V+A is available.

	
	Integrated disease surveillance system for climate sensitive disease is strengthened
	Disease surveillance system does not consider climate/weather data
	Integrated disease surveillance system considers climate/weather data
	Tailored products to inform decision making based on surveillance system which incorporates climate/weather data (6 countries)
	Appropriate climate/weather data can be obtained for linkage in a timely manner

	Outcome 3: Climate resilience is enhanced in health service delivery

	Disease control and prevention programmes are strengthened to account of the effects of climate variability and change. 
	Specific programmes and plans of climate-sensitive diseases don’t include climate/weather considerations.
	Disease control and prevention plans and programmes strengthened in two countries by including climate/weather considerations in the areas of intervention.
	Disease control and prevention programmes strengthened in 6 countries 
	Methods of prevention and control of climate sensitive diseases are effective under changed climate.

All local health facilities have necessary tools and capacity for timely reporting.

	
	Number of direct beneficiaries from enhanced health service delivery (AMAT 1.1 Indicator 1: number of direct beneficiaries)
	Health service responds to vulnerability to climate change and health
	0
	100,000
(estimated 50% female)
	Informed by vulnerability assessments and related tailored activities

	Outcome 4.1: Enhanced regional cooperation and knowledge exchange for promoting scale-up and replication of interventions
	Three regional trainings/meetings organized (Percentage of government stakeholders participated in national review meeting on CC&H)
	No regional exchange of experiences on climate change and health 
	One Regional training/ meeting on climate change and health organized by WHO.


	3 Regional Meetings on climate change and health (building on National experiences) for International South-South collaboration focused on CCH.  Reports on Improvements and Challenges will be generated and shared within the meeting. (Implemented by WHO)
	

	Outcome 4.2 HNAP are effectively integrated into ongoing NAP processes
	HNAP informed by economic analyses to support integration into the NAP 
	Economic analyses on climate change and health not available
	2 countries receive support to develop climate change and health economic analyses
	6 countries receive support to develop climate change and health economic analyses (Implemented by UNDP)
	


Annex B:  status of implementation of project preparation activities and the use of funds

A.  Provide detailed funding amount of the PPG activities financing status in the table below:
        

	PPG Grant Approved at PIF:       $480,000

	Project Preparation Activities Implemented
	GEF/LDCF/SCCF Amount ($)

	
	Budgeted Amount
	Amount Spent Todate
	Amount Committed

	Stocktaking, desk reviews, stakeholder consultations
	432,000     
	     338,415
	     93,585

	Formulation of full-sized project documents
	48,000 
	     37,602
	     10,398   

	Total
	480,000
	376,017
	103,983


annex C:  calendar  of expected reflows (if non-grant instrument is used)
Provide a calendar of expected reflows to the GEF/LDCF/SCCF Trust Funds or to your Agency (and/or revolving fund that will be set up)

N/A     
Project Board





Senior Beneficiary 


Ministry of Health representatives from participating countries





Executive


UNDP








Senior Supplier


WHO





Project Assurance


Senior Technical Advisor


(UNDP-GEF)








Project Organization Structure





Bangladesh


Ministry of Health & Family Welfare











Timor-Leste


Ministério da Saúde





Lao PDR


Ministry of Health








Cambodia


Ministry of Health











Myanmar


Ministry of Health & Sports








Nepal


Ministry of Health








Project Management Unit (PMU)


WHO





National Technical Advisory Groups


Representatives across Ministries to support cross-sectoral collaboration and provide technical guidance to the project








� Project ID number remains the same as the assigned PIF number.


� When completing Table A, refer to the excerpts on � HYPERLINK "https://www.thegef.org/gef/sites/thegef.org/files/documents/document/GEF6%20Results%20Framework%20for%20GEFTF%20and%20LDCF.SCCF_.pdf" ��GEF 6 Results Frameworks for GETF, LDCF and SCCF�.


� Financing type can be either investment or technical assistance.


� For GEF Project Financing up to $2 million, PMC could be up to10% of the subtotal;  above $2 million, PMC could be up to 5% of the subtotal.  PMC should be charged proportionately to focal areas based on focal area project financing amount in Table D below.�


�   Update the applicable indicators provided at PIF stage.  Progress in programming against these targets for the projects per the Corporate Results Framework in the � HYPERLINK "http://www.thegef.org/gef/sites/thegef.org/files/documents/GEF.C.46.07.Rev_.01_Summary_of_the_Negotiations_of_the_Sixth_Replenishment_of_the_GEF_Trust_Fund_May_22_2014.pdf" ��GEF-6 Programming Directions�, will be aggregated and reported during mid-term and at the conclusion of the replenishment period.


�  For questions A.1 –A.7 in Part II, if there are no changes since PIF , no need to respond, please enter “NA” after the respective question.  


� For biodiversity projects, in addition to explaining the project’s consistency with the biodiversity focal area strategy, objectives �   and programs, please also describe which � HYPERLINK "http://www.thegef.org/gef/content/did-you-know-%E2%80%A6-convention-biological-diversity-has-agreed-20-targets-aka-aichi-targets-achie" ��Aichi Target(s)� the project will directly contribute to achieving..


� IPCC (2014) Climate Change 2014 Impacts, Adaptation, and Vulnerability. Intergovernmental Panel on Climate Change.


� Source: � HYPERLINK "http://www.who.int/globalchange/resources/country-profiles/en/" �http://www.who.int/globalchange/resources/country-profiles/en/�; 


� OECD/WHO (2016) Health at a Glance Asia/Pacific 2016. WHO (2017) Building resilience of health systems to climate change in Bangladesh.


� WHO (2017) Building resilience of health systems to climate change in Bangladesh.


� IPCC (2014) Climate Change 2014 Impacts, Adaptation, and Vulnerability. Intergovernmental Panel on Climate Change.


� Vulnerability and adaptation assessment report. Geneva: World Health Organization; 2011


�  WHO (2017) GEF-LDCF Climate Change and Health Adaptation Project Proposal: Cambodia


� WHO (2017) GEF-LDCF Climate Change and Health Adaptation Project Proposal: Cambodia


� Cambodian Ministry of Health and World Health Organization (2010) Climate change and health in Cambodia: a vulnerability and adaptation assessment. 


� Cambodian Ministry of Health (2014) National Climate Change Action Plan for Public Health 2014–2018.


� WHO (2017) Building resilience of health systems in Asian least developed countries to climate change. GEF country proposal document: Lao People’s Democratic Republic


�� HYPERLINK "http://apps.who.int/iris/bitstream/10665/246139/1/WHO-FWC-PHE-EPE-15.39-eng.pdf?ua=1" �http://apps.who.int/iris/bitstream/10665/246139/1/WHO-FWC-PHE-EPE-15.39-eng.pdf?ua=1� 


� WHO (2014) Country Cooperation Strategy 2014–2018, Myanmar.


� Ministry of Environmental Conservation and Forestry (2012) Myanmar’s National Adaptation Programme of Action (NAPA) to Climate Change.


� World Bank (2017) World Development Indicators. � HYPERLINK "http://data.worldbank.org/products/wdi" �http://data.worldbank.org/products/wdi�  


� WHO (2017) Climate and health country profile 2015: Myanmar � HYPERLINK "http://www.who.int/globalchange/resources/country-profiles/en/" �http://www.who.int/globalchange/resources/country-profiles/en/�


� WHO (2017) GEF-LDCF Climate Change and Health Adaptation Project Proposal. Draft national report of Myanmar


� Baidya SK, Shrestha ML, Sheikh MM. Trends in daily climatic extremes of temperature and precipitation in Nepal. Journal of Hydrology and Meteorology. 2008;5:38–51.


� WHO (2017) GEF-LDCF Climate Change & Health Adaptation Project Proposal. Final National Report of Nepal


� Timor-Leste and FAO Achievements and success stories (FAO, 2011)


� � HYPERLINK "https://www.oxfam.org.au/what-we-do/health/food-and-nutrition/childhood-malnutrition-in-timor-leste/" �https://www.oxfam.org.au/what-we-do/health/food-and-nutrition/childhood-malnutrition-in-timor-leste/� 


� Tracking Progress on Child and Maternal Nutrition: A survival and development priority (UNICEF, 2009)


� � HYPERLINK "https://www.oxfam.org.au/what-we-do/health/food-and-nutrition/childhood-malnutrition-in-timor-leste/" �https://www.oxfam.org.au/what-we-do/health/food-and-nutrition/childhood-malnutrition-in-timor-leste/� 


� Climate Change and Population Growth in Timor Leste: Implications for Food Security (N. Molyneux, et. al, 2011)


� Timor-Leste and FAO Achievements and success stories (FAO, 2011)


� Timor-Leste and FAO Achievements and success stories (FAO, 2011)


� Climate Change 2013: The Physical Science Basis (IPCC, 2013)


� Secretariat for Environment (2014) Timor Leste’s Initial National Communication


� Ministry for Economy and Development (2010) Timor-Leste National Adaptation Programme of Action to Climate Change


� As per the GEF-6 Corporate Results Framework in the GEF Programming Directions and GEF-6 Gender Core Indicators in the Gender Equality Action Plan, provide information on these specific indicators on stakeholders (including civil society organization and indigenous peoples) and gender.  


� Same as footnote 8 above.


� See � HYPERLINK "http://www.undp.org/content/undp/en/home/operations/transparency/information_disclosurepolicy/" �http://www.undp.org/content/undp/en/home/operations/transparency/information_disclosurepolicy/� 


� See � HYPERLINK "https://www.thegef.org/gef/policy_guidelines" �https://www.thegef.org/gef/policy_guidelines� 


� MCCSAP is national level climate change strategy and Action Plan which was developed by Ministry of Natural Resources and Environmental Conservation and partner agencies. The draft od plan has been completed in July 2016 GIVE WEB LINK


� See � HYPERLINK "https://www.thegef.org/gef/policies_guidelines" �https://www.thegef.org/gef/policies_guidelines�


� See � HYPERLINK "https://www.thegef.org/gef/gef_agencies" �https://www.thegef.org/gef/gef_agencies�


� See guidance here:  � HYPERLINK "https://info.undp.org/global/popp/frm/pages/financial-management-and-execution-modalities.aspx" �https://info.undp.org/global/popp/frm/pages/financial-management-and-execution-modalities.aspx�





� Excluding project team staff time and UNDP staff time and travel expenses.


� The costs of UNDP Country Office and UNDP-GEF’s participation and time are charged to the GEF Agency Fee.


� GEF policies encompass all managed trust funds, namely: GEFTF, LDCF, and SCCF 


� Baseline, mid-term and end of project levels must be expressed in the same neutral unit of analysis as the corresponding indicator.


� Risks must be outlined in the Feasibility section of this project document.  


�   If at CEO Endorsement, the PPG activities have not been completed and there is a balance of unspent fund, Agencies can continue to undertake the activities up to one year of project start.  No later than one year from start of project implementation, Agencies should report this table to the GEF Secretariat on the completion of PPG activities and the amount spent for the activities.  Agencies should also report closing of PPG to Trustee in its Quarterly Report.





