Request for CEO endorsement/Approval

Project Type: Full-Sized Project

the GEF Trust Fund

# Submission Date:      3 November 2010

| Expected Calendar (mm/dd/yy) |  |
| --- | --- |
| Milestones | Dates |
| Work Program (for FSPs only) | 11/12/09 |
| Agency Approval date | January 2011 |
| Implementation Start | January 2011 |
| Mid-term Evaluation (if planned) | September 2012 |
| Project Closing Date | July 2014 |

# part i:  project Information

# GEFSEC Project ID: 3900

# gef agency Project ID: 4219

# Country(ies): Global

Project Title: GEF IW:LEARN: "Strengthening IW Portfolio Delivery

and Impact.”

# GEF Agency(ies): UNDP, UNEP

# Other Executing partner(s): UNOPS, UNEP-DEWA, UNESCO, GWP-Med, UNU-INWEH

# GEF Focal Area(s): International Waters

# GEF-4 Strategic program(s): Cross-cutting IW SP 1, 2, 3, 4

# Name of parent program/umbrella project:  MENARID

- Project framework  (Expand table as necessary)

| Project Objective: To strengthen global portfolio experience sharing and learning, dialogue facilitation, targeted knowledge sharing and replication in order to enhance the efficiency and effectiveness of GEF IW projects to deliver tangible results in partnership with other IW initiatives. |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| ### Project Components | ### Indicate whether Investment, TA, or STA2 | Expected Outcomes | ### Expected Outputs | ### GEF Financing1 |  | Co-Financing1 |  |  | Total ($) c=a+ b |
|  |  |  |  | ### ($) a | ### % | ### ($) b | ### % |  |  |
| 1. MENARID Programme – Support via Land/Ground Water Integrated Management and regional Portfolio Learning and Dialogue (UNDP) | TA/STA | 1) Improved effectiveness in combating Land Degradation in MENARID through an enhanced role of groundwater and improved subsurface space management 2) Enabling regional inter-basin coordination to enhance management capacity of institutions and project partners. | a) 5 mechanisms for integration of groundwater dimensions within 100% of the MENARID program projects (UNESCO) b) 2 regional approaches to transboundary water cooperation advanced in the Southeastern Europe and Mediterranean region (GWP-Med) c) 3 regionally-defined functioning communities of practice of GEF IW project stakeholders and partners, managed by regional institutions and conducting 15 twinning/learning experience exchanges and 9 workshops (UNDP, UNEP) | 941,000 | 48 | 1,000,000 | 52 |  | 1,941,000 |
| 2. Learning and Replication of Good Practices in Transboundary Surface and Groundwater Management (UNDP) | TA/STA | 1) Increased capacity of GEF groundwater and freshwater basin projects to exchange experiences and replicate successful groundwater management approaches and practices to address adaptive management. 2) Lessons and science from GEF groundwater portfolio incorporated into and disseminated through networks, partners, and processes, strengthening the GEF IW GW portfolio. | a) 2 functioning & facilitated communities of practice (COP) for at least 100% of GEF IW groundwater and 75% of river basin project stakeholders and partners (UNESCO, UNDP, IUCN) b) Functional dialogue, twinning, and 5 learning exchanges within and between groundwater and river basin CoPs and mechanism of partnership with the global LME network (UNDP) c) At least 2 dialogues with regional focus (Africa, Asia and the Pacific, Latin America and SIDS) facilitated between GEF groundwater projects and ongoing relevant efforts (UNESCO) d) 20 experience Notes, policy briefs, special articles and case studies on good practice solutions for groundwater management (UNESCO) | 431,000 | 40 | 650,000 | 60 |  | 1,081,000 |
| 3. Global and GEF IW Portfolio Learning and Dialogue to Enhance Project Delivery and Impact (UNDP/UNEP) | TA/STA | 1) Global GEF IW portfolio performance and capacities strengthened, in particular among project managers of GEF IW projects 2) Increased awareness of GEF IW experiences and achievements and partnership with non-GEF supported interventions 3) Improved technical implementation of projects through strengthening the science base of IW projects and improved integration of the wider science community into these projects. | a) 6th Biennial GEF International Waters Conference in the Mediterranean region for 300+ portfolio stakeholders (UNDP) b) 20 years of GEF IW project results presented at IWC-6 collated, analyzed and disseminated in proceedings, including 30 Experience Notes and an IWC-7 roadmap (UNDP) c) 4 IWC6 host Mediterranean region projects’ dedicated sessions at IWC6 (UNDP) d) Facilitated dissemination of best practices from GEF IW projects and partners in 8+ approved global dialogue processes to transfer experiences and know-how (UNDP) e) Completion of the first GEF IW Science Conference for 150 practicioners (UNEP) f) 2 functional scientific networks integrating IW project experts and the wider scientific community (UNDP, UNU) g) GEF IW project results & achievements captured in peer-reviewed 6 journal articles per year and 2 publications (UNDP, UNU) | 939,000 | 45 | 1,150,000 | 55 |  | 2,089,000 |
| 4. Information Management and Communications Platform to Support GEF IW Projects Learning and Dialogue (UNEP) | TA/STA | 1) Improved web-based information and knowledge management and utilization of the IW resource center and project communication platforms 2) Enhanced visibility and visualization of project activities and results facilitates cooperation and replication. 3) Enhanced stakeholder access to data and results from IW projects. | a) User-driven and user-friendly functionality for thematic Communities of Practice (CoPs)/workspaces and individual project toolkit websites at iwlearn.net (UNEP) b) Training and technical assistance for individual project website development and links to 26 UN-Water family platforms, to support targeted knowledge sharing and dialogues (UNEP) c) Portfolio visualization tools (utilizing e.g. Google Earth and video), applications and regular news dissemination including e-updates (UNEP) d) 10 workspaces for specific portfolio subgroups such as COPs, project managers and governments, and IWTF (UNEP) e) A comprehensive searchable catalogue of at least 100 GEF IW projects’ experiences and results (UNEP, UNU) | 810,000 | 50 | 809,824 | 50 |  | 1,619,824 |
| 5. Programmatic Management Tools and Innovative Approaches related to Climate / Water and Private Sector Participation to Enhance GEF IW Portfolio Project Performance (UNDP) | TA/STA | 1) Improved standardization and harmonization of new GEF methodological approaches as well as results-based management in IW projects to help address new global issues & improve performance, including vulnerability to climatic vulnerability & change in transboundary basins. 2) Public-private partnerships promoted and facilitate sustainability of GEF IW interventions | a) A revised, and GEF IWTF endorsed, TDA/SAP on-line training course that incorporates emerging issues of gender mainstreaming , financial sustainability, and supports new approaches to adaptive management for climatic variability & change (UNDP) b) Leadership training for IW project managers, based on an IW focal area on-line manual and capacity-building to support skills required, including understanding RBM and training in utilization of the IW tracking tool (UNDP) c) The climate issue introduced to the IW portfolio; testing 2-3 risk-insurance mechanisms and other economic instruments on the basis of vetted climate risk assessment methodology (UNDP) d) GEF IW and other experience with public-private partnerships codified and demonstrated in 2-3 new projects (UNDP) e) Methodology to address climatic vulnerability & change impacts in shared water bodies (UNDP) | 424,000 | 31 | 950,000 | 69 | 1,374,000 |  |
| 6. Monitoring, Learning, Adaptive Feedback and Evaluation |  |  |  | 150,000 | 48 | 165,500 | 52 |  | 315,500 |
| 7. Project management |  |  |  | 400,000 | 45 | 479,500 | 54 |  | 879,500 |
| Total Project Costs |  |  |  | 4,095,000 | 44 | 5,204,824 | 56 |  | 9,299,824 |

1    List the $ by project components.  The percentage is the share of GEF and Co-financing respectively of the total amount for the component.

2   TA = Technical Assistance; STA = Scientific & Technical Analysis.

# B.  Sources of confirmed Co-financing for the project (expand the table line items as necessary)

| Name of Co-financier (source) | Classification | Type | Project | %* |
| --- | --- | --- | --- | --- |
| UNDP Energy & Environment Group | Impl. Agency | In-kind | 1,348,000 | 25.90 |
| UNDP Energy & Environment Group | Impl. Agency | Grant | 415,000 | 7.97 |
| UNDP Bratislava Regional Centre | Impl. Agency | In-kind | 60,000 | 1.15 |
| UNEP-DEWA (Comp4) | Impl. Agency | In-kind | 701,824 | 13.48 |
| UNEP-Interdivisional Water Group (Comp3) | Impl. Agency | In-Kind | 200,000 | 3.84 |
| UNEP (Comp7 – PM/PCU) | Impl. Agency | In-kind | 50,000 | 0.96 |
| UNEP Caribbean Enivronment Programme (Comp1) | Multilat. Agency | In-kind | 100,000 | 1.92 |
| UNU-INWEH | Multilat. Agency | In-kind | 1,240,000 | 23.82 |
| UNESCO (Comp 1&2) | Multilat. Agency | In-kind | 550,000 | 10.57 |
| UNECE | Multilat. Agency | In-kind | 60,000 | 1.15 |
| Cornell University | NGO | In-kind | 40,000 | 0.77 |
| Sea-Start (Comp1) | NGO | In-kind | 130,000 | 2.50 |
| IUCN-WANI | NGO | In-kind | 202,000 | 3.88 |
| Sea-Start (Comp4) | NGO | In-kind | 108,000 | 2.08 |
| Total Co-financing |  |  | 5,204,824 | 100% |

* Percentage of each co-financier’s contribution at CEO endorsement to total co-financing.

# C. Financing Plan Summary For The Project ($)

|  | Project Preparation a | Project b | Total c = a + b | Agency Fee | For comparison: GEF and Co-financing at PIF |
| --- | --- | --- | --- | --- | --- |
| GEF financing | 220,000 | 4,095,000 | 4,315,000 | 431,500 | 3,900,000 |
| Co-financing | 250,000 | 5,204,824 | 5,454,824 |  | 4,265,000 |
| Total | 470,000 | 9,299,824 | 9,769,824 | 431,500 | 8,165,000 |

# D.  GEF Resources Requested by Agency(ies), Focal Area(s) and Country(ies)1

| GEF Agency | Focal Area | Country Name/ Global | (in $) |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  |  | Project (a) | Agency Fee ( b)2 | Total c=a+b |
| UNDP | International Waters | Global | 3,160,000 | 316,000 | 3,476,000 |
| UNEP | International Waters | Global | 935,000 | 93,500 | 1,028,500 |
| Total GEF Resources |  |  | 4,095,000 | 409,500 | 4,504,500 |

1  No need to provide information for this table if it is a single focal area, single country and single GEF Agency project.

2    Relates to the project and any previous project preparation funding that have been provided and for which no Agency fee has been requested from Trustee.

# E. Consultants working for technical assistance components:

| ### Component | ### Estimated person weeks | ### GEF amount($) | ### Co-financing ($) | ### Project total ($) |
| --- | --- | --- | --- | --- |
| ### Local consultants* | 335 | $275,000 | $490,000 | $765,000 |
| ### International consultants* | 96 | $226,000 | $295,000 | $521,000 |
| ### Total | 431 | $501,000 | $785,000 | $1,286,000 |

*  Details to be provided in Annex C.

# f. Project management Budget/cost

| ### Cost Items | ### Total Estimated person weeks/months | ### GEF amount ($) | ### Co-financing ($) | ### Project total ($) |
| --- | --- | --- | --- | --- |
| ### Local consultants* |  |  |  |  |
| ### International consultants* | 182 | 327,600 | 390,500 | 718,100 |
| ### Office facilities, equipment, vehicles and communications* |  | 57,400 | 69,000 | 126,400 |
| ### Travel* |  | 15,000 | 20,000 | 35,000 |
| ### Others** |  |  |  |  |
| Total |  | 400,000 | 479,500 | 879,500 |

*  Details to be provided in Annex C.   ** For others, it has to clearly specify what type of expenses here in a footnote.

G. Does the project include a “non-grant” instrument? yes     no 
      (If non-grant instruments are used, provide in Annex E an indicative calendar of expected 
        reflows to your agency and to the GEF Trust Fund).

# H. describe the budgeted m &E PLAN:

The project M&E plan is consistent with the GEF Monitoring and Evaluation policy. The Project Results Framework presented in Annex A includes SMART indicators for each expected outcome as well as mid-term and end-of-project targets. These indicators along with the key deliverables (outputs) and benchmarks will be the main tools for assessing project implementation progress and whether project results are being achieved. The means of verification and the costs associated with obtaining the information to track the indicators are summarized in below.

The M&E plan will be reviewed and revised as necessary during the project inception workshop to ensure project stakeholders understand their roles and responsibilities Indicators and their means of verification will be fine-tuned at the inception workshop. Day-to-day project monitoring is the responsibility of the PCU but other project partners will have responsibilities to collect specific information to track indicators under their respective component activities.

The project Steering Committee, including all project partners, will receive periodic reports on progress and will make recommendations to UNDP and UNEP concerning the need to revise any aspects of the Results Framework or the M&E plan. Project oversight to ensure that the project meets GEF policies and procedures is the responsibility of UNDP RTA and UNEP DGEF Task Manager. They will also review the quality of draft project outputs, provide feedback to the project partners, and establish peer review procedures to ensure adequate quality of scientific and technical outputs and publications.

Project supervision will take an adaptive management approach. The UNDP RTA and UNEP DGEF Task Manager will develop a project supervision plan at the inception of the project which will be communicated to the project partners during the inception workshop. The emphasis of the supervision will be on outcome monitoring but without neglecting project financial management and implementation monitoring.  Progress towards delivering the agreed project global environmental benefits will be assessed with the Steering Committee at agreed intervals. Project risks and assumptions will be regularly monitored both by project partners and GEF Agencies. Risk assessment and rating is an integral part of the Project Implementation Review (PIR) and will be regularly updated in Atlas. The quality of project monitoring and evaluation will also be reviewed and rated as part of the PIR. Key financial parameters will be monitored quarterly to ensure cost-effective use of financial resources.

A mid-term management evaluation will take place around July 2012. The review will include all parameters recommended by the GEF, UNDP and UNEP Evaluation Offices for evaluations and will verify information gathered through the GEF tracking tools, as relevant. The review will be carried out using a participatory approach whereby stakeholders will be consulted. The project Steering Committee will participate in the mid-term review and develop a management response to the evaluation recommendations along with an implementation plan.

An independent terminal evaluation will take place at the end of project implementation.

The GEF tracking tools will be updated at mid-term and at the end of the project.

| Type of M&E activity | Responsible Parties | Budget US$ Excluding project team staff time | Time frame |
| --- | --- | --- | --- |
| Inception Workshop and Report | - Project Manager - UNDP GEF – UNEP GEF | Indicative cost: 10,000 USD | Within first two months of project start up |
| Measurement of Means of Verification of project results. | - UNDP GEF – UNEP GEF /Project Manager will oversee the hiring of specific studies and institutions, and delegate responsibilities to relevant team members. | To be finalized in Inception Phase and Workshop. | Start, mid and end of project (during evaluation cycle) and annually when required. |
| Measurement of Means of Verification for Project Progress on output and implementation | - Oversight by Project Manager - Project team | To be determined as part of the Annual Work Plan's preparation. | Annually prior to ARR/PIR and to the definition of annual work plans |
| Project Steering Committee (incl IW project managers) | - Project Manager and PCU - UNDP GEF – UNEP GEF - Project partner agencies | Indicative cost: 20,000 USD | SC meetings held once per year |
| APR/PIR | - Project manager and PCU - UNDP RTA - UNDP EEG - UNEP GEF | None | Annually |
| Periodic status/ progress reports | - Project manager and PCU | None | Quarterly |
| Mid-term Evaluation | - Project manager and PCU - UNDP RCU - UNEP EO - External Consultants (i.e. evaluation PCU) | Indicative cost: 40,000 USD | At the mid-point of project implementation. |
| Final Evaluation | - Project manager and PCU, - UNDP RCU - UNEP EO - External Consultants (i.e. evaluation PCU) | Indicative cost : 70,000 USD | At least three months before the end of project implementation |
| Project Terminal Report | - Project manager and PCU - local consultant | 0 | At least three months before the end of the project |
| Audit | - UNDP RCU - Project manager and PCU | Audit is mandatory at least once in the project life. Indicative cost: 10,000 USD | Yearly |
| TOTAL indicative COST Excluding project team staff time and UNDP staff and travel expenses |  | 150,000 USD |  |

part ii:  project justification:

- State the issue, how the project seeks to address it, and the expected global environmental benefits to be delivered:

The GEF International Waters (IW) portfolio comprises 170 projects to date, including 16 multi-focal area projects, and consists of some US$1.1 billion of GEF grants invested in 149 different countries globally. This investment leveraged approximately US$4 billion in co-financing. By all accounts and many evaluations, since the inception of the GEF in 1992, the portfolio has delivered real results and replicable experiences to be scaled-up and mainstreamed globally. At the start, the portfolio was marginally interested in sharing its experience with itself. However, after previous phases of IW:LEARN demonstrated different learning methodologies, processes now exist that have engaged the portfolio in such experience sharing. Proven GEF IW:LEARN methodologies are now ready to be up-scaled portfolio-wide, utilizing the proposed project, to enhance the application of GEF IW experiences to improve portfolio quality and mainstream the capacity to address transboundary concerns and assist with addressing climatic vulnerability & change. Moreover, the need for a new GEF IW:LEARN project lies in the continued demand for:

- Assisting established and especially new projects in acquiring relevant knowledge related to transboundary waters management to improve project design

- Enhancing the understanding and application of GEF IW experiences across the portfolio to produce better quality project results

- Facilitating the replication and upscaling of good practices in transboundary waters management resulting in less costs and improved capacity to address transboundary concerns

- Ensuring that insights generated through project interventions are shared and add value to the portfolio and beyond

GEF IW:LEARN began in 1997 as an experimental portfolio-wide knowledge management and capacity building initiative, which encouraged networking, launched a Distance Masters program and organized the first GEF IW Conference (IWC) in Budapest in 2000. A foundational project during the period 2000-2003 provided knowledge management training and on-demand technical assistance for GEF IW projects, as well as piloting of a number of learning tools. The subsequent Operational Phase of IWLEARN (2004-2008), built on pilot phase lessons, and developed a strategic approach to knowledge management, manifested by a consolidated knowledge management service line: project-project exchanges, targeted training workshops, portfolio-wide learning at the GEF Biennial International Waters conferences, knowledge products on, for example, Payment for Ecosystem Services and Stakeholder Engagement, information management, technical support to website development, regional and global dialogue processes, support for communities of practice and a help desk. At this point, the IW:LEARN its conceptual framework & operational strategy constitutes the most advanced learning project in the portfolio, and will be uniquely positioned to help guide expanding GEF knowledge management processes.

Key results of the operational phase included, in brief, 9 targeted trainings (on inter alia, stakeholder engagement, economic valuation, environmental flows, payment for ecosystem services, IWRM planning, LME governance) serving 319 stakeholders from 57 projects, the two most recent Global International Waters Conferences (IWCs), 10 learning exchanges (on inter alia, TDA-SAP preparation, Project Communications, Coastal Zone and Tourism Management, Nutrient Pollution Management, Wetland Restoration, Climate Change Adaptation, Groundwater, Information Management) serving 23 projects, a content management platform with subsidiary website toolkit, and a DVD on Large Marine Ecosystems (LMEs). Operational phase outputs also resulted, amongst others, in the advancement of a transboundary water governance process in South Eastern Europe and other achievements, such as the signing of a joint groundwater management protocol.

The successful outcomes, ranging from tripled levels of co-finance for targeted workshops leveraged to the development of training courses based on IW:LEARN trainings, from previous IW:LEARN projects, compels the development of a full-scale effort among GEF agencies and new partners to address the new pressures on water systems such as climatic vulnerability & change and per OPS 3 recommendations for IW to scale up assistance. As explicitly noted in the independent terminal evaluation of the most recent Operational Phase, “The IW:LEARN model has successfully led to a number of products and a series of services which are highly valued by all who were asked. All wish to see these continue.” This sentiment is also confirmed in numerous post-conference and post-workshop evaluations. The GEF agencies are committing increasing amounts of programming resources toward knowledge management in their work plans. This provides a strong programmatic basis to benefit from and build upon in terms of knowledge management and experience-sharing across individual projects and initiatives. However, in the absence of the GEF increment, and a fully executed IW:LEARN Sustainability Plan to facilitate knowledge management across the GEF agencies, adult learning and experience-sharing across GEF IW projects will not occur comprehensively or efficiently portfolio-wide. This situation would needlessly constrain the pace and quality of project implementation and delivery thus limiting the potential depth and scope of IW success. Numerous opportunities would be missed for projects to leverage emerging information technology for greater stakeholder learning, transparency and participation in transboundary waters management. IW projects would become disconnected from broader global initiatives to share the natural resources of freshwater and marine ecosystems (e.g., Johannesburg Plan of Implementation (JPOI) and the Millennium Development Goals (MDGs)). Project personnel, agencies and government partners would operate in an experience vacuum significantly limiting opportunities to improve the overall performance and impact of the GEF IW portfolio.

Without the GEF increment, there is no mechanism for projects to highlight their successful innovations and to share their experiences, reducing the potential for up-scaling successful approaches.

As noted by a GEF Council Representative, in the absence of a global convention on water, the GEF IW:LEARN provides a forum for the meeting/discussions of stakeholders and projects. There is more work to be done on improving project performance, the accessibility of IW project results, mainstreaming experience sharing and developing a set of mechanisms to meet new and global IW-critical issues, such as climatic vulnerability & change, gender mainstreaming, and the use of public-private partnerships.

Finally, at a regional level, the GEF has increased its focus on the Mediterranean and MENARID regions, as well as on groundwater management issues. Work underway in these regions provide, in particular, useful lessons on nation-to-nation cooperation in transboundary management of water resources—resources of significant global as well as regional economic and social value which are also especially vulnerable to climatic changes. In response to country requests and global imperatives, the GEF IW focal area will direct attention to groundwater, recognising that this vital resource is often transboundary in nature, underlying multiple countries. The new IW:LEARN project includes cross-project and agency learning support to GEF project teams on methodologies for groundwater/surface water management, especially concerning aquifer protection and recharge issues in the MENARID region with mobilizing new partners.

The proposed project includes five inter-related and mutually supportive components: 1) MENARID Support via Land/Ground Water Integrated Management and Support to Regional Portfolio Learning & Dialogue, 2) Learning and Replication of Good Practices  in Transboundary Surface & Groundwater Management, 3) Global and GEF IW Portfolio Learning and Dialogue to Enhance Project Delivery and Impact, 4) Information Management and Communications Platform to Support GEF IW Projects Learning and Dialogue and 5) Programmatic Management Tools and Innovative Approaches related to climate/water and Private Sector Participation  to Enhance GEF IW Portfolio Project Performance.

Component 1: MENARID Programme - Support via Land/Ground Water Integrated Management and Regional Portfolio Learning & Dialogue (regional, to be carried out by UNESCO-IHP, GWP-Med, UNDP and partners). The Mediterranean Sea region, as well as the MENARID region, now benefit from significant GEF investment, especially in international waters. The region faces acute and distinct challenges that GEF projects are trying to address. Specifically, the MENARID region must manage acute water shortage and rely increasingly on stressed aquifers to meet water demand. It also offers existing and potentially new innovative approaches to transboundary water management that could benefit the entire GEF IW portfolio. UNESCO, with its International Hydrological Programme (UNESCO-IHP) lies at the forefront of transboundary aquifer management. Their core budget features a dedicated programme, ISARM, with a network of specialists, guidance tools, data management and advocacy (including the recent advancement of legal articles at the ILC). The GEF increment will support a technical group to convene both groundwater and land managers to foster an integrated approach to land, agriculture and groundwater management. The technical group will focus on regional land/groundwater learning, linking projects in the MENARID region with other IW groundwater projects elsewhere in the world. It will also support the development of more capacity building materials and targeted workshops to assist IFAD- and IBRD-implemented projects.

The Mediterranean, including the Southeastern Europe region, also features innovative approaches to fostering regional cooperation over transboundary waters. The Global Water Partnership Mediterranean (GWP-Med), helps lead the Athens-Petersberg Process, a regional dialogue initiative co-sponsored by the World Bank, GEF, Germany and the Greek government. In addition, GWP-Med helps coordinate other regional cooperation processes, including the EuroMed and COMPSUD. The GEF increment, will be matched by existing partners, in particular the German government, to support water governance processes in the region. The activity will further demonstrate an innovative multi-basin approach to water management, by deepening dialogue and experience-sharing in Southeastern Europe and around the Mediterranean, as well as sharing these experiences globally. Projects in other regions will be able to benefit from these and exchange experiences as well as non-GEF cooperation processes.

Finally, the component will focus on the replication and tailoring of the global IW:LEARN service line at the regional level. In three GEF regions, the project will work with a key regional partner institution (Rhodes University in sub-Saharan Africa, the Caribbean Regional Environment Programme in Latin America and the Caribbean and Sea-Start in Southeast Asia and the Pacific). These regional technical groups will be established to network among GEF IW projects (marine and freshwater) and provide a virtual (web) space to store region-specific information. Learning exchanges, including targeted training, will be conducted, and good practices and achievements will be captured and disseminated through GEF IW Experience Notes. As a result, the component will improve land and groundwater management in the MENARID region to help combat degradation, deepen inter-basin cooperation in the Mediterranean and finally, disseminate those lessons to enhance capacity in all GEF regions through the global IW:LEARN resource center and involvement in targeted learning activities.

Component 2: Learning and Replication of Good Practices in Transboundary Surface & Groundwater Management (global, to be carried out by UNESCO, UNDP and partners). CoPs for river & lake basin management and groundwater will be established within the IW portfolio with help of partners.  GEF IW surface water and groundwater projects and partners face increased urgency to share experiences given the impact of global financial and trade pressures and climatic vulnerability & change. UNESCO-IHP is aimed at supporting a study of good water management practices and management tools to enhance efficient use and protection of surface and ground water systems. The strong intergovernmental leadership with the IHP framework allows UNESCO to harmonize global plans with the national priorities through over 160 IHP national committees. UNESCO brings on board internationally accepted wealth of knowledge and networks for ecologically sustainable management of shared waters including relevant legal and policy articles and generic cooperative potential frameworks. UNESCO will be able to mobilize matching funds through partner countries commitments and the execution of synergistic IHP-VII regular program activities (2009-2013) which are formulated by the member countries and are in line with proposed action area. The GEF increment will build on these existing activities, with UNESCO heading the interlinking of groundwater projects in a CoP and UNDP and partners leading the river basin/surface water community of practice, supported by the standard suite of knowledge management services (learning exchanges and twinning, experience notes and supporting information management and communication platforms). The project will work with IUCN-WANI on the surface water community of practice. Ultimately, the component will result in an increased capacity among GEF projects in these water systems to replicate their experiences, reduce management transaction costs, enhance integration of surface and groundwater management and finally, increase the science-based understanding of groundwater resources, including the effects of climatic vulnerability & change.  Important partners with co-financing and know-how to help build portfolio capacity on the river basin/surface water CoP are the Danube Commission-ICPDR, Murray-Darling Basin Authority, International Joint Commission and Great Lakes Fishery Commission in North America, and the South Florida Water Management District.

Component 3: Global and GEF IW Portfolio Learning and Dialogue to Enhance Project Delivery and Impact (Global, to be carried out by UNDP, UNEP, UNU-INWEH, GWP-Med, host country(ies) and other partners). The Biennial GEF International Waters Conferences (IWC’s), five of them since 2000, offer a unique opportunity for representatives of the entire GEF IW portfolio, agencies, and partners to share experiences and build capacity in a South-to-South framework.  The GEF agencies are committing increasing amounts of their core programmes and budgets to support these portfolio learning events, including staff participation and agenda design, as well as resources for workshops before and during the event. The 6th GEF IWC will maintain a specific focus on targeted training and the sharing of experience from projects in the Mediterranean host region. Building on the active learning format of the 4th GEF IWC in Cape Town, and the 5th GEF IWC in Australia, the 6th GEF IWC will convene about 300 representatives of governments cooperating in strategic transboundary water resources management programs, GEF IW project managers and execution partners. The IWC will feature an innovation marketplace, extensive opportunities for focused learning on scientific and technical innovations, interaction with the GEF Secretariat, GEF agencies and executing agencies on policies, procedures and project management, as well as ample time for the participant-directed workshops, peer-to-peer project advising sessions and real-time video reflections. The conference will be utilized to highlight GEF IW projects contributions to ecosystem-based management and sustainable development targets. Given the 20th anniversary of the GEF International Waters focal area, it is also a unique moment to use the IWC to examine the results of 20 years of the GEF. Finally, the conference will also serve as the primary venue to showcase results from the project’s other components, but also importantly a venue to run training courses based on the outputs from Component 5 (i.e. the TDA-SAP course with its new features on RBM, gender mainstreaming and CC adaptive management as well as new emphasis on financial sustainability). The Component will also support the first GEF IW Science Conference bringing the experts involved in IW projects together with the wider scientific community to further enhance the projects’ performances. Lastly, the Component will support the further dissemination of GEF IW results through a journal and the preparation of a short film highlighting the achievements of the last 20 years of the GEF support to IW project activities. Without IW:LEARN, GEF IW projects would remain detached from global dialogue processes, such as the World Water Forum. As a result, GEF IW achievements would not be disseminated and global awareness in the water and fisheries sectors as well as potential partnerships would not be realized. The GEF agencies are currently often independently facilitating and supporting these events and coherence among GEF agencies and projects needs a platform for presentation and a focus on the GEF brand. This component will then correct this problem and help mobilize GEF IW projects sharing their experiences with global dialogues and policy debates under a GEF banner on freshwater, oceans, and groundwater.

Component 4: Information Management and Communications Platform to Support GEF IW Projects Learning and Dialogue (global, to be carried out by UNEP, and partners). Information management, backed by a robust content or knowledge management platform, forms a key IW:LEARN service that backstops the experience-sharing and capacity development activities the project conducts. UNEP brings to this component and the development of the IW Resource Center a robust understanding of data and information management to support ecosystem management and policy making. The organization has made significant investments in the realm of data management, science-based networking, early warning and assessment of emerging environmental issues and trends. Moreover UNEP will leverage its programs covering timely, scientifically credible, policy-relevant environmental data and information for decision-making and action planning. UNEP will utilize the GEF increment to service the GEF project community and support knowledge management of the GEF IW portfolio by effectively mating the IW:LEARN service line to its knowledge management activities. This component will improve information and communication about management practices by the portfolio through enhancement and expansion of technology utilized by both GEF IW:LEARN and the GEF IW project portfolio (i.e. the existing Website Toolkit) as well as good practices from UNEP’s portfolio on ecosystem-based management building upon its programmatic basis and experiences in ecosystem-based ground-, surface and coastal water management and the Regional Seas Programme. The current content management system will be improved with a more interactive functionality consistent with the growth of mainstream Internet-based applications. The improvements will facilitate the development of platforms, hosted at iwlearn.net, that support the communities of practice established by other components (see 1, 2 and 6) The improvements will also enable the platform to serve an important communications function. UNEP will deliver training workshops to catalyse the capacity of projects to apply cost effective technologies aimed at improving information exchange and learning and develop an online guide to bring projects on board with the new technology. This will ultimately increase dialogue among projects. Moreover, the component will make accessible and visible the results and achievements of 20 years of GEF IW projects by establishing an online archiving to systematically preserve IW project data and keep them available for future projects in a user-friendly way, and develop a portfolio visualization tool to ease the discovery of project activities in given spatial areas (using, for example, Google Earth or Microsoft Virtual Earth). A tool for visualizing the portfolio will be developed as a decision-support system by linking portfolio data to other information. Visualization will also include support for project multimedia capturing results whenever available. The component will also produce a monthly bulletin based on project updates. Finally, a long standing need to link the efforts of the GEF IW portfolio with efforts throughout the UN-Water family (other portfolios) will be addressed through the development of syndication links, i.e. the automatic sharing and searching of content across platforms (e.g. UN WaterWiki) throughout the global IW community. Additional cost-effectiveness will be realized through the access and replication of tools UNEP will develop. Finally, UNEP will utilize existing and new partnerships, for example the recently announced cooperation with Microsoft Corporation and ESRI, for addressing issues of knowledge sharing. In addition, UNEP will work with UNU-INWEH on the results archive, given the latter’s existing collection of project results established through the IW Science project.

Component 5: Programmatic Management Tools and Innovative Approaches related to climate/water and Private Sector Participation:  to Enhance GEF IW Portfolio Project Performance (global, to be carried out by UNDP, UNU-INWEH, and partners). While there are many policies and procedures that are common to most GEF IW projects, there is comparatively little guidance available to projects to implement those policies and procedures. Thus a need for such guidance exists based on efficiency gains that can be realized through the codification of such guidance. For their part, the GEF agencies have produced materials to guide their projects. The GEF increment will support the editing of such materials to support the broader portfolio, as well as online training courses for project managers to effectively utilize them. This component will produce a set of tools for the entire GEF IW portfolio, with the aim of improving project performance as well as the harmonization of GEF methodological approaches across the portfolio. The TDA-SAP approach is the primary GEF methodological tool for transboundary projects, and yet there is little official guidance or consistent sharing of experience in application of this methodology. The project will expand and revise an existing draft TDA-SAP methodology and training course for official GEF IWTF endorsement and subsequent dissemination

The new methodology is needed to build portfolio capacity to address emerging issues not previously included (adaptive management for climatic vulnerability & change, mainstreaming gender, financial sustainability of regional institutions, economic valuation) and also be diversified to address the different water ecosystem types. Second, the project will develop an online GEF International Waters focal area manual, which collects the common aspects of GEF IW project design, development and implementation into knowledge product that supplements existing guidance specific to GEF Agencies. This will enable new project managers to get quickly up to speed on GEF management and reporting requirements, including proper use of the results-based management framework and GEF IW tracking tool. Development of such a manual was recommended in the GEF Program Study on International Waters (2004). Finally, one of the important outputs from this component will be support for the publication of peer-reviewed articles for submission to international journals. As a result, this component will improve project performance, increase leadership skills, strengthen partnerships and increase awareness of GEF interventions at both the global and regional levels.

GEF IW:LEARN has historically been at the forefront of designing and delivering new tools and approaches for the portfolio. As a whole, the portfolio faces new challenges and needs to have its capacity built to mainstream climatic vulnerability & change as an issue and integrate adaptation strategies into its projects. Moreover, insufficient numbers of projects are effectively utilizing public-private partnerships as a means both to finance and sustain GEF project interventions. The GEF agencies are active in both of these areas, conceiving and implementing new partnerships and programs to address these needs. In particular, UNDP is developing a climate risk insurance facility, which will conduct pilots of an index-insurance scheme to mitigate the effects of climatic vulnerability & change, and UNEP is spearheading the Finance Initiative. The GEF increment will support multiple demonstrations of this and the dissemination of experience to other projects. Similarly, the increment will also support replication of successful public-private partnerships in other projects, as well as the codification of lessons from those experiences. UNDP’s specialized programs, such as Cap-Net, will be highly leveraged to disseminate the results of pilots and codification exercises. Also, building on existing GEF Agency work, under this component a specific study on integrating Climate Change adaptation into IW projects will be commissioned. The component will result in the IW:LEARN project feeding innovations back into the GEF IW Projects.

The project will deliver global environmental benefits by fostering conditions for improved GEF IW project delivery and impact for transboundary water systems per the GEF Operational Strategy, as well as facilitating inter- and intra-regional adaptive learning processes necessary to accelerate the achievement of water resource-related JPOI and MDG targets. This is a critical change in IW:LEARN in focusing more on global MDGs to help the portfolio ensure its contribution whenever local demonstrations are conducted and to ensure that capacity exists to include gender mainstreaming.  Building directly on the foundations of the GEF IW portfolio of river & lake basin, groundwater systems, and large marine ecosystem (LME) projects, as well as the last three phases of the GEF IW:LEARN (projects from 1998-2009 inclusive), the project will raise the profile of transboundary water governance at the international level as a united GEF contribution to make a difference globally on the dialogue for this scale of action involving one-half the people on the planet and 65% of land area and all ocean area. It will establish mechanisms for learning in three key GEF regions. It will aim at catalyzing action and enhancing the effectiveness of the GEF International Waters portfolio through the provision of knowledge and the application of innovative techniques.

- Describe the consistency of the project with national and/or regional priorities/plans:

- As with all GEF projects, country-driveness is the sine qua non for the proposed project, and all IW projects assisted by IW:LEARN have the country GEF focal point endorsement. GEF IW:LEARN aims at supporting and improving the management of GEF international waters projects and enhancing the  projects’ capacity to address national priorities and plans. In terms of indicators from the operational phase, the IW:LEARN website had users from over 120 countries and its targeted training activities served people from over 100 countries. It is envisioned that such service levels can be sustained and increased with the proposed project and will be tracked with new indicators related to results-based management. The IWC’s also have a specific focus on the inclusion of government representatives, featuring on average, about 70 countries per conference. While all components directly support countries by supporting projects, the first component of the project specifically targets aquifer recharge and groundwater management, a critical issue for the countries of the MENARID region. The component also advances water governance processes in the Mediterranean, processes that are aimed at facilitating transboundary cooperation across focal areas among countries in that region.  There will be no progress in the MENARID region without this focus on linking groundwater capacity to the land-based efforts programmed by GEF.

- Describe the consistency of the project with gef strategies and strategic programs:

- The project meets GEF IW Strategic Objective 1 to foster international, multi-state cooperation on priority transboundary water concerns through more comprehensive, ecosystem-based approaches to management, and Objective 2 to catalyze transboundary action addressing water concerns, by assisting countries to utilize the full range of technical assistance, economic, financial, regulatory and institutional reforms that are needed.

- The project contributes, through its various components, to all four strategic programs as delineated in the GEF 4 focal area strategy for international waters, and is wholly consistent with the goals and objectives of GEF 5 including portfolio learning. Given a sub-focus on groundwater and a sub-activity in the MENARID region, it is specifically aligned with SP3 “Balancing overuse and conflicting uses of water resources in surface and groundwater basins that are transboundary in nature”. In addition, climatic vulnerability & change is addressed by the project as a cross-cutting issue in two components, the enhancement of the TDA-SAP course and also the development of risk-based insurance schemes.

- As noted in the GEF4 Revised Focal Area Strategies (paragraph 31), "Knowledge management and systematic learning is equally important to ensure that insights generated through project interventions add value internally and externally." Portfolio-wide, regional and targeted learning activities will strengthen--and measure--gains in institutional capacity of regional and national level partners, and the establishment of learning outcomes indicators is expected to enable project partners on the ground to continue building implementation capacity in water governance beyond completion of the project. Under this strategic program, paragraph 42 states that: “[…] Additionally, targeted learning will be undertaken for the IW portfolio to enhance experience sharing and learning, KM, and replication of good practices that contribute to sustaining livelihoods as well as food and water security.”

- More generally, through targeted experience-sharing and learning among the new and existing GEF IW projects in the portfolio, the capacity of projects to achieve objectives and replicate good practices before project completion will be enhanced.  Building on the foundations of the GEF IW:LEARN program, its web-based resource center (www.iwlearn.net), and in consultation with the GEF IW Task Force, the project carries forward South-to-South experience sharing among IW projects and their partners that contributes to better management practice in the GEF IW portfolio.

- justify the type of financing support provided with the gef resources.

- IW:LEARN is the flagship of the GEF international waters focal area and setting the cross-project and cross-agency experience sharing and learning agenda.  With the focal area lacking a overarching governing convention, IW:LEARN can be seen as filling the gap of the function of experience sharing and learning under conventions and their subsidiary bodies. At the moment, GEF agencies are conducting increasing amounts of experience-sharing activities that this project will leverage as it mainstreams agency learning and capacity into the GEF IW portfolio and brings new partners for capacity building in the portfolio. The GEF grant for the proposed project will fund a set of activities that leverage cost-savings and improve project performance for all projects in the focal area. By its nature, the project needs a grant to generate the positive externalities that regular project processes would not otherwise provide. One traditional role of grants is to support this type of public good.

- Outline the Coordination with other related initiatives:

# GEF-supported initiatives

- The project builds on experiences with the previous GEF IW:LEARN phases and will specifically build on the sustainability plan and final evaluation of the operational phase jointly implemented by UNDP and UNEP. The project will also coordinate with the Coral Triangle Initiative - IW:LEARN project, in particular to exchange experiences on the organization of IWC5 and to integrate portfolio recommendations for IWC6. Globally and in each GEF region, the project will coordinate with the overall GEF IW portfolio, providing services and knowledge management functions to it.

- Regionally, the project will coordinate with the projects under the MENARID program, and in particular with the UNEP-supported project on the North West Sahara Aquifer project, the IBRD-supported Land and Water Optimization Project and the IFAD-supported knowledge management and monitoring and evaluation project. The project will also focus on the other active, all UNDP- implemented GEF international groundwater projects (Dinaric Karst, Nubian Aquifer and Nile Groundwater), all in the Mediterranean region. The various projects under the GEF-UNEP-IBRD Mediterranean Strategic Partnership will also receive special attention given the large GEF investment in this basin. The GEF has also previously supported the Athens-Petersberg Process in concert with the World Bank, German and Greek governments, which addresses cooperation in a region that drains into the Mediterranean.

- Finally, special attention will be devoted to close coordination with the five other GEF IW “learning” projects, namely: Regional Dialogue and Twinning to Improve Transboundary Water Resources Governance in Africa, Promoting Replication of Good Practices for Nutrient Reduction and Joint Collaboration in Central and Eastern Europe, Good Practices and Portfolio Learning in Transboundary Freshwater and Marine Legal and Institutional Frameworks, Enhancing the Use of Science in International Waters Projects to Improve Project Results and Development of Methodologies for GEF Transboundary Waters Assessment. All these projects will be linked to the project and will use iwlearn.net as a platform for disseminating projects results and achievements.

# Non-GEF initiatives

- Strong linkages will be established between IW:LEARN and the UNDP pioneered WaterWiki (http://WaterWiki.net) which is presently being expanded to cover activities of an increasing number of UN-Water members. UNDP will ensure data and information flow to IW:LEARN from its core water projects e.g. Central Asia IWRM project, Human-Rights Based Approaches to Access to Water Supply and Sanitation, etc. The project will also coordinate with the UNDP Water Governance Facility at SIWI (WGF) which is a UNDP funded programme to support the implementation of UNDP’s Water Governance Programme. Main activity areas include policy and technical advice and support to water governance reform in developing countries through the UNDP system. Improving the water governance knowledge base through development, compilation and dissemination of water governance information, knowledge, methodologies and tools as a service to promote and advocate improved water resources management and water related services. Finally, the project will realize synergies with UNDP's other flagship capacity-building programme, Cap-Net, which focuses on development of IWRM and achievement of MDGs. Cap-Net has an experienced framework of capacity builders and the opportunity to develop knowledge into capacity building materials and scale up action on the ground. The project will coordinate extensively with Cap-Net, but in particular to translate the project's outputs into practical lessons suitable for wider adoption.

- UNEP has a strong programmatic basis in data management, building partnerships and creating knowledge in support of assessment processes and ecosystem-based management. UNEP will ensure the linkage between this and the IW Resource Center. With regard to groundwater, a number of UNEP programmes relevant to this project are under implementation: the Water Vulnerability Assessment; support to countries on the development of Integrated Water Resources Management strategies; mobilization and exchange of good practices, and in particular support to the African Groundwater Commission established under the AMCOW together with UNESCO.

- Coordination of the project will also be secured with key Mediterranean processes, inter alia, with: Mediterranean Component of the EU Water Initiative, Horizon 2020 to De-pollute the Mediterranean, Water Governance Programme in the Arab States, -Rabat Declaration Process on National IWRM Planning in North Africa, BGR activities on groundwater management, IUCN-WESCANA activities on groundwater management, Activities of the Arab Water Security Studies Centre of the League of Arab States on sharing of experiences for water resources management, Activities of the Working Group on Water of the Mediterranean Commission for Sustainable Development, Petersberg Africa Programme, Circle of Mediterranean Parliamentarians for Sustainable Development, Circle of Mediterranean Journalists for Sustainable Development and the Mediterranean Education Initiative for Environment and Sustainability. Furthermore, the project will be linked and contribute to the follow up activities of the Euro-Mediterranean Ministerial Conference on Water (2008) in the framework of the Union for the Mediterranean.

- Discuss the value-added of GEF involvement in the project  demonstrated through incremental reasoning :

- While the IW:LEARN Sustainability Plan included pledges by both GEF Agencies (UNDP, UNEP) and other partners to mainstream IW:LEARN’s knowledge management services, the need for the GEF increment persists. The terminal evaluation itself wrote that, “Even if the GEF Agencies continue with steps to institutionalize IW-Learning, the GEF Secretariat with its pivotal position is best placed to ensure sustainability of the IW:LEARN products and services.” In other words, a need still exists for centralized coordination, and the GEF’s support for a project that coordinates the partially mainstreamed services exists, until full mainstreaming within Agencies and project budgets occurs.

- Moreover, while key IW:LEARN services will be mainstreamed, there are still significant components of the project that transcend the GEF Agencies ability to serve the entire GEF IW portfolio, the GEF IW Conference for example. The new project will, as a result of the GEF increment, also develop new demand-driven tools (index-based risk insurance, recommendations on public-private partnerships, the TDA-SAP course, IW Focal Area Manual) that serve the entire GEF IW portfolio. In the absence of GEF investment, these new portfolio-wide tools will not be produced and existing services will be only partially continued with part of the GEF IW portfolio.

- This project represents a modest incremental cost which aims to leverage increased project effectiveness and results for GEF IW investments across the GEF portfolio. Through regional, thematic and portfolio learning and experience-sharing the project integrates GEF-supported transboundary experiences into global efforts to improve freshwater and marine resources management in the context of achieving JPOI and MDG Goals and adapting to climate variability and change. As GEF Council documentation has emphasized, facilitating transfer of lessons and experiences between projects is an important investment: potential yields are large in terms of improvements in replication efficiency and scaling up successful approaches.  This project focuses on this as it adds an increment to agency activities included in their IWLEARN sustainability plans and fosters new partnerships for building IW project capacity with new partners to address the new global issues being faced by transboundary water systems.

- Indicate risks, including climate change risks, that might prevent the project objective(s) from being achieved and outline risk management measures:

| Risk description | Rating | Mitigation measures |
| --- | --- | --- |
| Not all GEF IW projects are willing to engage in various types of portfolio learning activities or to expose any weaknesses in project implementation to external scrutiny | L | Project stakeholders are officially encouraged to utilize GEF IW:LEARN services at all levels of implementation and execution |
| Participants are sufficiently aware of GEF IW:LEARN and know how to both engage its services and provide their own experience to peers (via CoP participation, IWEN production IWC engagement and information syndication) | M | The project will effectively market its basic service line to the portfolio |
| A flood index for an insurance based mechanism is not feasible. This is a highly innovative index in an emerging area of climate risk financing. As compared to other tested index-based insurance products, the complexity stems from (i) transboundary nature of the risk considered; (ii) potential human intervention and subsequent willingness of the insurance industry to adopt the index | M | If the demonstration does not succeed, a methodology would still have been developed and capacity built on climate risk assessment in transboundary basins |
| With a global spread of constituents, the website and similar mechanisms cannot be replied upon to “pull” beneficiaries. There is a need to “push” (as the previous IW:LEARM team did with their direct interaction) as well as rely on “pull” for electronic products and services. | L | The project will make an investment in direct interaction with beneficiaries. Constituents need to be engaged to the extent possible to create a sense of ownership. |
| The proposed regional context is a positive step but it risks fragmentation (between regions and themes) and might weaken its global dimension and hence the cost benefit is much reduced. | L | The project's management will be specifically tasked with ensuring coherence (in their terms of reference) |
| Partners do not interact between different CoPs or follow requests to increase interactions from PCU/PSC | M | Agreements between partners/IAs/EAs will reflect importance of co-operation to ensure integrated approach |

- explain how cost-effectiveness is reflected in the project design:

- The cost-effectiveness of the project components draws upon partnerships to effect efficiencies in implementation. Preliminary partnership discussions are underway with Mediterranean countries regarding the co-hosting of IWC6 in 2011. Drawing upon local logistical and technical expertise could reduce operational costs relative to prior conferences. Above all however, the IW:LEARN project will be cost-effective because its services and newly-developed tools can produce economies of scale, in that they are developed and subsequently replicated for the entire GEF IW portfolio. The alternative is production of these services at the Agency or even lower levels.  GEF has found that working across projects and across agencies can provide the most cost-effective approach to capacity building, south-to-south experience sharing, and rapid incorporation into existing projects and new projects of innovative and good practices in TWM.

- Many of the tools designed into this project will result in cost-savings among the entire portfolio of GEF IW projects, in the form of reduced need for training, in terms of TDA-SAP preparation and GEF IW project management. The update to information technology can be easily replicated by the entire GEF IW portfolio meaning, for example, that all projects can use a common platform to disseminate their data, results and news without the need to retain information technology staff, pay for website hosting and related training. The focus on land and water issues in the MENARID will generate lessons for the global portfolio.

- The project will build effectively on existing GEF Agency programmes. In particular, the project will build on UNDP’s awareness raising on TBW issues thru the UN-Water Task Force on Transboundary Waters, investments in the further development of WaterWiki, the UNDP Water Governance Facility at SIWI (WGF), global processes like the World Water Development Report, training programs on Water Integrity (with Cap-Net and WaterNet), mapping of existing water governance methodologies to provide basis for further developments of how to work with governance in water in more practical ways. UNDP works to assist sub-national authorities (regions and cities) in developing countries by building their capacity to design and implement climate change strategies and investment plans, through the umbrella project “Down to Earth: Territorial approach to Climate Change.” (TACC) Community-based Adaptation also helps to build the resilience of communities and the ecosystems upon which they rely in the face of climate change impacts. UNDP also works with Coca-Cola, on initiative, “Inclusive Community-based Water Management and Adaptation to Climate Change project for Catalyzing Achievement of the MDG’s” that will provide support and contribute to the success of the IW:LEARN project.

- UNDP is working with the Columbia University – International Research Institute on Climate and Society – to identify innovative financial instruments and mechanisms in relation to adaptation to climate change. As part of that work, IRI will be working closely with river basin organizations to develop a conceptual framework for climate risk assessment in transboundary basins and for the development of a flood insurance index. Should this flood insurance index prove viable, it will be piloted in several river basins, through a facilitated dialogue between insurance/re-insurance industry and river basin organizations and through the development of transactable products.

- Moreover, the UNDP Bratislava Regional Centre will support the project, with its competencies in knowledge management and as a center of innovation among the UNDP regional centres. The BRC is also the host of UN WaterWiki. UNDP country offices in the Mediterranean regional will also be utilized to help support the IWC6. Critically, over the next few years, the UNDP’s Water Governance Programme will support programme staff, operating out of the UNDP Bratislava Regional Centre (where the IW:LEARN project coordination unit will be co-located), with shared responsibilities as part of the PCU.

- UNEP will leverage various types of support for the project's overall knowledge management platform and agenda, as well as the previously mentioned core programmes (in section A). UNEP has developed a comprehensive framework for the study of various water systems with the main objective of proposing best management options. A series of water programmes and projects (including for fresh, coastal and marine waters), are included under this framework and include amongst others, the Freshwater programme, the Regional Seas Programme, GPA, GEMS/Water programme, the GEO water cluster, the GEF-IW Science programme, Transboundary Waters Assessment Programme (TWAP), GRAME and so on.  A series of water atlases have also been published by UNEP. These programmes are carried out at all levels (global, regional and local). UNEP has recently strengthened its role in science through its office of the Chief Scientist in order to raise the science profile of the Organisation in close collaboration with other UN agencies and the scientific community. The current UNEP Chief Scientist is a water specialist.

- UNESCO will mobilise matching funds through partner countries commitments and the execution of synergistic IHP-VII regular program activities (2009-2013) which are formulated by the member countries and are in line with proposed action area. Further details on UNESCO IHP-VII program plan, preferences of areas of action indicated by the member countries and delivery mechanisms can be found at the following url: http://unesdoc.unesco.org/images/0015/001594/159400e.pdf.

- Regarding GWP-Med, co-financing is linked with the activities that they would lead or participate to as well as with the foreseen magnitude of activities. The Global Water Partnership – Mediterranean (GWP-Med), a wide multi-stakeholder partnership for promoting IWRM in the Mediterranean, has demonstrated expertise on key subjects addressed by this project, convening power, proven managerial capacity, an active network of regional and national partners, and is leading or participating in a number of international, regional and national programmes supported by various donors. GWP-Med is willing to lead activities in the Mediterranean and Southeastern Europe that have to do with regional dialogue processes, sharing of experiences and, to a certain extend, innovative approaches.

- IUCN has led the Water and Nature Initiative (WANI) since 2001. WANI is a worldwide action learning initiative supporting implementation of IWRM at local, national and basin level, using demonstration projects to enable learning and provide the evidence base for policy change. There are WANI demonstration river basins in Latin America, Africa, the Middle East, Asia and Oceania. WANI is implemented through an extensive network of community, NGO, government and inter-governmental partners, including the GEF. WANI began its second phase, focused on scaling up of river basin demonstrations and lessons learned, in 2009. Facilitating and managing a Community of Practice for learning and exchange on river basin management. This would build on the resources and networks built through its role as PAL for river basin learning under the previous phase of IW:LEWARN while aiming to (re) engage the current GEF-IW freshwater basin constituency, including through innovations in applications of the new IW:LEARN online tools. IUCN-WANI, though its network of demonstration sites and from action learning on implementation, has case studies, guidance and analytical frameworks to support integration of climate change adaptation and climate resilience into IW projects, as well as capacities to facilitate knowledge exchange.

- The UNU Institute for Water, Environment & Health (UNU-INWEH) is a member of the United Nations University family of organisations. It is the United Nations Think Tank on Water, created by the UNU Governing Council in 1996 to strengthen water management capacity, particularly of developing countries, and to provide on-the-ground project support.

# part iii: institutional coordination and support

# A. Institutional arrangement:

- IW:LEARN involves a large number of organizations working under the direction of a Project Co-ordination Unit and a Steering Committee. Overall project oversight and supervision will be the responsibility of an Inter-Agency Forum involving the two GEF Agencies. The following figure summarises the groups involved and the inter-linkages. A full description is provided below in section Part III.B.

# Figure 1: Institutional organization

# B. Project Implementation Arrangement:

## Implementation Arrangements

- IW:LEARN will be co- implemented by UNDP and UNEP as described in section A (part I and Part II) above. UNDP will be responsible for ensuring overall project supervision and will ensure consistency with the GEF policies and procedures.

- IW:LEARN will be executed through UNOPS for Components 1, 2, 3, 5 and the Project Management (Component 7) including M&E (Component 6). Component 4 (and 3.c.i. “The IW Science Conference”)) will be executed by UNEP-DEWA.

- Following the recommendations from Terminal Evaluation of the previous phase of IW:LEARN, the project will be managed through a single Project Co-ordination Unit (PCU). The PCU will have direct responsibilities for the overall project management and be well linked to all the partners undertaking the project sub-components and activities. The project partners will report to the IW:LEARN CTA/Project Manager. The CTA/Project Manager will report directly to the UNDP RTA based at Bratislava Regional Centre. The PCU will be located at one of the partners’ offices and will house the UNOPS CTA/Project Manager. Other PCU staff will be co-located or work remotely as agreed by UNDP/UNEP but reporting to the UNOPS CTA/Project Manager.

- The PCU will speak with one voice to IW:LEARN stakeholders.  The PCU will prepare Standard Operating Procedures and a common communication strategy for the implementation of IW:LEARN and will seek steering committee approval for these at inception. All information queries and service requests from projects will be documented and shared across the PCU in a central register.

- No single member of the joint (but distributed) PCU will conduct separate arrangements with GEF IW projects to ensure redundancy in IW:LEARN service delivery. Requests for services by IW projects will be responded to within 72 hours. This will form an addition to the already existing UNEP Service Level Agreement regarding the Website Toolkit. The PCU will produce common brochures and bulletins that serve the entirety of the project and are signed off by the CTA/project manager. All outreach will be agreed, and if necessary, affirmed with the steering committee. All critical information regarding IT arrangements, infrastructure and related information will be shared across the entirety of the PCU. The PCU will conduct internal weekly teleconferences in order to ensure the smooth coordination of the global operation of the IW:LEARN project. UNEP will ensure that all data and project websites is backed up regularly and that two redundant and independently located servers are in operation.

- These actions and procedures to be adopted by the PCU under the direction of the CTA/Project Manager will help in ensuring that IW:LEARN is effectively and efficiently implemented on a global scale.

- IW:LEARN involves a large number of GEF Agencies, Executing Agencies and other partners. Most of these are providing co-finance inputs to the project and therefore will be members of the Project Steering Committee (with the Project Co-ordination Unit acting as the Secretariat). As these partners are also responsible for project execution an ‘Inter-Agency Forum’ will be created to ensure there is adequate project oversight by the GEF Agencies and representatives from GEFSEC.

## Project Management

- Comprehensive project management will be achieved through a range of co-ordination, supervisory and advisory bodies to ensure the smooth and efficient delivery of all five project components with its 12 expected outcomes. The global perspective of the IW:LEARN project with stakeholders and partners spread widely will necessitate good communications and clear understand of objectives and activities by all parties. The management of IW:LEARN will include a number of a dedicated body to discuss and agree issues ensuring that all the partners, agencies and other stakeholders are fully represented in the overall co-ordination of this important and influential GEF IW project.

The following groups are anticipated:

- Inter-Agency forum

- Project Steering Committee

- Technical Advisory Group

- Project Co-ordination Unit

- To minimise costs meetings these groups will meet face-to-face infrequently, but will utilise ‘virtual’ methods and/or links with other planned meetings frequently.

- Inter-Agency Forum will provide a formal mechanism for the GEF Agencies to discuss project implementation and to resolve any competing issues likely to impact overall project performance. The meetings will also agree common reporting formats for PIR/APR and agree the Terms of References for the Mid-Term and Terminal Evaluations. Any issues relating to project M&E will first be discussed at this meeting. The forum will assemble prior to the Project Steering Committee with the PCU providing the secretariat. UNEP and UNDP will collaboratively develop agenda for discussion and will alternate in chairing the meeting. This body will provide formal approval of outputs and any programme changes recommended by the Project Steering Committee.

- Project Steering Committee will provide strategic guidance to the project execution and will formally supervise all activities undertaken through the PCU. The Steering Committee (SC) will be assembled at the inception of the project to guide overall project execution and to recommend approval of key steps and outputs to the Inter-Agency Forum. The SC will be comprised of representatives of the GEF Agencies, key partner organisations and selected stakeholders representing GEF IW projects (CTA/Project Manager).The SC, as main project authority, will establish the execution baselines, and consider annual operations plans and budgets, as well as quarterly and annual technical and financial reports and final technical reports. The SC will operate on the basis of consensus among its members The SC will meet once per year: in person and ‘virtually’ by telecon/web conference.

- The first SC (held during the Inception Workshop) will agree voting procedures and other operational arrangements for future meetings (both in person and web based). The first SC will be chaired by UNDP.

- The SC will review the management arrangements discuss and recommend for approval the Annual Work Programme, budget, and approve any changes and conclusions for inclusion in the APR/PIR

- Technical Advisory Group will provide technical guidance and assistance, where necessary, to the PCU and the sub-component activities of the IW:LEARN. This ad hoc group is planned to assist a number of sub-components (e.g. TDA developments - 5a, Project Manual – 5b, etc.) and will provide input to both the PCU and sub-components on the essential cross-cutting issues that are central to the IW:LEARN (e.g. gender mainstreaming, climatic variability & change, public-private partnerships, etc.). The Technical Advisory Group will be formed from within the IW community of projects from CTAs and project expert staff. Meetings will be held on a ‘demand basis’ and opportunities for addressing multiple issues and / or combining meetings with other regional/global event will assist in reducing travel costs to supplement the expected ‘web meetings’ planned for this group.

- Project Co-ordination Unit for the day-to-day execution of IW:LEARN will be established within one of the project partners’ offices. The UNOPS CTA/Project Manager will have responsibility for all operational aspects of the project: including preparation of annual workplans and budgets, drafting Terms of Reference for consultants, communication with partners, reporting to UNDP/UNOPS/UNEP, etc. The PCU will comprise of two UNOPS full-time staff: (CTA/Project Manager and a project administrator / co-ordinator), UNEP DEWA Information Co-ordinator and other partner staff as required.  Component and sub-component leaders will take full responsibility for undertaking the work agreed by the SC and will report directly to the UNOPS CTA/Project Manager. It is expected that the PCU staff will also undertake technical activities in support of the five Components.

# part iv:  explain the alignment of project design with the original PIF:

- The approach adopted in the Project Document follows the concept presented and approved in the PIF. During the PPG phase a number of minor modifications to the project components, outcomes and outputs have evolved reflecting the adaptive nature of the PPG phase. In addition a new sub-component (IW Science Conference) has been added to IW:LEARN reflecting the importance of ensuring better integration of IW project experts and the wider scientific community – and vice versa. In summary the main changes are:

- A 5% increase in the overall budget to include a sub-component  - IW Science Conference;

- An amalgamation of PIF Components 5 & 6 to streamline the overall project. This resulted in the loss of one output (Online stakeholder forum piloted with a GEF pilot)

- Rationalisation and amalgamation of outcomes / output between components (e.g. PIF Output 5c – GEF IW project results achievements captured in peer-review journal articles moved to Component 3.

# part v: Agency(ies) certification

This request has been prepared in accordance with GEF policies and procedures and meets the GEF criteria for CEO Endorsement.

| Agency Coordinator, Agency name | Signature | Date (Month, day, year) | Project Contact Person | Telephone | Email Address |
| --- | --- | --- | --- | --- | --- |
| Mr. Yannick Glemarec UNDP-GEF Executive Coordinator |  | 3 November 2010 | Mr. Vladimir Mamaev | +421 2 59337 267 | vladimir.mamaev@undp.org |
| Maryam Niamir-Fuller Director, Division of GEF Coordination UNEP maryam.niamir-fuller@unep.org |  | October 26, 2010 | Isabelle Van der Beck | +1-202-974-1314 | isabelle.vanderbeck@unep.org |

# Annex A: Project Results Framework

|  | Indicator | Baseline | Targets End of Project | Source of verification | Risks and Assumptions |
| --- | --- | --- | --- | --- | --- |
| Project Objective To strengthen global portfolio experience sharing and learning, dialogue facilitation, targeted knowledge sharing and replication in order to enhance the efficiency and effectiveness of GEF IW projects to deliver tangible results in partnership with other IW initiatives | % IW projects participating at IW Conference and / or science conference or IW workshop or project-project learning exchange % of IW projects exchanging information between water ecosystem types % of active projects establish a project website according to the IW:LEARN guidelines % of active projects that produce IW Experience Notes, which center on a key project achievement or innovation. Number of IW projects attracting private sector finance % existing IW projects uploading results to iwlearn.net | Without co-ordination by IW:LEARN there would be limited inter-project information sharing and minimal guidance on project implementation activities | 100% of IW Projects participate in IW Conference and/or IW Science Conference or IW workshop or project-project learning exchange 50 % of existing projects demonstrate exchanges / sharing of information between different ecosystem water types 100% of active GEF IW projects establish a project website according to the IW:LEARN guidelines 100% of active FSP’s produce at least 2 experience notes, and MSP’s produce at least 1 experience notes, which center on a key project achievement or innovation. 10 projects have attracted private sector finance 85% of existing IW projects (and 50% of closed projects) provide results, etc. to iwlearn.net | Reports and registration figures from conferences, workshops, project exchanges PSC reports GEF IW portfolio analysis - Annual Monitoring Report CoPs, iwlearn.net, website toolkits Project documents, PIFs, PIR’s Documents covering technical reports, workshop results, datasets, activity reports, evaluations as well as information on results on project profiles at iwlearn.net | Projects and Agencies agree to strengthen projects through improved guidance and encourage stronger links between projects |
| Outcome 1.1 Improved effectiveness in combating Land Degradation in MENARID through an enhanced role of groundwater and improved subsurface space management | % MENARID projects incorporating GW management planning | Current MENARID projects address sustainable land management practices to mitigate land degradation while improving agricultural productivity, without consideration of groundwater protection and use of best management principles | 100% of MENARID projects incorporate 5 new management planning activities of GW use/protection in their activities. | Project PIRs, Mid Term Evaluations and Final Evaluations showing incorporation of groundwater, and good performance. | Facilitated technical groups and other IW LEARN tools promote effective exchanges among projects and countries and succeed in raising active participation / involvement of stakeholders. |
| Outcome 1.2 Enabling regional inter-basin coordination to enhance management capacity of institutions and project partners | Number of new regional processes in SEE Number of new regional processes in Middle East Number of new co-operation processes in transboundary basins Number of IW projects adopting new management approaches Number of new co-ordination activities between marine and freshwater projects | Existing dialogue within SEE established but not increasing. Limited involvement or sharing experiences within the Middle East To be established | 1 new regional political process / initiative in the SEE 1 new regional political process / initiative in the Middle East sub-region. Cooperation on at least two transboundary basins is enhanced or initiated. 5 IW projects demonstrate that partners have adopted at least 2 different management approaches as a result of sub-component Each of three regions delivers 1 new project as result of co-operation following the ‘ridge to reef’ concept | Attendance at dialogue and capacity building activities. Participant satisfaction at activities New project proposals PSC reports from IW projects PSC reports from IW:LEARN Sub-component activity reports Project proposals to GEFSEC/Council | National governments, development partners and stakeholders engage willingly and productively in the dialogue and knowledge sharing activities. Stakeholders are adequately represented in the dialogue and engage in effective interaction. GEF projects in the SEE and the Med region are well informed about the IWLEARN and are willing or able to engage Insufficient funding or capacity to hold 3 regional meetings Sufficient interest to hold 5 learning exchanges in each region Not all 3 ecosystem types (marine, groundwater, surface) participate equitably. GEF IW projects are open and see value in engaging with projects dealing with different resource sectors |
| Outcome 2.1 Increased capacity of GEF groundwater and freshwater basin projects to exchange experiences and replicate successful groundwater management approaches and practices to address adaptive management | Number of CoPs formed % of groundwater projects involved in CoP % surface freshwater projects involved in CoP Number of transboundary commissions (or equivalent) involved in CoP Number of groundwater practices replicated through IWL Number of exchanges between surface and groundwater projects Participation at groundwater CoP by surface water representatives and vice versa | Groundwater projects implemented in isolation with respect to interlinked freshwater and coastal marine ecosystems, | Two functional CoPs (surface freshwater and groundwater) established 100% of IW groundwater projects involved 75% of IW surface freshwater projects involved 10 transboundary commissions involved 3 groundwater related priority replicable practices disseminated through IW LEARN platform, and 2 cases of integrated cooperative approaches among water-bodies documented. 5 exchanges between groundwater and surface water projects. Groundwater and surface water CoP representatives routinely attend each others meetings | Reports from CoPs and membership lists Groundwater management related priority practices identified in GEF portfolio of projects, published by UNESCO and disseminated through IW LEARN. Cooperative approaches documented in PIRs and Independent Evaluations | Facilitated and structured dialogues succeed in engaging active participation of stakeholders and practitioners Learning champions fail to follow through in developing surface water agenda. COP members find IW:LEARN community platform hard to use or reluctant to use |
| Outcome 2.2 Lessons and science from GEF groundwater portfolio incorporated into and disseminated through networks, partners, and processes, strengthening the GEF IW GW portfolio | Number of examples/lessons/ good practices disseminated % of presentations focusing on groundwater at IW Science conference | Limited dissemination of groundwater lessons GEF groundwater portfolio has not yet harnessed the wealth of experience and the results of new approach of its previous and existing projects | 6 examples / lessons / good practices disseminated through networks and / or published through IW:LEARN and partner networks or programmes 30% of presentations at IW Science conference focus on Groundwater | Reports from groundwater and surface water CoPs Reports to PSC Project performance evaluations note impact on future project design Reports from IW Science Conference | GEF IW groundwater projects identify appropriate lessons for dissemination Sufficient interest from IW groundwater projects to participate in IW Science Conference. Continuing promotion of transboundary groundwater projects by GEF for future funding. GEF IW groundwater and surface water projects interact and future GEF IW projects reflect better integration |
| Outcome 3.1 Global GEF IW portfolio performance and capacities strengthened, in particular among project managers of GEF IW projects | % of IWC6 participants indicate increased capacity % of IWC6 exhibit an innovation or replicable experience % of IW project managers attend IWC6 | No portfolio-wide self-sustaining mechanism for GEF IW inter project exchanges, dialogues, learning etc. Information-sharing on project innovations occurs only periodically No self-sustaining mechanism for GEF IW inter project exchanges, dialogues, learning etc. | At least 75% of IWC6 participant evaluations confirm increased capacity vs. individual baselines, and/or indicate changes to personal or institutional work plans 50% of IWC6-attending GEF IW projects exhibit at least one top innovation and/or replicable experience 75% of IWC6-attending GEF IW project managers attend the IWC6 and pre-conference workshops | Reports of IWC6 (including presentations, feedback from participants, etc.) MTE and TE | Not all GEF IW projects are willing to engage in various types of portfolio learning activities or to expose any weaknesses in project implementation to external scrutiny. Geopolitical and economic conditions enable full participation in the IWC6 The previous four IW conferences have helped to build a sense of community and trust among all IW projects. |
| Outcome 3.2 Increased awareness of GEF IW experiences and achievements and partnership with non- GEF supported Interventions | Number of global policy discussions/events with GEF IW Projects on the agenda Number of partnerships (established between GEF IW projects and external partners), joint activities or co-funding resulting from global forum participation | To be established | 2 events featuring at least 4 projects per year At least one example each year | PSC reports | Mutual acceptance between GEF and meeting hosts regarding GEF IW projects’ participation side-events Contact will be made with event organizers well in advance |
| Outcome 3.3 Improved technical implementation of projects through strengthening the science base of IW projects and improved integration of the wider science community into these projects. | % of GEF IW projects participating at Science Conference sharing results Number of IW projects referenced in scientific literature % of IW projects submitting papers to journal % readers satisfied % IW projects demonstrate examples of shared practices | Current IW projects utilise science based results to aid management decision making without disseminating the technical data/information Limited sharing of information or replication of IW experiences in projects | 50% of IW projects participating in GEF IW Science Conference actively share results 10 IW projects are ‘cited’ in the Science Citation Index 40% of IW portfolio submit papers for consideration in Journal Reader surveys indicate 75% satisfied and willing to contribute / read future editions 50% of GEF IW projects indicate at least one example of sharing practices | Reports from Science Networks Reports from IW Science Conference Science citation index Summary reports from Journal showing statistics to PSC Survey results from readers IW project reports and APR/PIRs | IW projects collect and deliver ‘science’ information at IW Science Conference IW and international scientists willing to participate and interact Projects value the Journal publication Projects actively participate submitting papers |
| Outcome 4.1 Improved web-based information and knowledge management and utilization of the IW resource center and project communication platforms | % of IW Stakeholders satisfied with iwlearn.net \Number of hits per month on iwlearn.net increase Number of downloads per month increase | IW:LEARN website (end of phase 2) with content | Stakeholder satisfaction rating for iwlearn.net >75% ‘satisfied’ End of project show 25% more hits per month vs. baseline End of project show 25% more downloads per month vs. baseline | PSC reports Iwlearn.net survey data | Stakeholders have good access to internet Web-platform actively used by other IW:LEARN activities Availability of up-to-date content Other ‘waters’ web sites are up-to-date |
| Outcome 4.2 Enhanced visibility and visualization of project activities and results facilitates cooperation and replication | % of projects utilising the IW:LEARN Website toolkit or offering a website consistent with IW:LEARN Website Guidelines | IW:LEARN website (end of phase 2) with content | 75% of projects utilising the IW:LEARN Website toolkit or offering a website consistent with IW:LEARN Website Guidelines | PSC reports Iwlearn.net survey data Project reports, activities summaries, technical reports, datasets |  |
| Outcome 4.3 Enhanced stakeholder access to data and results from IW projects | % of IW projects have current information on project results iwlearn.net | IW:LEARN website (end of phase 2) with content | At least 90% of IW projects have current information on project results at iwlearn.net or maintain links to project sites housed elsewhere | PSC reports Iwlearn.net survey data |  |
| Outcome 5.1 Improved standardization and harmonization of new GEF methodological approaches as well as results-based management in IW projects to help address new global issues & improve performance, including vulnerability to climatic variability & change in transboundary basins. | Endorsement of TDA/SAP methodology by GEF IWTF Number of IW projects utilising new methodology | Existing, unendorsed TDA/SAP methodology continues to be used in an ad hoc manner by IW Projects | GEF IWTF endorsement 5 new projects utilise the new methodology by end of project | Minutes of GEF IWTF meetings Reports showing successful delivery of training course | The TDA/SAP methodology and training course will be endorsed by GEF IWTF. Sustainability will rely on continued support from GEF and the Agencies. The methodology and training course is perceived as prescriptive. Lack of institutional ownership leads to poor delivery coverage and little further development of the process. |
|  | Number of CTAs/PMs using the manual IW project start up time reduced | Leadership training is not carried out by all GEF agencies, and basic information on project startup not available to project managers | 50% CTAs/PM using the manual Start-up phase of projects take 50% less time | Minutes of GEF IWTF APR/PIR contents APR/PIR submissions | Agreement between GEF, Agencies and Projects on Manual contents |
|  | Majority of project stakeholders accept index-insurance methodology Number of IW projects using approach | No transboundary methodology available and no application of risk management at a transboundary scale | Acceptance by stakeholders of approach At least one IW projects utilize methodology | Endorsement by PSC of methodology Reports from pilot IW projects trialing approach | Co-operation needed between insurance and financial private sector with IW projects at the transboundary level |
|  | Number of IW projects using approach to climatic variability & change | Considerable information is available but these can be conflicting with IW projects needing further assistance to adapt current guidance for each ecosystem addressed | Agreed methodology developed and piloted in 5 GEF5 IW projects; Acceptance of approach by IWTF for use in all IW projects | Reports from pilot testing of methodology Minutes from GEF IWTF Project documents to GEF council | An agreed synthesis of current best practices can be prepared and accepted by experts/IWTF |
| Outcome 5.2 Public-private partnerships promoted and facilitate sustainability of GEF IW interventions | Number of IW projects with sustainable private sector finances % of IW projects included public-private partnerships in sustainability plans | Ad hoc support by the private sector for IW projects | 10 projects have developed/promoted public-private sector engagement 50% of IW projects have a sustainability plan / exit strategy that utilizes the best practices collated | APR/PIRs from IW projects | Projects and private sector are willing to participate in preparing guidance Private sector values involvement with GEF projects |

s

Annex B: Responses to Project Reviews (from GEF Secretariat and GEF Agencies, and Responses to Comments from Council at work program inclusion and the Convention Secretariat and STAP at PIF)

GEF Secretariat comments from the PIF stage were incorporated in the current Project Document

# STAP Comments:

|  | STAP Comment | Response |
| --- | --- | --- |
| 1 | STAP acknowledges that on scientific/technical grounds the concept has merit. However, STAP may state its views on the concept emphasising any issues that could be improved and the proponent is invited to approach STAP for advice at any time during the development of the project brief prior to submission for CEO endorsement. | The Science Conference will have full STAP involvement, and STAP will be invited to participate in the IW:LEARN Steering Committee |
| 2 | STAP has identified specific scientific/technical suggestions or opportunities that should be discussed with the proponent as early as possible during development of the project brief. One or more options that remain open to STAP include: (i) Opening a dialogue between STAP and the proponent to clarify issues (ii) Setting a review point during early stage project development and agreeing terms of reference for an independent expert to be appointed to conduct this review The proponent should provide a report of the action agreed and taken, at the time of submission of the full project brief for CEO endorsement. | Discussed and clarified at the IWC 5 in Cairns and subsequently. During the operational phase regular contact with STAP will be maintained, in particular via the steering committee and IW Task Force. |
| 3 | STAP proposes significant improvements or has concerns on the grounds of specified major scientific/technical omissions in the concept. If STAP provides this advisory response, a full explanation would also be provided. Normally, a STAP approved review will be mandatory prior to submission of the project brief for CEO endorsement. The proponent should provide a report of the action agreed and taken, at the time of submission of the full project brief for CEO endorsement. | Noted comments and incorporated changes |

# Annex c: consultants to be hired for the project using gef resources

| Position Titles | $/ person week* | Estimated person weeks** | Tasks to be performed |
| --- | --- | --- | --- |
| For Project Management |  |  |  |
| Local |  |  |  |
| International |  |  |  |
| Project Coordinator | 1800 | 182 | One coordinator will handle all project management duties broadly speaking, as well as coordinate amongst all project partners and consultants to ensure coherent delivery of the project. ($327,600) |
| Justification for Travel, if any: Annual travel to steering committee locations to coordinate reporting and project M&E activities. |  |  |  |
| For Technical Assistance |  |  |  |
| Local |  |  |  |
| Comp1: Adult Learning Specialists | $1000/week | 70 | Part-time technical consultants with an adult-learning background, facilitation experience and relevant expertise will be engaged under the PCU to take leading roles in coordinating and undertaking activities required in the activity. In particular, the coordination of delivering and organizing the IW:LEARN workshops at the regional level with partners. Consultants managed through the project coordination unit will help to ensure the effective linkages between the Component activities and the UNEP unit, as well as effective networking with IW projects on information management-specific activities, as well as help-desk services and training support. ($70,000) |
| Comp2: Facilitators | $1000/week | 20 | Learning champions, resource people with strong connections and recognition in the global groundwater and surface freshwater communities will be brought into facilitate key sessions at the two respective communities of practice. They will be hired as technical consultants as an extension of the PCU, and will assist both CoPs. At least 5 consultants are envisioned over 3.5 years for 10 such sessions. ($20,000) |
| Comp3: Local assistance, rapporteurs, meeting organizers and facilitators | $500/week | 60 | These limited funds will be utilized to bring on board additional assistance during the IWC6 as well as the IW Science conference, specifically in the realm of managing the participants with the multiple movements and site visits associated with the events. ($30,000) |
| Comp3: Editing, Scriptwriting and Drafting Assistance | $500/week | 60 | Assistants will be required to furnish content for the two major IW publications, especially in terms of capturing the appropriate results from the GEF IW portfolio under both ICM and IWRM. In addition, resources will be needed to produce the script for the IW Film and also help organize content and promotion of the IW Journal. ($30,000) |
| Comp5: Editors | $1000/week | 60 | Consultants operating under the PCU will be required to help assemble and finalize voluminous content developed to guide projects on private-sector partnerships and also mainstreaming the impacts of climatic variability and change into IW projects. Some 60 person-weeks are envisioned ($60,000) |
| Comp5: Project Manager Manual Technical Coordinator(s) | $1000/week | 65 | These resources will be used to develop the IW project manager manual utilizing one or more consultants. The funds will be used to support the costs of reviewing the development of content, interact with stakeholders and the Technical Advisory Group as well as conduct a training at the IWC6. ($65,000) |
| International |  |  |  |
| Comp 2: Network coordinators | $2500/week | 10 | Limited international consultant support is anticipated for this activity, however it is expected to be required to ensure that the most appropriate experiences from the GEF IW portfolio are captured and utilised in the communities of practice. Consultants will also help to ensure the facilitation of the community of practice/workspace platforms and provide design support to the enhancement of the iwlearn.net website. They will also help facilitate connections to concurrent efforts for marine projects. At least 10 person-weeks of work is envisioned over 3 years for each of the two primary communities of practice involving 2 or more consultants. ($25,000) |
| Comp3: Professional Facilitators and Strategic Coordinators | $2000/week | 28 | The PCU will require expertise on the organization of the IWC6 and Science Conference, specifically in the realm of strategic coordination. The PCU will require a consultant to help plan and coordinate and promote the overall event, specifically politically and also in terms of securing sponsorship. At least 28 weeks are needed to effectively prepare the events. ($56,000) |
| Comp5: Course Developers | $2500/week | 10 | Limited international consultant support is anticipated for this activity, however it is expected to be required that course developers, with a background in adult learning techniques, effectively adapt the manager’s training course and TDA-SAP course into an online format. Roughly 10 person weeks of work is envisioned over 3 years from at least 2 consultants in support of all activities. ($25,000) |
| M&E: Mid-term Evaluator | 2500 | 20 | This consultant will perform the mid-term evaluation. ($50,000) |
| M&E: Final Evaluator | 2500 | 28 | This consultant will perform the final evaluation. ($70,000) |
| Justification for Travel, if any: Travel to IW:LEARN Regional Workshops and the 6th GEF Biennial International Waters Conference and/or the IW Science Conference as well as Steering Committee meetings |  |  |  |

*  Provide dollar rate per person week.    **  Total person weeks  needed to carry out the tasks.

# Annex d:  status of implementation of project preparation activities and the use of funds

- explain if the ppg objective has been achieved through the ppg activities undertaken.

# The PPG objectives have been achieved.

# The PPG had the following components and related objectives.

Component One sought to identify, design and reach consensus among project partners on the list of indicative activities. Component outputs included: a project annual workplan, partner roles and responsibilities defined and project budget defined.

- In pursuit of this (and by design) an Inception Workshop was conducted in December 2009 at the UN Offices in Nairobi with all implementing partners and a representative set of stakeholders (selected GEF IW project managers). The Workshop featured two “back-to-back” meetings. The first meeting addressed exclusively the technical aspects of the project’s digitally-based activities, primarily involving proposed Components 1 and 3b (as they were in the original PIF). The second meeting will incorporate all project partners to obtain consensus on all previously-discussed activities and define the management arrangements that will ensure the project delivers-as-one.

- From that meeting, the annual workplan, partner definitions were defined. A basic budget emerged as well, but was heavily rebuilt in 2010.

Component Two sought to identify additional partners and cofinance for project activities. The component outputs included: additional co-financing for the project, and alignment of the project with global and regional processes.

- Several contracts were initited with partners including UNEP (via a consultant), UNESCO, UNU-INWEH, GWP-Med, University of British Columbia (implementing a GEF project), the International Research Institute on Climate and Society, the World Conservation Union and individual consultants. Co-finance was identified by these partners…

- In addition, the component supported inter alia, identification of project needs and capacity gaps in term of info-system functionality, identification of key content matter and needs for the GEF IW Focal Area manual, definition of objectives and guidelines for learning exchanges/twinning drawing from IW:LEARN experience to date, definition of objectives and methodologies for land-water integration and dialog and categorization of work-to-date on mainstreaming of adaptation to climate variability into international waters projects especially identifying lessons and best practices for such mainstreaming. Synergies with new partners were also identified.

- A full donor consultation event still needs to happen and will happen as part of the inception. Additonal meetings were held in various locations to begin designing the IWC6 and what modalities it would use.

Component Three set out to consult stakeholders and consequently customize activities. The output of this was project activities that meet portfolio needs.

- Stakeholder consultation occurred thru a variety of means. Besides the face to face meetings, individual bilateral contact was undertaken with several IW project managers, in addition several of the partners with the support of UNDP/UNOPS and UNEP IW:LEARN, conducted stakeholder surveys (of the IW portfolio) to assess learning gaps, existing knowledge, regional facilitators and trainers. GEF agency staff were also interviewed as well as the GEF IW focal area secretariat staff. Portfolio experience was also excessed to further refine FSP activities that target portfolio needs. All GEF IW project managers have been informed of ongoing developments with the project and the activities that are going to be operationalized.

- describe findings that might affect the project design or any concerns on project implementation, if any:

# None

- provide detailed funding amount of the ppg activities and their implementation status in the table below:

| Project Preparation Activities Approved | Implementation Status | GEF Amount ($) |  |  |  | Co-financing ($) |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | Amount Approved | Amount Spent To date | Amount Committed | Uncommitted Amount* |  |
| 1. Identification, design and consensus on project activities | Completed | 90,000 | 90,000 | 0 | $0 | 120,000 |
| 2. Identification of additional partners & co-financing for project activities | Completed | 50,000 | 50,000 | 0 | $0 | 45,000 |
| 3. Stakeholder consultation and activity customization | Yet to Complete | 80,000 | 55,440 | 24,560 | $0 | 85,000 |
| Total |  | 220,000 | 195,440 | 24,560 | $0 | 250,000 |

*  Any uncommitted amounts should be returned to the GEF Trust Fund.  This is not a physical transfer of money, but achieved through reporting and netting out from disbursement request to Trustee. Please indicate expected date of refund transaction to Trustee.

# annex e:  calendar  of expected reflows

Provide a calendar of expected reflows to the GEF Trust Fund or to your Agency (and/or revolving fund that will be set up) - Not applicable to this project.

Execution of all components in the proposed project will involve all partners. The agencies listed by each output do not exclude the other agencies from involvement, but are included to indicate the agencies which will take the lead in coordinating the delivery of those outputs.