Document of

The World Bank

FOR OFFICIAL USE ONLY

Report No:

PROJECT APPRAISAL DOCUMENT

ON A

PROPOSED CREDIT

IN THE AMOUNT OF SDR 46.2 MILLION

(US$ 70 MILLION EQUIVALENT)

AND

A PROPOSED GRANT FROM THE EUROPEAN UNION FOOD CRISIS

RAPID RESPONSE FACILITY TRUST FUND

IN THE AMOUNT OF EUR14.64 MILLION

and

PROPOSED GRANT FROM THE

GLOBAL ENVIRONMENT FACILITY TRUST FUND

IN THE AMOUNT OF us$ 6.2 MILLION

TO THE

REPUBLIC Of Mali

FOR A

Fostering Agricultural Productivity PROJECT

April 30, 2010

Agricultural and Rural Development

Sustainable Development Department

Africa Region

This document has a restricted distribution and may be used by recipients only in the performance of their official duties. Its contents may not otherwise be disclosed without World Bank authorization.

CURRENCY EQUIVALENTS

(Exchange Rate Effective March 31, 2010)

| Currency Unit | = | FCFA |
| --- | --- | --- |
| FCFA485 | = | US$1 |
| US$1 | = | SDR0.658 |

FISCAL YEAR

| January 1 | – | December 31 |
| --- | --- | --- |

ABBREVIATIONS AND ACRONYMS

| AASC | Agricultural Advisory Service Council |
| --- | --- |
| ACDP | Agricultural Competitiveness and Diversification Project |
| AfD | Agence Française de Développement (French Development Agency) |
| AfDB | African Development Bank |
| AGETIER | Agence d’Éxécution des Travaux d’Infrastructures et d’Équipements Ruraux (Executing Agency for Rural Equipment and Civil Works) |
| APCAM | Assemblée Permanente des Chambres d’Agriculture du Mali (Permanent Assembly of Mali Agricultural Chambers) |
| APL | Adaptable Program Loan |
| ARD | Agriculture and Rural Development |
| BSI | Budget Spécial d’Investissement (Special Investment Budget) |
| CAADP | Comprehensive Africa Agriculture Development Program |
| CAS | Country Assistance Strategy |
| CBA | Cost-Benefit Analysis |
| CENA | Capacity Enhancement Needs Assessment |
| CGSP | Contrôle Général des Services Publics (GoM’s internal audit) |
| CNRA | Comité National de la Recherche Agricole (National Agricultural Research Committee) |
| CNOP | Coordination Nationale des Organisations Paysannes (National Coordination of Producer Organizations) |
| COSOP | (IFAD) Country Strategic Opportunities Program |
| CPS | Cellule de Planification et de Statistiques (Statistics and Planning Unit) |
| CQBS | Consultants’ Qualifications-Based Selection |
| CRA | Chambre Régionale d’Agriculture (Regional Chamber of Agriculture) |
| CRCE | Comités Régionaux de Concertation et d’Échanges (Consultation and Dialogue Regional Committes) |
| CROCSAD | Comité Régional d’Orientation, de Coordination et de Suivi des Actions de Développement (Regional Steering Committee for the Coordination and Monitoring of Development Operations) |
| CSA | Commissariat à la Sécurité Alimentaire (Food Security Commissariat) |
| CSIF | Comprehensive Strategic Investment Program |
| CTCE | Comité Technique de Coordination et d’Exécution (Technical Execution Coordination Committee) |
| DAF | Direction Administrative et Financière (Financial and Administrative Division) |
| DNACPN | Direction Nationale de l’Assainissement et du Contrôle des Pollutions et Nuisances (Sanitation, Pollution and Nuisance Control National Division) |
| DNRFFH | Direction Nationale des Ressources Forestières, Fauniques et Halieutiques (Halieutic, Faunistic and Forestry Resources National Division) |
| DRACPN | Direction Régionale de l’Assainissement et du Contrôle des Pollutions et Nuisances (Sanitation, Pollution and Nuisance Control Regional Division) |
| DRGR | Direction Régionale du Génie Rural (Regional Division for Rural Civil Works) |
| EA | Environment Assessment |
| ECOWAP | ECOWAS Agricultural Policy |
| ECOWAS | Economic Community of West African States |
| ESIA | Environment and Social Impact Assessment |
| ESMF | Environment and Social Management Framework |
| EU / EC | European Union / European Commission |
| FAO | Food and Agriculture Organization |
| FM | Financial Management |
| FNAA | Fonds National d’Appui à l’Agriculture (Agricultural Support National Fund) |
| FODESA | Fonds de Développement en Zone Sahélienne (Sahel Areas Development Fund) |
| FY | Fiscal Year |
| GDP | Gross Domestic Product |
| GEB | Global Environment Benefits |
| GEF | Global Environment Fund |
| GEO | Global Environment Objective |
| GIE | Groupement d’Intérêt Économique (Economic Interest Group/Co-op) |
| GoM | Government of Mali |
| GPN | General Procurement Notice |
| GPRSF | Cadre Stratégique pour la Croissance et la Réduction de la Pauvreté (Growth and Poverty Reduction Strategy Framework) |
| GTZ | Deutsche Gesellschaft für Technische Zusammenarbeit (German Technical Cooperation) |
| Ha | Hectare |
| IAS | International Accounting Standards |
| IC | Individual Consultants |
| ICB | International Competitive Bidding |
| IDA | International Development Association |
| IER | Institut d’Économie Rurale (Institute for Rural Economics) |
| IFAD | International Fund for Agricultural Development |
| IFR | Interim Financial Report |
| IRR | Internal Rate of Return |
| KfW | Kreditanstalt fur Wiederaufbau (German Development Bank) |
| LOA | Loi d’Orientation Agricole (Agricultural Framework Law) |
| LCS | Least Cost Selection |
| LSIPT | Livestock Sector Investment and Policy Toolkit |
| MCC | Millennium Challenge Corporation |
| MinAgri | Ministry of Agriculture |
| MEA | Ministère de l’Environnement et de l’Assainissement (Ministry of Environment and Sanitation) |
| MFI | Micro-Finance Institution |
| M&E | Monitoring and Evaluation |
| MTEF | Mid-Term Expenditure Framework |
| NAPA | National Action Plan for Adaptation |
| NARS | National Agricultural Research System |
| NCB | National Competitive Bidding |
| NEPAD | New Partnership for African Development |
| NPV | Net Present value |
| NSC | National Steering Committee – PNISA |
| O&M | Operations and Maintenance |
| OIE | Office International des Epizooties (World Animal Health Organization) |
| OMA | Observatoire des Marchés Agricoles (Agricultural Market Observatory) |
| ON | Office du Niger |
| PACR | Programme d’Appui aux Communautés Rurales (Rural Community Development Project) |
| PASAM | Programme d’Appui au Secteur Agricole au Mali (Agricultural Sector Support Program in Mali) |
| PASAOP | Programme d’Appui aux Services Agricoles et aux Organisations Paysannes (Agricultural Services and Producer Organizations Program) |
| PASSIP | Programme d’Appui au Sous-Secteur de l’Irrigation de Proximité (Small-Scale Irrigation Promotion Program) |
| PFM | Public Financial Management |
| PCDA | Projet Compétitivité et Diversification Agricole (Agricultural Competitiveness and Diversification Project) |
| PDI-BS | Programme de Développement de l’Irrigation dans le Bassin du Bani et à Sélingué (Irrigation Development Program for the Bani and Sélingué Basins) |
| PDO | Project Development Objective |
| PDZL | Programme de Développement des Zones Lacustre (Lacustre Areas Development Program) |
| PER | Public Expenditure Review |
| PIDRN | Programme Intégré de Développement Rural du Nord (Northern Integrated Rural Development Program) |
| PIM | Project Implementation Manual |
| PIU | Project Implementation Unit |
| PIV | Périmètre Irrigué Villageois (Village Irrigation Perimeter) |
| PMP | Pest Management Plan |
| PNIR | Programme National d’Infrastructures Rurales (National Rural Infrastructure Project) |
| PNISA | Programme National d’Investissement Sectoriel Agricole (National Agricultural Sector Investment Program) |
| PO | Producer Organization |
| PPM | Petit Périmètre Maraîcher (Small Scale Irrigation Perimeter for vegetable production) |
| PPP | Public-Private Partnership |
| PRSC | Poverty Reduction Support Credit |
| PTF-EAR | Groupe des Partenaires Techniques et Financiers – Économie Agricole et Rurale (Financial and Technical Partners for Agricultural and Rural Economy) |
| PVS | Performance of Veterinary Services |
| QBS | Quality-Based Selection (QBS) |
| QCBS | Quality- and Cost-Based Selection |
| RCRE | Regional Committees for Research and Extension |
| ReSAKSS | Regional Strategic Analysis and Knowledge Support System |
| RAP | Resettlement Action Plan |
| REI | Request of Expression of Interest |
| RPF | Resettlement Policy Framework |
| SAM | Social Accounting Matrix |
| SAPI | Sécurité Alimentaire par les Périmètres Irrigués (Food Security through Irrigation Perimeters) |
| SBD | Standard Bidding Documents |
| SEDIZON | Secrétariat d’État pour le Développement Intégré de la Zone Office du Niger (State Secretariat for the Integrated Development of the Office du Niger Area) |
| SIL | Specific Investment Loan |
| SIP | Strategic Investment program (GEF) |
| SLWM | Sustainable Land and Water Management |
| SNFAR | Stratégie Nationale de Formation Agricole et Rurale (National Strategy for Rural and Agricultural Training) |
| SoSuMar | Société Sucrière de Markala (Markala Sugar Production Company) |
| SRI | System of Rice Intensification |
| STP/CIGQE | Secrétariat Technique Permanent du Cadre Interministériel de Gestion des Questions Environnementales (Permanent Technical Secretary of the Inter-Ministerial Framework for Environmental Issues) |
| SUKALA | Complexe Sucrier du Kala Supérieur (Sugar factory of the Upper Kala) |
| SWAp | Sector Wide Approach |
| UNCCD | United Nations Convention to Combat Desertification |
| UNDB | United Nations Development Business |
| UNDP | United Nations Development Program |
| VRES | Valorisation des Ressources en Eau de Surface (Surface Water Resources Use) |
| WAEMU | West African Economic and Monetary Union |
| WAAPP | West Africa Agricultural Productivity Project |

| Vice President: |  | Obiageli Katryn Ezekwesili |
| --- | --- | --- |
| Country Director: |  | Habib Fetini |
| Sector Director |  | Inger Andersen |
| Sector Manager: |  | Karen McConnell Brooks |
| Task Team Leader: |  | Olivier Durand |

Mali

Fostering Agricultural Productivity Project

Contents

Page

I.	STRATEGIC CONTEXT AND RATIONALE	1

A.	Country and sector issues	1

B.	Rationale for Bank involvement	1

C.	Past and current Bank support to agriculture and rural development:	2

D.	Higher level objectives to which the project contributes	4

II.	PROJECT DESCRIPTION	4

A.	Lending instrument	4

B.	Project development objective and key indicators	4

C.	Project components	6

D.	Lessons learned and reflected in the project design	10

E.	Alternatives considered and reasons for rejection	12

III.	IMPLEMENTATION	12

A.	Partnership arrangements	12

B.	Institutional and implementation arrangements	14

C.	Monitoring and evaluation of outcomes/results	15

D.	Sustainability and Replicability	16

E.	Critical risks and possible controversial aspects	16

F.	Credit conditions and covenants	18

IV.	APPRAISAL SUMMARY	19

A.	Economic and financial analyses	19

B.	Technical	20

C.	Fiduciary	20

D.	Social	21

E.	Environment	22

F.	Safeguard policies	22

G.	Policy Exceptions and Readiness	23

Annex 1: Country and Sector or Program Background	24

Annex 2: Major Related Projects Financed by the Bank and/or other Agencies	35

Annex 3: Results Framework and Monitoring	37

Annex 4: Detailed Project Description	46

Annex 5: Project Costs	70

Annex 6: Implementation Arrangements	73

Annex 7: Financial Management and Disbursement Arrangements	82

Annex 8: Procurement Arrangements	94

Annex 9: Economic and Financial Analysis	106

Annex 10: Safeguard Policy Issues	115

Annex 11: Project Preparation and Supervision	120

Annex 12: Documents in the Project File	122

Annex 13: Statement of Loans and Credits	124

Annex 14: Country at a Glance	125

Annex 15: Incremental Cost Analysis	127

Annex 16: Lessons Learned from Past Experiences	135

Annex 17: Key results of the SLWM-PER and CBA study	138

Annex 18: Land degradation and SLWM in target production systems	141

Annex 19: Maps	153

STRATEGIC CONTEXT AND RATIONALE

Country and sector issues

- Mali remains one of the poorest countries in Sub-Saharan Africa. GDP per capita was US$480 (2008) and the national poverty rate was estimated to be 47.4 percent in 2006. Poverty is more prevalent in the rural areas (57.6 percent) and most rural people continue to derive their livelihoods from agriculture.  Food insecurity and malnutrition are high and were aggravated by the fuel and food crisis of 2007/08. In 2009, food prices remain above the 2008 level and above the 5-year average. Natural resources degradation, population growth and climate change continue to pose serious challenges to medium and long term food security in the country.

- The recent high food prices highlight issues, challenges and opportunities for the agricultural sector. The 2007/08 food price crisis demonstrated the importance of increasing domestic food production and marketing. Food supply can be increased by expanding land areas under irrigation, raising productivity of lands currently farmed under rain-fed and irrigation methods, acting on untapped potential in the livestock sector, and improving post-harvest handling of crops and livestock products. Three key constraints hinder these objectives:

  - The lack of productive infrastructure, especially for irrigation, post-harvest management and processing capacities. The lack of investments in farm modernization, livestock development, storage and small scale processing constrains the ability of producers to use current assets productively and dampens incentives to invest in new assets;

  - The very low usage of modern agricultural inputs and sustainable practices, poor land and water management, and weak access to farm management advice and financial services in the crop and livestock sectors; agricultural productivity remains very low and yields still significantly below potential;

  - The lack of coordination in the agricultural sector, fragmented and scattered interventions with limited impact at the national level, a multiplicity of concurrent strategies for rural development and food security, and weak evidentiary base for policy-making by the Government of Mali (GoM).

- Degradation of soil and climate change present special concerns. Over the last 30 years, rainfall has declined by about 30 percent.  In addition, the natural resource base has been degraded through increased population pressure and depletion of soil, forests, and water quality.  The combination of climate change and degradation of resources presents a heightened urgency for shifts in agricultural technology.

Rationale for Bank involvement

- Agriculture sector has the potential to perform better. The current Country Assistance Strategy (CAS; 2007-11) places agriculture as one of the three key sectors to drive economic growth. As highlighted in the 2006 Country Economic Memorandum (CEM), Mali’s agricultural sector is showing steady growth in recent years but acknowledges that higher growth is attainable. The Bank has been an active partner on agriculture development in Mali and is well positioned to lead a shared effort, along with other development partners, to support improved performance in the sector. The Bank co-chairs the local Mali donor coordination group in the agriculture and rural development (ARD) sector.

- The Government of Mali places a high priority on agriculture.  The first strategic pillar of the GoM’s Growth and Poverty Reduction Strategy Framework (GPRSF) for 2007-2011 prioritizes food security and raising the incomes of rural producers through increasing, securing and diversifying food production. It is expected that this pillar will be achieved by ensuring sustainable management of natural resources, modernizing family farms, expanding productive infrastructure and developing agro-processing.

- In 2006, the GoM adopted the Loi d’Orientation Agricole (LOA) intended to spearhead modernization of the sector and increased value addition. In October 2009, within the framework of the Comprehensive Africa Agriculture Development Program (CAADP) and under guidance from the Economic Community of West African States (ECOWAS), the GoM adopted its roadmap and compact for the elaboration of a national agricultural sector investment program, PNISA – Programme National d’Investissement Sectoriel Agricole.  The Bank and IFAD’s involvement in financing the program through this proposed operation will help the GoM leverage further funding from other bilateral and multilateral donors, and facilitate dialogue on the quality of the overall program.

- The project will support institutional reforms and donor coordination to facilitate evolution toward a sector wide approach.  The GoM has informed donor partners of its desire to move towards a sector wide approach. This project is seen as a first step in that direction as well as a vehicle for refining the proposed PNISA. Consistent with CAADP’s pillar 1, the project will also support efforts to establish a comprehensive programmatic approach to sustainable land and water management (SLWM) through the implementation of Mali’s Country Strategic Investment Framework (CSIF) for sustainable land management.  Through the proposed field investments and activities, the project will contribute to implement the four pillars of the Bank Climate Change strategy in Sub Saharan Africa.

Past and current Bank support to agriculture and rural development:

- PASAOP and PNIR have left valuable institutional legacies.  The project will build upon the accomplishments of PNIR for large-scale and small-scale irrigation development, and on PASAOP for technology generation and transfer, promotion of private delivery for advisory services to farming communities, and empowerment of producer organizations (POs). Similar approaches and experiences from IFAD-funded projects, such as FODESA, PDZL and PIDRN will be replicated and complemented to assist producers in receiving both infrastructure and agricultural advisory services.

  - Stronger producer organizations: POs are now key partners for policy dialogue at the national level and implementation of investments at the local level. The project will build upon the present network of Chambres Régionale d’Agriculture (CRAs - Regional Agricultural Chambers) operating under the national leadership of the Permanent Assembly of Malian Agricultural Chambers (APCAM), and on grassroots producer associations and cooperatives. The project will support existing organizations to become more professional, better able to provide services, and more inclusive through increased outreach.

  - Better technology generation mechanism: Agricultural research institutions are now better organized and more responsive to producers’ needs. Increased emphasis is needed on dissemination of superior and sustainable technologies, as well as continued investment in research generation.

  - More efficient advisory services: Mali has embarked on a transition from a traditional top-down and state-led extension system to a more demand-driven and pluralistic network of service providers. The immediate challenge is to expand and strengthen the network of private service providers, and to help POs develop their own expertise and networks.

  - Sustainable irrigation development: Mali elaborated a National Irrigation Strategy in 1999 and reviewed it in 2007 to enhance focus on producers’ participation and co-financing, including the involvement of the banking sector. Current attention is focused on improving the linkage between irrigation infrastructures, support services, finance for operation and maintenance (O&M) expenses, and sustainable water management.

  - Development of Office du Niger area: A strong focus on irrigation development of the Office du Niger (ON) resulted, in December 2008, in the approval of a strategic Master Plan and creation of a State Secretariat dedicated to the development of the ON area. Investment planning and coordination has become a sensitive issue as water is now viewed as a limiting factor for irrigation development.  Although the ON has achieved commendable success, new challenges raise questions about options to improve governance and management. There is also a need to strengthen the viability of smallholder farms by carrying forward new development opportunities in diversification and area extension.

- The proposed project will complement the ongoing PCDA.  The Bank-financed PCDA focuses on fruits and horticulture production in selected areas, and processing for high value export markets. It also includes some activities in cattle production and milk processing. The proposed project will operate in the same administrative regions, and will complement PCDA’s approach by supporting production and early stages of product processing of staple foods for local and regional consumption. It will draw on approaches and financing mechanisms piloted under PCDA for technology dissemination, supply chain organization and infrastructure investments where relevant, but will target a different set of products and producers.

- The proposed project will link with WAAPP, a Bank-financed project supporting agricultural technology at the sub-regional level. The project will draw on technologies developed and disseminated under WAAPP, and will serve as the national conduit for technology transfer, linking researchers, extensionists and producers in Mali.

- The GEF contribution draws on the TerrAfrica partnership: This operation is aligned with the TerrAfrica Initiative and GEF’s Strategic Investment Program (SIP) for SLWM in Sub-Saharan Africa. Involvement of GEF’s Operational Program on SLWM will contribute to the generation of local, regional and global environmental benefits by mainstreaming SLWM techniques into project interventions of the targeted production systems.

Higher level objectives to which the project contributes

- The proposed operation will contribute to the higher level objective as set forth in the GPRSF of ensuring food security and increasing the income of rural producers.

PROJECT DESCRIPTION

Lending instrument

- Total project costs amount to US$160 million equivalent. The project will be financed by a six-year Specific Investment Loan (SIL) of US$70 million from the International Development Association (IDA), a grant of US$6.2 million from the Global Environment Fund (GEF) and a grant of 14.64 million Euros (US$19.5 million equivalent) from the European Union Food Crisis Rapid Response Facility Trust Fund. The International Fund for Agricultural Development (IFAD) will co-finance the project with a credit of US$32 million. The project will also benefit from an additional GEF parallel financing of US$1.9 million to be implemented by UNDP. The Government’s contribution to the project is estimated at US$23.7 million through taxe exemption. Beneficiaries’ contribution is estimated at US$6.7 million.

Project development objective and key indicators

- Project Development Objective (PDO) is to increase the productivity of smallholder agricultural and agribusiness producers in the targeted production systems and project areas.

- Global Environment Objective (GEO) is to increase the use of sustainable land and water management (SLWM) practices in the targeted production systems and project areas.

- Investments will be focused on four key production systems for staple foods with potential for productivity increase and confirmed domestic demand. These production systems have already been studied by research programs and innovative techniques are readily available. Within each production system, a reference agriculture product and SLWM technology have been selected to gage their production potential, productivity gains and significant environmental impacts. They will serve as core indicators to measure project performance and impact.

- The proposed production systems and reference products are briefly described hereafter. Annex 4 provides details on the justification and description of the selected production systems. Annex 1 gives technical and economic background information on the reference products.

- Irrigated rice and vegetables: This production system feeds much of Mali. The project will use rice as the reference product for this system. It encompasses both the expansion of irrigated areas and the increase of productivity on existing irrigated perimeters. System of rice intensification (SRI) will be the SLWM reference technology.

- Rain-fed cereals: This is the production system on which most rural people rely for their incomes, and it has been neglected for many years. Two sub-systems will be emphasized: cereal/leguminous and cereal/cotton, both of which are strongly associated with animal production. Cowpea will be the reference product under the cereal/leguminous system. The project will also pay attention to cotton yields, as cotton remains the crop rotation pillar of the mixed cereal/cotton production system. The SLWM reference technology selected is live fences.

- Fodder production: Demand for feed alternatives to cotton-seed cake is increasing. The fodder production system presents the highest potential for innovation, from the introduction of new crops to the dissemination of harvesting and processing equipment. Enhanced seeds and cropping techniques are already available for quick dissemination. The project will select fodder cowpea as the reference product. Pastoral conventions will be the SLWM reference technology.

- Livestock production: Mali is famous for livestock, yet it imports most of the milk consumed. Women and young people manage the short cycle animal production process. The project will focus on: (i) semi-intensive and agro-pastoral dairy production; (ii) semi-commercial and traditional poultry production; and (iii) sheep (ovine) fattening.  Cow milk will be the project’s reference product. Improved stable and manure management will be the SLWM reference technology.

- Geographic focus and target production basins: Project investments will be concentrated in the following production basins selected  on the basis of potential of targeted production systems, as well as market opportunities (proximity to urban consumers) and potential for poverty reduction and increased income for smallholders (Table 1):

Table 1 – Production Systems and Basins

| Crop and Livestock Production Systems | Production Basins |
| --- | --- |
| - Irrigated rice / vegetables | - Office du Niger for large-scale irrigation - Sikasso/Kayes for lowland irrigation - Along the Niger River for village irrigation perimeters + Diré (Wheat) + Kidal (palm) |
| - Rain-fed cereals - mixed cereals / leguminous / livestock - mixed cereals / cotton / livestock | Douentza/Bankass/Koro + Bla/Macina/Tominian Kati/Dioïla + Kita/Bafoulabé + Sikasso/Koutiala/Bougouni |
| - Fodder production (fodder crops for mixed dairy / meat farming and pastoral perimeters) | Office du Niger (Sokolo/M’Béwani) + Dilly/Nara + Diéma/Nara |
| - Livestock production (dairy, ovine fattening and poultry) | Periurban areas around Bamako/Koulikoro, Ségou, Mopti, Kayes and Sikasso |

- Target beneficiary group: The project’s primary target will be smallholder producers already connected to markets and ready to adopt improved technologies in the selected product groups. The entry point for interventions will be POs (cooperatives, associations and economic interest groups (GIEs)). The project will focus on POs’ inclusiveness, representation, social responsibility and accountability. It will also ensure that women and young people can access project resources and benefit from capacity building and advisory services. To reach vulnerable people such as agro-pastoralists, small-scale livestock breeders or fishermen, the project will build upon the targeting strategy developed by IFAD-funded projects in the Northern regions by: (i) mapping poverty by commune and village; (ii) strengthening the local planning process through participatory diagnostics so that the poorest groups are included and taken care of; and, (iii) ensuring that their priority needs are reflected in investments and activities to be financed.

- Key performance indicators: Project interventions will result in productivity increases for smallholder producers in the targeted production systems and regions. The project will also seek to enhance competitiveness of targeted food chains.  Indicators will include reduction in post-harvest losses and increased marketing of products for each of the reference products. Project performance will be measured by:

- Increase of rice production in targeted areas;

- Increase of rice yields on small-scale irrigation perimeters supported by the project;

- Increase of cowpea yield in project production basins;

- Increase of yield per animal unit for targeted product (milk) in project areas.

- Project performance with regard to the Global Environment Objective (GEO) will be measured by:

- Increase in areas under SLWM practices in the project target production basins(for a given list of priority SLWM techniques).;

- Increase in POs and producers that have adopted SLWM techniques.

(See Annex 3 for details on measurement of the above).

Project components

- The proposed project will have a three-pronged focus aimed at addressing the main bottlenecks to agriculture modernization, i.e. low agriculture productivity, insufficient productive infrastructure and weak sector coordination.  The project will include the following components aligned with the above focus: (i) Technology transfer and service provision to agricultural producers; (ii) Investments in small and large-scale irrigation; and, (iii) Comprehensive programmatic approach and sector monitoring.

Component 1 - Technology transfer and service provision to agricultural producers (US$59.1 million: IDA: US$27.8 million; IFAD US$13.8 million, GEF-IDA: US$3.8 million, Beneficiaries: US$3.7 million, GoM: US$10.0 million)

- The component’s objective is to foster the modernization of smallholder farming systems and supply chains through dissemination of improved technologies and practices, and through the professionalization of agricultural support services.  Project beneficiaries will (i) implement a range of innovative techniques and technologies to increase productivity, including SLWM techniques and technologies; (ii) gain access to critical financial investment services; and (iii) manage their newly-acquired productive assets (infrastructure and other investments) efficiently, to increase their competitiveness.  The project will help strengthen and expand the range of services delivered to producers and address the weak capacities for service provision.  The GEF dimension of the project will support technology generation and dissemination, as well as strengthening of the capacity of service providers and end-users, to mainstream SLWM practices in crop and livestock production, rangeland management and agro-forestry.

Sub-component 1.1 – Farming systems and supply chains modernization (US$37.0 million: IDA: US$15.4 million; IFAD US$8.6 million, GEF-IDA: US$3.8 million, Beneficiaries: US$3 million, GoM: US$6.2 million)

- The objective of this sub-component is to promote and disseminate productive technologies and techniques in order to increase smallholders’ farm productivity and enhance competitiveness of supply chains. The project will support the financing of profitable modernization packages, including production and processing technologies, related inputs, equipment and infrastructure, as well as critical support services such as technical assistance for investment design, implementation and follow-up, training and business management advice. For each selected production system, improved technologies exist and are readily available for dissemination.  The project will support the dissemination of these technologies through the funding of farmer-implemented investment ‘sub-projects’ that will be selected through a competitive demand driven process in the field of: (i) farm and agricultural technique modernization; (ii) livestock production system modernization; (iii) intensification and diversification techniques at Office du Niger; (iv) small scale irrigation intensification techniques; (v) post-harvest operation techniques; (vi) demand-driven and on-farm research; (vii) sustainable land and water management techniques. These sub-projects will cover specific training and advisory support packages for investments in irrigation infrastructure under component 2.  The project will capitalize on experiences gained from other projects to adapt procedures and expand them in each of the targeted production systems. It will also benefit from technical structures and service providers already existing in project’s intervention areas and will replicate their models in order to scale-up innovative technologies, including SLWM practices (See Annex 18 for a list of these technologies).

Sub-component 1.2 – Capacity building for POs and service providers 
(US$12.3 million: IDA: US$6.9 million; IFAD US$2.6 million, Beneficiaries: US$0.7 million, GoM: US$2.1 million)

- The project will support capacity building of APCAM, CRAs and POs. It will support the hiring or training of PO staff for selected internal functions so that they can deliver services to their members. The project will provide technical and managerial training programs that are targeted to production systems, producer leaders within advocacy organizations, and technical assistance to POs, including water users’ associations.  It will provide support to refurbish, equip and improve management and functioning of the existing network of CRAs so they can become professional service providers, where POs and others stakeholders will be able to find critical services, such as technical advice and market information. Along with other donors, such as the Canadian Co-operation, the project will help restore in-country training capacities for producers and agricultural technicians.

Sub-component 1.3 – facilitating rural credit development 
(US$3.1 million: IFAD US$2.6 million, GoM: US$0.5 million)

- The project will facilitate rural credit development, following recommendations from the Bank’s 2006 Rural Finance Study, by providing financial management and accounting assistance to investors in the agribusiness sector. In particular, the project will: (i) support small specialized units within banks and micro-finance institutions (MFIs) dedicated to farming systems and value chain modernization; (ii) strengthen CRAs and private actors in providing advice to producers; (iii) adapt existing financing tools to value chains by scaling-up innovative financing instruments well suited to the ARD sector (leasing, warranties, etc.); and (iv) undertake a study on index-based insurance. By the end of the project, it is expected that 75% of POs' sub-projects financed under sub-component 1.1 are cofinanced by a bank or MFI credit.

Sub-component 1.4 – Technology Generation and Research – Producers Linkages
(US$6.7 million: IDA: US$5.5 million; GoM: US$1.2 million)

- The project will facilitate technology generation by supporting the National Agricultural Research Committee and will strengthen linkages between research, extension and producers by supporting the Regional Committees for Research and Extension. The competitive financing mechanism set up under PASAOP will be maintained, with its two windows for strategic and demand-driven research. The project will place special emphasis on soil fertility and water management in targeted production basins, and will draw on the support provided under the WAAPP to make Niono a center of excellence specializing in rice production for the sub-region.

Component 2 - Irrigation Infrastructure (US$67 million: IDA: US$19.3 million; IFAD US$16.1 million, EU: US$19.5 million, Beneficiaries: US$3 million, GoM: MUS$9.1)

- This component will finance infrastructure to improve water management. Irrigation design will pay particular attention to the protection of soil and water resources. All irrigation development investments funded by the project will include a package of advisory support services financed under component 1.

Sub-Component 2.1 – Small-scale irrigation 
(US$23 million: IDA: MUS$2.2; IFAD: MUS$16.1, Beneficiaries: MUS$1, GoM: MUS$3.7)

- The project will contribute to the increase of rice production and diversification and enhance the competitiveness of related value chains by expanding the area under irrigation in the targeted production basins. The project will support feasibility and environment studies for small-scale irrigation investments. It will contribute to the development of 1,500 hectares (ha) of new small-scale gravity-fed village irrigation schemes and 3,100 ha of small-scale lowland development through sustainable rainwater management practices. Investments aimed at establishing profitable production areas will be done in partnership with local POs and sustainably managed by the beneficiaries. Expected features of these irrigation schemes include: (i) economic viability and compatibility of available resources within the farming systems; (ii) responsiveness to local beneficiaries’ needs; (iii) technical and reliable design that allows for high levels of water and soil productivity (e.g. drainage) without harmful environmental impacts; (iv) manageability through a local organization adapted to available capacities; and (v) design in accordance with the degree of beneficiaries’ involvement in the investment and management of the scheme. Support will include other governance and managerial issues such as O&M, water fees and land tenure.

Sub-Component 2.2 – Large-scale irrigation 
(US$44 million: IDA: MUS$17.1; EU: MUS$19.5, Beneficiaries: MUS$2, GoM: MUS$5.4)

- The project will contribute to the expansion and modernization of the Office du Niger (ON) area through expansion of the land under irrigation and improved management of the scheme along the lines of the ON area development master plan. The project will develop 2,200 ha of irrigable land at Sabalibougou for which a detailed design study is available. The scheme will follow the ON’s standard using a mix of on-supply and on-demand flow regulation. The project will also support 500 ha of new irrigation scheme at M’Béwani, as well as the extension of the drainage system (53 km). These investments will complement the EU-funded ACTION project, which will build the Kala Supérieur main drain (70 km).  The project will propose a range of options in terms of land tenure, technical and financing opportunities to farmers settling in the newly developed areas with a view to encouraging them to invest and increase their contribution to construction costs. The project will also pilot, on 1,000 ha, a voluntary consolidation of existing holdings to improve the economic viability of smallholders.

- The project will complement the on-going policy dialogue between GoM and donors on ON’s modernization and governance by promoting managerial reforms, updating the land tenure policy and undertaking strategic studies on maintenance, cost structure and socio-economic assessment of land and water management practices. Concurrently, the Bank will also pursue the same policy dialogue under the on-going Poverty Reduction Support Credit (PRSC) series to help clarify future public and private investments at ON with respect to water availability.

- The project will enhance efficiency of water management in the ON through for instance improved organizational framework of tertiary canal users’ associations, revision of incentives for efficient water management, and the dissemination of low water consumption cropping techniques. The project will also provide: (i) capacity building and equipment for a strict monitoring of environment and social safeguards and for a close supervision of mitigation measures; (ii)  equipment to replace auscultation instruments and technical assistance to update manuals and emergency preparedness plans for the Markala and Sélingué dams.

Component 3 - Comprehensive programmatic approach, sector monitoring and Project Coordination (US$26.9 million: IDA: US$15.9 million; IFAD US$2.1 million, GEF-IDA: US$2.4 million, GEF-UNDP: US$1.9 million, GoM: US$4.6 million)

- This component supports the evolution toward a programmatic approach in the agricultural sector through facilitating institutionalized policy dialogue between the GoM and donor partners, establishing the framework for shared financing, enhancing the design of key public programs, and improving the evidentiary base for monitoring sector performance.

Sub-component 3.1 - Policy dialogue and coordination (US$4.2 million: IDA: US$1.8 million; IFAD: US$1.1 million, GEF-IDA: US$0.6 million, GoM: US$0.7 million)

- The project will support policy dialogue between Ministries, POs, private sector representatives and donors to strengthen the coordination of the sector and forge a more consistent programmatic approach of investments and interventions. It will facilitate (i) the elaboration of the national agricultural sector investment program (PNISA) based on joint donor efforts and the NEPAD/CAADP process; (ii) the elaboration and implementation of the agricultural policy, including the development of policy options or institutional reforms within key Ministries and public entities (e.g., ON modernization, cotton subsector reforms); and, (iii) the implementation of the CSIF and the promotion of SLWM in agricultural investments.

Sub-component 3.2 – Sector monitoring and evaluation (US$5.5 million: IDA: US$2.7 million; GEF-IDA: US$1.8 million, GoM: US$1.0 million)

- The project will seek to: (i) restore the regular production of reliable statistics on the sector; (ii) provide reliable data and up-to-date information to policy decision makers; (iii) facilitate sector-wide consultation based on reliable information and analyses; and, (iv) monitor sector evolution and progress. The project will provide technical assistance and support for (i) assessing agricultural sector performances, based in particular on annual rural households’ surveys and production and yield assessments; and for (ii) monitoring the evolution of natural resources and the impact of agricultural investments on the environment.

Sub-component 3.3 – Delivery of Core Public Services (US$12.8 million: IDA: US$7.7 million; IFAD: US$1.0 million, GEF-UNDP: US$1.9 million; GoM: US$2.2 million)

- The project will facilitate the emergence of a pluralistic network of service providers through the creation of the National Agricultural Advisory Service Council. This sub-component will help line Ministries deliver core public services that are critical to agricultural productivity increases and to the competitiveness of value chains. Quality control will be among the most critical, not only for inputs (fertilizers, pesticides, seed certification), but also for extension services (accreditation and control of service providers) and public investments (irrigation schemes). In the livestock sector, this would include surveillance of animal diseases, control of veterinary medicinal products and food safety. The project will also support the supervision of environmental safeguards by MEA, the elaboration of the national strategy for small scale irrigation development by DNGR and the dissemination of information and training on SLWM by STP-CIGQE, as well as the dissemination of national legal text and guides developed on agriculture, natural resources and water management, forestry and pastoral codes.

Sub-component 3.4 – Project coordination and monitoring and evaluation 
(US$4.4 million: IDA: US$3.7 million; GoM: US$0.7 million)

- This sub-component will finance project implementation, coordination of stakeholders, monitoring and evaluation.

Lessons learned and reflected in the project design

- Demand-driven approaches are effective for service delivery and micro-projects, but they carry risks of fragmentation and dispersion of impact. Demand-driven mechanisms with a totally open menu can result in a large number of small-scale investments, each of which may be valued by beneficiaries, but when taken together do not demonstrate coherence or synergy sufficient to achieve impact.

- Capacity building should not be restricted to primary beneficiaries. Other stakeholders may also be key to success, and their capacity needs should be recognized and addressed. The project will focus its investments on producers but will provide training to other stakeholders critical to the project’s success, such as agricultural researchers and extension agents, and service providers for quality control and phyto- and zoo-sanitary surveillance.

- Empowering producer organizations can be a catalyst for change. PASAOP and similar projects in the sub-region, such as in Senegal, have demonstrated that POs are a critical vector of change and can play a lead role in policy dialogue to foster institutional changes, policy reforms or innovative implementation arrangements. This requires training programs tailored to producer leaders to help them, not only better manage their organizations, but to also better understand their socio-economic environment, policy issues or the challenges that they face within the supply chains. It also requires providing technical assistance to enable POs to hire their own technical staff.  As in Europe or in the United States, strong regional organizations such as the cotton union in Burkina Faso or the PO federation in Senegal have their own technicians to help leaders analyze studies, prepare meetings with Government or negotiate with other stakeholders.

- Combining soft and hard investments need to be done in parallel to maximize efficient use of resources. The PNIR and PASAOP partly failed in delivering simultaneously physical investments in irrigation and advisory services to producers to ensure the effective use of these investments. There are always scheduling or financing constraints, or even competition among projects or institutions, to efficiently deliver the two kinds of support at the same time. As is currently done under PACR and PCDA, it is critical to deliver soft and hard investments as a package with provision of mandatory training or advisory services to beneficiaries.

- Promoting a demand-driven approach to advisory services has been recognized as best practice. Malian agriculture is progressively moving away from a Government-led and top-down extension system. PASAOP, and similar projects supported by the French and Dutch Co-operations, have promoted a more demand-driven and private delivery of advisory services. This approach is well recognized in terms of offering customized agricultural advice to producers according to their needs. The proposed project will further this approach by supporting the strengthening of existing private providers and the emergence of new ones, including the development of advisory services internal to producer organizations.

- Beneficiaries can play a key role in greater ownership of small-scale irrigation investments. The PNIR as well as EU, German and Dutch-funded projects has shown that a labor-intensive approach allows for significant reduction in investment costs while increasing the beneficiaries’ contribution and sense of ownership. However, ownership and long-term sustainability are not guaranteed unless there is close supervision and adequate level of post-construction support especially on the marketing side.  It is important to be aware of social issues related to fair representation of users’ interest in irrigation schemes. Social assessments will be key inputs to the irrigation design and selection process.

- Policy dialogue on large-scale irrigation at Office du Niger is on-going. Previous experience of private co-financing has demonstrated that a turn-key approach to area expansion is feasible but that the selection of farmers needs to be done early in the process by targeting groups of organized farmers instead of a collection of individual applicants. Shortcomings in ON’s management need to be addressed simultaneously through continuous policy dialogue, including instruments such as the PRSC.

Alternatives considered and reasons for rejection

- APL approach: The PNIR and PASAOP were originally designed as APLs.  However, during the 2007-11 CAS discussions, a strategic decision was made to consolidate and realign the agriculture portfolio in order to scale up progress in the sector investment program. Three key projects were retained as part of a renewed World Bank ARD strategy to address: (i) grassroots socio-economic development, through the Rural Community Development Project; (ii) supply chain promotion, through the Agricultural Competitiveness and Diversification Project; and (iii) agricultural productivity, by merging the PNIR approach on irrigation with the experience of the PASAOP in delivering agricultural services and empowering POs.  This decision was consistent with the conclusions and recommendations of the 2006 CEM and the 2004-06 CAS completion report.

- SWAp approach: Initial discussions envisaged the proposed operation as a SWAp that would combine the various projects and programs into one large investment program. However this approach was rejected due to the lack of a well-prepared Public Expenditure Review (PER) and Medium Term Expenditure Framework (MTEF), and the on-going discussions with Government and donors that was launched over the past year. The project under component 3 will support the elaboration of PER and MTEF and thus will contribute to the transition towards a SWAp process.  At the MTR, some design features may be revisited to ensure proper alignment with the proposed programmatic approach.

IMPLEMENTATION

Partnership arrangements

- The project has been prepared in close collaboration with key development  partners.  Selection of project targeted production systems was based on an agricultural potential and market opportunity analysis.  Other donor interventions were also taken into account to target specific production basins and ensure coordination and synergies with other projects and programs.

- On-going discussions towards a harmonized sector investment approach are expected to result in a joint agreement of financing mechanisms and implementation arrangements.  Component 3 of the project will complement technical assistance currently being provided to the Statistics and Planning Unit (CPS - Cellule de Planification et de Statistiques) by the Danish and Belgium Co-operations. All donor financial assistance in support of SWAp preparation and PNISA elaboration will be pooled into a consolidated budget support operation, led by the CPS.

- Joint investments in irrigation provide opportunities for synergy and complementarity. In the area of small-scale irrigation, the GTZ-funded PASSIP leads the elaboration of a small-scale irrigation promotion strategy. The proposed project will implement this strategy in the targeted production basins. IFAD has also expressed strong interest in small-scale irrigation and will provide co-financing support to scale-up irrigation investments under sub-component 2.1, as well as support to the provision of advisory services and POs empowerment. For large-scale irrigation, traditional donors of the ON are progressively moving towards co-financing common irrigation schemes. This will be the case at M’Béwani (sub-component 2.2) where the EU, under the ACTION project, is financing a first tranche of investments.  The proposed project will complement EU’s investment by financing a second tranche for irrigation works and extension of the drainage network. The Dutch and Canadian Co-operations have already expressed interest in co-financing additional tranches.

- Consistent with this approach, the EC is allocating 14.64 million Euros (US$20 million) to the project as part of its Food Price Crisis Facility for Mali. On-going collaboration with IFC will be strengthened to seek complementarities with potential private investments in irrigation development and contract farming for smallholders, within the framework of the SoSuMar project. The proposed project will also complement the AfDB-funded PDI-BS with a focus on advisory services to producers on the Maninkoura irrigation scheme.

- Move towards basket funding for agricultural services: Under component 1, the project will work closely with the Denmark-funded PASAM to implement the LOA recommendations for establishing the FNAA, and to also create a harmonized financing mechanism - a basket of funds – to facilitate producers’ access to modernization techniques and technologies and advisory and training services. In the area of credit access facilitation, the project will collaborate with IFAD’s micro-finance support project to help build professional linkages between POs and MFIs and to develop innovative financing instruments for agricultural smallholder modernization.

- GEF partnership: As a fully blended IDA/GEF operation, the project will build upon on-going Bank/UNDP technical assistance on SLWM policy provided to the Ministry of Environment and Sanitation (Ministère de l’Environnement et de l’Assainissement - MEA), and institutional reviews under the TerrAfrica Initiative. The Bank, GTZ and other donor partners are supporting the preparation of a SLWM country strategic investment framework (CSIF) that will identify priority areas for intervention. The project’s interventions will rely on the ecosystem and SLWM technical study funded by TerrAfrica where a number of best practices were made available for the various production systems (see Annex 18). Dissemination has already been initiated by the SLWM technical committee through a dedicated GIS mapping tool. The project will contribute to mainstreaming SLWM best practices in the target production systems. Advisory services on reducing land degradation will also be delivered through the project under the GEF Strategic Investment Program (SIP). UNDP will play a leading role in environmental governance, notably in relation to better engaging the MEA in the overall supervision and implementation of the project, and in strengthening the environmental monitoring and impact evaluation of the agricultural and livestock sectors. UNDP will also contribute to disseminate climate-resilient agricultural techniques in project targeted production basins.

- Complementary support to production systems: The project will work closely with the Dutch and French Co-operations to support productivity increase of irrigated rice production systems within the ON area. For cotton productivity increase, the project will help scale-up some key findings from the AfD-funded PASE, which focuses on the cereal/cotton production system.

Institutional and implementation arrangements

- The project is expected to pave the way for a smooth transition towards a sector-wide approach. Financing mechanisms, including disbursements, will follow national procedures, consistent with the Paris Declaration and the project will not establish any stand-alone project implementation units (PIUs). Project implementation will rely on public-private partnerships (PPPs) for activity planning, decision making, funding allocation, and monitoring and evaluation. With the exception of core public functions, implementation of project activities will be contracted out (using performance contracts) to private agribusiness entrepreneurs, POs (including associations, cooperatives, GIEs), private service providers, and firms.

- Overall project supervision and strategic coordination will be led by the Ministry of Agriculture (MinAgri).  The National Steering Committee (PNISA-NSC), within MinAgri, is responsible for the preparation of the PNISA and is the legitimate entity to ensure overall supervision and strategic coordination of the project.  It includes other Ministries and Government agencies involved implementation, as well as the Ministry of Finance (Borrower representative) and the Ministry of Industries.

- Operational coordination will be under the responsibility of MinAgri that will establish a Technical Execution Coordination Committee (Comité Technique de Coordination et d’Exécution - CTCE) to monitor project implementation, ensure coordination of field interventions and build synergies among project stakeholders. Light regional TECCs will be setup in each region as interface with the national CTCE and to facilitate operational coordination of activities in the fields.

- Implementation of activities in the field under component 1 will be led by APCAM and its subsidiaries at the regional level (CRAs). The ON will be the executing agency for large scale irrigation investments under subcomponent 2.2 and the MinAgri will implement small-scale irrigation under subcomponent 2.1 and will be responsible for overall implementation of component 3.

- Financial Management (FM) information systems are in place in the ON and CRAs due to previous experience in implementing Bank financed projects. However, the FM unit is not adequately staffed in APCAM and CPS to ensure conformity with the project’s procedures. Two financial officers and two accountants will be appointed and a “multi projects” computerized accounting system will be customized to meet the project’s financial reporting needs. CPS, APCAM and CRAs will also be strengthened with procurement specialists.

- Project Implementation Manual. A detailed project implementation manual (PIM) is being prepared and will be ready prior to project effectiveness. It will include project guidelines, description of functional mandates of the various operational entities (supervision/coordination, execution/implementation, monitoring/evaluation), draft standard results-based contracts for service provision, draft terms of reference (ToRs) for recruitment, training modules, and draft accreditation procedures for service providers.

- Detailed implementation arrangements for specific sub-components (farming system and supply chain modernization, irrigation development, policy dialogue, agriculture sector and project M&E) are provided in Annex 6.

Monitoring and evaluation of outcomes/results

- Consistent with the project’s objective of improving policy decision making, the project will facilitate communication and dissemination of M&E results to all stakeholders in order to enhance knowledge of production systems and value chains. It will also support APCAM and the CRAs’ in the dissemination of synthesized analysis to rural farmers, through the POs and value chain inter-professional organizations.

- The CPS will have overall responsibility for M&E. At the regional level, one staff from the Agricultural Regional Division and from each CRA will be dedicated to data collection, compilation, communication and dissemination of M&E results to the central levels. The project will provide technical assistance and capacity building support to the CPS to carry out this function. Budget allocations under component 3.2 (sector monitoring) will be available to undertake on-demand studies and field surveys relevant to the M&E process. The CPS will delegate responsibility for collection of production yield measurements to the Mali Rural Economics Research Institute (IER – Institut d’Économie Rurale), and for data collection on urban markets to the Agricultural Market Observatory (OMA - Observatoire des Marchés Agricoles). POs, relevant public services and other implementing entities will also be actively involved in the overall collection and measurement methodology. The project will finance two impact evaluations, at the mid-term and at completion, to assess outcomes and results on the ground.

- The CPS will also delegate all environmental/social and SLWM-related M&E activities to its counterpart at the Ministry of Environment and Sanitation (MEA-CPS).  The MEA-CPS will be responsible for close monitoring of the Bank’s safeguard policies. Two dedicated staff will be assigned to work closely with the M&E team from MinAgri.

Sustainability and Replicability

- Sustainability of project interventions relies on the following elements: (i)  key stakeholders from line Ministries and professional organizations as well as representatives from primary beneficiaries contributed to project design and content, thereby ensuring relevance; (ii) implementation will be mainstreamed into Government structures and rural organizations (including POs, value chain inter-professional organizations, APCAM/CRAs, rural finance entities, etc); (iii) the “subsidiary principle” will guide all field interventions by empowering competent decentralized entities to be responsible for implementing investments and managing infrastructure; (iv) strengthening rural organizations is integrally embedded in the project to ensure that physical infrastructure and other investments are well managed and maintained after project closure; and (v) SLWM practices are mainstreamed within interventions for agricultural productivity increase.

- Since the project builds upon two predecessor projects (PASAOP, PNIR) and complements the ongoing PCDA, it will refine and scale-up already-established mechanisms to deliver infrastructure investments and services, as well as generate and disseminate technologies. The project will focus on specific farming systems and production basins, but its approaches will be replicable to other crops and animal productions, or to other production basins. Project activities have been designed to contribute to Government’s development program (LOA). The modernization fund is one such example where it will prefigure one of the core operational programs of the FNAA.

Critical risks and possible controversial aspects

- Summary of Sector, Operational and Overall Risks:

| Risks | Rating | Mitigation Measures | Resi-dual |  |
| --- | --- | --- | --- | --- |
| I. Sector Governance, Policies and Institutions |  |  |  |  |
| Weak sector coordination: Limited ability for sector Ministries to coordinate. | H | - Moving towards a sector programmatic approach is a key objective of the third component. | M |  |
| Limited professional and private sector capacities: Slow technology dissemination on a large scale. | S | - The project will invest in capacity building for POs, private and public service providers. | M |  |
| Natural Risks: Mali remains vulnerable to droughts, crop and epizootic pests. | S | - Investment in irrigation, intensification and diversification, as well as in ecosystem resilience through SLWM, will help producers mitigate natural risks. | M |  |
| Overexploitation of natural resources: Continued decline in soil fertility, aggravated by climate change, may hinder productivity. | S | - Disseminating SLWM practices and techniques will help reduce and reverse land degradation. | M to L |  |
| Difficult Access to agricultural inputs: Producers’ progress towards system modernization threatened by high prices. | S | - Technology dissemination, including SLWM techniques and farm modernization, will help producers mitigate or reduce its potential impact. | M |  |
| II. Operation-specific Risks |  |  |  |  |
| Limited Implementation capacity: Within Public institutions, professional organizations and private sector. | H | - Strengthening implementation capacities is at the core of the proposed operation; build a sound, pluralistic and reliable network of agricultural service providers. |  | S |
| Sustainability: Poor management and maintenance of irrigation infrastructure. | H | - Capacity strengthening of POs will ensure that physical infrastructures and other investments are well managed and maintained after project closure. |  | M |
| Competition over project coordination: Coordination may be subject to competition among public institutions involved. | M | - The lead role of the MinAgri CPS is well recognized and project interventions under component 3 will confirm and empower the CPS. |  | L |
| Financial Management: Project is complex; multi-sectors; and large number of activities. | S | - FM arrangements for this project will rely on national administrative and financial procedures agreed on during the FM assessment of the country system. |  | M |
| Procurement: Weak capacity may delay project implementation. | M | - The project will include capacity strengthening in procurement, especially with producer organizations. |  | L |
| Social and environmental safeguards (Category A): Fragmented institutional environment and weak public and private capacities may slow sown implementation. | H | - Capacity building activities will be undertaken to ensure a sound monitoring of safeguards and close supervision of mitigation measures implementation. |  | M |

| III. Overall Risk (including Reputational Risks) |  |  |  |
| --- | --- | --- | --- |
| - The project is an environmental Category A operation due to large scale investment in irrigation and risks associated with resettlement activities. - The fragmented institutional environment and the weak capacities of both public and private institutions may slow down implementation. | S | - The Bank will ensure close supervision of this operation. The project will finance technical assistance to support national institutions in the implementation of project activities with a particular attention to safeguards issues and to the implementation of the resettlement plan. - Under the PNISA elaboration process, the Bank along with other donors will pursue efforts to improve sector coordination and harmonization of field interventions. - The project will be critical in piloting common national financing instruments for technology dissemination and service provision to producers. | M |

- The proposed operation does not face any particular technical challenges or issues; it will build upon two predecessor projects that have been able to generate and test technologies ready for dissemination on a larger scale.

Credit conditions and covenants

- Effectiveness Conditions:

  - The APCAM Subsidiary Agreement has been executed on behalf of the Recipient and the APCAM.

  - The ON Subsidiary Agreement has been executed on behalf of the Recipient and the ON.

  - The GEF Co-financing Agreement and the EU Co-financing Agreement have been executed and delivered and all conditions precedent to their effectiveness or to the right of the Recipient to make withdrawals under such instruments (other than the effectiveness of this Agreement) have been fulfilled.

  - The Recipient has adopted a Project Implementation Manual in form and substance satisfactory to the Association.

  - The Recipient has established a financial and management system in form and substance satisfactory to the Association.

  - The Recipient has appointed the following staff of the CPS, under terms of reference and with qualifications and experience satisfactory to the Association:  a project planning and management specialist, two financial management specialists, a procurement specialist, and a monitoring and evaluation specialist.

- Covenants:

  - The Recipient shall establish and maintain a financial management system including records, accounts and preparation of related financial statements in accordance with accounting standards acceptable to the Bank. The Financial Statements will be audited in accordance with international auditing standards. The Audited Financial Statements for each period shall be furnished to the Association not later than six (6) months after the end of the project fiscal year;

  - The Recipient shall prepare and furnish to the Association not later than 45 days after the end of each calendar quarter, interim un-audited financial reports for the Project, in form and substance satisfactory to the Association;

  - The Recipient will be compliant with all the rules and procedures required for withdrawals from the Designated Accounts of the project.

- Disbursement conditions:

  - No withdrawal shall be made for expenditures for the construction of the M’Béwani irrigation system (under Component 2.2) unless the Recipient has provided evidence satisfactory to the Association that the Environmental and Social Impact Assessment for this investment has been carried out under terms and conditions satisfactory to the Association.

APPRAISAL SUMMARY

Economic and financial analyses

- The economic and financial analysis shows the efficiency of the investments planned by the operation until 2015 (Table 2). The internal economic rate of return (IRR) is estimated at 34 percent, which is significantly higher than the capital opportunity cost of 12. This shows that the operation’s investment choices are satisfactory in regard to alternative choices. The net present value (NPV) of the economic analysis amounts to over 92 billion CFAF or about US$184.2 million for the six years of the operation, well above the initial level of investment. The cost-benefit ratio is equal to 1.38, showing that benefits well surpass costs. These results show the profitability of the investments supported by the operation.

- With the adoption of technologies inferred by the operation’s implementation and the expected impact on yield levels and potential area increases, the internal financial rate of return for the targeted farming models is estimated at 23 percent, which is higher than the estimated 20 percent capital opportunity cost on the financial market. The NPV is estimated at 43 billion CFAF or about US$86.1 million and the cost/benefit ratio is equal to 1.25. These results show that the operation is financially profitable.

Table 2 - Efficiency of planned investment (2010-2015)

| Synthesis indicators | 2010-2015 (6 years) |
| --- | --- |
| Economic analysis |  |
| IRR | 34 % |
| NPV | 92.1 billion CFAF – US$184.2 million |
| Cost/Benefit Ratio | 1.38 |
| Financial analysis |  |
| IRR | 23 % |
| NPV | 43.1 billion CFAF – US$86.1 million |
| Cost/Benefit Ratio | 1.25 |

- When analyzing the financial profitability of the operation for the farming systems by geographical zones, the IRR remains relatively high ranging from 27 to 64 percent (see Annex 9). In the short term, small producers will benefit more from the investment, while for the medium producers, positive effects will be felt in the long term. If the results vary according to the farming system and geographical area, the indicators are generally satisfactory because superior to the 12 percent opportunity cost of capital. This means that the small and medium farmers targeted by the operation will benefit from it. Despite additional costs for the producers, the investment in research, service provision to producers and strengthening of producers’ organizations will lead to higher yields for small producers through the adoption of improved technologies.

- The economic and financial analysis thus shows the robustness of the operation and the efficient use of public and private resources. But the project’s results can be affected by various risks inherent to its implementation, such as falling yield levels, technological adoption rates below expectation, and unfavorable changes in product prices. The sensitivity analysis shows the results to be robust to these risks, even though the project’s profitability is sensitive to decreases in yield levels. If yields were to decrease by 12 percent from the project’s benchmark, the critical value of the IRR or NPV could be reached. But the probability of this situation occurring is very small because current (benchmark) yields are very low. The analysis clearly demonstrates the importance of investing in research and technology transfer by targeting an increase in yield levels, especially for the small producers.

- The economic and financial analysis also shows indirect impacts on income and employment in rural areas as well as on nutritional contribution for the targeted population. Some 90,000 jobs could be created over 6 years through the investments’ indirect effects. The increased rice production should lead to an import-substitution value of 127 billion CFAF if the price maintains itself at 400 F/kg. In terms of nutrition, the project should lead to increased availability of meat, milk and cereals for the Malian population (see Annex 9 for detailed numbers).

Technical

- The project’s design does not present any technical issues or challenges. It is built upon successful approaches developed under predecessor projects for irrigation, technology dissemination and service provision which have already been replicated by other donor-funded programs. Technologies proposed for dissemination by research institutions have been tested and adapted to local conditions. Particular attention will be given to selectivity so as to avoid fragmentation of investments.

- Under irrigation investments, the project will pilot a voluntary land consolidation process in the ON area.  Procedures are being designed, with the support from international experts and Malian sociologists with in-depth knowledge of the ON. The process will be implemented by POs and based on a demand-driven and voluntary approach. The project will also pilot the use of surface and groundwater in ON as a way to increase the overall efficiency of water management.

- As part of private sector development, increasing responsibilities will be given to POs and associations to customize and implement their own investments and advisory service needs. Capacity building, technical assistance, staffing, management and sustainability will be critical to ensure success.

Fiduciary

- Financial Management: In line with the Paris Declaration, project implementation will gradually use country systems based on the results of the FM assessment of Mali’s Public Financial Management (PFM) system. Conclusions of the assessment are provided in Table 3 below. The resolution on “National Implementation of Projects Financed by IDA” has been adopted on November, 2009 for all new projects. This resolution endorses the new arrangements for implementing World Bank-financed projects through the national expenditure channel and financial management mechanism. The assessment concluded that the PFM is partially adequate for Bank-financed investment lending: (i) national budget procedures, internal controls and audit institutions will be used with some adjustments in the FM Information System (PRED) to meet projects’ needs; and (ii) accounting and reporting, Treasury management and external controls are not yet adequate. Specific FM arrangements will be established to meet the Bank’s requirements.

Table 3 – Conclusions from FM Assessment

| CPS/DAF | APCAM | Office du Niger |
| --- | --- | --- |
| Financial management arrangements have to be set up and do not meet yet the Bank’s minimum financial management requirements under OP/BP10.02. The risk rating for the CPS/DAF is Substantial. | Conclusion of the assessment is that financial management arrangements have to be strengthened and will meet the Bank’s minimum requirements under OP/BP10.02 once the mitigation measures are implemented. The overall fiduciary risk rating is assessed as Moderate. | Conclusion of the assessment is that the “Office du Niger” has already implemented Bank-financed projects but does not meet the Bank’s minimum financial management requirements under OP/BP 10.02 due to high level of fraud and corruption. The risk rating is Substantial and therefore it will not have FM responsibility under the present project. |

- Procurement: Procurement capacities remain generally weak, especially at the decentralized level. However, the Government, upon advice from the Bank and other donors, has decentralized the Procurement Directorate (Direction Générale des Marchés Publics) with delegation of approval authority up to a certain amount at the regional level. Based on previous experience in the sector, the procurement risk for this operation is rated high. For other civil works associated with small-scale irrigation, the project may use procurement agents by introducing competition among the actual existing procurement agents and other private procurement agents. For demand-driven investment projects from the modernization funds, procurement arrangements will be developed with CRAs based on the on-going experience for demand-driven grassroots investments developed under the Bank-funded Rural Community Development Project. Staffing and training will be included to help CRAs. A procurement facilitator could be recruited to provide training and advice for the first phase of the project until the mid-term review.

Social

- The project is expected to yield substantial positive social impact in the following areas: (i) smallholder producers will be the primary target of project investments and will benefit from irrigation investments and technology transfer; (ii) POs will be empowered as they will be the main implementing entities on the ground and will receive training and technical assistance to increase their capacity and participate in policy dialogue; (iii) gender, as irrigated land allocation and technology dissemination will pay attention to young and women as priority beneficiaries.

- The proposed voluntary land consolidation at ON is expected to have also a strong social impact as smallholders will be able to increase the size of their farms and better ensure their financial viability. The project will also result in a multiplier effect on the local economy by supporting entrepreneurship and agribusiness for post-harvest operations and agricultural product processing.

- The project was prepared in close collaboration with APCAM and the National Coordination of POs (Coordination Nationale des Organisations Paysannes - CNOP) that federates different supply chain and region-based producer organizations. Regular consultations were organized with various producer groups and project design and implementation arrangement will be discussed with producer representatives prior to the appraisal mission. Implementation modalities will maintain active producers’ participation in the overall monitoring and evaluation of project investments and interventions.

Environment

- Environment category: The project is classified as a Category A operation because of key investments in large scale irrigation. These irrigation investments may have adverse but limited environmental impacts mainly on water resources and may require the resettlement of local villages. As the project will also promote intensification techniques and small-scale irrigation, an environmental and social management framework (ESMF) and a pest management plan (PMP) have been prepared. An EA for the Sabalibougou irrigation scheme has been updated and a resettlement action plan (RAP) has been prepared (see paragraphs 86 and 87 below).

- SLWM techniques: GEF’s contribution, under the TerrAfrica partnership, will place strong emphasis on disseminating value-added SLWM technologies and techniques. The project appraisal mission will prioritize the targeted areas for SLWM techniques in order to form baselines to measure project performance and impact on producer adoption rates and technology dissemination. In addition, UNDP will provide support to MEA for environmental governance of the project in particular and for the whole agricultural and livestock sector in general.

- Niger River water management: Mali is an active member of the Niger River Basin Pact and has an international obligation with its neighboring countries to abide within the framework.  The project will support the on-going policy dialogue on water management at the ON.  Policy dialogue will look at various incentive structures for adopting water saving techniques, and facilitate greater transparency in planning for public and private investments.

Safeguard policies

| Safeguard Policies Triggered by the Project | Yes | No |
| --- | --- | --- |
| Environmental Assessment (OP/BP 4.01) | [X] | [ ] |
| Natural Habitats (OP/BP 4.04) | [X] | [ ] |
| Pest Management (OP 4.09) | [X] | [ ] |
| Physical Cultural Resources (OP/BP 4.11) | [X] | [ ] |
| Involuntary Resettlement (OP/BP 4.12) | [X] | [ ] |
| Indigenous Peoples (OP/BP 4.10) | [ ] | [X] |
| Forests (OP/BP 4.36) | [ ] | [X] |
| Safety of Dams (OP/BP 4.37) | [X] | [ ] |
| Projects in Disputed Areas (OP/BP 7.60) | [ ] | [X] |
| Projects on International Waterways (OP/BP 7.50) | [X] | [ ] |

- To address potential adverse social or environmental impacts, an Environment and Social Management Framework (ESMF) and a Pest Management Plan (PMP) have been prepared and disclosed on January 8, 2010 in Bamako and on January 13, 2010 at the InfoShop. To anticipate any potential involuntary resettlement due to small-scale irrigation investments, a Resettlement Policy Framework (RPF) has been prepared and disclosed on January 18, 2010 in Bamako and on January 19, 2010 at the InfoShop. As per OP/BP 4.11 on Physical Cultural Resources, an archeological survey is being conducted on the proposed irrigation sites to determine the project’s potential impact on those resources and propose mitigation measures that will be taken into account in the design, implementation and monitoring of every irrigation scheme under the project. The draft report of this study will be available by end of April 2010. As per OP/BP 7.50 regarding “Projects on International Waterways”, on October 9, 2009, the Recipient notified the riparian countries through the Niger River Basin Authority in Niamey of the type and size of the irrigation investments planned under this project. A second notification was sent on January 11, 2010 to provide specifications regarding small scale irrigation investments proposed along the Niger River.

- Irrigation investments: in addition to the ESMF, an Environment Assessment (EA) for the Sabalibougou irrigation works was undertaken in 2006 and has been updated and disclosed on January 8, 2010 in Bamako and on January 13, 2010 at the InfoShop. As four hamlets will be displaced by this investment, a resettlement action plan has been prepared and disclosed on January 25, 2010 in Bamako and on January 26, 2010 at the InfoShop. The second irrigation investment (M’Béwani) will be prepared as part of project implementation and will require its own ESIA as a condition for financing by the Bank and other co-financiers. With regard to OP/BP 4.04, the Sabalibougou irrigation scheme’s EA does not foresee any major adverse impact on natural habitats. To minimize the potential risks for the other irrigation perimeters (i.e. M’Béwani and small scale irrigation schemes), preservation of natural habitats will be checked as part of the feasibility studies that will be specifically carried out for each sub-projects. The sustainability of irrigation investments depends on reliable water provision and proper management of the Markala weir and Sélingué dam. As per OP/BP 4.37, a dam safety expert study has been undertaken. These infrastructures are in good condition and do not require any major repairs or civil works. However, some auscultation instruments need to be replaced or upgraded, O&M manuals need to be updated and emergency preparedness plans need to be prepared and disseminated. These activities have been included in the project budget.

Policy Exceptions and Readiness

- No policy and readiness exceptions are required for this project.

Annex 1: Country and Sector or Program Background

Mali:  Fostering Agricultural Productivity Project

- Country overview:

- Mali, a landlocked nation, is one of the largest countries in Africa covering 1.2 million square kilometers. Its population of 14.5 million (2009) is rapidly growing at an annual rate of 3.6 percent (between 2001 and 2007), well above the annual average growth rate of 2.5 percent in Sub-Saharan Africa (SSA). Mali’s climate comprises two seasons: a long dry season (7-9 months) and a short rainy season ( 3-5 months).  Its climate is also divided into four major agro-climatic zones, depending on rainfall amounts: (i) the Sahara (below 150 mm), (ii) the Sahel (between 150 and 600 mm), (iii) Sudan (600 to 1,200 mm), and (iv) the Guinean (above 1,200 mm). Agriculture is an essential sector in Mali, accounting for 37 percent of total GDP, employing over 80 percent of the labor force, and serving as a key source of overall economic growth and welfare, food security and poverty reduction. Despite rapid urbanization in recent years, almost 70 percent of the population lives in rural areas and close to 80 percent rely on agriculture production for their livelihoods. Climate change, population growth and natural resources degradation pose serious challenges to medium and long-term food security in the country. The country is prey to the continuing deterioration of its natural resources, which constitutes its natural productive capital and source of development. The cost of land degradation alone has been estimated to cause a loss of roughly 0.4 percent of GDP.

- Growth and poverty: Mali remains one of the poorest countries in SSA. GDP per capita was US$480 (2008) and the national poverty rate was estimated to be 47.4 percent in 2006. The national incidence of poverty has declined by about 2 percent since 1990 and dollar a day rates declined by more than 30 percent. Poverty is more prevalent in rural areas (57.6 percent) compared to cities (25.5 percent). Population growth brings over 200,000 new job seekers on the market each year. The country has experienced large fluctuations in agricultural growth, ranging from -10 to 18 percent although recently, the growth rate has been both positive and less volatile. At 6.3 percent on average between 2003 and 2008, agricultural growth has been quite robust and close to meeting the CAADP target. Mali is one of few West African countries that has met CAADP’s goal of allocating 10 percent of the national budget to agriculture. In fact, since the early 1990s (except for 1995-1997), Mali has been allocating more than 10 percent of the total national budget to agriculture, well above the CAADP goal. In 2007, the country spent 13 percent of its budget on the sector. ReSAKSS estimates that if Mali can maintain CAADP’s 6 percent annual agricultural growth target, it has the potential to halve poverty by 2015. This goal is attainable but it will require efforts to stabilize output by maintaining high yields in the food staples sector (cereals, coarse grains, and livestock) in the short run and to diversify agricultural exports in the long run.

- Food security and nutrition: Mali is characterized by chronic food and nutritional insecurity, linked to endemic poverty. Thirty percent of the population benefited from food aid during the last decade. Households’ share of expenditures for food purchase was estimated to be 72.5 percent in 2001, with significant differences between urban (67.5 percent) and rural areas (75.6 percent; including self consumption). Today, it is estimated that 25 percent of rural households (2.7 million) experience chronic food insecurity, while 32 percent (3.5 million) are vulnerable. The national incidence of hunger has declined since 1990, but not by enough to put the country on track toward achieving the hunger targets of Millennium Development Goal (MDG) 1. Malnutrition is also severe in Mali, being directly or indirectly responsible for more than 50 percent of children’s death under the age of five. The proportion of underweight children decreased to 26 percent from 40 percent in 1990.  However this rate has remained stagnant since 2001 while anemia in women has increased from 63 to 68 percent. Food insecurity and malnutrition were aggravated by the fuel and food crisis of 2008, which induced severe price inflation. For example, in Sikasso, a major agricultural trading center, maize prices have increased by about 50 percent since January 2008 and the price for sorghum has also doubled.  In 2009, food prices remain above the 2008 level and above the 5-year average.

Source: http://www.wa-agritrade.net.

- Agricultural Sector Performance

- Although the share of the sector in the overall economy has been declining for the last decade and a half, agriculture remains one of the key drivers and still accounts for above one third of GDP (subsistence farming 15 percent; modern farming 5 percent; livestock 10 percent; forestry 4 percent; and fisheries 1 percent). Cotton is the principal agricultural export, contributing 25 percent of total export earnings in 2005, followed by livestock products (however registered data only partially capture livestock exports to neighboring countries). The decline in the world cotton price has reduced Mali’s production, forcing farmers to sell livestock and machinery to pay off outstanding debts.  The sector remains highly vulnerable to environmental risks, such as droughts, floods, irregular rains and locust invasions. In 2007, the country experienced the 12th highest frequency of environmental shocks of all low-income countries. Mali’s agriculture is mostly rain-fed and production varies greatly from one climatic zone to the other. After continuous decrease during the 1960s and the 1970s, overall cereal production has increased significantly over the last two decades, at a pace consistent with the population increase.  For example, between 1984 and 2004, rice production jumped from 190,000 to 850,000 metric tons (t); maize increased from 150,000 to 400,000 t; and millet also grew from 715,000 to 950,000 t.  With the exception of rice, yields have been relatively stagnant or even declining from already low levels.

Evolution of cereals yields in Mali (hectogram/ha), 2001-2007

Source: FAOStat

- Food production increase in Mali has essentially been driven by an increase of the area under cultivation and as a result, soils are progressively being degraded. The country stands today as a net exporter of agricultural products on aggregate and cereal production theoretically covers 98 percent of the country needs.

Evolution of cotton yields and production in Mali

Source: CPS/MA & CMDT

- Agricultural export diversification is progressively taking place in the fruits and vegetable sub-sector. Major imports (including food aid) are rice (from Asia) and wheat, but also include dairy products. Cereal imports have declined significantly from an average annual volume of 150,000 t (1979-89), to as low as 45,000 t over the last decade (1990-2001).

- Farming systems

- Subsistence farming from under-equipped and low productive smallholders: There are approximately 800,000 farms in Mali.  Commercial farming is limited while subsistence farming on small family farms remains the dominant model. Roughly 87 percent of Mali’s agricultural production is self-consumed. The vast majority of producers are smallholders: 68 percent of farmers work on less than 5 hectares and 86 percent on less than 10; in the livestock sub-sector, almost half (43 percent) of the producers own a fraction (6 percent) of the national herds.  Seventy-two percent of the cultivated area is devoted to cereals, mainly produced for self-consumption, with the exception of peri-urban areas (fruits and vegetables) and large irrigation schemes managed by the Office du Niger (rice). Only four percent of farm households deliver more than half of their produce to market.

- Farm productivity is very low. Most farms are under-equipped to adopt modern practices. Livestock rearing is widespread, but animal power is common in the cotton area only. Mechanization levels are low although motorized equipment such as small chisel is being increasingly utilized on irrigation schemes within the Office du Niger area. Use of agricultural inputs such as improved seeds, fertilizers, agrochemicals for crop protection, vaccines and other animal drugs, is presently quite limited to cotton and rice productions (these two productions alone account for 60 percent of fertilizers consumption and 80 percent of pesticides consumption nationwide). Organic matter contents of the soils, which are already low in the semi-arid climate, are not replenished sufficiently, resulting in soil degradation and lower soil productivity. Post harvest losses remain high and processing technologies of agricultural outputs are largely underdeveloped. Agricultural private investments are very low in rural areas and often nonexistent. This is largely attributed to very limited access to rural credit. Finance institutions are generally not familiar with the specificities of the rural economy and show reluctance to undertake the high risks, low levels of collateral and high transaction costs involved in lending to smallholders or community groups such as producers’ organizations (POs).

- An under-exploited agricultural growth potential: Mali is progressively showing its potential and comparative advantages in agricultural production and marketing within the sub-region. It is also making progress in diversifying its agricultural exports to international markets. As population and urbanization grows in Mali and in neighboring countries, there are larger domestic and sub-regional markets for value added locally processed products. Only 12 percent of the country’s large irrigation potential is currently developed.

- Cereals, dairy products and edible oil present interesting potentialities for import substitution. Rice is the main staple food in urban areas; production has rapidly developed over recent years, but it still continues to offer potential for import substitution and value-addition. Vegetable production is a growing sub-sector, already showing good prospects in local urban markets (shallot and cowpeas, for instance), as well as in sub-regional markets (potatoes).

- Mali is famous for animal production but livestock development is insufficiently exploited. Demand for Malian cattle remains high in neighboring countries and opportunities for stronger local value-addition exist on the domestic market. Beyond traditional crops, there is potential for fodder crops and for other animal feed sources derived from agro-processing as an alternative to cottonseed residues. Studies show that there are many other product development opportunities in the horticulture or agro-forestry sectors.

- Issues and Challenges

- Issues and challenges: The 2007/08 food price crisis showed the country’s vulnerability and the need to increase investments in agriculture and raise farm productivity. The crisis threatened the urban population’s purchasing power, but at the same time constituted an opportunity for rural producers to increase their incomes through higher producer prices. It also showed the importance of supplying the domestic market through increased market shares for local producers. Furthermore, population growth trends throughout the west-African sub-region and progress in regional economic integration, lead to an exceptional potential for food production development and processing. To raise agricultural and livestock production in Mali, there is a strong need to modernize farm practices based on a sustainable land and water management (SLWM) and further develop infrastructure, in order to seize the opportunity of an under-exploited agricultural potential. This, in turn, will strongly benefit economic growth and poverty reduction. Three key constraints are still hampering the development of Mali agricultural sector and need to be tackled urgently:

- Despite recent investments, especially at ON, there is still a lack of productive infrastructure, to fully exploit the irrigation potential and to increase post-harvest management and processing capacities.

- Productivity has improved slowly but yields remain far below potential, especially at the smallholders’ level due to the use of low-intensity production techniques including a very limited use of modern agriculture inputs, poor land and water management leading to soil fertility degradation and a weak access to farm management advise and financing services. The same applies to the livestock sub-sector, where animal feeding is generally poor, combined with low productivity breeding and a lack of access to animal health inputs and services.

- the lack of coordination in the agricultural sector leading to many fragmented and scattered interventions with limited impact at the national level, and to a multiplicity of strategies for rural development and food and a lack of a unified vision for short, mid and long-term investments in the sector, based on reliable sector data. The National Agricultural Sector Investment Program (PNISA – Programme National d’Investissement Sectoriel Agricole), was adopted in October 2009 as part of ECOWAP (the regional agricultural policy of ECOWAS) under the CAADP process.  The PNISA calls for operational follow-up and adequate management capacities under GoM’s leadership. It is critical that the functional chain between data production, analysis and political decision be restored in the agriculture sector.

- The lack of investments in farm modernization, productive livestock development, storage and small scale processing facilities, means that rural dwellers are often unable to expand their productive capacities or enter into new forms of productive micro-enterprises. Finance institutions claim that the lack of farm management advice to farmers and/or producers’ organizations (both technical and financial) is the major constraint to authorizing agricultural credit.

- Sustainable land and water management: Mali’s agricultural potential is facing major barriers and challenges: soil depleting agricultural practices, loss of vegetative cover through agricultural expansion, overgrazing, excessive cutting of wood and bushfires, resulting in an on-going process of natural resources degradation. Additionally, the weakened land use systems become more vulnerable when facing droughts, floods, air and water pollution, and increasing pressure from a growing population. The environmental, social and economic consequences are serious with increasing poverty and a continued decrease in agricultural, rangeland and forest productivity. In economic terms, the impact of land degradation is high, both at the local homestead level as well as for the country as a whole. The reduction in water availability for humans, animals and for irrigation is becoming an increasingly pressing issue in Mali. This concerns not only areas that are depending on rainfall for agriculture, drinking water and groundwater recharge, but also areas, such as the Niger Inner Delta, where people depend on surface water for their livelihoods. Well-organized and sustainable management of the land and water resources will be of critical importance for the future,

- Adaptation to climate change: The impact of climate change on environmentally weakened land use systems, carries a high risk of further exacerbating the speed and severity of depleting the natural resources, which are the base for the agriculture, livestock and forestry sector. Predicted increasing temperatures, reduction and higher variability in rainfall will impact aversively agricultural seasons, land use systems’ productivity, water availability, vegetation cover and species composition. Increased migration of people and animals can be expected towards areas with higher rainfall, thereby increasing the pressure on natural resources in these areas, which can lead potentially to conflicts over access to and use of natural resources. On the other hand, the current land use systems present significant opportunities for greenhouse gas mitigation through the reduction of emissions (abandonment of land degrading practices), as well as through enhancement of carbon sequestration by improving soil carbon contents and vegetation cover. Many techniques and practices are known and available in Mali that can contribute to carbon sequestration, such as reforestation, agro-forestry, soil and water conservation, augmentation of soil nutrients and organic soil carbon contents, improved grazing systems, and the production of energy crops, among others. These practices will also contribute to creating healthier and more stable production systems showing improved resilience towards climate change. By applying this holistic vision and by making sustainable land and water management practices the foundation of the agriculture sector, productivity increases will be possible in the long-term and investments into the sector can produce the expected results, including the improvement of food security and the reduction of poverty.

- Project’s Production Systems and Reference Products

- The project’s geographic coverage has been purposely limited to key production basins, to stay within the overall financial envelope available and avoid investment dispersion. In these basins, the project will target a limited number of production systems and reference products on which it will concentrate its infrastructure and technical assistance investments. Production systems for project interventions were selected based on their high productivity potential (as evidenced by research results and technologies available) and market demand. Project selection is justified by the following product by product analyses:

- Rice: Consumption is significantly increasing over time, rising from an average of 34 kg/capita/year in 1989 to 57 kg/capita/year in 2007 (+170 percent). Urban per capita yearly consumption grew even faster. It was estimated at 67 kg in 2001compared to the country’s average of 53 kg. Rice has become a major staple food in modern Mali. Production is also sharply rising due to consistent yield increases and progressive enlargement of areas under cultivation. Yields virtually doubled in 20 years as a result of improved water management techniques reaching an average of 4.5 metric tons/ paddy/ha on irrigated land today. In 2007, the area under rice cultivation was 315,000 ha, comprising 90,000 ha of irrigated land. Rice is cultivated by more than 170,000 farmers (nearly one out of four row crop farmers) with an average crop area of 1.9 ha/farm. Rice cultivation accounted for 16 percent of total cereal production (1961-1965) and significantly increased to over 30 percent (2001-2005). Processing capacities developed accordingly. Marketing prospects are bright, with an expanding domestic market (due to rapid population growth, strong urbanization rates and evolving consumption patterns), import substitution possibilities, and growing trade within the ECOWAS sub-region.

- Maize: Mali’s domestic market for maize is also growing as demand is rising both for animal feed (estimated at 45,000t/yr.; mainly for poultry feed and sheep fattening) and for human consumption. Annual production was estimated at 710,000 t in 2006, with an average yield of 1.7t/ha.  Maize production grew around 6 percent per year between 1990 and 2006 and total cereal production increased from 11 to 19 percent over the same time frame. In 2006, land used for maize cultivation was approximately 410,000 ha, by more than 210,000 farmers (average lot size of 1.95 ha). Exports are nonexistent and imports are extremely low. However, domestic marketing opportunities are promising, as well as within the sub-region where demand is already strong in Senegal.

- Cowpeas: There is little data available on this traditional crop. Recent research conducted in Mali and in other parts of West Africa has led to improved high-yielding seed varieties associated with modern cultivation techniques in open fields. The crop is currently being developed with demonstration and technical assistance from several ARD projects in Mali. Results are promising, showing good adoption rates by farmers and no marketing difficulty. Cowpea crops are not only an important nutritional source of human consumption but also as a fodder source for livestock.

- Cow milk: Milk has an excellent nutritional value. Average per capita yearly milk consumption in Mali is estimated around 38 liters, far from FAO’s recommendation of 60 liters. Demand is increasing particularly in urban areas. A 2007 preparatory study in the project’s target areas revealed that daily urban demand ranged from 130,000 to 170,000 liters although total local production barely exceeded 11,000 to 18,000 liters (or 9 to 11 percent). Mali’s total milk production is estimated around 500 million liters, of which 300 million liters are from cows.  Average yield per cow is extremely low at around 1.5 liters/day. It is estimated that 20 percent of Mali’s milk production is presently collected and processed in a dozen industrial units. Mali Lait is the largest milk processing firm: 10 percent of its input is locally bought (approximately 2,500 liters per day); the rest is imported mainly from Europe in the form of milk powder. Mali faces huge import bills for milk annually (close to 15 billion FCFA in 2007). Development of local milk production and processing has the potential to lead to an array of products which could easily penetrate the domestic market.

- Fodder: With the downturn in Mali’s cotton production, demand for animal feed alternatives to cotton-seed meal is increasing. Fodder production systems have been extensively studied and enhanced seeds associated with modern cropping techniques are available under Mali’s farming context. Consistent economic data on such crop is not available yet.

- Sheep meat: Average per capita consumption of sheep and goat meat is estimated at 6.3 kg/year which is comparable to other countries in the sub-region. It is expected that demand for sheep meat would rise in the future due to population increase, urban growth and related changes in consumption patterns.Mali’s national sheep meat production estimated at 37,000 t and 53,000 t for goat meat; largely meets its domestic market. Exports are dynamic due to the country’s central geographic position and close proximity to many importing countries from the Arab world. Religious festivals such as Aïd and Ramadan provide quite lucrative markets. Official data estimates that exports of live sheep and goats are approximately 180,000 heads per year. However, given informal trade that dominates this market, exports probably represent another 500,000 heads/year. Women play a key role in the rearing of small animals in Mali’s traditional farming households. Experts believe that easy to implement intensification techniques would quickly enhance rearing performances both in yield and improved quality.

- Poultry meat: Poultry farming was estimated to contribute 2.1 percent of GDP in 2007. Modern aviculture is very small in Mali (producing approximately 200 t. per year only), whereas traditional rearing would account for roughly 38,000 t. Population growth and rapid urbanization tend to increase the size of the domestic market. Mali’s exports of live hens are regular (Ivory Coast, Burkina Faso, Ghana and Guinea), but rather small (estimates are less than 400,000 birds/year). Poultry meat imports in Mali are negligible. Nevertheless, there is a large poultry meat market in the ECOWAS sub-region, still partly furnished through imports (initially from the EU and progressively more from Brazil). However, import volumes tend to decline in the sub-region, as local production is scaling up.

- Rationale for Bank involvement

- As highlighted by the 2006 Country Economic Memorandum (CEM), Mali’s agriculture sector has substantial potential for growth due to its comparative advantage relative to other sectors of the economy. Using a social accounting matrix, the CEM also suggests that pro-poor growth could be sustained if food crops, livestock, food processing, export crops and personal and collectivity services sub-sectors perform well. These sub-sectors are virtually all agriculture related and account for a large share of current GDP. The social accounting matrix (SAM) also shows that output growth in the agriculture sector would have the biggest impact on reducing poverty among rural households.

- The agriculture sector also has substantial potential to reduce poverty in view of the large share of population’s poor who are engaged in the sector. In Mali, growth in agriculture is definitely pro-poor: it harnesses poor people’s key assets of land and labor, and it creates a vibrant economy in rural areas where the majority of the poor live. Agriculture connects economic growth to the rural poor, increasing their productivity and incomes. Moreover, the importance of agriculture for poverty reduction goes well beyond its direct impact on rural incomes. Agricultural growth, particularly through increased agricultural sector productivity, also reduces poverty by lowering and stabilizing food prices, improving employment for poor rural people, increasing demand for consumer goods and services, and stimulating growth in the non-farm economy. The challenge is to generate high rates of growth in agricultural productivity, while also enabling a socioeconomic and political environment that fosters the links between agriculture and other sectors of the economy. The Bank is a long time partner of agricultural development in Mali and is particularly well placed to spearhead further development efforts as it is one of the leading donors in the rural sector.

- Supporting an explicit Government strategy: Agriculture is central to GoM’s development strategy; its development is recognized in all strategic documents as the main engine for economic growth and poverty reduction. The first strategic pillar of the Growth and Poverty Reduction Strategy Framework (GPRSF) sets priority on: (i) ensuring food security, and (ii) increasing the income of rural producers. This should be done through increasing, securing and diversifying food production. It is expected that this will be achieved by ensuring sustainable management of natural resources, modernizing family farms, expanding productive infrastructure and developing agro-processing.

- As a major step in 2006, the GoM adopted a founding agricultural development act (Loi d’Orientation Agricole, LOA), to lead towards a modern and competitive agriculture sector (moving smallholder family farms beyond subsistence), while also promoting agro-industries and private investments. The overall objective of the LOA is to improve the population’s livelihood by: (i) enabling the country to achieve food security, and (ii) transforming the agriculture sector into the engine of economic growth. It also provides guidance on operational tools and financing mechanisms to be set up for accelerating agricultural growth.

- In 2008, with the dual objective of tackling the food price crisis and seizing the opportunity to foster local production, the GoM launched an ambitious initiative to double rice production (from 800,000 metric tons to 1.6 million t.). This Initiative has been renewed for the current cropping season and expanded to other products such as maize and wheat.

- Finally, within the framework of CAADP and under sub-regional guidance from ECOWAS, GoM has just prepared and adopted its roadmap and compact for the elaboration of the future PNISA to cope with the general objective of sustaining at least 6 percent agricultural growth. The Bank is fully supportive of the CAADP process and its programmatic outcomes across the region.

- The Malian Government’s response to environmental degradation is articulated in several national strategies such as the GPRSF, the 2005 National Environment Report, the Mali Environmental Profile, the Action Plan for Integrated Management of Soil Fertility, the Special Program for Food Security, and the Master Plan for Rural Development. The recently adopted LOA reiterated the need to address land and water management as key constraints to the sustainable increase of crop and animal productivity. The Ministry of Environment and Sanitation (Ministère de l’Environnement et de l’Assainissement - MEA) initiated in December 2008 a cycle of national consultations on environment (“Assises Nationales sur l’Environnement”) to update the existing strategies and develop new ones to fill the gaps, including  action plans.

- The Bank’s strategy is aligned to the country’s approach: Over the last CAS period, the Bank’s portfolio in the ARD sector has been consolidated. Strategies and approaches have been fully renewed to reform public institutions and promote more demand-driven services (research and extension), to empower POs and support private sector development, to look at the organization of the entire agricultural supply chain instead of focusing on the upstream production segment, to accompany decentralization and better integrate grassroots communities and community-based organizations in economic development.

- The current Bank CAS (2007-11) places agriculture as one of the three key sectors to boost economic growth. The CAS aims at promoting a more productive agriculture sector, moving towards a more market-oriented and commercial agriculture model, and increasing factor productivity based on sustainable natural resource and environmental management. It also states that Mali should scale-up development of its irrigation potential by proactively attracting investments to supply the domestic, regional and international markets. Mali must strengthen the supply chains of existing products so as to better link those products to markets, thereby increasing the incentive for quality and productivity improvements. The project is fully aligned with the Bank’s approved CAS.

- Building on a comparative advantage and experience: As part of the CAS preparation process, the 2007 World Bank Mali client survey showed that stakeholders consider agriculture as a top development priority where the Bank has strong knowledge and comparative advantage. Not only has the Bank been very active for a long time in the sector, but its current portfolio is large, providing support to (i) institutional reforms and agricultural services, (ii) the development of productive and marketing infrastructure, (iii) supply chain organization and marketing, and (iv) socio-economic investments at grassroots level. The project will build upon the Bank’s experience of rural development in Mali.  The project will scale-up PNIR approach to expand irrigation and the PASAOP approach for delivering agricultural services to producers, with an emphasis on disseminating research results, on promoting the private delivery of advisory services, on facilitating access to rural credit and on empowering producers and their organizations. The project will also complement the on-going Bank support to supply-chain organization, post-harvest operations and product marketing. It will scale-up PCDA’s pilot experience in disseminating small-scale innovative technologies and equipments in rural communities, as well as in expanding financial services for agricultural development. Similarly, the project will complement PACR’s support to grassroots communities through the small-scale irrigation sub-component that will support POs connect with economic opportunities. On-going collaboration with IFC will be strengthened to seek complementarities with potential private investments in irrigation and contract farming for smallholders.

- The World Bank plays also a leading role in the TerrAfrica partnership initiative in regard to the Sustainable Land and Water Management (SLWM) agenda in Sub-Saharan Africa through the TerrAfrica initiative. The project will build upon the Bank’s experience of rural development and environmental management in Mali.

- Institutional reforms and donor coordination/harmonization towards a sector wide approach: Under the leadership of the Institutional Development Commissariat, ministerial structures and mandates have been revised and aligned with the general orientations of decentralization and the State’s withdrawal from economic functions (such as production, processing and marketing in the agricultural sector). This has led to a stringent refocus of public services on core public functions, although it has not yet been fully translated into coherent organizational charts and decentralization plans, with respect to staff and budget. The Bank is keen to support these institutional reforms in practical terms.

- The Bank co-chairs (with FAO) the local Mali donor coordination group in the ARD sector. There is a consensus among donors that institutional reforms are complex and sector investments, at the institutional level, should be re-focused on coordination and monitoring.  This would facilitate a more consistent approach to agricultural investments through shared policy orientations and directives, implementation strategies, harmonized service delivery and financing mechanisms. There is agreement between GoM and donors to move towards a sector wide approach. Donor agencies are expecting the Bank to lead this effort and the project is seen as a first step towards a SWAp and as a major building block to prepare and implement the future PNISA for which a roadmap and a compact has been recently adopted under the NEPAD/CAADP process. This program is acknowledged by all donor partners as the cornerstone of GoM’s vision for the agriculture sector, to ensure stronger coordination and coherence of interventions. Bank’s involvement is first and will help the Government leverage additional funding from other bilateral and multilateral donors.

- The project will also support government’s emerging efforts to establish a comprehensive programmatic approach to SLM, thus ensuring greater sector and donor alignment both horizontally and vertically through the implementation of Mali’s Country Strategic Investment Framework (CSIF) for sustainable land management.

- IFAD country strategy: The proposed project is consistent with the first strategic objective of the results based COSOP, which is to increase and diversify agricultural production in order to improve household food security and the accumulation of goods through: (i) investments to increase and diversify production and productivity; (ii) infrastructure and supporting services to process, store, and trade agricultural products; (iii) support to small scale producers and processors organization to manage productive investments and deliver technical and economic services to family farms upstream and downstream of production.

Annex 2: Major Related Projects Financed by the Bank and/or other Agencies

Mali:  Fostering Agricultural Productivity Project

- Related Bank-financed projects

| Sector Issues | Project | Last Super-vision Ratings |  |
| --- | --- | --- | --- |
|  |  | IP | DO |
| Infrastructure | P041723 - National Rural Infrastructure Project (PNIR) - Closed in December 2007 - IEG Project Outcome: S | S | S |
|  | P090075 – Projet Sectoriel Transport II – Transport Sector Project 2 – Active - Approved in FY07 | S | S |
| Technology transfer and service provision | P035630 - Agricultural Services and Producer Organizations Program (PASAOP) Approved in FY02 + Additional Financing in FY07 Closed in December 2009 | S | S |
| Supply chain development | P081704 – Agricultural Competitiveness and Diversification Project (ACDP) – Active – Approved in FY06 | S | S |
| Local development | P040653 – Rural Community Development Project Active – Approved in FY06 | MS | S |
| Water resources | P093826 - Senegal River Basin Multi-purpose Water Resources Development Project (regional) Active – Approved in FY06 | MU | MU |
|  | P093806 - Niger Basin Water Resources Development and Sustainable Ecosystems Management Project (regional) Active – Approved FY08 | MU | MU |

- Related EU and IFAD projects

| Donors | Sector Issues | Project | Coordination / Synergies |
| --- | --- | --- | --- |
| IFAD | Rural Finance | Rural Micro-Finance Program (MUS$20; 2009 to 2013) | Access to credit in rural areas |
|  | Small-scale Irrigation | PIDRN – Programme d’Investissement et de Développement Rural des Régions du Nord du Mali (MUS$37.5 – 2006- 2013) | Small scale irrigation development in Timbouctou, Gao and Kidal |
|  | Rural development | FODESA – Fonds de Développement en Zone Sahélienne (MUS$30 – 1999/09) | Demand driven investement projects – Natural resource management – Rural cerdit |
| EU | Large-scale irrigation | ACTION: Appui à la Consolidation Technique et Institutionnelle de l’Office du Niger (M€30; 2008-2012) | Irrigation expansion at M’Bewani; dedicated budget support for ON based on indicators related to managerial reforms and water management |

- Related projects financed by other donors or the GoM

| Donors | Sector / Themes | Project | Coordination / Synergies |
| --- | --- | --- | --- |
| AfD | Large-scale irrigation | PADON - Projet d’appui au développement de la zone Office du Niger (MUS$14 – 2006 – 2010) | Water savings experimentation at ON |
| AfDB | Irrigation Infrastructure | Programme de Développement de l’Irrigation dans les Bassins du Bani et du Sankarani (MUS$115 – 2010-2014) | Large scale irrigation infrastructure development in Koulikoro, Ségou and Mopti regions (Bani river basin) |
|  | Livestock | Projet d’appui au Développement des Productions Animales dans la zone de Kayes-Sud (MUS$30 – 2008 – 2013) | Livestock production |
|  | Seeds | PAFISEM – Projet d’appui à la filière semencière (MUS$5.8 - 2003/09) | Seed multiplication and dissemination |
|  |  | Projet de Diffusion du Riz Nerica (MUS$6.5 – 2005 – 2010) | Rice seed multiplication and dissemination |
| Canada | PO Capacity Building | PACCEM (Ségou) Closed | Rice and cereal marketing; support to POs |
| Denmark | SWAp and rural development | PASAM: Projet d’appui au secteur agricole au Mali (MUS$28 – 2008 – 2012) | PNISA elaboration and FNAA Demand-driven PO investment sub-projects |
| Dutch | Large-scale irrigation | Projet d’appui néerlandais au contrat plan de l’Office du Niger (MUS$7.5 – 2005 – 2010) | Technical assistance to ON |
|  | PO support | PDERK – Programme de Développement Économique Rural de la région de Koulikoro (MUS$10 – 2005 – 2010) | Support to CRAs and demand-driven investment projects |
| GTZ | Small-scale Irrigation | Programme d’Appui au Sous-Secteur de l’Irrigation de Proximité (MUS$1.4; 2008-2010) | PNIP preparation and elaboration |
| KfW | Large-scale irrigation | Expansion of N’Débougou scheme at ON | Irrigation expansion close to Sabalibugu scheme |
| GoM | Livestock | PRODEVALAIT: Projet de Développement et de Valorisation de la Production Laitière au Mali (MUS$0.5 – 2009/13) | Milk production, transformation and commercialization |
|  |  | PRODEPAM : Projet de Développement de l’Aviculture au Mali (MUS$10.5 – 1998/2008) | Poultry production (meat and eggs) |
|  |  | PADESO - Programme d’Appui au Développement de l’Élevage au Sahel Occidental (MUS$5.5 OPEP – 2008 -2012) | Fodder production and Agro-pastoral management |

Annex 3: Results Framework and Monitoring

Mali:  Fostering Agricultural Productivity Project

- Project Development Objective and Global Environment Objective (GEO):

- Project Development Objective (PDO) is to increase the productivity of smallholder agricultural and agribusiness producers in the targeted productions systems and project areas. It is expected that project interventions will result in productivity increase for the targeted crops (rice, cowpea) and animal productivity for the targeted products (milk).

- Global Environment Objective (GEO) is to increase the use of sustainable land and water management (SLWM) techniques in the targeted production systems and project areas. It is expected that land under SLWM practices has increased in the project intervention areas.

- Overall project result chain:

| Long Term Outcomes |  | Food Security |  | Sustainable Shared Agricultural Growth |
| --- | --- | --- | --- | --- |
|  |  | Increased agricultural production |  | Increased agricultural incomes for smallholders |

| Medium-Term Outcomes | Secured Production |  | Increased Productivity |  | Diversified and Value-added Production |
| --- | --- | --- | --- | --- | --- |

| Short-Term Outcomes | Availability and sustainable management of water for agriculture |  | Modernization of smallholders production systems and supply chains |  | Empowerment of Producer Organizations and availability of advisory services |  | Enabling policy environment and sector coordination |
| --- | --- | --- | --- | --- | --- | --- | --- |

| Outputs | Small & large scale irrigation extension |  | Public Private Partnership and Financing for irrigation development |  | Farming Systems and Supply Chain Modernization Fund |  | New crop varieties and animal breeds dissemination |  | Sustainable land and water management techniques |  | New cropping, breeding and processing techniques |  | Network of public and private service providers |  | Capacity building programs |  | National Agricultural Sector Investment Program |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |

- Project result framework

| Project Development Objective | Project Outcome Indicators | Use of Project Outcome Information |
| --- | --- | --- |
| Increase the productivity of smallholder agricultural and agribusiness producers in the targeted productions systems and project areas. | Increase of rice production in project targeted areas Increase of rice yield on small scale irrigation perimeters supported by the project Increase of cowpea yield in project production basins Increase of milk production per milking cow in the targeted areas. | Determine if the project approach is relevant and efficient in delivering agricultural productive infrastructure, equipment and advisory services. Asses the efficiency of financing mechanisms. |
| Global Environmental Objective | GEF Outcome Indicators | Use of Project Outcome Information |
| Increase the use of SLWM practices in the targeted production systems and project areas. | Increase in areas under SLWM practices in the project target production basins (for a given list of priority SLWM techniques). Increase of POs / producers adopting SLWM practices | Confirm the relevance of the proposed SLWM techniques and the efficiency of the dissemination strategy. |
| Intermediate Outcomes | Intermediate Outcome Indicators | Use of Intermediate Outcome Monitoring |
| 1 - Technology transfer and service provision to agricultural producers |  |  |
| Dissemination and adoption of technologies, cropping and breeding practices, including SLWM practices | Percentage of producers that have adopted new cowpea seeds Percentage of dairy producers that have adopted improved husbandry practices Percentage of producers that have adopted SRI techniques at ON Percentage of POs’ sub-projects that (i) have achieved their objectives; (ii) are cofinanced by a credit | Assess if the proposed technologies are adapted to producer needs and if transfer mechanisms are efficient Confirm the relevance and interest of the proposed sustainable practices. Confirm the relevance of the demand-driven approach for technologies and the project support to credit facilitation |
| 2 - Irrigation infrastructure |  |  |
| Increase in reliable water resources for agricultural production. | Irrigated areas developed (number of additional hectares). | Assess the efficiency of the project approach in delivering irrigation infra. |
|  | Targeted areas with improved drainage (number of hectares drained) | Assess the impact of project drainage investments |
| 3 - Comprehensive programmatic approach, sector monitoring and project coordination |  |  |
| Improved sector coordination and more consistent field interventions | Reduction in the number of stand-alone projects in the agricultural and livestock sector (MinAgri + MEP) | Confirm that project activities facilitate sector coordination. |
| Sector monitoring | Regular production of reliable statistical data and sector analysis | Check project contribution to policy decision making based on reliable data and analyses. |

- Indicators baseline and targets:

|  |  | Target Values |  |  |  |  |  | Data Collection and Reporting |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Intermediate Outcome Indicators | Baseline | YR1 | YR2 | YR3 | YR4 | YR5 | YR6 | Frequency and Reports | Data Collection Instruments | Responsibility for Data Collection |  |
| Project Outcome Indicators |  |  |  |  |  |  |  |  |  |  |  |
| Rice production increase in targeted areas |  |  |  |  |  |  |  | End of cropping season | Annual survey | Office du Niger DNA and CRAs |  |
| - Sabalibougou + M’Béwani + PIV (6t/ha) | 0 | 0 | 15,000t (2,500ha) | 21,150t (3,525ha) | 23,850t (3,975ha) | 25,200t (4,200ha) | 25,200t (4,200ha) |  |  |  |  |
| - Bas-fonds (Low-Land) (1.5t/ha to 1.8t/ha) | 0 | 0 | +580t (385ha) | +1875t (1,250ha) | +3,170t (2,115ha) | +3,750t (2,500ha) | +3,750t (2,500ha) |  |  |  |  |
| Rice yield increase on small scale irrigation perimeters supported by the project | CPS / ON Data 2009 survey |  |  |  |  |  |  | End of cropping season | Annual survey | DNA and CRAs |  |
| - PIV | 4.0t/ha | 4.0t/ha | 4.1t/ha | 4.2t/ha | 4.3t/ha | 4.3t/ha | 4.3t/ha |  |  |  |  |
| - Bas-fonds | 1.5t/ha | 1.5 t/ha | 1.6 t/ha | 1.7 t/ha | 1.8 t/ha | 1.9 t/ha | 2.0t/ha |  |  |  |  |
| Cowpea yield increase in project areas | 250 kg/ha (CPS 2009) | 250 kg/ha | 250 kg/ha | 350 kg/ha | 450 kg/ha | 600 kg/ha | 700 kg/ha | End of crop-ping season | Annual survey | DNA and CRAs |  |
| Increase of milk production per milking cow | 1.5l/d (DNPIA 09) | 1.5l/d | 2.0l/d | 2.5l/d | 3.5l/d | 4.5l/d | 6.0l/d | Daily record by producers | Bi-monthly | MEP / DNPIA |  |
| Total number of producers reached by project support | 0 farm / yr Cumul Pers. | 30,000 30,000 300,000 | 60,000 90,000 900,000 | 60,000 150,000 1.5M | 60,000 210,000 2.1M | 60,000 270,000 2.7M | 30,000 300,000 3.0M | Bi-annual | Progress reports | CPS |  |
| Global Environment Indicators |  |  |  |  |  |  |  |  |  |  |  |
| Increase in areas under SLWM techniques in project production basins | <5% (données STP 2009) | <5% | 5% | 15% | 15% | 20% | 25% | Mid-cropping season | Annual survey |  | ON / MinAgri / DNA and CRA |
| Percentage producers that have adopted SLWM practices | <5% (données STP 2009) | 5% | 10% | 20% | 40% | 50% | 60% | Mid-cropping season | Annual survey |  | DNA and CRA |

Component 1 - Technology transfer and service provision to agricultural producers

|  |  |  |  | Target Values |  |  |  |  |  |  |  |  |  | Data Collection and Reporting |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Intermediate Outcome Indicators |  | Baseline |  | YR1 | YR2 | YR3 |  | YR4 |  | YR5 |  | YR6 |  | Frequency and Reports | Data Collection Instruments | Responsibility for Data Collection |
| Share of producers that have adopted new cowpea varieties in the target production basins (Bankass/Koro +Bla/Tominian) | <1% (PASAOP data 2009) |  | <1% |  | 10% |  | 20% |  | 30% |  | 40% |  | 50% | Annually, Mid-cropping season | Annual survey on a sample of producers | MinAgri / DNA |
| [AFTAR] Dairy producers that have adopted improved husbandry practice (Mopti, Ségou, Sikasso) | <5% (PASAOP data 2009) |  | <5% |  | 10% |  | 25% |  | 30% |  | 40% |  | 50% | Annual | Survey of a sample of producers | MEP / DNPIA |
| [SLWM] Percentage of producers that have adopted the system of rice intensification (ON + PIV) | <1% |  | <1% |  | 5% |  | 10% |  | 15% |  | 25% |  | 30% | Annually, Mid-cropping season | Annual survey on a sample of producers | Office du Niger MEA |
| Percentage of POs’ sub-projects that have achieved their objectives as stated in request | 0 |  | 0 |  | 25% |  | 50% |  | 75% |  | 80% |  | 80% | Annual | External technical audit | APCAM et CRA |
| Percentage of POs’ sub-projects that are cofinanced by a bank or MFI credit | 0 |  | 0 |  | 20% |  | 35% |  | 50%% |  | 75% |  | 75% | Quarterly | Quarter progress report | APCAM et CRA |

Component 2 – Irrigation Infrastructures

|  |  |  |  | Target Values |  |  |  |  |  | Data Collection and Reporting |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Intermediate Outcome Indicators |  | Baseline |  | YR1 | YR2 | YR3 | YR4 | YR5 | YR6 | Frequency and Reports | Data Collection Instruments | Responsibility for Data Collection |
| [AFTAR] Total irrigation area developed (hectares) | Cumul (ha) Total / year |  | 0 |  | 2,980 2,980 | 5,095 2,115 | 6,585 1,490 | 7,295 710 | 7,295 - | Annual | Progress reports | Office du Niger DNGR |
| - Office du Niger (ha/year) | 0 |  | 0 |  | 2,200 | 500 | - | - | - |  |  |  |
| - PIV (ha/year) | 0 |  | 0 |  | 300 | 525 | 450 | 225 | - |  |  |  |
| - Bas-fonds (ha/year) | 0 |  | 0 |  | 385 | 865 | 865 | 385 | - |  |  |  |
| - PPM (ha/year) | 0 |  | 0 |  | 100 | 225 | 175 | 100 | - |  |  |  |
| Number of producers benefitting from newly or improved irrigated land | 0 Pers. Farms |  | 0 0 |  | 16,700 1,670 | 42,900 4,290 | 66,200 6,620 | 77,400 7,740 | 77,400 7,740 | Annual | Progress reports | Office du Niger DNGR |
| - Office du Niger (5ha / exploitation agricole) | 0 farm units |  | 0 |  | 440 | 540 | 540 | 540 | 540 |  |  |  |
| - PIV + Bas-fonds + PPM | 0 farm units |  | 0 |  | 1,230 | 2,520 3,750 | 2,330 6,080 | 1,120 7,200 | 7,200 |  |  |  |

Component 3 – Comprehensive programmatic approach, sector monitoring and project coordination

|  |  | Target Values |  |  |  |  |  | Data Collection and Reporting |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Intermediate Outcome Indicators | Baseline | YR1 | YR2 | YR3 | YR4 | YR5 | YR6 | Frequency and Reports | Data Collection Instruments | Responsibility for Data Collection |
| Reduction in the number of stand-alone projects in the agricultural and livestock sector (MinAgri + MEP) | 110 | 110 | 110 | 105 | 100 | 90 | 80 | Annual | GoM budget | CPS |
| Number of donors using the pooled financing mechanism | n/a | n/a | n/a | 1 | 2 | 4 | 6 | Annual | Progress report | CPS |
| Regular production of reliable statistical data and sector analysis: |  |  |  |  |  |  |  | Annual | Progress report | CPS MEA |
| - Number of rural households monitored | 610 RuralStruc IER 2008 | 610 | 900 | 1,200 | 1,800 | 1,800 | 1,800 | Bi-annual | Surrvey report | CPS APCAM/CRAs |
| - Rice yield and production assessment | 0 | 1 | 1 | 1 | 1 | 1 | 1 | Annual | Progress report | CPS |
| Increase of Government spending on SLWM | 4.7% [2007] IFPRI data 2009 | 4.7% | 5% | 5.2% | 5.4% | 5.6% | 6.1% | Annual | GoM budget | CPS MEA |

- Other monitoring indicators:

The indicators listed hereafter have been discussed and agreed on to be included in the monitoring and evaluation manual. Some indicators are specific to donor partners of the Project, especially IFAD and GEF.

- IFAD indicators:

- PDO indicators:

  - Percentage increase of rice yields on small scale irrigation perimeters supported by the project by category of household, gender and age of farm manager;

  - Percentage increase of cowpea yields in targeted areas by category of household, gender and age of farm manager;

  - Percentage increase of milk production per milking cow in the targeted areas by category of household, gender and age of farm manager;

  - Increase in areas under SLWM techniques in the project target production basins by type and category of land ( on common land vs. individual landholding, and for the latter by which category of households);

  - Households that have improved food security;

  - Prevalence of child malnutrition (boys/girls);

- Component 1 intermediate outcome:

  - Share of producers that have adopted new seeds and animal breeds, cropping techniques and husbandry practice, as well as SLWM techniques, by category of household, gender and age of farm manager;

  - Percentage of women benefitting from investment sub-projects;

  - Percentage of producers (and categories) receiving agricultural advisory services;

  - Number of POs and producers benefitting from investment projects and training;

  - Number of POs under contract with advisory service providers (by type and level of POs, whether public or private providers);

- Component 2 intermediate outcome:

  - Number of additional irrigated hectares by socio-economic category of households;

  - Percentage of women and percentage of youth benefitting from newly or improved irrigated land;

  - Maintenance of small scale irrigation perimeter; collection of fees.

- SIP and Global Environment Benefits Indicators:

  - Increase in areas under SLWM techniques in project production basins

  - Total areas under SRI practices in project irrigated perimeters (7,000 hectares)

  - Percentage increase in soil carbon in selected project sites (5% by year 3 ; 20% by year 4, 40% by year 5 and 50% by the end of the Project).

  - Change in net primary productivity (vegetation cover) against baseline (5% by mid-term review and 30% by the end of the Project).

  - Number of CSIF priorities implemented and related budget;

- SLWM intermediate outcomes:

  - Percentage of POs’ sub-projects that includes SLWM aspects and targeted activities;

  - Rate increase of producers using organic fertilization in the project production basins (10% increase per year);

  - Percentage of producers using live-fences in the project production basins (30% by mid-term review and 50% by the end of the project);

  - Number of communes involved in the elaboration, negotiation and implementation of pastoral conventions (with farmers and herders).

  - Percentage increase of agro-pastoral corridors and communal lands under SLWM techniques;

  - Percentage of POs’ requests for advisory services related to SLWM ;

  - Number of producers, public and private services providers trained in SLWM;

  - Number of demonstration, on-farm trials organized for SLWM promotion;

  - Percentage of irrigated land (by type) under SLWM techniques,

  - Number of donors contributing to the CSIF implementation;

  - SLWM integration in the PNISA and agricultural policy;

- Other intermediate Outcome Indicators:

- Rainfed Cereal Production Systems:

  - Reduction in cowpea post-harvest losses

  - Increase of cotton yield in targeted zones (kilogram / hectares)

- Fodder and Livestock Production Systems

  - Increase of hectares cultivated for fodder production

  - Quantity of hay produced (tons)

  - Number of producers that have adopted improved animal breeds: (i) Wassache for poultry; (ii) Guerra for goats

  - Number of milk collection centers rehabilitated or created in the targeted areas

  - Number of pastoral conventions signed with agro-pastoral producers

- Large and Small Scale Irrigation Infrastructure

  - Irrigation area developed at Office du Niger (hectares).

  - Reduction of water consumption at Office du Niger at partiteur intake on project targeted perimeters: (i) Wet season (m3/ha); (ii) Dry season (m3/ha).

  - Small scale irrigation area developed: (i) New PIV (ha); (ii) Lowlands (ha); and (iii) vegetable perimeters (ha)

  - Reduction in rice post harvest losses

- Core Public Services

  - Number of animal health specialists entering a graduating curriculum: (i) Veterinarians; (ii) Technicians.

  - Improved quality control of crops and livestock inputs: (i) Review of legislation for vet. medicinal products; (ii) Number of quality control inspections (vet medicine, pesticides and fertilizers)

- Arrangements for results monitoring:

- As part of its sector supervision and evaluation mandate, the CPS of the MinAgri will be responsible for the overall project monitoring and evaluation. At the national level, it will dedicate two staff members to this function.  The project will also provide technical assistance and capacity building support. At the regional level, one staff in the Agricultural Regional Division and one staff in each Regional Agricultural Chamber will be dedicated to data collection, compilation and communication to the central level. Protocols involving all relevant regional public services will detail data collection modalities for each target production system.

- The project will finance a (yearly revised) contractual arrangements for CPS to delegate yield measurements to the Mali Rural Economics Research Institute (IER – Institut d’Économie Rurale) and to ensure data collection on urban markets through the Agricultural Market Observatory (OMA - Observatoire des Marchés Agricoles). POs and other organized project partners, as well as all relevant public services will be associated to the elaboration of the data collection arrangements, including yield and marketing shares measurement methodologies. The baseline references will derive from the last rainy season (2009), which is expected to be “average to above average” as far as production is concerned. Budget allocations will be available to undertake any on-demand studies and field surveys relevant to M&E purposes.

- The CPS will also rely on project financed contractual arrangements to delegate all environment and SLWM related M & E activities and indicators to its counterpart at the Ministry of Environment and Sanitation (MEA-CPS). Specific arrangements and budget allocations will also be made for the close monitoring of the Bank’s safeguards policies, namely the Environmental and Social Management Framework, the Pest Management Plan and the Resettlement Policy Framework. Two staff members of the MEA-CPS will be dedicated to these tasks; they will coordinate closely with their MinAgri counterparts from the project M&E team.

- Consistent with the project’s objective of improving policy decision making, project resources will facilitate communication and dissemination of M&E results to all stakeholders. The project will support improvement of producers’ knowledge of their own production systems as well as understanding the value chains. The project will also support APCAM and its network of CRAs to assimilate the information and circulate readily synthesized analysis to rural farmers (through POs and value chains inter-professional organizations).

- The project will finance impact evaluations at mid-term and at the end of the project, to assess outcomes and results on the ground (at the farm, producer and value chains levels).

Annex 4: Detailed Project Description

Mali:  Fostering Agricultural Productivity Project

- Guiding principles for investments. Investments will be concentrated on key staple production systems with a high potential for productivity increases and a greater impact on agricultural growth and poverty reduction.  The following guiding principles and criteria were used to select the production systems and corresponding production areas (‘basins’):

- Consolidation and scaling-up of PNIR and PASAOP.  Project interventions will build upon previous investments undertaken by these two predecessor projects.  The proposed project will aim to consolidate the successful approaches and attendant results achieved by these projects, in particular in the area of irrigation development at the Office du Niger (ON), research and extension activities, and support to producer organizations (POs).

- Donor coordination and harmonization.  The proposed project has been designed in close consultation with other donors active in the sector.  It takes into account specific interventions by other projects co-funded by the Government of Mali (GoM) and other donors.  The project financing and implementation modalities have been designed to complement and develop synergies with these other projects.

- Internal Bank portfolio coherence.  Synergies within the Bank’s agricultural and rural development (ARD) portfolio have been sought, especially with the following programs and projects: (i) West Africa Agricultural Productivity Program (WAAPP), for research and extension activities; (ii) Agricultural Competitiveness and Diversification Project (ACDP), for post-harvest, processing and marketing activities within targeted supply chains; and (iii) TerrAfrica’s GEF Strategic Investment Plan (SIP), for sustainable land and water management (SLWM).

- Geographic focus on key production basins.  The project’s geographic coverage has been purposely limited to key production basins, to stay within the overall financial envelope available and avoid investment dispersion and dilution. In these basins, the project will target a limited number of production systems and reference products on which it will concentrate its infrastructure and technical assistance investments.

- Productivity increase and market potential.  Production systems for project interventions were selected based on their high productivity potential (as evidenced by research results and technologies available) and market demand.

- Target production systems:

- Irrigated rice and vegetables: this production system has been and remains a critical  food production system in Mali. It feeds a large share of the population (particularly in urban areas) and provides income to smallholder producers. Its potential for growth through irrigation development is high, although critical challenges have to be addressed for better land and water management. The project will encourage diversification (millet, sorghum, maize, wheat, tubers, yams, sweet potatoes, cassava…). However rice remains the main staple food in Mali, with rapidly increasing demand on urban markets. There is a strong interest in rice cultivation for import substitution. The project will use rice as the reference product for this production system.

- Rain-fed cereals: this is the most common production system in Mali, on which a large proportion of smallholders rely. It has been neglected for many years, however improved technologies (seed varieties, innovative SLWM techniques, etc.) are readily available to increase productivity. Two sub-systems will be more specifically addressed by the project: cereal/leguminous and cereal/cotton sub-systems, both in strong interaction with animal production. Technology demonstration and transfer mechanism, advisory services, access to rural credit and better linkages between research, extension and the POs are critical to fill the gap between research results and field realities. Cowpea will be the reference product based on its productivity increase potential and its high nutritive value, together with its fodder production potential. Cowpeas have present outlets on local markets, but also have opportunities to sell on sub-regional markets. The project will also pay attention to cotton yields, as it remains the crop rotation pillar of the mixed cereal / cotton production system.

- Fodder production: together with the downturn in cotton production, demand for animal feed alternatives to cotton-seed cake is increasing. The fodder production system presents the highest potential for innovation, from the introduction of new crops to the dissemination of harvesting and processing equipment. Enhanced seeds and cropping techniques are already available for quick dissemination. Interest for smallholders is high, as fodder production is a way to increase and diversify crop production, while providing animal feed for animal traction and additional food production. The project selected fodder cowpea as reference product.

- Livestock production: Mali is famous for farm animal rearing capacities. Moreover, short cycle animal production is overwhelmingly in the hands of women and young family members. Animal husbandry contributes significantly to the income of the most vulnerable groups. Project support will focus on the following animal production sub-systems: (i) semi-intensive and agro-pastoral dairy production; production of cow milk and other dairy products (yoghurt, butter and sour milk) are largely below demand in Mali and show very strong seasonal variations; In the project target areas, a recent FAO study estimates that the local milk production covers only 9 to 11 percent of the daily urban demand;. The dairy sub-sector also bears potential to reduce massive imports of milk powder; (ii) semi-commercial and traditional poultry production; it is a broad-base farming sub-system for many households in rural areas, benefitting from high demand for eggs and poultry meat as cheap sources of quality proteins. Import substitution is promising, while export possibilities also exist to neighbor markets and (iii) sheep fattening with promising potential for productivity increase; Mali sheep production is already quite competitive on local and sub-regional markets and benefits from a very high demand for well-shaped rams during religious celebrations. Animal production in Mali shows a high potential for productivity increase and competitiveness, through the adoption of improved animal husbandry practices (feeding, health care and genetics) that are already developed and ready for dissemination. Cow milk, sheep and poultry meat will be the project’s reference products.

- Production basins and geographic coverage.  Table 2 below presents the four targeted production systems, with corresponding production basins to be covered by the project, including the Office du Niger (ON) and other targeted areas.

Table 2 – Target Production Basins

| Production Systems |  | Crops and Animal Productions | Production basins |
| --- | --- | --- | --- |
| Irrigated | Large scale irrigation | Rice, vegetables, shallots and potatoes, maize; fodder, livestock and fish farming SLWM: SRI, composting | Office du Niger |
|  | Small scale irrigation | Rice, fruits and vegetables, agro-forestry, wheat, livestock; phoeniciculture SLWM: SRI, composting | Sikasso/Kayes for lowland irrigation Along the Niger River for village irrigation perimeters Diré/Tombouctou + Kidal |
| Cereals | Rain-fed cereals | Cereals, legumes and livestock SLWM: Live fences, assisted natural regeneration | Douentza/Bankass/Koro + Bla/Macina/Tominian |
|  |  | Cereals, cotton and livestock SLWM: Live fences, assisted natural regeneration | Kati/Dioïla + Kita/Bafoulabé + Sikasso/Koutiala/Bougouni |
| Fodder | Fodder production | Fodder crops (for mixed dairy / meat semi-intensive and pastoral production) SLWM: Pastoral conventions, bourgou and leguminous fodder crop | Office du Niger (Sokolo/M’Béwani) + Dilly/Nara + Diéma/Nara |
|  |  | Fodder (around urban areas) for intensive and semi-intensive dairy / meat production SLWM: Pastoral conventions, bourgou and leguminous fodder crop | Peri-urban areas around Bamako/Koulikoro, Ségou, Mopti, Kayes and Sikasso |
| Livestock | Dairy production | Dairy (semi-intensive and peri-urban; sedentary agro-pastoral) SLWM: Improved stables/compost production, leguminous fodder crop |  |
|  | Sheep fattening | Sheep / goats (agro-pastoral) SLWM: Improved stables/compost production, leguminous fodder crop | Ségou / Mopti |
|  | Poultry | Poultry (semi-commercial / village) SLWM: Improved stables/compost production; leguminous fodder crop | Around urban consumption markets |

- Project components.  The proposed project will have a three-pronged focus aimed at addressing the main bottlenecks to agriculture modernization, i.e., low agriculture productivity, insufficient productive infrastructure and weak sector coordination.  The project will include the following components aligned with the above focus: (i) Technology transfer and service provision to producers, such as research, training, advisory services, financing, input supply, equipments, etc.; (ii) Irrigation infrastructure: investments in small and large-scale irrigation; and, (iii) Comprehensive programmatic approach and sector monitoring, with view to creating the required enabling policy and institutional environment for productivity increase.  This component will also ensure close monitoring of sector progress to improve policy decision-making.

Component 1 –technology transfer and service provision to agricultural producers (US$59.1 million: IDA: US$27.8 million; IFAD US$13.8 million, GEF-IDA: US$3.8 million, Beneficiaries: US$3.7 million, GoM: US$10.0 million)

- The component’s objective is to foster the modernization of smallholder farming systems and supply chains through dissemination of improved technologies and practices, and through the professionalization of agricultural support services.  Project beneficiaries will (i) implement a range of innovative techniques and technologies to increase productivity, including SLWM techniques and technologies; (ii) gain access to critical financial investment services; and (iii) manage their newly-acquired productive assets (infrastructure and other investments) efficiently, to increase their competitiveness.  The project will help strengthen and expand the range of services delivered to producers and address the weak capacities for service provision.  The GEF dimension of the project will support technology generation and dissemination, as well as strengthening of the capacity of service providers and end-users, to mainstream SLWM practices in crop and livestock production, rangeland management and agro-forestry.

- The project will build upon financing mechanisms established by predecessor projects that have proved to be efficient in delivering services serving small farmers needs.  It will enable service providers to assist smallholder farmers and POs in selecting and implementing modernization investments.  Empowerment, awareness of responsibilities, accountability and capacity building will be critical to promote entrepreneurship and private initiative.  This is expected to contribute to the emergence of an agribusiness-centered sector.  Based on the above premises, the project will adhere to a two-pronged strategic approach:

- Setting-up an efficient matching grant mechanism for technology dissemination and adoption.  The project will include funding for the modernization of farming systems and supply, in the form of an agriculture modernization funding mechanism.  This mechanism is meant as a temporary mechanism operating for the project duration only.  It should lay the groundwork for the establishment of the future National Agricultural Support Fund (FNAA) envisioned in Mali’s Agriculture Orientation Law (LOA, 2006).  It will support sustainable access to key technologies and attendant advisory services.  It will also foster linkages with rural credit.  Technologies targeted will include SLWM technologies.

- Enabling the policy, institutional and financing environment for technology dissemination.  This requires project support for (i) a decentralized decision-making mechanism to enhance financing and service delivery, and bring service providers closer to clients; (ii) the development of a pluralistic network of public and private service providers; (iii) better credit access for technology adoption; and (iv) stronger linkages between research and end-users, to stimulate technology generation and dissemination, including on-farm research where SLWM practices are integrated and adapted to local conditions.  In parallel, the project (component 3) will help the Government to deliver the key public services critical to productivity increase, consistent with its core mandate.

Sub-component 1.1 – Farming systems and Supply Chains Modernization (US$37 million: IDA: US$15.4 million; IFAD US$8.6 million, GEF-IDA: US$3.8 million, Beneficiaries: US$3 million, GoM: US$6.2 million)

- Innovative practices and equipment are required to both (i) increase the productivity of targeted production systems, and (ii) add value at local level through post-harvest operations, agro-processing and marketing.  This will be achieved by implementing a range of already proven technologies, including specific SLWM technologies, for agriculture, rangeland management and agro-forestry in each of the targeted production systems.  As part of SLWM technologies, the project will seek to introduce, inter alia, alternative SLWM technologies to improve ecosystem resilience through increased carbon sequestration (above and below ground); a technology that enriches soils with organic carbon and improves biomass production and vegetation cover. As a consequence of these interventions, production systems will show increased resistance to external shocks, such as climate change (droughts, flooding, etc.), hence reducing the risks and improving the stability of smallholder farming systems and corresponding incomes.

- The objective of this sub-component is to promote and disseminate productive technologies and techniques (individual or collective) in order to increase smallholders’ farm productivity and enhance competitiveness of supply chains. The project will support the financing of profitable modernization packages, including production and processing technologies, related inputs, equipment and infrastructure, as well as critical support services such as technical assistance for investment design, implementation and follow-up, training and business management advice.

- For each selected production system, improved technologies exist and are readily available for dissemination.  The project will support the dissemination of these technologies through the funding of farmer-implemented investment ‘sub-projects’.  The most important part of the project funding will be earmarked for sub-projects selected through a competitive demand driven process. A lesser fraction of the funding will be earmarked for purposely selected sub-projects designed to (i) demonstrate specific innovative technologies, and (ii) proactively develop key activities and services serving the larger producer community, such as seed multiplication or development of broader support services.

- The Project will operate through the provision of matching grants to producers, covering both improved technology package and equipments, and technical assistance.  The matching grants will cover half the cost of improved technology package and equipments, and all the technical assistance costs.  The eligible inputs and equipment will only be those associated with the adoption of the new technologies.  Project funding will cover (i) neither consumable inputs regularly used by producers, such as seeds, fertilizers, agrochemicals, vaccines, etc., as these are normally procured using annual credit, nor working capital requirements. In contrast, the project will cover all technical assistance expenditures related to sub-project preparation, as well as sub-project implementation and follow-up over a three-year period, including training expenses and business management advice.  Project funding will also cover TA expenditure related to credit access to facilitate access to credit particularly in areas where financial institutions are not present currently.

- Implementation of productive sub-projects.  The types of investments will vary according to production systems, sub-project locations, and position of producers and actors within the supply chain.  For example, investments could be linked to irrigation development (pump and other irrigation equipment), farm intensification inputs and equipment (enhanced seeds, fertilizers, breeding stock, vaccines, animal traction equipment), or storage, agro-processing and marketing infrastructure and equipment.

- Individual farmers, POs such as agricultural or livestock cooperatives, associations or organizations with economic interests (GIEs), and agribusiness entrepreneurs or supply chain inter-professional organizations will be eligible to apply for project-funded matching grants.  To qualify for financing, sub-projects will have to comply with both (i) basic conditions, such as the requirement that they be aligned with project’s interventions and priority farming systems in target production areas, and (ii) specific criteria, such as size, type of investment, financing ceilings, individual contributions, etc.  These conditions and criteria will be detailed in the project’s implementation manual.

- The three categories of sub-projects (see para 8 above) will have to comply with differing sets of conditions and criteria.  As a general rule, the funding for demand-driven sub-projects will apply only to specific expenditure items with mandatory individual contributions to given levels.  Demonstration sub-projects and proactive sub-project for key collective investments will enjoy a higher level of funding or possibly be entire funded (including funding of all input and equipment costs depending on the innovative technique(s) being demonstrated and/or developed).  The PIM will list of eligible inputs, equipment, infrastructure and other assets, both positive and negative, for the different value chains in the target project areas.  These lists will be updated over time.

- Funding thresholds for micro-projects will be established, distinguishing between collective and individual applications, as well as demand-driven, proactive or demonstration investments.  There will also be a threshold under which small individual micro-projects will have to be consolidated under a larger legally-established entity as one single collective micro-project.  Certain sub-projects will be given priority and possibly considered through a simplified procedure.  This is the case in particular of collective sub-projects geared to key activities, such as input provision, or sub-projects involving productive alliances and partnerships along different stages of the target value chains.

- Modernization sub-projects funding mechanism:  The Project will operate at the regional level.  Each region will manage its own portfolio of sub-projects separately using a regional envelope entrusted to CRA.  Funds will be deposited in a locally-reputable bank.  Procedures and disbursement modalities will reflect decentralization principles.  Within each CRA, a dedicated unit will administer the funding mechanism.  The project will recruit three local experts whose responsibilities will include inter alia advertizing, management of the sub-project selection process, assistance to link sub-project applicants with service providers, funds disbursement, and monitoring of service providers’ work (including credit access facilitation, support to investment implementation and multi-year follow-up).  A regional selection committee with adequate representation of stakeholders, including decentralized public services, producer organizations and local governments, will be established to oversee the sub-project selection process.

Sub-component 1.2 – Capacity building for POs and service providers
(US$12.3 million: IDA: US$6.9 million; IFAD US$2.6 million, Beneficiaries: US$0.7 million, GoM: US$2.1 million)

- Capacity building of APCAM, CRAs and POs: The Project will support the hiring or training of PO staff for selected internal functions so that they can deliver services to their members. The project will provide technical and managerial training programs that are targeted to production systems, producer leaders within advocacy organizations, and technical assistance to POs, including water users’ associations.  It will provide support to refurbish, equip and improve management and functioning of the existing network of CRAs so they can become professional service providers, where POs and others stakeholders will be able to find critical services, such as technical advice and market information. As a complement to this project on its special investment budget (BSI), the GoM will finance the construction of a new headquarter for APCAM and some CRAs.

- Producer organizations: It is important to strengthen the capacity of farm leaders and POs to help address the issues facing smallholder producers. Although POs are progressively becoming better organized, they remain generally weak in policy formulation, providing advisory services, and interacting with other stakeholders in supply chain development.  In addition, they are often deficient in the areas of internal management and governance. Providing POs with specific and well targeted capacity building support is critical to achieving the project’s objectives of sustainability and replicability. Strengthening POs’capacities will include hiring or training staff for some specific internal functions to enable them to deliver quality services to their members. The development of marketing and commercialization strategies is also a key area in which capacities should be built within POs to increase the added-value of their products. A case in point is in the dairy sector where local milk is insufficiently promoted and is therefore considered unattractive compared to imported powder milk.

- The project will provide three kinds of capacity-building support to POs: (i) demand-driven technical and managerial training programs at the regional level linked to targeted production systems; (ii) training initiatives for farm leaders within large-scale, national and/or regional advocating organizations; (iii) technical assistance in the form of international expertise or national staff to support PO activities. The project will also take stock of PASAOP experience by assisting major POs develop advocacy activities and services to members, with a view to enlarging their base and becoming more inclusive.

- Irrigation associations: Support to irrigation organizations is critical to ensure proper management of irrigation investments and sustainable land and water use. Beyond the core PO management functions, irrigation organizations will benefit from pre-defined training and advisory service packages covering a wide range of topics: governance and management of irrigation organizations; irrigation scheme operation and maintenance (work program and procedures, implementation and supervision of works, establishment of maintenance contracts); water management (water distribution scheduling, water consumption monitoring); financial provisions for maintenance; renewal of works and related savings; investment and seasonal credit; and mutual insurance systems. In addition, an advisory package specific to pump maintenance, will include topics such as preventive and on-demand maintenance, spare-parts supply and emergency pump supply.

- Agricultural Chambers network: Agricultural chambers play a key interface role between producers, POs, and a wide range of public and private partners. At the national level, the project will continue current PASAOP support to APCAM, through staffing and training sessions. In addition, the project will provide support to CRAs in the four administrative regions. Support to each CRA will include the recruitment of three full time staff to create the unit tasked with administering the modernization fund.

- Agricultural Advisory Service Council: All economic activities related to agricultural production, processing and marketing have been transferred to the private sector (which includes POs).  However, advisory services continue to be a shared competence between both the public and private sectors. The project will engage in activities designed to facilitate the emergence of a well-identified pluralistic network of agricultural service providers from both the public and private sectors. The project will help set-up the Agricultural Advisory Service Council (AASC), as prescribed by the LOA, as a multi-stakeholder forum to organize the advisory services system. This forum will discuss policy orientations for agricultural advisory services along with implementation modalities, and monitor and evaluate performances. At the national level, this network will be jointly overseen by POs, CNRA, MinAgri and MEP. At the regional level, CRAs will help match producer needs and service providers by maintaining a roster of registered providers, such as individual technicians, firms, local POs or NGOs. Recruitment of advisory service providers through CRAs will be competitive and agreed activities will be linked to performance contracts. Decentralized services of MinAgri and MEP will be responsible for quality control.

- Other service providers: The project will invest in the private sector to provide technically specialized advisory services directly linked to production, storage, processing and marketing. Currently, weak capacity, coupled with limited numbers, within the private sector constrain the emergence of a professional network of service providers. The project will help develop technical and managerial training sessions to strengthen capacities of private actors in delivering services (shifting from an NGO service approach to a more professional one). The project will foster the creation of networks of specialized service providers, where POs and others will be able to buy important services (such as technical advice, market information, etc). The project will also train specialists from each targeted production system and support the private delivery of specific veterinary services such as advisory services, and medicinal veterinary products delivery.

- National Strategy for Agricultural and Rural Training: As part of its efforts to improve the agricultural service provision environment, the project will help GoM implement its Stratégie Nationale de Formation Agricole et Rurale (SNFAR). Along with other donors, such as the Canadian Co-operation, the project will help restore in-country training capacities for producers and agricultural technicians.

Sub-component 1.3 - Facilitating rural credit development 
(US$3.1 million: IFAD US$2.6 million, GoM: US$0.5 million)

- To facilitate credit access, the project’s interventions will follow recommendations of the Rural Finance Study undertaken by the Bank in 2006. The project will aim at restoring dialogue between the banking and the agricultural sectors. This is critical to sustain technology dissemination, smallholder farming systems modernization and agro-pastoral supply chain development. The study states that financial institutions need to improve their knowledge and understanding of ARD issues. The project will work with financial institutions towards this goal: this will include training sessions and ad hoc expert advice on value chain development potential and technicalities.

- The Rural Finance Study also stated that there is a serious and urgent need for rural dwellers and their organizations to become more professional and responsive to financing requirements. Commercial banks and MFIs share the view that the agricultural sector is too fragmented and even less accessible since the withdrawal of the traditional network of extension agents in the field. It is felt that POs and advisory service providers are critical to fill the gap and restore confidence. As part of its strategy for credit access facilitation, the project counts on the support advisory services to provide sound and profitable micro-projects design; business management (assistance to investors will include financial management and accounting); monitoring of investments implementation plans; and multi-year follow-up technical assistance. These are considered essential guarantees by credit institutions. The strategy also counts on a decentralized approach at the regional level to move the financial sector as close as possible to smallholder and agribusiness investors.

The project will work at the interface between investors and finance institutions by: (i) replicating the experience (already for SMEs) of supporting (through staffing and training) small specialized units within banks and MFIs especially dedicated to farming systems and value chain modernization; (ii) strengthening CRAs (through staffing and training) in providing advice to producers for the sound technical and financial elaboration of profitable investment projects; (iii) adapting existing financing tools to value chains development and farm modernization needs and scaling-up innovative financing instruments such as leasing and warrantage (studies on legal framework, on incentives and constraints, etc.); and, (iv) piloting innovation in the field of agricultural risk management (studies on index-based insurance). By the end of the project, it is expected that 75% of POs' sub-projects financed under sub-component 1.1 are cofinanced by a bank or MFI credit.

Sub-component 1.4 – Technology Generation and Research – Producers Linkages
(US$6.7 million: IDA: US$5.5 million; GoM: US$1.2 million)

- International experience demonstrates the critical need, in the ARD sector, to strengthen research capacities in order to generate new productivity increases or competitive hedges, develop new technologies or adapt previous ones, address producer constraints, provide solutions for new market requirements and opportunities. Medium and long term strategic research programs also help to anticipate production systems’ evolutions (notably, adaptation to climate change) and future agribusiness technological needs.

- National Agricultural Research System: Mali’s national agricultural research system (NARS) has been efficient in organizing the different research institutions and capacities around a common strategic plan for agricultural research, where producers play a role in defining strategic directions and programs. The competitive financing mechanism set up under PASAOP will be maintained, with its two windows for strategic and demand-driven research, respectively. The project will prepare the integration of this financing mechanism into the broader National Fund for Agricultural Development (as planned in the LOA) and further participate in the on-going process towards a sector approach in agriculture. The project will also pursue efforts to strengthen research capacities through institutional support and the continuation of regional partnerships so that NARS meets international standards of excellence.

- Regional Committees for Research and Extension (RCRE): Beyond research programs, the project will strengthen the linkages between research, extension and production. It will support RCREs in identifying regional priorities for research and in implementing technology dissemination programs. It will also contribute to the implementation of national and regional knowledge management systems to record and analyze a wide range of data on farming and pastoral activities.

- Research activities and priorities: CNRA (National Agricultural Research Committee) is the lead research coordination entity responsible for setting-up research directives, priority setting, managing the scientific and financial dimensions of research activities, and supervising research program implementation. Specific commissions of research users facilitate the interface between researchers and agribusiness entrepreneurs have been efficient in promoting a constructive participation of all stakeholders. As a result of this, producer needs have been better taken into account.

- Through CNRA, the project will contribute to financing strategic research programs in connection with the targeted production systems. The following priority themes have been identified:

- Irrigated systems: motorization and mechanization; water management and conservation; sustainable intensification (e.g. SRI); and diversification; invasive plant control.

- Livestock and fodder production systems:

- Animal feeding: update of the list of natural and cultivable fodder species and their nutritive qualities; formulation of well-balanced animal feeding rations for each species for mixed crops/livestock farming systems, using fodder and crops by-products.

- Maintenance and restoration of “bourghoutière” sites in conjunction with the regional Niger River Basin Management Project (KRBMP) and proposals for a more sustainable management of the sites.

- Integration of livestock, agriculture and agro-forestry systems

- Building on the successes of PASAOP by proposing improved animal breeds, such as the “Guerra” goat and the “Wassache” hen.

- Sustainable Land and Water Management (SLWM): The national strategic plan for agricultural research has placed SLWM-related issues in the forefront. Soil fertility and water management remain the key issues, however, the research agenda needs to be updated and strengthened with the addition of new themes. Emerging themes include:

- Soil fertility management in the different production systems and agro-ecological zones;

- Intensification systems based on organic inputs (e.g. fertilization with manure, composting, cover crops, etc.) and on environment-friendly techniques;

- Economically profitable and ecologically sound agro-forestry systems and alternatives within the scope of diversification and intensification of the production system;

- Practices and techniques that improve the nutrient balance of the ecosystems;

- Land and water management practices that increase resistance to drought;

- Good practices in agricultural mechanization in line with SLWM,

- Improved use of Jatropha and biofuels.

This plan needs to be strengthened by an operational monitoring and evaluation tool to assess the dynamics of soil fertility throughout the different production systems and agro-ecological zones. In addition, it has now become important to develop research that will inform users of agricultural machinery and policy makers on the relationship between agricultural mechanization and SLWM.

- Adaptation to climate change: The project will help introduce alternative SLWM technologies for the agricultural sector that are more resistant to the impact of climate shocks. It will help end users to adopt SLWM practices which mitigate climate change and sequester atmospheric carbon (inter alia conservation tillage or conservation agriculture, agro-forestry, sustainable grazing management, sylvo-pastoral systems and improved forest management). It will also support SLWM practices that improve the ecosystem services provided by the soil – leading to increased biomass production and more reliable crop yields – and build resilience in agricultural livelihoods. Despite the availability of many improved techniques, there is a need to further adapt technologies to the local conditions and to further develop innovations given the new opportunities and context provided by the project. The project will help fund demand-driven research anchored in SLWM principles and practices while improving productivity and responding to farmers’ means and resources.

- The project will follow the Bank funded WAAPP approach to invest in complimentary research activities. It will put special emphasis on soil fertility and water management (especially for ON) in targeted production basins. WAAPP will complement project support to the irrigated production system by helping the Niono research center become a center of excellence specializing in rice production for the entire sub-region.  As a complement to this project on its special investment budget (BSI), the GoM will finance the construction of a new headquarter for agricultural research institutions (IER and CNRA) and will support specific strategic research in the environment field in particular.

Component 2–Irrigation Infrastructure (US$67 million: IDA: US$19.3 million; IFAD US$16.1 million, EU: US$19.5 million, Beneficiaries: US$3 million, GoM: MUS$9.1)

- This component will finance infrastructure development with a focus on agricultural water management (village irrigation perimeters and lowland development, large-scale irrigation schemes). The project will build upon lessons learned from PNIR and other irrigation projects, as well as upon PCDA’s experience for infrastructure development in the targeted production basins. It will further enhance the participatory process using demand-driven and market-led approaches. Emphasis will be placed on the long term financial sustainability of investments, through proper management and O&M of infrastructure.

- Although GEF will not contribute directly to this component, infrastructure development will consider the wider landscape and ecosystem context, striving for the protection and improved sustainable use of the natural resources surrounding infrastructure. Irrigation design will pay particular attention to the protection of water and soil resources.

Sub-Component 2.1 – Small-scale irrigation (US$23 million: IDA: US$2.2 million; IFAD: US$16.1 million, Beneficiaries: US$ 1 million, GoM: US$3.7 million)

- Small-scale irrigation (“irrigation de proximité”) encompasses any irrigation scheme identified and developed in partnership with the local communities whose goal is to establish profitable production areas which can be sustainably managed. Expected features of these schemes include: (i) economic viability and compatibility of available resources within the farming systems; (ii) responsiveness to local needs expressed by beneficiaries; (iii) technical and reliable design that allows for high water and soil productivity (e.g. drainage) without harmful environmental impacts; (iv) manageability through a local organization adapted to available capacities; and (v) design in accordance with the degree of beneficiaries’ involvement in the investment and management of the scheme. The project will finance 1,500 ha of gravity-fed village irrigation schemes, as well as 3,100 ha of lowland development through rainwater management, directly targeting about 7,200 farm units.

- The Government’s approach towards successful small-scale irrigation development is being refined with the support of GTZ. A common feature of beneficiary communities is their low investment capacity. GoM will support communities (based on demand) to help harness land and water resources potential for agriculture production: the underlying challenge is that the communities tend to consider Government’s involvement as a contribution to their own initiatives, instead of viewing themselves as participants of a Government-led project. The general framework of decentralization in Mali, also calls for a need to increase the communities’ contributions to these types of investments.

- Focus will be on the long term viability of the schemes. This will require fulfillment of several conditions prior to investment: (i) secured market access whereby, to the extent possible, a market is identified, quality requirements are known, a distribution channel is established, selling prices and price volatility are taken into account, and, (ii) a transparent system for water fee collection and for the delivery of O&M functions, together with the establishment of a robust financial management system to ensure long term cost recovery. To achieve this, the project will involve collective entities regrouping the irrigating farmers at local, district and regional levels. Should these organizations not exist, they would have to be created along the lines of the existing regulatory framework and technical service provision will focus on improving economic returns from the schemes and on the sustainable use of the soil and water resources in order to maintain highly productive land surfaces. Economic returns can be improved, for instance through the choice of crops/varieties, improved cropping techniques, moderate and well applied water use, through organic matter enriched soils etc.

- Activities: Investments will include preparatory studies and construction works, following a demand-driven approach. Implementation modalities will adopt the best practices identified from SAPI (Dutch Cooperation), PNIR, VRES (EU), Mali-Nord (GTZ) and other recently closed projects that are being part of the knowledge building strategy supported by PASSIP. All construction works will use a labor-intensive approach, which has proved to be more efficient than the alternative turn-key approach.

- The project’s investments will concentrate on the targeted production basins and along the Niger River between Timbuktu and Gao to complement on-going projects financed by other donors. Specific complementarities will be developed with the GTZ-funded PASSIP to ensure a sound coverage of the small scale irrigation priority investment program. Investments will mainly consider:

- Village irrigation schemes (PIV - périmètres irrigués villageois): 20 to 40 ha individual gravity-fed schemes along the Niger River between Ségou, Mopti, Timbuktu and Gao, with pumping from the nearby river or pond; the tentative development target is 1,500 ha of new schemes (about 50 schemes of an average 30 ha each).  These schemes are usually cropped with rice and offer some degree of diversification; they are fed by a pump and water is distributed through earth channels that can be lined to limit water losses. Plots are allocated proportionally to the labor force’s contribution towards construction (generally 0.25 ha per worker).

- Lowland irrigation and water management (aménagement de bas-fonds): lowland perimeters of up to 100 ha each, equipped for rainwater harvesting mainly in Sikasso and Kayes (out of which a small section would be irrigated during the dry season using pumped water from wells or ponds).  The targets are 3,100 ha of lowland development through rainwater management (about 30 schemes of an average 100 ha, with average land holdings of 1 ha). Equipment for the lowland areas will consist of building small dykes along contour lines, in order to prevent water erosion and facilitate infiltration of rainwater. Lowland areas are generally used for rice cultivation during the rainy season, but may also allow for some diversification crops during the dry season using groundwater. Lowland schemes generally include small diversification schemes (Périmètre de production maraîchère – PPM) similar to PIV, but on a smaller scale (totaling less than 5 ha with average land holding of 0.1 ha) and dedicated to diversification crops (mostly vegetables). They are well adapted to women groups.

- Other types of irrigation schemes might be included, such as the semi-Californian system successfully developed by PCDA, as long as clear guidelines are available.

- In addition, it should be noted that all existing irrigation schemes within the four Regions will be targeted for on-demand service provision, with an aim to increase water and land productivity and enhance the competitiveness of food value chains (as part of the strategy and implementation modalities of project’s component 1). Irrigation investment will necessarily come as part of a package that will include all services required to deliver the expected agricultural development and market access.

- Implementation modalities: Small-scale irrigation development will be demand-driven.   The PO will own the infrastructure and be responsible for the overall process. The DRGR will have responsibility for the planning and oversight of the use of projects funds.  Investments’ selection will be handled following the operational guidelines of the modernization fund and will include the fulfillment of some key enabling conditions, such as guarantees regarding the mobilization of the financial contribution of the beneficiaries and clear land allocation recognized in the Commune Local Development Plan. Attention will be given to vulnerable groups in the selection process. Because of demonstrated low implementation capacity for these types of investments, the PO will hire a service provider from a list of accredited firms under a results-based service agreement. The service provider (called mandataire or maitre d’ouvrage délégué) will receive the financial contribution from the beneficiary PO (possibly also from the Commune) and from the project. It will contract-out the design and construction works, while concentrating on building the capacities of recipient POs (see details in Annex 6).

- Financing modalities: beneficiaries will be required to contribute to the construction costs in cash and/or in kind (using a labor-intensive approach) and to the equipment costs in cash (pump). The project subsidy will apply to the cash part of the investment and to the technical assistance package provided though sub-component 1.1. The cash contribution might be borne by the PO alone or it could be shared with the Commune on its own budget, as part of the Local Development Plan. As part of the technical assistance package, credit access facilitation will be provided by the mandataire to the POs (sub-component 1.3). Credit eligibility will require the PO to demonstrate sound cost recovery arrangements which have been included in its business plan. Additional guarantee elements might also be requested by the credit institution, such as a pump maintenance contract or support to storage and marketing. Should the case arise, these services will be included in the business plan. Project financing will be based on the PO’s business plan and will therefore integrate infrastructure, equipment and services. Project subsidy rates will depend on the type of investments and to the type of activities. The closing of the financing plan (e.g. credit agreement signed with an eligible financial institution) and the signature of the various service provision contracts required in the business plan will be a pre-condition to the first disbursement of the subsidy (see details in Annex 6).

Sub-Component 2.2 – Large-scale irrigation 
(US$44 million: IDA: MUS$17.1; EU: MUS$19.5, Beneficiaries: MUS$ 2, GoM: MUS$5.4)

- The project will contribute to the expansion and modernization of the ON area. Project investments are to: (i) increase the economic and financial viability of smallholder farmers through an expansion of the area under irrigation (leading to farm intensification and diversification possibilities, including better integration of crop and livestock productions); and (ii) improve water management of the entire irrigation system at farm level in order to increase water availability for producers, facilitate drainage and reduce soil degradation. The project will develop about 2,700 ha of new irrigable land, consolidate 1,000 ha existing smallholders farmland (on a pilot basis) and complete the construction of Kala Supérieur main drainage system. It will also contribute to improving water management with the aim of reducing average irrigation water consumption in existing areas.

- Main concerns for the ON include: (i) the small size of farms that constrains their development or undermines their viability (this is linked to population growth and family break-ups, compared to the limited pace of irrigation land development; (ii) the limited availability of water to fulfill the requirements of large development program planned by the Malian Government, and (iii) the low institutional and managerial capacity of ON, in spite of its 1994 Reform spelled out in a Décret de Gérance. To mitigate these constraints, the project will concentrate its investments on the expansion of the irrigable area dedicated to family farming with a target population of about 6,000 households; priority will be given to families already settled on existing schemes. In addition, a pilot voluntary land consolidation operation on existing command areas will be conducted in partnership with the local POs. Ongoing initiatives addressing the enhancement of water management efficiency (through the strengthening of Tertiary Canal Water User Groups - OERT) will be supported and progressively extended to the entire scheme, together with the implementation of an incentive financial mechanism. Drainage will be improved in the Kala Supérieur zone with the construction of the remaining sections of the main drainage network (53 km of drains), as well as through the development of pumped irrigation from either the groundwater table or from the drains themselves to complement fresh water supply (conjunctive use of water) and therefore contribute to the overall water management efficiency.

- The project will also support policy dialogue with the Government on ON’s institutional modernization with a view to secure its long term managerial and financial capacity according to the moto: “Towards enhanced efficiency within responsible governance”. In fact, the policy dialogue on the ON has always been very active since the major reform of 1994 which resulted in a complete reshuffling of ON along its core business lines, but there is still scope for improvement as reflected in a recommendation from PNIR’s organizational audit and currently pursued in the context of the PRSC. Moreover, the institutional framework has changed with the recent creation of a National Secretariat responsible for the ON zone development. A number of projects have also been initiated by public and private partners outside of the usual ON investment framework (MCC, WAEMU, SUKALA, SoSuMar, Malybia, etc.). Investment planning and coordination has become a sensitive issue as water resource is now a limiting factor for irrigation system development. The ON area development master plan gives the overall outlook for economic development until 2020. Its objectives are translated into an action plan through a five-year agreement (Contrat Plan) between the Government, the ON and the farmers. The project will build on these plans and the existing dialogue to further strengthen the institutional, financial and technical capacity of ON to deliver on its core functions.

- A broad range of opportunities will be proposed to farmers on newly developed areas, with a view to adapt irrigated land supply to actual farmers demand and to maximize the (financial and/or in-kind) contribution of beneficiaries to investment costs. Lessons learnt from PNIR and other projects (with regard to financing mechanisms) and the views of POs have been taken into account for the design and implementation arrangements of the new irrigation schemes. These will rely on the three following basic models:

- Model 1 – Traditional  Office du Niger approach: public scheme with maximum 3 ha individual plots; design and construction provided (contracted out) by ON, without prior organization of the beneficiaries; selection of beneficiaries managed by Joint Land Management Committees (Comités paritaires de gestion des terres) and land tenure secured through a usual Land Use Permit transferable to heirs (Permis d’Exploitation); in-kind contribution of beneficiaries to the investment costs (digging of quaternary canals and minor land leveling). This model is well adapted to small farmers with low or no initial capital. The land allocation process will give a fair degree of priority to young farmers, female-headed households and other disadvantaged groups.

- Model 2 - Demand-driven public schemes: land is allocated to an organized group of beneficiaries, with variable size individual plots (average 3 to 5 ha per farmer); design and construction provided (contracted-out) by ON, with oversight by the beneficiaries who contribute about 30 percent of the costs of secondary and tertiary infrastructure which is in addition to their in-kind contributions; land tenure secured through a lease contract to the farmers’ group. The basic technical option remains gravity-fed surface irrigation, but alternatives might be proposed depending on edaphic conditions and on the desired cropping patterns.

- Model 3 - Autonomous schemes: implemented based on POs’initiatives with public assistance; land holding varies depending on the POs (up to 10 ha); design and construction done under the ownership of organized POs, with technical and administrative supervision delegated to ON; significant cash contribution of POs up to 60 percent of investment costs; land tenure secured through lease contracts with POs. Various technical options will be proposed to the beneficiaries, including pressurized irrigation. This model will be used for the development of pumped irrigation out of the drainage system.

- Activities:

- Irrigation infrastructure development: Two specific schemes have been selected based on the donor coordination strategy in place at ON:

  - Sabalibougou: the project will support a 2,200 ha net area extension of the existing Siengo scheme, for which a detailed design study is available. The scheme will be built following the ON standard design for gravity-fed surface irrigation, using earth canals and a mix of on-supply and on-demand flow regulation. The investment includes the establishment of new settlements and a livestock corridor (couloir de transhumance). This scheme will be partly dedicated to the settlement of small-scale farmers from neighboring ON zones in model 1 and partly to test model 2.

  - M’Béwani: the project will finance about 500 ha of new irrigation scheme, as well as the construction of Kalankorola (33 km) and Tango (20 km) main drains. These investments will complement the EU-funded ACTION project, which will build the Kala Supérieur main drain (70 km) and develop another 2,500 ha irrigation scheme already planned. A feasibility study will be done for a total area of 4,900 ha, out of which the project’s 500 ha will be selected. Other donors, such as JICA, have expressed interest in financing the development of the remaining area. The M’Bewani scheme will be equally shared between the three irrigation development models. The feasibility study will determine the best allocation of land depending on the edaphic conditions and the actual demand for irrigated land.

- Voluntary Land consolidation: The project will support a pilot voluntary land consolidation process on the existing irrigated zones. It will rely on farmers’ organizations as the main vehicle for implementation. The pilot process will be fully demand-driven and on a voluntary basis. It will aim at increasing the size of small farms to ensure their viability (some farmers will voluntarily leave the area and be reallocated by the project on newly developed irrigation schemes) by combining single farm plots. This process is also geared at increasing the cohesion of Tertiary Canals Farmers Groups and enhancing solidarities within these groups. A key incentive for farmers to participate in the scheme will be the possibility to obtain a lease contract upon payment of a financial contribution towards investment costs. Another important incentive will be the facilitation of tertiary canal management and the possibility to save water during the dry season.  For example, by concentrating the farmers’ area under irrigation, water-saving irrigation methods can be applied, such as the alternate wetting and drying method used under SRI. This will result in lower water costs once the financial mechanism for efficient water management is in place.

- Water management efficiency improvement: The project will build upon the experience of PADON and HELEN projects to consolidate and expand the on-going pilot experiments aiming at enhancing water management efficiency, using a broad approach that encompass: (i) the establishment of the required organizational framework based on the tertiary canal users associations, (ii) the setting up of an incentive system that covers the entire supply chain from primary canals to the tertiary canals and to the actual farmer’s plot, (iii) the implementation of alternative water management technologies including conjunctive use of water from irrigation system, drains and groundwater and low water consumption cropping techniques like SRI, and (iv) a strong emphasis on communication about the objectives, urgency and feasibility of the water savings.

- Office du Niger governance and modernization: The project will support policy dialogue with the Government on the ON’s institutional modernization including improvement of its governance (e.g., enhance the efficiency of the decision-making process). Through on-going dialogue among the various stakeholders, donors will seek to strengthen governance and shape managerial reforms through budget support.  It will also include exchanges with selected external partners. This will be extended to a review of the Land Management Delegation Decree (Décret de Gérance), as well as the preparation of the Contrat de Plan for 2013-2017. In addition, the project will support: (i) the implemention of a financial mechanism for irrigation infrastructure development based on the PNIR approach (e.g. relying on the existing banking sector to develop credit offerings) and update the land tenure policy to facilitate the settlement of different types of farmers; (ii) the use of a result-based approach for irrigation development (ON is to receive a percentage of the construction costs to cover the supervision services it provides) in order to move towards budget support including other financing partners, and (iii) support to the ON’s environmental staff to ensure data collection and analysis on critical environmental issues.

- Studies: The project will undertake studies related to irrigation potential, both within and outside the ON area. In the ON area, where the irrigation development master plan is available, studies will include social assessments on land and water management practices, users’ satisfaction surveys, main system maintenance costs, technical audits, drainage service monitoring system, etc. Outside the ON area, studies are needed for irrigation master plans development, in order to build a pipeline of future public investment programs.

- Safeguards: The project will also provide: (i) capacity building and equipment for a strict monitoring of environment and social safeguards and for a close supervision of mitigation measures; (ii)  equipment to replace auscultation instruments and technical assistance to update manuals and emergency preparedness plans for the Markala and Sélingué dams.

- Implementation modalities: The design and construction of irrigation infrastructure will be the responsibility of the ON.  However, final responsibility for the schemes will vary according to models chosen: models 1 and 2 belonging to the Government, and model 3 to the beneficiaries. The voluntary land consolidation process will be implemented by POs under the oversight of the Joint Land Management Committee. ON governance and modernization support will be implemented by the SEDIZON. Land titles and land lease contracts fall under the responsibility of ON.  However, specific guidelines, which will be included in the PIM, will be used to allocate land to organized farmers groups, as described under models 2 and 3.

- Financing modalities: The project will take stock of recent innovative experiences in producer participation for investments financing. For the banking sector to finance irrigation development, a key requirement is that additional farm income generation be secured through adequate storage and marketing arrangements at the PO level. Financing modalities will differ from one irrigation development model to another. For models 2 and 3 where a cash contribution is required, the banking sector will be involved similar to the guidelines described for small-scale irrigation with the ON acting as the mandataire and financial closure achieved before construction starts.

Component 3 - Comprehensive programmatic approach, sector monitoring and project coordination (US$26.9 million: IDA: US$15.9 million; IFAD US$2.1 million, GEF-IDA: US$2.4 million, GEF-UNDP: US$1.9 million, GoM: US$4.6 million)

- The objective of this component is to support activities that will facilitate: (i) a stronger overall supervision, monitoring and coordination of the sector by the GoM; (ii) enhanced policy dialogue among sector stakeholders, especially between the Government and producer  representatives; (iii) harmonization of both Government and donor supported programs through the establishment of national financing mechanisms and; (iv) transition towards a sector-wide approach and the preparation of national agricultural investment program - PNISA.

- The project, along with other donors’ support and Government’s efforts, will help:

- Restore country ownership and domestic leadership on agricultural development and investment operations;

- Empower producers to participate in policy decision-making and agricultural service delivery;

- Reduce transactions costs and wastage of financial resources associated with multiple donors and scattered projects and programs;

- Encourage spending based on priorities, financial flows, and roles of both public and private sectors over the medium to long term; and

- Strengthen sector monitoring and a performance and impact assessment system that supports policy decision-making.

- The project will support MinAgri and other sector Ministries to move away from a project / program-led approach and converge towards a programmatic and sector-wide approach. The institutional set-up and implementation arrangements of the project will be revised at the project mid-term review to ease the transition towards a SWAp at the end of the project.

- Sector leadership and implementing agency: The project will help restore sector leadership through the Statistics and Planning Unit (Cellule de Planification et de Statistiques - CPS) as the lead Government entity for sector coordination. The CPS, attached to MinAgri, covers the entire rural development sector, constituted by the following Ministries: Ministry of Agriculture (MinAgri), Ministry of Livestock and Fisheries (Ministère de l’Élevage et de la Pêche - MEP) and the Food Security Commissariat (Commissariat à la Sécurité Alimentaire - CSA). Its mandate includes: (i) coordinate the preparation of plans, programs and projects as well as policy and strategy analysis; (ii) monitor and evaluate sector development plans, programs and projects to ensure intra-sector and spatial coherence, and build upon experiences that increase the effectiveness of interventions; (iii) elaborate projections and monitor environment and trends; (iv) follow up on issues related to financial and technical cooperation; (v) coordinate the planning and statistical training program; (vi) coordinate the production of statistical data  and the implementation of baseline studies as well dissemination of findings; and (vi) set up and manage sector database.

- The CPS structure comprises four units: (i) Planning and Analysis; (ii) Programming and Monitoring-Evaluation; (iii) Statistics; and (iv) Information Technologies.  The Documentation and Communication Center  is also an integral part of the CPS.

Sub-Component 3.1 - Policy dialogue and coordination (US$4.2 million: IDA: US$1.8 million; IFAD: US$1.1 million, GEF-IDA: US$0.6 million, GoM: US$0.7 million)

- The objective is to support the transition towards a sector-wide approach, based on a constructive policy dialogue and relevant sector analyses for policy decision making. It is expected that the project, at the mid-term review, would have contributed to the formulation of the PNISA, adopted by all the major donors in the sector.

- The project will follow the roadmap prepared by the CPS and discussed in June 2009 during the first joint donor-GoM sector review. The roadmap provides guidelines for preparing the PNISA to be implemented along the following lines: (i) elaboration and adoption of the overall agricultural policy; (ii) preparation of the sector monitoring; (iii) elaboration of tools and instruments for policy-decision (public expenditure reviews, mid-term expenditure frameworks); (iv) monitoring and evaluating projects and programs; and (v) collecting, analyzing and disseminating sector data. This approach is supported by all the donors involved in the donor-coordination group for the agricultural sector. It will mainly benefit from the on-going SLWM programmatic approach under which the SLWM Country Strategic Investment Framework is under finalization and from the recently adopted roadmap and compact under the CAADP process supported by ECOWAS under the leadership of the Ministry of African Integration and Malian Living Abroad.

- Activities: The project will provide means to facilitate the dialogue between key Ministries, POs, private sector representatives and donors, to achieve a better organization and coordination of the agricultural and livestock sectors. It will help forge a shared vision among all stakeholders towards a comprehensive / programmatic approach to agricultural productivity and around the implementation of the LOA. It will facilitate (i) the elaboration of the national agricultural sector investment program (PNISA) based on joint donor efforts and the NEPAD/CAADP process; (ii) the elaboration and implementation of the agricultural policy, including the development of policy options or institutional reforms within key Ministries and public entities (e.g., ON modernization, cotton subsector reforms); and, (iii) the implementation of the CSIF and the promotion of SLWM in agricultural investments.

- Technical assistance and expertise: The Danish, Belgium and Dutch Co-operations will provide technical assistance to strengthen the CPS. The proposed operation will finance capacity building programs, stakeholder consultation workshops, studies and communication activities. The project will pay close attention to the preparation and execution of studies critical for policy and strategy formulation.  Preparation of PERs and MTEFs should serve as solid analytical underpinnings for sound policy dialogue and PNISA elaboration.

- Sector-wide consultation: To ensure strong cohesion by all stakeholders, the project will support the CPS’ elaboration of its vision by organizing sector-wide consultations at the different stages of the process. Workshops, study tours and round-tables will be organized to stimulate dialogue and exchange on joint policy formulation and sector strategies.

- Capacity building: Staff from the various sector Ministries and umbrella producer federations will benefit from training programs that will be developed under the project. Particular attention will be given to farmer representatives who will participate in policy dialogue and provide assistance to national farmer leaders in the following areas: (i) organize consultations with their grassroots constituents at the regional and local levels; (ii) hire their own expertise so as to participate in policy consultation or elaborate their own strategic position, and (iii) undertake their own policy analysis.

- Critical issues to be addressed and linkages with the other project: To facilitate policy dialogue and efficiently address urgent issues, the project will support stakeholder consultations through thematic groups and task forces looking at a range of issues and themes.  For example, support could be provided for on-going or emerging policy, institutional and sector reforms, such as the finalization of the cotton sector reforms or the evaluation of the GoM’s rice initiative. Thematic groups will also be responsible for regularly reviewing and updating procedures established by the Project Implementation Manual (PIM) and harmonizing them with the procedures of the line agencies, so that the PIM becomes a manual for the sector. Policy dialogue and stakeholder consultation will primarily focus on issues related to the other project components, such as:

- Land and water management: Under component 2, the project will contribute to the policy dialogue on the modernization and governance of Office du Niger. In close collaboration with the GTZ-funded PASSIP, it will contribute to the elaboration of a specific financing mechanism for small-scale irrigation development and to the strengthening of the regulatory framework for Water Users Associations.

- Livestock sector: Since June 2008, a Malian team has been working to establish a diagnostic of the livestock sector at the national level using the “Livestock Sector Investment and Policy Toolkit” (LSIPT) developed under the umbrella of the ALive Partnership. Based on this diagnostic, the project will support the MEP in finalizing a National Livestock Action Plan and an Investment Program that will be fully integrated into the GoM-led SWAp. The results of this work could constitute the Livestock component of the broader PNISA.

- Financing mechanism: The project will contribute to ensuring sustainable access to agricultural services for producers by supporting the establishment of the Fonds National d’appui à l’Agriculture (FNAA – National Agricultural Support Fund) planned in the Agricultural Framework Law. This FNAA could be a joint GoM-donors’ basket fund for investment in agricultural and SLWM research and advisory services to producers. As such, the project will help the GoM elaborate a clear policy and strategy of smart and targeted subsidies to foster agricultural development and farming systems modernization. It would benefit from GoM’s budget allocation and donor contributions but could also be replenished by a national financing mechanism based on agricultural or professional levies or fees. The project will also support the elaboration and piloting of innovative financing instruments. Based on experiences from neighboring countries such as Senegal, weather-based insurance could be tested to help producers face climatic risks.

- Implementing modalities: Implementation of this sub-component will be under the leadership of the CPS along with various line Ministries (MEP, MEA, CSA and SEDIZON).  The line Ministries will lead the policy dialogue in their respective areas of responsibilities and competencies and will initiate their own policy consultations.  An annual work program will be prepared by the CPS, in close collaboration with the Ministries, and validated by the PNISA-NSC. Implementation modalities will include provision for undertaking urgent studies or consultation as needed during the course of project implementation.

Sub-Component 3.2 – Sector monitoring and evaluation (US$5.5 million: IDA: US$2.7 million; GEF-IDA: US$1.8 million, GoM: US$1 million)

- The sub-component’s objective is to: (i) restore the regular production of reliable statistics on the sector; (ii) provide up-to-date information to policy decision makers; (iii) facilitate sector-wide consultation based on reliable information and analyses; and, (iv) monitor sector evolution and progress.

- The sub-component will strengthen existing monitoring and evaluation services to develop a relevant programmatic approach to the sector. Within the framework of the Statistical Master Plan, it will restore the regular production of reliable agricultural statistics, expand existing market information services, and strengthen the capacity of the rural sector’s Statistics and Planning Unit to provide relevant analysis for decision making by policy makers and producers.

- The strategy will not re-establish internal statistics divisions within the line Ministries or organize large-scale agriculture census. The strategy will: (i) organize a sector information system based on different modules and institutions; (ii) undertake on-demand small-scale surveys, field studies, agricultural and livestock production monitoring, periodic market data collection; (iii) strengthen the capacities of existing information providers to produce and analyze information; (iv) support the Ministries in data collection, analysis and information dissemination; and, (v) develop a geographic information system for agricultural sector and environment monitoring.

- Activities: Priority activities will focus on implementing: (i) annual rural households’ surveys, based on the RuralStruc comparative study carried out by the Bank in several countries including Mali; (ii) annual assessments of production and yield levels with a focus on rice; (iii) regular assessment of the evolution of natural resources and the impact of agricultural investments on the environment

- In addition to resources required for data collection, field surveys and policy analyses, the project will provide resources to strengthen capacity at two levels: (i) the existing information systems level to collect data and produce analyses; and (ii) the Ministerial staff level to support, analyze and convert data into policy recommendations. Resources will also be available to hire national, regional and international expertise to carry out complex field surveys and analyses.

- Thanks to GEF and UNDP support to MEA, the sub-component will also support the development and improvement of tools to closely monitor land degradation, restoration and ecosystem evolution. These tools will draw upon lessons learned from on-going experiences and allow for improved field investment effectiveness. It will develop and use specific tools and indicators to monitor SLWM scaling-up activities and the impact of field investments through a dedicated geographic information system which will be jointly used by all donor partners.

- Implementing modalities: The various Ministries will be in charge of collecting some key data and information related to their core public functions and taking into account their own capacities and human resources. In-depth analyses and data collection on a large scale basis will be contracted out to specialized national and international firms, to existing information providers and to research institutions. Ministries will be responsible for supervising data collection, analyses and field surveys and contribute to data analysis and interpretation. More importantly they will have to disseminate and share the information with sector stakeholders.

- Financing modalities: Activities will be compiled by CPS in an annual program that will be validated by the PNISA-NSC before the project finances its implementation.

Sub-Component 3.3 – Delivery of core public services (US$12.8 million: IDA: US$7.7 million; IFAD: US$1.0 million, GEF-UNDP: US$1.9 million; GoM: US$2.2 million)

- The project will help Government focus on core public functions that are critical to agricultural productivity increases and to the competitiveness of value chains. Through annual budget programs and performance contracts, the project will finance targeted public services. Quality control of service delivery will be critical, not only for inputs (fertilizers, pesticides, seed certification) but also for extension services (accreditation and control of service providers) and public investments (irrigation schemes).

- In the livestock and animal health sub-sector, the veterinary service performance evaluation recently conducted by the World Organization for Animal Health (OIE) identified key weaknesses. Veterinary service priorities that are critical to the PDO achievement are (i) animal diseases surveillance and control (epidemiological network), (ii) the control of veterinary medicinal products (legislative framework, quality control, residues, field inspections, etc), (iii) food safety and quality control of milk and milk-based products and, (iv) animal identification and product traceability in targeted production systems. The project will support public veterinary services in delivering these core public functions.

- In the environment sector, project financing will be available for the close supervision of the environment and social management framework, the pest management plan and the resettlement policy framework.

- Project activities will include clarification of the core public service mandates, estimated budget requirements to deliver on those mandates, and establishment of a human resources management system (job description, result agreement, training plan etc.) that will be implemented on a pilot basis. At the regional level, public services critical to the project’s objective will be subject to a performance contract between CRAs and decentralized MinAgri and MEP services. The financing of core public services will be progressively streamlined through budget support to prepare for the transition towards a sector-wide approach.

- The project will support the dissemination of legal texts and strategies on agriculture, natural resources and water management, forestry, and pastoral codes. The analysis of SLWM best practices revealed that lack of knowledge of these texts is an underlying factor in many situations and conflicts. The STP-CIGQE with support from GTZ has developed legal guides on water resources, forestry and pastoralism to facilitate the understanding of the legal framework and legislation; however, they are yet to be translated into local dialect to facilitate dissemination and adoption by farmers. UNDP support to MEA will facilitate the dissemination of information to producers on policies and available techniques (soil restoration, agro-forestry, climate resilience, etc.).

- As a complement to this project on its special investment budget (BSI), the GoM will finance the rehabilitation of three training resource centers: the Vocational Agricultural Center of Samanko (Centre d’Apprentissage Agricole); Forestry Practical Training Center of Tabakoro (Centre de Formation Pratique en Foresterie) and Livestock Practical Training Center of Sotuba (Centre de Formation Pratique en Élevage).

Sub-Component 3.4 – Project coordination and monitoring and evaluation 
(US$4.4 million: IDA: US$3.7 million; GoM: US$0.7 million)

- This sub-component aims at: (i) facilitating project implementation in a complex institutional environment; (ii) coordinating project investments and activities under the responsibility of different implementing agencies and involving different stakeholders; and (iii) ensuring a close monitoring and evaluation of project interventions.  Consistent with the Paris Declaration, there will be no project implementation unit established under the project. All activities will be directly implemented by the Government institution in charge. Overall project coordination will be led by Min Agri with operational coordination delegated to the CPS.  The CPS will: (i) coordinate project investments and activities under the supervision of the CTCE; (ii) facilitate project financial management and procurement; and (iii) ensure overall project monitoring and evaluation.

- The project will finance: (i) operating costs for coordinating and supervising entities responsible for project implementation; (ii) goods and equipment for the CPS; (iii) staffing to include a technical adviser (well experienced in project planning and management), a financial management specialist, a procurement specialist and an M&E specialist who will provide assistance to the various implementing entities; and (iv) resources for annual audits or other studies related to project coordination, supervision and M&E.

Annex 5: Project Costs

Mali:  Fostering Agricultural Productivity Project

- Project Costs and Financing Plan by Source (US$ million):

| Components | IDA | EU | GEF IDA | IFAD | GEF UNDP | Benef. | GoM | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Component 1 - Technology transfer and service provision to agricultural producers | 27.8 | - | 3.8 | 13.8 | - | 3.7 | 10.0 | 59.1 |
|  | 39.7% | - | 61.3% | 43.1% | - | 55.2% | 42.2% | 36.9% |
| C1.1- Farming system and supply chain modernization | 15.4 | - | 3.8 | 8.6 | - | 3.0 | 6.2 | 37.0 |
| C1.2- Capacity building for POs and service providers | 6.9 | - | - | 2.6 | - | 0.7 | 2.1 | 12.3 |
| C1.3- Facilitating rural credit development | - | - | - | 2.6 | - | - | 0.5 | 3.1 |
| C1.4- Technology generation and research/prod. linkages | 5.5 | - | - | - | - | - | 1.2 | 6.7 |

| Composante 2 – Irrigation Infrastructures | 19.3 | 19.5 | - | 16.1 | - | 3.0 | 9.1 | 67.0 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 27.6% | 100% | - | 50.3% | - | 44.8% | 38.4% | 41.9% |
| SC 2.1- Small scale irrigation | 2.2 | - | - | 16.1 | - | 1.0 | 3.7 | 23.0 |
| SC 2.2- Large scale irrigation | 17.1 | 19.5 | - | - | - | 2.0 | 5.4 | 44.0 |

| Composante 3 – Comprehensive programmatic approach, sector monitoring project coordination | 15.9 | - | 2.4 | 2.1 | 1.9 | - | 4.6 | 26.9 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 22.7% | - | 38.7% | 6.6% | 100% | - | 19.4% | 16.8% |
| SC 3.1- Policy dialogue and sector coordination | 1.8 | - | 0.6 | 1.1 | - | - | 0.7 | 4.2 |
| SC 3.2- Sector monitoring and evaluation | 2.7 | - | 1.8 | - | - | - | 1.0 | 5.5 |
| SC 3.3- Delivery of core public services | 7.7 | - | - | 1.0 | 1.9 | - | 2.2 | 12.8 |
| SC 3.4- Project coordination / monitoring and evaluation | 3.7 | - | - | - | - | - | 0.7 | 4.4 |

| PPF refinancing | 0.95 | - | - | - | - | - | - | 0.95 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Unallocated | 6.05 | - | - | - | - | - | - | 6.05 |

| Total | IDA | EU | GEF IDA | IFAD | GEF UNDP | Benef. | GoM | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 70.0 | 19.5 | 6.2 | 32.0 | 1.9 | 6.7 | 23.7 | 160.0 |
|  | 43.7% | 12.2% | 3.9% | 20.0% | 1.2% | 4.2% | 14.8 | 100% |

- Financing plan by implementing agency and source of funding (US$ million)

| Implementing Entity | Legal Doc. | Project Activity | IDA | IFAD | GEF TF | EU TF |
| --- | --- | --- | --- | --- | --- | --- |
| APCAM | A 1 (a) | Agricultural technique modernization; livestock production system modernization; intensification and diversification | 15.4 |  |  |  |
|  | A 1 (b) | Small scale irrigation intensification techniques, post-harvest operation techniques; demand-driven and on-farm research; |  | 8.6 |  |  |
|  | A.1 (c) | Promote sustainable land and water management techniques. |  |  | 3.8 |  |
|  | A.2 (a) | Equip and improve management and functioning of APCAM/CRAs and POs | 6.9 |  |  |  |
|  | A.2 (b) | Carrying out of capacity building activities for APCAM, CRAs and POs |  | 2.6 |  |  |
|  | A.3 | Facilitate rural credit development |  | 2.6 |  |  |
|  | A.4 | Support CNRA to facilitate technology generation and strengthen linkages | 5.5 |  |  |  |
| ON | B.2 (a) | Sabalibougou 1 (1.200ha) |  |  |  | 12.5 |
|  | B.2 (b) | Sabalibougou 2 (1.000ha) | 6.5 |  |  |  |
|  | B.2 (c) | M'Béwani (500ha) | 5.4 |  |  |  |
|  | B.2 (d) | Kalankorola and Tango Drains |  |  |  | 7.0 |
|  | B.3 | ON modernisation and safeguards | 3.4 |  |  |  |
|  | B.4 | Safety of dams | 1.8 |  |  |  |
| MoA | B.1 (a) | Small scale irrigation studies | 2.2 |  |  |  |
|  | B1 (b) | Small scale irrigation constructions |  | 16.1 |  |  |
|  | C.1 (a) | Elaboration of the Agricultural investment program | 1.8 |  |  |  |
|  | C.1 (b) | Elaboration of Agricultural Policy |  | 1.1 |  |  |
|  | C.1(c) | Promotion of SLWM |  |  | 0.6 |  |
|  | C.2 (a) | Assessment and monitoring of agricultural sector performances | 2.7 |  |  |  |
|  | C.2 (b) | Monitoring of the evolution of natural resources and the impact of agricultural investments on the environment |  |  | 1.8 |  |
|  | C.3 (a) | National Agricultural Advisory Service Council to provide quality control | 7.7 |  |  |  |
|  | C.3 (b) | Develop the national strategy for small scale irrigation development |  | 1.0 |  |  |
|  | C.3 (c) | Disseminate information and develop training on SLWM |  |  | GEF TF UNDP |  |
|  | C.4 | Project coordination + M&E | 3.7 |  |  |  |
|  |  | PPF refinancing | 0.95 |  |  |  |
|  |  | Unallocated | 6.05 |  |  |  |
|  |  | Total | 70.0 | 32.0 | 6.2 | 19.5 |

- Project Costs by Types of Expenditures

| Project Cost By Component and/or Activity | Local US $million | Foreign US $million | Total US $million |
| --- | --- | --- | --- |
| Component 1: Technology Transfer and Service Provision to Agricultural Producers | 41.4 | 17.7 | 59.1 |
| C1.1: Farming system and supply chain modernization | 25.4 | 11.6 | 37.0 |
| C1.2: Capacity building for POs and service providers | 9.7 | 2.6 | 12.3 |
| C1.3: Facilitating rural credit development | 2.7 | 0.4 | 3.1 |
| C 1.4: Technology generation and research / producer linkages | 3.6 | 3.1 | 6.7 |
| Component 2: Irrigation Infrastructure | 47.1 | 19.9 | 67.0 |
| C2.1: Small-scale irrigation | 15.6 | 7.4 | 23.0 |
| C2.2: Large-scale irrigation | 31.5 | 12.5 | 44.0 |
| Component 3: Comprehensive Programmatic Approach, Sector Monitoring and Project Coordination | 23.0 | 3.9 | 26.9 |
| C3.1: Policy dialogue and coordination | 3.8 | 0.4 | 4.2 |
| C3.2: Sector monitoring and evaluation | 4.9 | 0.6 | 5.5 |
| C3.3: Delivery of core public services | 10.6 | 2.2 | 12.8 |
| C3.4: Project coordination and monitoring and evaluation | 3.7 | 0.7 | 4.4 |
| Total Baseline Cost | 111.4 | 41.6 | 153.0 |
| PPF refinancing | 0.5 | 0.45 | 0.95 |
| Price Contingencies | 5.3 | 0.75 | 6.05 |
| Total Project Costs1 | 117.2 | 42.8 | 160.0 |

1 Identifiable taxes and duties are MUS$23.7, and the total project cost, net of taxes, is MUS$136.3.  .

Annex 6: Implementation Arrangements

Mali:  Fostering Agricultural Productivity Project

A.	Guiding principles

- Throughout the preparation process, the project design has been guided by the following principles: (i) the project institutional set-up and implementation arrangements will rely on existing public and private institutions; (ii) the overall supervision and implementation coordination will be fully consistent with the mandates of existing official bodies and will follow the regionalization and decentralization frameworks; (iii) implementation, including physical investments and service provision, will rely on public and private service providers; (iv) implementation arrangements will give as much responsibility as possible to private operators (including producer organizations), especially as far as services supporting production, post-harvest operations and marketing are concerned; (v) public services will focus their contribution on their core public functions (such as quality control, phyto-sanitatry and zoo-sanitary surveillance, policy and regulatory measures formulation and enforcement, monitoring and evaluation of public investments, etc).

- The project is expected to help ensure: (i) a stronger coordination of overall ARD investments and activities in the field; (ii) a closer monitoring of operations and investments by public services, with respect to sector policies and the regulatory framework; (iii) a better use and monitoring of public spending; and (iv) a smooth transition towards a sector-wide approach.

- Consistent with the Paris Declaration, the project will not set up any independent or stand-alone project implementation unit. Project financing mechanisms, including disbursement, will follow national and regional procedures with a view to pilot the design of perennial financing tools (as already planned by the LOA) and as part of the transition to a multi-donor sector wide approach.

- Project implementation will rely on public-private partnerships for activity planning, decision making, project funding allocation, and for monitoring and evaluation. To the exception of core public functions, execution of activities on the ground will be delegated to private agribusiness entrepreneurs, producer organizations (including associations, cooperatives, GIE), private service providers and firms, on the basis of performance contracts.

B.	Overall Supervision and Strategic Coordination

- Five government bodies will take part in the overall project supervision and implementation: the Ministry of Agriculture, the Ministry of Livestock and Fisheries, the Ministry of Environment and Sanitation, the Food Security Commissariat and the recently created State Secretariat for the Integrated Development of the Office du Niger Area (SEDIZON - Secrétariat d’État pour le Développement Intégré de la Zone Office du Niger). MinAgri is the designated sector leader within the government; it will be the overall project supervising and coordinating government entity.

- The National Agricultural Sector Investment Program National Steering Committee (PNISA-NSC): MinAgri is also the lead ministry for the transition towards a sector-wide approach. As part of this process, a National Steering Committee has been set-up by a Decree of the Prime Minister to oversee the elaboration of the National Agricultural Sector Investment Program (PNISA). This Committee, which includes representatives of government agencies, as well as of the private sector and producer organizations, is in charge of supervising PNISA preparatory activities, ensuring the overall coherence with existing sector policies and strategic directions, and validating the PNISA architecture and content. The PNISA-NSC will also be responsible for overseeing the implementation of the program, and for its monitoring and evaluation. This Committee is therefore the legitimate entity to ensure the overall supervision and strategic coordination of the project. The Ministry of Finance (as the Borrower representative) and the Ministry of Industries (in charge of private sector and agribusiness development) are also important members of the PNISA-NSC. Donors of the sector will be invited as observers.

C.	Project Operational Coordination

- National level: Because of its mandate, the PNISA-NSC is not the appropriate entity for the close monitoring of field operational activities. The project operational coordination will be located in the MinAgri, under the responsibility of the CPS (Cellule de Planification et de Statistiques - Statistics and Planning Unit). This unit is the legally recognized entity for the coordination of operational activities in the rural sector (covering agriculture, livestock and food security).

- The CPS is in charge of: (i) policy formulation, implementation and monitoring/evaluation; (ii) projects and programs coordination, supervision and monitoring/evaluation; (iii) monitoring donor financing; (iv) coordinating training programs with the Human Resources Service; (v) coordinating the production of statistical data and the implementation of baseline studies, as well as the dissemination of results; (vi) setting-up the sector database and its management. CPS role includes policy dialogue coordination and donor coordination towards a sector wide approach, including the preparation of the PNISA.

- As project operational coordinator, the CPS will: (i) apply the overall project vision and strategy; (ii) ensure coherence of interventions between components and sub-components; (iii) monitor and harmonize procedures; (iv) consolidate annual work programs and budgets; (v) organize overall program supervision; (vi) consolidate monitoring and evaluation data; (vii) produce periodic implementation reports; and (viii) develop synergies and complementarities with other projects and programs.

- To this end, the project will strengthen the CPS with the (international) recruitment of four high level technical assistants: one technical adviser (well experienced in project planning and management), one M&E specialist, one financial management specialist and one procurement specialist. These experts will facilitate linkages between field operations and the Financial and Administrative Division of the MinAgri related to procurement and disbursement matters.

- The Technical Execution Coordination Committee: The CPS will call upon a Technical Execution Coordination Committee (Comité Technique de Coordination et d’Exécution - CTCE) to facilitate the coordination of field interventions. This Committee will include all directors and heads of the main entities involved in project implementation: Divisions of sector Ministries, CNRA and Office du Niger, as well as umbrella federation of POs such as APCAM and CNOP. The CTCE will meet once a month under the chairmanship of the CPS director; it will monitor project implementation, ensure coordination of field interventions and build synergies among project stakeholders. CTCE will validate investment programs prepared at the regional level, to make sure that project investments are not scattered and stay focused on the targeted production basins. At the beginning of each fiscal year, CPS will prepared detailed budget allocations and CTCE will validate and communicate them to project implementing entities; budget break-downs will be done according to regions and technical priorities within each target production system. CTCE will also supervise the collection of M&E data and the preparation of implementation reports.

- At the regional level, subsidiary and simplified CTCEs will interface with the national CTCE to facilitate operational coordination of activities in the fields. Depending on the dominant project activities in the region, one specific regional public service will lead the regional CTCE. For instance, in the Mopti region, DRPIA will thus coordinate the regional CTCE as the project will mainly invest in livestock production. To ensure a close supervision of environment safeguards, the MEA’s Regional Directorate for Sanitation and Nuisance and Pollution Control (DRACPN – Direction Régionale de l’Assainissement, du Contrôle des Pollutions et Nuisances) will assist the CTCE lead regional division. Regional project investment programs will be prepared by CRAs, in close collaboration with regional public services and drawing upon overall technical and financial guidance set at the national level (including annual priorities for each targeted production system). Regional directors of relevant (ARD related) regional public services will work with the CRAs for the programming of project support to core public functions. The regional CTCE will have the responsibility of ensuring overall consistency of project investments and activities with other interventions. As such, it will disseminate annual or semi-annual project investment programs, to regional authorities in particular, and will consult on a regular basis with the CROCSAD set up by the GoM to ensure overall coordination of all development projects and programs at the regional level.

D.	Field Implementation of Activities and Service Provision to Agricultural Producers

- Execution of activities will be delegated to operational entities on the basis of performance contracts. Clear attribution of the following main functions will be done among the various operational entities: (i) supervision and coordination; (ii) execution/implementation; and (iii) monitoring/evaluation. Operational entities will be producer organizations, agribusiness entrepreneurs, service providers (including NGOs) and private firms. Government services will contribute to the planning, coordination and oversight functions. Details of the functions attributed to each type of operational entities and related terms of reference will be provided in the Project Implementation Manual.

- Service providers: The availability of service providers comes as a key issue for the implementation of field activities (and, more broadly, for the ARD sector itself in Mali). Capacities have been built in many places and many fields of intervention thanks to previous projects. However, service providers remain weak and often show they are not efficiently organized to provide the right service at the time it is required. To mitigate this risk, the project will count on three different ways to deliver technical assistance and advisory services to rural dwellers:

- Building PO’s internal capacities: The project will help POs train their own staff or hire technicians to strengthen their own capacities to deliver services to their members. Whenever necessary, recruitment will be based on competition and subject to annual evaluation, based on performance contracts. Following a technical and financial audit of the requesting PO, the project will contribute to the costs on a decreasing basis and under a result-based agreement.

- Hiring service providers: When available, service providers will be recruited on a competitive basis and hired through result-based contracts. As part of component 2.2 towards a national agricultural advisory system, the project will help line Ministries set up a service provider certification process. The list of certified providers will be annually updated by a joint CRA/MinAgri Commission.

- Helping service providers start-up a business: This will be the solution when required service providers are not available in the area. The project will support the creation of dedicated private entities to develop specialized advisory services. Project support will depend on a result-based agreement to start developing the business. Start-up entities will adopt a private business approach to deliver paid services and generate income, with a view to become financially autonomous by the end of the project.

- Project Implementation Manual: A detailed project implementation manual (PIM) is being prepared and will be ready prior to project negotiations. It will describe project guidelines, standard result-based contracts for various types of services, ToR for personnel to be recruited, specification of training modules, accreditation procedures for service providers, etc.

Table – Summary of Implementation Responsibility by Component

| Component / Sub-Component | Implementing Agencies | Decision making mechanism | Financing Mechanism |
| --- | --- | --- | --- |
| Component 1 - Technology transfer and service provision to producers |  |  |  |
| C1.1- Farming System and Supply Chain Modernization | APCAM | - APCAM at the national level; - CRAs at the regional level. | Agricultural Modernization Funding Mechanism |
| C1.2- Capacity building for Pos and service providers |  |  |  |
| C1.3-Facilitating rural credit development |  |  | Project financing |
| C1.4-Generating technologies and strengthening linkages |  | CNRA – National Ag. Research Committee |  |
| Component 2 – Irrigation Investments |  |  |  |
| 2.1 - Large scale irrigation | Office du Niger | SEDIZON | Office du Niger |
| 2.2 – Small scale irrigation | MinAgri | CRAs / DRGRs | Project financing |
| Component 3 - Comprehensive programmatic approach, sector monitoring and project coordination |  |  |  |
| 3.1 - Policy dialogue and sector coordination | MinAgri | CPS and TECC | Project financing |
| 3.2 – Sector M&E |  |  |  |
| C3.3-Delivery of core public services |  |  |  |
| 3.3 – Project coordination and M&E |  |  |  |

E.	detailed implementation arrangements specific to some sub-components

- Farming System and Supply Chain Modernization: the agricultural modernization funding mechanism will finance demand-driven investment micro-projects related to the adoption of modern technologies or production techniques (including small scale irrigation under component 2.1). Micro-projets will consist of modernization packages that will include a physical investment, training of beneficiaries (technical training and business management training, through private service providers) and a multi-annual technical assistance to micro-project holders for investments and business management advice.

- Types of micro-projects and source of financing: the project will finance the following types of investments: (i) Farm and agricultural technique smodernization (IDA); (ii) Livestock production system modernization (IDA); (iii) Intensification and diversification at Office du Niger (IDA); (iv) Demand-driven and on-farm research (IFAD); (v) Small scale irrigation intensification (IFAD); (v) Post-harvest operation (IFAD); (vi) SLWM promotion (GEF).

- Based on the PASAOP experience, the AMFM will operate at the regional level under the authority of the CRA. Funds will be placed in a well implanted local bank. Procedures and disbursement modalities will derive from decentralization principles and build on predecessor and on-going project experience.

- Within each CRA, a “unit for farming systems and supply chains modernization” will be established and the project will finance three local rural finance experts to constitute the human resource base of this unit. It will be in charge of administrating the AMFM. This will include advertising the fund, the early pre-selection of micro-projects, assistance to pair micro-project holders with service providers, management of micro-project presentation to the selection process, management of fund disbursement, and quality monitoring of service providers’ work. A detailed manual (of operations) will be prepared to operate the funding mechanism.

- Capacity building for POs and service providers: based on capacity enhancement needs assessment, APCAM will prepare annual training programs to be submitted and validated by the CTCE. Joint training programs to benefit a large group of POs or to both producers and public services will be encouraged. APCAM and line Ministries will undertake capacity assessments of service providers and POs’ staff and will elaborate training programs to be submitted and validated to the CTCE as well.

- Comité Régionaux de Concertation et d’Échanges: For the selection of sub-projets under component 1.1 and capacity building activities under component 1.2, CRAs will use the existing Consultation and Dialogue Regional Committes (Comités Régionaux de Concertation et d’Échanges – CRCE) set-up under PASAOP to faciliate dialogue and coordination between POs and to select capacity building and investment projects submitted by producer groups. Eligible criteria will be detailed in the project implementation manual to ensure sub-projects are consistent with project objectives, focused on targeted production systems, properly designed in terms of institutional and implementation modalities, aimed at disseminating innovative technologies, based on a light but reliable economic analysis. All sub-projects will need to include capacity building activities, as well as technical, economic and managerial advice.

- Credit access facilitation: APCAM will recruit its own specialized staff within each CRA to interface and facilitate the dialogue between POs and credit institutions (MFIs and commercial banks). The project will also finance specialized staff to be deployed within banks that are interested to develop internal capacities with enhanced expertise in agricultural and livestock production systems. Studies on the legal framework and pilots of innovative financing instruments will be undertaken on-demand as part of the partnership that APCAM will develop with credit institutions.

- Technology generation: support to agricultural research activities will replicate the institutional set-up and decision making mechanism developed under PASAOP. APCAM will organize annual research needs assessment to be submitted to research institutions through CNRA.

- Small scale irrigation: small-scale irrigation investments will follow a demand-driven process under the “farming system and supply chain modernization fund”. Eligible POs will receive technical assistance to formulate a pre-feasibility analysis and an initial request. Site selection will be validated by the regional division for rural engineering (DRGR - Direction Régionale du Génie Rural). The project will concentrate such investments in areas with higher potential, with a view to reach the critical mass necessary to establish self-sustained services, while maintaining a demand-driven approach. A multi-annual planning will be prepared at the beginning of the project to determine the concentration areas in each region and the priority criteria for selection. Due attention will be given to vulnerable groups in the selection criteria, making sure, for example, that female-headed households and young farmers are fairly represented among the beneficiaries.

- Beneficiaries will be required to contribute in-cash and in-kind (using a labor intensive approach) to the financing of the investment (infrastructure and equipment). The cash contribution could be covered by a credit from a financial institution. Credit facilitation will be achieved through the preparation of a business plan that will cover all the necessary arrangements to generate sufficient incomes to cover installments. Depending on their managerial capacity, POs could be required to sign a management contract with a service provider financed by the project for the duration of the credit to ensure transparency and professional book keeping. As an additional guarantee for the credit institution, the business plan may also include a pump maintenance contract, and/or storage management and marketing assistance.

- Execution will be delegated to an operational entity –service provider or dedicated unit, see §14- called “mandataire” (or “maître d’ouvrage délégué”) accredited by the government and have local presence in the region. The “mandataire” will assist beneficiaries all along the implementation process, starting with credit facilitation. It will receive the financial contribution of the PO from the beneficiary’s credit institution and from the project. It will then contract out the design and construction of irrigation infrastructures, as well as the required package for service provision. It will accompany the beneficiaries until they completely take over the management of the scheme. It will be remunerated by a percentage of the subproject’s cost (3% of construction cost and 6% of consultancy cost).

- Once validated by DRGR, the investment will be presented for project financing as a collective demand-driven micro-project under the modernization fund. As such, project support will be provided as a package, including assistance for physical investments, credit facilitation, training, technical and management advice.

- Large scale irrigation: large scale irrigation development will be a mix of supply and demand-driven approaches. Investments will follow three options: (Model 1) the traditional ON-led approach; (Model 2) demand-driven public scheme; and (Model 3) the fully autonomous scheme (see Annex 4 for details). The design and construction of irrigation infrastructures will be under the full responsibility of Office du Niger, except for Model 3 where Office du Niger will be the mandataire of the PO (following the small scale irrigation approach, and therefore receiving the same percentage rate of the subproject’s cost). The Office du Niger will assign a team dedicated to the project under the supervision of the head of the engineering service (SAH: Service des Aménagements Hydrauliques). The team will include at least two engineers (one for each scheme: Sabalibougou and M’Béwani) and one socio-economist. Office du Niger will ensure adequate operational resources are made available to the team to perform its duties. Team members will receive a Letter of Assignment related to their responsibilities in the project.

- The project will also support a voluntary land consolidation process, to reallocate land to smallholders from existing irrigation perimeters. POs will implement the land reallocation plan under the oversight of the Joint Land Management Committee (Comité Paritaire de Gestion des Terres). Feasibility studies for the two new schemes (Sabalibougou and M’Bewani) will determine the optimal land allocation among the three models, depending on an assessment of the actual demand and on the appropriateness of the edaphic conditions.

- For Model 1, land allocation will be ruled by the traditional ON approach based on law (Décret de Gérance), under the oversight of the Joint Land Management Committees. For Models 2 and 3, land allocation will be initially based on letters of intent and identification reports; the actual allocation (lease contracts) will be signed upon payment of the beneficiaries’ financial contribution.

- Financing modalities: for Models 1 and 2, the traditional approach is a turn-key investment built by Office du Niger using project funds, with cash or in-kind user contribution limited to the quaternary canals and final land leveling. Model 3 investments are either turn-key or labor-intensive, with project funding and beneficiaries’ funds transferred to ON (who is contracted out by the beneficiaries to handle the scheme construction). The decision-making process and project financing described for small-scale irrigation under the modernization fund will apply for Models 2 and 3.

- Policy dialogue and coordination towards a sector approach: this component will be under the overall responsibility of the CPS. The CPS will delegate the coordination of sector-specific (or sub-sector) policy dialogues to the line Ministries in charge.

- Activities will be executed under the overall guidance of the PNISA-NSC regarding policy and strategy-related matters, and under the direct guidance of the CTCE for work programming. The CPS will have resources to: (i) support the progression towards a programmatic approach based on public expenditure reviews and mid-term expenditure frameworks; (ii) hire expertise and technical assistance to undertake policy studies; (iii) strengthen its own staff capacities with respect to policy formulation; (iv) facilitate the policy dialogue around the PNISA elaboration; and (v) organize large scale training programs on policies and strategies for staff of all line Ministries, professional organizations and rural leaders.

- On a demand-driven basis and as part of the transition towards a sector wide approach, the CPS will support other key project institutions in undertaking studies and/or stakeholders’ consultations on critical issues.

- Agriculture sector monitoring and evaluation: this is a core function of the CPS within MinAgri. The CPS will therefore implement activities related to sub-component 3.2, with a focus on strengthening its own capacities, as well as strengthening the capacities of other line Ministries (to collect, analyze and publish data and analysis results for policy decision making). The CPS will delegate data collection (field surveys, households census and price monitoring, for instance) to specialized national and international firms. It will hire expertise and technical assistance to organize the compilation and analysis of data, and the dissemination of results to policy makers and stakeholders (involved in programmatic approaches and/or in the preparation of PNISA, for example).

- Delivery of core public services: Some core public functions critical to PDO achievements have been identified during project appraisal. They cover in particular input quality control, phyto-sanitary alert and control, seed certification, veterinary medicine control and zoo-sanitary surveillance, service providers accreditation, environment safeguard supervision, civil work control for small and large scale irrigation investments. At the beginning of the year, each national directorate of the line Ministries will present its annual work program and budget to the CTCE and PNISA-NSC. The Ministry of Environment will prepare an annual program and budget specific to the supervision of project social and environment safeguards and implementation of mitigation measures. These core public functions will be primarily financed from the Ministries’ budget but the project will finance critical gaps to ensure sound implementation in the target production basins.

- Project coordination and M&E: the CPS will be responsible for: (i) the preparation of annual work programs and budgets to be submitted to CTCE; (ii) procurement and financial management; (iii) monitoring and evaluation of overall project activities; (iv) overall compliance with national procedures and Bank legal agreements and implementation manual; (v) reporting to CTCE and PNISA-NSC, as well as to project co-financiers; and (vi) preparing for technical and financial audits.

- To assist CPS in carrying out its mandate under the Project, its capacities will be strengthened and it will be staffed with: (i) a well experienced specialist in project planning and management to help the Director of the CPS in project coordination and management; (ii) a procurement specialist; (iii) a financial management specialist; and, (iv) an M&E specialist. Procurement and financial management will follow national procedures and will be internalized within each implementing agency (see Annex 7 on financial management). Resources under this component will also be available to strengthen the capacities of the administrative and financial divisions of the line Ministries, and fiduciary staff within the different implementing agencies. M&E activities will be supported by surveys and studies to be undertaken under component 3.2.

Annex 7: Financial Management and Disbursement Arrangements

Mali:  Fostering Agricultural Productivity Project

1. Summary of the Financial Management Assessment

- The objective of the Financial Management (FM) Assessment is to determine whether each of the project’s implementing agencies namely CPS/DAF (Statistics and Planning Unit and the Financial and Administrative Directorate) under the oversight of the Ministry of Agriculture, APCAM (Permanent Assembly of Mali Agricultural Chambers), and “Office du Niger”  (Public Agency in charge of the water system and land tenure) have acceptable FM arrangements (accounting system and reporting, auditing and internal controls) in place to carry out the project’s fiduciary responsibility. An implementing entity’s FM arrangement is acceptable if: (i) it is capable of recording correctly all transactions and activities; (ii) it supports the preparation of regular and reliable financial statements; (iii) it safeguards its assets, and (iv) it is subjected to a satisfactory audit process.

- In line with the Paris Declaration, the project will focus on improving the capacity of ministries and central systems. A gradual approach for using the country system will be considered subject to the implementation of the action plan. The resolution on “National Implementation of Projects Financed by IDA” endorses the new arrangements for implementing World Bank-financed projects through the national expenditure channel and financial management mechanism. The assessment concluded that the PFM is partially adequate for Bank-financed investment lending: (i) national budget procedures, internal controls and audit institutions will be used with some adjustments in the FM Information System (PRED) to meet projects’ needs; and (ii) accounting and reporting, Treasury management and external controls are not yet adequate. Specific FM arrangements will be established to meet the Bank’s requirements.

- The financial management (FM) assessments of the implementing agencies were carried out in accordance with the Financial Management Practices Manual issued by the Financial Management Sector Board on November 3, 2005. The conclusions of the assessment are summarized in the table below:

Table 1: Conclusions from FM Assessment

| CPS/DAF | APCAM | Office du Niger |
| --- | --- | --- |
| Financial management arrangements have to be set up and do not meet yet the Bank’s minimum financial management requirements under OP/BP10.02. The risk rating for the CPS/DAF is Substantial. | Conclusion of the assessment is that financial management arrangements have to be strengthen and will meet the Bank’s minimum requirements under OP/BP10.02 once the mitigation measures are implemented. The overall fiduciary risk rating is assessed as Moderate. | Conclusion of the assessment is that the “Office du Niger” has already implemented Bank-financed projects but does not meet the Bank’s minimum financial management requirements under OP/BP 10.02 due to high level of fraud and corruption. The risk rating is Substantial and therefore it will not have FM responsibility under the present project. |

2. Country issues

- The inherent risk of the PFM system is rated Substantial at the country level.  The Government’s Action Plan for improving and modernizing public financial management (PAGAM-GFP) is a component of the larger program on institutional development (Institutional Development Program) that the authorities are implementing in the context of the country’s growth and poverty reduction strategy. The 2008 PEMFAR prepared by the World Bank and the European Union, shows that the reform program has yielded progress in PFM but a number of challenges remain, including: (i) strengthening the integration between the budget and the country’s poverty reduction strategy towards a multi-year programming framework, (ii) eliminating delays in the consolidation of budget information, and the production of comprehensive and regular in-year annual budget execution reports, and (iii) reinforcing the external audit by increasing the capacity of the Section of Accounts of the Supreme Court.

- In view of critical weaknesses identified of the information systems which affect the PFM system’s capacity to provide timely and reliable information for managing and monitoring implementation of the Bank-financed projects and the independence constraints of the Chamber of Accounts of the Supreme Court to provide timely state financial statements audited reports, the overall risk rating for the project to use the country system is substantial.

3	Fiduciary Risks and Mitigation Measures

CPS/DAF

| ##### Risk | Risk Rating | ##### Risk Mitigation Measure | ##### Residual Risk Rating |
| --- | --- | --- | --- |
| Inherent Risks: | S |  | S |
| Country: Poor governance. Risks remain in term of quality and timeliness of in-year budget reports and annual financial statements and effectiveness of external audit and legislative scrutiny of the annual budget law. | S | The strengthening of public financial management through the PRSC is expected to enhance the PFM’s system to provide timely and reliable information and to make effective the external audit of the annual budget. But this risk will not impact the project as it will not rely on the national accounting and auditing system. | S |
| Entity: Risk remains in terms of coordination due to the involvement of many government bodies (five bodies will take part in the overall project supervision and implementation (MinAgri, MEP, MEA, CSA, SEDIZON) Delays in project implementation | H | The project implementation manual will define clear roles and responsibilities of the different stakeholders and segregation of duties. In addition, the monitoring of the Inter-ministerial Steering committee will help to mitigate this risk. | S |

| Project: The combination of several activities under the responsibility of different implementing agencies, involving multiple sectors and dispersed spending units increases the complexity of the project. Lack of FM capacity and weak internal control environment. | S | Some sectors have previous experience in implementation of Bank financed projects. A financial and accounting manual will be prepared and training will be provided to the team. | M |
| --- | --- | --- | --- |
| Control Risks: | S |  | M |
| Budgeting: Deviations in budget execution of some components not captured by the reports. Delays in project’s activities and implementation. | S | Changes in PRED’s parameters to capture individual projects financed by donors The FM manual will be prepared to clarify the roles and responsibilities of the stakeholders and training will be provided upon project effectiveness. | M |
| Accounting: Delays in the consolidation of financial information. Timeliness of Annual Financial Statements. | S | A “multi projects” computerized accounting system will be customized to fit project needs and generate useful information and financial statements. | M |
| Staffing: Lack of adequate qualified FMS familiar with the Bank FM procedures. | S | An FM team (financial management specialist and accountants), familiar with the Bank procedures will be recruited to strengthen the FM capacity within the CPS | M |
| Internal Control and audit: Lack of quality capacity assurance mechanisms to perform high quality controls. | S | The CGSP (Public Services General control) will carry out internal audit of the project with ToR acceptable to IDA and will issue a report on half yearly basis. | M |
| Funds Flow: Difficulties in the timely submission of acceptable WA may delay funds mobilization. | S | FM staff familiar with Bank FM and Disbursement procedures will be recruited. The project’s accounts will be maintained in commercial banks under the authorization of a public accountant. | M |
| Reporting and Monitoring: Delays in the submission of agreed IFRs and annual project financial statements. | S | Recruitment of a qualified and experienced FM staff. The accounting software will be customized to facilitate compilation of accounting information. | M |
| Auditing: Inadequate institutional arrangements in place for the appointment of external auditors. | S | Recruitment of qualified, experienced and independent external auditors with TORs acceptable to IDA. | M |
| Overall Risk: | S |  | S |

APCAM

| ##### Risk | Risk Rating | ##### Risk Mitigation Measure | ##### Residual Risk Rating |
| --- | --- | --- | --- |
| Inherent Risks: | S |  | M |
| Entity: Monitoring and coordination remain to be an area of weakness. | S | The FM manual will be prepared to clarify the roles and responsibilities of the regional Chambers of Agriculture and training will be provided upon project effectiveness. | M |
| Project: Dispersed spending units with various transactions. But previous experience in implementation of Bank financed projects. | S | The Chambers of Agriculture have already regional accountants trained during the implementation of the PASAOP (previous Bank financed project). The financial mechanisms will remain the same under the consolidation of APCAM, the umbrella of the CRAs. | M |
| Control Risks: | S |  | M |
| Budgeting: Monitoring of variations is not timely to make meaningful revisions to the budget. | S | The FM manual will define the budget process and calendar and the project’s FM staff will provide support to CRAs in preparing realistic budgets consistent with their disbursement plans and regular budget variance statements. | M |
| Accounting: An adequate system is not yet in place. | S | A “multi projects” computerized accounting system will be customized to fit project needs and generate useful information and financial statements. | M |
| Staffing: Lack of qualified FM staff. | S | A qualified FM officer familiar with the Bank procedures will be recruited to strengthen the FM capacity within the APCAM. | M |
| Internal Control and Audit No internal audit function exists. | S | The FM manual will set out a clear description of the Approval and authorization processes. The CGSP (Public Services General control) will carry out internal audit of the project with ToR acceptable for IDA and will issue a report on half yearly basis. | M |
| Funds Flow: Some instances of delayed fund flows affecting project implementation at the regional level. | S | The design of flow of funds arrangements is simple. | M |
| External Audit: Inadequate institutional arrangements in place for the appointment of external auditors. | S | A competent external auditor with sound TOR acceptable to IDA will be recruited. | M |
| Reporting and Monitoring: Delays in the submission of agreed IFRs and annual project financial statements. | S | Recruitment of a qualified and experienced FM staff and, the accounting software will be customized to facilitate compilation of accounting information. | M |
| Overall Risk: | S |  | M |

OFFICE DU NIGER

| ##### Risk | Risk Rating | ##### Risk Mitigation Measure | ##### Residual Risk Rating |
| --- | --- | --- | --- |
| Inherent Risks: | H |  | S |
| Entity: Lack of clear organization. Serious reserves raised in the audit opinion on the financial statements. Weak internal control environment and mismanagement. The Auditor General published in 2006 and 2007 an incriminating report exposing frauds and corruptions estimated to US$1 million. | H | The management team is implementing the key recommendations to strengthen the internal control environment. In addition an action plan resulted from an institutional audit is being implemented through a TA financed by donors. The Office du Niger will not have FM responsibility under the present project but the project will contribute to strengthen their governance capacity. | S |
| Project: Weak internal control environment. | S | Idem | S |
| Control Risks: | S |  | M |
| Budgeting: Regular budget variance statements are not prepared and used in a meaningful way. | S | The FMS of the project will provide support to Office du Niger in preparing and monitoring realistic budgets consistent with the disbursement plan of this component. | M |
| Accounting: The accounting software in place is “multi projects” and can accommodate this project’s transactions. | M | All the transactions of this component will be recorded in the project accounting system located in the central unit | L |
| Staffing: Lack of adequate qualified FMS | M | The Administrative and Financial Department has adequately staffed to support the implementation of this project | M |
| Internal Control and audit: Internal audit function exists, but adds little value to the control framework | S | The FM manual will set out a clear description of the Approval and authorization processes. The internal audit function will be strengthen to adopt risk-based approach and perform ex-post audits | M |
| Funds Flow: Difficulties in the timely submission of acceptable WA may delay funds mobilization | M | For this component, direct payment method will be used | M |
| External Audit: The legal auditors issued qualified opinions on the 2006, 2007 and 2008 financial statements and the quality of the reports is not satisfactory | S | In addition to the external audit of the project, an international independent firm will be recruited to carry out external audit of Office du Niger. | M |
| Reporting and Monitoring: Delays in the submission of agreed IFRs and annual project financial statements. | S | The IFRs will be prepared by the coordination unit | M |
| Overall Risk: | H |  | S |

H – High; 	S – Substantial		M – Moderate		L – Low

4.	Strengths:

- Previous experience in implementing Bank financed projects in APCAM, CRAs and ON;

- The CRAs have regional accountants trained during implementation of PASAOP and experience to manage sub-accounts for decentralized activities.

5. Weaknesses and Action Plan

The project financial management is weakened by the following salient features:

- Lack of fiduciary capacity in the CPS and no previous experience in coordinating a complex project;

- Dispersed spending units with various number of transactions;

- Lack of internal control function in the three execution agencies;

- Weak internal control environment and high risk of fraud and corruption in Office du Niger;

- FM procedures, the computerized accounting software and the FM staff are not yet in place in APCAM and CPS.

| ACTION | Deadline | Intermediate Milestones |
| --- | --- | --- |
| - Appoint FM staff (two FM officers and two accountants) in APCAM and CPS | By effectiveness | Process started during preparation |
| - Set up a “multi projects” computerized accounting system to fit project needs and generate useful information and financial statements | By effectiveness | Process started during preparation |
| - Prepare and adopt the operational manual including financial and accounting procedures | By effectiveness | Process started during preparation |
| - Draft the ToR for internal audit to be performed by the Public Services General Control (CGSP) | By 3 months after effectiveness | Process started on the date of Board’s approval |
| - Changes of parameters in PRED to capture individual projects financed by donors | By effectiveness | Process started during preparation |
| - Draft the TOR of the financial audit of the project and recruit an external audit firm | By effectiveness By 2 months after effectiveness | Process started during negotiations |
| - Assignation of an authorized Public Accountant by the MEF in accordance with PFM regulations | By effectiveness |  |

5.	Anti-corruption Measures

- Corruption is acknowledged as an issue in the public sector in Mali and more specifically in the Office du Niger. Increased spending through the public expenditure channel opens up opportunities, and this risk must be countered by specific anticorruption measures to be implemented under the project. The following measures are incorporated into the Project design to minimize the above risk:

- Internal control : the project will support the internal control of Office du Niger to build its capacity through training on audit methodology, preparing work programs based on risk assessment and the adoption of risk based approach to perform regular ex-post audits;

- Operational review : A technical audit will be carried out every two years  to supplement the annual financial audit;

- Financial audit : In addition to the regular financial audits of the project, an international independent firm will be recruited to carry out external audit of Office du Niger;

- Information dissemination: To increase transparency with regard to information dissemination, the Office du Niger’s website will be updated regularly providing comprehensive information including the audits reports and budgets;

- Control over project accounts: All payments from these accounts will be subject to multiple verification and authorization controls by the CPS members and the Treasury through the authorized Public Accountants assigned to operate the bank accounts.

6.	 Implementing entities and Fiduciary Responsibilities

- The CPS will be responsible for coordinating the Project’s activities, and information exchange among beneficiaries, line ministries and other stakeholders under the oversight of the Ministry of Agriculture (Min Agri). The CPS is also the execution agency of the component 3. The CPS will perform financial management function. A project management component is included to develop fiduciary capacity within the MinAgri in order to transfer this function to the regular MinAgri staff when appropriate conditions are in place.

- The aspects of project financial management that will be performed by the CPS include: accounting for the Project, producing consolidated project financial reports (IFRs) and organizing the Project’s annual audits, coordination with the Bank, including submission of withdrawal applications, and coordination with other implementing entities on implementation and financial management issues.

- The Permanent Assembly of Mali Agriculture Chambers (APCAM) is the umbrella of the Regional Chambers of Agriculture. It will implement all activities related to the producers and coordinate the regional activities delegated to the Chambers of Agriculture. The Chambers of Agriculture involved in the project implementation have qualified accountants with previous experience in implementing Bank financed activities and managing sub-accounts through the implementation of the PASAOP. The assessment of their capacity has been carried out and the arrangements made under the PASAOP are still in place.

- Office du Niger is the public agency in charge of the management of the water system and land tenure for the large irrigation development of Delta of the Niger River. It will handle technical functions of the second component related to the large scale irrigation. But the Office du Niger will not have FM responsibility under the present project.

7.	Disbursement arrangements

Disbursement methods

- Disbursements under the Credit would be transaction based. Direct Payment and SOE (Statement of Expenditures) methods will apply as appropriate. Three Designated Accounts will be opened at commercials banks to facilitate payment for eligible expenditures. The Designated Accounts will be managed by the implementing entities according to the disbursement procedures described in the Administrative, Accounting and Financial Manual and Disbursement Letter (see Appendix on Funds and Information Flow mechanism). For component related to the large scale irrigation, (few contracts with large amounts), direct payment method will be used. Office du Niger will submit through the coordination unit withdrawal applications for direct payments to the beneficiaries and the ON’s Designated Account will be managed by CPS.

- The allocation of each Designated Account will cover approximately four months expenditures. The minimum value of applications for reimbursement, direct payment and special commitment is 20 percent of outstanding advance made to each designated account.

Report based disbursement

- The conversion to report-based disbursements may be envisaged when the quality of IFRs is judged to be good by the team.

Flow of Funds

- Projects Designated Accounts will be maintained in commercial banks, but an authorized public accountant (comptable assignataire) will be designated to sign and authorize transactions and record transactions in the national system. The following accounts will be maintained by CPS:

- Three Designated Accounts in FCFA will be opened at commercial banks and managed by CPS and APCAM for payments of eligible expenditures incurred under the components 1, 2 and 3, as shown in Flow of Funds diagram on page 93.

- A project Account in FCFA will be opened at a commercial bank and managed by CPS into which Counterpart Funds and contributions of beneficiaries will be deposited.

8.	Budgeting arrangements

- The budgeting process will be clearly defined in the FM Manual and the budget will be adopted by the Steering Committee before the beginning of the year. Each entity will prepare its budget to be consolidated by the project FMS. The project consolidated budget will be submitted for IDA’s non-objection.

- Project’s transactions will be recorded in PRED to ensure the comprehensiveness of the budget execution reports. Some PRED parameters are being modified to include the project’s components.

9.	Accounting policies and procedures

- A “multi-projects” accounting software will be customized to meet project’s needs and generate IFRs and financial statements. The current accounting standards in use in Mali for on-going Bank-financed projects will be applicable. SYSCOHADA is the assigned accounting system in West African Francophone countries. Project accounts will be maintained on a cash basis, supported with appropriate records and procedures to track commitments and to safeguard assets. Annual financial statements will be prepared by the CPS in accordance with the SYSCOHADA. The ROSC Accounting and Auditing identified some differences with the International Accounting Standards but they are not expected to impact the project. Accounting and control procedures will be documented in the Administrative, Accounting and Financial Manual.

10.	Reporting and Monitoring

- Interim un-audited Financial Reports (IFRs) would be prepared by the CPS, integrating financial information from APCAM. The IFR will include sources and uses of funds by project expenditures classification. It will also include a comparison of budgeted and actual project expenditures (commitment and disbursement) to date and for the quarter. The CPS will submit copies of the IFRs to the Bank within 45 days following the end the calendar semester.

- The CPS will produce Annual Financial Statements, and these statements will comply with International Accounting Standards (IAS) and World Bank requirements. These Financial Statements  will comprise of:

- A Statement of Sources and Uses of Funds

- A Statement of Commitments

- Accounting Policies Adopted and Explanatory Notes

- A Management Assertion that project funds have been expended for the intended purposes as specified in the relevant financing agreements

11.	Audit arrangements

Internal Audit

- Internal audit functions for the project will be assumed by the Government internal audit entity within the oversight of the CGSP.

External audit

- The Financial Agreement will require the submission of Audited Financial Statements for the CPS to IDA within six months after year-end. External auditor with qualification and experience satisfactory to the World Bank will be appointed to conduct an annual audit of the project’s financial statements. A single opinion on the Audited Project Financial Statements in compliance with International Standards on Auditing (ISA) will be required.

- The external auditors will prepare a Management Letter giving observations and comments, and providing recommendations for improvements in accounting records, systems, controls and compliance with financial covenants in the Financial Agreement.

- In addition, “Office du Niger” audited report will be submitted to IDA within six months after the end of each fiscal year.

- The table below summarizes the auditing requirements:

| Audit report | Due Date |
| --- | --- |
| - Financial Statements - Management letter | End of June |

##### 12.	Supervision Plan

- The project will be subject to periodic supervision missions. Given the substantial FM risk rating, supervision will be done twice a year. This intensity will be accommodated according to the evolution of the FM risk rating.

- Supervision activities will include: (i) review the financial management aspects of quarterly IFRs; (ii) review of annual audited financial statements and management letter as well as timely follow up of issues arising; (iii) and participation in project supervision missions, as appropriate; and updating the FM rating in the Implementation Status Report (ISR).

13.	Financial Covenants

- The Borrower shall establish and maintain a financial management system including records, accounts and preparation of related financial statements in accordance with accounting standards acceptable to the Bank. The Financial Statements will be audited in accordance with international auditing standards. The Audited Financial Statements for each period shall be furnished to the Association not later than six (6) months after the end of the project fiscal year.

- The Borrower shall prepare and furnish to the Association not later than 45 days after the end of each calendar quarter, interim un-audited financial reports for the Project, in form and substance satisfactory to the Association

- The Borrower will be compliant with all the rules and procedures required for withdrawals from the Designated Accounts of the project.

14.	Table of Allocation of Funds (IDA, GEF-IDA and EU TF)

| Implementing Entity | Legal Doc. | Project Activity | IDA | GEF TF | EU TF |
| --- | --- | --- | --- | --- | --- |
| APCAM | A 1 (a) | Agricultural technique modernization; livestock production system modernization; intensification and diversification | 15.4 |  |  |
|  | A.1 (c) | Promote sustainable land and water management techniques. |  | 3.8 |  |
|  | A.2 (a) | Refurbish, equip and improve management and functioning of APCAM, CRAs and POs | 6.9 |  |  |
|  | A.4 | Support to CNRA to facilitate technology generation and CRRVA to strengthen the linkages | 5.5 |  |  |
| Office du Niger | B.2 (a) | Sabalibougou 1 (1.200ha) |  |  | 12.5 |
|  | B.2 (b) | Sabalibougou 2 (1.000ha) | 6.5 |  |  |
|  | B.2 (c) | M'Béwani (500ha) | 5.4 |  |  |
|  | B.2 (d) | Kalankorola and Tango Drains |  |  | 7.0 |
|  | B.3 | ON modernisation and safeguards | 3.4 |  |  |
|  | B.4 | Safety of dams | 1.8 |  |  |
| Ministry of Agriculture | B.1 (a) | Small scale irrigation studies | 2.2 |  |  |
|  | C.1 (a) | Elaboration of the Agricultural investment program | 1.8 |  |  |
|  | C.1(c) | Promotion of SLWM |  | 0.6 |  |
|  | C.2 (a) | Assessment and monitoring of agricultural sector performances | 2.7 |  |  |
|  | C.2 (b) | Monitoring of the evolution of natural resources and the impact of agricultural investments on the environment |  | 1.8 |  |
|  | C.3 (a) | National Agricultural Advisory Service Council to provide quality control | 7.7 |  |  |
|  | C.4 | Project coordination + M&E | 3.7 |  |  |
|  |  | PPF refinancing | 0.95 |  |  |
|  |  | Non allocated | 6.05 |  |  |
|  |  | Total | 70.0 | 6.2 | 19.5 |

15.	Diagram of Flow of Funds

Direct Payment

IDA CREDIT

Suppliers

&

Contractors

Designated Account

CPS

GOVERNMENT

Designated Account

APCAM

Project Account

Regional

Sub accounts

CRAs

Beneficiaries

Contributionn

Counterpart funds

Sub-Account for ON managed by CPS

Annex 8: Procurement Arrangements

Mali:  Fostering Agricultural Productivity Project

General Considerations

- Procurement for the proposed project would be carried out in accordance with the World Bank’s “Guidelines: Procurement under IBRD Loans and IDA Credits” dated May 2004, revised October 2006 (“the Procurement Guidelines”, and “Guidelines: Selection and Employment of Consultants by World Bank Borrowers” dated May 2004, revised October 2006 (“the Consultants guidelines”, and the provisions stipulated in the Legal Agreement. Each contract to be financed by the Credit will be in the Procurement Plan prepared by the Borrower and agreed with IDA.

- Publication: A General Procurement Notice (GPN) will be prepared by the Borrower and published in the United Nations Development Business online (UNDB online) and Development Gateway Market (dgMarket) to announce major consultancy services required in particular those services estimated at US$200,000 or above, as well as any ICB. Requests for Expression of Interest (REI) for consultant contracts estimated at more than US$200,000 should be published on the UNDB online website and dgMarket. REIs should be published in the Official Gazette or in a national newspaper and on a free access website for all consultancy firms regardless of the contract amount. For NCB, a specific procurement notice will be published in the Official Gazette or in a national newspaper or on a free access website. Contract awards will also be published on the UNDB online website, dgMarket and in a national newspaper or on a free access website.

Country Environment

National procurement system and ongoing reforms

- Mali adopted a Public Procurement Code in August 2008, as part of the action plan of the update of the Country Procurement Assessment Report (CPAR) for Mali carried out in FY04.  The legal framework is in line with the WAEMU’s guidelines. In addition, the Country has also adopted a law creating (i) an independent procurement regulatory body responsible for policy and handling complaints from bidders and (ii) the procurement control body responsible for the control of procurements transactions. However, only the controls body (the “Direction Générale des Marchés Publis” – DGMP) is fully operational and has been decentralized at regional level inside the country. As such, the project will benefit from the existence of the two bodies, and it is recommended that these bodies play their respective roles in procurement regulation and procurement control under the new financing on an agreed basis.

- In general, Mali’s procurement laws and regulations do not conflict with IDA guidelines.  However provisions related to the restriction of the eligibility of bidders to those coming from WAEMU countries only will not be applied. No special exceptions, permits, or licenses need to be specified in Credit documents since IDA procedures take precedence other those laws and regulations.

- NCB procedures may be used for contracts for work contracts with a contract less than US$ 5,000,000 and for goods contracts less than US$ 500,000. The procedures may be those described in the national public procurement code under its “Appel d'offres ouvert” , i.e. “Open Competitive bidding”. In order that this method be acceptable to IDA to be used in the present project, the following special requirements will be taken into account NCB procedures may be reviewed to ensure that: (i) the invitation to bid is advertized in national newspapers with wide circulation; (ii) the bid evaluation, qualification of bidders and contract award criteria are clearly indicated in the bidding documents; (iii) the bidders are given adequate response time (at least four weeks) to prepare and submit their respective bids; (iv) the contract is awarded to the lowest evaluated bidder which meet the qualification criteria; (v) the eligible bidders, including foreign bidders, are not precluded from participating; and (vi) no preference margin is granted to local suppliers or contractors.

Procurement of Works

- Procurement will be carried using the Bank’s Standard Bidding Documents (SBD) for all ICB and National (SBD) contracts deemed satisfactory to the Bank.

- Contracts estimated at less than US$5,000,000 for works that can be procured by local companies may be awarded through the NCB procedures.

- Contracts for small works estimated at US$50,000 or less may be procured under the shopping procedure in accordance with the provisions of clause 3.5 of the Bank’s Guidelines on Procurement: Procurement under IBRD Loans and IDA Credits” May 2004, revised October 2006 and  the Memorandum “Guidance on Shopping” issued by the Bank on June 2000. Works will be procured under lump sum, fixed price contracts awarded on the basis of quotations obtained from at least three qualified domestic contractors in response to a written invitation.  The invitation shall include a detailed description of the works, basic specifications, required completion date, basic form of agreement acceptable to the Bank, and relevant drawings where applicable.  The award will be made to the contractor with the lowest price quotation and who has the experience and resources to successfully complete the contract.

- Small works estimated to cost less than US$50,000 for demand-driven investments, micro-projects, may-be procured under simplified procedures for Community participation in procurement.

Procurement of Goods

- Procurement will be carried out using the Bank’s SBD for all ICBs, and National SBDs agreed with or satisfactory to IDA.

- Contracts estimated at less than US$ 500,000 for locally available goods will be awarded through NCB procedures.

- Contracts for small goods and office supplies, as well as minor equipment and furniture available locally and estimated at less than US$50,000 may be procured under shopping procedures in accordance with the provisions of clause 3.5 of the Bank’s “Guidelines on Procurement and the Guidance on Shopping Memorandum" issued by IDA, June 9, 2000. These include:  furniture; vehicles for the project if the contract estimate amount permits the use of this procedure; computers; accessories; software; communication; and office equipment, etc.

Procurement of Non-consulting Services

- These contracts generally cover project implementation through NGOs, firms or specialized agencies. For contracts estimated to be US$50,000 up to US$ 500 000, NCB procedures will be used and contracts awarded using the Bank’s SBDs or documents acceptable to the Bank. For contracts estimated at less than US$50,000, shopping procedures may be used.

Selection of Consultants

- Consultants will be selected using the Quality and Cost-Based Selection (QCBS) method in most cases. In special cases specified in the Procurement Plan (PP) the following methods will be used: (i) Quality-Based Selection (QBS); (ii) Least Cost Selection (LCS),; (iii) Selection Based on the Consultants’ Qualifications (CQS), (iv) Single-Source Selection (SSS) and (v) Individual Consultants (IC) Selection in accordance with paragraphs 5.1 to 5.4 of the Bank’s Guidelines.  Selection will be processed through Request of Expressions of Interest (REIs) prior to the establishment of short-lists, and using the Bank’s Standard Requests for Proposal where required under Bank’s Guidelines.

- Consultant short lists, required for services estimated at less than US$200,000 equivalent per contract, may be composed entirely of national consultants, in accordance with the provisions of paragraph 2.7 of the Consultants Guidelines.

- Concerning Training, Workshops and Study Tours if any, at the beginning of each year, the CPS will submit its proposed plans in the form of an annual action plan for the coming year, to be reviewed by IDA. The plan would indicate the persons or groups to be trained, the type of training to be provided, indicative learning outcomes, the provider and the location of the training, its estimated cost, and as the case may be, the financial contribution from the beneficiary(ies). Selection of training institutions for workshops/training should be based on a competitive process, using the selection method based on consultants’ qualification.

- The Standard Request for proposal (RFP), as developed by the Bank, will be used for the selection of consultants.  The CPS (or any Contract Management Agency involved in the project execution) will ensure widely publicized Requests for Expressions of Interest (REI) for all contracts for consultants, except for single source when applicable.

- Operating costs financed by the project consists of additional expenditures incurred, such as office equipment and supplies, rental costs, maintenance of vehicles, fuel and spare parts, as well as travel expenses and per diem, since these expenses are required for project monitoring. They will be procured using the shopping procedure and grouping, as much as possible, resorting to customer contracts for procurement of routine services. These procedures will be specified in detail in the Project Implementation Manual (PIM), and procurements scheduled in the Procurement Plan (PP) submitted to the Bank for prior approval.

Assessment of Agencies’ Capacity to Implement Procurement

- Implementation of project activities in the field under component 1 will be led by APCAM through the CRA. The ON will be the executing agency for irrigation investments under component 2. The CPS will be responsible for overall implementation of component 3.

- The Ministry of Agriculture (MinAgri) will be the overall supervising and coordinating Government entity. However, The Ministry of Finance (Borrower representative) and the Ministry of Industries (in charge of private sector and agribusiness development) will also be responsible for overall project coordination.

- At the national level, project coordination will be located in the MinAgri, under the responsibility of the CPS (Cellule de Planification et de Statistiques - Statistics and Planning Unit). This unit is legally mandated to coordinate operational activities in the rural sector (covering agriculture, livestock and food security). The project will strengthen the CPS with the (international) recruitment of four high level technical assistants: one technical adviser (planificateur- gestionnaire de projets), one M&E specialist, and one financial management specialist and one Procurement Specialist. The CPS will accommodate its own (small) project coordination unit. The procurement of goods works and services will be lead by the Financial and Administrative Department of the Ministry of Agriculture (DAF). Procurement will follow Bank’s procedures and will be internalized within each implementing agency, whenever possible (Office du Niger. Resources will also be available to strengthen the capacities of fiduciary staff within the different implementing agencies.

- At the regional level, project investment programs will be prepared by CRAs, in close collaboration with regional public services and drawing upon overall technical and financial guidance set at the national level.

- All procurement activities associated with large scale irrigation will be handled by the ON.

- A procurement assessment of the various project implementing agencies was conducted in November 2009, during pre-appraisal, by the IDA procurement specialist based Bamako. The assessment focused on the organization, and the supporting beneficiary agencies responsible for technical implementation of project activities.

- Capacity of the DAF and CPS: The project coordination unit led by the CPS and including technical divisions of this directorate is not yet put in place. The Implementation Manual which is being elaborated will set roles and responsibilities within the team. The CPS holds no experience in procurement and relies on the DAF of the Ministry of Agriculture to conduct procurement procedures. The CPS will be in charge of the bidding documents preparation and will transmit them to the DAF in charge of the process. The DAF which includes a division responsible for procurement is headed by a Division Manager who is assisted by a team of nine staff. The Division Manager for Procurement has been training on the use of Bank’s rules and procedures in 2003. The Team needs to be train on the latest updates of the Bank’s guidelines.

- Capacity of APCAM and CRAs: The APCAM and the CRAs were created in August 1993 by Law No. 93/044.  These are State-owned Vocational Establishments having corporate body status and financial autonomy. They constitute for the authorities consultative groups on agricultural matters. CRAs have two permanent members nominated and accountants hired by donors based on the needs of the projects they are managing. They have no experience using Bank procurement procedures and do not have qualified staff to deal with procurement matters. Due to their statute of State-owned vocational institution and to limited personnel, APCAM and CRAs do not have the authority and necessary technical capacities to perform public procurement. The supporting experts to be recruited by the Project do not cover all the expertise that might be needed for the design, analysis, and validation of sub-projects, and for the preparation of the necessary technical documents for procurement activities. To offset these shortcomings, it would befit that protocols be entered into between APCAM and the CRAs and Government technical services at regional and national levels. Through those protocols, the association and its divisions could benefit from expertise of these institutions at all stages from preparation to approval of sub-project and particularly all along the procurement process.

- Capacity of the ON: The Office du Niger is a national society under a Secretariat which in turn under the Prime Minister Office. A new organization chart was recently approved putting the procurement directorate under the supervision of the administrative and financial Division. A new implementation manual is being elaborated and should be available in June. Procurement is conducted by 2 divisions, “procurements” and “procedures and methods”. The procurement division is headed by a civil engineer having some experience in procurement and whose last training on World Bank procurement methods goes back to 2007. The unit staff includes in addition to the Chief of Division, an accountant and a lawyer. The Office du Niger plans to fill four other positions to expand the procurement division. A commission including the technical experts and the permanent secretariat is responsible for the evaluation of bids and proposals for awards. The Administrative and financial division is responsible for archiving , The Director of the Office du Niger is by order given authorization to sign contracts amounting to up to US$ 1,110,000. Over this amount, contacts are submitted to the signature of the Prime Minister and to the approval of the National Assembly.

- The Small-scale irrigation component outside of the zone of the Office du Niger will carried out by the Regional Directorate of the Rural Engineering Department or DRGR. This component will unfold on demand for m the POs who will be owners of the infrastructures and entirely responsible for the process. The DRGR will be in charge of the planning and the monitoring of the utilization of the funds. At this stage, the producers organizations that are responsible for implementing this small-scale irrigation are not yet identified. However, overall these POs have weak qualities both technical and for procurement. Due to the fact that funding will be on demand, there is no clear indication of the areas that might be concerned. Nonetheless, in some project areas, capacities in technical work delegation (MOD) are nearly non-existent. The proposed scheme could lead to a multitude of technical work delegations for which it will be difficult to evaluate capacities for each such delegation convention. A more global vision consists in leaving the responsibility for procurement with the DRGR which, beyond the ordered threshold could lean on the DNGR and the DAF.

The overall project procurement risk is rated high.

Procurement Action Plan

- Corrective measures, as detailed in the table below, have been proposed to address weaknesses of the two entities as follows:

- APCAM/CRA: (i) To sign protocols with the Government technical divisions for support in the technical design and the validation of sub-projects, and in the procurement process (ii) Provide APCAM/CRA with experts who can participate in procurement processes for their benefit (iii) Training for staff in Bank procurement procedures (iv) Prepare a community procurement manual acceptable to the Bank; and (v) put in place an procurement filing system for APCAM/CRA.

| Weakness | Recommendations | Activity | Responsible | Time Frame |
| --- | --- | --- | --- | --- |
| Inadequate procurement staff | Provide the structure with competent experts to participate in procurement | Some experts | APCAM | Before disbursement |
| Weak Authority for procurement | Entrust APCAM/CRA with the authority and the competences necessary for procurement | Sign protocols with State decentralized and deconcentrated technical services | APCAM/CRA | On effectiveness |
| No implementation manual | Prepare a simplified community procurement manual acceptable to the Bank | Prepare and have approved the manual Train staff in utilization of procedures | APCAM | Before effectiveness |
| No procurement plan | Prepare a procurement plan for the first 18 months for each project component | Prepare a procurement plan in accordance with the format agreed with IDA. | CPS | Before negotiations |
| No filing and archiving system for procurement documents | Establishment of a filing and archiving system for procurement documents in APCAM and the CRAs | Assign and train a person responsible for filing. Provide premises for archiving, as well as the required equipment and filing furniture | APCAM | Not later than the early months of project implementation |
| Limited knowledge of APCAM/CRA members with the Bank’s procurement procedures | Training of APCAM/ CRA members in the Bank’s procurement procedures | Train the members of APCAM/CRA in the Bank’s procurement procedures | APCAM | Not later than the three first months of project implementation |

- Office du Niger: The following actions will be undertaken: (i) recruitment of qualified staff for procurement activities; (ii) training staff involved in procurement to strengthen the procurement capacity of the ON; (iii) establishment of a procurement scheduling and management system for the project team within the Office, with links to the CPS; (v) establishment of a permanent procurement board, and its maintenance throughout project implementation, (vi) preparation of a procurement procedures manual acceptable to the Bank; and (vii) strengthening of the archiving and filing system for procurement documents and its updating throughout project implementation.

| Weakness | Recommendations | Activity | Responsible | Time Frame |
| --- | --- | --- | --- | --- |
| Inadequate staff assigned to procurement activities | Doter l’ON de personnel qualifies en passation de marches | Recruit qualified experts for procurements | Office du Niger | Before disbursement |
| Lack of a procurement procedures manual | a procedures manual deemed satisfactory by IDA | Prepare and approve the manual Train staff in the use of the manual. | Office du Niger | Before disbursement |
| No procurement plan | Prepare a procurement plan for the first 18 months for each project component | Prepare a procurement plan in accordance with the format defined by IDA | CPS | Before negotiations |
| Weaknesses of the filing and archiving system for procurement documents | Improve the filing and archiving system of DP procurement documents | Assign and train a person responsible for filing to the procurement division. Allocate larger premises to archiving, and provide the required filing equipment and furniture | Office du Niger | Not later than the early months of project implementation |
| Limited familiarity of Procurement Department agents with the Bank’s procurement procedures | Training of procurement department staff in the Bank’s procurement procedures | Train of procurement department staff in the Bank’s procurement procedures | Office du Niger | Not later than the first three months of project implementation |

- Ex-post procurement reviews will be conducted during the project supervision missions. Independent audit will be conducted once per year.

- Procurement Methods and Bank Review: Under the proposed Fostering Agricultural Productivity Project, the procurement method and Bank Review requirements will be agreed in the procurement plan and published on the Bank’s external website.

- Procurement Plan: During appraisal, the Borrower will develop a Procurement Plan for project implementation, which specifies the procurement methods. The plan will be agreed between the Borrower and the World Bank. It will be available with the Project Coordination Team. It will also be available in the project database and on the Bank’s external Website. The Procurement Plan will be constantly kept up to date and updated at least every six months in consultation with the World Bank to reflect the actual needs of project implementation and improvement of institutional capacities.

- Frequency of Procurement Control:  A PPR/IPR will be conduct once a year and a supervision mission at least twice a year.

- Publication of Results and Debriefing: On-line DG Market, UN Development Business, and/or Client Connection publication of contract awards will be required for all ICB, NCB, Direct Contracting and the Selection of Consultants for contracts exceeding the prior review threshold.  In addition, where prequalification has taken place, the list of pre-qualified bidders will be published.  With regard to ICB and large-value consulting contracts, the Borrower will be required to ensure publication of contract awards as soon as IDA has issued its “no objection” to the recommended award.  With regards to Direct Contracting and NCB, publication of contract awards can be done in aggregate on a quarterly basis and in local news papers.  All consultants competing for contracts involving the submission of separate technical and financial proposals, regardless of estimated contract value, should be informed of the results of the technical evaluation (number of points that each firm received) before the opening of the financial proposals.  The Executing Agencies will be required to offer debriefings to unsuccessful bidders and consultants should the individual firms request such a debriefing.  All approved post review contracts shall also be published on a free access website.

### Details of Procurement Arrangements Involving International Competition

Goods, Works and Non-consulting Services

1.  Prior Review Threshold

|  | Procurement Method | Threshold for Procurement Method | Prior Review Threshold USD | Comments |
| --- | --- | --- | --- | --- |
| 1. | ICB and LIB (Goods) | ≥500,000 | All contracts |  |
| 2. | NCB (Goods) | ≤500,000 | Contracts agreed in the procurement plan |  |
| 3. | ICB (Works) | ≥5,000,0000 | All contracts |  |
| 4. | NCB (Works) | ≤5,000,000 | Contracts agreed in the procurement plan |  |
| 5. | ICB (Non-Consultant Services) | ≥1,000,000 | All contracts |  |
| 6 | Direct Contracting | All | All contracts |  |
| 7 | Shopping | ≤50,000 | Contracts agreed in the procurement plan |  |

Note: ICB   = International Competitive Bidding; NCB =  National Competitive Bidding

2.	Prequalification:

- 3.	Proposed Procedures for CDD Components (as per paragraph. 3.17 of the Guidelines: N/A

- Reference to (if any) Project Operational/Procurement Manual:

(i)	Project Implementation Manual.

(ii)	Procurement Manual.

(iii)    The procurement plan will also form part of the Project Implementation Manual.

- Any Other Special Procurement Arrangements: [including advance procurement and retroactive financing, if applicable]. N/A

Procurement Packages with Methods and Time Schedule

1.  Goods, Works, and Non Consulting Services

- List of contract packages to be procured following ICB and direct contracting. All contracts following ICB are submitted to prior review.

| Contract Packages | Method |
| --- | --- |
| Achat Véhicules Lot 1 : véhicules SW Lot 2 : véhicules Pick up Lot 3 : Véhicules legers | ICB |
| Acquisition Equipements et matériels de collecte de semences fraiches, de conservation | ICB |
| Aménagement de Travaux adduction/drainage principal sabalibougou : lot 1 : travaux de drainage 1200 ha Lot 2 : 1000 d’aménagement irrigué | ICB |
| Aménagement irrigué M’Béwani : travaux drainage principal et 500 ha | ICB |
| Travaux de drainage Lot 1 : Travaux de drainage à karankorola Lot : 2 drains de Tango 20 Km | ICB |
| Réhabilitation de Centre de Formation du Centre d’Apprentissage Agricole de Samanko, Centre de Formation Pratique de Tabacoro et Centre de Formation Professionnelle de l’Elevage de Sotuba | ICB |

- List of contracts for goods, works and non consulting services.

| 1 | 2 | 3 |  | 4 |  | 5 | 6 | 7 | 8 | 9 |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Ref. No | Contract (Description) | Montant Estimatif en US $ |  | Méthode de Passation |  | Pré Qualification | Préférence nationale (oui/non) | Revue à priori ou à postériori | Clôture et ouverture des plis | Commentaires |  |
| FOURNITURES |  |  |  |  |  |  |  |  |  |  |  |
| 1 | Acquisition Matériels informatiques Lot 1 : matériels informatiques lot 2 : copieurs, scanner et video projecteur, GPS Lot 3 : Unités audiovisuelles (TV, magnétoscope, DVD) appareils photos et mini cameras | 313 405 |  | AON |  | NA | NA | priori | 15/11/2010 |  |  |
| 2 | Acquisition Equipements de bureau (APCAM, CPS, DNACPN, STP et Coord. Rég. | 142 553 |  | AON |  | NA | NA | Priori | 30/10/2010 |  |  |
| 3 | Achat Véhicules Lot 1 : véhicules SW Lot 2 : véhicules Pick up Lot 3 : Véhicules legers | 3 602 128 |  | AOI |  | NA | NA | priori | 25/10/2010 |  |  |
| 4 | Achat motos | 165 958 |  | AON |  | NA | NA | Priori | 30/10/2010 |  |  |
| 5 | Fournitures bureau APCAM, OPA et CPS | 106 383 |  | AON |  | NA | NA | priori | 30/10/2010 |  |  |
| 6 | Acquisition Equipements et matériels de collecte de semences fraiches, de conservation | 531 915 |  | AOI |  | NA | NA | priori | 30/03/2011 |  |  |
| 6 | Impression journaux APCAM | 25531 |  | CF |  | NA | NA | posteriori | 15/01/2011 |  |  |
| 8 | Achat logiciel base de données micro projets filières | 42553 |  | CF |  | NA | NA | posteriori | 15/11/2010 |  |  |
| 9 | Reconfiguration d u Site web et des bases de données de l’APCAM | 21276 |  | CF |  | NA | NA | posteriori | 15/01/2011 |  |  |
| 10 | Acquisition équipements modernisation des systèmes d’auscultation des barrages de Markala et Sélingué | 172 872 |  | AON |  | NA | NA | posteriori | 20/09/2011 |  |  |
| TRAVAUX |  |  |  |  |  |  |  |  |  |  |  |
| 1 | Travaux d’aménagement PIV neuf équipés de GMP |  | 1 276 595 |  | AON | NA | NA | Priori | 15/07/2011 |  |  |
| 2 | Travaux d’aménagement des bas fonds |  | 1 445799 |  | AON | NA | NA | priori | 15/08/2011 |  |  |
| 3 | Travaux d’aménagement de petits périmètres irrigués |  | 200 212 |  | AON | NA | NA | posteriori | 25/11/2011 |  |  |
| 4 | Aménagement de Travaux adduction/drainage principal Sabalibougou : lot 1 : travaux de drainage 1200 ha Lot 2 : 1000 d’aménagement irrigué |  | 11 023 274 |  | AOI | NA | NA | priori | 15/04/2011 |  |  |
| 5 | Exécution du plan de réinstallation : Lot1 : (habitations, voutes et autres structures, assainissement drainage et voiries greniers hangars Lot 2 : centre de santé, école, magasin céréalier maison de jeunes, centre d’alphabétisation, parc de vaccination et forages équipés |  | 713 050 |  | AON | NA | NA | priori | 15/02/2011 |  |  |
| 6 | Aménagement irrigué M’Béwani : travaux drainage principal et 500 ha |  | 5 200 000 |  | AOI | NA | NA | priori | 30/07/2011 |  |  |
| 7 | Réfection locaux à la CPS |  | 25 532 |  | CF | NA | NA | posteriori | 15/10/2010 |  |  |
| 8 | Construction siège APCAM |  | 2 000 000 |  | AON | NA | NA | posteriori | 15/09/2011 |  |  |
| 9 | Construction siège CRA Kayes, Tombouctou et Kidal |  | 319 150 |  | AON | NA | NA | posteriori | 15/09/2011 |  |  |
| 10 | Réhabilitation CRA et OPA |  | 372 340,43 |  | AON | NA | NA | posteriori | 15/09/2011 |  |  |
| 11 | Construction siège IER |  | 4 000 000 |  | AON | NA | NA | priori | 20/10/2011 |  |  |
| 12 | Réhabilitation DLCA |  | 851 064 |  | AON | NA | NA | posteriori | 15/09/2011 |  |  |
| 13 | Travaux de drainage Lot 1 : Travaux de drainage à karankorola Lot : 2 drains de Tango 20 Km |  | 7 900 000 |  | AOI | NA | NA | priori | 15/07/2011 |  |  |
| 14 | Réhabilitation de Centre de Formation du Centre d’Apprentissage Agricole de Samanko, Centre de Formation Pratique de Tabacoro et Centre de Formation Professionnelle de l’Elevage de Sotuba |  | 5 000 000 |  | AOI | NA | NA | priori | 15/11/2010 |  |  |
| 15 | Réfection du système de drainage à Sélingué |  | 531 915 |  | AON | NA | NA | priori | 30/06/2011 |  |  |

Selection of Consultants

- Prior Review Threshold: Selection decisions subject to Prior Review by Bank as stated in Appendix 1 to the Guidelines Selection and Employment of Consultants:

|  | Selection Method | Threshold for Selection Method | Prior Review Threshold | Comments |
| --- | --- | --- | --- | --- |
| 1. | Competitive Methods (Firms) | ≥200,000 | All | QCBS/QBS |
| 2. | Single Source Selection | N/A | All | SSS |
| 3. | Competitive Methods (Firms) | <200,000 | Contracts agreed in the PPM |  |
| 4. | Individual Consultant | N/A | ≥100,000 | All |
|  | Contracts for specific assignments such as contracts for the elaboration/update of manual of the project implementation and the manual of procedures, contracts for monitoring and evaluation assignments; contracts for financial assistance assignments; contracts for financial audit; contracts for procurement audit, Contracts for technical audit; contracts for environmental and social issues; contracts for legal assignments | N/A | All |  |

Any Other Special Selection Arrangements: None.

- Consultancy Assignments with Selection Methods and Time Schedule

| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Ref. No | Contract (Description) | Montant Estimatif en US $ | Méthode de Passation | Pré Qualification | Préférence nationale (oui/non) | Revue à priori ou à postériori | Clôture et ouverture des plis | Commentaires |
| 1 | Etudes d’aménagement et surveillance des PIV | 159 575 | SBQC | NA | NA | Posteriori | 01/03/2011 |  |
| 2 | Etudes d’aménagement et surveillance des Bas fonds | 204 788 | SBQC | NA | NA | priori | 15/03/2011 |  |
| 3 | Etudes d’aménagements et surveillance des Petits périmètres maraîchers | 26 596 | SBQC | NA | NA | posteriori | 15/03/2011 |  |
| 4 | Actualisation DAO et contrôle travaux Sabalibougou | 273 957 | SBQC | NA | NA | priori | 15/09/2010 |  |
| 5 | Etudes schéma d’aménagement Élaboration APS 4900 ha, APD 2000 ha et contrôle 500ha à M’Béwani | 1 700 000 | SBQC | NA | NA | priori | 20/04/2011 |  |
| 6 | Etudes APD/DAP et contrôle travaux Kalankorola et Tango | 425 532 | SBQC | NA | NA | priori | 20/08/2010 |  |
| 7 | Etudes faisabilité pour le remembrement des aménagements irrigués à Niono | 531 914,894 | SBQC | NA | NA | priori | 22/05/2011 |  |
| 8 | Etudes d’identification des IMF partenaires (APCAM) | 6 383 | CI | NA | NA | posteriori | 30/09/2010 |  |
| 9 | Consultant pour la réalisation des modules test en gestion de l’eau à l4office du Niger | 1 610 851,06 | SBQC | NA | NA | priori | 30/05/2011 |  |
| 10 | Analyse géodésique du barrage de Markala et Sélingué | 212 766 | SBQC | NA | NA | priori | 30/06/2011 |  |
| 11 | Elaboration des plans d’urgence et de renforcement des capacités | 106 383 | SBQC | NA | NA | posteriori | 27/05/2011 |  |
| 12 | Etude situation financière des ressources prêtables des IMF partenaires | 6383 | CI | NA | NA | posteriori | 30/10/2010 |  |
| 13 | Etude tarification incitative à l’Office du Niger | 212 766 | SBQC | NA | NA | priori | 15/10/2010 |  |
| 14 | Audit organisationnel de la CPS | 25 532 | SBQC | NA | NA | priori | 5/10/2010 |  |
| 15 | Audit annuel | 21 277 | SMC | NA | NA | priori | 3/02/2011 |  |
| 16 | Etude situation de référence secteur agricole | 6 383 | CI | NA | NA | priori | 7/11/2010 |  |
| 17 | Elaboration des plans d’affaire | 17 021 | SBQC | NA | NA | posteriori | 31/03/2011 |  |
| 18 | Evaluation qualité portefeuille | 212 766 | SQBC | NA | NA | priori | 25/04/2011 |  |
| 19 | Cabinet de recrutement du personnel | 13 051 | SQBC | NA | NA | priori | 30/05/2010 |  |
| 20 | Mise en place d’un Observatoire des ménages ruraux | 630 000 | SQBC | NA | NA | priori | 31/11/2010 |  |
| 21 | Enquête agricole de conjoncture | 1 553 191 | SQBC | NA | NA | priori | 15/10/2010 |  |
| 22 | Etude d’évaluation de rendement de la production rizicole | 106 383 | SQBC | NA | NA | posteriori | 30/04/2011 |  |
| 23 | Étude de Revue des dépenses publiques | 21 277 | SQBC | NA | NA | Priori | 30/10/2010 |  |
| 24 | Etude cadre de dépenses à moyen terme du secteur rural | 6 743 | CI | NA | NA | priori | 30/09/2010 |  |
| 25 | Recrutement des spécialistes en passation de marchés | 61 276 | CI | NA | NA | Priori | 30/09/2010 |  |
| 26 | Formation en passation de marchés | 25 000 | Gré a gré | NA | NA | Priori | 30/09/2010 |  |

Annex 9: Economic and Financial Analysis

Mali:  Fostering Agricultural Productivity Project

- The agricultural production potential in Mali is large and significantly under-exploited. The project proposes to invest in a number of profitable, but yet under-developed, farming systems that would lead to better use of this potential. The profitability of the targeted systems is demonstrated below.

- Rice. Today Mali produces 919,000 tons (t) of rice; with the project, an additional 9,000 t will be produced the first year and this will increase to reach an additional 384,000 t in 2015 resulting in a production of 1,334,874 t of rice at the end of the project’s life. This additional production will easily be absorbed on the domestic and sub-regional market: demand for rice on the domestic market was estimated at 740,000 t in 2008 and could reach 1.5 million t by 2025. Demand for imported rice in the sub-region is estimated at around 2.1 million tons. The additional rice production inferred by the project has a value of more the 220 billion CFAF in import substitution over the period 2010-2015 with a modest price of 208 CFAF/kg. This will have a significant impact on Mali’s trade balance.

- Investment in large-scale irrigation will be profitable if producers harvest rice twice in the year with a 6.5 to 7 t/ha yield, a level that can be achieved in the Office du Niger (ON) zone where average yields of irrigated rice today are 5.1 t/ha with a potential of 9 t/ha. Lowland and rain-fed rice can reach a potential yield of 3 t/ha. Investment costs do not exceed 1.5 million per ha and the production system contributes to water conservation and to water table replenishment. With its additional production potential, it offers other opportunities to vegetable production, fish production, livestock management and job creation in rural areas. The 2005/06 MinAgri census estimates that 290,000 ha can be created for low-land rice production and more than 1.5 million ha are suitable for rain-fed rice.

- In the ON zone today, rice contributes to 88 percent of producers’ income and does not lift the 52 percent of small farms above the poverty line. Through additional production potential, the project will promote diversification of production in the counter season to increase producers’ incomes through introduction of improved varieties such as cowpea, shallot and fodder. The industrial potential for rice transformation is also under-exploited: it is estimated at 150,000 t but only 20,000 t – less than 10 percent of the ON zone production – are transformed today.

- In addition to the increased production of paddy, 80,000 tons of bran and 320,000 tons of hay will be produced that could feed over 30,000 cattle heads during 6 months, notwithstanding the use of the husk to produce chipboard as a substitute charcoal. In terms of employment, the additional rice production will generate at least 700 to 1000 jobs, from farming and harvesting to transformation.

- Cowpea.  Current production of cowpea is estimated at 297,663 t (113,180 t for beans and 183,483 t for fodder). Experience with PASAOP shows that good interventions can lead to significant yield increases for cowpea. In one year, the share of farmers that achieved yields of more than 700 kg/ha jumped from just below 19 percent to almost 58 percent (see table below).

| PASAOP results | 2007/2008 | 2008/2009 |
| --- | --- | --- |
| Number of partner producers* | 508 | 1466 |
| Partner producers with yields ≥ 700kg/ha | 94 | 848 |
| Share of farmers with yields ≥ 700 kg/ha | 18.5% | 57.8% |

*Producers who adopted one of the improved cowpea variety (sankaranka, korobalen, dunanfana, yèrèwolo) in the Kayes, Koulikoro, Sikasso, Ségou and Mopti regions.

- Producing cowpea is profitable for producers. In the two main regions where the project will promote cowpea production, Ségou and Koulikoro, producers have a positive net margin. It is higher in Koulikoro than in Ségou because yields are higher, which shows that planned investment in the project, which are designed to increase yields, will increase producers’ profits. The project’s focus on smallholders is also justified by the fact that they currently have lower margins than medium holders because of significantly lower yields as a result of lower use of inputs. The project will equip smallholders with the tools needed to increase their use of inputs.

Production costs and benefits for cowpea, Ségou and Koulikoro regions (2009)

|  | SEGOU |  | KOULIKORO |  |
| --- | --- | --- | --- | --- |
|  | Smallholder | Mediumholder | Smallholder | Mediumholder |
| Area (ha) | 2 | 3 | 3 | 5 |
| Costs/ha | 31,700 | 53,600 | 27,600 | 78,665 |
| Yield/ha | 0.249 | 0.412 | 0.356 | 0.565 |
| Producer price (CFAF/kg) | 280 | 280 | 207 | 207 |
| Income/ha | 69,720 | 115,360 | 73,783 | 116,955 |
| Net margin/ha | 38,020 | 61,760 | 46,183 | 38,290 |
| Total Costs | 63,400 | 160,800 | 82,800 | 393,325 |
| Total income | 139,440 | 346,080 | 221,349 | 584,775 |
| Net margin | 76,040 | 185,280 | 138,549 | 191,450 |

Note : sample of 40 farming systems in the Ségou region, survey taken in November 2009.

- Milk. Mali produces around 296,454,000 liters of milk every year; with the project, an additional 7,088 liters will be produced the first year and this will increase to reach an additional 25,776 liters in 2015 resulting in a production of 296,512,664 liters of milk in 2015. But the potential demand for milk is much larger, between 565 and 870 million liters for the national market and 37 million liters for the sub-regional market. In the project intervention areas, commercialized milk production is estimated at around 130,000 liters with an average commercialization rate of 16 percent. This figure is low given that the intervention zones group the main milk basins in Mali. However, only a relatively small part of the produced milk reaches urban markets and coverage of urban demand by national milk production is thought to be only 3 percent. Considering the main urban centers of the project’s intervention areas in the table below, the daily quantity of milk that reaches urban markets is around 15,000 liters against a total urban demand currently estimated at 423,000 liters per day.

Estimated milk production and commercialized production in the project’s areas

| Cities | Population | Urban demand |  | Coverage rate |  |
| --- | --- | --- | --- | --- | --- |
|  |  | (‘000 liters/day) |  | (‘000 liters/day) | (%) |
|  |  | actual | potential | Act. | Act. |
| Bamako | 1,809,106 | 193 | 297 | 6 | 3% |
| Mopti | 368,512 | 39 | 61 | 5 | 11% |
| Ségou | 691,358 | 74 | 114 | 2 | 2% |
| Sikasso | 725,494 | 78 | 119 | 2 | 2% |
| Niono | 365,443 | 39 | 60 | 1 | 3% |
|  | 3,959,913 | 423 | 651 | 15 | 3% |

Note: actual is 39 l/year/person; potential is 60 l/year/person

- To collect enough milk to cover the increasing domestic demand, at least 1,272 collecting units with a minimum capacity of 500 l/day are needed. With 42 employees each, this would induce the creation of at least 53,424 jobs. The transformation and distribution of the additional milk production would induce another 500 jobs.

- Poultry meat. A cost/benefit analysis of the production of the “Wassache” hen shows that a production unit composed of 2 roosters and 11 hens with the hire of one wage worker is profitable, generating an annual benefit of 2,231,895 CFAF (see table below).

|  |  | Quantity | Unit cost |  | Total cost | Amortization (number of years) | Cost with amortization (CFAF) |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | (CFAF) |  |  |  |  |
| Costs |  |  |  |  |  |  |  |
| Infrastructure |  |  |  |  |  |  | 10,000 |
|  | Poultry house | 1 | 100,000 | 100,000 |  | 10 | 10,000 |
| Equipment |  |  |  |  |  |  | 100,100 |
| reproduction |  |  |  |  |  |  |  |
|  | Poultry feed | 1 | 2,000 | 2,000 |  | 1 | 2,000 |
|  | Drinking trough | 1 | 2,500 | 2,500 |  | 1 | 2,500 |
|  | Petrol incubator | 1 | 6,000 | 6,000 |  | 10 | 600 |
| Chicks and hens |  |  |  |  |  |  |  |
|  | Poultry feed | 30 | 1,500 | 45,000 |  | 1 | 45,000 |
|  | Drinking trough | 20 | 2,500 | 50,000 |  | 1 | 50,000 |

|  |  | Quantity | Unit cost |  | Total cost | Amortization (number of years) | Cost with amortization (CFAF) |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | (CFAF) |  |  |  |  |
| Costs |  |  |  |  |  |  |  |
| Poultry feed |  |  |  |  |  |  | 614,705 |
|  | Reproduction (0.12 kg x 365 days) | 569.4 | 75 | 42,705 |  | 1 | 42,705 |
|  | Chicks and hens (4 kg) | 5,720 | 100 | 572,000 |  | 1 | 572,000 |
| Veterinary care |  |  |  |  |  |  | 144,300 |
|  | reproduction | 13 | 100 | 1,300 |  | 1 | 1,300 |
|  | Chicks and hens | 1,430 | 100 | 143,000 |  | 1 | 143,000 |
| Functioning |  |  |  |  |  |  | 114,000 |
|  | Petrol incubator | 228 | 500 | 114,000 |  | 1 | 114,000 |
| Labor force |  |  |  |  |  |  | 360,000 |
|  | Employee (months) | 12 | 30,000 | 360,000 |  | 1 | 360,000 |
| Total costs |  |  |  |  |  |  | 1,343,105 |
| Revenues |  |  |  |  |  |  |  |
|  | Sale of chicks and hens | 1,430 | 2,500 | 357,5000 |  |  | 3,575,000 |
| Total revenue |  |  |  |  |  |  | 3,575,000 |
| Net income |  |  |  |  |  |  | 2,231,895 |

- In addition to introducing a more productive breed, it is expected that the project will decrease the mortality rate from 28.5 per cent in 2009 to 15 per cent in 2015. The total number of hens will increase from 12 million to 14.3 million during the project’s life and the project will infer a weight gain for about 800,000 animals over the project’s life. This will increase the availability of meat by 10 per cent, which is equivalent to an additional per capita consumption of 0.7 to 1 kg. The commercialization of poultry meat could create a hundred jobs by the end of the project. In total, the project will infer net additional revenue from poultry meat of 6,834,675,174 CFAF (about US$13.7 million).

- Size of farms and geographical potential. The impact of technology adoption at the farming system level varies according to farm size. This is partly due to unequal means and different implementation of technical advisory services. Smallholders have lower yields, but use fewer inputs and are not as well equipped. Furthermore, the farming systems of the “small producer” type have limited areas of cultivable land (on average 5 ha distributed between the main speculations).

- In the Ségou region, farmers produce rice and vegetables, which requires a high level of input consumption (seeds, fertilizers and phyto-sanitory products) and thus production costs are high. For rice, they vary between 227,000 CFAF/ha for small producers and 370,000 CFAF/ha for medium producers. The cost differential for cowpea between small and medium producers is currently over 20,000 CFAF/ha and the yield differential is over 1 ton/ha. The project, by promoting a better implementation of the recommendations of the research will improve the current average yield level by over 75 per cent for small producers and by 30 per cent for medium producers.

Production costs and benefits in Ségou region by farm size and product

| SEGOU | Small holders (60%) |  |  |  | Medium holders (40%) |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | rice | wheat | shallot | cowpea | rice | wheat | shallot | cowpea |
| Area (ha) | 0.75 | 0.16 | 0.1 | 2 | 1 | 0.25 | 0.25 | 3 |
| Costs/ha (FCFA) | 227000 | 113 000 | 107 000 | 31 700 | 370 825 | 153 600 | 136 020 | 53 600 |
| Yield (t/ha) | 2.7 | 1.07 | 4.967 | 0.249 | 4.650 | 1.5 | 8 | 0.412 |
| Producer price (CFAF/kg) | 282 | 150 | 329 | 280 | 282 | 150 | 329 | 280 |
| Income/ha (FCFA) | 761400 | 160 500 | 1634143 | 69720 | 1311300 | 225 000 | 2632000 | 115360 |
| Net margin/ha (FCFA) | 534400 | 47 500 | 1527143 | 38020 | 940475 | 71 400 | 2495980 | 61760 |
| Total Costs (FCFA) | 170 250 | 18 080 | 10 700 | 63 400 | 370 825 | 38 400 | 34 005 | 160 800 |
| Total income (FCFA) | 571050 | 25 680 | 163414 | 139440 | 1311300 | 56 250 | 658000 | 346080 |
| Net margin (FCFA) | 400800 | 7 600 | 152714 | 76040 | 940475 | 17 850 | 623995 | 185280 |

- In the Mopti region, farmers mainly produce dry cereals (millet) and rear livestock. As far as livestock rearing is concerned, fodder production, mainly cowpea, is very dynamic. Yields of cowpea hay for 0.25 ha plots vary from 245 and 575 bales, equivalent to 622 kg/ha for smallholders and 743 kg/ha for medium holders. Milk production is currently estimated at between 90 l/month for smallholders and 660 l/month for medium holders. Typically, the smallholder has a herd of local breeds (2 to 3) of which the number of lactating cows varies significantly and yields are low (1.5 l/day in rainy season, 1 l/day in dry season). With artificial insemination and/or introduction of new breeds, the project could increase the production level to 3.5 l/day. The introduction of new or additional equipments/infrastructures (dugout canoes, conservation units, dairies, etc.) will facilitate commercialization during the rainy season. Meat production through fattening is profitable with net margins between 14,500 CFAF (smallholder) and 38,700 CFAF (medium holder).

Production costs and benefits in Mopti region by farm size and product

| MOPTI |  | Small holders (70%) |  |  |  |  |  |  |  | Medium holders (30%) |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Millet |  | Fodder |  | Milk |  | Meat |  | Millet | Fodder |  | Milk |  |  | Meat |  |
| Area (ha) | 2.7 |  | 0.27 |  | 2 cows |  | 5 heads |  | 7 |  |  | 0.64 |  | 11 cows | 11 heads |  |
| Costs/ha (FCFA) | 31 000 |  | 10500 |  | 18760 |  | 112500 |  | 56 000 |  |  | 12800 |  | 21310 | 346500 |  |
| Yield (t/ha or kg/herd) | 1.102 |  | 0.397 |  | 90 l/month |  | 317.5 |  | 1.054 |  |  | 0.632 |  | 660 l/month | 963 |  |
| Producer price (CFAF/kg) | 125 |  | 47 |  | 250 |  | 400 |  | 125 |  |  | 47 |  | 250 | 400 |  |
| Income/ha (FCFA) | 137750 |  | 18659 |  | 22500 |  | 127000 |  | 131750 |  |  | 29704 |  | 165000 | 385200 |  |
| Net margin/ha (FCFA) | 106750 |  | 8159 |  | 23740 |  | 14500 |  | 75750 |  |  | 16904 |  | 143690 | 38700 |  |
| Total Costs (FCFA) | 83700 |  | 2835 |  | 18 760 |  | 112500 |  | 392 000 |  |  | 8192 |  | 21310 | 346500 |  |
| Total income (FCFA) | 371925 |  | 5038 |  | 45000 |  | 127000 |  | 922250 |  |  | 19011 |  | 165 000 | 385200 |  |
| Net margin (FCFA) | 288225 |  | 2203 |  | 26240 |  | 14500 |  | 530250 |  |  | 10819 |  | 143 690 | 38700 |  |

- Farmers in the Sikasso region produce cotton and dry cereals (sorghum, millet and corn). These activities are profitable as shown in the table below, even though sorghum’s yields remain low, from 631 kg/ha for smallholders to 765 kg/ha for medium holders. Cotton is the speculation where production costs are the highest and with a payment system unfavorable to the producer. Declining prices have led to a decline in cultivated areas (from 105,517 ha in 2004/2005 to 26,604 ha in 2008/2009). Yields vary from 0.911 to 1.2 t/ha, but the potential is over 2 t/ha. Milk production leads to a diversification of activities with the production of fodder and the introduction of artificial insemination. But because the latter is expensive (45,000 CFAF/cow today against 12,500 CFAF/cow when it was subsidized), the activity shows little profitability.

Production costs and benefits in Sikasso region by farm size and product

| SIKASSO | Small holders (65%) |  |  |  |  |  |  | Medium holders (35%) |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Cotton | Sorghum |  |  | Corn | Milk |  | Cotton |  | Sorghum | Corn |  |  | Milk |
| Area (ha) | 3 |  | 5 | 2 |  |  | 5 cows |  | 4 | 7 |  | 4.8 | 10 cows |  |  |
| Costs/ha (FCFA) | 99 700 |  | 22 000 | 70 752 |  |  | - |  | 138 590 | 46 000 |  | 83 340 | - |  |  |
| Yield (t/ha or kg/herd) | 0.911 |  | 0.631 | 1.419 |  |  | 225 l/mth |  | 1.205 | 0.765 |  | 2.103 | 600 l/mth |  |  |
| Producer price (CFAF/kg) | 165 |  | 120 | 117 |  |  | 250 |  | 165 | 120 |  | 117 | 250 |  |  |
| Income/ha (FCFA) | 150 315 |  | 75 720 | 166 023 |  |  | - |  | 198825 | 91800 |  | 246051 | - |  |  |
| Net margin/ha (FCFA) | 50 615 |  | 53 720 | 95271 |  |  | - |  | 60235 | 45800 |  | 162711 | - |  |  |
| Total Costs (FCFA) | 299 100 |  | 110 000 | 141 504 |  |  | 35 060 |  | 554 360 | 322 000 |  | 400032 | 98 320 |  |  |
| Total income (FCFA) | 450 945 |  | 378 600 | 332046 |  |  | 56250 |  | 795300 | 642600 |  | 1181045 | 150 000 |  |  |
| Net margin (FCFA) | 151 845 |  | 268 600 | 190542 |  |  | 21190 |  | 240940 | 320600 |  | 781013 | 51680 |  |  |

- In the Koulikoro region, the project targets in priority the production of cowpea and fodder (mainly peanut and cowpea hay), milk and poultry meat. Even though cowpea yields are below the 1.5 t/ha potential, the speculation is profitable both for small and medium farmers as shown in the table below. Poultry farming is dominated by traditional practice, which explains the very low profitably of this activity today, but modern aviculture is developing, encouraged by the large and growing Bamako market nearby. The project’s interventions will lead to an increase of the animals’ weight and to a reduction of mortality rates (see paragraph above on poultry meat).

Production costs and benefits in Koulikoro region by farm size and product

| KOULIKORO | Small holders (70%) |  |  |  | Medium holders (30%) |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Cowpea | Fodder | Milk | Poultry | Cowpea | Fodder | Milk | Poultry |
| Area (ha) | 3 | 2 | 7 cows | 9 heads | 5 | 4 | 13 cows | 15 heads |
| Costs/ha (FCFA) | 27 600 | 15600 | - | - | 78 665 | 17500 | - | - |
| Yield (t/ha or kg/herd) | 0.356 | 0.622 | 315 l/mth | 8 | 0.565 | 0.554 | 780 l/mth | 13 |
| Producer price (CFAF/kg) | 207 | 47 | 250 | 2500/head | 207 | 47 | 250 | 2500/head |
| Income/ha (FCFA) | 73783 | 29234 | - | - | 116955 | 26038 | - | - |
| Net margin/ha (FCFA) | 46183 | 13634 | - | - | 38290 | 8538 | - | - |
| Total Costs (FCFA) | 82 800 | 31200 | 55 800 | 5400 | 393 325 | 70000 | 123 800 | 12 000 |
| Total income (FCFA) | 221349 | 58468 | 78750 | 20000 | 584775 | 104152 | 195 000 | 32 500 |
| Net margin (FCFA) | 138549 | 27268 | 22950 | 14600 | 191450 | 34152 | 71 200 | 20 500 |

- Economic and financial analysis: synthetic indicators. Based on the level of concrete field investments planned under components 1 and 2, the economic and financial analysis shows the efficiency of the investment planned by the operation until 2015. The internal economic rate of return (IRR) is estimated at 34 per cent, which is significantly higher than the capital opportunity cost of 12 per cent. This shows that the operation’s investment choices are satisfactory in regard to alternative choices. The net present value (NPV) of the economic analysis amounts to over 92 billion CFAF or about 184 million USD for the six years of the operation; this is three times the initial level of investment. The cost-benefit ratio is equal to 1.38, showing that benefits well surpass costs. These results show the profitability of the investments planned by the operation.

- With the adoption of technologies inferred by the operation’s implementation and the expected impact on yield levels and potential area increases, the internal financial rate of return for the targeted farming models is estimated at about 23 per cent, which is higher than the estimated 20 per cent capital opportunity cost on the financial market. The NPV is estimated at 43 billion CFAF or about 86 million USD and the cost/benefit ratio is equal to 1.25. These results show that the operation is financially profitable. Investing in research, in service provision to producers and in capacity building of producer organizations on sustainable water and land management leads to good results at the farming system level.

| Synthesis indicators | 2010-2015 (6 years) |  |  |
| --- | --- | --- | --- |
| Economic analysis |  |  |  |
| IRR | 34 % |  |  |
| NPV | 92.1 billion CFAF – US$184.2 million |  |  |
| Cost/Benefit Ratio | 1.38 |  |  |
| Financial analysis |  |  |  |
| IRR | 23 % |  |  |
| NPV | 43.1 billion CFAF – US$86.1 million |  |  |
| Cost/Benefit Ratio | 1.25 |  |  |
| Financial analysis by geographical areas and farming systems |  |  |  |
| Synthesis indicators | Region | Small producers | Medium producers |
| IRR NPV | Segou | 36 % 63,750 CFAF | 38 % 113,226 CFAF |
| IRR NPV | Mopti | 29 % 47,263 CFAF | 39 % 146,500 CFAF |
| IRR NPV | Sikasso | 35 % 109,842 CFAF | 61 % 211,752 CFAF |
| IRR NPV | Koulikoro | 27 % 59,151 CFAF | 64 % 213,044 CFAF |

- When analyzing the financial profitability of the operation for the farming systems by geographical zones, the IRR remains relatively high ranging from 27 to 64 percent (table A1). In the short term, small producers will benefit more from the investment, while for the medium producers positive effects will be felt in the long term. If the results vary according to the farming system and the geographical area, the indicators are generally satisfactory because superior to the 12 percent opportunity cost of capital. This means that the small and medium farmers who are targeted by the operation will benefit from it: despite additional costs for the producers, the investment in research, service provision to producers and strengthening of producers’ organizations will lead to higher yields for small producers through the adoption of improved technologies.

- The economic and financial analysis thus shows the robustness of the operation and the efficient use of public and private resources. But the project’s results can be affected by various hazards inherent to its implementation, such as yield level variations, technological adoption rates below expectations and unfavorable changes in product prices. The sensitivity analysis shows the results to be robust to these hazards, but the profitability of the project is sensitive to decreases in yield levels. If yields decrease by 12 percent from the project’s benchmark, the critical value of the IRR or NPV could be reached. It is to be noted, however, that the benchmark is already at a very low level, so the probability of this situation to occur is very low. But it clearly shows all the importance of investing in research and technology transfer targeting an increase in yield levels, especially for the small producers.

- The economic and financial analysis also shows indirect impacts on income and employment in rural areas as well as on nutritional contribution for the targeted population. Some 90,000 jobs could be created over 6 years through the investments’ indirect effects. The increased rice production should lead to an import-substitution value of 127 billion CFAF if the price maintains itself at 400 F/kg. In terms of nutrition, the project should lead to increased availability of meat by 10 per cent (equivalent to an additional meat consumption of 0.7 to 1 kg per inhabitant), milk and cereals for the Malian population.

- Finally, the additional public expenditure on agriculture and livestock generated by the project does not exceed 10 per cent of current expenditures. Thus the costs of implementing the project constitute a reasonable and sustainable burden for the country’s budget, especially since the national development framework’s main lever to boost economic growth is to increase the productivity of agriculture.

Estimation of induced employment creation by sector and product

| Product | Maximum additionnal production induced by the projet (t or head) | Sector | Maximum capacity of production | Annual production (l or kg or ha) | Number of units potentially created | Number of jobs potentially created | Assumptions |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Milk | 25.776 | Milk collection unit* | 500 l/jour | 60 000 | 2 148 | 85 920 | 40 jobs per unit |
|  |  | Transformation | 1000 l/jour | 720 000 | 7 | 143 | 2 % of production transformed and 20 jobs/Unit |
|  |  | Distribution |  | 780 000 | 78 | 390 | 78 units of 10,000 l annually (transformed and not transformed) |
| Fattening | 18,805 | Caviers |  |  | 19 | 75 | 19 operators with ,1000 kg of meat for 4 jobs |
|  |  | Bouchers |  |  | 19 | 38 | 19 butchers with 2 persons |
|  |  | Coxeurs/intermédiaires |  |  | 19 | 19 | 19 intermediaries and transporters |
| Poultry meat | 1,525,345 | Aviculteur moderne |  | 80 000 | 10 | 286 | 10 Aviculteurs pour 80 000 sujets soit 50 % de la production |
|  |  | Aviculteur semi-traditionnel |  | 10 000 | 38 | 191 | 38 semi-traditionnels pour 10 000 sujets et 25% de la production |
|  |  | Autres acteurs/distribution |  | 90 000 | 90 | 90 | 90 acteurs divers du circuit distribution, transport, etc. |
| Rice | 384,851 | Opération travail sol | 49 9141 ha | 10 000 ha | 50 | 150 | Un prestataire pour chaque 10 000 ha with 3 jobs |
|  |  | Récolte et battage | 384 851 | 10 000 t | 38 | 77 | Un prestataire pour chaque 10 000 t with 2 jobs |
|  |  | Industrial transformation | 150 000 t/an | 192 425 t | 1 | 50 | One industrial unit with 50 jobs |
|  |  | Decortiqueuse | 30 000 t/an | 192 425 t | 6 | 18 | 3 jobs/ unit |
|  |  | Commercialisation | 254 002 | 10 000 t | 25 | 50 | Commerçant with 10 000 t/an with 1 collecteur et 1 transporteur |
|  |  | Valeur substitution a importation | 254 002 CFAF |  |  |  | Valeur monétaire à 127 milliards FCFA ou 254 milles US dollars |
| Millet | 422,425 | Industrial transformation | 20 000 t/an | 42 243 | 2 | 63 | 2 industries de transformation pour 10% production & 30 jobs |
|  |  | Semi-industrial transformation | 5 000 t/an | 21 121 | 4 | 42 | 4 semi-industriels pour 5 % production with 10 jobs/unit |
|  |  | Commerce/transport | 5 000 t/an | 84 485 | 17 | 51 | 17 commerçants pour 20 % production et reste autoconsommé |
| Corn | 935,759 | Industrial transformation | 20 000 t/an | 93 576 | 5 | 140 | 2 industries de transformation pour 10% production & 30 jobs |
|  |  | Acteurs filière avicole | 3 000 t/an | 46 788 | 16 | 78 | 16 opérateurs filière avicole pour 5 % production with 5 jobs/unit |
|  |  | Commerce/transport | 5 000 t/an | 187 152 | 37 | 112 | 37 commerçants pour 20 % production et reste autoconsommé |
| Sorghum | 275,984 | Acteurs filière avicole | 3 000 t/an | 13 799 | 5 | 23 | 5 acteurs dans l'alimentation de la volaille with 5 jobs/unit |
|  |  | Commerce/transport | 5 000 t/an | 55 197 | 11 | 33 | 11 commerçants pour 20 % production et reste autoconsommé |
| Cowpea | 145,311 | Opérateurs dans la restauration et transformation | 1 000 t/an | 4 359 | 4 | 13 | 4 acteurs dans la restauration pour 3 % production with 3 jobs/unit |
|  |  | Commerce/transport | 5 000 t/an | 29 062 | 6 | 17 | 6 commerçants pour 20 % production et reste autoconsommé |
| Cotton | 162,911 | Additional labour CMDT | 10 t/an | 16 291 | 1 629 | 1 629 | emploi dans la collecte, transport et traitement |
| Wheat | 2,323 | Semi-industrial transformation | 2 000 t/an | 2 323 | 1 | 6 | 1 unit de transformation pour totalité production & 5 jobs |
|  |  | Commerce/transport | 500 t/an | 2 323 | 5 | 9 | 6 commerçants/transporteurs pour totalité production |
| Total number of jobs potentially created |  |  |  |  |  | 89 715 | And a value of 127 milliards FCFA in import substitution of rice |
| * Exemple de mini laiterie : Mini laiterie de Ouéléssébougou (Koulikoro) d'un capacité de 600 l/jour pour 120 jours/an (DRPIA Koulikoro, 2008) |  |  |  |  |  |  |  |

Annex 10: Safeguard Policy Issues

Mali:  Fostering Agricultural Productivity Project

- Project location and potential environmental impacts: The project will target specific production systems and will concentrate on the following production basins: (i) Office du Niger (ON) for irrigated rice and vegetable production, as well as Mopti, Sikasso/Kayes,Tombouctou and Gao along the Niger River for small scale irrigation; (ii) Douentza / Bankass / Koro and Bla / Macina / Tominian for the mixed cereals / leguminous / livestock production system; (iii) Kati / Dioïla, Kita / Bafoulabé and Sikasso / Koutiala / Bougouni for mixed cereals / cotton / livestock; (iv) Office du Niger (Sokolo/M’Béwani) and  Dilly / Nara / Diéma / Nara for fodder production; (v) suburban areas around Bamako/Koulikoro, Ségou, Mopti, Kayes and Sikasso for livestock production.

- The agro-ecological areas linked to these production basins are characterized by their eco-systemic fragility and constant degradation of natural resources. The agricultural potential may be hindered in the future by agricultural practices that contribute to soil depletion, loss of vegetative cover due to the expansion of area under cultivation, overgrazing, excessive wood cutting and bushfires.

- The ON is located in the Niger River’s inner delta which is a hydraulic system considered to be of national – and even sub-regional – importance, especially for its high agricultural potential and for its rich and sensitive ecosystem as well. Water resources supplied to ON from the Markala dam are considered extremely valuable for a semi-arid environment that faces potential aggravation of an erratic rainfall profile due to climate change.

- The project’s irrigation investments at ON form part of a broader investment strategy that could have a medium to long term impact on cumulative water off-takes from the Niger River. The long term social impact is also a sensitive issue as agricultural development may lead to intense migration within the area. Consequently, the project will also support the on-going policy dialogue on water management at ON and the proposed measures to reduce water consumption for irrigation. This will include different measures and incentives to facilitate the adoption of water saving techniques, as well as a more transparent planning of public and private investments in the coming years. The objective is also to ensure that Mali will respect its international obligations with its neighboring countries within the framework of the Niger River Basin Pact.

- Project design has always sought to include measures and actions to prevent, anticipate and mitigate any potential social and environmental adverse impacts. For example, these include: (i) drainage investment on the M’Béwani site at ON with the construction of 55km of drains to complement the one being financed by the EU; (ii) deepening the multi-donor policy dialogue with the Government on water resources from the Niger river; (iii) dissemination of water saving techniques, with a particular focus on the SRI method; (iv) placing a strong emphasis on disseminating technologies and techniques, with a value added, in SLWM as part of GEF’s contribution under the TerrAfrica partnership; and (v) piloting a voluntary land consolidation process to help smallholders increase the size of their farms and thus to better ensure their financial viability.

- Environment Category: The project has been classified as an environmental Category A because of important investments in large scale irrigation. These irrigation investments may have adverse but limited environmental impacts mainly on water resources and may require the resettlement of local villages. Two irrigation perimeters will be constructed: (i) the first investment, at Sabalibougou, is a ready-to-go investment for which an environment assessment (EA) was undertaken in 2006; the EA has been updated and reviewed at the Bank’s request and the draft report has been disclosed on January 8, 2010 in Bamako and on January 13, 2010 at the InfoShop; and (ii) the second irrigation investment, at M’Béwani, will be prepared as part of project implementation and will be subject to another specific ESIA as a condition for financing by the Bank and other co-financiers.

- Safeguard Policies triggered:

| Safeguard Policies Triggered by the Project | Yes | No |
| --- | --- | --- |
| Environmental Assessment (OP/BP 4.01) | [X] | [ ] |
| Natural Habitats (OP/BP 4.04) | [X] | [ ] |
| Pest Management (OP 4.09) | [X] | [ ] |
| Physical Cultural Resources (OP/BP 4.11) | [X] | [ ] |
| Involuntary Resettlement (OP/BP 4.12) | [X] | [ ] |
| Indigenous Peoples (OP/BP 4.10) | [ ] | [X] |
| Forests (OP/BP 4.36) | [ ] | [X] |
| Safety of Dams (OP/BP 4.37) | [X] | [ ] |
| Projects in Disputed Areas (OP/BP 7.60) | [ ] | [X] |
| Projects on International Waterways (OP/BP 7.50) | [X] | [ ] |

- An Environment and Social Management Framework: in addition to the EA for the Sabalibougou irrigationworks, an ESMF has been prepared to address the potential environmental and social adverse impacts of the project. These include water-borne diseases, especially malaria, as health threats in the area may be exacerbated by irrigation extension. Irrigation may have also a negative impact on the water quality associated with the use of fertilizers and pesticides, as well as on the water-table level and contamination due to a poor drainage. The proliferation of aquatic invasive plants is also a threat with irrigation investments and will require close monitoring, prevention and treatment. The ESMF provides guidance and measures, with the associated implementation arrangements and budget plan, for preventing and mitigating all potential impacts. The ESMF was disclosed on January 8, 2010 in Bamako and on January 13, 2010 at the InfoShop.

- Natural Habitats: Although the project’s intervention area has not been described as a critical natural habitat, in terms of the characteristics of its biodiversity, whenever a wilderness is inundated there is loss of biodiversity no matter how small.  Irrigation causes the reduction of downstream water flow which affects flood plain use, end flood plain ecology, and fisheries.  The EA for the Sabalibougou irrigation scheme indicates minor impact on natural habitats.  To minimize the potential risks to natural habitats for the remaining irrigation perimeters (i.e., M’Béwani and small scale irrigation zones, etc.), preservation of such habitats will be a central focus in feasibility studies and EAs/EMPs to be undertaken as part of complex PO investment projects.

- Pest management: Although procurement of pesticides is not envisaged under the project, it is anticipated that the intensification of production systems will lead to an increased use of pesticides, as well as that of inorganic fertilizers. A Pest Management Plan (PMP) has been prepared. It includes mitigation measures, institutional arrangements for implementing those measures and associated budget that will be included in the project’s technical and financing plan. This PMP was disclosed on January 8, 2010 in Bamako and on January 13, 2010 at the InfoShop.

- Physical Cultural Resources: The project’s intervention area may be viewed as rich in physical cultural resources. Some of these areas are characterized as having sacred sites, natural features of cultural significance and unique human settlements.  The establishment of some of these physical cultural resources dates back to the Paleolithic Age. A light archeological study covering the two irrigation sites, Sabalibougou and M’Béwani, is being conducted by “Institut des Sciences Humaines” (Human Science Institute), the best institution in the country working in this field.  The objective of the study is to determine the project’s potential impact on these resources and propose mitigation measures for the preservation of such resources.  The results of the study will be taken into account in the design, implementation and monitoring of every irrigation scheme under the project. The draft report of this study will be available by end of April 2010.

- Involuntary resettlement: As small and large-scale irrigation investments may lead to the displacement of villages, a Resettlement Policy Framework (RPF) has been prepared and disclosed on January 18, 2010 in Bamako and on January 19, 2010 at the InfoShop. The EA for Sabalibougou and the field visit confirmed that some semi-nomadic hamlets from nearby villages have settled for some years on the proposed irrigation site under the project. The hamlets of Aly Gardia (8 families), Wéré Halodji (17 families), Anka Wéré (3 families) and the Fulani village (10 families) will be required to move from the future irrigation perimeter to another site. These people will be resettled on sites identified by the ON for this purpose.  In order to protect the rights of vulnerable groups and farmers / breeders who might lose land or income or lose access to other natural resources, a Resettlement Action Plan (RAP) has been prepared and disclosed on January 25, 2010 in Bamako and on January 26, 2010 at the Infoshop. The RAP has been prepared in compliance with the World Bank’s Policy on Involuntary Resettlement (OP 4.12) and its implementation has been budgeted as part of the project financing. In the event that other villages will need to be resettled due to the M’Béwani irrigation site, the RPF will apply and a specific RAP will be prepared.

- Social impact: The project has considerably more positive social and environmental impacts than negative.  Negative social impacts are associated with the displacement of population. Social conflicts over resources among local communities and migrating populations from Sabalibougou to the resettlement sites could occur. These conflicts could be caused by access to land or water and possible cumulative effects of redistribution, and unequal access to land or water rights. The RAP proposes some measures to mitigate loss.

- The RPF identified potential adverse impacts associated with project implementation and provides mitigation measures that include: eligibility criteria; asset valuation methods for compensation and resettlement of affected people; and grievance mechanisms for affected persons, in case of unsatisfactory arrangements. As project investments in small-scale irrigation infrastructure will use a demand driven approach, requests will be screened to determine the need for a RAP. The RPF describes the internal organization, management and reporting mechanisms to put in place within ON and DNACPN within the MEA. At the central level, DNACPN and its regional divisions will be responsible for monitoring adverse impacts, application of mitigation measures and compensation. Estimated provisions for the implementation of the RPF and supervision by DNACPN have been budgeted. The project will also support capacity building of various agencies to help implement safeguard policies.  Recommendations from both ASPEN and the stakeholders' validation workshop have been reflected in all final safeguard documents prior to disclosure.

- Project on International Waterways: Large-scale irrigation investments will rely on water from the Niger River. As per OP/BP 7.50, the Recipient has notified the riparian countries, through the Niger River Basin Authority in Niamey, of the type and size of irrigation investments planned under the project. The letter was sent on October 9, 2009 by the SEDIZON. Additional information will be sent on request by neighboring countries. A second notification was sent by the MinAgri on January 11, 2010 to provide specifications regarding small scale irrigation investments proposed along the Niger River.

- Safety of dams: The Safety of dams policy is triggered although the project will not finance any dam construction. This is due to the fact that the success and sustainability of the project’s irrigation investments will depend on reliable water supply and therefore on proper management of the Markala weir and Sélingué dam. A dam safety expert study has been undertaken. It showed that these infrastructures are in excellent condition and do not require any major repairs or civil works. However, some auscultation instruments need to be replaced or upgraded, O&M manuals need to be updated and emergency preparedness plans need to be prepared and disseminated. These activities have been included in the project budget.

- Safeguards Monitoring Mechanisms: Successful implementation of the project’s safeguard requirements and performance measurement requires regular monitoring and evaluation of activities to comply with national and Bank safeguard policies.  This will also help ensure that implementation of project safeguard measures are systematically carried out all throughout the life of the project. The EMSF, PMP, RPF, RAP, as well as the EA for the Sabalibougou irrigation scheme, outline the potential risks of adverse impacts associated with the different agricultural activities that the project will support., Although the Borrower has had a long experience implementing Bank safeguard policies, institutional capacities remain weak in the areas of implementation and supervision partly due to inappropriate monitoring plans and the lack of a meaningful budget allocation. All safeguards documents provide detailed arrangements and modalities to ensure an in-depth screening of the micro-investment projects that will be submitted by producer organizations.

- Implementation arrangements and capacity building: The various safeguards frameworks and plans provide details for capacity strengthening activities to be undertaken and institutional arrangements to be set up, as well as the associated budget requirements. The project has incorporated these elements in its design and costing. The DNACPN will be responsible for sound monitoring of safeguards and providing close supervision of mitigation measures implementation. The project will provide technical assistance (local consultants or NGOs, international expertise, etc.) to assist project stakeholders in implementing and monitoring the proposed safeguards measures, as needed. The ON will establish an environmental unit staffed with an environment specialist hired by PNIR. The unit will be strengthened by a sociologist to handle issues related to resettlement and will help ON internally develop this expertise beyond the specific requirements of the Bank-funded project.

- As the project will promote overall sector coordination and monitoring, capacity strengthening in the field of safeguards supervision and mitigation measures monitoring will benefit other key institutions, especially APCAM and CRAs, and public service agencies such as STP/CIGQE and DNCN.

- Consultations: All safeguard policy instruments (i.e., ESMF, PMP and RPF, and EA for Sabalibougou) were prepared following an in-depth and broad consultation approach, in line with national and World Bank safeguard policies. The preparation of the instruments involved relevant stakeholder groups in the public and private sectors and civil society.  These included POs, key Ministries and Government agencies, in particular STP/CIGQE, DNACPN, Nature Conservation National Division within MEA, as well as other Ministries responsible for Land Tenure, Local Governments and Decentralization, and Health and Social Development.

- Public consultations, attended by a large number of producers, took place in Sikasso (September 30, 2009), in Ségou (October 1, 2009), and in Koulikoro (October 3, 2009). A specific consultation was organized on the M’Béwani site at ON in connection with the planned large scale irrigation investment. As part of the RPF and RAP elaboration, several public consultations were held on the Sabalibougou irrigation site at ON. In addition, a public consultation was organized at Zanfina and Komola to assess the results of implementing the resettlement action plan as part of the former Bank-funded National Rural Infrastructure Project.

- The updated EA for the Sabalibougou irrigation investment and the RFP were subject to a public consultation meeting held in Diambey (Ségou Region) in October 2009, followed by a validation workshop in Sélingué to discuss the four safeguards studies prepared in October 2009. To update stakeholders about the project design and listen to their views, an additional consultation meeting at Diabaly took place on October 3, 2009.

- The main objective behind this approach was to foster ownership on the part of project stakeholders and to devise appropriate institutional arrangements for effective implementation and monitoring of the mitigation plan.  Future ESIAs, ESMPs and RAPs for PO investment projects, derived from the screening procedures outlined in the ESMF and RPF will be conducted following the same participatory framework, consistent with the approach adopted at the project’s inception. This approach will be carried on throughout project implementation, supervision, maintenance and evaluation.  Relevant provisions from the various sets of safeguard documents will be reflected in the PIM.

- None of these consultations have raised any particular concerns or objections. On the contrary, local population confirmed their interest in the proposed investments. Producers and local Government representatives have requested to be fully involved in the design and implementation of land allocation process.

Annex 11: Project Preparation and Supervision

Mali:  Fostering Agricultural Productivity Project

- Key milestones

|  | Planned | Actual |
| --- | --- | --- |
| PCN review | 11/06/2008 | 11/6/2008 |
| Initial PID to PIC |  | 12/23/2010 |
| Initial ISDS to PIC |  | 12/23/2010 |
| Appraisal | 02/15/2010 | 03/08/2010 |
| Negotiations | 03/29/2010 | 04/26/2010 |
| Board approval | 05/27/2010 | 05/27/2010 |
| Planned date of effectiveness | 09/15/2010 |  |
| Planned date of mid-term review | 09/15/2011 |  |
| Planned closing date | 05/26/2010 |  |

- Key institutions responsible for preparation of the project:

The overall project preparation process is under the leadership and coordination of the Ministry of Agriculture, represented by the Planning and Statistics Unit. The Ministry of Livestock and Fisheries, the Food Security Commissariat and the Permanent Assembly of Agricultural Chambers

- Bank staff and consultants who worked on the project included:

| Name | Title | Unit |
| --- | --- | --- |
| Olivier Durand | Sr. Agricultural Specialist (TTL) | AFTAR |
| Agadiou Dama | Sr. Agricultural Specialist | AFTAR |
| Yéyandé Sangho | Sr. Operations Officer | AFTAR |
| François Onimus | Sr. Irrigation Specialist | AFTWR |
| Stéphane Forman | Livestock Specialist | AFTAR |
| Christian Berger | Sr. Agricultural Specialist | AFTAR |
| Pauline McPHERSON | Operations Officer | AFTAR |
| Ziva Razafintsalama | Sr. Rural Development Specialist | AFTAR |
| Moussa Sidibé | Program Assistant | AFMML |
| Marie-Claudine Fundi | Program Assistant | AFTAR |
| Taoufiq Bennouna | Sr. Natural Resource Management Specialist | AFTEN |
| Amadou Konaré | Sr. Environmental Specialist | AFTEN |
| Erika STYGER | Environment Consultant | AFTEN |
| Salamata Bal | Sr. Social Development Specialist | AFTCS |
| Claire Harasty | Poverty Economist | PREM |
| Djibrilla Issa | Sr. Financial Specialist | AFTFP |
| Daria Goldstein | Sr. Counsel | LEGAF |
| Rokhayatou Samb | Sr. Procurement Specialist | AFTPC |
| Maïmouna Fam | Sr. Financial Mgt Specialist | AFTFM |
| Wolfgang Chadab | Sr. Finance Officer | CTRFC |
| Léoplod Sarr | Portfolio Manager | IFAD |
| Bakary Sékou Coulibaly | Sr. Agricultural Specialist | IFAD |
| Oury Diallo | Rural Institutions Specialist | FAO/CP |
| Vincent Gleasener | Economist | FAO/CP |
| Lazarre Hoton | Economist | FAO/CP |
| Ibrahim Djido | Irrigation Specialist | FAO/CP |
| Michael Marx | Rural Finance Specialist | FAO/CP |
| Annina Lubbock | Sr. Tehnical Adviser (Peer Reviewer) | IFAD |
| IJsbrand de Jong | Sr Water Resources Specialist (Peer Rev.) | ECSS1 |
| Richard Chisholm | Sr. Agriculturist (Peer Reviewer) | EASER |
| Christophe Crépin | Lead environment Specialist (Peer Rev.) | EASER |
| Franke Toornstra | Adviser (Peer Reviewer) | AFTRL |
| Abdoulaye Touré | Sr. Rural Dev Specialist (Peer Reviewer) | AFTAR |

Bank funds expended to date on project preparation:

- Bank resources:

- Trust funds:

- Total:

Estimated Approval and Supervision costs:

- Remaining costs to approval: US$10,000

- Estimated annual supervision cost: US$150,000

Annex 12: Documents in the Project File

Mali:  Fostering Agricultural Productivity Project

- Government of Mali’s strategy documents:

  - Cadre Stratégique pour la Croissance et la Réduction de la Pauvreté 2007-2011  – Growth and Poverty Reduction Strategy Framework (December 2006)

  - Loi 06-045 du 5 septembre 2006 portant Loi d’Orientation Agricole (Journal Officiel de la République du Mali – Septembre 2006)

  - Schéma directeur d’aménagement de la zone Office du Niger (MinAgri – December 2008)

  - Contrat plan État / Office du Niger / Organisations professionnelles 2008-20112

  - Politique Nationale de Développement de l’Élevage au Mali – National Livestock Development Policy (MEP/CPS – December 2004) - Volume I : Diagnostic et analyse critique de la situation actuelle du sous-secteur Elevage au Mali - Volume II : Enjeux et stratégies –Volume III : Cadre d’orientation politique

  - Programme Quinquennal d’Aménagements Pastoraux 2008-2012 - Pastoral Areas Development Program (MEP/SG -  June 2007)

  - Priorités et plan d’action de la Direction Nationale des Services Vétérinaires – Priorities and action plan for Vet Services (MEP/DNSV  - November 2008)

  - Stratégie de valorisation du lait cru local au Mali (MEP/SG - October 2008)

  - Projet de développement de l’élevage par la conservation, la sélection et la multiplication du  Zébu Maure dans le cercle de Nara (MinAgri/CPS - August 2008)

- Bank documents and analyses:

  - Country Economic Memorandum (World Bank - June 2006)

  - Country Assistance Strategy 2007-2011 (World Bank – November 2007)

  - Implementation Completion and Results Report for the Mali National Rural Infrastructure project (World bank – June 2008)

  - Mali Rural Finance Study (World Bank - Finance and Private Sector Department – June 2008)

  - Mali Population and Development Study (World Bank – Human Development Department / AFTH2 – June 2009)

  - Développement de l’Élevage et Réduction de la Pauvreté au Mali – Alive Guide Élevage-Pauvreté (MEP/SG / Équipe Nationale Alive – June 2009)

  - Dimensions structurelles de la libéralisation pour l’agriculture et le développement rural (Programme RuralStruc – IER/MSU/CIRAD – December 2008)

- Preparatory Studies

  - Revue des opportunités d’investissement à l’Office du Niger en matière de réhabilitation et d’extension des aménagements irrigués (Eric VERLINDEN – March 2009)

  - Analyse économique et financière du Projet d’Accroissement de la Productivité  Agricole au Mali (Amadou Abdoulaye FALL – January 2010)

  - Étude d’impact environnemental et social du périmètre de Sabalibougou / Office du Niger (BETEC – October 2009)

  - Cadre de Gestion Environnementale et Sociale et Plan de gestion des Pestes et Pesticides (Mbaye Mbengue FAYE – November 2009)

  - Cadre de Politique de Réinstallation (Abdoulaye SÈNE – December 2009)

  - Plan d’Action de Réinstallation pour l’Aménagement du Périmètre de Sabalibougou (Abdoulaye SÈNE – January 2010)

  - Rapport de pré-évaluation FIDA pour la petite irrigation (Ibrahim DJIDO – FAO – December 2009)

  - Rapport de pré-évaluation FIDA sur la facilitation de l’accès au crédit (Lazarre Hotton -  FAO – December 2009)

  - Filière lait - Accès aux marchés et écoulement des produits (FAO, September 2009)

  - Système de Suivi-évaluation sur la Gestion Durable des Terres au Mali (Omar Lyasse - April 2010).

  - Revue des dépenses publiques et analyse coûts / bénéfices de la gestion durable des terres et des eaux au Mali (ICRISAT/IFPRI, Octobre 2009)

- Others:

  - Performances et contraintes de l’élevage au Mali – OCDE, 19 septembre 2007

  - Outils pour l’Évaluation des Performances des Services Vétérinaires (OIE-PVS) : Mali – OIE, décembre 2007

  - Analyse des écarts PVS : Préparation d’un plan stratégique de renforcement de la conformité des Services Vétérinaires aux normes de qualité de l’OIE – OIE, mai 2009

Annex 13: Statement of Loans and Credits

Mali:  Fostering Agricultural Productivity Project

|  |  |  | Original Amount in US$ Millions |  |  |  |  |  | Difference between expected and actual disbursements |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Project ID | FY | Purpose | IBRD | IDA | SF | GEF | Cancel. | Undisb. | Orig. | Frm. Rev’d |
| P093991 | 2007 | ML-Educ Sect Invest Prog II (FY07) | 0.00 | 50.00 | 0.00 | 0.00 | 0.00 | 37.71 | 16.37 | 9.50 |
| P090075 | 2007 | ML-Transp Sec SIL 2 (FY07) | 0.00 | 90.00 | 0.00 | 0.00 | 0.00 | 70.02 | 10.75 | 0.00 |
| P081704 | 2006 | ML:Agr Compet & Diversif (FY06) - (PCDA) | 0.00 | 46.40 | 0.00 | 0.00 | 0.00 | 31.47 | 14.32 | 0.00 |
| P040653 | 2006 | ML-Rural Com. Dev. (PACR) | 0.00 | 60.00 | 0.00 | 0.00 | 0.00 | 39.95 | 20.96 | 0.00 |
| P080935 | 2005 | ML-Growth Support SIL (FY05) | 0.00 | 55.00 | 0.00 | 0.00 | 0.00 | 40.17 | 12.87 | 0.00 |
| P073036 | 2004 | ML-Household Energy & Univ Access (FY04) | 0.00 | 70.65 | 0.00 | 0.00 | 0.00 | 33.63 | -3.17 | 0.00 |
| P082957 | 2004 | ML-HIV/AIDS MAP (FY04) | 0.00 | 25.50 | 0.00 | 0.00 | 0.00 | 0.32 | -2.27 | 0.00 |
| P082187 | 2004 | ML-Dev Learning Ct LIL (FY04) - (PCFD) | 0.00 | 2.50 | 0.00 | 0.00 | 0.00 | 1.44 | 1.41 | 0.00 |
| P079351 | 2004 | ML-Transp Corridors Improv (FY04)-(PACT) | 0.00 | 48.70 | 0.00 | 0.00 | 0.00 | 1.89 | 0.76 | 0.00 |
| P035630 | 2002 | ML-Agr & Producer Org (FY02) - (PASAOP) | 0.00 | 63.50 | 0.00 | 0.00 | 0.00 | 6.17 | -20.61 | -20.61 |
|  |  | Total: | 0.00 | 512.25 | 0.00 | 0.00 | 0.00 | 262.77 | 51.39 | - 11.11 |

Mali

STATEMENT OF IFC’s

Held and Disbursed Portfolio

In Millions of US Dollars

|  |  | Committed |  |  |  | Disbursed |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | IFC |  |  |  | IFC |  |  |  |
| FY Approval | Company | Loan | Equity | Quasi | Partic. | Loan | Equity | Quasi | Partic. |
| 2003 | Hotel Bamako | 1.46 | 0.00 | 0.00 | 0.00 | 1.46 | 0.00 | 0.00 | 0.00 |
|  | PAL-Graphique Id | 0.22 | 0.00 | 0.00 | 0.00 | 0.22 | 0.00 | 0.00 | 0.00 |
| 1998 | SEF SIECO | 0.30 | 0.00 | 0.00 | 0.00 | 0.30 | 0.00 | 0.00 | 0.00 |
| 1995 | SEMOS | 0.00 | 4.80 | 0.00 | 0.00 | 0.00 | 4.80 | 0.00 | 0.00 |
|  | Total portfolio: | 1.98 | 4.80 | 0.00 | 0.00 | 1.98 | 4.80 | 0.00 | 0.00 |

|  |  | Approvals Pending Commitment |  |  |  |
| --- | --- | --- | --- | --- | --- |
| FY Approval | Company | Loan | Equity | Quasi | Partic. |
|  | Total pending commitment: | 0.00 | 0.00 | 0.00 | 0.00 |

Annex 14: Country at a Glance

Mali:  Fostering Agricultural Productivity Project

Annex 15: Incremental Cost Analysis

Mali:  Fostering Agricultural Productivity Project

- Background Context

- The development objective of this fully blended IDA/GEF operation “Fostering Agricultural Productivity Project” in Mali is to increase the productivity of smallholder producers involved in productions systems and within the geographic areas targeted by project interventions. The global environment objective is to increase the application of sustainable land and water management (SLWM) techniques in the targeted production systems. This objective will be achieved by a two-fold approach:

- Contribute to establishing an institutional framework conducive to the efficient delivery of SLM services to producers and to leverage the scope and impact of existing and future interventions in that field;

- Develop field interventions that contribute to mainstream and scale-up the sustainable management approach within the agriculture sector of Mali.

- To achieve the proposed objectives, the project will address major bottlenecks for agriculture modernization (i.e. lack of productive infrastructures, low agricultural productivity and deficiencies in sector coordination); it will therefore: (i) enhance farm modernization and the competitiveness of food value chains, through technology transfer and service provision to agricultural producers (component 1); (ii) invest in agricultural productive infrastructures (component 1); and (iii) support the policy and institutional environment towards implementation of a comprehensive programmatic approach and sector monitoring (component 3).

- Fit with GEF Strategic Priorities and SIP

- Eligibility for GEF co-financing: Mali is a member of many International Conventions. It ratified the Convention on Biological Diversity on March 29, 1995, and the UNCCD on October 31, 1995.

- Relevance to GEF Strategic Priorities: Land Degradation - This operation is part of the GEF Strategic Investment Program for SLM in Sub-Saharan Africa (SIP), which facilitates harmonization and improved targeting of SLM activities not only with the GEF but with the broader donor community. This project will contribute to SIP’s program goal of improving natural resource-based livelihoods in Sub-Saharan Africa by reducing land degradation. It will contribute to all of the four SIP intermediate results: IR1: SLM applications on the ground are scaled up in the country-defined priority agro-ecological zones; IR2: effective and inclusive dialogue and advocacy on SLM strategic priorities, enabling conditions, and delivery mechanisms established and ongoing; IR3: Commercial and advisory services for SLM are strengthened and readily available to land users; and IR4: Targeted knowledge generated and disseminated, monitoring and evaluation systems established and strengthened at all levels.

- The project is consistent with the GEF land degradation strategy. It will directly contribute to the implementation of its Strategic Program 1: Agriculture (SP1) and to its Strategic Objective 1: Creating an enabling environment for SLM, and Strategic Objective 2: Generating benefits for the global environment through the up scaling of SLM investments. In accordance with the GEF strategy, the focus on land management to secure ecosystem services for farmers and pastoralists will be (i) to provide and create an enabling environment for SLM (ii) upscale sustainable practices among land users on existing productive land, and (iii) to strengthen producer organizations and extensionists to ensure productive land systems long-term sustainability.

- The project is also consistent with the GEF Operational Program on Sustainable Land Management (OP15) regarding the mitigation and prevention of land degradation and desertification. Involvement of GEF’s OP 15 will enable to generate local, regional and global environmental benefits by mainstreaming sustainable land and water management (SLWM) techniques into project interventions of the targeted production systems. This will result in improved adaptation to climate change in connection with the NAPA priorities.

- Finally, this operation is consistent with TerrAfrica Business Planning Framework and will assist in implementing most particularly: Activity Line 1 Coalition building with; Objective 2: Develop inclusive regional dialogue and advocacy on strategic priorities, enabling conditions, and delivery mechanisms; Activity Line 2 Knowledge Management, with Objective 5: Harmonize monitoring and evaluation systems, and Activity Line 3 Investments with Objective 6: Advocate for SLM and mainstream into development strategies and policy dialogues at sub-regional (selectively), country and local levels, and Objective 7: Develop, mobilize, and harmonize investments at sub-regional (selectively), country and local levels

- Project Approach and Analysis

- This section discusses the incremental costs eligible for GEF funding for the Fostering Agricultural Productivity Project, defined as the difference between the GEF alternative scenario and the IDA baseline. For each of the three components of the project, the section will:

Component 1: Technology transfer and service provision to agricultural producers

- The focus of this component is to enhance modernization of smallholder farming systems and supply chains through the dissemination of innovative practices and improved agricultural services.

- Baseline: This component will have four main activities: i) putting in place a ‘farming systems and supply chains modernization fund’, ii) capacity building for producer organizations (POs) and service providers, iii) facilitating rural credit development, and iv) technology generation and promotion of research – producers linkages. A menu of technologies will be proposed by the project. POs and service providers can apply for funding for these technologies through the modernization fund. Favored will be projects that cover the supply chain from production to processing and marketing. Inputs, equipment but also technical assistance and credit access facilitation can be funded. The project will also support capacity strengthening of existing networks of specialized service providers. In addition, rural credit development will be facilitated and assistance regarding financial management will be provided to investors in agribusiness. The project will also facilitate technology generation and strengthen linkages between research and extension services and producers.

- Expected results under the baseline scenario: Mini-projects put forward by POs are funded by the modernization fund and implemented; in-country training capacities restored; agribusiness centers established and functional; financing tools will be modernized and adapted to the agriculture sector; and demand driven research will be implemented with emphasis on soil fertility and water management.

- Base line cost: US$55.3 million: IDA: US$27.8 million; IFAD US$13.8 million, Beneficiaries: US$3.7 million, GoM: US$10.0 million

- GEF Alternative Scenario: The GEF alternative will develop field interventions that contribute to mainstream and scale-up of the sustainable management approach within Mali’s agriculture sector. A set of proposed SLWM technologies (see Annex 19) will be integrated into production-oriented initiatives financed under the baseline scenario allowing long-term productivity constraints of the farming system to be addressed. While improving the productive capacity of the farming systems, resilience and ecosystem stability are also improved. This will ultimately reduce medium to long-term risks in the agricultural sector and allow improved adaptation to a changing climate and other external shocks. Incentives for farmers to adopt SLWM practices are provided through the ‘modernization fund’ where high-impact SLWM practices and technologies will be financed with priority status. In addition, the project will put much emphasis on training and capacity strengthening, so that the stakeholders receive an improved understanding of ecological linkages and processes within their production systems allowing them to apply informed decisions on land and water management. Demand-driven research from this improved awareness and knowledge will allow stimulating innovation and adaptation of SLWM practices by farmers in collaboration with extension and research. The project will strive to create and reinforce a holistic vision by the project stakeholders when identifying productive and environmental protective interventions within their production systems. This holistic view integrates all natural resource based sub-sectors, including crop and livestock production, aquaculture, rangeland management, agro-forestry and forestry.

- Expected results under GEF alternative scenario: Mini-projects on SLWM technologies and practices are funded; surface area under SLWM practices are substantially increased; a large number of POs integrate SLWM practices into their production oriented activities; SLWM and knowledge and awareness improves considerably for service providers and POs; above and below ground carbon accumulation will be significant; and land degradation dynamics will be reduced and reversed.

- GEF alternative costs: US$ 59,100,000 (IDA, IFAD, EU, GEF/IDA and GoM/Beneficiaries)

- Incremental costs: US$ 3,800,000 (GEF/IDA)

  - Component 2: Irrigation Infrastructure

- The focus of this component is to finance infrastructure to improve water management.

- Baseline:  This component will promote the development of small-scale and large-scale irrigation. All irrigation investments will be accompanied by a package of advisory support, financed under Component 1. Small-scale irrigation development includes village-based gravity fed irrigation schemes and small-scale lowland development through sustainable rainwater management practices. Investments will be done in partnership with local POs, who will be in charge of the infrastructure management. In addition to technical advice, support will be provided regarding governance and managerial issues, for instance on water fees and land tenure. Large-scale irrigation investments concentrate on the modernization, improved management and expansion of the Office du Niger (ON) area. It concerns about 5,700 ha. Focus will be given to enhancing efficiency of water management, and to complementing on-going policy dialogue between GoM and donors on ON’s modernization and governance.

- Expected results under the baseline scenario: For the small-scale irrigation schemes, the total area that will be developed is 2,100 ha for new village-based irrigation schemes; 1,500 ha of rehabilitation of village-based irrigation schemes; the development of 4,000 ha of lowland areas; and the establishment of 500 ha of small-scale dry season irrigation schemes. As for the large-scale irrigation scheme development, a total of 4,700 ha will be put in place in the ON zone.

- Baseline cost: US$ 67,000,000 IDA: US$19.3 million; IFAD US$16.1 million, EU: US$19.5 million, GoM: US$9.1 million, Beneficiaries: US$3.0 million

- GEF Alternative Scenario: Although GEF will not contribute to this infrastructure component, the planning and implementation of the infrastructure will respect environmental standards and will take into account the larger ecosystem context. It will also strive for synergies between agriculture, livestock and forestry sectors. Irrigation design will pay particular attention to the protection of soil and water resources. This includes for instance: complete water control at the plot level (irrigation and drainage), protection of soil resources through appropriate water management (e.g. avoiding salinization). Other agro-ecosystem related and synergy-creating aspects will be integrated, for example the design of windbreaks or the development of management plans for pastoral areas in proximity to irrigation schemes.

- Expected results under GEF alternative scenario: Water is used judiciously; soils are protected from excessive water application and from soil salinization; larger scale land use production and environmental issues are considered and respected surrounding the irrigation perimeters; agro-forestry techniques are associated with irrigation schemes; spatial planning and arrangements for improved livestock production are taken into consideration.

- GEF alternative costs: US$ 66,200,000 (IDA, IFAD, EU and GoM)

- Incremental costs: US$ 0 (GEF/IDA and GEF/UNDP)

  - Component 3:  Comprehensive programmatic approach, sector monitoring and project coordination:

- The focus of this component is to evolve toward a sector wide approach (SWAp) in the agricultural sector.

- Baseline: The project aims to forge a more consistent programmatic approach of investments and interventions. It will also help to design the National Agricultural Sector Investment Program (PNISA or Programme Nationale d’Investissement Sectoriel Agricole), and support the development of policy options and institutional reforms in key Ministries. The project will seek to restore production of reliable statistics on the sector, monitor its evolution, and provide up-to-date information to policy decision makers, the GoM, partners and the public.  The project will also facilitate the emergence of a pluralistic network of service providers through the creation of the National Advisory Service Council. The project will help line Ministries to deliver core public services with respected standards of quality.

- Expected results under the baseline scenario: Transition to a sector wide approach is made and support is provided for the design of PNISA; policy reforms within key Ministries are implemented; a sector wide monitoring and evaluation system is implemented, producing reliable sector statistics; National Advisory Service Council established, and quality control for inputs, extension services and public investments undertaken.

- Base line cost: US$22.6 million: IDA: US$15.9 million; IFAD US$2.1 million, GoM: US$4.6 million

- GEF Alternative Scenario: This component will help mainstream the SLWM programmatic approach already in place within the national policy dialogue and contribute to establishing an institutional framework conducive to the efficient delivery of SLM services to producers. In the alternative scenario, the project will assist the implementation of the Country Strategic Investment Framework (CSIF) for sustainable land management. Furthermore, GEF funding will contribute to strengthen the capacity of the rural sector’s Statistics and Planning Unit, and will support a dedicated geographic information system that will provide agricultural and environmental information to the GoM, the public and all partners.

- Expected results under GEF alternative scenario: Mali SLM CSIF is adopted and implemented; SLWM is mainstreamed in agriculture policy dialogue; the institutional framework is improved for SLWM integration; the monitoring and evaluation system of the project is strengthened; and a GIS is functional, up to date and accessible to the public.

- GEF alternative costs: US$ 26,900,000 (IDA, IFAD, EU, GEF/IDA, GEF/UNDP and GoM)

- Incremental costs: US$ 4,300,000 (GEF-IDA: US$2.4 million, GEF-UNDP: US$1.9 million)

- Incremental value added by GEF funding

- The incremental costs are calculated as the difference between the GEF alternative scenario and the IDA baseline scenario. The incremental value added and the benefits generated through GEF financing are elaborated below in the matrix.

| Comp. 1 | Category | Costs (US$) | Local Benefit | Global Benefit |
| --- | --- | --- | --- | --- |
| Technology Transfer and Service Provision t o agricultural Producers | Baseline | 55,300,000 | Classic value-chain approach, with focus on a few main crops for production increase. | Minor |
|  | With GEF Alternative | 59,100,000 | Comprehensive and integrated approach to promote crops, animals and tree components to respond to needs of end users, while at the same time protecting the ecosystem through SLWM practices. Increased agricultural (crop, livestock, forestry and aquaculture) productivity based on SLWM principles Increased vegetation cover through soil and water conservation techniques, agroforestry and reforestation activities, abandoning of degrading practices such as bushfires. | Increased above and below ground carbon sequestration based on improved organic matter management practices Reduced methane emissions in irrigated systems through improved irrigation practices Maintaining biodiversity within the production landscape: crop, livestock and woody species diversification, above and below ground biodiversity is increased through soil protecting management practices. Reduced environmental degradation and carbon emissions due to protecting measures for soils, vegetation, and habitats. |
|  | Increment | 3,800,000 |  |  |

| Comp. 2 | Category | Costs (US$) | Local Benefit | Global Benefit |
| --- | --- | --- | --- | --- |
| Irrigation Infra-structure | Baseline | 67,000,000 | Extension of irrigation surfaces | Minor global environmental benefits: people will concentrate on irrigation perimeters and abandon extensive and land degrading practices in rainfed areas |
|  | With GEF Alternative | 67,000,000 | Improved technical design of irrigation schemes by taking into account SLWM principles, allowing for higher land and water productivity in the irrigation scheme and the surrounding rainfed, pastoral and forestry areas Significant environmental and production benefits in irrigation schemes based on the activities from incremental GEF funding under Component 2 and 3. | Global benefits as created under component 2 and 3. |
|  | Increment | 0 |  |  |

| Comp. 3 | Category | Costs (US$) | Local Benefit | Global Benefit |
| --- | --- | --- | --- | --- |
| - Comprehensive Programmatic Approach, Sector Monitoring and project coordination | Baseline | 22,600,000 | Sector approach to agriculture is developed, M&E system to monitor baseline activities | A good framework for the sector is established, and a monitoring and evaluation system put in place but insufficient SLWM integration, thus limited benefits. |
|  | With GEF Alternative | 26,900,000 | Harmonizing approaches and creating synergies between programs in the agriculture sector and between donors that benefit the environment while striving for increased agricultural productivity Priority programs under CSIF implemented Increased coordination, management and M&E capacity related to SLM activities Comprehensive mechanism for monitoring SLM and land degradation processes | SLWM is mainstreamed into agriculture sector (national programs and strategies), which will contribute to maintain long-term ecosystem integrity and productivity, increase carbon sequestration and reduce environmental degradation. Increased knowledge and awareness on global environmental issues at local, regional, and international level, will allow for improved decision-making by stakeholders to engage in SLWM activities that create global environmental benefits. Significant contribution in monitoring environmental degradation trends and the impact of SLWM practices for global environmental benefits. |
|  | Increment | 4,300,000 |  |  |

| TOTAL | Baseline | 144,900,000 |  |  |
| --- | --- | --- | --- | --- |
|  | With GEF Alternative | 153,000,000 |  |  |
|  | Increment | 8,100,000 |  |  |

NB: PPF refinancing and unallocated resources excluded

- Role of Cofinancing  (US$ million):

| Components | IDA | EU | GEF IDA | IFAD | GEF UNDP | Benef. | GoM | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Component 1 - Technology transfer and service provision to agricultural producers | 27.8 | - | 3.8 | 13.8 | - | 3.7 | 10.0 | 59.1 |
|  | 39.7% | - | 61.3% | 43.1% | - | 55.2% | 42.2% | 36.9% |
| C1.1- Farming system and supply chain modernization | 15.4 | - | 3.8 | 8.6 | - | 3.0 | 6.2 | 37.0 |
| C1.2- Capacity building for POs and service providers | 6.9 | - | - | 2.6 | - | 0.7 | 2.1 | 12.3 |
| C1.3- Facilitating rural credit development | - | - | - | 2.6 | - | - | 0.5 | 3.1 |
| C1.4- Technology generation and research/prod. linkages | 5.5 | - | - | - | - | - | 1.2 | 6.7 |

| Composante 2 – Irrigation Infrastructures | 19.3 | 19.5 | - | 16.1 | - | 3.0 | 9.1 | 67.0 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 27.6% | 100% | - | 50.3% | - | 44.8% | 38.4% | 41.9% |
| SC 2.1- Small scale irrigation | 2.2 | - | - | 16.1 | - | 1.0 | 3.7 | 23.0 |
| SC 2.2- Large scale irrigation | 17.1 | 19.5 | - | - | - | 2.0 | 5.4 | 44.0 |

| Composante 3 – Comprehensive programmatic approach, sector monitoring and project coordination | 15.9 | - | 2.4 | 2.1 | 1.9 | - | 4.6 | 26.9 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 22.7% | - | 38.7% | 6.6% | 100% | - | 19.4% | 16.8% |
| SC 3.1- Policy dialogue and sector coordination | 1.8 | - | 0.6 | 1.1 | - | - | 0.7 | 4.2 |
| SC 3.2- Sector monitoring and evaluation | 2.7 | - | 1.8 | - | - | - | 1.0 | 5.5 |
| SC 3.3- Delivery of core public services | 7.7 | - | - | 1.0 | 1.9 | - | 2.2 | 12.8 |
| SC 3.4- Project coordination / monitoring and evaluation | 3.7 | - | - | - | - | - | 0.7 | 4.4 |

| PPF refinancing | 0.95 | - | - | - | - | - | - | 0.95 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Unallocated | 6.05 | - | - | - | - | - | - | 6.05 |

| Total | IDA | EU | GEF IDA | IFAD | GEF UNDP | Benef. | GoM | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 70.0 | 19.5 | 6.2 | 32.0 | 1.9 | 6.7 | 23.7 | 160.0 |
|  | 43.7% | 12.2% | 3.9% | 20.0% | 1.2% | 4.2% | 14.8 | 100% |

Annex 16: Lessons Learned from Past Experiences

Mali:  Fostering Agricultural Productivity Project

- The project will build upon the Bank experiences of PNIR for large-scale and small-scale irrigation development, and of PASAOP for technology generation and transfer, the promotion of private delivery for advisory services to farming communities and the empowerment of producer organizations. These two predecessor projects have strongly contributed to set up renewed institutions and to develop successful innovative approaches:

- Stronger producer organizations: Under the capacity building program developed under PASAOP, producer organizations (POs) have emerged as key partners for policy dialogue at the national level, as well as for the implementation of field investments at the local level. The project will build upon the present network of Regional Agricultural Chambers (CRAs) operating under the national leadership of the Permanent Assembly of Malian Agricultural Chambers (APCAM).  It will also rely on grassroots producer associations and cooperatives that have either emerged or developed in specific production sub-sectors. APCAM has successfully implemented the PASAOP component dedicated to the strengthening of producer organizations and is now recognized by GoM as the central partner for producers’ advocacy. Many donors and development agencies also use APCAM and CRAs as implementing partners for producer-oriented projects or activities.

The present challenge is not to create new POs, but rather to help existing organizations become: (i) more professional (better internal governance, accountability towards members, transparency towards donors and sound management); (ii)  more focused in providing one or two types of services (such as inputs supply, seed production, storage facilitation, marketing, etc, and avoiding mixing social and economic activities); (iii) broad-based and inclusive, serving as many producers as possible on a technically and financially sustainable basis.

- Better technology generation mechanism: Agricultural research institutions in Mali are now better organized and aligned to a common strategic plan that provides key directions and priorities for research programs. These institutions are more responsive to the producers’ needs due to decentralized consultation committees (to facilitate dialogue between producers and researchers at regional level), along with a financing mechanism to undertake applied research programs and on-farm trials. It is critical to maintain both this dynamic collaboration and research potential, however the main challenge is to boost the dissemination of technologies and agricultural techniques that have already been developed or adapted to the Mali context (this includes in particular new seed varieties or animal breeds, innovative production techniques, etc).

- More efficient advisory services: Through PASAOP, Mali has progressively moved from a traditional top-down and state-led extension system to a more demand-driven and pluralistic network of public and private advisory service providers. Results-oriented and performance-based contractual arrangements have been standardized to include public extension agents. One challenge is how to expand and strengthen the network of private service providers, help them become more professional, better specialized and consistent in their focus (less movement from one financing opportunity to another). Another challenge is how to help POs develop their own expertise and networks (notably by recruiting management staff and qualified technicians).

- Sustainable irrigation development: With support from PNIR, Mali elaborated a National Irrigation Strategy in 1999. It was reviewed in 2007 with a clear focus on producers’ participation and co-financing, including involvement of the banking sector. Drawing from lessons already learnt through several projects, challenges ahead include: (i) improving inter-relationships between irrigation infrastructure development, availability of agricultural support services and related financing mechanism, so that sufficient income is generated from the investment and transparently managed to provide for O&M expenses; (ii) addressing water resource management issues as irrigation water potential becomes increasingly exploited and as irrigation schemes show low levels of efficiency.

- The project will also build upon lessons learned from IFAD-financed interventions through complementary programs targeting vulnerable populations of the Sahalian and Sahelo-Saharan zones:

- The Sahelian Areas Development Fund Program (FODESA), the first program financed by IFAD under the Flexible Lending Mechanism, delegated implementation to farmers’ organizations. FODESA aims to improve the living conditions of populations of the Sahelian area by realizing productive and social micro investments adapted to the specifics of the area and by strengthening the capacities of rural organizations to provide technical and economic services to their members and to participate in local development. FODESA improved the population’s access to production factors (large-diameter wells, microcredit) through community projects, substantially increasing beneficiaries’ incomes. For example, approximately 278 households growing rice on 417.5 hectares of rice perimeters generated supplementary income of about US$474 per household. Another IFAD-funded program “Income Diversification Program in the Mali Sud Area”, which closed in 2005, improved household food security through regeneration of degraded lands, doubling the available cropping area.

- The Northern Regions Investment and Rural Development Program (PIDRN) assist the populations of Gao and Timbuktu in developing hydro-agricultural potential in their area to improve their living conditions. PIDRN capitalizes on the results of the second phase of the Zone Lacustre Development Project (PDZL) which closed in June 2006. The hydro-agricultural investments of PDZL have contributed to ensuring higher levels of food security for poor households in the lake area, which, before program implementation, faced chronic food shortages. There was an increase of about 100 kg of rice per year per person (54 percent of individual yearly consumption of cereals of 186 kg), which was the equivalent of US$350 or 186 percent. Furthermore, children’s basic food needs were increasingly met, raising height/weight and height/age ratios by respectively 0.49 and 0.46 points.

- From these IFAD-financed interventions, the following lessons have been learned :

- In  structurally food-deficient zones (Sahelian and Sahelo-Saharan), interventions should first focus on setting up production infrastructure to satisfy the population’s food needs, and social and health infrastructure to make living conditions less precarious.  Subsequently, the foundation for a more economic approach could then be laid, taking into account activities upstream and downstream of production (inputs, supplies, processing, marketing, collaboration and coordination). Higher levels of food security, health and hygiene conditions of vulnerable and poor households of PDZL zone, which before IFAD’s interventions, faced chronic and shortages were achieved through hydro-agricultural investments. In the “Income Diversification Program in the Mali Sud Area”, household food security was improved through regeneration of degraded lands, doubling the available cropping area. FODESA improved the population’s access to production factors (large-diameter wells, microcredit) through community projects, substantially increasing beneficiaries’ incomes.

- An area-based approach coupled with an integrated approach made it possible to take into account specific environmental factors and constraints, and the productive potential and level of social organization of the rural poor. The development potential of the Sahelian area is low and highly uneven. Micro investments are best adapted to these constraints and are most likely to increase household incomes. Strategic partnerships with, the West African Development Bank (BOAD), the Belgian Survival Fund (BSF), and the OPEC Fund for International Development, led to improvements in household living conditions and better access to basic social services. Joint efforts also opened up production areas and contributed to the creation of grass-roots rural organizations.

- Combination of geographic targeting/poor areas and concentration of investments helped to maximize impact and avoid fragmentation.

Annex 17: Key results of the SLWM-PER and CBA study

Mali:  Fostering Agricultural Productivity Project

- Sustainable land management practices are the foundation of durable agricultural development in Mali.  A range of agro-ecological zones and hydrological areas within Mali have encouraged agricultural producers to practice a variety of land management techniques to adapt to their environment.  However, Mali is confronted by significant land management issues not only in its arid regions (Kidal, Gao, Tombouctou), but in managing the significant water resources from which the country greatly benefits.

- In this report, public expenditure on sustainable land management is reviewed and the severity and extent of land degradation is examined. To better understand the costs of land degradation and the on-farm and off-farm impacts of land management practices, economic, environmental and hydrological modeling is integrated to estimate the outcomes of a variety of sustainable land management.  The study considers why household adopt sustainable land management (SLM) practices, the effect of increased sedimentation and off-site effects from land degradation, as well as the crop-specific effects from a variety of land management practices using benefit-cost analysis.

- Public expenditure on SLM: The public expenditure review (PER) study shows that Government expenditure on SLM has increased over the past 4 years from about XOF 30 billion in 2004 to about XOF 42 billion in 2007. The 40 percent increase demonstrates the Government’s commitment to enhance productivity of the natural resources, upon which a majority of the poor depend. However, SLM expenditure accounts for only 3.7 percent to 4.7 percent of the total Government budget. Considering the contribution of the land-based economic sectors to the GDP and the large share of the population depending (over 80 percent) on land and other natural resources, the Government’s expenditure on SLM is low and needs to be increased significantly.

| Table 1: Budgeting of SLM expenditures by the National Government (000 F CFA) |  |  |  |  |
| --- | --- | --- | --- | --- |
| Ministry | 2004 | 2005 | 2006 | 2007 |
| Agriculture | 10 053 500 | 7 638 442 | 11 104 016 | 14 101 370 |
| Environment and Sanitation | 329 000 | 746 292 | 4 383 194 | 1 723 230 |
| Livestock and Fishing |  | 1 082 830 | 1 609 000 | 2 614 205 |
| Infrastructure and Transport | 14 902 304 | 13 242 084 | 19 213 594 | 19 184 744 |
| Energy, Mines and Water | 2 591 000 | 2 542 706 | 1 627 000 | 1 849 955 |
| Territorial Administration and Local Collectives | 1 877 000 | 1 073 742 | 1 903 000 | 802 880 |
| Commission for Food Security |  |  |  | 1 351 420 |
| Total | 29 752 804 | 26 326 096 | 39 839 804 | 41 627 804 |
| National Budget | 657 992 505 | 782 197 143 | 852 510 248 |  |
| % | 4,52 | 3,37 | 4,67 |  |

- As is common in other African countries, donor contribution to SLM expenditure is much higher than Government expenditure. Donor expenditure on SLM accounts for 11-15 percent of the national budget. However, actual donor expenditure on SLM has been declining since 2005 –suggesting an unsustainable path that needs to be addressed by both the donors and the Government.

- Land degradation: Land degradation in Mali has been in the form of soil nutrient mining, soil erosion through wind erosion in the northern regions and sheet soil erosion in the southern regions. Overgrazing in the northern regions, deforestation in the southern regions unsustainable and generally unsustainable land management practices across all regions have been the major drivers of land degradation. The share of fallow land has dropped with increasing population. Over 80 percent of farmers no longer practice fallowing – a method that was used in the past as a way of restoring soil fertility. In light of this human pressure, the main alternative for the restoration of lands and their fertility management remains intensification through use of organic and inorganic soil fertility management practices.

- Many sustainable land management activities have often been undertaken successfully and have helped land restoration and substantial yield increase. However, many constraints hinder the widespread application of recommended practices. These constraints range from financial constraints to the poor availability of raw materials. A major issue is the land tenure issue which determines the land user’s willingness to apply SLM practices. In the case of a borrowed land (which is a very common practice), the borrowers are reluctant to invest manure in a land that might be taken away by the owner.

- The intensive management of residues also requires ownership. Similarly, innovations such as the recommended protection and enclosure techniques, agro-forestry and other forms of land improvement investments require formal land ownership. Studies in Mali and other countries have also shown that integrated soil fertility (ISFM), which includes agro-forestry, soil and water conservation practices, judicious use of fertilizer and organic matter is better and more sustainable than inorganic fertilizer or organic inputs only. Use of ISFM reduces the quantity of fertilizer required to achieve the same level of yield.

- Determinants of adoption of SLM practices: Results illustrate the adoption of SLM practices by households, especially the use of organic fertilizers.  Vocational training increased fertilizer and manure use in tandem, while training in a rural center increases manure use by 17 percent.  Household heads with formal education in the form of post-secondary education were 15 percent more likely to have used fertilizer. Household heads with secondary education were 6 percent more likely to use manure and 7 percent more likely to use chemical fertilizer.  Primary school had no statistically significant effects on the adoption of SLM practices.

- Cost-Benefit analysis of SLM practices: The off-site effects simulation results of multiple year averages of annual water and sediment inflow of 18 small reservoirs illustrate that reservoirs in the downstream areas tend to have more inflow of water.  Compared to water inflow estimates, the estimates of sediment inflow vary much more significantly among reservoirs, and the estimated sediment inflow rates of many reservoirs are close to zero. Although a conclusion is that sedimentation is not a severe problem in the Banifing River basin, the impacts of land conservation are still simulated and estimated.  In the estimation, the total dredging costs of removing the same amount of sediment as the annual inflow sediment are calculated as the substitute costs of land degradation. .  The off-site cost of soil erosion in the Banifing River watershed is XOF million 165.8. Control of soil erosion using contour ridges reduces the sediment deposition by 20 percent and leads to off-site benefit of XOF million 17.4 due to savings of dredging costs.

Table 2: Cost of land degradation and benefit of SLM practices in the Banifing river watershed

| Sediment without SLM(ton/yr) | Cost of land degradation (XOF million/yr) | Sediment with SLM(ton/yr) | % reduction of sediment | Off‐site benefit with SLM (XOF million/yr) |
| --- | --- | --- | --- | --- |
| 19722.1 | 165.8 | 17652 | 20.6 | 17.4 |

- The cost-benefit analysis in this report also shows that, for certain crops, land management practices that are sustainable are profitable and competitive in the rural labor market. This is consistent with other studies that have shown that the SLM practices are profitable (e.g. Doraiswamy, et al., 2007) and competitive. For example, Table 3 shows that maize and rice are profitable and their returns to labor are greater than the daily wage rate of XOF 1,000.

Table 3: Cost-Benefit analysis of maize and rice

| Land management practices | Net benefit (000 XOF/ha) | Returns to labor (XOF) | Net margin (000 XOF) | Returns to labor (XOF) |
| --- | --- | --- | --- | --- |
|  | Maize |  | Rice |  |
| Residue 100% | 9.43 | 3159.84 | 76.62 | 8055.91 |
| Compost 1, residue 50% | 7.66 | 3338.46 | 55.36 | 4512.55 |
| Manure 1, 50% residue | 12 | 3191.48 | 65.47 | 6260.24 |
| 80 kgN/ha | 75.69 | 17261.39 | 43.54 | 3560.44 |
| Compost 2, residue 50%, 80KgN | 65.1 | 7741.76 | 295.79 | 29258.01 |
| Manure 2, residue 100%, 80KgN/ha | 76.04 | 8440.03 | 320.39 | 15904.06 |
| All zero – baseline | 7.98 | 2483.7 | 148.74 | 12014.17 |

- Labor contributes a large share of production using SLM practices. Hence efforts to reduce the high labor intensity of SLM practices need to be increased in order to enhance their adoption. Investment in development and promotion of animal power and mechanization using simple and affordable equipment and machines need to be increased. This will increase the likelihood for labor intensive SLM practices – such as manure and compost – to be adopted. Similarly, extension services to promotion of animal power and appropriate technology mechanization need to be enhanced, especially in the rural areas, where they are weak.

- Land degradation leads to a large loss of the country’s income. Results show that for maize and rice crops only; about 2.6 percent of the Malian GDP is lost due to land degradation. This demonstrates the seriousness of land degradation in Mali and the need for the efforts to address this problem in the country.

- Maize and rice provide ecological services through carbon sequestration. Results show that the value of carbon sequestered by maize and rice farmers who use fertilizer and manure is about 1 percent of the GDP. These results demonstrate the large potential that agriculture can contribute to carbon mitigation.

Annex 18: Land degradation and SLWM in target production systems

Mali:  Fostering Agricultural Productivity Project

- Land degradation in Mali in Mali’s agriculture sector that comprises crops, livestock, forestry and fisheries poses a major threat to the productivity of the sector in the short and long term. Over the past 30 years, agricultural yields have stagnated or declined. Yields only increased for rice. It is the expansion of land area under cultivation that is responsible for agriculture production increase. Often marginal areas are taken under cultivation and natural habitats are occupied, among them woodlands and wetlands. Between 1970 and 1995, for instance, cultivated land area increased by almost 80 percent from 1,967,000 ha to 3,472,000 ha.

- Livestock is produced on 79 percent of the territory. In 2003, small ruminants comprised more than 20 million, which is double compared to 1990. Mali’s cattle count about 7.5 million heads, with an annual increase of 3 percent. After gold and cotton, cattle are the third export product. But the natural pastures, estimated at 35 million hectares, are in constant reduction. Each year, 14.5 million ha are burned through bush fires. The need for fodder largely exceeds the production capacity of the ecological zones. This drives overgrazing and results in further vegetation cover loss. Soils are exposed to wind and water erosion and become further impoverished. One notes a displacement of pastoralists with their herds leaving the north and moving further south towards the wetter zones. This increases competition between agricultural and pastoral land use and creates conflicts among farmers and herders.

- Mali’s forests have undergone serious modifications. This is a result of declining rainfall, droughts, and most importantly of human activities, such as land clearing for agriculture, extraction of wood, overgrazing and heavy pruning of trees for fodder, and bush fires. According to the DNRFFH, more than 100,000 ha of forests disappear each year. Annually more than 7 million tons of firewood is collected, which corresponds to the exploitation of 400,000 ha. Energy consumption in Mali is still covered with more than 90 percent by wood and charcoal.

- The loss of biodiversity in Mali is related to a range of complex factors. The most important ones are related to climate change, recurring droughts, and human activities. These comprise deforestation, overexploitation of wood, overgrazing, bush fires, clearing of woodlands for agricultural land, chemical pollution of soil and water resources, over extraction of fish resources, and the invasion of exotic species.

- The two largest rivers of West Africa, the Niger and the Senegal, run through Mali. Within their watersheds nearly 400 wetlands are identified, including several Ramsar sites. The most important is the Inner Delta of the Niger, the second greatest wetland of Africa. Although theoretically abundant, the surface and ground water resources are threatened by the irrational management of the irrigation networks, sedimentation of the riverbeds and from various pollution threats. The successive drought events and reduction in rainfall have seriously affected the extent of water surfaces, including the seasonally flooded areas. For instance, the Inner Delta of the Niger, which could reach up to 30,000 km2 in size in 1980, is currently only stretching over a surface of 5,000 km2.

- Annual rainfall has declined over the past 30 years, with a displacement of the isohyets further south. The isohyet for 1,400 mm, for example, still present in 1970 in the south of Mali, has disappeared from the country since then. With the decline in rainfall, the recharge of groundwater is also diminishing, resulting in the lowering of the groundwater table and in the drying out of certain wells. With less seasonally flooded surfaces, available water for agriculture and for livestock is diminishing and fishery resources are shrinking. It is foreseen, that temperatures will be rising, and that the isohyets will move further south. Irregular rainfall distribution will create much stress for agriculture. Strong winds and increasing flood risks will further contribute in destabilizing the primary sector.

- Land Degradation and Sustainable Land and Water Management (SLWM) analysis for the targeted production systems: The project will concentrate its efforts on four production systems: i) irrigation systems, ii) rainfed cereal systems, iii) fodder production systems, and iv) livestock production systems (dairy, sheep fattening and poultry). Production basins were selected within each of the systems. They are presented in Annex 4. These basins respond to an improved production potential, market opportunities (proximity to urban consumers), and a potential for income increase for smallholders and poverty reduction. The project is adopting a multi-sector approach to the agriculture sector, which includes agriculture, livestock, forestry, fisheries, environment and food security. In the next sections, the production systems are briefly outlined, and the constraints and SLWM options developed. For each system, a compilation of potential techniques is presented in the table at the end of this annex, indicating what constraints they respond to, noting observations and developing recommendations to be considered for the implementation of the technique.

  - Large scale irrigation (Office du Niger):

- Three categories of farms exist in the ON zone: (i) small size farms with about 1ha of surface, (ii) medium sized farms (5 to 10 ha), and (iii) large farms (10-100 ha). The project will assist small farmers and POs in improving the economic and financial viability of their agricultural activities. It will develop new irrigated land and will contribute to improving water and soil management.

- Constraints: With limited access to irrigated land and due to population growth, families break up and farm sizes get smaller, which threatens the economic viability of these small-scale family operations. Yields for rice, the dominant crop in ON, have been declining in recent years and off-season cropping is not well developed. Decline in soil fertility and salinization of soils have become major constraints to agricultural production. Soils are not replenished periodically with organic matter. Crop production depends on chemical fertilizers, which has in the long run serious consequences, including soil structure deterioration and water holding capacity. Non-efficient use of water contributes to excessive flooding with inadequate drainage. This can result in salinization of soils. Water availability is also a problem for off-season cropping. Exotic aquatic plants invade irrigation canals. This slows the flow of water and constrains distribution across the scheme. Post-harvest livestock grazing damages irrigation infrastructure, while overgrazing, in addition to excessive fuel woodcutting and deforestation, damages ON surroundings.

- SLWM options include the promotion of the System of Rice Intensification (SRI) and the diversification of cropping system based on shallots, potatoes, maize, wheat, fodder plants, and fish farming. Organic matter (OM) inputs will be crucial to improve soil structure, water and nutrient retention capacity, improve efficiency of chemical fertilizer applications, and benefit off-season crops with residual effects. It also increases ground carbon sequestration. OM production techniques will rely on composting, crop residue management, manure collection and application, planting of green manures, improved fallows, and agro-forestry (e.g. Gliricidia sepium hedges).

- Improved water management: Reducing water consumption and extensive flooding, the SRI method will facilitate the adoption of alternate wetting and drying techniques. Bio-drainage based on Eucalyptus trees will be encouraged. Aquatic invasive plants composting will help improve water flow. Better water use and saving will also be encouraged thanks to the proposed payment system for irrigation water.

- Afforestation and reforestation will increase wood availability for fuel and construction wood. They will help fodder production within pastoral areas, canal protection, windbreak creation, bio-drainage, organic matter production and carbon sequestration. Integrated pest management techniques will allow reducing the use of pesticides. The integration of crop and livestock production will create important synergies and win-win situations. Fodder production will help intensify livestock production and animals feeding in stables. Manure collection will be easier, as well as its application and composting. The promotion of aquaculture in fishponds will be explored.

- Climate change:  Environmental benefits include an Increase in soil carbon sequestration through the application of organic matter into soils, reforestation and agroforestry interventions within and around the ON zone, as well as reduced methane emissions thanks to SRI, less pesticide use, improved soil and water saving sw.

  - Small scale irrigation:

- The project will assist village communities in building small-scale irrigation schemes, based on a demand-driven approach. Three types of irrigation schemes will be promoted: (i) Village irrigation schemes, i.e. gravity fed schemes of 30 ha where water is pumped from a nearby river or pond; (ii) Small diversification schemes dedicated to vegetables, established in lowlands for dry season irrigation as well. (iii) Lowland (“Bas-fonds”) based on small dykes to prevent erosion and facilitate rainwater infiltration. Rainfed rice is cultivated in the rainy season, and a variety of crops and vegetables are grown in the dry season using groundwater for irrigation. As these systems are different, constraints and SLWM options are analyzed separately:

- Village irrigation schemes: constraints include monoculture of rice with little diversification, soil deterioration, loss of organic matter high cost of water pumping and scheme maintenance, poor scheme management resulting in inefficient water utilization. SLWM option will cover SRI introduction and diversification in agro-forestry species, fruits, vegetables, fodder production, and aquaculture. Water use efficiency will improve thanks to alternate drying and wetting irrigation techniques. When possible, drip irrigation will be introduced especially for off-season production.  Organic matter production and application will be encouraged based on various available techniques (composting, green manure, crop residue application etc.)

- Small diversification scheme: These schemes, often managed and used by women associations, play an important role in food security, nutrition and income generation. The small surfaces can be cultivated quite intensively with a range of vegetables, fruits and other profitable crops. Main constraints include: lack of diversification and good rotations; lack of good cropping techniques; soil fertility decline; pest and disease problems; and high water pumping costs. SLWM options will cover: crop diversification and optimizing rotations; maintain and improve soil fertility through organic matter inputs, such as cover crops, composts, manure etc.; integrated pest management; drip irrigation where possible; improve post harvest management.

- Lowland (Bas-fonds): The lowlands are used for rainfed rice cultivation during the rainy season, and for vegetable growing during the off-season. Constraints include: soil fertility decline; traditional methods (seed broadcasting) of rice cultivation with low yields; hand irrigation for vegetables using groundwater is very labor intensive and less efficient. SLWM options will cover: building small dykes along contours to facilitate infiltration of rainwater and prevent erosion; improved cropping techniques for rice, including mechanization and soil fertility management via rainfed SRI; improve irrigation methods for vegetable growing via small pumps; improve soil fertility through cover crops or composting.

- For all systems, the following recommendations are made to improve impact of SLWM options: Strengthen capacities of village community and/or the management committee of the irrigation scheme in regards to maintenance of the scheme, transparent and efficient accounting system, land tenure etc.; Improve technical service provision to farmers and encourage adapted mechanization; Improve post-harvest operations such as storage, transformation, and marketing of products; Organize access and storage of inputs

  - Rainfed cereals

- Cereals/leguminous fodder/livestock:This system is a diversified agro-sylvo-pastoral system. It is located in the sahelian climate zone with a rainy season of 3 to 4 months, and a yearly rainfall between 200-600mm. It is based on rainfed cereal production (millet and sorghum), leguminous crops (cowpea and peanuts), and livestock production. Depending on location, there is some potential for irrigation if close to water bodies (Niger River, Bani River, lakes and marshes). Extensive and transhumant livestock herding is an important component of this system. Project areas include Bankass, Koro, Douentza in the Mopti region; Macina, Bla, and Tominian in the Segou region, as well as Kita in the Kayes region.

- Constraints include: High population density; High variability of rainfall (inter and intra annum); Agriculture: Soil fertility loss, wind erosion, dry spells and drought; Water availability: Drinking water for humans and animals are major constraint (very deep groundwater tables); Rangeland: Overgrazing and desertification; Forestry: Deforestation and loss of vegetative cover (overgrazing, fuel wood extraction, bushfires); Lack of application of improved technologies. SLWM options will cover: Improve and maintain soil fertility: composting, crop associations and rotations, crop residue management; Live fences and windbreaks; Local conventions on landscape/rangeland management; Assisted natural regeneration,  Improving pastures and fodder production; Installing firebreaks; Bourgou cultivation along Niger River and seasonal streams.

- Cereals/cotton/livestock: This system is a diversified agro-sylvo-pastoral system, located further south of the cereal/leguminous/livestock system, and being part of the Sudan (rainfall 600-1000 mm) and Sudano-guinean climate zone (rainfall 1000-1200mm). The rainy season is between 5 and 6 months. Rivers, lowland zones and marshes maintain water all year long. Important agricultural production concerns cotton, maize, rainfed rice, sorghum, cowpea, peanuts, fruit trees, and vegetables. Farm sizes are usually 5 ha or more. Forest areas are still extensive in this farming system. The project areas include Bougouni, Koutiala, Sikasso in the Sikasso region, and Kati and Dioila in the Bamako/Koulikoro region.

- Constraints include: Declining soil fertility; Lack of organic matter for fertilization; Low yield levels; Lack of access to inputs (seeds, fertilizers); Weak access for farmers to new technologies; Forest degradation. SLWM options will cover: Improving soil fertility management (compost and manure application, cover-crops, improved fallows and rotation); availability and adoption of improved production techniques by farmers; improved service provision to farmers; local conventions on landscape/rangeland management; assisted natural regeneration.

  - Fodder production

- Fodder production around urban areas: These systems are located around urban areas and in proximity to dairy and meat production systems: i) Bamako and Koulikoro, ii) Sikasso and Koutiala, Bougouni and Sélingué, iii) Office du Niger, Ségou, iv) Circle of Mopti. Constraints include: diminishing fodder quality during the dry season; reduction in fodder resources through bush-fires; lack of materials and technical knowledge for fodder preservation techniques (hay etc); lack of awareness of nutritional value of fodder species; lack of seed multiplication/availability/seeding programs of fodder species; problem to access credits; land tenure problems in pastoral areas; impact on fodder resources from climate change. SLWM options will cover: Protection of rangelands and pastoral resources (fodder/water/salt); access and use of pastoral resources better regulated; cultivate herbaceous fodder crops (Mucuna, Dolique etc.); woody fodder species (Cajanus etc.); production of hay or silage; crop residue enrichment; provide better access to equipments and infrastructure, credits; seed production and network of distribution of high quality fodder species.

- Pastoral perimeters: the project will work in three identified pastoral perimeters, which are part of the PADESO zone. The locations are Sokolo (Niono), Dilly (Nara) and Blazimi (Kayes). Constraints include: lack of maintenance and improvement of pastoral resources; lack of water holes in rangelands; bush fires; non-optimal use of fodder resources during the rainy season. SLWM options will include: Rehabilitation of pastoral resources; fodder seeds produced and available; establish grazing conventions and support pastoral cooperatives and communities in implementing them; introduction and planting of woody fodder species; establish water holes in locations that respond to a sustainable grazing system;

  - Livestock production:

- In the three subsystems for dairy, sheep and poultry, special attention will be paid to the integration of agriculture and livestock production systems. This enables that both systems can benefit from each other, by creating important synergies that contribute to the sustainable use of the natural resources.

- Dairy production: the same intervention zones are selected as for the urban fodder production. Much of the improvement in this sector relates to better organization of the dairy producers, milk collectors and sellers, and in applying appropriate and improved technology. Constraints include: Fodder resources in quality and quantity not optimally available; Health problems related to nutritional problems. SLWM options will cover: fodder production; use of crop residues for fodder and bedding, creating a good manure/compost to be used on crop or fodder plants; manure production used in agricultural fields.

- Sheep fattening: Sheep fattening will be supported as some pilot initiatives in the regions of Ségou (San) and Mopti (Bankass, Koro, Douentza), which are part of the cereal / leguminous / livestock production system. The program is supporting the fatting of young male sheep during a 2 to 3 month period. The aim is to better use the available resources (fodder), and to produce an added value through fattening, which will provide farmers with an extra income. Constraints cover:  lack of knowledge for improved feeding techniques by farmers; lack of organization to acquire/sell animals; lack of access to veterinary services. SLWM options will cover: improved use of available natural resources and agricultural by-products for feeding the animals; fodder cultivation; collection of manure to be used for agriculture; improved knowledge of farmers how to efficiently feed sheep and therefore improve economic return.

- Poultry production will be promoted around the urban areas in the four regions. Constraints include: extensive poultry system produces a low economic return; health problems. SLWM options will cover: integration of crop and poultry production; improved use of available natural resources, and agricultural by-products for feeding the animals; collection of manure to be used for agriculture

|  | SLWM Technique | Responds to Constraints | Observations | Recommendations |
| --- | --- | --- | --- | --- |
| 1) Large-scale and small-scale irrigation systems |  |  |  |  |
| Agriculture and agro-forestry |  |  |  |  |
|  | SRI (System of Rice Intensification) | High production costs, high irrigation costs, diminishing soil fertility, methane production, difficult access to chemical inputs | Very good results in Timbuktu region by Africare in 2008 but also Gao, Mopti, and Ségou 2009. Increase yields and reduction of production costs. | Scaling up with good technical backstopping, based on Africare experience, and accompanied by IER |
|  | Crop diversification, crop associations and improved rotations | Dependence on monoculture rice and related risks with it, soil fertility depletion and reduced yields, increasing pest pressure | Needs technical and value chain development and its extension | Pilot operation on selected sites in collaboration with IER |
|  | Organic matter inputs (composting, manure) | Soil fertility decline, deterioration of soil structure, loss of water and nutrient retention capacity of soils | Already well known and established, local models need to be verified and improved | Provide support to local extension service |
|  | Composting of invasive aquatic plants | Invasive exotic plants grow on water surface of irrigation canals, which slows down water flow, and reduces the extent of irrigation | Tests are done by NGOs, a private company and IER | Initiate pilot activities |
|  | Use of Tilemsi phosphate | Soil fertility decline | Use of natural phosphate produced in Mali shows good results for crop development |  |
|  | Improved fertilizer and pesticide management and application | Irregular and difficult access of chemical inputs, often non appropriate application and handling of these products, high product costs. | Training on handling and correct and improved application of chemical inputs, establish partnership with FAO and IFDC, promote input supplier network | Provide assistance for all project sites |
|  | Integrated pest management | High costs and unreliable supply of pesticides, pollution of water resources and the environment, inadequate agricultural practices and soil fertility decline favor the pest pressure. | Improved cropping practices will lead to increase of crop productivity and reduction in pesticide use. | Provide thorough training of farmers and extension service, and follow up with a good monitoring on all sites |
|  | Reclaiming of saline soils | Mismanagement of soils and water resources, loss of agriculture land | Application of organic matter and gypsum, costly investment | Based on demand by POs |
|  | Live fences, including Jathropha live fences | Wind and water erosion, straying animals damaging irrigation infrastructure, high costs for fences, land tenure problems, | Species are known, demonstrations needed, a number of species can provide income generation (Jatropha, Henna etc), Some tests done for carbon markets | Systematic extension for project irrigation schemes, develop pumps that can work with Jatropha |
|  | Wind breaks | Wind erosion, wind stress and damage on rice plants (lodging), lack of fuel wood | Improves revenues and improves microclimate for crops, protects the ecosystem, | Extension in all project areas, to be organized with irrigation management committee and village communities. |
|  | Land tenure security | Difficulties to invest in land with a long term vision | Tests implemented; ex Baguinéda | Pilot operations to be supported. |

|  | SLWM Technique | Responds to Constraints | Observations | Recommendations |
| --- | --- | --- | --- | --- |
| Water management |  |  |  |  |
|  | Alternate wetting and drying (AWD) irrigation | Wasting of water resources, too much flooding of rice fields, raising groundwater table, salinization of soils | Up to 50 % of irrigation water can be saved through AWD method. Adoption will be favored if payment system of water is put in place | Extension of method along with SRI practices |
|  | Improved drainage and liming | Salinization and acidification of soils | Availability of lime to be guaranteed | To be promoted in ON and PIVs |
|  | Biodrainage | Salinization, Raising groundwater table | Use of Eucalyptus to evaporate much water, production of wood is an important plus | Identification of appropriate niches within ON landscape is important |
|  | Protection of canals and water points with woody species | Erosion of water points, deterioration of infrastructures | Use of Eucalyptus and shrub species as live-fences (different products/ | To be promoted at ON and PIVs |
|  | Drip irrigation | Wasting of water resources, high costs of water pumping | High cost of material, appropriate for small PIVs, and privately owned PIVs | Improve access to credit; assure technical support and backstopping |
|  | Environmental monitoring of soils and water | Environmental degradation such as soil salinity, weeds, sedimentation in canals etc. | Monitoring system is currently developed in ON | Support to environmental monitoring |
| Pastoral management |  |  |  |  |
|  | Fodder production on agriculture land | Rice monocrop, lack of fodder around settlements that are close to irrigation schemes. | Not much experience so far | To be piloted in selected sites, with support from research |
|  | Fodder production on marginal land | Zones not very productive, overexploited through extensive grazing and under degradation | Take advantage of available land resources, helps increase revenues. | Pilot operations in project zones |
|  | Manage & maintain peripheral pasture areas | Overgrazing and overexploitation of adjacent pastoral resources to ON and PIV areas | Big problem in ON, where pastoral zones are not integrated in overall management concept | Develop local conventions and provide good technical support on how to improve the pastoral resources |
|  | Establish cattle corridors | Deterioration of irrigation infrastructure, land tenure conflict, straying animals | Implemented via live-fences | Establish conventions and agreements on how land resources are used around irrigation schemes. |
|  | Intensification of animal husbandry | Nutrition and health problems of animals kept in proximity to irrigation perimeters. | Important activity in integration of crop and livestock production systems | Extension of known methods: Stabulation, cut&carry feeding systems, collection of manure. |

|  | SLWM Technique | Responds to Constraints | Observations | Recommendations |
| --- | --- | --- | --- | --- |
| 2) Rainfed cereal production systems |  |  |  |  |
| Agriculture and agro-forestry |  |  |  |  |
|  | Improved cropping techniques | low yield levels and high variability in crop productivity | Many techniques are known, but may not be well adapted to local conditions | Demonstrations, farmer tests, developing good technical packages in collaboration with farmers |
|  | Crop association and rotation, improved fallows | Decline of available cropping area per household, loss of soil fertility, costs of inputs | Many techniques are known, but may not be well adapted to local conditions |  |
|  | Organic cotton | Excessive use of pesticides, pollution, health hazards, high costs of inputs | Needs specialized technical service and follow up, and coordination with experienced organizations | Based on demand, provide support for ongoing programs |
|  | Cover crops | Loss of soil fertility, wind and water erosion, non-sufficient availability of manure and compost | To be developed with research, higher potential in higher rainfall areas | Demonstrations and on-farm experimentation |
|  | Composting | Loss of soil fertility, reduced efficiency of chemical fertilizer application, high fertilizer cost, non availability of fertilizers | Needs training, collaboration with farmers to develop best composting techniques that respond to their available resources; Composting is labor intensive. | Comprehensive training, targeted approach with farmers or POs the project collaborates already |
|  | Micro-dosing of fertilizer | Loss of soil fertility, reduced efficiency of chemical fertilizer application, high fertilizer cost, non availability of fertilizers | Already a proven technique, needs good technical support and backstopping, follow up | To be promoted at large scale and based on demands from POs |
|  | Zero tillage and mulching | Water and wind erosion, soil fertility depletion and soil structure deterioration through extensive soil preparation, loss of soil humidity | Needs to training, technical support and follow up, to be implemented in targeted areas. | Promoted on demand by POs or communities, supervision by IER |
|  | Live-fences along contour lines, Jatropha live-fences | Wind and water erosion, loss of soil fertility, lack of high quality fodder resources, lack of diversified income. | Live-fence technologies are well developed in Mali (ICRAF/IER), and can fulfill many functions and produce a wide variety of products. | Targeted promotion. Association with private sector for some of the products. |
|  | Seed access grants | Access to new seeds often difficult | 2 years of experience already with DNA | Increase access to grants for POs, increase number of cooperatives |
|  | Land tenure security | Difficulty to invest in land with a long term vision | Tests implemented; ex Baguinéda | Pilot operations to be supported. |
|  | Assisted natural regeneration | Loss of vegetation cover, loss of biodiversity, loss of soil fertility, due to deforestation activities. | Efficient and less costly technique, Demands good training of forest agents, | Communal approach, Integration of NGOs for implementation |
|  | Support to forest management plans | Pressure from agriculture and livestock sector on forest resources and forest habitats | Several plans have been established, but not efficiently implemented. | Based on demand by POs in zones with high pressures on natural resources |
|  | Private and communal tree planting | Lack of fuel wood, construction wood, loss of productive land, deforestation | Number of experiences, Identify techniques that are less costly and well adapted to local conditions | Assist either farmers or communes |

|  | SLWM Technique | Responds to Constraints | Observations | Recommendations |
| --- | --- | --- | --- | --- |
| Soil and water conservation |  |  |  |  |
|  | Stone bunds (cordon pierreux) | Water erosion, loss of soil fertility / humidity | Technique known and wide-spread, adapted to certain ecosystems | Initiate micro-programs on demand from POs and through communes, |
|  | Vegetation strips | Water erosion, loss of soil fertility / humidity | Limited application, reduced area for cropping | Demonstration on demand by POs |
|  | Tied ridges (billons cloisonnés) | Water erosion, loss of soil fertility / humidity | High demands for labor and good technical inputs, specific zone | Extension on demand by POs, supervision IER |
|  | Zai/half moons (demi-lunes) | Degraded land lost to agriculture, loss of soil fertility | Well known, adapted to specified zones | Targeted extension, support to communes or to POs |
|  | Ravines treatments | Water erosion, loss of soil fertility / humidity | Needs a watershed management approach, on slopes | Support targeted programs on demand |
|  | Bench terrace (fossés ados) | Water erosion, loss of soil fertility / humidity | Needs animal traction | On demand by POs |
|  | Barriers weirs | Water erosion, loss of soil cover | Long term duration limited | Extension on demand by POs |
| Pastoral management |  |  |  |  |
|  | Local conventions on natural resource management | Integration of agriculture, livestock and forestry sector | Needs good communication between stakeholders, NGOs have expertise, support to communes | Promote where possible, good training and backstopping needed |
|  | Fodder production on agriculture land | Lack of fodder around settlements and villages where livestock is kept | Not much experience so far | To be piloted in selected sites, with support from research |
|  | Fodder production on marginal land | Zones not very productive, overexploited through extensive grazing and under degradation | Take advantage of available land resources, helps increase revenues. | Pilot operations in project zones |
|  | Manage & maintain peripheral pasture areas | Overgrazing and overexploitation of pastoral resources | Improve pastoral areas through seeding of fodder species, tree planting, rotational grazing etc. | Develop local conventions and provide good technical support on how to improve the pastoral resources |
|  | Establish cattle corridors | Land tenure conflict, straying animals, damage to crops | Implemented via live fences | Establish conventions and agreements on how land resources are used |
|  | Intensification of animal husbandry | Nutrition and health problems of animals kept on extensive systems | Important activity in integration of crop and livestock production systems | Extension of methods, collection of manure for agricultural fields. |

|  | SLWM Technique | Responds to Constraints | Observations | Recommendations |
| --- | --- | --- | --- | --- |
| 3) Fodder production systems |  |  |  |  |
| Fodder cultivation and production |  |  |  |  |
|  | Fodder bank | Depletion of forage resources; High pressure on natural pastures. | Experiences in Mali by NGO, eg. Ecoferm with Gliricidia | Demonstrations and farmer trials in pilot zones |
|  | Fodder crops | Lack of seeds for fodder species, decline in pastoral productivity | Localized experiences on a rage of species, e.g. Mucuna, Stylosanthes. | Appui aux coopératives de multiplication des semences IER |
|  | Fodder crops in irrigated systems | Too much pressure on pastures around irrigation perimeters | Little experience to date, with leguminous fodder species, soil fertility improvement can be achieved | Demonstrations and tests with POs |
|  | Cropping of Bourgou grass | Disappearance and depletion of natural bourgou areas | Techniques well known to improve bourgou cultivation areas | Extension of improved bourgou cultivation |
|  | Hay and silage production | Problem of availability of fodder resources, especially in the dry season | Localized experience | Demonstrations and tests with POs |
|  | Agro-forestry | Decrease of available fodder resources within the pastoral landscapes | Trees deliver multiple ecological functions and products | Broad dissemination in identified zones of potential |
|  | Assisted natural regeneration | Lack of management plans degrades vegetation substantially | With relatively little but targeted interventions, much can be produced | In identified locations and on demand from POs, proceed to extension |
| Pastoral management |  |  |  |  |
|  | Respecting carrying capacity in pastures | Overgrazing | Integration in pastoral conventions, norms/targets to be reviewed | According to demand by livestock PO |
|  | Conventions on pastoral resources | Overgrazing and overexploitation of pastoral resources | Good examples to be reviewed for lessons learned | Based on demand by livestock PO and communes |
|  | Pastoral protection/enclosure | Overgrazing, declining productivity of pastures | Several experiences in Mali, restores biodiversity and habitats | According to demand to assist communal investment plans |
|  | Fight against bush fires | Destruction of pastures and wildlife habitat, loss of biodiversity | Experience in the Northern Mali | Based on demand by livestock PO |
|  | Establishment and maintenance of water holes | Overcrowding of livestock around limited amount of water holes | Strategic planning at landscape level, with appropriate tools (GIS) | Investments to be planned under communal plans |
|  | Establishment and maintenance of cattle-corridors | Conflicts between animal herders and farmers, non-rational use of natural resources | Calls for investment to establish corridors | Assistance according to communal plans |
|  | Maintenance of trails for transhumance | Non-rational use of pastures and natural resources | Several experiences in Mali, calls for investments | Inter-communal activities, |
|  | Reseeding of pastures | Decline in fodder quality of pastures | Needs seeds and well established pasture management, | Test operations according to demand |
|  | Rotation in pastures | Overgrazing, declining productivity of pastures | Needs good organization and pasture management. | Extension into hot-spots |
|  | Forest management plan | Non-rational use of forage resources in forests | Needs investment | At communal level |

|  | SLWM Technique | Responds to Constraints | Observations | Recommendations |
| --- | --- | --- | --- | --- |
| 4) Animal production systems |  |  |  |  |
| 4 a) Milk production |  |  |  |  |
|  | Integrated livestock production system | Insufficient nutrition year round, pressure on pastures | Intensification effort nutrition and health plan for entire year | Proceed to pilot actions that can be further expanded |
|  | Fodder crop production | Overexploitation of pastoral resources | Not much efforts and research put into it | Pilot program on demand by POs |
|  | Cultivation of bourgou | Disappearance and depletion of natural bourgou areas | Techniques well known on how to improve bourgou cultivation | Assist POs and communes according to demand, extension of improved bourgou cultivation |
|  | Pastoral conventions | Overexploitation of pastoral resources | Well known in tradition, that can inspire conventions | To be integrated in areas with improved infrastructure for pastoral resources, milk production etc. |
| 4 b) Sheep and goat fattening |  |  |  |  |
|  | Protection of wood species fodder resources within pastures | Degradation of woody fodder species in pastures | Techniques known for regeneration and good management of woody species | Training of herders according to demand, integrate it in communal and inter-communal plans |
|  | Keep animals in stables, production of compost | High pressure on pasture resources, gain weight/ productivity is slow in extensive systems, | Allows for improved nutrition, improved meat productivity, manure collection | Available through FDA, according to demand of POs |
|  | Assisted natural regeneration | Lack of management plans degrades vegetation substantially | With relatively little but targeted interventions, much can be produced | In identified locations and on demand from POs, proceed to extension |
| 4 c) Poultry production |  |  |  |  |
|  | Production of cereals for fodder | Good feeding products not available year round | Use part of production to transform in poultry feed, Use 'Cereal Grants' for production and marketing | Targeted extension to POs |
|  | Integrated poultry production system | Insufficient quality nutrition year round | Availability of quality feed is reduced | Make it better accessible through input suppliers, credits etc |
|  | Adapted breeds | Animal health often a problem with highly bred poultry breeds | Breeds tested and selected are available | Available at FDA, on demand of POs |

Annex 19: Maps

Mali:  Fostering Agricultural Productivity Project

PNIR: Programme National d’Infrastructures Rurales (National Rural Infrastructure Project) closed on December 31, 2007.  PASAOP: Programme d’Appui aux Services Agricoles et aux Organisations Paysannes - (Agriculture Services and Producer Organizations Program) closed on December 31, 2009.

FODESA: Fonds de Développement en Zone Sahélienne (Sahel Areas Development Fund);  PDZL: Programme de Développement des Zones Lacustre (Lacustre Areas Development Program) ;  PIDRN: Programme Intégré de Développement Rural du Nord (Northern Integrated Rural Development Program).

The traditional ON partners have long ago established a donor coordination group that supported a successful reform in 1994 and still drives the policy dialogue.

PCDA: Projet Compétitivité et Diversification Agricole (Agricultural Competitiveness and Diversification Project; approved  on June 6, 2005)

WAAPP: West Africa Agricultural Productivity Project; approved on March 2, 2007

Through its special investment budget (BSI – Budget Special d’Investissement) and as a complement to the Project, the GoM will finance for an estimated amount of US$12 million : strategic research programs, construction and rehabilitation of agricultural buildings for research and training institutions and for APCAM.

Such as the on-going Denmark-funded PASAM (Projet d’appui au secteur agricole au Mali) in the Mopti region

Office du Niger (ON) is the public agency in charge of the management of the water system and land tenure for the large irrigation development of in the inner delta of the Niger River. This system is considered to be of national importance due to its high agricultural development potential. About 80,000 ha are currently under irrigation.

ACTION: Appui à la Consolidation Technique et Institutionnelle de l’Office du Niger – Support to the Institutional and Technical Consolidation of Office du Niger (€30 million).

Groupe PTF-EAR: Groupe des Partenaires Techniques et Financiers – Économie Agricole et Rurale (Financial and Technical Partners for Agricultural and Rural Economy): the group is co-chaired by FAO and the WB; working groups are active for Office du Niger development (under the leadership of the Dutch Embassy), small scale irrigation promotion (GTZ), livestock and fisheries (Belgium Embassy), and cotton reform and supply chains development (AfD-France).

PASSIP : Programme d’Appui au Sous-Secteur de l’Irrigation de Proximité – Small-Scale Irrigation Promotion Program.

SoSuMar: Société Sucière de Markala – Sugar Company of Markala (with private investments from ILLOVO).

PDI-BS: Programme de Développement de l’Irrigation dans le Bassin du Bani et à Sélingué - Irrigation Development Program for the Bani and Sélingué Basins.

PASAM: Programme d’Appui au Secteur Agricole au Mali – Agricultural Sector Support Program in Mali.

http://ige.nfrance.com/~k1009/jws1/

PASE: Projet d’Amélioration des Systèmes d’Exploitation – Farming Systems Improvement Project.

The Committee includes representatives of government agencies, as well as of the private sector and producer organizations. It will be responsible for overseeing the PNISA implementation, as well as its monitoring/evaluation.

CTCE will include directors and heads of the main entities involved in project implementation: Divisions of sector Ministries, APCAM, CNRA and Office du Niger. It will meet once a month under the chairmanship of the CPS director.

Rating of risks on a four-point scale – High, Substantial, Moderate, Low – according to the likelihood of occurrence and magnitude of potential adverse impact.

Based on the level of concrete field investments planned under components 1 and 2.

Regional Strategic Analysis and Knowledge Support System, facilitated by IFPRI in support of CAADP implementation (Fan, S., et al. (2009) ReSAKSS Working Paper No. 25)

PNIR closed on December 31, 2007 and PSAOP closed on December 31, 2009.

PCDA was signed on July 5, 2005 and started operating in April 2006.

PACR was signed on September 15, 2005 and started operating in March 2006.

Five other donor sub-groups exist on: (i) cotton reform led by AfD; (ii) Office du Niger and irrigation led by the Dutch Embassy; (iii) livestock production led by the Belgian Embassy; (iv) food security led by WFP and FAO; and, (v) environment (including SLWM) led by GTZ.

Petit Périmètre Maraîcher (Small scale irrigation perimeter for vegetable production)

Baseline: 10 people par farm unit

i.e. POs of a significant scale at both  regional and national levels, including commodity-specific (or sub-sector) umbrella federations.

In Mali, irrigation organizations carry the status of cooperatives, similar to some POs.  There is no specific legal framework for water users’ associations.

Research institutions include the Rural Economy Institute, the Central Veterinary Laboratory, the Agricultural College (IPR/IFRA) and the University of Bamako.

NARC includes 17 members: 4 from the line Ministries, 6 representatives of the Regional Research Users Committees, 3 civil scientists, 2 representatives of agribusiness and the private sector, 1 donor and the President of APCAM.

Natural sites where “bourghou” is grown in the Niger river delta. Bourghou is a traditional cereal of high nutritional value showing attractive marketing prospects.

In Mali, the collective entities in charge of water management are not distinct from producers’ organizations and are registered as cooperatives.

Technical and economic models have been developed by PCDA and validated by IER

As an alternative, the PO could out-contract the water supply to a service provider instead of acquiring the pump. This alternative approach will be tested during the project.

A minimum contribution from the PO will however be required to ensure ownership.

For example, the PO might be requested to sign a management contract with a service provider for the duration of the credit to ensure transparency and professional book keeping.

Office du Niger is the public agency in charge of the overall management of the water system and land tenure for the very large irrigation development area in the center delta of the Niger River. This hydraulic system is considered to be of national –and even international- importance due to its high agricultural development potential. About 80,000 ha are currently under irrigation.

This is a concern for dry season irrigation; during the rainy season, the Niger River flow is not a constraint, but the capacity of the canal system becomes one.

These models are based on the PNIR experience with Sokolo (traditional approach), Koumouna 1 (demand driven public scheme) and Koumouna 2 (public private partnership resulting in an autonomous scheme).

Appui à la Consolidation Technique et Institutionnelle de l’Office du Niger – Support to the Institutional and Technical Consolidation of Office du Niger (€30 million).

The usual financial partners of ON have long ago established a donor coordination group: it supported a successful reform in 1994 and still drives the policy dialogue with the government and the ON. Some of the partners are now evolving towards budget support, relying on indicators set out in the Contrat Plan to assess the managerial performance of the company. However, governance issues are not yet part of the Contrat Plan, even though past experience shows that they are a requirement for any modernization of the institution.

For example, the possibility of a twinning of ON with another regional hydraulic authority abroad will be assessed.

One producer organization has already shown interest in contributing to 2,000 ha of newly developed irrigation scheme while pursuing land consolidation on the existing areas, and has secured resources from a financial institution to cover a significant contribution to the costs.

The total financing reflected here does not include the UNDP-Mali contribution of  0.3 m, which is inclusive in the UNDP-Prodoc.

Comité Régional d’Orientation, de Coordination et de Suivi des Actions de Développement (Regional Steering Committee for the Coordination and Monitoring of Development Operations)

One PO has already shown interest in contributing to 2,000 ha of newly developed scheme while pursuing land consolidation on the existing areas, and has secured resources from a financial partner to cover a significant contribution to the cost.

In the case of Sabalibugu, it will be a revision of the existing study.

For example, Model 3 would require light soils adapted to diversification.

Such as, inter alia: governance and modernization of Office du Niger, setting-up specific financing mechanisms such as the “irrigation development fund” or the “national agricultural development fund”…

It should be noted that the project financial statements should be all inclusive and cover all sources and uses of funds and not only those provided through IDA funding. It thus reflects all program activities, financing, and expenditures, including funds from other development partners.

ICB: International Competitive Bidding

NCB: National Competitive Bidding

The project will seek to increase irrigated areas for rice production and to increase yields through improved technologies and service provision to producers as well as to promote diversification of production in irrigated areas to diversify income sources for producers.

The yearly per capita income of small farmers in the Office du Niger zone is estimated at 74,736 CFAF, while the poverty line for the Ségou region (rural) is estimated at 110,566 CFAF.

The project will seek to increase production by promoting better veterinary services, better feeding and some genetic improvement and to enhance commercialization by supporting the development of collection networks and transformation units.

Based on the assumption that 2% of the production is transformed and each transformation unit employs 20 persons.

Based on the assumption that 780,000 liters a year are distributed by 78 units employing each 5 persons.

The project will promote techniques to improve habitat, health and feeding.

DNACPN: Direction Nationale de l’Assainissement et du Contrôle des Pollutions et Nuisances (Sanitation, Pollution and Nuisance Control Division)

Agriculture alone contributes a third of the GDP.

DNRFFH: Direction Nationale des Ressources Forestières, Fauniques et Halieutiques (Halieutic, Faunistic and Forestry Resources Division)

Ramsar Convention on Wetlands of International Importance – Ramsar, Iran - 1971