Request for CEO endorsement/Approval

Project Type:

the GEF Trust Fund

Submission Date:  March 22, 2010

| Expected Calendar (mm/dd/yy) |  |
| --- | --- |
| Milestones | Dates |
| Work Program (for FSPs only) | June 2007 (SIP) |
| Agency Approval date | June 15, 2010 |
| Implementation Start | July 1, 2010 |
| Mid-term Evaluation (if planned) | July 2012 |
| Project Closing Date | December 31, 2013 |

part i:  project Information

GEFSEC Project ID: 3384

gef agency Project ID: 109737

Country(ies): Nigeria

Project Title:  SIP - Scaling up Sustainable Land Management Practice, Knowledge, and Coordination

GEF Agency(ies):

Other Executing partner(s): n/a

GEF Focal Area(s):

GEF-4 Strategic program(s): LD-SP1

Name of parent program/umbrella project:  Strategic Investment Program for SLM in Sub-Saharan Africa (SIP)

- Project framework

| Project Objective: To improve the enabling environment for scaling up sustainable land management in participating communities. |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| ### Project Components | ### Indicate whether Invstmnt, TA, or STA | Expected Outcomes | ### Expected Outputs | ### GEF Financing |  | Co-Financing |  | Total ($) c=a+ b |
|  |  |  |  | ### ($) a | ### % | ### ($) b | ### % |  |
| A. Capacity Building, Local Government, and Communication and Information Support | Invstmnt, TA | - Improved participation of communities in the mgt of natural resources - Improved capacity of stakeholders to advise on or implement SLM - Strengthened capacity of participating Local Governments for participatory planning - Improved capacity of Federal and State institutions to coordinate on rural land and water management across sectors - Improved awareness of SLM approaches at all levels | - Local Development Plans prepared, include SLM activities, and are under implementation - “Community SLM Award” grant facility established, which finances185 micro-projects for 185 “model” communities that are successfully implementing SLM projects using baseline co-financing. - Extension agents, communities, local government officials (1070 total) - Development of train-the-trainers program on SLM (6 SLM trainers trained) - Rural land use planning support packages in 60 local governments (2 in each of 30 States) including: (i) Training, (ii) GIS equipment (iii) development of rural land use plans - Nigeria SLM Investment Framework (Federal and State levels) - National communication strategy for SLM - Set of outreach materials (broadcasting, pamphlets, etc) - National awareness seminars, policy workshops and learning events on SLM implementation - National SLM gateway website - Simplified geospatial information system on land productivity and climate | 6,000,000 | 6.42 | 87,500,000 | 93.58 | 93,500,000 |
| B. Monitoring, Evaluation, and Knowledge | TA | - Knowledge on SLM is increasingly accessible to stakeholders. - Project resources are used effectively | - SLM monitoring tools developed and applied: - Composite Index for the Enabling Environment for SLM - Land productivity (Net Primary Productivity or NDVI/Green index) - Adoption rates of SLM - Area of land with SLM - Environmental benefits estimation tool - M&E training - SLM technical knowledge base - Impact evaluation, Project M&E, dissemination of M&E findings | 800,000 | 6.45 | 11,600,000 | 93.55 | 12,400,000 |
| Total Project Costs |  |  |  | 6,800,000 | 6.42 | 99,100,000* | 93.58 | 105,900,000 |

* This amount includes $2.7 million in project cost for re-financing project preparation cost. These costs are included in the overall loan that was submitted for Board approval.

*It should be noted that the actual co-financing for the overall project is much higher ($450 million) than the amounts reflected above given its integration with the Fadama III project. Please see Annex 5 (Detailed Project Description), Annex 6 (summary of baseline project) and 9 (project cost) of the project document for details on the overall project structure.

B.   Sources of confirmed Co-financing for the project (expand the table line items as necessary)

| Name of Co-financier (source) | Classification | Type | Project | %* |
| --- | --- | --- | --- | --- |
| Federal Government of Nigeria |  | Cash/In-kind | 21,802,000 | 22% |
| IDA |  |  | 71,352,000 | 72% |
| Local Government |  | In-kind | 4,955,000 | 5% |
| Local Communities |  | Cash/In-kind | 991,000 | 1% |
| Total Co-financing |  |  | 99,100,000 | 100% |

* Percentage of each co-financier’s contribution at CEO endorsement to total co-financing.

C.   Financing Plan Summary For The Project ($)

|  | Project Preparation a | Project b | Total c = a + b | Agency Fee (9%) | For comparison: GEF and Co-financing at PIF |
| --- | --- | --- | --- | --- | --- |
| GEF financing | 0* | 6,800,000 | 6,800,000 | 612,000 | 6,800,000 |
| Co-financing | 0** | 99,100,000 | 99,100,000 |  | 60,000,000 |
| Total | 0 | 105,900,000 | 105,900,000 | 612,000 | 66,800,000 |

*$200,000 allocated for a PPG, but funds have not been used and are returned.

**The Government used its own sources to mobilize staff for project preparation and financed cost of in-country travel of staff. Some of these costs were re-financed by the IDA loan.

D.  GEF Resources Requested by Agency(ies), Focal Area(s) and Country(ies)1

No need to provide information for this table if it is a single focal area, single country and single GEF Agency project.

E.  Consultants working for technical assistance components:

| ### Component | ### Estimated person weeks | ### GEF amount ($) | ### Co-financing ($) | ### Project total ($) |
| --- | --- | --- | --- | --- |
| ### Local consultants* | 1160 | 854,612 | 18,288,529 | 19,143,141 |
| ### International consultants* | 48 | 59,959 | 1,167,352 | 1,227,311 |
| ### Total | 1208 | 914,571 | 19,455,881 | 20,370,452 |

*  Details to be provided in Annex C.

f.   Project management Budget/cost***

| ### Cost Items | ### Total Estimated person weeks/months | ### GEF amount ($) | ### Co-financing ($) | ### Project total ($) |
| --- | --- | --- | --- | --- |
| ### Local consultants* |  |  |  |  |
| ### International consultants* |  |  |  |  |
| ### Office facilities, equipment, vehicles and communications* |  |  |  |  |
| ### Travel* |  |  |  |  |
| ### Others** |  |  |  |  |
| Total |  |  |  |  |

*  Details to be provided in Annex C.

** For others, it has to clearly specify what type of expenses here in a footnote.

*** No GEF funds will be used for project management, which is fully co-financed  ($47.7 million)

G.  Does the project include a “non-grant” instrument? yes     no 
      (If non-grant instruments are used, provide in Annex E an indicative calendar of expected 
        reflows to your agency and to the GEF Trust Fund).

H.  describe the budgeted m&E PLAN:

- The National Food Reserve Agency (NFRA), through the National Fadama Coordination Office (NFCO), has overall responsibility for M&E. It works in close collaboration with the State Fadama Coordination Office (SFCO) M&E units and Local Government Project Desks.  These decentralized units feed Project-related data from the local governments and the communities directly into the central M&E system at NFCO, which consolidates the monitoring and evaluation reports and include them in the quarterly, bi-annual, and annual progress reports. These reports are submitted to the National Fadama Technical Committee and the World Bank for review and further action. A results-based monitoring and learning system has being developed for the Fadama III project to improve real time monitoring of the entire Project cycle. The GEF incremental grant will rely on this, while strengthening the monitoring of environmental trends by project officers. The current M&E system of the baseline Fadama III project consists of self-monitoring at the community level, input-output monitoring through an MIS, a process monitoring system, a dedicated knowledge management system (to be strengthened on land productivity and SLM monitoring with GEF support), and impact evaluation. GEF support also adds, among other things, a spatial analysis function through GIS at the national level (see Component B2 of the GEF Project Document).

- Further, an impact evaluation of the overall Project (baseline project and GEF incremental grant) will be carried out in three stages by an independent agency. The cost is fully borne by the IDA support but the substance is relevant to evaluate the effectiveness of GEF incremental support as well. This impact evaluation will assist in determining progress toward local and global environmental public goods. A baseline survey is currently underway to assess pre-project conditions in the Project areas. The second stage will coincide with the mid-term review of the Project. The third stage, coinciding with the end of the Project, will evaluate the impact and outcome indicators. The work includes a detailed household survey, which will measure livelihood impact at the household and community levels, degree of use of SLM practices and climate risk reducing measures, and related agricultural development metrics such as yields, market access, land ownership/access, etc.

- As described above, the cost of the overall Project M&E system and independent impact evaluation are covered by the baseline Fadama III project. However, GEF will finance the incremental cost associated with evaluating the local and global environmental impact of on-the-ground SLM practices financed and implemented under the baseline Fadama III project (see monitoring tools 2 and 3 described below). GEF will further finance the development and application of a monitoring tool that will measure overall land productivity trends in the country (see indicator tool 4). The GEF allocation for M&E activities is $660,000. This is incremental to the baseline co-financing for M&E of $11.6 million. This GEF budget allocation includes cost for development and application of monitoring tools, carrying out annual assessments to measure and track indicators, associated capacity building for key stakeholders involved in M&E on land monitoring and SLM uptake, as well as support to strengthen technical expertise within the national coordination office. One aim is to support the Government to adopt indicator tools for continued use upon completion of the project. The following indicator tools will be developed and tracked:

1. Composite index for tracking changes in the enabling environment for SLM. This tool was originally developed under the GEF SIP, and was then applied in Nigeria during project preparation. It is a simple and low-cost perception based survey among experts of the extent to which the enabling conditions for SLM are improving or deteriorating.

2. Monitoring tool for tracking adoption rates and spatial coverage of specific SLM practices. Adoption rates of SLM and hectares affected by SLM can be estimated from the on-going comprehensive baseline household survey being carried out for the baseline project. GEF incremental support will be provided to compile data to quantify estimated adoption rates of SLM practices in the project area nationwide. These indicators as a national aggregate of local and state level figures, broken down by: agro-ecological zone, type of activity, community level and household level.  These indicators will be reported to the regional GEF-SIP umbrella and the Fadama III operation. Additionally, the indicator “land area with SLM practices” will be tracked by this project to report on the Country Partnership Strategy II. An on-going survey will establish the baseline values

3. Monitoring tool for estimating the global and local environmental benefits from the SLM practices tracked above. The patterns in the adoption rates tracked using the tool described above will be used to quantify estimated global and local environmental benefits accruing from the improved land management practices.

4. Monitoring tool for tracking changes in land productivity, land degradation, and overall ecosystem function nationwide. This tool will use freely available satellite data to track net primary productivity to estimate overall land degradation trends in rain-fed environments.

- A detailed description of the indicator tools is provided in project component B in Section II.D and in Annex 5 of the Project Document.

part ii:  project justification:

- State the issue, how the project seeks to address it, and the expected global environmental benefits to be delivered:

- Why land is a key asset of the rural poor in Nigeria:

- Seventy-six million rural Nigerians, mostly poor, are reliant upon natural wealth, while incomes and productivity in the rural areas are low and stagnant. The economic and ecological services provided by Nigeria’s renewable natural resource base constitute the rural poor’s only safety net, while also serving as the foundation of the country’s non-oil economic growth and food security. As such, sustainable agricultural development depends on land management practices that conserve soil and water, improve soil fertility and the biological potential for productivity, and that allow communities to adapt to climate variability and future change.  Not only do such practices help deliver important local benefits, they also help secure global environmental benefits such as carbon accumulation in biomass and soil, improved nitrogen cycling, higher water tables, in-situ biodiversity, and general ecosystem function.

- The status of land degradation and its impact on ecosystem functions and rural livelihoods:

- Land is the key asset of the rural poor. How productive land is managed therefore has implications for poverty alleviation and economic growth. Unsustainable land-use practices in Nigeria’s floodplains and other areas prone to land degradation, over-exploitation of natural resources, and on-going climate variability all pose threats to maintaining the productivity of agricultural lands, as well as ecosystem functions. Deforestation, large-scale land clearing, bush burning and floodplain encroachment have taken place mainly for agricultural production. This has resulted in severe gulley erosion in the south, desert encroachment in the north, reduced vegetation cover, loss of valuable top soil, siltation of water bodies and flooding. These and other forms of land degradation are directly impacting the sustainability of key systems and livelihoods. More details are available in section I and Annex 1 of the Project Document.

- An estimated 5% reduction of agricultural GDP from on-farm soil erosion alone is being felt. In some areas of southern Nigeria, this has caused yield reductions of about 30% to 90% (Mbagwu et al in IFPRI 2009).  Including other forms of land degradation as well as off-site costs would add to the overall economic cost. Land degradation trends resist easy quantification at the national level (CEA 2006) given data constraints, but the 1990 Global Assessment of Soil Degradation estimated that 27 percent of Nigeria’s land had degraded sufficiently to affect productivity. This assessment estimates that approximately three quarters of the Nigerian population live in areas with “severe or very severe” land degradation. More recent analysis estimates about 90% of the total land area to be under some form of soil erosion, which is severe in the northern states where overgrazing, strong winds and poor vegetation cover lead to both water and wind erosion (Thiombiano and Tourino-Soto, 2007). The southern states also experience severe soil erosion due to the high rainfall and continuing deforestation.

- Improving smallholder yield is also critical for slowing Nigeria’s rapid land conversions. Forest and savannah have provided much of the new cropland for Nigeria’s agricultural growth. The country now has the world’s highest deforestation rate of primary forests. From 2000 to 2005 the country lost 56% of its primary forests (FAO 2005). Nigeria also has Africa's highest rate of total forest loss: 2.8% compared to a Sub-Saharan average of 0.8%. The forest cover is now less than a third of what it was in the 1960s. From 1990-1995, cropping expanded at an annual rate of 1.5% of the country’s total land area, with roughly 70% of this expansion at the expense of relatively carbon-rich areas such as woody biomass in the savannah zones and forests in the east (World Bank 2005).  Cropland and rangeland productivity growth is needed to help reduce deforestation and vegetation loss.

- Opportunities for sustainable land management (SLM) practices in Nigeria:

- Many sustainable land management (SLM) practices have positive cost-benefit ratios in agro-ecologies throughout Sub-Saharan Africa, yet adoption is low in Nigeria.  Nigeria does benefit from some best-bet practices; for example, alley cropping using the trees Gliricidia and Leucaena reduced soil erosion by 73% and 83% respectively, while providing additional fodder, fuel, and nitrogen fixation. Erosion is also managed in Nigeria using mechanical methods or structures which serve as barriers using stones or vegetation along contour lines (Morgan 1995). These structures operate as filters, encouraging sedimentation, increased infiltration, and formation of natural terraces (Lal, 1990). The perennial Vetiver grass has served this purpose in many places in northern Nigeria (Malgwi, 1995) and is recommended as an appropriate soil conservation technology for semi-arid zones as it also withstands climate and land degradation risks such as denudation, fire, drought, and flood. Integrated soil nutrient management by combining artificial fertilizer, organic fertilizers and using soil-protecting mulches or other cover have been shown to have the highest cost-benefit ratios in Nigeria in the south, central and northern areas (Nkonya 2010 pending). These and other specific SLM practices can deliver improved yield while sequestering carbon in soil and biomass (For details see Annex 1 of the Project Document). In western Nigeria, no-tillage combined with mulch application had a dramatic effect, increasing soil carbon from 15 to over 32 tonnes per hectare in 4 years (Ringius, 2002). Not only is carbon sequestration critical for long-term climate stability, changes in carbon present in soil and biomass are considered proxy indicators for overall ecosystem function and land productivity and therefore the services that ecosystems deliver such as water filtering, biodiversity, soil formation and fertility, and so on.

- The barriers to adoption of SLM practices:

- The barriers to improved land and water management in Nigeria are centered on the enabling environment, specifically fragmented institutions, knowledge, and awareness. One obstacle in Nigeria is the lack of detailed knowledge about how to cost-effectively address land degradation and climate risks, including soil fertility and erosion, open access to grazing land, and deforestation. Awareness of the severity of these problems is weak, disputed, or based on weak data. As a result, only limited progress has been achieved in developing and disseminating sustainable and climate-smart agricultural land management practices. Land conserving technologies such as use of crop and pasture rotations, agro-forestry practices, integrated nutrient management, and integrated crop-livestock systems have had low rates of adoption, either because the technologies have been lacking, because farmer awareness has been low, advisory services are under-capacitated or unavailable to farming communities, or because incentives to adopt have been weak (World Bank 2009).  Fragmented institutional coordination, capacities, mandates, and policy have together resulted in frequent policy shifts and disincentives such as poor land access and overlapping or unclear ownership. These weaknesses are found at all levels, local to federal. One effect of this fragmentation is that the capacity to implement SLM has been compromised, resulting in, among other things, relatively weak leadership from the Nigerian government on articulating its rural land management investment priorities across sectors. Institutional performance is also hampered by knowledge gaps and fragmentation. For example, limited classification of land use capabilities exists, research and extension is isolated from investment and policy decision making, M&E on the state of the land resource is poor, and the scientific evidence base of land degradation and climate risks is outdated, based on unclear data, or is anecdotal.  Despite this, there are good SLM practices that can be scaled up (see Annex 1 of the Project Document).

- The Government’s response to address barriers for SLM:

- To better address these barriers, the federal government established a multi-sector platform to improve investment programming across the many facets of land management.  Its National SLM Committee is actively building a coordinated program-based approach to investment in land and water management. It is doing this by improving vertical and horizontal coordination of institutions and sectors involved in investment planning, analytics, and policy. The committee recognizes that land quality is critical to key sectors driving current and future economic growth, and fundamental for ecosystem sustainability and to reduce climate risk. As such, it aims to “expand the public sphere” around addressing land degradation and climate risk. The Committee is developing an Investment Framework to prioritize costed investments needed to bring SLM to scale to reduce risks from poor land management and climate variability.  This is being carried out with technical assistance from teams at NEPAD Regional Secretariat and the World Bank in the context of CAADP and the TerrAfrica partnership.

- Project approach to address the identified issues and barriers:

- Scaling Up SLM Practice, Knowledge and Coordination will be an incremental GEF grant focused on mainstreaming SLM in Nigeria’s agricultural sector by improving the enabling environment for SLM. The Third National Fadama Development Project (Fadama III) is the baseline operation, which is a $450 million investment project that is increasing rural income and reducing poverty in rural areas nationwide via community-driven smallholder agricultural development and alternative livelihoods. This project has evolved into a large-scale national community-driven rural development program different from the predecessor operations, which focused on floodplain agriculture in a limited number of States.

- Of this $450 million, $99.1 million is considered direct co-financing to the GEF increment. Fadama III directly reaches 2.2 million households, or approximately 12 million individuals, with a proven government-led implementation mechanism with nationwide reach and credibility. Fadama III is an important opportunity for mainstreaming SLM to secure long-term sector goals, and it is this aspect that the GEF support will focus on, while still leveraging a small amount of community driven micro-projects that can help strengthen a community of practice around SLM.  The GEF grant will be fully integrated into and coordinated with the existing baseline Fadama III operation. The two projects share the same structure, institutional set-up, and implementation mechanisms.

- The GEF grant focuses squarely on improving the enabling environment necessary for greater adoption of SLM practices. This approach includes building capacity and awareness for SLM practice and policy at national, state, and local levels in order to stimulate demand for on-the-ground investments in the baseline operation that will improve or protect land productivity. In particular, the GEF incremental grant funds the development of a knowledge support network, strengthens the institutional environment for investment programming, improves monitoring of land productivity and adoption of SLM practice, raises capacity of 60 local governments to carry out land use planning, and promotes inclusion of SLM practices and alternative livelihoods strategies into the Local Development Plans (LDPs) of at least 10% of communities. The GEF increment also establishes a new innovative feature grant facility that reinforces awareness raising and mutual learning via community driven micro-projects. This facility is the Community SLM Award, which awards grants (in the form of a follow-on micro-project) for up to 185 participating and eligible communities that successfully implement an existing SLM micro-project identified in their LDPs.

- Project management costs are co-financed entirely by the baseline operation. This approach was taken to avoid any parallel implementation structures and to strengthen strategic mainstreaming of SLM in the government structures at all levels.

- See Section II.E of the Project Document for lessons learned and strategic decisions taken in project design.

- Expected global environmental benefits:

- The GEF goal to secure global environmental benefits: The GEF support will contribute to safeguarding the ecosystem services provided by intact production systems such as floodplain cropping, grazing reserves or other community defined areas, generating intertwined global and local environmental benefits in up to 7400 participating communities throughout all of Nigeria’s agro-ecological zones. These benefits accrue from the uptake of selected SLM practices  that aim to maintain or expand vegetation cover, and improve soil quality and water retention (See annex 1, appendix 1 of the Project Document). The SLM practices promoted by the project are customized to Nigeria’s main agro-ecologies, and if selected and implemented by communities, can help land users address land degradation while also adapting to the adverse impact of climate change and climate variability. These practices also enable farmers to accumulate carbon in soil and biomass. This is important, as long-term soil and biomass carbon trends are considered a proxy for overall ecosystem function.

- Adoption of SLM in turn is dependent on improvements in the enabling environment, and this is where the GEF incremental grant is directly focused. The benefits to be delivered by the project vary, depending on type and rate of technology demanded by and adopted by rural communities, the local land degradation and climate risks, and the agro-ecological zone.

- The project will contribute to delivering global environmental benefits that center on key primary ecosystem services from well-functioning production landscapes. These include soil formation, carbon accumulation in soil and biomass, above and below ground biodiversity from improved crop and range management as well as avoided deforestation, improved ability of communities to adapt to climate variability and change, and lastly, improved infiltration and freshwater availability in transboundary basins. Local environmental benefits to be delivered by the operation center on secondary ecosystem services that result from the primary ecosystem services and include food, fuel, fiber, fodder, and freshwater.

- See Annex 15 (Incremental Cost Analysis) of the GEF Project Document for a more detailed analysis of global environmental benefits.

- Describe the consistency of the project with national and/or regional priorities/plans:

- Please refer to the Project Document para 14. Also refer to Annex 1 of the Project Document for a more detailed discussion on the country and sector background to the Project.

- Describe the consistency of the project with gef strategies and strategic programs:

- Consistency with GEF programming. The Project will directly contribute to the implementation of the GEF-4 Land Degradation Focal Area Strategy as listed below:

- SO-1: An Enabling Environment will place SLM in the mainstream of development policy and practice at regional, national and local levels;

- SO-2: Mutual benefits for the global environment and local livelihoods through catalyzing SLM investments for large-scale impact.

- SP-1: support to sustainable agriculture and rangeland management

In accordance with the GEF LD strategy, the focus is to mainstream and upscale sustainable land management practices as part of a program of investments in rural livelihoods by using a proven demand-driven delivery mechanism and by supporting local development planning and capacity building for SLM across local, state and national institutional support structures.

This project incorporates the principles set out in the Strategic Program 1 of the GEF Land Degradation Focal Area Strategy, and seeks to build a policy and institutional environment conducive to prevention and control of land degradation and effective actions on the ground, that protect ecosystem functions, such as carbon stocks and fresh water availability, and simultaneously improving livelihoods of rural land users including their ability to adapt and cope with the effects of climate change impact.

- Consistency with the GEF Strategic Investment Program for SLM in Sub-Saharan Africa (SIP). The GEF financing will be drawn from the envelope secured for Sub-Saharan Africa by the Bank-led multi-agency SIP, which is a key activity of the AU-NEPAD TerrAfrica partnership. As such, the Project conforms to the SIP principles and delivers on the SIP goal, objectives, and SIP intermediate results 1, 2, 3, and 4, as follows:

• 	Alignment with SIP result 1 (upscaling SLM on the ground): Most of the GEF incremental support will stimulate uptake of SLM by communities by improving the enabling environment. Baseline financing funds the vast majority of on-the-ground investment. Limited direct GEF financing for on-the-ground SLM practices is provided via the Community SLM Award grant facility, which is 100% GEF financed.

• 	Alignment with SIP result 2 (enabling environment): Institutions at federal, state, and local levels are better equipped to manage SLM programs and projects, plan and monitor across sectors on integrated approaches, and partner with communities to implement SLM.

•  	Alignment with SIP result 3 (extension): Advisory services have greater capacity to promote SLM practice.

•  	Alignment with SIP result 4 (knowledge and M&E): Better support given for benchmarking, and decision-making at all levels, via the development and implementation of an integrated knowledge management and M&E system with associated monitoring tools, and communication/dissemination strategy and materials.

- justify the type of financing support provided with the gef resources.

- The GEF grant described below provides incremental support to improve the enabling environment for upscaling climate-smart SLM. GEF funding will be mainly in the form of technical assistance, particularly for: knowledge fertilization, environmental and institutional monitoring tools, institutional capacity building at federal, state and local levels, and outreach and advocacy on SLM practice and policy. Investment financing from GEF will fund a small grant facility to reward successful implementation of community-level investments in SLM sub-projects financed under the baseline Fadama III project, and help scale up community investments in SLM. This is called the Community SLM Award. It will help raise awareness on the benefits of SLM practices, help embed additional SLM activities into Local Development Plans, and help create a network of community practitioners. GEF incremental support will assist Nigeria to upscale improved land and water management, and set the stage for expanding SLM practice beyond the life of the Project.

- Outline the Coordination with other related initiatives:

The GEF Project falls under the umbrella of the multi-agency GEF Strategic Investment Program (SIP) for SLM in Sub-Saharan Africa, which was developed by the World Bank and NEPAD with TerrAfrica partners. Twenty-five African countries participate. The Project will therefore exchange experiences with other projects in the SIP portfolio through the NEPAD knowledge platform being established with UNEP and TerrAfrica multi-donor support managed by the World Bank.

The World Bank, along with NEPAD’s TerrAfrica partnership, are providing technical support to Nigeria in its on-going effort to strengthen investment programming on land use and management via national coordination and multi-sector, multi-State dialogue on investment priorities. Associated work to build institutional capacity to carry out this agenda is further supported under Project component A.  The World Bank, IFPRI, ICRISAT, and TerrAfrica are also engaged in complementary work to strengthen the analytical underpinnings for scaling up SLM, including a review of public expenditure, costs, and benefits of land management interventions, using the Niger basin cases of Cross River, Sokoto, and Niger States.

The portfolio of World Bank Assistance in Nigeria had three major projects which used the CDD approach in design and implementation and were recently completed. All three projects have a common origin, and so operated largely in rural communities and were similar in their approaches:  Community-based Poverty Reduction Project (CPRP); Local Empowerment and Environmental Management Project (LEEMP); and the Second National Fadama Development Project.

- Discuss the value-added of GEF involvement in the project demonstrated through incremental reasoning:

Please refer to Annex 15 of the Project Document for a detailed incremental cost analysis.

- Indicate risks, including climate change risks, that might prevent the project objective(s) from being achieved and outline risk management measures:

Critical risks that my prevent the project objectives form being achieved and respective risk mitigation measures are described in detail in Section III.E as well as Annex 8 of the Project Document.

Mitigation of climate change risks is an integral part of project design. There is broad-based recognition that sustainable land management is an effective response for addressing the challenges of land-related climate impact. SLM reduces the vulnerability of agricultural production systems to climate change and increases people’s ability to adapt to changing conditions and extreme weather events. In many cases, SLM even contribute to climate change mitigation through improved carbon sequestration and reduced emission of greenhouse gases.

As part of project preparation an assessment of climate risk perceptions and adaptation strategies of Nigerian farming communities was undertaken. Objective of the analysis was to assess community and household perception of environmental and climatic conditions and changes in a range of agro-ecological zones in Nigeria, and to document on-going adaptation strategies that can be inserted into investment operations. As part of the analysis recommendations for land management investments to better help farmers to reduce climate risks were formulated. Recommendations can be grouped in three broader categories: i) The need for improved knowledge and information access, ii) The need for economic and policy incentives, iii) the need for scaling-up successful land management practices and other adaptive strategies. More detailed information on the analysis is provided in Annex 2 of the Project Document.

- explain how cost-effectiveness is reflected in the project design:

A cost-benefit analysis was carried out for selected land management options in Nigeria as part of a parallel on-going analytical work sponsored by the World Bank and TerrAfrica and implemented by IFPRI. Key findings have been incorporated into project design. The approach compares profit of agricultural production with and without SLM practices.  Overall, preliminary results (February 2010) suggest that land management practices that combine organic and inorganic fertilizers and crop residues are more sustainable than those that use either one of them alone. A detailed description of the draft findings of this analytical work is summarized in Annex 1, Appendix 3 of the Project Document.

Cost effectiveness is also reflected in the strategic emphasis of the GEF grant on improving the enabling environment for SLM, rather than in subsidizing investments on the ground. GEF support is rather focusing on leveraging and influencing larger IDA financing and counterpart investment in communities nationwide. There is significant potential for the GEF grant to catalyze a transformational change in smallholder agriculture in Nigeria.

Lastly, the GEF grant is cost-effective to implement as its administration is covered by the larger baseline loan and integrated completely with the existing nationwide implementation arrangements. These are described further below.

part iii:  institutional coordination and support

- Institutional arrangement:

- Implementation arrangements for the GEF financed activities as described above simply build on the existing implementation arrangements in place for the baseline operation. The Federal Ministry of Agriculture’s National Food Reserve Agency leads implementation of the project. Implementation of the GEF incremental grant is fully integrated into the existing design and implementation arrangements of the baseline loan; no additional institutional structures or lines of accountability will be created.

- For more detail, please refer to Section III.A and Annex 10 of the Project Document.

- Project Implementation Arrangement:

- Implementation responsibilities for specific GEF-financed activities are summarized below by sub-component. Components A and B of the incremental GEF grant reinforce existing components 1 and 6 of the baseline loan, respectively.

- Implementation of Component A. Sub-Component A1, Capacity Building for Community Organizations, is implemented at the federal/zonal level under the lead of National Fadama Coordination Office (NFCO) using the train-the-trainers approach. SLM Trainers are deployed to the 6 zonal coordination levels, but administratively report to the NFCO. Implementation responsibilities for sub-Component A2, Capacity Building for Local Governments for Rural Land Use Planning, are at local government level and guided by Local Fadama Desks (LFDs).  60 Local Governments have been selected for support with rural land use planning support under the GEF grant. For Sub-Components A3, Communication and Outreach, and A4, National and State Coordination on Land and Water Management, implementation responsibilities are split between the federal level under the lead of NFCO and the state level under the lead of the State Fadama Coordination Office (SFCO), respectively. Activities financed through the small grant mechanism under Sub-Component A5, Community SLM Award, will be implemented at community level by Economic Interest Groups (EIGs) and Fadama Community Associations (FCAs) with support from the Local Fadama Desk (LFD). Award ceremonies at zonal level will be carried out by NFCO in coordination with SFCO. SFCO will monitor implementation of awarded sub-projects grants as per usual procedures under the baseline Fadama III project.

- Implementation of Component B. Both Sub-Components,B1, Monitoring Tools, and B2,  SLM Information System and Knowledge Base, are fully implemented at the federal level under the lead of NFCO.

- For more detail, please refer to Section III.A, Annex 5, and Annex 10 of the Project Document.

part iv:  explain the alignment of project design with the original PIF:

- The Project is fully aligned with the original design proposed in the PIF. However, the Project has evolved into a stronger design since PIF approval and is still focused on improving the enabling environment for SLM. This is fully in line with GEF-SIP priorities to remove barriers and improve enabling environments rather than fund pilots on the ground with limited GEF resources.  The proposed project design therefore aims for maximum mainstreaming opportunities. To achieve this goal, the following alternative design options were considered and rejected:

- Project Scope – nationwide coverage versus focus on three pilot States:  The final project design moves beyond a focus on SLM investments in three states to nearly nationwide coverage focusing on strategic mainstreaming of SLM into local, state and national planning, as well as related knowledge and information support that can convene and strengthen a Nigerian community of practice on SLM. The potential is now higher for the GEF to make a lasting positive impact on the enabling environment to drive and monitor SLM adoption, and leverage much greater financing. These aspects are summarized below.

- At the PIF stage, $2.4 million of the GEF grant was designed to target SLM adoption in only three selected States, with correspondingly smaller financial leveraging opportunities. The GEF grant would have served as a parallel or add-on financing to the CDD delivery mechanisms established under the baseline project and would have served to help cover the cost of community level investments into SLM interventions. Given the limited scope of GEF funding, on-the-ground investments and environmental impact would have been limited to a small number of sub-project sites within the three selected States.  This initial design would have allowed limited opportunities for up-scaling SLM practices and little impact in other States. This option was refined to fund instead a Community SLM grant facility. This refinement was partly in consideration of client wishes to avoid the perception of political favoritism among States --  but also of the enormous opportunity for mainstreaming environmental objectives into a flagship nationwide rural development program, Fadama III, that is expected to reach 2.2 million beneficiary households or roughly 12 million individuals, and that is already deeply part of implementation structures and priorities of the federal government, all 36 state governments, and a substantial number of local governments. The potential for a lasting impact on the enabling environment to drive and monitor SLM scale up is great.

- GEF financed activities implemented at the state level will not cover all 36 States of Nigeria though. Instead, GEF support will focus only on those 30 States plus the Federal Capital Territory that do not yet have institutional structures for cross-sectoral coordination and rural land use planning in place. In the six States not covered by this grant (Imo, Kebbi, Kwara, Kogi, Ogun, and Bauchi), state-level watershed committees have already been established. These state committees will operate as sub-committees to the National SLM Committee chaired by FMAWR, Consequently, these six States are excluded from additional GEF investments in an effort to avoid duplication of existing state-level external funding support for capacity building on SLM.

- Despite having a stronger emphasis on barrier removal than pilot demonstration investment that originally foreseen in the PIF, the GEF grant does still retain some direct investment on the ground. This support is channeled strategically directly to communities to (i) serve as an incentive to communities to incorporate SLM into their local development planning, (ii) to reward those communities that successfully implement SLM activities with public goods, and (iii) to strengthen an emerging community of practice around SLM.

- Focus on mainstreaming versus parallel pilot investments: Instead of creating parallel pilot investments, the proposed GEF project design takes advantage of the opportunity to mainstream environmental objectives by relying on the nationwide implementation structure of Fadama III. This structure is proven to be robust, and has been adapted and fine-tuned to the Nigerian context over the last 10 years. Relying on the already existing matching grant facility for community driven development sub-projects provides an opportunity for substantive investments in SLM practices across all of Nigeria. A high leveraging potential can be achieved if beneficiary communities are assisted in identifying SLM technologies with immediate or short-term economic returns and longer-term environmental benefits. As such, the proposed project hinges upon the assumption that the access to advisory services that can credibly promote profitable SLM technologies and knowledge sharing will incentivize community groups to prioritize SLM activities in local development planning.  Innovative features of the project, such as an implementation award grant for communities implementing SLM practices under Fadama III, will strengthen outreach and awareness-raising.

- Focus on barrier removal, rather than on pilot demonstration investments: Previous efforts to scale up SLM by investing in pilots in critical ecosystems were designed to demonstrate the multiple benefits of SLM and serve as a catalyst for replication. However, experience has shown that demonstration investments have fallen short of meeting expectations due to failure to address an entrenched set of barriers. Key barriers to SLM include: fragmented institutional coordination, capacities, and mandates, policy as well as knowledge gaps. These barriers result in persistent institutional underperformance and hinder greater adoption of SLM. Accordingly, the proposed design of the GEF project places a strategic focus on reducing these barriers by enhancing capacities and knowledge to promote greater adoption of SLM practices.

- Support an implementation award grant rather than limited top-up financing for the existing matching grant facilities: Ring-fenced GEF financing for SLM through the existing matching grant facilities under the Fadama III Project components 2 and 5 was considered. Ring-fencing is meant to provide an incentive for beneficiary communities to invest in SLM practices that only become economically viable in the long-term and/or generate predominantly off-farm benefits. The ring-fenced option was rejected for several reasons: (i) The limited scope of the GEF resource envelope would have resulted in a comparatively small ring-fenced grant facility with little added impact; (ii) Further, the prospect for sustainability and potential for self-financed uptake and replication by other farmers across Nigeria would have been low for SLM activities without competitive short-term profitability. As a result, the strategic focus of the GEF support for improved practice in the field centers on providing a reward for communities that implement SLM activities successfully under the Fadama III project, combined with associated knowledge management and institutional development. This will help build awareness while incentivizing greater adoption of SLM and helping mainstream SLM into community local development plans and local government planning.

Project objective: In line with the adjustments presented above (i.e. nation-wide scope, focus on strengthening the enabling environment), the Objective of the Project was also adjusted to better reflect the incremental nature of the GEF grant in terms of reinforcing capacities of stakeholders, improving the enabling environment with knowledge fertilization, outreach and advocacy on SLM practice and policy.

Project Components: The component design of the Project has not changed since PIF approval. However, instead of attaching support to advisory services to component 4, the incremental GEF grant is now using a train-the-trainers approach. The mass of community facilitators and public extension agents deployed under Fadama III was found to be substantive and adequate with GEF financing not adding significant value by financing additional staff. Instead GEF incremental financing will focus on building the capacity of public and private advisory services and facilitators to help communities to identify and prioritize climate-smart land and water management practices.

- Co-financing: Since PIF approval, the IDA envelope increased to $250 million and the counterpart secured financing of $200 million. Co-financing has thus increased in a corresponding manner. The portion of that co-financing that serves as the baseline for the GEF increment, however, is calculated at  $99,100,000.

part v:  Agency(ies) certification

This request has been prepared in accordance with GEF policies and procedures and meets the GEF criteria for CEO Endorsement.

| Agency Coordinator, Agency name | Signature | Date | Project Contact Person | Telephone | Email Address |
| --- | --- | --- | --- | --- | --- |
| Steve Gorman, Executive Coordinator, The World Bank |  | March 22, 2010 | Paola Agostini, GEF Regional Coordinator | 202 473 7620 | pagostini@worldbank.org |

Annex A: Project Results Framework

Note: This results framework includes only those incremental results for which the GEF incremental support is directly accountable, given that its implementation hinges upon already established and functioning implementation structures. For the results framework of the baseline loan, in which the below is integrated, see project #P096572 in the World Bank external website.

| Development and Global Environment Objective | Indicators |  | Use of Monitoring Information |
| --- | --- | --- | --- |
| To reinforce capacities of stakeholders to reduce the threat of land degradation and climate risks on ecosystems in participating communities | Stakeholders with perceived improvement in the enabling environment for sustainable land management (reported as an increase in score on tracking survey: Composite Index for the Enabling Environment for Sustainable Land Management). |  | To assess improvements or deterioration in the enabling conditions for implementing SLM (institutional capacities, policy, knowledge). |
| Intermediate Outcomes | Indicators |  | Use of Monitoring Information |
| Component A: Capacity Building, Communication and Information Support |  |  |  |
| - Improved participation of communities in management of natural resources. - Improved capacity of stakeholders to advise on or implement SLM. - Strengthened capacity of participating Local Government Authorities for participatory planning. - Improved capacity of Federal and State institutions to coordinate on rural land and water management across sectors. |  | - % of participating communities that have selected SLM sub-projects for inclusion in their Local Development Plans (LDPs). - Number of people reached through training and communications on SLM practice (disaggregated by stakeholder type: extension, community facilitators, etc) - Number of local governments trained in rural land use planning. - Nigeria’s multi-sector SLM Investment Framework developed by Federal and State governments. | - Confirms community interest in self-managing the use of their natural resources. - Helps target information and training efforts. - Informs local investment prioritization and resource use decisions. - Measures the ability of Government to convene knowledge and stakeholders to improve investment programming and resource use decisions related to rural land productivity and climate resilience. |
| Component B: Monitoring, Evaluation and Knowledge |  |  |  |
| - Knowledge on SLM is increasingly accessible to stakeholders. | - Improved monitoring tools developed to track adoption of SLM practices and changes in land productivity. - Key stakeholders trained in applying the monitoring tools. - SLM Information System developed |  | Informs knowledge on drivers and rate of adoption of SLM practices and the impacts on land resources. To assess progress on consolidating fragmented knowledge on climate-smart soil and water conservation. |

Results Monitoring Arrangements

|  | Indicators | Baseline Value | Target Values |  |  |  | Data Collection and Reporting |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Dec 2010 | Dec 2011 | Dec 2012 | Dec 2013 | Frequency of reporting | Data Collection Instruments | Responsibility for Data Collection |
| Development and Global Environment Objective |  |  |  |  |  |  |  |  |  |
| To reinforce capacities of stakeholders to reduce the threat of land degradation and climate risks on ecosystems in participating communities | Stakeholders with perceived improvement in the enabling environment for sustainable land management (reported as an increase in score on tracking survey: Composite Index for the Enabling Environment for Sustainable Land Management) | Score: -0.3 | Score: 0.0 | Score: +0.5 | Score: +1.0 | Score: +1.5 | Annual | Tracking surveys of experts (ie Composite Index for the Enabling Environment for SLM) | NFCO M&E specialist, with SFCO M&E specialists |
| Component A: Capacity Building, Communication and Information Support |  |  |  |  |  |  |  |  |  |
| 1. Improved participation of communities in the management of natural resources. | % of participating communities that have selected SLM sub-projects for inclusion in their Local Development Plans (LDPs). | 0 | 1% | 3% | 6% | 10% | Annually | Administrative Records | SFCO/M&E specialists NFCO aggregates |
| - Improved capacity of stakeholders to advise on or implement SLM | Number of people reached through training and communications on SLM practice (per year): - community facilitators - extension & advisory services - local govt - state govt - federal govt - Totals | - 0 - 0 - 0 - 0 - 0 - 0 | - 85 - 35 - 50 - 50 - 25 - 245 | - 250 - 50 - 50 - 50 - 150 - 550 | - 450 - 200 - 350 - 150 - 350 - 150 | - 300 - 100 - 450 - 150 - 250 - 125 | Annually | Administrative Records | SFCO/M&E specialists NFCO aggregates |
| - Strengthened capacity of participating Local Government Authorities for participatory planning. | Number of local governments trained in rural land use planning (cumulative). | 0 | 0 | 20 | 40 | 60 | Annually | Administrative Records | SFCO/M&E specialists NFCO aggregates |
| - Improved capacity of Federal and State institutions to coordinate on rural land and water management across sectors | Nigeria’s multi-sector SLM Investment Framework developed by Federal and State governments | Terms of Reference approved by Government’s National SLM Committee | Cross River State + federal govt | 5 total states + federal govt | 10 total states + federal govt | 20 total states + federal govt | Annually | Administrative Records | NFCO/M&E specialist, with National SLM Committee |
| Component B: Monitoring, Evaluation and Knowledge |  |  |  |  |  |  |  |  |  |
| 1. Knowledge on SLM is increasingly accessible to stakeholders. | Improved monitoring tools developed to track adoption of SLM practices and changes in land productivity | 0 | 0 | 2 tools | 0 | 0 | Annually | Administrative Records | NFCO/M&E specialist |
|  | Key stakeholders trained in applying the monitoring tools (per year) | 0 | 25 | 25 | 25 | 25 | Annually | Administrative Records | NFCO/M&E specialist |
|  | SLM Information System developed | None exists | Under develop-ment | On-line | On-line | On-line | Annually | Administrative Records | NFCO/M&E specialist |

Annex B: Responses to Project Reviews (from GEF Secretariat and GEF Agencies, and Responses to Comments from Council at work program inclusion and the Convention Secretariat and STAP at PIF)

A. Comments from GEF SEC at the time of Work Program Inclusion:

- Need for a consistent logframe with the detail of activities and outputs to reach the outcomes.

Response: A detailed project description is provided in Annex 5 of the Project Document, that explain objectives at project-level, component-level, and sub-component level, as well as activities financed by sub-component and outputs expected. The Project Framework presented in Table A of this memo aims to summarize outcomes and outputs consistently. Project outcomes and respective indicators are further presented in the Results Framework.

- To understand the role of the GEF grant, the budget needs to be broken down by sources.

Response: A detailed budget break-down by sub-component has been provided in the detailed project description in Annex 5. Baseline cost versus incremental cost are further presented in table 1 of the Incremental Cost Analysis in Annex 15.

- Component budgets and co-financing will need to be confirmed.

Response: Component (and sub-component) budgets as well as co-financing is presented in the Project Document. Minutes of negotiation will confirm all co-financing.

- Synergy and coordination with other initiatives.

Response: Please refer to Part II. E. of this memo.

- M&E programme consistent with the SIP results framework.

Response: The operation is aligned with the SIP M&E and TerrAfrica more broadly. The project will contribute data and information to the regional platform to be aggregated in order to reinforce country and project comparisons within and outside the SIP portfolio.

At the level of GEO, the key performance indicator is measured by applying a tool developed during SIP preparation: the composite index for the enabling environment for SLM.

At the level of intermediate results, the operation will deliver on a number of SIP results as follows:

- Knowledge on SLM is increasingly accessible to stakeholders. This is measured by the number of monitoring tools developed, number of stakeholders trained, and the operationalization of an SLM information system.

- Improved capacity of stakeholders to advise on or implement SLM.

- Improved capacity of Federal and State institutions to coordinate on rural land and water management across sectors. This is measured by Nigeria's preparation of a Country SLM Investment Framework, in accordance with the SIP.

- Additional SIP-compliant metrics will be used to track the environmental performance of the full integrated project (both GEF increment and baseline financing) by the project team but the GEF grant itself will not be accountable for delivering the environmental performance. This will be carried out as an activity to strengthen institutional capacities and knowledge. This approach has been taken because the GEF grant is focusing on improving the enabling environment, while the IDA financing is covering technology investment on the ground. The metrics include (i) adoption rates of SLM practice, (ii) estimations of environmental benefits from that adoption, including soil and biomass carbon, (iii) changes in Net Primary Productivity in rainfed systems. These metrics will be fed into the SIP/TerrAfrica regional M&E system once it is functional and good data is being generated.

- Detailed risk analysis.

Response: A detailed risk analysis has been provided in Section III E. of the PAD. Project risks pertain mainly to the community demand for SLM. Due to the community demand-driven nature of the baseline project, achievement of global environmental benefits on the ground hinges upon the prioritization of SLM in the local development plans. The Project is putting in place a comprehensive program to build awareness, knowledge, and eventually demand for SLM practices that are economically viable and competitive as well as suitable for the relevant agro-ecological zone. A multi-layered capacity building program is supporting communities in successfully scaling up investments in SLM.

Specifically on climate risks, an analysis of farming communities’ perceptions of climate risks and recommended response strategies was carried out during project preparation and is summarized in Annex 2 of the Project Document.

B. Comments from GEF SEC at the time of submission to the GEF CEO:

GEF Secretariat review question 8 and 24.

Please, confirm that these environmental indicators will be developed and implemented (question 8). … We would like to find some of these indicators in the M&E plan (question 24).

Response:

Yes, this is confirmed. A baseline for one of them is already available, and the baseline for the second will be this FY. The indicators will be developed, packaged and applied as tools to (i) help build client capacity to track global and local environmental benefits not only from this project but for all land related projects in Nigeria through the country’s SLM Investment Framework and CAADP planning now on-going, and (ii) to report on the Country Partnership Strategy-II (CPS-II) indicator for “land area with SLM practice.”  (The CPS-II is the assistance strategy for Nigeria that guides WB, DfID, USAID and AfDB).

However, these indicators cannot easily be used in the GEF Project’s Results Framework to report on the GEF investment because the GEF investment is focusing on the enabling environment. There is therefore an issue of direct attribution to GEF. As per the legal procedure at the WB  (and also best practice in M&E) projects report directly only on those elements that a project can directly control – in this case, activities to improve enabling environment. In fact, new World Bank regulations (March 2010) require that we attach results frameworks to legal agreements. Because the investments on the ground are financed from the IDA and counterpart financing, the baseline project M&E plan is already reporting on adoption rates of SLM practices; a baseline is now being prepared.

We do agree that it is important for the combined baseline and GEF incremental support to report on adoption rates of SLM practice and land affected. The M&E work therefore includes activities to carry this out in the form of institutional development activities. The GEF incremental support will also estimate the local and global environmental benefits arising from the increased adoption – but will not hold the GEF directly accountable for directly delivering on the increased adoption, although the GEF will influence it by improving the enabling environment.

Considering the above, we have inserted language in the CEO memo in section H on M&E that the project will report on adoption rates of SLM practices and affected land area to: the SIP regional M&E desk and for the Nigeria Country Partnership Strategy II (see question 11 below).

GEF Secretariat review question 9.

Please revise the logical framework to be consistent with the details given in the annex 5 of the project….  Please revise the framework including all outcomes and outputs mentioned in the text.

Response:

This has been revised. See specific answer below under question 24, and the updated GEF CEO memo in track changes.

GEF Secretariat review question 11.

Who are the other partners supporting agriculture in Nigeria? What has been the level of dialogue and partnerships between the IA and other partners? How partners are working together? Thanks to clarify.

Response:

The World Bank is the largest supporter of agriculture in Nigeria and works very closely with all other major partners active in the sector. The Country Partnership Strategy II is the assistance strategy for the Bank as well as DfID, USAID, and AFDB, which together account for 80% of ODA to Nigeria. A key indicator in the CPS-II is “area of land with SLM practices.”  The Fadama III project and GEF incremental grant are the vehicles for delivering on this. Due to its large-scale national footprint and integration into Government structures, the Fadama Project open doors for collaboration with other development partners’ projects. For example, there is collaboration with USAID’s MARKETS project on capacity building and assisting with farmers on linking with markets. DFID Propcom is assisting in areas where fadama farmers choose rice value chains. The project is linking with IFAD in Ogun State. Lastly, the project has close linkages with the CGIAR especially the International Institute on Tropical Agriculture on technology support, and with IFPRI which is carrying out analytical work for the project and is delivering for the World Bank a closely related cost-benefit analysis on SLM, and a major SLM and climate change analysis covering four countries including Nigeria. These are being used in project preparation and in formulating the country’s emerging SLM Investment Framework and CAADP process.

TerrAfrica, in which the Bank, NEPAD, and GEF participate, has been providing technical assistance and has liaised with key partners in the country to support the Government in its efforts to build an investment coalition on SLM (as noted in the project document). The main focus has been building capacity of the government’s National SLM Committee to lead the SLM dialogue among international partners. On this, the National SLM Committee has presented its work and vision to donors. The GEF support will provide for building and capacitating coalitions in each State, building on extensive in-State consultations led by the National SLM Committee in each State in 2009. The National SLM Committee has approved partnership principles, and one of their key tasks in 2010 is to extend this to international donors. The GEF support is expected to help capacitate the federal and state levels to do this, and will support the National Committee as it leads delivery of an SLM investment framework.

GEF Secretariat review questions 13, 14 and 16.

How to maintain a credible cost effectiveness approach with 30 States while the PIF was focusing on 3 States for the same GEF grant? Thanks to clarify.

(Consistency with PIF): - The PIF was focused on pilot demonstration investments in SLM….We may admit that the revised project is based on the same building blocks. However, the use of $6.8 million from the GEF is becoming quite different, as we cannot compare the work on 3 pilot States to the extension to 36 States (only 30 States will benefit from the GEF grant). Please clarify. … Second, the building blocks of the logical framework, plus the outcomes, and the outputs are more or less the same for the project document and the PIF. This argument is given in the section to check if the project document is sufficiently close to the PIF. However, this is difficult to imagine that the role of the GEF $6.8 million grant for 3 pilot States will be the same for 30 states. Is there not a risk of scattering? How can you convince the GEF Council that GEF resources representing 1.3% are going to influence the $450 million operation? … A third option may be to revise the incremental reasoning and to focus on the additional role of the GEF on improving the enabling environment for SLM (component 1 and 6). These changes will affect the project structure that may be simplified (and the components not deeply affected by the GEF grant may be removed - components 2, 3, and 4). Response: The “third option” above is best suited and the GEF CEO memo re-emphasizes the already existing focus on the enabling environment at Federal, State, and local levels. From the beginning, the majority of the GEF incremental support (nearly $5 million) has been for improving enabling environment at all levels, not only in three States; this has been constant from PIF stage to the current project, and is consistent with the GEF-SIP. In line with the above, see the revised GEF project framework on page 1, the updated section on project approach and global benefits on page 8 of the CEO memo, as well as updates in Part IV of the CEO memo. But first, it should be clarified that the PIF was not focusing only on three States; most of the GEF financing at PIF stage ($4.8 million) focused on the enabling environment at Federal level, all 36 States, and some local governments. That has not changed substantively. For the on-the-ground investment in SLM practices, the design evolution has followed a natural progression as would normally be expected in cases where GEF financing is blended with a larger program. In particular, during conceptualization at the PIF stage, only $2.4 million of the total grant was earmarked for SLM activities on the ground in three States based on a preliminary estimation and discussion with counterparts. Over the course of preparation, this has now evolved to $1.91 million (reflecting the actual cost) in community SLM award grants for up to 5 communities in each of 30 States which are so motivated on SLM that they successfully implemented a first SLM micro-project (with baseline co-financing) and would then be rewarded by GEF with a second follow-on micro-project. It should however be noted that, although the project will cover 30 states owing to its strong integration with the Fadama III and for better catalytic impact, only a handful of communities (185 in total) will be identified for the SLM award grants. Therefore, the number of communities to be targeted is not much different from the PIF stage, but only the options and range for selection of the communities has been increased from 3 to 30 states in line with the overall program. This will help solidify a nationwide community of practice by raising awareness and identifying success factors for later upscaling. It may also serve as an additional incentive to SLM uptake. The CEO memo has been revised to include the Community SLM Award as an output in Section A, the project framework. Second, during preparation, the government expressed reservations about a three-state approach and favors a nationwide mainstreaming approach focused on the enabling environment. This shift is not out of line with the PIF. Further, at PIF stage, GEF SEC review stated “The cost effectiveness will be looked for with the institutional and planning improvement, and the replication of the experience.” This approach is precisely the approach taken by the GEF incremental support. Thus, the GEF support is indeed focusing on the enabling environment for scaling up SLM. This support includes institutional and planning improvements, knowledge and advisory services, and improved monitoring tools – coupled with the aforementioned community SLM award grant facility. Together, such improvements will help replicate successes and build a community of practice nationwide, linking the community, local, state and federal levels. Third, this emphasis on the enabling environment is a key feature and result of the regional GEF-SIP SLM umbrella, from which this project is funded.

GEF Secretariat review question 18.

Based on the actual project document, the GEF grant represents 1.4 percent of the total investement. The GEFSEC is not sure to figure out how the project will be affected without the GEF. The reasoning was valid for 3 States, but strongly weakened by the exension to 30 States. Thanks to clarify.

- Response:

- Please see the previous response for the same context.  Additionally, it is important to explain that, first, GEF support is critical to build a community of practice in the country around SLM technology, planning, policy, and institutions. The GEF support is directly incremental to two components, and in accordance, the co-financing has been adjusted to reflect the direct co-financing for just these two components. More important than the funding levels, the values represented by GEF involvement in this project are ensuring that the parent project is prioritizing SLM interventions to a greater degree than would otherwise be the case. The Project Framework in section A of the CEO memo has been adjusted to focus on an increment that now reaches over 6% of the revised project total financing.

- Second, it is a mistake to think that the project simply expanded from 3 to 30 States (see response to questions 8 and 24, and 13, 14 and 16 above). The PIF stated that only the investments on the ground would focus on three State pilots; at PIF stage, the design was based on a preliminary discussion of the components. And this was always around $2 million of the project design. The design was refined during preparation (see responses to questions 13, 14, and 18 above). This refinement was partly in consideration of client wishes to avoid the perception of political favoritism among States -- but also of the enormous strategic opportunity for mainstreaming environmental objectives into a flagship nationwide rural development program, Fadama III, that is expected to reach 2.2 million beneficiary households or roughly 12 million individuals, and that is already deeply part of implementation structures and priorities of the federal government, all 36 state governments, and a substantial number of local governments. The potential for a lasting impact on the enabling environment to drive and monitor SLM scale up is great.  In any case, GEF support still retains $1.91 million in on-the-ground investment through the new Community SLM Award grant facility that would support a relatively small number of especially motivated communities in 30 States. Because this implementation award is considered part of the communications and awareness building strategy to help bring together a community of practice, this will have a much more catalytic impact than pilots in a few States.

- Importantly, the real ground-level investment in SLM comes from the IDA and counterpart financing – and this is catalyzed by GEF incremental support to strengthen the enabling environment for SLM to build awareness, share knowledge and begin the process of scaling up not only within this project but post-project, by setting the stage for institutionalizing SLM in the agriculture sector. The GEF has a great opportunity to be truly catalytic and strategic here.

GEF Secretariat review question 19 and 22.

Question 19:

- Activities related to project management and M&E should be under 10% ($680,000). Based on the elements given in the text, we understand the following elements:

- no GEF resources will be used for project management;

- the additional resources for monitoring ($660,000) are requested to design and implement a scientific and technical monitoring to assess the results in term of enabling environment and field outcomes (primary productivity).

- Training and knowledge management are also included in this component to strengthen national capacities ($140,000).

Based on these elements, above, the component may be accepted. Please, confirm.

Response:

Confirmed. The GEF incremental support is only focusing on these two elements, knowledge and M&E. The corresponding baseline component in the approved loan package finances project M&E but also finances project management and safeguards, which the GEF support is piggybacking entirely upon. Given the national scale of the project, this is extremely valuable to the GEF and enables the GEF incremental support to be well implemented through a proven robust implementation structure.

The GEF incremental support here provides only for developing and applying key tools that will help the government monitor the land resource and SLM uptake and affected land area. All activities under component B are focused on raising country capacity to monitor land productivity, SLM uptake and environmental benefits, and to methodically share knowledge from that M&E work. This will allow the country to know better which practices are working, where, and why. That will in turn facilitate scale-up and replication of SLM practices. These monitoring tools will be used not only in the project but can be used outside it as well through the SLM investment framework, CAADP investment plan, and future operations on climate risk, etc.

Question 22.

- Most of the GEF grant (6 million) is used in the component 1 on capacity building, with a cofinancing of $87 million.

- $800,000 are supporting knowledge management ($140,000) and monitoring ($660,000). The co-financing is very impressive: $59,300,000. Can the WB confirm that more than 59 million are going to be used for monitoring and evaluation?

Response:

Component A’s co-financing is confirmed at $87.5 million.

On component B, it is confirmed that no GEF resources will be used for project management. The $59.3 million in baseline co-financing breaks down as follows: Project management ($47.7 million) and M&E ($11.6 million). The GEF support is relying entirely on the $47.7 million in baseline financing for project management and implementation. The $800,000 in GEF support is incremental to the $11.6 million in baseline financing for M&E. In fact, the CEO memo on page 4 reads that the GEF support in component B “is incremental to the baseline co-financing for M&E of $11.6 million”  The GEF CEO memo has now been revised in table A to include only this baseline $11.6 million for M&E. Having said that, it should be kept in mind that because the GEF increment is integrated into the baseline Fadama III project, the true co-financing for project implementation is the entire financing of the baseline project. That is good value for money for the GEF. A footnote has also been included in the CEO memo explaining this.

GEF Secretariat review question 20.

- The annex 9 is much summarized and the table p.105 gives a breakdown for all the project. A breakdown of disbursement categories by component would have been appreciated. Thanks to clarify.

- For the consultants: based on the information provided in the table E of the CEO endorsement memo: the costs per week for local consultant are around $3,000 and $5,000 for international consultant. This is much higher than the usual practice in the region. Please, confirm.

Response:

For the first issue, below please find a table of World Bank disbursement categories broken down by component.

| Components |  | Cost by Project Year ($m) |  |  |  |  | Cost by Disbursement Category ($m) |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Title | Yr1 | Yr2 | Yr3 | Yr4 |  | Services | Operational Cost | Training& Workshops | Equipment | Community Grants | Total |
| A | Capacity Building, Local Government, and Communications and Information Support | 1.50 | 1.01 | 2.39 | 1.10 |  | 1.52 | 1.52 | 0.62 | 0.49 | 1.85 | 6.00 |
| A.1 | Capacity building support for community organizations for local development planning | 0.52 | 0.24 | 0.26 | 0.27 |  | 0.90 | 0.16 | 0.02 | 0.21 |  | 1.29 |
| A.2 | Capacity building for local governments for rural land use planning | 0.62 | 0.33 | 0.38 | 0.17 |  | 0.04 | 0.85 | 0.34 | 0.28 |  | 1.51 |
| A.3 | Communication and Advocacy | 0.22 | 0.30 | 0.29 | 0.01 |  | 0.45 | 0.30 | 0.05 |  |  | 0.81 |
| A.4 | Support national and state coordination on land and water management | 0.14 | 0.15 | 0.12 | 0.08 |  | 0.13 | 0.20 | 0.15 |  |  | 0.48 |
| A.5 | Community SLM Award |  |  | 1.33 | 0.58 |  |  |  | 0.06 |  | 1.85 | 1.91 |
| B | Monitoring, Evaluation, and Knowledge | 0.25 | 0.17 | 0.22 | 0.16 |  | 0.65 | 0.04 | 0.11 |  |  | 0.80 |
| B.2 | Monitoring tools | 0.14 | 0.16 | 0.21 | 0.16 |  | 0.51 | 0.04 | 0.11 |  |  | 0.66 |
| B.2 | National Technical Knowledge Base | 0.11 | 0.01 | 0.02 |  |  | 0.14 |  |  |  |  | 0.14 |
| TOTAL COST |  | 1.75 | 1.18 | 2.61 | 1.26 |  | 2.17 | 1.55 | 0.73 | 0.49 | 1.85 | 6.80 |

For the second issue, the consultant rates are actually in line with regional Bank practice but the wrong timeframe was listed giving the impression of higher than normal rates. This has been corrected. Thank you for pointing this out. It is worth noting that the Bank uses lump sum contracts for firms, and this can raise overheads.

GEF Secretariat review question 24.

- Under the component A-1, the expected result is to have 5% of the communities that will have selected SLM sub-projects in their Local Development Plans? That does not seem very motivating for a $6 million investment, does it? Please, confirm.

- Please clarify the monitoring indicator used under B1 (2 tracking tools to measure the adoption of SLM practices and changes in land productivity?).

Response:

Component A-1: The above target is now revised from 5% to total 10% by project end (see results framework). However, it should be clarified that it is not accurate to equate a $6 million expenditure with the result of mainstreaming SLM activities in communities’ Local Development Plans, when the Project is doing much more than that. These plans are only one way the project is investing in improvements to the enabling environment for SLM.  For example, of the total project funding, almost $2 million is going to investment in on-the-ground micro-projects through the Community SLM Award; $1.5 million is going to local government land use planning, almost $1 million is given to monitoring tools and knowledge systems, and nearly another $1 million is given to federal and state investment planning and coalition building (including the SLM investment framework process supported by GEF-SIP and TerrAfrica).  In any case, the project may very well exceed the target for the total % of communities that include SLM activities in their Local Development Plans. But 5% was a minimum target ensuring minimum success. Considering that there are 7400 participating communities in the baseline project, this seems to be good value for money. Now that the target is raised to 10%, it is even better value.

Second issue: Yes, the target refers to the number of tools delivered.  For more detail, please see the response to questions 8 and 24 above.

GEF Secretariat review question 27 (CEO Endorsement).

Thanks to address the comments above. Please focus on:

- revising the incremental reasoning,

- adjust accordingly the logical framework and the consistency from the outcomes to the outputs (please, include the activities described in the project document, as the environmental award).

- Adjust the Monitoring Plan.

- Adjust the cofinancing.

- Remove the mention to management costs in the component 6.

- And confirm the synergy and the coordination with other initiatives.

Response:

All changes made as requested, along the lines described in the responses above. These changes may be seen in track changes in the updated GEF CEO memo.

Annex c: consultants to be hired for the project using gef resources

|  | $/ | Estimated person weeks** |  |
| --- | --- | --- | --- |
| Position Titles | person week* |  | Tasks to be performed |
| For Project Management |  |  |  |
| Local |  |  |  |
| International |  |  |  |
| For Technical Assistance |  |  |  |
| Local |  |  |  |
| SLM training program | 72,134 | Firm contract (lumpsum) | Development of SLM training program and content of training material |
| 6 zonal SLM Trainers | 857 | 160 (each) | Lead capacity building efforts for SLM in the six different project zones |
| Communication Strategy | 63,648 | Firm contract (lumpsum) | Production of communication strategy, including content of communication message for different media channels (radio, tv, print, etc.) |
| Updates of Communication Strategy | 16,890 | Firm contract (lumpsum) | Annual updates of communication strategy and program (3 updates in 2011, 2012, 2013) |
| Technical Assistance - Backstopping SLM Committee | 572 | 40 | Back-stopping technical support for development and nurturing of Sate-level SLM Committees |
| SLM Website Development & Maintenance | 15,912 | Firm contract (lumpsum) | Develop SLM Website and maintain/update it |
| TA - Diagnostics to support process of investment alignment and institutional capacity building | 804 | 56 | Technical assistance with diagnostics and stocktaking exercises to provide quality information for SLM investment prioritiziation |
| SLM Investment Specialist | 829 | 32 | Finalization of Investment Framework |
| NRM Specialist | 516 | 72 | Technical input (technology guidance ) and coordination support related to SLM activities |
| M&E Specialist | 516 | 72 | Technical input, guidance and coordination support for SLM M&E |
| GIS Specialist | 341 | 72 | Technical input, guidance and coordination on GIS and land use mapping in coordination with Local Governments |
| M&E: Track Composite Index | 91,444 | Firm contract (lumpsum) | Track Composite Index for changes in SLM enabling environment (phased contracts: 2010, 2011, 2012, 2013) |
| M&E: Track SLM Adoption Rates | 45,722 | Firm contract (lumpsum) | Track SLM Adoption Rates (phased contracts: 2010, 2011, 2012, 2013) |
| Indicator Tool for local and global environmental benefits | 31,824 | Firm contract (lumpsum) | Develop Indicator Tool for local and global environmental benefits |
| M&E: Track environmental benefits | 91,444 | Firm contract (lumpsum) | Track environmental benefits (phased contracts: 2010, 2011, 2012, 2013) |
| M&E: Track NDVI, NPP | 91,444 | Firm contract (lumpsum) | Track NDVI, NPP (phased contracts: 2010, 2011, 2012, 2013) |
| Geospatial application for Knowledge Base | 140,007 | Firm contract (lumpsum) | Integration of geospatial tools in Knowledge Base: Develop GIS function that maps project interventions and SLM Investment Framework Priorities, online inventory of diagnostic work, etc. |
| International |  |  |  |
| Develop Tool for changes in land productivity, land degradation, and overall ecosystem function nationwide | 31,824 | Firm contract (lumpsum) | Develop Tool for tracking NDVI, NPP |
| TA - training, peer-review, advice on M&E | 2,345 | 12 | Technical assistance on M&E: peer review, training, |
| Justification for Travel, if any: Some daily subsistence and travel allowance will be provided when consultants travel within the country to local project sites. |  |  |  |

*  Provide dollar rate per person week.    **  Total person weeks  needed to carry out the tasks.

Annex d:  status of implementation of project preparation activities and the use of funds

- explain if the ppg objective has been achieved through the ppg activities undertaken.

A PPG in the amount of $200,000 was approved by the GEF, however the GEF funds were not used for preparation and are returned. The team relied on other sources to prepare the operations.

- describe findings that might affect the project design or any concerns on project implementation, if any:

- provide detailed funding amount of the ppg activities and their implementation status in the table below:

| Project Preparation Activities Approved | Implementation Status | GEF Amount ($) |  |  |  | Co-financing ($) |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | Amount Approved | Amount Spent Todate | Amount Committed | Uncommitted Amount* |  |
| Total |  |  |  |  |  |  |

*  Any uncommitted amounts should be returned to the GEF Trust Fund.  This is not a physical transfer of money, but achieved  through reporting and netting out from disbursement request to Trustee.  Please indicate expected date of refund transaction to Trustee.

No GEF support for project management costs, which are fully co-financed.

$800,000 breaks down to 660,000 for M&E and 140,000 for knowledge management.

In a study published by the U.S. National Academy of Sciences, an international team of scientists confirmed the rule of thumb emerging among crop ecologists that for each 1 degree Celsius rise in temperature above the norm during the growing season, farmers can expect a 10% decline in wheat, rice, and corn yield (S Peng et al., Proceedings of the National Academy of Sciences, 6 July 2004, pp. 9,971–75).

“Fadama” is a Hausa name for irrigable land, usually low-lying plains underlay by shallow aquifers found along major river systems.  They play an important role in the recharge of the shallow groundwater system through infiltration. Fadamas have historically supported highly productive natural vegetation consisting of dense acacia scrubland, open grassland and seasonally or permanently flooded open bodies of water supporting dense emergent vegetation. In addition to providing a source of water and forage for pastoral livestock during dry season, fadamas also support large and diverse resident or transient wildlife including herbivores, carnivores and migratory birds, many of global significance.

The widely cited Global Assessment of Human Induced Soil Degradation (GLASOD) was conducted for UNEP by the International Soil Reference and Information Centre (ISRIC) at Wageningen University. Soil scientists were asked to categorize soils degraded over the previous 45 years due to human intervention.

Includes Federal Ministry of Agriculture and Water Resources (Committee Chair, and includes CAADP focal point), Federal Ministry of Environment, the Federal Ministry of Finance, the National Planning Commission, Nigeria Meteorological Agency, and NEPAD Nigeria.

The SIP principles are: (i) Country has demonstrated commitment to the SLM related objectives of NEPAD’s environment and agriculture programs (CAADP, EAP) and the ECOWAS Implementation Action Plan; (ii) The operation contributes to reaching SIP results; (iii) The operation commits to using harmonized indicators and benchmarks to measure SLM scale up and progress toward established goals at regional program level; (iv) The operation exceeds the 1:4 financial leveraging ratio for SIP operations (GEF: non-GEF). The SIP is a key activity in the TerrAfrica joint work program, in which the Bank, Nigeria, GEF and NEPAD actively participate.

Component A is incremental to component 1 in the baseline loan.

Component B is incremental to component 6 in the baseline loan.