| No. | IOE comments | Responses |
| --- | --- | --- |
|  |  | Revisions have been made accordingly to Section / paragraph cited below. |
| 1 | Relevance: This section does not assess the relevance of the project and its objectives with the relevant GEF policies. Some more detail on which GEF Policies the project was aligned with would be required. The GEF terminal evaluation guidelines foresees an assessment of the appropriateness of the design for delivering the expected outcomes but this is not assessed (although there is an assessment of the log-frame under project performance and impact p.21 and an assessment of the design process para 91). Such an assessment would have been particularly useful given that the project seem to have been designed in a rather disjointed manner with the GEF part being added later. | Relevance is addressed under Outcome Relevance (para 55) as well as under Sustainability (para. 113) per TORs and Outline provided. |
| 2 | Outputs: Many outputs were changed and/or discarded making the assessment challenging. Nonetheless, the overall achievement of outputs is rated highly satisfactory. This assessment is based on the number of pasture herder groups established (120 against a target of 120) and development of pasture management plans (para 48) (no intended or actual target indicated) and increased knowledge of herders and local government on CC and the reduction of vulnerability. A number of other outputs were dropped and/or not met (e.g. pasture land under improved management and women participation in decision making bodies). The rating of highly satisfactory needs to be better justified. | Some outputs were dropped after the first supervision mission and these were explained in Para 48 – 50. The rating of highly satisfactory is given due to the meeting of the targets/outputs set during the mid-term review (para 51). However, since there are indicators that were not met and not suitable for measuring (and two rounds of changing targets para 10 -17), the rating is changed to satisfactory. |
| 3 | Outcome efficiency: This section does not contain a real assessment of whether the project was cost effective. Instead it mentions an incremental cost analysis (ICA) done for the CEO Endorsement submission and the cost of various activities but without assessing the efficiency with which activities were executed. | Outcome efficiency is addressed through a qualitative approach (para. 56). No quantitative-based analysis was attempted due to lack of easily accessible data in the PMU, absence of an economist on the mission and questionable relevance of assessing alternative economic returns based on grant funding. |
| 4 | The overall M&E system is rated satisfactory yet it appears to have been weak from design (e.g. not including bio-physical indicators) and poorly implemented which was raised in several supervision reports but not adequately followed up (para 87). | M&E design rating changed to moderately satisfactory based on the weaknesses identified by periodic supervision missions (page 24). Therefore overall rating changed to moderately satisfactory (page 25). |
| 5 | Sustainability is rated low but according to the GEF Guidelines should be rated likely to unlikely (low is not a rating). Under institutional framework and governance risks it would seem that the pending status of the pastoral law (which is not mentioned) could pose a threat to benefits streams. | Ratings changed page 22 |
| 6 | IFAD Performance in Ensuring Quality at Entry. The rating of moderately satisfactory seems overly positive as compared to the narrative which highlights that quality assurance focused on the Value chain development and did not sufficiently address (e.g. disconnect between logframe and PDR see para 93-97). | Agreed, IFAD performance in ensuring quality at time of entry changed to moderately unsatisfactory. |