H.1 INTERNAL STRUCTURE

The main mechanisms for the implementation of the project are the MEA Task force/Steering Committee and a Technical Advisory Panel (TAP).

As Executing Agency, NEPA will execute, manage and be responsible for the project and its activities on a day-to-day basis, with UNEP PCDMB acting as Execution Support agency to ensure technical, financial and administrative needs are met.  NEPA will establish the necessary managerial and technical teams to execute the project. UNEP PCDMB with NEPA collaboration will search for and hire any consultants necessary for technical activities and supervise their work. UNEP PCDMB will acquire equipment and monitor the project; in addition, it will organize independent audits in order to guarantee the proper use of GEF funds.  Financial transactions, audits and reports will be carried out in accordance with national regulations and UNEP procedures. UNEP PCDMB will provide regular administrative, progress and financial reports, and final audit report to UNEP DEWA.

A MEA Task Force and Project Steering Committee will be created and will meet on a quarterly basis throughout the project. This committee will be formed of the key Ministries involved in the project, with Secretariat services provided by NEPA and UNEP PCDMB. The committee will address substantive issues at political level, evaluate the project and take necessary measures to guarantee fulfillment of goals and objectives.

A Technical Advisory Panel (TAP) will be created to manage the technical aspects of the project. This will be composed from technical expert levels within the participating Ministries. The TAP will meet on a monthly basis and will develop the main substantive outputs of the project as well as providing information up to the MEA Taskforce/ Steering Group.

A Project Team (PT) and Project Coordinator will be established within NEPA as the Executing Agency: this team will be in charge of the execution and management of the project and will work together with the UNEP Afghan Country Programme Manager as well as the Scientific and Technical Advisory Panel and the MEA Taskforce/ Steering Group. This team will meet regularly to allocate specific responsibilities over the project activities.

H.2 EXTERNAL STRUCTURE & OVERSIGHT MECHANISM

UNEP’s Division for Early Warning and Assessment (DEWA) will provide the implementation oversight as part of UNEP’s Implementing Agency functions. The project will be executed by the National Environmental Protection Agency (NEPA) with technical execution support from UNEP Post Conflict and Disaster Management Branch via its Afghanistan country programme.

As Implementing Agency, UNEP DEWA is responsible for overall project supervision, overseeing the project progress through the monitoring and evaluation of project activities and progress reports, including technical issues. UNEP DEWA will work in close collaboration with the Executing Agency (EA) NEPA and the Execution Support Agency UNEP PCDMB.

H.3 ORGANIGRAM

Provincial and District Decision Makers and Natural Resource Managers

MoF

MoFA

ANDMA

MRRD

MAIL

UNEP DEWA (Implementing Agency)

Steering Committee

Committee for Environmental Coordination (as per Env Law)

TECHNICAL ADVISORY PANEL (made up of technical representatives from MAIL, MRRD, ANDMA, NEPA, MoFA, MoF, CBO & NGOs)

NEPA

(MEA Unit)

UNEP Afghanistan (execution support)

NEPA (executing agency)

Project Support Committee )

Executing cluster