GEF-6 Project Identification Form (PIF)

Project Type: full Size Project

Type of Trust Fund: GEF Trust Fund

PART I: Project Information

| Project Title: | Sixth Operational Phase of the GEF Small Grants Programme in Bolivia |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Country: | Bolivia | GEF Project ID: |  |  |  |  |
| GEF Agency: | UNDP | GEF Agency Project ID: |  |  |  | 5731 |
| Other Executing Partner(s): | UNOPS | Submission Date: |  |  |  | 1 Sep 2015 |
| GEF Focal Area(s): | Multifocal Areas | Project Duration (Months) |  |  |  | 48 months |
| Integrated Approach Pilot | IAP-Cities IAP-Commodities IAP-Food Security |  |  | Corporate Program: SGP |  |  |
| Name of parent program: |  |  | Agency Fee ($) |  | 345,297 |  |

A. indicative Focal Area  Strategy Framework and Other Program Strategies

| ### Objectives/Programs (Focal Areas, Integrated Approach Pilot, Corporate Programs) | ### Trust Fund | ### (in $) |  |
| --- | --- | --- | --- |
|  |  | ### GEF Project Financing | ### Co-financing |
| BD-4 Program 9 | GEFTF | 1,744,657 | 2,568,495 |
| CCM-2 Program 4 | GEFTF | 1,054,064 | 1,551,799 |
| LD-3 Program 4 | GEFTF | 835,982 | 1,230,737 |
| Total Project Cost |  | 3,634,703 | 5,351,031 |

B. indicative Project description summary

| ### Project Objective: To enable local communities in the Chaco, Chiquitania and Pantanal eco-regions in Bolivia to enhance and sustain their livelihoods by protecting natural habitats, restoring degraded ecosytems and improving productivity and sustainability of production landscapes for socio-ecological resilience. |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| ### Project Component | ### Financing Type | ### Project Outcomes | ### Project Outputs | ### Trust Fund | ### (in $) |  |
|  |  |  |  |  | ### GEF Project Financing | ### Co-financing |
| 1. Resilient landscapes in the Chaco, Chiquitania and Pantanal eco-regions for sustainable development and global environment protection | TA | 1.1 Local governance strengthened to promote and enhance resilience in the five prioritized Natural Parks and Natural Areas for Integrated Management (PN/ NAIMs) 1.2 Restored and enhanced ecosystem services and biodiversity through replication and scaling up of innovative community-based interventions in the five PN/NAIMs in the Chaco, Chiquitania and Pantanal eco-regions 1.3 Improved sustainability and productivity of agroecosystems in the PAs through community-based interventions in the prioritized PN/NAIMs 1.4 Alternative livelihoods enhanced in the target landscapes (PA/NAIMs) through the development of innovative products and market access 1.5 Practices to improve energy efficiency and renewable energy to improve livelihoods in the five NP/NAIMs | - Five landscape strategies developed with the participation of community stakeholders, PA/NAIMs Management Committees, and involved municipalities in the target landscapes. 1.1.2 Multi-stakeholder landscape agreements to enable and catalyze implementation by communities of the landscape management strategies 1.1.3 Participatory implementation of the NP/NAIM Monitoring Plans. 1.1.4 Policy and innovation platforms established for discussion of project lessons and experience by NGOs, communities and local government officials and other stakeholders 1.2.1 Landscape management plans implemented through joint (association of municipality and CSOs) actions for conservation of BD, water management and CC mitigation. 1.2.2 Community forest fire prevention strategies developed and under implementation in the NP/NAIMs. 1.3.1 Sustainable and high resilience agroecological practices and systems implemented in the target landscapes. 1.3.2 Traditional knowledge of crop genetic resources including wild relatives of domesticated species recovered, documented and disseminated (corn, peanuts, peppers, wild fruits and medicinal plants). 1.4.1 Innovative products and services (apiaries, nursery gardens, community ecotourism, non-timber forest products, native fish farming) identified and supported. 1.4.2 Strengthened market links for CSO agroecological products with market research supported by INIAF, identification of potencial commercialization channels. 1.5.1 Renewable energy technologies and energy efficiency (photovoltaic water pumping systems for human and animal consumption, micro-irrigation, water supply to health facilities and school, fuel efficient stoves) to support the development of productive uses in the five NP/NAIMs. | GEF | 3,000,000 | 4,433,711 |
| 2. Capacity building and knowledge management | TA | 2.1. Community and local civil society organizations increase their organizational and technical skills through training and knowledge management. | 2.1.1 Best practices for adaptive management for landscape resilience identified, systematized and shared with community organizations, CSOs, NP/NAIM Management Comittees, municipal and departamental governments. regional and national level (through SERNAP). 2.2.2 Dissemination of applied research results with the five NP/NAIMs and broader sector. | GEF | 461,622 | 662,509 |
| Subtotal |  |  |  |  | 3,461,622 | 5,096,220 |
| Project Management Cost (PMC) |  |  |  | GEF | 173,081 | 254,811 |
| Total Project Cost |  |  |  |  | 3,634,703 | 5,351,031 |

C. Indicative sources of  Co-financing for the project by name and by type, if available

| Sources of Co-financing | Name of Co-financier | Type of Co-financing | Amount ($) |
| --- | --- | --- | --- |
| CSO | Community grantee organizations | Grants | 250,000 |
| CSO | Community grantee organizations | In-kind | 1,000,000 |
| Recipient Government | SERNAP | Grants |  |
| Recipient Government | SERNAP | In-kind | 200,000 |
| Others | EU-VMA | Grants | 2,751,031 |
| Others | Local Goverments (Municipalities) | Grants | 480,000 |
| Others | Local Goverments (Municipalities) | In-kind | 320,000 |
| Others | BIOCULTURA – COSUDE/APMT | Grants | 150,000 |
| GEF Agency | UNDP | In-kind | 150,000 |
| GEF Agency | UNDP | Grants | 50,000 |
| Total Co-financing |  |  | 5,351,031 |

D. Indicative Trust Fund  Resources Requested by Agency,  Country and the Programming of Funds

| GEF Agency | Trust Fund | Country/ Regional/ Global | Focal Area | Programming of Funds | (in $) |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | GEF Project Financing (a) | Agency Fee (b) | Total (c)=a+b |
| UNDP | GEF | Bolivia | Biodiversity |  | 1,744,657 | 165,743 | 1,910,400 |
| UNDP | GEF | Bolivia | Climate Change |  | 1,054,064 | 100,136 | 1,154,200 |
| UNDP | GEF | Bolivia | Land Degradation |  | 835,982 | 79,418 | 915,400 |
| Total GEF Resources |  |  |  |  | 3,634,703 | 345,297 | 3,980,000 |

E.  Project preparation grant (ppg)

Is Project Preparation Grant requested? Yes    No  If no, skip item E.

PPG  Amount requested by agency, Trust Fund,  country and the Programming  of funds

| Project Preparation Grant amount requested: $ 91,324 PPG Agency Fee: 8,676 |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| GEF Agency | Trust Fund | Country/ Regional/Global | Focal Area | Programming of Funds | (in $) |  |  |
|  |  |  |  |  | PPG (a) | Agency Fee (b) | Total c = a + b |
| UNDP | GEF | Bolivia | Biodiversity |  | 43,835 | 4,165 | 50,000 |
| UNDP | GEF | Bolivia | Climate Change |  | 26,484 | 2,516 | 30,000 |
| UNDP | GEF | Bolivia | Land Degradation |  | 21,005 | 1,995 | 20,000 |
| Total PPG Amount |  |  |  |  | 91,324 | 8,676 | 100,000 |

F.  Project’s Target Contributions to Global Environmental Benefits

| Corporate Results | Replenishment Targets | Project Targets |
| --- | --- | --- |
| - Maintain globally significant biodiversity and the ecosystem goods and services that it provides to society | Improved management of landscapes and seascapes covering 300 million hectares | TBD |
| - Sustainable land management in production systems (agriculture, rangelands, and forest landscapes) | 120 million hectares under sustainable land management | TBD |
| - Promotion of collective management of transboundary water systems and implementation of the full range of policy, legal, and institutional reforms and investments contributing to sustainable use and maintenance of ecosystem services | Water-food-ecosystems security and conjunctive management of surface and groundwater in at least 10 freshwater basins; | Number of freshwater basins |
|  | 20% of globally over-exploited fisheries (by volume) moved to more sustainable levels | Percent of fisheries, by volume |
| - 4. Support to transformational shifts towards a low-emission and resilient development path | 750 million tons of CO2e mitigated (include both direct and indirect) | TBD |
| - Increase in phase-out, disposal and reduction of releases of POPs, ODS, mercury and other chemicals of global concern | Disposal of 80,000 tons of POPs (PCB, obsolete pesticides) | metric tons |
|  | Reduction of 1000 tons of Mercury | metric tons |
|  | Phase-out of 303.44 tons of ODP (HCFC) | ODP tons |
| - Enhance capacity of countries to implement MEAs (multilateral environmental agreements) and mainstream into national and sub-national policy, planning financial and legal frameworks | Development and sectoral planning frameworks integrate measurable targets drawn from the MEAs in at least 10 countries | Number of Countries: |
|  | Functional environmental information systems are established to support decision-making in at least 10 countries | Number of Countries: |

part ii:  project JustiFication

1. Project Description

In GEF 6, the SGP Bolivia project will be implemented in five priority areas in three biodiversity rich eco-regions - Gran Chaco, Chiquitania and Pantanal - in mosaic production/conservation landscapes under a mixed category regime: National Parks (NPs) and National Natural Areas with Integrated Management (NAIMs).  Three of the priority areas (PA/NAIMs) - Kaa-Iya, El Palmar, and Serrania del Iñao - encompass 3,763,698 ha of the Bolivian Chaco eco-region; the other two: San Matías (2,918,500 ha) and Otuquis (1,005,950 ha) together cover an area of 3,924,450 ha and include representation of both Chiquitania and Pantanal eco-regions. Although population density is relatively low, greater efforts need to be made to protect these fragile eco-regions and to arrest current degradation trends occurring from anthropic threats such as the expansion of the agricultural frontier, especially along the Brazilian border and in Chiquitania forests, where the worst deforestation rate occurs nationwide (mainly from extensive livestock raising, pasture establishment and forest fires associated with this expansion). Within these areas there is socio-economic and climatic vulnerability, especially for indigenous communities, as they practice mainly subsistence agriculture, depend directly on natural resources and have little or no support to develop alternative livelihoods. The project aims at enhancing the resilience of these landscapes through the synergistic implementation of a set of community livelihood practices in key landscapes that help maintain ecosystem services, conserve biodiversity, mitigate climate change and reduce land degradation, especially from overuse of pastures for extensive livestock raising and uncontrolled burning.

For detailed description of the three ecoregions, please see Annex I.

The five prioritized PA/NAIMs for GEF 6 are (please refer to Annex II for a location map of these five areas):

Within the Chaco eco-region (consolidation and extension of GEF 5efforts):

- Kaa-Iya del Gran Chaco National Park and Natural Area for Integrated Management;

- El Palmar Natural Area for Integrated Management;

- Serrania del Iñao National Park and Natural Area for Integrated Management.

Chiquitania-Pantanal (replication area for GEF 6):

- San Matías Natural Area for Integrated Management;

- Otuquis National Park and Natural Area for Integrated Management.

The first three areas were prioritized for SGP interventions in GEF5 and the consolidation of these activities will continue in GEF6. The areas newly prioritized for GEF 6 are San Matias NAIM and Otuquis NP/NAIM; these areas represent important national priorities for their social and natural characteristics, yet communities are materially poor and lack socio-economic support because of the difficult access and historical pattern of exclusion. In these areas, adaptation of best practices in a landscape management context will be carried out in strengthening governance through the consolidation of CSO and NGO participation within Management Commitees, implementation of best production practices in agriculture and forestry, development of innovative nontraditional products and alternative livelihood possibilities, provision of renewable energy for off-grid applications linked with productive uses, energy efficiency to reduce fuelwood and and improve health, and watershed management, among other successfully piloted practices described in section A.1.3, below.

There will be a participatory baseline assessment and planning process during the PPG-financed project preparation phase to further engage stakeholders in prioritizing and analyzing mosaic landscapes for production, conservation and/or restoration for each PA/NAIM based on the following criteria (and others that may be identified during the project preparation process):

- Threat level (e.g. dry Chiquitano forests near grasslands)

- Importance of ecosystem services (e.g. water provision in groundwater recharge zones, inundation regulation cycles such as Pantanal)

- Potential for improved and diversified livelihoods (e.g. caiman reproduction areas for sustainable use, ecotourism or cultural tourism sites)

- Uniqueness (eg. Endemic Palm forests in El Palmar)

Below is a brief description of the environmental and social significance of the selected areas (See PA maps in Annex 1):

A. EL PALMAR Natural Area for Integrated Management. Established in May 1997 it is located in the Department of Chuquisaca with an area of 59,484 hectares. A flora that includes some 270 species is the result of the area’s topography, geological variation and wide altitudinal range (from 1000 to 3,200 meters above sea level). El Palmar has three ecological zones: between 1000 and 2000 m. The vegetation is dominated by species adapted to prolonged dry periods such as Schinopsis haenkeana, Loxopterigium grisebachii, Pitadenia boliviana, Aspidosperma quebracho-blanco, Anadenanthera colubriana, Prosopis ssp, Acacifurcatispina, Coccoloba tiliácea, and Celtis spinosa. Between 2000 and 2500 m, the dominant shrub vegetation is Dadonea viscosa, Baccharis dracunculifolia and Eupatorium buniifolium. The most important tree associations are with Podocarpus parlatorei, Alnus acuminata, Schinus molle and Myrcianthes cisplatensis. Clusters of endemic palms (Parajubaea torallyi) start approximately from 2,400 meters above sea level continuing up to 3,200 meters. There are 24 mammal species recorded in El Palmar of which five are on the CITES Red Lists (Tremarctos ornatus, Felis concolor, Felis jacobita, Tayassu tajacu, Mazama americana). There are 112 recorded bird species of which the most representative are Vultur gryphus, Penelope dabbenei, and Piaya cayana. Six species of amphibians and 42 species of butterfly have also been identified.

The human population in the NAIM grew from 2,500 inhabitants (400 families) censused in 2000 to 9,853 in 2005, although the population is relatively dispersed and settlements difficult to access, with small communities of Yampara origin (Aramasi, Lomán, Torco, Tranca, Horno Kasa and El Palmar) located in the valley zones because of the abrupt topography, except for the municipality of Presto in the buffer zone where most of the population is concentrated and has better access. The Human Development Index was estimated at 0.356 (2005) and approximately 3.4% of the territory exhibits land tenure conflicts.

The natural flora is abundant, especially the endemic palm Parajubaea torallyi.  The palm fruits are used locally yet there is still no commercial value for these products. Alternative opportunities and emerging activities include ecotourism which is promoted within the area, and horticulture and apiculture through support from SGP 5 and the Program Biocultura.

Current threats to biodiversity include hunting, especially of wild turkeys and White-lipped or Chacoan peccaries, mainly from foreigners, and pumas are hunted by the local communities. The pine (Podocarpus parlatorei) is also threatened because of deforestation and timber extraction.  The area suffers from erosion and loss of forest cover from unsustainable ranching and farming practices and systems.

Elements for preliminary landscape prioritization in El Palmar:

- Endemic palm forests Parajubaea torallyi

- Chaco Dry Forest (reduce pressures from overhunting and forest fire prevention and control strategies)

- Agricultural fields and pastures (soil restoration, native species restoration, integrated livestock stabling, water harvesting)

- Riparian forests (to enhance biological connectivity)

- Groundwater recharge areas (restore with native species-reforestation, soil restoration)

B. KAA-IYA National Park and Natural Area for Integrated Management. Established in September 1995 as a National Park and Natural Area for Integrated Management, Kaa-Iya was also declared Originary Indigenous Territory. This 3,441,115 hectare protected area – the biggest protected area in Bolivia and perhaps the largest in South America – is located in the South of the Department of Santa Cruz and includes the Sabana del Chaco bio-geographic unit. The National Park is a reservoir of an extraordinary diversity of wild animals and wild and cultivated plant genetic resources. It is estimated that some 880 species of vascular plants are present in the area as well as 514 animal species. These include endemic species (Catagonus wagnery, Tolypeutes matacus, Chlamyphorus retusus, Dolichotis salinicola, Ctenomys conoveri), rare mammals such as the Guanaco (Lama guanicoe) – a camelid native to South America -, large numbers of felidae, over 300 bird species, as well as frogs (Chacophrys pierottii, Lepidobatrachus laevis), and reptile species such as Geochelone carbonaria, Geochelone chilensis, Acanthochelys sp, and Caiman yacare.

The pattern of human occupation in the area is comprised of Guaraní and Chiquitano villages as well as non-indigenous farmers. Human presence is only in the outlying areas of the Park although it is moving inwards as a result of the unsustainable use of the area's resources. The greatest concentration of people is found towards the west (Bañados de Izoso), where there are more than twenty Guaraní communities, including Guarirenda, Rincón, Huirapendi, Guirayasa, Coropo, Cacharí, Aguraigua, Guirapendio, Isiporenda, and Yapiroa. The largest Chiquitana community is San Pablo, located in the north. There are also Ayoreo nomadic groups in the area who may have not yet been contacted. Some sites of the PA have mystic or sacred significance for Ayoreo and Izoceño-Guarani indigenous peoples. There is an overlap with Originary Indigenous Territories of Santa Teresita, Yambiguasu, Isoso, Takovo, Charagua Norte, Charagua Sur, Kaaguasu, atipependi Karovaichu, Guaraníi Kaami (ZA).

Indigenous peoples of Izoceño-Guarani, Chiquitano, and Ayoreo ethnicity living within and around the protected area participated in its establishment and are involved in the implementation of the Protected Area (PA) management plan, as well as in the implementation of the management plans that exist for some specific faunal species. The management of the national park is being carried out under shared administration, within the framework of an agreement with the Upper and Lower Izozog Authority (Capitanía del Alto y Bajo Izozog), an indigenous Izoceño-Guaraní organisation, esablished on 24th November 1995. The development committee is composed of representatives from the municipalities of Charagua, Pailón, San José de Chiquitos, and the sub-mayoralty of Izoso, as well as the founding organisations of TURUBO, CABI, CICHIPA (Indigenous Office for Chiquitano Communities of Pailón), Santa Teresita (Ayoreo Community), CIMCI, and representatives of the government, the Protected Area System Authority (SERNAP) and the Departmental Prefecture.

There are several settlements of Ayoreo, Chiquitano, Weenhayek and Guarani indigenous peoples who maintain their languages and traditional lifestyles, often combining hunter-gathering activities with agriculture depending on the season, and thus are more vulnerable to degradation or loss of ecosystem services and climate change. There are other populations recently migrated from other regions of Santa Cruz (ranch owners, farm workers) who mostly work in cattle ranching.

Elements for preliminary landscape prioritization in Kaa-Iya:

- Chaco Dry Forest (reduce pressures from overhunting and forest fire prevention and control strategies, energy efficiency and off-grid renewable sources for productive uses)

- Agricultural fields and pastures (soil restoration, native species restoration, integrated livestock-stabling, water harvesting)

- Agricultural production in indigenous territories (conservation of traditional knowledge, use of genetic diversity of wild relatives of important crops, medicinal plants, enhance production systems to create surplus, aid in marketing and sale of crafts, capacity building for cultural tourism)

- Riparian forests (to enhance biological connectivity)

- Groundwater recharge areas (restore with native species-reforestation, soil restoration)

C. SERRANIA DEL IÑAO National Park and Natural Area for Integrated Management. Established in 2004 this PA is located in the Department of Chuquisaca and is the most recent PA to be gazetted in the country. It covers an area of 263,090 hectares and, with 500 plant species recorded, Iñao is one of the richest plant diversity areas of Bolivia. Although more research is needed, there are possible plant endemisms within the Acanthacea family, and also some endemic cacti and orchid species. There are 31 mammal species recorded including, among others, bats (five sub-families), primates (Cebus apella y Alouatta caraya, both listed in CITES appendix II), and carnivores, with five families represented and including species such as the Spectacled bear (Tremarctos ornatus) listed in CITES appendix I. Among the felidae family, there are five species all of which are listed in appendix I (Leopardus wiedii, Leopardus pardalis, Oncifelis geoffroyi, Puma concolor and Panthera onca). There are 140 bird species in the protected area, representing over 10% of all bird species recorded in Bolivia. Notably, 40 species of freshwater fish have been recorded, and amphibian and reptile biodiversity is also high.

From the 2000 census and PA report in 2005 the human population grew significantly from 17 to 32 communities. Original communities are mainly quechua and guarani. The southern area is affected by farming activities, given the presence of a higher rural population.

The gradual advance of the agricultural frontier determines the existence of problems associated with human settlements and agricultural practices such as burning of vegetation. In the community of El Frio migrant families coming from Azurduy, Tomina and Yamparáez provinces are settling and extending agricultural and livestock activities. Logging of timber species is intense from Jarka Mayu, near the community of Ticucha, until Chuya Yacu in the municipality of Villa Vaca Guzman. In the Azero and Grande rivers dynamite fishing is practiced, affecting both adults and juveniles, and in addition, interrupting the breeding cycle. Futhermore, there are risks from agreements with three oil companies who have concessions in the Iñao blocks.

Elements for preliminary landscape prioritization in Serrania del Iñao:

- Chaco Dry Forest (reduce pressures from overhunting and forest fire prevention and control strategies)

- Agricultural fields and pastures (soil restoration, native species restoration, integrated livestock-stabling, water harvesting, agrosylvopastoral systems)

- Rivers and other freshwater systems (sustainable fisheries and aquaculture)

- Groundwater recharge areas (restore with native species-reforestation, soil restoration, infiltration)

D. SAN MATÍAS Natural Area for Integrated Management.  The creation of this NAIM originates in the Santa Cruz Land Use Plan approved in 1995 in which the protected area covered an extended area of Chiquitanía (dry tropical forest) and Pantanal ecosystems, including transitions of Chaco-Chiquitanía to the south and Amazonia-Chiquitanía to the north. The NAIM is part of the upper watershed of the Paraguay River and is characterized by lakes, lagoons, marshes and rivers located in an extended flood plain. Rivers include the Tapanaquis, Curichi Grande, Bahía Las Tojas, San Fernando, Mercedes, La Cal, Santo Corazón and Las Conchas, and lagoons include La Gaiba, Uberaba, Mandioré y Vista Hermosa, among other hydrological systems including marshes, curichis and brooks.

The San Matias NAIM functions as a huge feeding and breeding center for aquatic bird species, which is also an important touristic feature. Other landscape attractions include the Curichi lakes and mountains. Important fauna include endangered mammal species such as the pejichi (Giant armadillo), marsh deer and londras (Giant otter). Vegetation is represented by Morado, Cuchi, soto, Tajibos, oak, curupaú, chick, cuta, tacuara, garabatá, carandá palms, lilies and tarope. Its proximity to the Brazilian Pantanal National Park may permit the establishment of a corridor that will enhance wildlife conservation, ensuring a sufficient area for the survival of animals and biological processes across both PAs.

Conservation of dry tropical forests, covering about 50% of the San Matias NAIM, is also a priority, as well as the wooded areas of the neighboring Sunsas which are unique biogeographically as they hold important endemic species as well as great tourism potential for their beauty. The greater Pantanal ecosystem undergoes dramatic changes during the year from dry to rainy seasons when the area is flooded, one factor contributing to its great diversity of flora and fauna.

The PA was legally established in 1997, and its latest Monitoring Plan (2012) emphasized the importance of the ecosystems and species of the Pantanal, Chiquitano and Cerrado forests, which are now more than ever threatened by agricultural expansion and diverse development projects, while at the same time these ecosystems are poorly represented in the National Protected Area System. Also, due to soil type, flooding, steep slopes and aluminum toxicity of exposed soil, the area has low aptitude for intensive agriculture and livestock.  Furthermore, the NAIM category of the PA ensures protection of territories where the indigenous Chiquitanos and Ayoreos may practice their traditional land and resource uses and serve as example of sustainable use of resources.

The San Matias NAIM, along with the other areas that cover the region, is one of the protected areas of highest risk in the NSAP due to various types of impacts and growing threats from mining and other projects, as in the case of the Mutún or Cerro Colorado, huge road projects, increased pressure from livestock expansion and recurrence of widespread fires. This also implies that the Management Plan and Monitoring Program must prioritize the ecosystems of the Pantanal and the Chiquitano dry forests.

There are 23 communities and population centers within the PA: Rincón del Tigre (Guaye) and Holy Heart of Chiquitano origin, yoreo and mestizo camba. The buffer zone has 7,028 people in 21 communities and 24,500 in cities and population centers including, San Matías, Roboré, San José de Chiquitos, Ascensión, Las Petas, El Tuna, and Santiago de Chiquitos.  There is an overlap with Originary Indigenous Territories of Guaye Rincón del Tigre (AP), Pantanal and Otuquis I (AP y ZA), Tobite II (ZA).

Elements for preliminary landscape prioritization in San Matias:

- Chiquitano Dry Forest (reduce pressures from overhunting and forest fire prevention and control strategies)

- Pantanal wetlands (sustainable fishing, caiman sustainable use, water quality monitoring warning system)

- Agricultural fields and pastures (soil restoration, native species restoration, integrated livestock-stabling, water harvesting, agrosylvopastoral systems)

- Rivers and other freshwater systems (sustainable fisheries and aquaculture)

- Potential ecotourism sites (capacity building, product-services development)

E. Otuquis National Park and Natural Area for Integrated Management.  The creation of this NAIM originates in the Santa Cruz Land Use Plan approved in 1995, in which the protected area covered an extensive eco-region of Pantanal and Chaco-Chiquitanía transition. According to the decree that created this protected area in 1997, and its Management Plan, it recognizes that the Pantanal is the largest and least damaged wetland in the world, and the best preserved representation in Bolivia, which also presents a heterogeneous ecosystem mosaic with the combination of elements from four of the most important biomes of South America: El Chaco, Amazon, Cerrado and Chiquitano forests.

The Otuquis National Park and Natural Integrated Management Area is located in the southeastern part of the Department of Santa Cruz. It has two management categories and aims to harmonize production activities with the maintenance of the hydro-biological processes that occur in this portion of the Pantanal, internationally acknowledged as “deep Pantanal”, since it is permanently flooded, more than six months of the year. A portion of Otuquis Protected Area territory is under the Natural Integrated Management Area, where natural resources are used sustainably. The area of Otuquis that is under National Park management is uniquely rich in terms of its flora and fauna, and is under strict and permanent protection. The only activities allowed are scientific research, ecotourism, environmental education and subsistence use by indigenous communities prior to obtaining a special permit. The use of natural resources and infrastructure development is not allowed within the National Park.

Within the Otuquis NP and NAIM there are 18 cattle ranches, 10 communities with a population of 4,188 from Ayoreo origin and Chiquitano, and 29,586 inhabitants in Suarez Port, Guijarro Port and El Carmen. There is an overlap with the Protected Area and the Originary Indigenous Territories of Otuquis II and Yambiguasú (AP y ZA). The population in the Bolivian Pantanal is dedicated primarily to commerce, industry, cattle ranching, transportation and small scale agriculture. The Pantanal provides food, materials water, transportation and recreation. The consumption of its products is of great importance for the survival of rural communities, as their hunting and fishing activities are primarily for self-consumption.

The ecosystems and species of the Pantanal, Cerrado and Chiquitano forests are threatened by uncontrolled expansion of the agricultural frontier and from various development projects, threats that have critically increased in recent years. Just as the San Martin NP/NAIM, the Otuquis area faces a huge set of potential environmental impacts and threats of enormous magnitude and intensity both from mining megaprojects, such as the case of Mutún and Cerro Colorado, from mega road projects, such as the railway and port terminal in Puerto Busch, as well as from increased livestock pressure and recurrence of extensive fires.

Elements for preliminary landscape prioritization in Otuquis:

- Chiquitano Dry Forest (reduce pressures from overhunting and forest fire prevention and control strategies)

- Pantanal wetlands (sustainable fishing, caiman sustainable use, water quality monitoring warning system)

- Agricultural fields and pastures (soil restoration, native species restoration, integrated livestock-stabling, water harvesting, agrosylvopastoral systems)

- Rivers and other freshwater systems (sustainable fisheries and aquaculture)

- Potential ecotourism sites (capacity building, product-services development)

The GEF Small Grants Program

The GEF Small Grants Program in Bolivia has operated continuously since 1993. During this time, the SGP Bolivia Country Program has strengthened capacities of approximately 952 communities, 222 non-governmental organizations (NGOs) and 87 Community Based Organizations (CBOs) for local conservation and sustainable use of biodiversity, use of renewable energy resources, adoption of energy efficient measures and technologies and restoration of degraded land with special attention to improving the productivity and sustainability of agro-ecosystems and livelihoods. The Program has invested over USD 6 million in grants through 328 projects.

The Country Program has been recognized nationally as a facilitating institution instead of a "bar" or excluding mechanism due to the fact that initial project proposals are accepted in a brief and simple format, thus enabling greater participation of final beneficiaries who usually lack project preparation skills, and avoiding third party costs at this initial stage. Project ideas selected and approved by the NSC are then required to be developed in a second more detailed project profile, with assistance provided to strengthen project preparation capacities.

Another success factor of the program is the monitoring and evaluation method, in which stakeholder proponents internalize M&E as continuous support and a learning and knowledge exchange process throughout the whole project cycle. It is through this process that systematization of valuable lessons learned from each operational phase has taken place. These systematizations have been edited, published and shared with stakeholders and decision makers, implementers and other beneficiaries of the projects, thus enabling replicability and scaling up of these experiences.

Transparency, representativeness, innovation, effectiveness and efficiency are other attributes of the program recognized by the National Steering Committee and in Bolivia, SGP is recognized as a fast, simple, sensitive mechanism for direct and effective response to local people’s needs and ideas for innovation. It has assisted communities to pilot, demonstrate and implement collective action for impacts on the global environment by improving livelihoods.

During the first four phases of the SGP in Bolivia (1992-2010), the focus and coverage of SGP was national in scope and manifested through annual periodic calls in the three regions of the country: the west (highlands), the valleys, and the east (lowlands), covering the nine departments of Bolivia. Throughout this period, SGP Bolivia generated valuable experience, contributing to obtaining countless lessons for conservation and local and regional development as well as proving to be effective means for local implementation of the UNFCC, UNCBD, UNCCD and other multilateral environmental agreements. On average, SGP has supported initiatives in a range between USD 25,000 to 35,000 with up to USD 50,000 for exceptional initiatives.

Bolivia was part of the first group of countries upgraded to GEF full size projects in 2012. During GEF 5, SGP Bolivia shifted from a national to a regional focus that introduced the landscape approach within four mixed land use regime Protected Areas of the Gran Chaco Region: Kaa-Iya del Gran Chaco NP and NAIM, El Palmar NAIM, Serrania del Aguaragüe NP and NAIM, Serrania del Iñao NP and NAIM. Concentrating activities and actions in a given geographic area resulted in tangible comparative advantages in terms of results, outcomes and impacts, but also in operational effectiveness and efficiency compared with the previous phases.

Prior to GEF 5, communities had hardly sensed direct benefits from being part of a Protected Area, according to evaluations and systematizations of this phase. Currently, local people from each area feel identified and empowered with their NP/NAIM and are integrated with SERNAP PA teams within the established Management Committees of each NP/NAIM.  Currently, the visibility of the PAs in the Chaco is much higher and with an increasing level of ownership and commitment of the population to these areas, compared with other mixed regime protected areas in the country.  Benefits from SGP GEF 5 have already been replicated on a larger scale, for example, a model for off-grid electrification with solar panels in El Palmar communities was upscaled by the municipality to three additional communities.

A success for local empowerment in this process has been the direct integration of community beneficiaries within the National Steering Committee. Through a self-selection process for their representation they have included directors and representatives of the management committees of each of the protected areas to participate in the process of selection and approval of project proposals. The PA management committees are the instances where proposals are first analyzed, discussed and prioritized in terms of legitimate demands and potential benefits to communities and coherence with the NP/NAIM objectives. The target population appreciates the speed with which their needs are satisfied, but also the empowerment of exercising agency in developing co-operation and management of their own projects.

Despite success in GEF 5, strategic partnerships with the state and other allies are required to ensure that there is long term empowerment and capacities are strengthened for community based and non-governmental organizations to maintain and include more beneficiaries and strengthen local governance. This is the reason why work will be continued in three of the four Gran Chaco areas - Kaa-Iya del Gran Chaco NP and NAIM, El Palmar NAIM, Serrania del Aguaragüe NP and NAIM, Serrania del Iñao NP and NAIM - to consolidate experience and impacts and to develop an exit strategy that will allow long term continuation of the work done by the respective multistakeholder groups.

The Government of Bolivia has allocated GEF 6 STAR funding to enhance and extend achievements of the SGP GEF 5 strategy, in line with national priorities, policies and agendas. Experience from GEF 5 using a regional focus within a single biome (Gran Chaco), as well as community capacity strengthening for adaptive management, provided the foundation for the landscape approach that is presented for GEF 6. During this new phase, the project aims to achieve further articulation of communities with their landscapes, strengthen governance schemes, and provide an active role for organizations to participate in PA/NAIM management in which they may be catalysts and protagonists of their livelihood improvement and increasing resilience.

The problem to be addressed

The main problem to be addressed by this project is the prevalent weakness of rural communities, including indigenous groups in the globally important biomes of Chaco, Chiquitania and Pantanal in Bolivia, to take collective action for integrated and sustainable landscape management for increased ecosystem and socio-economic resilience, and to participate in multi-level and multi-sector landscape governance. While this resilience is a consequence of actions to mitigate and adapt to climate change, as well as to optimize ecosystem services through the conservation of biodiversity and sustainable land and resource management, these actions can only be sustained by smallholder organizations and networks with the resources, commitment and capacities to carry out continuous, long-term processes of innovation and adaptive management. For these community actions to achieve sufficient scale to impact socio-ecological resilience in a meaningful way they must be adopted and implemented by communities across the landscape. Within the landscape, smallholder organizations must act within a common strategic framework that integrates ecological, social and economic outcomes with the goal of reaching a tipping point in adoption and implementation of individual and collective management innovations leading to landscape resilience.

Although population density is relatively low within the areas prioritized for GEF 6 in Bolivia - Chaco, Chiquitania and Pantanal - they are increasingly suffering from unsustainable production practices (deforestation; uncontrolled burning for livestock and agricultural expansion; river deviation for irrigation, depredatory fishing, excessive hunting or logging from communities migrating from other regions) that are leading to ecosystem and land degradation and increasing the vulnerability of communities to climate change, especially those who depend directly on ecosystem goods and services, such as subsistence agriculture or hunting/fishing.

Deforestation is among the primary causes of biodiversity loss identified in the Vth National Report to the CDB from Bolivia. The main land uses that contribute to deforestation and their relative weights are: livestock in planted pastures (50%), mechanized agriculture (30%), and small-scale agriculture (18%). The most affected areas are in the Yungas forest ecoregions; Southwestern humid Amazon forest; Chiquitano and Chaco dry forest. The areas with the highest deforestation are located in the department of Santa Cruz, having reached more than 4 million ha by 2010. In the last decade livestock was the main cause of deforestation, causing more than 50% of deforestation and increased incidence in Chiquitanía. At this rate, it is estimated that deforestation has occurred on more than 5 million hectares, or one tenth of the forests that existed in 1990.

Threats that directly affect species include: poaching for luxury markets (vicuña, suri, macaws, Giant otter) or sport i.e. not directed to traditional consumption; selective illegal logging; the extraction, sale or trafficking of species of fauna for illegal export or as pets; extensive livestock production and practices such as burning grasslands; pollution of water bodies, extraction of species with restricted, isolated or fragmented habitats with low connectivity and low genetic variability populations; overhunting and overfishing.

Threats linked to climate variability and climate change and affecting species and habitats would be related primarily to increased flooding, drought, frost, heat and other extreme weather events. The climate changes anticipated in Bolivia could have very severe impacts on biodiversity, especially in the highlands where an accelerated process of desertification is projected due to reduced precipitation and increased temperature variability. In the lowlands, climate change is not the greatest threat to biodiversity considering the importance of the advance of the agricultural frontier as the most dominant stressor.

The essential problem to be addressed by this project is that the necessary collective action in Bolivia for adaptive management of resources and ecosystem processes for sustainable development and global environmental benefits is hindered by the organizational weaknesses of the communities living and working in affected landscapes to act strategically and collectively in building social and ecological resilience.

The solution to the problem is for community organizations in rural landscapes of key areas of Bolivia - the Chaco, Chiquitanía dry forests, and Pantanal wetlands - to develop and implement adaptive landscape management strategies that build social, economic and ecological resilience maintained through the production of global environmental and local sustainable development benefits. To pursue achievement of the outcomes of these adaptive landscape management strategies, community organizations will implement grant projects reviewed and approved by the SGP National Steering Committee, supported by multi-stakeholder agreements involving local government, NGOs, academe and other partners, and evaluated periodically and systematically as part of the broader collective process of adjusting management strategies to new information, knowledge, capacities and conditions.

Barriers to achieving this solution include:

Barrier 1: Community organizations do not coordinate with relevant stakholders such as local governments in taking collective action in favor of landscape resilience outcomes built on global environmental benefits and the strengthening of social capital and/or have limited participation within formal inter-institutional governance structures at the landscape level.

To achieve meaningful impacts on ecosystem processes and functions to favor landscape resilience it is indispensable that community organizations act collectively and in synergy. This requires coordination among communities within an agreed strategic framework as well as a recognition of the importance of developing social capital through organizational interactions within networks and with external agents. Creating an enabling environment for community-driven landscape management is enhanced by inclusive multistakeholder partnerships across sectors, involving community organizations and networks, local and subnational governments, the private sector, NGOs and others. Currently, multistakeholder partnerships in the critical landscapes addressed by this project require further strengthening, particularly in regard to new communities in Chiquitanía and Pantanal landscapes receiving support from SGP for the first time.

Despite the legal existence of Management Committees (which are multistakeholder platforms for NP/NAIMs management) these governance structures lack pro-active community participation. Lack of coordination for accomplishment of goals and services by national institutions, in particular of those related to natural resource management, is also a constant problem that limits the potential of specific initiatives to be scaled up, especially through a landscape approach.

Barrier 2: Community organizations lack the means to manage and coordinate their rural production landscapes with a long-term vision for the conservation of biodiversity, land and ecosystem restoration and risk reduction including climate resilience within their rural production landscapes.

Communities have uneven knowledge, or have lost traditional knowledge, of ecosystem function and services provided, to address ecosystem stresses and the loss of biodiversity.  This is especially critical for frail ecosystems such as the dry forests of Chaco and Chiquitanía, which are naturally adapted to water limitations, but with uses such as conversion to pastures and climate stresses, water provision for human populations and agricultural production for community subsistence may be dramatically reduced.

Furthermore, some landscapes such as the Chiquitanía dry forests are experiencing a high rate of forest fires due to uncontrolled burning purposefully induced to expand the area for monocultures or for cattle ranching.

Barrier 3: Community organizations lack technical know-how and abilities to improve productivity and diversification of their agroecosystem landscapes.

Community organizations in the area, especially indigenous groups, practice subsistence agriculture that generates few surpluses for commercialization.  Increasing productivity and diversification in agroecosystems as well as improving water, forest and land management in their production landscapes allows greater food security, productivity and resilience in the long run.

Furthermore, within the priority biomes there is a great cultural richness in use of native biodiversity for medicine, food, and construction that has been lost or under utilized by communities that have generated this knowledge.  These areas are also hold significant wild populations of important crop species including corn, peanuts, peppers among other less known species.

Barrier 4. Community organizations lack adaptive management capacities to innovate, diversify, produce at scale and commercialize goods and services while improving their livelihoods and landscape resilience.

As stated previously, most rural communities in the priority landscapes and biomes in Bolivia practice subsistence agriculture, men seek work in cattle ranches or agroindustries and young family members and women are migrating to nearby towns or cities for low wage job opportunities such as maid services. Instead of abandoning their communities in search of a minimal income, alternative livelihoods may be developed to generate income and more job opportunities within the landscape if capacities are strengthened to provide goods and services with commercial potential. Through innovation, scaling-up of previous experiences such as honey production and developing market opportunities for raw products that may have an added value for niche markets are other alternatives. SGP support will aim at catalyzing this potential, which is not being sufficiently promoted in the area.

Chaco, Chiquitanía and Pantanal have opportunities in non-traditional uses of native biodiversity resources (palm fruits, alligator skins), genetic richness within wild populations of important crop species  (corn, peanuts, peppers), medicinal plants, amd potential sites for ecotourism and cultural wealth that may be sustainably used and promoted to enhance socio-economical resilience of these landscapes. Alternative tourism requires a significant degree of coordination among all community groups offering tourism services and sophistication in the delivery of the products. Promotion and marketing also require specific abilities that need time to develop. SGP with strategic allies such as INIAF will support the analysis of the scope and feasibility of these alternative options.

Barrier 5. Community organizations lack access to clean and efficient energy sources to enhance productivity or add value to productive uses and services.

The lack of energy from non-connectivity to the energy grid due to remoteness of some communities is also a limitation for productivity, livelihoods and entrepeneurs, and for overall resilience to climatic and socio-economic risks. The use of wood for energy has a long term negative effect on ecosystems as well as household health if stoves and ovens are not energy efficient and without adequate heating-ventilation systems.

Barrier 6.  Interinstitutional stakeholders country-wide lack knowledge and experience of community based interventions to restore and enhance sustainable livelihoods and landscape resiliency.

Another problem in areas vulnerable to climatic variability and climate change is lack of knowledge of watershed restoration processes; know-how to convert and enhance productivity while contributing to sustainable landscapes; how to strengthen community participation in governance schemes; water management practices; soil management practices; etc. This issue is  also associated with low levels of schooling or loss of traditional knowledge of sustainable production practices, and the lack of systematized knowledge that can be transmitted through appropriate methodologies (such as peer-to-peer encounters, visiting successful models, media reports, etc.) and knowledge products. There is also insufficient information about accessing technologies for soil and water conservation and how to benefit from financial resources available for rural development and conservation of biodiversity, among other government and non-government programs.

Barrier 7: Community organizations have insufficient capacities to plan their initiatives, implement and evaluate them effectively, and systematically derive practical lessons from the experience.

Throughout the 20 years of implementation of the SGP in Bolivia, the Country Programme has helped communities to successfully develop a set of production systems and practices that have benefited both the global environment and local sustainable development, especially in rural areas. These include diversified farming; honey production; non-timber forest products; aquaculture and fish farming with native species; recovery of traditional knowledge related to crops and medicinal plant production; community tourism and craft production. The lessons and knowledge of these systems need to be disseminated to and adapted by other smallholder communities throughout the landscape to create a critical mass of practitioners that will tip production in the landscape to a new standard of sustainable use of biodiversity (including agrobiodiversity), soil carbon, biomass, water, and other ecosystem components. For this to happen, it will be necessary to strengthen the capacities of community organizations to innovate, experiment, evaluate results, identify lessons and best practice, and use this knowledge to adapt to changing circumstances and information.

A.1.2 The baseline scenario and associated baseline projects

Component 1: Resilient landscapes for sustainable development and global environmental protection

There are currently no other small grants programmes in the five prioritized areas - Kaa-Iya, El Palmar, and Serrania del Iñao of the Bolivian Chaco eco-region and San Matías and Otuquis of the Chiquitania-Pantanal - that are aimed at building the capacities of rural communities to plan and manage their landscapes adaptively for socio-ecological resilience maintained through sustainable development and global environmental benefits. SGP Bolivia has, over the past years, developed multistakeholder partnerships with local governments, national agencies and Ministries, NGOs, the private sector and others. These partnerships have allowed these entities to facilitate support to community organizations implementing projects. At the same time, SGP has been able to match community initiatives with government priorities and programmes where community participation is a priority of communities and government agencies. These partnerships and long-standing collaborative arrangements around sectoral initiatives in the rural landscapes constitute a dynamic baseline of programmes and relationships on which further GEF investment will be built.

There are currently no rural socio-ecological landscape management initiatives underway at this time in the  Kaa-Iya, El Palmar, and Serrania del Iñao of the Bolivian Chaco eco-region and San Matías and Otuquis of the Chiquitania-Pantanal that take an integrated, participatory, community-based approach. The Government of Bolivia does implement a number of sectoral initiatives that pursue specific objectives in regard to rural energy, irrigation and water management, hillside reforestation, protected area management, agricultural production and other priorities, however, there is no integrated approach focused geographically that brings these initiatives together to produce synergistic benefits aimed at enhancing resilience based on global environmental benefits and community-driven sustainable development. The focus of government initiatives is primarily on individual smallholders, so there are few if any initiatives to explicitly empower community organizations, individually or collectively, to take a lead role as decision making agents in determining strategic landscape management priorities, which technologies or practices to adopt, how production systems should be designed, how they should be adapted to prevailing community conditions, etc. There are no current initiatives in the planning or implementation stages that focus on building capacities of community organizations and networks – and thus critical social capital - across the landscape for adaptive land and resource management aimed at enhancing and securing long-term social, economic and ecological resilience.

More detailed baseline assessments will be applied in each of the three landscapes during project preparation to define existing ecological, social and economic factors on which to build project activities.  Detailed analysis of institutional activities in each of the three areas will be carried out to fully comprehend the current governance frameworks, institutional programs and projects and the presence and availability of strategic partnerships with the project proposed here.

During GEF-5, community initiatives supported by SGP in El Palmar NAIM allowed important progress in terms of social empowerment within PA Management Committees, livelihood improvement, entrepeneurship in alternative uses such as honey production, reforestation of groundwater recharge areas, improved agricultural productivity, adoption of intensive horticulture and an overall recognition of benefits of living within the NAIM.  A positive replication experience was the support of SGP for off-grid electrification with solar panels in El Palmar communities.  For this experience co-investment of communities was promoted for maintenance and sustainability of the initiative. With this model 245 families in six out of nine communities in the PA benefited from pre-electrification and the installation of photovoltaic panels as did schools and community health centres.

The municipality of Presto in El Palmar NAIM, replicated this experience in three more communities and is interested in further expanding these initiatives. Currently, communities are empowered through the Management Committees to express concerns or alert local governments and institutions of external factors that may threaten El Palmar biodiversity and their livelihoods. The Program Biocultura supported horticulture and local biodiveresity use during GEF 5 in this area.

In the National Park and Natural Area of Integrated Management Kaa Iya, during GEF 5 SGP focused its support predominantly on strengthening the capacities of indigenous people of the area, the Izoceños, in the Originary Indigenous Community of Izoso.  SGP supported capacity development of local organizations such as the CABI (Indigenous Center of the Upper and Lower Isoso) and the CIMCI (Indigenous Central of Women of the Captainy of Isoso). The  CIMCI implemented an initiative to conserve an important non-timber forest resource, the cupesi, which after a transformation process, is turned into flour or coffee and is intended for family consumption; it is also sold at local fairs. This initiative was a nominee for the Equator Prize.

Another relevant experience that portrays SGP work in this area and its important social, economic and environmental impacts, was the establishment of a photovoltaic solar panel system (one of the largest in the country in terms of surface area) for water pumping for human and cattle consumption. This intervention benefited around 300 families in the community of La Brecha and generated a transformation in the energy matrix, replacing the pumping system that used fossil fuel (diesel), which was highly inefficient and inequitable in distribution of the service among the population. This initiative mobilized cash contributions from the Charagua municipality and local people.

In the Serrania del Iñao NP/NAIM corresponding to the Chuquisaca Chaco the greatest income is generated by livestock activity, thus SGP GEF 5 supported groups, within the municipality of Monteagudo, to carry out successful initiatives to protect the native forest, mountain pasture management, protection and closing of areas for the conservation and restoration of native grassland and planting grasses and legumes, and the establishment of silos for the conservation of fodder (hay and silage) to provide feed for livestock in the dry season. While small associations of farmers have been direct beneficiaries, they also value and recognize the importance of the activity supported by their own contributions; other funding sources include the municipality who has already promoted replication in several communities located within the protected area.

Component 2: Capacity building and knowledge sharing

Despite progress, the vast territories in these biomes require extending and scaling-up these experiences throughout the landscapes to catalyze long term impact and results. In this sense, knowledge management and formalization of strategic alliances within the landscape approach to be promoted during GEF 6 will provide a better foundation for replication and dissemination of practices within three of the original NP/NAIMs from GEF 5 and the two new areas that include other landscapes.

As part of the design process and strategy for resource mobilization for GEF 6, contacts and preliminary agreements for possible inter-institutional collaboration with other entities, public and private, working with PAs or in support of the local people living in PAs has already taken place with several initiatives: Biocultura Program (working with SDC resources in two of the PAs where the SGP will intervene; the PACSBio that works with EU funds and supports the entire SNAP, National System of Protected Areas and Environmental Liabilities Project, which is in the initial stage of implementation between the Ministry of Environment and UNDP with funding from the EU and will be developed in protected areas to be defined.

A.1.3 The proposed alternative scenario

Component 1: Resilient landscapes for sustainable development and global environmental protection

GEF incremental funding and cofinancing will be applied to overcome the barriers mentioned above and to add value, where appropriate and possible, to existing initiatives by the SNAP, state and local government, the private sector, CSOs and academia to achieve the landscape management and resilience objectives, generating global environmental benefits and local benefits. In addition to small grants to enable additional communities to benefit from sustainable livelihood activities that have proved to be environmentally sound, SGP will coordinate with other initatives (Biocultura, PacsBIO, Gran Chaco Regional GEF funded project and others) to work with other CSOs to overcome the regulatory, governance, technical, communications and participation barriers identified to make progress in achieving sustainability of strategic interventions such as ecotourism and apiculture, and to transition from a grant-making approach concerned primarily with local issues to a process-oriented approach in which planning, implementation and evaluation would increasingly address a larger geographic scale with longer time-horizons, production chains, landscapes and large ecosystems.

Currently, Bolivia has an institutional and legal framework that promotes participation of communities and respect for traditional practices of indigenous groups including the 1992 Constitution of the Plurinational State of Bolivia (CPE), the institutional framework modified by Law of Mother Earth and Integral Development for Living Well (No. 300), that created a national Authority for Mother Earth, and the SERNAP PA mixed regimes such as Natural Areas for Integrated Management and Originary Indigenous Territories, and Management Committees for each PA that enable social representation in management. Nevertheless, there are other conditions such as difficult access and transportation in this area and historical events and conflicts that date back to the Spanish Conquest, that result in weak technical and administrative capacities of communities that need to be strengthened to achieve effective landscape management and long term resilience. SGP will favor strengthening of the current framework and promote networking between the larger NP/NAIM Management Committees and the corresponding landscape level multistakholder platforms.

Funding will also be available for initiatives that help build the governance and organizational capacities of NP/NAIM Management Committees as well as those of second-level organizations that are best suited to interact with other state and non-state actors at the landscape level such as the Association of Organizations of Ecological Producers of Bolivia (AOPEB), and Associations of Local Producers Network Community Solidarity Tourism Organization (TUSOCO).

Furthermore, some landscapes such as the Chiquitanía dry forests are experiencing a high rate of forest fires due to uncontrolled burning, purposefully induced to expand monocultures such as soy or for cattle ranching.  In the first case, communities may reduce forest fire risks through prevention and attention to these risks, in the latter, law enforcement and community mechanisms may be developed or strengthened.

SGP will also seek to strengthen CSOs that may provide technical assistance to communities to plan and manage complex initiatives and test, evaluate and disseminate community level innovations. Major areas for SGP support will be: participatory social and environmental assessments of community organizations, their capacities, territories and production potential; education and training based on innovation results from sustainable production and conservation practices; participatory evaluation of results at landscape level and by production activity for learning and adaptive management; documentation and analysis for dissemination to community organizations, networks, second-level organizations, partners and policy makers.

Special attention will be given to the formation of networks and strengthening of second-level organizations to integrate and bring to scale production and marketing of sustainably produced goods and services. SGP will facilitate access to financial resources for sustainable production activities at scale by second-level organizations. Strategic projects will facilitate specific product development and enhance regional commercialization.

Monitoring and evaluation at all scales (grant level, landscape, NP/NAIM, and large ecosystem level) will take place at various intervals. A comprehensive data collection, monitoring and evaluation plan will be developed during the PPG phase and a budget will be allocated for this purpose.

Strategic Interventions for Sustainable Livelihoods

Strategic interventions are production activities associated with a particular ecosystem that generate both environmental and community benefits. Strategic interventions also allow for the integration of individual community-based initiatives with networks, associations, production chains, and marketing. They also allow for monitoring of the aggregated impact on specific landscapes and ecosystems. The SGP strategy specifies the activities eligible for SGP funding for each strategic intervention type:

Nursery gardens

The production of seedlings of different species, mainly forest species, but also native fruit trees is needed for reforestation and restoration, but also a demand in local communities with special emphasis on native species. Forest enrichment, soil protection, establishing agrosylvopastoral systems are, among others, the use or destination of production in nurseries. In some cases, it is intended that the nurseries be suppliers of seedlings for other communities, generated through marketing, conditions for sustainability. The same thing occurs with grafted fruit plants producers.

Agroforestry and Agroecological Innovation

SGP primarily funds in-situ conservation practices but may also consider ex-situ conservation initiatives such as local botanical gardens and green germplasm banks managed by local communities in collaboration with universities and research centres. During GEF 5 SGP began supporting the development of micro-regional networks for marketing agroforestry and agricultural products and for certification, which will be continued if relevant. Major landscape management practices and potential star products are described below:

Pasture Management

As previously described, Chaco soil and climate characteristics describe a dry area with limited availability of pastures and few conditions for extensive livestock production; however, depending on their livestock potential, the program promoted a series of practices for sustainable pasture production through the management of deferred enclosure protection and areas for planting grasses and legumes, management and livestock rotation and conservation of fodder through hay and silage, in order to provide food for livestock in the dry season. All these actions have reduced the pressure on the forest and generated increasing awareness and knowledge on the part of small livestock producers who in addition to applying these best practices, do not increase the size of their herds. The effect of all these good practices can be visualized when broader adoption of such successful experiences is carried out by other farmers in other communities near the sites of SGP support, using their own resources.

Peanuts

Peanut production in the Chaco has an interesting potential to be developed given the preference category due to its origin and organoleptic characteristics. The Chaco has the conditions and characteristics for good peanut production.  The area is the center of origin of the peanut, and SGP will support work with wild relatives and domesticated species maintained for their high value as agrobiodiversity resources.

Peppers

The Chaco has a large genebank of varieties and ecotypes of peppers that are highly valued for their genetic wealth, but also for its commercial value and market demand. The production of peppers is a category particularly well developed in the Chuquisaca Chaco, a traditional chili producing area in Bolivia, and possesses an interesting potential to be improved. Among its limitations are processing the raw material, as it must be properly dried, an aspect with improvement potential. The SGP supported the establishment of a collection and chili processing center, where the implementation of solar dryers produced a higher quality product in less time and with better market prices as it is already processed. In this way SGP will also contribute to strengthen pepper producer organizations, who have better conditions for processing the raw material and negotiate better prices at local, regional and national markets.

Apiaries

The establishment of apiaries is a great win-win example of a biodiversity and ecosystem friendly practice that also generates revenue for the local population, the reason behind the increased interest of local people to engage in this activity. Organic honey produced within a PA is an added value that may be enhanced through certification schemes with broad potential in other markets. Also, closer markets are the local municipalities who have the willingness, interest and conditions to acquire a part of the production of producers for distribution in schools and community centers within their breakfast  programs. Additionally, participatory research on the melliferous potential of communities in the PAs has been carried out so that they can better plan the establishment of apiaries to ensure a greater and more consistent production. The development and improvement of the capacities of producer organizations also enables them to face future challenges with greater certainty knowledge.

Biodiversity sustainable management

Recent reports indicate that between 2010 and 2013, trade in products derived from biodiversity in Bolivia has shown an increase of 22%, generating a total value of 1,106 million bolivianos. For the first half of 2014 export data for these products totaling US$ 197 million. Products such as the amazonic nut (Bertholletia excelsa) and quinoa (Chenopodium quinoa) cover 82% of the exports in this category; in recent years other crops and products have become important such as wild cacao, maca (Lepidium meyenii), alligator hide (Caiman Yacare), vicuña (Vicugna vicugna), the copaiba (Copaifera langsdorfii) chiquitana wild fruits such as almond (Dipteryx alata), the cusi (Attalea speciosa), and acai (Euterpe precatoria). This production has been shown to have a potential impact on social, economic and environmental spheres, becoming the spearhead to expand the value of natural resources in the local economy, boosting the synergistic participation of local and national authorities and cooperation agencies.

Pantanal landscapes (in Otuquis NP/NAIM and San Matías NAIM) have a large potential, with populations for sustainable use of the caiman and enhancement of leather products and commercialization chains existing as an opportunity to be supported during GEF 6.  SGP may aid small producer associations that meet the authorized quotas supervised by the General Direction of Biodiversity based on approved Management Plans.

Community Cultural and Eco-tourism

Given the huge natural potential in terms of biodiversity richness and conservation status of species of flora and fauna, and scenic beauty, all prioritized areas form part of the Strategy for Community Tourism and Protected Areas. Communities have also prioritized this activity as it promotes the appreciation of their environment and their culture while generating income. The areas that have prioritized community tourism have experience in developing initiatives and plans, as they have important tourist circuits within their municipalities, departments and regions, all aspects that favor development and growth. In this context, the promotion and dissemination of tourism through different means is key to its success, as are the establishment of strategic alliances with different actors, such as operators and travel agencies, municipalities and other companies and organizations linked to the sector.

An example of an SGP supported community ecotourism initiative, "Kayana: the spirit of the forest", in which visits to Kaa Iya NP/NAIM to observe fauna (mammals, such as jaguars, deer, tapirs, peccaries, foxes, monkeys, etc.), and for bird watching has generated enormous interest and participation of local people, rangers and others who have received the training and education to provide different services such as guidance, first aid , food, customer service, etc. etc.  The route has been tested with different groups of visitors, including tour operators with promising results.

Low Intensity Sustainable Fisheries and Aquaculture

In support of water resource conservation and especially the protection of groundwater recharge areas, SGP has promoted initiatives to conserve water resources through the construction, installation or improvement of small ponds for sustainable breeding of native fish, thereby promoting low-intensity aquaculture. The results have been very encouraging, and while these initiatives promote the consumption of animal protein and improve the diet of the target population, they are generating some additional income in the economy of the community members of the site. Since this is a new activity in the communities, technical support and assistance throughout the process has been especially important. Only native fish species are used in this production system.

Current production is insufficient and  there is an unmet demand for fish in the municipalities and local fairs, which has generated great expectations and interest in the local population to increase fish farming, something that is reflected in the personal investment of some producers to establish new ponds and fish production, as well as a growing interest from municipalities to support such initiatives through resource mobilization and technical assistance.

Origin Certification or Initiatives

The terms of current legislation and regulations in the country do not encourage certification in a comprehensive manner; however, some differentiation on labels of origin or brands may refer to the appropriateness of a Protected Area in production of key organic products such as honey, for example. In addition to having a secure market there is also growing potential as the government is installing large central collection and processing centers for honey in some municipalities, which may become, over the short term, the main market for producers and their associations and organizations.

A.1.4 Global Environmental Benefits

Global environmental benefits (GEB) will be achieved, in particular for biodiversity, climate change mitigation and adaptation and sustainable land management. These will result from the synergistic implementation of community-based landscape management initiatives proposed here over the short term and the aggregated longer-term impacts of new and previously funded SGP initiatives which continue operating in the Gran Chaco biome. The design and implementation of landscape resilience strategies, all of which are shaped and defined by their relation to local priorities for food security, income generation and the development of social capital for the global environment and socio-ecological resilience, will be the basis to determine the overall environmental outcomes to be achieved in GEF 6. At the same time, the project’s emphasis on multi-stakeholder partnerships will explicitly develop larger cross-cutting projects (up to USD 150,000) to upscale successful SGP-supported technologies, practices or systems identified from previous phases of the Bolivia SGP Country Programme that enhance resilient landscapes. Prospective GEB from these initiatives will be more precisely defined during project preparation.

It is expected that greater food security and/or generation of employment and income for resource-dependent communities from sustainable management of ecosystems and marketing of biodiversity products and other goods and services will provide the primary economic incentive to these communities, individually and collectively, to conserve biodiversity and optimize ecosystem services. Community organizations will build their capacities to plan and manage resources adaptively and in synergy with each other.

A.1.5 Innovativeness, sustainability and potential for scaling up

Innovativeness - This project proposes to carry out participatory, multistakeholder, landscape management in three biomes in Bolivia – Chaco, Pantanal and Chiquitanía - aimed at enhancing social and ecological resilience through community-based, community-driven projects to conserve biodiversity, optimize ecosystem services, manage land – particularly agro-ecosystems – and water sustainably, and mitigate climate change. Using the knowledge and experience gained from global and national landscape level initiatives delivered by SGP – through its COMPACT and COMDEKS initiatives and individual Country Programme approaches such as the BioCorredores para el Buen Vivir in Ecuador and others – this project will pilot distinct landscape planning and management processes in five National Parks and Natural Areas for Integrated Management: El Palmar, Kaa-Iya, Serranía del Iñao, San Matías and Otuquis, and, building on experience and lessons learned from previous SGP operational phases in Bolivia, assist community organizations to carry out and coordinate projects in pursuit of outcomes they have identified in landscape plans and strategies. This will build community ownership of individual initiatives as well as landscape management overall. Coordinated community projects in the landscape will generate ecological, economic and social synergies that will produce greater and potentially longer-lasting global environmental benefits, as well as increased social capital and local sustainable development benefits. The capacities of community organizations will be strengthened through a learning-by-doing approach in which the project itself is a vehicle for acquiring practical knowledge and organizational skills in a longer term adaptive management process. The project will also take prior years’ experience and identify and implement a number of potential upscaling opportunities during this project’s lifetime.

Sustainability - The sustainability of landscape management processes and community initiatives is predicated on the principle – based on SGP experience - that global environmental benefits can be produced and maintained through community-based sustainable development projects. Previous phases of the SGP Bolivia Country Programme have identified and promoted clear win-win opportunities with community initiatives and clusters of initiatives in areas such as sustainable use of biodiversity (medicinal plants, apiaries, ecotourism) and genetic resources, agro-ecological production practices and systems (sustainable sylvopastoral systems, permaculture, and integrated crop-livestock systems), sustainable land and water management (bunds, sediment traps, rainwater harvesting systems, small dams), renewable energy (mini-hydro power and solar), aquaculture/pisciculture, sustainable forest management and value addition to crops through sustainable practices (organic, sustainable certification schemes).  Sustainability of landscape planning and management processes will be enhanced through the formation of multistakeholder partnerships, involving local government, national agencies and institutions, NGOs, the private sector and others at the landscape level and the adoption of multistakeholder partnership agreements to pursue specific landscape level outcomes. NGO networks will be called upon for their support to community projects and landscape planning processes, and technical assistance will be engaged through government, NGOs, universities, academic institutes and other institutions.

Upscaling potential - An essential output of this project is the upscaling of successful initiatives that have been piloted successfully during previous phases of the SGP Bolivia Country Programme. The premise of upscaling in this context is that the aggregate of community adopters of successful SGP-supported technologies, practices and systems from previous SGP phases have been slowly acquiring critical mass to reach a tipping point of adoption more broadly by rural constituencies of adaptive practice and innovation and thus enhance resilience of larger landscape areas.

Multistakeholder partnerships in the five areas to be addressed by this Upgrading Country Programme will analyze the prospective critical mass of community adopters required to reach the tipping point in each of the landscapes for specific technologies, practices or systems and design and implement a program of action to reach it. Resources will be made available through the SGP strategic grant modality to finance key elements of the upscaling initiative to reduce the risk to other donors and investors. The multistakeholder partnerships will identify potential upscaling opportunities, analyze and plan upscaling processes, engage established microcredit and revolving fund mechanisms to finance upscaling components, design and implement the upscaling programme, and evaluate its performance and impacts for lessons learned for adaptive management, policy discussion and potential extension of the model to other areas of the country. Identification of specific potential upscaling initiatives will take place during project preparation.

2. Stakeholders

Project stakeholders can be identified and categorized as follows:

SGP direct partners and beneficiaries in Bolivia are community-based organizations, local communities and indigenous people who receive donations directly through their initiatives and actions that generate benefits for local sustainable development and global environmental benefits, contributing to resilience in their communities and productive landscapes. The program will work in the landscapes of 13 municipalities located in the buffer zones and natural areas of integrated management in which men, women, youth and children with high levels of vulnerability and indigenous people will be invited to participate in the planning and management of the landscape and to submit project proposals for specific initiatives of their choosing aligned with the outcomes of the landscape strategy.

These stakeholders are located in rural areas of the Chaco, Pantanal and Chiquitanía covering 13 municipalities. Local organizations will be identified primarily based on experience accumulated over 22 years and especially in new areas of intervention through participatory consultation and planning to take place during the process of project preparation to be financed by the PPG and during implementation of the project.

Community organizations: The main participants in the landscape planning exercises; prime partners in multisectoral partnerships for each landscape; signatories to the association agreements at Community level; agents of community projects and implementing landscape level. The project will support community organizations and indigenous peoples, farmers' organizations, forestry and agroforestry handlers, producers of honey, medicinal plants, plant breeders and growers, sustainable ecotourism entrepreneurs and associations of processors of biodiversity resources.

Organizations second level – landscape level: The primary participants in landscape planning exercises; prime partners in multisectoral partnerships for each landscape; agents of landscape-level projects implementation; Participants in the political landscape-level platforms. Potential partners and stakeholders include smaller networks of organic producers as the Association of Organizations of Ecological Producers of Bolivia (AOPEB), Associations of Local Producers Network Community Solidarity Tourism Organization (TUSOCO), water handlers community organizations, local electrification committees, Honey Producers Association and others.

SGP National Steering Committee: Functions as the Project Steering Committee; reviews and approves landscape strategies; advises regarding multistakeholder partnership composition and TORs; approves criteria for project eligibility for each landscape based on proposal by multistakeholder partnership and SGP Operational Guidelines; reviews and approves projects submitted by SGP Country Programme Manager; reviews annual project progress reports and recommends revisions and course corrections, as appropriate, representative participant on policy platforms.

SGP Program Manager (National Coordinator), and team: Responsible for the implementation and operation of the program in Bolivia SGP generally acts as Secretary of the National Steering Committee, mobilizing co-financing, the organization of strategic partnerships with NGOs and NGOs, and in general, to manage the achievement of the objectives of the Country Programme as described in the Project Document.

NGOs: Direct and provide initial baseline assessments; assist in leadership of participation and planning processes of the landscape; partners in multisectoral partnerships for each landscape; signatories to the association agreements at Community level; provide technical assistance to community organizations for application / presentation of their projects; potential participant in policy and innovation platforms. Potential interested NGOs include those with experience in the specific areas of action of each landscape plan. These may include organizations such as CEPAC, SAP, FCBC, WORLD VISION, CIPCA among others. These NGOs will be identified in greater detail during the project preparation phase and later during the formulation and implementation of community projects.

Local, departmental and regional governments and commonwealth organizations of local governments, mainly including 13 district municipalities, the municipal departments of Environment and Economic Development offices: Participate in baseline assessments and landscape planning processes; partners in multisectoral partnerships for each landscape; signatories to the association agreements at Community level; main participants in the political platforms.

National institutions, including the Ministries of Environment and Water, Rural Development, Agriculture and Lands, Productivity and Economy, Culture and Tourism, Labour and Employment, the National Association of Ecological Producers, and others. The partners in multisectoral partnerships for each landscape; selected members of the National Steering Committee where relevant or appropriate, to provide technical assistance to community organizations for the implementation of their projects; main participants in the political platforms. These entities may include specialized or specific deputy ministers as the Ministry of Environment, Biodiversity, Climate Change and Forest Management and Development, the National Protected Areas Service (SERNAP), and Management Committees, Municipal Departments of Environment, Economic Development, Tourism, and Regional Tourism, Technological Innovation Centers, Handicrafts and Tourism - CITES National Agricultural Health Service (SENASAG), National Institute of Agricultural and Forestry Research (INIAF)

Private Sector: Partners in multisectoral partnerships for each landscape; signatories to the association agreements at Community level, as appropriate; potential participant in political platforms. Potential partners include companies with social responsibility components, such as Destination Management Organization - OGD for tourism issues, chambers of commerce of Micro and Small Enterprises.

# Academic, public and private institutions: Assist in participatory assessments and planning processes of the landscape; partners in multisectoral partnerships for each landscape; signatories to the association agreements at Community level, as appropriate; provide technical assistance to community organizations in the implementation of their projects; develop and implement applied research initiatives with local participation and potential participant in political platforms.

3. Gender Considerations. Are gender considerations taken into account? (yes  /no ).

SGP brings benefits to the livelihoods of the greatest number of communities and individuals in the areas of project intervention. An important strategy of the Bolivia Country Program is to dedicate at least 20% of the resources exclusively to the most vulnerable groups such as women and marginalized groups of rural communities and indigenous groups present in the project area. It is expected that activities such as rural tourism; organic farming; beekeeping; production processing and transformation of medicinal plants; handicraft and other income-generating activities provide other tangible social benefits such as increased food availability or complementary income.

Access to clean energy sources will benefit women and children by reducing work collecting firewood as well as indoor pollution from their homes and dwellings. Renewable energy sources provide small-scale communities with electricity for lighting, communication, health and social and community services, and other important services in areas outside the network, but also allow the use of energy for productive purposes such as pumping water for human and animal consumption, food processing, efficient irrigation systems in agriculture, etc.

Gender is a cross-cutting theme in the criteria for disbursement of SGP initiatives and is permanently incorporated into the SGP grant project cycle. Under GEF 6, the same trend will continue, strengthening gender equality and the empowerment of women as essential to development projects and sustainable impacts on the global environment. Community projects supported by SGP promote equitable economic benefits for men and women, and incorporate them in the same way, in all decision-making positions. Projects and governance mechanisms established with support from the SGP aim to achieve this goal and efforts are made to remove participation constraints. SGP will also continue to collect and maintain data and indicators disaggregated by gender in grant projects.

The Country Program team as part of the preparation of the project will develop a specific strategy to engage women/girls groups and small local organizations formed by women as key stakeholders in managing the landscape and natural resources. During project preparation, consultations with community groups and non-governmental organizations during the formulation of the landscape strategy will be undertaken so as to guarantee the participation of woman, depending on their preference of mixed or separate groups.

The Country Program team will work with the gender focal point in the National Steering Committee to identify potential project ideas for the initial discussions with groups of women and girls. Gender sensitive NGOs dedicated to supporting women/girls groups will be consulted for the definition of grant objectives and activities as necessary. Women groups will be asked to evaluate the performance of their projects to identify lessons and insights for adaptive management, and recommendations of specific gender policies.

# 4 Risks.

# Risks to the proposed project, potential consequences and proposed mitigation measures are detailed below.

| Identified risks | Potential consequence | Risk rating (L: Likelihood, I: Impact) | Mitigation measures | Risk category |
| --- | --- | --- | --- | --- |
| Civil society organizations that have a low level of technical and management capacity implement grant projects | Low capacity and awareness of local NGOs and CBOs may decrease demand for community driven projects as well as influence the pace and implementation of grant projects once approved. | L: Low I: Medium | Risk mitigation systems in place will be strengthened to maintain or improve CBO and NGO performance. The Bolivia SGP Country Programme works with all grantees to help build capacities by identifying appropriate rates of disbursement, linking grantee partners to learn from each other (peer-to-peer), and working in a flexible manner that responds to the strengths and comparative advantages of grantees. The SGP Country Programme also reduces risk by supporting replication of good practices that have proven to deliver on GEF strategic priorities at the community level. The National Steering Committee (NSC), with representation from civil society leaders, government institutions, and donors further provides support for effective design and implementation of SGP-financed projects. | Programmatic |
| Low capacities of the different community organizations to coordinate with each other and with different government levels. | Lack of coordination among the essential actors in the landscape will affect landscape planning and management processes negatively and result in low government support and recognition of integrated landscape strategies. | L: Low I: medium | The participatory planning processes to take place in each landscape will build trust and communication between communities. The participation of the different government entities in this planning process as well as in the multistakeholder partnerships will also improve communication and facilitate collaboration. | Programmatic |
| Difficulty for communities in accessing markets for goods and services produced with SGP support | Production projects will not succeed in accessing markets for their goods and services. | L: Low I: medium | Sustainable production can be more expensive than conventional methods. Producers engaged in unsustainable production practices may be able to undercut prices for similar products and services produced by sustainable systems, resulting in unfair competition. Also remoteness and lack of access to different markets to commercialize products may reduce revenue or long term production in these areas. This risk can be mitigated by optimizing and scaling-up production, integrating commercialization chains and improving the end product through processing and by identifying certification of origin or other added value that may compensate these barriers. | Programatic |
| Influence of climate change will undermine efforts to arrest biodiversity loss and land degradation | A progressively drier and warmer climate may affect the availability of water resources and production revenues | L: medium I: medium | The risk of climate change is one of several reasons that the project has chosen to emphasize landscape-level management and coordination in production landscapes. The project will promote a variety of no-regrets adaptive biodiversity and land resource planning and management actions in forests, pastures and other agroecosystems. | Programmatic |

# 5. Coordination with other relevant GEF-financed and other initiatives.

The National Steering Committee of the SGP Country Programme in Bolivia has consistently promoted the collaboration of the Country Programme with GEF and government financed projects and programmes for many years.

Biocultura National Programme is a joint initiative of the Ministry of Environment and Water through the Ministry of Environment, Biodiversity, Climate Change and Forest Management and Development (VMA) and the Swiss Agency for Development and Cooperation (SDC) which aims to contribute to the conservation of ecosystems and the "Living Well" (poverty reduction) of indigenous people in the Andean region of the country and rural communities through sustainable management of biodiversity, as well as respect and the appreciation of local cultures.   To achieve the above objective, the program promotes: (i) the development of public policies based on local rules and practices of management of biodiversity; (ii) the development of inclusive, sustainable and viable economic alternatives; (iii) conservation of the critical functions of ecosystems and (iv) the appreciation of the cultural identity of communities. Also, Biocultura supports capacity building of the national government and local governments responsible for implementing the policies related to the use and conservation of biodiversity. The Biocultura program is aligned to the National Development Plan (NDP) of Bolivia, supports the implementation of the Convention on Biological Diversity (CBD) and the Millennium Development Goals (MDGs). The VMA leads and coordinates its implementation in close collaboration with public and private entities. Most of the activities are allocated to implementing partners through competitive mechanisms. Accountability of the activities of implementing partners is ensured through the participation of local governments, rural native indigenous representations and local counterparts. SGP has collaborated and identified synergies with Biocultura in GEF 5 phase, where there was a territorial coincidence of work and scope in El Palmar NAIM,  and for GEF 6, and Biocultura 2nd Phase, SGP has also forseen coordination in two other joint priorities: El Palmar NAIM and Iñao NP/NAIM.

The GEF financed Regional Program: “SFM Sustainable forest management in the transboundary ecosystem of the Great American Chaco - GEF Chaco", operates in the three countries (Argentina, Paraguay and Bolivia) and is executed via the Department of Water Resources in Bolivia and is implemented and administered by the OAS-UNEP and UNDP. This project seeks to contribute to the reversal of land degradation trends in the Gran Chaco through supporting sustainable land management in the production landscape. The project complements the efforts of Argentina, Bolivia and Paraguay, under the Sub-Regional Action Program for Sustainable Development of the Gran Chaco (SRAP) by: (i) mainstreaming Sustainable Forest Management (SFM) and Sustainable Land Management (SLM) principles into policy and legal frameworks; (ii) providing capacity building at regional, provincial/departmental and local levels; (iii) developing tools and instruments to mainstream SFM and SLM concerns into regional land use planning and decision making processes; and (iv) designing and implementing on-the-ground investments and increased stakeholder participation to implement sustainable management practices, in order to reduce land degradation and combat desertification. This project will conclude at the end of 2016. During the GEF 6 period the project will be developed in three municipalities and similar communities where SGP GEF 6 will be working, thus enabling synergies and further coordination and complementarities between both GEF funded initiatives.

The Project "Managing environmental liabilities in protected areas and their influence on water resources", is aimed at supporting a joint effort of the Ministry of Environment, Biodiversity, Climate Change and Forest Management and Development (MABCCGDF), the National Service for Protected Areas (SERNAP), the Geological Survey and Mining (SERGEOMIN) under the Ministry of Mining and Metallurgy, and the Ministry of Hydrocarbons and Energy, entities that addressed the issue related to the management of environmental liabilities in mining and hydrocarbon comprehensively in and around protected areas, including water resources. The expected strategic outcomes of the Project are: i) Update and/or generate information on extractive projects in operation and abandoned mining and hydrocarbon sites, their socio-economic impact and the risk of pollution, to manage environmental liabilities in 10 prioritized National Protected Areas; ii) To design policies, standards and intervention strategies designed to manage environmental liabilities of  mining and hydrocarbon activities in 10 National Protected Areas and minimize the future effects of this type of mining activities; and iii) Generating knowledge for managing environmental liabilities, institutional, social and academic level to increase capacity to manage environmental liabilities mining and hydrocarbon activities. The project is funded by the European Union and implemented through UNDP Bolivia.  It’s implementation started in January 2015 and concluded in December 2017; territorialy the project will share intervention with SGP in two protected areas: San Matías NAIM and Iñao NP/NAIM.

6. Consistency with National Priorities

- The new vision of the country, raised since the adoption of the Constitution of the State (CPE) in 2009, approaches and presents new challenges for environmental management and protection of natural resources. The search for the “Buen Vivir” or Living Well, through integral development must mantain harmony and balance with Mother Earth. CPE states that public policy must be oriented towards satisfying the interests of the Plurinational State of Bolivia and care for the needs of Bolivian people, ensuring the maintenance of the regenerative capacity of the life systems.  In this context the SGP project for GEF 6 is directly relevant,  supportive, and consistent with Bolivia’s new Constitution.

- One of the purposes stated in the CPE is to promote and ensure responsible and planned utilization of natural resources, and promote industrialization, through the development and strengthening of the productive base in different dimensions and levels, as well as environmental conservation, for the welfare of present and future generations (Article 6, paragraph 6). SGP provides local examples of how the well being of communities and community organizations may be achieved through the conservation, restoration, and enhancement of livelihoods may also contribute to climate resilient landscapes.

- To realize the mandate of the CPE, in 2013 the Patriotic Agenda 2025 was consolidated as a long-term plan whose purpose is to establish coordination and integrated approach between the different levels of government so that development plans be routed under common goals. Three of the thirteen Patriotic Agenda pillars are directly related to the management of natural resources and the environment: Pillar 6. Sovereignty with diversification and productive integral development without the dictatorship of the capitalist market, 7. Sovereignty over our natural resources nationalization, industrialization, and commercialization in harmony and balance of Mother Earth, and 9. Environmental sovereignty with integral development and respect for Mother Earth’s rights.

- A goal of the agenda which the SGP contributes directly to is: In 2025 we have achieved to consolidate the link between the agricultural and forest agenda and full complementarity exists between food production and forest conservation.

- In 2012 Bolivia adopted the Law of Mother Earth and Integral Development for Living Well (No. 300), as a framework law which is relevant as it becomes the framework under which specific sectoral legislation (e.g. water, environment, hydrocarbons, etc.) must be enacted in the coming years under the new Constitution of the emerging state for the transformation process in Bolivia.

- For the operational implementation of this Law, Bolivia has adopted an approach of life systems of Mother Earth, allowing a territorial scope of action based on complementarity and interdependence among human rights, development and Mother Earth. This approach is compatible and harmonious with the landscape approach for integral, sustainable development supported by this project and SGP.

- Regarding the Plurinational Climate Change Policy (2015 Work Document) the project is consistent with the following policy objectives:

- Integrated and sustainable forest and other life system management for adaptation and mitigation of climate change (No.1)

- Transformation of the energy grid towards less contaminating fuels and use of renewable energies to reduce GHG emissions. (No.2)

- Implementation of energy efficiency in the industry, productive development, commerce and services to reduce GHG emissions. (No.3)

- Strengthen climate resilience in productive agricultural, forestry, pisiculture, adaptation systems to improve food security and sovereignity in harmony with Mother Earth. (No.5)

- Restoration, protection and conservation of soils in climatically vulnerable areas. (No.6)

- Integrated water management in areas vulnerable to climate change, to strengthen climate resilience. (No.7).

- Reduction of risk and integrated capacity development and strengthening, based on knowledge management, for the prevention, mitigation and recuperation of disasters related to climate change. (No.8).

- Recuperation and application of traditional knowledge and techniques relevant to mitigation and adaptation to Climate Change complemented with modern sustainable technology.

- Inter-cultural and inter-scientific investigation and knowledge production for integral development  in harmony with Mother Earth.

- Furthermore, the SGP project for GEF 6 takes into account the three mechanisms for adaptation and mitigation as well as the fund described in the CC Policy and defined under the Law of Mother Earth and Integral Development for Living Well: a) The Joint Adaptation and Mitigation mechanism for Integrated Management of Forests and Mother Earth that has the objective so strengthen, conserve and protect life systems and environmental functions, b)  Mitigation mechanism for Living Well is oriented to strengthen and promote climate mitigation actions in industrial, productive, energy and other activities, c) Adaptation mechanism for Living Well is oriented to strengthen and promote adaptation processes especially for water management, food sovereignty and security, risk prevention and reduction, education and health. Furthermore the Mother Earth Plurinatural Fund is designated as the financial mechanism under the Mother Earth Plurinational Authority which will constitute the mechanism to administer, assign, mobilize resources to implement plans, programs, projects, initiatives and activities for the Mechanisms described above.

- Another relevant national instrument to which this project contributes is the Master Plan for the National System of Protected Areas (SNAP, in Spanish).  The landscape approach promoted by SGP is consistent with the capacity strengthening for the social participation of communities and social organizations within PAs as well as the promotion and application of management models with more social inclusion (Policy 4 of the Master Plan), and the generation of opportunities for economic development of local populations in harmony with Mother Earth (Policy 3 Master Plan) and the conservation of the natural patrimony for common well being (Policy 2).

- The Fifth National Report to the CDB of the Plurinational State of Bolivia states the importance of the consolidation of sustainable and harmonious relationship between all beings, life systems and Mother Earth and identifies the current policy framework related to biodiversity conservation, sustainable use, and links with climate change.  Although the NBSAP is still not consolidated, the national framework and priorities described above, under which it is being developed, are. It is important to highlight that SGP is aligned with these instruments and constitutes a mechanism for their implementation.

Contribution of the project to the Aichi targets - A central feature of this project is the development and implementation of landscape and seascape sustainable management plans at different geographic scales to ultimately have an impact on large ecosystems. The small grant projects financed by the project proposed here will achieve global environmental benefits as a consequence of the synergistic effects of activities that increase communities’ governance and technical capacities and skills, and that produce livelihood benefits. This project will in principle contribute to all Strategic Aichi goals, but in particular to the targets and specific elements listed below, where SGP can make a contribution through community sustainable livelihoods and landscape planning and management approaches:

Target 2: By 2020, at the latest, biodiversity values have been integrated into national and local development and poverty reduction strategies and planning processes and are being incorporated into national accounting, as appropriate, and reporting systems. By developing and implementing micro-regional and landscape sustainable management plans linking poverty reduction to biodiversity conservation and sustainable use and monitoring, SGP will contribute to local-level poverty reduction strategies consistent with this target.

Target 5: By 2020, the rate of loss of all natural habitats, including forests, is at least halved and where feasible brought close to zero, and degradation and fragmentation is significantly reduced. The project will support sustainable production practices that help conserve terrestrial (including dry forests), and freshwater habitats and avoid ecosystem fragmentation. SGP will collaborate with organizations working on REDD+ activities at the state and local levels.

Target 7: By 2020 areas under agriculture, aquaculture and forestry are managed sustainably, ensuring conservation of biodiversity. The project will support communities in these endeavors and will ensure that all species used for aquaculture and forestry community projects are native species. It will also support early detection and where possible eradication of invasive alien species, also contributing to Target 9.

Target 13: By 2020, the genetic diversity of cultivated plants and farmed and domesticated animals and of wild relatives, including other socio-economically as well as culturally valuable species, is maintained, and strategies have been developed and implemented for minimizing genetic erosion and safeguarding their genetic diversity. The project will support communities to maintain the genetic diversity of key species important for agriculture or culturally (traditional medicine).

Target 14: By 2020, ecosystems that provide essential services, including services related to water are restored and safeguarded. The project will support communities to maintain key ecosystem services within their territories in the selected landscapes and seascapes, particularly those of forests.

Target 15: By 2020, ecosystem resilience and the contribution of biodiversity to carbon stocks has been enhanced, through conservation and restoration, including restoration of at least 15 per cent of degraded ecosystems. The project will support forest ejidos and communities to sustainably use their forest resources while maintaining and, where possible, enhancing carbon stocks.

SGP contribution to these targets will be addressed, as appropriate and feasible, through individual grants to community projects approved and implemented in alignment with and pursuit of landscape/seascape outcomes for biodiversity conservation and sustainable use. The quantification of proposed targets and indicators will take place during the planning phases of each NP/NAIM and landscape management plans with the direct involvement of landscape stakeholders and under the guidance of the SGP National Steering Committee. A baseline assessment will be carried out in each landscape prior to outcome definition and target identification. Progress towards these landscape outcomes and targets will be tracked in landscape level stakeholder meetings at mid term and at the end of the project. More precise definition of the contribution of this project to the Aichi targets will be provided after the project planning phase financed by the PPG.

7. Consistency with GEF policies

GEF Policy on Upgrading SGP Country Programmes and Strategic Directions

The project proposed here is in full conformity with the policy for upgrading of SGP Country Programmes as first described in GEF/C.36/4 Small Grants Programme Execution Arrangements and Upgrading Policy for GEF-5 and then in GEF/C.46/13 GEF Small Grants Programme: Implementation Arrangements for GEF-6, approved by GEF Council in Cancun. This GEF SGP Upgrading Country Programme will continue to follow the SGP’s Operational Guidelines to ensure compliance with longstanding best practice and GEF policy for the SGP.

At the same time, the outcomes of the project proposed here are fully aligned with the SGP Strategic Directions for GEF 6 found on pages 200-206 of GEF/R.6/20/Rev.04, GEF Programming Directions, approved by GEF Council in March 2014.

8. Knowledge Management.

Knowledge management, including the dissemination of best practices and lessons learned, will remain an important element of the GEF-SGP Bolivia Country Programme during its 6th Operational Phase. The knowledge management approach will have as a primary product a case study summarizing lessons learned and best practices from the landscape approach for each of the project areas of the five PA/NAIM based on evaluation of implementation results and their contributions to global environmental benefits, local development objectives and landscape level outcomes, including the development of social capital.

Knowledge products (including multimedia recordings, systematization of best practices, the coverage of the media, radio spots, among other methods) will focus on the exchange of knowledge related to: processes watershed restoration; know-how to convert and improve productivity while contributing to sustainable landscapes; how to strengthen community participation in the annual operating plans of municipalities or local governments; implementation of management and monitoring plans of protected areas, risk management plans in vulnerable areas to climate variability and climate change; water management practices; land management practices; production development plans, etc. Specific examples of knowledge products that have resulted from applied investigation are the dissemination and practice of research in the pepper processing chain to add commercial value to local production in the Chaco production landscapes.  Peer to peer exchanges regarding community tourism experiences form GEF 5 and previous SGP phases has also provided effective dissemination of best practices.

This knowledge will be systematized for dissemination at the landscape level through policy dialogue platforms, networks of landscape management communities and multi-stakeholder partnerships and knowledge fairs and other exchanges; nationally through the National Steering Committee, strategic partnerships and networks and national knowledge fairs where appropriate; and globally through the worldwide network of the Small Grants Program knowledge management system, as well as that of UNDP.

part iii:  approval/endorsement by gef operational focal point and GEF agency

A. Record of Endorsement of GEF Operational Focal Point (s) on Behalf of the Government(s):  
      (Please find attached the Operational Focal Point endorsement letter)

| Name | Position | Ministry | Date (MM/dd/yyyy) |
| --- | --- | --- | --- |
| Lic. Gonzalo Rodriguez Camara | GEF Operational Focal Point | Ministry of Environment, Biodiversity, Climate Change and Management and Forest Development | 07/30/2015 |

B. GEF Agency Certification

This request has been prepared in accordance with GEF policies and procedures and meets the GEF criteria for project identification and preparation under GEF-6.

| Agency Coordinator, Agency name | Signature | Date (MM/dd/yyyy) | Project Contact Person | Telephone | Email |
| --- | --- | --- | --- | --- | --- |
| Adriana Dinu Executive Coordinator UNDP-GEF |  | 09/01/2015 | Nick Remple | (212) 906-5842 | nick.remple@undp.org |

ANNEX I.   Description of the three ecoregions: Gran Chaco, Chiquitania and Pantanal

The complex topography and geographic location of Bolivia has allowed it to be recognized as one of the countries with the greatest diversity of ecoregions. There are 12 described ecoregions that can be further subdivided into 23 subecoregions. Species richness is linked to this geographic diversity. In this respect, Bolivia is one of eleven countries with the greatest wealth of plant species, one of the top ten countries with the greatest diversity of birds and mammals, fourth in wealth of butterflies, included among the thirteen countries with greatest wealth of amphibians, and within the eleven most diverse in freshwater fish species. Moreover, the Country is also recognized for its high crop genetic diversity, making it a key part of the Andean center of origin of domesticated plants and their wild relatives. For example, along with Peru, it is the center of origin of the potato (more than 4,300 varieties of native potatoes).

The National System of Protected Areas (SNAP) fulfills a role of protecting important environmental functions regarding microclimate, landscape conservation, watershed protection, and water conservation, among others. In this sense, it is estimated that a total of 144 watersheds (level 4) are linked to the 22 national protected areas, of a total of 329 basins nationwide. This reflects the importance of SNAP in regulating the hydrological regime. Environmental functions of SNAP benefit a large number of people, as it is estimated that the population linked to protected areas is around two million people, corresponding to 20% of the total population. The population living within protected areas is estimated at 116,000 inhabitants.  The SNAP is administered nationally by SERNAP but operated territorially through Management Committees that include social representation and other stakeholders such as municipalities, and other local organizations based in the respective Areas.

Bolivia recognizes that the conservation of biodiversity is essential to ensure the resilience of ecosystems, and is  key to adaptation to climate change. Moreover, the integrated and sustainable management of ecosystems contributes to climate change mitigation. In this regard, protected areas act as one of the most important means of conserving ecosystems and protecting biodiversity in situ, as do other territorial units that implement and consider the management of biodiversity such as the Originary Indigenous Farmers Territories.

a) Chaco

The Gran Chaco is a transboundary eco-region shared by Argentina, Bolivia, Brazil, and Paraguay encompassing some 850,000 Km2 stretching from about 17° to 33° South latitude and between 65° and 60° West longitude. The eco-region harbours the largest forested area in South America after the Amazon region and shows an impressive wealth of plant and animal diversity. The predominant vegetation of the Gran Chaco is open dry woodland dominated by Schinopsis sp with cacti and bromeliads, stretching continuously over large areas, with a grass ground cover. Other typical vegetation types are palm savannahs, savannah parkland, low tree and shrub savannah, with halophytic shrubs on saline patches. The eco-region is an important bird migration route between the southern (Austral) and northern (Neotropical) regions. The Chacoan Pecary (Catagonus wagneri), discovered in the 1970’s is undoubtedly the most famous endemic mammal in the region. The Chaco is also a center of endemism for armadillos with at least ten species. Other important species include the Lesser mara (Pediolagus salinicola), Giant tuco-tuco (Ctenomys conoveri), Greater rhea (Rhea americana), Brushland tinamou (Nothoprocta cinerascens), Chaco chachalaca (Ortalis canicollis), Black-legged serieman (Chunga burmeisteri), Paraguayan caiman (Caiman yacare), Southern boa (Boa constrictor occidentalis), False water cobra (Hydronastes gigas), Horned frog (Ceratophrys sp.), and Argentine walking frog (Phyllomedusa sauvageii).

The Bolivian Chaco, which encompasses approximately 15% of the Gran Chaco area, covers the Eastern and Southeastern parts of the Departments of Chuquisaca (18,772 km2), Santa Cruz (22,737 km2), and Tarija (86,246 km2). Large tracts have high soil fertility and a topography that is favourable for agricultural development, but this comes in combination with challenges for farming: a semi-arid to semi-humid climate (600–1300 mm annual rainfall) with high evaporation levels, a six-month dry season and two thirds of the region without groundwater or with groundwater of high salinity. Soils are generally prone to wind erosion once the vegetative cover has been cleared.

The Bolivian Chaco is sparsely populated with an estimated 300,000 inhabitants, although the population has increased by 26.79% between the census in 2001 and the latest one in 2012. According to the 2012 census the population identifies itself as: Aymara (3.4% - 1,531); Quechua (20.61% - 9,284); Guaraní (14.05% - 6,328); Weenhayek (11.18% - 5,036); Intercultural (7.29% - 3,285); Mestizo (9.27% - 4,175); Mennonite (1.37% - 615); Tapiete (0.2% - 90) and Other (not identifying with any group) (29.24% - 13,172).  57% of the population of the three Departments is identified as urban. This means that the average population density in the rural areas of the Chaco is approximately one inhabitant per square kilometer, while the most densely settled area holds an average of 8.46 inhabitants per square kilometer.

There are several settlements of Ayoreo, Chiquitano, Weenhayek and Guarani indigenous peoples who maintain their languages and traditional lifestyles, often combining hunter-gatherer activities with agriculture, depending on the season. According to the 2001 census the indigenous population in the Bolivian Chaco is about 80,000 of which 78% live in poverty. The population of the Chaco eco-region also includes cattle ranchers and large and small-scale farmers.

b) Chiquitanía

The Chiquitania eco-region is located at the southeast corner of Bolivia, covering much of the eastern department of Santa Cruz and areas bordering Paraguay and Brazil. Most of the Chiquitania flora is very similar to that of the Gran Chaco, that is, mostly a shrub park with abundant species of hard and thorny woods scattered among bushes and pastures with trees like palms (especially yatay), drunk sticks, guayacanes, and quebrachos carob. However in the northern part of the Chiquitania, especially in the gallery forests along the banks and floodplains of major tributaries of the Amazon, are large softwood trees typical of the Amazon biome, including mahogany, as well as others valuable for their oils, essences, and balms.

Fauna includes the jaguar, puma, peccaries, tapirs, ocelots, maned wolf, the yaguarundí, the aguarachay, guazuncho, and the marsh deer in the cleared areas. Also to be found are rheas, and in the rivers and marshes, capybaras, caimans and giant otters. In addition to alligators, snakes such as the anaconda, and rattlesnake are also found. Avian wildlife species include important populations of toucans, chimangos, macaws, vultures, harpy eagles, hawks, wild turkeys, ñacurutú and other owl species.

A large part of the Chiquitania population lives in small communities of 30 to 50 families. The Chiquitano’s primary economic activity is agriculture, growing maize, manioc, beans, pumpkins, sweet potatoes, and other crops for subsistence and market along with hunting for forest animals for protein. Whenever possible, the men take work as labourers on livestock ranches or at sawmills. An important source of revenue is the wage earning jobs on haciendas, especially in activities connected to cattle raising. Some of the men in the communities also do sporadic work for the military garrisons, such as weeding, cattle slaughtering and cleaning. Women may also work as maids in nearby towns.

Currently, the economic driver for the region centres around extensive traditional livestock production, which also occupies the flatlands of the Pantanal and Cerrado. Nonetheless, there have been increasing numbers of Brazilian and Bolivian enterprises who leverage their economic power to buy up large tracts of forested land. They then clear the land and convert it to cultivated pasture through the use of heavy equipment and fire.

The second main activity in the region is forestry, with the Chiquitano forest holding one of the largest certified forests in Bolivia (1.2 million ha). A half dozen large private concessions and a growing number (currently approximately 30) of Agrupaciones Sociales del Lugar (ASLs) occupy a considerable portion of the forests in the region.

c) Pantanal

The Pantanal is an alluvial plain that covers the westernmost part of Brazil and neighboring parts of Bolivia and Paraguay. It is one of the largest wetlands in the world, located in the region of Mato Grosso and Mato Grosso do Sul in Brazil and reaching into Paraguay and Bolivia. In Bolivia it is located in the eastern part of Santa Cruz, where 10-15% of the ecoregion is located.

The Pantanal (known as Laguna de Jarayes in Bolivia and Paraguay) is supported in a depression of the crust formed by the same process that gave rise to the Cordillera The Andes; here flock several rivers, which together comprise an enormous internal delta formed by their sediments, including the Paraguay River. There is an average annual rainfall between 1000 and 1400 mm.  During the wet season between December and May, the water level rises 3m and the Pantanal is flooded by 80%, resulting in a system that dominates the aquatic flora, which reaches here an expression unequaled in any other in the world. Often reference is made to this area as "the ecological system of the world's largest freshwater" and although the calculations of its total area vary depending on the source of information, is certain to occupy much ground: between 140,000 km and 220,000 km².

During the rainy season, rain falls from 70- 80% of the total annual rainfall - some 800-1,600 mm, depending on the area it is located. With this rainfall, the water level in the marshland can go up to five meters compared with the dry season. Among the areas of seasonally flooded or dry plains, there are marsh areas and permanent wetlands. Various types of forest are mixed with large areas of the highlands, such as the Gran Chaco of Bolivia and Paraguay. It is these dynamic qualities that give the area its special characteristics.

The Pantanal belongs to the Brazilian-Paranaense biogeographic region. More than 3,500 known plant species, including diversity of greater aquatic flora is concentrated growing in the swamp. The ornithological diversity is also important, with about 657 species of tropical birds, many of them endemic. Among the larger animals that inhabit the region are the jaguar (Panthera onca), the capybara (Hydrochoerus hydrochaeris) and plain tapir (Tapirus terrestris). Other fauna include the anaconda, caiman, alligator, peccary, giant river otters, spider monkeys,  swamp deer, toucans and macaws, among many others. There are around 95 species of mammals in the area. The area is also an important step in the routes of migrant birds from around the world, and this increases the number of species. The result is one of the most diverse communities of birds on the planet. Even endangered species can still be seen in this area such as the Hyacinth macaw (Anodorhynchus hyacinthinus), which is the largest member of the family Psittacidade.

This area also has functions essential to the health of the entire water system. For example, a function is to purify the Paraguay River of heavy metals that come from the mining industry. Another function is to serve as a sponge to mitigate the impact of flooding during seasonal rains and resulting in a large flow regulator. Without the Pantanal, there is a high potential of the Paraguay and Parana rivers, with serious effects for communities and individuals in Paraguay, Brazil and Argentina.

Part of the Pantanal has the status of a national park; in Brazil the area under this protection add 1 878.18 km² while in Bolivia is 31 898.88 km². These parks have been designated of international importance under the Ramsar Convention. In the rest of the region fishing, poaching, tourism and agricultural activities represent threats for ecosystem conservation when done intensively. Yet the Bolivian portion of the Pantanal remains practically inaccessible and unknown due to the lack of access, hotel infrastructure and transport, for this reason, sustainable livelihoods are also a great challenge for communities living within the area.

The human population density is very low in the marshland area, although the numbers go up in the highlands around it. Cattle ranches are the most important industry of the Pantanal area. Other important economic activities are agriculture with crops of sugarcane, maize, rice, cassava, soy and others), mining (diamonds, gold, iron, natural gas, and manganese) as well as tourism. The Pantanal faces a major challenge for its future. The difficulty of maintaining a balance between the natural environment and the needs of the human population increases every year.

The Pantanal is relatively pristine when compared to many other wetland systems and in particularly this is true of the interior of the Pantanal, where population and infrastructure remain low. However, if one considers the entire watershed, there are numerous challenges to the Pantanal, and likewise growing concerns within the Pantanal itself.

Water pollution is one such threat to the integrity of the Pantanal. Among the challenges are mining byproducts, agrochemicals, sewage, and garbage. Mercury contamination from its use in concentrating placer gold is one such problem. Although in 1988 Brazil prohibited using mercury in gold mining, enforcement is difficult given the isolated area and innumerable mines, and high levels of mercury have been found in fish and fish-eating birds. Fertilizers, herbicides, and pesticides used in agricultural activities, and washed into the watery environment, are another problem, particularly given that the poor soil has led to the heavy use of agrochemicals. Untreated domestic sewage and garbage are likewise discharged into the wetlands and rivers, much coming from cities and towns in the highlands outside the Pantanal. Although the Pantanal has an amazing capacity to clean the wastes and chemicals, the extent that it can absorb the increased pollution is a concern.

Habitat destruction, poaching, over-fishing, illegal hunting, and the business of capturing threatened and endangered species for export or for the Brazilian pet trade is causing grave concern about loss of biodiversity. Many species that were once found in large numbers, such as the giant river otter, maned wolf, ocelot, cougar, jaguar, giant anteater, marsh deer, and giant armadillo are now all listed as endangered or threatened with extinction. In all, at least 50 species are reported to be threatened or endangered in the Brazilian Pantanal. Although Brazilian environmental law is significant, enforcement is difficult, especially given that animal traffickers can easily cross over the border to Paraguay or Bolivia.

The process of clearing land for agriculture, opening of new roads, logging, and extensive burning in the watershed accelerate erosion and sedimentation. During September to October, fires are particularly prevalent, as ranchers burn old pasturage to stimulate new green growth for cattle grazing, or as a cheap and easy means of clearing land for agriculture. Development in the Bolivian and Brazilian highlands (that drain in Pantanal), and subsequent land clearing, has led to extensive deforestation and increased erosion. The seriousness of this threat is evident in the Taquari River, where sedimentation has lead to significant channel alteration, to the extent of the loss of over one hundred farms, branching of the river to where the navigable channel is 30 percent of its former size, and significant decline in the fishing industry.

The natural hydrology of the Pantanal region is also being impacted by construction of local dams and dikes, many by landowners to keep water off their land. This creates new water-flow patterns and increased flooding outside of these areas, and a decline in soil fertility as a result of loss of the periodic nutrient-replenishing flooding.

The Bolivian Pantanal has considerably more protected area than the Brazilian side. 90 percent or more of the Bolivian Pantanal has some degree of legal protection, and substantial portions are inside two recently created federally protected areas. The first is the Otuquis Pantanal National Park and contiguous Otuquis Natural Area of Integrated Management (ANMI Qtuquis), which occupies 1,005,950 hectares total. The second is the San Matías Natural Area of Integrated Management—ANMI San Matías, which totals 2,918,500 hectares. These two protected zones, established in 1997, were designed not only to safeguard the Pantanal but also the greater basin, including a variety of other environments, such as subhumid Chaco forests, dry forests, and so forth. It is estimated that the surface area actually occupied by the Pantanal in these areas corresponds to about 12 percent of the San Matías protected area and 24 percent of the Otuquis protected area (Montaño 1999). Furthermore, the San Matías Natural Area of Integrated Management lies next to Brazil’s Pantanal National Park, thus permitting the establishment of an extensive tract that will aid preservation efforts.

Annex II.  Priority areas for SGP Bolivia for GEF 6

Gran Chaco SGP Bolivia GEF 6 Areas

14. el palmar Natural area for integrated management

19. Kaa Iya of the Gran Chaco National park and Natural area for integrated management

22. Inao National park and Natural area for integrated management

Chiquitania and pantanal SGP Bolivia GEF 6 Areas

15. San Matias Natural area for integrated management

20. Otuquis National park and Natural area for integrated management

GEF_PIF_60

Instituto Nacional de Investigaciones Agrícolas y Forestales

Kaa-Iya del Gran Chaco, El Palmar, Serrania del Aguaragüe, Serrania del Iñao, San Matías and Otuquis.

According to Article 25 of the General Protected Areas Regulations - Supreme Decree 24781: “The category of National Natural Area of Integrated Management (NNAIM) aims to reconcile the conservation of biodiversity with sustainable development of the local people. It is a mosaic of units including representative samples of ecoregions, biogeographic provinces, natural communities or species of flora and fauna of singular importance, areas of traditional systems of land use, areas for multiple use of natural resources and strictly protected core area.”

For the purposes of this project a landscape is a unit of land comprising a mosaic of land uses involving a number of communities - not individual landholdings but also not so large a unit that individuals are unfamiliar with ecosystem, socio-economic, and production processes in the landscape.

Where there is overlap of Protected Areas and Originary Indigenous Territories, management will be subject to the rules and procedures of the rural native indigenous peoples and nations, respecting the objective of creating these areas. (Article 385, Constitution of state)

COMPACT (Community Management of Protected Areas Conservation) is an initiative that was designed to complement and add value to existing conservation programmes, by supporting community-based initiatives that increase effectiveness of biodiversity conservation and improve livelihoods of local people. See, for example, whc.unesco.org/document/134265

Engaging Local Communities in Stewardship of World Heritage: a methodology based on the COMPACT experience. SGP implements the Japan-financed COMDEKS initiative in 20 countries around the world; it focuses on community-based landscape planning and management for socio-ecological resilience.  For more information, please see https://comdeksproject.files.wordpress.com/2014/10/communities-in-action-comdeks-web-v2.pdf.

See, for example, http://www.ppd-ecuador.org/ for more information.

Agrupaciones Sociales de Lugar ASL: are Social Local Groups defined in Article 1 paragraph II, the General Rules of the Forestry Law approved by Supreme Decree 24453, as a group of people with legal status, or who acquire it for this purpose, formed by traditional users, peasant communities, indigenous peoples and other users of the site that use forest resources within the jurisdiction of a municipality or Association of Municipalities.