Project Identification Form (PIF)

Project Type:

Type of Trust Fund:

For more information about GEF, visit TheGEF.org

PART I: Project Information

| Project Title: | Capacity development for the integration of global environmental commitments into national policies and development decision making |  |  |
| --- | --- | --- | --- |
| Country(ies): | Bosnia and Herzegovina | GEF Project ID: | 5302 |
| GEF Agency(ies): |  | GEF Agency Project ID: | 00967 |
| Other Executing Partner(s): | Ministry of Foreign Trade and Economic Relations of Bosnia and Herzegovina (MoFTER); Ministry for Spatial Planning, Construction and Ecology of Republika Srpska; Ministry of Environment and Tourism of the Federation of Bosnia and Herzegovina | Resubmission Date: | 27/06/2013 |
| GEF Focal Area (s): |  | Project Duration (Months) | 36 |
| Name of parent program (if applicable): - For SFM/REDD+ - For SGP - For PPP |  | Project Agency Fee ($): | 136610 |

A.  indicative Focal AREA STRATEGY Framework:

| ### Focal Area Objectives | ### Trust Fund | ### Indicative ### Grant Amount ### ($) | ### Indicative Co-financing ### ($) |
| --- | --- | --- | --- |
|  |  | 545000 | 680000 |
|  |  | 445000 | 550000 |
|  |  | 448000 | 285000 |
| Total Project Cost |  | 1438000 | 1515000 |  |

- indicative Project description summary

| ### Project Objective: To enhance capacities of institutions for environmental management in Bosnia and Herzegovina by institutionalizing identified tools and practices for environmental information and knowledge management |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| ### Project Component | ### Grant Type | ### Expected Outcomes | ### Expected Outputs | ### Trust Fund | ### Indicative ### Grant Amount ($) | ### Indicative Cofinancing ### ($) |
| 1 Managing Global Environmental Issues through improved monitoring and indicator development |  | 1.1 An indicator framework developed and an Environmental Management Information System (EMIS) introduced to manage national environmental issues in accordance with MEA guidance 1.2 Air quality monitoring enabled | 1.1.1 Core indicators are identified and guidance is developed for the management of cross-cutting MEA information management and the mainstreaming of environmental and developmental policies 1.1.2 MEA reporting and data flow system, incl. data analysis tools, is operational for institutions concerned with CBD, UNCCD and UNFCCC implementation 1.1.3 An environmental management information system (EMIS) is tested with the Entities' environmental authorities 1.2.1 Three air quality monitoring stations are established 1.2..2 Training conducted on collecting data for emissions, pollutants and air quality 1.2.3 Data is regularly analyzed in accordance with Air Quality Law and fed into environmental management information system |  | 808000 | 715000 |
| 2 Institutional Strengthening |  | 2.1 Institutional capacity of MoFTER and Entity environmental authorities strengthened for MEA reporting and implementation monitoring and for mainstreaming environmental issues into development planning | 2.1.1 Training programme developed and executed for MoFTER, Entity authoriries' staff and other relevant organizations on advanced planning tools, scenario development and knowledge management for environmental issues 2.1.2 Training programme developed and executed to enable the integration of environmental management into planning and monitoring processes 2.1.3 M&E system established, targeted to compliance monitoring of state and Entity development policies, programmes, and plans 2.1.4 A web-based environmental database for improved coordination and output analysis established, building on 1.1.3 above |  | 500000 | 580000 |
| Subtotal |  |  |  |  | 1308000 | 1295000 |
| Project Management Cost (PMC) |  |  |  |  | 130,000 | 220,000 |
| Total Project Cost |  |  |  |  | 1,438,000 | 1,515,000 |

- Indicative Co-financing for the project by source and by name if available, ($)

| Sources of Cofinancing | Name of Cofinancier | Type of Cofinancing | Amount ($) |
| --- | --- | --- | --- |
|  | MoFTER |  | 1,100,000 |
|  | Hydrometeorological Institutes of FBiH and RS |  | 100,000 |
|  | MoFTER |  | 135000 |
|  | UNEP |  | 180000 |
|  | BiH Environment Funds |  |  |
|  | EU |  |  |
| Total Cofinancing |  |  | 1,515,000 |

- indicative trust fund  Resources ($) Requested by Agency, Focal Area and Country1

| GEF Agency | Type of Trust Fund | Focal Area | Country Name/Global | Grant Amount ($) (a) | Agency Fee ($) (b)2 | Total ($) c=a+b |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Bosnia and Herzegovina | 1438000 | 136610 | 1574610 |
|  |  |  |  |  |  | 0 |
|  |  |  |  |  |  | 0 |
|  |  |  |  |  |  | 0 |
|  |  |  |  |  |  | 0 |
| Total Grant Resources |  |  |  | 1438000 | 136610 | 1574610 |

1  In case of a single focal area, single country, single GEF Agency project, and single trust fund project, no need to provide information for   
    this table. PMC amount from Table B should be included proportionately to the focal area amount in this table.

2   Indicate fees related to this project.

- Project preparation grant (ppg)

Please check on the appropriate box for PPG as needed for the project according to the GEF Project Grant:

Amount                         Agency Fee

Requested ($)	      for PPG ($)

- No PPG required.                                           		       ___-- 0--________       _  --0--_______

- (upto) $50k for projects up to & including $1 million	       ___    ________      ___     _____

- (upto)$100k for projects up to & including $3 million      ___45,000________      ___4,275_____

- (upto)$150k for projects up to & including $6 million      ___     ________      ___     _____

- (upto)$200k for projects up to & including $10 million   ___     ________      ___     _____

- (upto)$300k for projects above $10 million     	       ___     ________      ___     _____

PPG  Amount requested by agency(ies), focal area(s) and country(ies) for MFA and/or MTF roject only

| Trust Fund | GEF Agency | Focal Area | Country Name/ Global | (in $) |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | PPG (a) | Agency Fee (b) | Total c = a + b |
|  |  |  | Bosnia and Herzegovina | 45000 | 4275 | 49275 |
|  |  |  |  |  |  | 0 |
|  |  |  |  |  |  | 0 |
| Total PPG Amount |  |  |  | 45000 | 4275 | 49275 |

MFA:  Multi-focal area projects;  MTF:  Multi-Trust Fund projects.

part ii:  project JustiFication

Project Overview
A.1. Project Description. Briefly describe the project, including ; 1) the global environmental problems, root causes and barriers that need to be addressed; 2) the baseline scenario and any associated baseline projects, 3) the proposed alternative scenario, with a brief description of expected outcomes and components of the project, 4) incremental cost reasoning and expected contributions from the baseline , the GEFTF, LDCF/SCCF and co-financing; 5) global environmental benefits (GEFTF, NPIF) and adaptation benefits (LDCF/SCCF); 6) innovativeness, sustainability and potential for scaling up

# ,1) Problem Statement # Its constitution defines Bosnia and Herzegovina (BiH) as a sovereign state with a decentralized political and administrative structure: # a. The State Government of Bosnia and Herzegovina # b. Two Entities, with their own governments: # • The Federation of Bosnia and Herzegovina (FBiH); and # • The Republic of Srpska (RS); # c. The Brčko District, a small self-governing administrative unit. # The complex political organization of the country is the main reason for a considerable fragmentation of mandates and a lack of coordination among the many institutions dealing with the environment in BiH. # a. BiH State level: # • The Ministry of Foreign Trade and Economic Relations of Bosnia and Herzegovina (MoFTER) is tasked with defining policies, basic principles, coordinating activities and harmonizing plans of the Entity authorities and institutions at the international level. # • The Ministry of Foreign Affairs of Bosnia and Herzegovina, and the Directorate for European Integration within the Council of Ministers of Bosnia and Herzegovina also have authority over some environmental issues. # b. Entity level: # In the FBiH, the Ministry of Environment and Tourism is in charge of strategy and policy, air protection, water and soil conservation, and environmental standards. Further, the Ministry of Spatial Planning and the Ministry of Agriculture, Water Management and Forestry have respective environmental competences. # In the RS, the Ministry for Spatial Planning, Construction and Ecology is tasked with environmental protection (land, air and water) and waste management. The Ministry of Agriculture, Forestry and Water Management addresses related strategies, policies, standards and regulations. # The two entities often collect and analyze data with different indicators and time sets, which makes reporting for the country extremely complicated. This is a problem for any MEA reporting and in particular for climate change where the data on emissions and other pollutants cannot be roughly estimated but need to be as precise as possible. # 2) Baseline # The Millennium Development Goals Fund (MDG-F) Programme “Mainstreaming Environmental Governance: Linking Local and National Action in Bosnia and Herzegovina” is a programme jointly implemented by five UN Agencies (UNDP, UNEP, UNESCO, FAO and UNV), in partnership with institutions at State, Entity and municipality levels. The Joint Programme offers an innovative approach to strengthening the capacities for mainstreaming environment issues into policy planning, resource management and service delivery in BiH, reviving the environment sector which is critically stagnant and threatens to become one of the most serious obstacles on the country’s road to European integration. Interventions centre on providing capacity and support for developing Local Environmental Action Plans for 30 municipalities, and raising the awareness and national level support for environmental action. The budget for the programme is $5,500,000 and implementation is over three years (2010-2012, with a 6-months no-cost extension in 2013). In the framework of the MDG-F project, UNEP has led a pioneering process of preparing the first state of environment report for the country, which will be published in early 2013 following endorsement by the competent government authorities. # 3) Alternative scenario # The proposal builds upon the MDG-F programme's Outcome 3: Increased national environmental awareness and action, targeting increased public access to environmental information and strengthened capacity of state to manage local socio-economic development and engage key national partners. The State of Environment reporting process offers a comprehensive set of environmental indicators and a status review of environmental sectors, providing a good baseline for the development of a comprehensive environmental monitoring and information system (EMIS) There is an urgent need to continue this systematic collection and analysis of environmental information for national coordination purposes as well as for compliance with international MEAs. Otherwise, environmental data will remain piecemeal and cannot build the backbone for harmonized environmental management across BiH, nor for compliance with MEAs. # Component 1 of the project focuses on developing national capacities for improved environmental information and knowledge management by developing nationally relevant indicators, in line with global environmental management as part of the Bosnia and Herzegovina environmental governance regime. While focusing on the Rio Conventions to maintain a scale that is manageable through a medium-sized project, the aim will be to establish an Environmental Management Information System (EMIS) to strengthen environmental management capacities that can equally be applied to other conventions and environmental issues of relevance to Bosnia and Herzegovina. EMIS indicators will be based on internationally agreed standards and be in line with the GEF indicators for cross-cutting capacity development. # A particular focus will be on air quality and pollution monitoring. As illustrated in the recently completed State of the Environment report, data is missing for several indicators and so far available information is based on estimations by international organizations or contractors, which is not sustainable. Even where data is available they cover different timeframes among the different entities and therefore it is particularly challenging for the country to report in a consistent manner at the national/international level. # In line with the recently passes BiH Air Quality Law, the project aims at purchasing 3 monitoring stations, one for each of the entities (Republika Srpska, Federation of BiH and Brcko district). The cost per station is approx. USD 100,000 and maintenance will be ensured by the country as part of its co-financing (approx. USD 100,000 over 3 years for the 3 stations). Data collected through the stations will serve two purposes: (i) reporting to MEAs which at the moment is based on estimations; and (ii) guidance for decision makers on implementation of the MEAs at the country level. This component clearly has an incremental costs angle since GEF contributes with the initial capital while the country ensures the maintenance. It further strengthens sustainability as the environmental information system can be constantly and consistently fed with data relevant to environmental indicators and multiple MEA reporting requirements. # Air quality affects ecosystems, biodiversity, water and land, or gives an indication of ecosystem health (e.g. land degradation). Known or likely impacts of air pollution on the biodiversity and function of natural ecosystems require that the effects of air pollution be considered in any long-term conservation strategy. The stations will monitor: # 1. Basic air monitoring parameters, including a) temperature; b) humidity; c) sun radiation (including UV index); d) atmospheric pressure; and e) wind direction and speed # 2. Air quality parameters: a) SO2 - sulphur dioxide; b) NOx (NOX + NO2 + NO); c) O3 Ozone; d) CO carbonmonoxide; e) PM10 (dust, particulate matter, only 10 microns) # Climate Change: Climate change and air pollution are closely coupled. Conventional air pollutants such as ozone (2c), sulfur (2a) and particle pollution (2e) can also contribute to climate change. The warmer atmospheric temperatures (1a) observed over the past decades are expected to lead to a more vigorous hydrological cycle, including more extreme rainfall events. # Land degradation: Soil particles picked up during wind erosion are a major source of air pollution, in the form of airborne particulates—"dust" 2.e). # Water: Air pollution causes or contributes to acidification of lakes, eutrophication of estuaries and coastal waters. # Ecosystems: Nitrogen (2b) and sulfur (2a) in air pollution are carried by rain, snow, and fog into ecosystems where they threaten sensitive aquatic and terrestrial resources, causing acidification of soils, lakes, and streams. # Biodiversity: Ozone (3c) is known to cause reductions in photosynthesis in many terrestrial plant species. Changes in species composition caused by terrestrial or aquatic acidification or eutrophication can propagate throughout the food webs to affect many organisms beyond those that are directly sensitive to the pollution. Likewise, sub-lethal doses of toxic pollutants may reduce the reproductive success of the affected organisms or make them more susceptible to potentially lethal pathogens. State and Entity environmental institutions’ staff will be trained on data gathering and analysis, and information on emissions and pollutants be integrated into the EMIS. # Component 2 of the project is a complementary set of capacity building activities, developing individual and institutional capacities to better adapt and apply global environmental management indicators as a monitoring tool to assess the intervention performance and institutional sustainability. # 4) Environmental benefits # Beyond the immediate global environmental benefits that will be achieved through improved environmental management and monitoring at national scale, the project is envisaged to produce lessons learned on developing and applying environmental management indicators that are replicable in other national circumstances. These measures will thus increase the project’s cost-effectiveness and sustainability. # The project will provide the foundation for constant socio-economic benefits through the introduction of systematic, measurable and sustainable approaches to assessing global environmental achievements and linking them to national policies and initiatives. Implementing tools and practices for measuring, reporting, and verifying the cost-effectiveness of official development assistance (ODA) with regard to multilateral environmental agreements, in particular the Rio Conventions, will further contribute to strengthening cooperation among governmental agencies as well as with CSOs and academia. Further expected direct benefits will include: # • Increased scientific and technical knowledge on state and trends of the environment to inform public development policies and strategies; # • Increased awareness among the general public to enable sustainable behavioural changes for resource use and to better link local behaviour to global environmental concerns; # • Increased involvement of non-governmental organizations, the academia and the general public in information gathering and management as well as decision making processes that reflect on environmental management and sustainable development; # 5) Cost reasoning and expected contributions # The MDG-F baseline project is expected to contribute about USD 300,000 in-kind, through the established indicator framework, environmental assessment and data/information gathering processes initiated at local, entity and state levels, and through the data sets, and coordination procedures established through the SOE reporting process. The BiH government’s co-financing (USD 900,000) will mostly consist of in-kind contributions through the provision of staff time, premises, the use of existing ICT infrastructure and technical equipment, national data etc. The cash contribution (USD 135,000) will cover the maintenance of the air quality monitoring stations. # GEF funds will be used to establish the Environmental Management and Information System; further development, fine-tuning and application of environmental indicator frameworks; and the development and testing of an MEA reporting and data flow system. Three air quality monitoring stations will be purchased to enable BiH to gather, analyze and report on pollutants and emissions, in line with national, EU and UNFCCC requirements. Further, training programs relevant to above areas will be developed and implemented for improved knowledge management and the integration of environmental information in planning and policy development. # UNEP will bring in-kind assistance worth USD 180,000 through coordination, technical advice from DEWA, other divisions and its regional and national offices, but no additional grant co-financing can be mobilized at this time. At this early stage of the project development, UNEP is deliberately establishing its contribution at a conservative estimate, i.e. the minimum support it will be able to provide to support the project. UNEP will seek, however, to increase its contribution, involving other UNEP Divisions, e.g. ROE and DEPI, and to use its convening and networking power to identify further partners and resources during the PPG phase of the project. # 6) Innovativeness and Sustainability # The project's innovativeness is founded in the establishment of a centralized environmental monitoring and information system that will, among other uses, serve as an unique reference point and "one-stop-shop" for environmental reporting - at the national level as well as for international conventions. Developing an effective system for capturing environmental data will thus contribute to the identified need for better integrated national environmental management, which in itself is innovative and clearly needed in the fragmented policy context of Bosnia and Herzegovina. It also bears good potential for scaling up and replication as it responds to the often voiced need for harmonized MEA reporting and strenghtening capacities for mainstreaming environmental concerns into policy planning, resource management and service delivery. # The development of EMIS indicators will be based on internationally recognized standards and be in line with the GEF CCCD indicators. Experiences and lessons learned in the BiH case can thus be applied and scaled-up to other similar national circumstances of difficult institutional integration when lacking clear mandate and sufficient resources. Capacity development efforts and the continuation of the EMIS will have to be maintained and continued beyond the project life-time by national benefitiaries, and this will require extended commitment and resources. As similar measures in environmental monitoring and reporting are required by the process of European integration, the incentives for the government of Bosnia and Herzegovina to perpetuate the project’s outcomes are regarded as very high.

# A.2. Stakeholders. Identify key stakeholders (including civil society organizations, indigenous people, gender groups, and others as relevant) and describe how they will be engaged in project preparation:

# The proposal takes into account the data and information roles, responsibilities, and needs of various other key ministries, institutions, and agencies. Other project partners include Entity environmental funds, statistical agencies of both Entities and the State, Hydro-meteorological Institutes of both Entities, Entity ministries of agriculture, water management, forestry, health, spatial planning and energy etc.

# The above-mentioned institutions will collaborate and coordinate the structural reform of their databases and MIS through this project, in particular the identification and key sustainable development and global environmental indicators, the development of a networked indicator-cased EMIS. Partner ministries staff will be trained on best practice methodologies for data gathering and analysis, and the technical maintenance of the EMIS.

# Other important stakeholders are

# • Regional institutions that play an important role in data gathering, monitoring and the sharing of information through field extension offices.

# • Civil society, including academic institutions, as users of EMIS data and information, incl. farmers and agricultural cooperatives, faculties of agriculture, biology and other natural sciences of three main universities in Bosnia and Herzegovina, environmental NGOs etc;

# • The private sector, having a role and responsibility to collect and report data on resource use and pollution.

# Adaptive collaborative management will be used as an approach to engage stakeholders as collaborators in the design and implementation of project activities that take into account consequences arising from policy interventions, as well as gender issues to ensure equal participation by women and men in all activities and project structures. Wherever possible, subject to project preparation, gender-disaggregated indicators will be included in the project’s monitoring and evaluation plans.

# A.3 Risk. Indicate risks, including climate change, potential social and environmental risks that might prevent the project objectives from being achieved, and, if possible, propose measures that address these risks to be further developed during the project design (table format acceptable):

# Governance challenges Medium Risk # The complex political structures in Bosnia and Herzegovina’s Entities and the division of roles and responsibilities for the environment into various ministries and agencies can cause coordination challenges to the project. This risk will be mitigated through close collaboration with relevant stakeholders from the outset and by determining collaborative strategies and focal points in each of the key institutions;and equally through the improvement of institutional frameworks for information management, and the coordination and clarification of mandates. # Lack of interest of relevant stakeholders Medium Risk # Awareness raising will provide all stakeholder groups with the necessary knowledge on issues and opportunities that lie within their active engagement in environmental management at all levels. # Lack of accord on needs, format and methodology to collect, collate, and analyze data # Medium Risk # Consensus-based development of data portal, information system and indicators.

# A.4. Coordination. Outline the coordination with other relevant GEF financed and other initiatives:

# The project will be closely coordinated with the State of the Environment reporting process, which is an activity in the scope of the MDG-F Joint Programme Environment and Climate Change. # This project's development of global environmental indicators will be reconciled and integrated, as appropriate, with sustainable development indicators that are to be part of main state and Entity strategies and plans, ensuring that their implementation does not work against commitments of Bosnia and Herzegovina to meet and sustain Rio Convention obligations. # Various GEF-funded national reporting projects will be involved to avoid duplication efforts, such as the Second National Communication to the UNFCCC, Revision of the NBSAPs and Development of Fifth National Report to the CBD and Alignement of National Action Programme to the UNCCD 10 Years Strategy and Preparation of the the Fifth Reporting and Review process. # Cooperation with the EU-funded project “EnvIS BiH – Strengthening of BiH Environmental Institutions and Preparation for Pre-accession Funds” will be sought, especially in relation to its Component 3: Implementation of International Environmental Treaties and Component 4: Environmental Monitoring System Support and Public Communication. # Further opportunities for collaboration and co-finaning arise with the EU Instrument for Pre-Accession Assistance (IPA), having a focus on strengthening BiH's environmental institutions. These will be further explored and substantiated during the PPG phase. # Bosnia-Herzegovina takes part in most of EEA’s European Environment Information and Observation Network (Eionet) activities, but there are gaps in its delivery towards the Priority Data Flows, as can be seen in the latest annual progress report http://www.eea.europa.eu/publications/eionet-priority-data-flows-2012. EEA has been contacted about the present PIF, and further details of coordination between the two initiatives will be further developed at the stage of full project development.

Description of the consistency of the project with:

# B.1 National strategies and plans or reports and assessments under relevant conventions, if applicable, i.e. NAPAS, NAPs, NBSAPs, national communications, TNAs, NCSAs, NIPs, PRSPs, NPFE, Biennial Update Reports, etc.: # The National Capacity-Self Assessment (NCSA) project for Bosnia and Herzegovina identified a number of common weaknesses in the national implementation of the Rio Conventions. As a result, the NCSA Action Plan prioritized a suite of cross-cutting capacity development actions. The top priority actions identified was to strengthen coordination by the MoFTER in implementing conventions and/or to nominate a National Coordination Body for all conventions, to harmonize the country's environmental legislative framework, strategies and policies, so that they become fully compliant with Rio Convention commitments, to strengthen inter-sectoral coordination – horizontal and vertical, and to define the financing for the implementation of Entity and cantonal environmental policies, laws and standards for sustainable management of natural resources in general. This project will be an important contribution to these objectives by developing and piloting the application of global environmental management indicators that will help BiH assess the extent to which policy interventions are achieving global environmental benefits. # For more detailed information on the status of the Rio Conventions in BiH, please refer to the NCSA report pages 70-77, delineating the main problems in MEA implementation in BiH. The NCSA focused on the CBD and CCD as well as POPs and the Vienna Convention for the Protection of the Ozone Layer (referred to as POL). # The UNFCCC was not included in the NCSA process. BiH has submitted its Initial National Communication to the UNFCCC and development of the Second National Communication to the UNFCCC is ongoing. The INC includes an inventory of greenhouse gases (GHG) emissions in the Kyoto base line year (1990) and BiH as a Non-Annex I country has no obligation under the Kyoto Protocol to reduce its current emissions, as they are estimate to be 35% lower than in the baseline year. BiH has established an operational Designated National Authority (DNA) for the CDM, which was the last precondition for country to participate in the CDM.

# B.2. GEF focal area and/or fund(s) strategies, eligibility criteria and priorities:

# This project is specifically structured to meet the GEF-5 Capacity Development Results Framework, particularly CD Objective 2 – providing and increasing stakeholders’ skills to gather, diagnose and apply information for environmental management; and CD Objective 4 – enhancing institutional capacities to manage environmental issues and implement global conventions. The project is also consistent with the programmatic objectives of the three GEF thematic focal areas of biodiversity, climate change and land degradation, the achievement and sustainability of which is dependent on the critical development of capacities (individual, organizational and societal). Through the successful implementation of this project, a more integrated and cost-effective approach to adapting and applying global environmental management indicators across the focal areas will be demonstrated.

Therefore, and beyond contributing to the achievement of the GEF’s CCCD objectives 2 and 4, the project will support efforts of the Government and relevant stakeholders in Bosnia and Herzegovina in providing substantive input to the GEF’s focal area objectives under the Rio Conventions, particularly BD 5 (integrating BD objectives into national planning), CCM 6 (capacity development under the UNFCCC) and LD 3 and 4 (integrated natural resource management and adaptive management and learning).

B.3 The GEF Agency’s comparative advantage for implementing this project:

UNEP has a history of working with national and Entity authorities in BiH both on MEA reporting and assessment and other activities. UNEP has successfully worked with the Government of BiH on carrying out the National Capacity Self-Assessment process which proved to be a long-needed and highly recognized intervention in the country toward its international environmental obligations.

Local presence of UNEP in Bosnia and Herzegovina through a project office in Sarajevo, which is closely related to UNEP Vienna, is a valuable addition to the efforts of UNEP’s Regional Office for Europe to support the region of South-eastern Europe and BiH itself on the road to the European integration and mainstreaming of environmental issues into a broader political agenda.

This project further links with UNEP's Programme of Work for 2012-2013, output 443, "Institutional and technical capacities of Governmental and partner institutions in environmental monitoring, assessment and early warning are strengthened to support national decision-making." This work is led by UNEP's Division of Early Warning Assessment (DEWA), which coordinates global scientific assessments such as the Global Environment Outlook, and supports national and regional capacity building in areas such as environmental data and information, environmental assessment methodologies.

Execution arrangements:

Based on the request by the Government of Bosnia and Herzegovina for execution support, the project will be co-executed by the Government and the UNEP Office in Bosnia and Herzegovina, which is closely related to UNEP Vienna, and with technical support to execution by the UNEP Regional Office for Europe assessment team. The project preparation phase will also be used to bring on board additional expertise and support through organizations, possibly including the European Environment Agency (EEA), the UN Statistics Division (UNSD), and the World Conservation Monitoring Centre (WCMC).

part iii:  approval/endorsement by gef operational focal point(s) and GEF agency(ies)

A.   Record of Endorsement of GEF Operational Focal Point (S) on Behalf of the Government(S): (Please attach the Operational Focal Point endorsement letter(s) with this template. For SGP, use this OFP endorsement letter).

| Name | Position | Ministry | Date (MM/dd/yyyy) |
| --- | --- | --- | --- |
| Senad Oprašić | GEF OFP | MoFTER | 01/31/2013 |

B.  GEF Agency(ies) Certification

| This request has been prepared in accordance with GEF/LDCF/SCCF/NPIF policies and procedures and meets the GEF/LDCF/SCCF/NPIF criteria for project identification and preparation. |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Agency Coordinator, Agency name | Signature | Date (MM/dd/yyyy) | Project Contact Person | Telephone | Email Address |
| Maryam Niamir-Fuller Director, GEF Coordination Office, UNEP |  | 06/27/2013 | Ludgarde Coppens, Programme Officer Capacity Development Branch Division of Early Warning and Assessment | +254 20) 762 4158 | Ludgarde.coppens@unep.org |

Project ID number will be assigned by GEFSEC.

Refer to the reference attached on the Focal Area Results Framework and LDCF/SCCF Framework when completing Table A.

TA includes capacity building, and research and development.

To be calculated as percent of subtotal.

On an exceptional basis, PPG amount may differ upon detailed discussion and justification with the GEFSEC.

PPG fee percentage follows the percentage of the GEF Project Grant amount requested.

Part II should not be longer than 5 pages.