request for

Project Type:

Type of Trust Fund:

For more information about GEF, visit TheGEF.org

part i: project information

| Project Title: Generating, Accessing and Using Information and Knowledge Related to the Three Rio Conventions. |  |  |  |
| --- | --- | --- | --- |
| Country(ies): | Cambodia | GEF Project ID: | 5295 |
| GEF Agency(ies): |  | GEF Agency Project ID: | 5222 |
| Other Executing Partner(s): | Ministry of Environment | Submission Date: | 2014-09-05 |
| GEF Focal Area (s): |  | Project Duration(Months) | 36 |
| Name of Parent Program (if applicable): - For SFM/REDD+ - For SGP - For PPP |  | Project Agency Fee ($): | 94,050 |

- Focal Area Strategy framework

| ### Focal Area Objectives | ### Expected FA Outcomes | ### Expected FA Outputs | Trust Fund | Grant Amount ($) | ### Cofinancing ### ($) |
| --- | --- | --- | --- | --- | --- |
|  | 2.1 Institutions and stakeholders have skills and knowledge to research, acquire and apply information collective actions 2.2 Increased capacity of stakeholders to diagnose, understand and transform complex dynamic nature of global environmental problems and develop local solutions 2.3 Public awareness raised and information management improved | * Institutions and stakeholders trained how to use different tools available to manage information * Stakeholders are better informed via workshops and trainings about global challenges and local actions required * Ability of stakeholders to diagnose, understand and transform information and knowledge into local actions increased * Knowledge platform established to share lessons learned among CBOs and CSOs * Public awareness raised through workshops and other activities |  | 470,650 | 600,000 |
|  | 4.1 Enhanced institutional capacities to manage environmental issues and implement global conventions 4.2 Good environment management standards defined and adopted | * Institutional capacities for management of environment strengthened * Standards developed and adopted * Management capacities for implementation of convention guidelines and Reporting enhanced * Sustainable financing mechanisms developed |  | 429,350 | 645,000 |
|  | Project Management | N/A |  | 90,000 | 55,000 |
| Total project costs |  |  |  | 990,000 | 1,300,000 |

- Project Framework

| ### Project Objective: To improve access to environmental information related to the Rio Conventions through the harmonization of existing environmental management information systems and improving coordination of the implementation of these conventions in Cambodia. |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| ### Project Component | ### Grant Type | ### Expected Outcomes | ### Expected Outputs | ### Trust Fund | ### Grant Amount ($) | ### Confirmed Cofinancing ### ($) |
| Improved access and generation of information |  | 1. Improved access and generation of information related to the three Rio Conventions | 1.1 A harmonized information management system covering the three Rio Conventions 1.2 A common clearinghouse mechanism for the three Rio Conventions 1.3 Existing stakeholder platforms strengthened in order to increase stakeholder engagement in Convention related dialogues 1.4 Strengthened coordination between key sectors to address biodiversity, climate change and land degradation issues at systemic and institutional levels |  | 470,650 | 600,000 |
| Improved use of information and knowledge |  | 2. Improved use of information and knowledge related to the Rio Conventions | 2.1 Innovative tools piloted for decision-making using the economic valuation of the use of natural resources 2.2 Strengthened capacity of existing national implementing institutions on negotiation skills and national preparatory process for COPs and other related meetings for the Rio conventions 2.3 A unified reporting process on the implementation status of the three Rio Conventions |  | 429,350 | 645,000 |
| Subtotal |  |  |  |  | 900,000 | 1,245,000 |
| Project management Cost (PMC) |  |  |  |  | 90,000 | 55,000 |
| Total project costs |  |  |  |  | 990,000 | 1,300,000 |

- sources of confirmed Cofinancing for the project by source and by name ($)

Please include letters confirming cofinancing for the projeSct with this form

| Sources of Co-financing | Name of Co-financier (source) | Type of Cofinancing | Cofinancing Amount ($) |
| --- | --- | --- | --- |
|  | MOE |  | 150,000 |
|  | UNDP |  | 150,000 |
|  | UNDP |  | 1,000,000 |
| Total Co-financing |  |  | 1,300,000 |

- trust fund Resources Requested by agency, Focal Area  and country1

| GEF Agency | Type of Trust Fund | Focal Area | Country Name/ Global | (in $) |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | Grant Amount (a) | Agency Fee (b)2 | Total c=a+b |
|  |  |  | Cambodia | 990,000 | 94,050 | 1,084,050 |
|  |  |  |  |  |  | 0 |
|  |  |  |  |  |  | 0 |
|  |  |  |  |  |  | 0 |
|  |  |  |  |  |  | 0 |
|  |  |  |  |  |  | 0 |
|  |  |  |  |  |  | 0 |
|  |  |  |  |  |  | 0 |
|  |  |  |  |  |  | 0 |
|  |  |  |  |  |  | 0 |
| Total Grant Resources |  |  |  | 990,000 | 94,050 | 1,084,050 |

1  In case of a single focal area, single country, single GEF Agency project, and single trust fund project, no need to provide information for this
    table.  PMC amount from Table B should be included proportionately to the focal area amount in this table.

2   Indicate fees related to this project.

- Consultants working for technical assistance components:

| ### Component | ### Grant Amount ($) | ### Cofinancing ($) | ### Project Total ($) |
| --- | --- | --- | --- |
| ### International Consultants | 100,000 | 91,000 | 191,000 |
| ### National/Local Consultants | 240,000 |  | 240,000 |

- Does the project include a “non-grant” instrument?

(If non-grant instruments are used, provide in Annex D an indicative calendar of expected reflows to your Agency 
       and to the GEF/LDCF/SCCF/NPIF Trust Fund).

part ii:  project justification

A. describe any changes in alignment with the project design of the original pif

A.1 National strategies and plans or reports and assessments under relevant conventions, if applicable, i.e. NAPAS, NAPs, NBSAPs, national communications, TNAs, NCSA, NIPs, PRSPs, NPFE, Biennial Update Reports, etc. 1. Development and environmental management in Cambodia is led by a set of key policies, supported by Laws. It includes the “Rectangular Strategy-Phase III” that is the Socio-economic Policy Agenda of the political platform of the government of Cambodia of the Fifth Legislature of the National Assembly (2013-2018). This strategy (Phase III) recognizes that the environment and climate change has become another challenge for the sustainability of Cambodia’s economic growth and social development due to pressures from population growth, urbanization, expansion and intensification of agriculture as well as development of transport, energy and other sectors. It stated “many environmental issues are cross-sectoral in nature, which requires coordination across government agencies at both national and sub-national levels including cooperation with all the stakeholders”. This strategy is the government comprehensive policy framework guiding national development and in particular guiding the formulation of the NSDP. 2. The “National Sustainable Development Plan (NSDP)” formulated for the period 2009-2013 placed a high priority on tackling key sectoral challenges in the areas such as garments and other manufactured goods; tourism infrastructure; diversification of the agriculture sector; infrastructure development; and, improving people livelihoods. The recently drafted NSDP for the period 2014-2018 focuses on intensifying efforts to reduce the impact of climate change by strengthening the adaptation capacity and resiliency to climate change, particularly by implementing the "Cambodia Climate Change Strategic Plan 2014-2023", “National Policy on Green Growth” and the “National Strategic Plan on Green Growth 2013-2030”. 3. Finally, The “National Biodiversity Strategic and Action Plan (NBSAP)” was approved in July 2002 and consists of 98 priority actions covering 17 biodiversity related themes. Cambodia completed its NAPA in 2006, its initial national communication in 2002, its second national communication in 2010 and the approval of its NAP to combat land degradation is currently pending. 4. As a GEF eligible country, Cambodia obtained an UNDP-GEF grant to conduct its National Capacity Self-Assessment (NCSA), which started in 2005 and was concluded in 2006. The goal of the project was to develop and strengthen national capacities for sustainable management and use of natural resources and of the environment, for the benefit of the Cambodian poor. Its objective was to identify country level priorities and needs for capacity development, to address global environmental management requirements, particularly the thematic concerns of the three UN conventions. The project looked into existing capacities and capacity needs in Cambodia, to address domestic environmental issues and concerns that are also concerns of the three Rio Conventions: UNFCCC, UNCDB, and UNCCD, which Cambodia is a party to. 5. This extensive assessment identified a large number of common issues and capacity needs. As per the NCSA action plan, “existing thematic capacities in Cambodia are severely lacking, over-all. Capacities to attend to the thematic concerns and meet the obligations to all three Conventions are almost all weak. They hardly lend to being prioritized in that all are needed the soonest time they can be acquired”. It concluded that “the cross-cutting capacity needs, which address broad national conditions of the economy and socio-political system of Cambodia that constrain the thematic capacities, are essentially at the highest levels of government and Cambodian society”. This assessment also identified a list of priority actions including the need for better coordination for the implementation of the Rio Conventions, more public awareness and the need to mainstream the environment into policies, plans and programmes. This proposed project will address some of these priority actions.

A.2. GEF focal area and/or fund(s) strategies, eligibility criteria and priorities.

6.  The PIF provides an accurate description of the Project’s alignment to GEF focal areas and strategies.

A.3 The GEF Agency’s comparative advantage:

No change

A.4. The baseline project and the problem that it seeks to address:

7.  The PIF provides a description of the baseline project and the problem to be addressed. This description is still valid and the project document expanded on it.

A. 5. Incremental /Additional cost reasoning:  describe the incremental (GEF Trust Fund/NPIF) or additional (LDCF/SCCF) activities  requested for GEF/LDCF/SCCF/NPIF  financing and the associated global environmental benefits  (GEF Trust Fund) or associated adaptation benefits (LDCF/SCCF) to be delivered by the project:

8.  This project takes an incremental approach from a GEF construct towards strengthening Cambodia’s environmental information management and knowledge to meet Rio Convention objectives.  In the absence of this project, the necessary capacity building to address the environment data needs of GDANCP-MOE will remain an outstanding need at the national level. It would prevent Cambodia to achieve global environmental benefits through better environmental information and knowledge. Government staff would remain insufficiently equipped and knowledgeable about how to harmonize environmental management information systems and how to use it for better practices and decision-making. More generally, they would also remain insufficiently knowledgeable to fully understand the implications of global environmental directives under the conferences of the parties on national environmental and development policies, and how these directives can be strategically implemented and supported through existing national information systems. Other current funded activities funded by the GEF and other donors are more thematically focused on the implementation of a particular convention such as the national communication for UNFCCC or the support to prepare the national biodiversity strategy and action plan for the UNCBD or the strengthening of protected areas in Cambodia. Most of these projects are not fully addressing cross-sectoral issues (also called horizontal issues) such as environmental governance, stakeholder engagement and monitoring the implementation of Rio Conventions.

9.  Under the GEF Alternative, the GEF resources will allow Cambodia to address this long outstanding environmental information need within GDANCP-MOE. This GEF support is crucial to assist the government of Cambodia in this important area at the country level.  Barriers identified through the NCSA process will be thoroughly re-assessed and effective and efficient solutions to address those related to the availability of environmental information will be detailed and implemented with the support of the project. Overall, the expected outcomes of this project rely in its innovative and transformative approach to mainstream the Rio Conventions obligations within the existing national environmental governance framework. This project will test the assumption that by harmonizing the environmental management information systems, better environmental knowledge will be available to decision-makers in Cambodia and by extension will provide a better enabling environment, which in turn will deliver greater global environmental achievements.

A.6  Risks, including climate change, potential social and environmental risks that might prevent the project objectives from being achieved, and measures that address these risks:

10.  An initial analysis of Risks was provided in the PIF in section B.4. This has been developed in the Project Document (Section C3c). The risks and assumptions are summarized in the following table.

| Risks | Level | Assumptions |
| --- | --- | --- |
| - Political will to provide GDANCP with the necessary resources to sustain project achievements. - New information is not used and stays stored in computers at MOE and MAFF | Low | - MOE will support GDANCP and provide it with necessary resources - Better environmental information is readily available and actively utilized and used |
| - Communications and national reports are not submitted on time | Medium | - Communications and national reports are submitted on time and include information from the harmonized systems. |
| - Project activities and resources do not translate in increasing the capacity of GDANCP and MAFF to provide better environmental information. | Low | - The project is effective in developing the capacity in the area of environmental information management. |
| - Lack of relevant expertise in local market may result in delay of required outputs and distortion of targeted deadlines. | Low | - Implementation of project activities and recruitment of relevant national expertise is monitored and actions will be identified if the lack of expertise is affecting the timely implementation of the project. |
| - Government unwilling to give open-access to environmental information. | Low | - MOE will support GDANCP and provide it with necessary resources to develop this mechanism and give public open-access. |
| - No interest from Stakeholders to increase crosscutting dialogues on the implementation of the Rio Conventions. | Low | - All Stakeholders involved in implementing the Rio Conventions in Cambodia are demanding for greater exchange of environmental information and to better engage in crosscutting dialogues. |
| - Political - delays due to ministerial reforms. - Operational - Irregular frequency of meetings for relevant bodies, unclear approval mechanism for an inter-sectorial coordination body, unwillingness to participate in the inter-sectorial coordination body. | Low | - Supporting mechanism is in-place. |
| - No interest from decision-makers to use economic valuation as a tool to support decision-making. | Medium | - The benefit of using better economic valuation will encourage decision-makers to use it. |
| - The government does not fulfil its international obligations; including those from the 3 Rio Conventions. | Low | - The government continues to fulfill its international commitments. |

A.7. Coordination with other relevant GEF financed initiatives

11.  There are a number of key programmes and initiatives with which this project is to be coordinated.  Each of these programmes and initiatives has important data and information requirements. Likewise, each is generating the key data and information needs to facilitate and catalyze improved decision-making to meet global environmental objectives. They are also important components of a holistic approach to improve the management of the environment in Cambodia. This proposed project will build upon existing initiatives and their achievements and coordinate with related key programmes, plans, and projects. The main ones are presented below:

•  Cambodia Climate Change Alliance – Phase 2 (MOE/UNDP-EU-SIDA, 2011-2015, USD 12.9);

•  Forest Carbon Partnership Facility REDD+ Readiness Project (MAFF/UNDP-Forest Carbon Partnership Facility, 2014-2017, UDS 6.7M);

•  Promoting Climate-Resilient Water Management and Agricultural Practices in Rural Cambodia (NAPAFU Phase 2) (MAFF/UNDP-CIDA, 2013-2015, USD 2.4M);

•  Strengthening Sustainable Forest Management and Bio-Energy Markets to Promote Environmental Sustainability and to Reduce Greenhouse Gas Emissions in Cambodia (MAFF/UNDP-GEF-DANIDA-GERES, 2011-2015, USD 10M);

•  Cambodia UN REDD National Programme (UNDP-FAO-UN-REDD, 2011-2014, USD 4.2M);

•  Cambodia Community Based Adaptation Programme (CCBAP) (UNDP-SIDA, 2011-2015, USD 4.3M);

•  FFI initiative on sustainability finance of catchment areas in Cambodia, including a feasibility on Payment for Ecosystem Services (PES);

•  IUCN projects in Cambodia including: (i) the Regional Building Coastal Resilience to Climate Change Project (EU funded USD 4M, 2011-2014); (ii) Mekong Water Dialogues (regional project funded by Finland Euros 4M, 2010-2014); (iii) Strengthening capacity of fishing Communities in the Tonsle Sap to manage their natural resources sustainably (funded by EU); and (iv) Bridge 3S (Building River Dialogue and Governance) (regional project over three rivers: Sekong, Sre Pok, and Sesan);

•  CI initiatives in climate change – both adaptation (forestry management) and mitigation (REDD), and land degradation;

•  ECHO initiatives including the 2009 capacity development needs assessment of MOE and capacity development of civil society (22 NGOs);

•  WWF initiatives including policy level work with government of Cambodia in biodiversity and in the context of the Green Growth strategy currently being implemented; and

•  ADB funded projects including (i) Mainstreaming Climate Resilience into Development Planning (2013-2014), and (ii) Greater Mekong Sub-region Biodiversity Conservation Corridors Project (regional, 2011-2019).

B. additional information not addressed at Pif stage:

B.1 Describe how the stakeholders will be engaged in project implementation. 12. This project was developed on the basis of consultations with stakeholder representatives, most of whom will benefit directly from this project. They were consulted to review the institutional set up as well as the policy and legislation frameworks related to this project and to consolidate this information in the current project document. An inception workshop to kick-start the PPG phase was organized on January 24, 2014. This workshop invited a broad range of stakeholders with the participation of 120 people from relevant institutions and organizations in order to identify potential cooperation and partnerships for the development of this project. Finally, a validation workshop will take place on August 29, 2014 to validate the proejct document. 13. As a result of the project development phase (PPG), key project stakeholders were identified and consulted. Taking an adaptive and collaborative management approach to execution, the project will ensure that key stakeholders stay engaged throughout project execution as partners for development. This includes their participation in the Project Board to review the progress of the project as well as participating in monitoring activities. A key feature of this project is its learn-by-doing approach, which is intended to actively engage stakeholders. This approach should result in key stakeholders that will be more likely to validate the analysis and legitimize recommendations. It is also intended to catalyze the institutionalization of knowledge and experiences, which is critical for ensuring sustainability. 14. Given the project strategy, the key project stakeholders are government ministries and their subsidiary agencies and departments that are mandated with the management of natural resources. These stakeholder representatives will participate in activities to better monitor the environment and provide more accurate and timely environmental information; including fulfilling Cambodia’s reporting obligations under the MEAs that it is a Party to. In addition to these governmental stakeholders, there are also non-governmental stakeholders, including civil society organizations. These non-state organizations will also be invited in project activities to share their comparative expertise, but also to undertake selected project activities. Their participation will be determined during project implementation when defining annual work plans. The project document provides additional information on stakeholders who will be engaged in project implementation, including a list of stakeholders expected to participate in the implementation of this project and their anticipated roles (see section C.4).

B.2 Describe the socioeconomic benefits to be delivered by the Project at the national and local levels, including consideration of gender dimensions, and how these will support the achievement of global environment benefits (GEF Trust Fund/NPIF) or adaptation benefits (LDCF/SCCF):

15.  Full details on the sustainable development context in Cambodia are provided in the Project Document, section B2b. Cambodia is located in Southeast Asia, bordering Vietnam, Laos and Thailand, and has a total land area of 181,035 km2. The country's population grew from around 9 million in the 1960s to around 14,197,000 in 2006. The country has a relatively low population density of about 82 people per km2 (2011). With the current annual population growth rate of around 2.5%, the population could reach 19 million people in 2020 (National Institute of Statistics 2007). Approximately 80 percent of the country's inhabitants live in rural areas with limited access to electricity and seasonal food shortages. Cambodia's history of conflicts and isolation through the 1970s to 1990s resulted in destruction of almost all areas of national life, including human resources, which are most critical to underpinning the country's socioeconomic development efforts. As a consequence Cambodia is designated as a least developed country (LDC). The restoration of peace and policy stability over the past decade has brought steady economic growth in Cambodia, averaging between 8 and 10 percent since 1998, leading to substantial reductions in poverty.

16.	  However, Cambodia still faces significant poverty and governance challenges. As a response from the government, the National Sustainable Development Plan (NSDP) formulated for the period 2009-2013 placed a high priority on tackling key sectoral challenges, which include:

•	  Diversify the markets for our garments and other manufactured goods market to East Asia, the Middle East and Africa etc.

•	  Further improve tourism infrastructure and the development of more tourism destinations and attractive tour packages.

•	  Prioritize the use of resources and expertise of the government, and donors to broaden and diversify our agricultural sector, in order to attract more quality investments in agri-business and improve agricultural trade linkages, land reform, agricultural diversification and agro-processing.

•  	Further invest in infrastructure development, particularly energy generation to reduce energy costs to the private sector and to the community.

•	  Continue to promote and support wealth creation and improving the people’s livelihood according to the correct principles and procedures as stipulated in the Cambodia’s Constitution.

17.  Withing this context, the socioeconomic benefits of the project will be achieved indirectly toward the provision of better environmental decisions, strategies, plans and programmes; which in turn are expected to improve the management of the environment in Cambodia.  Preserving and conserving the environment in Cambodia is critical for the development of the country and particularly its socioeconomic development. Nationally, the main priorities to better manage the environment was the need for better environmental information and for mainstreaming global environment obligations into national institutional, legislative and policy frameworks (see section B.2.e). This project will address these issues.

18.  Every effort will also be made to incorporate gender issues in the implementation of this project. Roles of men and women to participate in activities of the project will be equally assigned without any discrimination. The project will take steps to ensure that women account for at least 40% of all training and capacity building in the project. Moreover, the project will strengthen data collection and monitoring programmes – gender segregation of data collection and monitoring will be introduced as a basis for ensuring long-term gender benefits.

19.  Overall, the project will contribute to the development of Cambodia's capacity to better manage its environment, including the fulfillment of its MEA obligations. As a result of strengthening the management of the environment, the project will contribute to the provision of an enabling environment supporting the socioeconomic development in Cambodia.

B.3. Explain how cost-effectiveness is reflected in the project design: 20. In line with the GEF strategy, the GEF finances only the ‘incremental costs’ of achieving global environmental benefits. In the case of this project, it builds on top of an existing baseline, it will influence investments by both government and development partners, and it will have an impact beyond the limited GEF contribution. The cost-effectiveness of this project lies largely in the project strategy, namely by building upon a significant baseline and leveraged commitments and an existing legislative framework for environmental and natural resource management in Cambodia. 21. The cost-effectiveness of this project is also demonstrated in efficiently allocating financial resources. The recruitment of consultants under the project will be financed mostly by the GEF contribution, reducing the transaction costs associated when contracting consultants and other services through multiple sources of finances. In-kind co-financing includes government staff time to support the work of consultants. Overall, the strategic use of GEF funds is to mainstream into/onto ongoing processes and to modify them in order to yield global environmental benefits, this is far more cost-effective than if GEF was to support the entire initiative. 22. Outcome 1 will use project resources to develop national capacities to effectively and efficiently standardize environmental information that is generated on the implementation of the Rio Conventions in Cambodia, and give open-access to this information. Under this outcome, it will also support the strengthening of Cambodia’s capacity to better engage stakeholders and better coordinate the implementation of the Rio Conventions in the country. 23. Outcome 2 will use project resources to improve the use of environmental information for the development of innovative tools supporting decision-making processes related to the implementation of the Rio Conventions. Project support will also include activities to develop the capacity in using this environmental knowledge of national institutions involved in international negotiations at Conventions COPs as well as using this knowledge to produce national reports meeting Conventions reporting obligations. 24. In almost all cases, GEF activities fill gaps and make connections, rather than supporting an entire process or complete initiative. The Project also intends to minimize the use of international consultants where national expertise is available. This will reduce the travel costs and the costs of consultancy fees. Notwithstanding, where international expertise is unique or exceptionally credible, it will be utilized.

C.  describe the budgeted m &e plan:

25.  The Project Document provides a detailed description of the monitoring, reporting and evaluation to be undertaken during the Project (Section C.5). Full details of indicators, baseline values and targets are presented in Annex 2 to this project document (Project Results Framework).

26.  Monitoring and evaluation activities will follow UNDP and GEF monitoring and evaluation policies and guidelines. Monitoring and evaluation of progress in achieving project results and objectives will be done based on the targets and indicators established in the Project Results Framework (PRF) (Annex 2 of project document). The project Monitoring and Evaluation Plan has been budgeted at $32,500 (see Table below). Integrated into all Outcomes, the Project monitoring and evaluation approach will also facilitate learning and mainstreaming of project outcomes and lessons learned into international good practice as well as national and local policies, plans and practices.

27.  A summary of the envisaged M&E activities is provided in the following table.

| Type of M&E activity | Responsible Parties | Budget US$ Excluding project team staff time | Time frame |
| --- | --- | --- | --- |
| Inception Workshop and Report | - Project Coordinator - UNDP CO, UNDP GEF | Indicative cost: 5,000 | Within first two months of project start up |
| Measurement of Means of Verification of project results. | - UNDP GEF RTA/Project Coordinator will oversee the hiring of specific studies and institutions, and delegate responsibilities to relevant team members. | To be finalized in Inception Phase and Workshop. | Start, mid and end of project (during evaluation cycle) and annually when required. |
| Measurement of Means of Verification for Project Progress on output and implementation | - Oversight by Project Coordinator - Project team | To be determined as part of the Annual Work Plan's preparation. | Annually prior to ARR/PIR and to the definition of annual work plans |
| ARR/PIR | - Project Coordinator and team - UNDP CO - UNDP RTA - UNDP EEG | None | Annually |
| Periodic status/ progress reports | - Project Coordinator and team | None | Quarterly |
| Mid-term Review (if needed) | - Project Coordinator and team - UNDP CO - UNDP RCU - External Consultants (i.e. evaluation team) | Not Required for MSP project but can be undertaken if it is deemed necessary by the Project Board | At the mid-point of project implementation. |
| Final Evaluation | - Project Coordinator and team, - UNDP CO - UNDP RCU - External Consultants (i.e., evaluation team) | Indicative cost: $20,000 | At least three months before the end of project implementation |
| Project Terminal Report | - Project Coordinator and team - UNDP CO - Local consultant | 0 | At least three months before the end of the project |
| Audit | - UNDP CO - Project Coordinator and team | Indicative cost per year: $3,500 | Yearly |
| Visits to field sites | - UNDP CO - UNDP RCU (as appropriate) - Government representatives | For GEF supported projects, paid from IA fees and operational budget | Yearly |
| TOTAL indicative COST Excluding project team staff time and UNDP staff and travel expenses |  | US$ 35,500 (+/- 3.5% of GEF budget) |  |

PART iII: Approval/endorsement by gef operational focal point(s) and gef agency(ies)

- Record of Endorsement of GEF Operational Focal Point(s) on Behalf of the Government(s): ): (Please attach the Operational Focal Point endorsement letter(s) with this form. For SGP, use this OFP endorsement letter).

| Name | Position | Ministry | Date (MM/dd/yyyy) |
| --- | --- | --- | --- |
| Dr. Lonh Heal | Director General, GEF Operational Focal Point | Ministry of Environment | 01/30/2013 |

B.  GEF agency(ies) certification

This request has been prepared in accordance with GEF/LDCF/SCCF/NPIF policies and procedures and meets the GEF/LDCF/SCCF/NPIF criteria for CEO endorsement/approval of project.

| Agency Coordinator, Agency Name | Signature | Date (Month, day, year) | Project Contact Person | Telephone | Email Address |
| --- | --- | --- | --- | --- | --- |
| Adriana Dinu Officer-in-Charge and Executive Coordinator UNDP/GEF |  | 09/04/2014 | Tom Twining-Ward, Seniro Technical Advisor, UNDP (Green-LECRDs) | (4212) 5933-7386 | tom.twining-ward@undp.org |

GEF_CEOENDR_52

ANNEX A:  PROJECT RESULTS FRAMEWORK (either copy and paste here the framework from the Agency document, or provide reference to the page in the project document where the framework could be found).

See Annex 2 of the project document

ANNEX B:  RESPONSES TO PROJECT REVIEWS (from GEF Secretariat and GEF Agencies, and Responses to Comments from Council at work program inclusion and the Convention Secretariat and STAP at PIF).

Annex C:  status of implementation of project preparation activities and the use of funds

A.  provide detailed funding amount of the ppg activities financing status in the table below:

| PPG Grant Approved at PIF: US$ 25,000 |  |  |  |
| --- | --- | --- | --- |
| Project Preparation Activities Implemented | GEF/LDCF/SCCF/NPIF Amount ($) |  |  |
|  | Budgeted Amount | Amount Spent To date | Amount Committed |
| Local Consultants | 5,000 | 5,000 |  |
| International Consultants | 16,000 | 10,562 | 5,438 |
| Workshops | 4,000 | 4,000 |  |
| Total | 25,000 | 19,562 | 5,438 |

annex D:  calendar of expected reflows (if non-grant instrument is used)

Provide a calendar of expected reflows to the GEF/LDCF/SCCF/NPIF Trust Fund or to your Agency (and/or revolving fund that will be set up)

N/A

Project ID number will be assigned by GEFSEC.

Refer to the Focal Area Results Framework and LDCF/SCCF Framework when completing Table A.

PMC should be charged proportionately to focal areas based on focal area project grant amount in Table D below.

For questions A.1 –A.7 in Part II, if there are no changes since PIF and if not specifically requested in the review sheet at PIF  stage, then no need to respond, please enter “NA” after the respective question.

If at CEO Endorsement, the PPG activities have not been completed and there is a balance of unspent fund, Agencies can continue undertake the activities up to one year of project start.  No later than one year from start of project implementation, Agencies should report this table to the GEF Secretariat on the completion of PPG activities and the amount spent for the activities.