United Nations Development Programme

Country:  CAMBODIA

PROJECT DOCUMENT

Project Title: Generating, Accessing and Using Information and Knowledge Related to the Three Rio Conventions.

UNDAF Outcome: I. Economic Growth and Sustainable Development; and V. Governance. UNDAF Country Programme Outcome 1.2: National institutions, local authorities and private sector are better able to ensure the sustainable use of natural resources (protected areas, fisheries, forestry, mangrove, and land), cleaner technologies and responsiveness to climate change; UNDAF Country Programme Outcome 4.3: Enhanced capacities for collection, access and utilization of disaggregated information (gender, age, target populations, region) at national and sub-national levels to develop and monitor policies and plans that are responsive to the needs of the people and incorporate priority population, poverty and development linkages.

UNDP Strategic Plan Outcome 1: Growth and development are inclusive and sustainable, incorporating productive capacities that create employment and livelihoods for the poor and excluded. UNDP Strategic Plan Output 1.3: Solutions developed at national and sub-national levels for sustainable management of natural resources, ecosystem services, chemicals and waste CPAP Cambodia Outcome 2: By 2015, National institutions, local authorities, communities and private sector are better able to sustainably manage ecosystems goods and services and respond to climate change.

Executing Entity/Implementing Partner: Ministry of Environment (MOE)

Implementing Entity/Responsible Partners: United Nations Development Programme (UNDP)

Brief Description:

This project is in line with the GEF-5 CCCD Programme Frameworks two (2) and four (4), which calls for countries (2) to generate, access and use information and knowledge and (4) to strengthen capacities to implement and manage global convention guidelines. It is also aligned with the first objective of GEF6 that is to integrate global environmental needs into management information systems (MIS). It is a direct response to national priorities identified through the NCSA conducted in 2005-2006 and it is also part of the institutional strengthening underway at MOE and MAFF. Through a learning-by-doing process, this project will harmonize existing environmental information systems, integrating internationally accepted measurement standards and methodologies, as well as develop a more consistent reporting on the global environment. Under the first outcome, the project will support the development of national capacities to effectively and efficiently standardize environmental related information that is generated on the implementation of the Rio Conventions in Cambodia, and give open-access to this information. In parallel to this, the project will support the strengthening of Cambodia’s capacity to better engage stakeholders and better coordinate the implementation of the Rio Conventions in the country. Under the second outcome, project resources will be used to improve the use of environmental related information for the development of innovative tools supporting decision-making processes related to the implementation of the Rio Conventions. Project support will also include activities to develop the capacity in using this environmental related knowledge of national institutions involved in international negotiations at Conventions COPs, as well as using this knowledge to produce national reports meeting Conventions reporting obligations.

| Programme Period: 2014-2017 Atlas Award ID: TBC Project ID: TBC PIMS # 5222 Start date: 01 Oct. 2014 End Date 30 Sept. 2017 Management Arrangements NIM PAC Meeting Date ?? 2014 |  | Total resources required USD 2,290,000 Total allocated resources: - Regular UNDP Cash USD 150,000 - Other: - GEF USD 990,000 - Government In-kind USD 150,000 - UNDP In-kind USD 1,000,000 |
| --- | --- | --- |

| Agreed by: |  |  |
| --- | --- | --- |
| H.E. Say Sam Al Ministry of Environment | _____________________________________ | _______________ |
|  | Minister of Ministry of Environment | Date/Month/Year |
| Agreed by: Ms. Setsuko Yamazaki |  |  |
| United Nations Development Programme (UNDP) | ____________________________________ | ______________ |
|  | Country Director UNDP-CO Cambodia | Date/Month/Year |

Table of Contents

Acronyms and Abbreviations	4

PART I - PROJECT	6

A 	Project Summary	6

A.1	Project Rationale	6

A.2	Project Strategy	7

A.3	Key Indicators, Assumptions, and Risks	7

B	Country Ownership	8

B.1	Country Eligibility	8

B.2	Country Drivenness	9

B.2.a	National Capacity Self-Assessment	12

B.2.b	Sustainable Development Context	13

B.2.c	Policy and Legislative Context	17

B.2.d	Institutional Context	20

B.2.e	Barriers to Achieving Global Environmental Objectives	24

C.	Programme and policy conformity	25

C.1	GEF Programme Designation and Conformity	25

C.1.a	Guidance from the Rio Conventions	28

C.2  Project Design	29

C.2.a	GEF Alternative	29

C.3	Sustainability and Replicability	35

C.3.a	Sustainability	35

C.3.b	Replicability and Lessons Learned	37

C.3.c	Risks and Assumptions	38

C.4	Stakeholder Involvement	39

C.5	Monitoring and Evaluation	41

D.	Financing	46

D.1	Financing Plan	46

D.2	Cost Effectiveness	52

D.3	Co-financing	53

E.	Institutional Coordination and Support	53

E.1	Core Commitments and Linkages	53

E.1.a	Linkages to Other Activities and Programmes	53

E.2	Implementation and Execution Arrangements	54

F	LEGAL CONTEXT	58

PART II:	ANNEXES	59

Annex 1:  Capacity Development Scorecard	60

Annex 2:  Project Results Framework	66

Annex 3:  Outcome Budget (GEF Contribution and Co-financing)	70

Annex 4:  Provisional Work Plan	72

Annex 5:  Terms of References	74

Annex 6:  Environmental and Social Review Criteria	79

Annex 7:  PPG Status Report	80

Annex 8:  Letter of agreement between UNDP and Government of Cambodia for the provision of support services	81

PART III:	Co-Financing Letters	84

# Acronyms and Abbreviations

APR		Annual Project Report

AWP		Annual Work Plan

CBO		Community Based Organization

CCCD		Cross Cutting Capacity Development

CCCD		Cambodia Climate Change Department

CD		Capacity Development

CDC		Council for the Development of Cambodia

CI		Conservation International

CITES		Convention on International Trade in Endangered Species

CLC		Civil Liability Convention

CO		Country Office

COP		Conference of Parties

CPAP		Country Programme Action Plan

CSO		Civil Society Organization

ELC		Economic Land Concessions

EMIS		Environment Management Information System

FAO		Food and Agriculture Organization

FFI		Fauna & Flora International

GDANCP	General Department of Administration for Nature Conservation and Protection

GEF		Global Environment Facility

GOC		Government of Cambodia

ICBD		International Convention and Biodiversity Department

INC		Initial National Communication

IPCC		Intergovernmental Panel on Climate Change

IUCN		International Union for Conservation of Nature

LDC		Least Developed Countries

M&E		Monitoring and Evaluation

MAB		Man and the Biosphere (programme)

MAFF		Ministry of Agriculture, Forestry and Fisheries

MARPOL	Marine Pollution (International Convention for the Prevention of Pollution From Ships)

MDG		Millennium Development Goal

MEA		Multilateral Environmental Agreement

MOE		Ministry of Environment

MOU		Memorandum of Understanding

MOWRAM	Ministry of Water Resources and Meteorology

NAPA		National Adaptation Programme of Action

NBC		National Biodiversity Committee

NBSAP		National Biodiversity Strategy and Action Plan

NCCC		National Climate Change Committee

NCSA		National Capacity Self-Assessment

NGGC		National Green Growth Council

NGO		Non Governmental Organization

NIM		National Implementation Modality

NSDP		National Strategic Development Plan

PA		Protected Area

PAC		Project Appraisal Committee

PB		Project Board

PIR		Project Implementation Review

PMU		Project Management Unit

POP		Persistent Organic Pollutant

PPG		Project Preparation Grant

RCU		Regional Coordination Unit

REDD		Reducing Emissions from Deforestation and Forest Degradation

RTA		Regional Technical Advisor

SBAA		Standard Basic Assistance Agreement

SBSTTA	Subsidiary Body on Scientific, Technical and Technological Advice

SC		Steering Committee

SMART	Specific, Measurable, Achievable, Relevant and Time-bound

SNC		Second National Communication

SPREP		Secretariat of the Pacific Regional Environment Programme

UN		United Nations

UNCBD	United Nations Convention on Biological Diversity

UNCCD	United Nations Convention to Combat Desertification

UNCLOS	United Nations Conventions on the Law of the Sea

UNDAF	United Nations Development Assistance Framework

UNDP		United Nations Development Programme

UNEP		United Nations Environment Programme

UNESCO	United Nations Educational, Scientific and Cultural Organization

UNFCCC	United Nations Framework Convention on Climate Change

USD		United States Dollar

WHC		World Heritage Convention

WWF		World Wildlife Fund

# PART I - PROJECT

# A 	Project Summary

## A.1	Project Rationale

- Cambodia's history of conflicts and isolation through the 1970s to 1990s resulted in destruction of almost all the areas of national life, including human resources, which are most critical to underpinning the country's socioeconomic development efforts. The restoration of peace and policy stability over the past decade has brought steady economic growth in Cambodia, averaging between 8 and 10 percent since 1998, leading to substantial reductions in poverty. However, despite this progress, Cambodia still continues to face significant poverty and governance challenges.

- Development and environmental management in Cambodia is led by a set of key policies, supported by Laws. It includes the “Rectangular Strategy-Phase III” that is the Socio-economic Policy Agenda of the political platform of the government of Cambodia of the Fifth Legislature of the National Assembly (2013-2018). This strategy (Phase III) recognizes that the environment and climate change has become another challenge for the sustainability of Cambodia’s economic growth and social development due to pressures from population growth, urbanization, expansion and intensification of agriculture as well as development of transport, energy and other sectors. It stated “many environmental issues are cross-sectoral in nature, which requires coordination across government agencies at both national and sub-national levels including cooperation with all the stakeholders”. This strategy is the government comprehensive policy framework guiding national development and in particular guiding the formulation of the NSDP.

- The “National Sustainable Development Plan (NSDP)” formulated for the period 2009-2013 placed a high priority on tackling key sectoral challenges in the areas such as garments and other manufactured goods; tourism infrastructure; diversification of the agriculture sector; infrastructure development; and, improving people livelihoods. The recently drafted NSDP for the period 2014-2018 focuses on intensifying efforts to reduce the impact of climate change by strengthening the adaptation capacity and resiliency to climate change, particularly by implementing the "Cambodia Climate Change Strategic Plan 2014-2023", “National Policy on Green Growth” and the “National Strategic Plan on Green Growth 2013-2030”.

- As a GEF eligible country, Cambodia obtained an UNDP-GEF grant to conduct its National Capacity Self-Assessment (NCSA), which started in 2005 and was concluded in 2006. The goal of the project was to develop and strengthen national capacities for sustainable management and use of natural resources and of the environment, for the benefit of the Cambodian poor. Its objective was to identify country level priorities and needs for capacity development, to address global environmental management requirements, particularly the thematic concerns of the three UN conventions. The project looked into existing capacities and capacity needs in Cambodia, to address domestic environmental issues and concerns that are also concerns of the three Rio Conventions: UNFCCC, UNCDB, and UNCCD, which Cambodia is a party to.

- This extensive assessment identified a large number of common issues and capacity needs. As per the NCSA action plan, “existing thematic capacities in Cambodia are severely lacking, over-all. Capacities to attend to the thematic concerns and meet the obligations to all three Conventions are almost all weak. They hardly lend to being prioritized in that all are needed the soonest time they can be acquired. It concluded that “the cross-cutting capacity needs, which address broad national conditions of the economy and socio-political system of Cambodia that constrain the thematic capacities, are essentially at the highest levels of government and Cambodian society”. This assessment also identified a list of priority actions including the need for better coordination for the implementation of the Rio Conventions, more public awareness and the need to mainstream the environment into policies, plans and programmes. This proposed project will address some of these priority actions.

- This project is also in line with the GEF-5 CCCD Programme Frameworks two (2) and four (4), which calls for countries (2) to generate, access and use information and knowledge and (4) to strengthen capacities to implement and manage global convention guidelines. Through a learning-by-doing process, this project will harmonize existing information systems, and integrate internationally accepted measurement standards and methodologies, as well as consistent reporting on the global environment. It will target the development of capacities at the individual and organizational level, strengthening technical skills to manage data and transform this information into knowledge. The project will also support activities to strengthen the coordination between key sectors to address biodiversity, climate change and land degradation issues at systemic and institutional levels.

## A.2	Project Strategy

- This proposed project will address some of the priority actions identified through the NCSA such as better use of environmental information in decision-making and policy-making, better coordination, mainstreaming environmental management into national policies, plans and programmes and development of the national negotiation capacities to advance Cambodian national interest on environmental matters in international fora. Its goal is to improve the implementation of the Rio Conventions in Cambodia through the development of national capacities to better coordinate and generate better information related to the implementation of these Conventions.

- The project’s objective is to improve access to environmental information related to the Rio Conventions through the harmonization of existing environmental management information systems and improving coordination of the implementation of these conventions in Cambodia.  The harmonization of these existing systems will be translated into better access to information related to the implementation of the Rio Conventions in Cambodia. This objective will be achieved through two (2) outcomes:

  - Improved access and generation of information related to the three Rio Conventions: Under this outcome, the project will support the development of national capacities to effectively and efficiently standardize environmental information that is generated on the implementation of the Rio Conventions in Cambodia, and give open-access to this information. In parallel to this, the project will support the strengthening of Cambodia’s capacity to better engage stakeholders and better coordinate the implementation of the Rio Conventions in the country.

  - Improved use of information and knowledge related to the Rio Conventions: Under this second outcome project resources will be used to improve the use of environmental information for the development of innovative tools supporting decision-making processes related to the implementation of the Rio Conventions. Project support will also include activities to develop the capacity in using this environmental knowledge of national institutions involved in international negotiations at Conventions COPs as well as using this knowledge to produce national reports meeting Conventions reporting obligations.

- The proposed project will develop crosscutting capacity to respond to the needs of the three conventions; particularly the reporting requirements. During the project implementation, the coordination and information generation capacities of the focal points established by the government will be enhanced.

- The project will take an adaptive collaborative management approach to implementation, which calls for stakeholders to take an early and proactive role in the mainstreaming exercises, as well as to help identify and solve unexpected implementation barriers and challenges.  By taking an adaptive collaborative approach, project activities and outputs can be more legitimately modified and adapted to maintain timely and cost-effective project performance and delivery.

## A.3	Key Indicators, Assumptions, and Risks

- A set of indicators was identified to measure progress against the objective and outcomes. It includes the summary results of the capacity development scorecard as one indicator used to measure progress on the development of capacities at the objective level. Two other indicators were identified at this level to measure the harmonization of environmental management information systems and the quality of reports/communications on the implementation of the Rio Conventions. A total of 11 indicators were identified to measure progress at the objective and outcomes level. For each indicator, a baseline was set as well as a target at the end of the project.

- The review of risks to the project indicates that these risks are manageable through the project’s learn-by-doing approach. This proposed project is a direct response to national priorities identified through the NCSA process; as a result, there is a strong national ownership and willingness to succeed, hence low risks that key stakeholders will not participate in the project and lack of political will.

# B	Country Ownership

## B.1	Country Eligibility

- Cambodia is eligible to receive technical assistance from UNDP, and is thus eligible for support under the Global Environment Facility (GEF).  Cambodia ratified the United Nations Convention on Biological Diversity (UNCBD) on February 9, 1995 and the United Nations Framework Convention on Climate Change (UNFCCC) on December 18, 1995, and ratified the United Nations Convention to Combat Desertification and Drought (UNCCD) on August 18, 1997. Cambodia ratified important protocols under the Rio Conventions in later years, namely:

  - It acceded to the Cartagena Protocol on Biological Safety on December 16, 2003 and ratified it on September 17, 2003 to protect biodiversity from the potential risks posed by genetically modified organisms that are the product of biotechnology.

  - It acceded to the Kyoto Protocol in 2002, participating with developed countries  to reduce greenhouse gas emission, through hosting the Clean Development Mechanism (CDM).

  - Cambodia acceded to the Nagoya-Kuala Lumpur Supplementary Protocol on Liability and Redress on remedial measures arising from damages caused by the transboundary movement of living modified organisms on August 30, 2013.

  - Cambodia signed the Nagoya Protocol on Access to Genetic Resources and the Fair and Equitable Sharing of Benefits Arising from their Utilization on February 1, 2012.

- Other global conventions signed or ratified by Cambodia and related to the environment include:

  - International Plant Protection Convention (1952)

  - World Heritage Convention (WHC) (Acceptance May 12, 2000)

  - CITES in 1997

  - Ramsar Convention on Wetlands (Entered into Force on October 23, 1999)

  - International Whaling Commission (IWC) (Adherence December 28, 2004)

  - Convention on the Conservation and Management of the High Seas Fishery Resources in the South Pacific Ocean (1982)

  - Pacific Tuna Fisheries (2008)

  - Vienna Convention for the Protection of the Ozone Layer (April 7, 1993)

  - Montreal Protocol to the Vienna Convention (Montreal Protocol on Substances that Deplete the Ozone Layer) and its Amendments (April 8, 1993)

  - Stockholm Convention on Persistent Organic Pollutants (POPs) (September 7, 2004)

  - Basel Convention on the Control of Trans-boundary Movements of Hazardous Waste and their Disposal (September 7, 2000)

  - Waigani Convention (June 28, 2001)

  - London Convention (July 12, 1979)

  - International Convention on Liability and Compensation for Damage in Connection with the Carriage of Hazardous and Noxious Substances by Sea, 1996: Marine Pollution: UNCLOS (Chapters 1 & 12)

  - MARPOL (International Convention for the Prevention of Pollution from Ships, 1973, as modified by the Protocol of 1978 relating thereto) Annexes I, II, III, IV, V and VI

  - CLC Protocol 92 (entered into force on February 5, 2008)

  - Fund Protocol 92 (February 5, 2007)

  - Bunkers Convention 2001

  - Anti Fouling Convention 2001

  - Ballast Water Management Convention 2004

  - SPREP Pollution Emergency (Protocol concerning Cooperation in Combating Pollution Emergencies in the South Pacific Region) (1986)

  - SPREP Dumping Protocol (1986)

- Cambodia is also part of several regional planning frameworks to support its work in managing the environment. It includes:

  - Cambodia signed an MoU on Conservation and Management of Marine Turtles and their Habitats of the Indian Ocean and Southeast Asia in 2003 which is a instrument under the Convention on Migratory Species. (Cambodia did not ratified the Convention on Conservation of Migratory Species)

  - Cambodia is also a member of Asia-Pacific Plant Convention. Cambodia adopts and involves in the implementing of inter-governmental conventions such as the Regional Code of Conduct established by FAO for Responsible Fisheries and ASREAN-SEAFDEC Agreement on Resolution and Plan of Action

  - A framework agreement on co-operation between the European Union (EU) and Cambodia was signed on 29 April, 1997 and came into force on 1 November 1999

  - Cambodia is a member country of Southeast Asian Ministers of Education Organization (SEAMEO) - an international treaty organization established in 1965 with the aim of promoting regional cooperation in education, science, and culture

  - Cambodia is among 12 coastal States of the East Asian region that have signed on 12 December 2003, the Putrajaya Declaration of Regional Cooperation for the Sustainable Development of the Seas of East Asia and adopted the Sustainable Development Strategy For The Seas of East Asia as an effort toward Regional Implementation of the World Summit on Sustainable Development Requirements for the Coasts and Oceans

  - Cambodia is involved in a number of ASEAN agreements and cooperative arrangements addressing key environmental issues of regional concerns such as the ASEAN Strategic Plan of Action on the Environment, 1999-2004 (SPAE), ASEAN Plan of Action for Energy Cooperation (1999-2004), and the ASEAN Agreement on Transboundary Haze Pollution (2002)

  - Cambodia is a member of the Association of South East Asian Nations (ASEAN) and thus is bound by its agreements, particularly on the Conservation of Nature and Natural Resources. ASEAN's forestry program includes, inter alias, the development of guidelines for criteria and indicators, trade harmonization and promotion through the ASEAN Forest Product Industry Club (AFPIC), and work on forest fires and haze

  - Cambodia also signed up to undertake the goals determined by the Millennium Resolution and Millennium Plan of Action on Sustainable Fisheries for Food Security for the ASEAN Region as part of its commitments to the participation of local communities in fisheries management

## B.2	Country Drivenness

- The United Nations Development Assistance Framework (UNDAF) for Cambodia is a five-year strategic programme framework that outlines the collective response of the UN system to development challenges and national priorities in Cambodia for the period 2011-2015. It provides a framework for coordinated UN development assistance in Cambodia in keeping with the UN reform process and the commitments laid out in the Paris Declaration on Aid Effectiveness. The UNDAF 2011-2015 is anchored in and aligned with the Government’s Rectangular Strategy Phase II and the National Strategic Development Plan (2009-2013). It builds on the achievements and progress made over the last decade and leverages the UN’s position as a trusted and neutral partner of the Royal Government of Cambodia and the people of Cambodia. This programme is based on the findings from the Common Country Assessment published in 2009. The UN Country Team also adopted a Human Rights-based Approach in undertaking the country analysis and to advocate for priorities in the national development framework. These principles require a specific focus on the marginalized, the disadvantaged and the excluded, and form one of the core programming principles of the UNDAF.

- This UNDAF sets out three levels of results expected from UN cooperation in Cambodia for the period 2011-2015: (a) at the UNDAF outcome level, the contribution is articulated in terms of specific development results that support national priorities as articulated in the Rectangular Strategy Phase II and the National Strategic Development Plan (NSDP); (b) at the country programme outcome level, results aim to capture institutional and behavioral changes that result from the collective efforts of two or more UN agencies alongside actions of others, in particular the government; and (c) at the output level, interventions will target capacity gaps that hinder the various levels of government from fulfilling their commitments and those that prevent people living in Cambodia from fulfilling their rights. Overall, the UN focuses on strengthening the knowledge and skills, human and financial resources, as well as coordination and communication that are necessary (but not sufficient) if Cambodia is to achieve its MDG targets by 2015.

- The UNDAF identified five priorities (also called UNDAF Outcomes) that form the core of the UN’s support to Cambodia for the period 2011 to 2015. There are presented below with their respective country programme outcomes:

  - Economic Growth and Sustainable Development: By 2015, more people living in Cambodia benefit from, and participate in, increasingly equitable, green, diversified economic growth

    - Sustainably developed agricultural sector promoting equitable physical and economic access to an increased number of safe and nutritious food and agricultural products;

    - National institutions, local authorities and private sector are better able to ensure the sustainable use of natural resources (protected areas, fisheries, forestry, mangrove, and land), cleaner technologies and responsiveness to climate change;

    - More diversified economy in Cambodia with increased pro-poor investment, trade and private sector development due to strengthened national and sub-national capacity;

    - Increased employability and productive and decent employment opportunities, particularly for youth and women, through diversified local economic development in urban and rural areas.

  - Health and Education: By 2015, more men, women, children and young people enjoy equitable access to health and education

    - Increased national and sub-national equitable coverage of quality reproductive, maternal, newborn, child health, and nutrition services

    - Strengthened health sector response on HIV

    - More women, men, children, and young people enjoy safe water, sanitation and hygiene conditions

    - Increase in reach and sustainability of children learning in relevant and quality basic education through increased institutional capacities

    - Enhanced national and sub-national institutional capacity to expand young people’s access to quality life skills including on HIV and technical and vocational education and training (TVET)

  - Gender Equality: By 2015, all women, men, girls and boys are experiencing a reduction in gender disparities and progressively enjoying and exercising equal rights

    - A harmonized aid environment that promotes gender equality and the empowerment of women

    - Strengthened and enhanced gender mainstreaming mechanisms at national and sub-national levels

    - Women are progressively empowered to exercise their rights to full and productive work with decent terms and conditions

    - Enhanced participation of women in the public sphere, at national and sub-national levels

    - Improved societal attitudes and preventive and holistic responses to GBV

  - Governance: By 2015, national and sub-national institutions are more accountable and responsive to the needs and rights of all people living in Cambodia and increase participation in democratic decision-making.

    - Effective mechanisms for dialogue, representation and participation in democratic decision-making established and strengthened

    - State institutions at national and sub-national levels better able to protect citizens’ rights under the Constitution and provide effective remedies for violations, in particular those relating to labor, children, land and housing, gender-based violence, indigenous people, people living with HIV and people with disabilities

    - Enhanced capacities for collection, access and utilization of disaggregated information (gender, age, target populations, region) at national and sub-national levels to develop and monitor policies and plans that are responsive to the needs of the people and incorporate priority population, poverty and development linkages

    - Sub-national governments have the capacity to take over increased functions

    - Strengthened multi-sectoral response to HIV

  - Social Protection: By 2015, more people, especially the poor and vulnerable, benefit from improved social safety net (SSN) and social security programmes, as an integral part of a sustainable national social protection system.

    - Increase in national and subnational capacity to provide affordable and effective national social protection through improved development, implementation, monitoring and evaluation of a social protection system

    - Improved coverage of Social Safety Net programmes for the poorest and most vulnerable

    - Improved coverage of social security for both formal and informal sector workers

- The project will contribute to priority 1 – Economic Growth and Sustainable Development and to a lesser degree to priority 4 – Governance. By improving the access to environmental information and developing the capacity to use this information and knowledge for better decision-making, the project will particularly contribute to the development of capacities of national institutions, local authorities and private sector to ensure the sustainable use of natural resources (protected areas, fisheries, forestry, mangrove, and land), cleaner technologies and responsiveness to climate change. The project will also contribute to strengthening the governance framework (priority 4) in the environmental area through improving coordination mechanisms and increasing stakeholder engagement in Rio Conventions related dialogues and decision-making.

- Within the context of the UNDAF 2011-2015 and of the UNDP Country Programme 2006-2010, UNDP developed its Country Programme Action Plan (CPAP) for the period 2011-2015. This programme was designed to respond to national priorities contained in the NSDP with a special focus on helping accelerate progress towards the MDGs before 2015, including the support of policies to plan local responses to climate change. This programme contributes directly to three UNDAF outcomes: economic growth and sustainable development; gender equality; and governance.

- The CPAP is divided into six components: a) Poverty reduction; b) Environmental and climate change; c) Democratic governance; d) Capacity and functions of the sub-national administrations; e) Planning; and f) Gender equality. Under the environment and climate change component, the expected outcome is by 2015, national and sub-national authorities, communities and private sector are better able to sustainably manage ecosystems goods and services and respond to climate change.

- As a crosscutting capacity development initiative, this proposed project falls under this component. It will contribute to the development of capacities at the individual level but also at the institutional and systemic levels. It will seek to improve engagement of stakeholders in the management of the environment, to better use environmental information for policy-making and plan/programme development, to better coordinate environmental sectors - particularly those related to Multi-lateral Environmental Agreements (MEAs) obligations, and develop the economic valuation of the use of natural resources in Cambodia.

### B.2.a	National Capacity Self-Assessment

- The aim of the National Capacity Self Assessment (NCSA) projects - funded by the GEF - was for countries that are Parties to the UNCBD, UNCCD and UNFCCC, to assess their own capacities and capacity development needs to address the requirements of the three conventions and identify measures to address these needs.

- As a GEF eligible country, Cambodia obtained an UNDP-GEF grant to conduct its NCSA, which started in 2005 and was concluded in 2006. The goal of the project was to develop and strengthen national capacities for sustainable management and use of natural resources and of the environment, for the benefit of the Cambodian poor. Its objective was to identify country level priorities and needs for capacity development, to address global environmental management requirements, particularly the thematic concerns of the three UN conventions. The project looked into existing capacities and capacity needs in Cambodia, to address domestic environmental issues and concerns that are also concerns of the three Rio Conventions: UNFCCC, UNCDB, and UNCCD, which Cambodia is a party to.

- It focused on issues and concerns within its jurisdiction to address Cambodia’s obligations under the three conventions. It was a national assessment of Cambodian capacities undertaken by the government of Cambodia and done by Cambodians. The project had two main parts: (1) stock taking and thematic assessment (assessment of existing capacities and capacity needs in Cambodia), and (2) developing an Action Plan to embark on developing the needed capacities in the country in the short- (1-3 years), medium- (4-6 years), and long- (6-10 years) terms:

  - The Stock Taking involved a series of several activities: (1) an inventory of Cambodian obligations under each of the three conventions; (2) the determination of the capacities that are required to fulfill these obligations; (3) assessing existing capacities, (4) determining present capacity needs, (5) identifying the constraints on developing the relevant capacities in Cambodia, and (6) assessing for common and cross-cutting issues and capacity needs that impinge on the capacities to fulfill the obligations to the three conventions.

  - The Action Plan followed the completion of the stock taking and thematic assessment activities.

- The approach taken by Cambodia in implementing the NCSA project included extensive stakeholder consultations through interviews, focus group discussions and 3 workshops (2 workshops to consult stakeholders on initial findings and 1 workshop to validate the final action plan). The process followed the guidance given in the NCSA Guide and was supported by the NCSA Global Support Programme overseen by UNDP and UNEP.

- The process that led to the prioritization of national capacity needs identified several “conditions” that were in place to promote Cambodian capacities for implementing the Rio Conventions. They include:

  - The increasing stability of governmental and political institutions, which encourage public and private investments on capacity development;

  - The increasing number of academic institutions offering degree programs and engaged in some research that are relevant to the conventions;

  - The presence of a large community of foreign-based and local NGOs that are engaged in activities relevant to the conventions;

  - The presence of a large community of donors, all committed to assist Cambodia build up its basic institutions and its national capacities;

  - The importance placed on agriculture by the government and the increasing mainstreaming of environmental and natural resource protection in national development strategies.

- On the contrary, the assessment also found few “conditions” that inhibited the implementation of the Rio Conventions. They include:

  - The capacity of the civil service that is still struggling to re-establish itself after it had been effectively dismantled for years prior to the 1990s;

  - Capacity and activities to address environmental issues;

  - The administrative systems and mechanisms in the Royal Government of Cambodia.

- This extensive assessment identified a large number of common issues and capacity needs. As per the action plan, “existing thematic capacities in Cambodia are severely lacking, over-all. Capacities to attend to the thematic concerns and meet the obligations to all three Conventions are almost all weak. They hardly lend to being prioritized in that all are needed the soonest time they can be acquired. What needs prioritizing is the development of the dimensions of capacities (human, financial, organizational, public support) in ways that will address the most number of thematic capacity needs of the country”. Furthermore, this same action plan states that “the cross-cutting capacity needs, which address broad national conditions of the economy and socio-political system of Cambodia that constrain the thematic capacities, are essentially at the highest levels of government and Cambodian society”. Using a timeframe divided into three timelines: short-term (1-3 years), medium-term (4-6 years), and long-term (7-10 years), the assessment was conducted in each thematic area, followed by an assessment of crosscutting capacity issues and needs. For each area, the review looked into human capabilities, financial capabilities, organizational commitments, and public support.

- On the basis of the assessment of issues and needs and their prioritization, a long list of priority actions was identified; 160 priority actions divided as follows: 53 in the short-term, 53 in the medium-term and 54 in the long-term. An action plan was then formulated for the implementation of the 53 priority actions in the short term with a budget of USD 16.15 million required for implementing this plan.

- Among these 53 priority actions, recurrent themes include: better coordination – including coordination mechanisms – for the implementation of Rio Convention obligations; more public awareness about these obligations; environmental mainstreaming into policies, plans and programmes; improve collect, update, storage, and access/use of environmental management information; more integrated approaches across sectors such as environment, agriculture, forestry; higher capacity of government staff in environmental management; more government resources allocated to environmental management; set-up innovative financing mechanisms for implementing obligations from the global environmental agenda; Improve and strengthen their ability to advance Cambodian national interests on environmental matters in international fora.

- This proposed project will address some of these priority actions such as better use of environmental information in decision-making and policy-making, better coordination, mainstreaming environmental management into national policies, plans and programmes and development of the national negotiation capacities to advance Cambodian national interest on environmental matters in international fora. By improving the access to environmental information, the project should also contribute in addressing the need for better reporting to these international Conventions.

### B.2.b	Sustainable Development Context

- Cambodia is located in Southeast Asia, bordering Vietnam, Laos and Thailand, and has a total land area of 181,035 km2. The country's population grew from around 9 million in the 1960s to around 14,197,000 in 2006. The country has a relatively low population density of about 82 people per km2 (2011). With the current annual population growth rate of around 2.5%, the population could reach 19 million people in 2020 (National Institute of Statistics 2007). Approximately 80 percent of the country's inhabitants live in rural areas with limited access to electricity and seasonal food shortages.

- Cambodia's history of conflicts and isolation through the 1970s to 1990s resulted in destruction of almost all the areas of national life, including human resources, which are most critical to underpinning the country's socioeconomic development efforts. As a consequence Cambodia is designated as a least developed country (LDC). The restoration of peace and policy stability over the past decade has brought steady economic growth in Cambodia, averaging between 8 and 10 percent since 1998, leading to substantial reductions in poverty.

- Cambodia is one of the poorest countries in Southeast Asia. Its Human Development Index is 0.543 (2013), which gives the country a rank of 138th out of 187 countries with data and which increased from 0.444 in 2000. In 2011, about 20% of Cambodians live under the national poverty line (World Bank), which is down from 50% in 2007. According to this same dataset, about 19% of the population live with less than $1.25 a day (PPP-2009) - which came down from over 32% in 2007 – and almost 50% live with less than $2 a day; down from about 60% in 2007.  Around 3 million people currently live in cities (about 20 % of the total). The rural population represents about 80% and 24 percent of the rural population lives below the national poverty line in 2011; down from 58% in 2007.

- Despite this progress, Cambodia still continues to face significant poverty and governance challenges. Cambodia's economy is heavily reliant on export markets and saw a steep decline in GDP growth following the 2008/09 economic crisis. Since then, the economy rebounded in 2010. Over 60% of the population is dependent on agriculture and the country is a net rice exporter and generally food self-sufficient. However, according to FAO, the level of food poverty in Cambodia was about 57% of the population (2007). Large proportions of the population are employed in agriculture although shifts in employment towards industry and services are taking place - 72 percent of the population was employed in agriculture in 2008 compared to 51 percent in 2012. Foreign investment in agriculture has expanded rapidly in recent years with the primary cash crop being rubber. At the same time, landlessness has risen steeply and was estimated at 20% in the 2004 Cambodia Socio-Economic Survey. Road networks are increasingly bisecting the country and providing greater access to rural areas and higher paying international markets. Major road building programmes are stimulating economic development and increasing opportunity costs of land but been criticized for inadequacy of social and environmental safeguards.

Biodiversity

- Compared with its neighboring countries, Cambodia still has a low population density and relatively large intact natural areas. WWF's eco-regional assessment has identified five critical ecosystems in Cambodia, including the Cardamom Mountain Range, which include the Tenasserim-South Thailand semi-evergreen rain forests, the Northern Plains, the Eastern Plain, the Upper Mekong and the Tonle Sap. Of these, the Cardamom Mountains rain forests and the Tenasserim-South Thailand semi-evergreen rain forests are included in the WWF Global 200 list of priority ecoregions.

- The Cardamom Mountain rainforests ecoregion occurs mostly in southwestern Cambodia, with a small section falling across the border in southeastern Thailand. It is considered by some to be one of the most species-rich and intact natural habitats in the Southeast Asia region. The Northern Plains of Cambodia are the largest remaining intact block of a unique landscape that once covered much of Indochina. Dominated by open deciduous forest, grasslands, and seasonal wetlands, the area has been described as the Asian equivalent of the African savannas. Cambodia's globally important ecosystems are home to globally important species as well. It is estimated that Cambodia hosts 806 globally threatened species, including 26 critically endangered species, 36 endangered and 51 vulnerable species. About 423 species are largely forest or forest-dependent species - including 9 critically endangered species, 9 endangered species and 23 vulnerable species.

- The total area of forest in Cambodia is estimated at 10,864,186ha, equivalent to approximately 56% of the total land area. The country's forests have suffered from both deforestation and degradation. Around 2.1 million ha of forestlands were converted to agriculture and other uses between 1960 and 1992-93. Additionally, a large proportion of the existing forest estate is degraded: it is estimated that there are around 2,600,000ha of degraded forest land that require restoration. The causes of this deforestation and degradation include logging, firewood extraction, wildfires, encroachment, land grabbing, establishment of rice fields, commercial agriculture, road development and human settlements.

- Cambodia has one of the highest percentages of national territory within protected areas in the world. There are 23 protected areas (PAs) in the country under the responsibility of the Ministry of Environment (MOE), covering approximately 18% of the total land area and including a total of 3,273,300 ha of forest (25% of the total forest area). In addition, the Royal Government of Cambodia also made a series of designation of 10 additional Protected Forest areas administered by the Forestry Administration of the Ministry of Agriculture, Forestry and Fisheries covering 1.63 million hectares and 8 fish sanctuaries supported by its Fisheries Administration. (Fifth National Report on CBD 2014)

Over 84% of households in Cambodia meet their energy needs through fuel wood, which supplies approximately 70% of the total national energy demand. Total residential firewood demand in 2007 was estimated at approximately 5,500,000 tons nationally.

- Cambodia has one of the highest levels of forest cover in Southeast Asia, with approximately 10.7 million hectares of forest in 2006 or 59% of Cambodia's land area. Based on the FAO 2005 Forest Resources Assessment, Cambodia has the 30th largest area of tropical forest in the world, but is the 13th most forested country by percentage of land area. Cambodia also has a relatively high rate of land-use change. Between 2000 and 2010, almost 3 million ha of forest has been lost (FAO 2010), which reduced the total forest cover to 57.7 percent of the total land area in Cambodia, dropping below the CMDG target of 60 percent.

Climate Change Vulnerability

- As an essentially agrarian country, Cambodia is highly vulnerable to the impacts of climate change. The result of modelling studies in the Initial National Communication (INC) and the Second National Communication (SNC) indicates that Cambodia’s mean surface temperature has increased by 0.8°C since 1960. The mean temperature is projected to increase between 0.013°C to 0.036°C per year by 2099, depending on location. The rate of temperature increase is higher in low altitude areas than in high altitude areas. The Fourth Assessment Report of the Intergovernmental Panel on Climate Change (IPCC) shows that the global sea level rise is projected to increase between 18 cm and 50 cm by 2100 based on the SRESB1 and SRESA2 respectively.

- An increase in the temperature is likely to affect agricultural productivity. According to the International Rice Research Institute, rice grain yields decline by 10% for each 1oC increase in minimum (night) temperatures during the growing period in the dry season. Additionally the frequency and intensity of floods may increase with changing climate conditions, and cause severe damage to rice harvests. Successions and combinations of droughts and floods have resulted in a significant number of fatalities and considerable economic losses. Losses arising from floods have been further exacerbated by deforestation. Floods have accounted for 70% of rice production losses between 1998 and 2002, while drought accounted for 20% of losses.

- Sea level rise may also affect the 435-km long coastline, which already suffers from storm surges, high tide, beach erosion and seawater intrusion. Low-lying areas, including settlements, beach resorts, seaports, coastal fisheries, and mangroves forests, may become submerged with rises in sea levels.

- In addition, vector-borne diseases, in particular malaria, may become more widespread under changing climatic conditions. With some 800 deaths per year, Cambodia already has the highest fatality rate from malaria in Asia (CNM, 2003). The actual death toll due to malaria may be 5-10 times the officially recorded figures (RGC, 2002). Poor infrastructures and high poverty rates make malaria treatment unaffordable for large segments of the population. Only 55% of the population has geographic access to public health facilities (RGC, 2001).

Land Degradation

- In 2010, agricultural land was about 24% while forest land was about 56% of the country’s total land area. The land used for agriculture was estimated to be about 3.7 million ha; excluding the Economic Land Concessions (ELC). Major agricultural production zones are scattered in the northeastern region of the country, near to Thai border, low land around the Tonle Sap lake and other main rivers down to the delta on the southern and south-eastern parts of the country.

- From 1993 to May 2010, the government of Cambodia has granted 142 companies the right to use ELCs for cultivation of agricultural and agro-industrial crops, forest and rubber trees, in the hopes that this action could help restore the forest cover and improve biodiversity. Since then, 43 of the 142 companies did not follow the investment contracts, cleared the land and left it without forest cover, which caused soil erosion and loss of biodiversity; contributing to land degradation. As a result, the government terminated these contracts and confiscated the corresponding land. There are now 99 valid ELCs companies exploiting a total area of 1,046,591ha scattered in 17 provinces6.

- Land degradation in Cambodia includes soil degradation, deforestation and the subsequent loss of biodiversity. The key effects include low agricultural productivity and increased vulnerability to drought and floods. The immediate causes of land degradation in Cambodia are inappropriate forest use and agricultural land use practices. Inappropriate land use practices are in turn influenced by such factors as population growth; urbanization; land tenure security and resource access by land users; the influence of prices and markets; the adequacy of regulations and enforcement; and availability of technical support to guide land users.

- At least two other factors exacerbate the effects of land degradation in Cambodia.  One is the inherent low soil fertility in large portions of agricultural lands, which has been reported as early as 1966. Related to this is the natural limitation of most soils to retain water which tends to limit the organic matter content of soils, thereby contributing to low soil fertility.

Development Challenges

- Since the 2008-09 global financial crisis, Cambodia is facing new unexpected challenges within the context of the global economic recession and the turmoil in the global financial markets. The National Sustainable Development Plan (NSDP) formulated for the period 2009-2013 placed a high priority on tackling key sectoral challenges:

  - Diversify the markets for our garments and other manufactured goods market to East Asia, the Middle East and Africa etc.

  - Further improve tourism infrastructure and the development of more tourism destinations and attractive tour packages.

  - Prioritize the use of resources and expertise of the government, and donors to broaden and diversify our agricultural sector, in order to attract more quality investments in agri-business and improve agricultural trade linkages, land reform, agricultural diversification and agro-processing.

  - Further invest in infrastructure development, particularly energy generation to reduce energy costs to the private sector and to the community.

  - Continue to promote and support wealth creation and improving the people’s livelihood according to the correct principles and procedures as stipulated in the Cambodia’s Constitution.

### B.2.c	Policy and Legislative Context

- Development and environmental management in Cambodia is led by a set of key policies, supported by Laws. It includes the following key policies:

Rectangular Strategy – Phase III

- The Rectangular Strategy-Phase III is the “Socio-economic Policy Agenda” of the political platform of the government of Cambodia of the Fifth Legislature of the National Assembly (2013-2018). The central themes of the rectangular strategy are Growth, Employment, Equity and Efficiency. This is the government comprehensive policy framework guiding national development and in particular guiding the formulation of the NSDP. Phase III of this strategy is to “guide activities of all stakeholders to further pursue and strengthen long-term sustainable development aimed at promoting economic growth, creating jobs, equitable distribution of the fruits of growth, and ensuring effectiveness of public institutions and management of resources”.

- The strategy includes four strategic objectives:

  - Ensuring an average annual economic growth of 7%

  - Creating more jobs for people especially the youth through further improvement in Cambodia’s competitiveness

  - Achieving more than 1 percentage point reduction in poverty incidence annually

  - Further strengthening institutional capacity and governance, at both national and subnational levels

- This strategy (Phase III) recognizes that the environment and climate change has become another challenge for the sustainability of Cambodia’s economic growth and social development due to pressures from population growth, urbanization, expansion and intensification of agriculture as well as development of transport, energy and other sectors. It stated “many environmental issues are cross-sectoral in nature, which requires coordination across government agencies at both national and sub-national levels including cooperation with all the stakeholders”. Furthermore, it stated that “as a response, the government will continue to take a comprehensive development approach toward environmental management in Cambodia, through:

  - Sustainable management of natural resources;

  - Intensifying efforts to reduce the impacts of climate change by strengthening adaptation capacity and resiliency to climate change, particularly by implementing the “National Policy on Green Growth” and the “National Strategic Plan on Green Growth 2013-2030”;

  - Continuing to strengthen technical and institutional capacity to promote the mainstreaming of climate change responses into the policies, laws and plans at national and sub-national levels;

  - Continuing to introduce measures to control environment and ecosystems pollution

National Strategic Development Plan (NSDP) Update – 2009-2013

- Development planning in Cambodia is done through a five-year planning cycle, which is aligned to the Rectangular Strategic Framework (see above).

- The National Strategic Development Plan (NSDP) Update 2009-2013 is a comprehensive development plan reviewing the major achievements under the period of the previous plan (NSDP 2006-2010) and challenges in key development sectors. Its main focus is to set the key policy priorities and actions for the period 2009-2013. The environmental sector is within the third priority “Enhancement of the Agricultural Sector”. It states that “the Ministry of Environment (MOE) will:

  - Ensure sustainable use of natural resources and will implement measures that will require the carrying out of Environmental Impact Assessments of proposed development projects before implementation;

  - Ensure ecology system and environment of water is not polluted;

  - Control and reduce environment pollution;

  - Strengthen management of protected areas in order to eliminate anarchy in Protected Areas, eliminate illegal exploitation of natural resources, control land clearing for use, and illegal cutting down of the forests;

  - Finding resources, support and financing for solving climate change issues.

- It was noted that a new NSDP 2014-2018 is being drafted (May 2014) and will focus on:

  - Sustainable management of natural resources.

  - Intensifying efforts to reduce the impact of climate change by strengthening the adaptation capacity and resiliency to climate change, particularly by implementing the "Cambodia Climate Change Strategic Plan 2014-2023", “National Policy on Green Growth” and the “National Strategic Plan on Green Growth 2013-2030”.

  - Continuing to strengthen the technical and institutional capacity to promote the mainstreaming of climate change responses into policies, laws and plans at the national and sub-national levels.

  - Continuing to introduce measures to control the environment and ecosystems

National Biodiversity Strategic and Action Plan (NBSAP) – 2002

- The National Biodiversity Strategy and Action Plan (NBSAP), which was approved in July 2002,  represents the national policy on biodiversity conservation and sustainable use including certain cross-cutting issues. It was developed through a participatory process involving input and extensive consultation with various line ministries, research institutions, local governments and NGOs in addressing international obligations as required by the CBD and its COP decisions.

- The vision of this action plan is an "equitable economic prosperity and improved quality of life through sustainable use, protection and management of biological resources”. The plan has three strategic goals:

  - Maintaining biological diversity and productivity of ecological systems by protecting the various species of living organisms in their natural and manmade environments, especially forests, aquatic ecosystems, wetlands and agricultural land.

  - Managing human activities and utilizing biological resources in a way that preserves for the long term the basic natural resources, which are necessary for human livelihood and development.

  - Ensuring that the benefits coming from the sustainable use of biological resources contribute to poverty reduction and improve quality of life for all Cambodians.

- The NBSAP consists of 98 priority actions covering 17 different themes in order to use and conserve biological resources in a sustainable manner. These priority actions can be grouped in three broad categories: (i) actions promoting awareness and capacity building of government staff and local communities for biodiversity conservation and sustainable use of biological resources; (ii) actions promoting the implementation of community-based natural resource management; and (iii) actions aimed at clarifying ministerial jurisdictions, reducing responsibility overlap and promoting inter-ministerial coordination and collaboration in a sustainable development perspective.

National Strategic Plan on Green Growth – 2013-2030

- The vision of this strategic plan is to develop a sustainable economy, together with environmental, social and cultural sustainability for poverty alleviation. Its objective is to promote a national economy with growth stability, reduction and prevention of environmental pollution, safe ecosystem, poverty reduction, and promotion of public health service, educational quality, natural resources management, and sustainable land use and water resources management to increase energy efficiency, ensuring food safety and glorify the national culture.

- It provides orientation to relevant ministries/institutions, authorities at subnational levels, private sector, civil society and stakeholders for efficiency of green growth with balance among economy, environment, society and culture, aiming at poverty eradication nationwide. This key strategy relies on duty fulfillment of relevant institutions with support, participation and close cooperation from all concerned parties, including the public, the private sectors, civil society and the general public.

- This National Strategic Plan on Green Growth 2013-2030 focuses on several strategic directions:

  - Green Investment and Green Jobs Creation;

  - Green Economy Management in balance with Environment;

  - Blue Economy Development with Sustainability;

  - Green Environment and Natural Resources Management;

  - Human Resources Development and Green Education;

  - Effective Green technology Management;

  - Promotion of a Green Social Safety System;

  - Uphold and Protection of Green Cultural Heritage and National Identity;

  - Good Governance on Green Growth

Cambodia Climate Change Strategic Plan – 2014-2023

- The CCCSP was developed following the guidelines of the Council of Ministers. The vision of this strategic plan is for Cambodia to develop towards a green, low-carbon, climate-resilient, equitable, sustainable and knowledge-based society. The plan is to create a national framework for engaging the public, the private sector, civil society organizations and development partners in a participatory process for responding to climate change to support sustainable development. It has three goals that are aligned with national goals and priorities:

  - Reducing vulnerability to climate change impacts of people, in particular the most vulnerable, and critical systems (natural and societal);

  - Shifting towards a green development path by promoting low-carbon development and technologies;

  - Promoting public awareness and participation in climate change response actions

- According to the Climate Change Vulnerability Mapping for Southeast Asia, Cambodia is among the most vulnerable country to climate change in this region because of low adaptive capacity. Through the analysis conducted for this mapping, several points in matters related to this project were highlighted. Interest in knowledge and information related to climate change was identified as a strength. However, weak knowledge and science-based decision making; lack of clear procedure for integration of climate change in the national development plans; limited capacity of the national institutions responsible for climate change and limited participation of stakeholders; outdated information to address climate impacts; and limited knowledge, research and technology were identified as weaknesses. Finally, the establishment of national knowledge and information structure was identified as an opportunity.

- Among the planned actions, several are related to this project. It includes the review of the institutional arrangements and the development of a national M&E framework, including the provision of information to fulfill the UNFCCC reporting obligations.

Other Policies related to the environment

- In addition to these key policies in Cambodia, the government also developed/formulated national sectoral strategies and plans; it includes:

  - National Protected Area System Strategic Management Framework (2014);

  - National Forest Programme (2010-2029);

  - Strategic Planning Framework for Fisheries (2010-2019);

  - National Adaptation Plan of Action (NAPA) to Climate Change (2006);

  - National Action Program to Combat Land Degradation (2011-2020) (Draft pending for approval);

  - Strategy for Agriculture and Water;

  - Strategic Agriculture Development Plan (2006-2010);

  - National Action Plan for Coral Reef and Seagrass Management in Cambodia (2006-2015);

  - Strategic Plan on Management of Mercury in Artisanal and Small Scale Gold Mining.

Brief Overview of the Legislative Framework

- On the legislation side, Cambodia is equipped with an environmental legislative framework that includes:

  - Law on Environmental Protection and Natural Resources Management (1996);

  - Land Law (2001);

  - Law on Mineral Resource Management and Exploitation (2001);

  - Law on Water Resources Management (2007);

  - Law on Fisheries (2006);

  - Forestry Law (2002);

  - Law on Protected Areas (2008);

  - Law on Biosafety (2008);

  - Law on Pesticide and Chemical Fertilizer Control (2011);

  - Law on Water Resources Management (2007);

  - Law on Crop Seed Management and Rights of Plant Breeders (2008);

  - Royal Decree on the Protection of Natural Areas (1993);

  - Royal Decree on the Establishment and Management of the Tonle Sap Biosphere Reserve (2001);

  - Sub-Decree on Environmental Impact Assessment (1999);

  - Sub-Decree on Solid Waste Management (1999);

  - Sub-Decree on Water Pollution Control (1999);

  - Sub-Decree on Air Pollution and Noise Disturbance Control (2000);

  - Sub-Decree on the Management of Ozone Depleting Substances (2005);

  - Sub-Decree on State Land Management (2005);

  - Sub-Decree on Economic Land Concessions (2005), amended 2009;

  - Sub-Decree on Community Fisheries (2007);

  - Sub-Decree on Forest Concession Management (2000);

  - Sub-Decree on Community Forestry Management (2003);

  - Sub-Decree on Procedures for Establishment Classification and Registration of Permanent Forest Estate (2005);

  - Sub-Decree on the Establishment of the Protected Forest for Biodiversity Conservation, Elephant Corridor; and,

  - Sub-Decree on Timber and Non-Timber Forest Products Allowed for Export and Import (2006);

### B.2.d	Institutional Context

- The key government ministries and agencies that play a critical role in addressing environmental management include:

- The Ministry of Environment (MOE) is the national environment authority in Cambodia. It was established in 1993 and it is responsible for environmental protection and natural resource management in the country.

- The Ministry of Agriculture, Forestry and Fisheries (MAFF) has an extensive network of staff at the national, provincial, district and commune levels. The Forestry Administration (FA) has the mandate for the management of Protected and Community Forests. Given this broad mandate, there is substantial overlap with MOE in the perception of functions and responsibilities. It is noteworthy that the 2006-2010 Strategic Agriculture Development Plan formulated by this Ministry does not take climate change adaptation or mitigation into account.

- The Ministry of Women Affairs (MOWA) is responsible for leading and managing activities concerning empowering and promotion of women in all social aspects, in particular gender equality.

- The Ministry of Water Resources and Meteorology (MOWRAM) has the responsibility of observing and managing all activities related to water resources and meteorology development and natural disasters.

- The Ministry of Land Management, Urban Planning and Construction is responsible for the formulation of development plans and land use plans at the national and sub-national levels.

- The Ministry of Mines and Energy is responsible for leading and managing mine and energy including oil, gas and electricity.

- The Ministry of Industry and Handicraft is responsible for leading and managing the industry and handicrafts sectors in Cambodia.

- The Ministry of Public Works and Transportation is responsible for the construction of roads and infrastructure such as bridges and ports.

- The Ministry of Rural Development is responsible for: i) supplying small-scale water supply infrastructure to households; ii) primary health care; and iii) small-scale infrastructure in the rural areas in Cambodia.

- The Ministry of Health is responsible for the development of the health sector for better health and well-being of Cambodians and thus contributes to poverty alleviation and socioeconomic development. The Health Strategic Plan (2008-2015) of the MOH does not consider climate change impacts.

- The Ministry of Tourism aims to preserve the scenic beauty and natural resources of Cambodia.

- The National Committee for Disaster Management, which was established in 1995, is an inter-ministerial body chaired by the Prime Minister. The members of the committee are drawn from all concerned ministries and the armed forces. NCDM plays a key role in disaster management, working both on disaster risk reduction/prevention and response preparedness.

- The Council for the Development of Cambodia (CDC) is the principle contact between the government and all donor countries, organizations and NGOs working in Cambodia. This Council was established by the “Law on Foreign Investment in the Kingdom of Cambodia” of 1994. This law made the CDC the highest decision-making level of the government for private and public sector investment. It is chaired by the Prime Minister and composed of senior ministers from related government agencies. It is also the government entity responsible for the development of the NSDP.

- The APSARA Authority is responsible for directing the management and tourism development, concerning the zoning and management of Siem Reap/Angkor. It also acts, with the Ministries concerned, as an umbrella organization over the establishments responsible for the administration and the management of the region of Siem Reap province.

- The Tonle Sap Authority is in charge of facilitation and coordination in management, conservation and development of Tonle Sap Lake. This authority is under direct management of the Royal Government of Cambodia.

- The Mekong River Commission, which was established in 1995, is responsible for sustainable management and development of water and related resources in the Mekong river. This commission works with concerned governmental agencies and the regional partners along the river.

- Additionally, to ensure a more effective and successful implementation of sustainable development related programmes, the government has established a few cross sectoral national committees, including:

  - National Climate Change Committee (NCCC): it was established in 2006 and chaired by MOE with the Prime Minister as honorary chair. The NCCC serves as a policymaking body (comprising policy-makers from 19 ministries), which coordinates the development and implementation of plans, policies and measures to address climate change risks across Cambodia. Its membership includes only government agencies. As such, the NCCC is the focal point for all climate change-related engagement within Cambodia. A Climate Change Technical Team (CCTT) was established as an inter-ministerial body to provide technical support to the NCCC.

  - Cambodia Climate Change Department (CCCD), Ministry of Environment: it was created in 2003 and serves as a secretariat for the NCCC. The CCCD has the mandate to implement the UNFCCC and Kyoto Protocol by creating an enabling environment for effective climate change mitigation and adaptation.

  - National Biodiversity Steering Committee (NBSC): The Inter-ministerial Biodiversity Steering Committee and a National Secretariat for Biodiversity have been established on April 3, 2001 to coordinate the implementation of the NBSAP, including monitoring, reviewing and reporting as well as providing recommendations for NBSAP revision.

  - National Green Growth Council (NGGC): it was established in October 2012 and it is chaired by MOE and the Prime Minister is the honorary Chair. This Council ensures coordination between different arms of government and it can also help remove constraints on investments to green projects and result in a better chance of success and increased green growth opportunities. It is noted that in the context of its institutional strengthening programme, the government plans to review its committee and council structure and may merge the NCCC with the NGGC and possibly other committees into the Sustainable Development Council.

- In addition to government entities, civil society groups and organizations have also an instrumental role and responsibilities in environmental management in Cambodia; particularly in enhancing involvement of local communities. According to a government study on aid effectiveness conducted in 2010, NGOs provide or manage almost a quarter of all aid that is delivered to Cambodia with the greater share of this aid distributed at the sub-national level. This study identified about 450 local NGOs and 316 international NGOs; however, other estimates put the total number of NGOs operating in Cambodia at over 3,000. The top three sectors in which these NGOs implement programmes are respectively agriculture, health and education; given that over a third of NGO disbursements are used to implement public health programmes. According to this same study, it was noted that the funding of NGO activities in “Environment and Conservation” in Cambodia is relatively low. It was estimated at about USD 7M for the period 2008-2009 over a total of over USD 203M, that is about 3.4%.

- Nevertheless, there are NGOs intervening in the management and conservation of the environment in Cambodia. Some of the key ones include:

  - Fauna & Flora International (FFI): It is an international conservation innovator that continues to make a lasting impact on global biodiversity – the variety of life on Earth. It has built strong relationships with the government of Cambodia over the past 13 years. FFI assists the national authorities in building up their institutional capacity and in developing environmental policies and legislation. FFI’s field activities focus on community engagement and empowerment, law enforcement, bio-monitoring and research related to biodiversity.

  - IUCN: The IUCN Cambodia project office is part of the Southeast Asia Group under the umbrella of the global IUCN. Occasional technical support to the country programme is provided through regional and international experts based in various IUCN offices, e.g. in ARO, Bangkok and in IUCN headquarters in Switzerland. IUCN Cambodia focuses on three core program themes: (1) Protected Areas; (2) Governance; and (3) Sustainable Financing.

  - WWF: It was established in Cambodia in 1995. As a part of the WWF Greater Mekong Programme, WWF-Cambodia is one of 4 country offices coordinating conservation efforts across Indochina, including Thailand, Cambodia, Lao PDR and Vietnam. Its mission in Cambodia is to ensure that there will be strong participation and support from all people to conserve the country’s rich biological diversity, while enhancing local livelihoods and contributing to poverty reduction in Cambodia.

  - Conservation International (CI): Building upon a strong foundation of science, partnership and field demonstration, CI empowers societies to responsibly and sustainably care for nature, our global biodiversity, for the well-being of humanity. Since 2008, CI has been working to ensure that Tonle Sap Lake and its floodplain remain a healthy freshwater ecosystem able to support Cambodia’s people, wildlife and economy.

  - Live and Learn: Live & Learn supports communities across the Asia-Pacific region to overcome the many challenges they face, whether that is violence against women, deforestation, limited incomes and savings, or other constraints. Vulnerability to natural disasters is posing an ever-increasing risk to communities and it recently became a focus for the Live & Learn network to strengthen community resilience.

  - Birdlife: BirdLife International in Indochina seeks to promote the conservation of habitats, sites and species by working with government and non-government partners to: (i) Provide support for improved planning and management of important habitats, sites and species; (ii) Introduce and advocate new ideas for integrating biodiversity conservation into planning and policy; (iii) Stimulate greater public interest in birds and biodiversity, and awareness of the need for biodiversity conservation; (iv) Develop capacity for improved management of habitat, sites and species; and (v) Provide information on biodiversity and protected areas to planners, policy makers and other interest groups.

  - WCS: The Wildlife Conservation Society, founded in 1895, has the clear mission to save wildlife and wild places across the globe. Their story began in the early 1900’s when they successfully helped the American bison recover on the Western Plains. Today, they protect many of the world’s iconic creatures in the US and abroad, including gorillas in the Congo, tigers in India, wolverines in the Yellowstone Rockies, and ocean giants in the world’s amazing seascapes. WCS has been working alongside the Cambodian government since the late 1990s to conserve the unique ecosystem of the Tonle Sap lake and floodplain, WCS currently supports two conservation projects that are protecting key species in the lake's flooded forest and greater floodplain.

  - Wildlife Alliance: Wildlife Alliance’s comprehensive approach to environmental conservation is to work directly with habitats and communities to protect, preserve, and provide. Wildlife Alliance’s focus is on direct action on the ground and direct access to the people actually performing the everyday tasks, to preserve habitats, conserve the environment, and alleviate poverty. It uses a comprehensive holistic approach to combat the drivers of environmental destruction in the tropical belt. Its forest programs tackle forest degradation and diminishing biodiversity in the wild; its community programs empower local people towards sustainable practices and incomes; its wildlife programs protect and care for endangered and trafficked animals; its education programs help bolster its conservation work in the long term; its advocacy programs coordinate its efforts with policy and decision makers both nationally and internationally.

  - ERECON: The Institute of Environment Rehabilitation and Conservation - called ERECON - is a non-profit international organization established in April 2000. ERECON aims to contribute to the sustainable use of natural resources in Asian countries. Therefore the organization pursues the environment rehabilitation and conservation as well as the environmental education for the harmony between agriculture and urban development and the natural environment.

  - RECOFTC: The Center for People and Forests is an international organization with a vision of local communities actively managing forests in Asia and the Pacific to ensure optimal social, economic, and environmental benefits. Its strategy is a pro-poor approach to building capacity for community forestry in Asia and the Pacific.

  - The NGO Forum on Cambodia: It is a membership organization that builds NGO cooperation and capacity, supporting NGO networks and other civil society organizations to engage in policy dialogue, debate and advocacy.  It was established in the early 1980s by international NGOs and has had full Cambodian leadership since 2006. It focuses on development issues, land and livelihood and environment. In this sector, the NGO Forum intervenes in climate change awareness, alternative energy, agriculture and forestry.

- The project will be executed by MOE. It will benefit from the key role of MOE in environmental management in Cambodia. It will provide a necessary communication and coordination mechanism for implementing project activities.

### B.2.e	Barriers to Achieving Global Environmental Objectives

- As described in Section B.2.a, Cambodia assessed its own capacities and capacity development needs to address the requirements of the three conventions through the NCSA. It focused on issues and concerns within its jurisdiction to address Cambodia’s obligations under the three conventions. It was a national assessment of Cambodian capacities undertaken by the government of Cambodia and done by Cambodians. The assessment was cross-cutting across the three Rio Conventions (climate change, biodiversity and land degradation) and was conducted at 3 levels: i) systemic capacity, or creation of an “enabling environment” – the overall policy, economic, regulatory and accountability frameworks within which institutions and individuals operate and the relationships between institutions, both formal and informal; ii) institutional (or organizational) capacity – the overall organizational performance and functioning capabilities or organizations as well as their abilities to adapt to change; and iii) individual capacity – the process of changing attitudes and behaviors, usually through imparting knowledge and developing skills through training (learning by doing, participating, owning, being motivated, accountable, responsible, and managing better).

- This extensive assessment identified thematic environmental issues. These thematic issues were then reviewed together across the three thematic areas and crosscutting capacity constraints were identified as well as ways to address these constraints and effectively promote linkages and synergies across the conventions and meet their respective requirements obligated by the Parties.

- Thematically, the assessment identified the following environmental issues:

Climate change

  - Altered patterns of rainfall and monsoons and sea level rise can affect coastal fisheries and farming in Cambodia;

  - Sea level rise can lead to increased salt water intrusion into inland water tables and this can affect the freshwater supply (and farming practices) in the country;

  - Climate change can alter drought regimes and is expected to lead to more frequent and more severe weather events and to the resurgence of certain pests and diseases. These put Cambodian agriculture, food security, economy and society at risk and vulnerable to serious harm.

Land degradation

  - Land degradation can have major economic, social and political impacts in Cambodia where 80% of the population is dependent on agriculture for income and subsistence;

  - Land degradation is most severe in coastal areas and in the border with Vietnam. Kampong Speu is experiencing widespread loss of soil fertility;

  - Siem Reap has widening sandy soils;

  - Svay Rieng is experiencing acidic soil while in Kampot the soil is increasingly becoming saline.

Biodiversity conservation

  - Cambodia’s losing its unique and valuable genetic pool, many of which are found in this general area of mainland Southeast Asia and nowhere else in the world (e.g., the Kouprey (Bos Sauveli, java rhinoceros, Siamese crocodile);

  - Cambodia’s forests are unique in that they are among the last remaining fringes of the dipterocarp forest biome in Asia. Forest covers still remained more than 11 million ha (61% in 2003);

  - The genetic resources of the country, spread across over 3.3 M ha of protected areas nationwide, could prove valuable in a world that is just now expanding its biotechnological industries for agriculture, pharmaceuticals, and veterinary products.

- In addition to these thematic environmental issues, the cross-cutting analysis identified five cross-cutting capacity issues; they included:

  - The capacity to develop and execute strategies to engage different sectors on addressing environmental issues in all levels of government in the country; this involves mustering a nationwide effort to arrest environmental degradation and to improve the quality of the environment;

  - The capacity to stabilize population fluxes in all areas of the country; this includes widening livelihood opportunities for the poor to stabilize migration and mobility rates across Cambodia; this includes as well intensifying efforts to deliver reproductive health services to vulnerable mothers and infants in order to stabilize the fertility and mortality rates among the poor;

  - The capacity to develop clear procedures, systems and tools on forming environmental policies and on selecting natural resources management strategies; this includes generating and updating data and information on environmental systems and on sharing them with different users and decision makers.

  - The capacity to stimulate the build-up of local capital and investments (e.g., venture capital, endowment funds, securities) to support environmental initiatives and resource regeneration in the country;

  - The capacity to procure support to build up the 4 preceding capacities.

- These crosscutting capacity issues are the justification of this project. These issues are common barriers to the management of all environmental areas in Cambodia at both national and sub-national levels. The project will particularly address the management of environmental information and the access and use of this information for improving policy and decision-making; it will, therefore, focus more on the third issue but also will contribute to improve the barriers under issues #1 and #4.

# C.	Programme and policy conformity

## C.1	GEF Programme Designation and Conformity

- The GEF strategy for Cross-Cutting Capacity Development (CCCD) projects serves to provide resources for reducing, if not eliminating, the institutional bottlenecks and barriers to the synergistic implementation of the Rio Conventions.  This particular project is in line with the GEF-5 CCCD Programme Frameworks two (2) and four (4), which calls for countries (2) to generate, access and use information and knowledge and (4). It is also aligned with the fist objective of GEF6 that is to integrate global environmental needs into management information systems (MIS). Through a learning-by-doing process, this project will harmonize existing information systems, and integrate internationally accepted measurement standards and methodologies, as well as consistent reporting on the global environment. It will target the development of capacities at the individual and organizational level, strengthening technical skills to manage data and transform this information into knowledge. The project will also support activities to strengthen the coordination between key sectors to address biodiversity, climate change and land degradation issues at systemic and institutional levels.

- The project has two outcomes that are (1) to improve access and generation of information related to the three Rio Conventions; and (2) to improve the use of information and knowledge related to the Rio Conventions. The project will develop skills and knowledge of staff at MOE and MAFF to research, acquire, organize and store environmental information. Through the provision of better environmental information, the project will also increase the capacity of national and sub-national levels’ stakeholders and counterparts to diagnose and understand complex dynamic nature of global environmental problems and develop local solutions. Through workshops and training activities, the project will raise the awareness of decision-makers on environmental matters and the need for strengthening the environmental governance system in place in Cambodia.

- The project will also enhance the mechanisms within MOE and the skills of the staff and key stakeholders to improve the use of this environmental information/knowledge. As a result, it is expected that the staff within MOE and key stakeholders will have a greater capacity to assess the state of the environment and report the implementation status of the Rio Conventions in Cambodia as well as participating to international dialogues in these areas.

- At the same time, the project will not support the financing of national campaign for raising environmental awareness and the financing of environmental education activities. The project will focus on the harmonization of environmental information management systems in Cambodia and the use of this knowledge for better policy- and decision-making related to the management of the environment.

- As part of the GEF CCCD programme, it does not lend itself readily to programme indicators, such as improving the estimation of greenhouse gas emissions, reducing the percentage of people to the impact of climate change, or percentage increase of protected areas containing endangered endemic species.  Instead, CCCD projects are measured by output, process, and performance indicators that are proxies to the framework indicators of improved capacities for the global environment.  To this end, CCCD projects – this one included - look to strengthen crosscutting capacities in the five major areas of stakeholder engagement, information and knowledge, policy and legislation development, management and implementation, and monitoring and evaluation. In order to help GEF funded projects to monitor the development of capacities in the environment, UNDP, UNEP and GEF developed a scorecard to measure the development of capacities.  It is a tool that attempts to quantify a qualitative process of capacity change through the use of appropriate indicators and their corresponding ratings. This tool is recommended to be used at three stages in a project life: design, mid-term and at end of project life. This scorecard was completed for this project at this stage (design) to establish a baseline (see Annex 1).

- As detailed in the Results Framework presented in Annex 2, a set of indicators was identified to measure progress against the objective and outcomes. The results of the scorecard discussed in the previous paragraph are one indicator used to measure progress at the objective level. Two other indicators were identified at this level, mostly measuring the quality of the products delivered with the support of the project. A total of 11 indicators were identified to measure progress at the objective and outcomes level. For each indicator, a baseline was set as well as a target at the end of the project.

- This project is a response to the national capacity self-assessment (NCSA) conducted in Cambodia during the period 2005-2006. It will address some of key priority actions such as better use of environmental information in decision-making and policy-making, better coordination, mainstreaming environmental management into national policies, plans and programmes and development of the national negotiation capacities to advance Cambodian national interest on environmental matters in international fora. By improving the access to environmental information, the project should also contribute in addressing the need for Cambodia to better report to the international Conventions.

- This project will implement capacity development activities through an adaptive collaborative management approach to engage stakeholders as collaborators in the design and implementation of project activities that take into account unintended consequences arising from policy interventions.

- The project is also consistent with the programmatic objectives of the three GEF thematic focal areas of biodiversity, climate change and land degradation, the achievement and sustainability of which is dependent on the critical development of capacities (individual, organizational and systemic).  The implementation of this project will leverage individual, institutional and systemic capacities to improving environment knowledge and information generation, management and sharing at the national and sub-national levels with all key environment stakeholders. As a result, Cambodia will have a greater capacity to manage and use environmental information/knowledge for better decision-making related to the environment; and also to improve the quality of national reports to MEAs.

- Through the successful implementation of this project, the 11 operational principles of capacity development identified in the GEF Strategic Approach to Capacity Building will be implemented in Cambodia. Table 1 below summarizes the project's conformity with these operational principles.

Table 1:  Conformity with GEF Capacity Development Operational Principles

| Capacity Development Operational Principle | Project Conformity |
| --- | --- |
| Ensure national ownership and leadership | Climate change impacts on the environment and more generally on the agriculture and biodiversity-based livelihoods of people in Cambodia is becoming a key priority for the government and also for donors. Better environmental knowledge is necessary for stakeholders to address key environmental issues. The timing of this project is excellent; it comes at a time when national leaders are looking for support in these areas. Hence, the project enjoys already a good national ownership with an excellent leadership from the ICBD/GDANCP-MOE. |
| Ensure multi-stakeholder consultations and decision-making | The project will use multi-stakeholder and expert consultative reviews or analyses towards the harmonization of environmental information and the use of this knowledge. Project implementation will take an adaptive collaborative management approach, which includes stakeholder representatives in the project decision-making structures. As described in section B.2.d, many institutions will be involved in the project. Through a project steering committee and the technical team established under this project, stakeholders at the national and sub-national levels will be engaged and consulted to oversee the implementation of the project. |
| Base capacity building efforts in self-needs assessment | The findings from the NCSA include the need to improve the capacity to develop clear procedures, systems and tools on forming environmental policies and on selecting natural resources management strategies. It includes the need for generating and updating data and information on environmental systems and on sharing them with different users and decision makers. Finally, it also includes the capacity to develop and execute strategies to engage different sectors on addressing environmental issues. The project is designed in such a way that it will support capacity development activities to address these needs. |
| Adopt a holistic approach to capacity building | The overall approach of the project to develop capacities will be holistic. It will proceed based on a review of crosscutting capacity gaps and then it will address these gaps at all levels: individual, institutional and systemic level. Necessary training will be provided, mechanisms within institutions and across institutions will be reviewed and improved as necessary and finally the enabling environment will also be reviewed to ensure it provides adequate policy and legislation frameworks to support the project achievements. |
| Integrate capacity building in wider sustainable development efforts | As a result of strengthening the process of harmonizing environmental information and better using this knowledge by decision-makers, environmental matters will be better integrated in national sustainable development. The capacity development approach of the project will contribute to mainstreaming these project supported capacity development activities within the sustainable development agenda of Cambodia. |
| Promote partnerships | By its very nature – focusing on the Rio Conventions that are under the responsibility of two ministries (MOE and MAFF) - this project requires collaboration and coordination among Cambodia’s government ministries and agencies and also among civil society organizations as well as local and indigenous communities. Partnering with all stakeholders will be a critical success factor of the project and will be promoted as needed. |
| Accommodate the dynamic nature of capacity building | The project's management arrangements include a multi-disciplinary and multi-sectorial steering committee and a technical support team (members drawn from the broad based steering committee) to guide and oversee the implementation of the project. Members will be drawn from key public and civil society sectors. Additionally, the management team will use adaptive management as a management tool to provide flexibility in the implementation of the project. It is well recognized that this type of projects needs to be flexible and to adapt as needed when national context/realities change. This project will be implemented with the recognition that capacity development is a dynamic process. |
| Adopt a learning-by-doing approach | The core of project’s capacity development activities is via a learning-by-doing approach. Government representatives and other stakeholders will be involved in the collaborative review, analysis for the formulation of recommendations for the various sectoral analyses and the implementation of project activities. |
| Combine programmatic and project-based approaches | This project takes a bottom-up and top-down approach to Rio Convention mainstreaming. This project effectively began with the NCSA, which was a bottom-up approach to develop a National Capacity Development Strategy. Using the Rio Convention provisions as the analytic framework for the sectoral analyses, recommendations were made to harmonize environmental information management systems and improve the use of this knowledge in Cambodia, as key area to strengthen environmental management in the country and which by extension would provide global environmental benefits. The project is part of a government programme to improve environmental management – including environmental governance - in Cambodia. |
| Combine process as well as product-based approaches | The project strategy is to support a change to reach two main expected results; environmental management information systems in Cambodia that are better harmonized and this environmental knowledge that is better used by any people who are in need and decision-makers. These two results will be the main products that will be developed with the support of the project. In order to achieve these results, most activities that will be supported by the project will be process-based but they will also be combined with the delivery of products such as databases, environmental information management systems, training syllabuses, etc. |
| Promote regional approaches | The project will partner with related on-going and upcoming GEF projects implemented at national level, including regional projects and project achievements will be disseminated in the region through various existing regional networks. |

### C.1.a	Guidance from the Rio Conventions

- Cambodia is fully committed to meet its obligations under the MEAs that it is a Party to. Among these obligations, there are capacity development needs that are required for Parties to be able to implement the Rio Conventions nationally and contribute to global environmental benefits. A summary of these capacity development requirements is presented in the table below.

- The proposed project is intended to facilitate an important step towards developing the capacities for an effective national environmental management framework by focusing on developing the national capacity to harmonize environmental information management systems in Cambodia and also to improve the use of this environmental knowledge by decision-makers. It will address several shared obligations under the three Rio Conventions, which call for countries to strengthen their national capacities for effective national environmental management systems. It will particularly address a set of Rio Convention articles that call for improving information management and knowledge and improving environmental governance to address global environmental issues (see second and third types of capacity in table below).

Table 2:  Capacity Development Requirements of the Rio Conventions

| Type of Capacity | Convention Requirements | UNFCCC | UNCBD | UNCCD |
| --- | --- | --- | --- | --- |
| Stakeholder Engagement | Capacities of relevant individuals and organizations (resource users, owners, consumers, community and political leaders, private and public sector managers and experts) to engage proactively and constructively with one another to manage a global environmental issue. | Article 4 Article 6 | Article 10 Article 13 | Article 5 Article 9 Article 10 Article 19 |
| Information Management and Knowledge | Capacities of individuals and organizations to research, acquire, communicate, educate and make use of pertinent information to be able to diagnose and understand global environmental problems and potential solutions. | Article 4 Article 5 Article 6 | Article 12 Article 14 Article 17 Article 26 | Article 9 Article 10 Article 16 |
| Environmental Governance | Capacities of individuals and organizations to enact environmental policies or regulatory decisions, as well as plan and execute relevant sustainable global environmental management actions and solutions. | Article 4 | Article 6 Article 14 Article 19 Article 22 | Article 4 Article 5 Article 8 Article 9 Article 10 |
| Organizational Capacities | Capacities of individuals and organizations to plan and develop effective environmental policy and legislation, related strategies, and plans based on informed decision-making processes for global environmental management. | Article 4 Article 6 | Article 8 Article 9 Article 16 Article 17 | Article 4 Article 5 Article 13 Article 17 Article 18 Article 19 |
| Monitoring and Evaluation | Capacities in individuals and organizations to effectively monitor and evaluate project and/or programme achievements against expected results and to provide feedback for learning, adaptive management and suggesting adjustments to the course of action if necessary to conserve and preserve the global environment. | Article 6 | Article 7 |  |

- As a project focusing on crosscutting issues, the implementation process will also contribute to the development of other capacities in addition to the environmental information management and use of this knowledge. The project will contribute to improve stakeholder engagement through a participative approach to implement the project; will provide better information to policy-makers; and use this knowledge to better report to international environmental agreements. As per the table above, this project will contribute to the development of these five types of capacities and increase the capacity of Cambodia in meeting its obligations under the MEAs that it is a Party to.

## C.2  Project Design

### C.2.a	GEF Alternative

#### C.2.a.1	Project Rationale

- This project takes an incremental approach from a GEF construct towards strengthening Cambodia’s environmental information management and knowledge to meet Rio Convention objectives.  In the absence of this project, the necessary capacity building to address the environment data needs of GDANCP-MOE will remain an outstanding need at the national level. It would prevent Cambodia to achieve global environmental benefits through better environmental information and knowledge. Government staff would remain insufficiently equipped and knowledgeable about how to harmonize environmental management information systems and how to use it for better practices and decision-making. More generally, they would also remain insufficiently knowledgeable to fully understand the implications of global environmental directives under the conferences of the parties on national environmental and development policies, and how these directives can be strategically implemented and supported through existing national information systems.

- From an external funding point of view, the objectives pursued by the current project alternative will not be attained in the baseline at this point in time. The baseline (status quo) would prevent Cambodia to achieve global environmental benefits through better environmental knowledge, which by extension should improve the environmental management framework in Cambodia such as better coordination, better decision and ultimately better policies; and no other projects will address these issues. Other current funded activities funded by the GEF and other donors are more thematically focused on the implementation of a particular convention such as the national communication for UNFCCC or the support to prepare the national biodiversity strategy and action plan for the UNCBD or the strengthening of protected areas in Cambodia. Most of these projects are not fully addressing cross-sectoral issues (also called horizontal issues) such as environmental governance, stakeholder engagement and monitoring the implementation of Rio Conventions.

- Cambodia would continue to govern its environment through the existing environmental knowledge base with mixed results.  While these results would still provide some global environmental benefits, they would do so at a lower level and at a higher transaction cost than through the proposed GEF Alternative. The main barriers to meeting and sustaining global environmental outcomes in Cambodia are described in section B.2.e.

- Addressing these horizontal issues need reforming procedures and protocols, developing an enabling environment, and developing capacity of institutions and staff to perform their revised expected duties. The government has limited resources and has currently other top priorities such as battling with socio-economic development to ensure a minimum level of human livelihood of its people. Support of an international partner such as GEF to undertake this major reform in a timely fashion is needed.

- Under the GEF Alternative, the GEF resources will allow Cambodia to address this long outstanding environmental information need within GDANCP-MOE. This GEF support is crucial to assist the government of Cambodia in this important area at the country level.  Barriers identified through the NCSA process will be thoroughly re-assessed and effective and efficient solutions to address those related to the availability of environmental information will be detailed and implemented with the support of the project. Overall, the expected outcomes of this project rely in its innovative and transformative approach to mainstream the Rio Conventions obligations within the existing national environmental governance framework. This project will test the assumption that by harmonizing the environmental management information systems, better environmental knowledge will be available to decision-makers in Cambodia and by extension will provide a better enabling environment, which in turn will deliver greater global environmental achievements.

- It is the government of Cambodia’s intent to harmonize its environmental management information systems, which is a perfect opportunity/entry point to mainstream global environment issues in the national development framework through better environmental information, hence for GEF to step in and complement the baseline. The allocation of the GEF increment and the government co-financing of project activities, demonstrate the proposed partnership. It will complement the baseline and strengthen the implementation of the Rio Conventions in Cambodia. The project will improve Cambodia’s environmental information base and the use of this knowledge for decision-making.

- Considering the issues rose during the NCSA process, the nature of this project is the logical way to go forward and address these main issues.  A limited coordination capacity and a limited access to environmental knowledge are critical barriers to good environmental management and good environmental decision-making in Cambodia.  The NCSA process included consultations with a broad group of stakeholders whom participated actively.  The results pointed to the need for harmonizing environmental management information systems and the need to better use this environmental knowledge.  It was viewed as critical barriers for a better holistic environmental management approach in the country and also to address the global environmental management commitments made by Cambodia.

- The expected global environmental results of the current project proposal is that Cambodia’s decision-making process to meet Rio Convention objectives will be greatly improved by having access to more complete, relevant and updated environmental knowledge. The project will be implemented through the participation of stakeholders in environmental information management and the sustainability of project achievements will be greatly enhanced by the strong support of key stakeholder groups and their representatives at the appropriate government level.

#### C.2.a.2	Project Goal and Objectives

- In order to address the issues presented above, a project has been designed over a period of 3 years in consultation with key stakeholders. A set of expected results has been identified (see the Project Results Framework in Annex 2) and is described below.  This project will address the critical need to provide better environmental knowledge in Cambodia. This is a timely response to address this priority, particularly when considering the emerging issues due to global climate change. The provision of better environmental knowledge will be useful for stakeholders to identify responses to threats including negative impacts of global climate change on the local environment, which is the basis of livelihoods, human health and economy in Cambodia. It will also contribute to the broader institutional strengthening initiative of MOE, currently underway.

- Every effort will be made to incorporate gender issues in the implementation of this project. Roles of men and women to participate in activities of the project will be equally assigned without any discrimination. The project will take steps to ensure that women account for at least 40% of all training and capacity building in the project. Moreover, the project will strengthen data management – gender segregation of data collection and data management will be introduced as a basis for ensuring long-term gender benefits.

- The goal of this project is to improve the implementation of the Rio Conventions in Cambodia through the development of national capacities to better coordinate and generate better information related to the implementation of these Conventions. The proposed project will develop crosscutting capacity to respond to the needs of the three conventions; particularly the reporting requirements. During the project implementation, the coordination and information generation capacities of the focal points established by the government will be enhanced. For example, improved access and generation of information will help to fill the data and information gaps required to guide planning and implementation of activities that yield global environmental benefits as exemplified in low-emission and climate resiliency e.g. REDD+ while at the same time sets out to meet the objectives under all three Rio Conventions through improved decision making.

- The project’s objective is to improve access to environmental information related to the Rio Conventions through the harmonization of existing environmental management information systems and improving coordination of the implementation of these conventions in Cambodia.  The harmonization of these existing systems will be translated into better access to information related to the implementation of the Rio Conventions in Cambodia. As a result, the project will lead to both direct and indirect global benefits. It will include the decision-making process to meet Rio Convention objectives, which will be greatly improved by having better access to more complete and relevant information.

- It will also include innovation to set up a network of enhanced information exchange, dialogue and cooperation between the state agencies and other civil society stakeholders. With the greatly improved information generated and accessible, this will provide the basis for better monitoring the implementation of the Rio Conventions in Cambodia, and be an input into planning and design of other development activities across the country. Improved management of forest under the REDD+, for example, will provide global environmental benefits in lowering greenhouse gas emission levels.

#### C.2.a.3	Expected Outcomes and Outputs

- The expected achievements of this project are a set of improved capacities to meet and sustain Rio Convention objectives. This project will have strengthened and helped institutionalize commitments under the Rio Conventions by harmonizing the existing national environmental management information systems, by improving the use of this environmental knowledge for better decision-making and by improving the coordination of the implementation of the Rio Conventions in Cambodia. It will also strengthen the capacity of Cambodia to report on the MEAs implementation in Cambodia. The Strategic Results Framework on which the intervention logic is based is outlined in Annex 2 of this project document. This Framework also outlines the indicators, sources of verification and risks and assumptions pertaining to the project objective and outcomes.

- The implementation of the project will achieve two expected outcomes:

  - Improved access and generation of information related to the three Rio Conventions;

  - Improved use of information and knowledge related to the Rio Conventions.

Outcome 1: 	Improved access and generation of information related to the three Rio Conventions.

- Under this outcome, the project will support the development of national capacities to effectively and efficiently standardize environmental information that is generated on the implementation of the Rio Conventions in Cambodia, and give open-access to this information. In parallel to this, the project will support the strengthening of Cambodia’s capacity to better engage stakeholders and better coordinate the implementation of the Rio Conventions in the country. The GEF support will support activities to achieve the following expected outputs:

Output 1.1:	A harmonized information management system covering the three Rio Conventions

- The project will support activities to inventory, assess and develop solutions to harmonize existing environmental management information systems monitoring the implementation of the Rio Conventions in Cambodia. Solutions will include the development of data needs, data collection and storage protocols, reporting formats, data storage mechanisms, data access mechanisms and tools to manage, process and give data access. It will include the review of monitoring indicators. The main aim under this output is to bring together and provide an easy access to information on the implementation of the three Conventions in Cambodia.

Main Activities:

1.1.1:	Conduct an inventory of existing environmental management information systems in Cambodia. This inventory will provide critical information on what kind of information systems exist in the environmental area, who owns/manages it, what is their use, etc.

1.1.2:	Assess these systems to identify overlaps and gaps to address Rio Conventions reporting obligations.

1.1.3:	 Identify solutions (options?) to harmonize these systems and provide open-access to this information on the implementation of Rio Conventions in Cambodia.

1.1.4:	Decide on the most appropriate solution(s) to be implemented to effectively standardize environmental information systems in Cambodia.

1.1.5:	 Implement solution(s) to increase harmonization of these environmental management information systems and give open-access.

Output 1.2:	A common clearinghouse mechanism for the three Rio Conventions

- The project will support the development of a clearinghouse mechanism. The vision is a single point of access giving open-access to all data, reports, research, plans and documents available on the implementation of the Rio Conventions in Cambodia. All stakeholders including government agencies, development partners, CSOs and academia will be able to post documents and data into the clearinghouse mechanism. It will have a bilingual (Khmer, English) referencing system if applicable; given that the Khmer language is a must. In addition, the project will support under this output the implementation of an information sharing/exchange mechanism such as the existing exchange “LaoFAB” in Laos.

Main Activities:

1.2.1:	Identify options for the development of a clearinghouse mechanism.

1.2.2:	Select the most appropriate solution(s) to develop an environmental information clearinghouse mechanism for Cambodia.

1.2.3:	Implement the selected environmental information clearinghouse mechanism.

1.2.4:	Identify and develop an information sharing/exchange mechanism for stakeholders to communicate and exchange information related to the implementation of the Rio Conventions in Cambodia.

Output 1.3:	Existing stakeholder platforms strengthened in order to increase stakeholder engagement in Convention related dialogues

- The existing coordination platforms in place in Cambodia focus mostly on one sector or on one Convention such as the Climate Change Technical Team. Under the current MOE institutional reform the government will establish the Sustainable Development Council, which will oversee the climate change and biodiversity areas. Under this output, a mechanism to support the future platform established by the government to bring stakeholders working on climate change, biodiversity and land degradation will be developed and implemented. Representatives from selected civil society organizations (CSOs) – including partners from the GEF UNDP Small Grant Programme (SGP) - will be invited to join this crosscutting platform.

Main Activities:

1.3.1:	Review existing operational coordination platforms in areas related to the implementation of the Rio Conventions in Cambodia.

1.3.2:	Support future crosscutting platform for dialogues on climate change, biodiversity and land degradation built on existing operational coordination platforms.

1.3.3:	Formalize this crosscutting platform through Ministry/Cabinet approval.

1.3.4:	Raise awareness of Stakeholders on MEAs obligations throughout the project lifetime for mainstreaming MEA obligations in the national development framework in Cambodia.

Output 1.4:	Strengthened coordination between key sectors to address biodiversity, climate change and land degradation issues at systemic and institutional levels

- The project will support activities with stakeholders involved in the implementation of the Rio Conventions to develop a single inter-sectoral, inter-agency coordination mechanism. It will build-up on the three existing Convention committees to develop a single Rio Convention coordination mechanism. Project resources will also be used to develop the mandate and terms of reference of this coordination mechanism as well as developing the capacity of the members involved in this mechanism; particularly focusing on the capacity to meet the Conventions reporting and negotiating requirements.

Main Activities:

1.4.1:	Review existing coordination mechanisms in areas related to the implementation of the Rio Conventions.

1.4.2:	Support a mechanism to address inter-sectorial coordination issues built on existing instruments such as national committees, working groups, etc.

1.4.3:	Formalize this inter-sectorial coordination mechanism through Cabinet approval.

1.4.4:	Raise awareness of Decision-Makers on MEAs obligations throughout the project lifetime for mainstreaming MEA obligations in the national development framework in Cambodia.

Outcome 2:	Improved use of information and knowledge related to the Rio Conventions.

- Under this second outcome project resources will be used to improve the use of environmental information for the development of innovative tools supporting decision-making processes related to the implementation of the Rio Conventions. Project support will also include activities to develop the capacity in using this environmental knowledge of national institutions involved in international negotiations at Conventions COPs as well as using this knowledge to produce national reports meeting Conventions reporting obligations.

Output 2.1:	Innovative tools piloted for decision-making using the economic valuation of the use of natural resources

- Building on ongoing work in Cambodia in environmental economic valuation, and using the improved environmental knowledge and the better coordination of activities related to the implementation of the Rio Conventions achieved under outcome 1, this output will pilot how economic valuation of global benefits/costs can feed into decision-making, and thereby help justify and validate investments in implementing the Rio Conventions in Cambodia. The process will demonstrate that placing monetary values on environmental impacts is an essential element in incorporating the benefits of costs of environmental effects into the analysis of alternatives. In this way, the wider array of benefits and costs associated with a project can be considered in deciding which alternative produces the largest net benefit to society.

- The pilot may take place in one Province, ready for up-scaling and replication across the country, or may possibly cover one sub-sector; the final decision will be taken during the implementation of the project.

Main Activities:

2.1.1:	Review ongoing work on environmental economic valuation, including review of local and international best practices.

2.1.2:	Design the pilot to demonstrate the environmental economic valuation, including the scope (geographical and focal area) and the set of activities to be conducted in the pilot.

2.1.3:	Implement the pilot.

2.1.4:	Assess the results obtained by the pilot and identify scale-up activities in Cambodia.

Output 2.2:	Strengthened capacity of existing national implementing institutions on negotiation skills and national preparatory process for COPs, SBSTTA, Ad-Hoc meetings, and other related meetings for the Rio conventions

- The Ministry of Environment (MOE) is implementing the two Rio conventions: UNFCCC and UNCBD, while the Ministry of Agriculture, Forestry, and Fisheries (MAFF) is in charge of implementing UNCCD. The project will support activities to develop the capacity of these institutions to prepare Conference of Parties (COPs) of MEAs; including the capacity to negotiate at these COPs, Ad-Hoc meetings and other related meetings to these Conventions. The capacity development activities under this output will promote the environmental knowledge improved under outcome 1 and also will use the decision-making tools piloted under output 2.1.

Main Activities:

2.2.1:	Review obligations from MEAs that Cambodia is a Party to and how these obligations are being implemented in Cambodia.

2.2.2:	Assess institutional mechanisms in place to implement MEAs in Cambodia, including monitoring their implementation and reporting.

2.2.3:	Design a training programme on MEAs, their global processes (COPs and other technical meetings), and the main issues being negotiated.

2.2.4:	Deliver training activities to staff in institutions mandated to implement MEAs to develop their capacity to actively prepare and participate in these international MEA gatherings; including the capacity to negotiate Cambodia’s position on MEA matters.

Output 2.3:	A unified reporting process on the implementation status of the three Rio Conventions

- Using the environmental knowledge and the open-access to this knowledge and the improved national coordination and dialogue mechanisms supported by project activities under outcome 1, the project will support the establishment of a reporting system that will deliver timely reports on the status of the implementation of the three Rio Conventions in Cambodia as per the MEA reporting obligations. As much as possible, these reports will be consolidated into one report meeting the reporting requirements of each Convention.

Main Activities:

2.3.1:	Review MEAs reporting requirements that Cambodia is a Party to.

2.3.2:	Design a unified reporting mechanism for all Conventions using the improved environmental knowledge achieved under outcome 1.

2.3.3:	Implement/formalize this reporting mechanism within the mandated institutions.

2.3.4:	Design and deliver training to staff involved in the new reporting mechanism.

2.3.5:	Produce the first national report under this new reporting mechanism.

## C.3	Sustainability and Replicability

### C.3.a	Sustainability

- The project will build mainly upon institutional structures and systems existing in Cambodia and strongly anchored at ICBD/GDANCP-MOE. The project will develop capacities and establish systems that enhance environmental knowledge, access and sharing this knowledge and improve national coordination, which are critical elements to allow national institutional mechanisms to continue to operate after the project is completed.

- A strong focus on building knowledge and generating information as well as a strong focus on stakeholder engagement in environmental management is expected to lead to social sustainability. The sustainability of the project will be greatly enhanced by the strong support from the government and representatives and champions from key stakeholder groups. The local development benefits of the environmental goods and services are critical incentives for sustainability.

- Through better access to environmental information/knowledge and better coordination of the implementation of the Rio conventions in Cambodia, the project will help overcome environmental degradation and contribute to global environmental benefits over the long term. Additionally, the project implementation team will also make every effort to be inclusive, including involving a large number of women in its activities. As much as possible, training activities will include an equal number of men and women. When harmonizing the environmental management information systems and developing a better coordination approach, the project will ensure that collecting data will be gender disaggregated and that reporting environment information will also be gender disaggregated. This approach will facilitate a focus on gender-based environmental issues and gender-based solutions.

- The nature, implementation strategy and the approach of the project are such that sustainability of project achievements should be ensured over the long-term. It includes several features that are forming the sustainability strategy of the project:

- The project will build upon existing strategies and programmes of the government.  The need for better environmental information was identified as a national priority through the NCSA process. The project is a full response to this priority and will be part of the proposed actions to address the environmental information needs. The project will also be part of the institutional strengthening process that is underway at MOE; it will become part of the ministry strategy to strengthen its operations. It is an excellent opportunity, which will translate into an institutionalization of project achievements as the project is being implemented; hence contributing to the long-term sustainability of project achievements.

- The project will be implemented by the ICBD/GDANCP-MOE itself; therefore, facilitating the institutionalization of project achievements. GDANCP was established by a Royal Decree in 2008; it is responsible for assisting the MOE with managing Protected Areas (PA) in Cambodia and for developing and implementing the Protected Areas Strategic Management Plan. GDANCP also has the responsibility to attend international environmental conventions and to develop - in collaboration with relevant agencies - national strategies, action plans, policies and legal instruments related to protected areas. Its role is also to promote research, education, dissemination of information, training and awareness raising. Finally, the department is also mandated to collaborate with national, regional and global agencies, development partners, civil society, and private sector related to biodiversity.  One of the foci of the project is to develop the capacity of GDANCP to provide more accurate and timely comprehensive information on the state of the environment in Cambodia. It is expected that results will be automatically institutionalized along the implementation of the project; therefore, contributing to the long-term sustainability of project’s achievements.

- The approach to implement the project will be as much as possible holistic; that is to focus on developing the overall capacity of GDANCP to be able to provide to the public and decision makers better environmental information/knowledge. Capacity development activities will be implemented through an adaptive collaborative management approach to engage stakeholders as collaborators in the design and implementation of project activities that take into account environmental information needs.

- In addition to a focus on the main agency of the government, the project will also include other agencies involved in sectoral environmental areas such as climate change, land degradation, forestry, environmental health, etc. The overall approach to develop this capacity will be holistic. It will proceed based on a review of capacity gaps and then will address these gaps at all levels: individual, institutional and systemic level. Necessary training will be provided, mechanisms within institutions and across institutions will be reviewed and improved as necessary and finally the enabling environment will also be reviewed to ensure it provides adequate policy and legislation frameworks for these two systems to work. This approach will ensure that staff at GDANCP and in other relevant agencies/ministries will have the necessary skills and knowledge needed to sustain project achievements but also that the mechanisms and procedures in these organizations are adequate to support these achievements over the long-term within a policy and legislation environment that are supportive of these results.

- Another important feature of this project’s strategy to sustain its achievements is the learn-by-doing approach.  Each project activity will seek the active participation of key stakeholders that are involved in the process that will be addressed by the project. This participation will lead to a calibration of activities towards user-friendliness of existing and new information instruments, which will contribute to the rapid uptake of these information instruments in the policy making and reporting processes. The rationale being that government and other stakeholders responsible for environmental planning, decision-making, monitoring and enforcement are the stakeholders that need more accurate and timely environmental information. Having a government agency to execute this project directly also builds capacities for the implementation of appropriate project activities, and will contribute to the institutionalization of results.  It is assumed that mistakes will occur and implementation will not always be smooth, but these problems should still be seen as opportunities for learning better practices.

- Sustainability will also be strengthened by the project’s attention to resource mobilization.  Notwithstanding a high level of commitment, championship, and strong baseline, the sustainability of project outcomes will require a certain amount of new and additional resources that is currently not available outside of the project’s construct, which is why this project is being supporting through an external grant.  The mobilization of project resources will explore the kind of resources needed to sustain project outcomes, and identify realistic sources from both the government of Cambodia, and through official development assistance as appropriate.

- Finally, the project will support the development of capacities and will harmonize environmental management information systems. These capacities and these systems will be institutionalized and should continue to operate after the project is completed. They will be used to (i) ensure coordinated and effective environmental data/information management; and (ii) mainstream the global environment into national decision-making in Cambodia. The training, the information, the awareness, the demand-oriented nature of these systems will all contribute to ensuring that project outputs are sustainable.

### C.3.b	Replicability and Lessons Learned

- The project will directly address national priorities that were identified through the NCSA process; it is not about piloting or demonstrating a new approach or a new system. The need for better environmental information is a priority capacity need for Cambodia to improve the implementation of the Rio Conventions in the country. Therefore, the project will support the development of a public good that will be used by the public and in particular by decision-makers and policy-makers. It will address an issue that has been clearly identified and that needs to be addressed.

- As discussed in the previous section, project’s achievements should be sustained after the project end, as it is a national need. With the support of the project, Cambodia should have access to more accurate and timely environmental information and a better coordination mechanism for the implementation of the Rio Conventions.

- Nevertheless, as a medium-size project, this intervention will also have certain limitations such as the capacity of the project to develop skills and knowledge of all actors involved in environmental management nationally. This project will serve as a catalyst of a longer-term approach to Rio Convention implementation by improving the generation and access to timely environmental knowledge and by strengthening the coordination of activities related to the implementation of the Rio Conventions.

- It is anticipated that the project will provide resources to transfer knowledge such as dissemination of lessons, training workshops, information exchange, national forums, etc., ensuring that the body of knowledge developed with the support of the project will be available to other stakeholders in Cambodia. As a result, it should contribute to its sustainability but also its up-scaling at the local level, closer to communities benefiting from a healthy environment. At the same time, the project should also benefit from lessons learned in the region but also in other parts of the world, particularly when the project will focus on economic valuation of the environment in Cambodia.

- Two main areas of the project will particularly need up-scaling/replicability: the use of economic valuation tools for better decision-making throughout the country and better coordination of actions in climate change, biodiversity and land degradation areas also throughout Cambodia.

- In the former area, the project will support the piloting of innovative tools for decision-making using the economic valuation of the use of natural resources. This is a good first step but the project intervention will mostly act as a catalyst in this innovative area and in order to ensure the long term sustainability of this initiative, up-scaling and replicability throughout government operations will be needed in the future.

- In the second area, a better coordination mechanism will be supported by the project at the national level. As a result, more coordinated actions should ensue to address crosscutting environmental issues. However, this approach will also need to be developed at the sub-national level in Cambodia through the regional and local levels of government, including the non-governmental partners intervening at the sub-national level.

- Part of the catalytic role of the project will be to demonstrate the value of its achievements. Therefore, it will also be important that the project prepares a timely exit. An exit strategy will be prepared 6 months before the end of the project to detail the withdrawal of the project and provide a set of recommendations to the government to ensure the long-term sustainability and the up-scaling of project achievements to other parts of Cambodia.

### C.3.c	Risks and Assumptions

- For each expected results at the objective, outcomes and outputs levels, risks and assumptions were identified (see Annex 2) during the preparation of this project. There are presented below:

Table 3:  Stakeholders Anticipated Roles in Implementing the Project

| Risks | Level | Assumptions |
| --- | --- | --- |
| - Political will to provide GDANCP with the necessary resources to sustain project achievements. - New information is not used and stays stored in computers at MOE and MAFF | Low | - MOE will support GDANCP and provide it with necessary resources - Better environmental information is readily available and actively utilized and used |
| - Communications and national reports are not submitted on time | Medium | - Communications and national reports are submitted on time and include information from the harmonized systems. |
| - Project activities and resources do not translate in increasing the capacity of GDANCP and MAFF to provide better environmental information. | Low | - The project is effective in developing the capacity in the area of environmental information management. |
| - Lack of relevant expertise in local market may result in delay of required outputs and distortion of targeted deadlines. | Low | - Implementation of project activities and recruitment of relevant national expertise is monitored and actions will be identified if the lack of expertise is affecting the timely implementation of the project. |
| - Government unwilling to give open-access to environmental information. | Low | - MOE will support GDANCP and provide it with necessary resources to develop this mechanism and give public open-access. |
| - No interest from Stakeholders to increase crosscutting dialogues on the implementation of the Rio Conventions. | Low | - All Stakeholders involved in implementing the Rio Conventions in Cambodia are demanding for greater exchange of environmental information and to better engage in crosscutting dialogues. |
| - Political - delays due to ministerial reforms. - Operational - Irregular frequency of meetings for relevant bodies, unclear approval mechanism for an inter-sectorial coordination body, unwillingness to participate in the inter-sectorial coordination body. | Low | - Supporting mechanism is in-place. |
| - No interest from decision-makers to use economic valuation as a tool to support decision-making. | Medium | - The benefit of using better economic valuation will encourage decision-makers to use it. |
| - The government does not fulfill its international obligations; including those from the 3 Rio Conventions. | Low | - The government continues to fulfill its international commitments. |

- The review of these risks indicates that these risks are manageable through the project’s learn-by-doing approach. This proposed project is a direct response to national priorities identified through the NCSA process; as a result, there is a strong government ownership and willingness to succeed, hence low risks that key stakeholders will not participate in the project and lack of political will.

- The fact that the project will also be housed at ICBD/GDANCP-MOE will contribute to managing any operational risks. The project will be tightly integrated to the operation of the Department, ensuring that project activities will be implemented in close collaboration with MOE but also other related ministries and agencies. It will also contribute to a better prospect for long-term sustainability of project results.

- Notwithstanding, this also assumes that project activities will be successful, and that the commitment to implement project activities through adaptive collaborative management remains intact. To this end, staff needs and motivation will be important considerations to reduce the risk of high staff turnover.  The project will help minimize this risk by instituting a training programme to better understand and apply global environmental issues into national environmental management.

## C.4	Stakeholder Involvement

- This project was developed on the basis of consultations with stakeholder representatives, most of whom will benefit directly from this project.  A team of three consultants (one international and two national consultants) was recruited during the PPG phase of this project to consult with key stakeholder representatives, to review the institutional set up as well as the policy and legislation frameworks related to this project and to consolidate this information in the current project document.

- An inception workshop to kick-start the PPG phase was organized on January 24, 2014. This workshop invited a broad range of stakeholders with the participation of 120 people from relevant institutions and organizations in order to identify potential cooperation and partnerships for the development of this project. The process to develop the project was presented at the workshop as well as an overview of the implementation status of the three Rio Conventions in Cambodia.

- As a result of the project development phase (PPG), key project stakeholders were identified and consulted. Taking an adaptive and collaborative management approach to execution, the project will ensure that key stakeholders will be involved early and throughout project execution as partners for development.  This includes their participation in the Project Board, review of project outputs such as recommendations for endorsing a set of environmental indicators, protocols to collect environmental data, institutional mechanisms to collect, share and exchange data, etc., as well as participation in monitoring activities.

- A key feature of this project is its learn-by-doing approach, which is intended to actively engage stakeholders.  This approach should result in key stakeholders that will be more likely to validate the analysis and legitimize the recommendations. It is also intended to catalyze the institutionalization of knowledge and experiences, which is critical for ensuring sustainability.

- Given the project strategy, the key project stakeholders are government ministries and their subsidiary agencies and departments that are mandated with the management of natural resources. These stakeholder representatives will participate in activities to better monitor the environment and provide more accurate and timely environmental information; including fulfilling Cambodia’s reporting obligations under the MEAs that it is a Party to. In addition to these governmental stakeholders, there are also non-governmental stakeholders, including civil society organizations.  These non-state organizations will also be invited in project activities to share their comparative expertise, but also to undertake selected project activities.  Their participation will be determined during project implementation when defining annual work plans.

- The table below indicates the role of key stakeholders for implementing the project.

Table 4:  Stakeholders Anticipated Roles in Implementing the Project

| Stakeholder | Anticipated role in the Project |
| --- | --- |
| Department of International Conventions and Biodiversity (ICBD) of the Ministry of Environment (MOE) in charge of the Convention on Biological Diversity (CBD) | - Implement project in close cooperation and support from relevant institutions, local authorities and communities and development partners; - Make relevant policies’ advices to GOC based on the technical outcomes of this project (produce policy relevant information based on the outcomes of this project implementation at national level) - Facilitate and coordinate technical inputs and support from other public, private and civil society sectors - Provide the technical support required to implement the project at all levels of society - Ensure alignment of the project outcomes to all MEAs to which this project supports, at the MEA level, in accordance to national priority needs - Undertake and spearhead the communication, education and public awareness on the role of this project and its relevant linkages and alignment to what GOC is also doing in other sectors, on related areas |
| Department of Climate Change of Ministry of Environment (MOE) in charge of the United Nations Framework Convention on Climate Change (UNFCCC) | - Support ICBD/GDANCP in providing the necessary and relevant coordination that may be required - Make relevant policies’ advices to MOE based on the technical outcomes of this project (produce policy relevant information based on the outcomes of this project implementation at national level) - Provide the technical support required to implement the project - Ensure alignment of the project outcomes to UNSCC to which this project supports in accordance to national priority needs |
| Department of International Cooperation of Ministry of Agriculture, Forestry and Fisheries in charge of the United Nations Convention to Combat Desertification (UNCCD)) | - Support ICBD/GDANCP in providing the necessary and relevant coordination that may be required - Make relevant policies’ advices to MOE based on the technical outcomes of this project (produce policy relevant information based on the outcomes of this project implementation at national level) - Provide the technical support required to implement the project - Ensure alignment of the project outcomes to UNCCD to which this project supports in accordance to national priority needs |
| Ministry of Women's Affairs (MOWA) | - Provide technical inputs and supports necessary and relevant from the perspective of gender equality and outreach activities - Provide advice and guide linkages to any existing gender policy through the project’s implementation |
| The Ministry of Water Resources and Meteorology (MoWRAM) | - Provide technical inputs and supports necessary and relevant from the water resources and meteorology development and natural disasters. - Provide advice and guide linkages to any existing water resources through the project’s implementation |
| The Ministry of Land Management, Urban Planning and Construction (MLMUPC) | - Provide technical inputs and supports necessary and relevant from the land use planning. - Provide advice and guide linkages to any existing land use management to be set up through the project’s implementation |
| The National Committee for Disaster Management (NCDM) | - Provide technical inputs and supports necessary from the relevant disaster management. - Provide advice and guide linkages to any existing disaster management to be set up through the project’s implementation. |
| The Ministry of Mines and Energy (MME) | - Provide technical inputs and supports necessary and relevant from the water use and hydropower. - Provide advice and guide linkages to any existing water and energy resources to be set up through the project’s implementation |
| The Ministry of Public Works and Transportation (MPWT) | - Provide technical inputs and supports necessary and relevant from the MCIC - Provide advice and guide linkages to any existing marine resources database to the EMIS to be set up through the project’s implementation |
| The Ministry of Rural Development (MRD) | - Provide technical inputs and supports necessary and relevant from the water supply, health care and infrastructure development. - Provide advice and guide linkages to any existing rural development to be set up through the project’s implementation |
| The Ministry of Health (MoH) | - Provide technical inputs and supports necessary and relevant from the health sector. - Provide advice and guide linkages to any existing health development in Cambodia to be set up through the project’s implementation |
| The Ministry of Tourism (MoT) | - Provide technical inputs and supports necessary and relevant from the tourism and ecotourism management and development. - Provide technical inputs and supports necessary from the scenic beauty and natural resources of Cambodia to be set up through the project’s implementation |
| The Council for the Development of Cambodia (CDC) | - Provide technical inputs and supports necessary and relevant from the principle contact between the royal government of Cambodia and all donor, and NGOs. |
| Donors (UNDP, ADB, USAID,..) | - Provide technical inputs and assistance necessary and relevant from the relevant implementing regulations. |
| Local & International NGOs | - Provide technical inputs and supports necessary and relevant from the relevant NGOs relevant portfolio and core functions/purposes. - Provide advice and guide linkages to any existing natural resources database to be set up through the project’s implementation. |

## C.5	Monitoring and Evaluation

- Project monitoring and evaluation will be conducted in accordance with established UNDP and GEF procedures.  The project team – based at GDANCP-MOE and the Cambodia UNDP Country Office (UNDP-CO) will undertake monitoring and evaluation activities, with support from UNDP-GEF, including independent evaluators for the mid-term and final evaluation. The project results framework matrix in Annex 2 provides a logical structure for monitoring project performance and delivery using SMART indicators during project implementation. The output budget and the work plan in the project document provide additional information for the allocation of funds, both the GEF and co-financing, for expected project deliverables and the timing of project activities to produce these deliverables. Annex 3 provides a breakdown of the total GEF budget by outcome, project management costs, and allocated disbursements on a per year basis. A GEF tracking tool for CCCD will be used as part of monitoring and evaluation activities to assess project delivery (see Annex 1).  The work plan is provisional, and is to be reviewed during the project inception phase and endorsed by the project board.

- The following sections outline the principle components of monitoring and evaluation.  The project’s monitoring and evaluation approach will be discussed during the project’s inception phase so as to fine-tune indicators and means of verification, as well as an explanation and full definition of project staff M&E responsibilities.

- A project Inception workshop will be conducted with the full project team, relevant government counterparts, co-financing partners, the UNDP-CO, with representation from the UNDP-GEF Regional Coordinating Unit as appropriate.  Non-governmental stakeholders should be represented at this workshop as well.

- A fundamental objective of this inception workshop will be to further instill and understanding and ownership of the project’s goals and objectives among the project team, government and other stakeholder groups.  The workshop will also serve to finalize preparation of the project’s first annual work plan on the basis of the project’s results framework matrix.  This will include reviewing the results framework (indicators, means of verification, assumptions), imparting additional detail as needed, and on the basis of this exercise, finalize the Annual Work Plan (AWP) with precise and measurable performance (process and output) indicators, and in a manner consistent with the expected outcomes for the project.

- The project inception phase, during the first two months of start-up, will begin with an induction training to: (i) introduce project staff to the UNDP-GEF expanded team that will support the project during its implementation, namely the UNDP-CO and responsible Project Management Unit  (PMU) staff; (ii) detail the roles, support services and complementary responsibilities of UNDP-CO and PMU staff with respect to the project team; (iii) provide a detailed overview of UNDP-GEF reporting and monitoring and evaluation (M&E) requirements, with particular emphasis on the combined Annual Project Reports - Project Implementation Reviews (APR/PIRs), Project Board (PB) meetings, as well as final evaluation.  The inception phase will also provide an opportunity to inform the project team on UNDP project-related budgetary planning, budget reviews, and mandatory budget re-phasing.

- The project inception workshop will be held at the end of the inception phase to provide an opportunity for all stakeholders to validate the project results framework and discuss the project’s work plan. As well, the workshop will provide an opportunity for stakeholders to agree on their roles, functions, and responsibilities within the project’s decision-making structures, including reporting and communication lines, and conflict resolution mechanisms.  The Terms of Reference for PMU staff and associated decision-making structures will be discussed again, as needed, in order to clarify for all, each party’s responsibilities during the project’s implementation phase.

- The inception workshop will present a schedule of M&E-related meetings and reports.  The Project Coordinator in consultation with UNDP will develop this schedule, and will include: (i) tentative time frames for PB meetings, and the timing of near-term project activities, such as the in-depth review of literature on natural resource valuation; and (ii) project-related monitoring and evaluation activities.  The provisional work plan will be approved in the first meeting of the PB.

- A project inception report will be prepared immediately following the inception workshop.  This report will include a detailed First Year Work Plan divided in quarterly time-frames as well as detailed activities and performance indicators that will guide project implementation (over the course of the first year).  This Work Plan will include the proposed dates for any visits and/or support missions from the UNDP-CO, the UNDP-GEF Regional Coordinating Unit, or consultants, as well as time-frames for meetings of the project decision-making structures (e.g., PB).  The report will also include the detailed project budget for the first full year of implementation, prepared on the basis of the Annual Work Plan, and including any monitoring and evaluation requirements to effectively measure project performance during the targeted 12 months’ time-frame.

- The inception report will include a more detailed narrative on the institutional roles, responsibilities, coordinating actions and feedback mechanisms of project related partners.  In addition, a section will be included on progress to date on project establishment and start-up activities and an update of any changed external conditions that may affect project implementation, including any unforeseen or newly arisen constraints.  When finalized, the report will be circulated to project counterparts who will be given a period of one calendar month in that to respond with comments or queries.

- Day-to-day monitoring of implementation progress will be the responsibility of the Project Coordinator based on the project’s Annual Work Plan and its indicators.  The Project Coordinator will inform the UNDP-CO of any delays or difficulties faced during implementation so that the appropriate support or corrective measures can be adopted in a timely and remedial fashion.

- The Project Coordinator will fine-tune outputs, main activities and performance indicators in consultation with the full project team at the inception workshop, with support from UNDP-CO and assisted by the UNDP-GEF.  Specific targets for the first year implementation performance indicators, together with their means of verification, will be reviewed at the inception workshop.  These will be used to assess whether implementation is proceeding at the intended pace and in the right direction and will form part of the Annual Work Plan.  Targets and indicators for subsequent years would be defined annually as part of the internal evaluation and planning processes undertaken by the Project Team, and agreed with the PB.

- Periodic monitoring of implementation progress will be undertaken by the UNDP-CO through monitoring discussions and site visits based on quarterly narrative and financial reports from the Project Coordinator. These quarterly progress reports will be prepared following guidelines provided by the UNDP-CO and UNDP-GEF RCU; they are short reports outlining the main updates in project performance.

- Furthermore, specific meetings may be scheduled between the PMU, the UNDP-CO and other pertinent stakeholders as deemed appropriate and relevant (particularly the PB members).  Such meetings will allow parties to take stock and to troubleshoot any problems pertaining to the project in a timely fashion to ensure smooth implementation of project activities.

- Annual Monitoring will occur through the Annual Project Board meeting.  This is the highest policy-level meeting of the parties directly involved in the implementation of a project.  The project will be subject to PB meetings at least twice per year.  The first such meeting will be held within the first twelve months following the initiation workshop.  For each year-end meeting of the PB, the Project Coordinator will prepare harmonized Annual Project Report / Project Implementation Reviews (APR/PIR) and submit it to UNDP-CO, the UNDP-GEF Regional Coordination Unit, and all PB members at least two weeks prior to the meeting for review and comments.

- The APR/PIR will be used as one of the basic documents for discussions in the PB year-end meeting.  The Project Coordinator will present the APR/PIR to the PB members, highlighting policy issues and recommendations for the decision of the Committee participants.  The Project Coordinator will also inform the participants of any agreement(s) reached by stakeholders during the APR/PIR preparation, on how to resolve operational issues.  Separate reviews of each project output may also be conducted, as necessary.  Details regarding the requirements and conduct of the APR and PB meetings are contained with the M&E Information Kit available through UNDP-GEF.

- The combined Annual Project Report (APR) and Project Implementation Review (PIR) is a UNDP requirement and part of UNDP-CO central oversight, monitoring and project management.  As a self-assessment report by project management to the CO, the APR/PIR is a key input to the year-end Project Board meetings.  The PIR is an annual monitoring process mandated by the GEF.  It has become an essential management and monitoring tool for project managers and offers the main vehicle for extracting lessons from on-going projects.  These two reporting requirements are very similar in input, purpose and timing that they have now been amalgamated into a single APR/PIR Report.

- An APR/PIR is to be prepared on an annual basis by June, but well in advance (at least one month) in order to be considered at the PB meeting.  The purpose of the APR/PIR is to reflect progress achieved in meeting the project’s Annual Work Plan and assess performance of the project in contributing to intended outcomes through outputs and partnership work.  The APR/PIR is discussed by the PB, so that the resultant report represents a document that has been agreed upon by all of the key stakeholders.

- A standard format/template for the APR/PIR is provided by UNDP-GEF.  This includes, but is not limited to the following:

- Progress made toward project objective and project outcomes - each with indicators, baseline data and end-of-project targets (cumulative)

- Project outputs delivered per project outcome (annual).

- Lesson learned/good practice.

- AWP and other expenditure reports

- Risk and adaptive management

- ATLAS QPR

- Portfolio level indicators (i.e. GEF focal area tracking tools) are used by most focal areas on an annual basis as well.

- UNDP will analyze the individual APR/PIRs by focal area, theme and region for common issues/results and lessons.  The APR/PIRs are also valuable for the independent evaluators who can utilize them to identify any changes in the project’s structure, indicators, work plan, among others, and view a past history of delivery and assessment.

- A mid-term review may be conducted if needed at the mid-point of the implementation of the project to review the progress of the project and provide recommendations for the remaining implementation phase, including recommendations for ensuring a smooth exit and maximize the sustainability of project achievements.

- An independent final evaluation will take place three months prior to the terminal tripartite review meeting, and will focus on: a) the cost-effectiveness, efficiency and timeliness of project implementation and performance; b) highlight issues requiring decisions and actions; and c) present initial lessons learned about project design, implementation and management.  Findings of this evaluation will be incorporated as lessons learned, and recommendations for improvement addressed to ensure the institutional sustainability of project outputs, particular for the replication of project activities.  The final evaluation will also look at project outcomes and their sustainability.  The final evaluation should also provide recommendations for follow-up activities, as appropriate.  The terms of reference for the final evaluation will be prepared by the UNDP-CO based on guidance from the UNDP-GEF Regional Coordinating Unit, in consultation with the PB.

- During the last three months of the project, the PMU will prepare the Project Terminal Report.  This comprehensive report will summarize all activities, achievements and outputs of the project, lessons learned, the extent to which objectives have been met, structures and mechanisms implemented, capacities developed, among others.  Together with the independent final evaluation, the project terminal report is one of two definitive statements of the project’s activities during its lifetime.  The project terminal report will also recommend further steps, if necessary, in order to ensure sustainability and replicability of the project outcomes and outputs.

- The terminal review meeting is held by the PB, with invitation to other relevant government stakeholders as necessary, in the last month of project operations.  The Project Coordinator is responsible for preparing the terminal review report and submitting it to UNDP-CO, the UNDP-GEF Regional Coordinating Unit, and all participants of the terminal review meeting.  The terminal review report will be drafted at least one month in advance of the terminal review meeting, in order to allow for timely review and to serve as the basis for discussion.  The terminal review report considers the implementation of the project as a whole, paying particular attention to whether the project has achieved its stated objectives and contributed to the broader environmental objective.  The report also decides whether any actions remain necessary, particularly in relation to the sustainability of project outputs and outcomes, and acts as a vehicle through that lessons learned can be captured to feed into other projects under implementation or formulation.  The terminal review meeting should refer to the independent final evaluation report, conclusions and recommendations as appropriate.

- The UNDP-CO, in consultation with the UNDP-GEF Regional Coordinator and members of the PB, has the authority to suspend disbursement if project performance benchmarks are not met as per delivery rates, and qualitative assessments of achievements of outputs.

- The Project Coordinator, in consultation with and clearance from the Project Director will provide the UNDP Resident Representative with certified periodic financial statements relating to the status of UNDP (including GEF) funds according to the established procedures set out in UNDP’s Programming and Finance manuals. An audit of the financial statements will be conducted by the legally recognized auditor of Cambodia UNDP-CO.

- Learning and knowledge sharing: Results from the project will be disseminated within and beyond the project intervention zone through existing information sharing networks and forums at the national, regional and global levels.

- The project will identify and participate, as relevant and appropriate, in scientific, policy-based and/or any other networks, which may be of benefit to project implementation though lessons learned. The project will identify, analyze, and share lessons learned that might be beneficial in the design and implementation of similar future projects.

- Communications and visibility requirements: Full compliance is required with UNDP’s Branding Guidelines.  These can be accessed at http://intra.undp.org/coa/branding.shtml, and specific guidelines on UNDP logo use can be accessed at: http://intra.undp.org/branding/useOfLogo.html. Amongst other things, these guidelines describe when and how the UNDP logo needs to be used, as well as how the logos of donors to UNDP projects needs to be used.  For the avoidance of any doubt, when logo use is required, the UNDP logo needs to be used alongside the GEF logo.   The GEF logo can be accessed at: http://www.thegef.org/gef/GEF_logo. The UNDP logo can be accessed at http://intra.undp.org/coa/branding.shtml.

- Full compliance is also required with the GEF’s Communication and Visibility Guidelines (the “GEF Guidelines”).  The GEF Guidelines can be accessed at: http://www.thegef.org/gef/sites/thegef.org/files/documents/C.40.08_Branding_the_GEF%20final_0.pdf.  Amongst other things, the GEF Guidelines describe when and how the GEF logo needs to be used in project publications, vehicles, supplies and other project equipment.  The GEF Guidelines also describe other GEF promotional requirements regarding press releases, press conferences, press visits, visits by Government officials, productions and other promotional items.

- Where other agencies and project partners have provided support through co-financing, their branding policies and requirements should be similarly applied.

- Audit on project will follow UNDP Financial Regulations and Rules and applicable Audit policies.

Table 5: Monitoring Work Plan and Budget

| Type of M&E activity | Responsible Parties | Budget US$ Excluding project team staff time | Time frame |
| --- | --- | --- | --- |
| Inception Workshop and Report | - Project Coordinator - UNDP CO, UNDP GEF | Indicative cost: 5,000 | Within first two months of project start up |
| Measurement of Means of Verification of project results. | - UNDP GEF RTA/Project Coordinator will oversee the hiring of specific studies and institutions, and delegate responsibilities to relevant team members. | To be finalized in Inception Phase and Workshop. | Start, mid and end of project (during evaluation cycle) and annually when required. |
| Measurement of Means of Verification for Project Progress on output and implementation | - Oversight by Project Coordinator - Project team | To be determined as part of the Annual Work Plan's preparation. | Annually prior to ARR/PIR and to the definition of annual work plans |
| ARR/PIR | - Project Coordinator and team - UNDP CO - UNDP RTA - UNDP EEG | None | Annually |
| Periodic status/ progress reports | - Project Coordinator and team | None | Quarterly |
| Mid-term Review (if needed) | - Project Coordinator and team - UNDP CO - UNDP RCU - External Consultants (i.e. evaluation team) | Not Required for MSP project but can be undertaken if it is deemed necessary by the Project Board | At the mid-point of project implementation. |
| Final Evaluation | - Project Coordinator and team, - UNDP CO - UNDP RCU - External Consultants (i.e., evaluation team) | Indicative cost: $20,000 | At least three months before the end of project implementation |
| Project Terminal Report | - Project Coordinator and team - UNDP CO - Local consultant | 0 | At least three months before the end of the project |
| Audit | - UNDP CO - Project Coordinator and team | Indicative cost per year: $3,500 | Yearly |
| Visits to field sites | - UNDP CO - UNDP RCU (as appropriate) - Government representatives | For GEF supported projects, paid from IA fees and operational budget | Yearly |
| TOTAL indicative COST Excluding project team staff time and UNDP staff and travel expenses |  | US$ 35,500 (+/- 3.5% of GEF budget) |  |

# D.	Financing

## D.1	Financing Plan

- The financing of this project will be provided by the GEF (US$ 990,000), with co-financing from the Government of Cambodia (US$ 150,000) and UNDP (US$ 1,150,000). The GEF leverage thus represents approximately a 1:1.3 ratio. The allocation of these sources of finances is structured by the two main project components, as described in section C.2.b above.  More detailed financial information is provided in Annex 3. The table below gives a summary of the allocation of the budget per component/outcome.

Table 6:  Project Costs (US$)

| Total Project Budget by Component | GEF ($) | Co-Financing ($) | Project Total ($) |
| --- | --- | --- | --- |
| Component 1 | 470,650 | 600,000 | 1,070,650 |
| Component 2 | 429,350 | 645,000 | 1,074,350 |
| Project Management | 90,000 | 55,000 | 145,000 |
| Total project costs | 990,000 | 1,300,000 | 2,290,000 |

Table 7:  Estimated Project management budget/cost (for the entire project)

| Component (*) | Estimated Staff weeks | GEF ($) | Co-Financing ($) | Project Total ($) |
| --- | --- | --- | --- | --- |
| Locally recruited personnel: Project staff | 156 | 46,800 |  | 46,800 |
| Rental & Maint. of Other Equip |  | 6,000 |  | 6,000 |
| Direct Project Costs |  | 19,000 | 15,000 | 34,000 |
| Office supplies, audits, miscellaneous |  | 15,200 | 40,000 | 55,200 |
| Equipment and Furniture |  | 3,000 |  | 3,000 |
| Total project management cost |  | 90,000 | 55,000 | 145,000 |

*  Local and international consultants in this table are those who are hired for functions related to the management of project.  Please see table below for consultants providing technical assistance for special services.

- An internationally recruited consultant will be contracted to undertake the independent final evaluation towards the end of the project.  The travel budget includes the costs of DSA, TE and return airfare for the international consultant.

- No UNDP Implementing Agency Project cycle management services are being charged to the Project Budget.  All such costs are being charged to the IA fee.  In agreement with the Government of Cambodia, UNDP may provide a few implementation support services (mostly recruitment of international consultants) under the National Implementation Modality; these will be charged to the Project Management Budget. A budget of $34,000 was allocated to these Direct Project Costs (DPCs), including $19,000 that will be funded by the GEF grant and $15,000 through the UNDP cash contribution to the project. Details of such charges are provided in Annex 8.

Table 8: Total GEF Budget and Work Plan

| Award ID: | TBC |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Project ID: | TBC |  |  |  |  |  |  |
| Award Title: | Generating, Accessing and Using Information and Knowledge Related to the Three Rio Conventions |  |  |  |  |  |  |
| Business Unit: | KHM10 |  |  |  |  |  |  |
| Project Title: | Generating, Accessing and Using Information and Knowledge Related to the Three Rio Conventions |  |  |  |  |  |  |
| PIMS No: | 5222 |  |  |  |  |  |  |
| Implementing Partner (Executing Agency): | Ministry of Environment |  |  |  |  |  |  |

| GEF Outcome/Atlas Activity | Responsible Party/ Implementing Agent | Fund ID | Donor Name | Atlas Budgetary Account Code | ATLAS Budget Desbcription | Amount Year 1 (US$) | Amount Year 2 (US$) | Amount Year 3 (US$) | Total (US$) | See Budget Notes |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Component 1: Improved access and generation of information related to the three Rio Conventions | MOE/UNDP | 62000 | GEF | 71200 | International Consultant | 20,000 | 20,000 | 10,000 | 50,000 | 1 |
|  |  |  |  | 71300 | Local Consultant | 42,000 | 42,000 | 37,000 | 121,000 | 2 |
|  |  |  |  | 71400 | Contractual Services - Individuals | 28,550 | 28,550 | 28,550 | 85,650 | 3 |
|  |  |  |  | 71600 | Travel | 10,000 | 10,000 | 10,000 | 30,000 | 4 |
|  |  |  |  | 72200 | Equipment & Furniture | 13,000 | 3,000 | 3,000 | 19,000 | 5 |
|  |  |  |  | 72300 | Material & Goods | 3,600 | 3,600 | 3,600 | 10,800 | 6 |
|  |  |  |  | 72500 | Supplies | 4,600 | 4,600 | 4,100 | 13,300 | 7 |
|  |  |  |  | 72800 | Information Technology Equipment | 10,000 | 10,000 | 5,000 | 25,000 | 8 |
|  |  |  |  | 73300 | Rental & Maint. of Info. Tech. Equip. | 1,000 | 1,000 | 1,000 | 3,000 | 9 |
|  |  |  |  | 73400 | Rental & Maint. of Other Equip. | 2,000 | 3,000 | 3,000 | 8,000 | 10 |
|  |  |  |  | 74500 | Miscellaneous | 6,000 | 5,000 | 4,900 | 15,900 | 11 |
|  |  |  |  | 75700 | Training Workshops and Conferences | 25,000 | 40,000 | 24,000 | 89,000 | 12 |
|  |  |  |  |  | Sub-Total GEF - Outcome 1 | 165,750 | 170,750 | 134,150 | 470,650 |  |
|  |  | 04000 | UNDP | 71200 | International Consultant |  | 9,000 | 9,000 | 18,000 | 13 |
|  |  |  |  | 74500 | Miscellaneous | 400 | 450 | 450 | 1,300 | 14 |
|  |  |  |  |  | Sub-Total UNDP - Outcome 1 | 400 | 9,450 | 9,450 | 19,300 |  |
| Component 2: Improved use of information and knowledge related to the Rio Conventions | MOE/UNDP | 62000 | GEF | 71200 | International Consultant | 40,000 | 5,000 | 5,000 | 50,000 | 15 |
|  |  |  |  | 71300 | Local Consultant | 39,000 | 41,000 | 39,000 | 119,000 | 16 |
|  |  |  |  | 71400 | Contractual Services - Individuals | 28,550 | 28,550 | 28,550 | 85,650 | 17 |
|  |  |  |  | 71600 | Travel | 12,200 | 10,000 | 10,000 | 32,200 | 18 |
|  |  |  |  | 72200 | Equipment & Furniture | 6,000 | 2,000 | 2,000 | 10,000 | 19 |
|  |  |  |  | 72400 | Communication & Audio Visual Equip. | 4,800 | 4,800 | 4,800 | 14,400 | 20 |
|  |  |  |  | 72500 | Supplies | 1,000 | 1,000 | 1,000 | 3,000 | 21 |
|  |  |  |  | 72800 | Information Technology Equipment | 15,000 |  |  | 15,000 | 22 |
|  |  |  |  | 73300 | Rental & Maint. of Info. Tech. Equip. | 300 | 300 | 300 | 900 | 23 |
|  |  |  |  | 73400 | Rental & Maint. of Other Equip. | 2,000 | 2,000 | 2,000 | 6,000 | 24 |
|  |  |  |  | 74500 | Miscellaneous | 1,200 | 1,000 | 1,000 | 3,200 | 25 |
|  |  |  |  | 75700 | Training Workshops and Conferences | 30,000 | 30,000 | 30,000 | 90,000 | 26 |
|  |  |  |  |  | Sub-Total GEF - Outcome 2 | 180,050 | 125,650 | 123,650 | 429,350 |  |
|  |  | 04000 | UNDP | 71200 | International Consultant | 60,000 | 6,500 | 6,500 | 73,000 | 27 |
|  |  |  |  | 74500 | Miscellaneous | 400 | 400 | 400 | 1,200 | 28 |
|  |  |  |  | 75700 | Training Workshops and Conferences | 20,000 | 10,000 | 10,000 | 40,000 | 29 |
|  |  |  |  |  | Sub-Total UNDP - Outcome 2 | 80,400 | 16,900 | 16,900 | 114,200 |  |
| Project Management | MOE/UNDP | 62000 | GEF | 71400 | Contractual Services - Individuals | 15,600 | 15,600 | 15,600 | 46,800 | 30 |
|  |  |  |  | 72200 | Equipment & Furniture | 1,000 | 1,000 | 1,000 | 3,000 | 31 |
|  |  |  |  | 73400 | Rental & Maint. of Other Equip. | 2,000 | 2,000 | 2,000 | 6,000 | 32 |
|  |  |  |  | 72500 | Supplies | 1,000 | 1,000 | 1,000 | 3,000 | 33 |
|  |  |  |  | 74100 | Professional Services | 3,500 | 3,500 | 3,500 | 10,500 | 34 |
|  |  |  |  | 74500 | Miscellaneous | 500 | 600 | 600 | 1,700 | 35 |
|  |  |  |  | 74599 | UNDP Cost-Recovery chrgs-Bills | 5,000 | 7,000 | 7,000 | 19,000 | 36 |
|  |  |  |  |  | Sub-Total GEF - PMC | 28,600 | 30,700 | 30,700 | 90,000 |  |
|  |  | 04000 | UNDP | 74500 | Miscellaneous | 500 | 500 | 500 | 1,500 | 37 |
|  |  |  |  | 74599 | UNDP Cost-Recovery chrgs-Bills | 5,000 | 5,000 | 5,000 | 15,000 | 38 |
|  |  |  |  |  | Sub-Total UNDP - PMC | 5,500 | 5,500 | 5,500 | 16,500 |  |
|  |  |  |  |  | TOTAL PROJECT GEF | 374,400 | 327,100 | 288,500 | 990,000 |  |
|  |  |  |  |  | TOTAL PROJECT UNDP | 86,300 | 31,850 | 31,850 | 150,000 |  |
|  |  |  |  |  | GRAND TOTAL | 460,700 | 358,950 | 320,350 | 1,140,000 |  |

Notes:

(1) International consultant (@600/day) to develop information management system for the three Rio Conventions

(2) National consultant (@300/day) to support the assessment and implementation of solutions for harmonizing environmental information systems

(3) Project Coordinator and other project staff technical work (50% of total cost under outcome 1)

(4) Travel budget for capacity building events, meetings, and other related national meetings for the Rio conventions

(5) Budget provision for office Machinery and Equipment for Outcome 1

(6) Material and Goods for component 1

(7) Office supplies for component 1

(8) Information Technology Equipment for Outcome 1

(9) Rental and Maintenance of Information Technology Equipment for Outcome 1

(10) Car rental for outcome 1 operations

(11) Miscellaneous Expenses

(12) Training, workshop, 3 Rio conference, meeting, and events to promote harmonize environmental system management, to promote access to the environmental management system, and to communicate and exchange information related to the implementation of the Rio Conventions

(13) Inter. Consultant (@600/day) for Mid-Term and Final Evaluations (UNDP)

(14) Miscellaneous Expenses (UNDP)

(15) CD International Advisor for a half year ($190,000/year, based on UNDP 2014 Pro Forma Cost 2014) (40% funded by GEF under Outcome 2)

(16) MEA Expert for 3 years

(17) Project Coordinator and other project staff technical work (50% of total cost under outcome 2)

(18) Travel budget for capacity building events, meetings, and other related national meetings for the Rio conventions

(19) Budget provision for office Machinery and Equipment for Outcome 2

(20) Communication and Audio Visual Equipment for Outcome 2

(21) Office supplies for component 2

(22) Information Technology Equipment for Outcome 2

(23) Rental and Maintenance of Information Technology Equipment for Outcome 2

(24) Car rental for outcome 2 operations

(25) Miscellaneous Expenses

(26) Training, workshop, 3 Rio conference meeting and related events improved capacity building, national coordination and dialogue mechanismson the 3 Rio Conventions

(27) CD Inter. Advisor for a half year (@190,000/year, based on UNDP 2014 Pro Forma Cost 2014) (60% funded by UNDP under Outcome 2) + Inter. Consultant (@600/day) for MT and F Evaluations (UNDP)

(28) Miscellaneous Expenses (UNDP)

(29) Expenses for participation in COPs, SBSTTA, Ad-Hoc meetings, and other related meetings for the Rio conventions (UNDP)

(30) Project management staff: Admin Officer (@$15,600/year)  based on UNDP 2014 Pro Forma Cost 2014)

(31) Budget provision for office Machinery and Equipment

(32) Car rental for project management

(33) Office supplies for project management

(34) Audit cost for 3 years

(35) Miscellaneous Expenses

(36) Direct Project Costs incurred by UNDP, according to Letter of Agreement (Annex 8)

(37) Miscellaneous Expenses (UNDP)

(38) Direct Project Costs incurred by UNDP and co-financed by UNDP

- The table below provides details on planned consultancies for implementing this project. One consultancy with one international environmental monitoring expert is planned under outcome 2. The other consultancies are planned to be conducted by local consultants.

Table 9:  Consultants for technical assistance components (estimated for entire project)

| Local Consultants | Estimated Staff weeks | GEF ($) | Co-Financing ($) | Project Total ($) |
| --- | --- | --- | --- | --- |
| International consultant to develop information management system for the three Rio Conventions | 20 | 50,000 | - | 50,000 |
| National consultant(s) to support the assessment and implementation of solutions for harmonizing environmental information systems | 100 | 121,000 | - | 121,000 |
| CD International Advisor to advise the project during the first year of implementation | 27 | 50,000 | 73,000 | 123,000 |
| MEA Expert for the duration of the project to support the Project Director in implementing the project | 156 | 119,000 | - | 119,000 |
| Inter. Consultant(s) for Mid-Term and Final Evaluations | 10 | - | 18,000 | 18,000 |
| Total | 313 | 340,000 | 91,000 | 431,000 |

## D.2	Cost Effectiveness

- An important indicator to consider for analyzing the project cost-effectiveness is the percentage of the total project that is being used for project management services. As per table 10 below, this percentage is 6%, which is reasonable for a project of this size. It is noted that due to the small size of the project budget, this project management cost cannot be lower.

- Due to a good co-financing of this project, the cost-effectiveness of this project is good. As described in the sections, above, this project is a response to a national need and it will benefit from a significant investment of government staff (decision-makers and planners) to actively participate in project activities. The table below is an estimate of this contribution over the three years of project implementation.

- The cost-effectiveness of this project is also demonstrated in efficiently allocating and managing the financial resources of this project.  The recruitment of consultants will consist mostly of local consultants, reducing the transaction costs associated when contracting international consultants.

Table 10:  Project Costs (%)

| Project Budget Component by Contribution type | Contribution (US$) | Percentage (%) |
| --- | --- | --- |
| Component 1: GEF | 470,650 | 21% |
| Component 1: Co-Financing | 600,000 | 26% |
| Component 2: GEF | 429,350 | 19% |
| Component 2: Co-Financing | 645,000 | 28% |
| Project Management: GEF | 90,000 | 4% |
| Project Management: Co-Financing | 55,000 | 2% |
| Total | 2,290,000 | 100% |

## D.3	Co-financing

- UNDP will allocate US$ 1,150,000 directly to this project in cash (US$150,000) and in-kind (US$1,000,000) as part of its commitment to supporting the Government of Cambodia to strengthen its environmental information management and monitoring functions. The Government of Cambodia, through MOE is contributing US$ 150,000 in kind, which includes the human resources and their salaries - to support the project team in the implementation of the project - office furniture and space. The table 11 below presents the co-financing sources for this project. Letters to support this co-financing are presented in Part III of this project document.

Table 11:  Co-financing Sources

| Name of Co-financier | Classification | Type | Amount |  |
| --- | --- | --- | --- | --- |
|  |  |  | Confirmed (US$) | Unconfirmed (US$) |
| MOE | National Executive Agency | In-kind | 150,000 |  |
| UNDP | GEF Implementing Agency | Grant | 150,000 |  |
| UNDP | GEF Implementing Agency | In-kind | 1,000,000 |  |
| Total Co-financing |  |  | 1,300,000 |  |

# E.	Institutional Coordination and Support

## E.1	Core Commitments and Linkages

### E.1.a	Linkages to Other Activities and Programmes

- The project is fully compliant with the comparative advantages matrix approved by the GEF Council.  UNDP was selected as the GEF Implementing Agency for this project based on their experience and expertise in supporting capacity development efforts in Cambodia, and the lessons learned and best practices that it could bring to bear from their experience in other countries.  UNDP and the Government previously worked jointly on implementing the NCSA and its follow up initiatives, and agreed to cooperate on environmental governance for future projects.

- More broadly speaking, UNDP has developed a global expertise in supporting the development of in-country environmental governance capacity, including the development of environmental indicators and monitoring/evaluation tools, which are extremely necessary in measuring impact of such capacity development programmes.

- There are a number of key programmes and initiatives with which this project is to be coordinated.  Each of these programmes and initiatives has important data and information requirements. Likewise, each is generating the key data and information needs to facilitate and catalyze improved decision-making to meet global environmental objectives. They are also important components of a holistic approach to improve the management of the environment in Cambodia. This proposed project will build upon existing initiatives and their achievements and coordinate with related key programmes, plans, and projects. The main ones are presented below:

- Cambodia Climate Change Alliance – Phase 2 (MOE/UNDP-EU-SIDA, 2011-2015, USD 12.9);

- Forest Carbon Partnership Facility REDD+ Readiness Project (MAFF/UNDP-Forest Carbon Partnership Facility, 2014-2017, UDS 6.7M);

- Promoting Climate-Resilient Water Management and Agricultural Practices in Rural Cambodia (NAPAFU Phase 2) (MAFF/UNDP-CIDA, 2013-2015, USD 2.4M);

- Strengthening Sustainable Forest Management and Bio-Energy Markets to Promote Environmental Sustainability and to Reduce Greenhouse Gas Emissions in Cambodia (MAFF/UNDP-GEF-DANIDA-GERES, 2011-2015, USD 10M);

- Cambodia UN REDD National Programme (UNDP-FAO-UN-REDD, 2011-2014, USD 4.2M);

- Cambodia Community Based Adaptation Programme (CCBAP) (UNDP-SIDA, 2011-2015, USD 4.3M);

- FFI initiative on sustainability finance of catchment areas in Cambodia, including a feasibility on Payment for Ecosystem Services (PES);

- IUCN projects in Cambodia including: (i) the Regional Building Coastal Resilience to Climate Change Project (EU funded USD 4M, 2011-2014); (ii) Mekong Water Dialogues (regional project funded by Finland Euros 4M, 2010-2014); (iii) Strengthening capacity of fishing Communities in the Tonsle Sap to manage their natural resources sustainably (funded by EU); and (iv) Bridge 3S (Building River Dialogue and Governance) (regional project over three rivers: Sekong, Sre Pok, and Sesan);

- CI initiatives in climate change – both adaptation (forestry management) and mitigation (REDD), and land degradation;

- ECHO initiatives including the 2009 capacity development needs assessment of MOE and capacity development of civil society (22 NGOs);

- WWF initiatives including policy level work with government of Cambodia in biodiversity and in the context of the Green Growth strategy currently being implemented; and

- ADB funded projects including (i) Mainstreaming Climate Resilience into Development Planning (2013-2014), and (ii) Greater Mekong Sub-region Biodiversity Conservation Corridors Project (regional, 2011-2019).

- UNDP’s activities in Cambodia are in line with the United Nations Development Assistance Framework (UNDAF) 2011-2015 and the UNDP Country Programme Action Plan (CPAP). Both UNDAF and CPAP identify the sustainable use of natural resources as a threat to development, and UNDP Cambodia is investing core resources to address this threat. Specifically, the project will particularly contribute to the achievement of the UNDAF Priority 1 that is the development of capacities of national institutions, sub-national authorities and private sector to ensure the sustainable use of natural resources, cleaner technologies and responsiveness to climate change. As for CPAP, this project will be part of the fourth component that is aiming by 2015 to contribute to developing the capacity of national institutions, sub-national authorities, communities and private sector to be able to sustainably manage ecosystems and respond to climate change threats. Under this fourth component, UNDP allocated a budget of about $10 million from its own regular resources and an additional budget of over $35 million from other resources for the period 2011-2015.

## E.2	Implementation and Execution Arrangements

- The project will be implemented according to UNDP’s National Implementation Modality (NIM) as per NIM guidelines agreed by UNDP and the Government of Cambodia.

- Establishing an effective project management structure is crucial for its success. Every project has a need for direction, management, control and communication, using a structure that differs from line management. As a project is normally cross-functional and involves partnership, its structure needs to be more flexible, and is likely to require a broad base of skills for a specific period of time. The UNDP project management structure consists of roles and responsibilities that bring together the various interests and skills involved in, and required by, the project. It is proposed that the management arrangements illustrated below be discussed and considered for the Cambodia CCCD project:

Project Management Unit:

Project Coordinator, Administrative Assistant, Finance Officer

Supporting Staffs

Cambodia CCCD Project Board

Senior Beneficiaries: 3 Focal Points: (CC, CBD and CCD), GEF-OFP, MOWA

Project Assurance

UNDP Cambodia and UNDP/GEF-RTA

Project Organization Structure

Technical support/consultants (likely to change depending on nature of activities):

1) Component 1: Improved access and generation of information related to the three Rio Conventions.

2) Component 2: Improved use of information and knowledge related to the Rio Conventions.

Technical Team

CD International Advisor and National MEA Expert

Project Director

Executive:

MOE

Senior Supplier:

UNDP

The Ministry of Environment (MOE) is the designated Implementing Partner for the project. It will execute the project through the Department of International Convention and Biodiversity of the General Department of Administration for Nature Conservation and Protection (GDANCP) – or its equivalent if restructured - on behalf of the Royal Government of Cambodia (RGC) under the National Implementation Modality (NIM) of the UNDP. The Implementing Partner (MOE) is the entity responsible and accountable for managing a project, including the monitoring and evaluation of project interventions, achieving project outputs, and for the effective use of GEF/UNDP resources. A single implementing partner is designated to manage each UNDP-supported project. The implementing partner may enter into agreements with other organizations or entities to assist in successfully delivering project outputs. Possible implementing partners include government institutions, other eligible UN agencies and inter-governmental organizations, UNDP, and eligible civil society organizations (CSOs). Eligible CSOs are those that are legally registered in the country where they will be operating. The implementing partner was identified based on an assessment of its legal, technical, financial, managerial and administrative capacities that will be needed for the project. In addition, its ability to manage cash was assessed in accordance with the Harmonized Approach to Cash Transfers (HACT). The implementing partner may enter into agreements with other organizations or entities, namely Responsible Parties, to assist in successfully delivering project outputs. The Implementing Partner will assign a Representative and provide its staff and network of experts as support to the Project Management (as part of government co-financing).

- Executive: An individual representing the project ownership to chair the group will be represented by a senior official of MOE.

- Senior Beneficiary: An Individual or group of individuals representing the interests of those who will ultimately benefit from the project. The Senior Beneficiary’s primary function within the Board is to ensure the realization of project results from the perspective of project beneficiaries. GDANCP, MOE and MAFF represent the Government of Cambodia and act as the Senior Beneficiary of the Project.

- Senior Supplier:  Individual or group representing the interests of the parties concerned, which provide funding for specific cost sharing projects and/or technical expertise to the project. The Senior Supplier’s primary function within the Board is to provide guidance regarding the technical feasibility of the project. UNDP-Cambodia, which provides support to the project on behalf of the GEF takes the role of the Senior Supplier. UNDP is the GEF Implementing Agency for this project, with the UNDP Country Office responsible for transparent practices, appropriate conduct and professional auditing.

- Project Board (PB): The three parties above (Executive, Senior Supplier and Senior Beneficiary) make up the core members of the Project Board of which the main function is to strategically guide the course of the project towards achieving its objective. It is specifically established by the project to provide management oversight of project activities and is to be chaired by the Senior Official of MOE.  The PB will review progress and evaluation reports, and approve programmatic modifications to project execution, as appropriate and in accordance to UNDP procedures.  Policy recommendations will be discussed and recommended for consideration by the Cabinet of Ministers and Parliament. The PB is also responsible for making by consensus, management decisions for a project when guidance is required by the Project Coordinator, including recommendation for UNDP/Implementing Partner approval of project plans and revisions. In order to ensure UNDP’s ultimate accountability, PB decisions should be made in accordance with standards that shall ensure management for development results, best value for money, fairness, integrity, transparency and effective international competition. The Project Board will report to the soon-to-be created Sustainable Development Council.

- In case a consensus cannot be reached within the PB, final decision shall rest with the UNDP Resident Representative. In addition, the PB plays a critical role in UNDP commissioned project evaluations by quality assuring the evaluation process and products, and using evaluations for performance improvement, accountability and learning. Project reviews by this group are made at designated decision points during the running of the project, or as necessary when raised by the Project Coordinator. This group is consulted by the Project Coordinator for decisions when Project Coordinator's tolerances (normally in terms of time and budget) have been exceeded (flexibility). Based on the approved annual work plan (AWP), the PB may review and approve project quarterly plans when required and authorizes any major deviation from these agreed quarterly plans. It is the authority that signs off the completion of each quarterly plan as well as authorizes the start of the next quarterly plan. It ensures that required resources are committed and arbitrates on any conflicts within the project or negotiates a solution to any problems between the projects and external bodies. Finally, it approves the appointment and responsibilities of the Project Coordinator and any delegation of its Project Assurance responsibilities.

- In addition to the three parties above, government membership of the PB may include representatives from the line ministries responsible and their respective state agencies.  Non-state stakeholders may also be represented on the PB, namely from the private sector, academic and research institutions, NGOs, and CSOs. Additional members of the PB are reviewed and recommended for approval during the project appraisal committee (PAC) meeting. The PB will meet at least two (2) times per year. This group contains at least the following representatives:

- Senior Beneficiary: MOE will represent the project ownership and chair the PB.

- Senior Supplier: UNDP will represent the interests of the parties, which provide funding and/or technical expertise to the project.

- Executive: MOE will represent the interests of managing the project. Its primary function within the Project Board is to ensure the realization of project results from the perspective of implementing the project.

- The Project Assurance role supports the Project Board Executive by carrying out objective and independent project oversight and monitoring functions. The Project Manager and Project Assurance roles should never be held by the same individual for the same project.  This will be the responsibility of the Head of the Environment and Energy Unit (EEU) of UNDP Cambodia and the UNDP-GEF Regional Technical Advisor.

- National Project Director (NPD): The NPD has the authority to supervise and provide overall operational management and guidance for the successful executions and implementation of the project within the constraints laid down by the Project Board as well as subcontract specific components of the project to specialized government agencies, research institutions, as well as qualified NGOs. The Implementing Partner appoints the NPD. He/she is responsible for financial management and disbursements with accountability to the government and UNDP. Prior to the approval of the project, the Project Developer from UNDP is responsible for project management functions during formulation until the National Project Director from the Implementing Partner is in place.

- National MEA Expert: Provide technical support on MEAs to National Project Director.

- Project Management Unit (PMU): The Executive will provide an office. It will be located at GDANCP-MOE. The PMU will be administered by a full-time Project Coordinator and supported by a full-time Administrative Assistant, Finance Officer, Secretary, and support staff.

- Project Coordinator: The Project Coordinator is in charge of running the project on a day-to-day basis on behalf of the NPD that is day-to-day management and decision-making for the project with approval from NPD. The Project Coordinator’s prime responsibility is to ensure that the project produces the results (outputs) specified in the project document, to the required standard of quality and within the specified constraints of time and cost. The Implementing Partner appoints the Project Coordinator, who should be different from the Implementing Partner’s representative in the Board (NPD).

- Project Administrative Assistant: The role provides project administration, management and technical support to the Project Coordinator as required by the needs of the individual project.

- Project Finance Officer: He/she is to provide financial arrangements and management and technical support to the Project Coordinator and duties as required by the PMU.

- Project support staff: Their roles to provide non-technical support and assistance for the day-to-day operation and management of the project. They also perform other duties as required by PMU.

- Technical Team: This team will be formed of technical experts and will support the NDP and/or PMU by providing technical support to the implementation of this project.

- Technical Support/Consultants/cies: Responsible for undertaking specific activities for project components as needed.

- Capacity Development Activities:  The project will take an adaptive collaborative management approach to implementation.  That is, UNDP and GDANCP will manage project activities in order that stakeholders are involved early and throughout project implementation, providing regular input of the performance of project activities.  This will help signal unforeseen risks and contribute to the timely modification and realignment of activities within the boundaries of the project's goal and objectives.

- Stakeholder Engagement:  Project activities will be implemented through the necessary engagement of Stakeholders where needed.

- GEF Visibility:  Visibility of GEF financial support will be ensured by using the global GEF branding in all electronic and printed materials.  The GEF logo will appear on all relevant project publications, including amongst others, project hardware and other purchases with GEF funds. Any citation in publications regarding projects funded by GEF will acknowledge the GEF.  Logos of the Implementing Agencies and the Executing Agency will also appear on all publications.  Where other agencies and project partners have provided support (through co-financing) their logos may also appear on project publications.  Full compliance will be made with the GEF’s Communication and Visibility Guidelines.

# F	LEGAL CONTEXT

- This document together with the CPAP signed by the Government and UNDP which is incorporated by reference constitute together a Project Document as referred to in the SBAA and all CPAP provisions apply to this document.

- Consistent with the Article III of the Standard Basic Assistance Agreement, the responsibility for the safety and security of the implementing partner and its personnel and property, and of UNDP’s property in the implementing partner’s custody, rests with the implementing partner.

- The implementing partner shall:

- Put in place an appropriate security plan and maintain the security plan, taking into account the security situation in the country where the project is being carried;

- Assume all risks and liabilities related to the implementing partner’s security, and the full implementation of the security plan.

- UNDP reserves the right to verify whether such a plan is in place, and to suggest modifications to the plan when necessary and with approval from the Project Board. Failure to maintain and implement an appropriate security plan as required hereunder shall be deemed a breach of this agreement.

- The implementing partner agrees to undertake all reasonable efforts to ensure that none of the UNDP funds received pursuant to the Project Document are used to provide support to individuals or entities associated with terrorism and that the recipients of any amounts provided by UNDP hereunder do not appear on the list maintained by the Security Council Committee established pursuant to resolution 1267 (1999). The list can be accessed via http://www.un.org/Docs/sc/committees/1267/1267ListEng.htm. This provision must be included in all sub-contracts or sub-agreements entered into under this Project Document.

# PART II:	ANNEXES

Annex 1:	Capacity Development Scorecard

Annex 2:	Project Results Framework

Annex 3:	Outcome Budget (GEF Contribution and Co-financing)

Annex 4:	Provisional Work Plan

Annex 5:	Terms of References

Annex 6:	Environmental and Social Review Criteria

Annex 7:	PPG Status Report

Annex 8:	letter of agreement between UNDP and Government of Cambodia

## Annex 1:  Capacity Development Scorecard

Project/Programme Name:	Generating, Accessing and Using Information and Knowledge Related to the Three Rio Conventions

Project/Programme Cycle Phase:	Project preparation (PPG)					Date:	May 2014

| Capacity Result / Indicator | Staged Indicators | Rating | Score | Comments | Next Steps | Outcome Contribution |
| --- | --- | --- | --- | --- | --- | --- |
| CR 1: Capacities for engagement |  |  |  |  |  |  |
| Indicator 1 – Degree of legitimacy/mandate of lead environmental organizations | Institutional responsibilities for environmental management are not clearly defined | 0 | 2 | The institutional mandates of lead organizations are partially recognized. However, lack of coordination among these lead organizations is a recognized problem in Cambodia. | The project will review these mandates and the capacity of these institutions to coordinate environmental activities including the implementation of the Rio Convention obligations. Then, recommendations will be made to improve the coordination at the national level. | 1. Improved access and generation of information related to the three Rio Conventions. |
|  | Institutional responsibilities for environmental management are identified | 1 |  |  |  |  |
|  | Authority and legitimacy of all lead organizations responsible for environmental management are partially recognized by stakeholders | 2 |  |  |  |  |
|  | Authority and legitimacy of all lead organizations responsible for environmental management recognized by stakeholders | 3 |  |  |  |  |
| Indicator 2 – Existence of operational co-management mechanisms | No co-management mechanisms are in place | 0 | 1 | Not all sectors are equal. Co-management mechanisms exist in the biodiversity area but are limited in other areas. | Through project activities, the coordination to manage natural resources will be improved and will provide a better framework for the development of such co-management mechanisms. | 1. Improved access and generation of information related to the three Rio Conventions. |
|  | Some co-management mechanisms are in place and operational | 1 |  |  |  |  |
|  | Some co-management mechanisms are formally established through agreements, MOUs, etc. | 2 |  |  |  |  |
|  | Comprehensive co-management mechanisms are formally established and are operational/functional | 3 |  |  |  |  |
| Indicator 3 – Existence of cooperation with stakeholder groups | Identification of stakeholders and their participation/involvement in decision-making is poor | 0 | 1 | The participation of stakeholders in decision-making regarding the management of the environment is happening in Cambodia but this participation is limited and not coordinated across focal areas. | Through the collaborative approach used by the project and the engagement of stakeholders in the implementation of the project, it is anticipated that the cooperation among stakeholders should increase, including a greater collaboration among government and non-government organizations. | 1. Improved access and generation of information related to the three Rio Conventions. |
|  | Stakeholders are identified but their participation in decision-making is limited | 1 |  |  |  |  |
|  | Stakeholders are identified and regular consultations mechanisms are established | 2 |  |  |  |  |
|  | Stakeholders are identified and they actively contribute to established participative decision-making processes | 3 |  |  |  |  |
| CR 2: Capacities to generate, access and use information and knowledge |  |  |  |  |  |  |
| Indicator 4 – Degree of environmental awareness of stakeholders | Stakeholders are not aware about global environmental issues and their related possible solutions (MEAs) | 0 | 1 | Cambodians have a certain level of awareness on global environment issues. However, the limited coordination of actors limits the participation of stakeholders in identifying and implementing solutions. |  | No direct contribution from the project to improve this capacity. |
|  | Stakeholders are aware about global environmental issues but not about the possible solutions (MEAs) | 1 |  |  |  |  |
|  | Stakeholders are aware about global environmental issues and the possible solutions but do not know how to participate | 2 |  |  |  |  |
|  | Stakeholders are aware about global environmental issues and are actively participating in the implementation of related solutions | 3 |  |  |  |  |
| Indicator 5 – Access and sharing of environmental information by stakeholders | The environmental information needs are not identified and the information management infrastructure is inadequate | 0 | 1 | Some environmental information exists and is shared among stakeholders but the access is limited and there is no clearinghouse mechanism to access environmental information in Cambodia. | With the project support existing environmental management information systems will be reviewed and solutions identified to harmonize these systems. Then a clearinghouse mechanism will be developed to provide an open-access to environmental information, including information on the implementation of the Rio Conventions. | 1. Improved access and generation of information related to the three Rio Conventions. |
|  | The environmental information needs are identified but the information management infrastructure is inadequate | 1 |  |  |  |  |
|  | The environmental information is partially available and shared among stakeholders but is not covering all focal areas and/or the information management infrastructure to manage and give information access to the public is limited | 2 |  |  |  |  |
|  | Comprehensive environmental information is available and shared through an adequate information management infrastructure | 3 |  |  |  |  |
| Indicator 6 – Existence of environmental education programmes | No environmental education programmes are in place | 0 | 1 | Some environmental education activities were implemented, often supported by externally funded projects. However, no national environmental education programme is in place in Cambodia. |  | No direct contribution from the project to improve this capacity. |
|  | Environmental education programmes are partially developed and partially delivered | 1 |  |  |  |  |
|  | Environmental education programmes are fully developed but partially delivered | 2 |  |  |  |  |
|  | Comprehensive environmental education programmes exist and are being delivered | 3 |  |  |  |  |
| Indicator 7 – Extent of the linkage between environmental research/science and policy development | No linkage exist between environmental policy development and science/research strategies and programmes | 0 | 1 | Limited environmental research is being done in Cambodia, due mostly to lack of resources but also lack of strategies to development research programme. |  | No direct contribution from the project to improve this capacity. |
|  | Research needs for environmental policy development are identified but are not translated into relevant research strategies and programmes | 1 |  |  |  |  |
|  | Relevant research strategies and programmes for environmental policy development exist but the research information is not responding fully to the policy research needs | 2 |  |  |  |  |
|  | Relevant research results are available for environmental policy development | 3 |  |  |  |  |
| Indicator 8 – Extent of inclusion/use of traditional knowledge in environmental decision-making | Traditional knowledge is ignored and not taken into account into relevant participative decision-making processes | 0 | 1 | Traditional knowledge is recognized but is not collected and used in decisions related to the management of natural resources. | As part of improving the knowledge on the environment in Cambodia, appropriate traditional knowledge will be collected, stored and made available. | 1. Improved access and generation of information related to the three Rio Conventions. |
|  | Traditional knowledge is identified and recognized as important but is not collected and used in relevant participative decision-making processes | 1 |  |  |  |  |
|  | Traditional knowledge is collected but is not used systematically into relevant participative decision-making processes | 2 |  |  |  |  |
|  | Traditional knowledge is collected, used and shared for effective participative decision-making processes | 3 |  |  |  |  |
| CR 3: Capacities for strategy, policy and legislation development |  |  |  |  |  |  |
| Indicator 9 – Extend of the environmental planning and strategy development process | The environmental planning and strategy development process is not coordinated and does not produce adequate environmental plans and strategies | 0 | 2 | There are environmental plans and strategies in place in Cambodia but they lack a good inter-sectorial coordination mechanism to facilitate their implementation. |  | No direct contribution from the project to improve this capacity. |
|  | The environmental planning and strategy development process does produce adequate environmental plans and strategies but there are not implemented/used | 1 |  |  |  |  |
|  | Adequate environmental plans and strategies are produced but there are only partially implemented because of funding constraints and/or other problems | 2 |  |  |  |  |
|  | The environmental planning and strategy development process is well coordinated by the lead environmental organizations and produces the required environmental plans and strategies; which are being implemented | 3 |  |  |  |  |
| Indicator 10 – Existence of an adequate environmental policy and regulatory frameworks | The environmental policy and regulatory frameworks are insufficient; they do not provide an enabling environment | 0 | 1 | There are environmental legislation and policies in place in Cambodia but they do not take fully into account MEA obligations, particularly the Rio Convention obligations. |  | No direct contribution from the project to improve this capacity. |
|  | Some relevant environmental policies and laws exist but few are implemented and enforced | 1 |  |  |  |  |
|  | Adequate environmental policy and legislation frameworks exist but there are problems in implementing and enforcing them | 2 |  |  |  |  |
|  | Adequate policy and legislation frameworks are implemented and provide an adequate enabling environment; a compliance and enforcement mechanism is established and functions | 3 |  |  |  |  |
| Indicator 11 – Adequacy of the environmental information available for decision-making | The availability of environmental information for decision-making is lacking | 0 | 1 | Environmental information exists but the quality is uneven and do not cover all MEAs reporting obligations, and its open-access is limited. | With the project support existing environmental management information systems will be reviewed, including the indicators being monitored. These systems will be then harmonized and a clearinghouse mechanism develop to give open-access to this information. | 1. Improved access and generation of information related to the three Rio Conventions. |
|  | Some environmental information exists but it is not sufficient to support environmental decision-making processes | 1 |  |  |  |  |
|  | Relevant environmental information is made available to environmental decision-makers but the process to update this information is not functioning properly | 2 |  |  |  |  |
|  | Political and administrative decision-makers obtain and use updated environmental information to make environmental decisions | 3 |  |  |  |  |
| CR 4: Capacities for management and implementation |  |  |  |  |  |  |
| Indicator 12 – Existence and mobilization of resources | The environmental organizations don’t have adequate resources for their programmes and projects and the requirements have not been assessed | 0 | 1 | There are not enough financial resources to support the environmental governance framework in place in Cambodia. Additionally, environment is not a top priority of the government, which renders allocation of national budget to this area more difficult. | The project will pilot the development of innovative tools for decision-making using economic valuation of the use of natural resources. | 2. Improved use of information and knowledge related to the Rio Conventions. |
|  | The resource requirements are known but are not being addressed | 1 |  |  |  |  |
|  | The funding sources for these resource requirements are partially identified and the resource requirements are partially addressed | 2 |  |  |  |  |
|  | Adequate resources are mobilized and available for the functioning of the lead environmental organizations | 3 |  |  |  |  |
| Indicator 13 – Availability of required technical skills and technology transfer | The necessary required skills and technology are not available and the needs are not identified | 0 | 2 | Consideration of environmental issues in sectoral planning and programming is not systematic and rarely carried out. Some training is provided to government of Cambodia staff, but none on integration of Rio Convention provisions into sectoral planning and programming |  | No direct contribution from the project to improve this capacity. |
|  | The required skills and technologies needs are identified as well as their sources | 1 |  |  |  |  |
|  | The required skills and technologies are obtained but their access depend on foreign sources | 2 |  |  |  |  |
|  | The required skills and technologies are available and there is a national-based mechanism for updating the required skills and for upgrading the technologies | 3 |  |  |  |  |
| CR 5: Capacities to monitor and evaluate |  |  |  |  |  |  |
| Indicator 14 – Adequacy of the project/programme monitoring process | Irregular project monitoring is being done without an adequate monitoring framework detailing what and how to monitor the particular project or programme | 0 | 1 | Limited monitoring of projects and programmes is happening besides monitoring mandated on donor funded projects and programmes. This information is not really communicated/collected into the national body of knowledge on environment. |  | No direct contribution from the project to improve this capacity. |
|  | An adequate resourced monitoring framework is in place but project monitoring is irregularly conducted | 1 |  |  |  |  |
|  | Regular participative monitoring of results in being conducted but this information is only partially used by the project/programme implementation team | 2 |  |  |  |  |
|  | Monitoring information is produced timely and accurately and is used by the implementation team to learn and possibly to change the course of action | 3 |  |  |  |  |
| Indicator 15 – Adequacy of the project/programme monitoring and evaluation process | None or ineffective evaluations are being conducted without an adequate evaluation plan; including the necessary resources | 0 | 1 | Adequate evaluation plan and evaluation results are partially used because of insufficient resources. The collection of this information into the national body of knowledge on environment is limited. |  | No direct contribution from the project to improve this capacity. |
|  | An adequate evaluation plan is in place but evaluation activities are irregularly conducted | 1 |  |  |  |  |
|  | Evaluations are being conducted as per an adequate evaluation plan but the evaluation results are only partially used by the project/programme implementation team | 2 |  |  |  |  |
|  | Effective evaluations are conducted timely and accurately and are used by the implementation team and the Agencies and GEF Staff to correct the course of action if needed and to learn for further planning activities | 3 |  |  |  |  |
|  | Total Score: |  | 18/45 |  |  |  |

## Annex 2:  Project Results Framework

This project will contribute to achieving the following Country Programme Outcome as defined in UNDAF: UNDAF Outcome: I. Economic Growth and Sustainable Development; and V. Governance UNDAF Country Programme Outcome I.2 and V.3: (I.2) National institutions and sub-national authorities and private sector are better able to ensure the sustainable use of natural resources (fisheries, forestry, mangrove, land, and protected areas), cleaner technologies and responsiveness to climate change; and (V.3) enhanced capacities for collection, access and utilization of disaggregated information (gender, age, target populations, region) at national and sub-national levels to develop and monitor policies and plans that are responsive to the needs of the people and incorporate priority population, poverty and development linkages.

UNDAF Outcome Indicators: Outcome I: Number of national and sectoral plans and strategies which explicitly refer to climate change; Outcome V: Implementation by the Government of recommendations formulated by treaty bodies in individual complaints submitted to them by Cambodian nationals; National dialogue mechanism established between Government and civil society for enhanced dialogue and cooperation including data disaggregated by province and sex; Disaggregated data and information used to monitor NSDP, CMDGs, sectoral and subnational plans; Increased coverage by the media of MDGs, extractive industries, climate change and land rights issues.

Primary applicable Key Environment and Sustainable Development Key Result Area (same as that on the cover page, circle one):

Applicable GEF Strategic Focal Area Objectives: CD-2: Generate, access and use of information and knowledge. CD-4: Strengthen capacities to implement and manage global convention guidelines.

Applicable GEF Outcome Indicators: CD-2: Institutions and stakeholders trained how to use different tools available to manage information; Stakeholders are better informed via workshops and trainings about global challenges and local actions required; Ability of stakeholders to diagnose, understand and transform information and knowledge into local actions increased and retained; Knowledge platform established to share lessons learned among CBOs and CSOs. CD-4: Institutional capacities for management of environment strengthened; Standards developed and adopted; Management capacities for implementation of convention guidelines and Reporting enhanced; Capacities of CSOs and CBOs as SGP partners, strengthened; Sustainable financing mechanisms developed.

| Objectives and Outcomes | Indicator | Baseline | Targets End of Project | Source of verification | Risks and Assumptions |
| --- | --- | --- | --- | --- | --- |
| Objective: To improve access to environmental information related to the Rio Conventions through the harmonization of existing environmental management information systems and improving coordination of the implementation of these conventions in Cambodia. | - Key environmental management information systems are harmonized with open-access and covering areas related to the Rio Conventions. | - Capacity of the main stakeholders for accessing environmental information from various existing systems is limited and dispersed over many organizations. | - Environmental knowledge related to the implementation of the Rio Conventions in Cambodia is comprehensive and easily accessible. | - Reference to the new harmonized systems in project documents; national strategies, programmes and plans; national assessments - State of the environment reports and communications/national reports sent to Conventions - Information products such as newsletters, flyers, articles, etc. - Policies referring to this new environmental information | Risk: - Political will to provide GDANCP with the necessary resources to sustain project achievements. - New information is not used and stays stored in computers at MOE Assumption: - MOE will support GDANCP and provide it with necessary resources - Better environmental information is readily available and actively utilized and used |
|  | - Quality of monitoring reports and communications to measure implementation progress of the Rio Conventions. | - Current reports are produced by sector, with limited data, weak analysis, weak trend analysis, and there are not fully responding to international requirements. | - Reports present adequate disaggregated data at sub-national level, are informative and present environmental trends over time. | - MOE reports - Environmental reports such as the State of Environment and Communications to Conventions | Risk: - Communications and national reports are not submitted on time Assumption: - Communications and national reports are submitted on time and include information from the harmonized systems. |
|  | - Capacity development scorecard rating | Capacity for: - Engagement: 4 of 9 - Generate, access and use information and knowledge: 5 of 15 - Policy and legislation development: 4 of 9 - Management and implementation: 3 of 6 - Monitor and evaluate: 2 of 6 (Total score: 18/45) | Capacity for: - Engagement: 7 of 9 - Generate, access and use information and knowledge: 10 of 15 - Policy and legislation development: 5 of 9 - Management and implementation: 5 of 6 - Monitor and evaluate: 4 of 6 (Total targeted score: 31/45) | - Mid-term review and final evaluation reports, including an updated CD scorecard - Annual PIRs - Capacity assessment reports | Risk: - Project activities and resources do not translate in increasing the capacity of GDANCP to provide better environmental information. Assumption: - The project is effective in developing the capacity in the area of environmental information management. |
| OUTCOME 1: IMPROVED ACCESS AND GENERATION OF INFORMATION RELATED TO THE THREE RIO CONVENTIONS |  |  |  |  |  |
| Output 1.1: A harmonized information management system covering the three Rio Conventions. Output 1.2: A common clearinghouse mechanism for the three Rio Conventions. Output 1.3: Existing stakeholder platforms strengthened in order to increase stakeholder engagement in Convention related dialogues. Output 1.4: Strengthened coordination between key sectors to address biodiversity, climate change and land degradation issues at systemic and institutional levels. | - A system and a data architectures to harmonize key environmental information systems | - Existing systems and data architectures are not communicating efficiently and do not provide good availability to environmental knowledge | - Environmental information systems are harmonized using internationally recognized standards. | - Technical reports - Database(s) - PIRs - Web pages | Risk: - Lack of relevant expertise in local market may result in delay of required outputs and distortion of targeted deadlines Assumption: - Implementation of project activities and recruitment of relevant national expertise is monitored and actions will be identified if the lack of expertise is affecting the timely implementation of the project |
|  | - A developed clearinghouse mechanism in place at MOE and covering all environmental areas related to the Rio Conventions. | - Limited mechanisms in place to access, share and exchange environmental information. | - Open-access to all data, reports, research, plans and documents available on the implementation of the Rio Conventions in Cambodia. | - Database(s) - Reports - Websites | Risk: - Government unwilling to give open-access to environmental information Assumption: - MOE will support GDANCP and provide it with necessary resources to develop this mechanism and give public open-access |
|  | - Stakeholders engagement in Rio Conventions related dialogues | - Current engagement is sector-based and mostly focusing on climate change. | - A platform to exchange environmental information related to the implementation of the Rio Conventions. - An increase of 50% of Stakeholders engagement in related dialogues | - Information exchange system - Meetings minutes - Paper presented | Risk: - No interest from Stakeholders to increase crosscutting dialogues on the implementation of the Rio Conventions. Assumption: - All Stakeholders involved in implementing the Rio Conventions in Cambodia are demanding for greater exchange of environmental information and to better engage in crosscutting dialogues. |
|  | - An operational inter-sectorial coordination mechanism that builds on existing coordination instruments. | - Few sector-based coordination mechanisms exist but none to coordinate across the three Rio Conventions. | - An operational inter-sectorial coordination mechanism in place to coordinate the implementation of MEAs in Cambodia. | - Policy paper on coordination - Formal approval (ministerial order?) of this new coordination mechanism. | Risks: - Political - delays due to ministerial reforms. - Operational - Irregular frequency of meetings for relevant bodies, unclear approval mechanism for an inter-sectorial coordination body, unwillingness to participate in the inter-sectorial coordination body. Assumption: - Supporting mechanism is in-place |
| OUTCOME 2: IMPROVED USE OF INFORMATION AND KNOWLEDGE RELATED TO THE RIO CONVENTIONS |  |  |  |  |  |
| Output 2.1: Innovative tools piloted for decision-making using the economic valuation of the use of natural resources. Output 2.2: Strengthened capacity of existing national implementing institutions on negotiation skills and national preparatory process for COPs and other related meetings for the Rio conventions. Output 2.3: A unified reporting process on the implementation status of the three Rio Conventions. | - Model to implement environmental economic valuation in Cambodia | - Environmental economic valuation as a policy instrument is not used in Cambodia | - A strategy on how to implement environmental economic valuation as a policy instrument in Cambodia | - Government strategy - Policy paper(s) | Risk: - No interest from decision-makers to use economic valuation as a tool to support decision-making Assumption: - The benefit of using better economic valuation will encourage decision-makers to use it. |
|  | - Use of environmental economic valuation in environmental decision-making | - Environmental economic valuation is not used in decision-making in Cambodia. | - 3-4 policies, programmes or plans are developed using environmental economic valuation. | - Policy, programme and plan documents |  |
|  | - Negotiation capacity of Cambodia at COPs | - Limited COP negotiations skills and knowledge | - Negotiations at 2-3 COPs with position papers for Cambodia | - Country position papers - Policy papers - COPs reports | Risk: - The government does not fulfill its international obligations; including those from the 3 Rio Conventions Assumption: The government continues to fulfill its international commitments |
|  | - Quality, quantity and timeliness of reports submitted to conventions | - Reports are sector-based, are not submitted on time and do not contain much primary collected data | - National communications/ reports are submitted on time and contain primary data provided by the harmonized system(s) | - National communications and reports |  |

## Annex 3:  Outcome Budget (GEF Contribution and Co-financing)

| Activity | Description | Year 1 | Year 2 | Year 3 | GEF | Co-financing | Total |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Outcome 1: | Improved access and generation of information related to the three Rio Conventions | 165,750 | 170,750 | 134,150 | 470,650 | 600,000 | 1,070,650 |
| Output 1.1 | A harmonized information management system covering the three Rio Conventions |  |  |  |  |  |  |
| 1.1.1 | Conduct an inventory of existing environmental management information systems | 15,000 |  |  | 15,000 | 30,000 | 45,000 |
| 1.1.2 | Assess these systems to identify overlaps and gaps | 15,000 | 11,000 |  | 26,000 | 40,000 | 66,000 |
| 1.1.3 | Identify solutions to harmonize these systems and provide open-access | 8,000 | 10,000 | 5,000 | 23,000 | 40,000 | 63,000 |
| 1.1.4 | Decide on the most appropriate solution(s) | 20,000 | 10,000 | 10,000 | 40,000 | 40,000 | 80,000 |
| 1.1.5 | Implement solution(s) | 20,000 | 12,000 | 18,000 | 50,000 | 40,000 | 90,000 |
| Output 1.2 | A common clearinghouse mechanism for the three Rio Conventions |  |  |  |  |  |  |
| 1.2.1 | Identify options for the development of a clearinghouse mechanism | 10,000 |  |  | 10,000 | 30,000 | 40,000 |
| 1.2.2 | Select the most appropriate solution(s) | 15,000 | 5,000 | 5,000 | 25,000 | 30,000 | 55,000 |
| 1.2.3 | Implement the selected environmental information clearinghouse mechanism |  | 20,000 | 12,550 | 32,550 | 40,000 | 72,550 |
| 1.2.4 | Identify and develop an information sharing/exchange mechanism |  | 20,000 | 10,000 | 30,000 | 50,000 | 80,000 |
| Output 1.3 | Existing stakeholder platforms strengthened in order to increase stakeholder engagement in Convention related dialogues |  |  |  |  |  |  |
| 1.3.1 | Review existing operational coordination platforms | 15,000 |  |  | 15,000 | 30,000 | 45,000 |
| 1.3.2 | Design a crosscutting platform for dialogues on climate change, biodiversity and land degradation | 15,000 | 10,000 | 13,600 | 38,600 | 40,000 | 78,600 |
| 1.3.3 | Formalize this crosscutting platform |  | 24,000 | 10,000 | 34,000 | 40,000 | 74,000 |
| 1.3.4 | Raise awareness of Stakeholders on MEAs obligations | 10,000 | 25,000 | 10,000 | 45,000 | 50,000 | 95,000 |
| Output 1.4 | Strengthened coordination between key sectors to address biodiversity, climate change and land degradation issues at systemic and institutional levels |  |  |  |  |  |  |
| 1.4.1 | Review existing coordination mechanisms | 10,000 |  |  | 10,000 | 20,000 | 30,000 |
| 1.4.2 | Design a mechanism to address inter-sectorial coordination issues | 12,750 | 3,000 |  | 15,750 | 30,000 | 45,750 |
| 1.4.3 | Formalize this inter-sectorial coordination mechanism |  | 10,750 | 20,000 | 30,750 | 30,000 | 60,750 |
| 1.4.4 | Raise awareness of Decision-Makers on MEAs obligations |  | 10,000 | 20,000 | 30,000 | 20,000 | 50,000 |
| Outcome 2: | Improved use of information and knowledge related to the Rio Conventions | 180,050 | 125,650 | 123,650 | 429,350 | 645,000 | 1,074,350 |
| Output 2.1 | Innovative tools piloted for decision-making using the economic valuation of the use of natural resources |  |  |  |  |  |  |
| 2.1.1 | Review ongoing work on environmental economic valuation | 30,000 |  |  | 30,000 | 50,000 | 80,000 |
| 2.1.2 | Design the pilot to demonstrate the environmental economic valuation | 30,000 |  |  | 30,000 | 85,000 | 115,000 |
| 2.1.3 | Implement the pilot | 5,000 | 22,650 | 19,200 | 46,850 | 40,000 | 86,850 |
| 2.1.4 | Assess the results obtained by the pilot and identify scale-up activities |  |  | 20,000 | 20,000 | 60,000 | 80,000 |
| Output 2.2 | Strengthened capacity of existing national implementing institutions on negotiation skills and national preparatory process for COPs and other related meetings for the Rio conventions |  |  |  |  |  |  |
| 2.2.1 | Review obligations from MEAs | 15,000 |  |  | 15,000 | 30,000 | 45,000 |
| 2.2.2 | Assess institutional mechanisms in place to implement MEAs | 15,000 | 5,000 |  | 20,000 | 50,000 | 70,000 |
| 2.2.3 | Design a training programme on MEAs, their global processes and the main issues being negotiated | 10,000 | 20,000 | 16,450 | 46,450 | 40,000 | 86,450 |
| 2.2.4 | Deliver training activities to staff in institutions mandated to implement MEAs | 15,000 | 20,000 | 20,000 | 55,000 | 40,000 | 95,000 |
| Output 2.3 | A unified reporting process on the implementation status of the three Rio Conventions |  |  |  |  |  |  |
| 2.3.1 | Review MEAs reporting requirements | 20,050 |  |  | 20,050 | 30,000 | 50,050 |
| 2.3.2 | Design a unified reporting mechanism for all Conventions | 20,000 |  |  | 20,000 | 40,000 | 60,000 |
| 2.3.3 | Implement/formalize this reporting mechanism | 10,000 | 20,000 |  | 30,000 | 40,000 | 70,000 |
| 2.3.4 | Design and deliver training to staff | 5,000 | 18,000 | 15,000 | 38,000 | 40,000 | 78,000 |
| 2.3.5 | Produce the first national report | 5,000 | 20,000 | 33,000 | 58,000 | 100,000 | 158,000 |
| Project Management |  | 28,600 | 30,700 | 30,700 | 90,000 | 55,000 | 145,000 |
| A | Locally recruited personnel: Project Staff | 15,600 | 15,600 | 15,600 | 46,800 |  | 46,800 |
| B | Office supplies, equipment, miscellaneous | 3,500 | 3,600 | 3,600 | 10,700 | 40,000 | 50,700 |
| C | Travel | 1,000 | 1,000 | 1,000 | 3,000 |  | 3,000 |
| D | Direct Project Services (DPCs) | 5,000 | 7,000 | 7,000 | 19,000 | 15,000 | 34,000 |
| E | Audit fee | 3,500 | 3,500 | 3,500 | 10,500 |  | 10,500 |
|  | Total | 374,400 | 327,100 | 288,500 | 990,000 | 1,300,000 | 2,290,000 |

## Annex 4:  Provisional Work Plan

| Activity |  | Description | Year 1 |  |  |  | Year 2 |  |  |  | Year 3 |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Q1 | Q2 | Q3 | Q4 | Q5 | Q6 | Q7 | Q8 | Q9 | Q10 | Q11 | Q12 |
|  |  | Inception: Organize project team, review project strategy, work plan, etc. |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Project Board Meetings |  |  |  |  |  |  |  |  |  |  |  |  |
| Outcome 1: |  | Improved access and generation of information related to the three Rio Conventions |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 1.1 | A harmonized information management system covering the three Rio Conventions |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.1.1 | Conduct an inventory of existing environmental management information systems |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.1.2 | Assess these systems to identify overlaps and gaps |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.1.3 | Identify solutions to harmonize these systems and provide open-access |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.1.4 | Decide on the most appropriate solution(s) |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.1.5 | Implement solution(s) |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 1.2 | A common clearinghouse mechanism for the three Rio Conventions |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.2.1 | Identify options for the development of a clearinghouse mechanism |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.2.2 | Select the most appropriate solution(s) |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.2.3 | Implement the selected environmental information clearinghouse mechanism |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.2.4 | Identify and develop an information sharing/exchange mechanism |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 1.3 | Existing stakeholder platforms strengthened in order to increase stakeholder engagement in Convention related dialogues |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.3.1 | Review existing operational coordination platforms |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.3.2 | Design a crosscutting platform for dialogues on climate change, biodiversity and land degradation |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.3.3 | Formalize this crosscutting platform |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.3.4 | Raise awareness of Stakeholders on MEAs obligations |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 1.4 | Strengthened coordination between key sectors to address biodiversity, climate change and land degradation issues at systemic and institutional levels |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.4.1 | Review existing coordination mechanisms |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.4.2 | Support a mechanism to address inter-sectorial coordination issues |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.4.3 | Formalize this inter-sectorial coordination mechanism through Cabinet approval |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.4.4 | Raise awareness of Decision-Makers on MEAs obligations |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Outcome 2: |  | Improved use of information and knowledge related to the Rio Conventions |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 2.1 | Innovative tools piloted for decision-making using the economic valuation of the use of natural resources |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.1.1 | Review ongoing work on environmental economic valuation |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.1.2 | Design the pilot to demonstrate the environmental economic valuation |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.1.3 | Implement the pilot |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.1.4 | Assess the results obtained by the pilot and identify scale-up activities |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 2.2 | Strengthened capacity of existing national implementing institutions on negotiation skills and national preparatory process for COPs and other related meetings for the Rio conventions |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.2.1 | Review obligations from MEAs |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.2.2 | Assess institutional mechanisms in place to implement MEAs |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.2.3 | Design a training programme on MEAs, their global processes and the main issues being negotiated |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.2.4 | Deliver training activities to staff in institutions mandated to implement MEAs |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 2.3 | A unified reporting process on the implementation status of the three Rio Conventions |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.3.1 | Review MEAs reporting requirements |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.3.2 | Design a unified reporting mechanism for all Conventions |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.3.3 | Implement/formalize this reporting mechanism |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.3.4 | Design and deliver training to staff |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.3.5 | Produce the first national report |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Project Management |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Project administration and management |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | International Evaluation Consultant(s): Mid-Term and Terminal Evaluation |  |  |  |  |  |  |  |  |  |  |  |  |  |

## Annex 5:  Terms of References

The following Terms of Reference outlines the general responsibilities to be carried out by consultants contracted under the project.

Background

Cambodia assessed its own capacities and capacity development needs to address the requirements of the three conventions through the NCSA process conducted from 2005 to 2006. It focused on issues and concerns within its jurisdiction to address Cambodia’s obligations under the three conventions. It was a national assessment of Cambodian capacities undertaken by the government of Cambodia and done by Cambodians. The assessment was cross-cutting across the three Rio Conventions (climate change, biodiversity and land degradation) and was conducted at 3 levels: i) systemic capacity; ii) institutional capacity; and iii) individual capacity.

This extensive assessment identified thematic environmental issues. These thematic issues were then reviewed together across the three thematic areas and crosscutting capacity constraints were identified as well as ways to address these constraints and effectively promote linkages and synergies across the conventions and meet their respective requirements obligated by the Parties. Five main crosscutting capacity issues were identified and the project will particularly address the management of environmental information and the access and use of this information for improving policy and decision-making.

Project Goal and Objectives

The goal of this project is to improve the implementation of the Rio Conventions in Cambodia through the development of national capacities to better coordinate and generate better information related to the implementation of these Conventions. The proposed project will develop crosscutting capacity to respond to the needs of the three conventions; particularly the reporting requirements. During the project implementation, the coordination and information generation capacities of the focal points established by the government will be enhanced.

The project’s objective is to improve access to environmental information related to the Rio Conventions through the harmonization of existing environmental management information systems and improving coordination of the implementation of these conventions in Cambodia.  The harmonization of these existing systems will be translated into better access to information related to the implementation of the Rio Conventions in Cambodia. It will include the decision-making process to meet Rio Convention objectives, which will be greatly improved by having better access to more complete and relevant information. It will also include innovation to set up a network of enhanced information exchange, dialogue and cooperation between the state agencies and other civil society stakeholders.

Project Strategy

The expected achievements of this project are a set of improved capacities to meet and sustain Rio Convention objectives. This project will have strengthened and helped institutionalize commitments under the Rio Conventions by harmonizing the existing national environmental management information systems, by improving the use of this environmental knowledge for better decision-making and by improving the coordination of the implementation of the Rio Conventions in Cambodia. It will also strengthen the capacity of Cambodia to report on the MEAs implementation in Cambodia.

Project Outcomes and Components

The implementation of the project will achieve two expected outcomes:

Under the first outcome, the project will support the development of national capacities to effectively and efficiently standardize environmental information that is generated on the implementation of the Rio Conventions in Cambodia, and give open-access to this information. In parallel to this, the project will support the strengthening of Cambodia’s capacity to better engage stakeholders and better coordinate the implementation of the Rio Conventions in the country.

Under the second outcome, project resources will be used to improve the use of environmental information for the development of innovative tools supporting decision-making processes related to the implementation of the Rio Conventions. Project support will also include activities to develop the capacity in using this environmental knowledge of national institutions involved in international negotiations at Conventions COPs as well as using this knowledge to produce national reports meeting Conventions reporting obligations.

Responsibilities

1.  Project Board (PB)

The Project Board is the group responsible for making by consensus management decisions for a project when guidance is required by the Project Coordinator (PC), including approval of project plans and revisions. In order to ensure UNDP ultimate accountability, Project Board decisions should be made in accordance to standards that shall ensure best value to money, fairness, integrity transparency and effective international competition. In case a consensus cannot be reached, final decision shall rest with the UNDP Programme Manager (i.e. the Country Director).

Project reviews by the Project Board are made at designated decision points during the running of a project, or as necessary when raised by the Project Manager. The Project Board is consulted by the Project Coordinator for decisions when project tolerances have been exceeded.

Based on the approved annual work plan (AWP), the Project Board may review and approve project quarterly plans when required and authorize any major deviation from these agreed quarterly plans.  It is the authority that signs off the completion of each quarterly plan as well as authorizes the start of the next quarterly plan. It ensures that required resources are committed and arbitrates on any conflicts within the project or negotiates a solution to any problems between the project and external bodies.

Specific responsibilities of the Project Board:

Running a project:

- Review and appraise detailed Project Plan and AWP, including Atlas reports covering activity definition, quality criteria, issue log, risk log and the monitoring and communication plan

- Provide overall guidance and direction to the project, ensuring it remains within any specified constraints

- Address project issues as raised by the Project Director

- Provide guidance and agree on possible countermeasures/management actions to address specific risks

- Agree on Project Manager’s tolerances in the Annual Work Plan and quarterly plans when required

- Conduct regular meetings to review the Project Quarterly Progress Report and provide direction and recommendations to ensure that the agreed deliverables are produced satisfactorily according to plans

- Review Combined Delivery Reports (CDR) prior to certification by the Implementing Partner

- Review each completed project stage and approve progress to the next

- Appraise the Project Annual Progress Report, make recommendations for the next AWP, and inform the Outcome Board about the results of the review

- Provide ad-hoc direction and advice for exception situations when tolerances are exceeded

- Assess and decide on project changes through revisions

Closing the project

- Assure that all Project deliverables have been produced satisfactorily

- Review and approve the final project report, including lessons learnt

- Make recommendations for follow on actions to be submitted to the Outcome Board

- Commission project evaluation

- Notify operational completion of the project to the Project Board

2.  National Project Director

The National Project Director (NPD) supports the project and acts as a focal point on the part of the Government.  This responsibility normally entails ensuring effective communication between partners and monitoring of progress towards expected results.

The National Project Director is the party that represents the Government’s ownership and authority over the project, responsibility for achieving project objectives and the accountability to the Government and UNDP for the use of project resources.

In consultation with UNDP, the Ministry of Environment, as the concerned ministry, will designate the NPD for this project. The NPD will be supported by a full-time Project Coordinator (PC).

Duties and Responsibilities of the NPD

The NPD will have the following duties and responsibilities:

- Assume overall responsibility for the successful execution and implementation of the project, accountability to the Government and UNDP for the proper and effective use of project resources)

- Serve as a focal point for the coordination of projects with other Government agencies, UNDP and outside implementing agencies;

- Ensure that all Government inputs committed to the project are made available;

- Supervise the work of the Project Coordinator and ensure that the Project Coordinator is empowered to effectively manage the project and other project staff to perform their duties effectively;

- Select and arrange, in close collaboration with UNDP, for the appointment of the Project Coordinator (in cases where the PC has not yet been appointed);

- Supervise the preparation of project work plans, updating, clearance and approval, in consultation with UNDP and other stakeholders and ensure the timely request of inputs according to the project work plans; and

- Represent the Government institution (national counterpart) at the tripartite review project meetings, and other stakeholder meetings.

Remuneration and entitlements:

The National Project Director may not receive monetary compensation from project funds for the discharge of his/her functions.

3.  Project Coordinator

The individual contracted as the Project Coordinator will be recruited to coordinate the implementation of the project. 50% of his/her time will be spent on overseeing the implementation of the project and 50% on managing capacity development activities undertaken under the two expected outcomes. The Project Coordinator will also be responsible to monitor and evaluate the progress made by the project. The main tasks for this position include:

- Oversee the day-to-day monitoring of project implementation

- In consultation with stakeholders, recommend modifications to project management to maintain project’s cost-effectiveness, timeliness, and quality project deliverables (adaptive collaborative management) to be approved by the Project Board

- Prepare all required progress and management reports, e.g., APR/PIR and project initiation report

- Support all meetings of the Project Board

- Maintain effective communication with project partners and stakeholders to dissemination project results, as well as to facilitate input from stakeholder representatives as project partners

- Support the independent terminal evaluation

- Ensure full compliance with the UNDP and GEF branding policy

4.  Administrative Assistant

The Administrative Assistant will support the Project Coordinator in carrying out his/her duties, which will include:

- Organizational and logistical issues related to project execution and as per UNDP guidelines and procedures

- Record keeping of project documents, including financial in accordance with audit requirements

- Ensure all logistical arrangements are carried out smoothly

- Assist Project Coordinator in preparing and updating project work plans in collaboration with the UNDP Country Office

- Facilitate timely preparation and submission of financial reports and settlement of advances, including progress reports and other substantial reports

- Report to the Project Coordinator and UNDP Programme Officer on a regular basis

- Identification and resolution of logistical and organizational problems, under the guidance of the Project Coordinator

The Project Assistant will have at least five (5) years’ experience in supporting the implementation of UNDP implemented projects, with preference in environment and natural resource management project.

5.  Project Finance officer

The Finance Officer will ensure timely project delivery, transparent reporting and record keeping, as well as compliance with NIM policies.  The Finance & Operations Officer will work closely with the UNDP CO, which will provide direct support to project implementation.  Responsibilities include to:

Work-planning & Budgeting

- Research and prepare for the Project Director and the Project Coordinator on cost/time estimates to support project activities, ensuring efficiency and cost-effectiveness

- Regular review of the overall project balance ensuring that ultimately cumulative expenditure is within the overall project budget

- Prepare of annual budgets to support the planned activities, ensuring that budgeted amounts and expected disbursement schedules are reasonable, and remaining funds are sufficient

- Draft procurement/recruitment plan to support agreed workplan

- Inform Project Director and Project Coordinator of financial issues affecting project delivery, propose budget revisions/adjustments as necessary

Project Delivery & Reporting

- Execute procurement and recruitment plan, ensuring transparency, cost-effectiveness/efficiency, and compliance with NIM

- Manage payroll and cash reserves of the project

- Prepare quarterly expenditure report, and request cash advance from UNDP (i.e. Fund Authorization and Certificate of Expenditure (FACE))

- Manage financial and administrative aspects of project assets, maintain registers for inventory of non-expendable equipment and ensure that the equipment is safe and in proper working condition, providing regular updates to inform further implementation (e.g. next phase of station installation)

- Prepare financial/operational progress reports for project team, PB, or other meetings

- Identify reporting challenges and make adjustments to internal reporting procedure as necessary to address problems (if any), ensure that the minimum reporting requirements are met

- Ensure documentation and records are up-to-date and complete, meeting audit standards

- Support the regular monitoring, as well as evaluation and audit processes by providing reports, supporting documentation and other information as needed

- Provide information as needed for other purposes or ad hoc requests (e.g. UNDP or donor request, publications, communication materials, etc…)

## Annex 6:  Environmental and Social Review Criteria

## Annex 7:  PPG Status Report

| Project Preparation Activities Implemented | 2013 Expenses |  |  | 2014 |  |  |  |  | 2013-2014 |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Budget | Amount Spend | Commit-ment | Total | Balance | Total budget | Amount Spend | Commit-ment | Total | Balance |
| Act 1:Stakehodler workshop | 19.20 | 11,980.80 | 11,980.80 |  | 11,980.80 | - | 12,000.00 | 12,000.00 | - | 12,000.00 | - |
| Act 2:Baseline study and strategy development - part A – Improved access and generate of information related to the three Rio Conventions | 63.50 | 11,936.50 | 4,062.50 | 6,500.00 | 10,562.50 | 1,374.00 | 12,000.00 | 4,126.00 | 6,500.00 | 10,626.00 | 1,374.00 |
| Act 3. Baseline study and strategy development—Part B—Improved use of information related to the Rio Conventions |  | 12,000.00 | 3,793.56 | 5,687.50 | 9,481.06 | 2,518.94 | 12,000.00 | 3,793.56 | 5,687.50 | 9,481.06 | 2,518.94 |
| Act 4. Secure government commitment |  | 13,000.00 | 13,000.00 |  | 13,000.00 | - | 13,000.00 | 13,000.00 | - | 13,000.00 | - |
| Act 5. Explore co-financing opportunities |  |  |  |  | - | - | - | - | - | - | - |
| Act 6. Develop M &E Plan |  | 13,000.00 |  | 13,000.00 | 13,000.00 | - | 13,000.00 | - | 13,000.00 | 13,000.00 | - |
| Act 7. Develop Sustainability Plan |  |  |  |  | - | - | - | - | - | - | - |
| Act 8. Validation workshop |  | 17,000.00 |  | 17,000.00 | 17,000.00 | - | 17,000.00 | - | 17,000.00 | 17,000.00 | - |
| Act9. Stakeholder meeting |  | 7,000.00 |  | 7,000.00 | 7,000.00 | - | 7,000.00 | - | 7,000.00 | 7,000.00 | - |
| Act 10. Project management |  | 9,000.00 | 3,419.20 | 5,600.00 | 9,019.20 | 19.20 | 9,000.00 | 3,419.20 | 5,600.00 | 9,019.20 | (19.20) |
|  | 82.70 | 94,917.30 | 36,256.06 | 54,787.50 | 91,043.56 | 3,873.74 | 95,000.00 | 36,338.76 | 54,787.50 | 91,126.26 | 3,873.74 |

## Annex 8:  Letter of agreement between UNDP and Government of Cambodia for the provision of support services

Project Title “Generating, Accessing and Using Information and Knowledge Related to the Three Rio Conventions”

Project number 5222

Excellency,

1.	Reference is made to consultations between officials of the Government of Cambodia (hereinafter referred to as “the Government”) and officials of UNDP with respect to the provision of support services by the UNDP country office for nationally managed programmes and projects.  UNDP and the Government hereby agree that the UNDP country office may provide such support services at the request of the Government through its institution designated in the relevant programme support document or project document, as described below.

2.	The UNDP country office may provide support services for assistance with reporting requirements and direct payment.  In providing such support services, the UNDP country office shall ensure that the capacity of the Government-designated institution is strengthened to enable it to carry out such activities directly.  The costs incurred by the UNDP country office in providing such support services shall be recovered from the administrative budget of the office.

3.	The UNDP country office may provide, at the request of the designated institution, the following support services for the activities of the programme/project:

(a)	Identification and/or recruitment of project and programme personnel;

(b)	Identification and facilitation of training activities;

- Procurement of goods and services;

4.	The procurement of goods and services and the recruitment of project and programme personnel by the UNDP country office shall be in accordance with the UNDP regulations, rules, policies and procedures.  Support services described in paragraph 3 above shall be detailed in an annex to the programme support document or project document, in the form provided in the Attachment hereto.  If the requirements for support services by the country office change during the life of a programme or project, the annex to the programme support document or project document is revised with the mutual agreement of the UNDP resident representative and the designated institution.

5.	The relevant provisions of the Standard Basic Assistance Agreement (SBAA) between the Authorities of the Government of Cambodia and the United Nations Development Programme (UNDP), signed by the Parties on May 5, 1987 (the "SBAA") including the provisions on liability and privileges and immunities, shall apply to the provision of such support services. The Government shall retain overall responsibility for the nationally managed programme or project through its designated institution.  The responsibility of the UNDP country office for the provision of the support services described herein shall be limited to the provision of such support services detailed in the annex to the programme support document or project document.

6.	Any claim or dispute arising under or in connection with the provision of support services by the UNDP country office in accordance with this letter shall be handled pursuant to the relevant provisions of the SBAA.

7.	The manner and method of cost-recovery by the UNDP country office in providing the support services described in paragraph 3 above shall be specified in the annex to the programme support document or project document.

8.	The UNDP country office shall submit progress reports on the support services provided and shall report on the costs reimbursed in providing such services, as may be required.

9.	Any modification of the present arrangements shall be effected by mutual written agreement of the parties hereto.

10.	If you are in agreement with the provisions set forth above, please sign and return to this office two signed copies of this letter.  Upon your signature, this letter shall constitute an agreement between your Government and UNDP on the terms and conditions for the provision of support services by the UNDP country office for nationally managed programmes and projects.

Yours sincerely,

________________________

Signed on behalf of UNDP

Ms. Setsuko Yamazaki

Country Director

Date:

_____________________

For the Government of Cambodia

H.E. Say Sam Al, Minister

Ministry of Environment

Date:

Attachment:  Description of UNDP Country Office Support Services

1.	Reference is made to consultations between the Ministry of Environment, the institution designated by the Government of Cambodia, and officials of UNDP with respect to the provision of support services by the UNDP country office for the nationally managed programme or project “Generating, Accessing and Using Information and Knowledge Related to the Three Rio Conventions”, project number 5222.

2.	In accordance with the provisions of the letter of agreement signed and the programme support document (project document), the UNDP country office shall provide support services for the Programme as described below.

3.	Support services to be provided:

| Support services | Schedule for the provision of the support services | Cost to UNDP of providing such support services (where appropriate) | Amount and method of reimbursement of UNDP (where appropriate) |
| --- | --- | --- | --- |
| 1. Support MOE in the identification and/or recruitment of project personnel * Project Coordinator * Finance Officer | August 2014 – July 2017 August 2014 – July 2017 | As per the UPL: US$ 1,420 per case, including recurring cost after hire (i.e. payments) | Should be approved by the Project Board; then UNDP will directly charge the project upon receipt of request of services from the Implementing Partner/Project Board |
| 2. Procurement of goods: * Data show * PCs * Printers | Nov. 2014 – April 2016 | As per the UPL: US$ 1,000 for each purchasing process | As above |
| 3. Procurement of Services Contractual services for companies | Ongoing throughout implementation when applicable | As per the UPL: US$ 1,237 each hiring process | As above |
| 4. Payment Process | Ongoing throughout implementation when applicable | As per the UPL: US$ 41 for each | As above |
| 5. Staff HR & Benefits Administration & Management | Ongoing throughout implementation when applicable | N/A | N/A |
| 6. Recurrent personnel management services: Staff Payroll & Banking Administration & Management | Ongoing throughout implementation when applicable | N/A | N/A |
| 7. Ticket request (booking, purchase) | Ongoing throughout implementation when applicable | As per the UPL: US$ 164.04for each | As above |
| 8. F10 settlement | Ongoing throughout implementation when applicable | As per the UPL: US$ 31.62 for each | As above |
| 9. Support Implementing Partner in conducting workshops and training events | Ongoing throughout implementation when applicable | As per the UPL: US$116 per day (for preparation and during workshop) | As above |
|  | Total: | $34,000 (Up to $19,000 from GEF grant) |  |

4.         Description of functions and responsibilities of the parties involved:

UNDP will conduct the full process while the role of the Implementing Partner (IP) will be as follows:

- The Implementing Partner will send a timetable for services requested annually/ updated quarterly

- The Implementing Partner will send the request to UNDP for the services enclosing the specifications or Terms of Reference required

- For the hiring staff process: the IP representatives will be on the interview panel,

- For Hiring CV: the IP representatives will be on the interview panel, or participate in CV review in case an interview is not scheduled

# PART III:	Co-Financing Letters

Annex A    Co-Financing Letters

UNDP, Government of Cambodia, Project Document: Strengthening Sustainable Forest Management

UNDP, Government of Cambodia, Project Document: Strengthening Sustainable Forest Management

Ministry of Environment, August 2002, Cambodia’s Initial National Communication Under the UNFCCC

Ministry of Environment, October 2006, National Adaptation Programme of Action to Climate Change (NAPA)

, 6 Royal Government of Cambodia, January 2012, National Action Programme to Combat Land Degradation in the Kingdon of Cambodia – 2011-2020

Cooperation Committee for Cambodia, NGO Contributions to Cambodia’s Development 2004-2009.

Ministry of Environment, February 2007, Thematic Assessments and Action Plan for the Three Conventions: CBD, UNFCCC and UNCCD to Contribute to the Poverty Alleviation.

LaoFAB is a document repository using the Google feature “Google Group”. It is a moderated active forum for sharing information about farmers and agribusiness in Laos. Members include Government officials, staff of donor agencies and NGOs, project experts, academics and business people.

See http://www.thegef.org/gef/sites/thegef.org/files/documents/C.40.08_Branding_the_GEF%20final_0.pdf.

UNDP Financial Rules and Regulations: Chapter E, Regulation 16.05: a) The administration by executing entities or, under the harmonized operational modalities, implementing partners, of resources obtained from or through UNDP shall be carried out under their respective financial regulations, rules, practices and procedures only to the extent that they do not contravene the principles of the Financial Regulations and Rules of UNDP.  b) Where the financial governance of an executing entity or, under the harmonized operational modalities, implementing partner, does not provide the required guidance to ensure best value for money, fairness, integrity, transparency, and effective international competition that of UNDP shall apply.

The Project Board has the responsibility to define for the Project Manager the specific project tolerances within which the Project Manager can operate without intervention from the Project Board. For example, if the Project Board sets a budget tolerance of 10%, the Project Manager can expend up to 10% beyond the approved project budget amount without requiring a revision from the Project Board.