United Nations Development Programme

Country:Costa Rica

PROJECT DOCUMENT

Project Title: Capacity building for mainstreaming MEA objectives into inter-ministerial structures and mechanisms

UNDAF Outcome(s): Outcome 4.2: Public, private and civil society will progress in adopting policies and implementing national strategies to consider environmental quality management and integrated management of natural resources, as well as the valuation of environmental goods and services, the protection, conservation and sustainable use of biodiversity. UNDP Strategic Plan Environment and Sustainable Development Primary Outcome:Strengthened national capacities for territorial management, protection and sustainability of natural resources, and management of climate risks UNDP Strategic Plan Secondary Outcome: Strengthened capacities of sectors and strategic territories to promote ecological soundness, emission-neutrality of emissions and the mitigation and adaptation to climate change to 2021

Expected CP Outcome(s): Mechanisms to strengthen capacities for developing policy and legislative frameworks, by integrating provisions of the three Rio Conventions capacity building of local actors in favor of environmental sustainability. Executing Entity/Implementing Partner: Ministry of the Environment and Energy (MINAE) Implementing Entity/Responsible Partners: United Nations Development Programme. Brief Description This project sets outto integrate and institutionalize inter-ministerial decision-making for MEA implementation in Costa Rica, with particular reference to the three Rio Conventions. The project’s strategy emphasizes a long-term approach to institutionalize capacities to meet Rio Convention obligations through a set of learn-by-doing activities to integrate Rio Convention and other key related MEA obligations into a consultative and decision-making process, the revision of one or two select legislation, and the strengthening of management capacities to better implement and enforce the more than 30 pieces of environmental legislation. This project is innovative in that it will take a counter-intuitive approach to meeting Rio Conventions bynot developing any new legislation or policy, but rather, what is actually needed is to help Costa Rica better manage and enforce provisions of existing legislation.

Total resources required		US$ 2,345,000

Total allocated resources	US$ 2,345,000

- UNDP			US$      15,000

- Other:

  - GEF			US$    980,000

  - MINAE		US$    900,000

  - GIZ			US$    350,000

  - LECB			US$    100,000

Programme Period:	2013-2017

Atlas Award ID:	00076472

Project ID:	00087842

PIMS #	5097

Start date:	January 2014

End Date:	December 2016

Management Arrangements: NIM

PAC Meeting Date:  ________________

| Agreed by: |  |  |
| --- | --- | --- |
| Ministry of Environment and Energy (MINAE) | _____________________________________ | _______________ |
|  | René Castro Salazar Minister of MINAE | Date/Month/Year |
| Agreed by: |  |  |
| National Planning and Economic Policy Ministry | _____________________________________ | ______________ |
|  | Roberto Gallardo Minister of MIDEPLAN | Date/Month/Year |
| Agreed by: |  |  |
| United Nations Development Programme | ____________________________________ | ______________ |
|  | Yoriko Yasukawa Resident RepresentativeUNDPCosta Rica | Date/Month/Year |

Table of Contents

Acronyms and Abbreviations	4

PART I - PROJECT	6

A	Project Summary	6

A.1   Project Rationale, Objectives, Outcomes/Outputs, and Activities	6

A.2   Key Indicators, Assumptions, and Risks	7

B	Country ownership	9

B.1   Country Eligibility	9

B.2   Country Drivenness	10

B.2.a	National Capacity Self-Assessment	10

B.2.b	Sustainable Development Context	12

B.2.c	Global Environmental Values	13

B.2.d	Policy and Legislative Context	14

B.2.e	Institutional Context	15

B.2.f	Barriers to Achieving Global Environmental Objectives	18

C.	PROGRAMME AND POLICY CONFORMITY	19

C.1   GEF Programme Designation and Conformity	19

C.1.a	Guidance from the Rio Conventions	22

C.2   Project Design: GEF Alternative	23

C.2.a	Project Alternative	23

C.2.b	Project Goal and Objective	23

C.2.c	Expected Outcomes	23

C.2.d	Project Components, Outputs, and Activities	24

C.3   Sustainability and Replicability	37

C.3.a   Sustainability	37

C.3.b   Replicability and Lessons Learned	38

C.4   Stakeholder Involvement	38

C.5   Monitoring and Evaluation	40

D.	Financing	45

D.1   Financing Plan	45

D.2   Cost-Effectiveness	46

D.3   Co-financing	47

E.	Institutional Coordination and Support	48

E.1   Core Commitments and Linkages	48

E.1.a	Linkages to other activities and programmes	48

E.2   Implementation and Execution Arrangements	48

PART II:	ANNEXES	51

Annex 1:    Costa Rica’s national environmental laws	52

Annex 2:    Capacity Development Scorecard	53

Annex 3:    Logical Framework	60

Annex 4:    Outcome Budget (GEF Contribution and Co-financing)	74

Annex 5:    Provisional Work Plan	77

Annex 6:    Terms of References	86

Annex 7:    Environmental and Social Review Criteria	95

Annex 8:    Costa Rica’s participation in the Low Emission Capacity Building Project	103

Annex 9:   Total GEF Input Budget and Work Plan	105

Annex 10:   PDF/PPG Status Report	109

Annex 11:   Letter of Agreement for Recovery of Direct Project Costs	110

PART III:	GEF Letters of Endorsement and Co-Financing	113

# Acronyms and Abbreviations

| ACM | Adaptive Collaborative Management |
| --- | --- |
| APR | Annual Progress Report |
| AWP | Annual Work Plan |
| BUN-CA | Biomass Users Network of Central America |
| CBD | United Nations Convention on Biological Diversity |
| CCAD | Comisión Centroamericana de Desarrollo (Central American Commission on Environment and Development) |
| CCCD | Cross-Cutting Capacity Development |
| CCD | United Nations Convention to Combat Desertification |
| CI | Conservation International |
| CO | Country Office |
| CONAI | Comisión Nacional de Asuntos Indígenas (National Commission of Indigenous Affairs) |
| CONAGEBIO | Comisión Nacional para la Gestión de la Biodiversidad (National Commission for the Management of Biodiversity) |
| COP | Conference of the Parties |
| DSA | Daily Subsistence Allowance |
| EEG | Energy and Environment Group |
| FONAFIFO | Fondo Nacional de Financiamiento Forestal (The National Forestry Financing Fund) |
| FCCC | United Nations Framework Convention on Climate Change |
| GEF | Global Environment Facility |
| GEF Sec | Secretariat of the Global Environment Facility |
| GIZ | Deutsche Gesellschaft für Internationale Zusammenarbeit (German Society for International Cooperation) |
| IADB | Inter American Development Bank |
| IMN | Instituto Meteorológico Nacional (National Meteorological Institute) |
| INBio | Instituto Nacional de Biodiversidad (National Institute of Biodiversity) |
| IUCN | International Union for Conservation of Nature |
| HR | Human Resources |
| LECRD | Low-Emission and Climate-Resilient Development |
| M&E | Monitoring and Evaluation |
| MAG | Ministerio de Agricultura y Ganadería (Ministry of Livestock and Agriculture) |
| MDGs | Millennium Development Goals |
| MEAs | Multilateral Environmental Agreements |
| MEP | Ministerio de Educación Pública (Ministry of Public Education) |
| MICYT | Ministerio de Ciencia y Tecnología (Ministry of Science and Technology) |
| MIDEPLAN | Ministerio de Planificación Nacional y Política Económica (Ministry ofNational Planning and Economic Policy) |
| MINAE | Ministerio de Ambiente y Energía (Ministry of Environment and Energy) |
| MREC | Ministerio de Relaciones Exteriores y Culto (Ministry of Foreign Affairs and Religion) |
| MSP | Medium Size Project |
| NCSA | National Capacity Self-Assessment |
| NGO | Non-Governmental Organization |
| OAS | Organization of American States |
| PARCA | Plan Ambiental de la Región Centroamericana (Regional Sustainable Development Framework) |
| PB | Project Board |
| PCB | Polychlorinated Biphenyl |
| PSC | Project Steering Committee |
| PIF | Project Identification Form |
| PIR | Project Implementation Review |
| PMU | Project Management Unit |
| RCU | Regional Coordination Unit |
| RTA | Regional Technical Advisor |
| SICA | Sistema de la Integración Centroamericana (Central American Integration System) |
| SINAC | Sistema Nacional de Áreas de Conservación (Conservation Areas National System) |
| TE | Terminal Expenses |
| TPR | Tripartite Project Review |
| UNDAF | United Nations Development Assistance Framework |
| UNDP | United Nations Development Programme |
| UNS | United Nations System |

# PART I - PROJECT

# A	Project Summary

## A.1Project Rationale, Objectives, Outcomes/Outputs, and Activities

- Costa Rica completed its National Capacity Self-Assessment (NCSA) in 2007, the final report of which included a prioritization of capacity development actions by GEF focal area as defined by the three Rio Conventions, as well as those capacity development needs that cut across the three self-same Conventions.  Inparticular, Costa Ricaprioritized the strengthening of national organizational capacities necessary towards having a better understanding of how to more effectively implement the three Rio Conventions and other multilateral environmental agreements (MEAs) within the framework of their existing national legislation.  Recommended activities included better training and sensitization of government decision-makers responsible for rule-making and enforcement, as well as strengthening inter-agency cooperation for improved planning of environmentally sound and sustainable development.

- The rationale for this project stems from the NCSA findings that there a great number (over 30) environment laws and decrees that generate much confusion, impeding Costa Rica’s ability to effectively comply with Convention objectives.  As a result, none of these legal instruments are effectively implemented or enforced, and in certain cases work against each other.  This is further exacerbated by decision-makers and planners not being adequately versed on the excessive legislation.  This is due to a variety of reasons including staff changes and insufficient training.

- This project was developed under the GEF-5 Cross-Cutting Capacity Development (CCCD) Strategy to meet two complementary outcomes:  The first isObjective 3 of the CCCD Results Framework, which sets out to strengthen capacities for policy and legislation development for achieving global benefits.  Objective 4 of the CCCD Results Framework complements Objective 3 by undertaking a set of capacity development activities to strengthen capacities for management and implementation of convention guidelines.

- Through a learning-by-doing process, this project will engage key decision-makers and planners, among other stakeholders, in the critical analysis of Costa Rica’s environmental governance.  Through this process, they will collaborate and negotiate on a shared approach on better approaches to deliver global environmental benefits through improved interpretation, planning, and decision-making on environmental and sectoral policies, plans and programmes from the lens of the three Rio Conventions.  These capacities will be institutionalized by the implementation of select recommendations that will serve to demonstrate the value of this approach through improved/reinforced compliance with Rio Conventions obligations.

- The project is also consistent with the main strategic lines of action of UNDP programming for Costa Rica, specifically with respect to environmental mainstreaming, strengthening environmental sustainability, and contributing to UN Development Assistance Framework (UNDAF) outcome 4.2 to adopting a more integrated approach to environmental management.  Complementing the UNDAF outcomes, the project also conforms to the Millennium Development Goal 7 that seeks to ensure environmental sustainability.  Civil society participation is also a key feature of this project, wherein their stakeholder representatives will be included in the consultative processes to ensure the relevancy, validity, and legitimacy of decision-making, and by extension the institutional sustainability of policy interventions.

- The design of this project takes into account the Costa Rica’s National Development Plan (NDP), which currently serves as the over-arching planning instrument to achieve sustainable development.  Within this framework, the integration of Rio Convention provisions into environment legislation and regulation through better approaches for their implementation and oversight will serve as a catalyst to implement the NDP in a way that not only meets national socio-economic priorities, but also delivers global environmental benefits.  This project also complements the Regional Sustainable Development Framework (PARCA) developed within the cooperation scheme of the Central American Integration System.  This CCCD project will be closely coordinated with key GEF-financed projects, including Costa Rica's work to pursue low-emission and climate-resilient development (LECRD); and the UNDP/GEF project Overcoming Barriers to Sustainability of Costa Rica's Protected Areas System, the IADB/GEF project on Integrated Management of Marine and Coastal Resources in Puntarenas, and the UNDP/GEF project Consolidating Costa Rica’s Marine Protected Areas currently under implementation.

- The project will be nationally executed by the Ministry of Environment and Energy (MINAE) in accordance to agreed policies and procedures between the Government of Costa Rica and UNDP.  With the support of UNDP, MINAE will establish the necessary planning and management mechanisms and facilitate government decision-making to catalyze implementation of project activities and timely delivery of project outputs.  The project was designed to be complementary to other related projects under implementation in Costa Rica, including those supported by the GEF.  Given these, careful attention will be given to coordinating project activities in such a way that activities are mutually supportive and opportunities capitalized to realize synergies and cost-effectiveness.

- This project is particularly innovative in that it does not seek to develop or revise any new environmental laws or decrees.  In of themselves, these legal instruments are not necessarily weak, and given their large number (over 30) there is a general consensus in Costa Ricathat no new instruments are needed.  Instead, this project will target capacity development activities to key decision-makers, planners, and their potential staff replacements on how to better implement (and amend as appropriate) the current set of environmental legal instruments to meet national and global environmental priorities.  This will necessarily call for a re-visiting of how to improve existing consultation and coordination mechanisms, and not create any new ones, taking into account the lessons learned and reality that there simply is no “institutional space” or absorptive capacity for new and additional responsibilities.  This approach is indeed counter-intuitive in that the traditional logic behind mainstreaming is an inherent weakness of the policy and legal framework.  With a long history of environmental and conservation successes, this is not the case for Costa Rica, and this project is intended to “push the envelope” by demonstrating a new and transformative approach to meeting MEA obligations.

- Towards meeting the above-mentioned outcomes, the objective of this targeted cross-cutting capacity development project is: Tostrengthen technical and institutional capacities for more effective decision-making to meet MEA objectives with Costa Rica’s existing environmental legislative framework.  This objective will be met by three coordinated project components:  Component A sets out to assess and strengthen existing consultative and decision-making structures and mechanisms to make more effective and integrated decision on the global environment.  Component B is structured as a set of learn-by-doing formulation of legislative responses and amendments to integrate Rio Convention provisions as well as to design best practices for enforcing current environmental legal instruments to deliver global environmental benefits.  Component C comprises a broader set of capacity development activities that serve to reinforce the resilience and institutional sustainability of project outcomes.  This includes the design and implementation of a comprehensive training programme and public awareness campaign targeted to technical staff, decision-makers, and key conservation and development practitioners.

- The project will take an adaptive collaborative management (ACM) approach to implementation, which calls for stakeholders to take an early and proactive rolein the mainstreaming exercises, as well as to help identify and solve unexpected implementation barriers and challenges.  By taking an ACM approach, project activities and outputs can be more legitimately modified and adapted to maintain timely and cost-effective project performance and delivery.

## A.2   Key Indicators, Assumptions, and Risks

- There are a number of risks to this project, but all are relatively low.  Notwithstanding that Costa Rica will be holding elections in early 2014, this project is designed from an apolitical stance in that it is not calling for any new policy instruments, but rather supporting targeted capacity building efforts at the mid- to high-levels of government where policy interventions, not policies themselves, are being decided, and the technical staffs that will help carry these out.  Project oversight is structured to engage champions that will help mobilize political support at the highest possible level.  The value of this project also lies in building Costa Rica’s absorptive capacity for accessing new and additional support from the international community for advancing more complex strategies for meeting global environmental obligations under the various MEAs to which the government is a signatory.

- Another low risk is the institutional resistance to change.  There are comfort zones within which individuals operate and one recognizes that at times there will be an unwillingness to change the status quo.  At the extreme, this could create concerted efforts against project implementation.  This risk is low because of the careful and protracted consultations undertaken with stakeholders to develop this project.  And yet, to address future potential resistance to change, project implementation arrangements were carefully structured to ensure a transparent and adaptive collaborative management approach.

- Other low risks include the possibility insufficiency of financial resources, lack of conceptual clarity, and institutional bureaucracy to continue key project activities post-project implementation.  These risks will be managed by the project’s hands-on approach by internal actors (decision-makers and planners), who themselves will agree on measured and incremental modification to the existing institutional structures and mechanisms.  A key aspect to the issue of financial sustainability will be a set of activities targeted to more creative approaches to sourcing financing domestically to service the recurrent costs of legislative oversight and enforcement, while developing an adaptive strategy of accessing international donor funds through an alignment of programme objectives and priorities.

3

Technical and management capacities for the global environment

Design and implement a comprehensive training programme and public awareness campaign targeted to technical staff, decision-makers, and key practitioners.

Key Outputs and Activities

- Integrated electronic platform for sharing progress, best practices, and innovations to Rio Convention implementation

- Comprehensive training modules on best practices and innovations for Rio Convention implementation through mainstreamed environmental legislation

- Communication strategy to raise stakeholder awareness on synergies between Rio Conventions and socio-economic development

- Resource mobilization strategy for replicating best mainstreaming practices

- Design and implement a pilot project to demonstrate the synergies and global environmental values of the mainstreaming exercise

- Public dialogues and awareness-raising on integrated MEA and national environmental legislation

Rio Convention provisions integrated into environmental legislation and regulation

Learn-by-doing formulation of legislative responses and amendments to integrate Rio Conventions as well as the design of best practices for enforcing current environmental legislation to deliver global environmental benefits.

Key Outputs and Activities

- Comprehensive analysis of environmental legislation

- In-depth legislative review of soil and forestry laws

- Technical working groups to recommend amendments to soil and forest laws per Rio Convention obligations

- Guidelines for the coordinated oversight and enforcement of environmental legislation

- Strengthened monitoring and compliance for the Rio Conventions

2

Integrated inter-ministerial decision-making process for the global environment

Assess and strengthen existing consultative and decision-making structures and mechanisms to make more effective and integrated decisions on the global environment.  This includes the appropriate councils, commissions, and technical committees.

Key Outputs and Activities

- Comprehensive institutional analysis of environmental decision-making

- Strengthened inter-ministerialcouncil(s)

- Strengthened MEA technical committees

- Strengthened networks with line ministries

- Strengthened civil society participation in decision-making

1

Figure 1:  Summary of Project Components

- Project outcomes will be measured through a set of output, process, and performance indicators.  Constructed using SMART design criteria, these indicators were developed to coincide with each major project activity.  Output indicators include the preparation an in-depth institutional analysis of environmental decision-making and agreed guidelines for the coordinated oversight and enforcement environmental legal instruments per Rio Conventions.  Process indicators include the convening of MEA technical committees that are directly linked to an appropriate Inter-Ministerial Council that serves to reinforce decision-makers’ support of technical and policy recommendations.  Performance indicators include the set of learn-by-doing legislative review of soil and forestry laws to identifying weaknesses and/or conflicts with the Rio Conventions.

# B	Country ownership

## B.1   Country Eligibility

- Costa Rica is eligible to receive technical assistance from UNDP, and is thus eligible for support under the Global Environment Facility (GEF).  Costa Rica ratified the Convention on Biological Diversity (CBD) on 28 July 1994, the Convention to Combat Desertification and Drought on 3November 1994, and the Framework Convention on Climate Change (FCCC) on 4 July 1994.  Costa Rica has also ratified two important protocols under the CBD and FCCC, namely:

- The Cartagena Protocol on Biological Safety on 6February 2007 to protect biodiversity from the risks posed by genetically modified organisms that are the product of biotechnology.

- The Kyoto Protocol was ratified on 9August 2002, committing to stabilize greenhouse gas emissions for the period 2008-2012 at the 1990 level.

- Costa Rica has demonstrated its commitment to becoming a full member of the world community by ratifying the other Multilateral Environmental Agreements (MEAs), and their associated protocols, and amending national legislation to comply with MEA obligations, including:

- Montreal Protocol on Substances that Deplete the Ozone Layer  (ratified in 1991).

- Ramsar Convention on Wetlands of International Importance (ratified in 1992).

- Basel Convention on the Control of Transboundary Movements of Hazardous Wastes and their Disposal (ratified in 1995)

- Stockholm Agreement on Persistent Organic Pollutants (POPs) (ratified in 2007).

- Rotterdam Convention on the Prior Informed Consent Procedure for Certain Hazardous Chemicals and Pesticides in International Trade (Ratified in 2009)

- Fit with the GEF-5 CCCD Strategy:  The GEF strategy for Cross-Cutting Capacity Development (CCCD) projects serves to provide resources for reducing, if not eliminating, the institutional bottlenecks and barriers to the synergistic implementation of the Rio Conventions.  The present CCCD project is consistent with GEF Capacity Development Objectives 3 and 4 of the GEF-Capacity Development Results Framework.  Linked project activities will strengthen Costa Rica’s capacities for policy and legislation development for achieving global benefits (CD-3) as well as capacities to more effectively manage and implement convention guidelines (CD-4).

- Under CD-3, the project will strengthen Costa Rica’s consultative and decision-making processes that will allow a more cost-effective integration and mainstreaming of global environmental priorities into national policy and planning frameworks, and institutionalize these capacities through learn-by-doing mainstreaming exercises.  The institutionalization of these capacities under CD-3 will be further enhanced by strengthening targeted legislation and regulation.  Capacity development activities under CD-4 also serve to strengthen Costa Rica’s underlying capacities to implement and sustaining integrated global environment and sustainable development strategies.  To that end, project activities will strengthen targeted knowledge and management capacities.

## B.2   Country Drivenness

- The present projectis aligned with national priorities and the 2013-2017 United Nations Development Assistance Framework (UNDAF) agreed between the Government of Costa Rica and the UN System Country Team on 17 April 2012.  Specifically, the project will contribute to meeting the following UNDAF outcomes: a) environmental sustainability and risk management; b) strengthened democratic governance; and c) promotion of equality, equity and access to opportunities for human development.  UNDAF is the result of an agreement of the UN System in Costa Rica based on the national priorities and needs, including those defined in the 2011-2014 National Development Plan (NDP) and the country's commitments around the Millennium Development Goals (MDGs), and other international commitments.

- Costa Rica’s NDP is a fundamental instrument with which the government focuses its decision-making, its resource allocation, the construction of regional, sectoral and institutional agendas, the public investment, and international cooperation programmes in the country.  Within this scope, the NDP defines objectives, targets and indicators that allow monitoring and feedback on the institutional management, the evolution of actions and the accountability mechanisms put in place.

- Costa Rica has adopted a number of strategic frameworks, in addition to the three Rio Conventions and other MEAs, which reflects the country´s vast array of environmental priorities.  These include the Alliance for Sustainable Development of Central America, which among others, aims to promote awareness and participation in society by incorporating environmental considerations into the formal education system and non-formal and to develop an implementation strategy for a system of environmental-economic account (SEEA).

- The project is also consistent with the main strategic lines of action of UNDP programming for Costa Rica, specifically with respect to environmental mainstreaming, strengthening environmental sustainability, and contributing to UN Development Assistance Framework (UNDAF) outcome 4.2 to adopting a more integrated approach to environmental management.  The design of this project takes into account the Costa Rica’s National Development Plan (NDP), which currently serves as the over-arching planning instrument to achieve sustainable development.  Within this framework, the integration of Rio Convention provisions into environment legislation and regulation through better approaches for their implementation and oversight will serve as a catalyst to implement the NDP in a way that not only meets national socio-economic priorities, but also delivers global environmental benefits.  This project also complements the Regional Sustainable Development Framework (PARCA) developed within the cooperation scheme of the Central American Integration System.  This CCCD project will be closely coordinated with key GEF-financed projects, including Costa Rica's work to pursue low-emission and climate-resilient development (LECRD); and the UNDP/GEF project Overcoming Barriers to Sustainability of Costa Rica's Protected Areas System, the IADB/GEF project on Integrated Management of Marine and Coastal Resources in Puntarenas, and the UNDP/GEF project Consolidating Costa Rica’s Marine Protected Areas currently under implementation.

### B.2.a	National Capacity Self-Assessment

- Costa Rica completed its National Capacity Self-Assessment (NCSA) in 2007, the final report of which included a prioritization of capacity development actions by Rio Convention as well as those capacity development actions that cut across the three Rio Conventions.  A key need mentioned in the report was the strengthening of governmental capacities in order to have a better understanding of the scope and scale of impactsby implementing MEAs.  Activities included better training and sensitization of government decision-makers responsible for rule making and enforcement, as well as strengthening inter-agency cooperation for improved planning of environmentallysound and sustainable development.

- Costa Rica’s NCSA undertook an analysis of the thematic and cross-cutting challenges, as well as identified priority capacity development needs: the NCSA Final Report had determined that a great number of environment laws and decrees generated much confusion, impeding Costa Rica’s ability to effectively comply with Convention objectives.  The NCSA also pointed out that decision-makers and planners are not adequately versed on the excessive legislation, resulting in the latter poor enforcement.  Another important barrier was the weak linkage between the obligations under the Rio Conventions with key planning tools, such as the National Development Plan, annual work plans, and sectoral strategies, opportunities to deliver global environmental benefits are not seized upon.

- The NCSA concluded that great progress could be made if the proper coordination mechanisms could be established between the most relevant international conventions that emerged from the Rio process.  And yet, this would still not be enough to solve the problem of harmonizing national plans and the myriad of prevailing international commitments.  The problems related to global environmental management are rooted in an overall institutional weakness of environmental governance.  Costa Rica’s compliance with international commitments under the three Rio Conventions does not include actions that clearly link Rio Convention objectiveswith current national development plans.  That is, Rio Convention obligations are not mainstreamed within the sustainable development baseline.  This challenge, once addressed appropriately, would become an opportunity to facilitate the allocation of human, financial, and technical resources to comply with the commitments, as well as to create synergies and achieve cost-effectiveness.

- The main barriers identified during the NCSA process can be summarized as follows:

Systemic

- Inadequate legal framework currently in force to facilitate the Conventions implementation

- Inadequate financial resources for the national implementation of MEAs

- Inadequate economic incentives to catalyze Rio Convention implementation

- Lack of a comprehensive approach to the strategic implementation of the Rio Conventions and creation of synergies

Institutional

- Lack of an effective national programme and institutional mechanisms to ensure a homogeneous framework for allocation of responsibilities, so as to transform the political environmental objectives into services to final users

- Inadequate system for environmental monitoring (lack of an information platform to facilitate the systematization, research and awareness activities related to Environmental commitments)

- Inadequate mechanisms for enforcing the fulfillment of Costa Rica’s obligations under multilateral environmental agreements

- Weak organizational capacity and lack of effective coordination and management at all levels to support Rio Convention implementation

- Inadequate tools and indicators to assess Rio Convention implementation

- Inadequate institutional capacities to address sustainable development policies that go beyond the environmental sector

Individual

- Poor awareness of state officials, specialists, and public at large about national responsibilities associated with the Conventions and their benefits

- Inadequate training of decision-makers and planners of the excessive legislation, resulting in the latter poor enforcement

Figure 2:  Map of Costa Rica

Fig 1: Map of Costa Rica

B.2.b	Sustainable Development Context

- Costa Rica is located in Central America and borders with Nicaragua to the North, Panama to the South, the Atlantic Ocean to the East, and the Pacific Ocean to the West.  With an area of 51,100 km2, it accounts for only 0.03 percent of the earth's surface.  However, it contains nearly 6 percent of the world's biodiversity and is considered to be one of 20 countries with the greatest biodiversity in the world in terms of total number of species.  Costa Rica is also among the few countries with the greatest density of biodiversity (number of species/area) as well as the largest known plant and vertebrate species diversity in Central America.

- Costa Rica is also a higher middle-income country that ranks 62nd out of 169 countries according to the 2012 UNDP Human Development Index.  Its population of 4.4 million people enjoys a literacy rate of 96% and a life expectancy of 79.3 years.  The country has also made significant investments in social services that have led to improved social indicators.

- Notwithstanding, 20.6 % of the population lived in poverty in 2012and the strong social safety net that had been put into place by the government has eroded due to increased financial constraints on government expenditures.  In addition, social inequalities have increased in the last two decades.  The Gini coefficient that measures inequality is now 0.513 (2012 data).  Women, youth, adolescents, indigenous people, persons of African descent, and migrants are subject to large disparities.

- The 2011 census showed significant changes in demographic trends.  Population growth has decreased from an average growth of 2.8%, (1984-2000) to 1.1% (2000-2011).  However, the positive consequences of this demographic have been impaired by the decrease of opportunities.  Although the populationis mostly youngand/or of working age,thecountry faces ademographictransition that willreverse thedependency ratio.  There is a high level of coverage of health services and education for adolescents and young people.  Nevertheless, there is a need to improve access to high-quality services for this segment of the population.

- Prior to the global economic crisis, Costa Rica enjoyed stable economic growth.  The economy contracted 1.3% in 2009 but resumed growth at about 4.5% per year in 2010-12.  While the traditional agricultural exports of bananas, coffee, sugar, and beef are still the backbone of commodity export trade, a variety of industrial and specialized agricultural products have broadened export trade in recent years.  Costa Rica exports thousands of distinctive products to the world and is highly recognized as one of the top 30 leading exporters of high-tech products.

- Tourism continues to be the largest source of foreign exchange, more than banana, coffee and pineapple combined, largely as a result of its impressive biodiversity and extensive system of national parks and protected areas that make it a key destination for ecotourism.  Foreign investors remain attracted by the country's political stability and relatively high education levels, as well as the incentives offered in the free-trade zones.  Costa Rica has attracted one of the highest levels of foreign direct investment per capita in Latin America.  However, many business impediments remain such as high levels of bureaucracy, legal uncertainty due to overlapping and at times conflicting responsibilities between agencies, difficulty of enforcing contracts, and weak investor protection.

- Economic reform is another major factor contributing to Costa Rica’s progress.  The shift away from agricultural exports and cattle farming as the primary model for economic growth was very important for securing environmental progress.  Before the economic crisis in Latin America in the 1980s, Costa Rica’s agricultural policies had focused on guaranteed prices, high subsidies and preferential interest rates.  These incentives had encouraged citizens to expand production to forested areas.  When the economic crisis hit, Costa Rica had to change its development model through several structural adjustment loans.  These forced the country to eliminate subsidies, favorable interest rates and price guarantees in agriculture.  Bank credit for cattle decreased, which coincided with a steep decline in the international price of meat and other commodities.  These structural adjustments, along with the exogenous factor of falling commodity prices, significantly contributed to reducing deforestation rates in Costa Rica by limiting the role of cattle ranching as a prosperous economic activity.  The deforestation rate decreased significantly, from 50,000 hectares per year in the 1970s to 18,000 in the early 1990s.

- Although Costa Rica is an internationally recognized country for its political and environmental achievements, lags and inconsistencies inits environmental policy have accumulated over the years.  The country's leading environmental development in Central America is also the one with the most polluted watershed Isthmus, in spite of having a hydroelectric potential which, for the most part, has not been exploited yet, the country is resorting to the use of oil to generate an increasing proportion of its electricity.  Even though the Costa Rica’s National System of Conservation Areas (SINAC) is an important contribution to the tourism industry, it is not allowed to manage the resources generated and, consequently, the national parks lack of financial, material and human resources for their maintenance and protection.  Costa Rica’spursuit of accelerated economic growth to reduce poverty is through clean and knowledge-based industries rather than through the predatory use of natural resources.

### B.2.c	Global Environmental Values

- Costa Rica’s natural wealth, both in species and ecosystems, is partly explained by its geographical position as Costa Rica serves as a bridge of countless species of animals and plants.  Other factors to consider are the broad expanse of both coasts, a mountain range which provides numerous microclimates and a territorial sea of 589,000km2.  The country harbors three biomes, 20 life-zones, 33 eco-regions, and more than 60 plant formations.  Costa Rica is considered one of only nine countries worldwide with an extremely high diversity of forest ecosystem organisms.  Habitats span from dry tropical forests, rainforests, cloud forests, high mountain wetlands, beaches, coral reefs, lakes, rivers, mangrove forests, swamps, and plains.  In relation to endangered species,amphibians, followed by reptiles, have the highest percentage of threat, last are birds and mammals.  With regard to plants, populations of 1,303 species are threatened or diminished.  Forty species are mentioned as having populations in danger of extinction (mainly orchids), and 18 wood species in danger of extinction were added to the list.  Concerning endemism,Costa Rica presents a moderate level of 1.3% with respect to known species.  The highest level of endemism is found among amphibians, followed by freshwater fish.

- Costa Rica is now the first and only tropical country in the world that has reversed a decades-long process of deforestation.  It was the first country to set a goal to be carbon neutral by 2021, and by most estimates it will be the first to realize this goal.  By protecting forests instead of destroying them, Costa Rica is leading the global effort to mitigate climate change.  Nonetheless, Costa Rica is prone to hurricanes and floods.  There is a need for disaster-preparedness measures, which include gathering data for risk management and implementing age- and gender-sensitive protocols that address the needs of vulnerable populations.

- Another effort to mitigate climate change in the country is the production of electrical power from clean sources such as hydraulic, geothermal and wind.  In 2006, 93.6% of electricity came from these sources, with only a 6.3% produced through thermal power plants.  In this sense, Costa Rica has become a leader in the Central American Region.

- The Republic of Costa Rica is one of the oldest democracies in the Americas.  It is a country proud of its heritage and tradition of negotiation over confrontation, social development over military spending and tolerance over hostility.  It is the home to many international organizations such as the Inter-American Court of Human Rights, the University for Peace of the United Nations and the Earth Council.  Costa Rica abolished its military forces in December 1948 and since then has devoted substantial resources to investment in health and education.  It is a country that has placed a high priority in investing in public education, including the university system, as well as technical and vocational training.

- Today Costa Rica is one of the few developing countries to have adopted a tax on hydrocarbons, partially funding the only national system of payment for environmental services, and becoming the largest buyer of forest carbon in the world.  Moreover, Costa Rica has set the goal to become a carbon-neutral country by 2021.  In 2009, Costa Rica was considered the country with the highest rate of happiness.

### B.2.d	Policy and Legislative Context

- The Costa Rican government is ruled by a series of constitutional controls.  The executive responsibilities rest on the President, supported by two Vice-Presidents and the legislative, which currently comprises a 21-member cabinet selected by the President.  The country has a strong legal system managed by a judiciary, which ensures compliance with national laws.  Costa Rica’s first set of national policies wasdeveloped in the late 1970s, leading to the creation of the first national forest policy and the system of Protected Areas.  The second of national policies deepened the previously established laws in the 1980s, and was followed in the 1990s on a set of policies that focused on the provision of environmental services (Brown, et al, 2011).

- According to the 2011-2014 National Development Plan (NDP), Costa Rica’s development agenda is organized into four areas: a) social welfare; b) public safety and social peace; c) environment and land management; and d) competitiveness and innovation.  Environment is widely considered by Costa Rican legislation leading to its inclusion in 1994 in article 50 of the constitution calling for the right to a healthy and ecologically balanced environment.  The NDP embodies a set of proposals in order to harmoniously articulate the protection of environmental with economic growth.  These include carbon neutrality, the use of clean energy and, in general, the rational use of resources, the commitment to land management that effectively incorporates environmental variables, protection of vulnerable ecosystems and water resources.

- Costa Rica has increasingly developed a clear vocation for the protection of natural resources and the promotion of favorable conditions for sustained human development.  Even before the United Nations Conference on Environment and Development (1992), the country had signed a large number of treaties and international agreements directed towards the preservation of natural resources and environmental protection.  This set of legislation became the main environmental legal framework since there was no previous legislation that specifically integrated a holistic concept of management, conservation and sustainable development of natural resources.

- Costa Rica has signed about 70 international legal instruments that are directly related to the environment and sustainable development.  Constitutionally, international treaties are assigned a value even higher than national laws.  However, the incorporation of new environmental norms into the national legal framework or through international agreements has not been complemented by the creation of an institutional framework that allows for adequate attention and incorporation into the national development plans.

- In spite of the significant progress Costa Rica has made in establishing a broad set of environmental legislation, serious gaps remain between the legal and strategic frameworks and their implementation.  The main barriers to an effective implementation are twofold: poor policy coordination and inadequate mechanisms to learn and apply best practices.  See section B.2.f for further details.

- In 2003, article 9 of the Constitution was amended to state that Costa Rica is not only a representative democracy but a participative one as well.  The Law of the Environment also states that public participation should be promoted by the central and municipal government authorities.  Towards meeting commitment under MEAs, Costa Rica has promoted mechanisms by which civil society, the private sector, and academia can participate in policy implementation at the national level, such as those for the National Conservation Areas System, but still they are scarce, especially when it comes to decision-making.

- With regards to the Rio Conventions, despite having enacted specific policy and legislation, these are neither integrated nor go beyond the sector specific approach to influence other stakeholders.  In 2008 the “blue flag” was created to recognize the efforts the public and private sector with actions to deal with climate change.  In 2009, Costa Rica developed its National Strategy and an Action Plan to orient the activities of the different sectors to increase the competitiveness of the country and reduce the impacts of climate change.  Costa Rica made a commitment to become the first country to be Carbon Neutral by year 2021, and to that end in 2012 developed the Carbon Neutrality country programme.  In mid-2013, a bill was introduced into the Congress to approve a climate change law in Costa Rica.

- Costa Rica has enacted three laws that are directly related to the Convention on Biological Diversity, namely the Wildlife Law (1992), Forestry Law (1995) and the Law on Biodiversity Conservation (1998).  Costa Rica is currently (mid-2013) updating its National Biodiversity Strategy and Action Plan.  Costa Rica ranks among one of the few Mesoamerican countries that have promoted reforestation and forest conservation through a robust Protected Area System and natural resource management legislation.  With respect to land degradation, Costa Rica approved the Law for the Management and Conservation of Soil in 1998.  By means of an Executive Decree, the National Action Plan against Land Degradation was signed in 2009.

- This project is also informed by Costa Rica’s being one of the world’s leaders in the development and application of market-based instruments for environmental management.  Incentives such as subsidized loans, tax credits and direct payments are a few suchinstruments.  These have contributed to Costa Rica’s progress in conservation outcomes through the significant increase in the proportion of land area protected and a significant reduction in the deforestation rate.

### B.2.e	Institutional Context

- The Ministry of Environment and Energy (MINAE) is the central governmental body that oversees the formulation, coordination, and implementation of a key set of Costa Rica´s environmental policies and regulations.  MINAE is the operational focal point institution for the three Rio Conventions and responsible for reporting on their national implementation to the respective secretariats.  MINAE provides leadership in environmental and energy issues, and coordinates the participation of other public and private institutions in the generation and implementation of policies, strategies and actions aimed at meeting national and international objectives.

- The work of MINAE is carried outthrough a number of executive bodies, such as the National Environmental Board, the National Environmental Technical Secretariat, the Environmental Comptroller, the Administrative Environmental Court, and the Environmental Regional Boards.  Departments within MINAE are dedicated to key issues, such as water resources, hydrocarbons, gender, environmental education, citizen participation, biodiversity, wetlands, climate change, and rational use of energy.

- In addition to MINAE, there are 18 other government ministries and two institutions whose executive president has minister rank:  Instituto Mixto de Ayudo Social, whose executive president is Minister of Welfare and Family, and Instituto Nacional de las Mujeres (National Institute of Women), whose executive president is Minister of Women issues.For the purposes of this project, those ministries that are more relevant to the proposed project are outlined in Table 1 below.  Many of these institutions, through various agencies, have Focal Pointsfor various international instruments and have also been involved in environmental policy and natural resource management.  Nevertheless, inter-institutional coordination efforts to comply with international commitments are practically non-existent to date.  Although these are supported by a small number of coordinating commissions, few take a clear and consistent approach to strategically integrating the international commitments within corporate work plans.

- At the highest level, there is the National Environmental Council that advises the President on environmental matters.  By Executive Decree, the current administration gave this council more duties, including proposing strategic and sectoral objectives.  There is a National Biodiversity Management Commission that was created by law and which includesrepresentation of public and private sectors, academia and NGOs.  An Advisory Commission on Land Degradation and an Inter-ministerial Technical Committee on Climate Change were both created by Executive Decree, but communication and coordination between them is rare.

- The efficiency of government actions to fulfilling the nation’s environmental commitments is sub-optimal sincemany of these are shared by the various public institutions and distribution of responsibilities is relatively unclear.  This causesfriction in specific areas between institutions that must attend to them from a substantive point of view, and there are also questions regarding the leadership of other institutions in matters of international policy, e.g., foreign affairs, international trade, and national development planning.

- MINAE in particular, by its governing nature has a series of generic responsibilities in environmental management, is not adequately structured to fulfill these responsibilities in an orderly, integrative, or efficient way.  Liaison functions are distributed among different departments, without adequate coordination despite their points in common.  This contributes to an inefficient use of resources due to unnecessary redundancies as well as gaps in addressing national priorities.

- Research and development are largely represented by major universities, technical institutions,and professional associations that have always actively participated in the environmental issues.  This includes the preparation of key studies and reports.  The private sector, with associations assembled by the Union of Chambers, Association of Private Enterprises, and the Chamber of Industry of Costa Rica, among many others, has also played an important role in the environmental national arena.

Table 1: Costa Rica's line ministries and their mandates as of September 2013

| - Ministry of Environment and Energy (MINAE) | This institution is responsible for environmental management, with authority for coordinating Rio Convention implementation at the national level. The Focal Points for the CBD, CCD, FCCC, and GEF are hosted here. |
| --- | --- |
| - Ministry of Education (MEP) | The MEP is responsible of promoting the development and consolidation of Costa Rica’s educational system allowing access for the entire population to quality education, focused on the development of people and promoting opportunity and social equity. MEP develops national environmental education plans and supports assessments of capacity in training and awareness at all levels. |
| - Ministry of Cattle and Agriculture (MAG) | This ministry is the lead institution of the agricultural sector and focal point for land degradation (CCD). MAG is also responsible for promoting competitiveness and the development of farming and rural areas, in line with environmental protection and productive resources, including catalyzing integration into the international market. |
| - National Planning and Economic Policy Ministry (MIDEPLAN) | MIDEPLAN is in charge of national and regional development plans and promotes national debates. |
| - Ministry of Foreign Affairs (MFA) | The Ministry of Foreign Affairs is the lead agency for foreign relations and defendsCosta Rica’s political, economic and social interests in the international arena. The MFA also ensures that international cooperation is in harmony with national prioritiesand principles. |
| - Ministry of Public Works and Transport (MOPT) | MOPT is responsible for regulating and supporting safe and efficient transportation infrastructure, with the aim of contributing to socio-economic growth. |
| - Ministry of Economy, Industry and Commerce (MEIC) | MEIC´s mission is to promote and protect the principles, criteria, rights and obligations that shape consumer advocacy to foster greater justice, freedom, transparency and equal treatment with consumers in balance with the rights of the trader. |
| - Ministry of Foreign Trade (COMEX) | The role of the Ministry of Foreign Trade is to promote, facilitate and strengthen the inclusion of Costa Rica in the international economy, in order to foster the growth of the country's economy and thus improving the living conditions of all Costa Ricans. |
| - Ministry of Housing and Human Settlements (MIVAH) | MIVAH is the technical body of the government related to housing and land. This ministry issues policies and guidelines related to the needs and demands of different socio-economic strata in order to facilitate access to housing, subject to coordination of comprehensive planning in Costa Rica. |
| - Ministry of Justice and Peace (MJP) | The Ministry of Justice and Peace is composed of different divisions: Social Adaptation; the National Registry; Attorney General of the Republic; and a sub-division on the Culture of Peace. |
| - Ministry of Labor and Social Security (MLSS) | The Ministry of Labor and Social Security is the lead institution for implementing labor policy and social security of Costa Rica. |
| - Ministry of Culture and Youth (MCY) | The MCY aims to promote universal access to culture and art as superior language communication and recognition of the multicultural identity of the Costa Rican society, conducive to improving the quality of life of the population. MCY also invests in entrepreneurship and cultural industries. |
| - Ministry of Public Security (MPS) | This Ministry calls for serving and protecting all human beings to the enjoyment of their rights and freedoms in the national territory, in partnership with the community. |
| - Ministry of Finance (MoF) | The MoF is the body that establishes and implements fiscal policy, and ensures the financial stability of the government bureaucracy. |

- There are numerous non-governmental organizations and associations that serve as important links between the government and civil society, including peasant and indigenous social groups, communal associations and small producers that have also been active participants in many environmental projects and programmes over the last decade.  The Biomass Users Network (BUN-CA)is an NGO that operates regionally to promote the efficient use of natural resources for sustainable energy, as well as helping local communities in job creation, among others.

- Costa Rica’s National Institute of Biodiversity (INBio) is also a public interest NGO that works in close collaboration with different government institutions, universities, the private sector and other public and private organizations to generate, manage, and transfer knowledge and information about Costa Rica’s biodiversity to society.  Another NGO is theMesa Nacional Indígena de Costa Rica MNICR - National Indigenous Platformof Costa Rica) that has been helping to make an impact on indigenous peoples’ issues such as their rights and contributions.

- There are also active community development associations such as the Hojancha Agricultural Committee (CACH) of the forestry sector that works with the participation of local organizations, and which have established municipal nurseries and signed agreements with producers to encourage the planting of trees in farmers’ fields.  There are a number of volunteer organizations (formal or informal groups and non-profit, as well as religious institutions) who direct their work to address the welfare needs of Costa Rica’s poorest population.  There are many indigenous organizations in Costa Rica, such as the cultural associations of the Teribe-Térraba, Sejekto, Bribrí Cabagra peoples.  However, these communal and indigenous associations have not been fully involved in the past in national environmental projects and programmes.

### B.2.f	Barriers to Achieving Global Environmental Objectives

- During the last 25 years environmental policies have been aimed at consolidating the efforts of use, protection and conservation of natural resources, with a strong focus on protected areas and in electricity generation from renewable sources.  Policy coordination and planning mechanisms are currently weak within the Ministry of the Environment and Energy (MINAE) and between the relevant institutions with specific responsibilities in environmental matters, which often overlap in coverage.  In addition to these, coordination is poor with the municipalities and other local communities, which are not effectively represented or engaged in environmental decision-making processes.

- Mechanisms to share national and international best practices and lessons learned are unfortunately inadequate.  Despite the many experiences and achievements that exist to integrate global environmental priorities and objectives into national policy frameworks, these best practices are neither adequately disseminated nor replicated in Costa Rica.  There is a need to establish/strengthen policy and programmatic coordination efforts with international and regional NGOs and research institutes, which play an important role in facilitating and catalyzing international cooperation as well as guaranteeing the effectiveness of investments.  The government is committed to ensuring that the country’s development plans are environmentally sustainable, but the lack of access to these national and international experiences obstructs their implementation.

- The priority capacity constraints encountered by MINAE are related to the development and implementation of the required cross-sectoral mechanisms and instruments.  One opportunity is to consolidate existing consultative mechanisms and strengthen them as a regular part of the National Planning System.  The capacity constraints that prevail at a national level on that regard are posing barriers to the effective implementation of the conventions and hence to addressing global environmental issues of priority concern in Costa Rica.

- One challenge for consultative and decision-making processes is information, without which there is no real participation.  Currently there is no platform to make the information coming from the Rio Conventions available for decision-making processes and planning.  The information is usually kept by the Focal Points and there are no reporting mechanisms for sharing that information.  Another challenge is that the information coming from these conventions is quite technical and complex and not sufficiently (if at all) adapted for different audiences, further marginalizing non-governmental stakeholders from their effective participation in decision-making, especially for local communities, small farmers and indigenous people.

- Although mandated by law, public participation is still thus a challenge for Costa Rica’s environmental management system.  There are a number of consultative mechanisms, mainly in the form of commissions, where there is some participation of the private sector and NGOs, but decision -making remains mainly a government process.  And even with this, the current consultative mechanisms are not formal mechanisms for the structured and managed coordination and preparation for negotiations at the various conferences of the parties of the Rio Conventions, including as mechanisms to strategically disseminate information on new conventions.

- Despite the creation of the National Environmental Council (see paragraph 16), decision-makingon climate change, land degradation and biodiversity conservation is not taken at the highest level.  The relevance of the NEC thus needs to be re-visited and decisions to be taken on whether or not to strengthen this mechanism.

- The majority of these barriers to achieving global environmental objectives in Costa Rica are mostly the result of the lack of awareness and understanding of the Rio Conventions' value at all levels.  The high levels of bureaucracy aggravate this situation, as does legal uncertainty due to overlapping and, at times, conflicting responsibilities between institutions.  The capacity constraints that prevail at a national level on that regard are posing barriers to the effective implementation of the conventions and hence to addressing global environmental issues of priority concern in Costa Rica.

- Counter-intuitively, the high priority that Costa Rica has historically attached to environmental issues is also the cause for inefficient institutional responses to the global environment.  Decision-makers and planners are overly occupied with participating in various environment-related consultative and coordination mechanisms that all such mechanisms have atrophied due to competing demands.  A clear consensus among decision-makers and planners is to address this unanticipated barrier to effective decision-making by further global environmental mainstreaming and reconciling existing policy and programme coordination mechanisms.

- Despite Costa Rica’s history of advancing the environmental conservation agenda globally, institutionally from a MINAE perspective, it does not enjoy the same level of institutional leadership as the other ministries that are more directly responsible for economic development, such as agriculture, energy, and transportation.  Due to the complex, technical and long-term relationships and implications, environmental conservation generally affords decision-makers to think critically and holistically.

- Related to these systemic and institutional barriers, is the relatively high work demand of the Rio Convention Focal Points.  This role is in addition to their regular job requirements, the time demands of which are underestimated.  As a result, MINAE’s organizational and staff structure does not appear to adequately reflect the increasing demand of monitoring and reporting on the Rio Conventions.  As a result, Focal Points are challenged in their ability to monitor the fulfillment of the obligations and to communicate and coordinate with the different stakeholders, to prepare national reports to the Rio Conventions, and to effectively participate in the related conferences of the parties.  Focal Points do not report on a formal basis to a specific authority in MINAE, thus follow up and accountability is scarce.  The issues and positions the Focal Points bring to the COPs are not always the result of a consensus built by different stakeholders or even an official governmental directive.  How the Focal Pointsmanage their agenda depends more on their personal interest and skills.

- Another technical challenge identified in the NCSA and a barrier that remains current today is the technical nature of the subject matter, making it not easily accessible to multiple audiences.  There have been an important number of training initiatives but the capacity built remains insufficient.  This is exacerbated by the lack of a mechanism that takes the policy and technical information from the conventions and makes it available to the public.  Despite the many environmental NGOs working in Costa Rica, public participation in decision-making mechanisms remains a challenge.

- Finance is a challenge that is faced by many countries, and Costa Rica is no exception, especially in the later years.  The budget is alsoincreasingly tight for delegations’ participation in the on-going discussions and deliberations of the Rio Conventions due to competing and pressing national priorities as well as to fulfill all the obligations and priorities set by the international agenda.  As a result, delegations to the COPs are relatively small and with limited capabilities, constraining the opportunities to get themost out of the conferences.

# C.	PROGRAMME AND POLICY CONFORMITY

## C.1GEF Programme Designation and Conformity

- GEF Cross-Cutting Capacity Development is a programme that does not lend itself readily to programme indicators, such as reduction of greenhouse gas emissions over a baseline average for the years 1990 to 1995, or percentage increase of protected areas containing endangered endemic species.  Instead, CCCD projects are measured by output, process, and performance indicators that are proxies to the framework indicators of improved capacities for the global environment.  To this end, CCCD projects look to strengthen cross-cutting capacities in the five major areas of stakeholder engagement, information and knowledge, policy and legislation development, management and implementation, and monitoring and evaluation.

- This project conforms to the GEF-5 Cross-Cutting Capacity Development (CCCD) Strategy, Programme Framework C, which calls for the strengthening of capacities of individuals and organizations to plan and develop effective environmental policy and legislation, related strategies, and plans based on informed decision-making processes for global environmental management, to meet Rio Convention objectives.  More precisely, this CCCD framework provides the vision for CCCD projects to integrate and mainstream Rio Convention (among other MEA) obligations into a country's policy and legislative frameworks, and to underpin these strengthened capacities with strengthening improved management and compliance.

- This project will implement capacity development activities through an adaptive collaborative management approach to engage stakeholders as collaborators in the design and implementation of project activities that take into account unintended consequences arising from policy interventions.  The project is also consistent with the programmatic objectives of the three GEF thematic focal areas of biodiversity, climate change and land degradation, the achievement and sustainability of which is dependent on the critical development of capacities (individual, organizational and systemic).  Taking into account the cross-cutting capacity development challenges and barriers assessed in the NCSA and outlined in sections B.2.a	National Capacity Self-Assessment and B.2.f	Barriers to Achieving Global Environmental Objectives.

Table 2:  Conformity with GEF Capacity Development Operational Principles

| Capacity Development Operational Principle | Project Conformity |
| --- | --- |
| - Ensure national ownership and leadership | The essence of this project is rooted in the belief that global environmental issues can best be addressed if local people are involved and direct community benefits and ownership are generated. Thus, the development of the present project includes consultations with relevant stakeholders of the following sectors of Costa Rica: NGOs, academia, the Government, the Civil Society, among others. These consultations included a dialogue on the capacity development needs:a basic consensus on assumptions and the capacity development strategy of the Project, as well as the clarity on the sequence and timing of its activities. |
| - Ensure multi-stakeholder consultations and decision-making | Preliminary consultations have already identified the stakeholders groups, namely research and academic institutions, NGOs, training centers, as well as business associations and key development practitioners, each with their own particular comparative advantages, to ensure a holistic approach to the integration of global environmental priorities into national development frameworks. This includes contributing to the identification and development of strategic policy and programmatic gaps to meet Rio Convention objectives, as well as to both deliver and receive training to better understand and operationalize integrated global/national environmental and development strategies, programmes and plans. The further narrowing of the targeted groups and their representatives will be undertaken through an open consultative to re-affirm and strengthen their commitment to project objectives and goals. |
| - Base capacity building efforts in self-needs assessment | Building on the existing capacities and those developed as part of the NCSA consultative process, the project will strengthen a policy dialogue process to catalyze effective consultation and collaboration in a cost-effective manner. This project will strengthen capacities of the MINAE, and the Local Government to effectively coordinate the policy decisions and catalyze implementation pertaining to the three Rio Conventions, as it was identified as a top cross-cutting capacity priority in the Costa Rica NCSA. |
| - Adopt a holistic approach to capacity building | The project will assess and structure an improved consultative and decision-making process that will operationalize integrated decision-making to achieve both national and global environmental objectives: this will be achieved by institutionalizing a holistic approach to policy coordination, and strengthening associated human capacities to manage this process. The project will also seek to address the priority barriers to implement the three conventions, particularly by strengthening cooperation among the various governmental units to develop policies and programmes and implement legislation that reduce the overlapping relationships among biodiversity, climate change, and land degradation. |
| - Integrate capacity building in wider sustainable development efforts | By integrating MEAs into an approved National strategy to national legislation and policies of Costa Rica, this project will lead to regional and local policies across the country that will effectively watch over sustainable use of natural resources, leading to benefits to local population. |
| - Promote partnerships | This project calls for the re- structuring of organizational relationships, promoting and forging stronger relationships, partnerships and commitments. By doing so, improved coordination and collaboration should reduce overlap and duplication of activities, catalyze the effective and efficient exchange of information, and improve the country’s implementation of the three Rio Conventions. Also, by raising public awareness, building partnerships, and promoting policy dialogue, the project will seek to promote an enabling environment within its government ministries and agencies, as well as with the civil society, academic and research institutes, NGOs and the private sector, for achieving sustainable development and addressing global environmental issues. |
| - Accommodate the dynamic nature of capacity building | The project's implementation arrangements include the coordination among different initiatives that will be managed through the support of the National Focal Points to the Rio Conventions and the inter-sectorial monitoring of the National GEF Focal Point (MINAE). Furthermore, bi-monthly meetings with project coordinators working on related initiatives will be held in order to analyze synergy opportunities, challenges and lessons learnt. A Project Board that includes MINAE and MIDEPLAN will convene regularly (once every four months and as needed) to oversee the performance of capacity development activities, manage risks, and to approve appropriate modifications to the project activities. |
| - Adopt a learning-by-doing approach | By providing resources to try out concrete and innovative efforts, the project creates the needed learning within its community: Stakeholders of Costa Rica, including civil society will be involved in the collaborative review, analysis for formulation of recommendations for the various sectoral analyses to implement solutions. The learning-by-doing approach will also be instituted through the implementation of selected recommended policy reforms of the respective sectoral analyses. |
| - Combine programmatic and project-based approaches | This project, by its very nature, promotes local ownership and equal partnership, as well as a cross-sectoral vision. Issued by the NCSA findings, which had a bottom-up approach to develop a national environmental policy, the proposed project is intended to assist the progress of maximizing synergies among the policies, rules and decision-making procedures governing the management of climate change, land degradation and biodiversity, among other environmental issues, for an effective national environmental framework. It will seek to reinforce institutional capacities to manage and implement global conventions and improve technical capacities, skills and attitudes of stakeholders and other key participants of different sectors of the society. |
| - Combine process as well as product-based approaches | This project will follow the process of applying adaptive collaborative management to allow project activities to be flexible to changing circumstances while maintain consistency to agree project objectives; and wherever appropriate, ensuring that stakeholders receive an equitable sharing of benefits to sustain their interest, commitment and accountability of project activities, outputs, and outcomes. Since the NCSA phase, this project has involved many multi-stakeholder representatives, and it will continue to engage champions that will have a leading role in the present phase in order to implement sectoral policy recommendations and actions. |
| - Promote regional approaches | This national project, by integrating MEAs into an approved national strategy to national legislation and policies, will lead to regional and local policies across the country that will effectively watch over sustainable use of natural resources, leading to benefits to local population. It is also complementary with the Regional Sustainable Development Framework (PARCA) developed within the cooperation scheme of the Central American Integration System. |

### C.1.a	Guidance from the Rio Conventions

- Costa Rica is fully committed to meet its obligations under the MEAs and the proposed project is intended to facilitate an important step towards developing the capacities for an effective national environmental management framework.  This project will address the shared obligations under the three Rio Conventions, which call for countries to strengthen their national capacities for effective national environmental management framework.  This project will address a set of Rio Convention articles (see Table 3) that call for improved stakeholder engagement to address global environmental issues.  Specifically, the project will strengthen Costa Rica's environmental governance for the global environment by targeting capacity development towards reconciling and harmonizing environmental legal instruments for a better understanding of how to strategically implement national environmental legislation to support global environmental objectives.  The project approach will build upon the 11 capacity development operational principles (see table 2 above) in its implementation arrangements to deliver technical and institutional capacities.  Although a number of capacity needs that cut across the three Rio Conventions will be developed, this project focuses on a targeted set of capacities that aim to strengthen Costa Rica’s environmental governance (See table 3).

Table 3:  Capacity Development Requirements of the Rio Conventions

| Type of Capacity | Convention Requirements | FCCC | CBD | CCD |
| --- | --- | --- | --- | --- |
| Stakeholder Engagement | Capacities of relevant individuals and organizations (resource users, owners, consumers, community and political leaders, private and public sector managers and experts) to engage proactively and constructively with one another to manage a global environmental issue. | Article 4 Article 6 | Article 10 Article 13 | Article 5 Article 9 Article 10 Article 19 |
| Organizational Capacities | Capacities of individuals and organizations to plan and develop effective environmental policy and legislation, related strategies, and plans based on informed decision-making processes for global environmental management. | Article 4 Article 6 | Article 8 Article 9 Article 16 Article 17 | Article 4 Article 5 Article 13 Article 17 Article 18 Article 19 |
| Environmental Governance | Capacities of individuals and organizations to enact environmental policies or regulatory decisions, as well as plan and execute relevant sustainable global environmental management actions and solutions. | Article 4 | Article 6 Article 14 Article 19 Article 22 | Article 4 Article 5 Article 8 Article 9 Article 10 |
| Information Management and Knowledge | Capacities of individuals and organizations to research, acquire, communicate, educate and make use of pertinent information to be able to diagnose and understand global environmental problems and potential solutions. | Article 4 Article 5 | Article 12 Article 14 Article 17 Article 26 | Article 9 Article 10 Article 16 |
| Monitoring and Evaluation | Capacities in individuals and organizations to effectively monitor and evaluate project and/or programme achievements against expected results and to provide feedback for learning, adaptive management and suggesting adjustments to the course of action if necessary to conserve and preserve the global environment. | Article 6 | Article 7 |  |

## C.2  Project Design: GEF Alternative

### C.2.a	Project Alternative

- This project takes a very incremental approach from a GEF construct towards strengthening Costa Rica’s environmental governance to meet Rio Convention objectives.  In the absence of this project, Costa Rica would continue to govern its environment through the existing set of legislation with mixed results.  While these results would provide global environmental benefits, they would do so at a higher transaction cost than through the proposed GEF Alternative.  Government staff would remain insufficiently knowledgeable about how to fully understand the implications of global environmental directives under the conferences of the parties on national environmental and development policies, and how these directives can be strategically implemented through existing national environmental legislation.  The barriers to meeting and sustaining global environmental outcomes are described in section B.2.f.

- Under the GEF Alternative, a targeted set of governance barriers and related technical and institutional capacities will be thoroughly assessed and modified to reduce the contradictions between environmental legislation, such as protected area and biodiversity conservation laws that do not adequately protect wildlife from ecotourism activities.  That is, the outcome of this project lies in its innovative and transformative approach to mainstreaming the Rio Conventions within existing national environmental and development policies and legislation.  This project will test the assumption that the existing policy and legislative baseline may be adequate to deliver global environmental objectives if sufficient institutional and technical capacities are appropriately strengthened.

- Through a learning-by-doing process, this project will engage key decision-makers and planners, among other stakeholders, in the critical analysis of Costa Rica’s environmental governance.  Through this process, they will collaborate and negotiate on better approaches to deliver global environmental benefits through improved interpretation, planning, and decision-making on environmental and sectoral policies, plans and programmes from the lens of the three Rio Conventions.  These capacities will be institutionalized by the implementation of select recommendations that will serve to demonstrate the value of this approach through improved/reinforced compliance with Rio Conventions obligations.

- Activities under this project are easily discernable as delivering either global environmental benefits or sustainable development benefits that Costa Rica should undertake in its own national self-interest.  The allocation of the GEF increment and co-financing to each activity is therefore a best estimate of how much of the GEF increment is needed to complement the baseline and co-financing that was leveraged to implement the project.

### C.2.b	Project Goal and Objective

- The goal of this project is tointegrate and institutionalize inter-ministerial decision-making for effective and sustainable MEA implementation through existing national environmental legislation.  To this end, the objective of this project is to mainstream the international commitments derived from the Rio Conventions into targeted national environmental legislation, and to do so by a learn-by-doing process that will institutionalize a long-term process for effective environmental governance.  The objective of this project is in line with the CCCD strategy of mainstreaming Rio Conventions into the national sustainable development baseline as a strategic approach to institutionalize national efforts that deliver global environmental benefits.  Annex 3 provides a logical framework of the project that deconstructs the project objective into component outputs and activities.

### C.2.c	Expected Outcomes

- At the end of the project, activities will have resulted in a targeted set of improved capacities to meet and sustain Rio Convention objectives.  This project will have strengthened and helped institutionalize commitments under the Rio Conventions by demonstrating practicable and cost-effective approaches to better implementing, monitoring and enforcing national environmental legislation to increase delivery of global environmental benefits.  Another project outcome is the revision of existing (not the drafting of new) national development and environmental strategies, plans, and programmes that will support a more harmonized approach to implement existing environmental legislation.  Guidelines will be developed to help decision-makers and planners apply legislation, and these will be tested for two select pieces of legislation.

- Through its learn-by-doing approach, the project will strengthen the technical capacities of government staff on their understanding of the various environment-related legislation, their overlap, conflicts, synergies, and how to reconcile these with Rio Convention priorities and obligations.  The project will strengthen and institutionalize a process by which government staff themselves are better able to continue long-term analyses and follow-up with appropriate actions.  Another institutional barrier that limited sharing, collaboration, and coordination is through the mandates of the relevant departments and agencies.  This process will be reflected in two ways: the first is by strengthening the inter-agency coordination and information sharing.  A second institutional outcome is the strengthened networking that the project will have facilitated by formalizing a more effective way for NGOs and civil society to make a better contribution to the decision-making process on environmental issues, with the expectation that the global environment will be better conserved.

### C.2.d	Project Components,Outputs, and Activities

Component 1:	Integrated inter-ministerial decision-making process for the global environment

- This first component focuses on assessing and structuring an improved consultative and decision-making process that effectively integrates global environmental objectives into existing national environmental legislation.  Without having to create any new environmental legislation, the project will make it easier for decision-makers to interpret and agree on how best to monitor and enforce environmental legislation that not only meets national priorities, but also global environmental obligations.  This component will focus on the processes to facilitate these decisions, whereas component 2 will focus on strengthening stakeholders’ and decision-makers’ knowledge and technical capacities towards the same result.  This component will also include strengthening the process by where expert interpretations from non-governmental stakeholders, such as NGOs, civil society, private sector and academia can provide their knowledge through the technical committees and other relevant mechanisms to be decided by the project.

- This project makes the assumption that more information and knowledge will help ensure a more holistic understanding of environmental legislative needs.  However, because so much information can be overwhelming and requires careful management, this component focuses on the institutional process to manage this knowledge.  To be clear, this project will not address management information system needs, as the project will build upon its existing baseline.  This includes strengthening how the various government ministries, agencies, and departments collaborate and coordinate with each other.

Expected Outcome 1:	Improved decision-making mechanisms for the global environment

Output 1.1:	Strengthened MEA technical committees

- This output focuses on strengthening the mechanism by which technical information is made available to decision-makers, which will be through the strengthening of existing MEA technical committees.  The surveys are part of this output because they will inform the structuring of the technical committees as well as the learn-by-doing capacity building that will take place under component 2.  The MEA technical committees will include membership of key representatives of these non-state actors, recognizing that membership should be dynamic on the basis of the specific issues of the meeting to be convened (see activity 1.1.2).

1.1.1:	Carry out surveys of line ministry staff on their awareness and understanding of environmental laws and the Rio Convention provisions.  The survey will take place at the beginning of the project to assess current awareness and will be compared with a similar survey taken near the end of the project to assess the extent to which the project has built awareness and understanding of Costa Rica’s environmental legislation from a Rio Convention perspective.  The baseline survey will inform the structuring of the MEA technical committees (activity (1.1.2) and Inter-Ministerial Council (activity 1.3.1) and their recommendations.  This activity will also be conducted in conjunction with the broader surveys on non-government decision-makers and planners that will be undertaken as part of activity 3.2.1.  Both sets of surveys will also inform the learning-by-doing by planners and decision-makers that will take place under Component 2.  The surveys and their analysis will also be coordinated with similar activities to be undertaken under the LECB project under Results 1.

Target indicator:	Baseline survey of decision-makers’ and planners’ awareness carried out with N>100 participants, completed by month 4of the project.

Target indicator:	Year-end survey of decision-makers’ and planners’ awareness carried out with N>250 participants, completed by month 32 of the project.

1.1.2.  	Organize and convene MEA technical committee meetings to discuss and recommend best environmental decision-making practices, with particular attention to a holistic approach to implementing environmental legislation that will also meet global environmental obligations.  In particular, the technical committees will review and endorse, as appropriate, the technical recommendations subsequent approval by the Inter-Ministerial Council (output 1.2).

Target indicator: 	Three (3) MEA technical committees (CBD, CCD, and FCC) are created by month 4with a membership of expert stakeholder representation of at least 10 different stakeholders (government, NGOs, academia, private sector, and civil society).  The technical committees will meet at least three (3) times per year.

Target indicator: 	MEA technical committees submit technical recommendations to line ministries, agencies at least twice (2) a year, the first by month 9.

Target indicator: 	MEA technical committees submit policy recommendations to inter-ministerial council at least twice (2) a year, the first by month 9.

Output 1.2:	Strengthened information sharing agreements with academia and civil society

- Complementing the need for ministries, their agencies and departments to share data and information for more informed planning and decision-making on the global environment, the expertise from non-state actors is also invaluable given their targeted investments in research and support to communities.  This output focuses on catalyzing increased and improved support from these social actors.  In addition to making access to information easier, this output would help increase the role of these organizations as partners of development.  While this is not the direct aim of this project, this output will make an important contribution by raising the level of these non-state actors in the consultative and decision-making processes.  A first step is to secure a clear agreement between and among the ministries and the non-state actors on the mutual sharing of data and information, with particular emphasis on that which is needed for a holistic approach to environmental planning and decision-making.

Activities:

1.2.1	Carry out an in-depth baseline analysis of information needs for the global environment, their sources, and existing mechanisms by which this information is made available to planning and decision-making.

Target indicator:	An in-depth baseline analysis carried out and substantively peer reviewed by at least 8 national experts, and completed by month 5 of the project.

1.2.2	Building on the recommendations of the MEA technical committee and the technical working groups (activities 1.1.2 and 2.2.1 respectively), as well as the in-depth baseline analysis of 1.2.1, prepare a feasibility study that structures an improved electronic information-sharing mechanism with an internet interface to facilitate easy access to lessons learned and best practices, including those identified under activity 2.2.3.  This will be carried out and implemented in conjunction with the feasibility study on the environmental legislation website of activity 3.5.1.

Target indicator:  	Feasibility study for the strengthening of an existing electronic platform and internet interface prepared and completed by month 7.  This will include a financial plan.

Target indicator:  	Undertake an independent assessment of the performance of the electronic information system as implemented under 3.5.1 by month 30.

Target indicator:  	Agreement signed by MINAE and key non-state actors on the sharing of information by month 18

Output 1.3:	Re-invigorated Inter-Ministerial Council meetings

- The Inter-Ministerial Council serves as the key existing decision-making mechanism for making institutionalizing the best practices through policy decisions, which in the case of this project means the strategic implementation and enforcement of existing environmental legislation.  Under this output, cooperative agreements will be negotiated among government ministries, agencies and departments to agree on information-sharing modalities, collaborations, and coordination of programme and project activities, all within the framework of meeting global environmental obligations through their respective mandates, authorities, and responsibilities.  One of the first decisions to be confirmed during project implementation is to confirm the Costa Rican National Environmental Council as the Inter-Ministerial Council and the existing Rio Convention-specific advisory commissions as the linked technical committees.

Activities:

1.3.1:	Negotiate and facilitate cooperative agreements with Inter-Ministerial Councilmembers and other line ministries.  The Inter-Ministerial Council will discuss the respective mandates and authorities of the key ministries’ as well as the legislative instruments for which they are responsible.  Upon the advice of the MEA technical committees of output 1.1, the Inter-Ministerial Council will negotiate and agree on streamlining their legislative oversight, and follow-up with memoranda of understanding and/or cooperative agreements, as appropriate.

Target indicator:	Key ministries sign relevant agreements by month 12.

1.3.2:	Convene Inter-Ministerial Council meetings to follow-up on policy recommendations of the MEA technical committees (activity 1.1.2).  This includes the policy and programme recommendations for the strategic implementation of existing environmental legislation (activity 2.2.4) and the new guidelines for monitoring and compliance of environmental laws (activity 2.3.7).

Target indicator:	The Inter-Ministerial Council meets twice (2) per year to discuss and approve MEA technical committee recommendations, and before month 9 of the project.

Target indicator:	At least 80% of the MEA technical committee recommendations are supported by appropriate inter-ministerial decisions by month 34.

- Figure 3 below outlines the flow of analysis, consultation and decision-making between the Rio Convention technical working groups (output 2.2), the MEA technical committees (output 1.1) and the Inter-Ministerial Council (output 1.3), respectively.

FCCC Technical Working Group

CCD Technical Working Group

CBD Technical Working Group

CCD Technical Committee

FCCC Technical Committee

CBD Technical Committee

Inter-Ministerial Council

Approves policy recommendations

MEA Technical Working Groups

- Identifies best practices based on lessons learned

- Drafts technical guidelines

- Recommends innovative approaches

MEA Technical Committees

- Reviews and endorses technical guidelines of the MEA technical working groups

- Negotiates programme coordination

Figure 3:		Relationship between working groups, technical committees, and the Inter-Ministerial Council

Component 2:	Integrating cross-cutting Rio Convention provisions into environmental legislation

- This second component is structured as a set of learn-by-doing formulation of legislative responses and amendments (as appropriate) to implement Rio Convention provisions as well as to identify and apply best practices for enforcing current environmental legal instruments to deliver global environmental benefits.  This will be addressed through three streams of activities:  The first is through a comprehensive analysis of all Costa Rica’s environmental regime (legislation, regulation, statutes, decrees, and institutional structures and mechanisms.  This analysis will complement the targeted analysis of 1.2.1 on the flow of information from non-state actors to planners and decision-makers.  The second stream of activities picks up where the first stream leaves off and focuses on two pieces of environmental legislation to pilot and test their differentiated implementation and enforcement from a Rio Convention perspective.  The third stream of activities focuses on the development of monitoring and compliance guidelines, building upon the analysis of output2.1 and the testing of output 2.2.  The latter will include training on monitoring and compliance best practices and innovations.

Expected Outcome:	Environmental legislation better serves Rio Convention obligations

Output 2.1:	In-depth analysis of environmental legislation and its governance

- The analysis to undertaken in this output actually consists of three distinct sets of analyses, mirroring the National Capacity Self-Assessment (NCSA) approach.  A first set of analyses will be three independent analyses and interpretations of how Costa Rica’s environmental legislation affects each of the three Rio Conventions.  These three analyses will be discussed and debated in the MEA technical working groups in parallel and then synthesized and integrated into one comprehensive report that highlights the contradictions, synergies, mutual exclusions, and gaps with respect to meeting Rio Convention obligations.  This latter report will be a fourth specific deliverable.  Each of the four analytical reports will be discussed in an open-ended stakeholder dialogue, followed by endorsement and appropriate policy recommendations by the MEA technical committees, and subsequently for the Inter-Ministerial Councilto legitimize policy recommendations, as appropriate.

Activities:

2.1.1:	Identify and secure independent peer reviewers.

Target indicator:	Identify an independent set of peer reviewers not involved in the preparation of analytical reports and legislative recommendations prepared under the project.  The review process will mirror the GEF Scientific and Technical Advisory Panel process, with each report requiring three independent reviews.  A roster of peer reviewers with minimum 30 experts is created by month 3.

2.1.2.	Prepare Rio Convention legal analytical framework.  This framework would be used to cross-reference and assess the coverage of Rio Convention obligations through Costa Rica’s national environment-related legal instruments (activity 2.1.3).

Target indicator:	Analytical framework prepared and completed by month 6.

Target indicator:	At least five (5) independent peer reviewers rate the framework of high quality.

2.1.3:	Using the Rio Convention legal analytical framework, undertake an analysis of Costa Rica’s environmental legislation and their compliance.  Particular attention must be given to socio-economic impacts, including impacts differentiated by gender and youth.  A separate analysis will be prepared for each of the three Rio Conventions and a fourth will be reconcile critically the three analyses into a synthesis report.

Target indicator:	Four (4) in-depth analyses (CBD, CCD, FCCC and Synthesis of the three) of Costa Rica’s environmental governance from a Rio Convention perspective.  All analyses will be completed by month 10.

Target indicator:	The analytical report that synthesizes all three Rio Conventions is endorsed by all members of the MEA technical working groups and the MEA technical committee by month 12.

Target indicator:	MEA technical committee drafts policy recommendationsfor the Inter-Ministerial Councilby month 14.

2.1.4:	Convene four (4) stakeholder constituent dialogues.  These dialogues are to be convened to present the technical findings of the expert analyses and results of the MEA technical working groups before they are discussed and endorsed by the MEA technical committees.  The stakeholder constituent dialogues to be convened under this and other project activities will ensure national and regional representation.  As with activity 2.1.3, particular attention must be given to understanding the socio-economic, gender, and youth impacts of environmental legislation enforcement (or lack thereof).  This activity will be coordinated with the LECB project, in particular Result 2 that will organize consultation workshops with interested stakeholders.  During project implementation, the timing of these four stakeholder dialogues will be decided to optimize synergies with the LECB and other appropriate stakeholder consultations.

Target indicator:	All reports are discussed and validated at open-ended stakeholder dialogues within two months of their completion.

Target indicator:	Each stakeholder constituent dialogue is attended by at least 30 representatives that cover the range of stakeholder views and perspectives.

Target indicator:	Each stakeholder constituent dialogue endorses the analyses and offers broad support for endorsement by the MEA technical committee and subsequent approval by the Inter-Ministerial Council.

Target indicator:	At least two (2) stakeholder representatives from each of the seven (7) provinces have participated in at least one of the stakeholder constituent dialogues by month 33.

Output 2.2:	Learn-by-doing integration of Rio Conventions into select environmental legislation

- Through a learning-by-doing process, the set of activities under this output will engage key decision-making champions and other stakeholders to collaborate and negotiate legislative interpretations and reforms.  In particular, technical staffs from government ministries, agencies, and departments will work together to agree on new and better approaches to meet Rio Convention obligations through their coordinated and differentiated implementation, monitoring, and enforcement of the environment-related legislation for which they are responsible.  They will draft the technical recommendations that the MEA technical committee will review and endorse, as well as the appropriate decision texts for approval by the Inter-Ministerial Council.

Activities:

2.2.1	Associated with the MEA technical committee meetings of 1.1.2, structure technical working group meetings of expert government and non-state actors from academia, research institutions, private sector, civil society and other organizations, as appropriate, to discuss how their particular programmes and projects that are relevant to the three Rio Conventions are either supported or hindered by existing environment-related legislation.  These technical working groups will meet at least twice (2) per year to discuss lessons learned and best practices of how expert knowledge is informing decision-making on the global environment (see activities 2.2.3).  These technical working groups will also be charged with the collective drafting of technical, programme, and policy recommendations that will go before the MEA technical committees and the Inter-Ministerial Council.  The work under this set of activities will be closely coordinated with the Low Emission Capacity Building (LECB) project, specifically Result 3 on the development of Measurement, Reporting, and Verification (MRV).

Target indicator:	Three technical working groups, one for each Rio Convention, are created and meet by month 7 of the project, and at least twice (2x) per year for the each of the three years of project implementation.

Target indicator:	Technical working groups present their findings and recommendations to the MEA technical committees by month 9 in the first instance, including the best appropriate electronic platform (see activity 1.2.3), and subsequently within one month of convening.

Target indicator:	Members of the technical working group draft a non-legally binding agreement on the mutual sharing of information among each other and with the government by month 12 of the project.

2.2.2:	Pilotthe implementation of policy recommendations of the Inter-Ministerial Council (activity 1.3.2).  Instead of the regular business-as-usual approach to monitoring and enforcing environmental legislation, the recommendations to emphasize alternative interpretationsin favour of Rio Convention objectives that remain legitimate will serve as a series of test cases of better decisions for the global environment.  The work under this set of activities will be closely coordinated with the LECB project, specifically Result 2 on the formulation and piloting of nationally appropriate mitigation actions.  Three policy recommendations will be selected for piloting: one targeted for each of the three Rio Conventions, and for which US$ 25,000 will be allocated for implementation over a 12 month period.

Target indicator:	Three policy recommendations piloted and completed by month 26.

2.2.3:	Identify best practices and cull lessons learned from pilot exercises.  This activity focuses on pushing the envelope with respect to new and improved ways to meet Rio Convention obligations through existing environmental legislation.  While best practices and innovative approaches will be identified through the expert analyses conducted under activity 2.1.3, this activity focuses on learning lessons and determining best practices from the pilot implementation of recommendations made and approved by the MEA technical committees and the Inter-Ministerial Council respectively (activity 2.2.2).  The work under this set of activities will be closely coordinated with the LECB project, specifically Result 2 on the lessons learned.

Target indicator:	Government agencies and departments responsible for testing policy recommendations submit quarterly progress reports to the MEA technical committees every three months with the first no later than month 12.

Target indicator:	Two (2) expert workshops with at least 30 relevant key actors each, organized and concluded by month 18

Target indicator:	Three (3) best practice and lessons learned reports are prepared on targeted regional Rio Convention mainstreaming activities by month 12, month 23, and month 33

2.2.4	Building on the technical recommendations of 1.1.2 and 2.2.1, as well as lessons learned from their pilot implementation (activity 2.2.3), draft technical guidelines for the consideration and approval by the MEA technical committees under activity 1.2.2.  As with other technical reports and analyses, the MEA technical working group will contribute to the drafting of these guidelines.  These guidelines will be endorsed by the MEA technical committees and the appropriate decisions taken up by the Inter-Ministerial Council.

Target indicator:	Technical guidelines are drafted and finalized by month 24

Target indicator:	Policy recommendations to legitimize these guidelines, as appropriate, are prepared, submitted, and approved by the Inter-Ministerial Councilby month 28

Output 2.3	Strengthened monitoring and compliance

- Compliance of environmental legislation is a cornerstone aspect of this project, with the assumption being made that certain provisions of existing environmental legislation must be enforced.  Others should not be if they are counter-productive to meeting Rio Convention obligations.  Indeed, there will be a number of provisions that clearly meet national sustainable development priorities but are in opposition to global environmental obligations.  For that reason, the best practices and lessons learned from Costa Rica’s current state of environmental governance must inform alternative approaches to meet both national sustainable development and global environmental priorities.  These alternative approaches are what will be tested in activity 2.2.2.  This output will focus of strengthening and institutionalizing monitoring and compliance capacities.  This will help catalyze the replication of the piloted exercises as well as to strengthen the institutional sustainability of the successful outcomes.  This output will also include the preparation of training material, tools, and other resources, and carry out training on monitoring and compliance procedures and reporting.  Trainings will be targeted not only to government staff, but also to other partner non-state stakeholders.

2.3.1:	Building on the analyses of 1.2.1 and 2.1.3, and the testing of differentiated implementation and enforcement of environmental legislation under activity 2.2.2, recommend improved monitoring and compliance reforms.  These recommendations will be made by the MEA technical working groups and submitted to the MEA technical committee for their review and endorsement, and subsequent approval by the Inter-Ministerial Council.

Target indicator:	Clear monitoring and compliance reforms are articulated within the framework of technical guidelines (activity 2.2.4) and submitted to the MEA technical committee after three monitoring phases: by month 12, by month 23, and by month 33

2.3.2:	Based on the recommendations of 2.3.1, pilot implementation of select monitoring and compliance reforms that cut across the three Rio Conventions.  These pilot reforms will be in addition to the policy recommendations that will be piloted as part of activity 2.2.2.  Special consideration will be given to piloting these recommendations within the framework of the LECB project’s work on a MRV system for prioritized sectors (Result 3).

Target indicator:	Quarterly progress reports are submitted to the MEA technical committees every three months, beginning by month 15

Target indicator:	Lessons learned of pilot monitoring and compliance reforms discussed in a stakeholder constituent dialogue by month 22

Target indicator:	Pilot monitoring and compliance reforms are deemed very successful on the basis of a survey of N>100 experts and other stakeholders by month 22 and a second survey by month 33

Target indicator:	MEA technical committee proposes monitoring and compliance reforms to institutionalize best practice monitoring and compliance procedures by month 32

Target indicator:	Inter-Ministerial Council authorizes at least 80% of MEA technical committee recommended reforms by month 34

2.3.3:   Undertake an assessment of existing guidelines, tools and resources.  This activity will assess the resources currently available to train planners and decision-makers on a more complete understanding of Costa Rica’s environmental legislation and associated governance structures.

Target indicator:	Report on guidelines, tools and resources for the effective interpretation, supervision and enforcement of environmental legislation completed by month 8

2.3.4:	Prepare a comprehensive training programme, including targeted training modules (in coordination with other donor-funded programmes and projects).  This programme will be informed by the baseline analysis of information needs carried out under activity 1.2.1.  The trainings proposed will also be informed by the learn-by-doing and pilot exercises of activities 2.2.2 and 2.3.2.

Target indicator:	Identify and collect new guidelines, tools, and other resources and make available through the electronic platform by month 12

Target indicator:	Comprehensive training programme drafted by month 18 and endorsed by the MEA technical committees by month 20

2.3.5:	Implement the training programme of 2.3.4 on best practices and innovations.  Not only does this include training on monitoring and compliance, but also training on best practices for the strategic enforcement of environmental legislation carried out under activities 2.2.3 and 2.2.4.

Target indicator:  	Four (4) training workshops and related exercises begin by month 20

Target indicator:	At least 80 government staff members that are directly implicated in the planning and decision-making process to monitor and enforce environmental legislation have participated in training workshops by month 33

2.3.6    Whereas activity 2.2.4 focuses on the development and endorsement of technical guidelines for the strategic enforcement of environmental legislation to deliver global environmental benefits, this activity focuses on the development of companion operational guidelines to monitor and enforcement compliance.  This activity will be coordinated with activity 2.2.4, with both set of guidelines submitted for validation, endorsement and approval as a package at the same time.

Target indicator:	Operational guidelines are drafted and finalized by month 24.

Target indicator:	Guidelines are validated in stakeholder workshop by month 26

Target indicator:	Policy recommendations to legitimize these guidelines, as appropriate, are prepared, submitted, and approved by the Inter-Ministerial Councilby month 28

Component 3:	Strengthened technical and management capacities

- The aim of this third component is to strengthen the institutional sustainability of the project results by ensuring that there is sufficient awareness, understanding and know-how surrounding the project so that when it ends, there is less likelihood of reverting to the baseline.  While activities in component 2 focus on the learn-by-doing integrating of the Rio Conventions into environmental legislation, there is still a need to train other staff and stakeholders who would or could eventually become future planners and decision-makers.  The sustainability of the project also rests on ensuring that a sufficient baseline of stakeholders value the project and has the support of champions.  Activities are therefore directed to raising the public profile of the project, convening targeted awareness-raising workshops and developing related materials, as well as developing a resource mobilization strategy to address the financial sustainability of project results.

Expected Outcome:	Improved technical and management capacities for sustained support of the global environment

Output 3.1	Kick-Off and Project Results Conferences

- At the beginning of the project, a conference will be held to introduce the project to a wider set of stakeholders to promote its objective of improving the implementation and oversight of Costa Rica’s environmental legislation.  Towards the end of the project, the results and lessons learned will be presented and discussed, with two main purposes.  The first is to maintain as high and as positive a profile of the project strategy and successful results.  This will strengthen the institutionalization (i.e., sustainability) of the MEA technical committees and Inter-Ministerial Council that are critical carrying on the project strategy post-project closure.  The second main purpose is to mobilizeon-going commitment to replicating and institutionalizing best practices and successful innovative approaches tested under component 2.  Both conferences will be convened over a one-day period, and include presentations and panel discussions.  During these conferences, a survey will be conducted to assess the stakeholders’ awareness and value of the project issues at both the beginning and end of the project (activity 3.2.1).

Activities:

3.1.1	Organize and convene a one-day conference at the project start.

Target indicator:	One-day Kick-Off Conference is held by month 3

Target indicator:	Over 200 participants attend this conference, representing a good diversity of stakeholders, including representation from other regions of Costa Rica

3.1.2	Organize and convene a one-day project results conference at the end of the project.

Target indicator:	One-day Project Results Conference is held by month 34.

Target indicator:	Over 200 participants attend this conference, representing a good diversity of stakeholders, including representation from other regions of Costa Rica

Target indicator:	At least four (4) expert panel discussions present the lessons learned to deliver Rio Convention obligations through existing national environmental and related legislation.  At least 30 participants attend each of the panel discussions

Output 3.2	Public awareness campaign, survey, and educational materials

- This output includes a number of activities that are directed to strategically organize in more detail and the awareness-raising to be undertaken by the project.  In addition to the conferences of output 3.1, this output will include carrying out a baseline and end-of-project survey, as well as to prepare awareness-raising and educational materials.  The project will also carry out awareness-raising workshops to targeted groups of stakeholders, namely the private sector, journalists, and regional decision-makers, as well as a more technical workshop targeting expert informants (e.g., experts from NGOs, academia and government agencies that are not involved in the learn-by-doing or training exercises of component 2).

Activities:

3.2.1	Carry out broad-based awareness survey (in conjunction with activity 1.1.1 on the awareness and understanding of line ministries staff and stakeholders of environmental laws and the Rio Convention provisions).  The baseline survey will serve as an assessment of awareness developed under the project when compared with the result of the year-end survey.  The surveys will be conducted immediately before and during both conferences of output 3.1.

Target indicator:	Two broad-based surveys carried out at the beginning of the project and with six months of project termination (N>500), completed by month 3 and by month 34

Target indicator:	Expert and independent analysis of the survey results will be completed by month 35

3.2.2	Prepare a comprehensive public awareness implementation plan.  This plan will be a more detailed organization of the awareness-raising activities to be carried out under the component.

Target indicator:	A comprehensive public awareness plan developed to completed by month 6

3.2.3	Prepare articles on legislative responses for Rio Convention implementation.  The articles on legislative responses for Rio Convention implementation will be targeted to the general population and published in print media with a high circulation.  They will also be printed as separate brochures for targeted distribution at special events.  Although special provisions will be made to translate the brochures into indigenous languages, further details will be discussed and agreed to during project implementation.

Target indicator: 	At least nine (9) articles on legislative responses for Rio Convention implementation in Costa Rica will be written and published in popular literature with high circulation before the end of the project.  By month 6, at least one article should be published.  By month 18, at least four (4) articles should be published.  By month 30, at least seven (7) articles should be published.

Target indicator:	Each article is to be edited and published as a brochure, with at least 100 copies each and distributed to at least two high value special events for greatest impact.

3.2.4	Develop a high school competition plan on the Rio Conventions, with a focus on local and individual action to implement them.  The competitions will be promoted on the Internet and on the project’s Facebook page (activity 3.6.2).

Target indicator:	High school competition plan completed by month 9

Target indicator:	At least two (2) high schools carry out high school competitions by month 20 and at least six (6) by month 33

3.2.5	Prepare and integrate, as appropriate, an education module that focuses on the global environment for high schools into the high school teaching curricula.  This module should be designed to help students think critically about the complex social, economic, and environmental issues affecting their country, their region, and the global community.

Target indicator:	Education module prepared for high schools completed by month 8

Target indicator:	At least two (2) high schools have implemented education module by month 20 and at least one high school in each of the seven provinces by month 33

3.2.6	Prepare and air a public service announcement (PSA) on the legislative links between the local and global environment on television and radio.  This activity will involve the conceptualization of the message, the story-boarding, filming, post-production and distribution.  This will be followed by its airing at strategic intervals.  Special consideration will be made to translate the audio version of the PSA into key indigenous language for the radio version.

Target indicator:	One PSA completed for both television and radio (audio version) by month 12, with the first airing by month 15.

Target indicator:	At least 50 airings of the PSA on television and at least 100 airings of the PSA on radio, both by month 34.

Output 3.3	Awareness-raising dialogues and workshops

- This output targets key categories of stakeholders, namely journalists, the private sector, planners and decision-makers from Costa Rica’s seven provinces, and expert practitioners who are working in the same field such as expert NGOs, academia and graduate students.  These awareness-raising activities may be organized as dialogues or as workshops, depending on the stakeholders.

Activities

3.3.1	Organize and convene private sector sensitization panel discussions on the global environmental issues and their relevance, and their involvement on the opportunities they have to actively participate.  Particular attention is to be paid to their views on the impact of environmental legislation on private sector goals and how to strategically reconcile these with global environmental priorities.

Target indicator:	Three (3) panel discussions, with at least 20 private sector representatives.  The first panel discussion should be completed by month 8; the second by month 18; and the third by month 28

3.3.2	Organize and convene workshops targeted to Costa Rican journalists of television, radio and print to better enable them to report on global environmental issues and their relevance, especially taking into account that, in general, journalists do not necessarily have a special training or understanding of Rio Convention mainstreaming issues.

Target indicator:	At least three (3) journalist awareness workshops held, each with at least 10 representatives.  The first workshop should be completed by month 9; the second by month 19; and the third by month 29

Target indicator:	By month 33, reporting on Rio Convention mainstreaming in the popular media shows a 10% increase over forecasted trends using baseline data and past trends

3.3.3	Organize and convene training workshops on MEA legislative mainstreaming.  These workshops will be directed to expert practitioners from non-governmental organizations, academia, and government staff that did not participate in the learn-by-doing or training exercises under output2.2.  These participants will be selected on the basis of their actual and potential involvement is future activities related to the development, monitoring, and enforcement of environmental legislation and contribution to replicating project activities.

Target indicator:	At least three (3) workshops are convened with at least 20 expert practitioner participants.  The first workshop should be completed by month 10; the second by month 20; and the third by month 30

3.3.4	Organize and convene regional awareness workshops.  These regional workshops will be structured to raise the awareness of planners and decision-makers, among other regionally-based stakeholders on their strategic enforcement of environmental legislation to increase global environmental benefits.

Target indicator:	At least three (3) regional workshops are convened, with local and regional government representatives with at least one representative from each of the seven Costa Rican provinceshaving participated in at least one workshop.  Each workshop should be attended by at least 20 local/regional representatives.  The first regional workshop should be completed by month 11; the second by month 21; and the third by month 31

3.3.5	Convene three (3) public policy dialogues.  This activity will be structured slightly differently than the workshops, in that they will serve as a public forum for Costa Rican intellectuals, leaders, and activists to present and exchange cutting-edge views on the national-global environment nexus.  These dialogues will be an expanded extension of the panel discussions of the kick-off conference.  These dialogues may be organized and incorporated within Costa Rica’s national public administration training programme or through the University of Costa Rica.

Target indicator:	Three (3) cutting-edge policy dialogues with invited leaders in the field of environmental governance.  The first dialogue should be convened by month 7; the second by month 17; and the third by month 27

Output 3.4	Resource mobilization strategy

- The resource mobilization strategy consists of a number of activities that will be targeted to ensuring the sustainability of monitoring and compliance of Costa Rica’s environmental legislation.  To this end, activities will include an in-depth analysis of the financing needs, as well as to assess the economic impacts of enforcement.  In keeping with UNDP’s recent guidance to ensure that social issues are appropriately considered during the upstream planning process, this analysis will include the social assessment of environmental legislation enforcement as this will be included as part of the analysis and stakeholder consultations of activities 2.1.3 and 2.1.4.  Based on the recommendations of this analysis, a working group comprised of finance and economic experts will be created to discuss opportunities for piloting and implementing best practice and innovative financial and economic instruments.  Recommendations from these experts will be discussed by the MEA technical working group, which would also take into account the social impacts.  The MEA technical committee’s policy recommendations on resource mobilization to the Inter-Ministerial Council will be informed by these two groups of expert analyses.

Activities:

3.4.1	Undertake an in-depth financial and economic analysis of associated with the monitoring and enforcement of environmental legislation.

Target indicator:	Analytical report drafted, peer reviewed, and finalized by month 12

3.4.2	Identify best practice and innovative financial and economic instruments for piloting.  This will take the form of a feasibility study and broad consultations on the strategic choice of instruments to pilot and implement.  This will build on the feasibility study conducted on the electronic information-sharing mechanism of activity 1.2.2 in year one.

Target indicator:	Feasibility study on financial and economic instruments to advance the monitoring and compliance of environmental legislation for the global environment completed by month 18

3.4.3	Establish expert group of finance and economic experts for the peer review of activities 3.4.1 and 3.4.2 as well as to champion resource mobilization efforts.  Experts will be government finance and economic experts, as well as independent experts working in the private and non-profit sectors.

Target indicator:	Expert working group is made up of at least 20 rotating members, who will undertake a desk review of the drafts of the analytical report and feasibility study, and meet at least once to discuss the findings of each within one month of their completion, i.e., by months 13 and 19.

Output 3.5	Internet visibility of integrated and streamlined environmental legislation

- This output serves two main key purposes.  The first is to facilitate a high profile of the project and generate more supporters and followers.  The second is to serve as a form of clearing mechanism for key information related to the Costa Rica’s enforcement of national environmental legislation towards meeting global environmental objectives.

Activities:

3.5.1	Develop and manage an easy-to-use one-stop environmental legislation website.  No intranet is envisioned under this project as this would only serve as a barrier to the sharing of information.  However, the website will include a membership-only forum for allowing electronic discussions on topical issues that are related to the project.  The website will also serve as the repository for materials produced under the project.  This website will require a significant investment of person-hours in the management, to ensure that it is functional on a daily basis.  In this respect, the website must ensure that hyperlinks to other websites remain functional; discussions are moderated on a daily basis; that articles and information remain current and relevant; and to clear the registry regularly to reduce the incidences of site crashes.  A feasibility study will be prepared and will include new and updated target indicators to measure the website utility and success.This will be carried out in conjunction with the feasibility study of activity 1.2.2.

Target indicator:	Feasibility study for the creation of a comprehensive environment legislation website prepared and completed by month 4

Target indicator:	Website architecture completed and endorsed by the MEA technical working group by month 6

Target indicator:	Website is updated at least once a month with new information, articles, and resources

Target indicator:	Website statistical data rank the quality of the website (unique users, visit sessions, and page views) as a top ten site of all Costa Rican websites by the twelfth month of being online.  This ranking should stay the same for the duration of the project.  Baseline indicators are to be determined when the website is put online and target indicators determined on the basis of an analysis of existing websites (part of the feasibility study)

3.5.2	Create and manage a Facebook page on Rio Convention mainstreaming.  This

Target indicator:	Facebook page created by month 3 and updated on a weekly basis, at minimum.

Target indicator:	At least 3,000 people are members of the Facebook page by month 32

## C.3   Sustainability and Replicability

### C.3.a   Sustainability

- The sustainability of the project will be strengthened by the targeted reinvigoration of the Inter-Ministerial Council (see output 1.3).  This Council will provide close follow-up to how the Rio Convention obligations are effectively implemented through existing environmental legislation, and will provide thehigh-level oversight to facilitating the appropriate reforms to ensure long-term implementation.  The Council is indeed a critical feature of this project’s sustainability, as it represents the best opportunity for mobilizing political commitment to sustain the project’s momentum after project closure.  Project sustainability will also require the long-term support of project champions, as well as ensuring that a sufficient critical mass of stakeholders remain committed and supportive of the project’s strategy.

- A third critical feature of the project’s sustainability lies in the project’s cost-effective strategy.  By seeking to use existing environmental and related natural resource management legislation to implement Rio Convention obligations by targeting current weaknesses in their monitoring and compliance, this project builds upon an existing strong baseline of legislation and institutional capacities.

- Sustainability will also be strengthened by the project’s attention to resource mobilization.  Notwithstanding that a high level of commitment, championship, and strong baseline, the sustainability of project outcomes will require a certain amount of new and additional resources that is currently not available outside of the project’s construct, which is why this project is being supporting through external grants.  The project’s resource mobilization will explore the kind of resources needed to sustain project outcomes, and identify realistic sources from both in Costa Rica, through official development assistance, among others as appropriate.  Importantly, the resource mobilization strategy will seek an improvement of the government’s allocation of resources directed to implementing the Rio Conventions through national environmental legislation.

- Another feature of the project’s sustainability is the Internet-based platform of the Rio Conventions in the country, the purpose of which is to improve the accessibility and availability of more useful information to implement the Rio Conventions within the framework of national environmental legislation.  This platform will be complemented by a communication strategy targeted to different audiences on the most important issues of the conventions.

- A final feature of the project’s strategy is through the implementation arrangements.  Most of the project activities are constructed as learn-by-doing activities, the rationale being that government and other stakeholders responsible for environmental planning, decision-making, monitoring and enforcement are the stakeholders that collaborate on the improved interpretation of environmental and natural resource management legislation from a heightened Rio Convention perspective.  Having the government execute this project directly also builds their capacities for the long-term implementation of appropriate project activities, and will contribute to their institutionalization.  Certainly, mistakes will occur and implementation will not always be smooth, but these problems should still be seen as opportunities for learning better practices.  The project’s sustainability rests on the success and replicability of the pilots and demonstrations.

### C.3.bReplicability and Lessons Learned

- As a medium-size project, this intervention has certain limitations, namely in being able to reconcile and undertake all the necessary legislative reforms identified as needed during project implementation.  Instead, this project serves as catalyst of a more long-term approach to Rio Convention implementation by creating a set of institutional arrangements, negotiating improvements to the modus operandi of environmental legislation monitoring and compliance, and building up a strong baseline of technical capacities.  Part of the catalytic role of the project is to demonstrate the value of this approach.  During early project implementation, the Project Board will approve the selection of a targeted set of environmental and natural resource management legislation to be tested.  The Project Board will also approve a selected set of recommendations from the Inter-Ministerial Council to be piloted.  These specific activities will be constructed as a set of technical workshops, regional and stakeholder consultations, policy negotiating meetings, and drafting of appropriate legislative and institutional reforms.  Together, they aim to remove contradictions among the multiple sets of legislation, reduce, if not remove,counter-productive institutional authorities and responsibilities, and undertake trainings and awareness-raising targeted specifically to the pilots and demonstrations.

- The resource mobilization strategy will also be a key feature of the project’s replicability (and sustainability as outlined above), in that activities of a similar construct under the project will need financing.  By developing the institutional and technical capacities through the pilot and demonstration activities, the replicability of the project is significantly enhanced as the learning curve is greatly reduced.  The project will further support reducing the learning curve by undertaking an assessment of lessons learned and best practices, not only from the pilot and demonstration activities, but from other projectactivities.

- The replication of project activities is further strengthened by the project implementation arrangements, which will involve numerous stakeholder representatives.  This includes working with NGOs that have a strong presence in the communities and/or are actively supporting related capacity development work.  Many such organizations operate in Costa Rica, for example, raising awareness of existing legislation to protect endangered species.  Research and academic institutions are also playing a leading role in identifying new and innovative interpretations and policy responses to improve environmental management.

- Replication will also be supported by raising the awareness of the project throughout Costa Rica.  Not only will the project facilitate this through awareness-raising workshops with journalists, with the purpose of helping them to write more articles about the environment.  The public service announcement on radio and television also serves the purpose of popularizing the project with the public in order to generate greater support and demand for replication activities.

## C.4   Stakeholder Involvement

- During the project development phase, key project stakeholders were identified and consulted.  Taking an adaptive and collaborative management approach to execution, the project will ensure that key stakeholders are involved early and throughout project execution as partners for development.  This includes their participation in the Project Board, review of project outputs such as recommendations for amendments to policies, plans, programmes and legislation, as well as participation in monitoring activities.

- Given the project strategy, the key project stakeholders are government ministries and their subsidiary agencies and departments that are authorized to oversee compliance with key environmental legislation.  These stakeholder representatives will participate in activities to negotiate the improved interpretation of environmental and natural resource legislation, which is structured as learn-by-doing exercises.  In addition to these governmental stakeholders, there are non-governmental stakeholders from academia, theprivate sector, and civil society organizations.  During the establishment of technical working groups on the three Rio Conventions, these non-state organizations will also be invited in the project activities to share their comparative expertise, but also to undertake selected project activities.  These will be determined during project implementation when setting up with the working group teams as well as when setting up the sub-contracts, e.g., broad-based survey of activity 3.2.1.

| MINAE (Ministry of Environment and Energy) | MINAE will guide the process of how global environmental concerns, priorities and objectives would be integrated into Costa Rica's key national development policy framework, including poverty reduction strategies and programmes, and associated management capacities strengthened. The MINAE is the focal point of the GEF. Both the CC (through its National Institute of Meteorology, IMN) and the BD Focal Points (through its Protected Areas System, SINAC) are hosted at this Ministry. |
| --- | --- |
| MEP (Ministry of Education) | The MEPwill play a key role in the inclusion of MEAs objectives into the national environmental education plans. It advises on the assessment of capacity in training and awareness at all levels. |
| MAG (Ministry of Agriculture and Livestock) | The Cattle and Agriculture Ministry is the lead institution of the agricultural sector. MAG will guide the integration of environmental priorities into the agro-industry productive sectors, including concerns related to low carbon climate resilient development strategies. It is the national focal point for land degradation and organic production. |
| MIDEPLAN (Ministry of Planning and Political Economy) | MIDEPLAN is in charge of national and regional development plans, improving governance in the short, medium and long terms, advising the executive power in decision-making strategies. It plays a key role in the project promoting national debate and coordinating the project objectives into the National Planning System. |
| MREC (Ministry of External Relations) | In charge of international cooperation. This project will benefit from the Foreign Affairs guidance ensuring it is at all times in harmony with national priorities and the principles of foreign policy of CR. |
| CONAI (National Commission of Indigenous Affairs) | CONAI is the public institution that promotes the social, economic and cultural improvement of indigenous people in Costa Rica. It is a governmental institution whose objectives include the development of participatory strategies for the sustainable management and use of water, flora, fauna and biodiversity in indigenous reserves. |

## C.5   Monitoring and Evaluation

- Project monitoring and evaluation will be conducted in accordance with established UNDP and GEF procedures.  The project team and the UNDP Country Office (UNDP CO) will undertake monitoring and evaluation activities, with support from UNDP/GEF, including by independent evaluators in the case of the final evaluation.  The logical framework matrix in Annex 3provides a logical structure for monitoring project performance and delivery using SMART indicators during project implementation.  Once the Project Manager is recruited, he/she will organize a small working group of national experts on project management to review the logical framework.  The outcome budget (Annex 4) and the work plan (Annex 5) in the UNDP project document provide additional information for the allocation of funds, both the GEF and co-financing, for expected project deliverables and the timing of project activities to produce these deliverables.   Annex 9is an input budget for the allocation of the GEF contribution according to the project’s outcomes, including project management costs and annual allocations.  The Capacity Development Scorecard (Annex 2) is the GEF tracking tool for CCCD and will be used as part of monitoring and evaluation activities to assess project delivery.  The work plan is provisional, and is to be reviewed during the first project board and endorsed at the project initiation workshop.

- The following sections outline the principle components of monitoring and evaluation.  The project’s monitoring and evaluation approach will be discussed during the project’s initiation report so as to fine-tune indicators and means of verification, as well as an explanation and full definition of project staff M&E responsibilities.

- A project initiation workshop will be conducted within the first two (2) months with the full project team, National Project Director, relevant government counterparts, co-financing partners, the UNDP CO, with representation from the UNDP/GEF Regional Coordinating Unit, as appropriate.  Non-governmentalstakeholders, including from the private sector, should be represented at this workshop.  For this project, the project initiation workshop has been expanded as a Kick-Off Conference, with the internal workshop activities remaining internal project management arrangements, and the conference component focusing on popularizing the project strategy and expected outcomes.

- A fundamental objective of this initiation workshop will be to further instill and understanding and ownership of the project’s goals and objectives among the project team, government and other stakeholder groups.  The workshop also serves to finalize preparation of the project’s first annual work plan on the basis of the project’s log-frame matrix.  This will include reviewing the log frame (indicators, means of verification, assumptions), imparting additional detail as needed, and on the basis of this exercise, finalize the Annual Work Plan (AWP) with precise and measurable performance (process and output) indicators, and in a manner consistent with the expected outcomes for the project.

- Specifically, the project initiation workshop will: (i) introduce project staff to the UNDP/GEF expanded team that will support the project during its implementation, namely the CO and responsible Project Management Unit (PMU) staff; (ii) detail the roles, support services and complementary responsibilities of UNDP CO and PMU staff with respect to the project team; (iii) provide a detailed overview of UNDP/GEF reporting and monitoring and evaluation (M&E) requirements, with particular emphasis on the combined Annual Project Reports - Project Implementation Reviews (APR/PIRs), Project Board (PB) meetings, as well as final evaluation.  The initiation workshop will also provide an opportunity to inform the project team on UNDP project-related budgetary planning, budget reviews, and mandatory budget re-phasing.

- The initiation workshop will provide an opportunity for all parties to understand their roles, functions, and responsibilities within the project’s decision-making structures, including reporting and communication lines, and conflict resolution mechanisms.  The Terms of Reference for PMU staff and associated decision-making structures will be discussed again, as needed, in order to clarify for all, each party’s responsibilities during the project’s implementation phase.

- The initiation workshop will also present a schedule of M&E-related meetings and reports.  The Project Manager in consultation with UNDP will develop this schedule, and will include: (i) tentative time frames for PB meetings, and the timing of near-term project activities, such as the in-depth review of literature on natural resource valuation; and (ii) project-related monitoring and evaluation activities.  The provisional work plan will be approved in the first meeting of the PB.

- Day-to-day monitoring of implementation progress will be the responsibility of the Project Manager based on the project’s Annual Work Plan and its indicators.  The Project Manager will inform the UNDP CO of any delays or difficulties faced during implementation so that the appropriate support or corrective measures can be adopted in a timely and remedial fashion.

- The Project Manager will fine-tune outcome and performance indicators in consultation with the full project team at the initiation workshop, with support from UNDP CO and assisted by the UNDP/GEF.  Specific targets for the first year implementation performance indicators, together with their means of verification, will be developed at the initiation workshop.  These will be used to assess whether implementation is proceeding at the intended pace and in the right direction and will form part of the Annual Work Plan.  Targets and indicators for subsequent years would be defined annually as part of the internal evaluation and planning processes undertaken by the Project Team, and agreed with the Executing Agency (MINAE), among other key project partners sitting on the PB.

- Periodic monitoring of implementation progress will be undertaken by the UNDP CO through the provision of quarterly reports from the Project Manager.  Furthermore, specific meetings may be scheduled between the PMU, the UNDP CO and other pertinent stakeholders as deemed appropriate and relevant (particularly the PB members).  Such meetings will allow parties to take stock and to troubleshoot any problems pertaining to the project in a timely fashion to ensure smooth implementation of project activities.

- Annual Monitoring will occur through the Annual Project Board meeting.  This is the highest policy-level meeting of the parties directly involved in the implementation of a project.  The project will be subject to PB meetings at least twice per year.  The first such meeting will be held within the first twelve months following the initiation workshop.  For each year-end meeting of the PB, the Project Manager will prepare harmonized Annual Project Report / Project Implementation Reviews (APR/PIR) and submit it to UNDP CO, the UNDP/GEF Regional Coordination Unit, and all PB members at least two weeks prior to the meeting for review and comments.

- The APR/PIR will be used as one of the basic documents for discussions in the PB year-end meeting.  The Project Manager will present the APR/PIR to the PB members, highlighting policy issues and recommendations for the decision of the Committee participants.  The Project Manager will also inform the participants of any agreement(s) reached by stakeholders during the APR/PIR preparation, on how to resolve operational issues.  Separate reviews of each project output may also be conducted, as necessary.  Details regarding the requirements and conduct of the APR and PB meetings are contained with the M&E Information Kit available through UNDP/GEF.

- The terminal review meeting is held by the PB, with invitation to other relevant Government and municipal stakeholders as necessary, in the last month of project operations.  The Project Manager is responsible for preparing the terminal review report and submitting it to UNDP COs, the UNDP/GEF Regional Coordinating Unit, and all participants of the terminal review meeting.  The terminal review report will be drafted at least one month in advance of the terminal review meeting, in order to allow for timely review and to serve as the basis for discussion.  The terminal review report considers the implementation of the project as a whole, paying particular attention to whether the project has achieved its stated objectives and contributed to the broader environmental objective.  The report also decides whether any actions remain necessary, particularly in relation to the sustainability of project outputs and outcomes, and acts as a vehicle through that lessons learned can be captured to feed into other projects under implementation or formulation.  The terminal review meeting should refer to the independent final evaluation report, conclusions and recommendations as appropriate.

- The UNDP CO, in consultation with the UNDP/GEF Regional Coordinator and members of the PB, has the authority to suspend disbursement if project performance benchmarks are not met as per delivery rates, and qualitative assessments of achievements of outputs.

- A project initiation report will be prepared immediately following the initiation workshop (Kick-Off Conference).  This report will include a detailed First Year Work Plan divided in quarterly time-frames as well as detailed activities and performance indicators that will guide project implementation (over the course of the first year).  This Work Plan will include the proposed dates for any visits and/or support missions from the UNDP CO, the UNDP/GEF Regional Coordinating Unit, or consultants, as well as time-frames for meetings of the project decision-making structures (e.g., PB).  The report will also include the detailed project budget for the first full year of implementation, prepared on the basis of the Annual Work Plan, and including any monitoring and evaluation requirements to effectively measure project performance during the targeted 12 months’ time-frame.

- The initiation report will include a more detailed narrative on the institutional roles, responsibilities, coordinating actions and feedback mechanisms of project related partners.  In addition, a section will be included on progress to date on project establishment and start-up activities and an update of any changed external conditions that may affect project implementation, including any unforeseen or newly arisen constraints.  When finalized, the report will be circulated to project counterparts who will be given a period of one calendar month in whichto respond with comments or queries.

- The combined Annual Project Report (APR) and Project Implementation Review (PIR)is a UNDP requirement and part of UNDP’s Country Office central oversight, monitoring and project management.  As a self-assessment report by project management to the Country Office, the APR/PIR is a key input to the year-end Project Board meetings.  The PIR is an annual monitoring process mandated by the GEF.  It has become an essential management and monitoring tool for project managers and offers the main vehicle for extracting lessons from on-going projects.  These two reporting requirements are very similar in input, purpose and timing that they have now been amalgamated into a single APR/PIR Report.

- An APR/PIR is to be prepared on an annual basis for the previous reporting period (30 June to 1 July), but well in advance (at least one month) in order to be considered at the PB meeting.  The purpose of the APR/PIR is to reflect progress achieved in meeting the project’s Annual Work Plan and assess performance of the project in contributing to intended outcomes through outputs and partnership work.  The APR/PIR is discussed by the PB, so that the resultant report represents a document that has been agreed upon by all of the key stakeholders.

- A standard format/template for the APR/PIR is provided by UNDP/GEF.  This includes, but not limited to, the following:

- An analysis of project performance over the reporting period, including outputs produced and, where possible, information on the status of the outcome;

- The constraints experienced in the progress towards results and the reasons for these;

- The three (at most) major constraints to achievement of results;

- Annual Work Plans and related expenditure reports;

- Lessons learned; and

- Clear recommendations for future orientation in addressing key problems in lack of progress.

- UNDP will analyze the individual APR/PIRs by focal area, theme and region for common issues/results and lessons.  The APR/PIRs are also valuable for the independent evaluators who can utilize them to identify any changes in project strategy, indicators, work plan, among others, and view a past history of delivery and assessment.

- Quarterly Progress Reportsare short reports outlining the main updates in project performance, and are to be provided quarterly to the UNDP Country Office.  UNDP CO will provide guidelines for the preparation of these reports, which will be shared with the UNDP/GEF RCU.  Progress made shall be monitored in the UNDP Enhanced Results Based Management Platform on quarterly basis.

- During the last three months of the project, the PMU will prepare the Project Terminal Report.  This comprehensive report will summarize all activities, achievements and outputs of the project, lessons learned, the extent to which objectives have been met, structures and mechanisms implemented, capacities developed, among others.  Together with the independent final evaluation, the project terminal report is one of two definitive statements of the project’s activities during its lifetime.  The project terminal report will also recommend further steps, if necessary, in order to ensure sustainability and replicability of the project outcomes and outputs.

- An independent final evaluation will take place three months prior to the terminal tripartite review meeting, and will focus on: a) the cost-effectiveness, efficiency and timeliness of project implementation and performance; b) highlight issues requiring decisions and actions; and c) present initial lessons learned about project design, implementation and management.  Findings of this evaluation will be incorporated as lessons learned, and recommendations for improvement addressed to ensure the institutional sustainability of project outputs, particular for the replication of project activities.  The final evaluation will also look at project outcomes and their sustainability.  The final evaluation should also provide recommendations for follow-up activities, as appropriate.  The terms of reference for the final evaluation will be prepared by the UNDP CO based on guidance from the UNDP/GEF Regional Coordinating Unit, in consultation with the MINAE.

- The Project Manager will provide the UNDP Resident Representative with certified periodic financial statements and an annual audit of the financial statements relating to the status of UNDP (including GEF) funds according to the established procedures set out in UNDP’s Programming and Finance manuals.  The audit will be conducted by the legally recognized auditor of UNDP Costa Rica. Audit on project will follow UNDP Financial Regulations and Rules and applicable Audit policies.

- Learning and knowledge sharing will be enhanced through the dissemination of project results within and beyond the project intervention zone through existing information sharing networks and forums.  The project will identify and participate, as relevant and appropriate, in scientific, policy-based and/or any other networks, which may be of benefit to project implementation though lessons learned. The project will identify, analyze, and share lessons learned that might be beneficial in the design and implementation of similar future projects.  Finally, there will be a two-way flow of information between this project and other projects of a similar focus.

- Communications and visibility requirements: Full compliance is required with UNDP’s Branding Guidelines.  These can be accessed at http://intra.undp.org/coa/branding.shtml, and specific guidelines on UNDP logo use can be accessed at:http://intra.undp.org/branding/useOfLogo.html.  Amongst other things, these guidelines describe when and how the UNDP logo needs to be used, as well as how the logos of donors to UNDP projects needs to be used.  For the avoidance of any doubt, when logo use is required, the UNDP logo needs to be used alongside the GEF logo.   The GEF logo can be accessed at: http://www.thegef.org/gef/GEF_logo.   The UNDP logo can be accessed at http://intra.undp.org/coa/branding.shtml.

- Full compliance is also required with the GEF’s Communication and Visibility Guidelines (the “GEF Guidelines”).  The GEF Guidelines can be accessed at: http://www.thegef.org/gef/sites/thegef.org/files/documents/C.40.08_Branding_the_GEF%20final_0.pdf. Amongst other things, the GEF Guidelines describe when and how the GEF logo needs to be used in project publications, vehicles, supplies and other project equipment.  The GEF Guidelines also describe other GEF promotional requirements regarding press releases, press conferences, press visits, visits by Government officials, productions and other promotional items.  Where other agencies and project partners have provided support through co-financing, their branding policies and requirements should be similarly applied.

Table 4: Monitoring Work Plan and Budget

| Type of M&E activity | Responsible Parties | Budget US$ Excluding project team staff time | Time frame |
| --- | --- | --- | --- |
| Inception Workshop and Report | - Project Manager - UNDP CO, UNDP GEF | Indicative cost: 10,000 | Within first two months of project start up |
| Measurement of Means of Verification of project results. | - UNDP GEF RTA/Project Manager will oversee the hiring of specific studies and institutions, and delegate responsibilities to relevant team members. | To be finalized in Inception Phase and Workshop. | Start, mid and end of project (during evaluation cycle) and annually when required. |
| Measurement of Means of Verification for Project Progress on output and implementation | - Oversight by Project Manager - Project team | To be determined as part of the Annual Work Plan's preparation. | Annually prior to ARR/PIR and to the definition of annual work plans |
| ARR/PIR | - Project manager and team - UNDP CO - UNDP RTA - UNDP EEG | None | Annually |
| Periodic status/ progress reports | - Project manager and team | None | Quarterly |
| Mid-term Evaluation | - Project manager and team - UNDP CO - UNDP RCU - External Consultants (i.e. evaluation team) | Not Required for MSP project | At the mid-point of project implementation. |
| Final Evaluation | - Project manager and team, - UNDP CO - UNDP RCU - External Consultants (i.e., evaluation team) | Indicative cost : 40,000 | At least three months before the end of project implementation |
| Project Terminal Report | - Project manager and team - UNDP CO - local consultant | 0 | At least three months before the end of the project |
| Audit | - UNDP CO - Project manager and team | Indicative cost per year: 3,000 | Yearly |
| Visits to field sites | - UNDP CO - UNDP RCU (as appropriate) - Government representatives | For GEF supported projects, paid from IA fees and operational budget | Yearly |
| TOTAL indicative COST Excluding project team staff time and UNDP staff and travel expenses |  | US$ 60,000 (+/- 5% of total budget) |  |

# D.	Financing

## D.1   Financing Plan

- The financing of this project will be provided by the GEF, with significant co-financing from the Government of Costa Rica, UNDP, and the Government of Germany through Deutsche Gesellschaft für Internationale Zusammenarbeit (GIZ).  The allocation of these sources of finances is structured by the three main project components, as described in section C.2.d above.  Table 5 below details this allocation.  For every US$ dollar contributed by the GEF, an additional US$ 1.40 has been leveraged.  See Table 9.

- The Total Input Budget and Work Plan for the GEF contribution is provided in Annex 9of this project document.

Table 5:  Project Costs (US$)

| Total Project Budget(by Component) | GEF (US$) | Co-Financing (US$) | Project Total (US$) |
| --- | --- | --- | --- |
| Component 1: Integrated inter-ministerial decision-making | 100,000 | 132,000 | 232,000 |
| Component 2: Integrating Rio Conventions into environmental laws | 370,000 | 457,000 | 827,000 |
| Component 3: Strengthened technical and management capacities | 440,000 | 490,000 | 930,000 |
| Project Management | 70,000 | 286,000 | 356,000 |
| Total project costs | 980,000 | 1,365,000 | 2,345,000 |

Table 6:  Estimated Project management budget/cost (estimated cost for the entire project) (1)

| Component | Estimated Staff weeks | GEF (US$) | Co-Financing (US$) (5) | Project Total (US$) |
| --- | --- | --- | --- | --- |
| Locally recruited personnel: Project Manager (2) | 48 | 40,000 | 55,000 | 95,000 |
| Locally recruited personnel: Project Assistant (5) | 60 | 15,000 | 60,000 | 75,000 |
| Internationally recruited consultant (3) | 4 | 15,000 | 0 | 15,000 |
| Office facilities and communications (4) |  | 0 | 150,000 | 150,000 |
| Travel(Regional Mainstreaming meetings) |  | 0 | 21,000 | 21,000 |
| Total project management cost |  | 70,000 | 286,000 | 356,000 |

(1)  Local and international consultants in this table are those who are hired for functions related to the management of project.  Please see Table 7 below for consultants providing technical assistance for special services

(2) The Environmental Lawyer will have additional duties as the Project Manager, to the extent possible.

(3) The International Consultant will conduct an independent terminal evaluation of the project

(4) In addition to office space for the project team, this budget will cover the cost of Project Board meetings, four times per year.

(5) The Project Assistant is part-time

- An internationally recruited consultant will be contracted to undertake the independent final evaluation towards the end of the project.  This fee is inclusive of the travel component that comprises the cost of DSA, TE and return airfare for the international consultant.  The travel budget will be used to finance the cost of the project manager and the project assistant’s travel to regional meetings.

Table 7:  Consultants for technical assistance components (estimated for entire project)

| Technical Assistance Consultants | Estimated Staff weeks | GEF (US$) | Co-Financing* (US$) | Project Total (US$) |
| --- | --- | --- | --- | --- |
| Natural Resource Management Expert | 44 | 55,000 | 10,000 | 65,000 |
| Environmental Education Specialist | 58 | 72,500 | 15,000 | 87,500 |
| Environmental Lawyer | 122 | 152,500 | 20,000 | 172,500 |
| Land Management Expert | 37 | 46,250 | 7,500 | 53,750 |
| Energy Specialist | 37 | 46,250 | 7,500 | 53,750 |
| Environmental Economist | 14 | 17,500 | 5,000 | 22,500 |
| Information Technology Expert | 26 | 32,500 | 7,500 | 40,000 |
| International Technical Specialist | 7 | 17,500 | 7,500 | 25,000 |
| Total |  | 440,000 | 80,000 | 520,000 |

* The in-kind co-financing includes government staff time to support the work of the consultants

- No UNDP Implementing Agency services are being charged to the Project Budget.  All such costs are being charged to the IA fee.  The Government of Costa Rica has requested UNDP to provide a few execution services (including procurement and recruitment) under the National Execution Arrangements, and these will be charged to the Project Budget.  Details of such charges can be provided at the time these services are requested, but are outline in Annex 11 relating to direct project costs.

## D.2   Cost-Effectiveness

- The cost-effectiveness of this project lies largely in the project strategy, namely by building upon a significant baseline and leveraged commitment and a legislative framework government environmental and natural resource management.  This cost-effectiveness is indicated by the government’s significant co-financing to project activities in the order of US$ 900,000.  Although largely in-kind, a large portion of this contribution is real financial resources, taking into account the significant investment of government staff (decision-makers and planners) to actively participate in project activities.  Table 8 is an estimate of this contribution over the three years of project implementation.

Table 8:  In-kind contribution of government staff time to project activities

| Government Staff Contribution | Estimated Staff Weeks | Government in-kind (US$) |
| --- | --- | --- |
| Natural Resource Management | 90 | 90,000 |
| Environmental Education | 60 | 60,000 |
| Environmental Law | 60 | 60,000 |
| Land Management | 45 | 45,000 |
| Energy and Climate Change | 45 | 45,000 |
| Environmental Economics | 45 | 45,000 |
| Information and Communication Technology | 75 | 75,000 |
| Total |  | 420,000 |

- The cost-effectiveness of this project is also demonstrated in efficiently allocation and management of financial resources.  The recruitment of consultants under the project will be financed by the GEF contribution, reducing the transaction costs associated when contracting consultants and other services through multiple sources of finances (see Table 7 above).  Cost-effectiveness is also pursued by contracting an individual who will carry out both the TORs of the environmental lawyer and the position of project manager.

Table 9:  Project Costs (%age)

| Project Budget Component (by Contribution type) | Contribution (US$) | Percentage (%) |
| --- | --- | --- |
| Component 1: GEF | 100,000 | 4.3 |
| Component 1: Co-Financing | 132,000 | 5.6 |
| Component 2: GEF | 370,000 | 15.8 |
| Component 2: Co-Financing | 457,000 | 19.5 |
| Component 3 GEF | 440,000 | 18.8 |
| Component 3 Co-Financing | 490,000 | 20.9 |
| Project Management: GEF | 70,000 | 3.0 |
| Project Management: Co-Financing | 286,000 | 12.2 |
| Total | 2,345,000 | 100 |

## D.3   Co-financing

- Co-financing to the project is being provided from a number of sources.  The first source of financing is from the Government of Costa Rica, Ministry of Environment and Energy (MINAE), whose US$ 900,000 is a significant contribution towards the active investment of staff time and other in-kind resources to strengthen the shared understanding and interpretation of existing environmental legislation from a Rio Convention perspective.  In particular, government planners and decision-makers in MINAE and Ministry of National Planning and Economic Policy (MIDEPLAN), including key stakeholders in other ministries and agencies, will agree on modifying their approach to the enforcement of selected environmental legislation.  Government in-kind resources will be made available to host various consultative and decision-making meetings.

- Co-financing is also provided bythe Government of Germany through Deutsche Gesellschaft für Internationale Zusammenarbeit (GIZ), which will support project activities in the form of in-kind co-financing of US$ 350,000.  These resources will be used largely for supporting improved awareness of non-state stakeholders on the value of enforcing environmental legislation.  GIZ support will also contribute to high quality analyses undertaken by the project by facilitating access to best practices and lessons learned from German experiences, among other sources worldwide.  This will include supporting the project’s activities to pilot the implementation of Inter-Ministerial Council decisions, such as convening special legislative reviews of selected plans from a newly negotiated harmonization/reconciliation of environmental legislation.

Table 10:  Co-financing Sources

| Sources of Co-financing | Name of Donor | Type of Co-financing | Amount (US$) |
| --- | --- | --- | --- |
| Government | MINAE | In-Kind | 900,000 |
| GEF Implementing Agency | UNDP | Cash | 15,000 |
| Bilateral Donor | GIZ | In-Kind | 350,000 |
| GEF Implementing Agency | UNDP/LECB | In-Kind | 100,000 |
| Total Co-financing |  |  | 1,365,000 |

- Significant co-financing is also being provided by UNDP.  The first contribution is in the amount of US$ 15,000, which will be used to contract an independent expert to undertake the terminal evaluation.  UNDP’s second contribution will come through the Costa Rica’s national component of the Low Emission Capacity Building Programme (LECB), which will carry out a number of related activities.  This includes awareness-raising dialogues, trainings, and learn-by-doing workshops.  See Annex 8.

# E.	Institutional Coordination and Support

## E.1   Core Commitments and Linkages

### E.1.a	Linkages to other activities and programmes

- There are a number of development projects underway in Costa Rica, a few of which are directly relevant and complementary to this project.  This includes the Low Emission Capacity Building project (See Annex 8) that will support the implementation of the National Climate Change Strategy by improving their national Greenhouse Gas inventory, formulating Nationally Appropriate Mitigation Actions (NAMAs) and developing Measurement, Reporting and Verification (MRV) systemsin selected sectors.  There are a number of activities of the LECB project that will be coordinated with this CCCD project.  This includes the surveys and analysis of activity 1.1.1; the stakeholder constituent dialogues of 2.1.4; the technical working groups to be carried out under activity 2.2.1; and the piloting of policy recommendations and monitoring and compliance reforms of activities 2.2.2 and 2.3.2 respectively.

- Another related project is the Integrated Polychlorinated Biphenyl (PCB) Management, the objective of which is to minimize risks of exposure from PCBs to people and the Environment in Costa Rica. To this end, this project sets out to decrease the barriers for achieving sound PCB management through the following components: 1) strengthened institutional capacity in Costa Rica for the environmentally sound management of PCBs; 2) environmentally sound management and interim storage of PCBs;  3) environmentally sound destruction of PCBs and management of contaminated equipment; and 4) awareness-raising and communication.  A particular feature of this project that is linked with the current CCCD project is the review and updating of PCB legislation as well as the development and adoption of norms and regulations for the environmentally sound management of PCBs.  This project will create a working committee on PCB to develop proposed legal instruments.  This activity is similar to the technical working groups and MEA technical committees that will identify priority legal instruments needing of strengthening.  Both sets of activities will be appropriately coordinated to promote synergies and cost-effectiveness, but more importantly to ensure that project activities are working in tandem and not counter-productively.

- Another project is the conservation, sustainable use of biodiversity, and maintenance of ecosystem services of internationally important protected wetlands.  This project includes trainings directed to protected area officials, judges, prosecutors, polices and other authorities on national legislation for the control of introduced species.  This training is directly related to and complementary to the training activities under this CCCD project that will help improve a better understanding and interpretation of legislative authorities towards their improved monitoring and enforcement.

- Coordination and linkages with other programmes and activities during the three years of project implementation will be facilitated by meetings of the Project Board and the Inter-Ministerial Council, ensuring that there is no duplication of donor resources and catalyzing cost-effectiveness through synergies.

## E.2   Implementation and Execution Arrangements

- UNDP is the GEF Implementing Agency for this project, with the UNDP Country Office responsible for transparent practices, appropriate conduct and professional auditing.  The Executing Agency is the Ministry of Environment and Energy (MINAE), which will assign a National Project Director (NPD) and provide its staff and network of experts as support to Project Management Unit (as part of government co-financing).

- This project will be implemented under the National Development Programme 2011-2014 of Costa Rica, on a programme of activities to meet national commitments to the Rio Conventions, among other multilateral environmental agreements.  With the objective of this project on mainstreaming MEA objectives into inter-ministerial structures and mechanisms, UNDP will also be supporting the Government of Costa Ricato fully meet sustainable development goals, to maintain momentum and eliminate barriers to delivering of the remaining commitments.

- The United Nations Development Assistance Framework (UNDAF) is the result of an agreement of the UN System in Costa Rica based on the national priorities and needs, including those defined in the National Development Plan (NDP) 2013-2017 and the country's commitments around the Millennium Development Goals (MDGs), and other international commitments.  The present project is aligned with national priorities and the UNDAF 2013-2017, agreed between the Government of Costa Rica and the U.N.  System Country Team.  It is consistent with the following outcomes: capacity building of local actors for a sustainable development, inclusive and equitable; promotion of effective participation of people in the formulation, implementation and evaluation of public policies; development of analytical skills in social organizations for an informed and sustained public participation; changes in economic and socio-cultural practices in priority groups, in favor of environmental sustainability; and creation and strengthening of social networks that work under the principles of solidarity and respect for human rights.

- The project will be implemented in line with established Government of Costa Rica and UNDP procedures in Costa Rica.  MINAE will take overall responsibility for implementation of the project, and for the project success.  It will establish the necessary planning and management mechanisms to oversee project inputs, activities and outputs.  The UNDP CO will support the Ministry as requested and as necessary.  The basic implementation and execution framework is depicted in Figure 4.

Ministers

National Executing Agency:  MINAE

National Project Director

Project Steering Committee

(Expanded Council of Focal Points)

Project Management Unit

Project Coordinator

Project Assistant

Technical Committees / Working Groups

National Consultants

Capacity Development Activities

- Figure 4:  Project execution

- Project Board:  This Board is specifically established by the project to provide management oversight of project activities and is to be chaired by the MINAE (Focal Point for the CBD, CCD, FCCC, and GEF).  The Board will review progress and evaluation reports, and approve programmatic modifications to project execution, as appropriate and in accordance to UNDP procedures.  Policy recommendations will be discussed and recommended for consideration by the Cabinet of Ministers.  The Board will be chaired by the NPD (see paragraph 151).  In addition to the MINAE, government membership of the Project Board will include the MIDEPLAN, as well as representatives from the line ministries responsible and their respective state agencies.  Non-state stakeholders will also be represented on the Project Board, namely from the private sector, academic and research institutions, NGOs, and CSOs.  The Project Board will meet four (4) times per year, practically at the UNDP Country Office Headquarters.  Meetings will be co-financed by UNDP.

- The MINAE is the Senior Beneficiary of the project on the basis that the project will be strengthening and integrating Rio Convention provisions into their sectoral policies, legislation, policies and plans and institutional mandates.  UNDP will be the Senior Supplier, providing technical guidance and support for the cost-effective procurement and implementation of project services and activities, including project implementation oversight through regular monitoring and reporting.

- National Project Director:  A senior government official will be designated at the National Project Director (NPD), and will be responsible for management oversight of the project.  The NPD will devote a significant part of his/her working time on the project.  Duties and responsibilities of the NPD are described in Annex 6.  In the fulfillment of his/her responsibilities, the NPD will be supported by the Project Board and a full-time National Project Manager (NPM).

- Project Management Unit:  The MINAE will establish a Project Management Unit (PMU) for the day-to-day management of project activities and subcontract specific components of the project to specialized government agencies, research institutions, as well as qualified NGOs.  The PMU will be administered by a National Project Manager (NPM) (who will have additional substantive functions as the Environmental Lawyer) and supported by a Project Assistant.

- National Consultants:  The project will contract seven (7) national experts as consultants to provide technical guidance and facilitate the learn-by-doing mainstreaming exercises.  See Annex 6 for indicative Terms of References for these national experts.

- Capacity Development Activities:  The project will take an adaptive collaborative management (ACM) approach to implementation.  That is, UNDP and MINAE will manage project activities in order that stakeholders are involved early and throughout project implementation, providing regular input of the performance of project activities.  This will help signal unforeseen risks and contribute to the timely modification and realignment of activities within the boundaries of the project's goal and objectives.

- Stakeholder Consultations:  These consultations will focus on the active participation of stakeholders in the training and awareness-raising activities.  Specifically, consultations with stakeholders will be led by the Project Manager and the National Project Director to secure their interest and commitment to participating actively in the workshops to reconcile the various environmental and natural resource management legislation from a Rio Convention lens.  Members of the Project Board will also be expected to act as project championsto further facilitate stakeholder participation in project activities.

# PART II:	ANNEXES

Annex 1:  Costa Rica’s Environmental and related Laws	52

Annex 2Capacity Development Scorecard:	53

Annex 3:Logical Framework	53

Annex 4:Outcome Budget (GEF Contribution and Co-financing)	53

Annex 5:Provisional Work Plan	77

Annex 6:Terms of References	86

Annex 7:Environmental and Social Review Criteria	93

Annex 8:Costa Rica’s participation in the Low Emission Capacity Building Project	103

Annex 9:Total GEF Budget and Work Plan	105

Annex 10:PDF/PPG Status Report	105

Annex 11:Standard letter of agreement between UNDP and Government of Costa Rica	110

## Annex 1:    Costa Rica’s national environmental laws

There are more than 30 laws covering environmental and natural resource management issues in Costa Rica.

1909-10-26	Law on Fencing and Burning (No.  121)

1942-08-25	Water Law (No.  276)

1961-07-20	Wildlife Conservation Law and its reforms (No.  2790)

1972-03-02 	Maritime Zoning Law (No.  6043)

1973-06-15 	Law Creating the National Weather Institute (No.  5022)

1977-08-17 	Law on the Establishment of National Parks (No.  6084)

1982-10-04 	Law Creating the Ministry of Industry, Energy and Mines (No.  6812)

1982-10-04 	The Mining Code (Law No.  6796) and

2002-04-24	Law Modifying the Mining Code (No.  8246)

1982-12-27 	Ratification of and Expansion of National Parks and Biological Reserves (No.  6794)

1985-12-16 	Law for the Import and Control of Agro Chemicals (No.  7017)

1990-06-05 	Law Converting the Ministry of Industry, Energy and Mines into the Ministry of National Resources, Energy and Mines(No.  7152)

1991-12-07 	Law Mandating Environmental Protection Awareness in Primary and Secondary Education(No.  7235)

1992-12-07 	Wildlife Conservation Law (No.  7317)

1994-04-05 	Law Creating Guidance on Improving the Environment (No.  7381)

1994-05-03 	Law of Hydrocarbons (No.  7399)

1994-11-13 	Law Regulating the Rational Use of Energy (No.  7447)

1995-10-04 	Organic Law of the Environment (No.  7554)

1996-02-05 	Forestry Law (No.  7575)

1997-04-08 	Phytosanitary Law (No.  7664)

1998-02-06 	Law Granting Concessions and Operation of Tourism Marinas (No.  7744)

1998-05-21 	Law on the Use, Management and Conservation of Soils (No.  7779)

1998-05-27 	Law on Biodiversity (No.  7788)

1999-09-24 	Law on the Inter-American Protection and Conservation ofSea Turtles (No.  7906)

1999-11-26 	Agreement between Costa Rica and the United States on the International Conservation of Dolphins (No.  7938)

2000-10-10 	Law on the Management of the ReventazónUpper River Basin (No.  8023)

2001-02-05 	Law Creating the Pacific Marine Park (No.  8065)

2001-10-09 	Law Creating the Board of Directors for the Manuel Antonio National Recreation Park (No.  8133)

2002-01-28 	Law on the Protection, Conservation and Recovery of the Marine Turtle Population (No.  8325)

2002-05-21 	Law on the National System on Quality (No.  8279)

## Annex 2:    Capacity Development Scorecard

| Capacity Result / Indicator | Staged Indicators | Rating | Score | Comments | Next Steps | Contribution to which Outcome |
| --- | --- | --- | --- | --- | --- | --- |
| CR 1: Capacities for engagement |  |  |  |  |  |  |
| Indicator 1 – Degree of legitimacy/mandate of lead environmental organizations | Institutional responsibilities for environmental management are not clearly defined | 0 |  | The MINAE has limitationsin itsleading roleinthefieldof the environmental sector and while enacting directives to other ministries and institutions with impacts on the environment. These limitations are more evident when it comes to other institutions and sectors outside MINAE such as those affecting transportation, agriculture or energy. Also, decision makers are not sensible to environmental issues, especially if they are outside the environmental sector. | MINAE will have strengthened its management and leading capacities to integrate global environmental priorities into national environmental and development strategies, plans, and programmes. The awareness and sensitization of non-environmental sectors, decision-makers, non-state stakeholders, and the civil society in general will have substantially improved. By the end of project, Costa Rica will have strengthened its capacities to better integrate global environmental objectives into national policy and planning frameworks | Project Outcome 1 |
|  | Institutional responsibilities for environmental management are identified | 1 |  |  |  |  |
|  | Authority and legitimacy of all lead organizations responsible for environmental management are partially recognized by stakeholders | 2 | 2 |  |  |  |
|  | Authority and legitimacy of all lead organizations responsible for environmental management recognized by stakeholders | 3 |  |  |  |  |
| Indicator 2 – Existence of operational co-management mechanisms | No co-management mechanisms are in place | 0 |  | Co-management/participation experiences are incipient in the country. Even though there is legislation and policies that promote citizen participation, the reality is that institutional mistrust to enforce such participation prevails. In relation to co-operation, there were incipient experiences in wildlife-protected areas, which were later on declared illegal, because it was considered that there was no legal framework for it. On the other hand, there are successful experiences of citizen involvement such as the regional boards for wild land and conservation areas of Costa Rica. | By reinvigorating the capacity of the existing ministerial council meetings responsible for Rio convention implementation, the abilities to negotiate and facilitate cooperative agreements among them will be strengthened. Also, by improving existing consultation and coordination mechanisms, and promoting information sharing agreements with academia and civil society, the decisions made in relation to the global environment will become more inclusive, legitimate, resilient and robust. | Project Outcome 2 |
|  | Some co-management mechanisms are in place and operational | 1 |  |  |  |  |
|  | Some co-management mechanisms are formally established through agreements, MOUs, etc. | 2 | 2 |  |  |  |
|  | Comprehensive co-management mechanisms are formally established and are operational/functional | 3 |  |  |  |  |
| Indicator 3 – Existence of cooperation with stakeholder groups | Identification of stakeholders and their participation/involvement in decision-making is poor | 0 |  | Key stakeholders have been identified for issues related to the conventions. There are also formal mechanisms for consultation and advisory committees that meet permanently. However, this participation does not always include decision-making processes, since they remain highly centralized. | The project will engage through a learning-by-doing process, key decision-making champions and other multi-stakeholders to collaborate and negotiate on an integrated approach to deliver global environmental benefits through improved interpretation, planning, and decision-making on environmental and sectoral policies, plans and programmes from the Rio Conventions perspective. Stakeholders will also participate in training workshops and national dialogues to better incorporate the best decision-making practices into the council meetings, decentralizing this process and make it more inclusive. | Project Outcomes 1 and 2 |
|  | Stakeholders are identified but their participation in decision-making is limited | 1 |  |  |  |  |
|  | Stakeholders are identified and regular consultations mechanisms are established | 2 | 2 |  |  |  |
|  | Stakeholders are identified and they actively contribute to established participative decision-making processes | 3 |  |  |  |  |
| CR 2: Capacities to generate, access and use information and knowledge |  |  |  |  |  |  |
| Indicator 4 – Degree of environmental awareness of stakeholders | Stakeholders are not aware about global environmental issues and their related possible solutions (MEAs) | 0 |  | Key stakeholders are aware of global issues related to the Conventions, but they are not provided with sufficient information to perform a substantive participation in framing solutions. Some stakeholders contribute with actions related to the convention obligations, but their participation is based on their own experience and not based on formal policies and or strategies. | Based on the an initial survey of stakeholders awareness and understanding of environmental laws and the Rio Convention provisions, MEA technical committees recommendations will be structured. Consequently, the project will conduct a series of MEA technical committees in order to recommend best environmental decision-making practices. | Project Outcomes 1 and 2 |
|  | Stakeholders are aware about global environmental issues but not about the possible solutions (MEAs) | 1 |  |  |  |  |
|  | Stakeholders are aware about global environmental issues and the possible solutions but do not know how to participate | 2 | 2 |  |  |  |
|  | Stakeholders are aware about global environmental issues and are actively participating in the implementation of related solutions | 3 |  |  |  |  |
| Indicator 5 – Access and sharing of environmental information by stakeholders | The environmental information needs are not identified and the information management infrastructure is inadequate | 0 |  | There are no formal mechanisms where key actors may have access to, or receive sufficient environmental information to effectively comply with the conventions provisions. Convention-related information is a complex issue, which also requires being adapted to different audiences. | Sinceon-going training is critical for the success of this initiative, the project comprises a provision of trainings, using the training of trainers methodology in order to create coaching programs on complex issues (land degradation, access to biodiversity, biotechnology, mitigation and adaptation to climate change) to extension workers, city officials, decision makers; as well as public administration for global environmental management and sustainable development. | Project Outcome 3 |
|  | The environmental information needs are identified but the information management infrastructure is inadequate | 1 | 1 |  |  |  |
|  | The environmental information is partially available and shared among stakeholders but is not covering all Project Outcome focal areas and/or the information management infrastructure to manage and give information access to the public is limited | 2 |  |  |  |  |
|  | Comprehensive environmental information is available and shared through an adequate information management infrastructure | 3 |  |  |  |  |
| Indicator 6 – Existence of environmental education programmes | No environmental education programmes are in place | 0 |  | Although Costa Rica has been internationally recognized on popular environmental awareness, there are no comprehensive programmes on Environmental Education. There are some initiatives both at formal and informal education levels, but they are neither comprehensive nor do they reach all audiences. Rio Convention topics are fairly new and are not necessarily included in environment educational programs. | An analysis of the Public perception, values, participation and factors of influence will be performed both at the beginning of the project and at the end to register the progress and the impact of its awareness activities, which also include the development a high-quality Public Service Announcement (PSA) to be broadcasting in both radio and television, and high school targeted educational modules. A webpage on Rio Conventionswill be updated and a social network page (Facebook) will be created. These materials will be elaborated taking into account the diversity of the population (age range, and socio-economic and cultural levels) and targeted information will be reproduced in two of the principal indigenous native languages besides Spanish. | Project Outcome 3 |
|  | Environmental education programmes are partially developed and partially delivered | 1 | 1 |  |  |  |
|  | Environmental education programmes are fully developed but partially delivered | 2 |  |  |  |  |
|  | Comprehensive environmental education programmes exist and are being delivered | 3 |  |  |  |  |
| Indicator 7 – Extent of the linkage between environmental research/science and policy development | No linkage exist between environmental policy development and science/research strategies and programmes | 0 |  | The country does environmental research, but the information that is generated does not feed either the decision-making process or the strategy/policy-making procedures. Nevertheless, the current national environmental research is still incipient, mainly due to the lack of technical, economic and staff resources, so that it could be consistent. | The project seeks to integrate a holistic and participatory approach to decision-making by strengthening information sharing agreements with universities, research institutions, and CSOs, and thus improving the existing consultation and coordination mechanisms. The project will also identify and participate, as relevant and appropriate, in scientific, policy-based and/or any other networks and platforms, which may be of benefit to project implementation though lessons learned. | Project Outcome 1 |
|  | Research needs for environmental policy development are identified but are not translated into relevant research strategies and programmes | 1 | 1 |  |  |  |
|  | Relevant research strategies and programmes for environmental policy development exist but the research information is not responding fully to the policy research needs | 2 |  |  |  |  |
|  | Relevant research results are available for environmental policy development | 3 |  |  |  |  |
| Indicator 8 – Extent of inclusion/use of traditional knowledge in environmental decision-making | Traditional knowledge is ignored and not taken into account into relevant participative decision-making processes | 0 |  | Although the protection of traditional knowledge associated with biodiversity should be protected under to the law, it has not been implemented effectively. This entails a participatory consultation process, which has not been implemented due to insufficient resources. There are also questions on issues such as representativeness and legitimacy, so that the consultation on these issues is in accordance with the provisions of the ILO Convention 169. | The project seeks to provide with tailored guidelines that assist the government, non-governmental organizations, private sector and all other relevant stakeholders in enhancing and supporting compliance with MEAs, laws and agreements. In the making of these guidelines to better comply with the MEAs provisions, Article 8(j) of the CBD will be analyzed, discussed and incorporated. Also, all project activities arestrengthened through indigenous-sensitive participation in forums, trainings, workshops and dialogues. Articles on legislative responses for Rio Convention implementation will be targeted to the general population and printed in two main indigenous languages, beside Spanish. | Project Outcomes 2 and 3 |
|  | Traditional knowledge is identified and recognized as important but is not collected and used in relevant participative decision-making processes | 1 | 1 |  |  |  |
|  | Traditional knowledge is collected but is not used systematically into relevant participative decision-making processes | 2 |  |  |  |  |
|  | Traditional knowledge is collected, used and shared for effective participative decision-making processes | 3 |  |  |  |  |
| CR 3: Capacities for strategy, policy and legislation development |  |  |  |  |  |  |
| Indicator 9 – Extend of the environmental planning and strategy development process | The environmental planning and strategy development process is not coordinated and does not produce adequate environmental plans and strategies | 0 |  | Costa Rica does not have a comprehensive and long-term public policy on sustainable development. The country has sectorial policies and a National Development Plan that guide the annual operational plans of the different institutions. The Rio Convention obligations are not fully included in these environmental plans and strategies, which in turn, are not fully implemented because of budgetary constraints of the public institutions with responsibilities in this area. | The aim of this project is to integrate global environmental objectives into national policy and planning frameworks. Specifically, it will involve the targeting of specific reforms to meeting global environmental objectives and the approval of a strategy for environmental policy reforms under implementation. It will also include the strengthening of an inter-ministerial committee to coordinate environmental policies in Costa Rica. In order to alleviate financial barriers to the implementation of the Conventions,MEA technical committees will organize a resource mobilization (RM) strategy to perform a set of RM activities in a coordinated manner (i.e. Audit the resource need; Identify target donors; Outline the approach for each donor; Develop targeted messages for advocacy; Track performance of funds and provide accountability, among others). | Project Outcomes 1 and 3 |
|  | The environmental planning and strategy development process does produce adequate environmental plans and strategies but there are not implemented/used | 1 |  |  |  |  |
|  | Adequate environmental plans and strategies are produced but there are only partially implemented because of funding constraints and/or other problems | 2 | 2 |  |  |  |
|  | The environmental planning and strategy development process is well coordinated by the lead environmental organizations and produces the required environmental plans and strategies; which are being implemented | 3 |  |  |  |  |
| Indicator 10 – Existence of an adequate environmental policy and regulatory frameworks | The environmental policy and regulatory frameworks are insufficient; they do not provide an enabling environment | 0 |  | Costa Rica has a large number of environmental policies and legislation, which result in the following issues: overlapping of powers between institutions; contradictions across laws and unawareness among law enforcers. Furthermore, there are relatively new issues of the Rio Convention obligations that need to be legislated such as climate change activities and GMOs, among others. | This project aims at the re- structuring of organizational relationships, promoting and forging stronger relationships, partnerships and commitments. As a result, improved coordination and collaboration should reduce overlap and duplication of activities, catalyze the effective and efficient exchange of information, and improve the country’s implementation of the three Rio Conventions. The project will pilot the sharing of information as well as lessons learned and best practices to document the findings. Furthermore, by raising public awareness, building partnerships, and promoting policy dialogue, the project will seek to promote an enabling environment within government ministries and agencies, as well as with the other sectors of the Costa Rican society for achieving sustainable development and addressing global environmental issues. | Project Outcomes 1 and 2 |
|  | Some relevant environmental policies and laws exist but few are implemented and enforced | 1 | 1 |  |  |  |
|  | Adequate environmental policy and legislation frameworks exist but there are problems in implementing and enforcing them | 2 |  |  |  |  |
|  | Adequate policy and legislation frameworks are implemented and provide an adequate enabling environment; a compliance and enforcement mechanism is established and functions | 3 |  |  |  |  |
| Indicator 11 – Adequacy of the environmental information available for decision-making | The availability of environmental information for decision-making is lacking | 0 |  | Decision-making is not always based on the best available scientific information. Often times, decision-making is done without scientific consultation and later on, if an issue arises, information is searched to alleviate this issue and to justify the decisions made at the time. | The project seeks to assess and strengthen existing consultative and decision-making structures and mechanisms to make more effective and integrated decisions on the global environment. This includes the National Environmental Council and the Rio Convention-specific advisory commissions and technical committees. Moreover, the project encompasses de design and implementation of a comprehensive training programme and public awareness campaign, which are targeted to decision-makers, technical staff, and key practitioners. | Project Outcomes 1 and 3 |
|  | Some environmental information exists but it is not sufficient to support environmental decision-making processes | 1 | 1 |  |  |  |
|  | Relevant environmental information is made available to environmental decision-makers but the process to update this information is not functioning properly | 2 |  |  |  |  |
|  | Political and administrative decision-makers obtain and use updated environmental information to make environmental decisions | 3 |  |  |  |  |
| CR 4: Capacities for management and implementation |  |  |  |  |  |  |
| Indicator 12 – Existence and mobilization of resources | The environmental organizations don’t have adequate resources for their programmes and projects and the requirements have not been assessed | 0 |  | There are serious difficulties in public institutions to implement projects and programs. These include lack of personnel, technical resources and equipment. Some environmental organizations may have these resources, but they cannot always provide public institutions with support to perform their work. | The project will contribute with comprehensive training modules of civil servants on best practices and innovations for Rio Convention implementation through mainstreaming. Also, a resource management strategy will be formulated to help address financial constraints. | Project Outcome 3 |
|  | The resource requirements are known but are not being addressed | 1 |  |  |  |  |
|  | The funding sources for these resource requirements are partially identified and the resource requirements are partially addressed | 2 | 2 |  |  |  |
|  | Adequate resources are mobilized and available for the functioning of the lead environmental organizations | 3 |  |  |  |  |
| Indicator 13 – Availability of required technical skills and technology transfer | The necessary required skills and technology are not available and the needs are not identified | 0 |  | To overcome some of the shortcomings in this matter, MINAE´s Bureau of International Cooperation (BIC) is frequently sought: as is the case of the CC bureau, in which half of its staff is financed by the BIC. The country must identify and implement new local sources of funding as economical instruments, because international cooperation in Costa Rica is becoming increasingly scarce. | Along with the resource mobilization strategy, this project will support an extensive programme of training, information dissemination and advocacy to ensure adherence and involvement of concerned stakeholders in the policy and institutional reforms. | Project Outcome 3 |
|  | The required skills and technologies needs are identified as well as their sources | 1 |  |  |  |  |
|  | The required skills and technologies are obtained but their access depend on foreign sources | 2 | 2 |  |  |  |
|  | The required skills and technologies are available and there is a national-based mechanism for updating the required skills and for upgrading the technologies | 3 |  |  |  |  |
| CR 5: Capacities to monitor and evaluate |  |  |  |  |  |  |
| Indicator 14 – Adequacy of the project/programme monitoring process | Irregular project monitoring is being done without an adequate monitoring framework detailing what and how to monitor the particular project or programme | 0 |  | Project monitoring is seldom made in a participatory way, since project elaboration is itself performed in a non-participatory manner. Generally, much of the effort is focused on the project design and implementation, but little effort is made in monitoring and in using lessons learned to improve project implementation. | All the project activities related to implementation and evaluation of public policies in favor of environmental sustainability have a lessons learned and best practices component. Moreover, the project seeks to strengthen monitoring and compliance of the environmental laws and will create, finalize and secure a high-level commitment of new monitoring and compliance guidelines of environmental laws and MEAs. A Working Group for monitoring and evaluation of progress in project implementation will be established. An external independent evaluation team will perform the terminal evaluation ensuring neutrality and objectiveness. | Project Outcomes 1, 2 and 3 |
|  | An adequate resourced monitoring framework is in place but project monitoring is irregularly conducted | 1 | 1 |  |  |  |
|  | Regular participative monitoring of results in being conducted but this information is only partially used by the project/programme implementation team | 2 |  |  |  |  |
|  | Monitoring information is produced timely and accurately and is used by the implementation team to learn and possibly to change the course of action | 3 |  |  |  |  |
| Indicator 15 – Adequacy of the project/programme monitoring and evaluation process | None or ineffective evaluations are being conducted without an adequate evaluation plan; including the necessary resources | 0 |  | The majority of international cooperation funded projects have evaluation plans. These evaluations are mainly performed internally, by the executing agency and by the funding agencies. But the results are not shared, thus lessons-learned cannot be extracted to be used for other projects to achieve improvement. | During the lifetime of the project, specific measures will be undertaken to promote the exchange of information and capture lessons learned that could be replicated within and outside Costa Rica. Moreover, this national project, by integrating MEAs into an approved national strategy to national legislation and policies, will lead to regional and local policies across the country that will effectively watch over sustainable use of natural resources, leading to benefits to local population. The project also complementsthe Regional Sustainable Development Framework (PARCA) developed within the cooperation scheme of the Central American Integration System. | Project Outcomes 1, 2 and 3 |
|  | An adequate evaluation plan is in place but evaluation activities are irregularly conducted | 1 |  |  |  |  |
|  | Evaluations are being conducted as per an adequate evaluation plan but the evaluation results are only partially used by the project/programme implementation team | 2 | 2 |  |  |  |
|  | Effective evaluations are conducted timely and accurately and are used by the implementation team and the Agencies and GEF Staff to correct the course of action if needed and to learn for further planning activities | 3 |  |  |  |  |

## Annex 3:Logical Framework

| Project Strategy | Objectively verifiable indicators |  |  | Sources of verification |  |  | Risks and Assumptions |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Indicator | Baseline value | Target value and date |  |  |  |  |  |  |  |
| Long-term goal: To integrate and institutionalize inter-ministerial decision-making for effective and sustainable MEA implementation through existing national environmental legislation |  |  |  |  |  |  |  |  |  |  |
| Project objectives: A. Tomainstream the international commitments derived from the Rio Conventions into targeted national environmental legislation | Outcome indicators: - A targeted set of improved capacities to meet and sustain Rio Convention objectives is improved - Commitments under the Rio Conventions will have been strengthened and institutionalized - Existing national development strategies, plans and programmes will better support a more harmonized approach to implementing existing environmental legislation | - Capacities to implement the Rio Conventions are not sustainable, requiring donor-funded projects - Commitments to implement the Rio Conventions are measured through Rio Convention-specific instruments - National environmental policy instruments contain provisions that counteract each other and are weakly implemented | By the end of the project: - Rio Convention obligations are being better implemented through existing environmental legislation, 15% increase in survey value response - A year-end analysis of environmental legislation shows an improvement in institutional responses to monitoring and enforcing environmental legislation for the Rio Conventions. - There is a minimum of 20% increase in the understanding of the Rio Convention mainstreaming among government staff - There is a minimum of 15% increase in the appreciation of the Rio Conventions among the general public | - Meeting Minutes - Working Group meeting reports - UNDP quarterly progress reports - Independent final evaluation reports - Rio Convention national reports and communications - Inter-Ministerial Council decisions - GEF Cross-Cutting Capacity Development Scorecard - Statistical analyses of surveys carried out under activities 1.1.1 and 3.2.1 |  |  | - The various government authorities maintain commitment to negotiate and agree on differential enforcement of environmental legislation to more effectively meet Rio Convention obligations - The project will be executed in a transparent, holistic, adaptive, and collaborative manner - Non-state stakeholder representatives, in particular project champions, remain active participants in the project - Policy, legislative and institutional reforms are politically, technically, and financially feasible, and are approved by the Inter-Ministerial Council |  |  |  |
| Project Strategy | Objectively verifiable indicators |  |  | Sources of verification |  |  | Risks and Assumptions |  |  |  |
|  | Indicator | Baseline value | Target value and date |  |  |  |  |  |  |  |
| Outcome 1: Integrated inter-ministerial decision-making process for the global environment strengthened |  |  |  |  |  |  |  |  |  |  |
| Output 1.1 Strengthened MEA technical Committees | - Awareness and understanding of Rio Convention (MEA) technical committee members - Frequency of MEA technical committee meetings - Policy recommendations submitted by MEA technical committee to Inter-Ministerial Council - Technical recommendations submitted to line ministries and agencies | - Advisory commissions exist as equivalents of MEA technical committee, but they meet on an ad hoc basis and there is communication and coordination among them - There is some representation of non-state actors in the advisory commission for biodiversity, but not for the climate change or land degradation - The work of the advisory commissions does not effectively contribute to government actions doe to unclear attribution of responsibilities | - Baseline survey of decision-makers’ and planners’ awareness carried out with N>100 participants, completed by month 4 of the project. - Year-end survey of decision-makers’ and planners’ awareness carried out with N>250 participants, completed by month 32 of the project. - Three (3) MEA technical committees (CBD, CCD, and FCC) are created by month 4 with a membership of expert stakeholder representation of at least 10 different stakeholders (government, NGOs, academia, private sector, and civil society). The technical committees will meet at least three (3) times per year. - MEA technical committees submit policy recommendations to the Inter-Ministerial Council twice (2) a year, the first by month 9. | - Survey analysis - Meeting minutes - Tracking and progress reports - Peer review ratings |  |  | - Members of the MEA technical committees will be comprised to proactive experts and project champions - Survey results will show an increased awareness and understanding of the Rio Conventions’ implementation through national environmental legislation over time. |  |  |  |
| Project Strategy | Objectively verifiable indicators |  |  | Sources of verification |  |  | Risks and Assumptions |  |  |  |
|  | Indicator | Baseline value | Target value and date |  |  |  |  |  |  |  |
| Output 1.2: Strengthened information sharing agreements with academia and civil society | - Baseline analysis of information needs for the global environment - Feasibility study for the strengthening of an electronic information-sharing mechanism - An information-sharing agreement signed by MINAE and key non-state actors (same as in output 2.2) | - Much data and information relevant to the Rio Conventions exists, but for the most part is not in a form that readily lends itself to sharing electronically. - Data and information is largely accessible on an ad hoc basis - There are multiple electronic sources of information, but do not contain all useful data and information | - In-depth baseline analysis substantively peer reviewed by at least 8 national experts, and completed by month 5 of the project - Feasibility study for the strengthening of an existing electronic platform and internet interface prepared and completed by month 7. - Independent assessment of the performance of the electronic information system as implemented under 3.5.1 by month 30. - Agreement signed by MINAE and key non-state actors on the sharing of information by month 18 | - Formal communications - Meeting minutes - Tracking and progress reports - Meeting minutes - Signed agreement |  |  | - An agreement to share information between government and non-state actors is realistic |  |  |  |
| Output 1.3: Re-invigorated Inter-Ministerial Council meetings | - Cooperative agreements on legislative oversight with Inter-Ministerial Council members and other line ministries - Meetings of the Inter-Ministerial Council - Inter-Ministerial Council supports MEA technical committee recommendations | - There is no formal agreement among ministries to reconcile overlapping oversight of environmental and related legislation - The Inter-Ministerial Council only meets to discuss climate change issues. | - Key ministries sign relevant agreements by month 12. - Inter-Ministerial Council meets twice (2) per year to discuss and approve MEA technical committee recommendations, and before month 9 - At least 80% of the MEA technical committee recommendations are supported by appropriate inter-ministerial decisions by month 34 | - Formal communications - Meeting minutes - Tracking and progress reports - Inter-Ministerial Council decisions |  |  | - Agreement to cooperate on modifying existing mandates and authorities on legislative oversight is realistic |  |  |  |
| Outcome 2: Cross-cutting Rio Convention provisions are integrated into environmental legislation |  |  |  |  |  |  |  |  |  |  |
| Project Strategy | Objectively verifiable indicators |  |  |  | Sources of verification |  |  |  | Risks and Assumptions |  |
|  | Indicator | Baseline value | Target value and date |  |  |  |  |  |  |  |
| Output 2.1: In-depth analysis of environmental legislation and its governance Output 2.1: In-depth analysis of environmental legislation and its governance (continued) | - Roster of expert peer reviewers on the global environment created - Rio Convention analytical framework - Targeted analytical reports on environmental governance per the Rio Conventions - Stakeholder consultations on Rio Convention governance at the national level - Regional and non-state representation in stakeholder constituent dialogues - Consensus agreements from MEA technical committee on recommendations for improved environmental governance | - There are many experts working on most, if not all, aspects of the Rio Conventions - There are many analyses pertaining to the Rio Conventions, but most all are focused on reporting requirements - There are numerous stakeholder consultations, but most all are either targeted to focal area or sustainable development objectives - Regional and non-state stakeholders participate in many government-sponsored consultative dialogues, but these are nearly all very targeted to focal area or sustainable development interventions - Technical recommendations by the advisory commissions do not take into account similar technical recommendations by other advisory commissions | - A roster of peer reviewers with minimum 50 experts is created by month 3 - Analytical framework prepared and completed by month 6 - At least five (5) independent peer reviewers rate the framework of high quality - Four (4) in-depth analyses targeting Costa Rica’s environmental governance from a Rio Convention perspective completed by month 10 - Synthesis analysis is endorsed by all members of the MEA technical working groups and the MEA technical committee by month 12 - MEA technical committee drafts policy recommendations for the Inter-Ministerial Council by month 14 - All reports are discussed and validated at open-ended stakeholder dialogues within two months of their completion - Each stakeholder constituent dialogue is attended by at least 30 representatives that cover the range of stakeholder views and perspectives. - Each stakeholder constituent dialogue endorses the analyses and offers broad support for endorsement by the MEA technical committee and subsequent approval by the Inter-Ministerial Council. - At least two (2) stakeholder representatives from each of the seven (7) provinces have participated in at least one of the stakeholder constituent dialogues by month 33. |  | - Formal communications - Meeting minutes, including list of participants - Analytical reports - Tracking and progress reports |  |  |  | - National experts agree to be expert reviewers and provide timely feedback on project analyses - Regional and non-state stakeholder representation in project activities legitimately reflect their stakeholder constituent views and priorities |  |
| Project Strategy | Objectively verifiable indicators |  |  |  | Sources of verification |  |  |  | Risks and Assumptions |  |
|  | Indicator | Baseline value | Target value and date |  |  |  |  |  |  |  |
| Output 2.2: Learn-by-doing integration of Rio Conventions into select environmental legislation Output 2.2: Learn-by-doing integration of Rio Conventions into select environmental legislation (continued) | - Three Rio Convention technical working groups established under the MEA Technical Committees - Draft agreement on information sharing (see output 1.2) - Modified enforcement of existing national environmental legislation per Rio Convention obligation - High quality progress reports and independent assessment of legislative reforms. - Expert workshops convened to regularly assess conflicts between environmental legislation - Best practice and lesson learned reports | - Technical working groups and workshops under Rio Conventions are not institutionalized by rather temporary organizational mechanisms under focal area projects - There is no formal or institutional agreement on the sharing of information across ministries, agencies or non-state actors - Numerous progress reports are prepared and submitted resulting in an over-burdening of government staff and low commitment, but these remain targeted to focal area priorities - Expert meetings do not adequately address the cross-cutting barriers to effective implementation of national environmental legislation - Development partners in Costa Rica are committed to supporting the country’s improved access to better data and information on innovative approaches to meeting global environmental objectives. | - Three Rio Convention technical working groups are created and meet by month 7 of the project and at least twice (2x) per year. - Technical working groups present their findings and recommendations to the MEA technical committees by month and subsequently within one month of convening. - Technical working group draft a non-legally binding agreement on the mutual sharing of information among each other and with the government by month 12 of the project - Three policy recommendations piloted and completed by month 26 - Government agencies and departments responsible for testing policy recommendations submit quarterly progress reports to the MEA technical committees every three months with the first no later than month 12. - Two (2) expert workshops with at least 30 relevant key actors each, organized and concluded by month 18 - Three (3) best practice and lessons learned reports are prepared on targeted regional Rio Convention mainstreaming activities by month 12, month 23, and month 33 - Technical guidelines are drafted and finalized by month 24 - Policy recommendations to legitimize these guidelines, as appropriate, are prepared, submitted, and approved by the Inter-Ministerial Council by month 28 |  | - Formal communications - Meeting minutes, including list of participants - Analytical reports - Tracking and progress reports - Inter-Ministerial Council decisions |  |  |  | - Best practices and lessons learned from other countries are appropriately used - GoCR officials at all levels remain committed to the modified interpretation of environmental legislation - The right representation from the various government ministries, departments and agencies participate in project activities - Pilot implementation of select modified interpretation and enforcement of environmental legislation |  |
| Project Strategy | Objectively verifiable indicators |  |  |  | Sources of verification |  |  |  | Risks and Assumptions |  |
|  | Indicator | Baseline value | Target value and date |  |  |  |  |  |  |  |
| Output 2.3: Strengthened monitoring and compliance Output 2.3: Strengthened monitoring and compliance (continued) | - Monitoring and compliance indicators - Monitoring and compliance assessment reports - Monitoring and compliance guidelines and tools - Policy decisions on legislative and institutional reforms to reconcile and harmonize environmental and related legislation to conform with Rio Convention obligations - Training workshops on monitoring of and compliance with environmental legislation - Number of relevant government staff having clear present and potential future roles in monitoring and compliance | - There are no clear monitoring or compliance indicators to assess the extent to which Rio Convention obligations are being delivered through existing national environmental legislation - Monitoring reports are internal documents that have unclear value to planners and decision-makers - Monitoring and compliance guidelines and tools are not widely known among planners and decision-makers - Inter-Ministerial Council focuses on climate change, but there is no equivalent policy decision-making mechanism that is as effective on biodiversity or land degradation - Trainings to take place on environment-related issues, however these remain targeted to focal area issues, with inadequate attention to environmental legislative reforms | - Clear monitoring and compliance reforms submitted to the MEA technical committee after three monitoring phases: by month 12, by month 23, and by month 33 - Quarterly progress reports are submitted to the MEA technical committees every three months, beginning by month 15 - Lessons learned of pilot monitoring and compliance reforms discussed in a stakeholder constituent dialogue by month 22 - Survey of N>100 experts and other stakeholders by month 22 and a second survey by month 33 rate successful piloting of monitoring and compliance reforms - MEA technical committee proposes monitoring and compliance reforms to institutionalize best practice monitoring and compliance procedures by month 32 - Inter-Ministerial Council authorizes at least 80% of MEA technical committee recommended reforms by month 34 - Report on guidelines, tools and resources for the effective interpretation, supervision and enforcement of environmental legislation completed by month 8 - New guidelines, tools, and other resources are available through the electronic platform by month 12 - Comprehensive training programme drafted by month 18 and endorsed by the MEA technical committees by month 20 - Four (4) training workshops and related exercises begin by month 20 - At least 80 government staff members that are directly implicated in the planning and decision-making process to monitor and enforce environmental legislation have participated in training workshops by month 33 - Operational guidelines are drafted and finalized by month 24 and validated by month 26 - Policy recommendations to legitimize these guidelines, as appropriate, are prepared, submitted, and approved by the Inter-Ministerial Council by month 28 |  | - Formal communications - Meeting minutes, including list of participants - Analytical reports - Tracking and progress reports - Inter-Ministerial Council decisions |  |  |  |  |  |
| Outcome 3: Strengthened technical and management capacities |  |  |  |  |  |  |  |  |  |  |
| Project Strategy | Objectively verifiable indicators |  |  | Sources of verification |  |  |  | Risks and Assumptions |  |  |
|  | Indicator | Baseline value | Target value and date |  |  |  |  |  |  |  |
| Output 3.1: Kick-Off and Project Results Conferences | - One-day Kick-Off Conference to raise high profile of project - One-day Project Results Conference to showcase lessons learned and best practices - Four (4) expert panel discussions on Rio Convention sub-themes | - The environmental movement in Costa Rica is relatively strong compared to other countries, and there is an overall strong interest among the NGO community and population to learn about innovative opportunities to catalyze environmental action - Development partners in Costa Rica are committed to supporting the country’s improved access to better data and information on innovative approaches to meeting global environmental objectives. | - One-day Kick-Off Conference is held by month 3 - One-day Project Results Conference is held by month 34 - Over 200 participants attend both the Kick-Off and Project Results conferences, representing a good diversity of stakeholders, including representation from other regions of Costa Rica - At least four (4) expert panel discussions present the lessons learned to deliver Rio Convention obligations through existing national environmental and related legislation - At least 30 participants attend each of the panel discussions | - Conference registration lists - Expert panelist participation - Meeting minutes - Tracking and progress reports |  |  |  | - Participation to the conference assumes that most all stakeholders are adequately represented at the conferences - Conferences will further enhance support for pursuing Rio Convention obligations |  |  |
| Project Strategy | Objectively verifiable indicators |  |  |  |  | Sources of verification |  |  |  | Risks and Assumptions |
|  | Indicator | Baseline value | Target value and date |  |  |  |  |  |  |  |
| Output 3.2: Public awareness campaign, survey, and educational materials Output 3.2: Public awareness campaign, survey, and educational materials (continued) | - Analysis of Costa Rica’s environmental values (survey results) - Public awareness plan on national environmental legislation and Rio Conventions - Articles on legislative responses to implement Rio Conventions - High School competition plan - Education module on environmental legislation and Rio Conventions implemented - Public Service Announcement airings on television and radio that promote compliance with existing environmental legislation | - Awareness and understanding of the Rio Conventions in Costa Rica is relatively good compared to other countries. However, this is not as effectively translated into compliance with environmental legislation, further exacerbated by conflicting provisions of environmental and natural resource management legislation and regulation | - Two broad-based surveys (N>500) completed by month 3 and by month 34 - Expert and independent analysis of the survey results completed by month 35 - A comprehensive public awareness plan developed to completed by month 6 - At least nine (9) articles on legislative responses for Rio Convention implementation in Costa Rica published in popular literature with high circulation before the end of the project. By month 6, at least one article should be published. By month 18, at least four (4) articles should be published. By month 30, at least seven (7) articles should be published. - Each article edited and published as a brochure, with at least 100 copies each and distributed to at least two high value special events - High school competition plan for completed by month 9 - At least two (2) high schools carry out high school competitions by month 20; at least six (6) by month 33 - Education module prepared for high schools completed by month 8 - At least two (2) high schools have implemented education module by month 20 and at least one high school in each of the seven provinces by month 33 - One PSA completed for both television and radio (audio version) by month 12, with the first airing by month 15. - At least 50 airings of the PSA on television and at least 100 airings of the PSA on radio, both by month 34 |  |  | - Survey instrument - Survey responses - Statistical and sociological analysis reports (2x) - Analytical reports - Popular press - High school curricula - Television and radio |  |  |  | - Survey respondents contribute their honest attitudes and values - Changes in awareness and understanding of national environmental legislation contribution to meeting Rio Convention obligations can be largely attributed to project activities (survey questionnaire can address this issue) - Socio-economic pressures do not de-value environmental attitudes and concern |
| Project Strategy | Objectively verifiable indicators |  |  |  |  | Sources of verification |  |  |  | Risks and Assumptions |
|  | Indicator | Baseline value | Target value and date |  |  |  |  |  |  |  |
| Output 3.3: Awareness-raising dialogues and workshops Output 3.3: Awareness-raising dialogues and workshops (continued) | - Awareness workshops targeted to the private sector, journalists, local and regional government representatives on national environmental legislation and the Rio Conventions - Survey data on environmental attitudes and values (activity 3.2.1) - Expert MEA legislative mainstreaming workshops (complements learn-by-doing workshops of output 2.2) - Cutting-edge panel discussions by leaders in the environmental field on environmental legislation for meeting Rio Convention obligations | - Media professionals generally have no special training of Rio Convention issues, in particularly of the linkages between non-compliance of national environmental legislation and global environmental impacts - The private sector is primarily focused on traditional approaches to maximizing profits, seeing environmental issues as an added transaction cost that reduces profits - Public dialogues take place through the construct of donor-funded projects on focal areas and do not adequately address the conflicting impacts on other environmental priorities - Regional government representatives are not adequately familiar with approaches to meet Rio Convention obligations given their heightened obligations to meet socio-economic development priorities within their short-term regional development plans - The general public in Costa Rica is generally aware and concerned about global environmental issues, but increasingly behaviour is detached from these values due to increasing socio-economic pressures and in the absence of innovative approaches to comply with existing environmental legislation | - Three (3) panel discussions, with at least 20 private sector representatives the completed by month 8; the second by month 18; and the third by month 28 - At least three (3) journalist awareness workshops held, each with at least 10 representatives the first completed by month 9; the second by month 19; and the third by month 29 - By month 33, reporting on Rio Convention mainstreaming in the popular media shows a 10% increase over forecasted trends using baseline data and past trends - At least three (3) workshops of MEA legislative mainstreaming are convened with at least 20 expert practitioner participants the first completed by month 10; the second by month 20; and the third by month 30 - At least three (3) regional workshops are convened, with local and regional government representatives with at least one representative from each of the seven Costa Rican provinceshaving participated in at least one workshop. Each workshop should be attended by at least 20 local/regional representatives. The first regional workshop should be completed by month 11; the second by month 21; and the third by month 31 - Three (3) cutting-edge policy dialogues with invited leaders in the field of environmental governance the first dialogue convened by month 7; the second by month 17; and the third by month 27 |  |  | - Meeting minutes - Tracking and progress reports - Participant registration lists - Awareness and sensitization workshop reports - Public dialogue meeting reports - Survey results - Newspaper citations |  |  |  | - Public attitudes towards environment are not too negative and socio-economic pressures not too great that they are willing to participate in awareness raising activities - There is sufficient commitment from policy-makers to maintain long-term support to public awareness raising activities - Media representatives and private sector representatives are open to learn about Rio Convention values and opportunities, and will actively work to support project objectives - Participation to the public dialogues attracts people that are new to the concept of Rio Convention mainstreaming, as well as detractors, with the assumption that dialogues will help convert their attitudes in a positive way |
| Project Strategy | Objectively verifiable indicators |  |  |  |  | Sources of verification |  |  |  | Risks and Assumptions |
|  | Indicator | Baseline value | Target value and date |  |  |  |  |  |  |  |
| Output 3.4: Resource mobilization strategy | - Resource mobilization strategy report - Feasibility study on financial and economic instruments to advance monitoring and compliance of existing environmental legislation to meet Rio Convention obligations - Expert working group established | - Costa Rica benefits from significant interest from the donor community to finance capacity development actions to meet global environmental objectives - Government of Costa Rica is very committed to taking a uniquely innovative and transformative approach to meeting Rio Convention obligations within existing environmental legislative frameworks to reduce the dependence of official development assistance, which is not sustainable. | - Analytical report drafted, peer reviewed, and finalized by month 12 - Feasibility study on financial and economic instruments to advance the monitoring and compliance of environmental legislation for the global environment completed by month 18 - Expert working group is made up of at least 20 rotating members, who will undertake a desk review of the drafts of the analytical report and feasibility study, and meet at least once to discuss the findings of each within one month of their completion, i.e., by months 13 and 19 |  |  | - Meeting minutes - Tracking and progress reports - Participant registration lists - Workshop reports - Letters confirming pledges of co-financing from national sources |  |  |  | - Global financial and economic pressures do have significantly adverse impacts on the opportunities to mobilize resources from national sources, such as raising park entrance fees, increased enforcement and collection of fees and fines. - Compliance with environmental legislation can be politically and expediently pursued in tandem with socio-economic development plans and programmes, in particular green economy policies - Champions for innovative approaches to finance the enforcement and compliance of environmental legislation are not outdone by champion detractors |
| Project Strategy | Objectively verifiable indicators |  |  |  |  | Sources of verification |  |  |  | Risks and Assumptions |
|  | Indicator | Baseline value | Target value and date |  |  |  |  |  |  |  |
| Output 3.5: Internet visibility of integrated and streamlined environmental legislation | - Website promotes Rio Convention obligations through existing national environmental and natural resource management legislation - Facebook page on environmental legislation for the Rio Conventions | - There are a number of websites promoting environmental issues in Costa Rica. However, none are specific to environmental legislation. MINAE is committed to strengthen a comprehensive website that will provide a one-stop shop for understanding how to better interpret existing environmental and related legislation to meet both sustainable development and global environmental priorities. - Development partners in Costa Rica are committed to supporting the country’s improved access to better data and information on innovative approaches to meeting global environmental objectives. | - Feasibility study for the creation of a comprehensive environment legislation website prepared and completed by month 4 - Website architecture completed and endorsed by the MEA technical working group by month 6 - Website is updated at least once a month with new information, articles, and resources - Website statistical data rank the quality of the website (unique users, visit sessions, and page views) as a consistent top ten site of all Costa Rican websites by the twelfth month of being online and throughout the project’s three years of implementation. - Facebook page created by month 3 and updated on a weekly basis, at minimum - At least 2,000 Facebook likes by month 32 |  |  | - Meeting minutes - Tracking and progress reports - Survey results - Website and unique site visits using site meters - Facebook ‘likes’ |  |  |  | - Interest in environmental issues can be assumed to contribute to improved attitudes and values in meeting national environmental priorities, and that these translate into increased environmental-friendly behaviour that also produce increased global environmental benefits - The increased popularization of environmental-friendly attitudes, values and behaviour does not have the unintended consequence of mobilization a counter-acting anti-environmental movement from Rio Convention detractors |

## Annex 4:    Outcome Budget (GEF Contribution and Co-financing)

|  |  | Year | Year | Year |  | Co- | Total |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Activity | Description | 1 | 2 | 3 | GEF | financing |  |
|  | Total | 876,500 | 682,500 | 786,000 | 980,000 | 1,365,000 | 2,345,000 |
| Component 1: Integrated inter-ministerial decision-making |  | 128,000 | 32,000 | 72,000 | 100,000 | 132,000 | 232,000 |
| Output 1.1 | Comprehensive institutional analysis of environmental decision-making |  |  |  |  |  |  |
| 1.1.1 | Survey of awareness and understanding of environmental laws | 30,000 | 0 | 30,000 | 25,000 | 35,000 | 60,000 |
| 1.1.2 | MEA technical committee meetings to recommend best decision-making practices | 15,000 | 15,000 | 15,000 | 15,000 | 30,000 | 45,000 |
| Output 1.2 | Strengthened information sharing agreements with academia and civil society |  |  |  |  |  |  |
| 1.2.1 | Carry out an in-depth baseline analysis of information needs, sources and flows | 30,000 | 0 | 0 | 10,000 | 20,000 | 30,000 |
| 1.2.2 | Prepare a feasibility study on an improved electronic platform for information-sharing | 30,000 | 0 | 10,000 | 20,000 | 20,000 | 40,000 |
| Output 1.3 | Re-invigorated Inter-Ministerial Council meetings |  |  |  |  |  |  |
| 1.3.1 | Negotiate and facilitate cooperative agreements with line ministries | 15,000 | 10,000 | 10,000 | 15,000 | 20,000 | 35,000 |
| 1.3.2 | Convene and re-invigorate Inter-Ministerial Council meetings based on 1.1.2 | 8,000 | 7,000 | 7,000 | 15,000 | 7,000 | 22,000 |
| Component 2: Integrating Rio Convention provisions into environmental laws |  | 220,000 | 327,000 | 280,000 | 370,000 | 457,000 | 827,000 |
| Output 2.1 | In-depth analysis of environmental legislation |  |  |  |  |  |  |
| 2.1.1 | Identify and secure independent peer reviewers | 10,000 | 10,000 | 10,000 | 15,000 | 15,000 | 30,000 |
| 2.1.2 | Prepare Rio Convention analytical framework | 25,000 | 0 | 0 | 20,000 | 5,000 | 25,000 |
| 2.1.3 | Undertake in-depth analyses of environmental legislation and compliance | 30,000 | 20,000 | 0 | 25,000 | 25,000 | 50,000 |
| 2.1.4 | Convene four (4) stakeholder constituent dialogues | 20,000 | 40,000 | 20,000 | 30,000 | 50,000 | 80,000 |
| Output 2.2 | Learn-by-doing integration of Rio Conventions into select environmental legislation |  |  |  |  |  |  |
| 2.2.1 | Structure technical working groups on legislative responses and amendments | 25,000 | 25,000 | 25,000 | 15,000 | 60,000 | 75,000 |
| 2.2.2 | Pilot the implementation of Inter-Ministerial Council decisions | 0 | 55,000 | 75,000 | 55,000 | 75,000 | 130,000 |
| 2.2.3 | Identify best practices and cull lessons learned on pilot exercises of 2.3.2 | 10,000 | 25,000 | 25,000 | 25,000 | 35,000 | 60,000 |
| 2.2.4 | Draft technical guidelines for the strategic implementation of environmental legislation | 0 | 25,000 | 10,000 | 20,000 | 15,000 | 35,000 |

| Output 2.3 | Strengthened monitoring and compliance (M&C) |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 2.3.1 | Recommend improved monitoring and compliance reforms based on 1.2.1 and 2.1.3 | 15,000 | 15,000 | 15,000 | 15,000 | 30,000 | 45,000 |
| 2.3.2 | Pilot implementation of select M&C reforms | 30,000 | 40,000 | 40,000 | 50,000 | 60,000 | 110,000 |
| 2.3.3 | Undertake an assessment of existing guidelines, tools, and resources | 30,000 | 5,000 | 5,000 | 20,000 | 20,000 | 40,000 |
| 2.3.4 | Prepare a comprehensive training programme, including targeted training modules | 20,000 | 25,000 | 5,000 | 35,000 | 15,000 | 50,000 |
| 2.3.5 | Conduct four (4) training workshops on M&C best practices and innovations | 0 | 30,000 | 30,000 | 20,000 | 40,000 | 60,000 |
| 2.3.6 | Draft operational guidelines for coordinated monitoring and compliance | 5,000 | 12,000 | 20,000 | 25,000 | 12,000 | 37,000 |
| Component 3: Strengthened technical and management capacities |  | 396,500 | 221,500 | 312,000 | 440,000 | 490,000 | 930,000 |
| Output 3.1 | Kick-Off and Project Results Conferences |  |  |  |  |  |  |
| 3.1.1 | Organize and convene a one-day Kick-Off Conference | 30,000 | 0 | 0 | 10,000 | 20,000 | 30,000 |
| 3.1.2 | Organize and convene a one-day Project Results Conference | 0 | 0 | 30,000 | 10,000 | 20,000 | 30,000 |
| Output 3.2 | Public awareness campaign, survey, and educational materials |  |  |  |  |  |  |
| 3.2.1 | Carry out broad-based awareness survey (in conjunction with activity 1.1.1) | 17,500 | 0 | 17,500 | 15,000 | 20,000 | 35,000 |
| 3.2.2 | Prepare public awareness implementation plan | 25,000 | 0 | 0 | 10,000 | 15,000 | 25,000 |
| 3.2.3 | Prepare articles on legislative responses for Rio Convention implementation | 25,000 | 25,000 | 25,000 | 25,000 | 50,000 | 75,000 |
| 3.2.4 | Develop plan for high school competitions on Rio Conventions and implement | 30,000 | 25,000 | 25,000 | 20,000 | 60,000 | 80,000 |
| 3.2.5 | Prepare global environmental education module for high schools | 15,000 | 5,000 | 5,000 | 15,000 | 10,000 | 25,000 |
| 3.2.6 | Prepare and air a PSA on legislative links between local and global on TV and radio | 50,000 | 15,000 | 15,000 | 50,000 | 30,000 | 80,000 |
| Output 3.3 | Awareness-raising dialogues and workshops |  |  |  |  |  |  |
| 3.3.1 | Organize and convene private sector sensitization panel discussions | 30,000 | 30,000 | 30,000 | 30,000 | 60,000 | 90,000 |
| 3.3.2 | Organize and convene journalist awareness workshops | 20,000 | 20,000 | 20,000 | 30,000 | 30,000 | 60,000 |
| 3.3.3 | Organize and convene awareness workshops on MEA legislative mainstreaming | 25,000 | 25,000 | 25,000 | 30,000 | 45,000 | 75,000 |
| 3.3.4 | Organize and convene regional awareness workshops | 40,000 | 30,000 | 30,000 | 50,000 | 50,000 | 100,000 |
| 3.3.5 | Convene four (4) public policy dialogues | 0 | 0 | 50,000 | 30,000 | 20,000 | 50,000 |
| Output 3.4 | Resource mobilization strategy |  |  |  |  |  |  |
| 3.4.1 | Undertake an in-depth financial and economic analysis of the environmental M&C | 25,000 | 7,500 | 7,500 | 25,000 | 15,000 | 40,000 |
| 3.4.2 | Select best practice and innovative financial and economic instruments for piloting | 12,000 | 7,000 | 0 | 10,000 | 9,000 | 19,000 |
| 3.4.3 | Use MEA technical committees (1.1.2) to facilitate resource mobilization | 12,000 | 12,000 | 12,000 | 20,000 | 16,000 | 36,000 |

| Output 3.5 | Internet visibility of integrated and streamlined environmental legislation |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 3.5.1 | Develop and manage an easy-to-use one-stop environmental legislation website | 30,000 | 10,000 | 10,000 | 40,000 | 10,000 | 50,000 |
| 3.5.2 | Create and manage a Facebook page on Rio Convention mainstreaming | 10,000 | 10,000 | 10,000 | 20,000 | 10,000 | 30,000 |
| Project Management |  | 117,000 | 112,000 | 127,000 | 70,000 | 286,000 | 356,000 |
| A | Locally recruited personnel: Project Manager (1) | 35,000 | 30,000 | 30,000 | 40,000 | 55,000 | 95,000 |
| B | Locally recruited personnel: Project Assistant | 25,000 | 25,000 | 25,000 | 15,000 | 60,000 | 75,000 |
| C | International Evaluation Consultant Fee (2) | 0 | 0 | 15,000 | 15,000 | 0 | 15,000 |
| D | Office facilities and communications (3) | 50,000 | 50,000 | 50,000 | 0 | 150,000 | 150,000 |
| E | Travel (Regional Mainstreaming meetings) | 7,000 | 7,000 | 7,000 | 0 | 21,000 | 21,000 |
| Notes |  |  |  |  |  |  | , |
| (1) The Environmental Lawyer will have additional duties as the Project Manager |  |  |  |  |  |  |  |
| (2) The International Consultant will conduct an independent evaluation of the project |  |  |  |  |  |  |  |
| (3) In addition to office space for the project team, this budget will cover the cost of Project Board meetings, 4x per year. |  |  |  |  |  |  |  |

## Annex 5:Provisional Work Plan

| Year 1 |  | Month |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Activity | Description | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 |
| A | Project start-up: Organize project team and review work plan |  |  |  |  |  |  |  |  |  |  |  |  |
| B | Policy Board Meetings |  |  |  |  |  |  |  |  |  |  |  |  |
| Component 1: Integrated inter-ministerial decision-making |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 1.1 | Strengthened MEA technical committees |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.1.1 | Surveys of awareness and understanding of environmental legislation |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.1.2 | MEA technical committee meetings to recommend best decision-making practices |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 1.2 | Strengthened information sharing agreements with academia and civil society |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.2.1 | Carry out an in-depth baseline analysis of information needs, sources and flows |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.2.2 | Prepare a feasibility study on an improved electronic platform for information-sharing |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 1.3 | Re-invigorated Inter-Ministerial Council meetings |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.3.1 | Negotiate and facilitate cooperative agreements with key ministries |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.3.2 | Convene Inter-Ministerial Council meetings |  |  |  |  |  |  |  |  |  |  |  |  |
| Component 2: Integrating Rio Conventions into environmental legislation |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 2.1 | In-depth analysis of environmental legislation and its governance |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.1.1 | Identify and secure independent peer reviewers |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.1.2 | Prepare Rio Convention analytical framework |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.1.3 | Prepare in-depth analysis of environmental governance |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.1.4 | Convene four (4) stakeholder constituent dialogues |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 2.2 | Learn-by-doing integration of Rio Conventions into select environmental legislation |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.2.1 | Structure MEA technical working groups on legislative responses and amendments |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.2.2 | Pilot the implementation of Inter-Ministerial Council decisions |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.2.3 | Identify best practices and cull lessons learned on pilot exercises |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.2.4 | Draft technical guidelines for the strategic implementation of environmental legislation |  |  |  |  |  |  |  |  |  |  |  |  |

| Output 2.3 | Strengthened monitoring and compliance |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 2.3.1 | Recommend improved monitoring and compliance reforms based on 1.2.1 and 2.1.3 |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.3.2 | Pilot implementation of select monitoring and compliance reforms |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.3.3 | Undertake an assessment of existing guidelines, tools, and resources |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.3.4 | Prepare a comprehensive training programme, including targeted training modules |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.3.5 | Conduct trainings (4x) on best practices and innovations |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.3.6 | Draft and validate guidelines for coordinated monitoring and compliance |  |  |  |  |  |  |  |  |  |  |  |  |
| Component 3: Strengthened technical and management capacities |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 3.1 | Kick-Off and Project Results Conferences |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.1.1 | Organize and convene a one-day Kick-Off Conference |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.1.2 | Organize and convene a one-day Project Results Conference |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 3.2 | Public awareness campaign, survey, and educational materials |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.2.1 | Carry out broad-based awareness survey (in conjunction with activity 1.1.1) |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.2.2 | Prepare public awareness implementation plan |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.2.3 | Prepare articles on legislative responses for Rio Convention implementation |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.2.4 | Develop plan for high school competitions on Rio Conventions and implement |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.2.5 | Prepare global environmental education module for high schools |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.2.6 | Prepare and air a PSA on legislative links between local and global on TV and radio |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 3.3 | Awareness-raising dialogues and workshops |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.3.1 | Organize and convene private sector sensitization panel discussions |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.3.2 | Organize and convene journalist awareness workshops |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.3.3 | Organize and convene awareness workshops on MEA legislative mainstreaming |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.3.4 | Organize and convene regional awareness workshops |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.3.5 | Convene four (4) public policy dialogues |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 3.4 | Resource mobilization strategy |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.4.1 | Undertake an in-depth financial and economic analysis of the environmental M&C |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.4.2 | Select best practice and innovative financial and economic instruments for piloting |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.4.3 | Use MEA technical committees (1.1.2) to facilitate resource mobilization |  |  |  |  |  |  |  |  |  |  |  |  |

| Output 3.5 | Internet visibility of integrated and streamlined environmental legislation |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 3.5.1 | Develop and manage an easy-to-use one-stop environmental legislation website |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.5.2 | Create a Facebook page on Rio Convention mainstreaming |  |  |  |  |  |  |  |  |  |  |  |  |
| Project Management |  |  |  |  |  |  |  |  |  |  |  |  |  |
| A | Locally recruited personnel: Project Manager (1) |  |  |  |  |  |  |  |  |  |  |  |  |
| B | Locally recruited personnel: Project Assistant (1) |  |  |  |  |  |  |  |  |  |  |  |  |
| C | International Evaluation Consultant: Terminal Evaluation |  |  |  |  |  |  |  |  |  |  |  |  |
| D | Office facilities and communications (2) |  |  |  |  |  |  |  |  |  |  |  |  |
| E | Travel (Regional Mainstreaming meetings) |  |  |  |  |  |  |  |  |  |  |  |  |
| Notes |  |  |  |  |  |  |  |  |  |  |  |  |  |
| (1) Full-time position. The Environmental Lawyer will have additional duties as the Project Manager. |  |  |  |  |  |  |  |  |  |  |  |  |  |
| (2) In addition to office space for the project team, this budget will cover the cost of Project Board meetings, 4x per year. |  |  |  |  |  |  |  |  |  |  |  |  |  |

| Year 2 |  | Month |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Activity | Description | 13 | 14 | 15 |  | 16 |  | 17 |  | 18 | 19 | 20 |  | 21 |  | 22 |  | 23 |  | 24 |
| A | Project start-up: Organize project team and review work plan |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| B | Policy Board Meetings |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Component 1: Integrated inter-ministerial decision-making |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 1.1 | Strengthened MEA technical committees |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.1.1 | Surveys of awareness and understanding of environmental legislation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.1.2 | MEA technical committee meetings to recommend best decision-making practices |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 1.2 | Strengthened information sharing agreements with academia and civil society |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.2.1 | Carry out an in-depth baseline analysis of information needs, sources and flows |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.2.2 | Prepare a feasibility study on an improved electronic platform for information-sharing |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 1.3 | Re-invigorated Inter-Ministerial Council meetings |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.3.1 | Negotiate and facilitate cooperative agreements with key ministries |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.3.2 | Convene Inter-Ministerial Council meetings |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Component 2: Integrating Rio Conventions into environmental legislation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 2.1 | In-depth analysis of environmental legislation and its governance |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.1.1 | Identify and secure independent peer reviewers |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.1.2 | Prepare Rio Convention analytical framework |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.1.3 | Prepare in-depth analysis of environmental governance |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.1.4 | Convene four (4) stakeholder constituent dialogues |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 2.2 | Learn-by-doing integration of Rio Conventions into select environmental legislation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.2.1 | Structure MEA technical working groups on legislative responses and amendments |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.2.2 | Pilot the implementation of Inter-Ministerial Council decisions |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.2.3 | Identify best practices and cull lessons learned on pilot exercises |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.2.4 | Draft technical guidelines for the strategic implementation of environmental legislation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

| Output 2.3 | Strengthened monitoring and compliance |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 2.3.1 | Recommend improved monitoring and compliance reforms based on 1.2.1 and 2.1.3 |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.3.2 | Pilot implementation of select monitoring and compliance reforms |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.3.3 | Undertake an assessment of existing guidelines, tools, and resources |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.3.4 | Prepare a comprehensive training programme, including targeted training modules |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.3.5 | Conduct trainings (4x) on best practices and innovations |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.3.6 | Draft and validate guidelines for coordinated monitoring and compliance |  |  |  |  |  |  |  |  |  |  |  |  |
| Component 3: Strengthened technical and management capacities |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 3.1 | Kick-Off and Project Results Conferences |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.1.1 | Organize and convene a one-day Kick-Off Conference |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.1.2 | Organize and convene a one-day Project Results Conference |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 3.2 | Public awareness campaign, survey, and educational materials |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.2.1 | Carry out broad-based awareness survey (in conjunction with activity 1.1.1) |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.2.2 | Prepare public awareness implementation plan |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.2.3 | Prepare articles on legislative responses for Rio Convention implementation |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.2.4 | Develop plan for high school competitions on Rio Conventions and implement |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.2.5 | Prepare global environmental education module for high schools |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.2.6 | Prepare and air a PSA on legislative links between local and global on TV and radio |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 3.3 | Awareness-raising dialogues and workshops |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.3.1 | Organize and convene private sector sensitization panel discussions |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.3.2 | Organize and convene journalist awareness workshops |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.3.3 | Organize and convene awareness workshops on MEA legislative mainstreaming |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.3.4 | Organize and convene regional awareness workshops |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.3.5 | Convene four (4) public policy dialogues |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 3.4 | Resource mobilization strategy |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.4.1 | Undertake an in-depth financial and economic analysis of the environmental M&C |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.4.2 | Select best practice and innovative financial and economic instruments for piloting |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.4.3 | Use MEA technical committees (1.1.2) to facilitate resource mobilization |  |  |  |  |  |  |  |  |  |  |  |  |

| Output 3.5 | Internet visibility of integrated and streamlined environmental legislation |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 3.5.1 | Develop and manage an easy-to-use one-stop environmental legislation website |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.5.2 | Create a Facebook page on Rio Convention mainstreaming |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Project Management |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| A | Locally recruited personnel: Project Manager (1) |  |  |  |  |  |  |  |  |  |  |  |  |  |
| B | Locally recruited personnel: Project Assistant (1) |  |  |  |  |  |  |  |  |  |  |  |  |  |
| C | International Evaluation Consultant: Terminal Evaluation |  |  |  |  |  |  |  |  |  |  |  |  |  |
| D | Office facilities and communications (2) |  |  |  |  |  |  |  |  |  |  |  |  |  |
| E | Travel (Regional Mainstreaming meetings) |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Notes |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| (1) Full-time position. The Environmental Lawyer will have additional duties as the Project Manager. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2) In addition to office space for the project team, this budget will cover the cost of Project Board meetings, 4x per year |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

| Year 3 |  | Month |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Activity | Description | 25 | 26 | 27 |  | 28 |  | 29 |  | 30 |  | 31 | 32 |  | 33 |  | 34 |  | 35 |  | 36 |  |
| A | Project start-up: Organize project team and review work plan |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| B | Policy Board Meetings |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Component 1: Integrated inter-ministerial decision-making |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 1.1 | Strengthened MEA technical committees |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.1.1 | Surveys of awareness and understanding of environmental legislation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.1.2 | MEA technical committee meetings to recommend best decision-making practices |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 1.2 | Strengthened information sharing agreements with academia and civil society |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.2.1 | Carry out an in-depth baseline analysis of information needs, sources and flows |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.2.2 | Prepare a feasibility study on an improved electronic platform for information-sharing |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 1.3 | Re-invigorated Inter-Ministerial Council meetings |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.3.1 | Negotiate and facilitate cooperative agreements with key ministries |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.3.2 | Convene Inter-Ministerial Council meetings |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Component 2: Integrating Rio Conventions into environmental legislation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 2.1 | In-depth analysis of environmental legislation and its governance |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.1.1 | Identify and secure independent peer reviewers |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.1.2 | Prepare Rio Convention analytical framework |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.1.3 | Prepare in-depth analysis of environmental governance |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.1.4 | Convene four (4) stakeholder constituent dialogues |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 2.2 | Learn-by-doing integration of Rio Conventions into select environmental legislation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.2.1 | Structure MEA technical working groups on legislative responses and amendments |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.2.2 | Pilot the implementation of Inter-Ministerial Council decisions |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.2.3 | Identify best practices and cull lessons learned on pilot exercises |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.2.4 | Draft technical guidelines for the strategic implementation of environmental legislation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

| Output 2.3 | Strengthened monitoring and compliance |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 2.3.1 | Recommend improved monitoring and compliance reforms based on 1.2.1 and 2.1.3 |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.3.2 | Pilot implementation of select monitoring and compliance reforms |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.3.3 | Undertake an assessment of existing guidelines, tools, and resources |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.3.4 | Prepare a comprehensive training programme, including targeted training modules |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.3.5 | Conduct trainings (4x) on best practices and innovations |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.3.6 | Draft and validate guidelines for coordinated monitoring and compliance |  |  |  |  |  |  |  |  |  |  |  |  |
| Component 3: Strengthened technical and management capacities |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 3.1 | Kick-Off and Project Results Conferences |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.1.1 | Organize and convene a one-day Kick-Off Conference |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.1.2 | Organize and convene a one-day Project Results Conference |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 3.2 | Public awareness campaign, survey, and educational materials |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.2.1 | Carry out broad-based awareness survey (in conjunction with activity 1.1.1) |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.2.2 | Prepare public awareness implementation plan |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.2.3 | Prepare articles on legislative responses for Rio Convention implementation |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.2.4 | Develop plan for high school competitions on Rio Conventions and implement |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.2.5 | Prepare global environmental education module for high schools |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.2.6 | Prepare and air a PSA on legislative links between local and global on TV and radio |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 3.3 | Awareness-raising dialogues and workshops |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.3.1 | Organize and convene private sector sensitization panel discussions |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.3.2 | Organize and convene journalist awareness workshops |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.3.3 | Organize and convene awareness workshops on MEA legislative mainstreaming |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.3.4 | Organize and convene regional awareness workshops |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.3.5 | Convene four (4) public policy dialogues |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 3.4 | Resource mobilization strategy |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.4.1 | Undertake an in-depth financial and economic analysis of the environmental M&C |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.4.2 | Select best practice and innovative financial and economic instruments for piloting |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.4.3 | Use MEA technical committees (1.1.2) to facilitate resource mobilization |  |  |  |  |  |  |  |  |  |  |  |  |

| Output 3.5 |  |  | Internet visibility of integrated and streamlined environmental legislation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 3.5.1 |  |  | Develop and manage an easy-to-use one-stop environmental legislation website |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.5.2 |  |  | Create a Facebook page on Rio Convention mainstreaming |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Project Management |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| A |  |  | Locally recruited personnel: Project Manager (1) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| B |  |  | Locally recruited personnel: Project Assistant (1) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| C |  |  | International Evaluation Consultant: Terminal Evaluation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| D |  |  | Office facilities and communications (2) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| E |  |  | Travel (Regional Mainstreaming meetings) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Notes |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| (1) The Environmental Lawyer will have additional duties as the Project Manager. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

## Annex 6:    Terms of References

The following Terms of Reference outlines the general responsibilities to be carried out by consultants contracted under the project.  They will be developed in detail at the onset of project implementation.

Background

Costa Rica completed its National Capacity Self-Assessment (NCSA) in 2007, the final report of which included a prioritization of capacity development actions by GEF focal area as defined by the three Rio Conventions, as well as those capacity development needs that cut across the three self-same Conventions.  In particular, Costa Ricaprioritized the strengthening of national organizational capacities necessary towards having a better understanding of how to more effectively implement the three Rio Conventions and other multilateral environmental agreements (MEAs) within the framework of their existing national legislation.  Recommended activities included better training and sensitization of government decision-makers responsible for rule-making and enforcement, as well as strengthening inter-agency cooperation for improved planning of environmentally sound and sustainable development.

The rationale for this project stems from the NCSA findings that there a great number (over 30) environment laws and decrees that generate much confusion, impeding Costa Rica’s ability to effectively comply with Convention objectives.  As a result, none of these legal instruments are effectively implemented or enforced, and in certain cases work against each other.  This is further exacerbated by decision-makers and planners not being adequately versed on the excessive legislation.  This is due to a variety of reasons including staff changes and insufficient training.

This project was developed under the GEF-5 Cross-Cutting Capacity Development (CCCD) Strategy to meet two complementary outcomes:  The first isObjective 3 of the CCCD Results Framework, which sets out to strengthen capacities for policy and legislation development for achieving global benefits.  Objective 4 of the CCCD Results Framework complements Objective 3 by undertaking a set of capacity development activities to strengthen capacities for management and implementation of convention guidelines.

Project Goal and Objectives

The goal of this project is tointegrate and institutionalize inter-ministerial decision-making for effective and sustainable MEA implementation through existing national environmental legislation.  To this end, the objective of this project is to mainstream the international commitments derived from the Rio Conventions into targeted national environmental legislation, and to do so by a learn-by-doing process that will institutionalize a long-term process for effective environmental governance.  The objective of this project is in line with the CCCD strategy of mainstreaming Rio Conventions into the national sustainable development baseline as a strategic approach to institutionalize national efforts that deliver global environmental benefits.  Annex 3 provides a logical framework of the project that deconstructs the project objective into component outputs and activities.

Project Strategy

Through a learning-by-doing process, this project will engage key decision-makers and planners, among other stakeholders, in the critical analysis of Costa Rica’s environmental governance.  Through this process, they will collaborate and negotiate on a shared approach on better approaches to deliver global environmental benefits through improved interpretation, planning, and decision-making on environmental and sectoral policies, plans and programmes from the lens of the three Rio Conventions.  These capacities will be institutionalized by the implementation of select recommendations that will serve to demonstrate the value of this approach through improved/reinforced compliance with Rio Conventions obligations.

The design of this project takes into account the Costa Rica’s National Development Plan (NDP), which currently serves as the over-arching planning instrument to achieve sustainable development.  Within this framework, the integration of Rio Convention provisions into environment legislation and regulation through better approaches for their implementation and oversight will serve as a catalyst to implement the NDP in a way that not only meets national socio-economic priorities, but also delivers global environmental benefits.  This project is complementary with the Regional Sustainable Development Framework (PARCA) developed within the cooperation scheme of the Central American Integration System.  This CCCD project will be closely coordinated with key GEF-financed projects, including Costa Rica's work to pursue low-emission and climate-resilient development (LECRD); and the UNDP/GEF project Overcoming Barriers to Sustainability of Costa Rica's Protected Areas System, the IADB/GEF project on Integrated Management of Marine and Coastal Resources in Puntarenas, and the UNDP/GEF project Consolidating Costa Rica’s Marine Protected Areas currently under implementation.

The project will take an adaptive collaborative management (ACM) approach to implementation, which calls for stakeholders to take an early and proactive role in the mainstreaming exercises, as well as to help identify and solve unexpected implementation barriers and challenges.  By taking an ACM approach, project activities and outputs can be more legitimately modified and adapted to maintain timely and cost-effective project performance and delivery.

Project Outcomes and Components

Component 1:	Integrated inter-ministerial decision-making process for the global environment

This first component focuses on assessing and structuring an improved consultative and decision-making process that effectively integrates global environmental objectives into existing national environmental legislation.  Without having to create any new environmental legislation, the project will make it easier for decision-makers to interpret and agree on how best to monitor and enforce environmental legislation that not only meets national priorities, but also global environmental obligations.  This component will focus on the processes to facilitate these decisions, whereas component 2 will focus on strengthening stakeholders’ and decision-makers’ knowledge and technical capacities towards the same result.  This component will also include strengthening the process by where expert interpretations from non-governmental stakeholders, such as NGOs, civil society, private sector and academia can provide their knowledge through the technical committees and other relevant mechanisms to be decided by the project.

Component 2:	Integrating cross-cutting Rio Convention provisions into environmental legislation

This second component is structured as a set of learn-by-doing formulation of legislative responses and amendments (as appropriate) to implement Rio Convention provisions as well as to identify and apply best practices for enforcing current environmental legal instruments to deliver global environmental benefits.  This will be addressed through three streams of activities:  The first is through a comprehensive analysis of all Costa Rica’s environmental regime (legislation, regulation, statutes, decrees, and institutional structures and mechanisms.  This analysis will complement targeted analyses on the flow of information from non-state actors to planners and decision-makers.  The second stream of activities picks up where the first stream leaves off and focuses on two pieces of environmental legislation to pilot and test their differentiated implementation and enforcement from a Rio Convention perspective.  The third stream of activities focuses on the development of monitoring and compliance guidelines.  The latter will include training on monitoring and compliance best practices and innovations.

Component 3:	Strengthened technical and management capacities

The aim of this third component is to strengthen the institutional sustainability of the project results by ensuring that there is sufficient awareness, understanding and know-how surrounding the project so that when it ends, there is less likelihood of reverting to the baseline.  While activities in component 2 focus on the learn-by-doing integrating of the Rio Conventions into environmental legislation, there is still a need to train other staff and stakeholders who would or could eventually become future planners and decision-makers.  The sustainability of the project also rests on ensuring that a sufficient baseline of stakeholders value the project and has the support of champions.  Activities are therefore directed to raising the public profile of the project, convening targeted awareness-raising workshops and developing related materials, as well as developing a resource mobilization strategy to address the financial sustainability of project results.

Responsibilities

National Project Director (NPD)

The Government of Costa Rica will appoint a national director for this UNDP-supported project.  The National Project Director supports the project and acts as a focal point on the part of the Government.  This responsibility normally entails ensuring effective communication between partners and monitoring of progress towards expected results.

The National Project Director is the party that represents the Government’s ownership and authority over the project, responsibility for achieving project objectives and the accountability to the Government and UNDP for the use of project resources.

In consultation with UNDP, the Ministry of Energy and the Environment, as the concerned ministry, will designate the National Project Director from among its staff at not lower than the Deputy Minister or Head of Department level.  The National Project Director (NPD) will be supported by a full-time National Project Manager (NPM).

Duties and Responsibilities of the NPD

The NPD will have the following duties and responsibilities:

- Assume overall responsibility for the successful execution and implementation of the project, accountability to the Government and UNDP for the proper and effective use of project resources)

- Serve as a focal point for the coordination of projects with other Government agencies, UNDP and outside implementing agencies;

- Ensure that all Government inputs committed to the project are made available;

- Supervise the work of the National Project Manager and ensure that the National Project Manager is empowered to effectively manage the project and other project staff to perform their duties effectively;

- Select and arrange, in close collaboration with UNDP, for the appointment of the National Project Manager (in cases where the NPM has not yet been appointed);

- Supervise the preparation of project work plans, updating, clearance and approval, in consultation with UNDP and other stakeholders and ensure the timely request of inputs according to the project work plans;

- Represent the Government institution (national counterpart) at the tripartite review project meetings, and other stakeholder meetings.

Remuneration and entitlements:

The National Project Director may not receive monetary compensation from project funds for the discharge of his/her functions.

A.	National Project Manager

The individual contracted as the Project Manager will also be recruited under a separate parallel contract for the position of the Environmental Lawyer.  One-quarter (25%) of this national consultant’s time will be spent overseeing the execution of the project’s capacity development activities as well as carrying out the monitoring and evaluation procedures as outlined in Section C.5.  These include:

- Oversee the day-to-day monitoring of project implementation

- In consultation with stakeholders, recommend modifications to project management to maintain project’s cost-effectiveness, timeliness, and quality project deliverables (adaptive collaborative management) to be approved by the Project Board

- Prepare all required progress and management reports, e.g., APR/PIR and project initiation report

- Support all meetings of the Project Board

- Maintain effective communication with project partners and stakeholders to dissemination project results, as well as to facilitate input from stakeholder representatives as project partners

- Support the independent terminal evaluation

- Ensure full compliance with the UNDP and GEF branding policy

B.	Project Assistant

The Project Assistant will support the Project Manager in the carrying out of his/her duties.  He/she will have at least three (3) years’ experience in supporting the implementation of UNDP implemented projects, with preference in environment and natural resource management projects.  Duties include:

- Organizational and logistical issues related to project execution per UNDP guidelines and procedures

- Record keeping of project documents, including financial in accordance with audit requirements

- Ensure all logistical arrangements are carried out smoothly

- Assist Project Manager in preparation and update of project work plans in collaboration with the UNDP Country Office

- Facilitate timely preparation and submission of financial reports and settlement of advances, including progress reports and other substantial reports

- Report to the Project Manager and UNDP Programme Officer on a regular basis

- Identification and resolution of logistical and organizational problems, under the guidance of the Project Manager

C.	Environmental Lawyer

The individual contracted as the Environmental Lawyer will also be recruited under a separate parallel contract for the position of theProject Manager.  He/she will undertake substantive project activities, including:

- Preparing technical materials and facilitating the MEA technical committee meetings (activity 1.1.2)

- Undertake an in-depth baseline analysis of information needs, sources and flows to implement environmental legislation (activity 1.2.1) (to be coordinated with activity 2.1.3)

- Facilitate negotiations among line ministries on cooperative agreements (activity 1.3.1)

- In collaboration with other national consultants, contribute to the preparation of the Rio Convention analytical framework (activity 2.1.2)

- Undertake an in-depth analysis of environmental legislation and compliance (activity 2.1.3) (to be coordinated with activity 1.2.1)

- Facilitate targeted consultations and negotiations to implement Inter-Ministerial Council decisions as well as select monitoring and compliance (activities 2.2.2 and 2.3.2)

- In collaboration with other national consultants, undertake an analysis of best practices and lessons learned (activity 2.2.3)

- Lead drafter of technical guidelines for the strategic implementation of environmental legislation (activity 2.2.4)

- In collaboration with other national consultants, draft recommended monitoring and compliance  reforms (activity 2.3.1)

- In collaboration with other national consultants, undertake an assessment of existing guidelines, tools and resources (activity 2.3.3)

- In collaboration with other national consultants, prepare a comprehensive training programme and targeted training modules (activity 2.3.4)

- In collaboration with other national consultants, draft operational guidelines for coordinated monitoring and compliance (activity 2.3.6)

- In collaboration with other national consultants, support sub-contracted NGO to carry out broad-based survey (activity 3.2.1)

- Contribute to the preparation of the public awareness implementation plan (activity 3.2.2)

- Contribute to the preparation of articles on legislative responses for Rio Convention implementation (activity 3.2.3)

- Contribute to the preparation and implementation of the high school competitions on the Rio Conventions (activity 3.2.4)

- In collaboration with other national consultants, prepare a global environmental education module for high schools (activity 3.2.5)

- In collaboration with other national consultants and the sub-contracted video production, prepare the narrative for the public service announcement (activity 3.2.6)

- In collaboration with other national consultants, undertake an in-depth financial and economic analysis of environmental monitoring and compliance (activity 3.4.1)

- In collaboration with other national consultants and based on consultations with stakeholders and the MEA technical committee members, facilitate meetings and at least one workshop to select best practice and innovative financial and economic instruments to piloted (activity 3.4.2)

- Contribute to the development of the environmental legislation website and Facebook (activities 3.5.1 and 3.5.2)

The Environmental Lawyer will have a post-graduate degree in law, with a specialization on environmental law, as well as have a minimum of ten (10) years’ experience in progressively responsible and substantive areas in environmental and natural resource governance programming and planning.

Other national experts and consultants will be recruited to support the implementation of project activities.  These include the:

D.  Environmental Education Specialist		G.  Information Technology Expert

E.  Environmental Economist			H.  Land Management Expert

F.  Energy Specialist				I.  Natural Resource Management Expert

In addition to the above national experts, a video production company will be sub-contracted to produce a high-quality public service announcement (PSA) for both radio and television.  This company will have had at least five (5) years’ experience in video production and will advise the Project Manager and UNDP on the best strategy for airing the PSAs.  Two international consultants will also be recruited under the project.  The International Evaluation Consultant(J) will carry out the independent terminal evaluation and an international technical specialist (K) will be retained on a part-time basis to provide necessary technical advisory services on the implementation of key project activities, in particular the preparation of technical analyses and drafting of integrated Rio Convention/sectoral policies, programmes, plans and/or legislation, as appropriate.  These services will be provided over the course of the three-year implementation period to provide technical backstopping to help ensure the timely and high quality project delivery.

The following table maps out the estimated number of weeks that each consultant will allocate to supporting the implementation of project activities.  This table will help inform the development of the Terms of References for each of the consultants at the beginning of the project.

Table A6.1    Project activities undertaken with direct support by consultants

Legend

| A | National Project Manager |  | G | Information Technology Expert |
| --- | --- | --- | --- | --- |
| B | Project Assistant |  | H | Land Management Expert |
| C | Environmental Lawyer |  | I | Natural Resource Management Expert |
| D | Environmental Education Specialist |  | J | International Technical Specialist |
| E | Environmental Economist |  | K | Terminal Evaluator |
| F | Energy Specialist |  |  |  |

| Activity | Description | A | B | C | D | E | F | G | H | I | J | K |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Component 1: Integrated inter-ministerial decision-making |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 1.1 | Comprehensive institutional analysis of environmental decision-making |  |  |  |  |  |  |  |  |  |  |  |
| 1.1.1 | Survey of awareness and understanding of environmental laws |  |  | 15 |  |  |  |  |  |  |  | 1 |
| 1.1.2 | MEA technical committee meetings | National Project Director and Project Manager |  |  |  |  |  |  |  |  |  |  |
| Output 1.2 | Strengthened information sharing agreements with academia and civil society |  |  |  |  |  |  |  |  |  |  |  |
| 1.2.1 | In-depth baseline analysis of information needs |  |  | 8 |  |  |  |  |  |  |  |  |
| 1.2.2 | Feasibility study on an improved information-sharing platform |  |  |  |  |  |  | 16 |  |  |  |  |
| Output 1.3 | Re-invigorated inter-ministerial council meetings |  |  |  |  |  |  |  |  |  |  |  |
| 1.3.1 | Cooperative agreements with line ministries |  |  | 10 |  |  |  |  |  |  |  |  |
| 1.3.2 | Inter-ministerial council meetings | National Project Director and Project Manager |  |  |  |  |  |  |  |  |  |  |

| Activity | Description | A | B | C | D | E | F | G | H | I | J | K |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Component 2: Integrating Rio Convention provisions into environmental laws |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 2.1 | In-depth analysis of environmental legislation |  |  |  |  |  |  |  |  |  |  |  |
| 2.1.1 | Identify and secure independent peer reviewers | National Project Director, Project Manager, Project Board |  |  |  |  |  |  |  |  |  |  |
| 2.1.2 | Prepare Rio Convention analytical framework |  |  | 4 |  |  | 2 |  | 2 | 2 |  |  |
| 2.1.3 | In-depth analyses of environmental legislation and compliance |  |  | 10 |  |  | 2 |  | 2 | 2 |  |  |
| 2.1.4 | Convene four (4) stakeholder constituent dialogues | National Project Director and Project Manager |  |  |  |  |  |  |  |  |  |  |
| Output 2.2 | Learn-by-doing integration of Rio Conventions into select environmental legislation |  |  |  |  |  |  |  |  |  |  |  |
| 2.2.1 | Technical working groups on legislative responses and amendments |  |  | 2 |  |  | 2 |  | 2 | 2 |  |  |
| 2.2.2 | Pilot the implementation of inter-ministerial council decisions |  |  | 2 |  |  | 2 |  | 2 | 2 |  |  |
| 2.2.3 | Identify best practices and cull lessons learned |  |  | 4 | 2 |  | 2 |  | 2 | 2 |  | 1 |
| 2.2.4 | Technical guidelines for the strategic implementation of environmental laws |  |  | 4 |  |  | 2 |  | 2 | 2 |  |  |
| Output 2.3 | Strengthened monitoring and compliance (M&C) |  |  |  |  |  |  |  |  |  |  |  |
| 2.3.1 | Recommend improved monitoring and compliance reforms |  |  | 3 |  |  | 2 |  | 2 | 2 |  |  |
| 2.3.2 | Pilot implementation of select M&C reforms |  |  | 2 |  |  | 2 |  | 2 | 2 |  |  |
| 2.3.3 | Undertake an assessment of existing guidelines, tools, and resources |  |  | 4 |  |  | 2 |  | 2 | 2 |  |  |
| 2.3.4 | Comprehensive training programme, including targeted training modules |  |  | 4 | 5 |  | 2 |  | 2 | 2 |  | 4 |
| 2.3.5 | Training workshops on M&C best practices and innovations |  |  | 3 | 1 |  | 2 |  | 2 | 2 |  |  |
| 2.3.6 | Draft operational guidelines for coordinated monitoring and compliance |  |  | 4 |  |  | 2 | 4 | 2 | 2 |  |  |

| Activity | Description | A | B | C | D | E | F | G | H | I | J | K |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Component 3: Strengthened technical and management capacities |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 3.1 | Kick-Off and Project Results Conferences |  |  |  |  |  |  |  |  |  |  |  |
| 3.1.1 | Organize and convene a one-day Kick-Off Conference |  |  | 1 |  |  | 1 |  | 1 | 1 |  |  |
| 3.1.2 | Organize and convene a one-day Project Results Conference |  |  | 1 |  |  | 1 |  | 1 | 1 |  |  |
| Output 3.2 | Public awareness campaign, survey, and educational materials |  |  |  |  |  |  |  |  |  |  |  |
| 3.2.1 | Broad-based awareness survey |  |  | 4 |  |  |  |  |  |  |  |  |
| 3.2.2 | Prepare public awareness implementation plan |  |  | 2 | 4 |  |  |  |  |  |  | 1 |
| 3.2.3 | Prepare articles on legislative responses to the Rio Conventions |  |  | 3 | 3 |  | 2 |  | 2 | 2 |  |  |
| 3.2.4 | High school competitions on Rio Conventions |  |  | 2 | 6 |  | 2 |  | 2 | 2 |  |  |
| 3.2.5 | Global environmental education module for high schools |  |  | 3 | 5 |  |  |  |  |  |  |  |
| 3.2.6 | PSA on legislative links between the local and global environment |  |  | 3 | 4 |  |  |  |  |  |  |  |
| Output 3.3 | Awareness-raising dialogues and workshops |  |  |  |  |  |  |  |  |  |  |  |
| 3.3.1 | Private sector sensitization panel discussions |  |  | 3 | 2 | 1 | 1 |  | 1 | 1 |  |  |
| 3.3.2 | Journalist awareness workshops |  |  | 3 | 2 |  | 1 |  | 1 | 1 |  |  |
| 3.3.3 | Awareness workshops on MEA legislative mainstreaming |  |  | 3 | 2 |  | 1 |  | 1 | 1 |  |  |
| 3.3.4 | Regional awareness workshops |  |  | 3 | 2 | 1 | 1 |  | 1 | 1 |  |  |
| 3.3.5 | Public policy dialogues |  |  | 3 | 2 | 1 | 1 |  | 1 | 1 |  |  |
| Output 3.4 | Resource mobilization strategy |  |  |  |  |  |  |  |  |  |  |  |
| 3.4.1 | In-depth financial and economic analysis of the environmental M&C |  |  | 4 |  | 9 |  |  |  | 4 |  |  |
| 3.4.2 | Best practice and innovative financial and economic instruments |  |  | 4 |  | 2 |  |  |  | 2 |  |  |
| 3.4.3 | Use MEA technical committees on resource mobilization | National Project Director and Project Manager |  |  |  |  |  |  |  |  |  |  |
| Output 3.5 | Internet visibility of integrated and streamlined environmental legislation |  |  |  |  |  |  |  |  |  |  |  |
| 3.5.1 | Easy-to-use one-stop environmental legislation website |  |  | 1 |  | 4 |  | 6 |  | 1 |  |  |
| 3.5.2 | Facebook page on Rio Convention mainstreaming |  |  |  | 2 | 10 | 2 |  | 2 | 2 |  |  |

| Activity | Description | A | B | C | D | E | F | G | H | I | J | K |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Project Management |  |  |  |  |  |  |  |  |  |  |  |  |
| A | Locally recruited personnel: Project Manager (1)(5) | 48 |  |  |  |  |  |  |  |  |  |  |
| B | Locally recruited personnel: Project Assistant (2)(5) |  | 60 |  |  |  |  |  |  |  |  |  |
| C | International Evaluation Consultant Fee (3) |  |  |  |  |  |  |  |  |  | 12 |  |
| D | Office facilities and communications (4) |  |  |  |  |  |  |  |  |  |  |  |
| E | Travel (Regional Mainstreaming meetings) |  |  |  |  |  |  |  |  |  |  |  |
|  | Total Work Weeks | 48 | 60 | 122 | 42 | 14 | 37 | 26 | 37 | 44 | 12 | 7 |
| Notes |  |  |  |  |  |  |  |  |  |  |  |  |
| (1) The Project Manager and the Environmental Lawyer should be the same individual |  |  |  |  |  |  |  |  |  |  |  |  |
| (2) The Project Assistant will be co-financed by MINAE |  |  |  |  |  |  |  |  |  |  |  |  |
| (3) The International Consultant will conduct an independent terminal evaluation of the project |  |  |  |  |  |  |  |  |  |  |  |  |
| (4) In addition to office space for the project team, this budget will cover the cost of Project Board meetings, 4x per year. |  |  |  |  |  |  |  |  |  |  |  |  |
| (5) A portion of MINAE's co-financing will cover the non-salary HR costs |  |  |  |  |  |  |  |  |  |  |  |  |

## Annex 7:    Environmental and Social Review Criteria

QUESTION 1:

Has a combined environmental and social assessment/review that covers the proposed project already been completed by implementing partners or donor(s)? Select answer below and follow instructions: XNO Continue to Question 2 (do not fill out Table 1.1) - YES No further environmental and social review is required if the existing documentation meets UNDP’s quality assurance standards, and environmental and social management recommendations are integrated into the project. Therefore, you should undertake the following steps to complete the screening process: 1. Use Table 1.1 below to assess existing documentation. (It is recommended that this assessment be undertaken jointly by the Project Developer and other relevant Focal Points in the office or Bureau). 2. Ensure that the Project Document incorporates the recommendations made in the implementing partner’s environmental and social review. 3. Summarize the relevant information contained in the implementing partner’s environmental and social review in Annex A.2 of this Screening Template, selecting Category 1. 4. Submit Annex A to the PAC, along with other relevant documentation.

| TABLE 1.1: CHECKLIST FOR APPRAISING QUALITY ASSURANCE OF EXISTING ENVIRONMENTAL AND SOCIAL ASSESSMENT | Yes/No |
| --- | --- |
| 1. Does the assessment/review meet its terms of reference, both procedurally and substantively? |  |
| 2. Does the assessment/review provide a satisfactory assessment of the proposed project? |  |
| 3. Does the assessment/review contain the information required for decision-making? |  |
| 4. Does the assessment/review describe specific environmental and social management measures (e.g., mitigation, monitoring, advocacy, and capacity development measures)? |  |
| 5. Does the assessment/reviewidentify capacity needs of the institutions responsible for implementing environmental and social management issues? |  |
| 6. Was the assessment/review developed through a consultative process with strong stakeholder engagement, including the view of men and women? |  |
| 7. Does the assessment/review assess the adequacy of the cost of and financing arrangements for environmental and social management issues? |  |
| Table 1.1 (continued) For any “no” answers, describe below how the issue has been or will be resolved (e.g., amendments made or supplemental review conducted). |  |

QUESTION 2:

Do alloutputs and activitiesdescribed in the Project Document fall within the following categories? - Procurement (in which case UNDP’s Procurement Ethics and Environmental Procurement Guideneed to be complied with) - Report preparation - Training - Event/workshop/meeting/conference (refer to Green Meeting Guide) - Communication and dissemination of results Select answer below and follow instructions: XNO Continue to Question 3 - YES No further environmental and social review required. Complete Annex A.2, selecting Category 1, and submit the completed template (Annex A) to the PAC.

QUESTION 3:

Does the proposed project include activities and outputs that support upstream planning processes that potentially pose environmental and social impacts or are vulnerable to environmental and social change (refer to Table 3.1 for examples)?(Note that upstream planning processes can occur at global, regional, national, local and sectoral levels) Select the appropriate answer and follow instructions: - NO Continue to Question 4. XYES Conduct the following steps to complete the screening process: 1. Adjust the project design as needed to incorporate UNDP support to the country (ies), to ensure that environmental and social issues are appropriately considered during the upstream planning process. Refer to Section 7 of this Guidance for elaboration of environmental and social mainstreaming services, tools, guidance and approaches that may be used. See Output 3.4 in the project document 2. Summarize environmental and social mainstreaming support in Annex A.2, Section C of the Screening Template and select ”Category 2”. 3. If the proposed project ONLY includes upstream planning processes then screening is complete, and you should submit the completed Environmental and Social Screening Template (Annex A) to the PAC. If downstream implementation activities are also included in the project then continue to Question 4.

| TABLE 3. 1 EXAMPLES OF UPSTREAM PLANNING PROCESSES WITH POTENTIAL DOWNSTREAM ENVIRONMENTAL AND SOCIAL IMPACTS | Check appropriate box(es) below |
| --- | --- |
| - Support for the elaboration or revision of global-level strategies, policies, plans, and programmes. For example, capacity development and support related to international negotiations and agreements. Other examples might include a global water governance project or a global MDG project. |  |
| - Support for the elaboration or revision of regional-level strategies, policies and plans, and programmes. For example, capacity development and support related to transboundary programmes and planning (river basin management, migration, international waters, energy development and access, climate change adaptation etc.). | X |
| 3. Support for the elaboration or revision of national-level strategies, policies, plans and programmes. For example, capacity development and support related to national development policies, plans, strategies and budgets, MDG-based plans and strategies (e.g., PRS/PRSPs, NAMAs), sector plans. | X |
| 4. Support for the elaboration or revision of sub-national/local-level strategies, polices, plans and programmes. For example, capacity development and support for district and local level development plans and regulatory frameworks, urban plans, land use development plans, sector plans, provincial development plans, provision of services, investment funds, technical guidelines and methods, stakeholder engagement. | X |

QUESTION 4:

Does the proposed project include the implementation of downstream activities that potentially pose environmental and social impacts or are vulnerable to environmental and social change? To answer this question, you should first complete Table 4.1 by selecting appropriate answers. If you answer “No” or “Not Applicable” to all questions in Table 4.1 then the answer to Question 4 is “NO.” If you answer “Yes” to any questions in Table 4.1 (even one “Yes” can indicated a significant issue that needs to be addressed through further review and management) then the answer to Question 4 is “YES”: - NO No further environmental and social review and management required for downstream activities. Complete Annex A.2 by selecting “Category 1”, and submit the Environmental and Social Screening Template to the PAC. X YES Conduct the following steps to complete the screening process: 1. Consult Section 8of this Guidance, to determine the extent of further environmental and social review and management that might be required for the project. 2. Revise the Project Document to incorporate environmental and social management measures. Where further environmental and social review and management activity cannot be undertaken prior to the PAC, a plan for undertaking such review and management activity within an acceptable period of time, post-PAC approval (e.g., as the first phase of the project) should be outlined in Annex A.2. 3. Select “Category 3” in Annex A.2, and submit the completed Environmental and Social Screening Template (Annex A) and relevant documentation to the PAC.

| TABLE 4.1: ADDITIONAL SCREENING QUESTIONS TO DETERMINE THE NEED AND POSSIBLE EXTENT OF FURTHER ENVIRONMENTAL AND SOCIAL REVIEW AND MANAGEMENT |  |
| --- | --- |
| 1. Biodiversity and Natural Resources | Answer (Yes/No/ Not Applicable) |
| 1.1 Would the proposed project result in the conversion or degradation of modified habitat, natural habitat or critical habitat? | No |
| 1.2 Are any development activities proposed within a legally protected area (e.g., natural reserve, national park) for the protection or conservation of biodiversity? | No |
| 1.3 Would the proposed project pose a risk of introducing invasive alien species? | No |
| 1.4 Does the project involve natural forest harvesting or plantation development without an independent forest certification system for sustainable forest management (e.g., PEFC, the Forest Stewardship Council certification systems, or processes established or accepted by the relevant National Environmental Authority)? | No |
| 1.5 Does the project involve the production and harvesting of fish populations or other aquatic species without an accepted system of independent certification to ensure sustainability (e.g., the Marine Stewardship Council certification system, or certifications, standards, or processes established or accepted by the relevant National Environmental Authority)? | No |
| 1.6 Does the project involve significant extraction, diversion or containment of surface or ground water? For example, construction of dams, reservoirs, river basin developments, groundwater extraction. | No |
| 1.7 Does the project pose a risk of degrading soils? | No |
| 2. Pollution | Answer (Yes/No/ Not Applicable) |
| 2.1 Would the proposed project result in the release of pollutants to the environment due to routine or non-routine circumstances with the potential for adverse local, regional, and transboundary impacts? | No |
| 2.2 Would the proposed project result in the generation of waste that cannot be recovered, reused, or disposed of in an environmentally and socially sound manner? | No |
| 2.3 Will the propose project involve the manufacture, trade, release, and/or use of chemicals and hazardous materials subject to international action bans or phase-outs? For example, DDT, PCBs and other chemicals listed in international conventions such as the Stockholm Convention on Persistent Organic Pollutants, or the Montreal Protocol. | No |
| 2.4 Is there a potential for the release, in the environment, of hazardous materials resulting from their production, transportation, handling, storage and use for project activities? | No |
| 2.5 Will the proposed project involve the application of pesticides that have a known negative effect on the environment or human health? | No |
| 3. Climate Change |  |
| 3.1 Will the proposed project result in significantgreenhouse gas emissions? Annex E provides additional guidance for answering this question. | No |
| 3.2 Is the proposed project likely to directly or indirectly increase environmental and social vulnerability to climate change now or in the future (also known as maladaptive practices)? You can refer to the additional guidance in Annex C to help you answer this question. For example, a project that would involve indirectly removing mangroves from coastal zones or encouraging land use plans that would suggest building houses on floodplains could increase the surrounding population’s vulnerability to climate change, specifically flooding. | No |
| 4. Social Equity and Equality | Answer (Yes/No/ Not Applicable) |
| 4.1 Would the proposed project have environmental and social impacts that could affect indigenous people or other vulnerable groups? | No |
| 4.2 Is the project likely to significantly impact gender equality and women’s empowerment? | No |
| 4.3 Is the proposed project likely to directly or indirectly increase social inequalities now or in the future? | No |
| 4.4 Will the proposed project have variable impacts on women and men, different ethnic groups, social classes? | No |
| 4.5 Have there been challenges in engaging women and other certain key groups of stakeholders in the project design process? | No |
| 4.6 Will the project have specific human rights implications for vulnerable groups? | No |
| 5. Demographics | No |
| 5.1 Is the project likely to result in a substantial influx of people into the affected community? | No |
| 5.2 Would the proposed project result in substantial voluntary or involuntary resettlement of populations? For example, projects with environmental and social benefits (e.g., protected areas, climate change adaptation) that impact human settlements, and certain disadvantaged groups within these settlements in particular. | No |
| 5.3 Would the proposed project lead to significant population density increase which could affect the environmental and social sustainability of the project? For example, a project aiming at financing tourism infrastructure in a specific area (e.g., coastal zone, mountain) could lead to significant population density increase which could have serious environmental and social impacts (e.g., destruction of the area’s ecology, noise pollution, waste management problems, greater work burden on women). | No |
| - Culture |  |
| 6.1 Is the project likely to significantly affect the cultural traditions of affected communities, including gender-based roles? | No |
| 6.2 Will the proposed project result in physical interventions (during construction or implementation) that would affect areas that have known physical or cultural significance to indigenous groups and other communities with settled recognized cultural claims? | No |
| 6.3 Would the proposed project produce a physical “splintering” of a community? For example, through the construction of a road, powerline, or dam that divides a community. | No |
| - Health and Safety |  |
| 7.1 Would the proposed project be susceptible to or lead to increased vulnerability to earthquakes, subsidence, landslides, erosion, flooding or extreme climatic conditions? For example, development projects located within a floodplain or landslide prone area. | No |
| 7.2 Will the project result in increased health risks as a result of a change in living and working conditions?In particular, will it have the potential to lead to an increase in HIV/AIDS infection? | No |
| 7.3 Will the proposed project require additional health services including testing? | No |
| - Socio-Economics |  |
| 8.1 Is the proposed project likely to have impacts that could affect women’s and men’s ability to use, develop and protect natural resources and other natural capital assets? For example, activities that could lead to natural resources degradation or depletion in communities who depend on these resources for their development, livelihoods, and well-being? | Yes |
| 8.2 Is the proposed project likely to significantly affect land tenure arrangements and/or traditional cultural ownership patterns? | No |
| 8.3 Is the proposed project likely to negatively affect the income levels or employment opportunities of vulnerable groups? | No |
| 9. Cumulative and/or Secondary Impacts | Answer (Yes/No/ Not Applicable) |
| 9.1 Is the proposed project location subject to currently approved land use plans (e.g., roads, settlements) which could affect the environmental and social sustainability of the project? For example, future plans for urban growth, industrial development, transportation infrastructure, etc. | N/A |
| 9.2 Would the proposed project result in secondary or consequential development which could lead to environmental and social effects, or would it have potential to generate cumulative impacts with other known existing or planned activities in the area? For example, a new road through forested land will generate direct environmental and social impacts through the cutting of forest and earthworks associated with construction and potential relocation of inhabitants. These are direct impacts. In addition, however, the new road would likely also bring new commercial and domestic development (houses, shops, businesses). In turn, these will generate indirect impacts. (Sometimes these are termed “secondary” or “consequential” impacts). Or if there are similar developments planned in the same forested area then cumulative impacts need to be considered. | No |

ANNEX A.2:  ENVIRONMENTAL AND SOCIAL SCREENING SUMMARY

(To be filled in after Annex A.1 has been completed)

Name of Proposed Project:	Capacity building for mainstreaming MEA objectives into inter-ministerial structures and mechanisms

A. Environmental and Social Screening Outcome

Select from the following:

- Category 1. No further action is needed

X

Category 2.  Further review and management is needed.  There are possible environmental and social benefits, impacts,and/or risks associated with the project (or specific project component), but these are predominantly indirect or very long-term and so extremely difficult or impossible to directly identify and assess.

- Category 3. Further review and management is needed, and it is possible to identify these with a reasonable degree of certainty. If Category 3, select one or more of the following sub-categories:

- Category 3a:Impacts and risks are limited in scale and can be identified with a reasonable degree of certainty and can often be handled through application of standard best practice, but require some minimal or targeted further review and assessment to identify and evaluate whether there is a need for a full environmental and social assessment (in which case the project would move to Category 3b).

- Category 3b: Impacts and risks may well be significant, and so full environmental and social assessment is required. In these cases, a scoping exercise will need to be conducted to identify the level and approach of assessment that is most appropriate.

B. Environmental and Social Issues(for projects requiring further environmental and social review and management)

In this section, you should list the key potential environmental and social issues raised by this project. This might include both environmental and social opportunities that could be seized on to strengthen the project, as well as risks that need to be managed.  You should use the answers you provided in Table 4.1 as the basis for this summary, as well as any further review and management that is conducted.

The strategic design of this project rests on reconciling existing environmental and natural resource management legislation with a view more effectively meeting Rio Convention obligations as well as national environmental and resource management priorities.   The baseline of this project is that environmental legislation is not effectively monitored or enforced, leading to ineffective conservation objectives.  However, the leading causes are due to social pressures, and why question 8.1 in Table 4.1 above is answered in the affirmative.  Due to potential social pressures, social development criteria will form an important set of criteria for determining the optimal approaches for enforcing select articles of environmental legislation.  Activity 2.1.3 of the project on the analysis of environmental legislation will pay particular attention to the socio-economic impacts, including impacts differentiated by gender and youth.  The project will also ensure that community issues are fully taken into account by including stakeholder representatives from the regional provinces and communities.

C. Next Steps(for projects requiring further environmental and social review and management):

In this section, you should summarize actions that will be taken to deal with the above-listed issues. If your project has Category 2 or 3 components, then appropriate next steps will likely involve further environmental and social review and management, and the outcomes of this work should also be summarized here. Relevant guidance should be obtained from Section 7 for Category 2, and Section 8 for Category 3.

An inherent aspect of this project is the strengthening of monitoring and compliance of environmental legislation, and this includes monitoring potential socio-economic impacts of non-compliance with environmental legislation.  The entire premise of the project is based on strengthening criteria and indicators for meeting Rio Convention obligations and the project strategy recognizes that improve monitoring, compliance and enforcement to that end will only be sustainable if socio-economic priorities are not compromised.  The project’s approach is that the MEA Technical Committee will include socio-economic criteria as a parallel analytic framework for assessing and recommending improved implementation of environmental legislation.

The UNDP PAC will be held after CEO endorsement.

D. Sign Off

Project Manager								Date:

PAC										Date:

Programme Manager								Date:  12/12/2013

## Annex 8:Costa Rica’s participation in the Low Emission Capacity Building Project

Costa Rica joined the Low-Emission Capacity Building Project to support its activities on the National Climate Change Strategy by improving their national Greenhouse Gas inventory, formulating Nationally Appropriate Mitigation Actions (NAMAs) and developing Measurement, Reporting and Verification (MRV) systemsin selected sectors.  This projectis being implemented under the leadership of the Ministry of Environment and Energy (MINAE) and its Department of Climate Change (DCC).  The DCC’s functions include coordinating the Technical Secretariat of the Inter-Ministerial Council on Climate Change, a forum that has broad representation in the executive branch.  The integration of project activities with other public policies is ensured through this Council, which will be kept informed during scheduled sessions and committee work.

Planned Outputs of the Project

The main goal of the project is to support the Costa Rica’s transformation to low-carbon use in two specific sectors, such as livestock and transport, in line with the national objective of becoming carbon neutral by 2021.  Specific results expected are:

Result 1:	Development, in association with the IMN, of the GHG National Inventory in the transport and livestock sectors

Transport:

Activity 1: Workshop to validate the objectives, scope and other aspects of the national transport survey.

Activity 2: Conduction of National transport survey.

Activity 3: Workshop on survey results and impact on systematization of transport sector inventories.

Activity 4: Incorporation of the results in the broad stakeholder process.

Activity 5: Integration of inputs that strengthen the transport inventory in the GHG National Inventory.

Livestock:

Activity 1: Capacity development for the systematization of emissions calculation of the livestock sector.

Activity 2: Develop capacities for a periodical characterization of the livestock activity.

Activity 3: Training in techniques to determine emission factors in the livestock sector.

Activity 4: Result validation workshop on the national emission factors in livestock.

Activity 5: Incorporation of national emission factors into GHG National Inventory.

Result 2:	Formulation of nationally appropriate mitigation actions (including NAMAs) in the livestock and transport sector

Transport and Livestock:

Activity 1: Establish criteria to select sound mitigation actions.

Activity 2: Build a GHG reference scenario.

Activity 3: Build mitigation scenarios with measures proposed.

Activity 4: Development of marginal abatement cost curves.

Activity 5: Integration of social and development co-benefit analysis.

Activity 6: Identification of barriers and proposal of solutions for the selected measures.

Activity 7: Consultation workshops with interested stakeholders.

Activity 8: Financing structure proposal for the prioritized measures.

Activity 9: Policy instruments proposal to encourage investment of the prioritized measures.

Activity 10: Workshops, consultations and validation with all stakeholders after each process stage.

Activity 11: Formulation of NAMA proposals for livestock and transport sector.

Livestock:

Activity 1: Pilot Implementation of the NAMA proposal for the livestock sector.

Activity 2: Demonstrative field activities on emission reductions, in association with private sector.

Activity 3: Results compilation of the pilot NAMAs.

Activity 4: Progress workshops, lessons learned, identification of barriers and recovery measures.

Result 3:	Development of MRV systems for prioritized sectors

Activity 1: Assessment of monitoring requirements of the proposed NAMA measures.

Activity 2: Integration of monitoring parameters to account for NAMA co-benefits.

Activity 3: Design of the base concept for the MRV system for the transport sector.

Activity 4: Development of MRV system for the livestock sector

## Annex 9:   Total GEF Input Budget and Work Plan

| Award ID: |  |  | 00076472 |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Award Title: |  |  | Capacity building for mainstreaming MEA objectives into inter-ministerial structures and mechanisms |  |  |  |  |  |  |
| Business Unit: |  |  | GEF |  |  |  |  |  |  |
| Project Title: |  |  | Capacity building for mainstreaming MEA objectives into inter-ministerial structures and mechanisms |  |  |  |  |  |  |
| PIMS No: |  |  | 5097 |  |  |  |  |  |  |
| Implementing Partner (Executing Agency): |  |  | Ministry of the Environment and Energy (MINAE) |  |  |  |  |  |  |
| GEF Outcome/Atlas Activity | Responsible Party/ Implementing Agent | Fund ID | Donor Name | Atlas Budgetary Account Code | ATLAS Budget Description | Amount Year 1 (US$) | Amount Year 2 (US$) | Amount Year 3 (US$) | Total (US$) |
| COMPONENT 1: Integrated inter-ministerial decision-making | MINAE | 62000 | GEF | 71300 | Environmental Lawyer | 26,250 | 5,000 | 16,250 | 47,500 |
|  |  |  |  | 71300 | Information Technology Expert | 12,500 | 0 | 7,500 | 20,000 |
|  |  |  |  | 71300 | International Technical Specialist | 1,250 | 0 | 1,250 | 2,500 |
|  |  |  |  | 71200 | MEA Technical Committee meetings (1.1.2) | 5,000 | 5,000 | 5,000 | 15,000 |
|  |  |  |  | 71200 | Working group consultations and meetings to re-invigorate Inter-Ministerial Council (1.3.2) | 5,000 | 5,000 | 5,000 | 15,000 |
|  |  |  |  |  | Sub-total GEF | 50,000 | 15,000 | 35,000 | 100,000 |
|  |  |  |  |  | Total Outcome 1 | 50,000 | 15,000 | 35,000 | 100,000 |

| GEF Outcome/Atlas Activity | Responsible Party/ Implementing Agent | Fund ID | Donor Name | Atlas Budgetary Account Code | ATLAS Budget Description | Amount Year 1 (US$) | Amount Year 2 (US$) | Amount Year 3 (US$) | Total (US$) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| COMPONENT 2: Integrating Rio Conventions into environmental legislation | MINAE | 62000 | GEF | 71300 | Natural Resource Management Expert | 12,500 | 12,500 | 11,250 | 36,250 |
|  |  |  |  | 71300 | Environmental Education Specialist | 5,000 | 5,000 | 5,000 | 15,000 |
|  |  |  |  | 71300 | Environmental Lawyer | 21,250 | 21,250 | 21,250 | 63,750 |
|  |  |  |  | 71300 | Land Management Expert | 12,500 | 12,500 | 11,250 | 36,250 |
|  |  |  |  | 71300 | Energy Specialist | 12,500 | 12,500 | 11,250 | 36,250 |
|  |  |  |  | 71300 | Information Technology Expert | 0 | 2,500 | 2,500 | 5,000 |
|  |  |  |  | 71300 | International Technical Specialist | 3,750 | 5,000 | 3,750 | 12,500 |
|  |  |  |  | 71200 | Independent peer review fees of project analyses (2.1.1) | 5,000 | 5,000 | 5,000 | 15,000 |
|  |  |  |  | 71200 | Meeting services for stakeholder constituent dialogues (2.1.4) | 10,000 | 10,000 | 10,000 | 30,000 |
|  |  |  |  | 71200 | Technical working groups (2.2.1) | 5,000 | 5,000 | 5,000 | 15,000 |
|  |  |  |  | 71200 | Working group meetings and consultations to implement selected Inter-Ministerial Council decisions (2.2.2) | 0 | 25,000 | 20,000 | 45,000 |
|  |  |  |  | 71200 | Working group meetings and consultations to negotiate select monitoring and compliance reforms (2.3.2) | 5,000 | 20,000 | 15,000 | 40,000 |
|  |  |  |  | 71200 | Training workshops on monitoring and compliance (2.3.5) | 0 | 10,000 | 10,000 | 20,000 |
|  |  |  |  |  | Sub-total GEF | 92,500 | 146,250 | 131,250 | 370,000 |
|  |  |  |  |  | Total Outcome 2 | 92,500 | 146,250 | 131,250 | 370,000 |

| GEF Outcome/Atlas Activity | Responsible Party/ Implementing Agent | Fund ID | Donor Name | Atlas Budgetary Account Code | ATLAS Budget Description | Amount Year 1 (US$) | Amount Year 2 (US$) | Amount Year 3 (US$) | Total (US$) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| COMPONENT 3: Strengthened technical and management capacities | MINAE | 62000 | GEF | 71300 | Natural Resource Management Expert | 6,250 | 6,250 | 6,250 | 18,750 |
|  |  |  |  | 71300 | Environmental Education Specialist | 12,500 | 17,500 | 17,500 | 47,500 |
|  |  |  |  | 71300 | Environmental Lawyer | 13,750 | 13,750 | 13,750 | 41,250 |
|  |  |  |  | 71300 | Land Management Expert | 2,500 | 3,750 | 3,750 | 10,000 |
|  |  |  |  | 71300 | Energy Specialist | 2,500 | 3,750 | 3,750 | 10,000 |
|  |  |  |  | 71300 | Environmental Economist | 5,000 | 6,250 | 6,250 | 17,500 |
|  |  |  |  | 71300 | Information Technology Expert | 3,750 | 2,500 | 1,250 | 7,500 |
|  |  |  |  | 71300 | International Technical Specialist | 1,250 | 0 | 1,250 | 2,500 |
|  |  |  |  | 71200 | Conference services for Kick-Off and Project Results Conferences (3.1.1 & 3.1.2) | 10,000 | 0 | 10,000 | 20,000 |
|  |  |  |  | 71200 | Sub-contract NGO to carry out broad-based awareness survey (3.2.1) | 5,000 | 0 | 0 | 5,000 |
|  |  |  |  | 71200 | Video production company to produce and air PSA on TV and radio (3.2.6) | 25,000 | 10,000 | 5,000 | 40,000 |
|  |  |  |  | 71200 | Meeting services for private sector sensitization panel discussions (3.3.1) | 10,000 | 10,000 | 10,000 | 30,000 |
|  |  |  |  | 71200 | Journalist awareness workshops (3.3.2) | 10,000 | 10,000 | 10,000 | 30,000 |
|  |  |  |  | 71200 | MEA legislative mainstreaming awareness workshops (3.3.3) | 10,000 | 10,000 | 10,000 | 30,000 |
|  |  |  |  | 71200 | Regional awareness workshops (3.3..4) | 20,000 | 15,000 | 15,000 | 50,000 |
|  |  |  |  | 71200 | Conference services for four public policy dialogues (3.3.5) | 0 | 0 | 30,000 | 30,000 |
|  |  |  |  | 71200 | Meeting venues negotiate resource mobilization (3.4.3) | 5,000 | 5,000 | 10,000 | 20,000 |
|  |  |  |  | 71200 | Website development and promotion fees (3.5.1) | 10,000 | 10,000 | 10,000 | 30,000 |
|  |  |  |  |  | Sub-total GEF | 152,500 | 123,750 | 163,750 | 440,000 |
|  |  |  |  |  | Total Outcome 3 | 152,500 | 123,750 | 163,750 | 440,000 |
| GEF Outcome/Atlas Activity | Responsible Party/ Implementing Agent | Fund ID | Donor Name | Atlas Budgetary Account Code | ATLAS Budget Description | Amount Year 1 (US$) | Amount Year 2 (US$) | Amount Year 3 (US$) | Total (US$) |
| Project Management | MINAE | 62000 | GEF | 71200 | International Expert Final Evaluation (Fee only) | 0 | 0 | 10,000 | 10,000 |
|  |  |  |  |  | Travel for International Expert Final Evaluation | 0 | 0 | 4,500 | 4,500 |
|  |  |  |  |  | Locally recruited personnel: Project Manager (1) | 10,000 | 10,000 | 10,000 | 30,000 |
|  |  |  |  |  | Locally recruited personnel: Project Assistant | 5,000 | 5,000 | 5,000 | 15,000 |
|  |  |  |  | 74599 | UNDP cost recovery charges - Bills (3) | 2,750 | 2,750 | 5,000 | 10,500 |
|  |  |  |  |  | Sub-total GEF | 17,750 | 17,750 | 34,500 | 70,000 |
|  |  |  |  |  | Total Outcome 4 | 17,750 | 17,750 | 34,500 | 70,000 |
| Total Project |  |  |  |  | Total Project | 312,750 | 32,7500 | 364,500 | 980,000 |
|  |  |  |  |  | Percentage allocated per year | 31.9 | 30.9 | 37.2 | 100 |
|  |  |  |  |  | GEF Agency fee (9.5%) |  |  |  | 98,000 |
| (1) The Environmental Lawyer and Project Manager are the same individual |  |  |  |  |  |  |  |  |  |
| (2) In addition to office space for the project team, this budget will cover the cost of Project Board meetings, 4x per year. |  |  |  |  |  |  |  |  |  |
| (3) Due to recent guidance to include UNDP Cost recovery from the project management fee, this amount is withdrawn from that allocated to the Project Manager fee |  |  |  |  |  |  |  |  |  |

## Annex 10:   PDF/PPG Status Report

status of implementation of project preparation activities and the use of funds

- provide detailed funding amount of the ppg activities financing status in the table below:

The activities undertaken within the framework of PPG were directed towards the design and development of the medium size project “Capacity building for mainstreaming MEA objectives into inter-ministerial structures and mechanisms.”

The Project Preparation Stage envisioned the preliminary analysis Costa Rica’s policy and legal framework, as well as the associated institutional framework surrounding environmental management.  This analysis served as the basis for stakeholder consultations to determine the barriers to be addressed by the project, including appropriate performance indicators of environmental governance.  These and other outputs called for by the PPG were performed by a locally recruit expert on environmental law, and supported by the UNDP Country Office and two international consultants.

As important as the data and information was needed to prepare the project document, so too was the process of stakeholder consultations.  For this reason, a well-respected and expert national consultant was recruited to carry out these consultations.  This process led to the national consultant’s validation of the project strategy, which was then presented at a stakeholder validation workshop.  This workshop fine-tuned the project strategy as well as agreed on the preferred implementation arrangements.

A.1:  describe findings that might affect the project design or any concerns on project implementation, if any:

The findings obtained during the preparatory phase confirmed that the approach identified during the PIF stage remains valid.  However, during stakeholder consultations as part of the initiation mission, the project strategy was further refined to take into account the general consensus that integrating inter-ministerial decision-making for the global environment should be pursued through existing environmental legislation, complemented by strengthened institutional structures and mechanisms.  This approach serves to further strengthen the innovativeness and transformative nature of the project.

UNDP’s contributed in excess of US$ 20,000 to support the preparation of this project.  This included, among others, logistical arrangements for meetings, time spent by two UNDP staff to undertake stakeholder consultations and coordinatewith other workshops, communication costs and materials.

| PPG Grant approved at PIF: |  |  |  |
| --- | --- | --- | --- |
| Project Preparation Activities Implemented | GEF Amount ($) |  |  |
|  | Budgeted Amount ($) | Amount Spent to date($) | Amount Committed ($) |
| Preliminary assessments of the policy, legal and institutional framework for environmental management and governance, including preliminary assessment of training needs and awareness | 9,500 | 9,500 | 0 |
| Preparation of MSP document per UNDP/GEF guidelines; Facilitation of Validation workshop | 10,500 | 10,500 | 0 |
| Stakeholder consultations and Validation workshop, plus communications, printing (all activities). (UNDP co-financed) | 0 | 0 | 0 |
| Total | 20,000 | 20,000 | 0 |

## Annex 11:   Letter of Agreement for Recovery of Direct Project Costs

United Nations Development Programme

STANDARD LETTER OF AGREEMENT BETWEEN UNDP AND THE GOVERNMENT OF COSTA RICA FOR THE PROVISION OF SUPPORT SERVICES

Under project “Capacity building for mainstreaming MEA objectives into inter-ministerial structures and mechanisms”

Ms.  María Guzmán

Vice Minister- Ministry of Environment and Energy (MINAE)

Excellency,

1.	Reference is made to consultations between officials of the Government ofCosta Rica(hereinafter referred to as “the Government”) and officials of UNDP with respect to the provision of support services by the UNDP country office for nationally managed programmes and projects.  UNDP and the Government hereby agree that the UNDP country office may provide such support services at the request of the Government through its institution designated in the relevant programme support document or project document, as described below.

2.	The UNDP country office may provide support services for assistance with reporting requirements and direct payment.  In providing such support services, the UNDP country office shall ensure that the capacity of the Government-designated institution is strengthened to enable it to carry out such activities directly.  The costs incurred by the UNDP country office in providing such support services shall be recovered from the administrative budget of the office.

3.	The UNDP country office may provide, at the request of the designated institution, the following support services for the activities of the programme/project:

(a)	Identification and/orrecruitment of project and programme personnel;

(b)	Identification and facilitation of training activities;

(c) 	Procurement of goods and services;

4.	The procurement of goods and services and the recruitment of project and programme personnel by the UNDP country office shall be in accordance with the UNDP regulations, rules, policies and procedures.  Support services described in paragraph 3 above shall be detailed in an annex to the programme support document or project document, in the form provided in the Attachment hereto.  If the requirements for support services by the country office change during the life of a programme or project, the annex to the programme support document or project document is revised with the mutual agreement of the UNDP resident representative and the designated institution.

5.	The relevant provisions of the Standard Basic Assistance Agreement (SBAA) between the Authorities of the Government of Costa Ricaand the United Nations Development Programme (UNDP), signed by the Parties (the "SBAA") including the provisions on liability and privileges and immunities, shall apply to the provision of such support services.  The Government shall retain overall responsibility for the nationally managed programme or project through its designated institution.  The responsibility of the UNDP country office for the provision of the support services described herein shall be limited to the provision of such support services detailed in the annex to the programme support document or project document.

6.	Any claim or dispute arising under or in connection with the provision of support services by the UNDP country office in accordance with this letter shall be handled pursuant to the relevant provisions of the SBAA.

7.	The manner and method of cost-recovery by the UNDP country office in providing the support services described in paragraph 3 above shall be specified in the annex to the programme support document or project document.

8.	The UNDP country office shall submit progress reports on the support services provided and shall report on the costs reimbursed in providing such services, as may be required.

9.	Any modification of the present arrangements shall be effected by mutual written agreement of the parties hereto.

10.	If you are in agreement with the provisions set forth above, please sign and return to this office two signed copies of this letter.  Upon your signature, this letter shall constitute an agreement between your Government and UNDP on the terms and conditions for the provision of support services by the UNDP country office for nationally managed programmes and projects.

Yours sincerely,

________________________

Signed on behalf of UNDP

Yoriko Yasukawa

Resident Representative

_____________________

For the Government

María Guzmán

Vice-Ministry of the Environment and Energy (MINAE)

[Date]

Attachment:  Description of UNDP Country Office Support Services

1.	Reference is made to consultations between the Ministry of Environment and Energy (MINAE), the institution designated by the Government of Costa Rica and representatives of UNDP with respect to the provision of support services by the UNDP country office for the nationally managed programme or project

Capacity building for mainstreaming MEA objectives into inter-ministerial structures and mechanisms (Award 00076472).

2.	In accordance with the provisions of the letter of agreement signed and the programme support document (projectdocument), the UNDP country office shall provide support services for the Programme as described below.

3.	Support services to be provided:

| Support services (insert description) | Schedule for the provision of the support services | Cost to UNDP of providing such support services (per UPL) | Amount and method of reimbursement of UNDP (where appropriate) |
| --- | --- | --- | --- |
| 1. Identification and/or recruitment of project personnel * Project Manager * Project Assistant | Jan 2014 – Dec 2016 | US$ 260.53 | UNDP will directly charge the project upon receipt of request of services from the Implementing Partner (IP) |
| 2. Procurement of goods: * Data show, computers, printers | Nov. 2009 – April 2010 | US$ 232.74 (per purchasing process) | As above |
| 3. Procurement of Services Contractual services for companies | On-going as appropriate | US$ 232.74 (per hiring process) | As above |
| 4. Payment Process | On-going as appropriate | US$ 36.39 (per transaction) | As above |
| 5. Staff HR & Benefits Administration & Management | On-going as appropriate | US$ 215.73 | As above |
| 6. Recurrent personnel management services: Staff Payroll & Banking Administration & Management | On-going as appropriate | US$ 474.48 | As above |
| 7. Ticket request (booking, purchase) | On-going as appropriate | US$ 34.36 for each | As above |
| 8. F10 settlement | On-going as appropriate | US$ 32.45 (per transaction) | As above |

4.  Description of functions and responsibilities of the parties involved:

UNDP will conduct the full process while the role of the Implementing Partner (IP) will be as follows:

- The Implementing Partner will send a timetable for services requested annually/ updated quarterly

- The Implementing Partner will send the request to UNDP for the services enclosing the specifications or Terms of Reference required

- For the hiring staff process: the IP representatives will be on the interview panel,

- For Hiring CV: the IP representatives will be on the interview panel, or participate in CV review in case an interview is not scheduled

# PART III:	GEF Letters of Endorsement and Co-Financing

Annex A    GEF Endorsement Letter

Annex B    Letters of Co-Financing

…. Letters are attached in a separate attachment.

See Annex 1.

Further details of the project’s indicators are provided in the project document narrative and the logical framework.  For further information please see http://www.thegef.org/gef/Policies_and_Guidelines

Subsequent amendments were ratified in 1998, 2005, and 2008

The following are participating countries:Costa Rica, El Salvador, Guatemala, Honduras, Nicaragua, Panama and Belize.  For further information see http://www.inbio.ac.cr/estrategia/coabio/ALIDES.html#Objetivos_especificos

Happy Planet Index, http://www.happyplanetindex.org/

MIDEPLAN (2010) Plan Nacional de Desarrollo “María Teresa Obregón Zamora”.  Ministerio de Planificación Nacional y Política Económica, Gobierno de Costa Rica.

J.  Brown & N.  Bird (2011) Costa Rica’s sustainable resource management: Successfully tackling tropical deforestation.  Overseas Development Institute (ODI).  London, UK.

For example, the noise of zip lining that is allowed in certain protected area zones frighten the endemic monkeys that live in these areas, adversely affecting their roaming and foraging habitat, and thus diminishing their survival.

These policy recommendations are based on the legislative analyses, whereas the policy recommendations of activity 1.1.2 will be based on information, consultations and agreements made up to month 9.

For example, a youth activist working to protect the endangered leatherback turtle in Costa Rica’s Caribbean coast from poachers was murdered in mid-2013 a few days after posting a call on Facebook for more enforcement.

See paragraph 99.

See paragraph 99.

See activities 2.2.2 and 2.3.2.

The Project Management Unit (PMU) will be an administrative extension of MINAE.

Meeting minutes includes records of key meetings such as local, regional and national consultations regarding inputs on the design and implementation of the relevant output and associated activities.  Meetings may be individual or group meetings, with government officials or non-state stakeholders.

Tracking and progress reports include UNDP Quarterly Reports, Annual Performance Reports (APRs), and Project Implementation Reports (PIRs).  Each output will be tracked by a report that records the activities and milestones of each output using tools such as Gantt or PERT charts.

Significant corresponds to CO2 emissions greater than 100,000 tons per year (from both direct and indirect sources). Annex E provides additional guidance on calculating potential amounts of CO2 emissions.

Women are often more vulnerable than men to environmental degradation and resource scarcity. They typically have weaker and insecure rights to the resources they manage (especially land), and spend longer hours on collection of water, firewood, etc. (OECD, 2006).  Women are also more often excluded from other social, economic, and political development processes.