Project Identification Form (PIF)

Project Type:

Type of Trust Fund:

PART I: Project Identification

| Project Title: | GEF SGP Fifth Operational Phase--implementing the program using STAR resources I |  |  |
| --- | --- | --- | --- |
| Country(ies): | 16 Countries | GEF Project ID: | 4541 |
| GEF Agency(ies): |  | GEF Agency Project ID: | PIMS # 4561 |
| Other Executing Partner(s): | UNOPS | Submission Date: | 2011-09-20 |
| GEF Focal Area (s): |  | Project Duration (Months) | 48 months |
| Name of parent program (if applicable): - For SFM/REDD+ | GEF Small Grants Programme | Agency Fee ($): | 1,436,981 |

A.  Focal AREA STRATEGY Framework:

| ### Focal Area Objectives | ### Expected FA Outcomes | ### Expected FA Outputs | ### Trust Fund | ### Indicative ### Grant Amount ### ($) | ### Indicative Co-financing ### ($) |
| --- | --- | --- | --- | --- | --- |
|  | 1.1 | 1.1; 1.2 |  | 5,142,012 | 5,142,012 |
|  | 2.1 | 2.3 |  | 5,142,012 | 5,142,012 |
|  | 1.1 | 1.1 |  | 2,536,990 | 2,536,990 |
|  | 4.2 | 4.2; 4.3 |  | 2,536,990 | 2,536,990 |
|  | 5.1 | 5.2 |  | 2,536,989 | 2,536,989 |
|  | 1.3 | 1.2; 1.3; 1.5 |  | 2,406,447 | 2,406,447 |
|  | 3.2 | 3.2; 3.4 |  | 2,406,448 | 2,406,448 |
|  | 1.1 | 1.3 |  | 1,621,992 | 1,621,992 |
|  | 2.1 | 2.3 |  | 1,621,992 | 1,621,992 |
|  | 1.1 | 1.1.1 |  | 3,243,984 | 3,243,984 |
|  | 1.1 | 1.6 |  | 1,621,992 | 1,621,992 |
|  | 5.1 | 5.4; 5.5 |  | 1,621,992 | 1,621,992 |
| Others |  |  |  |  |  |
| Sub-Total |  |  |  | 32,439,840 | 32,439,840 |
| Project Management Cost |  |  |  | 3,484,679 | 3,484,679 |
| Total Project Cost |  |  |  | 35,924,519 | 35,924,519 |

- Project Framework

| ### Project Objective: Global Environmental Benefits secured through community-based initiatives and actions |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| ### Project Component | ### Grant Type | ### Expected Outcomes | ### Expected Outputs | ### Trust Fund |  | ### Indicative ### Grant Amount ($) | ### Indicative Cofinancing ### ($) |
| Conservation of Globally Significant Biodiversity Through Community-based Initiatives and Actions |  | 1. Improved sustainability of protected areas and indigenous and community conservation areas through community-based actions 2. Mainstreamed biodiversity conservation and sustainable use in production landscapes, seascapes and sectors through community initiatives and actions | At least 103 community and civil-society based projects funded supporting biodiversity conservation in indigenous and community conservation areas At least 103 community and civil-society based projects funded supporting biodiversity conservation through mainstreaming |  |  | 10,284,024 | 10,284,024 |
| Reduction or Avoidance of GHG Emissions While Building Climate Resilience at the Community-level |  | 3. Demonstration, development and transfer of low-GHG technologies at the community level 4. Increased energy efficient, low-GHG transport at the community level 5. Conservation and enhancement of carbon stocks through sustainable management and climate proofing of land use, land use change and forestry | At least 51 community and civil-society based projects funded supporting the transfer of low-carbon technologies At least 51 community and civil-society based projects funded supporting low-GHG transport At least 50 community and civil-society based projects funded supporting conservation and enhancement of carbon stocks |  |  | 7,610,969 | 7,610,969 |
| Reverse and Prevent Desertification/Land Degradation and Mitigate the Effects of Drought in Affected Areas Through Community-based Initiatives and Actions |  | 6. Maintenance or improvement in flow of agro-ecosystem and forest ecosystem services to sustain livelihoods of local communities 7. Reduction of pressures at community level from competing land uses (in the wider landscapes) | At least 48 community and civil-society based projects funded supporting maintenance or improvement of flow of ecosystem services At least 48 community and civil-society based projects funded supporting reduction of pressures from competing land uses |  |  | 4,812,895 | 4,812,895 |
| Sustainable Management of Transboundary Water Bodies at the Community-level |  | 8. Communities support the implementation of Strategic Action Programmes (SAPs) in trans-boundary surface and groundwater basins; 9.Communities support the implementation of Strategic Action Programmes (SAPs) in large marine ecosystems management | At least 32 community and civil-society based projects funded supporting community initiatives for sustainable management of transboundary surface and groundwater basins; At least 32 community and civil-society based projects funded supporting community initiatives for sustainable management of large marine ecosystems management |  |  | 3,243,984 | 3,243,984 |
| Reduce and Eliminate the Release of Harmful Chemicals into the Environment Through Community-based Initiatives and Actions |  | 10. Phase out of POPs and chemicals of global concern at community level | At least 64 community and civil-society based projects funded supporting the phase out of POPs and chemicals of global concern |  |  | 3,243,984 | 3,243,984 |
| Enhance and Strengthen Capacity of Communities and Civil Society to Address Global Environmental Challenges, primarily focusing on biodiversity, climate change and land degradation focal areas, while also covering international waters and POPs |  | 11. Enhance and strengthen capacities of community-based and civil society organizations (CSOs) to engage in consultative processes, apply knowledge management to ensure adequate information flows, and implement convention guidelines 12. Enhance capacities of CBOs and CSOs to monitor and evaluate environmental impacts and trends | SGP National Steering Committees and National Focal Groups (both groups on voluntary services to SGP) actively engaged with GEF national consultative processes Learning and knowledge management platform established to share lessons learned among CBOs and CSOs across all SGP countries At least 649 CBOs and CSOs as SGP partners with strengthened capacities |  |  | 3,243,984 | 3,243,984 |
| Sub-Total |  |  |  |  |  | 32,439,840 | 32,439,840 |
| Project Management Cost |  |  |  |  |  | 3,484,679 | 3,484,679 |
| Total Project Costs |  |  |  |  |  | 35,924,519 | 35,924,519 |

- Indicative Co-financing for the project by source and by name if available, ($)

| Sources of Cofinancing | Name of Cofinancier | Type of Cofinancing | Amount ($) |
| --- | --- | --- | --- |
|  | Multiple |  | 5,500,000 |
|  | Multiple |  | 600,000 |
|  | Multiple |  | 2,400,000 |
|  | Multiple |  | 3,000,000 |
|  | Multiple |  | 6,000,000 |
|  | Multiple |  | 14,924,519 |
|  | Multiple |  | 2,000,000 |
|  | Multiple |  | 1,500,000 |
|  | Multiple |  |  |
| Total Cofinancing |  |  | 35,924,519 |

- GEF/LDCF/SCCF  Resources Requested by Agency, Focal Area and Country1

| GEF Agency | Type of Trust Fund | Focal Area | Country Name/Global | Grant Amount (a) | Agency Fee (b)2 | Total c=a+b |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Global (STAR 1st Tranche) | 35,924,519 | 1,436,981 | 37,361,500 |
|  |  |  |  |  |  | 0 |
|  |  |  |  |  |  | 0 |
|  |  |  |  |  |  | 0 |
|  |  |  |  |  |  | 0 |
|  |  |  |  |  |  | 0 |
|  |  |  |  |  |  | 0 |
|  |  |  |  |  |  | 0 |
|  |  |  |  |  |  | 0 |
|  |  |  |  |  |  | 0 |
| Total Grant Resources |  |  |  | 35,924,519 | 1,436,981 | 37,361,500 |

1  In case of a single focal area, single country, single GEF Agency project, and single trust fund project, no need to provide 
    information for this table

2   Please indicate fees related to this project.

part ii:  project JustiFication

- Description of the consistency of the project with:

A.1.1   the GEF focal area strategies:

The objectives and expected outcomes of the GEF SGP for the 5th Operational Phase (OP5) directly support the GEF’s strategic priorities for GEF-5. In the area of biodiversity conservation, SGP will support the first two GEF biodiversity objectives: 1) Improving the sustainability of protected area systems, and 2) Mainstreaming biodiversity conservation and sustainable use into production landscapes, seascapes, and sectors. To date, in the countries covered by this PIF, SGP has provided 1,512 community-based biodiversity conservation projects with $32.2 million, generating an additional $60.6 million in cash and in-kind co-financing. SGP grants in OP5 will generate global benefits by leveraging community-based efforts to conserve biodiversity through improving the effectiveness and sustainability of community conservation areas and indigenous protected areas, which make up a critical component of the global protected areas system, even if they are not always recognized as such. To support sustainable use of biodiversity, the SGP will promote the mainstreaming of biodiversity friendly practices in production landscapes and seascapes, through measures such as organic certification for community level and small-scale producers of biodiversity-based products; improved community-based resource use of non-timber forest products; and community level enforcement measures in near shore fisheries. With SGP’s support, civil society and community-based organizations will develop the capacity to improve conservation and sustainable use efforts and ensure benefits for community livelihoods, contributing to long-term sustainability. SGP objectives will be consistent with and support the first, fourth and fifth climate change strategic objectives for GEF-5, which are the most relevant, in the context of SGP’s civil society and community-based focus, of the six GEF climate change objectives. To date, SGP has provided 676 community-based climate change projects with $14.3 million, generating an additional $16.5 million in cash and in-kind co-financing in the countries covered by this PIF. In line with the first GEF strategic objective, for OP5 SGP will provide grants to promote the demonstration, development and transfer of innovative low-carbon solutions at the community level, such as micro-solar power and fuel-efficient stoves. In line with the fourth GEF strategic objective for climate change, SGP will promote energy efficient, low carbon transport at the community level, for example with support for low-emission and energy efficient motor scooters and small boat motors, which make up the majority of individual motorized transport in rural areas. Also in the climate change focal area, SGP will support the conservation and enhancement of carbon stocks through sustainable management and climate proofing of land use, land use change and forestry, which is consistent with the fifth GEF strategic objective. To address land degradation, SGP will support two objectives, both of which are consistent with the GEF land degradation strategic priorities for GEF-5. To date, SGP has provided 310 community-based land degradation projects with $5.4 million, generating an additional $6.2 million in cash and in-kind co-financing. The first SGP objective for OP5 is directly linked to the first strategic objective of the broader GEF for the land degradation results framework: SGP will seek to maintain or improve the flow of agro-ecosystem and forest ecosystem services to sustain community livelihoods. Second, SGP will work with community partners to reduce pressures on natural resources from competing land uses at the community level. In international waters, the SGP will support transboundary water body management with community-based initiatives, including community-level linkages for implementation of SAPs, in partnership with other GEF initiatives. This SGP objective is consistent with the first, second and third GEF strategic objectives for the international waters focal area. To date, SGP has provided 243 community-based international waters projects with $3.6 million, generating an additional $5.8 million in cash and in-kind co-financing. SGP will also promote and support the phase out at the community level of POPs and chemicals of global concern, for example through the introduction of POP substitutes and promotion of environmentally friendly practices in pesticide management. This is consistent with the first strategic objective of the chemicals focal area for GEF-5. To date, SGP has provided 47 community-based POPs projects with $0.76 million, generating an additional $1.81 million in cash and in-kind co-financing in the countries covered by this PIF. Capacity development is a cross-cutting issue that SGP will continue to address. This is also in line with GEF focal area strategies in GEF-5 that include capacity development aspect in every focal area strategy. For the purpose of this specific PIF, 10% of project fund will be used to promote capacity development. Given the sources of the STAR fund, the capacity development activities will primarily focus on biodiversity, climate change and land degradation, while also covering international waters and POPs focal areas. An integrated multi-focal area approach to capacity development will be undertaken to strengthen the capacity of CSOs and CBOs in project development, implementation, monitoring and evaluation in alignment with GEF policies and requirements that will result in global environmental benefits. SGP will continue developing capacity of civil society organizations (CSOs), with priority for community-based organisations (CBOs) and indigenous peoples organisations in the areas such as engagement through consultative process; generation, access and use of information and knowledge; supporting participatory processes in policy and legislation development; and monitoring and evaluation of environmental impacts and trends. This is consistent with the GEF’s long-standing programmatic support for capacity development, as outlined in the GEF-5 programming document. When possible and relevant, the SGP supports integrated and synergistic multi-focal area approaches. While the SGP is consistent with GEF strategies for each focal area, the SGP is a strategic programme of the GEF that addresses environmental issues in an integrated manner through all focal areas. Because the grants to be provided by the SGP in the 5th Operational Phase have yet to be selected, in each country SGP can support a strategic approach by ensuring funding only for community-level grants that are in line with global GEF priorities. This project identification form covers the STAR fund contribution made by Country Programmes with no core grant allocation, while the non-grant component (staffing cost and country operating budgets) will be drawn from both global core funds and STAR management budgets. In each SGP Country Programme, funding may be drawn from the national STAR allocations. GEF Council Document GEF/C.36/4 specified various funding criteria for different categories of Country Programmes. Specifically, "Countries which have an indicative overall STAR country allocation of more than $15 million will no longer be able to access the SGP’s core funding and will need to finance their projects from their STAR allocations. A maximum cumulative amount of up to $3.6 million, with an average up to $900,000 per year can be allocated." (GEF/C.36/4). Sixteen SGP countries with more than $15 million STAR, have no access to the global core fund for grants, and it is critical for these countries to obtain sufficient STAR funds to sustain the Country Programmes' grant-making activities. This PIF is intended to obtain STAR funds to cover the grant allocation of these sixteen SGP Country Programmes, so that GEF continues to channel funds to CBOs and CSOs in these countries. Additionally, while SGP running costs remain more or less stable, higher STAR funds (mainly used for grants) will contribute to achieving optimal SGP cost efficiency globally.

A.1.2. For projects funded from LDCF/SCCF:  the LDCF/SCCF eligibility criteria and priorities:

A.2.   National strategies and plans or reports and assessments under relevant conventions, if applicable, i.e. NAPAS, NAPs, NBSAPs, national communications, TNAs, NIPs, PRSPs, NPFE, etc.:

The SGP is a country-driven programme in that Country Programme policies and priorities are developed and owned by in-country stakeholders to benefit the global environment while bringing in local sustainable development results. National strategies and plans, along with GEF’s policies and strategies, form the basis for SGP’s programming and operation.  Almost all national policies and strategies such as NBSAPs, NAPs, NIPs and others emphasize the importance of engaging the widest possible array of stakeholders (including CSOs and other groups) in achieving the objectives, and in particular the community-based approaches to environmental protection. Hence, SGP’s community-based approach that targets small-scale local actions is very relevant to the implementation of these national policies and strategies.

The SGP operates in countries where specific requests to initiate the programme have been received from the appropriate national authorities, represented by the GEF Operational Focal Point. By first requesting and subsequently supporting implementation of the SGP, a government commits to SGP being a country-driven and owned initiative supporting community-level and civil society environmental projects.

National priorities are reflected through the constitution of the SGP National Steering Committee (or National Focal Group for sub-regional programmes), which guides implementation of the SGP in each respective country.  NSC members are leading national government and civil society representatives in the environmental field, who provide strategic guidance and oversight for the programme, and ensure its focus on and coherence with national priorities as they apply to and are relevant for community-level needs and priorities.

SGP Country Programme strategies are governing documents for SGP programming and operation in-country. The development and updating of the strategies are based on national policies and action plans, such as NBSAPs, NAPs, NIPs and other national key documents, which are directly linked to GEF focal area strategies and priorities. SGP’s Country Programme strategies are developed and updated to reflect national priorities, while ensuring alignment with GEF policies and priorities. Each of the strategies draws on priorities and activities included in these national policy documents, particularly those that are suitable for communities and CSOs small-scale interventions.

- Project Overview:
B.1. Describe the baseline project and the problem that it seeks to  address:

Today’s Global Environmental Challenges: The Baseline International attention has been focused on global environmental issues for decades (including nearly 20 years of existence of the GEF and SGP), and there have been some positive steps in that time. Yet, the scale and scope of these problems are such that they remain critical areas for ongoing investment and require a wide range of simultaneous, integrated and multi-focal approaches. The SGP is predicated on the idea that community-driven, stakeholder owned, civil society led initiatives that generate local as well as global benefits are among the most effective ways to address global environmental challenges, and this model has repeatedly achieved success. In effect, SGP operationalizes the maxim “think globally, act locally,” and has, based on its effectiveness at the community-level, become the “public face” of the GEF. The SGP supports community-level initiatives across the range of global environmental issues addressed by the GEF, and participation, democracy, flexibility, and transparency are cornerstones of the SGP approach. The communities targeted by SGP are often the poorest and most vulnerable, and typically have low levels of capacity to adequately address global environmental problems. Providing support for community-based and civil society initiatives is an effective and necessary component of comprehensively addressing global environmental problems, and the SGP plays a critical role in channeling this support. There are few resources targeted towards and available for community-level actions, and stakeholders at this level often lack the capacity to access national or international donors. SGP has a proven track record of effectively engaging with and leveraging community and civil society based initiatives, and this support must continue, as well as be scaled-up, to achieve a sustainable future. The Third Global Biodiversity Outlook, presented in May 2010, reflecting the most recent state of knowledge of the status of global biodiversity, found that “there are multiple indications of continuing decline in biodiversity in all three of its main components – genes, species and ecosystems.” The Millennium Ecosystem Assessment (MA) showed that the most important drivers of biodiversity loss are habitat change, climate change, invasive alien species, overexploitation, and pollution. Throughout OP4, the SGP contributed to the strengthening of almost 12 million hectares of protected areas. According to the most recent Intergovernmental Panel on Climate Change synthesis report, “global GHG emissions due to human activities have grown since pre-industrial times, with an increase of 70% between 1970 and 2004.” While the majority of current global GHG emissions come from developed economies, 17.4% of GHG emissions come from the forestry sector (including deforestation), while 13.5% comes from agriculture. The 2007 “Stern Review” noted that deforestation and forest degradation are the main emission sources in many developing countries. The MA reported that drylands occupy 41% of the earth’s land area, and 10-20% of drylands are already degraded with a much larger percentage under threat from desertification. The MA identified the direct drivers of land degradation, including land use change, natural resources consumption and climate change, which are further highlighted in the 10-year (2008-2018) strategy of the UNCCD. In OP4, more than 600 SGP-supported projects generated models and good practices for sustainable agriculture, and rangeland and forestry management. The Fourth Overall Performance Study of the GEF (OPS4) found that “The conditions that gave rise to the GEF and creation of an international waters focal area have not abated, and there are rising challenges.” Key issues in this area include coastal pollution and erosion, unsustainable fisheries, nutrient transfer (particularly nitrogen) from the land to the sea resulting in eutrophication and algal blooms, unsustainable management of fresh water supplies, and invasive species. Previous SGP efforts have supported the rehabilitation of coastal habitats, sustainable fishing practices, and the reduction of land-based pollution. Persistent Organic Pollutants bio-accumulate in the environment and can lead to serious health effects for humans. The World Health Organization estimates that pesticides may cause 250,000 unintentional deaths a year (particularly among agricultural workers), and nearly three million people may suffer additional effects, mostly in developing countries. In Africa, it is estimated that more than 50,000 tons of obsolete pesticides have accumulated. Other key harmful chemicals are PCBs, dioxins and mercury. To contribute to resolving these challenges, the SGP provides small-scale grants to community-based and non-governmental organizations for projects in-line with the strategic priorities of the GEF. Through its first 18 years, SGP has supported 2,846 community-level projects with over $64.3 million in funding, leveraging over $96.7 million in cash and in-kind co-financing in the countries covered by this PIF. Within the SGP portfolio, 90% of projects have achieved outcome ratings in the satisfactory range, and 80% of projects are considered to have low risks to the sustainability of outcomes. Across GEF focal areas the SGP empowers local communities to seek integrated multi-focal area solutions that can be replicated and scaled-up, and helps spark successful initiatives that grow beyond SGP’s initial support. SGP contributes to the building of networks, and strengthens civil society to unlock local capacity for solutions to these critical environmental problems. More than 60% of SGP grants target poor communities in participating countries, which have the greatest need for assistance. Indigenous peoples, who have the knowledge and experience to create sustainable solutions to environmental challenges, are also targeted by at least 15% of SGP grants. More than a quarter of SGP grants specifically support women, another priority target group. The SGP approach leverages shifts toward environmentally sustainable livelihood options, and increases education and awareness on environmental issues. While the SGP seeks solutions integrated across focal areas, the specific strategic objectives below are designed to address the global environmental problems described above. These strategic objectives are in-line with the GEF-5 strategic priorities, and are the means to long-term impact level results. For GEF-5, it is anticipated that the SGP STAR funding will support at least 649 projects (should the maximum grant amount of $50,000 be utilized) to as many as 1,298 projects (at the average grantmaking of $25,000 per project). Small Grants Programme Objectives for the 5th Operational Phase SGP OP5 Objective 1: Improve sustainability of protected areas and indigenous and community conservation areas through community-based actions Protected areas are one of the main global strategies for addressing the loss of biodiversity, and are a key Program of Work under the Convention on Biological Diversity. Protected areas are far from a perfect tool, but can be effective with well-considered implementation in appropriate circumstances. Community-based management, community-conservation areas, and indigenous protected areas have proven they can be an effective means of conserving biodiversity, but the sustainability of these areas must be ensured. At present, much of the global support for protected areas focuses on national parks and other areas that are formally gazetted at the national level, with insufficient attention or resources directed toward community conservation areas and indigenous protected areas. Community-level stakeholders require financial and technical support to maximize biodiversity conservation and local benefits from community conservation areas and indigenous protected areas. The SGP will support communities and the CBD protected areas Program of Work by working at the community-level to promote community conservation areas and indigenous protected areas, increase their recognition and support at the national level, improve their effectiveness in conserving biodiversity, and ensure the generation of local benefits, which are critical for the success of protected areas. Potential activities for funding will include the development and improvement of management frameworks, the promotion and recognition of CCAs and indigenous protected areas in national systems of protected areas, and development of communities’ capacity to apply protected area approaches. This will also include continuation of SGP’s innovative Community Management of Protected Areas Conservation (COMPACT) initiative in priority areas such as World Heritage Sites and Biosphere Reserves. Knowledge management with respect to community-conservation and indigenous protected areas is critical to improve effectiveness over time. In addition, one of the three main GEF biodiversity learning objectives is “enhancing social impacts through improved understanding of the causal relationships between protected area management and local community welfare,” an objective to which the SGP will contribute through the sharing of experiences and lessons learned under this strategic objective. The Global Environmental Benefits to be generated through this strategic objective are the conservation of globally significant biodiversity at the species, ecosystem and genetic levels. SGP OP5 Objective 2: Mainstream biodiversity conservation and sustainable use into production landscapes, seascapes and sectors through community initiatives and actions While protected areas are an effective approach, much biodiversity is located in production landscapes and seascapes. The second strategic objective is to mainstream sustainable biodiversity-friendly practices into the use of national resources across integrated landscape mosaics consisting of an array of land-use types. Activities that depend on biodiversity resources will be addressed, including agriculture, fisheries, forestry, and tourism, and SGP has an established history of supporting a range of biodiversity-based sustainable products in these sectors. While international efforts to mainstream biodiversity often focus on large-scale industries, supporting the integration of biodiversity considerations in community-level activities is also necessary to conserve biodiversity resources, where the people living in biodiversity rich areas are key partners. In developing countries, community level stakeholders have direct interaction with their environment, and, with SGP’s support for community and non-governmental organizations, can contribute to the conservation of biodiversity while utilizing it for sustainable livelihoods. SGP has supported more than 1500 projects for the sustainable use of biodiversity in production landscapes and seascapes, and building on this experience, SGP will support community-based initiatives and frameworks to incorporate market mechanisms such as recognized environmental standards that include biodiversity considerations, and the development of markets for biodiversity-friendly products. Private sector actors at the community-level are important partners, and SGP will support collaborative initiatives that develop the capacity of all stakeholders to mainstream biodiversity considerations in production landscapes. In this dynamic realm, knowledge management is critical to continuously improve good practices and identify lessons for innovative market-based approaches to biodiversity conservation. Activities under this objective will support implementation of the CBD’s Addis Ababa Principles and Guidelines for the Sustainable Use of Biodiversity. The Global Environmental Benefits to be generated through this strategic objective are the conservation of globally significant biodiversity at the species, ecosystem and genetic levels. SGP OP5 Objective 3: Promote the demonstration, development and transfer of low-GHG technologies at the community level To mitigate climate change and develop long-term low-GHG economies, the SGP will support demonstration, development and transfer of low-GHG technologies that are appropriately targeted and relevant for implementation through community-based and civil-society approaches. This strategic objective supports the UNFCCC technology transfer framework, including identified capacity development priorities. Community level stakeholders in developing countries are often overlooked and bypassed by global climate change technology transfer efforts, yet they are critical partners for the future as the developing world continues down the path of industrialization. The SGP has had widely recognized successes in applying innovative low-GHG technologies, for example with a program to develop cost-effective solar houses in Pakistan. Activities in the 5th Operational Phase will build on past experiences, and seek to continue replicating and scaling up successful approaches, while developing the capacity of community-based and non-governmental organizations to develop and implement low-GHG technologies. Examples of such activities include support for distributed micro-solar, micro-hydro, biogas and methane energy generation, and solar/fuel-efficient stoves. The development of partnerships between civil-society, government and private sector actors will be critical to the successful deployment and development of low-GHG technologies. Knowledge management to highlight best practices and lessons from the demonstration of low-GHG technologies will also be supported. With respect to climate change, the SGP contributes to the overall objectives of the UNFCCC, and the anticipated Global Environmental Benefits under this strategic objective include the reduction and avoidance of GHG emissions. SGP OP5 Objective 4: Promote and support energy efficient, low-GHG transport at the community level The transportation sector makes up a significant percentage of global GHG emissions, and this is even truer in the remote rural areas where SGP frequently works, where transportation systems are often old and inefficient, emitting high amounts of GHGs relative to the energy input. This strategic objective supports the UNFCCC Common Policy Framework to Support Sustainable, Low Carbon Transport in Developing Countries. Current efforts to address transportation related-GHG emissions generally focus on existing systems, while inefficient transportation options continue to self-propagate as motorization increases in rural areas. SGP will leverage its comparative advantage of working at the community-level to catalyze investment in low-GHG transportation through community and civil-society initiatives in this underfunded and presently ignored market segment. By improving the efficiency of transportation infrastructure at the community-level through the demonstration and deployment of low-GHG transportation options, SGP will contribute to mitigating the effects of climate change and set the course for limiting GHG emissions in the future. There are numerous transportation markets that can be targeted at the community level, particularly in remote areas where goods, and people, must be transported to and from markets over long-distances. The rural transportation network often involves high GHG-emitting trucks, buses and vans, and, increasingly at the personal level, motor scooters. In coastal and marine areas boats, both small and large, which rely on old and inefficient outboard motors are often the most common form of transportation. Through community and civil society actions SGP will seek to catalyze technology markets and address key barriers to low-GHG transport, while developing the capacity of stakeholders to develop sustainable transportation systems. Partnership and knowledge management to ensure replication and scaling up will again be key elements of all SGP supported activities under this strategic objective. With respect to climate change, the SGP contributes to the overall objectives of the UNFCCC, and the anticipated Global Environmental Benefits under this strategic objective include the reduction and avoidance of GHG emissions. SGP OP5 Objective 5: Support the conservation and enhancement of carbon stocks through sustainable management and climate proofing of land use, land use change and forestry As previously highlighted, the majority of GHG emissions in developing countries results from land-use change, such as deforestation, and the degradation of soils, forest lands, and other high carbon sequestering ecosystems such as peatlands, and “blue forests” in the marine realm. Engaging community-level partners to combat unsustainable land management is critical, as they are the direct users and beneficiaries of well-functioning ecosystems, and are the most affected by climate change. The SGP will work to mitigate GHG emissions and strengthen climate resiliency at the community level through the conservation, restoration, enhancement and management of carbon stocks in forest and non-forest lands, including peatlands. Such activities are supported by UNFCCC COP decisions 15/4, and13/2, which recognized “that the needs of local and indigenous communities should be addressed when action is taken to reduce emissions from deforestation and forest degradation in developing countries.” It has been shown, particularly in the forest sector, that activities addressing deforestation and forest degradation can be cost effective in both mitigating climate change, and reducing the vulnerability of social systems and ecosystems to climate change. SGP will support community and civil society driven initiatives such as community-forestry, and the restoration of degraded lands through afforestation and other measures. Sharing of lessons and best practices through knowledge management will assist in developing the capacity of community-based and non-governmental organizations to address land use, land use change and forestry issues. This strategic objective presents the opportunity to generate integrated Global Environmental Benefits in multiple focal areas including climate change, biodiversity conservation and land degradation, in addition to local economic benefits. SGP OP5 Objective 6: Maintain or improve flow of agro-ecosystem and forest ecosystem services to sustain livelihoods of local communities Maintaining ecosystem services – provisioning, regulating, supporting and cultural - is critical for long-term sustainable livelihoods at the community level. Rural communities are highly dependent on agro-ecosystems and forest ecosystems for their livelihoods, and have a vested interest in ensuring the necessary flow of ecosystem services. They are therefore motivated and necessary partners in fighting land degradation. The SGP will support community-level actions and civil society initiatives for integrated natural resource management and sustainable land management to reverse and prevent desertification and land degradation, supporting the first and second strategic objectives under the 10-year strategic action plan of the UNCCD. In addressing land degradation, multi-focal synergies can also be found with biodiversity, climate change, international waters, and potentially chemicals. Approaches that consider the broader landscape will be pursued, such as integrated watershed management, in which local communities and civil society are important partners whose efforts can be leveraged with SGP support. The agricultural and forestry sectors are important focus areas, and SGP will support activities and develop capacity to demonstrate and scale-up good practices for crop and livestock production through community-based agricultural management, to enhance agro-ecosystem services. Agro-ecosystems may include rangelands, grasslands and other landscape types that provide multiple ecosystem services. In the emerging ecosystem services area of practice, knowledge management to identify and share lessons and best practices will be highly important, as SGP has the ability to reach the poorest and most distant communities to develop capacity for improved natural resources management. Global Environmental Benefits to be generated include the maintenance or improvement of agro-ecosystem and forest ecosystem services, reduced GHG emissions from agriculture and landscape degradation, and reduced vulnerability to climate change. SGP OP5 Objective 7: Reduce pressures at community level from competing land uses (in the wider landscape) To improve landscape management and arrest land degradation in the wider landscape, land use degradation frontiers, such as forest/agricultural and rural/urban boundaries, must be targeted. Across the landscape, such frontiers are the nexus of competing land use pressures, and key areas where ecosystem services begin to be degraded. Community-level stakeholders live, and seek their livelihoods, in these areas, and are witness to the dynamic changes occurring as a result of intensive land use demands. Community-based and non-governmental organizations can therefore be effective partners in reducing pressures in the wider landscape, and must be engaged and supported in this effort. SGP will work with communities and civil society to improve community-level actions and practices, and reduce negative impacts in land use frontiers to demonstrate sustained ecosystem functionality, which also supports the strategic objectives of the UNCCD strategic action plan. In forest, agricultural and rural landscapes SGP stakeholders are well-positioned to demonstrate win-win solutions to address competing land uses. SGP will support community and civil society-based initiatives and knowledge management to develop capacity to test innovative and adaptive approaches such as payments for ecosystem services and other market mechanisms, as appropriate. As with the first SGP Land Degradation strategic objective, integrated, multi-focal and cross-sectoral approaches will be applied. The expected Global Environmental Benefits are the maintenance or improvement of ecosystem services, and cross-focal area benefits of reduced GHG emissions from land degradation, the conservation of biodiversity, and sustainable management of water resources. SGP OP5 Objective 8: Support transboundary water body management with community-based initiatives Effective approaches to transboundary water body management require multi-government solutions at the policy level, but must include implementation at the community level. Communities and resource users in coastal border regions and within transboundary watersheds are the local actors affected by policies and plans, and their participation and support is essential for the sustainable management and governance of transboundary water bodies. SGP will cultivate partnerships and initiatives to support implementation of international waters Strategic Action Programs (SAPs) through community-based and civil society actions. An SAP has been developed (or is in the process of being developed) for each transboundary water body where the GEF has worked, and the SGP will support the implementation of SAPs under the theory of intervention that these strategies are technically sound and appropriate road maps to supporting sustainable transboundary water body management. In OP4, SGP has supported more than 200 projects in 24 countries to implement SAP priorities at the community-level. In OP5, SGP will develop the capacity of stakeholders and support knowledge management to address important issues such as the reduction of land-based pollution, improved water use efficiency, sustainable fisheries through approaches such as “fish refugia”, habitat restoration and conservation, and the demonstration of water supply protection including catchment protection. Approaches may include community level integrated coastal management and sustainable fisheries practices. Communities and civil society are key partners in approaches such as integrated watershed management and integrated coastal zone management. SGP will support the relevant regional international waters conventions, such as those related to the South China Sea/East Asian Seas, Mekong River, Black Sea, Caspian Sea, Mediterranean Sea, Caribbean Sea, and Lake Tanganyika and other transboundary waterbodies. This strategic objective will produce Global Environmental Benefits for international waters including sustainable use of water resources, reduced nutrient flows and land-based pollution to transboundary water bodies, conservation of critical habitats, and conservation of species important for ecosystem function and economic benefits. SGP OP5 Objective 9: Promote and support phase out of POPs and chemicals of global concern at the community level SGP’s strategy addressing POPs and other harmful chemicals is two-fold – first managing and reducing use of these substances; and second, addressing the disposal, clean-up and mitigation of environmental contamination. Community-level stakeholders in developing countries are often unaware of the full-extent of potential negative environmental and health effects from POPs, and lack the technical capacity to safely manage and dispose of harmful chemicals. The comparative advantage of SGP is the demonstration, piloting and testing of community-based models to address POPs which can be scaled-up and replicated to catalyze successful large-scale approaches. An important element of the chemicals objective is increasing the awareness of the potential harm from POPs and other dangerous chemicals. As in all focal areas, developing community-level capacity to implement the relevant convention (i.e. Stockholm Convention) will be a key focus area, including activities to promote the environmentally sound use of exempted POPs, and other areas of convention guidance. In OP4, data indicates that SGP projects are supporting implementation of the National Implementation Plans (NIPs) in 70% of countries that have developed a NIP. Other activities may include the reduction, elimination or avoidance of harmful chemicals, such as mercury that is commonly used in small-scale mining, and agricultural pesticides. Knowledge management for replication and scaling-up will support additional activities building on previous SGP experiences to promote appropriate waste management and test alternatives to waste burning. Capacity building will remain a critical component in the POPs portfolio. SGP will continue promoting the use of the POPs Training Module developed in OP-4, and raise awareness and technical capacity to address POPs issues at the local level. As a whole, the SGP will support the objectives of the Stockholm Convention, and the Global Environmental Benefits generated will be reduced releases of POPs to the environment, and the mitigation of previous environmental contamination. SGP OP5 Objective 10: Enhance and strengthen capacities of CSOs (particularly community-based organizations and those of indigenous peoples) to engage in consultative processes, apply knowledge management to ensure adequate information flows, and implement convention guidelines as well as monitor and report on-the-ground project results The SGP is an important contributor to the GEF’s long-standing support for capacity development. Capacity development activities in the pure STAR countries will primarily focus on the focal areas that funding resources are drawn from, i.e. biodiversity, climate change and land degradation, while also incorporating activities to address capacity development in international waters and POPs focal area. An integrated multi-focal area approach to capacity development will be applied to strengthen CSOs and CBOs in developing, implementing and monitoring GEF eligible projects that will generate global environmental benefits. All SGP country programs are driven by the underlying goal of developing community and civil society capacity to engage and respond to key environmental challenges. Support for capacity development is critical among SGP’s primary stakeholders – capacity is frequently limited among communities in poor rural areas to self-organize and address environmental problems. Local communities have much to offer in terms of local knowledge and experience, but may require external support to unlock this potential, and to build linkages for engagement at higher levels, for example, through the SGP National Steering Committee. In SGP’s experience, the most effective approach to capacity development at the community level is through “learning by doing”, rather than through highly technical classroom training. Results expected for capacity development will be achieved through the types of activities such as network development, experiential learning related to good practices and lessons learned, support for contributing to local, regional and national environmental dialogues and consultations, and environmental education and awareness raising. Other types of capacity development activities may be supported, based on the specific context, priorities and barriers within each country. The current PIF covers a specific capacity development component targeting the CSOs and CBOs in the countries with no core grant allocation. As is outlined in Table B above, SGP expects that support for capacity development will contribute to the effective engagement of SGP stakeholders in national consultative processes, the establishment of knowledge platforms to share lessons learned and good practices, and more than 724 CSOs with strengthened capacities (the number of CSOs expected to be engaged in SGP projects in OP5). The capacity development activities will particularly focus on enhancing capacities of community-based and civil society organizations (CSOs) to engage in consultative processes in policy development and implementation, improving their capacity to consolidate knowledge and information; and strengthen their operational capacities to implement the Convention Guidelines at the community level. While successfully implementing projects and delivering results on the ground is critical to SGP success, it is equally important to build CBOs and CSOs capacity in monitoring and reporting progress on the ground that will contribute global aggregation of results and impact. Local ownership, participation, knowledge sharing and effective networking are key to ensure the retention of capacity developed at the community level. To ensure sustainability of community capacity, SGP will ensure beneficiaries of capacity development are rooted in and deeply connected within the communities, so when projects are completed, the knowledge and technical skills remain within the communities to continue carrying out environmental protection activities. Rather than importing techniques, SGP tries to utilize locally available and suitable solutions, which will be continued after project completion. SGP will also strengthen grantees’ capacity to participate in national and international forum, and advocate good experiences for upscaling and replication. It will support grantees’ network for knowledge sharing and exchange of information. Lessons learnt will be consolidated at the Country Programme level for national dissemination and international sharing. Implementation Arrangements The global SGP will continue operating in partner countries with the same implementation approach that has proven effective previously in the past eighteen years. The implementation arrangements outlined below have been covered mostly by the SGP global core funding PIF. SGP is a country-driven grant-making programme that aims to provide direct funding access to local communities and CSOs. SGP maintains a small Central Programme Management Team (CPMT) and establishes an effective Country Programme team where possible composed of National Coordinator, a National Steering Committee (NSC) and a Programme Assistant that work closely with the government, the UNDP country office and other stakeholders. At the Country Programme level, a National Coordinator, supported by a programme assistant, operates the SGP Country Programme Office on a day-to-day basis. The staffing cost and country operating budgets are drawn from core fund and STAR management cost. The National Coordinators report directly to the Global Manager, and such arrangement has proved to help the National Coordinators withstand pressures at domestic level in terms of the overall politics of controlling SGP as intended by some stakeholders. For each operational phase, the Country Programme Strategy (CPS) in each country will be developed or revised to articulate in detail how the SGP supports national and GEF strategic priorities as outlined in focal area strategies. The voluntary National Steering Committee (NSC) of each SGP Country Programme, composed of government national leaders with majority non-governmental membership to reflect the programme’s mandated focus for CSO capacity building, provides overall country guidance and provide direct linkages to national policy-making and development planning. The NSC provides strategic direction of SGP development, oversees Country Programme performance, and reviews/approves grant proposals. Often, the NSC also serves to transfer local community experiences and practices into national policies development and implementation. In many cases, the NSC also plays a key role in securing STAR fund endorsement from the governments to SGP. At the global level, the CPMT is in charge of managing the global programme and supervising the SGP National Coordinators as well as facilitating the start up of new Country Programmes and supporting the implementation of existing Country Programmes. CPMT is supported by and coordinates the work of UNOPS which provides execution services. Strategic guidance is provided to SGP by a GEF SGP Steering Committee chaired by the GEF CEO. All GEF agencies and the GEF NGO Network are members of this Steering Committee. SGP will also continue to be supported by UNDP country offices, and will link with relevant GEF FSPs and MSPs when possible. In addition to the standard SGP grants, the Country Programme Office activities will include strategic efforts in line with the CPS and the GEF strategic priorities that will enable aggregation of community-driven impacts for global environmental benefits, local to global strategic portfolio learning and capacity development, dissemination of best practices, or linkage and network building for SGP portfolio grantees. This approach will support the SGP and GEF catalytic role by contributing to replication and upscaling of good practices. SGP is a cost-effective instrument for the GEF to generate global environmental benefits through NGOs and community-based organizations (Joint Evaluation 2007, pp. 46). The efficiency of outcome ratings for the SGP grants appear to be better than those for the FSPs and MSPs” (Joint Evaluation 2007, pp. 50). In GEF-5, SGP will undertake the following measures to further enhance the programme’s and grant projects’ cost efficiency: 1) be integrated as delivery mechanism for community/NGO components of FSPs – in which case they would have a share of the FSPs’ management budget; 2) raise cofinancing from non-GEF sources in ways that management costs are defrayed. At the project level, SGP will engage voluntary NSC members to provide technical and management assistance to communities, obtain local governments and other partners’ co-financing and support, ensure linkages and synergies with other ongoing activities and other proper activities to further improve projects’ cost effectiveness.

B. 2. incremental /Additional cost reasoning:  describe the incremental (GEF Trust Fund) or additional (LDCF/SCCF) activities  requested for GEF/LDCF/SCCF  financing and the associated global environmental benefits  (GEF Trust Fund) or associated adaptation benefits (LDCF/SCCF) to be delivered by the project:

The SGP provides support to achieve global environmental benefits at the community level. The current baseline scenario, partly described in Section II.A. above, would remain the status quo in a business-as-usual scenario without GEF support. On the one hand, community-level stakeholders in remote and marginalized areas have the least access to technical and financial resources to address global environmental issues, and the SGP is a critical partner to assist communities tackling environmental challenges. At the same time, over its initial 18 years the SGP has developed an efficient and effective system while building a growing portfolio of demonstrated community-based approaches. The programme is a critical resource for SGP’s partner organizations and communities, without which their available support channels would be reduced and their ability to confront environmental issues limited. The SGP strengthens the capacity of communities and non-governmental organizations, increases knowledge and awareness about environmental threats, and provides financial leverage to overcome short-term decision-making that negatively affects environmental resources. Short-term decision-making is often unavoidable in poor regions where individuals have to secure the basic elements for survival on a day-to-day basis, and therefore do not have the possibility to plan for long-term sustainable livelihoods ensuring environmental protection. Many of the communities where SGP works are in remote or marginalized areas often not targeted by large-scale national development efforts. At the same time, these communities often have detailed knowledge of their local environment built up over generations, and should be primary partners in environmental conservation and sustainable development. Critical global environmental issues benefiting from the SGP’s integrated multi-focal support are those addressed by the GEF: biodiversity conservation, climate change, land degradation, degradation of international water bodies, and the use and disposal of harmful chemicals. The baseline scenario without GEF support would therefore see: • Ongoing poverty and unsustainable practices in communities that depend on the environment for their livelihoods; • Continued degradation of ecosystem function due to biodiversity loss, deforestation and pollution; • Business-as-usual increasing GHG emissions, leading to negative environmental and human impacts from climate change and air pollution; • Further degradation and desertification of productive and non-productive land-use systems; • Continued negative environmental trends in international water bodies; • Unsafe use and disposal of environmentally harmful chemicals; and • Lower levels of capacity development and knowledge management related to key global environmental issues. Such conditions, if not addressed, will continue contributing to loss of ecosystem function, and the continuation or increase of corresponding poverty levels. The baseline scenario acknowledges that partners at local, national and international levels make an important contribution to addressing these issues, but that greater synergistic results to achieve incremental global environmental benefits will be secured with SGP support, since SGP brings together a range of diverse partners at the national level to address community-level issues. In addition, efforts to address global environmental challenges in an innovative and community-driven manner are underfunded by orders of magnitude in relation to the potential need, including currently limited funding for capacity development and knowledge management at the community-level. SGP provides incremental added value by catalyzing new development models, improving knowledge flows, and informing policy. The 2007 Independent Evaluation of the SGP found that some of SGP’s greatest contributions are in the realm of national policy development, catalyzed by country-specific SGP initiatives. Replication and scaling-up will continue to be key tenets of the SGP approach to achieve incremental benefits, and SGP will work with key partners, such as the GEF NGO network, to disseminate good practices throughout global civil society and promote the GEF agenda. Furthermore, without SGP there would be limited monitoring and reporting on environmental conservation efforts and environmental trends in targeted areas and communities, which is critical for data collection, documenting and disseminating good practices. With its integrated and scaled-up approach to addressing environmental issues at the community level, the SGP fills a critical niche in environmental efforts to achieve impact-level results for global environmental benefits.

B.3. 	Describe the socioeconomic benefits to be delivered by the Project at the national and local levels, including consideration of gender dimensions, and how these will support the achievement of global environment benefits (GEF Trust Fund) or adaptation benefits (LDCF/SCCF). As a background information, read Mainstreaming Gender at the GEF.":

SGP is rooted in the belief that global environmental problems can best be addressed if local people are fully involved in project design and formulation, have strong ownership of the actitivities undertaken through a "demand-driven" approach, and that direct socioeconomic benefits will accrue to communities as a result of project implementation, a consequence that provides the incentives and motivation to sustain the projects after the end of grant funding. In contrast with "expert-reliant" development interventions, the emphasis in SGP is on creative problem-solving and innovation by the communities themselves, often based on the comparative strengths of an intimate understanding of local circumstances. SGP is premised on the principle that through the provision of relatively small amounts of funding, local communities can undertake cost effective activities that will make a significant socioeconomic difference in their own lives, whilst generating global environmental benefits. SGP has always recognized the importance of socio-economic benefits to local communities, such as poverty reduction and livelihood, water and sanitation, health, education, and women’s empowerment, as essential to achieving sustainable global environmental benefits. One of the key elements of SGP is that it considers the human needs of the communities it works with to be fundamentally tied to the use of natural resources to attain sustainable livelihoods. Some of the strategic considerations for project development are to increase productivity or generate new livelihood opportunities, as well as income and access to financial capital. SGP understands that the sustainability of its projects will only be possible if there is a high level of ownership by the community and if it generates local benefits. SGP projects help communities to improve their access to tools and machinery, land, and key infrastructure such as energy and water supply. But as important as having the right infrastructure is to enhance the social capital, institutional capacity and equity of the communities, SGP places special emphasis on enhancing the institutional capacities of the communities, by providing training and expanding their networks, as well as by improving their ability to address global environmental issues. To do this, the programme invests in strengthening the human capital of the community, by enhancing the skills, knowledge and abilities necessary to implement and sustain the projects. In GEF-5, SGP will further systematize its approach to local livelihoods by consolidating good experiences and identifying and securing strategic partnerships for funding opportunities. In the past, SGP has raised co-financing to finance sustainable alternative livelihoods activities and address the community needs for community buy-in of the projects. For instance, the Community Water Initiative (CWI) funded by bilateral donors and implemented by SGP has provided water supply and sanitation services to communities implementing SGP projects, ensuring communities’ acceptance and support for SGP projects. Such an approach to combine and sequence GEF funding with non-GEF funding has proven to be mutually beneficial and re-enforcing. SGP understands the importance of gender equality and women’s empowerment as essential elements to achieve sustainable development and project impacts for the GEF. As such, gender is mainstreamed throughout the SGP programme and its associated portfolio of projects. Gender is one of the mandatory cross-cutting requirements in the SGP grant-making criteria and is incorporated within the SGP project cycle. About 17 percent of SGP projects supported world-wide have focused speciﬁcally on the engagement and empowerment of women. Although obstacles remain at the local and community level, SGP has been able to support projects that have benefitted both men and women within the same communities. Many SGP projects have been recognized for their success in promoting gender equality and womens’ leadership. SGP Country Programme Strategies are required to include references to gender, and all SGP staff members are encouraged to take the UNDP online gender training, as well as to take advantage of related opportunities offered by UN agencies. Gender is one of the key results of the SGP National Coordinators’ annual Performance and Review Assessment (PRA) carried out by UNDP Country Offices and the Central Programme Management Team at the global level. SGP has also established a global partnership with the Huairou Commission to pilot capacity building for women and dissemination of gender-related good practices between SGP countries worldwide.

B.4	Indicate risks, including climate change risks that might prevent the project objectives from being achieved, and if possible, propose measures that address these risks to be further developed during the project design:

There are few new risks to be faced since the programme has been operating for nearly 20 years. Potential risks are known, and through the past experience of the SGP risk mitigation measures are in place. There remains the challenge of working directly with community-based and non-governmental organizations that have a low level of technical and management capacity. Past performance of the SGP portfolio has shown that 90% of SGP grants achieve outcomes in the satisfactory range. To mitigate risks, especially in the small underperforming portion of the portfolio, the SGP works with all grantees to help build capacity by identifying appropriate rates of disbursement, linking grantee partners to learn from each other, and working in a flexible manner that responds to the strengths and comparable advantages of grantees. Risks of underperformance due to capacity limitations will also be mitigated by consistent and comprehensive oversight and monitoring of the SGP portfolio in each country by SGP CPMT and the UNDP CO. The SGP also reduces risk by supporting replication of good practices that have proven to deliver on GEF strategic priorities at the community level. In each SGP country, the National Steering Committee, with representation from civil society leaders, government institutions, and donors provides further support for effective design and implementation of SGP projects. There are two important operational risks that must be recognized for the SGP in the 5th Operational Phase. First, the programme is expanding to include an even greater number of countries. As the programme expands, the overall level of effort for coordination and implementation at the central level increases. The SGP CPMT is undergoing a review of the internal management arrangements to ensure that efficient and effective structures and adequate financial and human resources are in place to meet the needs of a growing portfolio of countries. A second, related, risk is that as the programme continues to expand, it reaches countries that present potentially greater operational challenges and increased political and institutional risks, related to low levels of individual, institutional and systemic capacity. At the same time, such countries, including LDCs and SIDS, represent areas where SGP has the potential to leverage significant global environmental benefits with relatively small levels of funding. Expansion risks in low-capacity areas will be mitigated through above-average levels of supervision attention, and by the transference of relevant lessons and best practices from other SGP countries. There is potential for climate effects to influence SGP grant results, positively or negatively, particularly with respect to biodiversity and land degradation. For example, climate effects could have adverse impacts on agricultural biodiversity conservation through drought or flooding, and on the application of protected areas as a conservation measure due to geographically shifting ecosystems. Such risks are not specific to the SGP, but to all GEF-supported interventions. At the community level, climate risks may however disproportionately affect SGP grantees: the poorest, most marginalized, least developed communities are the least able to finance climate resilience measures. Such communities, and associated organizations, are among the primary SGP partners. Grants will be made keeping in mind the potential climate risks, and steps will be taken to minimize and adapt to effects when possible. Finally, there remain possible exogenous risks to desired outcomes at the programme and project level, such as severe weather and other force majeure events, political stability, and global economic crisis. Mitigation measures for exogenous risks are implemented in an ongoing ad-hoc manner as necessary and appropriate. In addition to the general risks the SGP faces as a global programme, for the STAR funding in particular, there are risks related to government support, STAR fund availability and inadequate STAR amounts to meet the cost/grant ratio of 10%. The SGP depends on governments to contribute part of the STAR allocation to provide grant or complement the low core grant of SGP Country Programmes with no core or very low core grant allocation. Some governments may take the occasion to exert dominant influence in the Country Programme overall governance, or may opt to provide no STAR fund to the specific Country Programmes. Where governments strive to have an influence on resource allocation, SGP relies on the global Operational Guidelines to avoid sacrificing key SGP principles. Given the fact that 16 Country Programmes completely depend on STAR resources for grant allocation, it is critical to ensure STAR fund availability to continue grant-making activities. Obtaining STAR funding late could pose great programme, financial and operational risks to SGP. Programmatically, SGP Country Programme staff will have no grant-making activities to work on, and also have the possiblity to lose co-financing opportunities. Financially and operationally, before STAR funding is made available, it is intended that SGP would “advance” some of the core funding to the countries with no core allocation so that these countries can continue grant-making activities until STAR fund is made available. This could be risky to SGP’s global financial situation. CPMT will work closely with UNDP and UNOPS to conduct various financial scenario analyses to ensure highest cost-efficiency without jepardizing the programme’s financial status. This risk can be controlled by conducting financial analysis and working effectively to secure STAR funds as soon as possible. STAR grants play a key role in reducing management cost ratios over grant allocations (see Annex 1 the endorsed STAR fund from the countries). SGP Country Programmes have a relatively stable structure of one NC with or without a PA (depending on Country Programme sizes). Aside from the countries that completely rely on STAR funds for grants, most other countries cannot achieve the desired management cost ratio of 10%. Significant STAR amounts should be endorsed by countries to help SGP Country Programmes fully utilize their human and programme resources. It is recommended by the Joint Evaluation 2007 that an annual grant of $1-1.1 million be the optimal grant-making size to ensure cost efficiency of SGP. Without such levels of STAR, SGP might run into risks of not being able to achieve optimal efficiency. This risk can be managed by convincing governments to contribute adequate STAR funds. Additionally, sufficient co-financing raised could further enhance cost efficiency. In case that STAR funding is not released on time after core funds are advanced, or STAR funds are not sufficient to achieve the cost efficiency level as required by Council, the SGP will resort to the Programme Steering Committee and the Council to determine solutions and possibly reallocate the fund resources between various activities.

B.5. Identify key stakeholders involved in the project including the private sector, civil society  organizations, local and indigenous communities, and their respective roles, as applicable:

As an integral part of its decentralised system of national-level steering committees, SGP operates through a multi-stakeholder approach engaging a range of stakeholders including NGOs, CBOs, indigenous people, the private sector, government, academia, and donor partners. During OP5, CSOs will be both beneficiaries and direct participants in SGP through their inclusion in NSCs and National Focal Group, where non-governmental members must be in the majority, as well as by taking on the role as National Host Institutions and other key roles related to knowledge sharing and policy advocacy. Although SGP grants are targeted specifically at community-based and non-governmental organizations, a broad range of stakeholders are engaged as active partners during grant implementation, including inter alia research institutes, local and municipal governments, international NGOs, as well as national and international volunteers. With regard to indigenous peoples and marginalised populations, SGP follows a set of principles that advocate for a flexible, time sensitive, and simple project cycle in order to allow these "difficult to reach" groups to access SGP support. The programme has pioneered numerous user-friendly modalities to work with poor and marginalized groups including alternative proposal formats such as participatory video, photo stories, and community theatre, and allowances are made for concept and project submission in local and vernacular languages. SGP also allows for flexible disbursement terms to cope with indigenous peoples’ culture, customs and seasonal movements. Through stakeholders workshops, CSOs are able to learn of SGP projects and activities and provide inputs on how to improve on them.

B.6. Outline the coordination with other related initiatives:

The SGP has formed mutually beneficial long-standing relationships with international, national and community-level initiatives and partners, and will continue to seek synergies in the coming operational phase. SGP works with relevant stakeholders in the geographic and thematic areas supported by SGP to ensure coordination of donor funding on relevant initiatives. SGP will also seek linkages with other relevant GEF MSPs and FSPs whenever synergies can be found. The table below highlights selected key SGP relationships with related global level initiatives relevant to the 5th Operational Phase. There are also numerous national and local level SGP partnership initiatives (although, given their number, it is not possible to list them in the table below), and these will continue to be a priority for SGP in the 5th Operational Phase. Table 1 Initiative Name; Organization(s); Relevance to SGP; Brief description of coordination, synergy with SGP. Mekong Asia-Pacific Community Based Adaptation programme (MAP CBA); AusAID; Co-financing for community-based adaptation to climate change; Cost-sharing for project activities on resilience to climate change, including regional technical support and knowledge management components.. Community Management of Protected Areas Conservation (COMPACT); United Nations Foundation (UNF); Strategic aggregation of small grants at landscape scale; Cost-sharing from UNF for the targeted delivery of GEF grant funding to target World Heritage Sites and Biosphere Reserves. World Heritage ‘Local Ecological Entrepreneurship Programme’ (WH-LEEP); UNF & Conservation International Verde Ventures programme; Extension of COMPACT landscape approach; Cost-sharing from UNF and CI for support to SME and producer organisations through the provision of biodiversity-friendly loans.. Community Water Initiative (CWI); SIDA, Govt of Norway, and Govt of Luxembourg; Co-financing for water-related portfolio of projects; Cost-sharing for small project activities pertaining to water security and sanitation as complementary co-financing for sustainable development at the local level ..

C.   describe the GEF agency’s comparative advantage to implement this project:

In the GEF’s modality typology, the SGP is considered a capacity development and technical assistance intervention type, which is deemed to be UNDP’s comparative advantage in all GEF focal areas, as highlighted in the comparative advantage matrix of Annex 1 in the relevant GEF council paper, GEF/C.31/5 rev.1. UNDP has valuable experience in human development, civil society and institutional strengthening, and non-governmental and community participation, which are all key tenets of the SGP. UNDP has served as the implementing agency for the global SGP since the programme’s inception, playing this role on behalf of the GEF partnership. A key comparative advantage is UNDP’s network of country offices, which provides helpful support and backstopping for the programme at the national level in each SGP country. Throughout its many years of experience implementing the SGP, UNDP has helped develop an efficient and effective implementation approach. UNDP has also established the necessary relationships with UNOPS and global partners who provide administrative, technical, and financial support for SGP. It is anticipated that UNOPS will continue to play its important role supporting disbursement and financial management, in partnership with UNDP. UNDP is also proposed as the implementing agency for the ten upgrading SGP Country Programme FSPs, and it will be essential for the upgraded programmes to remain in close communication with the global SGP CPMT to facilitate global level SGP monitoring, and the identification and sharing of good practices and key lessons learned. This is even more important in view of the fact that this will be the first cohort of countries to adopt an individual upgraded SGP through the FSP modality, and these countries will be able to provide valuable insights to any countries making this shift in the future.

C.1   Indicate the co-financing amount the GEF agency is bringing to the project:

SGP has a standing expectation of 1:1 co-financing (50% in cash and 50% in kind), thus for this PIF the expected co-financing would be $36,000,000. UNDP will directly contribute to this through its TRAC funds as well as from those that will be fund-raised with other bilateral and multilateral donors, foundations and the private sector. While there is yet no exact amount for the additional co-financing that will be fund-raised in the next four years of OP5, as this will be an on-going effort throughout GEF-5, UNDP has now established a post called “Senior Technical Adviser for Communities, Livelihoods and Markets” supported by a high level advisor. These posts are tasked to develop new initiatives to provide co-financing to SGP. It should also be noted that UNDP Country Offices provide significant in-kind resources in their voluntary membership in the SGP National Steering Committees, and in faciltating access to and helping negotiate with donors additional co-financing for SGP Country Programmes and their projects.

C.2  How does the project fit into the GEF agency’s program (reflected in  documents such as UNDAF, CAS, etc.)  and staff capacity in the country to follow up project implementation:

The SGP is consistent with UNDP policies and procedures applying to all countries where UNDP is present and the SGP is implemented. As the programme covers more than 120 countries, individual country-based planning framworks cannot be exhaustively listed. SGP contributes to UNDP's objective of fostering human development, as well as localising the achievement of the Millennium Development Goals (MDGs) agreed upon by the international donor community. As the development network of the United Nations system, UNDP has country offices in the vast majority of countries where SGP is located. In the case of SIDS in the Pacific, the UN Resident Coordinator system, led by UNDP, has put in place a 'Joint Presence' mechanism between UNDP, UNICEF and UNFPA which provides on-the-ground support. SGP country teams are responsible for implementing the programme within their respective countries, as well as to align with and complement the objectives of the UN Development Assistance Framework (UNDAF). At the global level, as captured in the UNDP Strategic Plan 2008-2011, the goal of the 'Local Pillar' of the Environment and Energy Group (EEG) is to strengthen national capacity to manage the environment in a sustainable manner while ensuring adequate protection of the poor. Four key result areas have been identified to achieve this goal: (1) mainstream environmental and energy; (2) catalyze environmental finance; (3) adapt to climate change; and (4) expand access to environmental and energy services for the poor: developing national capacity for service delivery. In addition, the SGP complements numerous other programmes identified in the UNDP Civil Society strategy approved in 2009.

The SGP online database is the tracking tool to capture project information and portfolio results.  The database will be further enhanced during GEF-5 and will feature a streamlined and simplified system of indicators. SGP will track its global environmental benefits and other socio-economic benefits through the mandatory inclusion of online indicators, and incorporate these indicators and targets in Country Programmes’ annual reports. SGP will strengthen its M&E framework to capture global environmental and socio-economic dimensions of projects.  Periodic portfolio reviews will also be systematically conducted to capture results and achievements as measured against indicators and targets.

part iii:  approval/endorsement by gef operational focal point(s) and GEF agency(ies)

A.   Record of Endorsement of GEF Operational Focal Point (S) on Behalf of the Government(S): (Please attach the Operational Focal Point endorsement letter(s) with this template. For SGP, use this OFP endorsement letter).

| Name | Position | Ministry | Date (MM/dd/yyyy) |
| --- | --- | --- | --- |

B.  GEF Agency Certification

| This request has been prepared in accordance with GEF/LDCF/SCCF policies and procedures and meets the GEF/LDCF/SCCF criteria for project identification and preparation. |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Agency Coordinator, Agency name | Signature | Date (MM/dd/yyyy) | Project Contact Person | Telephone | Email Address |
| Yannick Glemarec, UNDP GEF Executive Coordinator |  | 09/20/11 | Delfin Ganapin | 646-781-4383 | delfin.ganapin@undp.org |

PIF_WITHOUT_MACROS

1.0

It is very important to consult the PIF preparation guidelines when completing this template.

Project ID number will be assigned by GEFSEC.

Refer to the reference attached on the Focal Area Results Framework when filling up the table in item A.

GEF will finance management cost that is solely linked to GEF financing of the project.

Same as footnote #3.