# Project PREPARATION GRANT (ppg)

Project Type:

type of Trust Fund:

Submission date:  January 11, 2013

GEF Project ID:4660

GEF Agency  Project ID: 614525

Country(ies): Global

Project Title: Sustainable fisheries management and biodiversity conservation of deep-sea living marine resources and ecosystems in the Areas Beyond National Jurisdiction (ABNJ)

GEF Agency(ies): , UNEP,

GEF Focal Area(s):

a.   Project preparation Timeframe

| Start date of PPG | 12/1/2012 |
| --- | --- |
| Completion date of PPG | 5/31/2013 |

B.  proposed project preparation activities ($)

| Describe the PPG activities and justifications: This PPG presents all the preparation activities and outputs needed for completing the full design of the Project “Sustainable fisheries management and biodiversity conservation of deep-sea living marine resources and ecosystems in the ABNJ”. The project preparation activities consist of: (i) the necessary stakeholder consultations and consensus building on the project preparation process and activities, workplan and timetable, as well as on roles, responsibilities for the detailed design and costing of the project/ components described in the PIF. This Project is results-oriented and therefore contains a number of pilot activities aimed at identifying and demonstrating practical solutions to existing constraints and barriers to sustainable Deep-Sea Fisheries (DSF) and associated biodiversity (BD) conservation in the ABNJ. Although these pilot activities relate to specific project components, their preparation is presented in one single group of activity, to better appreciate their mutually reinforcing outcomes. It is important to note that DSF development has accelerated much ahead of existing scientific understanding and that more practical information is necessary as well as adapting what is already available to specific deep-sea issues. Therefore, while Activities 4 and 5 are essential, their successful implementation greatly depends on carrying out Activites 2 and 3 which are prerequisites. The preparation activities are laid out as follows (with details in the matrix hereafter) : Preparation Activity 1: Stakeholders consultations and consensus building at regional and global levels. The purpose of this activity is to build broad agreement among all stakeholders, including industry partners, on the preparation activities, workplan and timetable for project preparation, roles and responsibilities, agreement on pilot activities, co-financing arrangements and commitments, and endorsement of the draft Project Document. These consultations are important for ensuring the participation of the key stakeholders both in project preparation and implementation and will result in agreed institutional and implementation arrangements. This activity is further enhanced through Preparation Activity 6. Preparation Activity 2: Review of relevant existing policy and legal frameworks as well as global and regional networks in the ABNJ, for the purpose of mainstreaming specific obligations about sustainable DSF and BD conservation, with focus on selected regions. This specific preparation activity comes in support of Project Component 1 “Policy and legal frameworks for sustainable fisheries and biodiversity conservation in the ABNJ deep seas”. The purpose is to provide project implementors with an overview of the institutional legal and policy environment at the global and regional levels, with respect to DSF and BD conservation in the ABNJ. Outputs of this activity include: (i) inventory of relevant policy and legal frameworks; (ii) initial identification of constraints and barriers to implementation of international instruments; iii) overview of existing global and regional networks, and initial identification of where networks for DSF and biodiversity conservation should be strengthened or created; and (iv) needs assessment for strengthening policy and legal frameworks as well as for networking and partnerships (see also Preparation Activity 4 for the two pilot activities related to this project component). In addition to the above outputs, specific criteria will be developed for the selection of at least ten developing countries to be supported for integrating best practices for sustainable DSF and biodiversity conservation into their management processes. Preparation Activity 3: Review of relevant existing DSF management systems and tools in the ABNJ, for the purpose of mainstreaming BD issues into DSF management. This specific preparation activity comes in support of Project Components 2 and 3, as follows: Project Component 2 “Reducing adverse impact on VMEs and EBSAs” Under Activity 3, the relevant outputs are: (i) an inventory of biological, ecological and socio-economic information available; (ii) overview of management measures and tools used for reducing threats to sustainable DSF and BD conservation; and (iii) assessment of institutional strengthening and capacity building needs for applying management tools to reduce negative impacts, particularly in VMEs and EBSAs. In addition, two related pilot activities are being prepared under Preparation Activity 4. Project Component 3 “Improved planning and adaptive management for ABNJ DSF” Under Activity 3, the relevant outputs are: (i) overview of current management systems, identifying gaps, constraints and barriers with regards to DSF; and (ii) assessment of the stakeholders’ capacity needs for planning and development of processes for achieving sustainable DSF and BD conservation, particularly allowing for adaptive changes. In addition, three related pilot activities are being prepared under Preparation Activity 4. Preparation Activity 4: Preparation of comprehensive implementation plans for all pilot activities. This specific preparation activity comes in support of Project Components 1, 2 and 3 and includes the corresponding workplans, cost tables, financing plans, institutional setup and arrangements for each activity. The seven pilot activities are as follows: Under Project Component 1: The two pilot activities consist of the development, testing and demonstration, in at least one selected project area, of: i) options for rights-based management systems and market-based incentives; and ii) the development of model policy and legal frameworks for sustainable DSF and BD conservation. Under Project Component 2: The two pilot activities are: (i) identification and agreement of indicators for species and critical habitats for VMEs and EBSAs - linked to (ii) under Project Component 3 below; and (ii) improved fishing practices and management measures to reduce impacts on VMEs and EBSAs. Under Project Component 3: The three pilot activities are: (i) demonstration of adaptive management processes, including through participatory risk analysis, in at least one selected project area; (ii) selection of objective-based indicators and reference points (for target species, catch/bycatch composition, etc.) and testing of a related monitoring program in one selected project area; and (iii) formulation and adoption of action plan for use of best MCS practices in one of the previously selected areas. In addition, there will be a pilot activity will be designed to test a specific methodology for area-based management planning in the ABNJ deep seas. This is presented separately under Preparation Activity 5 since it is part of Project Component 4 for which UNEP is the GEF Agency. Preparation Activity 5: Preparation for developing and testing a methodology for area-based planning in the ABNJ deep seas. This specific preparation activity comes in support of Project Component 4 “Development and testing of a methodology for area-based planning”. The preparatory activities include: (i) an inventory of relevant area-based management tools and instruments, (ii) the formulation of a workplan to develop a specific methodology for area-based management planning in the ABNJ deep seas, and (iii) the preparation of an implementation plan for the testing of the specific methodology in two selected regions. Preparation Activity 6: Fostering pro-active support and participation in the project on the part of all stakeholders. This preparation activity will be linked to the overall communication strategy for the ABNJ Programme. An action plan for raising awareness of ABNJ deep sea fisheries and biodiversity conservation and enhancing communication, with a view to securing meaningful and constructive support and participation from all stakeholders will be prepared. The action plan is important for achieving the project’s stated results and transformational impacts. All linkages with IW-Learn will be specified. Preparation Activity 7: Feasibility analysis and budget preparation. PPG funding will be used to assess the feasibility of the project and to develop its detailed budget. This preparatory activity will cover: (i) detailed description of the baseline on deep sea fisheries and biodiversity conservation; (ii) incremental reasoning analysis and “GEF alternative” to address the gaps, threats and barriers identified and elaborated in baseline project(s); (iii) assessment of the social, economic and financial sustainability of proposed outputs and activities; (iv) quantification of tangible socioeconomic benefits with gender dimensions; (v) risk analysis; (vi) assessment of complementary/related initiatives and coordination strategies; (vii) replication strategy for project activities; (viii) monitoring and evaluation (M&E) plan and budget; (viii) financing plan, including co-financing commitments and incremental costs analysis; (ix) assessment of cost-effectiveness of project outputs and outcomes; (x) an initial set of ToRs for project inputs; (xi) IW and BD tracking tools; (xii) results framework elaborated with SMART indicators of success; (xiii) implementation arrangements, partnership strategies and capacities agreed and adequate for successful project implementation and sustainability - described in a separate annex on institutional and implementation arrangements; and (xiv) environmental screening completed (with FAO resources). The final outputs of the PPG will be the Project Document, CEO Endorsement Request, completed IW and BD tracking tools. |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| ### List of Proposed Project Preparation Activities | ### Output of the PPG Activities | Trust Fund | Grant Amount (a) | Co-financing (b) | Total c = a + b |
| 1.Stakeholders consultations and consensus building at regional and global levels | 1.1 Regional and global consultations held and broad agreements reached with competent authorities, industry partners and other stakeholders in DSF and associated BD conservation in the ABNJ on : i) work program and timetable for project preparation; ii) preliminary project results framework; iii) roles and responsibilities of stakeholders in project preparation, including needed technical and financial contributions; iv) specific criteria for selection of pilot activities under the project components agreed, including co-financing requirements; (v) agreement on pilot activities and sites; (vi) agreed institutional and implementation arrangements, including roles and responsibilities; (vii) draft project document endorsed by key stakeholders and feedback provided; and (viii) co-financing arrangements agreed. To the extent possible, these consultative events will be arranged to piggy back on/coincide with other regular meetings held by stakeholders. Not all stakeholders can be consulted meaningfully through these meetings, and one additional dedicated general stakeholders meeting will be necessary for achieving full consultation. The main outputs will be meeting and other reports describing the various agreements reached regarding the detailed design of the project. |  | 66,925 | 81,000 | 147,925 |
| 2. Review of relevant existing policy and legal frameworks as well as global and regional networks in the ABNJ, for the purpose of mainstreaming specific obligations about sustainable DSF and BD conservation, with focus on selected regions. | 2.1 Inventory of relevant policy and legal frameworks and instruments used by competent authorities in the ABNJ deep-seas. Inventory will include fisheries and biodiversity related legislation, policy and regulations, as well as of fishery and conservation institutions and programs relevant to deep-seas in the ABNJ. Although there is relevant baseline information available, most of it is in raw form and/or not collected and processed in manner that makes it immediately useful for project implementation. More practical information is necessary as well as adapting what is already available to specific deep-sea issues. 2.2 Initial identification of constraints and barriers to the implementation of relevant international policy and legal instruments for sustainable DSF and BD conservation, including the potential conflicts between user groups and recommendations for their resolution; 2.3 Overview of existing global and regional networks, and initial identification of where networks for DSF and BD conservation should be strengthened or created ; 2.4 Assessment of capacity needs for strengthening the policy and regulatory frameworks, networking and partnerships, on the part of the competent authorities, industry partners and other stakeholders in DSF and BD conservation. The focus of the analytical work at the regional level will be on the Indian Ocean, the SE Atlantic and the SE Pacific. Region-specific issues treated will be: (i) policies integrating EAF or marine biodiversity conservation and fisheries; (ii) networking arrangements between RFMOs, RSPs, coastal and flag states, fishing industry and scientific communities; and (iii) willingness of these stakeholders to participate in pilot activities. | GEF TF | 18,975 | 56,820 | 75,795 |
| 3 Review of relevant existing DSF management systems and tools in the ABNJ, for the purpose of mainstreaming BD issues into DSF management. | 3.1 Background documentation on DSF and associated BD, including: (i) inventory of biological, ecological and socio-economic information available; ii) overview of existing management measures and tools, for the purpose of reducing threats to and negative impacts on DSF and associated biodiversity, particularly in VMEs and EBSAs. (iii) overview of current management systems, identifying gaps, constraints and barriers with regards to DSF and initial recommendations for the future Focus will be on mainstreaming BD conservation into management practices, including monitoring of ecosystem status. 3.2 Assessment of capacity needs of stakeholders (technical, institutional and financial) for using management tools for: i) reducing threats to sustainable DSF and BD conservation, particularly concerning concepts and criteria for VMEs and EBSAs; and ii) planning and development of processes for achieving sustainable DSF and BD conservation, particularly allowing for adaptive changes. The assessment will include the identification of existing and potential incentives and disincentives for RFMOs, RSPs, coastal and flag states to adopt EAF addressing BD conservation into their management practices, as well as their capacity to sustain DSF and BD conservation work over the long term. Particular attention will be given to the three project’s focus areas (Indian Ocean, SE Atlantic and SE Pacific). |  | 45,350 | 56,820 | 102,170 |
| 4. Preparation of implementation plans for pilot activities | 4.1 Implementation plans, including workplans, cost tables/budgets, financing plans, institutional setup and arrangements, for the following pilot activities: i) development and testing of options for rights-based management systems and market-based incentives; ii) development of model policy and legal frameworks for sustainable DSF and BD Conservation; iii) identification of indicators for species and critical habitats for VMEs and EBSAs; (iv) improved fishing practices and management measures to reduce negative impacts on VMEs and EBSAs; (v) demonstration of adaptive management processes, including through participatory risk analysis; (vi) selection of objective-based fisheries management indicators and reference points (for target species, catch/bycatch composition, etc); and testing of a related monitoring programme; (vii) formulation and adoption of action plan for use of best MCS practices in one of the previously selected areas. 4.2 Development of selection criteria for at least ten developing countries to be supported for integrating best practices for sustainable DSF and BD conservation into their management processes. In particular, for each pilot activity, the spatial extent of the pilot area will be defined and relevant baseline data compiled. Distribution of the fisheries will be reviewed as well as existing and potential conflicts between resource users. Specific output and outcome indicators will be identified and agreed and a corresponding area-based, costed M&E plan formulated, linking to the project’s M&E and tracking tools. Significant parts of the time of the consultants involved in policy/legal matters, VMEs, EBSAs, and EAF, will be devoted to preparing an implementation plan for their respective pilot activities. |  | 95,350 | 75,000 | 170,350 |
| 5. Preparation for developing and testing a specific methodology for area-based planning in the ABNJ deep seas | 5.1 Inventory of available area-based management tools and instruments that may be used to develop a specific methodology for area-based management planning in the ABNJ deep seas 5.2 Workplan for developing the specific area-based management planning methodology; 5.3 Implementation plans (including work programs, cost tables, financing plans, institutional setup and arrangements) for testing this specific methodology in two selected regions. | GEF TF | 67,000 | 62,820 | 129,820 |
| 6. Fostering pro-active support and participation in the project on the part of all stakeholders | 6.1 Under the umbrella of the overall communication strategy of the ABNJ Program, a customized action plan will be prepared for raising awareness, enhancing communication, building support and participation in the present project, particularly among all decision-makers and other critical stakeholders. All relevant linkages with the overall communication strategy will be specified, including for IW Learn tools. |  | 0 | 33,740 | 33,740 |
| 7. Feasibility analysis and budget preparation | 7.1 Description of baseline initiatives, ongoing investments and financing sources. 7.2 Incremental reasoning in relation to the GEF investments, addressing gaps, threats and barriers identified in baseline initiatives and investments, in order to achieve global environmental benefits in sustainable management of deep sea fisheries and their ecosystems, including biodiversity conservation. 7.3 Detailed design of project components, including: a) description of component activities; b) output and outcome indicators and their baseline; c) financing plan and detailed budget by co-financier; and d) risk analysis, including mitigation measures for successful implementation. | GEF TF | 50,400 | 25,800 | 76,200 |
| Total Project Preparation Financing |  |  | 344,000 | 392,000 | 736,000 |

C.  Financing plan summary for project preparation grant: ($)

|  | Project Preparation | Agency Fee |
| --- | --- | --- |
| Grant Amount | 344,000 | 30,960 |
| Co-financing | 392,000 |  |
| Total | 736,000 | 30,960 |

D.  PPG  Amount requested by agency(ies), focal area(s) and country(ies) 1

| Trust Fund | GEF Agency | Focal Area | Country Name/ Global | (in $) |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | PPG (a) | Agency Fee (b) | Total c = a + b |
|  |  |  | Global | 131,819 | 11,864 | 143,683 |
|  | FAO |  | Global | 135,681 | 12,211 | 147,892 |
|  | UNEP | Biodiversity | Global | 76,500 | 6,885 | 83,385 |
|  |  |  |  |  |  | 0 |
|  |  |  |  |  |  | 0 |
|  |  |  |  |  |  | 0 |
|  |  |  |  |  |  | 0 |
|  |  |  |  |  |  | 0 |
|  |  |  |  |  |  | 0 |
|  |  |  |  |  |  | 0 |
|  |  |  |  |  |  | 0 |
|  |  |  |  |  |  | 0 |
| Total PPG Amount |  |  |  | 344,000 | 30,960 | 374,960 |

1 No need to provide information for this table if it is a single focal area, single country and single GEF Agency project.

E.   PPG Budget

| ### Cost Items | ### Total Estimated Person Weeks for Grant (PW) | ### Grant Amount ($) | ### Co-financing ($) | ### Total($) |
| --- | --- | --- | --- | --- |
| ### Local consultants * |  |  |  |  |
| ### International consultants* | 61 | 165,750 | 59,400 | 225,150 |
| Travel |  | 61,000 | 102,000 | 163,000 |
| Staff time |  |  | 98,600 | 98,600 |
| Workshops |  | 117,250 | 102,000 | 219,250 |
| Baseline compilation(Studies) |  |  | 30,000 | 30,000 |
| Total PPG Budget |  | 344,000 | 392,000 | 736,000 |

* Annex A for Consultant cost details should be prepared first before completing this table.  See notes on Annex A for the 
     required detailed information.  This table is the sum of all local and international consultants presented in Annex A.

F.   GEF Agency(ies) Certification

This request has been prepared in accordance with GEF policies and procedures and meets the GEF LDCF/SCCF/NPIF Trust Fund criteria for project identification and preparation.

| Agency Coordinator, Agency Name | Signature | Date (Month, day, year) | Project Contact Person | Telephone | Email Address |
| --- | --- | --- | --- | --- | --- |
| Laurent Thomas Officer-in-Charge Investment Centre Division Technical Cooperation Department FAO TCI-Director@fao.org Barbara Cooney FAO GEF Coordinator Email: Barbara.Cooney@fao.org Tel: +3906 5705 5478 |  | December 28, 2012 | Merete Tandstad | +3906 57052019 | Merete.Tandstad@fao.org |
| Maryam Niamir-Fuller Executive Coordinator GEF Coordination Office UNEP |  |  | Mohamed Sessay | +2542076224294 | Mohamed.Sessay@unep.org |

Annex A

Consultants Financed by the Project Preparation Grant (PPG)

| Type of Consultant | Position / Titles | $/ Person Week1 | Estimated PWs2 | Tasks to be Performed |
| --- | --- | --- | --- | --- |
|  | Team Leader (with practical experience in project formulation as well as institutional and implementation arrangements) | 3000 | 18 | The consultant will act as the Team Leader responsible for the general carrying out of the project preparation activities as well as the overall preparation of the Project Document and CEO Endorsement Request, in close consultation with FAO, UNEP, the executing partners and other stakeholders Specifically, the Team Leader, will : (i) organize/supervise the carrying out of the preparation activities, based on the work program and time table agreed, and in accordance with the approved PIF and PPG; (ii) organize and lead the discussions in consultative workshops and meetings; (iii) liaise with other organizations and projects to ensure consistency and linkages with ongoing and planned activities related to DSF management and BD conservation in the ABNJ; (iv) ensure that the project documentation produced is results-oriented and reflects agreements reached during project preparation; (v) develop the baseline description, incremental reasoning an rationale for GEF financing; (vi) formulate and describe in project document all institutional and implementation arrangements, including for pilot activities; (vii) prepare the Project Results Framework, M&E Plan and costing; (viii) in collaboration with other team members, consolidate the formulation of tracking tools for IW and BD; (ix) finalize the project’s cost tables and financing plan with the financial analyst; and (x) evaluate the socio-economic and gender impacts of the project. |
| International | Policy and Legal Specialist | 2500 | 5 | The main task of the Policy and Legal Specialist will be to provide general guidance and support to the Project Preparation Team Leader and other team members, on all policy and legal aspects related to ABNJ deep-sea fisheries and biodiversity conservation in the context of project preparation. Specifically, the specialist will carry out the following tasks: (i) prepare an inventory of all relevant policies, legislation and institutional arrangements for deep-sea fisheries and biodiversity conservation in the ABNJ, with particular focus on the pilot areas covered by the project (Project Components 1 and 3); (ii) identify constraints and barriers to the implementation of international policy and legal instruments for sustainable deep-sea fisheries management and biodiversity conservation at the national and regional levels, iii) in close collaboration with partners, prepare the design of the pilot activity related to the development of model-policy and legal frameworks. (iv) in close collaboration with the other team members and all relevant stakeholders, prepare the eligibility and selection criteria for the participation of competent authorities and industry partners in the project pilot activities (Project Components 1, 2 and 3). |
| International | VME/EBSA Specialist | 2750 | 9 | In close collaboration with the Project Preparation Team Leader and other team members, the VME/EBSA Specialist will be responsible for the preparation of the parts of Project Component 2 related to VMEs and EBSAs, that also include interactive web databases on VMEs and EBSAs and the demonstration of internationally-agreed VME and EBSA criteria. The specialist will also provide technical support to other team members responsible for Project Components 1 and 3. In addition, the specialist will carry out the following tasks: (i) prepare a consolidated inventory of available ecological, environmental and socio economic information on baselines from deep-sea-RFMOs, regional seas organizations, selected developing member countries and others; (ii) contribute to, first, the identification of stakeholders for the VME and EBSA processes globally as well as for the pilot areas, and, second, to the industry engagement process to provide information and collaboration on VMEs and EBSAs; (iii) conduct a capacity building needs assessment and identify priorities with regards to the VME and EBSA processes and the VME database/EBSA repository, to ensure countries' effective contribution and engagement in the project, (iv) prepare an overview of existing management measures and tools for reducing threats to DSF and BD, particularly VMEs and EBSAs (v) in close collaboration with partners, prepare the design of two pilot activities: development of indicators for species and critical habitats in the context of VMEs and EBSAs, and demonstration of improved fishing practices and management measures to reduce impacts on VMEs and EBSAs; (vi) prepare the relevant tracking tools for IW and BD |
| International | Ecosystem Approach to Fisheries (EAF) Specialist | 2750 | 8 | In close collaboration with the Team Leader and other team members, the EAF Specialist will be responsible for the preparation of the parts of Project Component 3 related to EAF issues, including reaching agreement with the fishing industry on their involvement in the practical implementation of the work program. The specialist will also provide technical support to other team members responsible for Project Components 1 and 2. In addition, the specialist will carry out the following tasks: (i) prepare an overview of current management systems, identifying gaps, constraints and barriers with regards to DSF, including a scoping analysis related to adopting EAF processes at national and regional levels for deep-sea fisheries and integration of biodiversity consideration into regular management planning processes and identification of key stakeholder groups in pilot area; (ii) in close collaboration with partners, prepare the design of two pilot activities: (a) demonstration of adaptive management processes, selection of objectives-based indicators and reference points; and (b) testing of a related monitoring program, (iv) carry out an initial identification of constraints and barriers to create, strengthen and expand global and regional networks for achieving sustainable DSF and BD conservation and coordinate the assessment of capacity needs for networking and partnerships. |
| International | RBM Specialist | 2500 | 4 | The RBM Specialist will review the existing RBM and trade-related systems (including traceability-types) and practices in deep-sea RFMOs; and evaluate their scope, functioning and cost-effectiveness as well as the potential for scaling up and integration with relevant global instruments. In close collaboration with partners, the specialist will prepare the design of the pilot activity concerning the development of options for RBM-based systems and market-based incentives. S/he will also formulate the relevant tracking tools for IW and BD. |
| International | MCS Specialist | 2500 | 3 | The MCS Specialist will review the existing MCS systems and practices in deep-sea RFMOs; and evaluate their scope, functioning and cost-effectiveness as well as the potential for scaling up and integration with relevant global instruments. In close collaboration with partners, the specialist will prepare the design of the pilot activity concerning the formulation ad adoption of an action plan for use of best MCS practices in one of the selected pilot areas. S/he will also formulate the relevant tracking tools for IW and BD. |
| International | Area-based management expert | 2500 | 8 | The consultant will: (i) collect information on the available area-based management tools and instruments that may be used to develop a specific methodology for area-based management planning in the ABNJ deep seas; (ii) formulate a workplan for developing this specific methodology; and (iii) in coordination with relevant stakeholders, prepare an implementation plan for testing this methodology in two selected regions. |
| International | Communications Expert | 2000 | 2 (covered through co-financing) | The Communications Expert will produce a Public Awareness and Communication Action Plan for DSF development and related biodiversity conservation, addressing all specific issues relevant to the various stakeholder groups as identified in close collaboration with the FAO, UNEP and the Project Preparation Team. The strategy will become an integral part of the overall ABNJ Program Communication Strategy. The expert will also produce the communication materials (audio-visual, in print, etc.) supporting the ABNJ Program Communication Strategy as it relates to deep seas as well as a draft implementation plan. |
| International | Financial Analyst | 2500 | 6 | The Financial Analyst, under the supervision of the Team Leader, will prepare the project budget to include: (i) collection and compilation of the project costs information in COSTAB format; (ii) the results budget and FAO-GEF Oracle/FPMIS Budget; (iii) the project financing plan, including co-financing commitments and the incremental costs analysis; and (iv) an assessment of the cost-effectiveness of the project’s outputs and outcomes. |

1 Provide dollar amount per person-week.

2  Provide person weeks needed to carry out the task

Annex B