request for  CEO ENDORSEMENT

Project Type:

Type of Trust Fund:

For more information about GEF, visit TheGEF.org

part i: project information

| Project Title: GEF SGP Fifth Operational Phase--implementing the program using STAR resources II |  |  |  |
| --- | --- | --- | --- |
| Country(ies): | 69 countries | GEF Project ID: | 4678 |
| GEF Agency(ies): |  | GEF Agency Project ID: | 4561 |
| Other Executing Partner(s): | UNOPS | Submission Date: | April 25 2013 |
| GEF Focal Area (s): |  | Project Duration(Months) | 48 months |
| Name of Parent Program (if applicable): - For SFM/REDD+ - For SGP - For PPP | GEF Small Grants Programme | Project Agency Fee ($): | $ 2,950,589 |

- Focal Area Strategy framework

| ### Focal Area Objectives | ### Expected FA Outcomes | ### Expected FA Outputs | ### Trust Fund | ### Indicative ### Grant Amount ### ($) | ### Indicative Co-financing ### ($) |
| --- | --- | --- | --- | --- | --- |
|  | 1.1 | 1.1; 1.2 |  | 9,058,899 | 9,398,000 |
|  | 2.1 | 2.3 |  | 9,058,899 | 9,398,000 |
|  | 1.1 | 1.1 |  | 5,639,608 | 5,886,000 |
|  | 4.2 | 4.2; 4.3 |  | 5,639,608 | 5,886,000 |
|  | 5.1 | 5.2 |  | 5,639,608 | 5,886,000 |
|  | 1.3 | 1.2; 1.3; 1.5 |  | 5,795,030 | 6,053,000 |
|  | 3.2 | 3.2; 3.4 |  | 5,795,031 | 6,053,000 |
|  | 1.1 | 1.3 |  | 3,330,478 | 3,500,000 |
|  | 2.1 | 2.3 |  | 3,330,478 | 3,500,000 |
|  | 1.1 | 1.1.1 |  | 6,660,955 | 7,000,000 |
| CD-2 | 2.2 | 2.2.1; 2.2.2 |  | 3,330,478 | 3,500,000 |
|  | 5.1 | 5.4; 5.5 |  | 3,330,478 | 3,500,000 |
| Others |  |  |  |  |  |
| Sub-Total |  |  |  | 66,609,550 | 69,560,000 |
| Project Management Cost |  |  |  | 7,155,179 | 7,156,000 |
| Total Project Cost |  |  |  | 73,764,729 | 76,716,000 |

- Project Framework

| ### Project Objective: Global Environmental Benefits secured through community-based initiatives and actions |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| ### Project Component | ### Grant Type | ### Expected Outcomes | ### Expected Outputs | ### Trust Fund | ### Grant Amount ($) | ### Confirmed Cofinancing ### ($) |
| Conservation of Globally Significant Biodiversity Through Community-based Initiatives and Actions |  | 1. Improved sustainability of protected areas and indigenous and community conservation areas through community-based actions 2. Mainstreamed biodiversity conservation and sustainable use in production landscapes, seascapes and sectors through community initiatives and actions | At least 181 community and civil-society based projects funded supporting biodiversity conservation in indigenous and community conservation areas At least 181 community and civil-society based projects funded supporting biodiversity conservation through mainstreaming |  | 18,117,798 | 18,796,000 |
| Reduction or Avoidance of GHG Emissions While Building Climate Resilience at the Community-level |  | 3. Demonstration, development and transfer of low-GHG technologies at the community level 4. Increased energy efficient, low-GHG transport at the community level 5. Conservation and enhancement of carbon stocks through sustainable management and climate proofing of land use, land use change and forestry | At least 113 community and civil-society based projects funded supporting the transfer of low-carbon technologies At least 113 community and civil-society based projects funded supporting low-GHG transport At least 113 community and civil-society based projects funded supporting conservation and enhancement of carbon stocks |  | 16,918,824 | 17,658,000 |
| Reverse and Prevent Desertification/Land Degradation and Mitigate the Effects of Drought in Affected Areas Through Community-based Initiatives and Actions |  | 6. Maintenance or improvement in flow of agro-ecosystem and forest ecosystem services to sustain livelihoods of local communities 7. Reduction of pressures at community level from competing land uses (in the wider landscapes) | At least 116 community and civil-society based projects funded supporting maintenance or improvement of flow of ecosystem services At least 116 community and civil-society based projects funded supporting reduction of pressures from competing land uses |  | 11,590,062 | 12,106,000 |
| Sustainable Management of Transboundary Water Bodies at the Community-level |  | 8. Communities support the implementation of Strategic Action Programmes (SAPs) in trans-boundary surface and groundwater basins; 9.Communities support the implementation of Strategic Action Programmes (SAPs) in large marine ecosystems management | At least 66 community and civil-society based projects funded supporting community initiatives for sustainable management of transboundary surface and groundwater basins; At least 66 community and civil-society based projects funded supporting community initiatives for sustainable management of large marine ecosystems management |  | 6,660,956 | 7,000,000 |
| Reduce and Eliminate the Release of Harmful Chemicals into the Environment Through Community-based Initiatives and Actions |  | 10. Phase out of POPs and chemicals of global concern at community level | At least 133 community and civil-society based projects funded supporting the phase out of POPs and chemicals of global concern |  | 6,660,955 | 7,000,000 |
| Enhance communities and CSOs’ capacity to diagnose, understand and transform complex dynamic nature of global environmental problems and develop local solutions focusing on biodiversity, climate change and land degradation, while also covering international waters and chemicals |  | 11. Communities and CSOs are better informed via global, national and local knowledge sharing/learning, workshops and trainingsabout global challenges and local actions required 12. Ability of communities and CSOs to diagnose, understand and transform information and knowledge into local actions increased and retained | At least 666 communities and CSOs involved in knowledge sharing/learning, workhops and training with increased understanding of global environmental challenges; At least 666 communities and CSOs will have increased capacity to develop local solutions to global environmental challenges |  | 6,660,955 | 7,000,000 |
| Subtotal |  |  |  |  | 66,609,550 | 69,560,000 |
| Project management Cost (PMC) |  |  |  |  | 7,155,179 | 7,156,000 |
| Total project costs |  |  |  |  | 73,764,729 | 76,716,000 |

- sources of confirmed Cofinancing for the project by source and by name ($)

Please include letters confirming cofinancing for the project with this form

| Sources of Co-financing | Name of Co-financier (source) | Type of Cofinancing | Cofinancing Amount ($) |
| --- | --- | --- | --- |
|  | Multiple |  | 13,000,000 |
|  | Multiple |  | 2,000,000 |
| (UNDP) | UNDP | Grant | 3,000,000 |
|  | Multiple |  | 7,000,000 |
|  | Multiple |  | 13,000,000 |
|  | Multiple |  | 31,716,000 |
|  | Multiple |  | 4,000,000 |
|  | Multiple |  | 3,000,000 |
|  | Multiple |  |  |
| Total Co-financing |  |  | 76,716,000 |

- trust fund Resources Requested by agency, Focal Area  and country1

| GEF Agency | Type of Trust Fund | Focal Area | Country Name/ Global | (in $) |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | Grant Amount (a) | Agency Fee (b)2 | Total c=a+b |
|  |  |  | Global (STAR 2nd Tranche) | $73,764,729 | $ 2,950,589 | $76,715,318 |
|  |  |  |  |  |  | 0 |
|  |  |  |  |  |  | 0 |
|  |  |  |  |  |  | 0 |
|  |  |  |  |  |  | 0 |
|  |  |  |  |  |  | 0 |
|  |  |  |  |  |  | 0 |
|  |  |  |  |  |  | 0 |
|  |  |  |  |  |  | 0 |
|  |  |  |  |  |  | 0 |
| Total Grant Resources |  |  |  | $73,764,729 | $ 2,950,589 | $76,715,318 |

1  In case of a single focal area, single country, single GEF Agency project, and single trust fund project, no need to provide information for this
    table.  PMC amount from Table B should be included proportionately to the focal area amount in this table.

2   Indicate fees related to this project.

- Consultants working for technical assistance components:

| ### Component | ### Grant Amount ($) | ### Cofinancing ($) | ### Project Total ($) |
| --- | --- | --- | --- |
| ### International Consultants |  |  | 0 |
| ### National/Local Consultants |  |  | 0 |

- Does the project include a “non-grant” instrument?

(If non-grant instruments are used, provide in Annex D an indicative calendar of expected reflows to your Agency 
       and to the GEF/LDCF/SCCF/NPIF Trust Fund).

part ii:  project justification

A. describe any changes in alignment with the project design of the original pif

A.1 National strategies and plans or reports and assessments under relevant conventions, if applicable, i.e. NAPAS, NAPs, NBSAPs, national communications, TNAs, NCSA, NIPs, PRSPs, NPFE, Biennial Update Reports, etc.

The primary mechanism by which the GEF Small Grants programme incorporates national strategies and plans is through the development of a Country Program Strategy (CPS) in each programme country.  The development of the CPS is facilitated by the SGP country team with support and eventually the endorsement of the SGP National Steering Committee (NSC), and shared with the GEF Operational Focal Point and the relevant Convention focal points.  This document considers and integrates the relevant data from NBSAPs, NIPs, and other national communications to the conventions plus results from NCSAs. The CPS is also linked to the country’s GEF STAR resources allocation strategy, which in turn reflects GEF policies and strategic priorities for GEF-5.  The CPS is a living document that is updated as needed to reflect the most recent changes in national policies, strategies and action plans.  SGP country programmes contribute to the NPFEs where relevant, to the update of NBSAPs and NAPAs and take on additional strategic roles identified by the resulting strategies and plans of action. National priorities are also reflected through the constitution of the NSC (or National Focal Group for sub-regional programmes), which guides implementation of the SGP in each respective country.  NSC members are leading national government and civil society representatives in the environmental field, who provide strategic guidance and oversight for the programme, and ensure its focus on and coherence with national priorities as they apply to and are relevant for community-level needs and priorities.

Total funding request (inclusive of agency fee) has been increased from the original PIF requested amount by $2,619,200.  These changes resulted from receipt of new or revised endorsement letters from the following countries (Sierra Leone: $629,200; Suriname: $710,000; Uzbekistan: $480,000; and Vietnam: $1,000,000), as well as the reduction of endorsed amount from Armenia by $200,000.  The CPS in these countries have been developed or revised to support the implementation of national priorities in combination with GEF objectives.

A.2. GEF focal area and/or fund(s) strategies, eligibility criteria and priorities. No change has occurred in GEF focal area strategies, eligibilities and priorities since the approval of PIF.  SGP is in alignment with GEF focal area strategies, eligibility criteria and priorities in the biodiversity, climate change, land degradation areas as shown in Annex A to this document. As per SGP policy to promote synergies between and among focal areas, up to 10% of the STAR focal areas allocation may be used to fund projects in international waters, chemicals and capacity development respectively.

A.3 The GEF Agency’s comparative advantage: No changes from the PIF.  UNDP remains the most suitable agency for the implementation of SGP because of its capacity development focus, country presence and the coordination role among UN agencies at the country level.

A.4. The baseline project and the problem that it seeks to address:  No changes from the PIF.  The project seeks to address the problems as described in PIF mainly covering climate change, biodiversity and land degradation.

A. 5. Incremental /Additional cost reasoning:  describe the incremental (GEF Trust Fund/NPIF) or additional (LDCF/SCCF) activities  requested for GEF/LDCF/SCCF/NPIF  financing and the associated global environmental benefits  (GEF Trust Fund) or associated adaptation benefits (LDCF/SCCF) to be delivered by the project:   No change from the PIF.

A.6  Risks, including climate change, potential social and environmental risks that might prevent the project objectives from being achieved, and measures that address these risks: No change from PIF.  SGP will undertake measures to mitigage and prevent the risks outlined in the PIF.

A.7. Coordination with other relevant GEF financed initiatives: No changes from the PIF.  SGP will work and coordinate with GEF full-sized projects.  It will also seek to act as a delivery mechanism where appropriate for relevant full-sized projects.

B. additional information not addressed at Pif stage:

B.1 Describe how the stakeholders will be engaged in project implementation.

SGP operates through a multi-stakeholder approach engaging a range of stakeholders including NGOs, CBOs, indigenous people, the private sector, government, academia, and donor partners.  SGP country programs’ decision making body is the National Steering Committee, which is composed of government agencies, civil society leaders, research institutes, donors and private sectors.  Such a multi-stakeholder committee plays a critical role in the entire program cycle of SGP, including strategy development, grant review and approval, as well as promoting policy influence, networking, and partnership development.  During project implementation, a broad range of stakeholders are engaged as active partners during grant implementation, including inter alia research institutes, local and municipal governments, international NGOs, as well as national and international volunteers. Such multi-stakeholder cooperation is sometimes formalized through legal agreements, and often is undertaken informally through provision of technical assistance, parallel co-financing, information sharing, knowledge dissemination, networking as well as replication and upscaling.

With regard to indigenous peoples and marginalized populations, SGP follows a set of principles that advocate for a flexible, time sensitive, and simple project cycle in order to allow these "difficult to reach" groups to access SGP support. The programme has pioneered numerous user-friendly modalities to work with poor and marginalized groups including alternative proposal formats such as participatory video, photo stories, and community theatre, and allowances are made for concept and project submission in local and vernacular languages. SGP also allows for flexible disbursement terms to cope with indigenous peoples’ culture, customs and seasonal movements. Through stakeholders’ workshops organized by SGP, CSOs are able to learn of SGP projects and activities and provide inputs on how to improve on them.

B.2 Describe the socioeconomic benefits to be delivered by the Project at the national and local levels, including consideration of gender dimensions, and how these will support the achievement of global environment benefits (GEF Trust Fund/NPIF) or adaptation benefits (LDCF/SCCF):

The communities targeted by SGP are often the poorest and most vulnerable, and typically have low levels of technical and institutional capacity to adequately address global environmental problems.  According to the Joint Evaluation (2008), more than 60% of SGP grants target poor communities in participating countries, which have the greatest need for assistance. Indigenous peoples, who have the knowledge and experience to create sustainable solutions to environmental challenges, are also targeted by at least 15% of SGP grants.  Approximately a quarter of SGP grants specifically support women, who constitute another priority target group.  SGP helps utilize the full potential of women and men and transform marginal and vulnerable sectors into active actors for sustainable development.  The third independent evaluation report of SGP noted:

Access to and acceptance by communities - the GEF/SGP’s principal clients - almost invariably requires an emphasis on activities which communities perceive are closely linked to their own immediate concerns, a characteristic by no means limited to poorer countries. Ask a low-income rural community in the developing world what their priority problems are, and the answer is unlikely to feature biodiversity or climate change. Few, if any, communities begin with an understanding or awareness of these terms.

SGP works to develop sustainable livelihoods, including through the creation and support for small and medium enterprises at the community level that contribute to sustainable resource use, generate local benefits from environmental conservation measures, and promote innovative and entrepreneurial approaches to critical problems such as energy conservation and generation.  Thus, where poverty once forced communities to take a short-term view and an exploitatively opportunistic approach to natural resource utilization, the realization of livelihoods and enterprises linked to natural resources creates a desire for a long term view and careful resource management. In SGP communities, sustainable livelihoods and enterprises create the capacity and also provide additional resources for environmental protection. Thus, a key factor in the success of SGP projects is the linkage of the generation of socioeconomic benefits with the generation of global environmental benefits, which can be achieved in many different and creative ways depending on the specific issue targeted.

SGP will continue to apply its gender mainstreaming approach, ensuring that priority is given to women led projects and those with high participation of women, and gender specific components.  SGP makes efforts to seek gender disaggregated information to the extent possible about project beneficiaries and participants.  The National Steering Committees of SGP in each country are curently being strengthened to ensure designation of a gender focal point on each NSC to track grant making towards women focused projects.

B.3. Explain how cost-effectiveness is reflected in the project design: As noted by the Joint Evaluation of the SGP in 2007, "GEF SGP is a cost-effective instrument for the GEF to generate global environmental benefits through NGOs and community-based organizations" (Joint Evaluation 2007, pp. 46), and "The efficiency of outcome ratings for the GEF SGP grants appear to be better than those for the FSPs and MSPs” (Joint Evaluation 2007, pp. 50). Furthermore, the GEF Council paper (GEF/C.33/5, p. 1) "Small Grants Program: Follow up to the 2007 Joint Evaluation" recommended a "level of management costs on the basis of services rendered and cost efficiency rather than a set percentage". The principle of determining SGP management costs on the basis of services rendered was recently reconfirmed by the GEF Secretariat and UNDP in GEF5. Among the services provided by SGP which go beyond simply grant administration, are notably its focus on capacity building of grantees (working with some of the poorest and low capacity groups who are at the same time more vulnerable to environmental challenges), strengthening networking of civil society organizations, learning and knowledge management, partnership building and resource mobilization with a view to scaling up and strengthening sustainability of projects. In addition, SGP will further enhance the programme’s and grant projects’ cost efficiency by actively exploring opportunities to: 1) be utilized as delivery mechanism for community/NGO components of FSPs – whereby it would have a share of additional management budgets while providing an on-the-ground mechanism to deliver a greater volume of grants; 2) raise additional co-financing from non-GEF sources in ways that management costs are defrayed. At the project level, GEF SGP will engage voluntary NSC members to provide technical and management assistance to communities, obtain local governments and other partners’ co-financing and support, ensure linkages and synergies with other ongoing activities and other proper activities to further improve projects’ cost effectiveness.

C.  describe the budgeted m &e plan:  SGP’s M&E plan is designed and developed to address how SGP will meet all reporting requirements, which also contribute to and support SGP’s knowledge management approach and activities that emphasize the importance of effective sharing of lessons and good practices to consistently strengthen and improve SGP’s contribution to the generation of Global Environmental Benefits.  As appropriate, M&E reports and information within SGP countries will be shared with national GEF focal points and convention focal points, which can then be incorporated in national convention reporting.  All M&E activities outlined in the M&E plan will be undertaken as necessary and appropriate to ensure cost-effectiveness, with M&E carried out as appropriate relative to the size of any given project and other associated factors such as complexity and risks involved.  SGP includes a robust monitoring and evaluation system fully in-line with GEF and UNDP monitoring and evaluation policies and minimum standards, including consistency with UN Evaluation Group standards and norms. The SGP monitoring and evaluation plan complies with all GEF M&E minimum standards, including: SMART indicators for implementation and results, baseline information, identification of required programme reviews and evaluations, specified roles and responsibilities, and a budget allocated to support M&E activities.  The SGP M&E Plan is attached as Annex F to this template.

SGP's enhanced approach to M&E during OP5 covers multiple fronts.  The strategic objectives for SGP in OP5 include specific outcomes on M&E within the framework of capacity development, including enhancing SGP stakeholders and partners capacity to apply M&E methodologies and tools.  At the global level, SGP will continue to improve the SGP database, and facilitate the tracking of outcomes across the portfolio. The SGP Results Framework is attached as Annex A to this document.  The indicators identified in this results framework are the global level indicators designed to meet reporting on GEF-5 strategic objectives.  At the country and project levels appropriate additional focal area specific results-oriented indicators are applied to ensure projects achieve expected results, and to track successful approaches, including socio-economic outcomes where possible.  To support results reporting linked to the GEF-5 results framework, SGP will continue to improve indicators and mechanisms for reporting on results.  Further revision and development of results indicators may include capacity development indicators, as appropriate.  SGP recognizes the importance of identifying and documenting results beyond the output level, and will undertake approaches to move current reporting further down the results chain, toward documentation of impact.  M&E activities will include partnerships with relevant organizations and stakeholders that can positively contribute to SGP’s work in this area.

PART iII: Approval/endorsement by gef operational focal point(s) and gef agency(ies)

- Record of Endorsement of GEF Operational Focal Point(s) on Behalf of the Government(s): ): (Please attach the Operational Focal Point endorsement letter(s) with this form. For SGP, use this OFP endorsement letter).

Please refer to complete list of endorsements provided in Annex 1

| Name | Position | Ministry | Date (MM/dd/yyyy) |
| --- | --- | --- | --- |

B.  GEF agency(ies) certification

This request has been prepared in accordance with GEF/LDCF/SCCF/NPIF policies and procedures and meets the GEF/LDCF/SCCF/NPIF criteria for CEO endorsement/approval of project.

| Agency Coordinator, Agency Name | Signature | Date (Month, day, year) | Project Contact Person | Telephone | Email Address |
| --- | --- | --- | --- | --- | --- |
| Adriana Dinu, UNDP GEF OIC and Deputy Executive Coordinator |  | April 25, 2013 | Delfin Ganapin | 646-781-4383 | delfin.ganapin@undp.org |

ANNEX A:  PROJECT RESULTS FRAMEWORK (either copy and paste here the framework from the Agency document, or provide reference to the page in the project document where the framework could be found).

| SGP OP5 Objectives | SGP OP5 Outcomes | SGP OP5 Results Indicators | OP5 Target | Sources of Verification | Assumptions |
| --- | --- | --- | --- | --- | --- |
| SGP OP5 Immediate Objective 1: Improve sustainability of protected areas and indigenous and community conservation areas through community-based actions | SGP BD Outcome 1.1: Improved community-level actions and practices, and reduced negative impacts on biodiversity resources in and around protected areas, and indigenous and community conservation areas Category II Step-up: Good practices replicated and scaled up outside SGP supported areas, as appropriate SGP BD Outcome 1.2: Benefits generated at the community level from conservation of biodiversity in and around protected areas and indigenous and community conservation areas Category II Step-up: Sustainable financial mechanisms for benefit generation identified and piloted, as appropriate SGP BD Outcome 1.3: Increased recognition and integration of indigenous and community conservation areas in national protected area systems Category II Step-up: Information about recognition of indigenous and community conservation areas within national level protected area systems shared through an established network, as appropriate SGP BD Outcome 1.4: Increased understanding and awareness at the community-level of the importance and value of biodiversity Category II Step-up: Environmental education programs formally integrated in school curricula, as appropriate | Number and hectares of ICCAs and other PAs positively influenced through SGP support Number of community members with improved livelihoods related to benefits from protected areas Number of significant species with maintained or improved conservation status Number and hectares of significant ecosystems with maintained or improved conservation status Number of communities with increased understanding and awareness | 240 ICCAs and PAs positively influenced through SGP. Support 6,800,000 hectares of ICCAs and PAs positively influenced through SGP support 99,000 community members with improved livelihoods related to benefits from ICCAs and PAs 250 significant species benefited 130 significant ecosystems with conservation aware communities resulting in their maintained or improved conservation status 120,000 hectares of significant ecosystems with maintained or improved conservation status More than 360 communities with increased understanding and awareness | GEF SGP database, project reports and monitoring visits SGP case studies SGP grantee data from innovative monitoring approaches | Governments and international agencies commit to CBD obligations regarding local and indigenous populations |
| SGP OP5 Immediate Objective 2: Mainstream biodiversity conservation and sustainable use into production landscapes, seascapes and sectors through community initiatives and actions | SGP BD Outcome 2.1: Improved community-level sustainable use of biodiversity in production landscapes / seascapes through community-based initiatives, frameworks and market mechanisms, including recognized environmental standards that incorporate biodiversity considerations Category II Step-up: Market mechanisms and standards replicated and scaled-up, as appropriate SGP BD Outcome 2.2: Increased understanding and awareness of sustainable use of biodiversity Category II Step-up: Environmental education programs formally integrated in school curricula, as appropriate | Hectares of production landscapes / seascapes under improved sustainable use practices, leading, where possible, to certification through recognized environmental standards that incorporate biodiversity considerations (supported by SGP) Number of significant species with maintained or improved conservation status Number and hectares of significant ecosystems with maintained or improved conservation status | 120,000 hectares of production landscapes / seascapes under improved sustainable use practices, leading, where possible, to certification through recognized environmental standards that incorporate biodiversity considerations (supported by SGP) 250 significant species with maintained or improved conservation status 130 significant ecosystems with communities adopting sustainable use resulting in maintained or improved conservation status 120,000 hectares of significant ecosystems with maintained or improved conservation status | GEF SGP database, project reports and monitoring visits | Market differentiation of value-added labels sufficiently “scale-sensitive” to meet the needs of small producers |
| SGP OP5 Immediate Objective 3: Promote the demonstration, development and transfer of low carbon technologies at the community level | SGP CC Outcome 3.1: Innovative low-GHG technologies deployed and successfully demonstrated at the community level Category II Step-up: Up-scaling and replication of good practices and lessons, as appropriate SGP CC Outcome 3.2: GHG emissions avoided | Number of countries with demonstrations addressing community-level barriers to deployment of low-GHG technologies Number of national or international partners or agencies are aware of SGP practices and lessons | 56 countries with demonstrations addressing community-level barriers to deployment of low-GHG technologies At least 50 national or international partners or agencies are aware of SGP practices and lessons | GEF SGP database, project reports and monitoring visits SGP case studies | Progress will continue for complimentary initiatives by GEF and other development agencies to removing market barriers and improving energy access policies particularly at the local level. |
| SGP OP5 Immediate Objective 4: Promote and support energy efficient, low carbon transport at the community level | SGP CC Outcome 4.1: Low-GHG transport options demonstrated at the community level Category II Step-up: Up-scaling and replication of good practices and lessons, as appropriate SGP CC Outcome 4.2: Increased investment in community-level energy efficient, low-GHG transport systems SGP CC Outcome 4.3: GHG emissions avoided | Number of countries where community-level low-GHG transport options have been demonstrated Number of governments having been influenced by SGP demonstration practices | 25 countries with community-level low-GHG transportation demonstrations At least 10 governments (local or national) having been influenced in policy development and implementation | GEF SGP database, project reports and monitoring visits SGP case studies | Progress will continue for complimentary initiatives by GEF and other development agencies to removing market barriers and improving policies supporting low-GHG transportation, particularly at the local level. |
| SGP OP5 Immediate Objective 5: Support the conservation and enhancement of carbon stocks through sustainable management and climate proofing of land use, land use change and forestry | SGP CC Outcome 5.1: Sustainable land use, land use change, and forestry management and climate proofing practices adopted at the community level for forest and non-forest land-use types Category II Step-up: Up-scaling and replication of good practices and lessons, as appropriate SGP CC Outcome 5.2: Restoration and enhancement of carbon stocks in forests and non-forest lands, including peatland Category II Step-up: Up-scaling and replication of good practices and lessons, as appropriate SGP CC Outcome 5.3: GHG emissions avoided | Hectares under improved sustainable land management and climate proofing practices Hectares of forests and non-forest lands with restoration and enhancement initiated | 55,000 hectares under improved sustainable land management and climate proofing practices Restoration and enhancement of 25,000 hectares of forests and non-forest lands initiated | GEF SGP database, project reports and monitoring visits SGP case studies | Change is possible on the ground at the community level whether or not national and international policy measures are in place |
| SGP OP5 Immediate Objective 6: Maintain or improve flow of agro-ecosystem and forest ecosystem services to sustain livelihoods of local communities | SGP LD Outcome 6.1: Improved community-level actions and practices, and reduced negative impacts on agro-, and forest ecosystems and ecosystem services demonstrated to sustain ecosystem functionality Category II Step-up: Analysis of economic value of ecosystem services in target areas, as appropriate SGP LD Outcome 6.2: Community-based models of sustainable forestry management developed, and tested, linked to carbon sequestration for possible upscaling and replication where appropriate, to reduce GHG emissions from deforestation and forest degradation and enhance carbon sinks from land use, land use change, and forestry activities Category II Step-up: Up-scaling and replication of good practices and lessons, as appropriate | Hectares under improved agricultural, land and water management practices (by management practice) Number of national and international agencies or partners are aware of successful SGP demonstrations and innovative approaches Number of national/local governments or international policy making processes with SGP influence | 55,000 hectares under improved agricultural, land and water management practices (by management practice) At least 50 national or international agencies/partners have learned of SGP demonstrations and innovative approaches At least 5 policy-making bodies (governments or international agencies) having been influenced by successful SGP demonstration practices | GEF SGP database, project reports and monitoring visits SGP case studies | Government policy is in place and supportive of community-level sustainable land management practices |
| SGP OP5 Immediate Objective 7: Reduce pressures at community level from competing land uses (in the wider landscapes) | SGP LD Outcome 7.1: Improved community-level actions and practices, and reduced negative impacts in land use frontiers of agro-ecosystems and forest ecosystems (rural/urban, agriculture/forest) Category II Step-up: Partnerships with private sector, as appropriate | Number of community members with improved actions and practices that reduce negative impacts on land uses | At least 30,000community members having improved actions and practices that have reduced pressure on land uses | GEF SGP database, project reports and monitoring visits | Government policy is in place and supportive of community-level sustainable land management practices |
| SGP OP5 Immediate Objective 8: Support transboundary water body management with community-based initiatives | SGP IW Outcome 8.1: Effective and climate resilient community-based actions and practices supporting implementation of SAP regional priority actions demonstrated Category II Step-up: Scaling-up and replication of good practices and lessons learned, as appropriate SGP IW Outcome 8.2: Synergistic partnerships developed between SGP stakeholders and transboundary water management institutions and structures supporting implementation of SAP regional priority actions Category II Step-up: Scaling-up and replication of good practices and lessons learned, as appropriate | Number of SAPs to which SGP is providing implementation support Number of regional transboundary water management processes to which SGP is contributing good practices and lessons | 5 SAPs for which SGP is supporting on the ground implementation of regional priority actions 7 regional transboundary water management processes to which SGP is contributing good practices and lessons | GEF SGP database, project reports and monitoring visits | Regional water body management organizations are institutionally willing and able to engage with community-level stakeholders |
| SGP OP5 Immediate Objective 9: Promote and support phase out of POPs and chemicals of global concern at community level | SGP CH Outcome 9.1: Improved community-level initiatives and actions to prevent, reduce and phase out POPs, harmful chemicals and other pollutants, manage contaminated sites in an environmentally sound manner, and mitigate environmental contamination Category II Step-up: Scaling-up and replication of good practices and lessons learned, as appropriate | Tons of POPs waste avoided from burning Tons of obsolete pesticides disposed of appropriately Number of countries where SGP is contributing to the implementation of national plans and policies to address POPs, harmful chemicals and other pollutants | 50 tons of POPs waste avoided from burning 15 tons of obsolete pesticides disposed of appropriately 7 countries where SGP is contributing to the implementation of national plans and policies to address POPs, harmful chemicals and other pollutants | GEF SGP database, project reports and monitoring visits | There are adequate opportunities for community-level stakeholders to address POPs, harmful chemicals, and other pollutants Community-level stakeholders develop the awareness and capacity to proactively address POPs, harmful chemicals and other pollutants |
| SGP OP5 Immediate Objective 10: Enhance and strengthen capacities of CSOs (particularly community-based organizations and those of indigenous peoples) to engage in consultative processes, apply knowledge management to ensure adequate information flows, implement convention guidelines, and monitor and evaluate environmental impacts and trends | SGP CD Outcome 10.1: Active participation of NSCs and NFGs in GEF focal areas at the national level SGP CD Outcome 10.2: Improved information flows to/from CBOs and CSOs in SGP countries regarding good practices and lessons learned, and application of such practices SGP CD Outcome 10.3: Increased public awareness and education at the community-level regarding global environmental issues SGP CD Outcome 10.4: Capacity of CBOs and CSOs strengthened to support implementation of global conventions SGP CD Outcome 10.5: Increased application of community-based environmental monitoring SGP CD Outcome 10.6: Evaluation of SGP projects and programs against expected results strengthened, including increased capacity of CBOs and CSOs to apply relevant evaluation methodologies | Number of SGP representatives participating in national GEF coordination meetings Quantity and quality of SGP knowledge base, and use of knowledge base; Quantity and quality of contributions to knowledge fairs, conferences, publications and research. Number of demonstrations and piloted examples of community-based environmental monitoring systems used in SGP projects Quantity and quality of evaluation documentation of expected project results, and unexpected effects Number of CBOs and CSOs demonstrating understanding of the role of evaluation through application of relevant evaluation methodologies | SGP National Steering Committees established and National Focal Groups in 70 countries actively participating in GEF National coordination mechanisms Knowledge platform established to share lessons learned among CBOs and CSOs across 100 SGP countries Capacities of 2,500 CSOs and CBOs strengthened At least 85% of projects incorporate M&E activities in their design At least 70% of projects specify sufficient indicators which are covered in completion reports | GEF SGP database, project reports and monitoring visits SGP case studies | National coordination mechanisms are open to input and participation from community-level stakeholders |
| Cross-Cutting Results: Livelihoods and Gender | SGP’s Results Framework for OP5, as approved by the SGP Steering Committee, does not include specific objectives on livelihoods and gender. Nonetheless, SGP does produce positive results in these areas, which contribute to the overall achievement of Global Environmental Benefits through sustainable development. Generally, SGP seeks to improve livelihoods through increasing local benefits generated from environmental resources, and mainstream gender considerations in community-based environmental initiatives. | Percentage of projects that include gender analysis or incorporate gender relevant elements in a positive manner Percentage of projects with appropriate gender balance of participants and target beneficiaries Percentage of projects that include socioeconomic analysis Number of community members with sustained livelihood improvement resulting from SGP support | 100% of projects that include gender analysis or incorporate gender relevant elements in a positive manner (baseline TBD in OP5) 100% of projects with appropriate gender balance of participants and target beneficiaries (baseline TBD in OP5) 100% of projects that include socioeconomic analysis (baseline TBD in OP5) 50,000 community members with sustained livelihood improvement resulting from SGP support | GEF SGP database, project reports and monitoring visits SGP case studies | All SGP projects have sufficient scope to include gender mainstreaming |

ANNEX B:  RESPONSES TO PROJECT REVIEWS (from GEF Secretariat and GEF Agencies, and Responses to Comments from Council at work program inclusion and the Convention Secretariat and STAP at PIF).

| REVIEW COMMENTS | RESPONSE |
| --- | --- |
| Comments from GEF Secretariat |  |
| 9. Is the project consistent with the recipient country’s national strategies and plans or reports and assessments under relevant conventions, including NPFE, NAPA, NCSA, or NAP Yes, consistent and further details will be required at endorsement stage. | Please refer to additional explanation provided in section A.1 regarding SGP’s consistency with the national strategies and plans. |
| 23. Is funding level for project management cost appropriate? Not appropriate. They seems higher then it is agreed for global program. Please revise and provide additional clarification. 4/04/2012 Some information provided. however, more details should be provided during endorsement stage. Cleared 9/13/2012 | Please refer to additional information provided in section B.3 |
| Comments from STAP (received 12 March 2013) |  |
| Attention to the GEF Focal Area 'learning objectives' is highly relevant to the selection of individual small grant projects. In particular, this allows for additional opportunities to further evaluate the effectiveness of common approaches such as product certification, payments for ecosystem services, and community forest management among others. | Alignment to the “learning objectives” of the GEF Focal Areas will be further fostered in GEF SGP OP5 through an enhanced focus on capacity development, which includes the enhancement of community methodologies and practices, as a key objective in GEF-5. Aside from grants targeted for capacity development, each GEF SGP project is inherently capacity development through a “learning by doing” approach. In this approach, community relevant and appropriate methodologies and practices are tested and modeled. GEF SGP has already piloted product certification of timber and honey as well as community carbon accounting as a basic step towards payments of ecosystem services particularly linked to REDD+ and plans to support more of these. Strengthen approaches in community forest management will also come about in the increased support targeting Indigenous and Community Conserved Areas (ICCAs). The portfolio of GEF SGP projects are then reviewed for “best practices” and proven methodologies to produce technical guidance notes and training materials to enhance the effectiveness of GEF SGP projects, and of other projects through its KM sharing networks. For example GEF SGP has captured knowledge from different regions to produce sustainable biodiversity products catalogues that show how biodiversity resources become commercially valuable products and also help link small producers to markets. Similarly lessons are being exchanged between a number of projects focusing on reduced emissions in dairy farms. Past projects will be identified and planned future projects will be encouraged to form the basis of planned manuals on Community Carbon Accounting and Community-Based Adaptation that is focused on the ecosystem approach. |
| STAP understands that the GEF SGP tends to be treated very much as a stand-alone project in each UNDP Country Office, often weakly integrated with other national and local-level multi-focal area initiatives. As such, STAP recommends attention be given as to how the GEF SGP will be integrated institutionally in-country so that the GEF SGP's outputs support multiple objectives, influence other activities, and where possible are sustained over the long term. | GEF SGP has several mechanisms in place to ensure integration and coordination of its Country Programme portfolios with UNDP Country offices and other national and sectoral initiatives: 1) the country programme strategy (CPS) development involves multi-stakeholder consultation and discussions, and linkages, partnerships and synergies with country-level actors and programmes are explored during this process to ensure greater synergy and portfolio effectiveness; 2) Each GEF SGP Country Programme is governed by a multi-stakeholder National Steering Committee (NSC) that includes government officials, UNDP country office representative, NGOs, academics and other key stakeholders from different sectors. Members of the NSC bring their knowledge and experience to guide and advise on project development and implementation, ensuring linkages and helping to establish partnerships with other national and focal area initiatives; 3) Linkages with other ongoing national processes, such as NAPAs, NAPs, and NIPs (see section A.2) are systematically explored with NCs, NSC members or GEF SGP grantees often involved as members in national dialogues or committees; 4) In GEF SGP OP5, links with Convention Focal Points will be further strengthened with periodic meetings and briefings. In many countries, convention focal points often serve as members of GEF SGP NSCs. The GEF SGP Operational Guidelines now provide for the formation of Technical Advisory Groups to further provide participation for representatives of Convention Focal Points in the technical review of GEF SGP project proposals; 5) GEF SGP National Coordinators have joined as members of national committees in GEF National Portfolio Formulation Exercises. GEF SGP has also served as a delivery mechanism for key national and regional projects and programmes such as the Nile Transboundary Environmental Action Project, the South China Sea project and the EU Tropical Forest programmme in South East Asia. In OP5, opportunities will continue to be explored for GEF SGP to serve as an effective grassroots delivery mechanism for GEF and other donor programmes addressing environment and sustainable development objectives. Through such collaboration synergies and linkages will be strengthened between GEF SGP and other national and focal area initiatives. |
| Finally, STAP would recommend that the contribution of these projects to the development of human and institutional capital and improved knowledge management at national level be further elaborated wherever possible. The contribution to GEF learning objectives, noted above, is one such step. However, these projects are uniquely placed to improve learning and knowledge management at the national level, and contribute directly to our understanding of the delivery of global environmental benefits and sustainable development objectives. | GEF SGP works with poor and vulnerable people and communities to take action to address global environmental challenges. In the process of developing, implementing and monitoring and evaluating these projects, communities are empowered to organize themselves to take action while the knowledge and capacity of these communities is strengthened to deal with global environmental issues, and to pilot and adopt sustainable approaches and techniques. Generating and sharing knowledge is an important goal of the GEF SGP as already stated above. All projects and country programmes will incorporate a significant knowledge generation and sharing component as part of project design and in the update of the OP5 country programme strategy. Each grantee will be expected to develop and submit knowledge products, including a final project report summarizing project activities and achievements that can be included in the GEF SGP global database. The GEF SGP database will be improved to reflect the growth and expansion of the programme, so that it will be able to accommodate more sophisticated monitoring and evaluation indicators and tools as well as knowledge sharing and exchange mechanisms. GEF SGP will help maximize global learning through the sharing of experiences and best practices, both in person through horizontal grantee exchanges and national workshops, as well as virtually through the online system. Based on these experiences, the programme will promote the adoption and replication of these best practices when designing new projects across similar thematic areas. It should be noted that in the sharing of these experiences, as is the practice in the development of GEF SGP knowledge products, successes of communities, special sectors such as indigenous peoples, women, and youth, and civil society organizations in developing enhanced organizational skills, awareness of, networking and advocacy for the environment, and participation in policy consultations and development planning have always been elaborated and highlighted. In GEF SGP OP5, the organization of “Knowledge and Best Practice Fairs” which would highlight these successes at the national level is a target activity for each GEF SGP Country Programme. |

Annex C:  status of implementation of project preparation activities and the use of funds

A.  provide detailed funding amount of the ppg activities financing status in the table below:

| PPG Grant Approved at PIF: |  |  |  |
| --- | --- | --- | --- |
| Project Preparation Activities Implemented | GEF/LDCF/SCCF/NPIF Amount ($) |  |  |
|  | Budgeted Amount | Amount Spent Todate | Amount Committed |
| Total | 0 | 0 | 0 |

annex D:  calendar  of expected reflows (if non-grant instrument is used)

Provide a calendar of expected reflows to the GEF/LDCF/SCCF/NPIF  Trust Fund or to your Agency (and/or revolving fund that will be set up)

Project ID number will be assigned by GEFSEC.

Refer to the Focal Area Results Framework and LDCF/SCCF Framework when completing Table A.

GEF will finance management cost that is solely linked to GEF financing of the project.

PMC should be charged proportionately to focal areas based on focal area project grant amount in Table D below.

For questions A.1 –A.7 in Part II, if there are no changes since PIF and if not specifically requested in the review sheet at PIF 
    stage, then no need to respond, please enter “NA” after the respective question

GEF SGP participating countries have been broadly classified according to the number of years they have participated in the program and the amount of cumulative resources disbursed through the program.  There is an expectation that SGP programs in those countries with the most SGP experience (Category II countries) should be able to deliver “higher level” results within each focal area.  Suggested higher level outcome add-ons are included in the results framework as the “Category II Step-up.”

“Avoided GHG emissions” is among the GEF-5 indicators for the climate change focal area, and is a relevant outcome for SGP.  The SGP approach, and level of available resources, inherently implies that SGP cannot, by itself, generate a transformative influence on the global climate problem directly through the amount of GHG emissions avoided.  At the same time, many, if not all, SGP climate change mitigation projects directly contribute to a reduction or avoidance of GHG emissions, and these positive results should be documented.  Recognizing that addressing global climate change will require action by the entire global community, SGP’s theory of intervention (in all focal areas) is heavily predicated on its catalytic effects, and thus the SGP results framework focuses on results of this nature.

Agro-ecosystems including grasslands and rangelands

If at CEO Endorsement, the PPG activities have not been completed and there is a balance of unspent fund, Agencies can continue undertake the activities up to one year of project start.  No later than one year from start of project implementation, Agencies should report this table to the GEF Secretariat on the completion of PPG activities and the amount spent for the activities.