FAO/GLOBAL ENVIRONMENT FACILITY

PROJECT DOCUMENT

| PROJECT TITLE: Delivering Sustainable Environmental, Social and Economic Benefits in West Africa through Good Governance, Correct incentives and Innovation FAO PROJECT SYMBOL: |  |  |  |
| --- | --- | --- | --- |
| Recipient Countries: Cabo Verde (CPV), Cote d’Ivoire (CIV) and Senegal (SEN) |  |  |  |
| Resource Partner: Global Environment Facility (GEF) |  |  |  |
| FAO Project ID: 641577 (Co-implemented by UNEP) |  | GEF Project ID: 9126 |  |
| Executing Partner(s) : Governments of CPV (Ministère de l’économie et de l’emploi & Ministère de l’agriculture et de l’environnement), CIV (Ministère des ressources animales et halieutiques & Ministère de l'environnement et du développement durable) and SEN (Ministère de la pêche et de l’économie maritime & & Ministère de l'environnement et du développement durable), and the Abidjan Convention Secretariat |  |  |  |
| Expected EOD (starting date): 1 October 2016 |  |  |  |
| Expected NTE (End date): 30 September 2021 |  |  |  |
| Contribution to FAO’s Strategic Framework | a. Strategic Programme: SP2 b. Organizational Outcomes: 2.1, 2.2, 2.4 |  |  |
| GEF Focal Area(S): international waters and biodiversity |  |  |  |
| GEF Strategic Objectives: IW3-Program 7: Foster Sustainable Fisheries, and BD4-Program 9: Managing the Human-Biodiversity Interface |  |  |  |
| Environmental Impact Assessment Category (insert √): A B C√ |  |  |  |
| Financing Plan: GEF allocation: Co-financing: FAO (in-kind) UNEP (in-kind) Gov CPV (in-kind) Gov CIV (in-kind) Gov SEN (in-kind) Abidjan Convention (in-kind) NGO BirdLife International (in-kind) NGO Marine Stewardship Council (MSC) (in-kind) Industry group CONXEMAR (in-kind) CSOs Small-scale fisheries organisations (in-kind) Subtotal Co-financing: Total Budget: |  |  | USD 6,433,027 USD 27,000,000 USD 150,000 USD 3,000,000 USD 6,000,000 USD 5,000,000 USD 1,000,000 USD 300,000 USD 1,000,000 USD 2,000,000 USD 101,500 USD 45,551,500 USD 51,984,527 |

TABLE OF CONTENTS

EXECUTIVE SUMMARY									   4

ABBREVIATIONS AND ACRONYMS							   8

GLOSSARY											   12

MAP

SECTION 1 – Relevance									   14

1.1 General Context                                                                                                         14

1.1.1 Introduction									   14

1.1.2 Sector overview								   19

1.1.3 Policy and institutional framework						   22

1.1.4 Global Environmental Problems, Climate Change and Root Causes that need to be addressed							                26

1.2 Rationale                                                                                                                     29

1.3 FAO’s and UNEP’s comparative advantages	2

1.4 Participants and other stakeholders	3

1.5 Links to national development goals, strategies, plans, policy and legislation, and FAO’s Strategic Objectives	5

SECTION 2 – Project Framework And Expected Results	11

2.1 Project strategy	11

2.2 Project objective	14

2.3 Project components, expected outcomes and outputs	15

2.4 Cost effectiveness	26

2.5 Innovativeness	27

SECTION 3 – Feasibility									   28

3.1 Environmental impact assessment	28

3.2 Risk Management	28

3.2.1 Risks and mitigation measures						   28

3.2.2 Risks deriving from changing external conditions				   29

SECTION 4 – IMPLEMENTATION and MANAGEMENT ARRANGEMENTS			   31

4.1 Institutional arrangements	31

4.2 Implementation arrangements	36

4.2.1 GEF Agency									   36

4.2.2 Executing partners/agencies							   39

4.3 Financial planning and management	39

4.3.1 Financial plan (by component, outputs and co-financier)			   39

4.3.2 GEF inputs									   40

4.3.3 Government inputs								   40

4.3.4 FAO inputs									   40

4.3.5 Financial management of and reporting on GEF resources			   42

4.4 Procurement	43

4.5 Monitoring and Reporting	44

4.5.1 Oversight and monitoring responsibilities					   44

4.5.2 Indicators and information sources						   45

4.5.3 Reporting schedule								   46

4.5.4 Midterm Review and Final Evaluation Plan					   49

4.6 Provision for evaluations	50

4.7 Communication and visibility	50

SECTION 5 – Sustainability of RESULTS							   54

5.1 Social Sustainability	54

5.2 Environmental sustainability	55

5.3 Financial and economic sustainability	56

5.4 Sustainability of capacities developed	56

5.5 Appropriateness of technology introduced	57

5.6 Replicability and scaling up	57

APPENDIX 1: RESULTS FRAMEWORK	58

APPENDIX 2: WORK PLAN (RESULTS BASED)	59

APPENDIX 3: RESULTS BUDGET	73

APPENDIX 4: RISK MATRIX	77

APPENDIX 5: PROCUREMENT PLAN	80

APPENDIX 6: TERMS OF REFERENCE (TORs)	81

APPENDIX 7:  CFI  STRATEGIC FRAMEWORK DOCUMENT	92

APPENDIX 8: CFI PROGRAM FRAMEWORK DOCUMENT (PFD)	93

APPENDIX 9:  RELATION BETWEEN CFI PROGRAMME LEVEL TARGETS AND OUTCOME INDICATOR TARGETS OF THIS PROJECT	94

APPENDIX 10: CFI PROGRAM KNOWLEDGE SHARING	96

APPENDIX 11: CFI THEORY OF CHANGE	97

APPENDIX 12: SYNERGIES CFI, WARFP, CCLME and GCLME	98

# EXECUTIVE SUMMARY

This Project – Delivering sustainable environmental, social and economic benefits in West Africa through good governance, correct incentives and innovation – is part of the Coastal Fisheries Initiative global program (the CFI Program) and constitutes one of four child projects. The CFI Program intends to demonstrate and promote more holistic processes and integrated approaches leading to sustainable use and management of coastal fisheries complementing the GEF multi-country Large-Marine Ecosystem (LME) approach. The CFI Program includes knowledge management and research mechanism for sharing experiences and furthering effective fisheries management globally.

As a Program, consisting of five interlinked Projects, the CFI will play an important role in catalyzing greater collaboration and fostering knowledge sharing in coastal fisheries.The CFI will examine how different approaches work in different situations – at the same time as impact is generated on the ground – through its regional/national child projects and in bringing this new knowledge to the international arena to be examined, shared, understood and replicated, as appropriate. Through a CFI Programme level Theory of Change and a Results Framework progress will be monitoried and knowledge sharing is an important component of the package.

This Project includes the three countries Cabo Verde, Cote d’Ivoire and Senegal in West Africa. It is implemented by FAO in collaboration with UNEP/the Abidjan Convention and through collaboration with relevant government agencies and other stakeholders, including fisher and fish worker organisations, in the three countries. The Project, which has been developed through a consultative process involving governments, representatives of fishers and fish workers and other coastal fisheries stakeholders, is set up to improve fisheries governance and management arrangements and strengthen the seafood value chain.

The Atlantic Coast off West Africa is one of the world’s most productive regions for aquatic resources, with major localized upwelling areas all along the coast. Coastal fishing and other fisheries activities are essential for providing food and employment – for both men and women – supporting livelihoods and generating revenues for the coastal populations and nations. Fish contributes up to two thirds of the animal protein consumed in the West African countries. Coastal fisheries constitute an important engine in local economies and also benefit Africa at large, as well as the global community, as fish in the region is a major commodity traded regionally and worldwide. For coastal communities, fisheries – and in particular small-scale fisheries – also hold fundamental cultural and social values and fishing and related activities often represent a way of life.

However, the contribution of coastal fisheries to environmental, economic, and social sustainability is threatened by high fishing pressure, unsustainable practices and wastage in the postharvest sector leading to sub-optimal benefits, degradation of coastal habitats – including mangrove areas – as well as poor working conditions and insecure livelihoods. The root causes and drivers of this situation include weak governance arrangements and limited capacity of institutions to drive processes and to effectively regulate fishing, promote responsible practices and strengthen value chains.

Although progress is being made in improving governance of the coastal fisheries in the three countries, the pace and scope of the various initiatives need to be augmented substantially given the increasingly adverse impacts on the valuable fish stocks, fishing communities and ecosystems. Main barriers for eliminating or at least reducing, the threats to coastal fisheries and their contribution to livelihoods, food security and sustainable development can be summarized as follows:

- Insufficient and fragmented knowledge on the dynamics of the value chain and on approaches allowing for addressing coastal fisheries in a holistic and integrated way.

- Lack of the tools, means and institutional arrangements to create the necessary enabling environment for successful coastal fisheries.

- Lack of attention to and recognition of the role of coastal fisheries actors and resource users in promoting responsible fisheries and sustainability, in particular with regard to women in the postharvest sector.

Within this context, the present Project will address the following issues:

- Ineffective and non-coherent fisheries policies, strategies and actions

Legal and policy frameworks are inadequate and while initiatives are under way to review these, there is still not sufficient consideration of EAF and the implementation of relevant international instruments. There is generally limited knowledge among decision-makers and politicians on the importance of EAF and the need for implementation of international instruments. Moreover, there are no mechanisms at national level for assessing how well fisheries policy contribute to overall food security and development goals. Initiatives and activities with regard to fisheries management are often driven by donors and development partners and governments have limited capacities to ensure consistency, take ownership of results and manage a viable implementation process.

- Lack of effective and systematic fisheries management based on EAF

There are several management plans that have been developed by development partners in the three countries but that have not yet been implemented. Often the provisions for operationalizing them are lacking. Some of these plans also need to be reviewed to ensure that they comply with EAF and the coastal habitats, including mangroves, are considered. Management plans also need to consider relevant international instruments and foresee the necessary support measures to make them implementable taking livelihoods of coastal communities into consideration. Capacities for implementing fisheries management, in particular in a holistic manner, are lacking both on behalf of government authorities and resource users.

- Coastal communities do not have the capacities and opportunities required to participate in fisheries management and development processes

Co-management is promoted but the regulatory and institutional tools and capacities are not yet in place for its successful implementation, including the capacity of coastal communities to effectively engage in and contribute to management and development processes. Fisher and fish worker organisations are non-existent or generally weak and do not always represent the real stakeholders.

- Low quality of fishery products, postharvest losses and unhealthy and difficult working conditions in the coastal fisheries value chain

Postharvest losses are estimated to some 20-25 %, sometimes up to 50%, in Africa and occur in particular in the artisanal sector. Practices for artisanal fish processing, in particular smoking, constitute a health hazard and consume precious wood (mangroves) with negative environmental effects. There are successful examples of improving both product quality and working conditions in the region, in particular in Cote d’Ivoire.

- Inefficient coastal fisheries value chains and lack of incentives for adopting better practices

There is limited understanding and consideration of the how the different stages of the value chain are linked and contribute to sustainable fisheries and livelihoods. Postharvest actors are generally not part of decision-making with regard to fisheries management and tend to have insecure access to resources.  Small-scale processing and trading activities do not to have a recognised professional status and unequal competition for catches implies risks for in particular women processors and contributes to poverty and unsustainable coastal fisheries.

- Knowledge and lessons learnt are not sufficiently communicated and shared

There is limited exchange of experiences and lessons learnt among governments, development partners and regional organisations. Coherent approaches to fisheries governance and management are lacking both at national and regional levels.

The Project will take a combined governance and value chain approach and aims to support the implementation of an ecosystem approach to fisheries (EAF) together with the application of relevant international instruments, in particular the Voluntary Guidelines for Securing Sustainable Small-scale Fisheries in the Context of Food Security and Poverty Eradication (SSF Guidelines), focusing on ensuring participation, capitalising on existing experiences and generating know-how, developing capacity and supporting innovative governance partnerships along the value chain, supported by effective strategies, national laws and regulations. The Project will provide additional support to existing regional, national and local processes to facilitate the transition of strategic and management planning processes to operational level, and combining these with the integration of local on the ground results. Accordingly, Project activities will be closely coordinated with other on-going initiatives and close collaboration with other projects is not only considered desirable but necessary. The Project will also benefit from being part of the CFI Program and sharing of lessons learnt within the CFI will contribute to the achievement of Project objectives. The knowledge management components of the Project (component 3 – see below) and the CFI Program as a whole are hence key elements of Project/Program design.

The overall Project objective is to:

Strengthen fisheries governance, management and value chains, through the implementation of an ecosystem approach to fisheries, of relevant international instruments and of innovative governance partnerships in three countries in West Africa (Cabo Verde, Cote d’Ivoire and Senegal).

The Project consists of three interlinked components that will address the barriers described above in an integrated manner:

- Component 1: Improving fisheries governance and management

- Component 2: Strengthening the seafood value chain

- Component 3: Strategic communication, monitoring and evaluation, and upscaling best practices

Components 1 and 2 are closely linked and constitute the two sides of the same coin; primary production and postharvest in the value chain. Component 1 will assist the countries to transit towards more effective use of existing governance mechanisms and management tools, facilitating the move from planning to on the ground action, promoting participatory approaches and creating incentives for the communities to contribute to improved management. In Component 2, small-scale operators, in particular women, who represent a major workforce and entrepreneurial drive in postharvest operations and are key agents for reducing postharvest losses, will be supported to improve product quality, the access to markets and working conditions. Improving incomes and livelihoods with same or lower levels of catch should ultimately contribute to reducing the pressure on fish stocks.

Component 3 aims at ensuring that Project experiences and results are shared broadly, within the Project countries, the region, the CFI Program and globally. This Component will also ensure the setting up of an M& E system allowing for close monitoring of Project progress.

This Project will in particular contribute to the GEF-6 International Waters Focal Area Strategy, Program 7: Fostering sustainable fisheries, and the Biodiversity Focal Area Strategy No 4 Mainstream biodiversity conservation and sustainable use into production landscapes/seascapes and sectors. The Project is aligned with the FAO Strategic Framework and with the priorities in the FAO Country Programming Frameworks (CPF).

The Project will have a duration of 5 years. The total budget is estimated at USD 51.9 million, including total GEF grants amounting to USD 6.4 million.

# ABBREVIATIONS AND ACRONYMS

| AfDB | African Development Bank |
| --- | --- |
| ATLAFCO | Ministerial Conference on Fisheries Cooperation Among African States Bordering the Atlantic (COMAFAT) |
| AU | African Union |
| AU-IBAR | Interafrican Bureau for Animal Resources |
| AWP/B | Annual Work Plan and Budget |
| ABNJ | Areas Beyond National Jurisdiction |
| AWP/B | Annual Work Plan and Budget |
| BGI | Blue Growth Initiative |
| BGI | Blue Growth Initiative |
| BH | Budget Holder |
| CAADP | Comprehensive Africa Agriculture Development Program (AU) |
| CAMFA | Conference of African Fisheries and Aquaculture Ministers |
| CAOPA | African Confederation of Artisanal Fisheries Professional Organizations |
| CBD | Convention of Biological Diversity |
| CCLME | Canary Current Large Marine Ecosystem |
| CCRF | Conduct for Responsible Fisheries |
| CECAF | Fishery Committee for the Central Eastern Atlantic |
| CFI | Coastal Fisheries Initiative |
| CI | Conservation International |
| CI | Conservation International |
| CIV | Cote d’Ivoire |
| COFI | Committee on Fisheries (FAO) |
| CONFISH | Collaborative Management for a Sustainable Fisheries Future |
| CONXEMAR | Spanish Association of Wholesalers, Importers, Manufacturers and Exporters of fish products and Aquaculture |
| COP | Conferences of Contracting Parties |
| CRC | Coastal Resources Centre |
| CPUE | Catch Per Unit Effort |
| CPF | Country Programming Framework (FAO) |
| CRODT | Centre de Recherches Océanographiques de Dakar Thiaroye (Senegal) |
| CPV | Cabo Verde |
| CSF | FAO Finance Division |
| CSO | Civil Society Organization |
| CTA | Chief Technical Advisor |
| EAF | Ecosystem Approach to Fisheries |
| EAFM | Ecosystem Approach to Fisheries Management |
| ECOWAS | Economic Community of West African States |
| EEZ | Exclusive Economic Zone |
| EU | European Union |
| FAO | Food and Agriculture Organization |
| FCWC | Fishery Committee of the West Central Gulf of Guinea |
| FENACOPECI | Fédération Nationale des Coopératives de Pêche de Côte d’Ivoire |
| FIP | Fisheries Improvement Programme |
| FLO | Funding Liaison Officer |
| FPAI | Fisheries Performance Assessment Instrument |
| FTT | FAO Thiaroye kiln |
| GCLME | Guinea Current Large Marine Ecosystem |
| GCU | Global Coordination Unit |
| GDP | Gross Domestic Product |
| GEB | Global Environment Benefit |
| GEF | Global Environment Facility |
| GRG | Global Reference Group |
| GSC | Global Steering Committee |
| ha | Hectare |
| ICCAT | International Commission for the Conservation of Atlantic Tunas |
| INDP | Institut national de développement des pêches (Cabo Verde) |
| IOTC | Indian Ocean Tuna Commission |
| IPOA-Seabirds | International Plan of Action for Reducing Incidental Catch of Seabirds in Longline Fisheries |
| IUCN | International Union for Conservation of Nature |
| IUU fishing | Illegal, Unreported, and Unregulated fishing |
| IWC | International Whaling Commission |
| JICA | Japanese International Cooperation Agency |
| KM | Knowledge management |
| KS | Knowledge sharing |
| LME | Large Marine Ecosystem |
| LTO | Lead Technical Officer |
| NPC | National Project Coordinator |
| NPO | National Project Officer |
| M&E | Monitoring and Evaluation |
| MoU | Memorandum of Understanding |
| MPA | Marine Protected Area |
| MSC | Marine Stewardship Council |
| MSP | Marine Spatial Planning |
| NAPA | National Environmental Plan of Action |
| NBSAP | National Biodiversity Strategies and Action Plans |
| NEPAD | New Partnership for Africa’s Development |
| NFFP | NEPAD-FAO Fish Project |
| NGO | Non-Governmental Organization |
| OHS | Occupational Health and Safety |
| PES | Payment for Environmental Services |
| PFD | Program Framework Document |
| PIR | Project Implementation Review |
| PGRP | Plan for Fishery Resources Management (Cabo Verde) |
| PPG | Project Preparation Grant |
| PPP | Public-Private Partnership |
| PPR | Program Progress Report |
| PRCM | Regional Partnership for the Conservation of the Coastal and Marine Zone in West Africa |
| PRSP | Poverty Reduction Strategy Paper |
| PSC | Project Steering Committee |
| PTF | Project Task Force |
| PTM | Project Task Manager |
| REC | Regional Economic Communities |
| RFB | Regional Fisheries Body |
| RSP | Regional Seas Program (UNEP) |
| SAP | Strategic Action Plan |
| SDG | Sustainable Development Goals |
| SEN | Senegal |
| SP | Strategic Programme |
| SPS | Sanitary and Phytosanitary Measures |
| SRFC | Sub-Regional Fisheries Commission |
| SSF Guidelines | Voluntary Guidelines for Securing Sustainable Small-scale Fisheries in the Context of Food Security and Poverty Eradication |
| TCP | Technical Cooperation Project |
| TDA | Transboundary Diagnostic Analysis |
| ToC | Theory of Change |
| ToR | Terms of Reference |
| TURF | Territorial User Rights in Fisheries |
| UEMOA | West African Economic and Monetary Union (Union économique et monétaire ouest africaine) |
| UN | United Nations |
| UNDP | United Nations Development Program |
| UNEP | United Nations Environment Program |
| UNIDO | United Nations Industrial Development Organization |
| USAID | United States Agency for International Development |
| VGGT | Voluntary Guidelines on the Responsible Governance of Tenure of Land, Fisheries and Forests in the Context of National Food Security |
| WARFP | West Africa Regional Fisheries Program |
| WTO | World Trade Organization |
| WWF | World Wide Fund for Nature |

# GLOSSARY

Fisheries and development terminology sometimes vary from one context, organization or country to another. This glossary provides the definitions of commonly used concepts as used in this project document. Most of the definitions correspond to FAO usage and can be found in http://www.fao.org/faoterm/en/ (other sources are provided when relevant).

Access or use rights

The rights held by individual fishers, fishing groups, fishing communities or companies to use the fishery resources. These may be in the form of rights to an amount of fishing effort (effort rights) or catch that can be taken in the fishery (harvest rights or harvest quotas). They can be defined by local custom, mutual agreements, or prescribed by other entities holding access rights. They may restrict the use of particular harvesting techniques.

Co-management

A partnership arrangement in which government, the community of local resource users (fishers), external agents (non-governmental organizations, research institutions), and sometimes other fisheries and coastal resource stakeholders (boat owners, fish traders, credit agencies or money lenders, tourism industry, etc.) share the responsibility and authority for decision-making over the management of a fishery.

Ecosystem approach to fisheries (EAF)

An approach to fisheries management and development that strives to balance diverse societal objectives, by taking into account the knowledge and uncertainties about biotic, abiotic and human components of ecosystems and their interactions and applying an integrated approach to fisheries within ecologically meaningful boundaries. The purpose of EAF is to plan, develop and manage fisheries in a manner that addresses the multiple needs and desires of societies, without jeopardizing the options for future generations to benefit from the full range of goods and services provided by marine ecosystems.

Secure tenure and access rights regimes

Tenure means socially defined agreements held by individuals or groups (either recognised by law or customary norms) on the rights to access and the rules for use of either a land area or associated resources (Garcia, Rice and Charles, 2014). Access rights (or use rights) are the rights held by individual fishers, fishing groups, fishing communities or companies to use the fishery resources. These may be in the form of rights to an amount of fishing effort (effort rights) or catch that can be taken in the fishery (harvest rights or harvest quotas). They can be defined by local custom, mutual agreements, or prescribed by other entities holding access rights. They may restrict the use of particular harvesting techniques.

Accordingly, when referring to secure tenure and access rights regimes in this document, it refers to wide range of possible rights-based management systems – potentially including both community and individual rights according but that are based on principles contained in the Voluntary Guidelines on the Responsible Governance of Tenure of Land, Fisheries and Forests in the Context of National Food Security (VGGT) and the Voluntary Guidelines for Securing Sustainable Small-scale Fisheries in the Context of Food Security and Poverty Eradication (the SSF Guidelines).

The project sites are as follows:

Cabo Verde: Maio and S. Vincente / S. Luzia;

Cote d’Ivoire: Abidjan (Locodjro) and Cassandra;

Senegal: Iles du Salaam.

Figure 1: MAP

# SECTION 1 – Relevance

## 1.1 General Context

1.1.1 Introduction

This Project - Delivering sustainable environmental, social and economic benefits in West Africa through good governance, correct incentives and innovation – is part of the Coastal Fisheries Initiative (CFI) global program and constitutes one of four child projects (see below). The Project is set out to address unsustainability in the coastal fisheries in Cabo Verde, Cote d’Ivoire and Senegal as the contribution of coastal fisheries to environmental, economic and social sustainability in the Project countries is threatened by high fishing pressure, unsustainable practices and wastage in the postharvest sector leading to sub-optimal benefits, degradation of coastal habitats as well as poor working conditions and insecure livelihoods. Root causes of this situation include weak governance arrangements and limited capacity of institutions to drive processes and to effectively regulate fishing, promote responsible practices and strengthen value chains as well as low capacity adapt to new emerging issues such as climate change and variability.

The Project will take a combined governance and value chain approach and aims to support the implementation of an ecosystem approach to fisheries (EAF) together with the application of relevant international instruments, in particular the Voluntary Guidelines for Securing Sustainable Small-scale Fisheries in the Context of Food Security and Poverty Eradication (SSF Guidelines), focusing on ensuring participation, capitalising on existing experiences and generating know-how, developing capacity and supporting innovative governance partnerships along the value chain, supported by effective strategies, national laws and regulations. The Project will provide additional support to existing regional, national and local processes to facilitate the transition of strategic and management planning processes to operational level, and combining these with the integration of local on the ground results.

##### a) The CFI Programme

The CFI has been developed based on the recognition of the importance of coastal fisheries, the richness of initiatives and experiences in coastal fisheries but also that there is still no globally agreed solution to how to make them environmentally, economically and socially sustainable. Because many actors work independently from one and other and because there is limited capacity in many countries, in particular developing countries, to analyze, coordinate and effectively steer various initiatives towards a similar outcome, there is a great need to improve collaboration and to identify and refine agreed best practices.

As a Programme, consisting of 5 interlinked Projects, the CFI will play an important role in catalyzing greater collaboration and fostering knowledge sharing in coastal fisheries.The CFI will examine how different approaches work in different situations – at the same time as impact is generated on the ground – through its regional/national child projects and in bringing this new knowledge to the international arena to be examined, shared, understood and replicated, as appropriate. The CFI will also examine existing initiatives and results generated by such programmes and projects with a view to identify good (and bad) practices, including from ongoing LME projects. The CFI will work towards a more harmonized view on what different approaches and concepts in coastal fisheries mean and can do and promote a more holistic process for and integrated perspective on sustainable management. This implies an integration of approaches and priorities in respect of sector-focused management, safeguarding of human well-being, biodiversity and ecosystem health, postharvest and value chain, and wealth and investments. The CFI as a Programme will therefore deliver much more than just the sum of its Projects; while individually, the Projects will deliver valuable outputs in their geographies, aggregation of the knowledge gained from activities across a range of projects and contexts, together with the synthesis and dissemination of that knowledge, is something that can only be done at the global level, and thus the CFI is somewhat unique in this respect.

The Programme consists of 5 inter-linked Projects that benefit from, and contribute, to each other to ensure a Programme that is greater than the sum of its individual parts(Appendix 9). At the core of the Programme are three regional projects (West Africa, Latin America and Indonesia – totaling 6 countries), which are structured to test and pilot frontier tools and approaches in these three geographies. Each regional project is tailored to its own regional context, and contains unique elements (e.g., CFI-Indonesia is developing a trust fund; CFI-LA is conducting an Ocean Health Index assessment; CFI West Africa is improving working conditions). There are also some similar or common elements such as integrating “ecosystem based management” into fisheries policies, promoting marine protected areas and furthering gender equality. The outcomes of these elements will be shared between projects, creating opportunities to learn from each other’s unique experiences as well as draw lessons across common elements – so that each project will benefit from, and contribute to, the other projects. With respect to the activities in the other projects, specifically Latin America and Indonesia there are areas of interest for this project: the fisheries management experiences of developing FIPs and traceability systems in Latin America and Indonesia; while this project will not undertake CMSP, erosion is significant in the three countries of this project and there will be interest in how this issue will be dealt with in Latin America; and the challenges the other two projects face in applying the FPAI and its influence in policy and management decision making.

These three regional projects are supported by the Challenge Fund Project, which will provide technical asssistance for the development of a pipeline of investable projects, while providing a platform for interested investors to engage early and adequately assess—and address—potential investment risks. The ultimate outcomes are private investments made in the fisheries of the three regions.The Challenge Fund will benefit the West Africa project by providing access to technical assistance for developing investable projects and ties to potential investors in the post-harvest sector and possibly empowering women’s groups. At the same time, the regional projects will contribute to the Challange Fund by  providing local knowledge and context, including fisheries assessment information.

Coordination of CFI , including ensuring the projects are working together as a Program, assessing fisheries management performance (via the Fisheries Performance Indicators project), conducting analyses of the four projects’ outcomes and M&E activities, and sharing knowledge within and beyond the CFI Programme, will be managed through the Global Partnership Project. The FPA project will develop a methodology for fisheries assessments from a social, economic and environmental perspective specific to data poor contexts. It will be piloted in the three regions to consolidate the tool for wider dissemination globally. It will benefit the projects by providing access to the latest tool for assessing the status of their fisheries esepcially for data poor fisheries which applies to many of the fisheries in West Africa including the three countries of this project and the projects will contribute to FPA by serving as a testing ground for the tool with a focus on data poor fisheries in West Africa.

Similarly the Partnership Project will play a key role in knowledge sharing and analyses of outputs and outcomes across the three regions and with coastal fisheries globally for the production of global knowledge products and coordination of dissemination mechanisms (e.g. listserve, webinars, knowledge products, website, workshops, newsletters, blogs, stakeholder exchanges, conferences) (Figure 2). Contributions from the other 4 projects will be critical to the success of this knowledge sharing (KS). At the same time, the other four projects will benefit from learning about experiences from the other projects as noted earlier. Given the importance of M&E and KS, for each project a total of 25% of funds have been allocated to these components, including 5-10% for M&E, 10-15% for KS within the project and 10-15% for KS with the program. Knowledge sharing products, including the themed product that this project will champion, developed in this project as well as the lessons learned will be shared through the various platforms coordinated by the Global Partnership as well as through regional and national platforms (Figure 2). These platforms will also enable stakeholders in the West Africa project to learn from other projects and partners. For this project more than 25% of the total budget is allocated to knowledge sharing and monitoring and evaluation, with approximately 5% of the budget for M&E.

Overall guidance of the programme will be provided by a Global Steering  Committee and technical advice as needed through a Global Reference Group.

The CFI Program is informed by the CFI Theory of Change (Appendix 11), which identified a series of tiered building blocks critical to achieving the program’s outcomes.  The projects are expected to progress through these tiers starting with establishing necessary enabling conditions (Tier 1), which will lead to implementing changes in practices (Tier 2), achieving benefits to fisheries and stakeholders (Tier 3) and ulimately leading to system sustainability (Tier 4) (Figure 3).

This Theory of Change, therefore, provides a programme-level framework for the analysis of emerging challenges and learning across the varios initiatives making up the CFI.

The Program Results Framework builds upon the CFI Theory of Change, specifically the Tier 1 enabling conditions, which are focused around conditions and incentives for stakeholders, institions and collaboration. As noted in the first component, CFI will promote sustainability incentives in the value chain addressing the need for correct incentives at the harvesting stage, including new or amended management regimes, reduction in post-harvest losses, implementation of private-public partnerships and development of innovative market incentive systems. As noted in the second component, CFI will strengthen institutional structures and processes, including policy, legislation and institutions, including co-management and access rights regimes, and integrate MPAs into fisheries.  Finally, as noted in the third component, CFI will share best practices, promote collaborate and strengthen fisheries performances measures and assessments.

- Within the Programme, the objective of the West Africa Project is to build upon ongoing national and regional initiatives in the three countries, bringing examples of good practices in terms of governance, value chains and community participation, and explicitly linking local achievements with national strategies and action plans. Moreover, the Project will provide additional support to existing national and local processes to facilitate the transition of strategic and management planning measures to the operational level. For the small-scale fisheries sector, the SSF Guidelines will be followed. Examples of expected synergies include analysing and building on good practices for co-management developed by the WARFP in Senegal and Cabo Verde and on the achievements within post-harvest technology development at the community level funded through the FAO Framework Agreement (FMM) with the Netherlands in Cote d’Ivoire. Furthermore, the carrying out of these activities will be supported by strengthening existing institutions, coupled with putting into place economic incentives and additional consultative mechanisms as required.

The CFI Programme Results Framework provides the structure that guides the 5 projects. The first component of this project is in line with the CFI Programme which will strengthen institutional structures and processes with a focus on EAF, including policy, legislation and institutions, including co-management and access rights regimes, and in the case of West Africa incorporate management and conservation of mangroves into fisheries management regimes. Similarly, the second component of the West Africa is totally aligned to the CFI programme and promotes sustainability incentives in the value chain addressing the need for correct incentives at the harvesting stage, including new or amended management regimes, reduction in post-harvest losses, implementation of private-public partnerships and development of innovative market incentive systems. Finally, as noted in the third component and as per the CFI, this project will share best practices, promote collaboration and strengthen fisheries performances measures and assessments.

The present project outcomes contribute to building and to the realization of CFI outcomes and targets. Annex 9 maps the CFI programme results framework and the outcomes and targets from this project (CFI West Africa).

Components 1 and 2 contribute to the CFI Programme components: WA-Component 1 will assist the countries to transit towards more effective use of existing governance mechanisms and management tools, facilitating the move from planning to on the ground action, promoting participatory approaches and creating incentives for the communities to contribute to improved management. In WA-Component 2, small-scale operators, in particular women, who represent a major workforce and entrepreneurial drive in postharvest operations and are key agents for reducing postharvest losses, will be supported to improve product quality, the access to markets and working conditions. Improving incomes and livelihoods with same or lower levels of catch should ultimately contribute to reducing the pressure on fish stocks. While Component 3 aims at ensuring that Project experiences and results are shared broadly, within the Project countries, the region, the CFI Program and globally. This Component will also ensure the setting up of an M& E system allowing for close monitoring of Project progress as well as piloting a new fisheries performance assessment instrument (FPAI).

| CFI PROGRAMME Outcomes | Contribution from the CFI-WA Project |
| --- | --- |
| The efficiency of and transparency in the fisheries value chain from harvest to consumer has been improved through appropriate incentive structures and contribute to sustainable resource utilization and equitable social and economic development. | At least 2 fisheries in the Project countries are under implementation in accordance with agreed management plans and include co-management and secure tenure and access rights regimes, as appropriate; 700 ha of mangrove are under sustainable management; and 5 communities are involved in co-management supported by national institutions. At least one women processor organisation has adopted improved practices and their postharvest losses have been reduced by 20 % and fishers and fish processors state that their working conditions have improved at the Project sites. Fuel wood consumption has decreased in fish smoking in Project sites by 10 %. At least one successful innovative pilot activity on how a value chain approach has positively influenced fisheries management applying, inter alia, co-management, secure tenure and access rights, PPPs, eco-labelling/certification schemes, or other. Fishery products from project sites can be found in supermarkets in capital cities of the three countries. At least one women processor organisation has increased their revenues from sales in national and regional markets thanks to better product quality. |
| Policies, legislation and institutions have been improved at local, national and regional levels allowing for enhanced resource management through integrated and holistic approaches that allow for effective incentive structures and that lead to more environmentally, economically and socially sustainable coastal fisheries. | EAF is referred to as the approach for fisheries management and development in relevant policy and strategy documents and implementation plans follow EAF principles. The intention to implement relevant international instruments, including the SSF Guidelines, is explicitly mentioned in policy statements. Information on how coastal fisheries contribute to overall national development goals exists and is shared among national and local institutions and development partners. Fisheries policies and strategies are more coherent and new projects and programmes refer to common priorities Fishers and fish workers (men/women) benefit from improved natural resources management through improved incomes and/or other perceived livelihood improvements as well as through active participation in decision-making processes related to coastal fisheries management and development. |
| The understanding and application of integrated, participatory and collaborative approaches have been enhanced among local and global partners who utilize agreed tools for measuring coastal fisheries performance and progress towards environmental, economic and social sustainability. | - Key messages based on project experiences on key subject matters are communicated and taken up by relevant regional organisations and are reflected in their policy statements. |

Within the Programme, the objective of the   West Africa Project is to West Africa Project is to build upon ongoing national and regional initiatives in the three countries, bringing examples of good practices in terms of governance, value chains and community participation, and explicitly linking local achievements with national strategies and action plans. Within the Programme Results Framework, this project will substantially contribute to the other CFI projects in sharing lessons learned on the implementation of the FAO Guidelines for Small Scale Fisheries, value chains for small-scale fisheries, strengthening the role of women and the community in general and in the application of the ecosystem approach to fisheries (EAF). The West Africa project will benefit from the other CFI projects in gaining a better understanding of the use of tools such as marine spatial planning and MPAs in the management of fisheries, the challenges and benefits of using a trust fund mechanism for community management fisheries and the challenges in moving small-scale fisheries to some form of certification. The West Africa project hopes to also take advantage of the funding available from the CFI Challenge Fund to assist small scale fisher associations in being ready to access finance mechanisms.

##### b) The CFI West Africa project

This Project, which is implemented by FAO in collaboration with the United Nations Environment Program (UNEP), includes three countries in West Africa: Cabo Verde, Cote d’Ivoire and Senegal. The three countries were selected because of the importance of coastal fisheries in these countries and based on a number of criteria agreed for the CFI as a whole (see the CFI Program Framework Document – PFD, see Error! Reference source not found.).

Within the overall strategy of the CFI Program, this Project was developed through a consultative process involving coastal fisheries stakeholders in the three countries, including governments and representatives of fishers and fish workers. The Project is set up to improve fisheries governance and management arrangements and strengthen the seafood value chain with a view to improving environmental, social and economic benefits from fisheries. It will apply strategic communication and effective monitoring and evaluation mechanisms to learn from and share experiences – within the Project, the CFI Program and more broadly in the regional and global fisheries arenas – and to identify best practices to be promoted for upscaling.

The Project contributes to the CFI Program’s overall outcomes by providing experiences from its three West African countries. In Section 2 below where the Project components, expected outcomes and outputs are described, these linkages are stated. Moreover, in APPENDIX 9, Project outcome targets are mapped against CFI targets. The Project also contributes to the CFI Theory of Change (ToC) as part of its monitoring and the development and use of CFI Fisheries Performance Assessment Instrument – FPAI. Likewise, this Project will benefit from experiences and lessons learnt from the other CFI projects through the program knowledge management processes. The benefits of program level knowledge sharing, ToC and PGAI are elaborated on in the Global Partnership project document but also referred to below in Section 4.

Achieving sustainable coastal fisheries is a long-term goal and this five-year Project should be seen as an important step in a process that will require continued support, commitment and collaboration to be successful.

1.1.2 Sector overview

The Atlantic Coast off West Africa is one of the world’s most productive regions for aquatic resources, with major localized upwelling areas all along the coast. Senegal and Cabo Verde border the Canary Current that, with its cold water upwelling, ranks 3rd in the world in terms of primary production after the Humboldt and Benguela currents. The Guinea Current, where Cote d’Ivoire is situated, is also characterized by areas of upwelling supporting biological productivity but to a lesser extent than in the other two countries.

Coastal fishing and other fisheries activities are essential for providing food and employment, supporting livelihoods and generating revenues for the coastal populations and nations. Fish contributes up to two thirds of the animal protein consumed in the West African countries. Women, working in particular in the postharvest sector, represent about half of the people employed in capture fisheries on an average in the world. In Cote d’Ivoire, they represent 60 percent of the total workforce, in Senegal 30 percent and in Cabo Verde an estimated 16 percent.

Coastal fisheries constitute an important engine in local economies and also benefit Africa at large, as well as the global community, as fish in the region is a major commodity traded regionally and worldwide. There are also foreign fleets operating in many West African countries, for example, the European Union has fisheries agreements with all three Project countries, mainly for tuna fishing. For coastal communities, fisheries – and in particular small-scale fisheries – also hold fundamental cultural and social values and fishing and related activities often represent a way of life.

The three countries participating in the project share many similar characteristics, concerns and issues but there are also differences. Data are not always available to clearly illustrate the importance of fisheries and the marine environment.

Table 1 below attempts to summarise existing information and key features by country.

Cabo Verde is an archipelagic small island state, which is highly vulnerable to climate variability, with low capacity to adapt. The country is one of the top ten coral reef biodiversity hotspots in the world and is important for humpback whale mating and calving, and for breeding of five species of sea turtle. Marine biodiversity is concentrated around the islands of Sal, Boa Vista and Maio.

Capture fisheries production was estimated at 23,600 tonnes in 2013. Important fishery resources include migratory species such as large pelagic (e.g., tuna), small pelagics (big-eye scad, black mackerel, frigate tuna), various demersal species (grouper, sea bream, moray eels) and lobster (coastal brown, green and stone lobster, and deep pink lobster). An important part of the fishery production is exported and fisheries statistics indicate that seafood exports represented 85 percent of the total merchandise export in 2014. It is estimated that fisheries contribute for 3.9 percent of GDP, 65-70 percent of which is fish processing and marketing. Fish and seafood are important components of the national diet providing some 10 percent of the population’s animal protein consumption.

Small-scale fisheries have a significant socio-economic and cultural value given that more than 80 percent of the population live in coastal areas. In 2011, it was estimated that there were some 4 800 fishers in Cabo Verde and an estimated 1 000 people employed in the postharvest sector. The majority of the fishers are small-scale, i.e., about 3 700, and 95 percent of the postharvest workers are women.

The Cabo Verdian economy is dominated by the service sector, which represents 75 percent of the GDP, and in particular tourism. Still, the primary sector – agriculture, livestock, fisheries - is very relevant to the country’s economy, and guarantees food security to the diverse layers of the population, including the most vulnerable, and fish is the main source of animal proteins for the population of Cabo Verde. However, there are weak linkages between the tourism sector and the domestic food production sector and estimates suggest that about 80 percent of the fish consumed in the tourist areas is imported.

Cote d’Ivoire is situated in the Gulf of Guinea and has a rich aquatic fauna, including 501 identified fish species. The eastern coastline includes lagoons and includes ecologically and biologically important marine areas. There are six RAMSAR sites including mangrove areas along the coast.

Table 1: Selected fisheries sector data – Cabo Verde, Cote d’Ivoire and Senegal

|  | Cabo Verde | Cote d’Ivoire | Senegal | Source |
| --- | --- | --- | --- | --- |
| EEZ area (km2) | 796 555 | 173 764 | 157 709 | Sea Around Us (seaaroundus.org/data) |
| Continental shelf (km2) | 5 382 | 10 200 | 23 893 |  |
| Water area fished (km2) | 734 265 | N/A | N/A | FAO Fishery country profiles (2008) |
| Coast line (km) | 1 020 (10 islands and 5 islets) | 550 | 718 |  |
| Number of people directly employed in coastal fisheries (fishing and postharvest activities) | 5 800 | 70 000 | 108,900 | CPV: FAO Fishery country profile (2008) |
| Percentage of women in above | 16% | 60% | 30% | Information from countries and FAO/de Graaf, & Garibaldi (2014) |
| Annual capture fisheries production (inland and marine waters), tonnes (2014) | 35 680 | 74 900 | 458 713 | FAO statistics and information from countries. Data do not include production/trade of marine mammals, crocodiles, corals, sponges, shells and aquatic plants and of fish waste for trade statistics |
| Value of annual fish/seafood capture fisheries production (USD, 2014) | N/A | 92 700 000 | N/A |  |
| Fish exports, tonnes, product weight (2013) | 16 834 | 37 604 | 149 917 |  |
| Fish exports, USD 1 000 (2013) | 58 281 | 110 835 | 288 730 |  |
| Fish imports, tonnes, product weight (2013) | 882 | 305 644 | 8 913 |  |
| Fish imports, USD 1 000 (2013) | 4 502 | 377 941 | 19 283 |  |
| Per capita annual fish consumption (kg) (2011) | 12.2 | 18.1 | 23.5 |  |
| Share of fish in animal protein intake (%) (2011) | 10.2 | 38.6 | 42.8 |  |
| Fishing GDP (% of total GDP) | 1.28 | 0.76 | 1.81 | World Bank, 2012, based on various sources. |
| Postharvest GDP % | 2.66 | 0.76 | 2.29 |  |
| Total fisheries GDP % | 3.94 | 1.52 | 14.10 |  |
| Mangrove coverage (ha) en 2012 | N/A | 3200 | 122 000 | PRCM, IUCN, Wetlands International, Abidjan Convention, Nov 2015 |

Despite a relatively narrow coastline of 566 km, Cote d’Ivoire benefits from seasonal upwelling towards the border with Ghana. Fishing and fish processing are estimated at 1.5 percent of GDP, of which processing accounts for half. The total capture fishery production, from both industrial and artisanal fisheries, was about 78 800 tons in 2013 and is far from sufficient to meet the country’s consumption needs. Considerable amounts of fish are imported – some 323,800 tonnes in 2011, consisting mostly frozen fish for the domestic market but also tuna for canneries and subsequent export to the European Union. Fish contributes close to 40 percent of the total animal protein consumed in the country.

Fisheries generate over 70 000 direct jobs and 400 000 indirect jobs, of which more than 60 percent are women, who are involved in fish processing and trading. A large portion of the artisanal fishers, about 90 percent are of Ghanaians origin. The coastal fisheries – mostly small pelagic (sardinella) with an estimated production of some 23,000 tons per year (2012) – play an important role in the sustainable supply of local and central markets such as in Abidjan and San Pedro. Smoked fish – the bulk of the processed fish marketed – is almost exclusively for domestic markets. It is said that its conservation properties allow it to be transported over long distances, even in very precarious conditions, and then to be stored for several weeks for later consumption.

Senegal has a rich marine biodiversity and benefits from upwelling. The country has the natural and human assets forming the basis of the coastal fisheries, mainly the existence of a 718 km long maritime facade, rich fishery resources and a tradition and long experience in canoe fishing as well as in artisanal and industrial fish processing, with a preponderant role played by Senegalese women. Fishing, fish processing and trade activities are of major economic and social importance in Senegal, estimated at 1.8 percent of GDP in 2013. Some 450,000 tons of fish are landed per year, mostly made up of small pelagics. The country’s average consumption is of 25 kg per capita (2011). Fishery products represent on average some 43 percent of the total animal protein intake and could be as high as 80 percent in coastal areas.

Coastal artisanal fisheries account for 80 percent of the total capture and 60 percent of the supply for exporting companies, as well as the biggest part of the national consumption of fish. In most towns and coastal villages, small-scale fisheries and their related trades are the main drivers of the local economy. Post-harvest activities, including small-scale processing and fish trade, are very important given the employment and income they provide to coastal populations (particularly to women) and their contribution to food security. Estimates put the total number of people directly employed in coastal fisheries at some 108,900 (58,100 fishers, 25,200 fish traders and 25,600 fish processors including 6,600 women heading fish processing facilities). In addition, there are thousands of people employed in other up- and downstream jobs. About 90 percent of all direct and indirect jobs are in small-scale fisheries.

1.1.3 Policy and institutional framework

Globally, there is increasing attention to the need for sustainable development and to take into account the three pillars of environmental, economic and social sustainability as expressed in the United Nations Conference on Sustainable Development Rio+20 outcome document The Future We Want (2012). The United Nations (UN) Sustainable Development Goals (SDG), adopted by UN Member States in September 2015, also make specific reference to the oceans as in Goal 14 “Conserve and sustainably use the oceans, seas and marine resources for sustainable development”. During the last few decades, there has been progressive recognition of the need for ecosystem-based approaches to oceans governance and fisheries management. The 1995 Code of Conduct for Responsible Fisheries (CCRF), related instruments and guidance provide a basic framework for sustainable fisheries in an ecosystem context. The CCRF is a voluntary instrument that is widely referred to in regional and national fisheries policies, including in the three Project countries. Its implementation is promoted through the ecosystem approach to fisheries (EAF), which also includes attention to the human dimension.

A recent international instrument that is complementary to the CCRF and that has great relevance to the West African region and the three Project countries is the SSF Guidelines. These guidelines were endorsed by the FAO Committee on Fisheries (COFI) in 2014 and provide a framework for enhancing the understanding of actions needed for small-scale fisheries governance and development. Considering the important role of small-scale fisheries in the region and their contribution to livelihoods and food and nutrition security, the principles and provisions of the SSF Guidelines need to be taken into consideration and put into practice.

At the regional level, there is strong support for policy reform from the African Union (AU). A Policy Framework and a Reform Strategy for fisheries and aquaculture in Africa were adopted by African ministers in May 2014 providing the basis for improved fisheries governance. These documents refer specifically to, among other things, improving governance and institutional arrangements, developing sustainable small-scale fisheries, promoting responsible and equitable fish trade and marketing, strengthening resilience and reducing vulnerabilities to climate change, and developing coordinated mechanisms among Regional Economic Communities (RECs), Regional Fishery Bodies (RFBs) and LME based commissions. The fisheries issues are also referred to in the AU 2050 Africa’s Integrated Maritime Strategy, which was adopted at an AU Summit in January 2014. The Policy Framework and Reform Strategy are being promoted by the AU Interafrican Bureau for Animal Resources (AU-IBAR) and NEPAD, in collaboration with other African national institutions and partners, including FAO, the European Union (EU) and the World Bank.

The Convention for Cooperation in the Protection, Management and Development of the Marine and Coastal Environment of the Atlantic Coast of the West, Central and Southern Africa Region (Abidjan Convention in short) covers a marine area from Mauritania to South Africa which has a coastline of just over 14,000 km. The Abidjan Convention is a comprehensive umbrella agreement and legal framework for the protection and management of the marine and coastal areas. It identifies environmental management issues from which co-operative efforts are to be made: coastal erosion, specially protected areas, combating pollution in cases of emergency; and environmental impact assessment.

At the sub-regional level, there is the Economic Community of West African States (ECOWAS), which was established in 1975. ECOWAS is a 15-member regional group with a mandate of promoting economic integration in all fields of activity of the constituting countries: Benin, Burkina Faso, Cabo Verde, Cote d’Ivoire, the Gambia, Ghana, Guinea, Guinea Bissau, Liberia, Mali, Niger, Nigeria, Sierra Leone, Senegal and Togo. ECOWAS is in the process of developing a food security strategy including fisheries.

The West African Economic and Monetary Union (Union économique et monétaire ouest africaine - UEMOA), created in 1994, promotes economic integration among its member countries by strengthening of their competitiveness with in an open market and a harmonised legal framework. The UEMOA agriculture policy includes component for the development of the fisheries sector. The member countries are Benin, Burkina Faso, Cote d’Ivoire, Guinea Bissau, Mali, Niger, Senegal and Togo.

There are several RFBs covering the Project area and the three countries (see also Table 2):

- Sub-Regional Fisheries Commission (SFRC) covering Cabo Verde, the Gambia, Guinea, Guinea Bissau, Mauritania, Senegal and Sierra Leone.

- Fishery Committee of the West Central Gulf of Guinea (FCWC) including Benin, Cote d’Ivoire, Ghana, Liberia, Nigeria and Togo.

- Ministerial Conference on Fisheries Cooperation Among African States Bordering the Atlantic (ATLAFCO; better known by its French acronym, COMHAFAT, Conférence ministérielle sur la coopération haleutique des États Africains riverains de l’Océan Atlantique).

The objectives of these organizations are based around the promotion and strengthening of regional cooperation on fisheries development and the coordination and harmonization of efforts and capacities of stakeholders for the conservation and exploitation of fisheries resources. Memorandums of Understanding (MoUs) have been established between them to facilitate collaboration as memberships both overlap and are complementary. The focus of the RFBs is on fisheries management and in particular of shared or transboundary resources and their mandates do generally not cover postharvest and trade issues.

In addition to the above mentioned RFBs, the Fishery Committee for the Central Eastern Atlantic (CECAF) is an RFB established under the FAO constitution (Article VI) and it includes African FAO Member/Associate Member States along the Atlantic coasts as well as those that fish or carry out research in the area. The purpose of the Committee is to promote the sustainable utilization of the living marine resources within its area of competence by the proper management and development of the fisheries and fishing operations. Its working groups carry out stock assessments (links to reports are available at http://www.fao.org/fishery/rfb/cecaf/en) and CECAF also has an artisanal fisheries working group that was recently reactivated with new terms of reference.

The International Commission for the Conservation of Atlantic Tunas (ICCAT) is an inter-governmental fishery organization responsible for the conservation of tunas and tuna-like species in the Atlantic Ocean and its adjacent seas. All three Project countries are contracting parties to ICCAT.

Many of these RFBs are also working with the Abidjan Convention through existing and planned MoUs. The Abidjan Convention, a UNEP Regional Seas Program (RSP), is concerned with marine environment, coastal zones and related inland waters falling within the jurisdiction of the States of the West and Central African Region.

Table 2: Membership in marine RFBs

|  | Cabo Verde | Cote d’Ivoire | Senegal |
| --- | --- | --- | --- |
| ATLAFCO/ COMHAFAT | X | X | X |
| CECAF | X | X | X |
| ICCAT | X | X | X |
| FCWC |  | X | X |
| SRFC | X |  | X |
| Indian Ocean Tuna Commission (IOTC) |  |  | Cooperating non-contracting party |
| International Whaling Commission (IWC) |  | X | X |

There are also important GEF investments in LME projects in the West African region, including the Canary Current LME and the Guinea Current LME (GCLME). Other initiatives with a subregional level include the World Bank funded West Africa Regional Fisheries Program (WARFP) and the FAO Blue Growth Initiative (BGI). These and other relevant programs and projects are further discussed in chapter 1.2 on Rationale and baseline projects and investments below, and coordination of the different initiatives is also discussed in Section 2.

At the national level, the institutional structures vary from country to country but capacities tend in general to be inadequate for supporting coastal fisheries management and development. There is also a general lack of coordination and collaboration with environmental and other ministries and agencies. These weaknesses are further discussed below. Basic structures and policies for fisheries in the three countries are described below.

In Cabo Verde, fisheries fall under the Minister for infrastructure and maritime economy (Ministre des infrastructures et de l’économie maritime). The National Institute for Fisheries Development (Institut national de développement des pêches – INDP), based in Mindelo, São Vicente, is in charge of fisheries research and plays an important role in fisheries management and development. The main vehicle for consultation between the Cabo Verde government administration and fisheries sector actors is the National fisheries council (Conseil national de la pêche) that was established in 2005.

Coastal fisheries are guided by a Fishery Sector Policy paper and the multi-annual Plan for Fishery Resources Management 2016-2020 (Plan de Gestion des Ressources Halieutiques - PGRP). The current executive plan was published in March 2016 and covers 2016-2017. The PGRP reflects priorities contained in the National Environmental Plan of Action (NAPA) and other overarching policy instruments such as the Growth and poverty reduction strategy (Document de Stratégie de Croissance et de Réduction de la Pauvreté) and National Development Plan. The sustainable and integrated management of fishery resources is also one of the goals of its Comprehensive Africa Agriculture Development Program (CAADP).

In Cote d’Ivoire, there is a Ministry for animal and fishery resources (Ministère des Ressources Animales et Halieutiques). With regard to research, there is a network consisting of research centres and universities that share their results with the fisheries administration (Direction de l’Aquaculture et des Pêches) for the benefit of fisheries management.

The Cote d’Ivoire Poverty Reduction Strategy Paper (PRSP) from 2009 focuses on four principal outcomes: (i) re-establishment of the foundations of the Republic; (ii) transforming Cote d'Ivoire into an emerging economy; (iii) social well-being for all; and (iv) becoming a dynamic actor on the regional and international scene. Key policy documents relevant to the fisheries sector in Cote d’Ivoire include the Strategic plan for the development for fisheries and aquaculture (Plan stratégique de développement des pêches et de l’aquaculture) of 2014 and Plan d’Action de Gestion de l’Environnement Côtier.

In Senegal, fisheries are managed by the Ministry of fisheries and maritime economy (Ministère de la Pêche et de l’Economie maritime). Research is carried out by the Centre de Recherches Océanographiques de Dakar Thiaroye (CRODT). There is a National Advisory Council for marine fisheries and consultative councils at the local level. A new draft sector policy has recently been developed (Lettre de Politique Sectorielle de Développement des Pêches et de l’Aquaculture) in collaboration with FAO.

Senegal's third Poverty Reduction Strategy for 2013-17, renamed the National Strategy for Economic and Social Development, is articulated around three strategic pillars: 1) economic growth, productivity, and wealth creation; 2) human capital, social protection and sustainable development; and 3) governance, institutions, peace and security. Social and economic development is also guided by the (2014). Emerging Senegal Plan (Plan Sénégal Emergent), is the new reference framework for economic and social policy of the Government for the period 2014 – 2035, and is based on three pillars:

- A structural transformation of the economy through the consolidation of current engines of growth and the development of new sectors to create wealth, jobs, and social inclusion, with a strong capacity to export and attract investment

- A significant improvement in the well-being of the population, a more sustained struggle against social inequality, while preserving the resource base and supporting the emergence of viable regions

- The reinforcement of security, stability, governance, the protection of rights and liberties, and the consolidation of the rule of law in order to create better conditions for social peace and the fulfilment of potential.

1.1.4 Global Environmental Problems, Climate Change and Root Causes that need to be addressed

The contribution of coastal fisheries to environmental, economic and social sustainability in the Project countries is threatened by high fishing pressure, unsustainable practices and wastage in the postharvest sector leading to sub-optimal benefits, degradation of coastal habitats as well as poor working conditions and insecure livelihoods. Some of the root causes and drivers for this situation are found at the macro level outside the fisheries sector itself, e.g., population growth, the political economy and institutional context as well as climate change. Other root causes relate more directly to coastal fisheries and include weak governance arrangements and limited capacity of institutions to drive processes and to effectively regulate fishing, promote responsible practices and strengthen value chains as well as low capacity adapt to new emerging issues such as climate change and variability.

Fish stocks in the region of relevance to the three project countries are generally fully or overexploited. Not all stocks are assessed (see table below based on the CECAF 2015 Stock Status Report) and lack of data is one weakness for improving fisheries management. CECAF regularly reviews existing data through its scientific working groups and management advice for the stocks is given in relation to reference points.  On the basis of projections, this advice is intended to provide guidance to management on how to make the different stocks develop in a direction where each stock is exploited at an optimum level. More information on current stock status in 2015 can be found in the CECAF report on the 2015 scientific meeting.

Stock Assessments that include Cabo Verde, Senegal and Cote d’Ivoire

| Stock | Assessed |
| --- | --- |
| Small pelagics - CECAF North |  |
| Sardine S. pilchardus Zone A+B | Non-fully exploited |
| Sardine S. pilchardus Zone C | Non fully exploited |
| Sardinella S. aurita S.maderensis Sardinella spp. Whole subregion | Overexploited |
| Horse mackerel T. trachurus Whole subregion | Fully exploited |
| Horse mackerel T. trecae Whole subregion | Overexploited |
| Chub mackerel Scomber colias Whole subregion | Fully exploited |
| Anchovy Engraulis encrasicolus North Fishery Bonga Ethmalosa fimbriata | Overexploited |
| Small pelagics - CECAF South |  |
| Sardinella Sardinella aurita West12 | Overexploited |
| Sardinella maderensis West | Fully exploited |
| Bonga E. fimbriata West | No reliable results from model. Catches fluctuate annually |
| Anchovy (E. encrasicolus) West | fully exploited |
| Horse mackerel and other Carangidae Trachurus trecae West | No reliable results from assessments |
| Demersals- CECAF North |  |
| Arius spp | Non- Fully Exploited |
| Pseudotolithus spp. | Not conclusive |
| Epineplehus aeneus | Overexploited |
| Pagrus caeruleostictus | Not conclusive |
| Dentex macropthalmus | NA |
| Pagellus belottii | Non-Fully Exploited |
| Parapenaeus longirostris | Non-Fully Exploited |
| Parapenaeus longirostris | Non-Fully Exploited |
| Penaeus notialis | Overexploited |
| Octopus vulgaris | Overexploited |
| Sepia officinalis | Non-Fully exploited |
| Loligo vulgaris | Not Known |
| Demersals- CECAF South |  |
| Cephalopholis taeniops | Fully exploited |
| Muraenidae | Fully exploited |
| Pseudopeneus prayensis | Fully exploited |
| Seriola spp | No results from assessment |
| Diplodus spp | No results from assessment |
| Brachydeuterus auritus | Overexploited |
| Galeoides decadactylus | Overexploited |
| Dentex spp. | No results from model |
| Pagellus bellottii | Overexploited |
| Pseudotolithus spp | Fully exploited |

In the West Africa region, including in the project countries Cabo Verde, Cote d’Ivoire and Senegal, the marine and coastal environment and related ecosystems are impacted by a number of drivers and pressures. Some country level information include:

- In Cabo Verde, key threats to biodiversity in coastal and marine ecosystems include localized pollution and habitat loss due to infrastructure developments related to urbanization and rapid coastal tourism development, including construction, inappropriate tourist activities and solid waste disposal. Unsustainable fishing practices threaten certain species, including some highly-targeted species such as the endemic Cabo Verde Spiny Lobster (Palinurus charlestoni) and Conch species (Strombus spp). Bycatch of sea turtles (Chelonididea), as well as direct exploitation of adults and eggs for consumption, threaten these species also on-going conservation actions have improved the situation.

- In Cote d’Ivoire, the main threats to biodiversity are associated climate change; invasive alien species; epizootic outbreaks; overexploitation of biological resources (e.g. poaching, overfishing); habitat destruction (e.g. agriculture, exploitation of forests, urban development, pollution); structural causes (e.g. poverty; perception of the importance of biodiversity; weak conceptual and operational capacity).

- In Senegal, the major threats to biodiversity have been identified in Senegal’s National Biodiversity Strategy and include natural causes (drought and its consequences, water and soil degradation and salinization, wind and water erosion) and human causes (bush fires, over exploitation, land clearing, hydro-agricultural works, fragmentation and destruction of habitats, poaching and pollution).

At the regional and subregional level, the two large marine ecosystem  (LME) projects – the Canary Current (CCLME) and the Guinea Current (GCLME) – have identified key problems in their Transboundary Diagnostic Analyses (TDAs):

- The CCLME TDA identifies the following main shared and transboundary concerns:

- Decline of living marine resources, including fish and fisheries resources as well as marine species of conservation concern;

- Modification of natural habitat including (1) disappearance and destruction of mangroves; (2) degradation and modification of seabed habitats and seamounts; and (3) degradation and modification of wetlands (Ramsar: coastal zones, coral reefs, estuaries);

- Declining water quality: 1) modified transport of sands and sediments; 2) invasive alien species; 3) salinity changes upstream of river mouths; 4) increased levels of heavy metals in fishery products; and 5) pollution (various types).

- The GCLME TDA identifies the following four broad coastal and marine environmental problems and issues:

- Decline in GCLME fish stocks and unsustainable harvesting of living resources;

- Loss of ecosystem integrity (changes in community composition, vulnerable species and biodiversity, introduction of alien species) and yields in a highly variable environment including effects of global climate change;

- Deterioration in water quality (chronic and catastrophic) from land and sea-based activities, eutrophication and harmful algal blooms;

- Habitat destruction and alteration including, inter alia, modifications of the sea floor and coastal zone, degradation of coastscapes and coastline erosion.

The above concerns are addressed in the CCLME and GCLME Strategic Action Plans (SAPs) that will be implemented in the planned follow-up phases of the projects. The CFI Program is intended to be complementary to the LME projects and focus specifically on fisheries issues. The following description of root causes and problems hence focuses on fisheries and do not address other environmental threats. It is however recognised that environmental drivers and pressures are interlinked and that impacts are reinforced by a combination of problems. This project will hence be closely coordinated and work with the CCLME and GCLME to ensure a holistic approach (see also below)

With regard to governance weaknesses (mentioned in paragraph 0 above), a fundamental issue in the three countries is the compartmentalised way by which the fisheries sector tends to be dealt with. There is insufficient understanding of how the value chain functions and how its different links are interconnected all the way from harvesting to the consumer. Demand at the consumer level is generally not considered in fisheries management and efforts to improve the postharvest sector tend not to make relate to fisheries management. This leads to ineffective and even sometimes contradictory efforts to improve the sector and its sustainability.

Another aspect of governance relates to the need for adequate capacity and capabilities to address the often complex coastal fisheries issues. The over-exploitation of tuna in Cabo Verde is a critical example where insufficient institutional capacities combined with the government’s limited knowledge and control over the exploitation of this resource becomes a key obstacle to resolving it. In Cote d’Ivoire, old and inadequate policy, legal and regulatory frameworks for coastal fisheries as well as lacking administrative structures hinder effective fisheries management. In the case of Senegal, the absence of enforcement legislation (primarily regulatory texts) backing the relevant laws is a key issue as well as a lack of recognition and clarity concerning coastal fishing communities’ rights in fisheries co-management arrangements.

Fisheries value chains in West Africa are complex and lack transparency, and in particular small-scale actors have difficulties obtaining decent incomes. Inadequate postharvest infrastructure leads to quality deterioration, postharvest losses and poor revenues, exacerbating overfishing. In For example, in Cabo Verde, there are weak linkages between the tourism sector and the domestic food production sector and, as noted above, estimates suggest that about 80 percent of the fish eaten on the tourist islands is imported. Improving these linkages through the provision of higher quality, more regular supply, improved health and safety, and standardized products could benefit local fishers and create incentives for more responsible practices.

While co-management is increasingly recognised as a good practice, resource users feel marginalised from decision-making and lack incentives to engage in management and development processes. This concerns both fishers and fish workers in the postharvest sector. The understanding of the coastal fisheries value chain dynamics and how coastal fisheries are situated in a wider environmental, economic and social reality is not sufficiently taken into account. There is competition from other sectors in the coastal and marine areas (urbanization, mineral exploitation and tourism) and also within the fisheries sector itself with conflicts between traditional small-scale fisheries and large-scale fishing fleets. More fundamentally, the coastal habitats (in water and on land) are gradually being degraded, not only due to the multiplication of unregulated landing sites and processing activities (see also below on mangroves) but also because of pollution (industrial discharges, garbage, etc.) as well as uncontrolled urban planning and tourism (particularly in Cabo Verde). When tourist development leads to social conflicts because local communities only accrue limited economic benefits from tourism and are displaced to make room for tourist developments, there will be a lack of incentives for coastal populations to conserve biodiversity and natural resources.

Climate change amplifies these threats and complicates fisheries management as it can modify the abundance, composition and distribution of species, thus affecting fisheries, as well as amplify existing challenges (e.g. shoreline erosion, coastal flooding and pollution with subsequent impact on infrastructures, coastal communities and ecosystems). An inter-sectorial approach, a higher degree of policy coherence and use of appropriate participatory approaches would be needed.

Moreover, in spite of their importance, as illustrated by the figures above, the valuable role of fisheries for food and nutrition security and livelihoods is not always properly recognized and translated into national priorities for development. Paradoxically though there are quite a few projects and initiatives by development partners, donors and NGOs attempting to address in particular environmental concerns in the fisheries arena. This tends to result in an overall fragmented approach to fisheries governance and development as national capacities to lead and coordinate are inadequate.

Coastal fisheries are closely linked to coastal habitats and show high interdependence with coastal ecosystems. Mangroves represent ecosystems that are extremely important with regard to natural productivity and biodiversity, often constituting nursing grounds for fish. However, mangroves are not only important from a biological point of view but also from a socioeconomic perspective. In Cote d’Ivoire and Senegal, coastal communities depend on mangroves as firewood, including for fish smoking. In Cote d’Ivoire, the area of mangroves has been reduced by 50 percent between 1990 and 2015 and in Senegal by close to 16 percent for the same time period.

Degradation of coastal ecosystems such as mangroves may increase the vulnerability of coastal populations to climate change consequences, including extreme weather events and natural disasters. Climate change will have major impacts on most coastal and marine ecosystems and their associated fisheries through increased ocean temperatures, ocean acidification, sea-level rise and reduced productivity.

## 1.2 Rationale

##### 1.2.1 Baseline projects and investments for the next 3-5 years addressing the identified GEB threats and causes (main co-financing sources of the Project)

In general terms, the coastal fisheries baseline scenario in the three countries includes all government fisheries management arrangements and national level efforts to optimize the benefits generated by fisheries within EEZ. International (and regional) development partners provide support to these efforts in a variety of ways, including for improving regional collaboration. Key examples of initiatives are described here and emphasis to coordination with these and other relevant activities will be given during work planning at Project inception as well as throughout the Project, in particular through output 1.1.4 (see Section 2 below).

The main regional projects that this Project will collaborate and coordinate with include the GEF funded CCLME, GCLME and the WARFP. There is also the EAF Nansen project, which works closely with in particular the CCLME. The synergies between this Project and the WARFP, CCLME and GCLME are further discussed below in Section 4.The two LME projects will address key problems and barriers related to broader ecosystem considerations that lie outside the CFI Program that focuses on fisheries. Accordingly, the LME projects have components that explicitly address, among other things, the pollution and water quality concerns described above in addition to fisheries.

- The GEF funded CCLME is jointly implemented by FAO and UNEP. It includes Cabo Verde, the Gambia, Guinea, Guinea-Bissau, Morocco, Mauritania and Senegal. The CCLME is currently in its last year (2016) of its phase one and is developing a phase two proposal based on its agreed SAP. The SAP has three main objectives (i) Restore degraded fish stocks and vulnerable species; (ii) Rehabilitate and/or preserve critical habitats in marine and coastal areas, and (iii) Ensure that the water quality of the CCLME is of a high standard contributing to the good health of the ecosystem.

- The GCLME is also in-between phases with a second phase for implementation of the SAP pending. The fisheries component of the GCLME Phase II is to be led by FAO and is expected to include work on improving governance and strengthening fisheries management through the application of EAF and promotion of the CCRF.

The World Bank West Africa Regional Fisheries Program (WARFP) aims to sustainably increase the overall wealth generated by the exploitation of the marine fisheries resources of West Africa, and the proportion of that wealth captured by West African countries. Among the Project countries, the WARFP has been implemented in Cabo Verde and Senegal since 2010, focusing on (i) reducing illegal, unreported, and unregulated fishing (IUU); ii) strengthening good governance and sustainable management of the fisheries; iii) increasing contribution from fish resources to the local economy; and iv) monitoring and evaluation (M&E), and regional coordination through the SRFC. The first phase of the program will be closed at the end of 2016, and a second phase is currently under development in several countries, including in Cabo Verde and Senegal, focusing on regional, national and local level investments that reinforce and expand the investments of Phase 1 beginning in 2016. A first phase WARFP is also planned in Cote d’Ivoire in early 2017.

The regional component of the WARFP, focusing on communication, regional integration and M&E, has been implemented by the SRFC. The Commission, in which Cabo Verde and Senegal are members, has also been carrying out work on small-scale fisheries, small pelagic fisheries and marine protected areas (MPAs) in the region. Also related to regional integration is the GEF-funded Regional Partnership for African Fisheries Policy Reform, which supports the AU in taking the lead on a long lasting fisheries partnership mechanism for Africa (expected to close in 2018).

The EAF-Nansen Project Strengthening the Knowledge Base for and Implementing an Ecosystem Approach to Marine Fisheries in Developing Countries is an initiative to support the implementation of the ecosystem approach in the management of marine fisheries. The aim is to promote sustainable utilization of marine living resources and improved protection of the marine environment. The long term objective of the EAF-Nansen project is to strengthen regional and country specific efforts to reduce poverty and create conditions to assist in the achievement of food security through development of sustainable fisheries management regimes and specifically through the application of the ecosystem approach to fisheries in a number of developing countries at global level, with an early emphasis on Sub-Saharan Africa. The FCWC has been collaborating with the EAF Nansen project on, among other things, the development of management plans for key fisheries in the region.

FAO has a strong presence in the region also through other initiatives and the three Project countries have joined the FAO BGI in support of food security, poverty alleviation and sustainable management of living aquatic resources, with a view to streamline the Blue Growth concept into national fisheries policy. The BGI was designed to provide a clear pathway that can ensure fisheries and aquaculture are mainstreamed into Green or Blue Economies.  The initiative is aimed at reconciling economic growth with improved livelihoods and social equity, and strengthening transparent, reliable and more secure food systems. Blue Growth also places greater responsibility on national and regional policies for protecting and managing living aquatic resources. Both Cabo Verde and Cote d’Ivoire are engaging in developing BGI strategies.

Other FAO engagements include the Strategic response to HIV/AIDS for fishing communities in Africa project, which works in Cote d’Ivoire and other countries in the Gulf of Guinea and aims to enhance the contribution of fisheries to poverty alleviation and food security through reduced HIV/AIDS vulnerability in fishing and fish trade communities in Africa. Also in Cote d’Ivoire, FAO has worked together with NEPAD through the NEPAD-FAO Fish Project (NFFP) to strengthen women fish processing organizations and on the introduction of a new fish smoking oven, the FAO Thiaroye kiln (FTT). A Techncial Cooperation Project (TCP) was carried out (TCP/IVC/3501) and further activities on strengthening women postharvest workers and their organisations are carried out in the framework of the FAO Multi- Partner Programme Support Mechanism (FMM/GLO/003/MUL). The new FTT technology is proving popular in other African fishing nations as well, and its use is starting to spread in Senegal, Tanzania and Ghana. NFFP and the EAF-Nansen project have also commissioned a study on the impact of climate change on specific fisheries including small pelagic fisheries in Senegal.

The FAO – Norway project in support of the SSF Guidelines aims at enhancing the contribution of small-scale fisheries to food security and sustainable livelihoods through better policies, strategies and initiatives in FAO member countries and regions by promoting the application of the principles of the SSF Guidelines. The project is global but also carries out regional and national activities and Cote d’Ivoire is a candidate for support.

FAO and EU collaborate with regard to fisheries and food security. Guidance material is currently under development for reviewing sector policies in relation to food security and nutrition. For the West Africa region and the Project countries, two important recruitment processes are under way (April 2016): a FIRST Programme Senior Policy Officer for fisheries and aquaculture will be appointed in ECOWAS and another fisheries and aquaculture officer will be based in the FAO Representation in Cote d’Ivoire.

FAO collaborates with a selection of countries, including Senegal, on the FAO's Integrated Country Approach (ICA) for promoting decent rural employment. This initiative is not specific for fisheries but deals with the agriculture sector in general (including fisheries and forestry) to enhance the employment content of national strategies, policies and programmes for agricultural and rural development in order to optimize the contribution of the sector to improve the quantity as well as the quality of rural jobs.

There are projects aimed at the development of infrastructure, e.g., a project by the Japanese International Cooperation Agency (JICA) for fish landing sites and a central market in Cassandra, Cote d’Ivoire, and also assistance from Morocco for the construction of integrated fishing villages in Grand-Lahou and Locodjro/Abidjan. These projects are of particular importance to this project as synergies can be created by combining the infrastructure investments with support to capacity development and management systems and processes, taking a value chain perspective and focusing on the postharvest sector. In Mbour, Senegal, there is also the PROVOCAL, a JICA project promoting co-management in a value chain perspective and the two projects will be able to exchange experiences from their different locations of activities.

UNEP has been implementing relevant activities through, inter alias, the Abidjan Convention.  UNEP has been promoting the ecological foundation for food security and has been, together with FAO, designing a project for West Africa on securing foundation for food security through the partnership between the Abidjan Convention and relevant RFBs. Within the CCLME project, the UNEP component is attributed to habitat conservation and water quality management, which have close relevance to the fishery-relevant FAO components. As identified under the Abidjan Convention, the mangrove ecosystems are considered to be key and important ecosystems in the region, where many commercially important fish species spend part of their life.  UNEP, under the Blue Carbon Initiative, started addressing the conservation and sustainable use of mangrove ecosystem services with the important one being the service to function as fish habitats.

The Alcyon project, funded by the MAVA foundation and implemented by the International Marine Programme, has led work on marine conservation, marine spatial planning initiatives and seabird-fisheries interaction work in the region since 2013, with work in all CCLME countries. A second phase of Alcyon is planned to commence in 2017 (covering the same countries), which will explicitly address seabird bycatch matters in West African fisheries. This will be done in a framework of strengthening fisheries management systems nationally and regionally, sharing lessons learned from BirdLife International’s successes in reducing seabird bycatch elsewhere in Africa, Latin America and the high seas, building capacity and empowering fishers to understand and manage their impacts on the marine environment in a more sustainable way, and implementing key EAF elements.

The African Development Bank (AfDB) is engaging the strengthening value chains and will build on FAO’s experiences in Cote d’Ivoire supporting further work on the postharvest sector. The AfDB will also develop a project in relation to the FAO BGI in Cabo Verde which includes a strong fisheries component.

With regard to value chains, the United Nations Industrial Development Organization (UNIDO) project on sanitary and phytosanitary (SPS) norms in Cote d’Ivoire and Senegal aims at improving access to regional and international markets by small-scale fishers and fish workers through the improvement of fishery product quality within the framework of the World Trade Organization (WTO) Agreement on the Application of Sanitary and Phytosanitary Measures (SPS Agreement).

Regarding specific support to climate change, the NFFP carried out a gap analysis and organised a regional workshop on climate change, disasters and crises in the fisheries and aquaculture sector in Western and Central Africa in Accra, Ghana on 1–2 November 2012 to provide recommendations for addressing climate change adaptation and disaster risk management in fisheries and aquaculture. Four areas of adaptation and disaster risk management action were identified as follows: strengthened governance to address disasters and climate change impacts affecting fisheries and aquaculture; addressing and reducing underlying risks through prevention and adaptation measures; managing effective response and improving preparedness for disasters and climate change; and improved early warning systems and availability of information. The findings were used amongst other things to inform advice for the formulation of the Policy Framework and Reform Strategy for Fisheries and Aquaculture in Africa.

Other relevant projects include:

- The Go-WAMER project (Governance, Marine Resource Management Policies and Poverty Reduction in the West Africa Marine Eco-region) is co-funded by the EU and the UNDP for a six-year period.

- In Cabo Verde, there is an important GEF-UNDP project addressing biodiversity concerns and tourism sustainability: Mainstreaming biodiversity conservation into the tourism sector in synergy with a further strengthened protected areas system in Cabo Verde. This 5-year project is expected to start in 2016.

- The Regional Partnership for the Conservation of the Coastal and Marine Zone in West Africa (PRCM) was established as a combined initiative of several international organizations i.e. IUCN, MAVA, WWF, and Wetlands International, in partnership with the SRFC. It is primarily focused on conserving and sustainably managing the natural resources, biological and cultural diversity of the marine and coastal zone in West Africa. Projects are funded and implemented within the framework of three components, namely: Conservation of biodiversity, sustainable fisheries, and integrated management.

- The Collaborative Management for a Sustainable Fisheries Future (COMFISH) project in Senegal promotes sustainable fisheries co-management and to support the government of Senegal’s efforts to achieve reform of its fisheries sector (USAID through the Coastal Resources Centre [CRC] of the University of Rhode Island).

There are also other completed, on-going or planned projects and initiatives in the three countries and the region and it will be important for the Project to ensure broad collaboration, as appropriate. The Project contains an output explicitly supporting improved coordination and capitalisation of experiences (output 1.1.4) and component 3 of the Project deals with strategic communication and up-scaling of good practices at regional and global levels (see also Section 2).

##### 1.2.2 Remaining barriers to address

Although progress is being made in improving governance of the coastal fisheries in the three countries, the pace and scope of the various initiatives need to be augmented substantially given the increasingly adverse impacts on the valuable fish stocks, fishing communities and ecosystems. There is a need to deal simultaneously with improving fisheries governance and management and strengthening the seafood value chains in order to create environmental, economic and social benefits. This can only be accomplished by taking a value chain perspective, combining implementation of fisheries management plans using EAF and supporting postharvest activities. To be successful, an approach that synchronizes the implementation of both legal and operational measures is required. Furthermore, success will largely be dependent on the active participation of all stakeholders and consequently it is essential to strengthen stakeholder representation and engagement as well as to improve overall communication and cooperation for sharing experiences, lessons and best practices among the three countries.

It must also be recognized that sustainable coastal fisheries is a long-term goal and hence cannot be achieved completely within a five-year period. Thus the present Project should be seen as the first phase, focusing on putting the necessary structures in place, of an undertaking with a longer time horizon.

Accordingly, within the context of concerns described above, the main barriers to eliminating, or at least reducing, the threats to coastal fisheries and their contribution to livelihoods, food security and sustainable development in the three Project countries in West Africa can be summarized as follows:

- Insufficient and fragmented knowledge on the dynamics of the value chain and on approaches allowing for addressing coastal fisheries in a holistic and integrated way.

- Lack of the tools, means and institutional arrangements to create the necessary enabling environment for successful coastal fisheries.

- Lack of attention to and recognition of the role of coastal fisheries actors and resource users in promoting responsible fisheries and sustainability, in particular with regard to women in the postharvest sector.

The weak governance arrangements and limited capacities of the institutions dealing with coastal fisheries in the three countries are due a complex mix of circumstances. One dimension is the lack of a knowledge base that can provide direction. The experiences and lessons acquired over time by the various institutions and development partners involved in coastal fisheries are not sufficiently shared – not in the subregion, nor between or within the three countries – and hence not converted into good practices and sustainable management. The insufficient coordination between the numerous and sometimes overlapping support programs and projects tends to exacerbate this situation. For instance, inter-institutional cooperation is considered almost inexistent in Senegal while it is recognized that the challenges observed would require coordinated and even joint actions.

The capacities and capabilities to apply approaches that allow for addressing the problems in coastal fisheries holistically and in an integrated manner are inadequate, e.g., with regard to the EAF and a human rights based approach to development as promoted by the recently endorsed the SSF Guidelines.

Moreover, there is insufficient knowledge on how demand for fisheries products influences production through the different value chain stages and how incentives for responsible fishing could be created. The potential for promoting responsible fishing and improving resource sustainability by actions integrated throughout the value chain is hence not recognized and issues related to primary production – the fishing subsector – and the postharvest subsector tend to be addressed separately, not together. A frequent lack of coherence and quality of the data available, particularly for market dynamics and environmental considerations, worsens the problem.

While reviews and updates of policy and legal frameworks are currently under way in all three countries, there are still considerable needs in ensuring that these frameworks are adequate and allow for operationalizing EAF and implementing relevant international instruments such as the SSF Guidelines. Moreover, coastal fisheries laws and regulations – including those concerning sanitary, health and labour standards – have limited effectiveness if the related public and private institutions do not have the necessary capacity for their implementation. In many cases, the concrete tools for implementation are missing, e.g., regulatory texts have not been finalized and existing fisheries management plans are not put into practice because of a lack of implementation plans.

The necessary incentive measures – financial or otherwise – for resource users to engage in management and development processes, or to comply with existing regulations, are inappropriate or inexistent. In particular in the small-scale fisheries sector, these actors often have low educational levels and technical skills as well as a general lack of organizational and planning capacities. There also tends to be a lack of clarity with regard to how they should participate in decision-making processes and co-management. In addition, because of inadequate financial facilities, small-scale operators (in particular women processors) are often at the mercy of those of have sufficient financing and behave opportunistically. The economic value of fish processing and marketing is typically understated in the governments’ public accounts and insufficient attention given to supporting the postharvest actors. This is coupled with a lack of understanding how the wastage along the value chain – postharvest losses are estimated at more than 25 percent of the production from the net to the plate – impact negatively on resources and how a reduction of this waste could conversely lead to more sustainable fishing. Moreover, there is limited control of a lack of appropriate infrastructures for handling of produce when landed as well as for effective processing, in particular for fish smoking that is often carried out with traditional methods requiring high levels of fuel wood and creating precarious working conditions.

Women play a critical role in every link of the value chain in small-scale fisheries but because of their often unrecognized or underrewarded fisheries-related activities, women continue to be best known for their roles processing/ marketing of fish and related products. However, this generalization can make projects and fisheries governance blind to women's other valuable inputs to the sector. A gender analysis is needed to better understand the importance of the post-harvest and livelihood/food security support that women provide, barriers that they face, as well as other roles women can and should play, including fisheries resource management, policy decisionmaking, and access, rights and ownership of other resources/materials, e.g., gear and boats as well as legal recognition for women’s processing groups and access to financial resources. As a consequence this project will do a gender analysis and strategy during project inception.

Based on the above, the barriers to be addressed by this Project are:

- Ineffective and non coherent fisheries policies, strategies and actions

Legal and policy frameworks are inadequate and while initiatives are under way to review these, there is still not sufficient consideration of EAF and the implementation of relevant international instruments. There is generally limited knowledge among decision-makers and politicians on the importance of EAF and the need for implementation of international instruments. Moreover, there are no mechanisms at national level for assessing how well fisheries policy contribute to overall food security and development goals. Initiatives and activities with regard to fisheries management are often driven by donors and development partners and governments have limited capacities to ensure consistency, take ownership of results and manage a viable implementation process

- Lack of effective and systematic fisheries management based on EAF

There are several management plans that have been developed by development partners in the three countries but that have not yet been implemented. Often the provisions for operationalizing them are lacking. Some of these plans also need to be reviewed to ensure that they comply with EAF and that coastal habitats, including mangroves, are considered. Management plans also need to consider relevant international instruments and foresee the necessary support measures to make them implementable taking livelihoods of coastal communities into consideration. Capacities for implementing fisheries management, in particular in a holistic manner, are lacking both on behalf of government authorities and resource users.

- Coastal communities do not have the capacities and opportunities required to participate in fisheries management and development processes

Co-management is promoted but the regulatory and institutional tools and capacities are not yet in place for its successful implementation, including the capacity of coastal communities to effectively engage in and contribute to management and development processes. Fisher and fish worker organisations are non-existent or generally weak and do not always represent the real stakeholders.

- Low quality of fishery products, postharvest losses and unhealthy and difficult working conditions in the coastal fisheries value chain

Postharvest losses are estimated to some 20-25 percent, sometimes up to 50 percent, in Africa and occur in particular in the artisanal sector. Practices for artisanal fish processing, in particular smoking, constitute a health hazard and consume precious wood (mangroves) with negative environmental effects. There are successful examples of improving both product quality and working conditions in the region, in particular in Cote d’Ivoire.

- Inefficient coastal fisheries value chains and lack of incentives for adopting better practices

There is limited understanding and consideration of the how the different stages of the value chain are linked and contribute to sustainable fisheries and livelihoods. Postharvest actors are generally not part of decision-making with regard to fisheries management and tend to have insecure access to resources.  Small-scale processing and trading activities do not to have a recognised professional status and unequal competition for catches implies risks for in particular women processors and contributes to poverty and unsustainable coastal fisheries.

- Knowledge and lessons learnt are not sufficiently communicated and shared

There is limited exchange of experiences and lessons learnt among governments, development partners and regional organisations. Coherent approaches to fisheries governance and management are lacking both at national and regional levels.

Each of these barriers corresponds to a Project outcome. Project outcomes, outputs and intended activities are described in Section 2.

##### 1.2.3 Incremental/additional reasoning

Without the present Project and GEF financing, individual initiatives – such as those described in the baseline situation – could still be continued and new ones undertaken, but at a much slower pace and in a more fragmented manner, with far more limited prospects of useful impact. In contrast, the Project will create a critical mass and concentration of efforts that could generate even stronger political will and yield significant results.

The CFI has been developed based on the recognition of the importance of coastal fisheries, the richness of initiatives and experiences in coastal fisheries but also that there is still no globally agreed solution to how to make them environmentally, economically and socially sustainable. Because many actors work independently from one and other and because there is limited capacity in many countries, in particular developing countries, to analyze, coordinate and effectively steer various initiatives towards a similar outcome, there is a great need to improve collaboration and to identify and refine agreed best practices.

As a Programme, consisting of 5 interlinked Projects, the CFI will play an important role in catalyzing greater collaboration and fostering knowledge sharing in coastal fisheries.The CFI will examine how different approaches work in different situations – at the same time as impact is generated on the ground – through its regional/national child projects and in bringing this new knowledge to the international arena to be examined, shared, understood and replicated, as appropriate. The CFI will also examine existing initiatives and results generated by such programmes and projects with a view to identify good (and bad) practices, including from ongoing LME projects. The CFI will work towards a more harmonized view on what different approaches and concepts in coastal fisheries mean and can do and promote a more holistic process for and integrated perspective on sustainable management. This implies an integration of approaches and priorities in respect of sector-focused management, safeguarding of human well-being, biodiversity and ecosystem health, postharvest and value chain, and wealth and investments. The CFI as a Programme will therefore deliver much more than just the sum of its Projects; while individually, the Projects will deliver valuable outputs in their geographies, aggregation of the knowledge gained from activities across a range of projects and contexts, together with the synthesis and dissemination of that knowledge, is something that can only be done at the global level, and thus the CFI is somewhat unique in this respect.

The Programme consists of 5 inter-linked Projects that benefit from, and contribute, to each other to ensure a Programme that is greater than the sum of its individual parts(Appendix 9). At the core of the Programme are three regional projects (West Africa, Latin America and Indonesia – totaling 6 countries), which are structured to test and pilot frontier tools and approaches in these three geographies. Each regional project is tailored to its own regional context, and contains unique elements (e.g. CFI-Indonesia is developing a trust fund; CFI-LA is conducting an Ocean Health Index assessment; CFI West Africa is improving working conditions). There are also some similar or common elements such as integrating “ecosystem based management” into fisheries policies, promoting marine protected areas and furthering gender equality. The outcomes of these elements will be shared between projects, creating opportunities to learn from each other’s unique experiences as well as draw lessons across common elements – so that each project will benefit from, and contribute to, the other projects. With respect to the activities in the other projects, specifically Latin America and Indonesia there are areas of interest for this project: the fisheries management experiences of developing FIPs and traceability systems in Latin America and Indonesia; while this project will not undertake CMSP, erosion is significant in the three countries of this project and there will be interest in how this issue will be dealt with in Latin America; and the challenges the other two projects face in applying the FPAI and its influence in policy and management decision making.

These three regional projects are supported by the Challenge Fund Project, which will provide technical asssistance for the development of a pipeline of investable projects, while providing a platform for interested investors to engage early and adequately assess—and address—potential investment risks. The ultimate outcomes are private investments made in the fisheries of the three regions.The Challenge Fund will benefit the West Africa project by providing access to technical assistance for developing investable projects and ties to potential investors in the post-harvest sector and possibly empowering women’s groups. At the same time, the regional projects will contribute to the Challange Fund by  providing local knowledge and context, including fisheries assessment information.

Coordination of CFI , including ensuring the projects are working together as a Program, assessing fisheries management performance (via the Fisheries Performance Indicators project), conducting analyses of the four projects’ outcomes and M&E activities, and sharing knowledge within and beyond the CFI Programme, will be managed through the Global Partnership Project. The FPA project will develop a methodology for fisheries assessments from a social, economic and environmental perspective specific to data poor contexts. It will be piloted in the three regions to consolidate the tool for wider dissemination globally. It will benefit the projects by providing access to the latest tool for assessing the status of their fisheries esepcially for data poor fisheries which applies to many of the fisheries in West Africa including the three countries of this project and the projects will contribute to FPA by serving as a testing ground for the tool with a focus on data poor fisheries in three countries in West Africa.

Similarly the Partnership Project will play a key role in knowledge sharing and analyses of outputs and outcomes across the three regions and with coastal fisheries globally for the production of global knowledge products and coordination of dissemination mechanisms (e.g. listserve, webinars, knowledge products, website, workshops, newsletters, blogs, stakeholder exchanges, conferences) (Figure 2). Contributions from the other 4 projects will be critical to the success of this KS.  At the same time, the other four projects will benefit from learning about experiences from the other projects as noted earlier. Given the importance of M&E and KS, for each project a total of 25% of funds have been allocated to these components, including 5-10% for M&E, 10-15% for KS within the project and 10-15% for KS with the program. Knowledge sharing products, including the themed product that this project will champion, developed in this project as well as the lessons learned will be shared through the various platforms coordinated by the Global Partnership as well as through regional and national platforms (Figure 2). These platforms will also enable stakeholders in the West Africa project to learn from other projects and partners. For this project more than 25% of the total budget is allocated to knowledge sharing and monitoring and evaluation, with approximately 5% of the budget for M&E.

Overall guidance of the programme will be provided by a Global Steering  Committee and technical advice as needed through a Global Reference Group. Both entities will be constituted at Project Inception.

The CFI Program is informed by the CFI Theory of Change (Appendix 11), which identified a series of tiered building blocks critical to achieving the program’s outcomes.  The projects are expected to progress through these tiers starting with establishing necessary enabling conditions (Tier 1), which will lead to implementing changes in practices (Tier 2), achieving benefits to fisheries and stakeholders (Tier 3) and ulimately leading to system sustainability (Tier 4) (Figure 3).

Figure 2:  Knowledge Sharing Platform

Figure 3: Theory of Change

This Theory of Change, therefore, provides a programme-level framework for the analysis of emerging challenges, learning and evaluting CFI impacts across the various initiatives making up the CFI.

The Program Results Framework builds upon the CFI Theory of Change, specifically the Tier 1 enabling conditions, which are focused around conditions and incentives for stakeholders, institions and collaboration. As noted in the first component, CFI will promote sustainability incentives in the value chain addressing the need for correct incentives at the harvesting stage, including new or amended management regimes, reduction in post-harvest losses, implementation of private-public partnerships and development of innovative market incentive systems. As noted in the second component, CFI will strengthen institutional structures and processes, including policy, legislation and institutions, including co-management and access rights regimes, and integrate MPAs into fisheries.  Finally, as noted in the third component, CFI will share best practices, promote collaborate and strengthen fisheries performances measures and assessments.

Within the Programme, the objective of the West Africa Project is to build upon ongoing national and regional initiatives in the three countries, bringing examples of good practices in terms of governance, value chains and community participation, and explicitly linking local achievements with national strategies and action plans. Moreover, the Project will provide additional support to existing national and local processes to facilitate the transition of strategic and management planning measures to the operational level. For the small-scale fisheries sector, the SSF Guidelines will be followed. Examples of expected synergies include analysing and building on good practices for co-management developed by the WARFP in Senegal and Cabo Verde and on the achievements within post-harvest technology development at the community level funded through the FAO Framework Agreement (FMM) with the Netherlands in Cote d’Ivoire. Furthermore, the carrying out of these activities will be supported by strengthening existing institutions, coupled with putting into place economic incentives and additional consultative mechanisms as required.

The CFI Programme Results Framework provides the structure that guides the 5 projects. The first component of this project is in line with the CFI Programme which will strengthen institutional structures and processes with a focus on EAF, including policy, legislation and institutions, including co-management and access rights regimes, and in the case of West Africa incorporate management and conservation of mangroves into fisheries management regimes. Similarly, the second component of the West Africa is totally aligned to the CFI programme and promotes sustainability incentives in the value chain addressing the need for correct incentives at the harvesting stage, including new or amended management regimes, reduction in post-harvest losses, implementation of private-public partnerships and development of innovative market incentive systems. Finally, as noted in the third component and as per the CFI, this project  will share best practices, promote collaboration and strengthen fisheries performances measures and assessments.

The Project and its activities will build upon ongoing national and regional initiatives in the three countries, bringing examples of good practices in terms of governance, value chains and community participation, and explicitly linking local achievements with national strategies and action plans. Moreover, the Project will provide additional support to existing national and local processes to facilitate the transition of strategic and management planning measures to the operational level. Examples of expected synergies include analysing and building on good practices for co-management developed by the WARFP in Senegal and Cabo Verde and on the achievements within post harvest technology development at the community level by the NFFP in Cote d’Ivoire. Furthermore, the carrying out of these activities will be supported by strengthening existing institutions, coupled with putting into place economic incentives and additional consultative mechanisms as required.

Experience from the development of fisheries management plans following an EAF approach, building on the experiences of the EAF-Nansen project and the CCLME will be harnessed. Project activities will be complementary and support the implementation of the SAPs of CCLME and GCLME. The Project will also strengthen the capacity of the countries involved to contribute to regional initiatives such as the work of RFBs providing examples of good management practices and procedures that can be scaled up to other countries in the region.

## 1.3 FAO’s and UNEP’s comparative advantages

Within the overall mandate of FAO to eradicate hunger and malnutrition, to eliminate poverty and to promote sustainable utilisation of natural resources, the FAO Fisheries and Aquaculture Department develops technical guidance, standards and instruments for a wide range of fisheries management and development issues. The Department provides technical inputs to the Committee on Fisheries (COFI), which is presently the only global inter-governmental forum where major international fisheries and aquaculture problems and issues are examined. COFI is also used as a forum in which global agreements and non-binding instruments are negotiated. The Code of Conduct for Responsible Fisheries (CCRF), developed by FAO and endorsed by Member States in 1995, remains a fundamental document for fisheries governance around the world. With regard to small-scale fisheries, the SSF Guidelines were developed and endorsed in 2014. These guidelines, complementing the CCRF, were endorsed by COFI in 2014 and provide a framework for enhancing the understanding of actions needed for small-scale fisheries governance and development.

FAO has a long history of support to the creation and strengthening of RFBs and RFMO/As and of providing technical support to GEF Large LME programs. Hence, FAO has an acknowledged global mandate with competences in regard to the technical and developmental areas covered by the Project.

Gender equality is central to FAO's mandate to achieve food security for all by raising levels of nutrition, improving agricultural and fisheries productivity and natural resource management, and improving the lives of rural populations. FAO has launched the Policy on Gender Equality – Attaining Food Security Goals in Agriculture and Rural Development to attain this goal (see also chapter 1.5 below).

UNEP is the leading global environmental authority that sets the global environmental agenda, promotes the coherent implementation of the environmental dimension of sustainable development within the United Nations system and serves as an authoritative advocate for the global environment. UNEP is the Secretariat of the Abidjan Convention, which has a regional coordinating unit in Abidjan, Cote d’Ivoire.

## 1.4 Participants and other stakeholders

The Project has taken a participatory design approach and several stakeholder meetings have been held, at the national and regional levels, for the development of the Project. Participation has included representatives from civil society organizations and of fishers’ and fish workers associations, in addition to government representatives and partner organisations.

Key partners and stakeholders to the Project include:

- National authorities responsible for fisheries management: The institutional set-ups vary from one country to another (see chapter 1.2 above) but the formal Project co-executing partner in each country is the fisheries authority or institute as listed at the front page of this Project Document. Generally, Project countries experience constraints in terms of capacity (as described above) and the intention of the Project is to strengthen the capacities of the national authorities.

- Civil society organizations (CSOs) and the private sector: Fishers and fish workers and related enterprises in both harvesting and accessory activities, such as postharvest processing and marketing, constitute a key group of stakeholders as they are directly concerned by the Project and what the Project is trying to achieve. Small-scale fishers, fish workers and communities tend to be organized in associations or civil society organizations (CSOs). There is generally a need to strengthen these organizational structures and build capacity to allow actors to become effective partners in co-management. The Project will work extensively with in particular women’s postharvest and fish smoking organisations, building their capacity at the same time as promoting their involvement in decision-making for coastal fisheries management and development. CSOs and professional organizations that already have a certain level of capacity will collaboration with the Project to help develop capacity of others. Noting the selected Project sites (see paragraph 0 and Table 3), the following organisations were engaged in the project preparation grant (PPG) phase and have been pre-identified for collaboration with the Project (list to be validated/complemented during Project inception) (see also below):

- Cabo Verde:

Association des Pêcheurs de S. Pedro, Federation des Associations de Pêcheus de l'Aire Marine Protegé de Santa Luzia et Ilots   Branco et Raso and Association des Armateurs de Pêche du Cabo Verde (Sao Vicente) - S. Luzia, Maio and S. Vincente are the 3 isles proposed as specific GEF CFI pilot sites but all the others CSOs mentioned for Cabo Verde will be involved in component 1 "improving fisheries governance and management (co-management) in continuation of the co-management pilot experience develop by WARFP programme and other projects by reinforcing CSOs capacity and involvement in the management process and regulation. These professional Associations will be concerned and engaged in the component 2 for strenghtening the seafood value chain to benefit to women’s groups and SSF communities

Association des Acteurs de Co-Gestion des pêches Venues du Sud and Association des Acteurs de Co-Gestion des pêches Venues du Nord (Maio) Maio is engaged due to their extensive experience in co-management systems through the World Bank WARFP programme and the objective is to reinforce the CSOs capacity and support them to implement the institutional reforms proposed as TURFs system for co-management and the  participatory process. Similarly they will be involved in the value chain to reinforce capacity building and to increase the benefits and improve livelihood for SSF community from a gender perpective.

Fishers’ Association – Palmeira, Sal (WARFP project site). The Sal CSOs are involved in the local economy in relation to tourism and ecotourism and they can reinforce inclusive and support for a more integrated economic development on Palmeira.

- Cote d’Ivoire: The Fédération Nationale des Coopératives de Pêche de Côte d’Ivoire (FENACOPECI)

- Senegal (and region, as appropriate): The African Confederation of Artisanal Fisheries Professional Organizations (Confédération Africaine des Organisations Professionnelles de la Pêche Artisanale - CAOPA)

- Senegal: Réseau des femmes de la pêche artisanale du Sénégal (REFEPAS)

For the Senegal and for the Ivory Coast the project has been defined by the broad participation of the CSOs’ federations which included all the specific CSO covering women associations for processing and marketing,  and small fishermen groups. Their interests in this project include the development of a national proposal to reinforce co-management systems (the design and conditions for their implementation at the national level) and to test the feasibility of some proposals at specific geographical locations with specific CSO sub-groups members of the federation for different value chain conditions.

- Regional organisations and development partners: as described above.

- National and regional science/research institutions (research institutions and universities): relevant research partners will be identified at national and local level during the project inception phase and collaborative agreements put in place for the implementation of specific Project activities. Relevant institutions will also be invited to Project workshops and awareness raising activities, as appropriate.

- Non-governmental organizations (NGOs) working on fisheries in the region: although NGOS were invited to the initial planning meetings and did not attend or show intereste in the projet, nvevertheless relevant NGOs (to be identified during Project inception and implementation) will be invited to collaborate with the Project, as appropriate.

- Two non-governmental organizations (NGOs) [SOS-Forêts à son siège social au Centre National de Floristique d’Abidjan-Cocody and H2O based in Abidjan] working on mangroves in the region were consulted during the PPG phoase and will be engaged in the mangrove work, as well any other relevant NGOs identified during Project inception and implementation will be invited to collaborate with the Project, as appropriate.

- Relevant fisheries industry groups and other organisations: the Project will work with international organisations promoting fisheries and seafood sustainability and relevant industry groups, e.g., the Marine Stewardship Council (MSC) and CONXEMAR (Spanish Association of Wholesalers, Importers, Manufacturers and Exporters of fish products and Aquaculture). These organizations will provide important links to and knowledge about international markets and global trade and provide support to Project capacity development for local, regional and national fisher and fish worker organisations. The Project will also work with BirdLife International to incorporate relevant ecosystem dimensions in legislative reforms and fisheries management plans.

Several of the stakeholder groups mentioned above have committed co-funding to the Project:

- The women fish processors organised through the FENACOPECI will both continue work already initiated through FAO collaboration (see above) to improve their practices, working conditions and livelihoods, and support the Project in reaching out to other postharvest.

- CAOPA is a sub-regional small-scale fisheries professional organization that will work with the Project to ensure participation of small-scale fisheries actors, in particular in Senegal.

- Fishers’ Association – Palmeira, Sal – Cabo Verde – have participated in Project planning and has experience from the WARFP.

- Marine Stewardship Council (MSC) will provide technical support on matters related to their area of expertise in certification and fisheries improvement programmes (e.g., output 2.2.3).

- BirdLife International will provide in-kind contributions in the form of their knowledge on ecosystem approaches in particular in relation to fisheries management.

- CONXEMAR will facilitate participation (including travel funds) of representatives from the three countries, in particular (women) fish processor organisations, to go to their annual Vigo exhibition/conference and hence promote trade contacts and capacity building accordingly.

## 1.5 Links to national development goals, strategies, plans, policy and legislation, and FAO’s Strategic Objectives

##### a) Alignment national development goals and policies

The present Project is fully in line with the relevant goals and policies of the three countries. The main sector policies of the three countries were mentioned in the chapter 0 in the text on Policy and institutional frameworks above:

- Cabo Verde’s Fisheries Policy Strategy paper promotes sustainable and integrated management of fishery resources in order to improve the levels of food security and living conditions of communities. In the NAPA, Cabo Verde includes support to populations that live off the exploitation of coastal resources including small-scale fisheries. Furthermore GPRSP and NDP identify fisheries as a key sector.

- In Côte d’Ivoire the Strategic plan for the development for fisheries and aquaculture highlights three main areas of work:

- Sustainable and Responsible Management of Aquatic Resources, including Development and validation of a draft Law on Fisheries; Development of fisheries management plans; Strengthening of the surveillance of the EEZ; and Strengthening the fight against illegal fishing.

- Improving productivity and competitiveness of fisheries, including Construction / rehabilitation of landing sites, fish markets; Signing of new fisheries agreements with other countries; and Fishing port construction

- Enhancing capacity of fishery stakeholders, including Accompanying the implementation of professional organisations; Strengthening the technical and managerial capacities of professional organizations; Rehabilitation of basic and advanced training schools; Strengthening capacity of the fisheries administration/agency; and Support to fisheries research.

- Senegal’s Plan Sénégal Emergent (2014) paragraphs 307 and 308 identifies as priorities (i) Sustainable management of fisheries resources and marine habitat restoration through the development and implementation of fisheries management plans, promotion of co-management, and (ii) Increasing value addition through establishment of integrated clusters for industrial and artisanal processing and reduction of post harvest losses. The prerequisites for achieving this include the adaptation of the regulatory framework; landing, storage and processing infrastructures, improved marketing conditions and safety and quality of products; and improved access management.

The regional Policy Framework and Reform Strategy for fisheries and aquaculture in Africa, adopted by the Conference of African Fisheries and Aquaculture Ministers (CAMFA) in 2014, was also referred to above. This regional policy framework identifies seven policy objectives including:

- Enhancing conservation and sustainable use of fisheries resources through the establishment of national, and sub-national governance and institutional arrangements that ensure the societal contribution generated by Africa’s sectors;

- Developing sustainable small-scale fisheries by improving and strengthening the contribution of those fisheries to poverty alleviation, food and nutrition security, and socio-economic benefits of fishing communities and beyond;

- Promoting responsible and equitable fish trade and marketing by significantly harnessing the benefits of Africa’s fisheries and aquaculture endowments through accelerated trade and marketing;

- Strengthening South-South (bilateral and regional) cooperation, and developing coordinated mechanisms among RECs, RFBs and LME-based commissions to ensure coherence of fisheries policies and aquaculture development and their adoption and adaptation.

##### b) Alignment with NAPA, NAPs, NBSAP, NIPs, NAMA

The Policy Framework and Reform Strategy for fisheries and aquaculture in Africa, adopted by the Conference of Fisheries and Aquaculture Ministers (CAMFA) in 2014, identified seven policy objectives including:

- Enhancing conservation and sustainable use of fisheries resources through the establishment of national, and sub-national governance and institutional arrangements that ensure the societal contribution generated by Africa’s sectors;

- Developing sustainable small-scale fisheries by improving and strengthening the contribution of those fisheries to poverty alleviation, food and nutrition security, and socio-economic benefits of fishing communities and beyond;

- Promoting responsible and equitable fish trade and marketing by significantly harnessing the benefits of Africa’s fisheries and aquaculture endowments through accelerated trade and marketing;

- Strengthening South-South (bilateral and regional) cooperation, and developing coordinated mechanisms among RECs, RFBs and LME-based commissions to ensure coherence of fisheries policies and aquaculture development and their adoption and adaptation.

National Biodiversity Strategies and Action Plans (NBSAPs) are the principal instruments for implementing the Convention of Biological Diversity (CBD) at the national level (Article 6):

- The revised NBSAP (2016-2020) of Cote d’Ivoire focuses on six strategic directions: protection of natural environments and their functions and services; preservation of species diversity and genetic diversity; strengthening of conservation infrastructure; valuation and sustainable use of biodiversity; mobilization of civil society and diffusion of knowledge on living organisms; and strengthening national coordination and international cooperation.

- Senegal’s new Stratégie Nationale et Plan National d’Actions pour la Biodiversité was formulated with the guidance in Decision IX/8 taken into account. Its vision to 2030 considers the global biodiversity agenda and the country’s new socioeconomic development plan to 2035, known as “Plan Sénégal Emergent”, among other plans. Four strategic directions aim to: improve biodiversity knowledge and strengthen institutional and technical capacity; reduce pressures and restore and conserve biodiversity; promote biodiversity accounting in socioeconomic development policies; and promote the sustainable use of biodiversity and mechanisms for accessing biological resources and equitably sharing the benefits derived from them.

- In Cabo Verde, the NBSAP for the period 2014-20130 sets seven national priorities: (i) civil society involvement (population, public and private organizations, NGOs and associations) in biodiversity conservation; (ii) mainstreaming biodiversity into strategies, policies, plans and programs of action; (iii) reducing pressures and threats on biodiversity; (iv) conservation of priority habitats and sustainable management of natural resources; (v) recovery and increased resilience of ecosystems; (vi) increased knowledge, monitoring and evaluation of biodiversity, and (vii) mobilization of funds.

The Project aligns with these NBSAP priorities in the three countries as it aims at improving sustainable resource utilisation and has a strong focus on stakeholder involvement and institutional strengthening.

##### c) Alignment with GEF focal area strategies and Aichi targets

The CFI Program as a whole is part of the GEF-6 International Waters Focal Area Strategy and it is expected that successful coastal fishery reforms will aggregate up to an intervention model that could be expanded also into geographic areas outside the current CFI scope at multiple scales.

This Project will in particular contribute to the International Waters Program 7: Fostering sustainable fisheries, which gives a focus to the use of ecosystem-based approaches – such as EAF used by this Project – and the need to strengthen fisheries institutions, promoting market platforms, introducing or expanding the use of sustainable standards through the supply chain and, as appropriate, experimenting with and testing, among other things, the scaling up of rights-based approaches. The program also aims at the implementation of international agreements and at stimulating effective and coordinated regulations. The GEF strategy also supports the piloting and scaling-up of successful local initiatives on small-scale coastal fisheries, which collectively have the largest impact on biodiversity, food security and incomes. All of these aspects are included in the present Project.

The Project will also contribute to the GEF-6 focal area strategy for Biodiversity No 4 Mainstream biodiversity conservation and sustainable use into production landscapes/seascapes and sectors, Program 9:  Managing the human-biodiversity interface. The Project will support ecosystem restoration by its focus on mangrove rehabilitation and strengthening existing mangrove management arrangements, in particular in Cote d’Ivoire but also in Senegal. This is also in support of the Aichi Target 5: By 2020, the rate of loss of all natural habitats, including forests, is at least halved and where feasible brought close to zero, and degradation and fragmentation is significantly reduced.

The Project will also contribute more generally to the Aichi targets, particular Target 6: By 2020 all fish and invertebrate stocks and aquatic plants are managed and harvested sustainably, legally and applying ecosystem based approaches, so that overfishing is avoided, recovery plans and measures are in place for all depleted species, fisheries have no significant adverse impacts on threatened species and vulnerable ecosystems and the impacts of fisheries on stocks, species and ecosystems are within safe ecological limits.

##### d) Alignment with FAO Country Programming Frameworks and FAO Strategic Framework

The Project aligns with priorities in the FAO Country Programming Frameworks (CPF):

- In Cabo Verde, the CPF includes priorities relating to improving food availability, enhancing access to food, stabilising food supply, supporting food security programs and providing regulatory, political and institutional support. Within this context, attention is given to, among other things, the reinforcement of capacities to design and implement policies and plans for the management of natural resources; development of markets and reduction of postharvest losses; promotion of food quality through the enhancement of the legal and operational frameworks; and capacity building - at both central and local level - for the assessment, formulation and harmonization of agricultural policies and investment plans, the dissemination and adoption of international standards and best practices, including those aimed at the sustainable use of natural resources, and the ratification and implementation of protocols and international conventions.

- In Cote d’Ivoire, the CPF includes the improvement of governance of the agricultural, forestry and fisheries sectors, and to strengthen the resilience of vulnerable population groups by supporting their sustainable natural resource utilisation and livelihoods. The CPF results framework includes several outputs that are directly relevant to the Project, e.g., strengthening of legal and institutional structures, capacity development and improved subregional, regional and international cooperation.

- In Senegal, the CPF refers to, among other things, sustainable management and restoration of natural resources and the environment, and the prevention and management of food and nutritional crises. There are specific outputs for fisheries management, the improvement of fisheries infrastructures for the improvement of sanitary standards, and the development of government capacities with regard to fisheries planning. FAO has already provided support for the revision of its fisheries policy (Lettre de Politique Sectorielle de Développement des Pêches et de l’Aquaculture).

The Project will take guidance from relevant FAO supported approaches and instruments, paying particular attention to EAF and the SSF Guidelines. The SSF Guidelines are, together with the VGGT, referred to in the GEF-6 IW Focal Area Program 7 and are of relevance to the CFI as small-scale fisheries play an important role in the coastal area.

The Project falls in line with FAOs goals and Strategic Programmes (SPs) with its multifaceted approach and long-term vision. The Project is particularly relevant to SP 2: Increase and improve provision of goods and services from agriculture, forestry and fisheries in a sustainable manner and its outcomes 2.1, 2.2 and 2.4:

The Project will assist in improving sustainable fisheries and aquaculture practices (outcome 2.1) as well as to increasing the mangrove forest area under management plans for sustainable production in Cote d’Ivoire and strengthening existing mangrove management arrangements in Senegal (in particular in the Bamboung MPA, the National Park of the Saloum delta and the Community National Reserve Palmarin) (outcome 2.1). The Project will also contribute to strengthening governance, including with regard to policy and planning documents on issues and options for natural resource management and national governance frameworks (outcome 2.2) as well as data collection for improved decision making and planning for natural resource utilization (outcome 2.4).

The Project does also contribute to other SPs:

- SP 1: Contribute to the eradication of hunger, food insecurity and malnutrition. The Project will assist in improving policies/strategies and investment programs as well as improved resource allocation (outcome 1.1) and improved governance coordination mechanisms (outcome 1.2).

- SO 3: Reduce rural poverty. The CFI Program aims to improve access by poor rural men and women to productive resources, appropriate services and markets, and promote the sustainable management of natural resources and enhance capacities to improve equitable access to resources and markets (outcome 3.1)

- SO 4: Enable more inclusive and efficient agricultural and food systems at local, national and international levels. An increase in efficient and inclusive trade and market systems (outcome 4.1), value addition (outcome 4.2), and investment opportunities (outcome 4.3) is part of the results foreseen in the Project.

- SO 5: Increase the resilience of livelihoods to threats and crises. This Project will assist in understanding risk associated with potential, known and emerging threats (outcome 5.2) and increase resilience of ecosystems (outcomes 5.3 and 5.4).

- The Project takes a strong interest in promoting gender equality and addresses in particular the often disadvantageous role of women in the fisheries sector in the Project countries. Women postharvest actors will be directly targeted, both in the context of postharvest activities and with regard to promoting their involvement in fisheries management and having more secure access rights to resources. The FAO Policy on Gender Equality – Attaining Food Security Goals in Agriculture and Rural Development will be followed.

# SECTION 2 – Project Framework And Expected Results

## 2.1 Project strategy

This Project is part of the global CFI Program and hence intends to contribute to the CFI Program objective to demonstrate holistic ecosystem based management and improved governance of coastal fisheries. In accordance with the GEF mandate, the CFI Program and its child projects will have a strong focus on ecosystem health, but the initiative recognizes it will succeed only if it is supported by action in the social and economic dimensions. Food security will be a priority, especially given the context of poverty and livelihood dependence on fisheries among many coastal fishing communities. Accordingly, this Project aims to contribute to the global goal of having coastal fisheries sustaining healthy environment, and delivering social and economic benefits.

The Project will take a combined governance and value chain approach to deliver sustainable environmental, social and economic benefits to the countries in West Africa. Thus the Project aims to support the implementation of an ecosystem approach to fisheries together with the improved application of relevant international instruments, in particular the Code of conduct for responsible fisheries and the SSF Guidelines (see Box 1), focusing on ensuring participation, capitalising on existing experiences and generating know-how, developing capacity and supporting innovative governance partnerships along the value chain, supported by effective strategies, national laws and regulations. The Project will provide additional support to existing regional, national and local processes to facilitate the transition of strategic and management planning processes to operational level, and combining these with the integration of local on the ground results.

Box 1: The SSF Guidelines

The Voluntary Guidelines for Securing Sustainable Small-Scale Fisheries in the Context of Food Security and Poverty Eradication (SSF Guidelines) are the first international instrument dedicated entirely to the immensely important - but until now often neglected – small-scale fisheries sector. Having been endorsed by the FAO COFI in 2014, they represent a global consensus on principles and guidance for small-scale fisheries governance and development. The SSF Guidelines - Emphasize the important role of small-scale fisheries for food security and poverty eradication: a source of nutrition, income and economic growth. - Complement the Code of Conduct for Responsible Fisheries to achieve sustainable small-scale fisheries through a human rights based approach. - Provide guidance on the development and implementation of socially, economically and environmentally sustainable small-scale fisheries policies, legislation and legal frameworks. - Are a product of extensive consultations between governments, NGOs, CSOs, academia, regional organizations and fisher-communities.

Accordingly, Project activities will be closely coordinated with other on-going initiatives and close collaboration with other projects is not only considered desirable but necessary. Synergies will be sought by pulling resources together around joint areas of work (both FAO projects and others). A thorough planning process will hence be required at the beginning of the Project and at the start of key individual activities. It will be particularly important coordinate with the CCLME, the GCLME and the WARFP but the Project design also includes an explicit emphasis on improving coordination among fisheries governance and development initiatives at the national level (output 1.1.4) and support to regional experience sharing in component 3.

The interventions in the three Project countries will be location specific taking local constraints and opportunities into account. It should also be noted that while co-management and rights-based fisheries management approaches (including more secure tenure and access rights) are likely to be best practice in general(see Box 2), there is still a need for a systematic process, including analysis and stakeholder participation, to determine what type of management arrangement is the most suitable in each situation. In Cabo Verde, Cote d’Ivoire and Senegal, there is already considerable investment in different management tools but it would appear that many of these actions are fragmented and there is a need to bring good practices together and incorporate them in national and regional frameworks. Stakeholder participation will be fundamental in this process of developing and implementing coherence.  The first phase of the WARFP project established Territorial User Rights in Fisheries (TURF) arrangements in Senegal and piloted co-management in Cabo Verde. This Project will assess and build on these experiences taking a value-chain approach and promoting the creation of equitable benefits.

Box 2: Incentives

The incentives that stakeholders in the coastal fisheries sector perceive for their activities, and the extent to which they are able to realize concrete benefits based on those incentives, are a key element in effective governance of the sector. Secure tenure rights over the resource and its use, controls on access to fisheries, the elimination of perverse incentives, and market arrangements that reward responsible fishing are all key to ensuring that stakeholders in fisheries recognize the value of better management and support effective governance arrangements. In parallel with improved resource management, other dimensions of livelihoods, including social and economic development, need to be addressed to ensure that the full benefits of better governance are realized. Where appropriate incentives are in place, the coastal fisheries sector will also attract more appropriate investment as its potential to generate economic returns will be secured and its capacity to generate wealth will be recognized. Introducing more secure tenure and access rights to fishery resources to resource users fulfils two key functions. First, tenure and access rights are a tool for fisheries management for promoting environmentally, economically and socially sustainable resource utilization. Second, users need secure access – defined in relation to other potential users – to the resources they depend on for their livelihoods or income. By giving users a stake in the future of the resource, a more responsible behavior is expected and the incentives behind the “race for the fish” are dismantled. For this approach to work, the right given to a user or a group of users has to be secure – if the risk is high that the right will be taken away, the incentive to manage the fishery sustainably is diminished. A rights-based fisheries management system does not however automatically remedy overfishing and induce good management. The appropriate type of rights regime needs to be in place and a variety of other conditions apply, e.g. there is a need for enforcement mechanisms and (scientific) information. Secure access to resources is a prerequisite for livelihood security and for many investments. People are more likely to invest in their own future or companies in their business when they are confident that they will continue to be able to draw on the resources they need.

The EAF process and principles will be used together with implementation of relevant international instruments, including the recently approved SSF Guidelines, which are based on a human rights based approach. Small-scale fisheries are very important in the three Project countries and will hence be given particular attention although it is recognised that coastal fisheries includes also larger-scale fleets. Some stocks are shared between small and large-scale operators and it is hence important to take their interactions into consideration (e.g., tuna fisheries).

EAF will also constitute the basis for reviewing and implementing fisheries management plans. A number of management plans already exist in the three countries and during Project inception, fisheries management plans for review and implementation by the Project will be selected. Experiences from the CFI Indonesia and Latin America projects will be taken into consideration. The CFI Indonesia has a strong EAF component and the CFI Latin America will work on, among other things, TURFs. Close contact with these projects and exchanges of good (and bad) practices will be essential.

While pulling together experiences at the national (and regional) level to create a more coherent approach coastal fisheries governance, management and development, the Project will also provide field level support with two sites each in Cabo Verde and Cote d’Ivoire, and one site in Senegal. This field level support is considered essential for capitalizing on existing experiences and for creating impact at the local level. This support will be combined with the national level support with regard to legal, institutional and policy frameworks and capacities. In Senegal where there is already a large number of field activities (by other development partners), relatively more support will be provided at the central level.

Criteria for selecting sites include their importance for communities dependent on fisheries, the existence of significant small-scale fish processing, and their potential to create local and national benefits. With regard to mangroves, at least one site in Cote d’Ivoire and the site in Senegal should be important for mangrove management and/or restoration. The role of mangroves as fuel wood for fish smoking (by women) and the importance for fisheries as spawning and nursery grounds should be considered and integrated in fisheries management. Accordingly, the proposed sites are:

- Cabo Verde: Maio and S. Vincente / S. Luzia;

- Cote d’Ivoire: Abidjan (Locodjro) and Sassandra;

- Senegal: Iles du Salaam.

Table 3: Selected data on each proposed Project site

|  | CPV: Maio | CPV: S. Vincente / S. Luzia | CIV: Abidjan (Locodjro) | CIV: Cassandra | SEN: Iles du Salaam |
| --- | --- | --- | --- | --- | --- |
| Coastal water area fished (km2) | 269 km² | 227 km² | 550 km² | 550 km² | 1 445 km² (65 km coastline; assumed 12 miles fishing zone) |
| Mangrove coverage (ha) | No mangroves | No mangroves | No mangroves | Mangroves exist but data not available | 60 000 ha |
| Population | 8 300 | 76 100 | 13 400 | 4700 | 76 400 |
| Fishers (direct employment) | N/A | N/A | 7 800 | 2 000 | 5 900 |
| Fishworkers (processors / traders – direct employment) | N/A | Approx. 1 300 (in canneries) | 5 300 | 1 200 | 645 |
| Percentage of women in above (%) | N/A | 14-42% | 39,55% | 38% | 85% |
| Migrants (% and origin) | N/A | N/A | 100% (Ghanaians) | 100% (Ghanaians) | 2% (Guinean) |
| Indirect employment (transport, fish scaling / cleaning, sales of ice, fuel, wood, and food services | N/A | N/A | 300 | N/A | 300 |

The Project has a specific focus on gender and includes women empowerment in the value chain and will also mainstream gender considerations throughout its implementation. A gender analysis and a gender strategy will be developed during the Project inception phase. The strategy will include indicators for M&E, e.g., for assessing changes in access, benefits and/or control for women (with regard to, among other things, resource access and participation in decision-making). Baseline data will also be collected during the inception phase. The strategy and indicators will be developed in close collaboration with Project stakeholders, in particular postharvest women groups, to ensure that they measure what is considered important at the local level. Also, advantage has been and will be taken of other initiatives in the countries promoting gender equality, for example, partners and stakeholders of this Project participated in a workshop organised by the FAO Multi-Partner Programme Support Mechanism (FMM/GLO/003/MUL) in Cote d’Ivoire on gender sensitive value chain analyses in November 2016. Moreover, collaboration will be undertaken with the other CFI projects in Indonesia and Latin America to learn from their approaches to gender.

Climate change and disaster risks are other cross-cutting themes that is not directly addressed by the Project but will be considered in all relevant activities, for example, with regard to fisheries management plans, climate change will be one of the aspects that is taken into account when reviewing and implementing plans. It is also expected that the work with fishers and fish workers and fishing communities will strengthen their resilience and hence make them better prepared for facing climate change and potential disaster risks (see also chapter on risks in Section 3 below).

The outcome document of the United Nations Conference on Sustainable Development, held in 2012, entitled “The future we want”, reiterated the need to enhance the resilience of marine ecosystems and of the communities whose livelihoods depend on them, while enhancing resilience to climate change and natural disasters in line with relevant key instruments (the “Sendai Framework” and the “Paris Agreement”). This Project will contribute to reducing the exposure and vulnerability of coastal ecosystems and the livelihoods of coastal fishing communities through dedicated action focusing on preventing and reducing underlying risk drivers, such as poor management and unsustainable uses of fisheries resources and compounding factors such as weak institutional arrangements. The Program will focus on reducing existing risks, preventing new risks and strengthening resilience in the context of sustainable development and poverty eradication. Experience in integrating resilience and climate change in fisheries management plans in line with EAF will be shared amongst partners through field visits and/or workshops.

## 2.2 Project objective

The overall project objective is to

Strengthen fisheries governance, management and value chains, through the implementation of an ecosystem approach to fisheries, of relevant international instruments and of innovative governance partnerships in three countries in West Africa (Cabo Verde, Cote d’Ivoire and Senegal).

This objective can be divided into a Global Environment Objective and a Development Objective:

- Global Environmental Objective: To promote responsible fisheries governance and management leading to more sustainable coastal fishery resource utilisation and safeguarding of marine ecosystems in three countries in West Africa (Cabo Verde, Côte d’Ivoire and Senegal).

- Project Development Objective: To support enhanced fisheries and value chain governance and management creating sustainable contributions to social and economic development in West Africa (Cabo Verde, Côte d’Ivoire and Senegal)

## 2.3 Project components, expected outcomes and outputs

The project consists of three interlinked components that will address the barriers described above in an integrated manner:

- Component 1: Improving fisheries governance and management

- Component 2: Strengthening the seafood value chain

- Component 3: Strategic communication, monitoring and evaluation, and upscaling best practices

The outcomes, outputs and key activities of these components are described below. Details are also found in the Project Results Matrix in APPENDIX 1 as well as in the work plan in APPENDIX 2. It should be noted that all indicators and targets will be reviewed and validated at the Project inception phase and those still undefined (indicated with XX) will then be developed, including with the necessary baselines. Moreover, a table is included in APPENDIX 9 showing how the Project outcomes (targets) contribute to the CFI Program targets.

Table 4: Overview of Project components, outcomes and outputs

Component 1: Improving fisheries governance and management

Outcome 1.1 National fisheries policies, strategies and actions are coherent and effective Output 1.1.1: The national legal and institutional frameworks are reviewed and amended / complemented so that EAF principles are integrated and relevant international instruments can be operationalized (including co-management). Output 1.1.2: Information and capacity building programs are implemented to raise awareness and encourage government policy makers at all levels (MPs, directors, etc.) and relevant institutions to apply EAF and implement international instruments in coastal fisheries and integrate these in relevant policies and strategies. Output 1.1.3: Evaluation mechanisms are established for assessing governance effectiveness and the coherence of fisheries related policies, strategies and legal frameworks with sustainability and development objectives (poverty reduction, food security, employment, national economic growth). Output 1.1.4: Government coordination mechanisms, including consultative frameworks, are put in place and promote coherence and synergies among existing development projects and initiatives in coastal fisheries and related sectors.

Outcome 1.2: Management plans are implemented and create sustainable benefits Output 1.2.1: Coastal fisheries management plans are improved in line with EAF and relevant international instruments and implemented. Output 1.2.2: Mangrove management and rehabilitation programs are carried out and linked to fisheries management objectives. Output 1.2.3: Support has been provided to national institutional structures responsible for fisheries management for them to have appropriate capacities and mandates to apply EAF, relevant international instruments and co-management.

Outcome 1.3: Coastal communities participate in fisheries management and sustainable development processes Output 1.3.1: Coastal fishers and fish workers organisations are formalised and/or strengthened. Output 1.3.2: The capacity of coastal fishers and fish workers to participate in fisheries management and development processes is enhanced.

Component 2: Strengthening the seafood value chain

Outcome 2.1: Fishery product quality and decent working conditions are improved throughout the value chain Output 2.1.1: The understanding of the links between consumption and production in the value chain is improved and value chain actors are sensitised on incentives for good practices Output 2.1.2: The regulatory and normative frameworks for control of fishery products (quality/sanitary standards) and for decent working conditions are improved. Output 2.1.3: Participatory arrangements are in place to support improvement and control of fishery product quality and working conditions.

Outcome 2.2: Value chains are more efficient and create incentives for responsible fisheries and sustainable livelihoods Output 2.2.1: Good practices and innovations are developed to increase incomes and create livelihood benefits while contributing to sustainable fisheries. Output 2.2.2: Appropriate equipment and material, with an emphasis on ‘passive innovations’ (not leading to increased fishing pressure) are available to value chain actors for increasing income and creating other livelihood benefits, including improved working conditions. Output 2.2.3: Access to national and regional markets by small-scale fishers and fish workers, especially women, is facilitated and improved.

Component 3: Strategic communication, monitoring and evaluation, and up-scaling of best practises

Outcome 3.1: Knowledge generated and results achieved are communicated and shared with local, national and regional partners Output 3.1.1: Project communication strategy is developed and implemented and effective communication products developed for sharing project results and lessons learnt. Output 3.1.2: Project experiences are shared through existing platforms and networks, and collaboration is strengthened Output 3.1.3: Training, awareness raising and other communication products needed for project activities are developed and utilised.

Outcome 3.2: A functional project M&E system is in place Output 3.2.1: Project monitoring system operating and providing systematic progress information related to project outcome and output targets in all three countries. Output 3.2.2: Implementation and evaluation reports as well as to CFI Program ToC assessments allow project management and supervisory bodies to ensure operations and achievement of expected results.

Component 1: Improving fisheries governance and management.

.

Component 1 will assist the countries of CFI West Africa to transit towards more effective use of existing governance mechanisms and management tools, facilitating the move from planning to on the ground action, considering national and local scale constraints and opportunities working with national and local level structures, promoting participatory approaches and creating incentives for the communities to contribute to improved management. The Project will build on existing experiences, capitalise on work already done and collaborate with other ongoing initiatives.

Outcome 1.1: National fisheries policies, strategies and actions are coherent and effective

Legislative reform is underway in all three Project countries – and some work has been carried out by the WARFP in Cabo Verde and Senegal – but there is a lack of due consideration of EAF and relevant international instruments. There is also a need to support the operationalization of existing frameworks and those under review and support will be provided to developing regulatory texts. Reviews of existing legal frameworks will be carried out in a participatory manner. In at least one country (Cote d’Ivoire), it is expected that the legal review will take a broad perspective and include assessment of needs for the implementation of the SSF Guidelines through collaboration with the FAO Norwegian SSF Guidelines project. Lessons learnt generated in this process will contribute to international guidance on legislation in particular in the context of the SSF Guidelines. Moreover, collaboration with BirdLife International and their expected second phase Alcyon project will ensure that the seabird aspect is considered in legal reviews in Senegal.

This results of this outcome will contribute to the CFI Program outcome No 2: Policies, legislation and institutions have been improved at local, national and regional levels allowing for enhanced resource management through integrated and holistic approaches that allow for effective incentive structures and that lead to more environmentally, economically and socially sustainable coastal fisheries. The policies, legislation and institutions will be strengthened in the three Project countries with a view to improve fisheries management by basing it on EAF and the application of relevant international instruments, including the SSF Guidelines as well as incorportating climate change management responses. In addition, the Project will not only generate results at the national level but will also contribute to international knowledge products.

- There is generally limited knowledge among decision-makers and politicians on the importance of EAF and the need for implementation of international instruments and information and capacity building program, which include components on climate change and resilience thats will be covered to raise awareness. This is expected to lead to better integration of relevant approaches and principles in policies and strategies. Some broad considerations in the context of fisheries resilience that will be further considered in the EAF training by FAO and at Project inception when developing detailed works plans include:

- Ocean acidification and impacts of climate change (such as sea level rise, more frequent and/or intense coastal storms and accelerated coastal erosion, flooding and increased salinity of mangroves, changes in temperature (which can effect fish reproductive cycles, fish spatial range, rate of spread of disease in farmed fish species, etc.);

- Disruptions to fishery/aquaculture supply chains and seafood distribution systems, e.g., which disruptions are more likely, and how can they be managed? Are backup systems in place?

- Basic safety equipment and information alerts for fishers, to cope with severe weather;

- Cross-sectoral, integrated and participatory planning can aid in development of resilient approaches;

- Reliance on diversity of fish species, and diverse sources of income, can enhance resilience of fisherfolk;

- Safety nets for fisherfolk that have lost income can help reduce vulnerability (e.g., due to disaster, loss of fish stock to disease, etc.).

This capacity building with regard to EAF and climate change will support work across the project under all its components.

While policy and legal reviews and reforms are under way, there are no mechanisms at national level for assessing how well fisheries policy contribute to overall food security and development goals. Taking a basis in the need to ensure that EAF is adequately referred to and applies, the Project will assist the countries in carrying out assessments of coastal fisheries governance effectiveness and policy coherence. By establishing key indicators and mechanisms that allow for regular assessments, policy frameworks will be strengthened. There are opportunities to work in collaboration with FAO and the ECOWAS/FIRST project using guidance material currently under development for reviewing sector policies in relation to food security and nutrition. The EAF Nansen project has developed an EAF tracking tool and is in the process of developing EAF indicators and there are likely to be synergies found in collaboration. All Project work will also be coordinated with the FPAI under the CFI Global Partnership project although the FPAI (see also below on FPAI and fisheries management plans).

As already mentioned several times and described above, there are many different initiatives ongoing in the three countries that are relevant to coastal fisheries. Governments often lack the capacity and resources to effectively coordinate partner activities and to assess experiences in order to distil best practices. In both Cote d’Ivoire and Senegal, there are frameworks for consultations with development partners but these need strengthening. At the same time as the governments can benefit from lessons learnt by development partner projects, there is also a need to ensure that development partners are aware of government priorities. Accordingly, the Project will support the fisheries administrations in the three countries to better capitalise on experiences generated on the ground and support more coherent fisheries strategies and actions.

The following indicators and targets are expected to be reached by Outcome 1.1:

- EAF is referred to as the approach for fisheries management and development in relevant policy and strategy documents and implementation plans follow EAF principles and consider climate change impacts.

- The intention to implement relevant international instruments, including the SSF Guidelines, is explicitly mentioned in policy statements.

- Information on how coastal fisheries contribute to overall national development goals exists and is shared among national and local institutions and development partners.

- Fisheries policies and strategies are more coherent and new projects and programs refer to common priorities.

Outcome 1.2: Management plans are implemented and create sustainable benefits

This outcome aims to support the project countries to develop and implement management plans with targeted actions aiming at strengthening the different institutional actors at national and local level, and bringing examples of good practices of what might have worked at a local scale and see how this can be nested in a national framework. Attention will be given to co-management and the development of incentives to support improved management in line with EAF by all actors, evidencing environmental, economic and social benefits. Special attention will be given to providing a space for postharvest workers, in particular women, to engage in fisheries management.

This outcome will generate results that support outcome 1 of the CFI Program: The efficiency of and transparency in the fisheries value chain (from harvest to consumer) has been improved through appropriate incentive structures and contribute to sustainable resource utilization and equitable social and economic development. In line with the integrated approach promoted in the CFI as a whole, this Project takes a value chain approach using improved fisheries management plans as one tool to achieve more sustainable fisheries and related livelihoods. While the outcome focuses on fisheries management plan review and implementation, it links closely to component 2 and aims at integrating postharvest actors and considerations also in the harvesting part of the value chain.

There are several management plans that have been developed for important fisheries and areas in the three countries but that have not yet been implemented. Often the provisions for operationalizing them are lacking. Hence, the Project does not intend to develop new management plans but to ensure that a selected number of existing plans are implemented. The Project will assist governments in reviewing existing plans and their coherence with EAF and current priorities, including promotion of co-management, gender equality, improving tenure and access rights, participatory data collection and MCS, etc., and the consideration of appropriate incentives for compliance. Lessons learnt and good practices from existing experiences, e.g., with regard to co-management, will be taken into consideration. There is also a need to identify and include support measures, as required, for social and economic development. Robust implementation plans will be developed and support provided for carrying these out and to ensure compliance with the SSF Guidelines. Likewise, collaboration with BirdLife International in Senegal will support implementation of the International Plan of Action for Reducing Incidental Catch of Seabirds in Longline Fisheries (IPOA-Seabirds). Fisheries management planning and implementation will be done in collaboration with stakeholder and resource users (fishers and fish workers) based on stakeholder analyses and relevant partners such as the EAF Nansen project and RFBs. The role of RFBs is particularly important in the context of managing resources that are shared among several countries in the region.

For assessment and monitoring purposes, the selected fisheries will be reviewed using the preliminary FPAI. This will create a baseline for monitor progress towards sustainability. Work on the FPAI is included in component 3 of this Project. The FPAI will also be an important basis for possible support from the CFI Challenge Fund (see further discussons on both these aspects below).

The fisheries management plans will consider climate change impacts and include spatial measures, e.g., fish refugias, as appropriate, and there will be a close link between mangrove management and rehabilitation and fisheries management. Mangroves are important for the sustainability of fishery resources as spawning and nursery grounds but there are also value chain links as mangroves are used as firewood for fish smoking. Taking a value chain perspective, there will be integration between the fisheries management plan implementation and the postharvest sector, in particular women, with a view to involve postharvest actors in management decision-making and better securing their access to fish (see also Component 2).

In addition to the need to review and operationalize fisheries management plans, there tend to be limited capacities for implementation on behalf of both governments and stakeholders. Under this Outcome 1.2, support to capacity within government structures is foreseen and Outcome 1.3 will address the need for capacity on behalf of resource users (see below). Support at the government level includes both the development of human resources and ensuring that the necessary institutional structures are in place to allow for participatory processes and co-management. There will also be awareness raising on international instruments such as the CCRF and the SFF Guidelines with a view to facilitate the inclusion of innovative elements to promote small-scale fisheries communities in coastal fisheries management and development processes.

The indicators for measuring impact under Outcome 1.2 include (quantitative targets to be reviewed and validated during the Project inception phase):

- At least 2 fisheries in the Project countries, representing up to 0.01% of world catches, are under implementation in accordance with agreed management plans and include co-management and secure tenure and access rights regimes, as appropriate.

- 700 ha of mangrove are under sustainable management1.

- 5 communities are involved in co-management supported by national institutions.

Outcome 1.3:  Coastal communities participate in fisheries management and sustainable development processes

This outcome looks at integrating the fisheries actors and communities into the management cycle by strengthening their organisations and capacities. Strong and well functioning organisations are a basis for effective participation in decision-making on coastal fisheries management and development but also those fishers and fish worker organisations that exist often lack organisational and financial skills. Within the framework of the implementation of fisheries management plans and closely coordinated with activities under Component 2, selected organisations will be supported to become autonomous. Activities will also include leadership training and the development of community based capacities. Actions will be based on participatory needs assessments and carried out in close collaboration with civil society and other relevant partners.

This outcome is particularly relevant to outcome 2 of the CFI Program and its target to strengthen the capacity of fishers and fish workers. It is also relevant to outcome 1 of the CFI Program in relation to Public-Private Partnerships (PPPs – see Box 3) and investigating and promoting innovative approaches. However, the work under this outcome is broader than only looking directly into designing (market) incentives as it supports developing the capacity and organisations of fishing communities and fisheries actors to be able to participate in fisheries management and development. This is an important precondition for promoting sustainable and innovative management measures.

Box 3: Public-Private Partnerships (PPPs)

High levels of investments are required to unleash the potential of agriculture, including fisheries, for sustainable development and poverty reduction in developing countries, but low public budgetary allocations to the sector have slowed progress. To address this problem, innovative partnerships that bring together business, government and civil society actors are increasingly being promoted as a mechanism for pooling much-needed financing while mitigating some of the risks of doing business in the agriculture sector. Commonly referred to as public–private partnerships (PPPs), these initiatives are expected to contribute to the pursuit of sustainable development that is inclusive of small-scale producers. In the Project region, it would appear that there is a scope for important PPPs as this is something that is not yet fully explored. The Project will hence explore PPPs both in the context of developing mechanisms for effective management of infrastructures and resources and for creating inclusive market incentives. All Project activities involving or affecting small-scale fisheries will respect the principles of the SSF Guidelines.

Awareness raising and training will be provided in selected communities on, among other things, EAF, the SSF Guidelines and other relevant international instruments, and fisheries assessments and data needs, collection and analysis, with a view to enhance the capacities of fishers and fish workers to effectively participate in fisheries management. The project will also support participatory research initiatives through selected research institutes. Research institutes will be associated with the Project to work on specific topics, identified together with communities, in support of fisheries management. It is expected that one research institute in each country will be involved in the Project throughout its duration (see also Section 4 on Project implementation arrangements).

The exact communities and organizations with which the Project will work will be identified within the Project sites outlined above (see paragraph 0). Collaboration with professional and CSOs has already been established during the Project preparation phase (see chapter 1.4 above).

Indicators and targets for Outcome 1.3 include (quantitative targets to be developed during the Project inception phase):

- XX fishers and fish workers (men/women) benefit from improved natural resources management through improved incomes and/or other perceived livelihood improvements.

- XX fishers and fish workers (men/women) actively participate in decision-making processes related to coastal fisheries management and development.

- At least one successful innovative pilot activity on how a value chain approach has positively influenced fisheries management applying, inter alia, co-management, secure tenure and access rights, PPPs, eco-labelling/certification schemes, or other.

Component 2. Strengthening the seafood value chain

.

Component 2 will benefit small-scale fishers and fish workers, in particular women. Components 1 and 2 are closely linked and constitute the two sides of the same coin; primary production and postharvest in the value chain. Small-scale operators, in particular women, represent a major workforce and entrepreneurial drive in postharvest operations and are key agents for reducing postharvest losses. Working conditions need to be improved and better product quality and access to markets should lead to improved income and livelihoods with same or lower levels of catch, ultimately contributing to reducing the pressure on fish stocks. Attention to climate change will be a cross-cutting theme also with regard to value-chain activities and include consideration of how climate change may impact postharvest and other activities.

Both the outcomes of component 3 contribute to outcome 3 of the CFI Program in relation to sharing experiences more broadly. The Project supports coordination, communications and experience sharing at all levels – local, national, regional and international.

Outcome 2.1: Fishery product quality and decent working conditions are improved throughout the value chain

This outcome will support the improvement of fishery product quality and promote decent working conditions by improving the knowledge on the value chain, strengthen the regulatory and normative frameworks and put in place participatory management arrangements for key infrastructures and processes.

This outcome supports outcome 1 of the CFI Program with regard to reducing postharvest losses and fuel wood consumption. Important experiences in West Africa to date will further analysed, developed, scaled up and shared and contribute to both local results and global knowledge.

A key perquisite for promoting a value chain approach is to understand the links in the value chain and how producers and consumers are related. Demand exercises pressure on production through the value chain and this needs to be considered in order to have successful fisheries management. By carrying out participatory cost-benefit analyses of the value chain, including non-monetary values and the distribution of costs and benefits, actions that will support a more transparent and effective value chain can be identified. This knowledge will also help identify and develop incentives in support of improved practices and management. Value chain actors need to be sensitized with regard to the opportunities that exist and become actively involved as change agents. The Project will focus on working with women fish processing organisations as there is an apparent potential for improvements; current fish smoking is suboptimal with regard to working conditions and health, postharvest losses and the use of firewood.

The regulatory and normative frameworks for control of fishery products (quality and sanitary standards) and for decent working conditions are either non-existent or inadequate. The Project will assist the countries reviewing the needs for improved legislation and regulations through a participatory process. Often there are norms for export products but not for local and national markets allowing for low quality products. Using existing normative frameworks, the Project will test how standards could be introduced in national markets. There will also be an assessment of how Occupational Health and Safety (OHS) standards are or could be applied.

While support to landing sites and market infrastructures is sometimes provided by development partners, there is still a lack of sustainable and functional management systems that allow these infrastructures to be effectively used and maintained. Likewise, when the legal and regulatory frameworks for fishery product quality and decent working conditions have been put in place, there is a need for a mechanism to promote and monitor compliance with the norms and rules. Accordingly, the Project will develop and try new PPP arrangements for the management of landing sites and other facilities and services. This will constitute an important supplement to ongoing and planned infrastructure projects by other development partners (e.g. JICA in Cote d’Ivoire). PPP arrangements for the control for product quality and working conditions will also be tested.

The indicators and targets relevant to this outcome are (targets to be validated or developed, as required, during the Project inception phase):

- XX women processor organisations have adopted improved practices and their postharvest losses have been reduced by 20%.

- XX fishers and fish processors state that their working conditions have improved.

Outcome 2.2: Value chains are more efficient and create incentives for responsible fisheries and sustainable livelihoods

While the previous outcome focuses on knowledge and legal and institutional structures for fishery product quality and working conditions, this outcome is more concerned with improving the economic activities of value chain actors and creating livelihood benefits that also contribute to sustainability. Within this context, the focus is on access by postharvest actors, in particular women: access to resources, access to good practices and related equipment, and access to markets.

As outcome 2.1 above, also this outcome will support the CFI Program outcome 1 and its target to reduce postharvest losses and fuel wood consumption. It will also contribute to the CFI target on implementation of innovative market incentive systems by investigating possible fisheries improvement, certification or similar. It will also address the need for better market access through improving institutional and governance structures and improved access to resources for postharvest actors and how they need to have a role and say in fisheries management, which is an innovative approach with respect to fisheries management.

Focusing on women artisanal fish smoking organisations, the Project will provide assistance for identifying existing good practices with regard to fish handling and processing. Also bad practices will be identified, in particular with regard to the use of dangerous chemicals in fish processing, and be used in awareness raising campaigns supporting the abolishment of such practices. The Project will also look into tenure and access rights of women fish workers and how they could gain more secure access to raw material and the land they need for processing and living. Through a participatory process working closely with women organisations, opportunities to increase incomes and/or reduce costs through better practices will be investigated. Moreover, the need for credit facilities will be assessed and successful existing mechanisms will be modified and strengthened, as required, to be suitable for artisanal processing and complementary income generating activities.

Equipment and material used for artisanal processing tend to be of low standard and there is a lack of technological innovation. The unsustainable utilisation of firewood, often mangroves, constitutes a threat to vulnerable coastal ecosystems. Building on the example of the successful experiences in Cote d’Ivoire with the Thiaroye smoking kiln that is more fuel efficient and also create healthier working environments, opportunities for investments in equipment and material will be analysed. Value chain actors, in particular women processor organisations, will be supported in developing investment plans and engaging with potential funders (donors, banks, etc.). Subject to the results of initial studies carried out in collaboration with the CFI Challenge Fund, support to developing such plans could be provided through the Challenge Fund.

Artisanally processed fishery products rarely make it to more lucrative local and national markets, such as supermarkets and restaurants. Moreover, small-scale fisheries actors often have limited access to regional markets, or national markets beyond the local area. The Project will hence provide support for strengthening the access to markets and regional exports, e.g. through mutualisation arrangements and the establishment of appropriate government structures for facilitating exports (to regional markets) of small-scale fisheries products (marketing, transaction risk mitigation, customs regulations, etc.). The Project will also carry out preliminary assessments for Fisheries Improvement Programme (FIP), labelling or certification schemes for selected products, suitable for small-scale fisheries, in collaboration with technically competent partners (e.g., MSC). These partners will advise on how greater market access can be achieved but it should be recognised that to actually proceed to a FIP or certification is outside the scope of this Project. Moreover, CONXEMAR will support participation in their annual Vigo exhibition/conference and hence promote trade contacts and capacity building accordingly. Organisational development for small-scale fisheries and women fish workers will also be supported through enhanced organizational and managerial capacity of post-harvest actors, especially women, as described in outcome 1.3 above.

Box 4: The Marine Stewardship Council (MSC) and FIPs

Fisheries Improvement Projects (FIPs) involve the development of multi-stakeholder partnerships that collaborate and work to support a fishery as it improves towards the point where it could become certified. The partnerships usually include, government, NGO’s, research, academia, fisher organisations, industry and the private sector. The process of improving towards certification starts with an initial gap analysis (pre-assessment) against the certification standard. The MSC Standard has 28 Performance Indicators that elaborate on the three main Principles of the standard – (1)Target stocks, (2)Ecosystem impacts and (3)Management. The gap analysis against the 28 Performance Indicators provides a diagnostic overview of the issues that need to be addressed in the course of the improvement project and will generate a Benchmarking and Tracking (BMT) Index for the fishery. The BMT Index provides a mechanism to communicate progress being made in the fishery to other partners in the project over time. Changes in the BMT Index will be tracked throughout the period of the improvement phase. The gap analysis is followed by the development of a collaborative action plan for the improvement project, which identifies actions necessary to address the gaps, and also roles and responsibilities for implementation which are spread across different actors. Two key components of improvement projects are the market participation and the regular monitoring and checking in, of progress of the FIP over time. These two components provide important incentives for the fishery to make improvements. In order to build stakeholder awareness, and to build local audit and technical capacity on initiation and implementation of FIPs, the MSC provides a comprehensive capacity building programme on the certification standard which is designed to ensure that stakeholders are able to effectively initiate, participate in, and drive the FIP. As the fishery performance improves, the fishery may take the decision to proceed to certification, which then provides the opportunity for the fishery to harness the economic benefits associated with certification.

Experiences generated by the CFI Indonesia and Latin Amercia projects on FIPs as well as payment for environmental services (PES) will be considered and good practices integrated into this Project as appropriate.

The GEF biodiversity funding available to Cote d’Ivoire through this Project will be mainly used in the above described context with a view to contribute particularly to GEF Biodiversity Focal Area Program 9:  Managing the human-biodiversity interface. This will also include linking the postharvest work to the implementation of fisheries management plans included in outcome 1.2, with a particular emphasis to integrate the postharvest sector and its actors, especially women, in management and resource access arrangements.

- Indicators and targets for this outcome include are (targets to be validated or developed, as required, during the Project inception phase):

- Fuel wood consumption has increased in fish smoking in project sites by 10%.

- Fishery products from project sites can be found in supermarkets in capital cities of the three countries.

- XX women processor organisations have increased their revenues from sales in national and regional markets thanks to better product quality.

Component 3. Strategic communication, monitoring and evaluation, and upscaling of good practices

.

Component 3 aims at ensuring that Project experiences and results are shared broadly, within the Project countries, the region, the CFI Program and globally. Furthermore this component will ensure the setting up of an M&E system, allowing for close monitoring of project activities, outputs, outcomes and impacts as well as for mid-term and final evaluations, to capitalize on the experience acquired for future investments. The content of this component is also linked to Section 4 with regard to Monitoring and reporting, and Communication and visibility.

- The expected outcome is lessons and best practice on improved fisheries governance, post-harvest processing and the role of mangroves and their management in the context of fisheries has been shared with stakeholders within each country, among both countries and with global partners of the CFI Programme and worldwide. This component is the backbone of the learning process and will support the communities and other stakeholders in changing their understanding and practices. It will be aligned and articulated with the CFI Knowledge Management Strategy and CFI Communication and Outreach Strategy.

- Three lines of work will be developed:

- Develop and maintain a simple electronic platform to facilitate communication and exchange of information.

- Follow-up and analyse key indicators of CFI theory of change.

- Test the Fishery Performance Assessment tool (FPA).

- The electronic platform (output 3.1) will be a simple web-based communication platform with pages providing news (CFI project/programme related as well as regional) and other relevant information (project and non-project), and links to other electronic media (e.g., Twitter, WhatsApp, YouTube, Telegram) to facilitate interaction and virtual sharing of knowledge and information among project participants and other CFI projects. Depending on the cost/complexity, the platform may be also established as an app with iphone and Android. Social networking platforms such as Facebook, Twitter, WhatsApp, Flickr and Instagram to facilitate interaction and networking among CFI participants and worldwide audiences, and to build a social media presence of the project will be linked to the CFI Programme site as well as FAO’s corporate sites to provide global dissemination and to take advantage of FAO’s wide media network as well as being linked to the IW:Learn platforms.

- A quarterly electronic newsletter in French and English will be sent to people and institutions that sign up as subscribers and will be posted in the website and linked to the IW:Learn wevsite. This newsletter will summarise progress and information to worldwide audiences. Three (3) Short videos with lessons, experience and briefs from the project will be available on the website with links also to the main CFI website as well as being distributed through FAO’s corporate communications network and the IW:Learn platforms. It is acknowledged that electronic media may not be accessible to all local stakeholders, therefore at project start specific communication interests and channels (electronic, tv/ radio and print) will be identified on each site and target group, and a communication strategy will be designed and implemented (output 3.1).

- The project team will systematically work with the community leaders, partners, the project committees and other interested stakeholders to document experiences and lessons and disseminate them through the electronic platform and other media. Project experience and lessons will be documented in learning experience documents and other media that will be available through the project´s electronic platform. At least one learning experience document will be prepared (see output 3.1). In addition, the lessons and recommendation on the use of the FPAI will also be captured and shared with the communication consultant and FPAI team within the CFI Global Partnership. It is foreseen that the project team will lead one of the CFI´s global products that systematise lessons across projects and will contribute to the thematic syntheses to be developed by the other child projects. The details on the theme and format will be decided with the CFI team during project implementation.

- To complement virtual communication, there will be face-to-face meetings between stakeholders in the three countries and where possible across the three countries using other regional meetings opportunities. It is planned to have (i) exchange visits between the pilot sites and also between women post-harvest groups. At the global level, there will be (i) joint analysis with other CFI projects on the advances of the programme theory of change, (ii) exchange visits with the Indonesia and Latin America projects, (iii) participation in CFI events, (iv) presentation of results in regional and international events (e.g., RFB meetings, Abidjan COP, COFI and possibly regional economic forums) with priority given to regional forums as they have the most potential to influence policy and management at national and local levels, (v) share experience with related projects and initiatives, (vi) participation in two International Waters Conferences (IWC), and (vii) contribute to CFI´s communication tools and channels (e.g., web portal, newsletter, workspace, e-mail discussion groups)(Figure 2). For the present project, it will be valuable to share experiences in empowering post-harvest groups and the links between mangroves and fisheries Latin America and Indonesia. Also, it will be important to learn from the work on rights based fisheries in Latin America, and the work with MPAs in Indonesia. The project will contribute to the annual CFI Programme meeting overall and has allocated approximately $40,000 over the life of the project.

- The role on knowledge sharing will be key to analyse outcomes across the three regions involved to draw out lessons and the impact of changing to best practices, and with coastal fisheries globally, in order to produce global knowledge products and participate and coordinate visits and learning exchange experiences.  In particular the project will share lessons and knowledge with projects in the region and to the extent possible worldwide through interactive fora (e.g. webinairs, regional workshops/conferences).The Global Partnership will manage knowledge sharing activities, as shown in Figure 2.

- The Mid-term Review (MTR) and Terminal Evaluation (TE) will contribute to the project´s learning process and will be inputs to the communities of learning.

- To close the project there will be a Terminal Workshop in which project participants present their experience and accomplishments. A final report will be prepared and disseminated with executive summaries in English, French and Portuguese.

- Pertinent CFI ToC indicators (Annex 11) will be documented and analysed at project start, mid-term and end. The MTR and TE will include a review of progress of the theory of change. A set of ToC indicators of the first and second tiers will be selected at project inception. At the start of the project, this set of indicators will be validated with the CFI M&E team. Also, the common methodology to be used to measure the indicators will be agreed with the CFI partners.

Outcome 3.1: Knowledge generated and results achieved are communicated and shared with local, national and regional partners

This outcome includes the establishment of a communication strategy and mechanisms for sharing including a simple electronic platform linked to the main CFI Programme website.  Communication materials and tools will be developed both for implementing Project activities and for sharing Project results as part of the knowledge sharing of the CFI programme. Communication products need to be adapted to specific audiences (in local language, French and/or English, as required) and will be developed in collaboration with partners and stakeholders. An important part of the Project will be the organisation of experience sharing events: training courses, workshops, seminars etc. These will take place at both national and regional levels and through collaboration with relevant partners. At the regional level, relevant RFBs are expected to play an important role (see also chapter on Communication and visibility in Section 4).

The Project will contribute to the CFI Program website by posting experiences and also share Project results using a range of media in regional and international meetings and conferences, as well as through publishing articles. As described in the chapter on Communication and visibility in Section 4, this Project will take a role in leading knowledge sharing on EAF and the SSF Guidelines as well as on the links between mangroves and coastal fisheries. More details on how this will be done will be developed in the communication strategy.

Outcome 3.2: A functional project M&E system is in place

This outcome refers to the need for the Project to have appropriate mechanisms for monitoring progress and evaluate results. There will be regular reporting to FAO and to GEF as well as a midterm and a final evaluation including the Abidjan Secretariat reporting on mangrove-related work. This will also include carrying out assessments using the CFI Program Theory of Change (ToC) framework at baseline, and during mid-term and terminal assessment (see also chapter on Monitoring and reporting in Chapter 4.5). The project will be responsible, including costs, for identifying and measuring the Programme Theory of Change indicators which will be coordinated by the Global Partnership Project.

Moreover, this outcome will include activities in collaboration with the CFI Global Partnership project for piloting of the CFI Fishery Performance Assessment instrument (FPAI) development in selected fisheries. The CFI FPAI instrument will promote the identification and dissemination of best practices in fishery management by developing a common framework for assessing the ecological, economic and social outcomes arising from development project interventions.  This tool will build on existing models for capturing both fishery outcomes and enabling conditions, representing exogenous factors and elements of management strategies. The FPAI instrument developed will provide a common framework for knowledge sharing within the regional projects as they seek to identify pathways for fishery improvement. The FPAI will be measured as follows:

1.    Baseline assessment between 3 to 6 months of project inception (pre-FPAI, diagnosis tool)

2.    Pilot assessment using first version of FPAI (Year 3-4)

3.    Terminal assessment using revised and final version of FPAI (Year 5).

The FPAI design will begin with an initial consultation to understand the ecological, economic and social data that is available in each project, drawing in project managers, and ecological and social science staff.  The workshop outputs will also characterize current data and capacities, as well as planned project interventions and theories of change for each output. Based on the information discussed and recommendations, the specific strategies for each activity and outputs will be formulated.

## 2.4 Cost effectiveness

The Project takes a holistic approach addressing simultaneously fisheries management and postharvest issues and engages with stakeholders in an integrated manner. The sites for local Project activities have been selected to make this possible and also with internal Project cross-component synergy effects in mind. The Project will collaborate closely with other initiatives by governments and partners into account and promote the pulling of efforts and resources to ensure cost effective results. Accordingly, the Project will build as far as possible on existing investments in institutional frameworks and processes.

Cost effectiveness has also been considered in relation to Project execution. As described in Section 4 below, a Project Coordinator will be shared with the CFI Global Partnership project and based in FAO, Rome. The Project Coordinator will be able to link this Project with the other CFI child projects to ensure that lessons learnt, including those that will contribute to improved cost-effectiveness, are shared across the CFI Program. At the national level, execution will be streamlined using existing government, FAO and partner institution structures.

It is expected that the cost-effectiveness of the project will be high; the direct and indirect environmental, social and economic benefits created by the Project are expected to exceed GEF investment.

## 2.5 Innovativeness

The Project will foster an innovative value chain approach integrating improved governance and a market driven approach whereby stakeholders from the government, the coastal communities, fishers and fish workers will embrace best practices to improve income, livelihoods, working conditions and resource utilisation. It is expected that this combined governance and value chain approach will be a powerful mean of delivering environmental, social and economic benefits. The Project will work both at the national and local levels – with important exchanges of experiences at the regional and global levels – capitalising on existing experiences and building on successes, rather than starting from scratch and wanting to create ‘new’ experiences. The approach to work closely with women organisations and link the postharvest sector to fisheries management is also considered something that has not necessarily received attention before.

As this Project is part of the CFI Program, it will be part of a global movement of using new processes for combining existing best practices and applying a more integrated approach to fisheries governance and management that is innovative. The CFI Program as a whole will promote sustainability incentives in the value chain addressing the need for correct incentives at the harvesting stage, including co-management and innovative or improved secure tenure and access rights regimes, as appropriate, and improving the efficiency and transparency of the postharvest sector. The set-up of the CFI Program will allow for innovative sharing of experiences among regions, countries and development partners.

# SECTION 3 – Feasibility

## 3.1 Environmental impact assessment

Overall, none of the project activities carry any particular risk for causing negative environmental impacts. Accordingly, the environmental review of the project arrives at the unambiguous conclusion that the project has to be classified as “Category C”, conforming to the pre-approved list of projects excluded from further environmental assessment. The project will have minimal or no adverse environmental impacts. No further analysis is required.

## 3.2 Risk Management

### 3.2.1 Risks and mitigation measures

The following table summarizes the main identified risks. The risks are also presented in the Results Matrix in APPENDIX 1 as assumptions at the outcome level and in risk matrix in APPENDIX 4.

Table 5: Risks and mitigation measures

| Risk | Mitigation measures |
| --- | --- |
| Changes in decision makers, or other events beyond the control of the Project, lead to changes in policies and or the political will to support the Project. | In the Project formulation phase, governments – as well as other stakeholders – have been closely involved and the Project will continue to work closely with governments to foster buy-in and commitment from relevant institutions, as well as through national and local champions. In addition, specific activities have been incorporated for creating awareness among government officials and politicians (output 1.1.2). |
| Coastal communities do not engage with the Project and key stakeholders do not participate in the Project. | The Project mitigates this risk through planned and significant networking and coordination and collaborative activities, joint planning, regular meetings between the main partners and sharing of information and development. At Project site level, Project staff will be based close to communities and, together with government counterparts, work in partnership with communities and fisheries actors. |
| The required data and information, or the means for obtaining the data needed (through partner collaboration), are not available. | The lack of data is a common weakness in the context of fisheries governance and management. The Project will work closely with both relevant authorities and resource users and will hence have access to existing data. Through partnerships with other initiatives, such as the EAF Nansen project, new data will also be generated. |
| Insufficient capacity to implement the proposed governance and fisheries management changes in a manner that builds long-term sustainability. | The scope of the Project has been agreed with relevant authorities and representatives of fisheries actors (small-scale fisheries CSOs). The Project will assist governments to better assess strategies and tools that are available and support capacity building accordingly. The Project will promote arrangements that are feasible and sustainable in the long-term. |
| Regional and national market demand for improved quality products is weak. | Existing information and perceptions indicate that there is not a lack of demand but of good quality products and of distribution channels. The Project will base its support to improved market access and enhanced product quality on through value chain and market analyses (outcome 2.2). |
| Better quality products lead to fish becoming inaccessible for poorer population groups. | While the intention is that improvement of quality will lead to that some products can be sold with a premium price in order for small-scale fishers and fish workers improve their income and livelihoods, a major effect of introducing better postharvest practices will be a decrease in postharvest losses. This means that more produce will be available in the markets overall. It will be important though that the Project monitor prices and possible effects on food and nutrition security in the Project sites. |
| Lack of willingness and ability of development partners to collaborate. | Many different partners were involved in the Project preparation phase and the CFI Program as a whole is a partnership. Continued dialogue and collaboration with partners will mitigate risks of non-cooperation. |
| Necessary decisions beyond national level, for example with respect to shared stock management and migration of fisherfolk, cannot be made because of lack collaboration at the regional level | The Project will ensure contacts with governments of neighbouring countries and regional bodies to promote collaboration on issues beyond national control or through regional initiatives or existing processes such as CECAF, SRFC, WCFC, CCLME and GCLME. |
| Perceived gender roles and cultural practices do not hinder increased involvement of women in strengthened livelihood activities. | The Project will apply a gender sensitive approach and work with both men and women, as appropriate, also for activities that target women more specifically. Women already play an important role in the postharvest sector and the Project is not seeking to drastically change gender roles but to support those who are more vulnerable and promote gender equity. |

### 3.2.2 Risks deriving from changing external conditions

External drivers of change impact coastal fisheries and can hence also impact the Project and the possibilities to implement it. Climate change is a long-standing risk factor that can affect the Project fisheries and communities in several ways including through biological and ecological responses to physical changes (e.g., productivity, species abundance, ecosystem stability, stock locations and pathogen levels and impacts), indirect wider socio-economic effects and direct physical effects (e.g., sea level change, floods and other extreme weather events). The possible biological, ecological and socio-economic impacts of climate change on coastal fisheries and livelihoods will be considered throughout Project implementation in a cross-cutting manner. There are also other projects and initiatives in the Project countries addressing climate change (see chapter 1.2 above) and the Project will collaborate with these initiatives.

Risks related to extreme weather events are more difficult to mitigate or include in Project planning and implementation in a systematic way. This is also the case with regard to other disaster risks, such as outbreaks of disease (e.g. ebola), political unrest or complex emergencies. It will be important that the Project monitors its natural and political environment to ensure that the possible effects of any unforeseen disaster events are minimised.

Improving resilience will be an important general strategy for mitigating climate change risks. While factors affecting resilience of the fishery and aquaculture sectors will differ across the three countries and specific fisheries, some broad considerations in the context of fisheries resilience that will be further considered in the EAF training by FAO and at Project inception when developing detailed works plans include:

- Ocean acidification and impacts of climate change (such as sea level rise, more frequent and/or intense coastal storms and accelerated coastal erosion, flooding and increased salinity of mangroves, changes in temperature (which can effect fish reproductive cycles, fish spatial range, rate of spread of disease in farmed fish species, etc.);

- Disruptions to fishery/aquaculture supply chains and seafood distribution systems â€“ which disruptions are more likely, and how can they be managed? Are backup systems in place?

- Basic safety equipment and information alerts for fishers, to cope with severe weather;

- Cross-sectoral, integrated and participatory planning can aid in development of resilient approaches;

- Reliance on diversity of fish species, and diverse sources of income, can enhance resilience of fisherfolk;

- Safety nets for fisherfolk that have lost income can help reduce vulnerability (e.g., due to disaster, loss of fish stock to disease, etc.).

# SECTION 4 – IMPLEMENTATION and MANAGEMENT ARRANGEMENTS

## 4.1 Institutional arrangements

##### a) General institutional context and responsibilities

The CFI Program is based on a partnership of six GEF agencies leading one or more of the three national and sub-regional child projects covering six countries, plus a technical assistance facility to develop a pipeline of investable fisheries projects, the CFI Challenge Fund, and a global knowledge management mechanism (the Global Partnership project) for sharing experiences and furthering effective fisheries management globally. The six GEF agencies are FAO, which is the overall lead for the CFI Program, CI, UNDP, UNEP, World Bank and WWF.

The CFI child projects with the lead agencies and the six countries are:

- Child 1: Ecosystem-based management and improved governance of coastal fisheries in the Southeast Pacific (Ecuador and Peru), implemented by UNDP in collaboration with WWF and CI;

- Child 2: Delivering sustainable environmental, social and economic benefits in West Africa (Cabo Verde, Côte d'Ivoire and Senegal), implemented by FAO in collaboration with UNEP;

- Child 3: Ecosystem approach to fisheries management in Eastern Indonesia, implemented by WWF in collaboration with CI;

- Child 4: The CFI Challenge Fund, for sustainable marine resources management, implemented by the World Bank;

- Child 5: The Global Partnership, implemented by FAO in collaboration with the other CFI agencies.

The Global Partnership, implemented by FAO, constitutes the umbrella project for the CFI Program and it will be established involving all six GEC Agencies and other relevant partners. The project will promote sharing of the experiences and lessons generated at country and regional levels, giving it a catalytic role in replicating best practices on coastal fisheries management. A knowledge management (KM) strategy will ensure that effective dissemination of new knowledge acquired to inform and advocate policies and capacity strengthening. The project will also include a research component for developing – based on existing tools and initiatives - and implementing a fisheries performance assessment instrument that can be used to effectively monitor the sustainability of coastal fisheries management and to evaluate improvements in sustainable environmental, social and economic benefits of the CFI and other programs. The Global Partnership project will provide both the common platform for the CFI Program – as well as for broader collaboration and communication – and contribute innovation with regard to fisheries performance assessment. The project will have a key role in collating best practices and ensuring that these influence future developments for coastal fisheries governance and management.

Under the Global Partnership project, a Global CFI Program Coordination Unit (GCU) and a Global Steering Committee (GSC) will be established. The GCU will involve the FAO plus the six executing partners: CI, GEF, UNDP, UNEP, World Bank, WWF and the University of Washington; whilst the GEF Secretariat, CSOs and private sector representatives will be added in the case of the GSC.

A Global Reference Group (GRG) will also be established for this programme and composed mainly of the RFBs, project regional representatives, representatives from producers groups and others involved in the fisheries value-chains, CSOs and the academia. The GRG will extend its membership as needed while ensuring appropriate north/south and gender representation.

As this Project is part of the CFI Program, its institutional arrangements are nested within the overall CFI institutional structure described above but with its own implementation arrangements (see below). The Global Partnership project will act as CFI Program coordinator and this Project will be supported accordingly. The CFI Program’s institutional structure is shown in Figure 4.

Figure 4: CFI Institutional Structure

Within the overall CFI Program Framework, the Project will have its own governance and management structure. The following structure and staffing is proposed (see also Error! Reference source not found.5 and TORs in APPENDIX 6):

- Project Steering Committee

A Project Steering Committee (PSC) will oversee Project management. It will consist of the fisheries administration and relevant environment authorities of the three countries, FAO and UNEP/the Abidjan Convention, GEF (and other donors, as appropriate and required), representatives of a CSO and the industry/private sector, respectively, as well as representatives of relevant regional organisations (SFRC, FCWC) and projects (CCLME, GCLME, WARFP).

Figure 5: Project governance and management structure

- National Project Committees

In each country, there will be a National Project Committee consisting of public and private stakeholders and chaired by the National Project Coordinator.

- National Project Coordinators (NPCs)

In each country, there will be a (full time) National Project Coordinator responsible for Project implementation at the national level. The National Project Coordinators will be government counterpart staff from the fisheries administrations1. They will work closely with the Project National Officers and the Project site teams and have a key role in ensuring sustainability of Project results after its completion.

- Project recruited staff: National Project Officers (NPOs) and administrative support staff

The National Project Officers will be Project recruited staff and support the NPCs both technically and administratively/operationally and will assist the NPCs in the communication and knowledge sharing aspects of the project. The NPOs will be embedded in the Ministries responsible for Fisheries in each of the three countries, however, they will also work with the national FAO communication consultants and the FAO regional communications officer to ensure effective knowledge sharing in the regional and will closely liaise with the their counterparts in the other CFI projects including the CFI-Global Partnership communications consultant and the Sciene to Policy specialist to ensure effective knowledge sharing across the CFI projects and globally. There will also be part time Project funded administrative support staff (General Service staff) in each country.

- Partner institutions

The Project will establish close collaboration with at least one national research or similar institution in each country. These institutions will carry out specific activities in the field, requiring more in-depth research. They will also be active partners in analysing and internalising Project results, contributing to the sustainability of the work of the project when completed.

- Project site teams (two Project sites in Cabo Verde and Cote d’Ivoire and one in Senegal)

At each Project site, there will be a team of three National Technical Consultants. These will be junior professionals and have the following three profiles:

- Processing and marketing (with emphasis on artisanal processing);

- EAF fisheries management (and co-management);

- Livelihoods and organisational development.

At least one of the three staff in each site will be a woman and all will have language skills suitable for their site. It is expected that these staff will be based at the site itself where a small office will be established, preferably integrated within the local government structure. They will be responsible for local implementation of Project activities. At the beginning of the Project, they will be given training on key subject matters (EAF, relevant international instruments, etc.) and will be technically supported by FAO and government staff throughout the Project.

In Senegal, there is a stronger need to support the central fisheries administration and in addition to staffing at one site, three junior staff will be placed with the fisheries administration. Exact profiles are to be decided but they would be similar to the above.

- Consultants

National and international consultants will support the Project as required. They will include expertise with regard to, among other things:

- Processing and marketing (with emphasis on artisanal processing);

- EAF fisheries management (and co-management);

- Livelihoods and organisational development;

- Legislation and regulations;

- Communication, knowledge sharing and M&E; for this consultancy fluency in English will be required as well as French.

- Technical backstopping

FAO staff will contribute to the Project with regard to technical support and coordination with other relevant activities. A Project Task Force will be set up for this purpose (see also below).

- Project Task Manager (PTM)

Overall project coordination will be the responsibility of a Rome-based Project Coordinator who will be shared with the Global Partnership project.

Both FAO and UNEP are implementing agencies and FAO together with the Abidjan Convention will be the coordinating the execution of the Project. The Abidjan Convention will be responsible for output 1.2.2 addressing mangrove management (see also below). However, this output will be an integral part of the fisheries elements of the Project and work will be closely coordinated between the NPCs, the Abidjan Convention Secretariat, Ministres of Animal Resources and Fisheries, National Adminstrative Authorit and of Enviornment and Sustainable Development.  The Abidjan Convention will engage the appropriate national and local institutions to undertake activities at the pilot sites in Cote d’Ivoire and Senegal with regard to the sustainable use and conservation of mangroves in line with the Mangrove Protocol currently under consideration by the 22 Abidjan Convention member countries. These institutions will report to NFOs and be represented on the National Project Committees, as appropriate. The PTM will oversee the coordination between the NFOs embedded in the national fisheries offices, including at each Project site, and those responsible for the Abidjan Convention led mangrove work in Cote d’Ivoire and Senegal.

##### b) Coordination with other ongoing and planned related initiatives

This Project is one of five child projects under the CFI Program. Through the Global Partnership child project, collaboration with the other three projects – the Latin American, Indonesia and CFI Challenge Fund projects (see CFI PFD) – will be ensured. The Global Partnership project will also promote collaboration with other initiatives of the CFI GEF agency partners, in West Africa and elsewhere.

The coordination among the CFI child projects also implies two-way learning processes. By exchanges experiences, the different child projects will learn from one and other. These aspects are part of the CFI knowledge management work and are further described below (see the chapter on Communication and visibility).

Collaboration with the CFI Challenge Fund will be particularly important as it constitutes a technical assistance facility to develop a pipeline of investable projects. It is a pioneering financing facility utilizing a robust theory of change with the ultimate goal of catalysing investment capital for the long-term sustainability of coastal fisheries around the world. The CF will provide technical assistance for improvements that are designed to eventually attract private investors into sustainable fisheries. Countries of this Project will be eligible for requesting assistance from the CFI Challenge Fund to leverage and complement these effort to attract private investments. Accordingly, a joint activity with the Challenge Fund will be developed with regard to selected fisheries and management plans (see outcome 1.2 above in Section 2) to assess the relevance of potential technical assistance from the Challenge Fund for development of investment proposals. Requests for assistance from the Challenge Fund could be submitted by postharvest organisations (among those foreseen as Project partners in particularly component 2).

At the global level, alignment with FAO support to the implementation of relevant international instruments, such as the SSF Guidelines, will be ensured. The Project will also be closely linked to pan-African policy processes such as the AU Policy Framework and Reform Strategy for Fisheries and Aquaculture in Africa, and maintain close links with the work of AU-IBAR and NEPAD. At the regional level, the linkages with the relevant regional fisheries bodies such as CECAF, SRFC, FCWC and ATLAFCO will be ensured as well as with GEF supported LME projects, in particular the CCLME and GCLME projects.

At the national level, Project activities will be coordinated with the various government programs, national initiatives and projects at national and local level within the three countries, including the activities related to, among others, the FAO Blue Growth Initiative, the EAF-Nansen Project activities in Cote d’Ivoire and Senegal (through the CCLME) and the WARFP national projects in Senegal and Cabo Verde and later in Côte d’Ivoire. The Project will also benefit from national network and committees set up under the CCLME project in Cabo Verde and Senegal. Examples of other projects and initiatives with which the Project could seek collaboration are mentioned in chapter 1.2 above.

Coordination with other initiatives, both at the national and regional levels, will be essential. The Project includes specific activities and outputs promoting coordination (in particular output 1.1.4 and outcome 3.1). Through these mechanisms, experience sharing will be supported throughout implementation.

During Project design, discussions have been held with partner representatives of the other major regional initiatives, including the CCLME, GCLME and WARFP. While there are some similarities in overall scope and objectives, the different initiatives will work in different locations at the local level and hence experience sharing will be essential for identifying good practices for broader application and mainstreaming. The more detailed planning of Project activities including knowledge sharing need to be dealt with during Project inception and in discussion with these partners. This Project is ahead of these three other initiatives with regard to being finalised and moving towards implementation. Involving relevant partners in the work planning at the inception phase of this Project will allow the other initiatives to ensure that they are complementary in their design. Moreover, the CCLME, GCLME and WARFP will be invited as members to the Project Steering Committee (see above).

## 4.2 Implementation arrangements

### 4.2.1 GEF Agency

The FAO will be the GEF Lead Agency for the CFI Program as a whole as well as the Executing Agency for this Project. UNEP will also be a GEF Agency and, through the Abidjan Convention, be directly responsible for the implementation of Output 1.2.2 with respect to mangroves in Cote d’Ivoire and Senegal. UNEP/the Abidjan Convention will also be part of overall Project planning and implementation and the Project takes an integrated approach, i.e., mangrove management should be an integral part of overall fisheries and value chain management and governance.

FAO will provide supervision and technical guidance services during program and Project execution. The FAO role will be mainly supporting and coordinating CFI activities in each country with the actual work carried out by national (and regional, as appropriate) institutions under execution arrangements in addition to staff and consultants. The administration of the GEF grant will be in compliance with the rules and procedures of FAO, and in accordance with the agreement between FAO and the GEF Trustee. As the main Co-lead Agency, FAO will:

- Manage and disburse GEF funds in accordance with the rules and procedures of FAO;

- Enter into Execution Agreements, Letters of Agreement and/or UN to UN Agreements with the CFI executing partners/agencies (UNEP and the Abidjan Convention, Governments of Cabo Verde (Ministère de l’économie et de l’emploi & Ministère de l’agriculture et de l’environnement), Côte d’Ivoire (Ministère des ressources animales et halieutiques & Ministère de l'environnement et du développement durable) and Senegal (Ministère de la pêche et de l’économie maritime & & Ministère de l'environnement et du développement durable), and other partners) for the provision of services to this Project;

- Regarding coordination between ministries regarding mangroves, FAO will liaise with the Abidjan Convention Secretariat as an EA in this project to ensure that in Côte d’Ivoire coordination between the Ministry of Animal Resources and Fisheries, the National Administration, the Ministry of Environment and Sustainable Development and the National Project Coordinator is undertaken for not just mangroves but for other related links such as those with relevant fisheries. Similar arrangements are expected if mangrove work is extended to Senegal. In addition FAO will coordinate with the Abidjan Convention Secretariat in sharing knowledge and, monitoring and evaluation and providing TA related to mangroves across the three countries.

- Oversee Project implementation in accordance with relevant documents (in particular this Project document and the annual work plans and budgets (AWP/Bs) that will be prepared during Project implementation), agreements with the co-financiers and the rules and procedures of FAO;

- Provide technical guidance to ensure that appropriate technical quality is applied to all Project activities;

- Report to the GEF Secretariat and Evaluation Office on Project progress (through annual Project Implementation Review – PIR) and provide financial reports to the GEF Trustee;

- Carry out midterm and terminal project evaluations through the FAO Office of Evaluation.

The Budget Holder (BH) will be responsible for the management of the GEF resources and all aspects in the Execution Agreements, Letters of Agreement and/or UN to UN Agreements, which will be signed between FAO and the Project executing partners/agencies. As a first step, a Project Task Force (PTF) is established. This is done in consultation with the LTO and with the lead Strategic Objective Core Team, integrating the necessary technical qualifications from relevant units at FAO Headquarters and in decentralized locations and also including an Funding Liaison Officer (FLO) from the relevant Funding Liaison Unit to guide the implementation of this Project. The BH will in particular be responsible for:

- Ensuring that PTF members are aware of their obligations regarding the Project and that the Project Document and related annexes (including results matrix, work plans, budgets) and the composition of the PTF – are available and known to all members;

- Contacting the FAO Finance Division (CSF) - through the FLO or with copy to the FLO - to request the payment of the first instalment of Project funds by the resource partner/s;

- Reviewing the adequacy of the PTF skills mix with other PTF members (such as the LTO) and with the Technical Officer from the FAO headquarters technical unit (through the LTO), and ensures that membership of the PTF is continuously updated in response to changing needs;

- In close consultation with the LTO, the officer from the FAO headquarters technical unit to which the LTO directly relates from a technical perspective, and other PTF members as needed, the BH leads the finalization of the ToR for project staff who need to be recruited and appointed and proceeds with recruitment and appointment procedures;

- In prompt consultation with PTF members, the BH monitors the work plan and budget and prepares work plan and budget revisions, according to established procedures and whenever updated planning indicates that a budget revision is required;

- Identifying requirements for cash and notifies CSF to prepare a call for funds to the resource partners (through the FLO);

- With the support of the FLO and FAO Finance Division as/if needed, the BH ensures that all conditions in the agreement with the resource partners are respected;

- By drawing on the expertise of other PTF members, the BH coordinates all project activities related to results monitoring, performance assessment and reporting, including the timely and quality preparation and submission of Project Progress Reports (PPRs), midterm and terminal reports.

The BH will, in consultation with the FAO/GEF Coordination Unit, give no-objection to the AWPs/Bs submitted by the executing partners/agencies. Disbursement of GEF funds for the provision of goods, minor works, and services to the Project will be carried out by the BH in accordance with the provisions of the Execution Agreement, Letters of Agreement and/or UN to UN Agreements. The disbursement will be carried out upon submission by the executing partners/agencies to the BH of six-monthly financial statements of expenditures, procurement and contract documentation, and disbursement requests based on an updated AWP/B including detailed budget for the following six months period to be cleared and approved by the BH and a PPR to be approved by the Project Coordinator.  The BH will submit the PPR to the FAO/GEF Coordination Unit for clearance and uploading on the FAO/FPMIS.

The role of the LTO is central to FAO’s comparative advantage for projects and is designated with due attention to the location (subsidiarity principle), technical expertise, and available time to support the Project. The LTO coordinates and ensures the flow of technical expertise and backstops the Project throughout the project cycle. In the formulation prophase, the LTO’s roles and responsibilities cover three broad areas: (i) management and technical oversight of the PTF, (ii) environmental and social risk management, and (iii) technical clearance.

More specifically, the LTO will:

- Maintain a technical support and backstopping schedule, in consultation with PTF members, other technical officers, and the BH;

- Oversee and carry out technical backstopping to the project and prepare back-to-office reports from all backstopping missions and submit them to the PTF members and others;

- Support the BH in the implementation and monitoring of the work plan and the budget, including work plan and budget revisions and the preparation of progress and terminal reports;

- For technical information in project standard narrative reports for which the BH is responsible (such as progress, terminal), ensure accuracy and soundness;

- Prepare other technical reports or oversees their preparation by Chief Technical Advisors (CTA) or other technical staff;

- Technically clear all project reports (progress, terminal and ad hoc technical reports);

- Prepare (or oversees preparation) of technical specifications for procurement, and provides or obtains clearance of technical specifications for procurement;

- If not already finalized during project formulation and implementation, support the BH and oversees the technical aspects in the development of ToR for staff who are recruited for the project implementation (such as CTAs, national coordinators, and technical staff);

- Beyond individual projects, all technical officers (regardless of whether they are the LTO) are required to share knowledge with other projects to contribute to good results.

- Support the Project Coordinator in reviewing and clearing final technical products delivered by consultants and contract holders financed by GEF resources before the final payment can be processed;

- Assist with the review and provision of technical comments to draft technical products/reports on request from the executing /partners agencies during project execution;

Review and approve PPRs submitted by the executing partners/agencies to the BH in coordination with the Project Coordinator;

- Prepare the annual PIR, supported by the Project Coordinator (see below) and inputs from the executing partners/agencies, to be submitted for clearance and completion by the FAO/GEF Coordination Unit which will subsequently submit the PIR to the GEF Secretariat and its Evaluation Office as part of the Annual Monitoring Review Report of the FAO-GEF portfolio;

- Review and revise the TOR for the midterm evaluation and participate in the midterm workshop with all key project stakeholders.

The FAO/GEF Coordination Unit will review PPRs, financial reports and budget revisions. It will review the annual PIR and undertake supervision missions if considered necessary. The PIRs will be included in the FAO/GEF Annual Monitoring Review submitted to GEF by the FAO/GEF Coordination Unit. The Unit will also participate in the midterm and terminal evaluations as well as the development of corrective actions in the Project implementation strategy in the case needed to mitigate eventual risks affecting the timely and effective implementation of the Project. The FAO/GEF Coordination Unit will, in collaboration with the FAO Finance Division, request transfer of project funds from the GEF Trustee based on six monthly projections of funds needed.

The FAO Finance Division will assist in the provision of annual Financial Reports to the GEF Trustee and, in collaboration with the FAO/GEF Coordination Unit, call for project funds from the GEF Trustee upon the approval of the project document.

### 4.2.2 Executing partners/agencies

The Project will be implemented by executing partners/agencies within the framework of FAO’s role as the GEF Lead Agency. The executing partners/agencies are directly responsible for technical implementation of the Project activities that they have entered agreements, including day-to-day monitoring as well as financial management and purchase of goods, minor works, and services (procurement) in accordance with FAO rules and regulations and GEF minimum fiduciary standards. As described above, the executing partners/agencies will enter into execution agreements with FAO that outline in details their roles and responsibilities and the procedures with respect to financial management, procurement, recruitment, project progress reporting, financial reporting and audit, copyright, and other legal aspects of collaboration.

With regard to staffing, there will be national project teams consisting of National Project Coordinators and Project technical and support staff (see above and ToRs in Appendices).

## 4.3 Financial planning and management

### 4.3.1 Financial plan (by component, outputs and co-financier)

The financial planning by component, output and co-financier is given in Table 6 below.

### 4.3.2 GEF inputs

The GEF contribution to the Project will be used to support the described activities (see Section 2) supporting the generation of global benefits in support of environmental, economic and social sustainability and cannot be adequately funded by local stakeholders at present. These activities will complement the baseline projects as described in detail in previous sections, leveraging and complementing the existing investments.

### 4.3.3 Government inputs

Government inputs will be made in the context of national in kind contributions to the Project implementation. These in kind contributions will consist mainly of staff time and the provision of office space.

### 4.3.4 FAO inputs

FAO as the Project’s implementing agency will contribute US$ 27 million in kind, consisting mainly of staff time for technical and coordinating support.

Table 6: Financing plan by outputs and co-financers

| Component / output | Cabo Verde | Cote d’Ivoire | Senegal | Abidjan Convention & UNEP | CSOs (CAOPOA FENACOPECI, Fisher Ass. CPV | MSC | BirdLife | CONXEMAR | FAO | Total Co-financing | % Co-financing | GEF | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Component 1: Improving fisheries governance and management |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Sub-Total | 1,350,000 | 2,700,000 | 2,250,000 | 802,631 | 45,675 | 236,842 | 235,294 | 900,000 | 10,295,000 | 18,815,442 | 863% | 2,179,288 | 20,994,730 |
| Component 2: Strengthening the seafood value chain |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Sub-Total | 900,000 | 1,800,000 | 1,500,000 | 189,474 | 30,450 | 631,579 | 35,294 | 600,000 | 8,090,000 | 13,776,797 | 577% | 2,386,042 | 16,162,839 |
| Component 3: Strategic communication, monitoring and evaluation, and up-scaling of best practises |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Sub-Total | 750,000 | 1,500,000 | 1,250,000 | 157,895 | 25,375 | 131,579 | 29,412 | 500,000 | 8,305,000 | 12,649,261 | 810% | 1,561,362 | 14,210,623 |
| PMC |  |  |  |  |  |  |  |  | 310,000 | 310,000 | 101% | 306,335 | 616,335 |
| Total Project | 3,000,000 | 6,000,000 | 5,000,000 | 1,150,000 | 101,500 | 1,000,000 | 300,000 | 2,000,000 | 27,000,000 | 45,551,500 | 708% | 6,433,027 | 51,984,527 |

### 4.3.5 Financial management of and reporting on GEF resources

All financial management and reporting in relation to the GEF resources will be carried out in accordance with FAO’s rules and procedures for the implementation of projects under FAO’s direct execution.

Financial Records: FAO shall maintain a separate account in USD for the Project’s GEF resources showing all income and expenditures. Expenditures incurred in a currency other than US$ shall be converted into US$ at the United Nations operational rate of exchange on the date of the transaction. FAO shall administer the Project in accordance with its regulations, rules, and directives.

Financial Reports: The BH shall prepare six-monthly project expenditure accounts and final accounts for the Project, showing amount budgeted for the year, amount expended since the beginning of the year, and separately, the un-liquidated obligations as follows:

- Annually: Details of project expenditures on a component-by-component and output-by-output basis, reported in line with project budget codes as set out in the Project document, as at 30 June and 31 December each year.

- Final report: Final accounts on completion of the Project on a component-by-component and output-by-output basis, reported in line with project budget codes as set out in the Project document.

- A final statement of account in line with FAO Oracle Project budget codes, reflecting actual final expenditures under the Project, when all obligations have been liquidated.

Financial reports for submission to the donor (GEF) will be prepared in accordance with the provisions in the GEF Financial Procedures Agreement and submitted by the FAO Finance Division

Budget Revisions. Budget revisions will be prepared by the BH in accordance with FAO standard guidelines and procedures as needed. The budget revision will take into consideration the status of the implementation of the Project activities towards achieving specific outputs and outcomes. The budget revision will be submitted by BH through FPMIS. The budget revision should be prepared based on field needs and the agreed AWP. The Project Task Manager (PTM) normally prepares the draft budget revision proposal to BH and LTO for their reviews, and then BH will submit the budget revision to FAO/GEF Coordination Unit for approval. Budgets are the costed equivalent of the work plan in that they foresee the transformation of inputs into activities and activities into outputs. Budget management, monitoring, and revision are the responsibility of the BH and constitute a substantive, integral, and essential component of project management. The BH is required to carry out at least two budget revisions per year in full consultation with the FAO Project Technical Task Force: (i) in March following the corporate equalization process (explained in the following paragraph), and (ii) in September/October to support work-planning for the following year, to ensure that expenditures that have occurred in the year are adequately covered by the corresponding budget.

Responsibility for Cost Overruns. The BH is authorized to enter into commitments or incur expenditures up to a maximum of 20 percent over and above the annual amount foreseen in the project budget under any budget sub-line provided the total cost of the annual budget is not exceeded.

Any cost overrun (expenditure in excess of the budgeted amount) on a specific budget sub-line over and above the 20 percent flexibility should be discussed with the FAO/GEF Coordination Unit with a view to ascertaining whether it will involve a major change in project scope or design. If it is deemed a minor change, the BH shall prepare a budget revision in accordance with FAO standard procedures. If it involves a major change in the project’s objectives or scope, a budget revision and justification should be prepared by the BH for discussion with the GEF Secretariat.

Savings in one budget sub-line may not be applied to overruns of more than 20 percent in other sub-lines even if the total cost remains unchanged, unless this is specifically authorized by the GCU upon presentation of the request. In such a case, a revision to the Project document amending the budget will be prepared by the BH. Under no circumstances can expenditures exceed the approved total Project’s budget or be approved beyond the NTE date of the project. Any over-expenditure is the responsibility of the BH.

Audit: The Project shall be subject to the internal and external auditing procedures provided for in FAO financial regulations, rules, and directives and in keeping with the Financial Procedures Agreement between the GEF Trustee and FAO. The audit regime at FAO consists of an external audit provided by the Auditor-General (or persons exercising an equivalent function) of a member nation appointed by the Governing Bodies of the Organization and reporting directly to them, and an internal audit function headed by the FAO Inspector-General who reports directly to the Director-General. This function operates as an integral part of the Organization under policies established by senior management, and furthermore has a reporting line to the governing bodies. Both functions are required under the Basic Texts of FAO, which establish a framework for the terms of reference of each. Internal audits of accounts, records, bank reconciliation, and asset verification take place at FAO field and liaison offices on a cyclical basis.

## 4.4 Procurement

Careful procurement planning is necessary for securing goods, services and works in a timely manner, on a “Best Value for Money” basis. It requires analysis of needs and constraints, including forecast of the reasonable timeframe required to execute the procurement process. Procurement and delivery of inputs in technical cooperation projects will follow FAO’s rules and regulations for the procurement of supplies, equipment, and services (i.e. Manual Sections 502 and 507). Manual Section 502: “Procurement of Goods, Works and Services” establishes the principles and procedures that apply to procurement of all goods, works and services on behalf of the Organization, in all offices and in all locations, with the exception of the procurement actions described in Procurement Not Governed by Manual Section 502. Manual Section 507 establishes the principles and rules that govern the use of Letters of Agreement by FAO for the timely acquisition of services from eligible entities in a transparent and impartial manner, taking into consideration economy and efficiency to achieve an optimum combination of expected whole life costs and benefits.

As per the guidance in FAO’s Project Cycle Guide, the BH will draw up an annual procurement plan for major items, which will be the basis of requests for procurement actions during implementation. The first procurement plan will be prepared at the time of project start-up, if not sooner, in close consultation with the National Project Coordinators/Officers, the PTM and the LTO. The plan will include a description of the goods, works, or services to be procured, estimated budget and source of funding, schedule of procurement activities and proposed method of procurement. In situations where exact information is not yet available, the procurement plan should at least contain reasonable projections that will be corrected as information becomes available.

The procurement plan shall be updated every 12 months and submitted to BH and LTO for clearance, together with the AWP/B and annual financial statement of expenditures report for the next instalment of funds.

The BH, in close collaboration with the National Project Coordinators/Officers, the PTM and the LTO will procure the equipment and services provided for in the detailed budget in APPENDIX 5, in line with the AWPs/Bs and in accordance with FAO’s rules and regulations.

The BH for extra budgetary funds is responsible for development and submission of a Procurement Plan for use of the extra budgetary funds based on reasonable estimates of annual requirements or as soon as possible after identifying new requirements (which may be at the time of finalization of the project documents).

Procurement plan included in APPENDIX 5.

## 4.5 Monitoring and Reporting

### 4.5.1 Oversight and monitoring responsibilities

The PTM in collaboration with National Project Coordinators/Officers and project staff will be responsible for monitoring and reporting activities, including of collection of baseline data. FAO and GEF monitoring and evaluation policies and guidelines will be followed. The M&E is an essential part of the CFI Program as it will also facilitate learning and mainstreaming of CFI outcomes and lessons learned. The Global Partnership project will support M&E and sharing of learning generated by the child project at the CFI Program level.

The CFI Program Results Framework (as originally appended to the CFI PFD as Annex 7) will form the basis of the overall monitoring and evaluation of the Programme. A detailed M&E system for the overall program will be developed by the Global Partnership project, which will form the common M&E framework for the CFI Program as a whole. This will also outline how a clear conceptual framework is necessary to produce consistent and objective, evidence-based analysis. The CFI Program is also informed by the CFI Theory of Change (ToC), which identified a series of tiered building blocks critical to achieving the program’s outcomes (see below and (APPENDIX 11).

The M&E system will have explicit inclusion of gender indicators and baseline data. This will be developed in collaboration with Project stakeholders, in particular the postharvest women gourps, when elaborating the Project gender strategy.

The details of the Project’s M&E system, including establishment of a CFI Program ToC baseline, will be put in place during the first six months of Project implementation and will feed back into Project implementation.  Component 3 contains the activities related to M&E and this component has been budgeted at USD 180,000 (see table in chapter 4.5.4 below).

### 4.5.2 Indicators and information sources

M&E of progress in achieving Project results and objectives will be done based on two parallel processes:

- Using the targets and indicators established in the project Results Framework (APPENDIX 1) and in accordance with the descriptions of the Project framework and expected results in Section 2.

- Using the CFI Program ToC which spans the four tiers of the CFI ToC outcomes (i) enabling conditions, (ii) changes in behaviour, (iii) improvements to the fisheries-related social and environmental conditions, and (iv) ultimate goal of dynamic sustainability in resilient ecosystem, the relevant markes of change include the 3-6 common CFI programme markers that will be identified and used at the baselines and at the mid-term and terminal assessmsents. The markers of change will include the ToC pathways: fisheres stakeholders;  legal frameworks and governance procedures; and CFI partners collaboration. At the start of the project and in coordination with the CFI projects the ToC progamme markers will be validated with at least three common markers across the 5 projects after being identified and agreed to. The methods used to measure these common markers will also be discussed and agred to. Projects can measure more than one of the markers, and each project will cover the costs of measuring the markers. Having a wider analytical framework, the ToC will complement the overall Results Framework M&E and help all actors involved to better appreciate and measure the overall/key changes and impacts on coastal fisheries generated by the CFI child projects.

All CFI projects will use the CFI Program ToC and are expected to progress through the tiers starting with establishing necessary enabling conditions (Tier 1), which will lead to implementing changes in practices (Tier 2), achieving benefits to fisheries and stakeholders (Tier 3) and ulimately leading to system sustainability (Tier 4) (see Error! Reference source not found.). This ToC therefore, provides a programme-level framework for the analysis of emerging challenges and learning across the varios initiatives making up the CFI.

The CFI Program Results Framework and the CFI ToC are linked, specifically the Tier 1 enabling conditions, which are focused around conditions and incentives for stakeholders, institions and collaboration. As noted in the CFI Program first component, CFI will promote sustainability incentives in the value chain addressing the need for correct incentives at the harvesting stage, including new or amended management regimes, reduction in post-harvest losses, implementation of private-public partnerships and development of innovative market incentive systems. As noted in the second component, CFI will strengthen institutional structures and processes, including policy, legislation and institutions, including co-management and access rights regimes, and integrate MPAs into fisheries.  Finally, as noted in the third component, CFI will share best practices, promote collaborate and strengthen fisheries performances measures and assessments.

Within the Program, the objective of the Global Partnership project is to coordinate the other four CFI projects so that collectively the CFI Program goal is achieved. Given the strong coordination and knowledge management role of the Global Partnership project across the four CFI projects, within the Results Framework, this project will contribute strengthening the impact of the CFI interventions and outcomes through coordination of project outputs, knowledge sharing

Additional gender responsive indicators will be developed to measure impact and change, e.g., in terms of improved rights, access, benefits and/or control for women. For example, it would be important to be able to assess men and women's active participation in in decision-making. Increased numerical representation does not automatically translate into increased influence for women. Accordingly, the Project will develop qualitative indicators to measures the extent to which women are able to be actively involved in and influence decisionmaking processes at all levels through their participation. The elaboration of indicators (as well as the gender strategy) will be done in collaboration with stakeholder, in particular the postharvest women groups, to capture their perspective on what aspects are important. Once the indicators are selected they will be measured during baseline, mid-term and terminal assessments.

Moreover, the FPAI developed under the Global Partnership Project will also come in complement to and support of the CFI M&E system, including for this Project. The FPAI will provide a readily available methodology that will be used at project-level M&E to ensure a common and uniform standard of monitoring across the triple bottom line. An updated first version of the FPA containing core indicators will be available within the first 3-6 months of the start of the project and will measure the FP baseline covering the three aspects of the triple bottom line for fisheries selected in consultation with the FPAI experts in the Global Partnership project. This first version will include a combination of data driven and expert judgement indicators, which are commonly available in the selected fisheries of the three regional child projects, and will allow a first diagnosis of the pilot fisheries as well as identification of priorities for future data collection. Once a full suite of indicators, which include the core indicators used during the baseline, are developed, they will be used to assess the state of the fisheries and to measure their performance at the mid-term and terminal evaluation. In summary the FAPI will be measured:

1.       Baseline assessment between 3 to 6 months of project inception (pre-FPAI, diagnosis tool)

2.       Pilot assessment using first version of FPAI (Year 3-4)

3.       Final assessment using revised and final version of FPAI (Year 5).

To the extent relevant, first-order M&E indicators and targets for each of the child projects should mirror those used in the FPAI. Technical assistance, training and procurement of the necessary equipment to administer the M&E System will be provided by the GP, while other costs such as travel associated with training and data collections will be covered by the project.

The Project will also report on the GEF Tracking Tools, both for IW and Biodiverstiy. The Abidjan Convention will be responsible for reporting on the progress of the mangrove work including with regard to the GEF Tracking Tool.

To assess and confirm the congruence of outcomes with Project objectives, physical inspection and/or surveying of activity sites and participants will be carried out. This latter task will be undertaken by the national project teams supported by the PTM.

### 4.5.3 Reporting schedule

The specific project-level reports to be prepared for the Project are:

- Project Inception Report;

- Annual Work Plans and Budgets (AWPs/Bs);

- Project Progress Reports (PPRs);

- Annual Project Implementation Reviews (PIRs);

- Technical reports;

- Co-financing reports; and

- Midterm and terminal reports.

Project Inception Report: After FAO approval of the Project and signature of the execution agreement, an inception workshop will be held. The PTM together with the National Project Coordinators will prepare a draft project inception report in consultation with the Project Task Force (PTF) and other project partners prior to a Project Inception Workshop. Key information from this report should be discussed during the Project Inception Workshop and the report subsequently finalized. The report will include a narrative on the institutional roles and responsibilities and coordinating action of Project partners, progress to date on project establishment and start-up activities, and an update of any changed external conditions that may affect project implementation. It will also include a detailed first year AWP/B and a detailed Project monitoring plan. The draft inception report will be circulated to the Project Steering Committee and the CFI Program management for review and comments before its finalization, no later than one month after project start-up. The report should be cleared by the BH and LTO and the FAO/GEF Coordination Unit and will be uploaded in the FPMIS.

Annual Work Plans and Budgets (AWPs/Bs): The executing partners/agencies will submit AWPs/Bs to the BH that are divided into monthly timeframes detailing the activities and progress indicators that would guide implementation during the year of the Project. The PTM will include inputs from the National Project Coordinators/Officers and executing partners/agencies and draft the first AWP/B, in consultation with the Project Task Force. As noted earlier, the first AW/B will be presented at the project Inception Workshop. As part of the AWP/B, a detailed Project budget for the activities to be implemented during the year should be included together with all monitoring and supervision activities required during the year. The inputs of the Inception Workshop will be incorporated and the PTM will submit a final draft AWP/B within two weeks of the workshop to the BH. For subsequent AWP/B, the PTM will organize a PPR and plan meetings for its review. Once comments have been incorporated, the BH will circulate the AWP/B to the LTO and the FAO/GEF Coordination Unit for comments/clearance prior to uploading in FPMIS by the BH. The AWP/B must be linked to the Project’s Results Framework indicators so that the Project’s work is contributing to the achievement of the indicators. The AWP/B should include detailed activities to be implemented to achieve the project outputs and output targets and divided into monthly timeframes and targets and milestone dates for output indicators to be achieved during the year. A detailed project budget for the activities to be implemented during the year should also be included together with all monitoring and supervision activities required during the year. The AWP/B should be approved by the Project Steering Committee and uploaded on the FPMIS by the BH.

Project Progress Reports (PPRs): PPRs will be prepared by the PTM based on the systematic monitoring of output and outcome indicators identified in the Project’s Results Framework. The purpose of the PPR is to identify constraints, problems, or bottlenecks that impede timely implementation and to take appropriate remedial action in a timely manner. They will also report on projects risks and implementation of the risk mitigation plan. The PPR will be submitted to the BH and LTO for comments and clearance. The FAO/GEF Coordination Unit will upload the PPR on the FPMIS. The executing agencies will submit to the BH six-monthly project progress reports. The 3rd report should accompany the following year’s draft AWP/B and the 1st and the 2nd reports should be accompanied by the updated AWP/B, for review and no-objection by FAO.

Project Implementation Reviews (PIRs): The PTM will prepare annual PIRs covering the period July (the previous year) through June (current year) to be submitted to the LTO for finalization, which will be shared with BH and the TCI GEF Funding Liaison Officer (FLO) for review and approval no later than (check each year with GEF Unit but roughly end June/early July each year). The FAO/GEF Coordination Unit will submit the PIR to the GEF Secretariat and GEF Evaluation Office as part of the Annual Monitoring Review report of the FAO-GEF portfolio. PIRs will be uploaded on the FPMIS by the FAO/GEF Coordination Unit.

Key milestones for the PIR process:

- Early July: the LTOs submit the draft PIRs (after consultations with the BH and project teams) to the FAO/GEF Coordination Unit for initial review;

- Mid July: the FAO/GEF Coordination Unit’s responsible officers review the main elements of PIR and discuss with the LTO as required;

- Early/mid-August: the FAO/GEF Coordination Unit prepares and finalizes the FAO Summary Tables and sends to the GEF Secretariat by a date that is communicated each year by the GEF Secretariat;

- September/October: the PIRs are carefully and thoroughly reviewed by the FAO/GEF Coordination Unit and discussed with the LTOs for final review and clearance;

- Mid November 17: (date to be confirmed by the GEF): the FAO/GEF Coordination Unit submits the final PIR reports to the GEF Secretariat and GEF Evaluation Office.

Technical Reports: Technical reports will be prepared by national and international consultants as part of project outputs and to document and share project outcomes and lessons learned. The drafts of any technical reports must be submitted by the PTM to the BH who will share it with the LTO. The Project Steering Committee may also be involved in peer review of relevant technical reports. The LTO will be responsible for ensuring appropriate technical review and clearance of said report. The BH will upload the final cleared reports onto the FPMIS. Copies of the technical reports will be distributed to project partners and the Project Steering Committee as appropriate.

Co-financing Reports: The BH, with support from the PTM, will be responsible for collecting the required information and reporting on co-financing as indicated in the Project Document and CEO Endorsement Request. The PTM will compile the information received from the executing partners/agencies and transmit it in a timely manner to the LTO and BH. The report, which covers the period 1 July through 30 June, is to be submitted on or before 31 July and will be incorporated into the annual PIR. The format and tables to report on co-financing can be found in the PIR.

Tracking Tools: Following GEF policies and procedures, the relevant IW tracking tools submitted with the Project Document, at CEO Endorsement Request, will be updated at the project’s midterm review/evaluation, and with the project’s terminal evaluation or final completion report. The tools will be uploaded in FPMIS by the FAO/GEF Coordination Unit. The GCU will coordinate the filling of the tools, with inputs from relevant stakeholders. The LTO will ensure the technical accuracy of the tools.

Terminal Report: Within two months before the end date of the project, and one month before the final evaluation, the Project Coordinator will submit to the BH and LTO a draft Terminal Report. The main purpose of the Terminal Report is to give guidance on the policy decisions required for the follow-up of the project, and to provide the donor with information on how the funds were utilized. The report is accordingly a concise account of the main products, results, conclusions, and recommendations of the project, without unnecessary background, narrative, or technical details. The target readership consists of persons who are not necessarily technical specialists but who need to understand the policy implications of technical findings and needs for insuring sustainability of project results.

### 4.5.4 Midterm Review and Final Evaluation Plan

The BH, in consultation with the FAO Project Technical Task Force, and with concurrence of the Project Steering Committee, will field an independent midterm review of the Project. This midterm review will be undertaken at Project mid-term to review progress and effectiveness of implementation in terms of achieving the project objectives, outcomes, and outputs. Findings and recommendations of this review/evaluation will be instrumental for bringing improvement in the overall project design and execution strategy for the remaining period of the project’s term. FAO will arrange for the mid-term review/evaluation in consultation with the project partners. The evaluation will, inter alia:

- review the effectiveness, efficiency and timeliness of project implementation;

- analyse effectiveness of partnership arrangements;

- identify issues requiring decisions and remedial actions;

- propose any mid-course corrections and/or adjustments to the implementation strategy as necessary; and

- highlight technical achievements and lessons learned derived from project design, implementation, and management.

The FAO’s Office of Evaluation will field an independent Final Evaluation, which will be carried out three months prior to the terminal review meeting of the project partners, following the GEF Terminal Evaluation Guidelines. The evaluation will be aimed at identifying the Project’s impacts, the degree of achievement of the Project’s results and their sustainability. This evaluation will also have the purpose of indicating future actions needed to sustain project results and disseminate products and best practices within the country and to neighbouring countries.

A summary of the Project’s M&E activities at the project level is presented below.

| Type of M&E activity | Responsible Parties | Time-frame | Budgeted costs |
| --- | --- | --- | --- |
| Inception Workshop | Executing partners/agencies, BH, LTO and PTM | Within two months of project start | USD 40,000 (primary costs coming from CFI GP) |
| Project Inception Report | Executing partners/agencies BH, LTO and PTM | Immediately after workshop | None (in-kind co-financing and GEF agency fee) |
| Design and set-up of M&E System including training of staff and equipment | PTM and executing partners/agencies | As early as possible after project start | USD 20,000 |
| Supervision visits and Implementation Reports | PTM with inputs from executing partners/agencies | Quarterly | FAO visits to be paid by GEF agency fee. PTM’s visits to be paid from project travel budget. |
| Project Progress Reports | Executing partners/agencies | Four-monthly | In-kind co-financing |
| Project Implementation Review | PTM and FAO/GEF Coordination Unit | Annually | Paid by GEF Agency fee |
| Co-financing Reports | Executing partners/agencies | Annually | In-kind co-financing |
| Technical reports | PTM and executing partners/agencies | As appropriate | In-kind co-financing and GEF agency fee |
| Supervisory visits to project and field sites | LTO and PTM | Yearly or as required | Paid by GEF Agency fee |
| Midterm Review | External consultants, FAO/GEF Coordination Unit with the project team and stakeholders | At mid-point of project implementation | USD 40,000 |
| Terminal evaluation | FAO Office of Evaluation in consultation with the project team and stakeholders and support by external consultants as required | At the end of project implementation | USD 80,000 |
| Total (GEF funding) |  |  | USD 180,000 |

## 4.6 Provision for evaluations

An independent midterm evaluation will be undertaken during the third year of project implementation. The evaluation will determine progress being made towards achievement of objectives, outcomes, and outputs, and will identify corrective actions if necessary. It will, inter alia:

- review the effectiveness, efficiency and timeliness of project implementation;

- analyse effectiveness of implementation and partnership arrangements;

- identify issues requiring decisions and remedial actions;

- identify lessons learned about project design, implementation and management;

- highlight technical achievements and lessons learned; and

- propose any mid-course corrections and/or adjustments to the implementation strategy as necessary.

An independent terminal evaluation will take place three months prior to the terminal review meeting of the project partners and will focus on point (d) and (e) listed above. In addition, the final evaluation will review the Project’s impacts, analyze the sustainability of the results and whether the Project has achieved its environmental and development objectives. The evaluation will furthermore provide recommendations for follow-up actions.

Draft Terms of Reference for the midterm and terminal evaluation will be prepared and finalized in close consultation with the PTM, the FAO/GEF Coordination Unit; under the ultimate responsibility of the FAO Office of Evaluation, in accordance with FAO evaluation procedures and taking into consideration evolving guidance from the GEF Evaluation Office.

## Communication and visibility

The Global Partnership Project will play a key role in knowledge sharing and analyses of outputs and outcomes across the three regions and with coastal fisheries  globally for the production of global knowledge products and coordination of dissemination mechanisms (e.g. listserve, webinars, knowledge products, website, workshops, newsletters, blogs, stakeholder exchanges, conferences) (see figure in APPENDIX 10). Contributions from all projects will be critical to the success of this knowledge sharing. Given the importance of M&E and knowledge sharing, for each project a total of 25 percent of funds have been allocated to these components, including 5-10 percent for M&E, 10-15 percent for knowledge sharing within the Project and 10-15 percent for knowledge sharing within the CFI Program.

The budget of component 3 is contributing to the communication, visibility and knowledge sharing of the Project. There are also knowledge products produced by other outputs of the Project, in particular by output 1.1.1 (contribution to international legal guidance), output 1.1.3 (indicators), and 1.1.4 (coordination and knowledge sharing at national level). The cost-sharing (with the Global Partnership project) of the testing of the FPAI is also included in component 3..

Through the Global Partnership Project, the CFI will develop a Knowledge Management Strategy, building on the strategic principles contained in the 2011 FAO Knowledge Strategy. The CFI strategy will use existing GEF approaches and platforms such as IW-LEARN. The purpose is to stimulate the generation, dissemination and application of information and knowledge, including statistics. The strategy will use the CFI Program Global Reference Group as one important source of knowledge; the group participants will serve as peer reviewers and disseminators of lessons learnt. The strategy will also build on the best practices that have been outlined in the Knowledge Management Toolkit (http://www.kstoolkit.org/home).

This CFI Program strategy will assist this Project and the other CFI child projects in developing their own knowledge strategies and ensuring strong coherence and linkages between them. The CFI and project strategies must be conceptually rigorous, practical and results-based. They will build upon successful techniques already being used and encourage innovation. Technology is an important enabler but it should be subordinated to policy, people and process considerations. Since certain technologies change over time, the strategy will strive to be “technology-neutral”. To promote continuous improvement, the strategies will also be iterative and every opportunity will be taken to learn from both successes and failures. The scope of support activities may include coordination, provision of an enabling environment, specific services to technical programs, and direct services to member states.

At the CFI Program level, a plan will be established for catalyzing discussions and exchanges of experiences. The key issues of interest upon which collaborative learning will focus are:

- Fisheries governance: legislation/policies and management plans that apply the principles and practices of EAF;

- Gender issues: the involvement and responses to issues raised by women involved in the fisheries value chain;

- Application of Marine Spatial Planning (MSP) to EAF principles and practices, with an emphasis on MPAs that allow some forms of fishing:

- Recognition that coastal community well-being is a foundation for sustainable coastal fisheries outcomes.

Under the overall coordination and support of the Global Partnership project, each child project will be responsible for one of the four issues for ensuring that knowledge is shared. This Project will lead the fisheries governance issue, including EAF and the application of the provisions and principels of the SSF Guidelines. The CFI knowledge management sharing mechanism is illustrated in APPENDIX 10 and is further described in the Global Partnership project document. The role of this Project will also be developed in the Project’s communication strategy that will be elaborated during the inception phase.

It is expected that the main lessons and best practices shared through the knowledge management mechanism will originate mainly from the following cross-cutting subjects/issues with the thematic areas [as listed above]:

- Participation and inclusiveness: Ensuring that all concerned stakeholders are engaged in the process of decision-making about the resources they depend on is vital;

- Gender equality and equity: Gender equality is fundamental to any development but particular attention will be paid to this principle in CFI in recognition of the vital role of women in coastal fisheries. CFI will promote equal rights and opportunities for women and men, and ensure women's representation and involvement in decision-making that effects them and their livelihoods;

- Compatibility with international instruments: CFI will ensure that its activities incorporate and are compatible with other key instruments related to fisheries including international conventions and guidelines to which countries and international organizations have subscribed;

- Adaptability and flexibility: Global experience in fisheries management has demonstrated clearly that solutions need to be adapted to local contexts. While transferable lessons and best practice will be sought out and disseminated, the limitations of replicability will be recognized;

- Building on strengths: CFI will seek to build on the strengths and capacities of the partners involved. This will include the GEF Agencies cooperating in the initiative, governments, other partner organizations involved in its different components, the wider international community of concerned agencies, academia, civil society and private sector representatives;

- Addressing the whole fisheries value chain: CFI will ensure that initiatives it supports address issues along the entire fisheries value chain and the stakeholders involved from production to sale;

- Transparency: Clearly defining and widely publicizing policies, laws and procedures in applicable languages, and widely publicizing decisions in applicable languages and in formats accessible to all;

Accountability: Holding individuals, public agencies and non-state actors responsible for their actions and decisions according to the principles of the rule of law, and providing opportunities for feedback and discussion of interventions between agencies responsible for their implementation and those affected by them

The CFI FPAI, to be developed by the CFI Global Partnership project and pilot tested in the CFI child project fisheries including in this Project, intends to initially provide a framework for knowledge sharing and learning within the CFI. The longer term vision for the CFI FPAI instrument is a common framework that can be applied to a wide range of fisheries, in a wide range of data conditions, at a sufficiently low cost that a critical mass of case studies can be assembled for purposes of comparison and identification of what management strategies consistently improve fishery outcomes in different contexts. Accordingly, the CFI Global Partnership FPAI component will develop a methodology for fisheries assessments from a social, economic and environmental perspective specific to data poor contexts. It will be piloted in the three regions to consolidate the tool for wider dissemination globally. It will benefit the projects by providing access to the latest tool for assessing the status of their fisheries and the projects will contribute to FPA by serving as a testing ground for the tool.

Knowledge sharing at the national and regional levels will be promoted through collaboration with relevant regional bodies and projects (see descriptions above in Section 1). The Project budget, in particular in component 3, includes funding of national and regional workshops and relevant regional bodies will be invited as appropriate, or meetings will be organised with regional organizations. Key RFBs are the SFRC and the FCWC, as well as CECAF. Moreover, FAO will ensure that results and experiences are shared more broadly, also outside the West Africa region. The Abidjan Convention through its Conferences of Contracting Parties (COP) and bureau meetings, as well as other meeting and training/capacity building occasions, will share the results and outcomes and, where possible, embed any relevant mangrove training/manuals etc into other national and regional meetings.

It is noted that knowledge sharing should take place in both French and English, as well as in local languages as required (in particular Portuguese for Cabo Verde). Staff and consultants recruited with knowledge management responsibilities will be have the necessary language skills and knowledge products will be produced in the languages required and appropriate.

The Project will participate in IWLEARN, including biannual IW Conferences, annual LME conferences and other activities, as appropriate. It is expected that 1 percent of the Project budget will be allocated towards these activities (included in the overall budget in component 3).

# SECTION 5 – Sustainability of RESULTS

The different dimensions of sustainability are interlinked. In accordance with the United Nations Conference on Sustainable Development (Rio+20) outcome document “The future we want”, there is a need for considering economic, social and environmental sustainability at the same time. This Project will ensure multi-dimensional sustainability by leveraging community-based, national and regional efforts to responsibly utilize and process fishery resources, while reducing the threats to the environment and ensuring human benefits.  The Theory of Change of the global CFI Program highlights how better governance of coastal fisheries is key to ensuring that the potential environmental, social and economic benefits from the sector are sustained. And three interrelated elements are identified as underpinning the achievement of better governance:

- Adopting a holistic approach to the process of developing better governance arrangements;

- Ensuring that resource users recognize, and are able to realize the benefits from, appropriate incentives for better management;

- Putting in place a policy and institutional environment that enables the establishment and realization of those incentives.

As the global CFI Program involves GEF Agencies with significant roles in coastal fisheries both globally and nationally, the lessons learnt and best practices from this Project will be disseminated, shared and applied in new initiatives. The close links and involvement of global and regional bodies will further support Project sustainability and provide opportunities for upscaling.

## 5.1 Social Sustainability

The CFI Program in general – and this Project in particular – address important dimensions of human well-being through their focus on the social aspects. Social sustainability will be achieved through the participatory project implementation strategy that applies to all Project components. Special focus will be given to small-scale fishing communities and their livelihoods. By seeking to empower fishers and fish workers to engage effectively in coastal fisheries governance, management and development along the value chain, the Project will ensure that all actors – men, women, youth – have a stake in the overall sustainability of coastal fisheries.

The Project will support the implementation of the SSF Guidelines that provide a framework for governance and development of small-scale fisheries within a context of sustainable resource utilisation and human rights with the objective to contribute to food security and poverty eradication. Principles of equitable development and gender equality will guide Project implementation and decision-making.

Specific actions included in the Project for strengthening participatory management processes and ensuring social sustainability include, among other things:

- Support capacity development at the community level to enable fishers and fish workers to participate in fisheries management and development processes, and promote co-management.

- Review legislation and practices in relation to working conditions, in particular for women in the postharvest sector, with a view to promote decent work.

- Support value chain actors, in particular women processor organisations, in applying best practices, developing investment plans and gaining better access to resources as well as markets.

Particular attention will be given to the need to strive for a proper gender balance, not only in terms of the immediate Project target group but also among all other actors in the Project and CFI Program institutional arrangements, including those for, for example, peer reviewing, experience sharing and identification of good practices. Women play a major role in fisheries and their involvement is critical to the functioning of the sector. Most postharvest operations are conducted by women, who are entrepreneurs in artisanal operations (e.g. fish smoking) and marketing. The Project includes targeted interventions to contribute to gender equality through the empowerment of women.

With regard to promoting gender equality, the Project will apply the following principles:

- Gender analysis informs the planning and design of activities and interventions.

- A transparent and participatory approach to gender-equality interventions is promoted. Issues, concerns and proposed activities are discussed with communities, partners and other concerned parties.

- Gender awareness is an integral part of training and capacity-building activities.

- Information and data collected and published by the Program are, whenever feasible, gender disaggregated and presented together with an analysis of the meaning and implications of such data.

- Success indicators – for tracking progress toward agreed objectives – on gender-specific measures are included in the monitoring and evaluation system.

## 5.2 Environmental sustainability

A main thrust of the project is about introducing more environmentally sustainable fishing and postharvest practices. The Project will form the basis for sustainable aquatic based livelihoods for generations to come by contributing to the safeguarding of the aquatic and coastal resources that constitute an important basis for food security. FAO and UNEP provide complementary competences for Project implementation with a strong focus on environmental sustainability.

The governance and value chain approach of the Project will lead to more sustainable fisheries and conservation of ecosystems. By ensuring that the knowledge, institutional structures and incentives are in place, practices introduced by the Project will be continued and replicated and environmental sustainability can be ensured. The Project’s focus on building effective institutional structures, including policy and legal frameworks, capacity building and empowerment of resource users as key to successful results and long-term sustainability.

Project interventions particularly in support of environmental sustainability include:

- Review existing legal frameworks and institutional structures and their coherence with EAF, relevant international instruments, co-management and improved rights systems, and promote policy coherence.

- Implement fisheries management plans and strengthened mangrove management and rehabilitation programs based on EAF.

- Improve postharvest practices to decrease the use of firewood and reduce postharvest losses to provide opportunity for improved livelihoods without increasing fishing.

## 5.3 Financial and economic sustainability

The financial and economic sustainability refers to two main aspects: the sustainability of fishing and postharvest activities and related livelihoods, and the sustainability of institutional arrangements – often supported by governments – needed to implement improved governance, including more responsible fisheries management and postharvest practices.

The long-term economic and financial sustainability in relation to fishing operations is closely linked to environmental sustainability. Better management of fishery resources and related ecosystems is a requirement for the existence of sound and profitable fisheries in the future. In the short- and medium-term, there is a risk that fishing incomes will decrease if there is a need to reduce capacity and fishing effort. The integrated value chain approach is crucial in this context where reduced postharvest losses, improved product quality and market access can generate increased incomes. The development of incentives included in Project design will play a crucial role in this respect. The project will also promote PPPs and assist Project stakeholders (e.g., women fish processors) to find interested investors.

With regard to the financial sustainability of institutional arrangements and the funding of these – in particular after Project completion – a key Project approach will be to build on existing structures and develop these rather than creating new ones. National authorities and other stakeholders have been closely involved in Project design, and the Project addresses national priorities. The work planned by the Project is well integrated into existing government programs and this will also support the longer-term sustainability of project results.

## 5.4 Sustainability of capacities developed

The Project will assist in building both institutional structures and capacity in various forms. Support will be provided to, among other things, legal and institutional assessments and training in EAF. Institutional arrangements promoted by the Project and new structures and organizational development will be based on stakeholder analyses and institutional assessments and take an inclusive and participatory approach.

Through PPPs with existing local, national and regional organizations, government agencies, NGOs and other structures, Projects results are absorbed and utilized broadly.  Existing institutional structures and capacity will be strengthened through these new linkages and knowledge, and a broad base for continued action is created.

The sharing of information during the course of the Project will entail that knowledge is held by a range of countries and partners in the region. Through the CFI Program, the knowledge sharing will be supported also at the global level.

## 5.5 Appropriateness of technology introduced

The Project will build on existing experiences and explicitly assist governments and stakeholders to identify best practices for improved fisheries and postharvest sector governance and management. The Project will identify, adapt and develop management measures and postharvest technologies in close collaboration with those who will use it, i.e. fishers and fish workers. FAO and UNEP have considerable experience and technical capacities relevant to the Project and will draw on these resources. Combining local knowledge with international experiences and expertise will ensure the appropriateness of the technologies introduced.

## 5.6 Replicability and scaling up

The Project will explicitly support replicability and scaling up, in particular through its Component 3. There is a great potential for scaling up within the West Africa sub-region and beyond. This can be achieved by disseminating successful pilots into countries faced with similar challenges in West Africa. This is more so because of the role of FAO and UNEP supporting other important programs in the region and collaborating with other development partners. These include, inter alia, the WARFP, the LME projects and the FAO Blue Growth Initiative.

APPENDIX 1: RESULTS FRAMEWORK

(in separate file)

APPENDIX 2: WORK PLAN (RESULTS BASED)

| Output | Activities | Responsible institution/ entity | Year 1 |  |  |  | Year 2 |  |  |  | Year 3 |  |  |  | Year 4 |  |  |  | Year 5 |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 |
| Component 1: Improving fisheries governance and management |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 1.1.1 The national legal and institutional frameworks are reviewed and amended / complemented so that EAF principles are integrated and relevant international instruments can be operationalized (including co-management). | Review existing legal frameworks and their coherence with EAF and relevant international instruments, including the SSF Guidelines, and assess required amendments. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Provide technical support to a consultative process for the preparation of relevant legal and regulatory texts and proposals for modifications of legal frameworks (according to needs in each country) to allow for co-management and improved rights systems. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Review existing institutional structures and support amendments necessary for new co-management arrangements, including improved tenure and access rights systems, and multi-sectorial consultations and planning (EAF) (link to output 1.2.3). |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Support awareness raising and information campaigns with regard to new laws and regulations. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Support and contribute to the development and publication of international good practices guidance for legislation in relation to EAF and the SSF Guidelines. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 1.1.2 Information and capacity building programs are implemented to raise awareness and encourage government policy makers at all levels (MPs, directors, etc.) and relevant institutions to apply EAF and implement international instruments in coastal fisheries and integrate these in relevant policies and strategies | Organise training / awareness raising workshops on EAF and relevant international instruments for government officials in all relevant ministries/departments (also outside fisheries – environment, employment, markets, MPAs, coast guard/MCS, finance). |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Provide support for developing policies and strategies, as required, in line with EAF and promoting the implementation of relevant international instruments. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 1.1.3 Evaluation mechanisms are established for assessing governance effectiveness and the coherence of fisheries related policies, strategies and legal frameworks with sustainability and development objectives (poverty reduction, food security, employment, national economic growth). | Carry out an overall coastal fisheries governance assessment to evaluate whether EAF is effectively applied and to what extent relevant international instruments are reflected. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Support the development of key indicators for assessing coastal fisheries governance effectiveness and policy coherence (in collaboration with development of FPAI of Global Partnership project – see also output 3.2.1). |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Provide support to the establishment of national mechanisms, and development of related guidelines, to regularly evaluate key governance elements and their coherence with environmental, economic and social sustainability goals. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Put in place a mechanism for validating evaluation results with stakeholders and for lessons learnt to feed back into policy making processors. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 1.1.4 Government coordination mechanisms, including consultative frameworks, are put in place and promote coherence and synergies among existing development projects and initiatives in coastal fisheries and related sectors. | Carry out an inventory of existing and planned projects and initiatives in the fisheries sector. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Prepare and implement a permanent advocacy programme on government policies and priorities. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Assist the government to convene meetings twice a year of all relevant donors and development partners for sharing of experiences and joint planning. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 1.2.1 Coastal fisheries management plans are improved in line with EAF and relevant international instruments and implemented. | Identify key fisheries and management plans to be included in the project linking these with project post harvest activities and ensuring a value chain perspective (see project site selection in main text chapter 2.1). |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Carry out stakeholder analysis and assess the potential contribution of postharvest actors (women in particular) to have a role in fisheries and ecosystem management and support their inclusion (see also outcome 1.3). |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Review existing co-management (including rights-based systems and participatory approaches to MCS and data collection) and spatial management measures (e.g., fish refugia – link to output 1.2.2) and identify good practices and incentives to support the implementation of fisheries management plans. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Review selected fisheries management plans and develop implementation plans. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Review fisheries in collaboration with the CFI Challenge Fund to assess potential for further Challenge fund technical assistance (in consultation with value chain actors) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Identify support activities needed for implementing fisheries management plans for economic and social development, e.g., complementary income generating activities, health services and education, and integrate these into the implementation plan. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Support the implementation of the selected and reviewed fisheries management plans. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 1.2.2 Mangrove management and rehabilitation programs are carried out and linked to fisheries management objectives. | Select pilot sites for mangrove rehabilitation/management activities (integrated with other project activities). |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | In selected project sites (i) Assess the importance of mangroves for fisheries and coastal livelihoods, including as potential fish refugia and sustainable use of firewood for fish smoking, and define how mangrove rehabilitation can be integrated into fisheries management plan implementation (output 1.1.1) and sustainable postharvest activities (outcome 1.3); (ii) Review the status of mangroves, including species and abundance; and (iii) Identify main factors influencing mangrove development, utilisation and degradation. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Develop or improve management plans in accordance with EAF, including taking into consideration the dependency of communities (women) on the resource (seafood collectors and processors) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Carry out awareness raising activities. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Support implementation of management plans. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 1.2.3 Support has been provided to national institutional structures responsible for fisheries management for them to have appropriate capacities and mandates to apply EAF, relevant international instruments and co-management. | Assess needs for capacity development and reorganisations within government institutions for EAF management, implementation of relevant international instruments and co-management. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Provide technical support for strengthening government institutions at national and local levels according to needs assessment. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Organise training / awareness raising workshops according to identified needs. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 1.3.1 Coastal fishers and fish workers organisations are formalised and/or strengthened. | Select organisations to be included for support that are relevant to outcome 1.1 and other project value chain activities (see project site selection in main text chapter 2.1) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Assess needs for capacity development and prepare work plan for strengthening organisations to become autonomous. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Provide support for strengthening fishers and fish workers organisations with regard to financial and organisational skills. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Organise training / awareness raising workshops and carry out support activities in close collaboration with civil society and other relevant partners. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Develop community based capacity development arrangements and support leadership training. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 1.3.2 The capacity of coastal fishers and fish workers to participate in fisheries management and development processes is enhanced | Carry out training and capacity development needs. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Organise training and workshops in selected communities on, among other things and according to needs: (i) EAF, (ii) international instruments, in particular SSF Guidelines, and (iii) co-management, (iv) fisheries assessment and data needs, collection and analysis. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Carry out participatory practical research activities involving communities and selected research institutions to strengthen links between fishers and scientists and to support fisheries management plan implementation (see outcome 1.1). |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Component 2: Strengthening the seafood value chain |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 2.1.1 The understanding of the links between consumption and production in the value chain is improved and value chain actors are sensitised on incentives for good practices. | Carry out cost-benefit analysis of selected value chains and distribution of benefits (including equity aspects, and local, national and regional economic impacts) and analyse how demand influences fishing. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Demonstrate and create awareness (through workshops and training) of potential benefits at individual and community levels of applying better postharvest practices and (business) management and how this can influence fishing and resource sustainability. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Carry out training in selected communities and for selected organisations, including leadership training and Training for Trainers (ToT) for community based resource persons/champions. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 2.1.2 The regulatory and normative frameworks for control of fishery products (quality/sanitary standards) and for decent working conditions are improved. | Review existing relevant (i) product regulations and norms in international, regional and national markets, and (ii) current working conditions and related legislation, and assess need for improvements (see also output 1.1.1). |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | In pilot sites, carry out a participatory assessment how norms for international markets could be applied to national markets. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Carry out an assessment of how Occupational Health and Safety (OHS) standards are applied selected value chains / sub/-sectors. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Provide technical support to a consultative process for the preparation of relevant legal and regulatory texts and proposals for modifications of legal frameworks, as required. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Support awareness raising and information campaigns with regard to new laws and regulations. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 2.1.3 Participatory arrangements are in place to support improvement and control of fishery product quality and working conditions. | Develop PPP arrangements for the management of landing sites and other facilities and services. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Develop and test PPP arrangements for the control of fishery product quality and working conditions. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Develop the capacities of value chain actor organisations to be able to participate in and promote PPP arrangements. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 2.2.1 Good practices and innovations are developed to increase incomes and create livelihood benefits while contributing to sustainable fisheries. | Review available experiences with improved fish handling practices, in particular artisanal processing techniques, and identify good practices as well as bad practices, such as use of dangerous chemicals in fish processing. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Through a participatory process, identify potential incentives in support of improved practices and management, test the utilisation of these incentives and support further application of successful results. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Review the access to raw material (fish) for women artisanal processors and traders and how to improve their tenure and access rights. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Implement pilot activities on improved secure tenure rights, focusing on women artisanal processing organisations. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Assist value chain actor organisations (especially women processors) in reviewing their current practice and analyse how improved practices could reduce costs/increase incomes. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Assess existing (micro-) credit schemes and strengthen successful mechanisms suitable for artisanal processing and alternative income generating activities. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Provide support for improving the capacities of value chain actors to implement improved practices and innovations (link to output 2.2.2 and 2.2.3). |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 2.2.2 Appropriate equipment and material, with an emphasis on ‘passive innovations’ (not leading to increased fishing pressure) are available to value chain actors for increasing income and creating other livelihood benefits, including improved working conditions. | Analyse and identify opportunities for investments in equipment and material that will support value chain efficiency (without increasing fishing pressure) and create fairly distributed benefits to value chain actors. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Support value chain actors, in particular women processor organisations, in developing investment plans and engaging with potential funders (donors, banks, etc.), in collaboration with the CFI Challenge Fund, as appropriate. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 2.2.3 Access to national and regional markets by small-scale fishers and fish workers, especially women, is facilitated and improved. | Review market opportunities and develop market strategies for selected products in close collaboration with value chain actors (women small-scale processors). |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Provide support for strengthening value chain actor organisations with regard to market access and regional exports, e.g. through mutualisation arrangements. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Carry out preliminary assessment on Fisheries Improvement Programme (FIP), labelling or certification schemes for selected products carried out. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Component 3: Strategic communication, monitoring and evaluation, and up-scaling of good practises |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 3.1.1 Project communication strategy is developed and implemented and effective communication products developed for sharing project results and lessons learnt. | Develop Project communication strategy |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Develop audio-visual material for disseminating project results and lessons learnt for different media (radio, articles in the press, television, internet) and different stakeholder groups. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 3.1.2 Project experiences are shared through existing platforms and networks, and collaboration is strengthened. | Project work planning in collaboration with partners (see also output 3.2.1) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Organise (two) regional workshops and national ones to share and discuss project results with partners and stakeholders (see also output 1.1.4) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Participate in national and international meetings and conferences and present project results. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Prepare and publish Project results in journals, conferences etc. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Include reports on Project results in CFI and other relevant websites |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 3.1.3 Training, awareness raising and other communication products needed for Project activities are developed and utilised. | Develop communication material (EAF, international instruments, co-management, fisheries assessment and data needs, collection and analysis (see also outcome 1.4). |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Develop training and communication material for improving postharvest practices (see also output 2.1.1) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Produce other training, awareness raising and communication material as needed for Project activities |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 3.2.1 Project monitoring system operating and providing systematic progress information related to Project outcome and output targets in all three countries. | Hold Project inception workshop |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Select Project sites and carry out stakeholder analysis. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Develop Project gender strategy, including indicators, and collect baseline data |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Review of Project document indicators and targets and development of M&E tools. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Develop detailed work plans |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Regular monitoring of project progress, including preparation of progress reports according to FAO, GEF, country and partner requirements. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Participate and support piloting of CFI FPAI development in selected fisheries. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 3.2.2 Implementation and evaluation reports as well as CFI Program ToC assessments to allow Project management and supervisory bodies to ensure operations and achievement of expected results. | Carry out Project mid-term review |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Carry out Project final evaluation. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Carry out assessments according to CFI Programme ToC (including baseline). |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Project management | Recruitment/designation Project staff and establishment of execution agreements etc. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Continuous Project management and oversight. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

APPENDIX 3: RESULTS BUDGET

APPENDIX 4: RISK MATRIX

| Risk Description | Category | Impact | Likeli-hood | Mitigating actions | Owner | Status |
| --- | --- | --- | --- | --- | --- | --- |
| Changes in decision makers, or other events beyond the control of the Project, lead to changes in policies and or the political will to support the Project. |  | H | M | In the Project formulation phase, governments – as well as other stakeholders – have been closely involved and the Project will continue to work closely with governments to foster buy-in and commitment from relevant institutions, as well as through national and local champions. In addition, specific activities have been incorporated for creating awareness among government officials and politicians (output 1.1.2). |  |  |
| Coastal communities do not engage with the Project and key stakeholders do not participate in the Project. |  | H | L | The Project mitigates this risk through planned and significant networking and coordination and collaborative activities, joint planning, regular meetings between the main partners and sharing of information and development. At Project site level, Project staff will be based close to communities and, together with government counterparts, work in partnership with communities and fisheries actors. |  |  |
| The required data and information, or the means for obtaining the data needed (through partner collaboration), are not available. |  | M | M | The lack of data is a common weakness in the context of fisheries governance and management. The Project will work closely with both relevant authorities and resource users and will hence have access to existing data. Through partnerships with other initiatives, such as the EAF Nansen project, new data will also be generated. |  |  |
| Insufficient capacity to implement the proposed governance and fisheries management changes in a manner that builds long-term sustainability. |  | M | M | The scope of the Project has been agreed with relevant authorities and representatives of fisheries actors (small-scale fisheries CSOs). The Project will assist governments to better assess strategies and tools that are available and support capacity building accordingly. The Project will promote arrangements that are feasible and sustainable in the long-term. |  |  |

| Regional and national market demand for improved quality products is weak. |  | M | M | Existing information and perceptions indicate that there is not a lack of demand but of good quality products and of distribution channels. The Project will base its support to improved market access and enhanced product quality on through value chain and market analyses (outcome 2.2). |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Better quality products lead to fish becoming inaccessible for poorer population groups. |  | M | M | While the intention is that improvement of quality will lead to that some products can be sold with a premium price in order for small-scale fishers and fish workers improve their income and livelihoods, a major effect of introducing better postharvest practices will be a decrease in postharvest losses. This means that more produce will be available in the markets overall. It will be important though that the Project monitor prices and possible effects on food and nutrition security in the Project sites. |  |  |
| Lack of willingness and ability of development partners to collaborate. |  | M | L | Many different partners were involved in the Project preparation phase and the CFI Program as a whole is a partnership. Continued dialogue and collaboration with partners will mitigate risks of non-cooperation. |  |  |
| Necessary decisions beyond national level, for example with respect to shared stock management and migration of fisherfolk, cannot be made because of lack collaboration at the regional level |  | M | M | The Project will ensure contacts with governments of neighbouring countries and regional bodies to promote collaboration on issues beyond national control or through regional initiatives or existing processes such as CECAF, SRFC, WCFC, CCLME and GCLME. |  |  |
| Perceived gender roles and cultural practices do not hinder increased involvement of women in strengthened livelihood activities. |  | H | L | The Project will apply a gender sensitive approach and work with both men and women, as appropriate, also for activities that target women more specifically. Women already play an important role in the postharvest sector and the Project is not seeking to drastically change gender roles but to support those who are more vulnerable and promote gender equity. |  |  |

APPENDIX 5: PROCUREMENT PLAN

| Ref. No. | Requirement (Item Description) | Unit (Lts, MT, Kg., etc.) | Estimated quantities | Estimated cost | Unit price | Solicitation Method | Procurement Method | Buyer | Targeted tender launch date | Targeted contract award date | Targeted Delivery date | Final destination and delivery terms | Status | Other Constraints/ Considerations |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |

As per FAO Project Guidelines, this will be completed during inception of the project.

APPENDIX 6: TERMS OF REFERENCE (TORs)

- Project Task Manager (PTM)

- National Project Coordinators (NPCs)

- National Project Officers (NPOs)

- Project site teams

- International consultants

- National consultants

- CFI Project Task Manager

Under the overall supervision of the CFI Programme Coordinator and in close cooperation with other CFI and Fisheries and Aquaculture Departmental staff, the incumbent will be responsible for all technical and coordination aspects and overall implementation of the Global Partnerships and West Africa projects. Specifically, he/she will:

- Be responsible for and ensure that all technical and coordination aspects and overall implementation of the projects are in accordance with FAO and GEFs rules and procedures, and that technical activities implemented within the projects are consistent with the Project Results Frameworks indicators and results-based management target (both);

- Be responsible for global and regional (West Africa) coordination of knowledge sharing and management and the development and implementation of project communication strategies in close collaboration with West Africa NPCs and NFOs, counterparts in the other CFI projects and the Global Partnership communication consultant and Science to Policy officer (WA).

- Be responsible for the implementation of the Project gender strategy (WA).

- Develop and maintain the CFI projects’ M&E systems to support the delivery of the CFI Program and track output and outcome indicators as established in the Projects Results Framework (both);

- Prepare M&E related documentation for the CFI Project and Program Steering Committees and Technical Advisory Groups and the FAO GEF Unit (both);

- Assist in training on M&E and facilitating M&E design and implementation processes with executing partners, as required (both);

- In close collaboration with and based on inputs from National Co-executing and other Partners and the Abidjan Convention Secretariat (where applicable) prepare and follow up on the implementation of Annual Work Plans and Budgets for the projects (both);

- Collect inputs from National Co-executing Partners and others, the Abidjan Convention Secretariat (where applicable)  and prepare six-monthly Project Progress Reports in accordance with FAO-GEF reporting requirements and submit them to the FAO Project Task Forces for comments and clearance (by the LTO) and to the Project Steering Committees for information (both);

- Collect inputs from National Co-executing Partners, Abidjan Convention Secretariat (where applicable)  and other project co-financing partners and prepare an annual report on the invested co-financing (WA);

- Support the LTO in preparing the annual Project Implementation Reviews (PIR) to be submitted to the FAO-GEF Coordination Unit for clearance, (which subsequently submits it to GEF) (both);

- Provide support to Government counterpart institutions as appropriate, and the Abidjan Convention Secretariat (where applicable) and ensure effective and timely execution of planned activities in the countries and at regional level involving other related parties (both);

- Review and clear disbursement requests under the contractual agreements with National Co-executing and other Partners, and procurement and contract documentation for goods and services to be purchased in accordance with the project approved budgets and procurement plans (both);

- Review TOR for consultancies and contracts to be performed under the contractual agreements with National Co-executing Partners for submission to FAO for clearance (both);

- Review and provide comments on technical products delivered by consultants and contract holders contracted by the GEF projects (both);

- Be responsible for partner coordination and liaison with donors and other projects, programmes and organizations and coordinate institutional arrangements and meeting/workshop activities needed to exchange lessons learned, harmonize approaches and coordinate activities to create synergies, and execute the projects at the regional level (both);

- Develop materials for capacity development in collaboration with the LTO, LTU, the Project Task Forces, and in close coordination with participating countries and partners (both);

- Organize the PSC meetings and act as Secretary of the meetings (both);

- In consultation with the FAO Office of Evaluation, LTO, and the FAO GEF Coordination Unit, support the organization of the mid-term review and the final evaluation, contribute to the development of an eventual agreed adjustment plan for project execution and supervise its implementation (both);

- Represent the project in international meetings and in high-level regional and national meetings, as required (both);

- Undertake missions as appropriate to monitor project progress (both); and

- Perform any other duties as required (both).

Location:  Rome Italy/ Praia, Cabo Verde/ Abidjan, Cote d’Ivoire/ Dakar, Senegal

Duration: 4 years (65% WA and 35% GP)

Language: English and French

- National Project Coordinators (NPCs)

The fulltime National Project Coordinators (NPCs) will be appointed by the Government executing partners in the three countries and will lead the Project execution at the national level. Accordingly, the NPCs will take primary responsibility for the implementation of Project activities within his/her country of operation and will ensure that all national inputs and processes required for producing the planned outputs. The NPCs will work closely with the National Project Officers (NPOs) and the PTM. Specifically he/she will:

- Act as Chairperson and Secretary of the National Project Committee with responsibility for convening meetings, drafting agendas and assembling and preparing materials for consideration by the National Project Committee;

- In consultation with the National Project Committee and NPO, identify consultants to undertake national level assignments in accordance with the approved Annual Work Plan, and submit all required documentation to the PTM for their approval and contracting;

- Monitor the work of the above consultants, and as far as possible, ensure the timely and responsive delivery of contracted outputs;

- Provide assistance and support to staff of the PTM or regional consultants visiting, or engaged in assignments in, his/her country of responsibility, including preparing itineraries, appointments and assisting with travel and other logistical arrangements;

- In consultation with the National Project Committee and NPO, determine dates, agendas, budgets and participation for national workshops, and upon approval of these plans by the PTM, undertake the organization and conduct of the workshops;

- Ensure adequate communication and knowledge sharing  of national activities to all stakeholders, including government, private sector and NGOs, and invite and encourage the participation of stakeholders who are not members of the National Project Committee, particularly local groups, in national activities and consultations when appropriate. Also with the support of the NPO identify communication material to be developed and identify  most appropriate one and two-way communication channels for dissemination, and support national and regional communication activities in collaboration with the PTM, and participate, contribute to and coordinate with the CFI Global Partnership communications consultant on programme-wide communication products as well as with counterparts in the other coastal fisheires initiatives and knowledge sharing activities including working with counterparts in other CFI projects as appropriate.

- Support the implementation of fisheries and mangrove activities as appropriate and in the case of mangrove-related work liaise with the Abidjan Secretariat.

- Support implementation of Project gender strategy.

Location:  In Praia, Cabo Verde; Abidjan, Cote d’Ivoire and Dakar, Senegal, respectively. Travel as required, to national Project sites and relevant national, regional and international meetings.

Duration: 4.5 years

Language: French and English, and local languages, as required.

3. National Project Officers (NPOs)

Under the supervision of the national FAO Representative and the overall direction and supervision of the PTM and the technical support and guidance of the LTO, and in close collaboration with the NPCs, the fulltime NPOs will be supporting the administrative / operational and technical implementation of the project at the national and local level. Specifically, he/she will:

- Advise the NPC and facilitate his/her role as Chairperson and Secretary of the National Project Committee, with responsibility for convening meetings, drafting agendas and assembling and preparing materials for consideration by the NTF;

- Assist the National Project Coordinators to prepare national work plans and budgets, and be responsible for the implementation of national work plans;

- Ensure that monitoring mechanisms are in place at the national and local level allowing for tracking progress according to targets established in national work plans as well as to output and outcome indicators in the Project’s Results Matrix;

- Coordinate the project operational arrangements through contractual agreements with key project partners;

- Arrange the operations needed for signing and executing Letters of Agreement (LoA) and Government Cooperation Programme (GCP) agreements with relevant project partners;

- Maintain inter-departmental linkages with FAO units for donor liaison, Finance, Human Resources, and other units as required;

- Ensure the accurate recording of all data relevant for operational, financial and results-based monitoring;

- Ensure that relevant reports on expenditures, forecasts, progress against work plans, project closure, are prepared and submitted in accordance with FAO and GEF defined procedures and reporting formats, schedules and communications channels, as required;

- Execute accurate and timely actions on all operational requirements for personnel-related matters, equipment and material procurement, and field disbursements;

- Provide progress reports to the PTM for compilation into overall Project Progress reports;

- Support national activities, especially related to fisheries and mangroves in the country, supervise national project staff and consultants and prepare contractual arrangements;

- Liaise with relevant national and regional organizations and partners, and identify and support communication (one and two-way) and knowledge sharing, coordination and collaboration activities; in the case of mangrove-related work liaise with the Abidjan Convention Secretariat; in addition support the NPC to identify communication and knowledge sharing products and liaise with the FAO national and regional communication consultants/officers and the CFI Global Partnership communication consulting and Science to Policy specialists (as appropriate)  in the further development and dissemination of communication and knowledge management products including lessons learnednas well as participating in knowledge sharing activities with other CFI projects.

- Participate in Project national and regional workshops and meetings and prepare meeting minutes and proceedings;

- Participate, together with the NPC, in relevant national events and conferences, as required;

- Support the implementation of the Project communication strategy and gender strategy; for example, prepare Project communications, including posts for the CFI website, project newsletter and journal articles or other written communications on Project experiences and achievements;

- Perform other related duties as required.

Location:  In Praia, Cabo Verde; Abidjan, Cote d’Ivoire and Dakar, Senegal, respectively. Travel as required, to national Project sites and relevant national, regional and international meetings.

Duration: 4.5 years

Language: French and English, and local languages, as required.

4. Project Site Teams: National Technical Consultants

Under the supervision of the NPC and the NPO and the overall direction and supervision of the PTM and the technical support and guidance of the LTO, will carry out Project activities in the selected Project sites. There will be three National Technical Consultants in each site with the following profiles:

- Processing and marketing (with emphasis on artisanal processing);

- EAF fisheries management (and co-management);

- Livelihoods and organisational development.

At least one person on the team should have documented knowledge on applying a gender perspective and implementing gender strategies.

The Project’s team will be responsible for Project implementation at the local level. The tasks and responsibilities of each of the Project site team members will be:

- Within one’s field of technical expertise, carry out and technically support local Project activities;

- Collaborate with the other Project site team members and ensure that an integrated approach is taken to Project implementation;

- Ensure involvement and participation of relevant stakeholder groups, paying attention to gender and ensuring that the needs of men, women and youth are taken into consideration in the implementation of activities;

- Support the establishment / strengthening of fisher, fish worker and fishing community organisations and capacity development;

- Liaise with relevant local organizations and partners, and support communication, coordination and collaboration among stakeholders and partners;

- Organise local Project workshops and participate in national Project workshops and meetings;

- Contribute to Project work planning, reporting and M&E in collaboration with the NPC and NPO.

- Document lessons learnt and good practices and share with the NPC and NPO;

- Perform other related duties as required.

Location:  Cabo Verde: Maio and S. Vincente / S. Luzia; Cote d’Ivoire: Abidjan (Locodjro) and Cassandra; Senegal: Iles du Salaam and Dakar. Travel as required.

Duration: 4.5 years

Language: French and local language(s)

5. International Consultants

International consultants will be recruited for specific tasks during Project implementation and will work under the overall direction and supervision of the PTM and the technical support and guidance of the LTO and in close collaboration with the NPCs and the NPOs, and Project site teams and other consultants, as required. The PTM in consultation with the National Project Committees, NPCs and NPOs will assess the need for international consultants but expertise within the following technical fields is expected to be required:

- Legislation and regulations;

- EAF fisheries management (and co-management);

- Processing and marketing (with emphasis on artisanal processing);

- Livelihoods and organisational development.

Specifically, the following consultations are foreseen:

| TASK | OUTPUT |
| --- | --- |
| Carry out legal and institutional reviews and propose amendments, as required | 1.1.1 & 2.1.2 |
| Support awareness raising among decision makers and politicians | 1.1.2 |
| Support the development of policies and strategies, as required, in line with EAF and promoting the implementation of relevant international instruments | 1.1.2 |
| Carry out an overall coastal fisheries governance assessment to evaluate whether EAF is effectively applied and to what extent relevant international instruments are reflected and how they contribute to overall development goals | 1.1.3 |
| Draft Project communication strategy and communication products in English and French | 3.1.1 |
| Draft Project M&E system | 3.2.1 |
| Support the development of gender strategy | 3.2.1 |
| Carry out stakeholder analysis | 3.2.1 |
| Support the organisation of Project inception workshop | 3.2.1 |

6. National Consultants

National consultants will be recruited for specific tasks during Project implementation and will work under the overall direction and supervision of the PTM and the technical support and guidance of the LTO and in close collaboration with the NPCs and the NPOs, and Project site teams and other consultants, as required. The National Project Committees, NPCs and NPOs will assess the need for national consultants but expertise within the following technical fields is expected to be required:

- Legislation and regulations;

- EAF fisheries management (and co-management);

- Processing and marketing (with emphasis on artisanal processing);

- Livelihoods and organisational development.

Specifically, the following consultations are foreseen:

| TASK | OUTPUT |
| --- | --- |
| Support the carrying out of legal and institutional reviews | 1.1.1 & 2.1.2 |
| Carry out awareness raising activities with regard legislation | 1.1.1 |
| Carry out an overall coastal fisheries governance assessment to evaluate whether EAF is effectively applied and to what extent relevant international instruments are reflected and how they contribute to overall development goals | 1.1.3 |
| Support the selection, assessment and implementation of fisheries management plans | 1.2.1 |
| Support mangrove rehabilitation/management activities | 1.2.2 |
| Support the assessment of needs for capacity development and reorganisations within government institutions for EAF management and provide technical support for strengthening government institutions | 1.2.3 |
| Organise and implement workshop and training in accordance with needs assessment on EAF and international instruments | 1.2.3 |
| Provide support for strengthening fishers and fish workers organisations | 1.3.1 |
| Carry out value chain analyses | 2.1.1 |
| Assist in implementing awareness raising and training on value chain dynamics | 2.1.1 |
| Develop PPP arrangements for the management of landing sites and other facilities and services | 2.1.3 |
| Support the development of Project communication strategy and communication products in English and French | 3.1.1 |
| Develop Project M&E system | 3.2.1 |
| Support the development of gender strategy | 3.2.1 |
| Assist in carrying out stakeholder analysis | 3.2.1 |
| Support the organisation of Project inception workshop | 3.2.1 |

APPENDIX 7: CFI  STRATEGIC FRAMEWORK DOCUMENT

(see separate file)

APPENDIX 8: CFI PROGRAM FRAMEWORK DOCUMENT (PFD)

(see separate file)

APPENDIX 9:  RELATION BETWEEN CFI PROGRAMME LEVEL TARGETS AND OUTCOME INDICATOR TARGETS OF THIS PROJECT

| Program Results Framework |  | CFI West Africa |
| --- | --- | --- |
| Components | Targets | Outcomes and targets |
| PROGRAMME COMPONENT 1: Sustainability incentives in the value chain | Outcome 1: a) In XX fisheries in at least XX CFI countries, new or amended management regimes – including co-management and secure tenure and access rights regimes, as appropriate - are implemented successfully. | Outcome 1.2 At least 2 fisheries in the Project countries, representing up to 0.01% of world catches, are under implementation in accordance with agreed management plans and include co-management and secure tenure and access rights regimes, as appropriate. - 700 ha of mangrove are under sustainable management. - 5 communities are involved in co-management supported by national institutions. |
|  | b) Post-harvest losses in at least XX value chains in the CFI geographies have been decreased by XX % and fuel wood consumption reduced in all fish smoking value chains covered by the CFI. | Outcome 2.1 - XX women processor organisations have adopted improved practices and their postharvest losses have been reduced by 20 %. - XX fishers and fish processors state that their working conditions have improved. Outcome 2.2 - Fuel wood consumption has decreased in fish smoking in Project sites by 10 %. |
|  | c.1) PPPs implemented for, for example, improved landing site management, information sharing and market access. c.2) Innovative market incentive systems implemented for improved environmental, economic and social sustainability of coastal fisheries | Outcome 1.3 - At least one successful innovative pilot activity on how a value chain approach has positively influenced fisheries management applying, inter alia, co-management, secure tenure and access rights, PPPs, eco-labeling/certification schemes, or other. Outcome 2.2 - Fishery products from project sites can be found in supermarkets in capital cities of the three countries. - XX women processor organisations have increased their revenues from sales in national and regional markets thanks to better product quality. |
| PROGRAMME COMPONENT 2: Institutional structures and processes | Outcome 2: a.1) Policy, legislation and institutions in at least XX CFI countries amended as required to allow for implementation of revised fisheries management approaches, including co-management and revised tenure and access rights regimes as appropriate | Outcome 1.1 - EAF is referred to as the approach for fisheries management and development in relevant policy and strategy documents and implementation plans follow EAF principles. - Information on how coastal fisheries contribute to overall national development goals exists and is shared among national and local institutions and development partners. - Fisheries policies and strategies are more coherent and new projects and programmes refer to common priorities |
|  | a.2) The SSF Guidelines are reflected in national policy in at least XX CFI countries. | Outcome 1.1 - The intention to implement relevant international instruments, including the SSF Guidelines, is explicitly mentioned in policy statements. |
|  | b) At least XX MPAs in the CFI geographies have functioning multiple use legally recognised co-management plans (including protection of vulnerable habitats and marine ecosystems) and are integrated into broader fisheries management/EAF (M) frameworks. |  |
|  | d) The capacity of XX fishers, fish workers and local and national government staff (XX men and XX women) strengthened through training (formal and on-the-job) on key topics related to, among other things, EAF(M) and co-management (identified through needs assessments) in XX CFI countries. | Outcome 1.3 - XX fishers and fish workers (men/women) benefit from improved natural resources management through improved incomes and/or other perceived livelihood improvements. - XX fishers and fish workers (men/women) actively participate in decision-making processes related to coastal fisheries management and development. |
| PROGRAMME COMPONENT 3: Best practices, collaboration and performance assessment | Outcome 3: a.1) Best practices are shared through IW: LEARN activities and other learning mechanisms. | Outcome 3.1 - Consolidated lessons learnt on key subject matters (as identified and agreed by the CFI Program partners) have been communicated within the CFI programme |
|  | a.2) At least XX new national and/or regional project/programme proposals by GEF Agencies, other partners and governments are based on CFI best practices and include strong collaboration between different GEF Agencies and other partners. | Outcome 3.1 - Key messages based on project experiences are taken up by relevant regional organisations and are reflected in their policy statements. |
|  | b.1) All fisheries/value chains supported through CFI are assessed by agreed performance evaluation system and information is available on key environmental, economic and social aspects. |  |
|  | b.2) CFI best practices reflected in relevant fisheries polices and strategies in at least XX CFI countries. |  |
|  |  | Outcome 3.2 - The project is successfully implemented and receive good ratings by evaluators. |

APPENDIX 10: CFI PROGRAM KNOWLEDGE SHARING

APPENDIX 11: CFI THEORY OF CHANGE

(see separate file)

APPENDIX 12: SYNERGIES CFI, WARFP, CCLME and GCLME

| Overall focus of projects: |  |  |  |
| --- | --- | --- | --- |
| CFI | WARFP | CCLME | GCLME |
| Cabo Verde, Cote d’Ivoire, Senegal: national level support and five local sites: Cabo Verde: Maio and S. Vincente / S. Luzia; Cote d’Ivoire: Abidjan (Locodjro) and Cassandra; Senegal: Iles du Salaam. - Coastal fisheries (EEZs); only capture fisheries. - Local (selected project sites) and national level focus. - Value chain approach and explicit focus on women postharvest organisations. - Legal and regulatory framework , also in postharvest sector. - Empowerment and participation of fishers and fish workers. | 9 countries, including Cabo Verde and Senegal, and Cote d’Ivoire (new) - Both coastal and deep sea fisheries. - Also covers aquaculture. - Regional coordination through SFRC. - Reduce IUU fishing and improvement of fisheries surveillance. - TURFs - Increasing contribution from fish resources to the local economy. - Support to postharvest sector and value addition. | 7 countries (from Morocco to Guinea) - LME approach, i.e. fisheries, habitats and water quality. - Regional collaboration and transboundary resources. - Data collection and fisheries science. - Promoting EAF. - Combatting IUU fishing. - Limited inclusion of activities in postharvest and trade. | 6 countries in Gulf of Guines, including Cote d’Ivoire. - LME approach, i.e. fisheries, habitats and water quality. - Regional collaboration and transboundary resources. - Strengthening the policy and governance framework for EAF management. - Establishment of monitoring and inspection for combatting IUU fishing. - Monitoring and assessment of the LME for the status of productivity, fish stocks, pollution, ecosystem health, and social and economic conditions. - Improved resiliance for fisheries. |
| OUTCOMES/OUTPUTS CFI | Synergies with: WARFP | CCLME (from SAP) | GCLME (first draft PIF) |
| Component 1: Improving fisheries governance and management |  |  |  |
| Output 1.1.1 The national legal and institutional frameworks are reviewed and amended / complemented so that EAF principles are integrated and relevant international instruments can be operationalized (including co-management). | WARFP phase 1 has supported revision and adoption of new legal frameworks in Cabo Verde and Senegal but further reviews are required to ensure consideration of EAF and international instruments (e.g., SSF Guidelines). There is also a need to support implementation of the new legislation. Experiences from WARFP TURFs will inform potential institutional and legislative needs with regard to co-management. | CCLME has supported the establishment of inter-ministerial committees in Cabo Verde and Senegal but these are not functional. |  |

| Output 1.1.2 Information and capacity building programs are implemented to raise awareness and encourage government policy makers at all levels (MPs, directors, etc.) and relevant institutions to apply EAF and implement international instruments in coastal fisheries and integrate these in relevant policies and strategies |  | The CCLME will support harmonization of methodologies and protocols for data collection and analysis in support of fisheries management (including socio-economic data) as well as strengthening scientific capacity in fish stock assessment and monitoring of resources. | The GCLME will support the development and adoption of methodologies for fishery related biological social, economic and governance assessments. |
| --- | --- | --- | --- |
| Output 1.1.3 Evaluation mechanisms are established for assessing governance effectiveness and the coherence of fisheries related policies, strategies and legal frameworks with sustainability and development objectives (poverty reduction, food security, employment, national economic growth). | The WARFP will carry out analysis of fisheries contribution to national economies. | CFI evaluation mechanisms will take into account all relevant activities and outcomes. The EAF Nansen (also collaborating closely with the CCLME) has an EAF tracking tool and is in the process of developing EAF indicators, and this could be used as one input into this broader governance assessment mechanism. |  |
| Output 1.1.4 Government coordination mechanisms, including consultative frameworks, are put in place and promote coherence and synergies among existing development projects and initiatives in coastal fisheries and related sectors. | These coordination mechanisms will supplement the closer coordination and dialogue between the CFI and the WARFP, the CCLME and GCLME to also involve all other relevant actors and initiatives (the WARFP, CCLME and GCLME are invited to be part of the CFI PSC). CCLME and GCLME have some inventories of projects and initiatives in the region that will be used as a starting point. The GCLME will support coordination between and sstrengthen partnerships with the BCC, sister LMEs, GGC, Regional fisheries bodies, basin organization and Abidjan Convention. |  |  |
| Output 1.2.1 Coastal fisheries management plans are improved in line with EAF and relevant international instruments and implemented. | The WARFP has developed and implemented fisheries management plans for TURFs in Senegal and co-management and TURFs in Cabo Verde. In Senegal, the CFI will review experiences from these initiatives (and others, as appropriate) and assess how lessons learnt can inform national policy and be replicated in CFI project sites, if appropriate. CFI and WARFP project sites are not the same. In Cabo Verde, WARFP experiences from the Sal will be assessed and will inform CFI activities in Maio and S. Vicente/S.Luzia. (which are different from WARFP sites). | Several management plans exist, developed by different projects, and during CFI inception, it will be decided which ones to be reviewed and implemented. For example, the CCLME has developed a draft framework for management of shared small-pelagic resources in relevant CCLME countries. LME projects will focus on management of transboundary resources. The GCLME will also assist countries to implement EAF/EAA management and capacity of national fisheries authorities on EAF/EAA increased including through the development and implementation of fisheries management plans that address fisheries sustainability and biodiversity concerns. |  |

| Output 1.2.2 Mangrove management and rehabilitation programs are carried out and linked to fisheries management objectives. | N/A | The CCLME Demonstration Project No. 5, Developing a mangrove conservation plan with several pilot activities for mangrove restoration, conducted training, conservation planning and restoration of mangroves, revised assessment methodologies and services provided by mangrove ecosystems, and contributed to the ratification of the charter on mangroves, the establishment of guidelines, standards and best practices for ecosystem monitoring. Pilot projects have been carried out to conserve and restore mangroves, disseminate good practices and develop income-generating activities. More than 35 hectares of mangroves were planted in Gambia and Guinea-Bissau as part of a restoration process. In the 2nd phase, further work on mangroves is anticipated but with focus on regional level and in sites/countries not covered by the CFI. |  |
| --- | --- | --- | --- |
| Output 1.2.3 Support has been provided to national institutional structures responsible for fisheries management for them to have appropriate capacities and mandates to apply EAF, relevant international instruments and co-management. | The WARFP experiences of fisheries management, including TURFs and co-management, in Cabo Verde and Senegal experiences and lessons learnt will be considered. | The CCLME will strengthen the capacity of fisheries institutions in the following areas: - EAF for the development, implementation and monitoring of fisheries management plans - Designation, development and management of MPAs - Governance and management of transboundary fisheries plans. These activities will be coordinated with the CFI. | The GCLME will assess the respective roles of the GCC, regional fisheries bodies and regional economic communities clarified and agreed, and related legal issues addressed. |
| Output 1.3.1 Coastal fishers and fish workers organisations are formalised and/or strengthened. | The WARFP also foresee strengthening of fisher and fish worker organisations but the project sites are different. A preliminary list of organisations to be included in the CFI is given in the section on “Participants and other stakeholders”. |  |  |

| Output 1.3.2 The capacity of coastal fishers and fish workers to participate in fisheries management and development processes is enhanced | The WARFP intends to focus on technical capacities and with respect to combatting IUU fishing, including piloting participatory MCS with small-scale fishers, whereas the CFI will provide more general empowerment support for participation in fisheries management and also in accordance with needs assessments. See also above. | The CCLME will support the development of the capacity of fishermen and members of fishing communities to address: - Co-management and participatory data collection - Gear selectivity and use of environmentally friendly catching techniques - Sanitary standards, post-harvest processing and adding value to products - Alternative income generating activities e.g. ecotourism These activities will be coordinated with the CFI. |  |
| --- | --- | --- | --- |
| Component 2: Strengthening the seafood value chain |  |  |  |
| Output 2.1.1 The understanding of the links between consumption and production in the value chain is improved and value chain actors are sensitised on incentives for good practices. |  | The CCLME plans to conduct and/or update regional studies on fisheries socio-economics: - Value of ecosystem goods and services - Market and seafood trade - Stakeholder and their roles in the different fisheries - Cost/benefits analysis of management options |  |
| Output 2.1.2 The regulatory and normative frameworks for control of fishery products (quality/sanitary standards) and for decent working conditions are improved. | The enabling environment created by the CFI will support WARFP activities |  |  |
| Output 2.1.3 Participatory arrangements are in place to support improvement and control of fishery product quality and working conditions. | The WARFP will support improvements of land site infrastructures and also PPPs but in different sites from the CFI. |  |  |

| Output 2.2.1 Good practices and innovations are developed to increase incomes and create livelihood benefits while contributing to sustainable fisheries. | The WARFP intends to develop sustainable small-scale fisheries investments in pilot co-management sites to reduce overfishing and create new economic activities. Some similar activities between the WARFP and CFI but in different sites. |  | The GCLME will support the development of approaches for improving the livelihoods of the households of artisanal fishing communities. |
| --- | --- | --- | --- |
| Output 2.2.2 Appropriate equipment and material, with an emphasis on ‘passive innovations’ (not leading to increased fishing pressure) are available to value chain actors for increasing income and creating other livelihood benefits, including improved working conditions. | Some similar activities between the WARFP and CFI but in different sites. |  | The GCLME will facilitate applications for development bank loans to improve fisheries management and utilisation of fishery resources. |
| Output 2.2.3 Access to national and regional markets by small-scale fishers and fish workers, especially women, is facilitated and improved. |  |  |  |
| Component 3: Strategic communication, monitoring and evaluation, and up-scaling of good practises | The WARFP will sharing of experiences among its 9 countries and links can be made with CFI communication and experience sharing. | The CCLME will support the organization of regional scientific working groups for the analysis of data |  |

Three regional consultative meetings were held (in Dakar, Senegal, February 2015: Abidjan, Cote d’Ivoire, December 2015; and Dakar, Senegal, February 2016) as well as national meetings in each country (during 2015).

See http://www.fao.org/fishery/ssf/guidelines/en.

New Partnership for Africa’s Development.

Convention for the Co-operation in the Protection and Development of the Marine and Coastal Environment of the West and Central African Region (Abidjan Convention).

The CECAF Report of the seventh session of the Scientific Sub-Committee, Tenerife, Spain, 14–16 October 2015 is available at www.fao.org/3/a-i5301b.pdf.

There are no mangroves in Cabo Verde.

Assistance technique sur les normes SPS et la chaine de valeur pour faciliter l’accès aux marchés internationaux aux pêcheurs artisans de l’Afrique de l’Ouest. The project also coves Guinea and Mauritania.

FAO. 2014. Report of the FAO/NEPAD Workshop on Climate Change, Disasters and Crises in the Fisheries and Aquaculture Sector in West and Central Africa, Accra, Ghana, 1–2 November 2012.

FAO. 2014. Gap analysis of national and regional fisheries and aquaculture priorities and initiatives in Western and Central Africa in respect to climate change and disasters. FAO Fisheries and Aquaculture Circular No. 1094. Rome, FAO.

See http://www.fao.org/fishery/ssf/guidelines/en.

Text on each country from www.cbd.int/nbsap/.

The available CPF for Cote d’Ivoire is for the period 2012-2015.

There are no mangroves in Cabo Verde.

See baseline information on existing management plans in output 1.2.1 the Results Matrix in APPENDIX 1; The management plans to be reviewed and implemented will be selected during the Project inception phase.

These indicators are relevant for the GEF CFI Program’s Target Contributions to Global Environmental Benefits No 1: At least 3 million hectares of coastal marine areas with EEZs under sustainable fisheries management regimes;  and 3: At least 8 percent of fisheries as per the GEF corporate target of 20%, by volume or 410,000 tonnes (FAO 2016)  of overexploited fisheries, moved to more sustainable levels.

Annex 12 list the main projects and initiatives for coordination and collaboration that existed when the present project was prepared. Other projects and initiatives might develop during project execution.

Governments of CPV (Ministère de l’économie et de l’emploi & Ministère de l’agriculture et de l’environnement), CIV (Ministère des ressources animales et halieutiques & Ministère de l'environnement et du développement durable) and SEN (Ministère de la pêche et de l’économie maritime & & Ministère de l'environnement et du développement durable).

USD 302 752 from Cote d’Ivoire’s BD STAR allocation will only be used in Cote d’Ivoire.

Risk categories defined in the FAO ERM Strategy: CLEAR INTENDED PURPOSE (IMPACT &OUTCOME); EFFECTIVE DELIVERY STRATEGY; EXTERNAL STAKEHOLDER SUPPORT; INTERNAL STAKEHOLDER SUPPORT; RIGHT RESOURCES; VIABLE DELIVERY STRUCTURES; STRONG DELIVERY MANAGEMENT.

H: High, M: Medium, L: Low

H: High, M: Medium, L: Low

To be updated during implementation and monitoring phase (no change, reduced, increased).

To be completed during project cycle implementation and monitoring phase.

RFP: Request for Proposal; RFQ: Request for Quotation; ITB: Invitation to Bid.

Direct Procurement, re-use of tender results, UN, Framework, etc.

CSAP, Non-HQ Location, Procurement Mission.

Planned, Requested, Tendered, Order Placed, Delivered, Completed.