Project Identification Form (PIF)

Project Type:

Type of Trust Fund:

PART I: Project Identification

| Project Title: | Strengthening decentralized management of the environment to meet Rio Convention objectives |  |  |
| --- | --- | --- | --- |
| Country(ies): | Guinea | GEF Project ID: | 5041 |
| GEF Agency(ies): |  | GEF Agency Project ID: | 4963 |
| Other Executing Partner(s): | Ministry in charge of the Environment, Forests and Water - MEEF | Submission Date: | 10 April 2013 |
| GEF Focal Area (s): |  | Project Duration (Months) | 36 |
| Name of parent program (if applicable): - For SFM/REDD+ |  | Agency Fee ($): | 49,875 |

A.  Focal AREA STRATEGY Framework:

| ### Focal Area Objectives | ### Expected FA Outcomes | ### Expected FA Outputs | ### Trust Fund | ### Indicative ### Grant Amount ### ($) | ### Indicative Co-financing ### ($) |
| --- | --- | --- | --- | --- | --- |
|  | Strengthened capacities for management and implementation on convention guidelines | - Enhanced institutional capacities to manage environmental issues and implement global conventions - Good environment management standards defined and adopted - Sustainable financing mechanisms in place at national level |  | 500,000 | 550,000 |
|  | Others |  |  |  |  |
| Sub-Total |  |  |  | 500,000 | 550,000 |
| Project Management Cost |  |  |  | 25,000 | 75,000 |
| Total Project Cost |  |  |  | 525,000 | 625,000 |

- Project Framework

| ### Project Objective: to strengthen institutional capacity in Guinea to mainstream MEA and LCERD into decentralized environmental management activities. |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| ### Project Component | ### Grant Type | ### Expected Outcomes | ### Expected Outputs | ### Trust Fund |  | ### Indicative ### Grant Amount ($) | ### Indicative Cofinancing ### ($) |
| Component I: To create and operationalise a mechanism for integration of the MEA into the process of decentralization |  | The decentralisation process and its governance structures are modified to integrate the obligations under the MEA and so facilitate MEA implementation at the local level. | 1) MEA integrated into the national decentralization strategy, in order to ensure top-down and bottom-up compliance with MEA obligations and across-levels reporting to the conventions. 2) Strengthen the Environmental Management Information System as a Clearing House Mechanism for decision making on environmental issues and MEA implementation and LCERD at the decentralized level. 3) Strengthen the PACV as a facility for ongoing dialogue and coordination within the decentralised governmental environmental management support network. |  |  | 250,000 | 275,000 |
| Component II: To strengthen the capacity of key government organisations to integrate the MEA into the planning processes at the national, prefectoral and local level. |  | Strengthened technical and managerial capacities in the structure supporting the integratation of MEA into local development planning Strengthened capacity of lead agencies to disseminate and replicate best practices in decentralized environmental management across the country | 1) The existing network of capacity development institutes is strengthened to support the efforts to integrate the MEA and LCERD into the national, prefectoral and commune planning and reporting processes. 2) Capacity building programme developed and tested for the key management staff of the central and decentralized network of public administration field agencies. These agencies support the decentralisation process to ensure integrated natural resources management approaches and standards of good environmental management are central to the decentralization process. 3) Capacity in key national institutions (CNDD, FSE and MEEF) to replicate the successes across Guinea. This includes accessing FSE funds in order to support activities that (i) adapt to climate change (ii) conserve biodiversity. |  |  | 250,000 | 275,000 |
| Sub-Total |  |  |  |  |  | 500,000 | 550,000 |
| Project Management Cost |  |  |  |  |  | 25,000 | 75,000 |
| Total Project Costs |  |  |  |  |  | 525,000 | 625,000 |

- Indicative Co-financing for the project by source and by name if available, ($)

| Sources of Cofinancing | Name of Cofinancier | Type of Cofinancing | Amount ($) |
| --- | --- | --- | --- |
|  | MEEF |  | 150,000 |
|  | MEEF |  | 100,000 |
|  | UNDP |  | 150,000 |
|  | PACV |  | 225,000 |
| Total Cofinancing |  |  | 625,000 |

- GEF/LDCF/SCCF/NPIF  Resources Requested by Agency, Focal Area and Country1

| GEF Agency | Type of Trust Fund | Focal Area | Country Name/Global | Grant Amount (a) | Agency Fee (b)2 | Total c=a+b |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Guinea | 525,000 | 49,875 | 574,875 |
|  |  |  |  |  |  | 0 |
|  |  |  |  |  |  | 0 |
|  |  |  |  |  |  | 0 |
|  |  |  |  |  |  | 0 |
|  |  |  |  |  |  | 0 |
|  |  |  |  |  |  | 0 |
|  |  |  |  |  |  | 0 |
|  |  |  |  |  |  | 0 |
|  |  |  |  |  |  | 0 |
| Total Grant Resources |  |  |  | 525,000 | 49,875 | 574,875 |

1  In case of a single focal area, single country, single GEF Agency project, and single trust fund project, no need to provide 
    information for this table

2   Please indicate fees related to this project.

part ii:  project JustiFication

- Description of the consistency of the project with:

A.1.1   the GEF focal area/LDCF/SCCF strategies /NPIF Initiative:

Of the five objectives under the GEF-5 Capacity Development Results Framework (GEF/C.37/3), this project sets out to meet Capacity Development Objective 4. Under that Objective, the expected Outcomes to which the project will contribute are enhanced institutional capacities to manage environmental issues and implement global conventions. It will contribute to the following strategy outputs: Institutional capacities for management of environment strengthened and Management capacities for implementation of convention guidelines and Reporting enhanced countries. As has been noted in the various Enabling Environment Reports, the country of Guinée suffers from the absence of a clear vision on how to integrate the MEA into its decentralized development planning processes. The structure governing this decentralized process (the decentralized public administration agencies working towards assisting communities to better manage their surrounding environment and the education institutes working with these agencies, providing staff and training to this governing structure) lack capacity to transfer the complexity of the MEA guidelines to the field agencies. The current project will change this situation by: (a) creating an enabling environment for decentralised MEA implementation (i.e. integration of MEA into decentralisation strategy and support structure; an information database for decentralized decision making; the Village Communities Support Program (PACV) is established as a pivotal coordination unit); (b) a strengthened institutional environment for implementation of the strategy (i.e. network of capacity building institutions, a capacity building programme for the support structure); and (c) a way to disseminate best practices via the key national agencies (including the Environmental Protection Fund, FSE). An institutional capacity building programme will be introduced through which the staff of educational institutions will provide focused capacity building to decentralized government staff on Convention implementation and the mainstreaming of Conventions into agency policies, laws and regulations, incentive structures and awareness raising. Under the coordination of the 4 lead Institutions (Ministry in charge of the Environment, Forests and Water - MEEF, National Council for Sustainable Development - CNDD, FSE and PACV), this ‘NGEM Academy’ will ensure that during the implementation of this project, the capacity of over an estimated 150 key management staff members of various public administration agencies will be directly enhanced. For example, their capacity to push through organizational changes, their capacity to develop and use EMIS for decision making, and their ability to inform and train grassroots’ communities on best practices for Integrated Water Resources Management and environmental protection. The staff to be trained will be selected from the technical sections of several ministries (Ministry in charge of the Environment, Forests and Water, Agriculture, Territorial Administration and Decentralization, etc.) and their decentralized affiliates in the 33 prefectures and 303 sub-prefectures in the country. These strengthened personnel will be encouraged to remain at their respective stations and will continue to take an active part in the implementation of the Multilateral Environmental Agreements (MEA) in their respective fields. The Government will make managers and high-level officers of both Central and decentralised services available to support implementation of the project. This should ensure the sustainability of the project achievements. This project is in support of the three Rio Conventions, in particular: Article 18, subparagraph 2 of the CBD; Article 4, subparagraph 5 of the UNFCCC; and Article 19, subparagraphs of the UNCCD. This project is also fully in line with the commitments made by the GEF for the United Nations Conference on Sustainable Development (Rio+20), particularly: 2. Seek to expand opportunities for joint implementation of the Rio Conventions through GEF-funded projects and programs by promoting synergies in the generation of global environmental benefits; 3. Commit to promptly act on guidance from the conferences of the parties of the Rio Conventions to promote joint reporting, particularly of Small Island Developing States and Least Developed Countries; and 5. Continue to support capacity development in recipient countries as well as addressing their needs through funding of enabling activities and the GEF Country Support Program, together with other national and regional consultation processes.

A.1.2.   For projects funded from LDCF/SCCF:  the LDCF/SCCF eligibility criteria and               priorities:

Not Applicable A.1.3 For projects funded from NPIF, relevant eligibility criteria and priorities of the Fund: Not Applicable

A.2.   national strategies and plans or reports and assessments under relevant conventions, if  applicable, i.e. NAPAS, NAPs, NBSAPs, national communications,  TNAs, NIPs, PRSPs, NPFE, etc.:

The Guinean Strategy and Action Plan for Capacity Development 2009-2015 (ANCR, 2008) aims to develop, consolidate, and improve the capacities of the public and private national institutions to implement the respective obligations of the Multilateral Environmental Agreements. The ANCR identified the following major constraints as obstacles to the development of capacities in Guinea: a) Segregation and the lack of information on the programs; b) The difficulties of coordination and lack of replicability of programmes; and c) The reduced dimension of capacity building programs, limited to improving individual capabilities (information, awareness and training) and institutional support. The ANCR identified the following cross-cutting capacity development objective as a priority for a follow-up standalone project: “To ensure the coordination and dialogue between the various institutions concerned with promoting synergy, programmatic integration and the harmonization of policies and legal and regulatory frameworks with an aim of avoiding duplications and of saving resources by sharing technical resources, data, approaches, models and toolkits for more effectiveness in the implementation of planned actions. For this purpose, to set up a facility of coordination of conventions equipped with the necessary resources to ensure a continuous follow-up of the implementation of the various MEA”. This Project addresses this need. The Project also aligns well with several other priorities from the ANCR: Priority 8 - ensuring an effective participation of the local communities in the implementation of the MEA to achieve their sustainable anchorage and ongoing execution at the local level; Priority 9 - promotion of the Ecosystems Approach and Integrated Water Resources Management in development projects to favour a greater partnership in the implementation of the MEA, and; Priority 10 - to conceive and adopt a mechanism for efficient mobilization and transparent management of financial resources necessary for the achievement of capacity building activities. The Project is in conformity with the objectives and priorities of the Guinean Government in its fight against poverty and the promotion of the socio-economic development through the sustainable use of the abundant natural resources of the country. These have been noted in their Poverty Reduction Strategy Documents (DSRP1, 2 and 3). This Project will also take into account findings from the Enabling Activities under the Conventions, such as the National Strategy and Action plan for Biodiversity (NBSAP); the National Communications for the UNFCCC and the NAPA; the National Action Plan against desertification (SAP-CCD); the National Environmental Action Plan (PNAE) and other plans and programmes including for the water sector. When it comes to promoting Low Carbon Emission and Resilient Development (LCERD), Guinea is involved in various plans and programmes to promote both mitigation and adaptation to climate change, for which the NAPA will be the coordinating framework.

- Project Overview:
B.1. Describe the baseline project and the problem that it seeks to  address:

The baseline of this project consists of various capacity-building activities and institutional support to various current or planned environment management projects and programs, of enabling activities for major conventions, and of the regulatory country corpus in environmental management and other related areas. Such a mono-sectorial and dispersed approach to capacity building has as yet not solved the deficit capacity in environmental management. The situation is even more serious at the local level, where governing institutions lack coordination capacity, and although projects and sectorial agencies work alongside each other they do not collaborate. In the baseline, decentralization is an important vehicle for sound environmental management at the local and national level. Decentralization consists above all of a transfer of competences, responsibility and resources from the centre towards the periphery. Within the framework of the operationalization of an important visionary document, the `'Guinea, vision 2010 '', many development programs were enacted, of which the majority are support programs at the local communities level. For example, the Decentralization Sector and the Land Administration received support from the Village Communities Support Program (PACV), which has contributed to the improvement of the capacity of farmers in participatory diagnosis and the development of community development plans. Likewise, the Institutional Capacity Building Programme (PRCI) intervened to provide training and logistical support to the decentralized technical support services. The PACV is extending its approach during the second phase (2008 – 2014) to all 304 rural communes (CRD) in Guinea, privileging their participation in the development of plans, decentralized financing, contractualization and reinforcing their capacities in priority sectors. PACV financing will rise to more than 30 Million dollars distributed as follows: World Bank, 17 million USD; IFAD, 10 USD million; and mining Companies, 2 USD Million. Funds are also being mobilised from the French government (AFD). Of the 304 targeted CRD’s, 37 already enjoy GEF support, amounting to 10 Million USD. As yet, the PACV does not provide training centres. The programme coordination has indicated that it is very open to establishing such centres in certain key CRDs. The PACV Coordination Unit has indicated that it is keen to establish linkages with the current proposed GEF Project. One of the PACV programme components is also looking to establish and operationalize Local Investment Funds, this is also a potential partner of the current proposed GEF Project. In spite of the marked political good-will and the establishment of important legislative and regulatory devices, the implementation of decentralization on the ground encounters constraints and challenges. For example, each actor seems to act according to its own interests - often without taking into account the tools developed by the Ministry in charge of Decentralization and the training already carried out by others. Also, there is a noted weak dialogue and coordination between the various actors. The need for individual, institutional and systemic capacity building to empower local communities and their governing structures to take part in environmental management and protection is strong. For decentralization to work, fiscal, administrative and political aspects of decentralization must be aligned to ensure subsidiarity, capacity, and accountability. As a first step, roles and responsibilities need to be clearly defined. This has been accomplished in general by the Decentralization Code (2006) but needs to be detailed out for each sector. As a second step, capacities will have to be aligned with functions to ensure that local governments have the financial and human resources necessary to fulfil their new responsibilities. Having clarity on responsibilities, autonomy in decision making without unnecessary interference also contributes to local government capacity. Third, local governments (and service providers) need to be held accountable by their citizens to provide an incentive for performance. Coordination also seems to be weak within the national environmental management mechanism. Diagnoses made during previous studies (i.e. the Enabling Activities under the conventions) on the state of capacity-building interventions for the development sectors show that most actions are sectorial and non-collaborative. In the field of training and research, noteworthy is the opening of specialized training branches for environmental sciences at the University of Conakry (CERE, Faculty of science), which contributes to improved national expertise in environmental studies. In certain sectors, such as animal husbandry, institutional reforms following the establishment of a training program helped to strengthen the intervention capabilities of field agents and the force of veterinary officers and to improve the management of pastures by agriculturalists, especially youths. The National Department of Agriculture, which has training and learning centres in the interior of the country, is faced with difficulties in implementing its programme of training of staff, technicians and farmers. Nevertheless, there is no coordinated programme taking into account the cross-sectoral aspects, and no related clear priority to capacity-building. Additionally, the non-explicit character of the sectoral capacity-building programmes with regards to the mainstreaming of environmental considerations in sectoral initiatives should be noted. Guinea needs a greater capacity for study, analysis, research and environmental management to reverse the increasing magnitude of environmental degradation on both the national and the local level. As a follow up to the ANCR, the National Capacity Building Programme (NCBP) for National and Global Environmental Management 2009-2015 was developed. The NCBP is intended to develop, strengthen and improve the capacities of public and private national institutions, NGOs and local communities in the implementation of the respective obligations under MEAs. The NCBP proposes to use known and proven integrated approaches, such as the Ecosystems Approach and the internationally accepted concept of Integrated Water Resources Management (IWRM) as an opportunity to create a common language in development work. The issues to which the project must find solutions for a better management of natural resources and poverty reduction are: Problem I: the MEA information fails to reach key players. Indeed, many structures and individuals do not know the Conventions, or the Conferences of Parties (COP), and they know even less about the directives of the COPs. Many do not even know the concerned national strategies and action plans. This weakness of access to information by the main actors and the public is considered to be one of the main causes of the faltering implementation of the MEAs. Integrated land management approaches such as the Ecosystems approach and IWRM are also poorly known to development actors. Problem II: Local communities are not familiar with conventions and other multilateral environmental agreements. While they are considered to be major environmental management actors, they remain loosely involved in the implementation of the MEAs. Problem III: The various national structures responsible for the implementation of the MEAs do not sufficiently coordinate their efforts in pursuit of their respective activities. They do not co-operate enough during the implementation of national plans. This results in a lack of synergy, and the weak integration and harmonization of policies and legal frameworks. The idea for this Cross-Cutting Capacity Development project, is to start tackling these problems from the grassroots level up: i.e. working with the Rural Development Committees (CRD) and their Local Development Plans (LDP). The aim is to develop a mechanism for the central and decentralized government agencies to support, and train CRDs, and to revamp the LDPs for better incorporation of the MEA and coordination of the outcomes on a national level. This will build on the experiences and mechanisms of the PACV and the PRCI- both of these have worked with local communities on strengthening their capacities for local level planning. The project will ensure that Global Environmental Management and implementation of the MEA can be mainstreamed into their planning processes, and ensure a special focus on Low Carbon Emission and Resilient Development. As local agents, the decentralized training institutes such as training centers of the National Department of Agriculture can be employed. Once the mechanisms have been developed and tested, best practices for mainstreaming of MEAs into local development plans will be up-scaled and replicated by the key national institutions such as FSE, MEEF and CNDD.

B. 2. Incremental /Additional cost reasoning:  describe the incremental (GEF Trust Fund/NPIF) or additional (LDCF/SCCF) activities  requested for GEF/LDCF/SCCF/NPIF  financing and the associated global environmental benefits  (GEF Trust Fund/NPIF) or associated adaptation benefits (LDCF/SCCF) to be delivered by the project:

Guinea is adopting the decentralized approach to national development. The baseline consists mainly of an on-going decentralization process, overseen by a national enabling framework, and supported by a network of local capacity development institutes, with overall support from international community (for example through the PACV). The project will build into this ongoing decentralization process. The increment consists of a series of measures to ensure that MEA concerns are integrated into the on-going decentralization process, thereby yielding global environmental benefits. This project will show how global environmental benefits can be generated by developing capacity to implement the Rio conventions at the local level, and mainstreaming implementation of the conventions into the local development process. The Project will test this at a small number of representative sites. Then, it will develop the capacity to replicate/disseminate this successful approach across the country. Through this, the project’s impacts will be achieved at the local level through local capacity across the country. Hence, country wide, global environmental benefits will be generated. An institutional capacity building programme will be introduced through which the staff of educational institutions will provide focused capacity building to decentralized government staff on Convention implementation and the mainstreaming of Conventions into agency policies, laws and regulations, incentive structures and awareness raising. Under the coordination of the 4 lead Institutions (Ministry in charge of the Environment, Forests and Water - MEEF, National Council for Sustainable Development - CNDD, FSE and PACV), the ‘NGEM Academy’ will ensure that during the implementation of this project, the capacity of over an estimated 150 key management staff members of various public administration agencies will be directly enhanced. For example, their capacity to push through organizational changes, their capacity to develop and use EMIS for decision making, and their ability to inform and train grassroots’ communities on best practices for Integrated Water Resources Management and environmental protection. The staff to be trained will be selected from the technical sections of several ministries (Ministry in charge of the Environment, Forests and Water, Agriculture, Territorial Administration and Decentralization, etc.) and their decentralized affiliates in the 33 prefectures and 303 sub-prefectures in the country. These strengthened personnel will be encouraged to remain at their respective stations and will continue to take an active part in the implementation of the Multilateral Environmental Agreements (MEA) in their respective fields. The Government will make managers and high-level officers of both Central and decentralised services available to support implementation of the project. This should ensure the sustainability of the project achievements. During the implementation of this project, the capacity of over an estimated 150 staff members of various public administration agencies and ONG will be directly enhanced by the activities of the aforesaid project. These staff will come from the technical directions several ministries: Ministry in charge of the Environment, Agriculture, the Administration and Decentralization, etc. The trained personnel will be encourage to remain at their respective stations and will continue to take an active part in the implementation of the Multilateral Environmental Agreements (MEA) in their respective fields. In addition to developing individual capacity of at least 150 key government staff, the project will provide organizational strengthening and systemic support: the project will train government employees, but also to coordinate the education institutions to provide a type of NGEM academy where government employees can be strengthened in their capacity to mainstream the conventions into policy, laws and regulations, etc. But also a selection process for targeting ‘high potentials’ among agency staff at the various levels to be trained (150 as a first trial batch), who will be the change agents within their specific agencies. And, the 4 lead agencies will be supported in becoming the driving force behind the changes, with FSE being the financing entity In the first component, GEF funds will ensure the enabling environment for decentralization is strengthened to account for global environmental benefits. This entails the following Outputs and activities: Activity 1: MEA integrated into the national decentralization strategy, in order to ensure top-down and bottom-up compliance with MEA obligations and across-levels reporting to the conventions. 1.1. Establish and operationalize a coordination facility for decentralized MEA implementation and across-levels reporting to the conventions. 1.2. Decentralisation policy and programme adapted to incorporate MEA implementation and Low Carbon Emission and Resilient Development (LCERD). Activity 2: Strengthen the Environmental Management Information System as a Clearing House Mechanism for decision making on environmental issues and MEA implementation and LCERD at the decentralized level 2.1. Create and render consultable a central digital library (CDL) consisting of electronic versions of the convention texts and COP directives, national strategy and action plans, national communications, guidelines and tools on MEA implementation and LCERD. 2.2. Create a national distribution network for distribution of library material and Convention information. Activity 3: Strengthen the PACV as a facility for ongoing dialogue and coordination within the decentralised governmental environmental management support network. 3.1. Analysis of the PACV coordination structure on key entry points for promotion of environmental management; 3.2. Strengthen PACV dialogue mechanism via key entry points. 3.2. Special MEA/LCERD units within PACV set up to coordinate and maintain dialogue with capacity development institutes, CBOs, NGOs and field agents of public sector. The second component aims to strengthen the capacity of key organisations to integrate the MEA in the planning processes at the local level. The Outputs and Activities are: Activity 1: The existing network of capacity development institutes is strengthened to support the efforts to integrate the MEA and LCERD into the national, prefectoral and commune planning and reporting processes. 1.1. Inventory of the state of the various decentralized capacity development initiatives concluded or underway in Guinée (PACV, PRCI, centers de formation DNA, CERE, etc.) 1.2. Agreement reached with most relevant institutions to act as MEA and LCERD implementation decision making structures for local communities. Activity 2: Capacity building programme developed and tested for the key management staff of the central and decentralized network of public administration field agencies. These agencies support the decentralisation process to ensure integrated natural resources management approaches and standards of good environmental management are central to the decentralization process. 2.1. Selected body of staff of the decentralized network of capacity development institutes is trained on integrated natural resources management approaches and standards of good environmental management. 2.2. A Training-of-Trainers programme is designed by participants of action 2.1. 2.3. Selection of 4 local communities to test training programme; 2.4. A community of practice is established in which best practices and replication potential of capacity building efforts are shared. Activity 3: Develop capacity in key national institutions (CNDD, FSE and MEEF) to replicate the successes across Guinea. This includes accessing FSE funds in order to support activities that (i) adapt to climate change (ii) conserve biodiversity. - Build capacity of key national institutes to analyze legal and financial mechanisms supporting the decentralization process and evaluate potential for resources mobilization for mainstreaming MEA into decentralized planning procedures; - Establish partnership between the coordination facility (Component I, Output 1.1) and the key national institutions to disseminate information through the EMIS distribution network. The details of this approach, and how to monitor and quantify, will be determined through the PPG.

B.3. 	Describe the socioeconomic benefits to be delivered by the Project at the national and local levels, including consideration of gender dimensions, and how these will support the achievement of global environment benefits (GEF Trust Fund/NPIF) or adaptation benefits (LDCF/SCCF). As a background information, read Mainstreaming Gender at the GEF:

Benefits at the national level will include enhanced technical capacities among key national authorities, as well as stakeholder groups that include decision-makers and technical advisors across sectors. At the national level, the implementation of the project allows for ensuring synergy, coordination and consultation between the different institutions concerned with the implementation of the MEAs with the full participation of stakeholders in the process. Strengthening the overarching organisation in defence of sustainable development (i.e. theCNDD) will ensure that policies and programmes will be reoriented from sectoral and national perspective to included more integral ambitions towards sustainable development and the valuation of Guinea’s natural resources to that end. At the local level, the development in the CRD of pilot projects on biodiversity protection, integrated management of water resources, fight against climate change and land degradation will have a positive impact and sustainable socio-economic benefits for local, national and global environment. The project will develop best environmental management practices, creation of wealth for local communities and good environmental governance. Stakeholders will gain a better appreciation that planning decisions are based on more objective criteria and methodologies that place a greater value of the socio-economic risks associated to global environmental impacts, such as droughts and floods. Strenthening the decentralised planning and financing system (through the LPDs and the Local Investment Funds) for sustaining activity programmes for the main beneficiaries of this project will contribute to the stability of both central and local government structures. Improved tools and methodologies to reflect global environmental values will produce improved decision-making that meets both global environmental commitments as well as national development priorities. The project will focus on income generating activities to improve the socio-economic conditions of populations and thus reduce poverty and promote a rational management of natural resources. In Guinea, the woman is the pillar of the family and the engine of development and has always taken an active part in the development of the country's development. Gender will be a cross-cutting ‘leitmotif’ in the revision and strengthening of key policies and legislative instruments, at the national, sub-regional, and local levels, as numerous negative social outcomes associated with environmental degradation are experienced by women, with many more unaccounted for. The anchoring of the MEAs at the local level will be an opportunity to involve women in the process at the start of activities and have them participate in the implementation of MEAs through pilot projects that will be developed. Bringing the need for sound environmental management down from the national level to the local level via the decentralisation process will ensure that the requirements of the most vulnerable groups in society, such as women, youth groups and the landless can be incorporated in policy making and programme desing from a bottom-up perspective. As part of the project implementation arrangements, directed attention will be paid to ensuring an appropriate gender balance in the training and capacity development activities.

B.4	Indicate risks, including climate change risks that might prevent the project objectives from being achieved, and if possible, propose measures that address these risks to be further developed during the project design:

Risks and their mitigation measures are explained in the following table. Risk; Mitigation measures. 1. Political/societal Barriers a) lack of political will and institutional instability b) timid adherence of key decision-makers and stakeholders of the project strategy; Political commitment secured from the authorities at the highest level by the adoption of the strategy and action plan as one of the priorities of the Government in capacity-building. CNDD acts as Project Steering Committee, consisting of lead ministries and key representatives of NGO and Civil Society Umbrella organisations and Private Sector.. 2. Technical and institutional barriers A) insufficient capacity, due to Institutional deficiencies; b) lack of human resources; c) Absence of adequate scientific research capacity to support all of the objectives of the project d) lengthy time it may take to assign capable people to key positions e) Inadequate synergies and effective partnership at the national and local level among stakeholders; Where possible, the Project will create synergies between the capabilities of the actors of the project via MOUs to make use of each other strengths and properly cooperate in the project implementation. 3. Consequences of climate change are excluded from local planning because of abstractness and priority towards natural resources valuation.; The concept of Low Carbon Emission and Resilient Development will be built into the approach, ensuring that mitigation and adaptation are integral components in the strategies.. 4. Lack of accessible information a. existing scientific and traditional knowledge are not fully exploited. The dissemination of information at the national and local levels is not effective.; Make full use of the preparation studies for the Environmental Management Information System currently being set up by the Ministry and the central and decentralised research facilities mentioned in the project overview.. 5. strong dependence on existing structures a. the decentralization process is strongly dependent on the mechanism already put in place, relying on the local authorities and CRD’s; lack of commitment from these structures will be a deal breaker.; During the preparation phase (PPG) a clear commitment of the decentralized authorities should be sought and formalized via letters of intent.. In line with the Global Environment Facility’s (GEF) Strategic Approach to Enhance Capacity Building (2003) and Results-Based Management (RBM) Framework (2007) and the Monitoring Guidelines of Capacity Development in Global Environment Facility, the Project will propose an approach to monitoring and evaluation in such a way that supports the integration of capacity development into programme and project design and will ensure risk mitigation.

B.5. Identify key stakeholders involved in the project including the private sector, civil society  organizations, local and indigenous communities, and their respective roles, as applicable:

The implementation of this project will pursue the effective participation of the central and decentralized structures involved in the management of natural resources and the protection of the environment. The private sector, civil society, NGOs and local communities will be heavily involved in the implementation of the activities of the pilot projects, which will be identified at the level of the CRD or watersheds. Key stakeholders involved in the project are: - the public sector through the staff of sector ministries and departments, in particular the Ministry in charge of Environment, Water and Forests (MEEF) and the Ministry in charge of Decentralization, the network of decentralized training and research facilities and their mother organizations, such as National Department of Agriculture; - the Environmental Protection Fund (FSE); - National Commission for Sustainable Development (CNDD); - Universities and research centers, such as the University of Conakry and its research centers, etc. - employers’ associations; - NGO and CSO networks, including women’s associations and youth groups; - local communities within the decentralization process, via their CRD; - local authorities in sources pilot areas; The existing network of capacity development institutes, such as the universities and research and training institutes will be involved to develop a ‘NGEM Academy’ for key management staff of central and decentralized public administration agencies. Within this academy, the existing capacity development institutes will enhance their capacity to translate the MEA objectives and obligations to the local context and effectively support NGO’s and CBO’s to contribute to the implementation of the Rio Conventions via local activities. The staff of the decentralized network of public administration field agencies supporting the decentralisation process will be trained on integrated natural resources management approaches and standards of good environmental management. The role of this trained staff will be supporting the CRD’s and their NGO/CBO support structure in elaborating and executing their Local Development Plans. The project will be implemented in line with established Government of Guinea and UNDP procedures in Guinea. The Ministry in charge of Environment (MEEF) will take overall responsibility for implementation of the project, and for the project success. It will establish the necessary planning and management mechanisms to oversee project inputs, activities and outputs. The UNDP CO will support MEEF as requested and as necessary. UNDP Guinea Energy and Environment Team is facilitated by an advisor and a UNV specialist who will work in close cooperation with the project team. The team will be supported by the UNDP Guinea M&E unit which ensures the management of the project in accordance with the rules and procedures of UNDP and GEF. The PPG process will be used to further define management, coordination and consultation mechanisms.

B.6. Outline the coordination with other related initiatives:

The project is focused on the approach of decentralization of responsibilities for sound environmental management by local authorities. However, this must build upon a conducive national environment. Strong linkages will be sought with the national instruments of implementation of the DSRP3, such as the Village Communities Support Program (PACV2&3), the Project for Sustainable Socio-economic Development of Haute and Moyenne Guinea (PDSD - HMG), the Poverty Reduction Strategy Support Project (ASRP) financed by the GIZ, the USAID funded Project Faisons-Ensemble, the Poverty Reduction Assistance Project (Projet Appui à la lutte contre la Pauvreté (ALP/GDO)). The European Union (EU) has launched Rehabilitation and development Program (PRD). In addition, the EU will finance the Support of Project for consolidation of the process of decentralization in Guinea. Another potential partner in the process is PLAN Guinea, who is strongly involved in the decentralization process. Linkages will be established between this project and the other initiatives in progress through the planning of the development specifically at the local level within the framework of the formulation of the local development plans of on the one hand and in the regular communication between the recipients which will be supported by the implementation of the project on the other hand. The exchanges between the various parts as well as the complementarity sought on the level of the various programs/projects will be also an approach of consolidation of the linkages between the interested parts. UNDP, PACV, CNDD and MEEF, through the coordination facility established during the project, will have a pivotal role to play in coordinating and strengthening linkages. As for adaptation and Low Carbon Emission and Resilient Development; linkage will be sought with the baseline of the National Action Plan for Adaptation (NAPA) currently under development, but also with the Project Increasing Resilience and Adaptation to Adverse Impacts of Climate Change in Guinea’s Vulnerable Coastal Zones. Linkages can also be found with the GEF project Adaptation to Climate Change - Responding to Shoreline Change and its human dimensions in West Africa through integrated coastal area management, the African Adaptation Programme and the CC DARE programme. Whenever possible, synergy will be sought with these projects in order to apply lessons learned to make sure that the interventions proposed under the Project will decrease carbon emission and improve climate change resilience. As such, UNDP can coordinate this project with other important UNDP interventions to assist the government to counteract the degradation of the natural resources and to arrive to a better environmental protection, such as the development of the Initial and Second National Communication and the NAPA under the UNFCCC, the Support project for the implementation of the SAP-CCD, the Institutional Capacity Building Programme for the combat of land degradation and deforestation in Guinea, etc. The UNDP-BDP regional office will support the initiative by ensuring a liberal sharing of best practices and information from similar projects in the region. Visibility of GEF financial support will be ensured by using the global GEF branding in all electronic and printed materials. UNDP will also apply the following UNDP-GEF policy: “The GEF logo should appear on all relevant project publications, including amongst others, project hardware and other purchases with GEF funds. Any citation in publications regarding projects funded by GEF should also acknowledge the GEF. Logos of the Implementing Agencies and the Executing Agency will also appear on all publications. Where other agencies and project partners have provided support (through co-financing) their logos may also appear on project publications.” Full compliance will be made with the GEF’s Communication and Visibility Guidelines (“GEF Guidelines”): http://www.thegef.org/gef/sites/thegef.org/files/documents/C.40.08_Branding_the_GEF%20final_0.pdf

C.   describe the GEF agency’s comparative advantage to implement this project:

UNDP, traditional partner of the Government in the areas of environment and poverty reduction will also be a lead partner in the current project. The choice of UNDP as implementing agency is justified for the following reasons: - UNDP is the institution that guided Guinea in the financing of development phase of the NCSA strategy and action plan – hence UNDP Country Office (CO) Guinea is an ideally suited Agency for the co-financing of the current project; - Discussions have already taken place with the UNDP - Guinea country office at the time of the preparation of the final report of the project by an International Consultant, asking the CO to also be the lead development partner for the implementation of the Guinea NCSA strategy and action plan; - As such, UNDP would be well placed to be the leader of the group of development partners involved in the management of the environment in Guinea in a quest towards a common strategy for strengthening the capacities of the national institutions, civil society, local communities and the private sector. The project is also fully compliant with the comparative advantages matrix approved by the GEF Council. Considering that this is a capacity building project for natural resources management and poverty reduction, which fits well with the mandate of UNDP among other development partners, UNDP was selected as the GEF Implementing Agency for this project. This is also based on their experience and expertise in supporting capacity development efforts in Guinea, and the lessons learned and best practices that UNDP could bring to bear from its experience in other countries. Moreover, UNDP has developed a global expertise in supporting the development of environmental indicators and capacity-building and monitoring/evaluation tools, which are extremely necessary in measuring impact of such capacity building programmes. UNDP and the Government previously worked jointly on implementing the NCSA and the National Capacity Building Programme for the National and Global Environmental Management, and agreed to cooperate on environmental governance for future projects. The short-term work plan of the latter document foresaw a round table with the main partners in development in Guinea to discuss their involvement in PNRC. The future reference to UNDAF will be used as leverage in this process.

C.1   Indicate the co-financing amount the GEF agency is bringing to the project:

The Government will provide $250,000 including a contribution in kind (US$150,000) that encompasses making available certain staff of technical departments for mining, the environment, water and forests, agriculture, economy and finance, youth, promotion of women to perform certain technical tasks relatively specific to their sector. The Ministry in charge of the environment will contact UNDP by letter to support Guinea in funding for the project. Significant co-financing has been pledged by the PACV from its 17 million USD budget for this project. The PACV has preliminarily pledged co-financing, this should be negotiated to US$225,000 during the PPG phase. Resources of the communities (local development plans) and of the State will also be mobilized. UNDP Guinea office pledges US$ 150,000 from the TRAC allocation to the implementation of this project. It will also provide significant in-kind support to the project. Its technical and administrative staff will provide ongoing advice and logistical support to the project when needed. It will provide meeting facilities, communication facilities, transport facilities, as requested and as necessary. UNDP will further use its role as the UN resident coordinator office to make sure the project is aligned with all UN system work. UNDP senior management will play a key role in advocacy, and in awareness raising by attending key public events.

C.2  How does the project fit into the GEF agency’s program (reflected in  documents such as UNDAF, CAS, etc.) and staff capacity in the country to follow up project implementation:

The project is in conformity with the UNDP Country Cooperation Framework (CCF) as well as the United Nation Development Assistance Framework (UNDAF 2007-2011) with regard to environmental management and governance for the coordination of the global environmental processes, including those related to the implementation of the MEA. These challenges were identified during the development of the Common Country Assessment, which put forward the root causes for development of the country. It was elaborated within a narrow framework of dialogue between the UNS members and those of the Government and was the object of a fertile collaboration integrating on the one hand, the national priorities identified in the Poverty Reduction Strategy Document and on the other hand, being aligned with the international development objectives, culminating in the Millennium Development Goals (MDG). The UNDAF 2007-2011 aims at assisting the Government to break down certain barriers hindering the sustainable management of the natural resources and the improvement of the livelihoods of the rural and urban populations. The UNDAF is currently under revision for the next period. The results of the NCSA have already been integrated in the Common Country Program (CCP) of the United Nations in Guinea, which guarantees good integration in the new UNDAF. UNDP Guinea has provided technical and financial assistance to a number of institutional and pilot projects initiated by the Government of Guinea. Among others, UNDP supported the revision and adoption of the NAP-CCD , the development and adoption of a National Environmental Policy, the establishment of an Environmental Information system, the development of a National Strategy of Sustainable Land Management. Under the NAP-CCD, UNDP supported a pilot project for participative management of 10 Community forests, management of the bush fires, diffusion of improved stoves, afforestation, production of sea salt by valorization of solar energy (without use of fuel wood and in favour of safeguarding of mangrove forest), strengthened by a professionalization of the grassroots actors. In this CCCD project, the Guinea UNDP country office will play a major role as facilitator of the process of implementation to ensure adequate participation and interaction with all partners of the GEF and non - GEF projects in the country. As lead development partner in the National Capacity Building Programme for MEA implementation, the joint strategy of UNDP and the GEF in Guinea for the project is inspired by the MDG designed to achieve a sustainable environmental management by 2015. Visibility of GEF financial support will be ensured by using the global GEF branding in all electronic and printed materials. UNDP will also apply the following UNDP-GEF policy: “The GEF logo should appear on all relevant project publications, including amongst others, project hardware and other purchases with GEF funds. Any citation in publications regarding projects funded by GEF should also acknowledge the GEF. Logos of the Implementing Agencies and the Executing Agency will also appear on all publications. Where other agencies and project partners have provided support (through co-financing) their logos may also appear on project publications.” Full compliance will be made with the GEF’s Communication and Visibility Guidelines (“GEF Guidelines”): http://www.thegef.org/gef/sites/thegef.org/files/documents/C.40.08_Branding_the_GEF%20final_0.pdf

part iii:  approval/endorsement by gef operational focal point(s) and GEF agency(ies)

A.   Record of Endorsement of GEF Operational Focal Point (S) on Behalf of the Government(S): (Please attach the Operational Focal Point endorsement letter(s) with this template. For SGP, use this OFP endorsement letter).

| Name | Position | Ministry | Date (MM/dd/yyyy) |
| --- | --- | --- | --- |
| Ms. Kadiatou N'Diaye | GEF Operational Focal Point, Secrétaire Générale du Secrétariat Permanent du Conseil National de l'Environnement | Ministère Délégué à l’Environnement aux Eaux et Forêts | 03/27/2012 |

B.  GEF Agency(ies) Certification

| This request has been prepared in accordance with GEF/LDCF/SCCF/NPIF policies and procedures and meets the GEF/LDCF/SCCF/NPIF criteria for project identification and preparation. |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Agency Coordinator, Agency name | Signature | Date (MM/dd/yyyy) | Project Contact Person | Telephone | Email Address |
| Adriana Dinu, Officer-In-Charge UNDP/GEF |  | 04/10/2013 | Tom Twining-Ward | +421 2 59337 386 | tom.twining-ward@undp.org |

It is very important to consult the PIF preparation guidelines when completing this template.

Project ID number will be assigned by GEFSEC.

Refer to the reference attached on the Focal Area Results Framework when filling up the table in item A.

GEF will finance management cost that is solely linked to GEF financing of the project. PMC should be charged proportionately   
     to focal areas based on focal area project grant amount.

Same as footnote #3.

Decentralization in Guinea: Strengthening Accountability for Better Service Delivery, Public Sector Reform and Capacity Building Unit, Worldbank, june 2007.

NCSA X-cutting Evaluation, NCSA, 2007.