GEF-6 Project Identification Form (PIF)

Project Type: MSP

Type of Trust Fund: GEF Trust Fund

For more information about GEF, visit TheGEF.org

PART I: Project Information

| Project Title: | Strengthening natural resource valuation capacities for improved planning and decision-making to conserve the global environment |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Country(ies): | Guinea-Bissau | GEF Project ID: |  |  |  | 9502 |
| GEF Agency(ies): | UNDP | GEF Agency Project ID: |  |  |  | 5737 |
| Other Executing Partner(s): | Secretary of State for the Environment | Submission Date: |  |  |  | 16 Nov 2016 |
| GEF Focal Area(s): | Multi-focal Areas | Project Duration (Months) |  |  |  | 48 |
| Integrated Approach Pilot | IAP-Cities IAP-Commodities IAP-Food Security |  |  | Corporate Program: SGP |  |  |
| Name of parent program: | Cross-Cutting Capacity Development |  | Agency Fee ($) |  | 90,250 |  |

A. indicative Focal Area  Strategy Framework and Other Program Strategies

| ### Objectives/Programs (Focal Areas, Integrated Approach Pilot, Corporate Programs) | ### Trust Fund | ### (in $) |  |
| --- | --- | --- | --- |
|  |  | ### GEF Project Financing | ### Co-financing |
| CCCD-1 | GEFTF | 475,000 | 1,100,000 |
| CCCD-4 |  | 475,000 | 1,100,000 |
| Total Project Cost |  | 950,000 | 2,200,000 |

B. indicative Project description summary

| ### Project Objective: To develop a national integrated and coordinated environmental accounting and monitoring system for improved decision-making on the global environment |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| ### Project Components | ### Financing Type | ### Project Outcomes | ### Project Outputs | ### Trust Fund | ### (in $) |  |
|  |  |  |  |  | ### GEF Project Financing | ### Co-financing |
| 1: Strengthening targeted policy and legislative instruments for effective monitoring and decision-making on the global environment | TA | Targeted policy and legislative instruments are improved for better monitoring and decision-making on the global environment | 1.1: Assessment on the feasibility of environmental accounting in Guinea-Bissau 1.2: Recommendations on the integration of natural resource valuation into relevant policies, legislation and/or regulation 1.3: Targeted revision and development of policy and legal instruments to catalyze the use of natural resource valuation in decision-making 1.4: Memoranda of agreement(s) to catalyze inter-agency collaboration and coordination for the cost-effective use of natural resource valuation to meet and sustain Rio Convention obligations. 1.5: Targeted training and awareness on national policy and legal instruments for improved compliance to MEAs | GEFTF | 235,000 | 235,000 |
| 2: Strengthening effective monitoring and decision-making mechanisms for the global environment | TA | Institutional arrangements and technical capacities for monitoring and meeting global environmental targets are strengthened | 2.1: Comprehensive assessment of economic indicators and information systems for improved monitoring and decision-making on the global environment 2.2: Environmental monitoring indicators and associated tools for improved knowledge management 2.3: Development of an improved institutional mechanism, standards, norms, and procedures to catalyze the integration of the global environment into sector development plans. 2.4: Preparation of relevant training material for monitoring global environmental values, with particular attention to their econometric indicators 2.5: Learning-by-doing workshops on best practice and innovations for Rio Convention mainstreaming through the use of environmental accounting and natural resource valuation. 2.6: Resource mobilization strategy for the long-term financial sustainability of improved planning and decision-making for the global environment | GEFTF | 250,000 | 600,000 |
| 3: Development of natural resource valuation tools for improved decision-making on the global environment | TA | Tools for the valuation of natural resources and environmental services are developed and piloted | 3.1: Development of natural resource and environmental valuation methodologies that fully account for global environmental values, opportunities, and other benefits 3.3: Natural resource values and related economic indicators are organized into an appropriate information system 3.4: Relevant training courses and programmes improved by the integration of natural resource valuation tools 3.5: Learning-by-doing workshops to integrate natural resource valuation into planning and monitoring frameworks 3.6: Natural resource valuation tools, techniques, and the early application of recommended institutional reforms through pilot exercises in one site/sector to demonstrate value of environmental accounting to global environmental objectives and sustainable development. The pilot exercises will test the applicability of innovative tools for performing natural resource valuation 3.7: Lessons learned and best practices documented to fine-tune piloted natural resource valuation tools 3.8: Toolkit on natural resource valuation. | GEFTF | 250,000 | 640,000 |
| 4: Improving awareness of global environmental values through the use of natural resource valuation | TA | Awareness and understanding of the value of conserving the global environment to catalyzing sustainable development is improved | 4.1: Broad-based survey on public awareness on the global environment 4.2: Public awareness campaign and implementation plan 4.3: Brochures and articles on the Rio Conventions and other MEAs 4.4: Education module on global environmental issues for high schools developed and applied 4.5: Public service announcement on Rio Conventions 4.6: Public dialogues and awareness-raising workshops on global environmental values (journalists, private sector, civil society) | GEFTF | 129,000 | 425,000 |
| Subtotal |  |  |  |  | 864,000 | 1,900,000 |
| Project Management Cost (PMC) (including Direct Project Cost: 15,000) |  |  |  | GEFTF | 86,000 | 300,000 |
| Total Project Cost |  |  |  |  | 950,000 | 2,200,000 |

For multi-trust fund projects, provide the total amount of PMC in Table B, and indicate the split of PMC among the different trust funds here: (     )

C. Indicative sources of Co-financing for the project by name and by type, if available

| Sources of Co-financing | Name of Co-financier | Type of Co-financing | Amount ($) |
| --- | --- | --- | --- |
|  | Secretary of State for the Environment |  | 100,000 |
|  | Secretary of State for the Environment |  | 500,000 |
|  | UNDP |  | 650,000 |
|  | To be determined |  | 950,000 |
| Total Co-financing |  |  | 2,200,000 |

D. Indicative Trust Fund Resources Requested by Agency(ies),  Country(ies) and the Programming of Funds a)

| GEF Agency | Trust Fund | Country/ Regional/ Global | Focal Area | Programming of Funds | (in $) |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | GEF Project Financing (a) | Agency Fee (b)b) | Total (c)=a+b |
| UNDP | GEFTF | Guinea-Bissau | Multi-focal Areas | Cross-Cutting Capacity | 950,000 | 90,250 | 1,040,250 |
| Total GEF Resources |  |  |  |  | 950,000 | 90,250 | 1,040,250 |

- Refer to the Fee Policy for GEF Partner Agencies.

E.  Project preparation grant (ppg)

Is Project Preparation Grant requested? Yes x   No  If no, skip item E.

PPG  Amount requested by agency(ies), Trust Fund,  country(ies) and the Programming  of funds

| Project Preparation Grant amount requested: $50,000 PPG Agency Fee: 4,750 |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| GEF Agency | Trust Fund | Country/ Regional/Global | Focal Area | Programming of Funds | (in $) |  |  |
|  |  |  |  |  | PPG (a) | Agency Fee (b) | Total c = a + b |
| UNDP | GEFTF | Guinea-Bissau | Multi-focal Areas | Cross-Cutting Capacity | 50,000 | 4,750 | 54,750 |
| Total PPG Amount |  |  |  |  | 50,000 | 4,750 | 54,750 |

F.  Project’s Target Contributions to Global Environmental Benefits

Provide the expected project targets as appropriate.

| Corporate Results | Replenishment Targets | Project Targets |
| --- | --- | --- |
| - Maintain globally significant biodiversity and the ecosystem goods and services that it provides to society | Improved management of landscapes and seascapes covering 300 million hectares | Hectares |
| - Sustainable land management in production systems (agriculture, rangelands, and forest landscapes) | 120 million hectares under sustainable land management | Hectares |
| - Promotion of collective management of transboundary water systems and implementation of the full range of policy, legal, and institutional reforms and investments contributing to sustainable use and maintenance of ecosystem services | Water-food-ecosystems security and conjunctive management of surface and groundwater in at least 10 freshwater basins; | Number of freshwater basins |
|  | 20% of globally over-exploited fisheries (by volume) moved to more sustainable levels | Percent of fisheries, by volume |
| - 4. Support to transformational shifts towards a low-emission and resilient development path | 750 million tons of CO2e mitigated (include both direct and indirect) | metric tons |
| - Increase in phase-out, disposal and reduction of releases of POPs, ODS, mercury and other chemicals of global concern | Disposal of 80,000 tons of POPs (PCB, obsolete pesticides) | metric tons |
|  | Reduction of 1000 tons of Mercury | metric tons |
|  | Phase-out of 303.44 tons of ODP (HCFC) | ODP tons |
| - Enhance capacity of countries to implement MEAs (multilateral environmental agreements) and mainstream into national and sub-national policy, planning financial and legal frameworks | Development and sectoral planning frameworks integrate measurable targets drawn from the MEAs in at least 10 countries | Number of Countries: 1 |
|  | Functional environmental information systems are established to support decision-making in at least 10 countries | Number of Countries: 1 |

part ii:  project JustiFication

1. Project Description. Briefly describe: 1) the global environmental and/or adaptation problems, root causes and barriers that need to be addressed; 2) the baseline scenario or any associated baseline projects, 3) the proposed alternative scenario, GEF focal area strategies, with a brief description of expected outcomes and components of the project, 4) incremental/additional cost reasoning and expected contributions from the baseline, the GEFTF, LDCF, SCCF,  and co-financing; 5) global environmental benefits (GEFTF) and/or adaptation benefits (LDCF/SCCF); and 6) innovation, sustainability and potential for scaling up.

1.1:   The global environmental problems, root causes and barriers to be addressed

Guinea-Bissau houses a wealth of natural resources that is of local, national, regional and global significance.  However, despite its enormous potential, the country embodies some of the world’s toughest development challenges, combining acute and rising poverty with persistent fragility.  It is lowly ranked at 176 of 187 countries in the 2011 Human Development Index and is considered one of the poorest countries in the world with one of the highest maternal death rates, a life expectancy at birth of only 49 years and considerable disparity in income distribution.  Being a coastal country, Guinea-Bissau’s challenges are magnified as a Least Development Country (LDC) and Small Independent Developing State (SIDS), due to its environmental and socio-economic vulnerabilities, geographical situation and climate conditions.  This context of poverty and weak economy translates into an increased pressure on natural resources resulting in their degradation.  Guinea-Bissau climate variability phenomena, biodiversity loss, desertification and land degradation constitute a real threat to all vital sectors of the national economy.

The primary drivers of the climate vulnerability of the coastal areas and communities are physical exposure, dependence on agriculture and fishing as main livelihood options, and poor governance.  Specifically, variability in weather patterns will affect the rate of economic growth, exacerbate poverty and social inequalities, as well as jeopardize chances of success of development policies meant to fight poverty.  Furthermore, sea-level rise exposes the population to risks of flooding and coastal erosion, which can potentially lead to the disappearance of beaches, vegetation, road and touristic infrastructure, schools, homes, entire villages, in addition to important active biodiversity reserves on which the local economy is based.  The majority of the Bissau-Guinean population directly depends on the exploitation of natural resources for their survival.  The agriculture, forestry and, in particular, fisheries, are the basis for economic development of the country.

Guinea-Bissau marine and estuarine waters are known to be among the richest on the West African coast in terms of diversity, productivity and food potential and are essential for the survival of several globally endangered or threatened species and for species that are economically important.  Practices such as intensive farming and fishing accelerate the natural resource and land degradation, which in turn threatens the loss of biodiversity.  Moreover, official projections indicate a doubling of the country´s population by the year 2025: based on an average growth rate of 2.3%, the population should increase to 2,030,000 inhabitants.  In addition to high dependency of the population on natural resources, the country has very limited capacity to adapt to negative impacts of climate change climate developments.

A major factor contributing to the loss of global environmental values is due to the non-consideration of the long-term economic values of the environment and natural resources.  While this is exacerbated by the country’s widespread poverty, planning and decision-making in Guinea-Bissau does not benefit from objectively verified data and indicators on environmental values.  As a result, the country continues to pursue economic options that are able to guarantee short-term hard currency revenues instead of alternative strategies that allows for environmentally sound and sustainable development that conserves global environmental values.  Guinea-Bissau’s national accounts currently contains and manages statistics that used to measure Gross Development Product using traditional metrics, to the exclusion of the more innovative metrics of environmental values and costs. In other words, the GDP index does not reflect any environmental accounting information.  A major barrier to collecting and calculating the relevant data and information is due to the inadequate monitoring capacities and weak databases and information systems.

Guinea-Bissau has experienced several cycles of political and institutional instability over the past few years, particularly, during the 2009-2014 five-year period.  This situation of military-political disruption contributed significantly to environmental problems in the country, which resulted in increased pressure on natural resources.  Also, the complexities and challenges associated with the effective implementation of the various multilateral environmental agreements threaten to overwhelm the existing administrative structures and capacities of the country.  At present, the country’s degraded and limited infrastructure combined with a low technical and institutional capacity severely limit Guinea-Bissau’s environmental governance framework and thus its potential to conserve the natural environment, let alone secure long-term benefits from it.  Aware of the fragility of its ecosystems and the fact that its economy is heavily dependent on sectors sensitive to climate variability and convinced that sustainable economic growth and human resources development are decisive factors in the significant reduction of poverty, the country identified the capacity development needs leading to solutions at the national and institutional levels for a sound and effective management of natural resources through financial and technical support from development partners.

1.2:   The baseline scenario or any associated baseline projects

The Government of Guinea-Bissau has undertaken various initiatives to address environmental issues.  The Government of Guinea-Bissau ratified the three Rio Conventions relating to biodiversity (UNCBD), desertification (UNCCD), and climate change (UNFCCC) in accordance with recommendations of the Rio Conference in 1992.  Under these agreements, in order to respect its commitments, the country has taken various measures in planning and implementing programmes for conventions: the elaboration of the National Plan Environmental Management, National Biodiversity Strategy and Action Plan, the National Action Plan on Adaptation, and the Second National Communication to the UNFCCC, among others.

Towards meeting obligations under the three Rio Conventions (among other multilateral environmental agreements) Guinea-Bissau has implemented a number of projects with the support of many development partners.  These include strengthening the country’s a subset of legislative and regulatory instruments on forestry and protected areas, environmental codes, and other related by-laws to catalyze their implementation.  In spite of these efforts, these actions are not adequately supported by the practical procedures and working methods needed for an integrated and broad implementation of the Rio Conventions.  The measures taken until now are deemed inadequate in view of the multiple commitments made in accordance with the principles and measures set forth in the various conventions to ensure rational and sustainable management of the environment and natural resources.  Indeed, the arrangements do not register through a well-defined time horizon, over the long-term in line with the 17 Sustainable Development Goals.  For example, the National Strategy for Poverty Reduction (PRSP I), which is the strategic planning reference document for developing countries is characterized by the absence of links to environmental conservation.

Deficiencies still remain in both the availability and qualification of human resources at the level of institutional, financial and legal capacity, and finally in the field of strategic planning in the long term.  The principle of sustainability in the management of natural resources, especially from the perspective of integration between the agricultural, forestry, pastoral, fishing, on the one hand and to ensure consistency with national economic policies on the other hand, remains a concern yet inadequately answered at present.  Preserving the country´s natural resource values is a challenging situation due to the national priority of socio-economic development and institutional framework governing natural resource use and environmental management, which mainly favors the extraction and exploitation of natural resources for short-term economic gains.

Participatory approaches are not sufficiently understood among the government technicians and political decision-makers as indispensable to project formulation and implementation.  Guinea-Bissau has recently launched REDD+ readiness programme, which would require the same capacities as for the establishment of a comprehensive environmental accounting and monitoring system for the country.  A Fund for Local Environmental Initiatives, financed by the World Bank, has helped launching local development activities related to biological resources around protected areas.  This includes skills development for local communities in the economic exploitation of wood products, wildlife, and gathering and training for managers and local technicians to monitor and assess the recovery process of local biological resources.  However, this work is limited does not currently linked capacity building of the National Statistic Office, which is short of well-trained staff and using outdated and dysfunctional technology to collect and manage data and information.  Among the government’s national priorities is the development of sustainable development indicators per the post-2015 Sustainable Development Goals.

Also, the Government of Guinea-Bissau presented its strategic and operational plan entitled "Terra Ranka" for the period 2015-2020.  The document, prepared in consultation with main national and international stakeholders, is based on the Government's development programme adopted in September 2014, particularly on its strategic pillars, such as: Governance and Peace, Infrastructures, Industrialization, Urban development, Human Development and Biodiversity.  The strategy stressed the need to work towards economic recovery on the basis of structural reforms to ensure sustainable development.  Four main drivers for economic growth were identified: agri-business, fisheries, tourism and transparent and sustainable use of the country's natural resources.

Aside from the GEF-funded projects that this project would need to coordinate activities in order to avoid duplication of resources, such as US$ 16.7 million protected areas project, there are a small number of non-GEF projects that could possibly be considered as a baseline to this CCCD project.  This includes the World Bank project to strengthen Guinea-Bissau’s public sector for improved public financial management.  The European Union has limited non-GEF funded projects in Guinea-Bissau, and is currently exploring strategic options for its development options.  An important set of baseline projects that this CCCD project will build on will be through the work of a number of non-governmental organizations working in the communities, such as Palmerinho and research institutes such as the Centre for Applied Fisheries Research and Institute for Biodiversity and Protected Areas.  During the PPG, consultations and negotiations on the design of project activities with development partners will confirm which programmes and projects will constitute the baseline to this CCCD project.  These will be determined on the basis that their activities will be directly implicated in the project.

1.3:   The proposed alternative scenario, GEF focal area strategies, with a brief description of expected outcomes and project components

This project is in line with the Cross-Cutting Capacity Development programming frameworks 1 and 4, which aim to integrate global environmental needs into management information and monitoring systems and the piloting of innovative economic and financial tools for Rio Convention implementation.

Despite the achievements made during the recent years, the country still struggles to face important challenges to meeting environmental goals.  The 2011 NCSA proposed a comprehensive, integrated approach to strengthening environmental capacity by inserting it into the general process of national development planning.  Guinea-Bissau’s 2014 National Report to the UNCBD reiterated this priority, calling for further work to understand and minimize the pressures on natural resources and ecosystems that affect the quality of the goods and services they provide.  Guinea-Bissau is also committed to advance the use of internationally agreed standards of environmental accounting, with particular attention to fulfilling the post-2015 Sustainable Development Goals and meeting Rio Convention obligations.

This CCCD project sets out to develop capacities along these lines, specifically to develop a national integrated and coordinated environmental accounting and monitoring system for improved decision-making to meet global environment and sustainable development priorities.  To this end, the project will develop and pilot the early use of methodologies and associated tools that will attach an economic and/or financial value to environmental goods and services, followed by the use of this information for improved decision-making and planning on the global environment.  By embracing financial and economic value to natural resource functions and services, the country would allow for a more accurate representation of the costs associated with development.  This project will require close coordination with other similar exercises currently underway in Guinea-Bissau, to incorporate the economic valuation of global environmental goods and services and participate in the devlopment a of national environmental information system for Rio Conventions and other MEAs monitoring, verification and reporting.

The proposed project would develop a targeted set of systemic, institutional, and individual capacities to strengthen the country’s underlying capacities to meet and sustain global environmental obligations that will generate global environmental benefits.  The project will explore options for building on best practices for incorporating environmental accounting statistics within the Guinea-Bissau’s system of national accounts, recognizing that the latter requires significant leveraged co-financing.  Best practices will be identified from various sources, with particular emphasis given to what is being in Brazil and Portugal, the European Union more broadly, and the work of the National Account Section of the United Nations Statistics Division.  During the project preparation phase, careful structuring of the project activities will ensure that the best appropriate methodologies and standards are developed, tested, and piloted within the the limits of Guinea-Bissau’s absorptive capacities.  This project will be implemented through four components:

Component 1: Strengthening policy and legislative instruments for effective monitoring and decision-making on the global environment

This first component will focus on targeting and improving policy and legislative instruments for better monitoring and decision-making on the global environment.  An in-depth assessment of the feasibility of environmental accounting is a key first early activity that will set the stage for much of the subsequent work to be carried under the project.  The findings from this assessment will inform the strategic choices of realistic policy and legislative reforms, although these will be limited to by-laws and interpretive manuals.  The project will take a holistic approach to enabling and catalyzing policy coordination, and strengthening associated human capacities to manage this process.  To the extent realistic, and determined by the feasibility study, the project will seek to address the integration of natural resource valuation into relevant legislation and/or regulation.  Building on the existing capacities and those developed as part of the NCSA consultative process, the project will strengthen a policy dialogue process to review and develop both policy and legal instruments to catalyze the use of natural resource valuation in decision-making in a cost-effective manner.  Also, under this component the project will strengthen the necessary policy arrangements, e.g., memoranda of agreement, that will catalyze more effective inter-agency collaboration and coordination for Rio Convention mainstreaming and decision-making (that latter being strengthened under components 2 and 3).  This will include reconciling the mandates of targeted stakeholder institutions, both government and non-state institutions as well as other relevant social actors.  Under component 4, the project will design and implement a targeted training and awareness on national policy and legal instruments for improved compliance to MEAs.

Component 2: Strengthening effective monitoring and decision-making mechanisms for the global environment

Whereas the first component will focus on strengthening systemic capacities to institutionalize environmental accounting in Guinea-Bissau, component 2 will emphasize the strengthening of targeted institutional and individual capacities, e.g., improved processes and skillsets on the monitoring and information systems.  This is in contrast to comnponent 3 that will be more targeted to institutional and individual capacity building on natural resource valuation.

A first activity under this component will be an in-depth assessment of all relevant environmental indicators and information systems for improved monitoring and decision-making on the global environment.  Particular attention will be given to best practices for the preparation of Strategic Environmental Assessments and Environmental Impact Assessments.  Based on this assessment and in line with internationally agreed standards of environmental accounting and indicators related to the Sustainable Development Goals, the project will develop a set of environmental monitoring indicators and associated tools for improved knowledge management.  This component will also include the strengthening and development of an improved institutional mechanism and compliance with the SEEA standards, norms, and procedures in order to catalyze the integration of the global environment into sector development plans.  The latter will include the integrating these environmental monitoring indicators into the management information system currently managed by the National Office of Statistics and Census. This will include strengthening inter-agency collaboration and improving and aligning the mandates of key institutions to institutionalize natural resource valuation.  The project will be limited to strengthening targeted capacities, i.e., additional software, technology, as well as learning-by-doing training to use new and additional data and information for planning and decision-making purposes.  Technical skills will help planners and decision-makers to better collect and interpret data and information within the construct of the five development development sectors and internationally agreed standards on environmental-economic accounting (agriculture, energy, fisheries, land and ecosystems, and water resources).

The project will prepare relevant training material for monitoring environmental targets.  Learning-by-doing workshops and trainings on best practice and innovations for Rio Convention mainstreaming will be carried out to a sufficiently large number of government staff and other social actors that have some role in the planning and decision-making on environmental and natural resource management.  Additional technical trainings will be undertaken in order to ensure that a critical mass of people have the requisite skillsets to fill vacant positions as a result of high staff turnover.

Component 3:  Development of natural resource valuation tools for improved decision-making on the global environment

This outputs and activities under this component are implicitly tied to those of component 2, targeting the effective use of natural resource valuation for improved decision-making on the global environment.  Co-benefits under this component are the improved capacities to meet post-2015 Sustainable Development Goals.  The technical features of this project will be closely aligned those of the System of Environmental and Economic Accounting.  There are many examples of best practices and lessons learned on the incorporation of environmental accounting data into national accounts.  The project will explore opportunities to use relevant best practices from the National Accounts Section of the United Nations Statistic Division.  Other important lessons learned and best practices will be sought from Brazil and Portugal, as well as the European Union, among other countries as appropriate.  Key outputs of this component will focus on the development of a set of natural resource valuation tools and to pilot their mainstreaming into organizational processes, such as environmental impact assessments, and decision-making.  Activities includes improve inter-agency collaboration so as to institutionalize natural resource valuation and monitoring and prepare, in conjunction with activities under component 2, a methodology for natural resources and environmental valuation that fully accounts for global environmental costs and benefits.  As with component 2, learning-by-doing workshops will ensure that a sufficient critical number of staff and other stakeholders are adequately trained to integrate natural resource valuation into planning and monitoring frameworks for the sake of the global environment.

Component 4:  Improving awareness of global environmental values

Education and awareness are key components in the development of this project, since they will contribute to a greater empowerment and participation in many aspects of the environmental management.  The activities under this component will focus on a broad range of underlying capacity development at all levels to create awareness, understanding and appreciation of the value of conserving the global environment to catalyze sustainable development while meeting and sustaining national socio-economic development priorities.  To this end, the project will design and implement a comprehensive training and public awareness campaign targeted to technical staff, decision-makers, and key practitioners which will include, among others, educational materials.  Project results will be delivered by including specific activities, namely: a broad-based survey on public awareness on the global environment; public awareness campaign and implementation plan; brochures and articles on the Rio Conventions and other MEAs; public dialogues and awareness-raising workshops on global environmental values (journalists, private sector, civil society).

1.4:   Incremental/additional cost reasoning and expected contributions from the baseline, the GEFTF, LDCF, SCCF, and co-financing;

The present project will invest US$ 950,000 as the GEF increment to the baseline to strengthen the required capacities and know-how to develop a national integrated and coordinated environmental accounting and monitoring system for improved decision-making on the global environment.  The GEF contribution will be targeted to activities that provide demonstrable global environmental benefits.  The GEF increment of this project complements an equal amount of co-financing from the Government of Guinea-Bissau, UNDP, and other donor agencies, which will be confirmed during the PPG with the assistance of a fundraising specialist.  Significant co-financing from UNDP is pledged in the amount of US$ 550,000 cash from TRAC resources at the time of PIF formulation, and during PPG, further in-kind contribution will be identified from among the set of relevant programme activities of non-GEF projects that will directly contribute to the delivery of expected CCCD deliverables.

1.5:   Global environmental benefits (GEFTF) and/or adaptation benefits (LDCF/SCCF);

The global environmental benefits to be delivered are indicated by the capacities to be developed that respond to specific articles under the three Rio Conventions outlined in the table below.

| Project components | UNCBD | UNFCCC | UNCCD |
| --- | --- | --- | --- |
| Component 1: Strengthening policy and legislative instruments for effective monitoring and decision-making on the global environment | - Article 6 (a, b): Integrate the conservation and sustainable use of biological diversity into relevant sectoral or cross-sectoral plans, programmes and policies. - 8 (1e, 1f): Commitments related to the promotion of environmentally sound and sustainable development &rehabilitation and restoration through the development and implementation of plans or other management strategies. - Article 20 (7): Financial considerations to the special situation of most environmentally vulnerable countries | - Article 4: Take climate change considerations into account in relevant social, economic and environmental policies and actions - Article 5 (c): Research and systematic observation - Article 12: Communication of information related to implementation | - Article 4: General provisions (Commitments and obligations of African country Parties) - Article 8 (3 (a)): Measures to improve the economic environment with a view to eradicating poverty - Article 9: National action programmes and implementation & evaluation indicators - Article 10 (c): Review of national legislation |
| Component 2: Strengthening effective monitoring and decision-making mechanisms for the global environment | - Article 7: Identification and monitoring - Article 10 (a, e): Integrate consideration of the conservation and sustainable use of biological resources into national decision-making - Article 11: Incentive measures for the conservation and sustainable use of components of biological diversity. | - Article 2: Enable economic development to proceed in a sustainable manner - Article 11 (a): Modalities to address climate change in conformity with the CoP policies and programme priorities - Article 12: Communication of information related to implementation | - Article 8 (d): Measures to improve knowledge of desertification: (i) promoting research and the collection, processing and exchange of information on the scientific, technical and socio-economic aspects of desertification; - Article 13 (e): Information exchange - Article 16: Technical assistance and cooperation |
| Component 3: Development of natural resource valuation tools for improved decision-making on the global environment | - Article 10 (a, b, e): Sustainable use of components of biodiversity. - Article 17: Exchange of information from all publicly available sources, relevant to the conservation and sustainable use of biological diversity | - Article 3 (3): Principles: policies and measures to deal with climate change should be cost-effective so as to ensure global benefits at the lowest possible cost - Article 6 (a (ii)): Public access to information on climate change | - Article 6 (2): Strategic planning framework for sustainable development - Article 8 (c (ii)): Management and decision-making of local authorities, and encouraging initiatives and the assumption of responsibility by local communities and the establishment of local structures |
| Component 4: Improving awareness of global environmental values | - Article 13: Promote and encourage understanding of the importance of, and the measures required for, the conservation of biological diversity, as well as its propagation through media, and the inclusion of these topics in educational programmes | - Article 6 (a (ii) and b (i)): Public access to information on climate change | - Article 8 (b (ii)): Capacity building, education and public awareness: strengthening, public awareness and environmental education campaigns and disseminating knowledge of techniques relating to the sustainable management of natural resources |

1.6:   Innovation, sustainability and potential for scaling up.

Integrating natural resource valuation into environmental decision-making procedures and mechanisms is a new and innovative approach for Guinea-Bissau.  The transformative nature of this project is that the use of natural resource valuation will catalyze the Government’s planning and decision-making processes in a more environmentally friendly and sustainable direction.  Importantly, the improved plans and decisions are expected to provide the country with a stronger basis for mobilizing new and additional financial resources for their implementation.  However, the relatively small size of the project to institute a resilient and sustainable system of environmental accounting through the use of natural resource valuation in monitoring and decision-making means that the project will be limited to setting up the institutional framework and piloting the early implementation of the aforementioned system.

Thus, a significant portion of the project will be directed to learning-by-doing exercises and pilot projects.  This will include the integration of natural resource valuation metrics and methodologies in the planning stages of development interventions, including the environmental impact assessments, and the development of roadmaps for implementing and monitoring development plans to measure their contributions and impacts on the global environment.  The lessons learned from these pilot exercises will inform their replication and scaling up, as well as their adaptive collaborative management to strengthen their resilience and sustainability.

The sustainability of project outcomes is inherent in the project design and implementation approach.  In relation to the organization, the project will engage a large number of stakeholders in raising their awareness and understanding of the value ofincorporating a set of natural resource valuation tools into the policies and procedures governing the preparation and use of environmental services and relevant processes.

The present project will embrace an adaptive collaborative management approach which is fundamental for strenghtening sustainability.  This approach places a special emphasis of engaging a broad public participation in the decision-making process, in order to validate project activities, outputs and decisions related to the management of ecological systems with multiple economic benefits and environmental values.  Project champions will play a key role in advocacyto increase the reach of the project to a greater number of important stakeholders.

2. Stakeholders. Will project design include the participation of relevant stakeholders from civil society and indigenous people?  (yes  /no ) If yes, identify key stakeholders and briefly describe how they will be engaged in project design/preparation.

The main project stakeholders are the government ministries and agencies that are responsible for key sectoral policies and legislation, in particular the Secretary of State for Environment, in charge of the environmental management policy and coordination since 2003 through the Environment General Directorate.  Key ministries and agencies that provide general environment and natural resource management service and/or specialized services that carry on day-to-day environmental and natural resource management are also likely to be involved, which will be further narrowed during project development.

- Ministry of Agriculture and Rural Development, which has a Forest and Hunting Directorate, an Agriculture General Directorate, a Livestock General Directorate, Institute for Biodiversity and Protected Areas (IBPA) and the National Institute for Agricultural Research (INPA)

- Ministry of Education which is mandated to provide training in environmental issues

- Ministry of Fisheries and Maritime Economy

- Ministry of Public Works, Construction and Urbanism -Planning whose activities on construction of infrastructures, bridges and roads, impact on the environment

- Ministry of Commerce, Tourism & Tradecrafts

- Ministry of Social Communication and Parliamentarian Affairs

- Ministry of Foreign Affairs, International Cooperation & Communities, which manages international conventions and plead their causes with donors

- Ministry of Finance

- Ministry of Energy & Industry

- Ministry of Economy & Regional Integration

- Ministry of Public Health

- Ministry of Public Administration & Reform

- Ministry of Interior

- Ministry of Justice

- Ministry of Tourism & Territorial Order

- Ministry of Social Solidarity and Struggle against Poverty and

- The State Secretariat for Culture

The private sector will also participate, namely the chambers of agricultural trade as well as several NGOs.  International NGOs may include World Conservation Union (IUCN), Swiss Aid and the Netherlands Development Organization (SNV).  Other stakeholders include the decentralized services that act as an interface between public sector services and grassroots populations providing them with guidance to adequately participate in a sustainable natural and environmental resource management, and academic institutions that are important to ensuring the long-term sustainability of the project, such as the Universidade Lusófona Guiné / Universidade Amílcar Cabral (UAC).

3. Gender Considerations. Are gender considerations taken into account? (yes x /no ).  If yes, briefly describe how gender considerations will be mainstreamed into project preparation, taken into account the differences, needs, roles and priorities of men and women.

Women face a number of inequalities and tend to be more impacted by environmental degradation and climate change.  Especially, in rural and remote areas, women and young children are particularly vulnerable to resource degradation.  The present CCCD project, by contributing to the protection/sustainable use of natural resources, should therefore have a positive impact on gender equality.  Where possible, the project will also introduce gender disaggregated data and information management mechanisms, in order to facilitate measures to improve gender balance in the future.  It will ensure that all key outputs take account of gender related concerns, and where possible generate gender benefits, including steps to determine how project activities will affect both men and women, and it will examine how the project might promote gender equity in its policy, research, and educational aspects.  Finally, draft project documents will be shared with gender specialists for their input.

Gender considerations for this project are informed by the 2015 report on Mainstreaming Gender at the GEF.  During the PPG phase, the design of project implementation arrangements will include the structuring of consultative and decision-making mechanisms that will mobilize the unique perspectives of Rio Convention implementation from the lens of gender priorities and differences.

No budget allocation from the GEF grant will be made to specifically address gender equality.  Rather, to the extent appropriate, gender issues will be addressed by co-financing to the project, and determined during the PPG phase.

4 Risks. Indicate risks, including climate change, potential social and environmental risks that might prevent the project objectives from being achieved, and, if possible, propose measures that address these risks to be further developed during the project design (table format acceptable).

| Identified risks | Risk Level | Mitigation measures |
| --- | --- | --- |
| Inadequacy/uncertainty of funding. There are relatively few opportunities for sourcing cash co-financing. The government has relatively little finances, resulting in poor maintenance and low staffing of their agencies | High | - UNDP will facilitate linkages during the PPG phase to on-going and planned baseline development activities implemented by donors, securing of the necessary co-financing - The proposed project has strong commitment from the Government (Secretary of State for Environment) that will work the Ministry of Finance and other government agencies to secure in-kind support to the project through stakeholder engagement and convening workshops, among others to mobilize the necessary resources |
| Coordination between the Government and other agencies is not structured or effective | Medium | - UNDP will facilitate consultations at all levels, including the highest level in order to facilitate and catalyze coordination among government agencies. This will be through the work of the project board as well as project activities that pay particular attention to institutionalize consultative mechanisms. |
| Delays in project implementation and ineffective project execution | High | - Carefully selected project indicators and an adaptive monitoring practice will facilitate timely implementation and effective execution - The project will adopt best practice management techniques to identify risks throughout project implementation, with the project board and development partners ensuring the project’s adaptive collaborative management |
| Political instability mitigates against effective coordination across key development sectors. | Medium | - Strong support for policy and institutional changes in key ministries and agencies will be identified at all levels, with the project board serving to validate and legitimize recommended reforms. |

5. Coordination. Outline the coordination with other relevant GEF-financed and other initiatives.

The coordination and the management arrangements will be defined in detail during the PPG of the project.  Based on initial discussions with the Government of Guinea-Bissau, the Secretary of State for Environment and Sustainable Development will ensure the overall coordination of the project as the national main implementing agency, and in close collaboration with the General Directorate of Environment, the Rio Conventions National Focal Points and UNDP as the Implementing Agency.  UNDP's current role in Guinea-Bissau intends to eradicate poverty, violence and hunger, and assists the Government of Guinea-Bissau to translate economic growth into long-lasting, inclusive human development: It also helps to develop capacity, share knowledge and mobilize funds for sustainable development.  During the PPG phase, a thorough analysis of initiatives with similar scope, area coverage or involved agencies will be performed to ensure maximum synergies, and to prevent duplication of efforts, especially with other GEF-6 country project proposals and enabling activities that are either ongoing or currently in advanced development stages.  This proposed project is particularly building upon the conclusions of the Government of Guinea-Bissau NCSA and aims to address the identified capacity gaps that have not yet been addressed by other projects, namely the following GEF financed projects: "Strengthening the resilience of vulnerable coastal areas and communities to climate change in Guinea-Bissau"; "The Second National Communication of Climate Changes in Guinea-Bissau"; and the project "Strengthening the financial and operational framework of the national PA system in Guinea-Bissau", among others.  The key stakeholders for these projects will be included in the PPG phase to ensure avoiding duplication.  In line with the Gender Action Plan (GAP) of UNICEF Strategic Plan 2014-2017 that embodies the promotion of gender equality across all of the organization’s work at the global, regional and country levels, all project strategies and activities will integrate gender considerations, including the encouragement of the equal participation of women at all levels and in all activities at institutional and local levels.

6. Consistency with National Priorities. Is the project consistent with the National strategies and plans or reports and assessements under relevant conventions? (yes x  /no ).  If yes, which ones and how:  NAPAs, NAPs, ASGM NAPs, MIAs, NBSAPs, NCs, TNAs, NCSAs, NIPs, PRSPs, NPFE, BURs, etc.

As a Rio Convention capacity development project, the proposed strategy sets out to meet barriers identified in Guinea-Bissau’s 2011 NCSA.  Thus, this project and its strategy are consistent with the findings of the NCSA, as well as with Guinea-Bissau’s national plans, priorities and policies.  The Government of Guinea-Bissau has elaborated various plans and reports to safeguard the environment and promote sustainable development, including the National Adaptation Programme of Action (2006) and Second National Communication on Climate Change (2011) with which this project is fully in line.  It will also take into account Guinea-Bissau’s PAN/LCD and National Strategy and Action Plan on Biological Diversity and the National Action strategies.  Indeed, the project will contribute with the establishment of a reliable environmental accounting and monitoring system which allows presentation of the state of the environment in terms understandable to political decision-makers, both national and international, and regular updating of such evaluation in strengthening the capacity of Guinea-Bissau to plan its future for sustainable development by establishing an important and useful tool for that purpose

Notwithstanding the above-mentioned strategies, the project is grounded within the priorities identified in the 2015-2020 Terra Ranka, which is an strategic and operational plan for Guinea-Bissau to ensure the sustainable management of natural capital and to preserve biodiversity, as well as to expand the use of information communication technologies to promote sustainable development.  The plan makes a special call for the valuation of Guinea-Bissau’s natural resources (page 28 of the Terra Ranka).

7. Knowledge Management. Outline the knowledge management approach for the project, including, if any, plans for the project to learn from other relevant projects and initiatives, to assess and document in a user-friendly form, and share these experiences and expertise with relevant stakeholders.

Knowledge management is an important element of the project, as it is part of capacity building in the country that encourages regional cooperation as well as knowledge and information exchanges.  Partnerships and collaboration will also catalyze the transfer of knowledge and competencies among actors, stakeholders and champions.  Lessons learned from other projects will be included, as appropriate (for example, in the training programmes and the knowledge management system).  In particular, the project will build on the work of the United Nations Statistics Division on the System of Environmental and Economic Accounting.  This project also contains specific activities to increase the use and sharing of knowledge such as brochures, youth engagement, and learning-by-doing training to strengthen individual and institutional capacities to use knowledge in decision-making.

The project’s approach to knowledge management is consistent with the International Resource Panel Report on Policy Coherence of the Sustainable Development Goals, which emphasizes the need for developing widespread awareness and creating and disseminating decision support tools.  To make these tools more practical the project will promote the development of user-friendly guidelines, instructions and manuals.  Many of these documents will be technical materials supporting the development of a national integrated and coordinated environmental accounting and monitoring system for improved decision-making to meet global environment and sustainable development priorities.

part iii:  approval/endorsement by gef operational focal point(s) and GEF agency(ies)

A. Record of Endorsement of GEF Operational Focal Point (s) on Behalf of the Government(s):  
      (Please attach the Operational Focal Point endorsement letter(s) with this template. For SGP, use this SGP OFP 
      endorsement letter).

| Name | Position | Ministry | Date (MM/dd/yyyy) |
| --- | --- | --- | --- |
| Joao Raimundo Lopes | GEF Operational Focal Point | Secretariat of the State for Environment | 04/27/2016 |

B. GEF Agency(ies) Certification

This request has been prepared in accordance with GEF policies and procedures and meets the GEF criteria for project identification and preparation under GEF-6.

| Agency Coordinator, Agency name | Signature | Date (MM/dd/yyyy) | Project Contact Person | Telephone | Email |
| --- | --- | --- | --- | --- | --- |
| Adriana Dinu Excecutive Coordinator UNDP/GEF |  | 05/23/2016 | Tom Twining-Ward Senior Technical Advisor, UNDP (Green-LECRDs) | +90 5396532807 | tom.twining-ward@undp.org |

GEF_PIF_60

C. Additional GEF Project Agency Certification (Applicable Only to newly accredited GEF Project Agencies)

Not applicable

Project ID number will be assigned by GEFSEC and to be entered by Agency in subsequent document submissions.

When completing Table A, refer to the excerpts on GEF 6 Results Frameworks for GETF, LDCF and SCCF.

Financing type can be either investment or technical assistance.

For GEF Project Financing up to $2 million, PMC could be up to10% of the subtotal; above $2 million, PMC could be up to 5% of the subtotal. PMC should be charged proportionately to focal areas based on focal area project financing amount in Table D below.

Indicative. The exact amount will be determined during PPG phase.

PPG requested amount is determined by the size of the GEF Project Financing (PF) as follows: Up to $50k for PF up to$2m (for MSP); up to $100k for PF up to $3m; $150k for PF up to $6m; $200k for PF up to $10m; and $300k for PF above $10m. On an exceptional basis, PPG amount may differ upon detailed discussion and justification with the GEFSEC.

PPG fee percentage follows the percentage of the Agency fee over the GEF Project Financing amount requested.

Provide those indicator values in this table to the extent applicable to your proposed project.  Progress in programming against these targets for the projects per the Corporate Results Framework in the GEF-6 Programming Directions, will be aggregated and reported during mid-term and at the conclusion of the replenishment period. There is no need to complete this table for climate adaptation projects financed solely through LDCF and/or SCCF.

For biodiversity projects, in addition to explaining the project’s consistency with the biodiversity focal area strategy, objectives and programs, please also describe which Aichi Target(s) the project will directly contribute to achieving.

For regional and/or global projects in which participating countries are identified, OFP endorsement letters from these countries are required 
  even though there may not be a STAR allocation associated with the project.

GEF policies encompass all managed trust funds, namely: GEFTF, LDCF, and SCCF