Project Identification Form (PIF)

Project Type:

Type of Trust Fund:

For more information about GEF, visit TheGEF.org

PART I: Project Information

| Project Title: | Improvement of the decision-making process in Kazakhstan through introduction of mechanisms of economic assessment of fulfilling national obligations under global environmental agreements |  |  |
| --- | --- | --- | --- |
| Country(ies): | Kazakhstan | GEF Project ID: | 5399 |
| GEF Agency(ies): |  | GEF Agency Project ID: | 5248 |
| Other Executing Partner(s): | Ministry of Environment Protection of the Republic of Kazakhstan | Submission Date: | 11 June 2013 |
| GEF Focal Area (s): |  | Project Duration (Months) | 36 |
| Name of parent program (if applicable): - For SFM/REDD+ - For SGP - For PPP | N/A | Project Agency Fee ($): | 47,500 |

A.  indicative Focal AREA STRATEGY Framework:

| ### Focal Area Objectives | ### Trust Fund | ### Indicative ### Grant Amount ### ($) | ### Indicative Co-financing ### ($) |
| --- | --- | --- | --- |
|  |  | 500,000 | 650,000 |
| Total Project Cost |  | 500,000 | 650,000 |  |

- indicative Project description summary

| ### Project Objective: To develop individual and institutional capacities for undertaking an economic valuation of global environmental goods and services as potentially impacted by proposed development policies, programmes, plans and projects |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| ### Project Component | ### Grant Type | ### Expected Outcomes | ### Expected Outputs | ### Trust Fund | ### Indicative ### Grant Amount ($) | ### Indicative Co-financing ### ($) |
| Development of natural resource valuation tools |  | Decisions to protect the global environment are better enabled | • Expert review of lessons learned and best practices on natural resource valuation • A set of tools to value environmental goods and services developed • Inter-agency collaboration to institutionalize natural resource valuation • Resource valuation tools are integrated into decision-making processes |  | 159,000 | 100,000 |
| Capacities to use natural resource valuation tools |  | Technical and management staff sufficiently trained in the use and application of natural resource valuation tools, and decision-makers fully aware of the value of natural resource valuation tools | • Development of pilot site demonstration project • Natural resource valuation tools and techniques piloted in one site/sector • Lessons learned and best practices documented to refine piloted natural resource valuation tools • Introduction of tested natural resource valuation tools into the screening process of sectoral strategies and plans • Proposal to integrate guidelines on natural resource valuation into relevant legislation and/or regulation • Development of proposals to integrate natural resource valuation tools into training courses and programmes • Sensitization workshops • Agreed approaches and methodologies to apply natural resource valuation tools in training and education curricula • Methods and recommendations for applying natural resource valuation criteria and tools published |  | 300,000 | 500,000 |
| Subtotal |  |  |  |  | 459,000 | 600,000 |
| Project Management Cost (PMC) |  |  |  |  | 41,000 | 50,000 |
| Total Project Cost |  |  |  |  | 500,000 | 650,000 |

- Indicative Co-financing for the project by source and by name if available, ($)

| Sources of Co-financing | Name of Co-financier | Type of Co-financing | Amount ($) |
| --- | --- | --- | --- |
|  | Ministry of Environmental Protection/ |  | 500,000 |
|  | Ministry of Environmental Protection/ |  | 100,000 |
| GEF agency | UNDP | In Kind | 50,000 |
| Total Cofinancing |  |  | 650,000 |

- indicative trust fund  Resources ($) Requested by Agency, Focal Area and Country1

| GEF Agency | Type of Trust Fund | Focal Area | Country Name/Global | Grant Amount ($) (a) | Agency Fee ($) (b)2 | Total ($) c=a+b |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Kazakhstan | 500,000 | 47,500 | 547,500 |
| Total Grant Resources |  |  |  | 500,000 | 47,500 | 547,500 |

1  In case of a single focal area, single country, single GEF Agency project, and single trust fund project, no need to provide information for   
    this table. PMC amount from Table B should be included proportionately to the focal area amount in this table.

2   Indicate fees related to this project.

- Project preparation grant (ppg)

Please check on the appropriate box for PPG as needed for the project according to the GEF Project Grant:

Amount                         Agency Fee

Requested ($)	      for PPG ($)

- No PPG required.                                           		       ___-- 0--________       _  --0--_______

- (upto) $50k for projects up to & including $1 million	       ___25000________      ___2375_____

- (upto)$100k for projects up to & including $3 million      ___     ________      ___     _____

- (upto)$150k for projects up to & including $6 million      ___     ________      ___     _____

- (upto)$200k for projects up to & including $10 million   ___     ________      ___     _____

- (upto)$300k for projects above $10 million     	       ___     ________      ___     _____

PPG  Amount requested by agency(ies), focal area(s) and country(ies) for MFA and/or MTF roject only

| Trust Fund | GEF Agency | Focal Area | Country Name/ Global | (in $) |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | PPG (a) | Agency Fee (b) | Total c = a + b |
|  |  |  | Kazakhstan | 25,000 | 2,375 | 27,375 |
| Total PPG Amount |  |  |  | 25,000 | 2,375 | 27,375 |

MFA:  Multi-focal area projects;  MTF:  Multi-Trust Fund projects.

part ii:  project JustiFication

Project Overview

- A.1. Project Description. Briefly describe the project, including ; 1) the global environmental problems, root causes and barriers that need to be addressed; 2) the baseline scenario and any associated baseline projects, 3) the proposed alternative scenario, with a brief description of expected outcomes and components of the project, 4) incremental cost reasoning and expected contributions from the baseline , the GEFTF, LDCF/SCCF and co-financing; 5) global environmental benefits (GEFTF, NPIF) and adaptation benefits (LDCF/SCCF); 6) innovativeness, sustainability and potential for scaling up

# The global environmental problems and root causes

# Kazakhstan inherited significant environmental concerns related to past military nuclear testing programs, industrial and mining activities, as well as land degradation, desertification, and water scarcity problems. Air and water pollution are a significant environmental concern in Kazakhstan.

# As the site of the former Soviet Union's nuclear testing programs, areas of the nation have been exposed to high levels of nuclear radiation, and there is significant radioactive pollution. The nation also has 30 uranium mines, which add to the problem of uncontrolled release of radioactivity.

# The country accumulated over 100 million tons of solid domestic wastes, over 23 million tons of industrial wastes, including 12 technogenic mineral formations. They contain solid organic polluters: chrome and heavy metals, such as lead, cadmium and zinc. Nineteen oil fields with 1,485 wells are located in the storm surge flood areas of the Caspian Sea, of which 90 wells are in constant floods area. This poses a serious threat for the sea as the country has no clear understanding of ways to fighting possible oil spills at the Caspian Sea. Moreover, there is no integral and integrated monitoring system to reflect the current pollution load and track levels of biodiversity and water quality degradation at the Caspian Sea. Finally, the country lacks professionals capable of ensuring ecological security at industrial facilities.

# Air pollution in Kazakhstan is another significant environmental problem. The air is annually polluted with 3 million tons of industrial wastes from 42 major companies. This is 65 percent of all the emissions in Kazakhstan. All this is apart from cars emissions that are heaviest in Almaty and Shymkent. Acid rain damages the environment within the country and also affects neighboring countries. Kazakhstan has the seventh most carbon-intensive economy in the world, emitting about 1,200 tonnes of CO2 equivalent per million dollars of economic output, as compared with a world average of about 500 tCO2e per million dollars.

# Wastes recycling remains at the low level, despite of the annual growth of the wastes volume. Only 20 percent are utilized, whereas in developed countries 30 percent of waters are recycled. Over 2.5 million tons of sewage waters are discharged into the country’s rivers annually. For many regions of Kazakhstan this makes the access to fresh water particularly challenging.

# Mismanagement of irrigation projects has caused the level of the Aral Sea to drop by 13 m, decreasing its size by 50%. The change in size has changed the climate in the area and revealed 3 million hectares of land that are now subject to erosion.

# Desertification is becoming another disaster for Kazakhstan. Degraded and deserted lands make around 70 percent of the country. As stated by the Ministry of Environment (2012), 26 million hectares out of 188 million hectares of lands have reached the extreme form of degradation, which is an irrecoverable damage to the nature. Unsustainable farmining practices, extensive resource use and overgrazing are by far the leading causes of land degradation and wildlife habitat degradation in the country.

# According to the 4th National Report to the Convention on Biodiversity Conservation, major threats to degradation of habitats and ecosystems as well as to the extinction of species come from human disturbances. These include the destruction of natural ecosystems, unsustainable use of biological resources, unsustainable agricultural practices (overgrazing, irrational hay cutting), chemical and radioactive contamination of soil and water, violation of the hydrological regime of rivers and lakes caused by regulation of river flow, poaching, trading of species under the threat of extinction, uncontrolled introduction of alien species of plants and animals, unauthorized felling of trees and shrubs.

# Kazakhstan has unique opportunities for the "green economy" development.  Current economic growth in Kazakhstan is mostly focused on the quantity to the detriment of the quality.  In particular, due to the rapid industrial development the ecological system in the country is fast degrading.   The general value of the country is falling down with the depletion of the natural capital.  At the World Summit “RIO+20” Kazakhstan suggested the programme “Green bridge” and the concept of the global, energy and ecological strategy. The President of Kazakhstan tasked the government to make a move over to a “green” economy by 2050 and the green economy strategy is to be developed by August 2013. The strategy will be primarily aimed at resolving many social and ecological issues. It will focus on increasing economic indicators and improving welfare of people with low use of non-renewable energy resources and renewable natural resources. The following priority sectors of the green growth are outlined: agriculture, transport, waste & water management, urban planning, industry (including mining), extraction and use of natural gas, construction and power production.

# The baseline scenario, associated baseline projects and barriers to be addressed

# The Ministry of Environmental Protection (MEP) is the central executive agency in charge of environmental protection and is responsible for implementing multilateral environmental agreements, national environmental policies, monitoring, environmental impact assessments, and enforcement.  The Sustainable Development Council (SDC), comprised of representatives from government, private sector, research institutions and NGOs is among a number of structures and mechanisms to implement the Rio Conventions.  The SDC bases its activities on inter-agency cooperation with the aim of catalyzing the integration of economic, social, and environmental policies to achieve sustainable development.

# Kazakhstan’s growing economy has led to the planning and implementation of large-scale projects in many of the economic sectors, most, if not all, of which did not sufficiently take into account Rio Convention obligations in their planning phase. As a rule, economic considerations are the primary criteria for deciding the legitimacy and value of development projects, thereby minimizing associated environmental impacts.  Decision-makers lack knowledge of the entire range of project impacts and benefits including, for instance, benefits from adaptation to climate change, social impacts of soil degradation and biological diversity.

# Though available, the scientific knowledge available in Kazakhstan is not adequately incorporated into the development of innovative practices, partly because key agencies do not share a common understanding of how to use scientific knowledge to formulate environmentally sound and sustainable policies, plans, and projects.   This is exacerbated by the institutional challenges of Kazakhstan’s public administration, which seriously limits transparency and collaboration. Although Kazakhstan is undertaking important steps to meet global environmental commitments, concern remains that the measures and initiatives currently underway and planned are neither sufficiently comprehensive nor innovative.

# In 2006, the NCSA identified Kazakhstan’s legal and regulatory framework as being critically deficient in its limited economic incentives for meeting MEA obligations. The NCSA recommended the development and use of tools that could identify and measure environmental and economic costs and values for decision-making on development plans, programmes and projects.  Under the business-as-usual scenario, the current ad hoc management of international obligations will continue.  Even though the necessary legislation and regulation are in place, they are not supported by the practical procedures and working methods needed for an integrated and broad implementation of these conventions.  Although resource saving is a declared principle in key instruments, e.g., the Environmental Code of Kazakhstan and Law on Energy Saving, these do not adequately take a holistic approach to sustainable development or demonstrate their contribution to meeting global environmental commitments.

# Baseline programs: Under the baseline situation, the Government will be pursuing a number of programs that have a bearing on effective natural resources management.

# The chief among these is the Natural Resources Program (henceforth referred to by its name in the Kazakh language, Zhasyl Damu) for 2010-2014 with an approved budget of US$ 1,405 million. Zhasyl Damu is coordinated by the MEP, who is also the proponent and the national executing agency of this GEF proposal. The overall objective of the program is to cover basic investment costs for protection of the country’s environment and for rehabilitation of degraded sites. This umbrella program includes the following ongoing government programs: the Concept of Environmental Safety for 2004-2015; Expansion and creation of Protected Areas (PAs) in Kazakhstan till 2030; a sectoral program “Environmental protection of the Republic of Kazakhstan for 2008-2010; and the program on protection and sustainable use of wildlife and expansion of PAs till 2010. Originally, the idea was to devise a unified and coordinated cross-sectoral approach to environmental management and protection in the country with financial contributions from various government agencies and institutions. Rather, the Zhasyl Damu program represents a compilation of ad-hoc and fragmented government actions with major government financing being diversted for large-scale infrastracture projests like hydropower stations and dams--the very necessity and cost-effectiveness of which are questionable in the first place. The program lacks an overall strategic vision and adequate government financing for projects that can potentially be environmentally and economically sustainable. Finally, the program provides no tools for assessing environmental, social and economic values of proposed projects.

# The two important programs that focus on the country’s development are the Kazakhstan’s 2020 Strategic Plan for Development and State Program for Forced Industrial Innovation Development for 2010-2014. The former calls for accelerating technological improvements in order to reduce greenhouse gas emissions, the introduction of green policies, and undertaking economic reforms in support of a low-carbon economy. The latter is aimed at ensuring sustainable and balanced economic growth in the country with regard to different priorities including the need for environmental protection and rational management.

# Another government program of relevance to this project is the Territorial Development Strategy to 2015, which seeks to improve the ecological status of administrative territories and contribute to environmental security by ensuring environmental sustainability and reducing the environmental burden on the environment. The territorial development strategy outlines the needs to develop a methodology for determining payments for environmental pollution and to develop measures encouraging the use of energy efficient and resource-saving production technologies.

# These programs in the baseline scenario are significant insofar as they provide a framework for socio-economic development of the country while addressing some of the global environmental issues. These programs may sound perfect on paper but when it comes to implementation on the ground they contain no methodology and tools for assessing cost-effectiveness as well as social and environmental values of proposed projects and available alternatives. Moreover, government employees at the national and local levels have little or no understanding of how these tools can be used to formulate environmentally and economically sound policies/projects/programs.

# The long-term solution to addressing major causes of environmental degradation needs to take an improved and more strategic approach to decision-making related to fulfilling the country’s national obligations under global environmental agreements. The solution relies on two key elements. The first element relates to the creation of a set of natural resources valuation tools applicable to Kazakhstan settings to be integrated into decision-making on development projects that generate global environmental benefits. The second approach relies on (i) enhanced capacities of technical and management staff of relevant government agencies and institutions on the use and application of natural resources valuation tools as well as on (ii) increased awareness of decision-makers of the importance and practical value of valuation tools for a more accurate representation of the costs associated with development projects in their respective sectors. The two important barriers to the long-term solution and meeting Rio Convention commitments are described below.

# Lack of economic incentives:  Kazakhstan does not effectively employ economic incentives to conserve biodiversity, catalyze sustainable land management, assess vulnerability to the impacts of climate change, or encourage measures to mitigate the negative impacts of climate change.  Economic leverage is based on fees for the use of natural resources, notably land and wildlife.  However, users appear to prefer a pay-as-you-go approach rather than being taxed in advance, the relatively meager contributions of which are currently deposited into a national environmental trust fund.  As a result, there is little funding generated to promote the use of more effective technologies and approaches. Kazakhstan’s administrative mechanisms and regulatory instruments relevant to economic development, as well as the compensation and rehabilitation mechanisms incentives do not adequately incorporate environmental considerations and are poorly understood.  There is an underlying skepticism related to quantifying economic benefits from environmental goods and services.

# Lack of capacity, tools and data:  Decision-makers in key sectors, especially those not collaborating closely with the MEP, have little understanding of how their own work influences the achievement of convention obligations. There is little understanding of how to determine (global) environmental indicators, value natural resources, and calculate socio-environmental risks of environmental degradation.  The system for accounting the contribution of different sectors and activities towards meeting the commitments under the Conventions is weak. Data needed to estimate the economic value of environmental goods and services is either non-existent or outdated.  Frequent reforms and changes in government agencies lead to a loss of institutional memory.  Even though there are a number of scientific and research institutes involved in the assessment of environmental trends and values, limited knowledge is shared across sectors and among experts.

# The Proposed Alternative Scenario with a brief description of expected outcomes and components of the project:

Component 1. Development of natural resource valuation tools for the global environment.

Kazakhstan has not yet linked the value of natural resources and ecosystem services to its own national development goals, including the fight against poverty, natural resource management and sustainable livelihoods. Through this activity, the project will be able to demonstrate the benefits and values of natural resources at a national level, and better link ecosystems and priority sectors in national development plans, in order to guide allocation of resources.

Under Component 1, the development of a set of natural resource valuation tools associated with ecosystem functions and services, natural resource commodities, opportunity cost of environmental damage arising from land degradation, among others. This involves the development of tools to create this data.

The project will focus on a review and preliminary analysis of existing natural resource valuation tools for the economic valuation of sectoral and cross-sectoral programmes, strategies, projects and initiatives. This will include a review of national and international experience on natural resource valuation applicable to meeting global environmental objectives in order to identify and structure the types of expert analyses needed to develop natural resource valuation tools and their corresponding guidelines.  The specific natural resource valuation tools will be identified and a feasibility study undertaken. Project activities will also include identifying and creating the best appropriate consultative mechanism to catalyze collaboration and decision-making needed to institutionalize natural resource valuation tools, resulting in preliminary agreements on the key modalities for their application, adoption and enforcement. The project will work within the framework of the Government’s current program under Zhasyl Damu (2010-2014), by supporting the development and implementation of the approaches to value environmental goods and services components of the program. It will also lay the groundwork for the next phase of Zhasyl Damu (2015-19). The Committee on Forestry and Hunting (CFH) will lead this component, in cooperation with regional and local authorities. The output is described below.

Output 1.1 Decisions to protect the global environment are better enabled

Expert review of lessons learnt and best practices on natural resources valuation will be conducted. Natural resource valuation tools will be developed for the Kazakhstan context, building upon existing models and lessons learned elsewhere. Building upon the field of ecological economics and a wide range of approaches to undertake economic valuation, natural resource valuation tools are a set of decision-makers must recognize that certain approaches may be more appropriate than others, depending the natural resource or environmental function assessed. Resources valuation tools are integrated into decision-making process.  Non-use values will play a key role in natural resource valuation, facilitating decision-making on natural resource conservation, evaluation of restoration alternatives, and determining compensatory packages for damages sustained as a result of natural resource and environmental degradation. Interagency collaboration to institutionalize natural resources valuation will be recommended.

Component 2. Capacities to use natural resource valuation tools.

The second component is improving the decision-making process by using data and information on the economic and financial value of ecosystem functions and services within the framework of EIAs. This is largely directed towards developing the human and institutional capacities to manage natural resource valuation tools and the actuarial data produced thereof.

A second part of this component involves the set of training needs associated with the development and piloting of natural resource valuation.  To this end, the set of training and public awareness activities to be undertaken during the project, building upon similar existing training programmes in order to ensure synergies and cost-effectiveness.  This will also include an opportunities to develop training courses in professional research centers and academia.

Output 2.1 Technical and management staff sufficiently trained in the use and application of natural resources valuation tools, and decision-makers fully aware of the value of natural resources valiation tools.

Pilot project will be developed and implemented to test natural resource valuation in a site of joint significance to the CBD, CCD. An in-depth and balanced analysis of proposed development and alternatives are presented to the stakeholder consultation process (public review of proposed development). Lessons learned from the pilot project documented and utilized to institutionalize the use of natural resource valuation within the EIA process. Recommendations for the development of SEA implementation guidelines provided. Analysis of the pilot project provides the basis for the review and reform of socio-economic policies in terms of their environmental implications/impacts (as part of the development of SEA' implementation guidelines under the Green Economy Strategy).

Specialized expertise will be hired to develop an implementation plan for undertaking a pilot EIA that includes the use of natural resource valuation tools and techniques. Regular meetings will be undertaken with development and planning agencies to identify and negotiate modifications to existing decision-making and approval processes, building upon lessons learned from the implementation of the EIA and new natural resource valuation tools and techniques.

The project will provide develop a training programme to impart specialized skills on the using natural resource valuation skills, as well as training to government on the interpretation of natural resource valuation data and information. Awareness raising workshops for policy-makers and other relevant stakeholders will also be held to impart the need to incorporate natural resource accounting into the national programme/plans. This output is critical to the institutionalization of natural resource valuation, as well as the sustainability of project benefits.

Training modules for undertaking natural resource valuation will be strengthened and/or created as part of course offerings at the level academic institutions. Specialized expertise will be hired to develop an educational programme to natural resource valuation.  The project will provide training as a first priority to professionals (e.g., ecologists, economists) currently working in the area of environmental impact assessments.

Awareness raising workshops will be targeted to policy-makers, politics, private sector representatives, non-governmental organizations. Policy-makers are a critical target audience since they play a key role in supporting the policy, regulative and institutional framework for natural resource valuation, EIAs and SEAs.

Project Preparation Phase and Its Outputs

The purpose of the PPG is to develop and validate the GEF project strategy.  The MSP document will include a detailed budget, GEF incremental cost analysis and log frame analysis that defines the project goal, objective, outcomes, outputs, including verifiable performance and output indicators and targets, means of verification.  The PPG will complete the Capacity Development Scorecard and develop a replication strategy for project activities.

Activities undertaken during the preparatory phase will include collecting information on the existing natural resource valuation tools for the economic valuation of sectoral and cross-sectoral programmes, strategies, projects and initiatives, and identifying and filling key gaps to strengthen the strategic design of the GEF project.  This information is a central to ensuring that the resource valuation tools selected and applied in Kazakhstan will catalyzed improved decision-making for the meeting global environmental objectives.

Project preparatory activities will include an analysis and consultations of best practice implementation arrangements as a GEF project. Donor agencies will be actively consulted as partners in development in the strategic design and implementation arrangements, securing the necessary partnerships and co-financing necessary to making this project viable, legitimate, and cost-effective.

Identification of the targeted stakeholder groups and their representatives will be undertaken through an open consultative process to re-affirm and strengthen their commitment to the GEF project objectives and goals.  Consultations will be undertaken with key representatives of stakeholders in the implementation of the Rio Conventions, including focus group discussions and individual interviews with key informants to assess the key drivers and barriers to decision-making on environmental policies, both of national and global priorities.  Consultations will ensure that the representatives consulted represent the full range of views so as to ensure an appropriate holistic construct and legitimacy of the recommended project strategy and approach.

In order to ensure replicability and sustainability of project outcomes, preparatory activities will include the identification and development of measurable indicators within a broader framework of monitoring and evaluation in order to assess project performance towards meeting immediate objectives. Outcome indicators will also be developed to the extent possible, with performance indicators used as proxy outcome indicators, as appropriate.  These will be used for the MSP logical framework, complementing the Capacity Development Scorecard.

The formulation of this project will be based on best practices for GEF cross-cutting capacity development projects.  In particular, lessons learned from the similar GEF-funded project on natural resource valuation currently under implementation in Jamaica will be taken into account.  The PPG's GEF grant and co-financing will cover the costs of the following preparatory activities:

Key PPG outputs include:

(i) Secure government commitment to project strategy: Negotiate with key government representatives to ensure full agreement on the project objectives, outcomes, outputs, and activities, including partnerships for support and government co-financing.  Agree on mechanisms and measures to ensure accountability of project partners.  Undertake an analysis of the financial implications of the project strategy and activities to construct a budget, and consult with key government representatives to identify sources of funds from among potential national, regional, and international donors.

(ii) Secure government commitment to project implementation arrangements: Undertake consultations with key government representatives to secure agreement to the detailed arrangements to execute project activities, including the roles, responsibilities, and accountabilities of lead and partner agencies, and the policy guidance to be provided by the Project Steering Committee.  Implementation arrangements are to be negotiated and agreed upon by UNDP and MEP, following to UNDP implementation guidelines.

(iii) Secure bilateral and multilateral financing opportunities: Develop partnerships and co-financing opportunities with bilateral and multilateral donor agencies and organizations, including networking among other potential regional and international development organizations.  A donors’ roundtable will be convened towards the end of the project development phase to finalize donor and partner commitment to the proposed project.  A resource mobilization strategy will be prepared that outlines the near-term financing of the project, and will form the basis of the long-term strategy to achieve financial sustainability.  Negotiated partnerships with on-going projects to re-align their activities to meet project objectives will be considered as co-financing, whereas related activities that will contribute to the institutional sustainability and resilience of project outcomes will be considered as parallel financing.

(iv) Definition of a Monitoring and Evaluation (M&E) Plan: A detailed M&E work plan and delivery strategy will be defined, including clear identification of responsibilities and accountabilities, as well as an appropriate budget allocation (based on best practices and UNDP guidelines).  The Plan will reflect the requirements of the GEF M&E Policy and Capacity Building M&E framework.  The Plan will include qualitative and quantitative performance and output indicators that will measure the state of the absorptive and adaptive capacity at various stages of project implementation.  The Plan will also include provisions for an independent evaluation and provision to ensure the learning of lessons from implementation at both the mid-point and termination of the project.

(v) Capacity Development (CD) Scorecard (GEF Tracking Tool): The methods set out in the Monitoring Guidelines of Capacity Development in GEF projects will be incorporated into the project framework and its overall M&E plan.  These methods include the use of a Capacity Development (CD) Scorecard, which was developed specifically for the Cross-Cutting Capacity Development (CCCD) projects and which build upon recent work on capacity and capacity development from the GEF, its Implementing Agencies, and from external research. The CD scorecard uses indicators and their corresponding ratings in order to quantify the qualitative process of capacity change, and will be applied as a three-point time series programme evaluation of how the project contributes to CD outcomes. CD ratings for all 15 indicators will be assessed by stakeholder participants during the inception workshop, and by the independent evaluation consultant(s) as part of the mid-term and final evaluation. Incorporating this CD framework into project design, implementation, and monitoring will provide a comprehensive monitoring framework aimed at assessing the range of needed capacities to achieve global environmental outcomes and ensure their sustainability, i.e., global environmental sustainability.

(vi) Sustainability Plan: Building on the M&E plan, the Sustainability Plan will outline an exit strategy that allows for those project activities necessary to sustain outcomes will continue without the need of long-term international financing.  This plan will also outline an approach of adaptive collaborative management to facilitate the necessary management changes agreed by representatives of key stakeholder groups to sustain and replicate project outcomes.

(vii) Medium-Size Project Guidelines: Review guidelines for the preparation of a Medium-Size Project based on GEF and UNDP requirements, as well as best practices for the holistic design of a resilient project that takes an adaptive collaborative management approach.  Standard UNDP reporting, monitoring and evaluation procedures will apply to this project and will be elaborated in the project document.

(viii) Final stakeholder validation workshop: The workshop will gather representatives from all relevant stakeholders of decentralized environmental management to present the final draft MSP.   The workshop will seek to further legitimize the project strategy and activities, and maintain the full engagement of stakeholders throughout the project development process and onwards to the implementation phase.

(ix) Official letters of endorsement and donor financing commitment: Official letter of endorsement from the GEF Operational Focal Foint as well as letters of commitment from donor partners.

Technical assistance will be required by national and international consultants who are experienced in: a) GEF project formulation; b) UNDP project implementation requirements; c) Rio Convention interventions; d) capacity development for environmental sustainability; and e) public administration and institutional analysis.  The final product of the proposed PPG phase will be a UNDP/GEF compliant medium-sized project document for submission to UNDP and GEF.

# Incremental Cost Reasoning and Co-financing:

# The above-described alternative scenario funded by GEF and co-financing resources is expected to result in key modifications to the baseline scenario that will generate global environmental benefits. A comparison of the baseline project with GEF-project scenarios and associated global benefits are presented below.

# By contributing to the development of the green economy strategy with a set of tools for natural resources valuation and by testing the use and applicability of selected tools in a pilot project, the government will have readily-available instruments for sound decision-making across all sectors of the economy that take into account environmental concerns. Moreover, the legal environment will be amended to promote wide application of such instruments in the country. As a result, the government will have a common understanding of and skills for how to use valuation tools in devising and screening for environmentally and economically justified policies/projects that—in addition to economic and social values—will generate global environmental benefits.

# By increasing the knowledge of decision-makers as well as of technical and management staff on the importance of attaching economic value to ecosystem functions, and providing them with the necessary capacities to conduct such valuations, decision-makers will get a more accurate representation of the costs associated with development projects in their respective sectors. Global environmental benefits will be delivered by introducing tools and methodologies that produce more knowledge of global environmental values, allowing for a more holistic and institutionally sustainable approach to decision-making (in both the name of national socio-economic priorities as well as the global environment).

# The project will assess, pilot and develop capacities to apply targeted resource valuation tools as part of the decision-making and planning of environmental and sectoral development programmes, plans, and projects.  Resource valuation tools that could be applied to the global environment will be identified and a pre-feasibility study undertaken during the project preparation phase. The project will support work in pilot sites where local governments are supportive of this approach, laying the groundwork for a major focus of discussion on nature resources finance. The project will strengthen key public administrative structures and mechanisms in such a way that will allow for the institutionalization of resource valuation tools.  This means clarifying, strengthening and streamlining decision points for the global environment (i.e., who, when and how to apply resource valuation criteria to different planning stages, such as conceptual designs, feasibility studies, environmental impact assessments, and committee decisions) that will result in improved inter-agency coordination and collaboration.

# Global Environmental Benefits:  The opportunities to achieve Rio Convention objectives will be improved through better knowledge of global environmental values, new tools and methods that encourage rational decision-making, as well as increased awareness and technical knowledge of the opportunity costs stemming from integrating Convention objectives into development sectors.  The project will develop and manage a website to promote its innovative work that will represent an important contribution to the global community to help meet Rio Convention objectives.

- Natural resource valuation tools specific to the global environment will be coupled with existing sets of environmental and socio-economic criteria and incentives, including economic instruments, within planning and decision-making processes that govern sectoral development and natural resource management.  Development plans, programmes, and projects are required to contain an expert and standardized economic valuation of the global environmental benefits that are expected to be lost or gained;

- The institutionalization of natural resource valuation tools in cross-sectoral collaboration and coordination among agencies and departments will contribute to more informed and balanced decision-making on development and global environmental priorities;

- Improved understanding among individual and institutional decision-makers and stakeholders of the principles and methodologies to apply and integrate economic valuation of the global environment into development programming and planning processes.

# Benefits at the national level will include enhanced technical capacities among key national authorities, as well as stakeholder groups that include decision-makers and technical advisors across sectors.  Stakeholders, including civil society, will gain a better appreciation that planning decisions are based on more objective criteria and methodologies that place a greater value of the socio-economic risks associated to global environmental impacts, such as droughts and floods.  The piloting of natural resource valuation to be undertaken within the project will thus explicitly pay attention to the indirect socio-economic benefits that can be achieved through conducting proper environmental assessments and using them as the basis for decision-making.  Improved tools and methodologies to reflect global environmental values will produce improved decision-making that meets both global environmental commitments as well as national development priorities.

# Gender will be included into the economic valuation framework, as numerous negative social outcomes associated with environmental degradation are experienced by women, with many more unaccounted for.  By the very holistic nature of natural resource valuation, a life-cycle analysis will be among the early set of natural resource valuation tools, allowing for gender variables to be factored into the econometric calculations along side of valuation estimates of global environmental benefits.  As part of the project implementation arrangements, directed attention will be paid to ensuring an appropriate gender balance in the training and capacity development activities.

# Co-financing: The GEF contribution has leveraged a 1:1 ratio of co-financing to strengthen technical and institutional capacities to make more informed decisions to achieve and sustain global environmental objectives within the framework of national development policies.  Additional parallel financing can be also found through a range of other related projects and initiatives, such as the UNDP/MEP project to integrate climate change priorities into national strategic planning. During the project preparation phase, further consultations will identify those on-going projects and initiatives that can be strategically linked to this project.

# Co-financing will be targeted to the identifying and assessing the types of environmental and sustainable development benefits of national priority, with the GEF contribution building upon this to identify global environmental benefits.  Co-financing will also be used to strengthen the existing methologies and tools used in decision-making on proposed developments, such as Environmental Impact Assessments, with the GEF increment used to tailor these to ensure that they adequately reflect global environmental priorities.  Co-financing will be used to improve the application analytical tools and methodologies, with the GEF increment use to catalyze the integration of resource valuation of global environmental benefits within decision-making and planning processes.  Project activities will also build upon a number of on-going parallel government initiatives and other donor-funded initiatives, adding to the project's cost-effectiveness.  A detailed justification of the project’s cost-effectiveness will be provided in the MSP.

# Innovativeness, sustainability and potential for scaling-up:

The green economy strategy—that is being currently developed—will set a constructively new path for the country’s development with enhanced quality of life for its citizens and economic benefits to the society as a whole. In the first time, Kazakhstan will be exploring the relationship between environmental and economic benefits resulting from effective management of nature resources. This is totally innovative to the country in terms of understanding full impacts of this policy instrument. Moreover, this project will be exploring opportunities and challenges of some financial intruments, particularly the Real Options Approach to Valuations, that will promote financial innovation, thus contributing to economic stability.

Making the economic valuation of natural resources a unified system of public valuation tools, as part of the green economy strategy, will result in effective use of natural resources across all sectors of the economy—thus contributing to sustainability of government programs/projects. Once piloted, tools for valuation of natural and environmental resources will be included into the green economy strategy as a key benchmark for selecting one policy/project vis-à-vis other available alternatives, thus making it a common practice in the public sector with high potential for scaling up across national and local governments. This will also result in the financial and institutional sustainability of the project’s results given that the project will contribute to on-going government efforts in devising a green development strategy which will have a secure government financing.

# Sustainability of the project results will also stem from enhanced capacities of decision-makers as well as technical and management staff in the government on natural resources valuation tools, the use of which will be scaled up from pilot application to development projects/programs across all sectors of the economy.

Important too, the green economy strategy advances the use of a bottom-up approach to generating policies/programs that best respond to local needs and address local concerns given an overall “green growth” framework. As such, equipping local stakeholders with most advanced valuation tools for decision-making will ensure sustainability of government activities at local levels.

# A.2. Stakeholders. Identify key stakeholders (including civil society organizations, indigenous people, gender groups, and others as relevant) and describe how they will be engaged in project preparation:

# In addition to government partners outlined in B.6 below, preliminary consultations have already identified the general groups of research and academic institutions, training centers, key government agencies, as well as business associations and key development practitioners to participate in the training programs as well as to deliver the courses and contribute to the preparation of the guidelines.   The further narrowing of the targeted groups and their representatives will be undertaken through an open consultative process during the preparatory phase to re-affirm and strengthen their commitment to project objectives and goals.  This includes the identification of relevant indigenous communities that may be project stakeholders as part of the site selection process when determining where to pilot natural resource valuation.

# A.3 Risk. Indicate risks, including climate change, potential social and environmental risks that might prevent the project objectives from being achieved, and, if possible, propose measures that address these risks to be further developed during the project design (table format acceptable):

| Risks | Impact & Probability | Mitigation |
| --- | --- | --- |
| Government agencies see natural resource valuation as an additional burden in the review and approval of plans, programmes, and projects. | Medium | Early consultations and negotiated agreements to ensure that key partners fully support the project strategy, objective and activities. All partners and stakeholder representatives will be fully involved and consulted during the project preparation and implementation phases, and will be requested to provide continual input and to endorse the selected project strategy, including pilot project to be valued. On-going feedback from agency staff will be solicited and integrated into modified approaches to promote the use of natural resource valuation tools. |
| Sectoral agencies show lack of cooperation initiative | Medium | The involvement of stakeholders from different sectors at an early stage will help strengthen the legitimacy and recognition of natural resource valuation as part of their work towards meeting common goals and objectives. |

# A.4. Coordination. Outline the coordination with other relevant GEF financed and other initiatives:

# This project has already benefited from national consultations on the strategic fit between project objectives and other GEF-funded initiatives.  The implementation of this project will take place under a national advisory mechanism through the MEP to ensure on-going coordination and adaptive collaborative management towards meeting national development priorities.  This includes:

# a) The MEP’s 2010-2014 Environmental Protection Action Plan, which includes important capacity building recommendations that are being coordinated through national coordinators and focal points, as well as cross-sectoral working groups and commissions.

# b) Kazakhstan’s 2020 Strategic Plan for Development (approved in February 2010 by order of a presidential decree), which calls for accelerating technological improvements in order to reduce greenhouse gas emissions, the introduction of green policies, and undertaking economic reforms in support of a low-carbon economy.

# c) Transition of Kazakhstan to Sustainable Development (approved in 2006 by order of a presidential decree), which proposes a range of economic measures to be taken in order to promote environmental sustainability, which includes the development of new tools for decision-making in order to implement sustainable technologies; implementing economic instruments for environmental protection (damage compensations and emissions compensation); including the full value of natural objects and ecosystem services when assessing economic performance; assessing emissions and sinks of natural systems; and introducing market mechanisms for environmental protection.

# d) Territorial Development Strategy to 2015, which seeks to improve the ecological status of territories and contribute to environmental security by ensuring environmental sustainability and reducing the environmental burden on the environment.  The territorial development strategy outlines the needs to develop a methodology for determining payments for environmental pollution and to develop measures encouraging the use of energy efficient and resource-saving production technologies.

# e) 2010-2014 State Programme for forced industrial innovation development.  This programme is aimed at ensuring sustainable and balanced economic growth in the country with regard to different priorities including the need of environmental protection and rational management.

# f) UNDP/MEP project on capacity building for sustainable development, which sets out to integrate climate change issues into the national and regional development policies. Within the framework of this project, intensified collaboration with the Ministry of Industry and New Technologies (MINT) is foreseen, beginning in 2011 on how to integrate low-carbon development with contrived industrial development

# The above-mentioned policies and strategic initiatives all underline the need to understand the socio-economic aspects of environmental systems, and to view sustainable development in a holistic manner. This project provides an excellent opportunity to strengthen the foundational capacities need to shift and sustain Kazakhstan’s development sectors to be environmentally friendly while as the same time meeting global environmental commitments.  Initiatives by other stakeholders such as the Ministry of Economic Development and Trade, the Ministry of Finance, the Ministry of Agriculture, the Ministry of Oil and Gas, the Ministry of Industry and New Technologies, the Land Management Agency, the Agency for Construction, Housing and Utilities and the Ministry of Education and Science, will also be taken into account.

This project represents a contribution to the fulfilment of Kazakhstan's 2010-2015 UN Development Assistance Framework (UNDAF), in particular Development Outcome 2 on Environmental Sustainability. This outcome calls for "communities, national, and local authorities [to] use more effective mechanisms and partnerships that promote environmental sustainability" (UNDAF, 2009:15).  Among the UNDAF priorities is the development of integrated services to bridge the gap between competitive industrial production and environmental concerns (UNDAF, 2009:17).  The integration and application of natural resource valuation with particular emphasis of global environmental benefits is one such important mechanism.  Kazakhstan's 2008 Country Analysis, prepared in fulfilment of the Common Country Assessment that analyzes the national development situation and identifies key development issues,  determined that the "United Nations is well-placed to contribute to environmental sustainability in Kazakhstan, in a gender-sensitive manner" (UN, 2008:34).

Critically, also, the project will build on the process currently being overseen by the Secretariat of the Convention on Biological Diversity (SCBD) through which countries are revising their National Biodiversity Strategy and Action Plans (NBSAPs) to tie in with the CBD’s Strategic Plan 2011-2020, providing policy-makers with a new vehicle and opportunity for promoting enhanced mainstreaming of biodiversity considerations in development planning, development finance and strategies aimed at managing climate risk. The project will be linked to the UNDP-supported GEF-financed project on supporting the “National Biodiversity Planning to Support the implementation of the CBD 2011-2020 Strategic Plan in Republic of Kazakhstan”.

Description of the consistency of the project with:

B.1 National strategies and plans or reports and assessments under relevant conventions, if applicable, i.e. NAPAS, NAPs, NBSAPs, national communications, TNAs, NCSAs, NIPs, PRSPs, NPFE, Biennial Update Reports, etc.:

Kazakhstan is a party to the three Rio Conventions on biodiversity conservation, climate change, and desertification and drought, among other multilateral environmental agreements (MEAs).  A number of national reports and communications were prepared, with the Third National Communication to the FCCC currently underway.  Kazakhstan’s National Capacity Self-Assessment (NCSA) undertook an analysis of the thematic and cross-cutting challenges, as well as identified priority capacity development needs.  Although the NCSA determined that the country has a relatively strong scientific capacity for implementing a holistic approach to environmental protection at the national level, an important weakness was the insufficiency of positive incentives to implement the Rio Conventions, among which is an economic assessment of implementing Convention provisions.  The valuation of the global environmental benefits using econometric criteria and standards will create a more equal playing field within governance and decision-making structures and processes to better meet Rio Convention objectives.

# B.2. GEF focal area and/or fund(s) strategies, eligibility criteria and priorities:

# The GEF strategy on capacity development serves to support countries' ability to meet and sustain Rio Convention objectives, i.e., to achieve global environmental sustainability.  Of the five objectives under the GEF-5 Capacity Development Results Framework (GEF/C.37/3), this project sets out to meet Objective 2, "Generate, access, and use of information and knowledge."  To this end, the project will develop and pilot the use of natural resource valuation tools in order to increase the value and legitimacy of global environmental goods and services, including their opportunity costs, in development planning processes.  The project will: a) increase the capacity of decision-makers and stakeholders to diagnose, understand, and transform the complex dynamic nature of global environmental problems in order to develop local solutions; and b) raise public awareness and improve management information systems.  Towards meeting these outcomes, the project takes a strategic approach to decision-making, one that is building on the innovative research that has been undertaken in academic institutions on the development of key econometric values of the key global environmental goods and services, as well as their testing and the application of natural resource valuation methodologies in select countries, including the GEF-funded and UNDP-implemented cross-cutting capacity development project in Jamaica.

B.3 The GEF Agency’s comparative advantage for implementing this project:

The Government of Kazakhstan has requested UNDP assistance in designing and implementing this cross-cutting capacity development project, taking into account UNDP’s proven track record of supporting similar projects in a number of other countries.  This request also stems from the successful implementation of Kazakhstan’s NCSA that was supported by UNDP.  The project will benefit from synergies and opportunities arising from an expanding portfolio of environmental projects implemented by UNDP. In particular, UNDP currently supports numerous national efforts to protect globally significant biodiversity as well as to address the threats of global warming and ozone depletion.  As a partner to the Central Asian Countries Initiative for Land Management (CACILM), UNDP implements and supports projects promoting sustainable land management.  A number of UNDP-implemented interventions promote the management of wetlands, mountain agro-biodiversity, and rangeland ecosystems.  They support improved energy efficiency in heat and water supply systems, and increased use of renewable energy sources.  UNDP has provided extensive support to the Ministry of Environment, the Committee for Water Resources, the Committee for Forestry and Hunting, and other government bodies, to develop strategic documents and legislation. UNDP has also assisted the country in the ratification processes of a number of international agreements.

# The UNDP Country Office will assign two staff members (both with Master’s degrees and cumulative 16 years experience in environmental management) to be responsible for the overall management and supervision of the project implementation. Implementation support will be provided by three staff members with a cumulative work experience of over 24 years at UNDP.

From the programme side the project will be under the overall supervision of the Head of the Energy and Environment unit, who has a M.Sc. in environmental management and 10 years of experience within the environmental field and in project implementation, more than half as director of the UNDP/GEF Small Grants Programme in Kazakhstan. He will be directly supported by an Environment Programme Analyst with a M.Sc. in chemical technology and 6 years of experience in the environmental field, with specific focus on environmental risk and impact assessments. Implementation support on Procurement, Finance and Human Resources will be provided by three staff members – Head of Finance Unit (BA, 10 years of experience in UNDP finance), Procurement Officer (BA, 4 years of experience in UNDP) and HR associate (MA, 10 years of experience in UNDP). These three staff members are directly supported and supervised by the Operations Manager (MA, 13 years of experience, of which 6 in UNDP).

part iii:  approval/endorsement by gef operational focal point(s) and GEF agency(ies)

A.   Record of Endorsement of GEF Operational Focal Point (S) on Behalf of the Government(S): (Please attach the Operational Focal Point endorsement letter(s) with this template. For SGP, use this OFP endorsement letter).

| Name | Position | Ministry | Date (MM/dd/yyyy) |
| --- | --- | --- | --- |
| Nurlan Kapparov | Minister of Environment Protection, GEF Operational Focal Point | MINISTRY OF ENVIRONMENTAL PROTECTION | 12/25/2012 |

B.  GEF Agency(ies) Certification

| This request has been prepared in accordance with GEF/LDCF/SCCF/NPIF policies and procedures and meets the GEF/LDCF/SCCF/NPIF criteria for project identification and preparation. |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Agency Coordinator, Agency name | Signature | Date (MM/dd/yyyy) | Project Contact Person | Telephone | Email Address |
| Adriana Dinu Officer in Charge UNDP/GEF |  | 06/11/2013 | Tom Twining-Ward UNDP/GEF Regional Technical Advisor (Green-LECRDS) | +421 2 59337 386 | Tom.twining-ward@undp.org |

Project ID number will be assigned by GEFSEC.

Refer to the reference attached on the Focal Area Results Framework and LDCF/SCCF Framework when completing Table A.

TA includes capacity building, and research and development.

To be calculated as percent of subtotal.

On an exceptional basis, PPG amount may differ upon detailed discussion and justification with the GEFSEC.

PPG fee percentage follows the percentage of the GEF Project Grant amount requested.

Part II should not be longer than 5 pages.

Ministry of Environment (February 2012): http://en.tengrinews.kz/environment/Environment-Minister-on-ecological-problems-of-Kazakhstan-7688/

Ibid

Climate Analysis Indicators Tool (CAIT) Version 6.0. Washington, DC: World Resources Institute, 2009 (2005 data).

Ministry of Environment (February 2012): http://en.tengrinews.kz/environment/Environment-Minister-on-ecological-problems-of-Kazakhstan-7688/

US$ 1,050 million is from the national budget and US$ 355 million from local budgets.