request for

Project Type:

Type of Trust Fund:

For more information about GEF, visit TheGEF.org

part i: project information

| Project Title: Integrating global environmental priorities into national policies and programmes |  |  |  |
| --- | --- | --- | --- |
| Country: | Kiribati | GEF Project ID: | 5130 |
| GEF Agency: |  | GEF Agency Project ID: | 4936 |
| Other Executing Partner(s): | Ministry of Environment, Lands and Agriculture Development (MELAD) | Submission Date: | 2014-07-02 |
| GEF Focal Area (s): |  | Project Duration (Months) | 36 |
| Name of Parent Program (if applicable): - For SFM/REDD+ - For SGP - For PPP |  | Project Agency Fee ($): | 47,500 |

- Focal Area Strategy framework

| ### Focal Area Objectives | ### Expected FA Outcomes | ### Expected FA Outputs | Trust Fund | Grant Amount ($) | ### Co-financing ### ($) |
| --- | --- | --- | --- | --- | --- |
|  | Outcome 2.1: Institutions and stakeholders have skills and knowledge to research, acquire and apply information collective actions. | 2.1: Institutions and stakeholders trained how to use different tools available to manage information 2.2: Stakeholders are better informed via workshops and trainings about global challenges and local actions required 2.3: Ability of stakeholders to diagnose, understand and transform information and knowledge into local actions increased 2.4: Public awareness raised through workshops and other activities |  | 232,500 | 240,000 |
|  | Outcome 5.1: Enhanced skills of national institutions to monitor environmental changes | 2.1: Monitoring systems established 2.2: Learning system established to provide feedback to policy, strategies and management decisions from evaluation reports 2.3: Capacities for monitoring of projects and programs developed |  | 225,028 | 220,000 |
|  | Project Management |  |  | 42,472 | 70,000 |
| Total project costs |  |  |  | 500,000 | 530,000 |

- Project Framework

| ### Project Objective: To improve information management and compliance monitoring in order to achieve global environmental benefits |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| ### Project Component | ### Grant Type | ### Expected Outcomes | ### Expected Outputs | ### Trust Fund | ### Grant Amount ($) | ### Confirmed Co-financing ### ($) |
| Component 1: Environmental Management Information System (EMIS) |  | Outcome 1: An operational Environmental Management Information System (EMIS) providing accurate and timely information | 1.1: An environmental data repository with standards, norms and protocols to collect, analyze, store and make available accurate, and reliable environmental information related to all three Rio Conventions, and of direct use by decision-makers 1.2: An information technology architecture in place to store, manage and provide public access to environmental information 1.3: Environmental information available and disseminated to stakeholders |  | 232,500 | 240,000 |
| Component 2: Environmental Indicators and Compliance Monitoring System (CMS) |  | Outcome 2: A Compliance Monitoring System (CMS) developed and tracking key environmental indicators | 2.1: An institutionalized set of environmental indicators 2.2: An operational compliance monitoring system |  | 225,028 | 220,000 |
| Subtotal |  |  |  |  | 457,528 | 460,000 |
| Project management Cost (PMC) (including Direct Project Cost: 972) |  |  |  |  | 42,472 | 70,000 |
| Total project costs |  |  |  |  | 500,000 | 530,000 |

- sources of confirmed Cofinancing for the project by source and by name ($)

Please include letters confirming cofinancing for the projeSct with this form

| Sources of Co-financing | Name of Co-financier (source) | Type of Co-financing | Co-financing Amount ($) |
| --- | --- | --- | --- |
|  | MELAD |  | 320,000 |
|  | MELAD - ICCAI - SPREP Project |  | 30,000 |
|  | MELAD - KAPIII Mangrove Replanting |  | 150,000 |
|  | UNDP |  | 30,000 |
| Total Co-financing |  |  | 530,000 |

- trust fund Resources Requested by agency, Focal Area  and country1

| GEF Agency | Type of Trust Fund | Focal Area | Country Name/ Global | (in $) |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | Grant Amount (a) | Agency Fee (b)2 | Total c=a+b |
|  |  |  | Kiribati | 500,000 | 47,500 | 547,500 |
|  |  |  |  |  |  | 0 |
|  |  |  |  |  |  | 0 |
|  |  |  |  |  |  | 0 |
|  |  |  |  |  |  | 0 |
|  |  |  |  |  |  | 0 |
|  |  |  |  |  |  | 0 |
|  |  |  |  |  |  | 0 |
|  |  |  |  |  |  | 0 |
|  |  |  |  |  |  | 0 |
| Total Grant Resources |  |  |  | 500,000 | 47,500 | 547,500 |

1  In case of a single focal area, single country, single GEF Agency project, and single trust fund project, no need to provide information for this
    table.  PMC amount from Table B should be included proportionately to the focal area amount in this table.

2   Indicate fees related to this project.

- Consultants working for technical assistance components:

| ### Component | ### Grant Amount ($) | ### Co-financing ($) | ### Project Total ($) |
| --- | --- | --- | --- |
| ### International Consultants | 25,000 |  | 25,000 |
| ### National/Local Consultants | 90,000 |  | 90,000 |

- Does the project include a “non-grant” instrument?

(If non-grant instruments are used, provide in Annex D an indicative calendar of expected reflows to your Agency 
       and to the GEF/LDCF/SCCF/NPIF Trust Fund).

part ii:  project justification

A. describe any changes in alignment with the project design of the original pif

A.1 National strategies and plans or reports and assessments under relevant conventions, if applicable, i.e. NAPAS, NAPs, NBSAPs, national communications, TNAs, NCSA, NIPs, PRSPs, NPFE, Biennial Update Reports, etc.

1.  Environment has emerged as a Key Policy Area (KPA) of the Kiribati Development Plan (KDP) – the overarching national development plan - since 2008. Protecting the environment became one of the six key policy areas in the KDP 2012-2015. It is part of the national development priority that is to facilitate sustainable development by responding and mitigating the effects of global climate change and through approaches that protect island biodiversity and supports the reduction of environmental degradation. In order to implement this national development plan, the government of Kiribati has been developing/strengthening its environmental governance framework. In 2013, Cabinet approved the Kiribati Integrated Environment Policy (KIEP). It is intended to contribute to the review and revised targets and activities under the environmental key policy area of the KDP 2012-2015 and to set the direction towards building and enhancing the resilience of Kiribati, its local communities and people to respond to the impacts of global climate change. Among the strategic objectives of this policy, several of them are related to the current proposed project. They include: (i) to improve knowledge, information and national adaptive capacity for responding and adapting to climate change (as listed in the climate change theme); (ii) to enhance the storage, protection and dissemination of knowledge, and information to the general public on the conservation, sustainable use, and management of island biodiversity (as listed in the island biodiversity conservation and management theme); and (iii) to improve monitoring and management of data for MEAs and state of the environment reporting and make this available for national development policy and planning processes (as listed in the environmental governance theme).

2.  Currently, the government of Kiribati is also finalizing its Kiribati Joint Implementation Plan for Climate Change and Disaster Risk Management (KJIP). It is part of the commitments Kiribati made under the Pacific Islands Framework for Action on Climate Change, the Regional Framework for Action on Disaster Risk Management endorsed by the Pacific Leaders in 2005 and the Pacific Islands Meteorological Strategy approved in 2012. The goal of the soon-to-be approved KJIP is to increase resilience through sustainable climate change adaptation and disaster risk reduction using a whole of country approach; it will be achieved through 12 strategies. Similar to the KIEP, this plan is also linked to this project. Under its second strategy that is Improving knowledge and information generation, management and sharing, three results are anticipated: (i) An integrated and up-to-date national database providing all relevant information for resilient development is available and accessible for all; (ii) Capacities to communicate science and best practices are strengthened by developing and disseminating effective and relevant information, communication and awareness products for decision-making and awareness raising across sectors and at all levels; and (iii) Capacities for data collection, assessment, analysis, interpretation, monitoring and reporting are strengthened across sectors.

A.2. GEF focal area and/or fund(s) strategies, eligibility criteria and priorities.

3.  The PIF provides an accurate description of the Project’s alignment to GEF focal areas and strategies.

4.  Nevertheless, the expected FA Outcomes and Expected FA Outputs indicated in the PIF were not completed according to the GEF5 CCCD strategy. It is now corrected in the project document and above in Section A.

A.3 The GEF Agency’s comparative advantage:

5.  UNDP developed a sub-regional programme document for the region and for the same period as the UNDAF 2013-2017. This programme states that protection and conservation of the environment are ever more important because of the effects of climate change – such as rising sea levels – and ocean acidification, as well as large-scale forest logging, commercial agriculture and associated land clearing, which threaten the sustainability of natural resources. The marine environment is under threat despite the implementation of coastal management strategies, which severely affect the livelihoods of the island communities. One of the areas of this programme is “environmental management, climate change and disaster risk management”.

6.  Under this area, UNDP support will bolster the resilience of communities in the region to cope with climate change, and will implement strategies that integrate environmental management, climate change adaptation and mitigation, and disaster risk reduction. It will facilitate transition to ‘green’, low-carbon development through the mainstreaming of climate change into sectoral planning and national strategic development strategies, and through public expenditure and institutional reviews, as appropriate. The project will contribute to strengthening the management of the environment by developing the capacity of national key stakeholders involved in this area.

A.4. The baseline project and the problem that it seeks to address:

7.	The PIF provides a description of the baseline project and the problem to be addressed. This description is still valid and the project document expanded on it.

A. 5. Incremental /Additional cost reasoning:  describe the incremental (GEF Trust Fund/NPIF) or additional (LDCF/SCCF) activities  requested for GEF/LDCF/SCCF/NPIF  financing and the associated global environmental benefits  (GEF Trust Fund) or associated adaptation benefits (LDCF/SCCF) to be delivered by the project:

8.  This project takes an incremental approach from a GEF construct towards strengthening Kiribati’s environmental information management and knowledge to meet Rio Convention objectives.  In the absence of this project, the necessary capacity building to address the environment data needs of MELAD-ECD will remain an outstanding need at the national level in Kiribati. It would prevent Kiribati to achieve global environmental benefits through better environmental information. Government staff would remain insufficiently equipped and knowledgeable about how to develop, maintain and sustain an environmental management information system (EMIS) and a compliance monitoring system. More generally, they would also remain insufficiently knowledgeable to fully understand the implications of global environmental directives under the conferences of the parties on national environmental and development policies, and how these directives can be strategically implemented and supported through existing national information systems. Kiribari, as both a SIDS and a LDC, has many limitations including the small office with limited number of staff members in place who work at MELAD-ECD. At the same time, environment data are widely scattered and fragmented and the generation of environment data is also ad hoc at the country level; responding to reporting needs and not conducted on a regular basis. In most cases, environment data are produced when there are opportunities through externally funded projects. Under the GEF Alternative, the external resources will allow Kiribati to address this long outstanding environmental information need within MELAD-ECD. This GEF support is crucial to assist the Government of Kiribati in this important area at the country level.  Barriers identified through the NCSA process will be thoroughly re-assessed and effective and efficient solutions to address those related to the availability of environmental information will be detailed and implemented with the support of the project. The project will build on the existing baseline, seeking to improve the mechanisms and procedures in institutions responsible for environmental information management and to develop the capacity of the staff in these institutions in Kiribati.

Note that the expected outcomes and expected outputs in the project framework in the PIF (section B) were reviewed and revised, following the consultations conducted during the PPG phase. The changes are mostly a refinement of the project framework with no fundamental changes. These changes are reflected in section B Project Framework above and also in the Project Results Framework in the project document.

A.6  Risks, including climate change, potential social and environmental risks that might prevent the project objectives from being achieved, and measures that address these risks:

9.	An initial analysis of Risks was provided in the PIF in section B.4. This has been developed in the UNDP Project Document (Section C3c). The risks and assumptions are summarized in the following table.

| Risk | Level | Mitigation measure |
| --- | --- | --- |
| Political will to provide ECD with the necessary resources to sustain the EMIS and the CMS | Low | MELAD will support ECD and provide it with necessary resources |
| New information is not used and stays stored in computers at ECD | Medium | Better environmental information is readily available and actively utilized and used |
| Communications and national reports are not submitted on time | Medium | Communications/ reports are submitted on time and include information stored in the EMIS |
| Project activities and resources do not translate in increasing the capacity of ECD to provide better environmental information | Low | The project is effective in developing the capacity in the area of information management |
| Lack of relevant expertise in local market may result in delay of required outputs and distortion of targeted deadlines | Medium | Implementation of project activities and recruitment of relevant national expertise is monitored and actions will be identified if the lack of expertise is affecting the timely implementation of the project |
| Acquire inadequate hardware within the ECD context and the EMIS hardware requirements | Low | Specification requirements will be done carefully to identify the adequate hardware, communication and network equipment |
| Political will to accept sharing data among government institutions | Medium | Government will see the benefit of sharing data through cabinet support |
| No interest from decision-makers to use better environmental information | Medium | The benefit of using better environmental information will encourage decision-makers to use it Cabinet support is in place |
| There is no regional commitment to share environmental information | Low | Regional organizations will lead the sharing of environmental information |
| The government does not fulfill its international obligations; including those from the 3 Rio Conventions | Low | The government continues to fulfill its international commitments |
| Socio-economic pressures do not de-value environmental attitudes and concern | Medium | Survey results will show an increased awareness and understanding of the Rio Conventions’ implementation for decision-makers |
| New indicators are adopted but they require additional resources to be monitored; which might not be available | Medium | The government pursues its budget support to integrate the 3 Rio Conventions obligations into the Kiribati information management approach and monitoring system |
| New standards, norms and procedures are identified but might not be adopted by the Government | Low | The government pursues its policies to integrate the 3 Rio Conventions obligations into the Kiribati information management approach and monitoring system |
| The in-service training system for public servants might not be interested in integrating into its catalogue the training curricula developed with the support of the project | Low | The related in-service training institution(s) will be contacted early on to establish a partnership with the project and involved them in designing and delivering the course |
| No interest in better integrating environmental information in government decision-making | Low | There is sufficient commitment from decision-makers to maintain long-term support to public servant training in the environmental area, including MEAs implementation in Kiribati |

A.7. Coordination with other relevant GEF financed initiatives

10.  This project will make an important contribution to Kiribati's pursuit of low-emission and climate resilient development (LECRD). Specifically, this project will add value to existing environment projects that Government of Kiribati is implementing in Kiribati through MELAD-ECD such as the Implementation of Montreal Protocol on ODS, the International Climate Change Adaptation Initiative (ICCAI), the Urban Development Programme Project, the Kiribati National Biodiversity Strategies and Actions Plan, the Programme of Work on Protected Areas, the Phoenix Islands Protected Area (PIPA), to name a few. The ODS project promotes and support low emission in Kiribati while the latter projects simultaneously work to build and support a climate resilient environment in Kiribati. Building and enhancing the resilience of Kiribati to global climate change is critical and this project will add value to. Thus given the centralized nature of the EMIS, the project will build upon the multi-stakeholder consultation and participatory process created under the NCSA, and which embodies the first stage of UNDP's LECRD approach. The second LECRD phase is the preparation of climate change profiles and vulnerability assessments, which are being undertaken as part of Kiribati's SNC, and which also build upon the thematic assessments carried out under the NCSA. The EMIS will help to further institutionalize the data and information that went and goes into the preparation of these assessments and strategies, thereby reducing the transaction costs as well as reinforcing national capacities to develop and implement strategic options to pursue LECRD.

B. additional information not addressed at Pif stage:

B.1 Describe how the stakeholders will be engaged in project implementation. 11. During the project development phase, key project stakeholders were identified and consulted. Taking an adaptive and collaborative management approach to execution, the project will ensure that key stakeholders are involved early and throughout project execution as partners for development. This includes their participation in the Project Board, review of project outputs such as recommendations for amendments to policies, plans, programmes and legislation, as well as participation in monitoring activities. 12. Given the project strategy, the key project stakeholders are government ministries and their and departments that are mandated with the management of the environment in Kiribati. These stakeholder representatives will participate in activities to develop the EMIS and the CMS, which will be done as learn-by-doing exercises. In addition to these governmental stakeholders, the project will also actively engage non-governmental stakeholders from civil society organizations (CSOs), academia and private sector. They will be invited in project activities to share their comparative expertise, but also to undertake selected project activities, which will be determined during project implementation. 13. Key stakeholders include the Ministry of Environment, Lands and Agriculture Development (MELAD) and the Office of Te Beretitenti (OB). The project document provides additional information of who stakeholders will be engaged in project implementation, including a list of stakeholders expected to participate in the implementation of this project and their anticipated roles (see section C.4).

B.2 Describe the socioeconomic benefits to be delivered by the Project at the national and local levels, including consideration of gender dimensions, and how these will support the achievement of global environment benefits (GEF Trust Fund/NPIF) or adaptation benefits (LDCF/SCCF):

14.	  Full details on the sustainable development context in Kiribati are provided in the Project Document, section B2b.  Kiribati is an oceanic nation comprises 33 atolls spread out across a vast Economic Exclusive Zone area of 3.5 million square kilometers (13th largest in the world) with a total land area of just only 800 sq km. In 2010 the total population was 103,058, of whom 50.7% were female and 49.3% male. In all, 48.7% of the population lives in the capital of South Tarawa (in the Gilbert Islands), which has a population density of 3,173 people per square kilometer. The mean age of the I-Kiribati population is 24.9 years and 15.9% of the population is aged five years or younger, reflecting the high birth rate of 31,3 per 1,000 people per year.

15.	The public sector dominates Kiribati’s economy. It provides two-thirds of all formal sector employment and accounts for almost 50% of gross domestic product. Kiribati is highly exposed to external economic shocks, particularly surges in food and fuel commodity prices, due to its limited revenue base and high dependency on imports.

16.	  Kiribati is blessed with rich marine resources that has sustained its people since time immemorial and has influenced its culture, traditions and way of life. The inshore fisheries continue to be a main source of food and livelihood while oceanic fisheries, particularly tuna resources, provide the country with much needed revenue from fishing licenses and catch sales. Land and in-shore marine ecosystems and resources are intimately linked and also very vulnerable to disturbances from human activities, climate variability and climate change. Small disturbances do not take long to have knock-on effects resulting in degradation in habitats and ecosystem services that people and species rely heavily on. Land is also an extremely precious resource given their very limited area and the critical ecosystem services they provide in sustaining the environment, people and economy of the country.

17.	  However, given its geographic characteristics and setting, the country's environment is very vulnerable. It is also exacerbated by the increasing human population pressure on natural resources and the rising threat of extreme weather conditions due to the impacts of climate change. Kiribati is extremely vulnerable to the predicted negative impacts of climate change. Rising sea levels and extreme events such as storm surges and king tides are a real threat to terrestrial biodiversity, quality of underground water resources and peoples very survival given the very low lying nature of the atolls and islands.

18.  The project socioeconomic benefits will be indirectly toward the provision of better environmental information, which will be used by all stakeholders in Kiribati, especially by decision and policy-makers to make better decisions, policies, plans and programmes related to the management of the environment in Kiribati.

19.   Preserving and conserving the environment in Kiribati is critical for the development of Kiribati and particularly its socioeconomic development. Nationally, the main priority to better manage the environment was the need for better information (see section B.2.e). This project will address this issue.

20.  Every effort will also be made to incorporate gender issues in the implementation of this project. Roles of men and women to participate in activities of the project will be equally assigned without any discrimination. The project will take steps to ensure that women account for at least 40% of all training and capacity building in the project. Moreover, the project will strengthen data collection and monitoring programmes – gender segregation of data collection and monitoring will be introduced as a basis for ensuring long-term gender benefits.

21.  Globally, the project will contribute to the development of Kiribati's capacity to better manage its environment, including the fulfillment of its MEA obligations. The monitoring of the environment will be strengthened and by extension the capacity to report to the intenrational conventions will be developed.

B.3. Explain how cost-effectiveness is reflected in the project design: 22. In line with GEF strategy, the GEF finances only the ‘incremental costs’ of achieving the global environmental benefits. This means that the UNDP/GEF project builds on top of a baseline. The UNDP/GEF project will influence investments by both government and development partners, and will have an impact beyond the limited GEF contribution. 23. For both Outcomes, the strategic use of GEF funds is to mainstream into/onto ongoing processes and to modify them in order to yield global environmental benefits, this is far more cost-effective than if GEF was to support the entire initiative. 24. Outcome 1 will use project resources to develop a comprehensive Environmental Management Information System (EMIS) at ECD that serves to create new and improved environmental data and information. This system will be developed on the existing body of environmental knowledge existing at ECD, ensuring that global environmental concerns are adequately considered and addressed and optimizing the impact of GEF investment. 25. Outcome 2 will use project resources to support the development of a compliance monitoring system (CMS). It will include the identification of a set of environmental indicators that will provide information on the state of the environment in Kiribati, including the drafting of national reports to international conventions. The project will notably contribute to (rather than implement alone) the development of this monitoring system and to the training of staff. 26. In almost all cases, GEF activities fill gaps and make connections, rather than supporting an entire process or complete initiative. 27. The Project also intends to minimize the use of international consultants where national expertise is available. This will reduce the travel costs and the costs of consultancy fees. Notwithstanding, where international expertise is unique or exceptionally credible, it will be utilized.

C.  describe the budgeted m &e plan:

28.  The UNDP Project Document provides a detailed description of the monitoring, reporting and evaluation to be undertaken during the Project (Section C.5).

29.  Full details of indicators, baseline values and targets are presented in Annex 2 to this document (Project Results Framework).

30.  Monitoring and evaluation activities will follow UNDP and GEF monitoring and evaluation policies and guidelines. Monitoring and evaluation of progress in achieving project results and objectives will be done based on the targets and indicators established in the Project Results Framework (PRF) (Annex 2). The project Monitoring and Evaluation Plan has been budgeted at $25,000 (see Table below). Integrated into all Outcomes, the Project monitoring and evaluation approach will also facilitate learning and mainstreaming of project outcomes and lessons learned into international good practice as well as national and local policies, plans and practices.

31.  A summary of the envisaged M&E activities is provided in the following table.

| Type of M&E activity | Responsible Parties | Budget US$ Excluding project team staff time | Time frame |
| --- | --- | --- | --- |
| Inception Workshop and Report | - Project Coordinator - UNDP CO, UNDP GEF | Indicative cost: 5,000 | Within first two months of project start up |
| Measurement of Means of Verification of project results. | - UNDP GEF RTA/Project Coordinator will oversee the hiring of specific studies and institutions, and delegate responsibilities to relevant team members. | To be finalized in Inception Phase and Workshop. | Start, mid and end of project (during evaluation cycle) and annually when required. |
| Measurement of Means of Verification for Project Progress on output and implementation | - Oversight by Project Coordinator - Project team | To be determined as part of the Annual Work Plan's preparation. | Annually prior to ARR/PIR and to the definition of annual work plans |
| ARR/PIR | - Project Coordinator and team - UNDP CO - UNDP RTA - UNDP EEG | None | Annually |
| Periodic status/ progress reports | - Project Coordinator and team | None | Quarterly |
| Mid-term Review (if needed) | - Project Coordinator and team - UNDP CO - UNDP RCU - External Consultants (i.e. evaluation team) | Not Required for MSP project but can be undertaken if it is deemed necessary by the Project Board | At the mid-point of project implementation. |
| Final Evaluation | - Project Coordinator and team, - UNDP CO - UNDP RCU - External Consultants (i.e., evaluation team) | Indicative cost: $14,000 | At least three months before the end of project implementation |
| Project Terminal Report | - Project Coordinator and team - UNDP CO - Local consultant | 0 | At least three months before the end of the project |
| Audit | - UNDP CO - Project Coordinator and team | Indicative cost per year: $2,000 | Yearly |
| Visits to field sites | - UNDP CO - UNDP RCU (as appropriate) - Government representatives | For GEF supported projects, paid from IA fees and operational budget | Yearly |
| TOTAL indicative COST Excluding project team staff time and UNDP staff and travel expenses |  | US$ 25,000 (+/- 5% of GEF budget) |  |

PART iII: Approval/endorsement by gef operational focal point(s) and gef agency(ies)

- Record of Endorsement of GEF Operational Focal Point(s) on Behalf of the Government(s): ): (Please attach the Operational Focal Point endorsement letter(s) with this form. For SGP, use this OFP endorsement letter).

| Name | Position | Ministry | Date (MM/dd/yyyy) |
| --- | --- | --- | --- |
| Ms. Nenenteiti Teariki-Ruatu | GEF Operational Focal Point | Ministry of Environment, Lands and Agriculture Development (MELAD) | 08/21/2012 |

B.  GEF agency(ies) certification

This request has been prepared in accordance with GEF/LDCF/SCCF/NPIF policies and procedures and meets the GEF/LDCF/SCCF/NPIF criteria for CEO endorsement/approval of project.

| Agency Coordinator, Agency Name | Signature | Date (Month, day, year) | Project Contact Person | Telephone | Email Address |
| --- | --- | --- | --- | --- | --- |
| Adriana Dinu Executive Coordinator and Director a.i. UNDP-GEF |  | 06/30/2014 | Tom Twining-Ward, Senior Technical Advisor UNDP (Green-LECRDs) | +421 2 2 59337 386 | tom.twining-ward@undp.org |

GEF_CEOENDR_52

ANNEX A:  PROJECT RESULTS FRAMEWORK (either copy and paste here the framework from the Agency document, or provide reference to the page in the project document where the framework could be found).

See Annex 2 of the UNDP Project Document

ANNEX B:  RESPONSES TO PROJECT REVIEWS (from GEF Secretariat and GEF Agencies, and Responses to Comments from Council at work program inclusion and the Convention Secretariat and STAP at PIF).

The GEF Secretariat Review of the PIF made no specific requirements to be addressed through this Request for CEO Endorsement

Annex C:  status of implementation of project preparation activities and the use of funds

A.  provide detailed funding amount of the ppg activities financing status in the table below:

| PPG Grant Approved at PIF: 24,000 |  |  |  |
| --- | --- | --- | --- |
| Project Preparation Activities Implemented | GEF/LDCF/SCCF/NPIF Amount ($) |  |  |
|  | Budgeted Amount | Amount Spent To date | Amount Committed |
| Local Consultants | 10,000 |  |  |
| International Consultants | 7,500 | 8,568 | 8,691 |
| Travel | 1,500 |  | 2,741 |
| Workshops | 5,000 |  | 4,000 |
| Total | 24,000 | 8,568 | 15,432 |

annex D:  calendar  of expected reflows (if non-grant instrument is used)

Provide a calendar of expected reflows to the GEF/LDCF/SCCF/NPIF  Trust Fund or to your Agency (and/or revolving fund that will be set up)

N/A

Project ID number will be assigned by GEFSEC.

Refer to the Focal Area Results Framework and LDCF/SCCF Framework when completing Table A.

PMC should be charged proportionately to focal areas based on focal area project grant amount in Table D below.

For questions A.1 –A.7 in Part II, if there are no changes since PIF and if not specifically requested in the review sheet at PIF  stage, then no need to respond, please enter “NA” after the respective question.

If at CEO Endorsement, the PPG activities have not been completed and there is a balance of unspent fund, Agencies can continue undertake the activities up to one year of project start.  No later than one year from start of project implementation, Agencies should report this table to the GEF Secretariat on the completion of PPG activities and the amount spent for the activities.