United Nations Development Programme

PROJECT DOCUMENT

| Project Title: Strengthening National Capacities to Meet Global Environmental Obligations with the Framework of Sustainable Development Priorities |  |  |  |
| --- | --- | --- | --- |
| Country: Liberia | Implementing Partner: Environmental Protection Agency (EPA) |  | Management Arrangements: National Implementation Modality (NIM) |
| UNDAF and Country Programme Outcome 2: Inclusive and sustainable economic transformation informed by evidence-based macro-economic policy promoting access to livelihood, innovative and competitive private sector and efficient natural resource management. UNDAF and Country Programme Outcome 4: Liberian governance systems strengthened to ensure consolidation of peace and stability supported by effective and well-functioning institutions that foster inclusive participation of stakeholders, especially women and youth, with enhanced service delivery at local levels. |  |  |  |
| UNDP Strategic Plan Output: 1: Growth and development are inclusive and sustainable, incorporating productive capacities that create employment and livelihoods for the poor and excluded |  |  |  |
| UNDP Social and Environmental Screening Category: Low Risk |  | UNDP Gender Marker: 2 |  |
| Atlas Project ID/Award ID number: TBD |  | Atlas Output ID/Project ID number: TBD |  |
| UNDP/GEF PIMS ID number: 5796 |  | GEF ID number: 9390 |  |
| Planned start date: July 2017 |  | Planned end date: July 2021 |  |
| LPAC date: TBD |  |  |  |

| - Brief project description: This project is in line with the GEF-6 CCCD Strategy objective 1, 3, and 5 which call for countries to: a) integrate global environmental needs into management information systems and monitoring, b) integrate MEA provisions into national policy, legislative, and regulatory frameworks, and c) update NCSAs, respectively. The goal of this project is for Liberia to make better decisions to meet and sustain global environmental obligations. This requires the country to have the capacity to coordinate efforts, as well as best practices for integrating global environmental priorities into planning, decision-making, and reporting processes. To that end, the objective of this project is to strengthen a targeted set of national capacities to deliver and sustain global environmental outcomes within the framework of sustainable development priorities. The project will be carried out via four linked components. Component 1 calls for the establishment of an integrated environmental knowledge management system to meet global environment and sustainable development priorities. Component 2 focuses on enhanced institutional and technical capacities to mainstream, develop, and utilize policies for implementation of the three Rio Conventions. Component 3 works to improved environmental attitudes and values for the global environment. Component 4 is the updating of the National Capacity Self-Assessment. The project will take an adaptive collaborative management (ACM) approach to implementation, which calls for stakeholders to take an early and proactive role in the mainstreaming exercises, as well as to help identify and solve unexpected implementation barriers and challenges. By taking an ACM approach, project activities and outputs can be more legitimately modified and adapted to maintain timely and cost-effective project performance and delivery. |  |  |
| --- | --- | --- |
| Financing Plan |  |  |
| GEF Trust Fund or LDCF or SCCF or other vertical fund | US$ 1,500,000 |  |
| UNDP TRAC resources | US$ 200,000 |  |
| Cash co-financing to be administered by UNDP | US$ 0 |  |
| - Total Budget administered by UNDP | US$ 1,700,000 |  |
| Co-financing |  |  |
| Government | US$ 1,300,000 |  |
| - MFDP Co-financing in-kind | US$ 1,300,000 |  |
| - Grand-Total Project Financing (1)+(2) | US$ 3,000,000 |  |
| Signatures |  |  |
| Signature: Ministry of Finance and Development Planning | Agreed by Government | Date/Month/Year: |
| Signature UNDP Resident Representative Liberia | Agreed by Implementing Partner | Date/Month/Year: |
| Signature: UNDP Headquarters | Agreed by UNDP | Date/Month/Year: |

# Table of Contents

Table of Contents	3

A.	Development Challenge	6

A.1	Global Environmental Challenges	6

A.2	Capacity Barriers	7

A.3	Consistency with National Priorities	7

A.4	Baseline Scenario and Associated Baseline Projects	9

B.	Strategy	10

B.1	Alternative Strategies	10

B.2	Selected Scenario	11

B.3	Theory of Change	11

B.4	Knowledge Management	12

B.5	Innovativeness	12

B.6	Potential for Replication	12

B.7	Sustainability and Scaling Up	13

C.	Project Results	14

C.1	Project Goal, Objective, and Expected Results	14

C.2	Project Components, Outputs, and Activities	14

C.3	Project Indicators	20

C.4	Global Environmental Benefits	20

D.	Project Partnerships	21

D.1	Stakeholder Engagement	22

D.2	Linkages with other Initiatives	28

D.3	Mainstreaming Gender	29

D.4	South-South and Triangular Cooperation	31

E.	Feasibility	31

E.1	Risk Management	31

E.2	Social and Environmental Safeguards	33

F.	Project Results Framework	34

G.	Monitoring and Evaluation Plan	35

G.1	Evaluation Schedule	39

H.	Implementation and Management Arrangements	40

I.	Project Financing	42

I.1	Co-financing	42

I.2	Incremental Cost Reasoning	43

I.3	Cost-Effectiveness	44

I.4	Financial Planning and Management	44

I.5	Project Outcome Budget	46

I.6	Total Input Budget and Work Plan	47

J.	Legal Context	48

K.	Required Annexes	49

Annex 1:	Capacity Development Scorecard	50

Annex 2:	Provisional Multi-year Work Plan	59

Annex 3:	Monitoring Plan	60

Annex 4:	UNDP Social and Environmental and Social Screening Template (SESP)	61

Annex 5:	UNDP Project Quality Assurance Report	68

Annex 6:	Standard Letter of Agreement between UNDP and Government of Liberia	79

Annex 7:	Terms of References	83

Annex 8:	References	90

Acronyms and Abbreviations

| APR | Annual Progress Report |
| --- | --- |
| CBD | United Nations Convention on Biological Diversity |
| CCCD | Cross-Cutting Capacity Development |
| CCD | United Nations Convention to Combat Desertification and Drought |
| EKMS | Environmental Knowledge Management System |
| EPA | Environmental Protection Agency |
| FAO | Food and Agriculture Organization |
| FCCC | United Nations Framework Convention on Climate Change |
| GEF | Global Environment Facility |
| MDG | Millennium Development Goal |
| MEA | Multilateral Environmental Agreement |
| M&E | Monitoring and Evaluation |
| NCSA | National Capacity Self-Assessment |
| NGO | Non-Governmental Organization |
| NPD | National Project Director |
| PMU | Project Management Unit |
| PSA | Public Service Announcement |
| UNDAF | United Nations Development Assistance Framework |
| UNDP | United Nations Development Programme |
| UNDP/CO | UNDP Country Office |

# A.	Development Challenge

## A.1	Global Environmental Challenges

Liberia is located on the southwest coast of Africa, and boarders the Ivory Coast, Guinea, and Sierra Leone.  Liberia is divided into 15 counties, which are subdivided into 90 districts.  Although Liberia is a rather small country, it has significant biodiversity.  There are 600 bird species, 150 mammals, 75 reptiles and over 2000 flowering plants.   Some notable species in Liberia include western chimpanzees, forest elephants, and leopards.   Liberia also has rich forests; around 42% of the Upper Guinea Forest of West Africa is contained within Liberia (Republic of Liberia, 2014; Republic of Liberia, 2004). Liberia also has numerous natural resources such as timber, rubber, gold diamonds, and iron ore.  Economically, the forestry and agriculture sectors are two of the most important sectors in Liberia. Agriculture accounts for over 70% of livelihoods (Dorliae, 2012).

Liberia faces numerous environmental challenges including land degradation, fragmentation, deforestation, soil erosion, and pollution.  The dependence on forestry presents a unique environmental risk as Liberia’s forest is part of the West African Hotspot.  This (once) rich ecosystem has faced severe deforestation; only ten percent of the original forest remains, of which around 40% lies in Liberia.  Unfortunately, this remaining forest is at risk serious risk of deforestation.  Over the past two centuries, Liberia has lost over 60% of its forest cover (Republic of Liberia, 2004), and deforestation rates have increased since 2000.  Increases in deforestation and land degradation are largely due to displaced people clearing land.  Also contributing to deforestation, biodiversity loss, and land degradation is unsustainable farming practices, mining, charcoal production, invasive species, hunting, and unregulated timber extraction.  Poaching is also rampant and mitigation measures are lacking; the draft Wildlife Management and Protected Areas Act remains in draft form (Dorliae, 2012).

Climate change also poses a real threat to Liberia.  Among other threats, Liberia’s economy and human health could be threatened by rising temperatures and water scarcity. Currently, the country does not have strong capacities for mitigation and adaptation; Liberia has no institutions that offer climate change education or research programs (although, the University of Liberia does offer programs on the environment).  Additionally, there are no organized or coordinated programs for meteorological, hydrological, or climate research and observation.  Currently, only fragmented services are available. Along with a lack of observation networks, government bodies are hindered by inadequately-trained staff (Environmental Protection Agency of Liberia, 2013).

Although aware of the environmental situation, Liberia has struggled to address these environmental issues. The civil wars, which lasted for more than 10 years, served to exacerbate the situation. Poverty also presents a serious challenge; causing degradation and drawing attention and resources from environmental concerns.  Over 60% of Liberians live in poverty.  Of these, over 40% of citizens live in extreme poverty (Dorliae, 2012).  The outbreak of Ebola in 2014 also threatened Liberia’s progress, as the crisis became a priority for the government and stretched already limited resources.  Fortunately in January 2016 the outbreak was declared resolved.  Overall, there has been slow progress in sustainable development and meeting obligations under the Rio Conventions.

- Root Causes

There are a few key root causes of environmental degradation in Liberia. The most critical include: human settlements and population pressures; shifting cultivation; timber exploitation; and rubber plantations.  More generally, root causes are related to over-exploitation of biological resources; poverty; political instability and wars; education; and inadequate law enforcement (Republic of Liberia, 2004).  From a reporting perspective, one root cause of Liberia’s development challenges is the fact that Focal Points are located in different agencies, which thereby limits coordination and collaboration between them.

## A.2	Capacity Barriers

Liberia has undertaken numerous initiatives to address environmental issues.  Despite the achievements Liberia made, Liberia continues to face important challenges to meeting environmental goals.  As a Rio Convention mainstreaming project, the proposed strategy sets out to meet barriers identified in Liberia’s 2006 National Capacity Self-Assessment (NCSA), which was undertaken though a consultative process and participatory approach that involved numerous stakeholders from various sectors.   Through the inclusive and consultative process of the NCSA, stakeholders identified a number of areas that explain the difficulty in fulfilling the obligations of the Rio Conventions.  The NCSA identified the following barriers that cut across the three Rio Conventions:

- Inadequate public awareness and education/training

- Inadequate institutions and institutional frameworks

- Inadequate political commitment

- Inadequate planning skills and resources, as well as incomplete structures at all levels of policy implementation

- Inadequate financial resources and economic framework

- Inadequate strategic plans and implementation

- Inadequate access to information

- Inadequate policies and legal frameworks

- Low level of involvement of civil society

- Inadequate natural resources management systems

- Lack of institutional capacities

- Lack of effective mechanism for information processing and sharing

- Poor governance

Liberia’s Agenda for Transformation 2012-2017 confirmed many of the barriers identified in the NCSA.  Specifically, the agenda noted the following barriers:

- Weak technical, administrative and managerial capacities;

- Weak institutional coordination;

- Unclear policies and mechanisms to enable effective participation by especially non-state actors; at the national and local levels;

- Limited stakeholder participation in planning and decision-making processes;

- Limited dissemination of key information (Republic of Liberia, 2013).

Barriers were also reaffirmed in the Liberia Constraints Analysis (Government of Liberia, 2013).

## A.3	Consistency with National Priorities

The country has demonstrated a desire to improve the environmental policy framework with the preparation of multiple new policies including the National Environmental Protection and Management Law (2003), the National Environmental Policy (2003), the establishment of an Environmental Protection Agency, in 2003, the National Forestry Law (2000), and the New Mineral and Mining Laws (2000).

In the first Poverty Reduction Strategy, the environment was considered a cross-cutting issue.  Some achievements made during implementation of this strategy include passage of the Community Rights Law, which established a system for community harvesting of forests. Efforts were also undertaken to improve protected areas management and increase the size/number of protected areas.  In Liberia’s medium-term Poverty Reduction Strategy II (2012-2018) there is a fifth pillar: Cross-Cutting Issues which includes the environment. Additionally, environmental issues have been integrated into other pillars of the strategy specifically the economic pillar.

During the Liberia Rio +20 National Consultative Workshop, Liberia identified five issues that are essential for accomplishing its development goals and objectives.  Additionally, Liberia has also developed a National Capacity Development Strategy (2010), which calls for investing in areas needed to achieve development goals.

The project will assist the Government of Liberia to achieve the national priorities it has set in Liberia RISING 2030.  The aim of this is to transform Liberia through a new development strategy, which was launched in December 2012. The overall objective is to turn Liberia into a middle income country by 2030.

The project is also in line with Liberia’s National Biodiversity Strategy and Action Plan II (NBSAP) which aims to, as part of Liberia’s commitment to the Millennium Development Goals, and in line with the National Environmental Policy of Liberia, assist the people of Liberia to acknowledge and exercise responsible stewardship over biological resources to meet the needs of the present without endangering the ability of future generations to meet their own needs.  Some of the goals are to protect critical ecosystems, create biodiversity awareness, and increase commitment to sustainable use of biological diversity (Republic of Liberia, 2017).

Liberia’s 2008 National Adaptation Plan of Action (NAPA), as a response to the impacts of climate change, aligns with National Environmental Policy which calls for the sustainable management of Liberia’s environment and natural resources.  The NAPA also aims to establish synergies between adaptation and national development plans, such as the National Reconstruction and Development Plan, Millennium Development Goals, and the National Biodiversity and Strategy Action Plan.  The NAPA identifies key adaptation needs and list priority actions, such as enhancing resilience to increasing rainfall variability through agriculture, to address the needs.

This project is also in line with Liberia’s UNDAF 2013-2017.  The UN Country Team decided that the new UNDAF would also take into account the requirements of Delivering as One. Thus, in addition to the Strategic Framework and Results Matrix, the UNDAF is accompanied by a detailed Costed Action Plan. Together they constitute the One Programme. The four pillars of the One UN Programme are:

- Peace, Security, Rule of Law

- Sustainable Economic Transformation

- Human Development

- Inclusive Governance and Public Institutions

The UNDAF (One Programme) also aligns with Liberia’s National medium-term strategy, known as the Agenda for Transformation.  The Agenda for Transformation is based on five pillars:

- Peace, Security and Rule of Law

- Economic Transformation

- Human Development

- Governance and Public Institutions

- Cross-cutting issues

The Agenda contains a specific goal to improve management of the environment to safeguard sustained economic development and growth. Specific actions called for in this agenda include: a) developing environmental quality standards and regulatory tools; b) harmonizing environmental laws and policies to ensure improved environmental management; c) undertake a gap analysis of sectoral environmental laws and policies; d) create environmental awareness; e) create training and education programmes; f) develop a public awareness strategy and campaign; g) train professionals in effective environmental management;  strengthen environmental units in ministries through training and improved coordination; and h) develop a system to collect and disseminate environmental information/data.

The design and implementation of the proposed CCCD project would also take into account the development plans of other bilateral and multilateral donors in Liberia to ensure appropriate alignment as well as to leverage the necessary co-financing.

## A.4	Baseline Scenario and Associated Baseline Projects

Liberia is struggling to fulfill many of the objectives set forth in the Rio Conventions.  Many of the developed frameworks and plans for action face limited implementation due to limited government resources, limited human capacity, and a lack of appropriate technologies. Liberia struggles with an inadequate system for information and knowledge management and the poor information sharing between or within sectors. Additionally, the country’s degraded and limited infrastructure combined with a low technical and institutional capacity severely limit Liberia’s environmental governance framework and thus its potential to conserve the natural environment, let alone secure long-term benefits from it. The civil war only exacerbated the situation, leading to displacement of individuals and unprecedented amounts of resource exploitation.  Although Liberia is recovering from the war, 85% of the population still lives below the international poverty line.  Liberia’s HDI (2014) is 0.430, ranking the country 177 out of 188 (UNDP, 2015).

Multilateral donor agencies specifically in the field of natural resource management currently working in Liberia now include the African Development Bank, GEF, IFAD, UNDP, and the World Bank.  Bilateral donor agencies are also very important development partners from, Norway, and the United States (USAID), as well as other inter-governmental organizations such as the CARE International, Conservation International, and the Society for the Conservation of Nature in Liberia.

National environmental NGOs, with assistance from Conservation International, organized themselves into the Alliance for Conservation in Liberia. The goal of this body is to ensure that all local NGOs who are or would like to be involved in conservation of biodiversity can do so without overlapping efforts or functions.

Liberia has made significant progress since the end of the civil war by investing in infrastructure, revising existing policies and laws, and reviewing the mandates of political institutions to reduce duplication.  One area of progress is updating the mandates and restructuring Government ministries and agencies to improve effectiveness and efficiency. Liberia has also established new agencies like the Rural and Renewable Energy Agency to promote the sustainable development strategy. Reforms in Liberia have been undertaken on an institution-by-institution basis and have not been considered on a holistic basis, nor have they increased coordination and harmonization.

Between 2010 and 2012, UNEP implemented a global project, entitled Piloting Integrated Processes and Approaches to Facilitate National Reporting to Rio Conventions that included Liberia as a beneficiary country.  This project focused on helping Liberia (among other countries) to better organize modalities for accessing and preparing their national reports.  Notwithstanding the capacities developed, a number of important capacities remained to be developed, such as the standardization of data collection and information analysis, improved coordination and collaboration to facilitate streamlined national reporting, and increased awareness and stakeholder engagement in the national reporting process.  During the project implementation, activities under component 4 will undertake an updated assessment of the systemic, institutional, and individual capacities that remain a priority to be developed in order to meet and sustain Rio Convention obligations.

A description of on-going projects that this project will coordinate with appears in section C.4 Partnerships.  Relevant completed UNDP GEF projects that form the baseline of this project include:

- Associated Baseline Projects

| Project name | Description of project’s alignment with CCCD project |
| --- | --- |
| GEF Enhancing Resilience to Climate Change by Mainstreaming Adaption Concerns into Agricultural Sector Development in Liberia (Ending September 2015) | The expected results of this project included improving the rural communities’ capacities, increasing sustainable livestock and crop production, and reducing poverty. |
| FAO to Support MOA Statistics and Information Management System | The objective of this project was to support the implementation of a linked information and knowledge system. |
| Smallholder Agricultural Productivity Enhancement and Commercialization Project (SAPEC) | The goal this project was to reduce rural poverty and household food insecurity. One component is capacity building and institutional strengthening, which includes trainings. |

# B.	Strategy

## B.1	Alternative Strategies

During the conceptualization of the present cross-cutting capacity development project, a number of alternative approaches were considered, taking into account the current set of interventions currently underway and planned for Liberia.  An important starting point was the findings and recommendations of the National Capacity Self-Assessment, followed by a consideration of the lessons learned from other projects, such as a review of the Final Evaluation of the Mainstreaming and Capacity Building for Sustainable Land Management project.  A review of the recommendations contained in the more recent Rio Convention reports was also considered, such as the 2016 National Biodiversity Strategy and Action Plan.

The single most common cross-cutting capacity development constraint that was recurring in the various assessments and action plans was the significantly low institutional capacity for managing data and information for improved planning and decision-making to meet and sustain Rio Convention obligations.  Taking into account the GEF-6 Cross-Cutting Capacity Development priority of strengthening mainstreaming capacities as a strategy to meet the duality of national development and global environmental priorities, this project’s objective was formulated.

From an implementation perspective, a number of alternative approaches were considered to meet the stated objective.  One was for Liberia to continue the same approach of implementing focal area projects, and to strengthen the key set of systemic, institutional, and individual capacities through focal area projects.  However, this approach will not address the capacity development gaps nor result in creating synergies.  Another aspect considered was to have different components executed by different agencies.  The challenge with this approach is the relative weak coordination among government ministries and agencies – indeed an important capacity development need that the project would help address.  A related issue was the government’s keen desire to use the project to strengthen national capacity of the Environmental Protection Agency.

The selected strategy was based on the real need to strengthen meaningful capacities that can be successfully institutionalized.  The key here is not for the project to take on more than the Environmental Protection Agency can absorb, but rather, through the process of project execution, learn how to formulate better plans and make better decisions regarding the global environment within the framework of their institutional mandates.  That is, this project places a premium on address institutional sustainability by emphasizing the execution of the project through a wide range of learning-by-doing exercises by the EPA.  This will require that they reach out of other government ministries and agencies to meet complementary and shared mandates as well as to effectively negotiate resolution of real or perceived conflicts of interests that come about through Rio Convention mainstreaming.

## B.2	Selected Scenario

This project is in line with the GEF-6 CCCD Strategy objective 1, 3, and 5 which call for countries to: a) integrate global environmental needs into management information systems and monitoring, b) integrate MEA provisions into national policy, legislative, and regulatory frameworks, and c) update NCSAs, respectively.

The uniqueness of this project is centered on its cross-cutting nature.  Other projects currently under implementation focus on strengthening targeted capacities under one of the three Rio Conventions, and thus have a relatively narrower system boundary than the CCCD programme approach.  In the absence of the CCCD project, there remains likelihood that Liberia would not realize its full potential for sustainable development due to limited coordination and decentralization.  Additionally, it is likely that environmental management in Liberia would continue to focus on traditionally narrow constructs.

## B.3	Theory of Change

This project will lead to change by addressing the barriers that limit Liberia’s ability to meet obligations under the three Rio Conventions and other MEAs.  By systematically targeting the key barriers, the project will help Liberia make incremental improvements. These short-term changes will in turn lead to long-term improvements; while the project develops capacities, it also lays groundwork for improved systems and frameworks to sustain outcomes.

More specifically, this project will address specific cross-cutting capacity development priorities identified in the NCSA in order to catalyze Liberia’s more effective participation in environmentally sound and sustainable development in a way that produces co-benefits for the global environment.  Capacity development is an essential component of development effectiveness (Organisation for Economic Co-operation, 2006).  Additionally, as local and global benefits are strongly interlinked, changing human behavior is a key underlying premise of this project’s (as well as the GEF’s) approach to achieving global environmental and local benefits.

Notwithstanding the important activities currently underway in Liberia to address these important priorities, this CCCD project creates an institutional space to remove certain key barriers to mainstreaming global environmental obligations into national, county, and district information systems, development policies, and planning frameworks.  The project is also designed to help Liberia sustain these outcomes and realize long-term change.  Specifically, the project will transform how Liberia pursues socio-economic development that integrates global environmental objectives and priorities within decision-making and improved knowledge management.  The project will also contribute to change by catalyzing Liberia’s road to self-reliance and environmental sustainability, assuming that the capacities developed will be institutionalized, thereby resulting in an incrementally reduced dependency on external funding.

This project aligns with best practices for capacity development including acknowledging the complex nature of collaboration and incorporating it into the project design. This project includes numerous stakeholders (including the government and the private sector) to mitigate the risk of crowding out and to help build ownership (Greijn, 2013).  The project design also benefited from lessons learned from previous phases of the GEF and CCCD projects, and includes many good practices such as a SWOT and gap analysis, and an entire component focused on awareness building (OECD, 2012; World Bank Institute Capacity Development and Results Practice, 2011; Hill, Rife, & Twining-Ward, 2015; United Nations, 2011).

The project makes the assumption that project stakeholders will in the short-term directly benefit through improved capacities through the learning-by-doing trainings.  The public and stakeholders will benefit in the long-term through improved outcomes including sustainable development and environmental improvements.  The theory of change is also based on the assumption that learning-by-doing will translate into a greater mobilization of efforts and resources, and that building commitment will help countries overcome the internal resistance to change and adopt new and stronger modalities of engagement and collaboration (Hill, Rife, & Twining-Ward, 2015), which will in turn lead to long-term change.

The project approach is the best one at this point in time as it meets the primary objective of CCCD projects; it responds directly to the programme strategy.  Additionally, this project approach will build on the government’s strong commitment to strengthening sustainable development.  Finally, the strategy garners support from the fact that currently other development partners are supporting similar development work in the country.

## B.4	Knowledge Management

This project is part of a portfolio of capacity building interventions in Liberia that encourages regional cooperation and knowledge and information exchanges.  Partnerships and collaboration will also catalyze the transfer of knowledge and competencies among actors and stakeholders.  Lessons learned from other projects will be included, as appropriate (for example, in the training programmes and the knowledge management system).  This project also contains specific activities to increase the use and sharing of knowledge, and to strengthen critical thinking in understanding the implications of the global environment towards the pursuit of sustainable development.  These include a series of learning-by-doing workshops and public dialogues among a diverse set of stakeholders.  Component one focuses on establishing a system for collecting and sharing information and data between the institutions for better environmental management and the fulfilment of the obligations of the Rio Conventions (an EKMS).

The system that the project will strengthen is the ideal platform to share lessons learned and experiences with the main stakeholders of environmental information and knowledge.  Universities and research centers will be at the center of the information and knowledge management and will ensure the integration of innovative scientific and technical information into the project setup and into other baseline initiatives.

The project’s approach to knowledge management is consistent with the International Resource Panel Report on Policy Coherence of the Sustainable Development Goals which emphasizes the need for developing widespread awareness and creating and disseminating decision support tools.

## B.5	Innovativeness

The innovativeness of this project is stems from its strategy of engaging stakeholders from the local level to the top decision-making level to build and sustain the country’s underlying capacities to meet Rio Conventions obligations.  This project will develop innovative approaches for knowledge management, mainstreaming, and capacity self-assessments that may be useful for other LDC to learn from.  While the project’s outputs may not necessarily be innovative when compared to the portfolio of GEF-funded projects in other countries, these will be innovative for the Liberia.  The project will therefore review and assess the extent to which better and best practices to mainstream Rio Conventions through strengthened coordination and decentralization are innovative and transformative for the Liberia.

## B.6	Potential for Replication

As a medium-size project, this initiative has certain limitations, namely in being able to reconcile and undertake all the necessary institutional reforms identified as needed during project implementation.  Instead, this project serves as catalyst of a more long-term approach for improved decision-making for the benefit of the global environment.

Given that the barriers addressed by the project are largely shared by regions around the Liberia, and the approaches used are transferable, the project’s outcomes are replicable.  The project’s outcomes will contribute towards larger national policy, regulatory, fiscal, monitoring and communication initiatives in support of the Rio Conventions.  This will include informing national policy development on issues such the pursuit of green development, use of innovative financing mechanisms, and more effective stakeholder engagement approaches.  Successful models will be identified and lessons learned and best practices will be captured and disseminated to promote scaling-up/replication.

The project’s trainings and learning-by-doing exercises complemented by piloting of best practices and methodologies for monitoring and for Rio Convention mainstreaming, will serve as the basis for testing the robustness of long-term initiatives.  By strengthening the institutional and technical capacities, the replicability and extension of the project strategy through future pilot projects will be greatly enhanced and the learning curve greatly reduced.  The replication and extension of project activities is further strengthened by the large number of stakeholders that the project envisages engaging.  This includes working with NGOs and civil society associations that have a strong presence and extensive reach in local communities and/or are actively supporting related capacity development work.  Many such organizations operate in the Liberia, and are particularly active in forestry, biodiversity conservation, and education.  NGOs and institutions also play an important role in land rehabilitation, soil conservation, and monitoring in the Liberia.  Project activities will be undertaken with the engagement of the private sector as well.

Replication will also be supported by raising awareness of the project throughout the Liberia.  This project will facilitate this through awareness-raising workshops with key stakeholders from the local and national government, the private sector, academia, civil society and the media.  The public service announcements on radio and television also serve the purpose of popularizing the project with the public in order to generate greater support and demand for replication activities.

## B.7	Sustainability and Scaling Up

The project’s fundamental approach to sustainability lies in building underlying capacities to make more informed decisions on best practice approaches for integrated global environmental and sustainable development.  The project will promote sustainability of outcomes through mainstreaming the use of environmental data, information, and knowledge into decision-making at the national and sub-national level.

Sustainability will also be enhanced by undertaking an extensive set of awareness-raising activities targeted at a broad range of stakeholders, including the general public and particularly youths where the addition of appropriately framed information can have an important impact on the early stages of value formation.  Another approach to ensuring sustainability is to align multilateral environmental agreements with key national development priorities.  Aligning global environmental priorities with high value sector development priorities should help strengthen the legitimacy of both priorities if they are reconciled through thoughtful and transparent consultative and decision-making processes, as well as being based on widely accepted data, information, knowledge and best practices.  The project will also undertake targeted awareness-raising activities to secure high-level commitment from key decision-makers, such as parliamentarians, and foster a sufficient number of project champions to sustain project outcomes following project completion.

Another critical feature of the project’s sustainability is its cost-effective strategy.  See Section I.3 below.  The sustainability of the project’s outcomes will also be strengthened by the project’s attention to resource mobilization.  See Output 2.7 below.

# C.	Project Results

## C.1	Project Goal, Objective, and Expected Results

The goal of this project is for Liberia to make better decisions to meet and sustain global environmental obligations.  This requires the country to have the capacity to coordinate efforts, as well as best practices for integrating global environmental priorities into planning, decision-making, and reporting processes.  To that end, the objective of this project is to strengthen a targeted set of national capacities to deliver and sustain global environmental outcomes within the framework of sustainable development priorities.

At the end of the project, activities will have resulted in a set of improved capacities to meet and sustain Rio Convention objectives.  This project will have strengthened and helped institutionalize commitments under the Rio Conventions by ensuring a flow of assistance and information between the local, national and global level.

The expected outcome of the project is that Liberia’s will be able to achieve global environmental benefits at a lower transactional cost as well as being able to respond faster and more appropriately to conservation needs.  This means: a) improving access to best practices and best available knowledge, including innovative research; b) improving coordination, collaboration, and delegation of responsibilities among key agencies and other important organizations; c) enhancing institutional and technical capacities; d) improving awareness of global environmental values; and e) updating the NCSA to reflect post 2015-SDGs.

While the expected outcomes of the project from a GEF perspective are improved capacities to meet and sustain global environmental priorities, the expected outcomes from a national socio-economic development perspective are improved capacities to plan and make decisions that will meet and sustain sustainable development priorities.  This will be achieved by mainstreaming global environment into planning and decision-making process (i.e., integrating environmental-development best practices that reflect global environmental priorities and the Post-2015 Sustainable Development Goals into planning).

## C.2	Project Components, Outputs, and Activities

This will be carried out via four linked components.

Component 1:		Integrated environmental knowledge management system (EKMS)

This first component will focus on the establishment of an environmental knowledge management system by integrating and reconciling relevant existing systems.  A key feature of this system is that it seeks to use the latest tools and innovations, including technological, to access and create new knowledge that would allow for better decisions to be made to protect the global environment.  Not only will this component seek to develop this institutional mechanism, it will also provide the learning-by-doing training so that stakeholders make best use this system (output 1.6)

Output 1.1 	Institutional mapping and analysis of an optimal knowledge management system

This output will include the undertaking of a SWOT and gap analysis of the institutional requirements to use best available and innovation data, information and knowledge to implement the Rio Conventions and other relevant multilateral environmental agreements.  This will be undertaken through mainstreamed sectoral development plans that are more resilient and reflective of global environmental obligations.  This analysis will include recommendations to inform the strengthening of an integrated environmental knowledge management system.

An assessment of stakeholders' awareness and absorptive capacities to manage and monitor environmental information relevant to the Rio Conventions will be carried out.  MEA technical committee meetings to discuss and recommend best practices for collecting and managing environmental data, information, and knowledge will be organized.

- Target indicator(s)

- A SWOT and gap analysis of the institutional requirements to use best available and innovation data, information and knowledge is undertaken and peer-reviewed by month 5.

- An assessment of stakeholders' awareness and absorptive capacities to manage and monitor environmental information relevant to the Rio Conventions  is undertaken and peer-reviewed by month 5.

- MEA technical committee meetings to discuss and recommend best practices for collecting and managing environmental data, information, and knowledge are convened between months 3 and 6, with at least 20% female stakeholder actively engaged representatives.

Output 1.2 	Design of an integrated environmental knowledge management system

Workshops on the management of information and knowledge for planning and policy-making will be undertaken with the active engagement of representatives from various ministries, agencies, academic and research institutions, among other social actors.

Under this output, the technological requirements for collecting, storing, and sharing data and information will be designed.  This activity will build upon the institutional mapping exercise of output 1.1.  A feasibility study on the design and operation of the EKMS based on best practices and successes from other similar information management systems to meet global environmental information needs will also be prepared.  An independent peer review of the EKMS feasibility study will also be independently peer-reviewed then finalizes, followed by stakeholder validation and securing the required official approvals.

- Target indicator(s)

- Stakeholder workshops on the management of information and knowledge for planning and policy-making are convened.  One workshop for each of the three Rio Conventions, and one workshop that synthesizes those information and knowledge management needs that cut across the three Rio Conventions.  These will be convened and completed by month 7.

- The technological requirements for collecting, storing, and sharing data and information will have been expertly assessed and independently peer-reviewed by month 9.

- The preparation and independent peer review of the EKMS feasibility study will have been undertaken, validated by stakeholders, and the required official approvals secured by month 12.

Output 1.3:  	Targeted technological networking of existing information and knowledge management systems.  This output begins the implementation of the EKMS feasibility study.

This output will begin by negotiating and facilitating the formulation and adoption of networking cooperative agreements on information and knowledge management with key institutions.  These agreements are to facilitate and secure improved communication, coordination and collaboration among stakeholders.

Further consultations and negotiations will serve to catalyze agreements among key agencies and ministries to institute targeted management arrangements for sharing information.  This includes developing and testing a tracking mechanism (i.e., data flow and sharing protocols) to monitor the use of the EKMS for planning and policy-making.

- Target indicator(s)

- The formulation and adoption of networking cooperative agreements on information and knowledge management with key institutions will have been negotiated through a transparent and broad-based stakeholder consultative process by month 14.

- Targeted management arrangements for sharing information will be undertaken between months 14 and 24.

Output 1.4: 	Selected updating of technologies to create cost-effective synergies for knowledge management.  Whereas output 1.3 focuses on institutional arrangements, this output focuses on the technological hardware and software to set up the EKMS.

The key set of work under this output is to procure and install the technological hardware and software of the EKMS as recommended in the approved feasibility study of output 1.3.

- Target indicator(s)

- The procurement and installation of the technological hardware and software of the EKMS as recommended in the approved feasibility study will have been initiated by month 15, tested by month 31, and fully operational by month 40.

Output 1.5: 	Integration of new and improved global environmental indicators into select sectoral development plan(s)

Building on output 1.1, a set of best applicable indicators for measuring global environmental trends within the context of planning and policy-making in Liberia will be identified and agreed as a first manageable set to be included in the EKMS (output 1.2).  This exercise will include identifying best practicable and cost-effective methodologies for their collection and inclusion in the EKMS.  This exercise will be informed by a series of local and regional consultations and technical working group meetings with specialist producers and users of environmental information.

Technical guidance material will also be prepared for planners and other users of indicators relevant to the monitoring of the global environment.  This will include methodologies to facilitate integrated ecosystem and landscape planning and management that reflect adherence to Rio Convention obligations.

- Target indicator(s)

- A set of best applicable indicators for measuring global environmental trends within the context of planning and policy-making in Liberia will have been identified and validated by month 6.

- Technical guidance material for planners and other users of indicators relevant to the monitoring of the global environment will have been prepared and validated by month 9.

Output 1.6: 	Learning-by-doing training on improved methodologies and analytical skills for interpreting global environmental trends and understanding their relevance to sectoral development

A comprehensive assessment of training needs to manage data and information will be undertaken to ensure a good design of a long-term training programme and curriculum.  Particular attention will be given to training on the use of the EKMS and environmental data, information, and knowledge for integrating Rio Convention obligations with national planning and policy frameworks.  This programme will be improved as a result of lessons learned through its early implementation (i.e., trainings) and is intended to be applied for post-project trainings.  This will include the training needs on monitoring and compliance of output 2.5.

Training workshops will be carried out on the management of existing and new data and information through the EKMS.  Trainings will also be undertaken through learning-by-doing workshops on the use of data and information to strengthen the holistic construct and resilience of planning frameworks.

- Target indicator(s)

- A comprehensive assessment of training needs to manage data and information will have been prepared and independently peer reviewed by month 7.

- A training programme and curriculum that builds on the earlier analyses will have been prepared and validated by month 11.

- Training workshops on the management of existing and new data and information through the EKMS will have been organized and convened.  At least five (5) workshops will be convened, two in years 2 and 3, and one in year 4.  Each workshop having at least 30 unique participants (i.e., no repeat participants).  Gender balance will be reflected by at least 20% females over the total number of workshop participants.  Participants should reflect a balance of all relevant public and non-state agencies.  The total number of unique participants in the workshops should be at least 120 people.

Output 1.7: 	Early implementation and piloting of the integrated environmental knowledge management system through a select sectoral plan.  This will be undertaken in conjunction with output 2.6.

This output will serve to reinforce the appreciation and contribution that the EKMS will make for improved planning and decision-making.  To that end, with technical input through stakeholder consultations, the Project Steering Committee will select one high value sectoral development plan for early implementation and piloting through a broad-based consultative process.  Building on the trainings of output 1.6, learning-by-doing workshops will be convened to use the EKMS to demonstrate its value at improving a more holistic and resilient construct of the selected sectoral plan in keeping with Rio Convention obligations.

The choice of a high value sectoral plan was discussed during the project formulation phase, which forestry and agricultures identified as the two key sectors.  These sectors were identified as being of high priority in Liberia’s National Sustainable Development report (2012) and Liberia’s National Vision 2030.  However, due to the national elections coming up in October 2017, it was felt that it would be more appropriate for the selection of the high value sectoral plan to be decided during early project implementation.

Public dialogues on the EKMS and its implementation will be carried out targeted to decision- and policy-makers in order to enhance their understanding and secure their support and championship.  A study on best practices and lessons learned will be prepared on how the project used the EKMS to mainstream Rio Convention obligations into sectoral plans and policies.  This study will be a critical knowledge material to reinforce institutional memory and will complement the resource mobilization strategy (output 2.7).

- Target indicator(s)

- One high value sectoral development plan will be selected for early implementation and piloting through a broad-based consultative process by month 12.

- At least six (6) learning-by-doing workshops to use the EKMS to demonstrate its value at improving a more holistic and resilient construct of the selected sectoral plan in keeping with Rio Convention obligations.  These will be begin in year two and involve at least 20 government staff directly and indirectly involved in the formulation of sectoral development plans.  A total of at least 120 unique stakeholders will have actively engaged in these workshops, with at least 25% being female and at least 35% being stakeholders from the outside regions.

- Dialogues on the EKMS and its implementation with decision- and policy-makers to enhance their understanding and secure their support and championship will be facilitated as senior level events.  Two dialogues will be held each year, with at least 15 unique stakeholder representatives for each dialogue beginning in year two.

- A lessons learned study on the use of the EKMS to mainstream Rio Convention obligations into sectoral plans and policies will be prepared and independently peer-reviewed by month 43.

Component 2:		Enhanced institutional and technical capacities for mainstreaming

Components 1 and 2 are important complements of each other.  Whereas the first component will establish and provide training on the how substantive content of the integrated environmental knowledge management system, component 2 follows with a set of institutional capacity development actions to use this system for improved mainstreaming and monitoring.  This will include systemic capacity building by strengthening the enabling environment, i.e., relevant policies and legislative frameworks, to make legitimize the long-term use of this system.  Activities will also focus on strengthen institutional arrangements in order to embed this system within existing management structures and operational procedures.  A third set of capacity development activities will include learning-by-doing use of the system to formulate policy responses and programme interventions and to test these in the field.  Participants in this second set of trainings will go through the first set of trainings under component 1 where they will learn new and improved methodologies and skills to understand global environmental metrics and their impacts on socio-economic development.   Through learning-by-doing workshops and exercises, participants will review, revise, and develop appropriate legislative and regulatory instruments to better reflect and support global environmental objectives within the framework of socio-economic policies.  An important set of activities under this component will be to demonstrate and pilot mainstreamed best practices.

Output 2.1	In-depth SWOT and gap analysis of existing environmental policies and legislation, and the effectiveness of their enforcement

An in-depth analysis of Liberia's policy, legislative, and regulatory framework on environmental governance, with particular reference to the global environment will be undertaken in order to have a most up-to-date and accurate contextualizing of the systemic challenges and opportunities to meeting and sustaining Rio Convention obligations.  This will build on recently concluded studies, most of which are thematic, in order to highlight the cross-cutting challenges and barriers.  The analysis will be peer reviewed and validated through stakeholder consultations and workshops.

A SWOT and gap analysis of sector policies will be undertaken to ascertain the extent to which they support or work against meeting and sustaining Rio Convention obligations.  This will build on recently concluded studies, be peer reviewed, and validated through stakeholder consultations, in particular the private sector.

- Target indicator(s)

- An in-depth analysis of Liberia's policy, legislative, and regulatory framework on environmental governance will have been updated by month 6.

- A SWOT and gap analysis of sector policies to ascertain the extent to which they support or work against meeting and sustaining Rio Convention obligations will have been prepared by month 6.

Output 2.2	Strengthened policy and regulatory framework through improved operational interpretation, enforcement tools, and by-laws

Learning-by-doing training workshops will be organized and carried out to promote a greater understanding and as well as to reconcile weaknesses and gaps in key environmental policies and legal instruments.  They will also serve as opportunities to address weaknesses and gaps in sectoral plans and policies.  These trainings will be directed to planners and decision-makers to help them better think critically about the formulation and interpretation environmental policies and legislation.

The trainings will provide an opportunity to identify and agree on a select set of high priority recommendations related to the drafting of manageable policy and/or legal texts to improve environmental governance.  One or two manageable and appropriate by-laws (or perhaps a code of conduct) and operational guidance to mainstream Rio Conventions will be formulated through learning-by-doing workshops, validated and endorsed for approval by the Project Steering Committee.

An activity under this output will include the distribution of existing relevant codes, laws and texts pertaining to Rio Convention implementation.  The purpose of this activity is to circulate a complete set of key texts, including already gazetted instruments, in order that planners and other users have a complete set of the key texts that inform effective environmental governance of the Rio Conventions.

- Target indicator(s)

- At least six learning-by-doing training workshops to understand and reconcile weaknesses and gaps in key environmental policies and legal instruments will have been undertaken, beginning in year two.  Each workshop having at least 30 unique participants (i.e., no repeat participants).  Gender balance will be reflected by at least 20% females over the total number of workshop participants.  Participants should reflect a balance of all relevant public and non-state agencies.  The total number of unique participants in the workshops should be at least 120 people.

- The targeted small set of by-laws that were recommended to catalyze Rio Convention mainstreaming for formulation by the Project Board will be formulated, and the supporting operational guidance prepared by month 21.  The formulation exercise will benefit for an independent peer-review process followed by stakeholder validation.

- Approval of by-laws and any other amended policy, legislative, or regulatory texts are secured by month 24.

- Updated codes, laws and relevant texts pertaining to Rio Convention implementation are distributed to all relevant government bodies, both regional and national.  There will be four distribution runs, two in year 2, one in year three, and one in year four.  The number of copies to be printed will be determined closer to the time of publication.

Output 2.3	Strengthened consultative and decision-making processes for mainstreaming of Rio Convention obligations.

This output will include, among others, information-sharing and collaborative agreements, inter-ministerial committee(s) on MEAs; and non-state consultative committee(s).  Consultations will result in the identification and agreement on priority channels of environmental information exchange across sectors and ministries.  Working group meetings will be convened to negotiate best consultative and decision-making processes.  These will be important to catalyze action to monitor and enforce environmental policy.  One or more memoranda of agreement on consultative and decision-making processes will be drafted and approved.

- Target indicator(s)

- A series of working group meetings to negotiate best consultative and decision-making processes will be convened.  The number of meetings will be determined on an as needed basis, beginning in year one, with a validation on the best appropriate and applicable processes completed by month 19.

- Memoranda of agreement on consultative and decision-making processes will be drafted and agreed upon on a yearly basis.  More than one memorandum may be needed, and this will be decided during project implementation on the basis of need.

Output 2.4	Targeted updating and streamlining of institutional mandates to facilitate and catalyze long-term action to meet global environmental obligations

The various mandates and operational plans of the relevant national commissions, local and regional authorities, and other key institutions to integrate Rio Convention obligations will be reconciled and harmonized.  This work will be based on the project's analyses and recommendations, with particular reference to institutionalize the learning-by-doing exercises carries out in outputs 1.6, 1.7, and 2.2.  Drafts will be prepared through stakeholder consultations and learning-by-doing workshops, peer reviewed, and validated.

- Target indicator(s)

- The various mandates and operational plans of the relevant national commissions, local and regional authorities, and other key institutions to integrate Rio Convention obligations will be reconciled and harmonized.  This will be undertaken in four manageable sets of harmonization exercises, to take place in each of the four years of project implementation.  The final harmonization will have been completed by month 39.

- Output 2.5	Enhanced monitoring and compliance arrangements, e.g., environmental impact and strategic environmental assessments

Current data collection and generation methods of key agencies will be assessed, paying particular attention to harmonization and metrics, relevance, validity, and quality.  This will be complemented by an assessment of existing guidelines, tools, and resources.  These assessments will inform activities to strengthen the relevant policy and legal texts and arrangements of outputs 2.2 and 2.3.

Improved monitoring and compliance reforms based on learning-by-doing exercises to formulate best practices and guidelines will be recommended after broad-based consultation with stakeholders.  Taking into account these recommendations, learning-by-doing working groups meetings will be organized and actively attended by relevant stakeholders to draft and validate guidelines for coordinated monitoring and compliance.  Quality control/validation procedures will be developed to ensure accuracy and validity, and responsible scientific and institutional correspondents will be identified to strengthen the objectivity and independence of control and validation procedures.

- Target indicator(s)

- An assessment of the current data collection and generation methods of key agencies with attention to harmonization and metrics, relevance, validity, and quality will have been prepared, peer reviewed, and completed by month 7.

- Recommendations for improved monitoring and compliance reforms based on learning-by-doing exercises to formulate best practices and guidelines will be approved by the Project Board on the basis of the assessment of 2.5.1.  Accompanying guidelines for coordinated monitoring and compliance will be drafted, peer reviewed and validated by month 28.  Supporting quality control/validation procedures will be developed and the final and longer-term responsible scientific and institutional correspondents identified by month 39.

Output 2.6	Demonstration and piloting of integrated environmental-development best practices that reflect global environmental priorities and the Post-2015 Sustainable Development Goals

In conjunction with outputs 1.7 and 2.3, technical working groups for each of the three Rio Conventions on legislative responses and amendments will be organized.  Consideration of other MEAs would be appropriately included in the working groups.  Stakeholder consultations will help identify and select the environmental-development best practices that are to be piloted through the use of the EKMS for a high value sectoral development plan.  The results of the demonstrations and piloting will feed into a comprehensive assessment of lessons learned and best practices through the early implementation and piloting of the EKMS for Rio Convention mainstreaming that will be undertaken as part of out 1.7.

- Target indicator(s)

- Four technical working groups for each of the three Rio Conventions on legislative responses and amendments will be organized and convened at regular intervals (twice per year) throughout project implementation.  Three technical working groups will be organized, one for each of the three Rio Conventions, while the fourth technical working group dedicated to the selected sector.

- Environmental-development best practices will be identified and used to inform the piloting of the EKMS for a high value sectoral development plan.  This will be undertaken through a broad-based process of stakeholder consultations and their active engagement of stakeholders in the actual piloting exercises.  The piloting exercises may begin as early as in the latter months of year and completed by the end of year three.

- An assessment of lessons learned and best practices will be undertaken of the piloted EKMS will be prepared in year 4, and completed by month 40.

Output 2.7	Resource mobilization strategy

Under this output, a financial and economic analysis of monitoring, enforcement, and compliance of Rio Convention implementation will be undertaken.  The analyses will seek to emphasize realistic sources of traditional and innovative financing that will inform the development of the resource mobilization strategy.  This background analyses will be peer reviewed by an expert group of independent finance and economic experts, and work with champion stakeholders to champion resource mobilization efforts.

The background analyses will serve as the foundation of series of learning-by-doing workshops to draft the resource mobilization strategy.  This will include independent peer review of drafts and its finalization through a validation process.  The strategy will also be formally approved to ensure its legitimacy among key social actors.  Particular attention in the strategy will be given to catalyzing the implementation of the NCSA Action Plan developed under output 4.4 and to ensure the long-term financial sustainability of the EKMS for Rio Convention mainstreaming.

- Target indicator(s)

- A financial and economic analysis of monitoring, enforcement, and compliance of Rio Convention implementation will be undertaken, peer reviewed, and completed by month 8.

- A series of learning-by-doing workshops will be convened to draft a resource mobilization strategy.  The number of workshops will be determined at the time that this activity is being organized.  At least 50 stakeholders from different agencies will have participated through the entire drafting process, which will be completed by month 16.  The strategy will be reviewed in year three, identifying areas where the strategy needs to be improved, followed by a last set of learning-by-doing workshops to revise and update the strategy.  This will be completed by month 40.

Component 3:		Improving awareness of global environmental values

This component is critical to addressing the institutional sustainability of project outputs by raising an overall understanding and greater value of how addressing global environmental obligations under the Rio Convention contribute to addressing important and immediate socio-economic development priorities.  The outputs and activities are a critical element of the project’s strategy to ensure long-term sustainability of the capacities developed under the project.  As outlined above, there is inadequate understanding of the importance that global environmental values contribute to sustainable development, and even fewer that are responsible for strategic planning, decision-making, and policy formulation.   These outputs will complement the capacity building activities of components 1 and 2 by widening the field of stakeholders that are less directly implicated in policy and planning processes.  These outputs and activities will be further elaborated and organized through a public awareness campaign that will be prepared at the initiation of the project.

At the time that these activities will be implemented, their substantive content will be largely informed by the analyses and technical workshops carried out under components 1 and 2.  For example, the three public policy dialogues to be convened under output 3.1 will be structured to highlight key challenges and missed opportunities to catalyze Rio Convention mainstreaming through improved data and information management and policy formulation.  In another example, brochures and articles will be prepared to help reach wider audiences.

Output 3:1	Stakeholder dialogues on the value of Rio Conventions

Activities under this output will comprise a set of consultations with expert informants and stakeholders, in the form of simple one-on-one meetings to larger workshops and two major conferences to launch and wrap-up the project.  They will include dialogues to catalyze awareness-raising on global environmental issues among all stakeholder types, including and in particular the private sector and the media.

- Target indicator(s)

- A one-day Kick-Off Conference will be organized and convened to launch the project (convened by month 3) and a one-day Project Results Conference to present the lessons learned at the conclusion of the project (by month 44).  At least 100 stakeholder representatives are expected to participate from beginning to end of both conferences.

- A public awareness and communication campaign plan will be developed, peer reviewed, and validated by month 7.

- Six public policy dialogues will be convened, each with at least 30 unique stakeholder representatives, for a total of at least 180 unique stakeholders.  Two sets of dialogues will be convened at the beginning of years two, three, and four.

- Six national and sub-national awareness workshops will be convened, each with at least 30 unique stakeholder representatives, for a total of at least 180 unique stakeholders.  Two sets of workshops will be convened at the beginning of years two, three, and four.

- Three private sector sensitization panel discussions on the global environmental issues will be convened, each with at least 30 unique stakeholder representatives, for a total of at least 90 unique stakeholders.  The dialogues will be convened at the beginning of years two, three, and four.

- Four sets of workshops targeted to media professionals to improve environmental reporting will be convened, one each year beginning in year one, about one year apart, with the last one convened by month 41.  At least 15 unique stakeholder representatives will participate in each workshop, for a total of at least 60 unique stakeholder representatives.

Output 3.2	Brochures and articles on the Rio Conventions

This output will be focused on the preparation of brochures and articles that are intended to be strategically distributed and published to reach a wide Liberian audience.  The brochures will be translated into the local dialect as these will be largely targeted to regional communities.

- Target indicator(s)

- Brochures and articles on linkages between the global environment and socio-economic issues will be prepared and published in popular media for wide circulation.  At least three relevant articles and five brochures will be prepared and published in years 1, 2 and 3.  The brochures will be translated into the local dialect.  At least 2,000 copies of the brochures will be printed and distributed at high schools throughout Liberia.

Output 3.3	Public service announcement(s) on globally sensitive and environmentally-friendly behavior

A public service announcement will help promote awareness on the importance of the global environment, especially because of the relatively low literacy rate in Liberia.  This will be prepare in the local dialect and targeted to people throughout Liberia, with the preferred medium being radio as the predominant means of communication with the public.

- Target indicator(s)

- A public service announcement on Rio Convention mainstreaming will be prepared and aired in years 2, 3, and 4 on a regular basis.

Output 3.4	Improved environmental educational curriculum and youth civic engagement

Improving environmental education and youth civic engagement is a major contribution to helping institutionalize long-term environmentally-friendly behaviour for Liberia to meet and sustain Rio Convention obligations.  This output is for the improvement of educational curricula, not the creation or formulation of an entire educational curriculum.  This output is focused on the development of an environmental module that would be integrated into targeted educational curricula at a select number of schools for piloting.  The activities under this output will strengthen a set of key systemic capacities that will ensure the resilience of institutions mandated to meet environmental objectives by increasing a large number of environmentally-friendly adherents.

- Target indicator(s)

- An awareness module for institutions on Rio Conventions mainstreaming and monitoring will be prepared, independently peer-reviewed, and validated by stakeholders.  The first module will be prepared by month 17, revised and updated at the beginning of year 3, and updated by month 39.

- An environmental awareness module will be prepared and integrated into pilot school educational curricula between months 13 and 17, and revised at the beginning of years three and four.  The integrated module will be tests in at least three schools in year two, six schools in year three, and nine schools in year four.

- A report on the lessons learned on the formulation and integration of an environmental module into school curricula will be prepared between months 40 and 44, with the results presented in the Project Results Conference in month 44.

Output 3.5	Internet visibility of integrated approaches to meet Rio Convention obligations and national sustainable development priorities

Internet visibility is an increasing opportunity and need to ensure that awareness on the importance of meeting obligations under the Rio Conventions will have on meeting Liberia’s socio-economic development priorities.  This visibility will help spread awareness and catalyze the adoption on alternative and better environmentally-friendly and sustainable development practices.

- Target indicator(s)

- A series of working group meetings among key agencies that have websites relevant to environmental governance will be convened to negotiate opportunities to improve the design and content of their respective webpages.   After a preliminary set of working group meetings in months 6 - 8 to review and major initial tweaks agencies' website, subsequent working group meetings at the beginning of years two, three and four will be conducted to update and improve the content of the websites.  The last set of working group meetings will produce a memorandum of agreement of all agencies to continue this process post-project closure over the long term.

- A Facebook page on environmental information and Rio Convention mainstreaming will be created by month 3, with relevant content uploaded at least twice per week.  The number of members will be 1,500 by month 12, 3,000 by month 24, 4,000 by month 36, and 5,000 by month 44.

Component 4:		Updating the National Capacity Self-Assessment

This fourth component will update Liberia’s NCSA that was prepared in 2005.  This will serve to reinvigorate the consultative and collaborative approach developed under the NCSA to reconcile and integrate the capacities necessary to strengthen global environmental outcomes.  This new NCSA will emphasize the underlying capacity development needs (systemic, institutional, and individual) that cut across the three Rio Conventions.  The Capacity Development Action Plan will be formulated in a way that serves to reinforce parallel capacity building strategies and action plans.  These activities will be carried out in the last two years of the project, building on the assessments and work carried out in the first two years of the project, including the resource mobilization strategy and the lessons learned study.

In particular, the updated NCSA will reflect post 2015- Sustainable Development Goals and the latest opportunities to strengthen priority foundational capacities for the global environment.  The previous assessment was undertaken in 2006, and serves as a basis for the present project to strengthen targeted capacities.  However, in the decade since the NCSA was undertaken, there have been a number of important policy and institutional changes that have emerged as a basis of the change in political leadership.  The updating of the NCSA will serve as an opportunity to reconcile and update the current capacity challenges necessary to support the government’s pursuit of sustainable development in tandem with the fulfillment of Rio Convention obligations.

A very important requirement in the execution of this component, as with the other activities of the other components, is to ensure that stakeholder engagement is broad-based among various agencies and ministries, academic and research institutions, private sector, non-governmental organizations, and civil society representatives.

Output 4:1	Updated assessments of capacity challenges to meet and sustain Rio Convention obligations, building upon GEF focal area enabling activities

This output will comprise activities to prepare and validate baseline assessments and strategic directions to strengthen systemic, institutional, and individual capacities needed to meet and sustain long-global environmental outcomes.

- Target indicator(s)

- A methodology to update the NCSA and integrate the post-2015 SDGs will be prepared and validated at a stakeholder workshop no earlier that month 25.

- A survey to assess public awareness of the importance of the Rio Conventions to catalyzing sustainable development will be designed between months 7 and 9, with the survey repeated between months 29 and 30, and once more between 42 and 44.  The total number of survey respondents for each survey should be at least 500.

- Individual stakeholder interviews, as many as is deemed necessary, to gather additional inputs on national priorities and constraints for improved and sustained environmental governance will be conducted.  Summaries of all interviews will be prepared and collated into a report by month 30.

- Three thematic assessments, one for each of the three Rio Conventions, of the challenges and opportunities to meet obligations will be drafted by 32.

Output 4.2	Integrated cross-cutting analysis of systemic, institutional, and individual capacity development priorities

This output will build on the results of earlier project activities, emphasizing the preparation of a synthesis and integrated analysis of capacities that cut across the three Rio Conventions.  This exercise will include other relevant multilateral environmental agreements.  Particular attention will be given to integrating the Post-2015 MDGs.  Stakeholder consultations as the local, regional and national level, as well independent peer review and validation processes.

- Target indicator(s)

- A synthesis report on the findings and assessments of output 4.1 will be organized according to the systemic, institutional, and individual capacity development challenges, priorities, and opportunities to meet and sustain Rio Convention obligations within the framework of national sustainable development priorities.  This report will be completed by month 36 and presented at a two-day stakeholder workshop.

Output 4.3	Capacity Development Strategy and Action Plan, building on action plans of GEF focal area enabling activities

This output will bring together the work of the consultations, assessments, and agreements undertaken and made to construct an integrative and strategic programme of work to build foundational capacities to meet and sustain global environmental objectives.

- Target indicator(s)

- The action plans of GEF focal area enabling activities (such as the national strategies and actions plans under the three Rio Conventions) as well as other national sustainable development strategies will be reviewed and discussed in working group meetings.  These will be organized as thematic working group meetings for each of the three Rio Conventions and concluded by month 39.

- A capacity development strategy and action plan will be formulated on the basis of the results of 4.3.1 and outputs 4.1 and 4.2 by month 41.  This plan will be validated at a stakeholder validation workshop by month 41.

Output 4.4	Update NCSA Final Report

This output will include activities to prepare the NCSA final report, validate it at a large stakeholder workshop, leverage financial support, and encourage wider national support at its presentation at the CCCD Project Result Conference.

- Target indicator(s)

- An NCSA Final Report will be drafted and validated at a stakeholder validation workshop by month 44.

- A roundtable for donors will be convened immediately after the NCSA Validation Workshop to present the NCSA and Action Plan in order to leverage financial support from development partners.

- The NCSA Final Report and Action Plan will be presented at the Project Result Conference by month 45.

## C.3	Project Indicators

At the project objective level, there are three key outcome indicators (per the Integrated Results and Resources Framework – IRRF) that will serve to guide the overall adaptive collaborative management of the project through effective monitoring and feedback mechanisms.  At the project objective level, there are three indicators that respond specifically to the requirement for all UNDP/GEF projects to track their contribution to meeting expected outcome targets under the UNDP 2014-2017 Strategic Plan.  An assessment of the baseline for the relevant indicator is provided, as well as end-of-project target indicators.  As a medium-sized project, there will not be an independent midterm evaluation to monitor and track project indicators.  The Outcome Indicators against which project results will be measured are:

Indicator 1 (IRRF Output 1.3): Solutions developed at national and sub-national levels for sustainable management of natural resources, ecosystem services, chemicals and waste.

Indicator 1.3.1:  Number of new partnership mechanisms with funding for sustainable management solutions of natural resources, ecosystem services, chemicals and waste at national and/or subnational level.

Indicator 1.3.2: a) Number of additional people benefitting from strengthened livelihoods through solutions for management of natural resources, ecosystems services, chemicals and waste b) Number of new jobs created through solutions for management of natural resources, ecosystem services, chemicals and waste.

Indicator 2 (IRRF Output Indicator 2.5): Legal and regulatory frameworks, policies and institutions enabled to ensure the conservation, sustainable use, and access and benefit sharing of natural resources, biodiversity and ecosystems, in line with international conventions and national legislation.

- Indicator 2.5.1:  Extent to which legal or policy or institutional frameworks are in place for conservation, sustainable use, and access and benefit sharing of natural resources, biodiversity and ecosystems.

- Indicator 2.5.2: Extent to which capacities to implement national or local plans for integrated water resource management or to protect and restore the health, productivity and resilience of oceans and marine ecosystems have improved.

- Indicator 3 (IRRF):  Number of direct beneficiaries.  This indicator is a measure of how many stakeholders have benefitted from project capacity building activities.  During project execution, participants to all learning-by-doing workshops will be recorded and the number of unique participants counted (to avoid double counting).

The fourth key outcome indicator is: Indicator 4: Sectoral plans and policies include targets that measure progress toward achieving global environmental obligations.

During project implementation, the structuring of activities that serve to deliver project outputs should include the development of a set of output-specific indicators, comprised of an appropriate blend of product, process, and performance indicators.  These should also be formulated using SMART design criteria.  Product indicators include the preparation of in-depth baseline analyses including an analysis of the policy and legal framework limiting Rio Convention mainstreaming, an analysis of data and information indicators, an analysis of the current management information system, and a baseline analysis of the understanding of Rio Convention mainstreaming.  Process indicators include the convening of working groups that will facilitate better inter-agency communication, coordination, and collaboration with regard to the development of an environmental information management and decision support system.  Performance indicators include the set of learn-by-doing review of best practices, codes, laws, and texts pertaining to protection of the global environment.  Taking into account the above, there are certain key indicators that the project must deliver in order that the project can be deemed transformative and sustainable.

By the end of the project, the following key output indicators should be achieved:

- Indicator 5: Memoranda of agreement must be negotiated and signed among government and non-state stakeholders on the sharing of data and information.

- Indicator 6: Liaison protocols between key government agencies must be updated and signed to strengthen sharing of data and information and proactive collaboration in the operation of the integrated EKMS.

- Indicator 7: The project facilitates broad-based stakeholder workshops to negotiate and institutionalize best practice consultative and decision-making processes to access best available data, information and knowledge.

- Indicator 8: Operational by-laws are developed to improve and legitimize Rio Convention mainstreaming into sector development plans.

- Indicator 9: All stakeholders agree by consensus on a key set of higher-order indicators to monitor the progress the country is making towards meeting and sustaining Rio Convention obligations.

- Indicator 10: A data protocol system is developed and tested that allows data, information, and knowledge to be tracked through the life cycle of their creation to informing policy and plans to the latter’s adaptive management.

- Indicator 11: Key existing databases, management information systems, and monitoring systems are strategically networked into an integrated system (the EKMS).

- Indicator 12: A pilot project to test the application of the EKMS is carried out on a high value sector development plan at the local self-governing authority.

- Indicator 13: A long-term training programme is developed and institutionalized on Rio Convention mainstreaming based on lessons learned from the project’s learning-by-doing workshops and related exercises

- Indicator 14: A resource mobilization strategy for the long-term operation (e.g., 15 years) of the EKMS is developed and approved by the Government Apparatus

- Indicator 15: A government-based website is created to network existing sources of electronic data and information

- Indicator 16: Education module on the importance of the global environment to national sustainable development is adopted and integrated within teaching curricula at the secondary school level

- Indicator 17: Collectively and over the three years of project implementation, the awareness-raising workshops engage over 700 unique stakeholders

- Indicator 18: NCSA Final Report and Capacity Development Action Plan is completed

The project will monitor other indicators as a means to help the regular monitoring of project performance.  These indicators take into account the key risks and assumptions made on the project’s design.  During project implementation, indicators may be added or refined in keeping with practical realities, while taking care not to reduce the standards of project performance or delivery.

## C.4	Global Environmental Benefits

Cross-cutting capacity development projects focus on strengthening the underlying capacities of programme activities, thus, they do not directly yield global environmental benefits.  Rather, this project, like other CCCD projects, will provide Liberia with additional tools and strengthen institutional arrangements to facilitate effective and sustained action to meet Rio Convention obligations.

CCCD projects are measured by output, process, and performance indicators that are proxies to the framework indicators of improved capacities for the global environment.  Project indicators will include output indicators such as the systematic identification of data needs for all three Rio Conventions, process indicators such as workshops that include technical staffs from all key departments and agencies

CCCD projects look to strengthen cross-cutting capacities in the five major areas of stakeholder engagement, information and knowledge, policy and legislation development, management and implementation, and monitoring and evaluation.  This project responds to all five categories of articles under the three Rio Conventions, demonstrating both the global environmental value of the project and its cross-cutting capacity development strategy.

- Table 1:  Capacity development requirements of the Rio Conventions

| Type of Capacity | Convention Requirements | UNFCCC | UNCBD | CCD |
| --- | --- | --- | --- | --- |
| Stakeholder Engagement | Capacities of relevant individuals and organizations (resource users, owners, consumers, community and political leaders, private and public sector managers and experts) to engage proactively and constructively with one another to manage a global environmental issue. | Article 4 Article 6 | Article 10 Article 13 | Article 5 Article 9 Article 10 Article 19 |
| Organizational Capacities | Capacities of individuals and organizations to plan and develop effective environmental policy and legislation, related strategies, and plans based on informed decision-making processes for global environmental management. | Article 4 Article 6 | Article 8 Article 9 Article 16 Article 17 | Article 4 Article 5 Article 13 Article 17 Article 18 Article 19 |
| Environmental Governance | Capacities of individuals and organizations to enact environmental policies or regulatory decisions, as well as plan and execute relevant sustainable global environmental management actions and solutions. | Article 4 | Article 6 Article 14 Article 19 Article 22 | Article 4 Article 5 Article 8 Article 9 Article 10 |
| Information Management and Knowledge | Capacities of individuals and organizations to research, acquire, communicate, educate and make use of pertinent information to be able to diagnose and understand global environmental problems and potential solutions. | Article 4 Article 5 | Article 12 Article 14 Article 17 Article 26 | Article 9 Article 10 Article 16 |
| Monitoring and Evaluation | Capacities in individuals and organizations to effectively monitor and evaluate project and/or programme achievements against expected results and to provide feedback for learning, adaptive management and suggesting adjustments to the course of action if necessary to conserve and preserve the global environment. | Article 6 | Article 7 | N/A |

# D.	Project Partnerships

The project supports the meaningful participation and inclusion of all stakeholders, during the design, implementation, monitoring, and adaptive collaborative management of the project.  Stakeholders will participate in capacity development activities and the project will support the development of an enabling environment conducive to the active engagement of stakeholders in the management of natural resources.  This approach is consistent with the participation and inclusion of human rights principle.

Taking an adaptive collaborative management approach to execution, the project will ensure that key stakeholders are involved early and throughout project execution as partners for development.  Stakeholder representatives from NGOs, communities, the private sector, academia, among others, will be encouraged to actively engage with government representatives as partners in carrying out project activities or components thereof.  This will help capitalize on stakeholders’ comparative advantages, as well as to create synergies, strengthen a more accurate holistic and resilient construct of policy interventions, and improve legitimacy.  These partnerships will also help ensure a more equitable distribution of benefits.

## D.1	Stakeholder Engagement

During the project formulation phase, consultation sessions and meetings were undertaken with a diverse group of stakeholders in order to construct as holistic as possible an understanding of the challenges and barriers related to coordination and decentralization for improved decision-making for the global environment, i.e., the project baseline.  The project design makes the assumption that the consultations during project formulation strengthens the transparency and legitimacy of the proposed project activities, notwithstanding that during project implementation, activities can and should be adapted to ensure that the human rights of stakeholders are preserved and/or reinforced.

During implementation, the project’s extensive stakeholder consultations, learning-by-doing workshops, and awareness-raising dialogues are intended to engage as many people as possible in order to reduce the risks of marginalizing stakeholders and incorporating their diverse perspectives in as many project activities as possible.  During implementation, stakeholder engagement should also be as early as possible, allowing for increased ownership and thus sustainability.  Notwithstanding, decisions must be negotiated in a way that also ensure that all stakeholders receive satisfactory levels of benefits and equity, which are also critical to sustainability.  As part of consultations and workshops, stakeholders will be informed of mechanisms to submit concerns about the social and environmental impacts of the project.  This is intended to support the adaptive collaborative management of the project.

The formulation phase of the project involved undertaking a number of individual consultations, as well as workshops to both launch the project as well as to validate the project design.  The specific civil society and non-governmental organizations that participated in the formulation of this project were as follows:

- Society for the Conservation of Nature of Liberia:  This organization is mainly involved in nature conservation and protected area management.

- Farmers Associated to Conserve the Environment:  This civil society association works with farmers to learn and apply new and improved sustainable agricultural practices and mangrove conservation

- Fauna and Flora International:  This is an international NGO currently working Liberia to support on-the-ground activities to conserve biodiversity and adapt to the impacts of climate change

- Conservation International:  This is an international NGO is also working in Liberia involved in biodiversity conservation and is an accredited GEF Implementation Agency

Once implementation of the project begins, key stakeholders will meet on a regular basis through the Project Steering Committee so that they are aware of the progress of the project and contribute to the project.  Additionally, the project has select activities to strengthen institutional mechanisms for improved coordination and collaboration.

The first mechanism stakeholders may utilize to express concerns about the project’s impacts is the implementing partner’s grievance resolution mechanism.  The second is the UNDP Country Office’s existing project management procedures.  Concerned stakeholders can engage with UNDP project staff through Project Steering Committees or through direct contact with the relevant UNDP programme manager.  UNDP’s Social and Environmental Compliance Review and the Stakeholder Response Mechanism will provide a third avenue for situations in which project stakeholders have not been satisfied with the responses they have received through the first two mechanisms.  The Stakeholder Response Mechanism should also be used when the Implementing Partner’s or UNDP’s actions are the source of the grievance.

Indigenous peoples are present in Liberia.  Thus, the application of the principles of Free Prior and Informed Consent is necessary to avoid risks which might arise from policy changes and/or the use of local knowledge in the project design and implementation.  Gender-equality issues will be considered to the extent that they are appropriate, defined by the criterion of gender inequality being a direct barrier to coordination; the access of information and creation of knowledge to inform decision-making; and decentralization; to meet global environmental obligations.  For a more detailed description of gender inclusion see the section on gender mainstreaming below.

The main project stakeholders are the government ministries that are responsible for key sectoral policies and legislation.  A number of government bodies operating at both the national and local levels are responsible natural resource and environmental management, working with local community organizations and in some cases partnering with NGOs to undertake particular activities.  Other stakeholders include the private sector and academic institutions that are important to ensuring the long-term sustainability of the project.  The private sector is a particular important stakeholder to environmental issues.  Other key stakeholders are those from the rural areas in that they have a major stake in the sustainable management of natural resources.  For the most part, these stakeholders are most at risk from land degradation as well as contributing to it through poor and unsustainable land management practices.  Table 2 provides more details about stakeholder involvement.

- Table 2: Stakeholders, mandates, and roles in project implementation

| Stakeholder | Mandate | Possible roles in project execution |
| --- | --- | --- |
| EPA | The EPA protects the environment by implementing policy that ensures the long-term economic prosperity of Liberia through sustainable, social and economic development. The aim is to meet the needs of the present generation without undermining the potential of future generations. As its key function, the EPA (Section 5 of the Environmental Protection Agency Act), is mandated to collaborate with line ministries and agencies to (i) co-ordinate, integrate, harmonize and monitor the implementation of environmental policy and integrate environmental concerns in overall national planning; (ii) collect, collate, and analyze basic scientific data and other information pertaining to pollution, degradation of ecosystems and on environmental quality and resource use, (iii) train and build the capacity of line ministries and agencies; and (iv) ensure the preservation and promotion of important historic, cultural and spiritual values of natural resource heritage and, in consultation with local authorities, enhance effective natural resource management plans and activities. | As the executing government agency, the Ministry will be responsible for overall implementation of the project. |
| Ministry of Internal Affairs | The Ministry of Internal Affairs is responsible for decentralization, progress, and development in Liberia. It also promotes and encourages communal farming, particularly seed production, as a means of ensuring food security. | - Participation in capacity building working group meetings - Contribute to cross-sectoral integration - Contribution to national and regional level Rio Convention mainstreaming - Beneficiaries of mainstreaming activities - Beneficiaries of awareness raising and skill development activities |
| Ministry of Lands, Mines and Energy | This ministry administers activities relative to land, mineral, water and energy. The Ministry formulates and implements policies and provides industry with information about Liberia’s geology. It also works along with the Ministry of Agriculture and the University of Liberia to conduct training and research on land rehabilitation. | - Participation in capacity building working group meetings - Contributions to capacity needs assessment - Participation in national stakeholders fora - Contribution to the determination of appropriate environmental information channels and flow - Contribution to national level Rio Convention mainstreaming - Contribution to national level long-term mainstreaming strategy - Beneficiaries of mainstreaming activities - Beneficiaries of awareness raising and skill development activities |
| Ministry of Agriculture | The Ministry of Agriculture works to develop the agriculture sector through effective organizational structures and agricultural development programs. | - Participation in capacity building working group meetings - Contributions to capacity needs assessment - Participation in policy and finance core team - Participation in high-level policy dialogue events - Participation in national stakeholders fora - Contribution to identify type and format of environmental information - Contribution to the determination of appropriate environmental information channels and flow - Contribution to national level Rio Convention mainstreaming - Contribution to national level long-term mainstreaming strategy - Beneficiaries of mainstreaming activities - Beneficiaries of awareness raising and skill development activities |
| Ministry of Transport | The Ministry of Transport establishes policy frameworks to ensure an effective and efficient service delivery, and infrastructure development. | - Participation in capacity building working group meetings - Contributions to capacity needs assessment - Participation in policy and finance core team - Participation in high-level policy dialogue events - Participation in national stakeholders fora - Contribution to identify type and format of environmental information - Contribution to the determination of appropriate environmental information channels and flow - Contribution to national level Rio Convention mainstreaming - Contribution to national level long-term mainstreaming strategy - Beneficiaries of mainstreaming activities - Beneficiaries of awareness raising and skill development activities |
| Ministry of Finance and Development Planning | The Ministry of Finance and Development Planning formulates, institutionalizes and administers fiscal, economic development, and tax policies. | - Participation in capacity building working group meetings - Contributions to capacity needs assessment - Participation in policy and finance core team - Participation in high-level policy dialogue events - Participation in national stakeholders fora - Contribution to identify type and format of environmental information - Contribution to the determination of appropriate environmental information channels and flow - Contribution to national level Rio Convention mainstreaming - Contribution to national level long-term mainstreaming strategy - Beneficiaries of mainstreaming activities - Beneficiaries of awareness raising and skill development activities |
| Department of Rural Development | This department develops and implements strategies and programmes to improve the living conditions of the rural population. | - Participation in capacity building working group meetings |
| Ministry of Commerce and Industry | The Ministry of Commerce and Industry develops policies for commerce and trade to facilitate private sector growth and innovations. | - Participation in capacity building working group meetings - Contributions to capacity needs assessment - Participation in policy and finance core team - Participation in high-level policy dialogue events - Participation in national stakeholders fora - Contribution to identify type and format of environmental information - Contribution to the determination of appropriate environmental information channels and flow - Contribution to national level Rio Convention mainstreaming - Contribution to national level long-term mainstreaming strategy - Beneficiaries of mainstreaming activities - Beneficiaries of awareness raising and skill development activities |
| Forestry Development Authority | The Forestry Development Authority is responsible for the sustainable management of forest and forest resources, and is charged with ensuring the effective governance and management of the country’s protected areas system. | They can support the project activities and also benefit from the project capacity building activities. - Participation in national stakeholders fora - Participation in learning networks - Participation in learning activities |
| Land Authority | The Land Authority proposes, advocates and coordinates reforms of land policy, laws, and programs with the ultimate aim of ensuring equitable and productive access to the nation’s land, both public and private, security of tenure in land and the rule of law with respect to landholding and dealings in land, and effective land administration and management. | They can support the project activities and also benefit from the project capacity building activities. - Participation in national stakeholders fora - Participation in learning networks - Participation in learning activities |
| Liberia Reconstruction and Development-Committee | The Liberia Reconstruction and Development-Committee provides the Presidency with a means of enhancing partner coordination and internal government management. | They can support the project activities and also benefit from the project capacity building activities. - Participation in national stakeholders fora - Participation in learning networks - Participation in learning activities |
| Ministry of Public Work | The Ministry of Public Works provides basic social and physical services such as feeder roads, improved sanitation and piped water as a means to improve the livelihood of rural peoples. | They can support the project activities and also benefit from the project capacity building activities. - Participation in national stakeholders fora - Participation in learning networks - Participation in learning activities |
| National Bureau of Concession | Has the mandate to monitor concessions and report to the relevant ministries and National Legislature to inform decision-making. | - Participation in capacity building working group meetings |
| Ministry of Education | The Ministry of Education Liberia works to build a better future for the country’s children by delivering quality and affordable education. | They can support the project activities and also benefit from the project capacity building activities. - Participation in national stakeholders fora - Participation in learning networks and activities - Will work with the EPA to formulate and integrate an environmental module into a subset to educational curricula (see output 3.4) |
| Local Government | These stakeholders are responsible for planning, development, and implementation at the community levels. They work closely with the NGOs and CBOs. | Their roles would be to support the implementation of the project at the local levels. They can support the project activities and also benefit from the project capacity building activities. - Participation in national stakeholders fora - Participation in learning networks - Participation in learning activities - Participation in improved data and information availability activities |
| NGOs | - These non-state stakeholders are important partners for development. They provide financial and technical support. | Their roles would be to work in collaboration with the EPA to implement activities of the project. Additionally, they can be potential financial or technical partners. - Participation in learning events - Participate in developing strategy for replication and up-scaling of - Act as a vehicle for the introduction of new ideas - Represent the interests of the most vulnerable people in society - During project implementation, NGOs will participate in stakeholders’ consultations; potentially provide financial or technical advice; and provide data and information. |
| Private Sector | This includes development project proponents and investors whose operations are regulated by the government law/policy in terms of environmental management. | They can be potential financial and technical partners, and sources of data and information. - Participation in national stakeholders fora - Participation in learning events |
| Central Agricultural Research Institute | The Central Agricultural Research Institute is the only research organization in the country that has been carrying out applied and adaptive research covering food and tree crops, livestock, aquaculture, and related areas. | They can be potential financial and technical partners, and sources of data and information. - Participation in national stakeholders fora Participation in learning events |
| Academia and Research Institutions | Technical and research institutes include national universities and research institutes involved in conservation, agriculture and rural development, and ministerial institutes such as the University of Liberia. | These stakeholders are essential for data networks and provision of information for the monitoring of progress; they may also provide technical inputs and can benefit from capacity building. They will ensure that the planning and decision making at all levels is based on the most current information. |
| Rural communities | This includes individuals who face the greatest threat from the negative impacts of climate change | - Participation in national stakeholders fora - Participation in learning events |
| Gender/ Ministry of Gender and Development | These include a range of social actors that serve to promote the interest of gender, such as the Ministry of Gender and Development. | - Participation in national stakeholders fora - Participation in learning events |
| - International development and technical assistance partners | These partners are already involved in the Liberia with programmes, projects and financial assistance. These include multilateral (EU, IFAD, FAO, UNDP) and bilateral organizations (AFD/BMZ). | - Their role would be to work in collaboration with the EPA to implement activities of the project. Additionally, they can be potential financial or technical partners, providing co-financing and needed data and information. |

## D.2	Linkages with other Initiatives

Despite the important weaknesses in the government’s capacities to mainstream MEAs as described in the baseline section of this document, key agencies and institutions are undertaking important activities.  This includes the work of the Environmental Protection Agency as the focal point for the three Rio Conventions, to gather and analyze data and information for preparing policy notes to cabinet members, parliamentarians, and other policy-makers.  The EPA also prepares reports that document the country’s progress towards meeting their international obligations.

There are a number of initiatives that this project will coordinate with, as appropriate, including those receiving GEF financing.  In addition to these, there are a number of other non-GEF funded projects that contain related capacity building activities, and with which this project will require appropriate coordination.

- Projects include:

| Project name | Project activities that align with this project |
| --- | --- |
| Increasing energy access through the promotion of energy efficient appliances in Liberia | This project aims to increase access to electricity in rural Liberia while mainstreaming energy efficiency. Relevant activities include: training of staff, policy and legislation development, knowledge dissemination. |
| Improve Sustainability of Mangrove Forests and Coastal Mangrove Areas in Liberia through Protection, Planning and Livelihood Creation- as a Building Block Towards Liberia’s Marine and Costal Protected Areas | The objective of this project is to promote the conservation and sustainable use of mangrove forests. Relevant activities include awareness-raising within the government agencies, ministries and legislatures; and the creation of a multi-stakeholder integrated land-use planning and decision support toolkit. |
| GEF/UNDP Strengthening Liberia’s capability to provide climate information and services to enhance climate resilient development and adaptation to climate change | This project will increase the capacity of hydro-meteorological services; promote the efficient and effective use of climate, environmental, and socio-economic data to create information for government entities and communities to enable informed decision-making; and increase awareness in government, private sector and local communities. |

The design and implementation of the proposed CCCD project would also take into account the development plans of other bilateral and multilateral donors in Liberia to ensure appropriate alignment as well as to leverage the necessary co-financing.

During the implementation,  further discussions will be held with partner donor agencies, such as the World Bank and the Government of Norway,  that are supporting similar capacity building activities to determine the extent to which current and planned programmes and projects are complementary to the proposed CCCD project.  In 2015 Liberia accepted $150 million in aid from Norway.  This aid is ensure that by the year 2020 Liberia will stop legal logging, build up protection infrastructure, and make 30% or more of forest under protected area.  Additionally, the Government of Liberia has pledged to place a moratorium on new logging contracts, increase support and training for community based management of forests, and respect the rights of rural landowners, ensuring that decisions are made with their free, prior and informed consent.

A project steering committee will be created to facilitate active participation in project activities from these stakeholders and that recommendations and agreements negotiated will be deemed legitimate by the respective institutions of the participating stakeholder.  During the PPG phase, these coordination arrangements will be further discussed and elaborated.  These donor consultations will also serve to confirm the amount of co-financing to support project activities.

A Project Steering Committee will be created to facilitate active participation in project activities from these stakeholders and that recommendations and agreements negotiated will be deemed legitimate by the respective institutions of the participating stakeholder.  Donor consultations will confirm the amount of co-financing to support project activities.  Consultations with the project managers of the above-mentioned projects will reveal further complexities, potential synergies and conflicts with the proposed project activities.  These consultations will also begin the formal process of in-country coordination with related donor-funded projects that will continue throughout the project implementation in order to capitalize on emerging synergies.  Completed GEF projects will also be reviewed through evaluation reports and consultations with past project managers to identify lessons learned and best practices.

## D.3	Mainstreaming Gender

Women in Liberia face several equality issues.  While women comprise 54 percent of the labor force in both the formal and informal sectors, they disproportionately work in the least productive sectors, such as agriculture.  Additionally, illiteracy rates among women is particularly high (around 60 percent), and the maternal mortality rate is one of the highest in the world (United Nations, 2014).

Acknowledging these gender issues, the Government of Liberia has expressed commitment to achieving rights for women and gender equality.  Not only has the government acknowledged the link between gender issues and maintaining peace, promoting justice, advancing sustainable development, and reducing poverty, but the country has made great strides toward gender equality.  For example, two policy documents have been developed: the National Gender Policy and the National Action Plan on Implementation of UN Security Council Resolution 1325 (on women and peace and security).  Additionally, in 2005 Liberia elected Ellen Johnson-Sirleaf, the first female Head of State in all of Africa (United Nations, 2014).

Under current President Ellen Johnson-Sirleaf, the situation for women continues to improve.  As of 2012, women held 31 % of top ministerial posts and 29 % of the Deputy Minister positions.  Women were also head of 28% of key government agencies (i.e., Ministries of Foreign Affairs, Finance, Justice and Commerce and Industry) (The Office of the Executive Mansion, 2012).

The GEF policy on Gender Integration addresses the link between gender equality and environmental sustainability and towards the integration of the gender aspect in its policies, programs and operations.  It requires its agencies to have their own accredited gender policy.  UNDP has translated this commitment in its own UNDP Gender Strategy 2014 - 2017, which provides guidance on how to integrate gender in all UNDP supported activities.  Particularly in the promotion of biodiversity-based income generating activities, gender will be monitored in order to particularly concentrate on those activities most beneficial for the most vulnerable groups, such as women, youth, children, the elderly, landless and displaced people.  In the context of FPIC, particular attention will be given to the voice of these vulnerable groups in decentralized planning and consultation frameworks.

In much the same way that the GEF is supporting countries to mainstream the global environment into their national sustainable development planning frameworks, so too are they calling for gender equality issues to be mainstreamed in the GEF-funded capacity development interventions.  This strategy is consistent and complementary to UNDP’s 2014-2017 Strategic Plan that similarly calls for projects implemented by UNDP to meet high standards to meeting gender equality criteria.  Similarly, UNDP has prepared important guidance on their policy on Gender Equality, notably the UNDP Gender Equality Strategy 2014-2017 and Powerful Synergies: Gender Equality, Economic Development and Environmental Sustainability.

Gender mainstreaming from a project construct requires deliberate action to address the policy and institutional barriers that marginalize women.  While culture is certainly an important issue that generally have minimized or restricted access to economic and social benefits equal to their male counterparts, awareness-raising and alternative roles for women offer an opportunity for them to play a greater role in promoting ethical approaches to sustainable development.  The GEF policy for mainstreaming gender in the projects that they finance call for three requirements to be met (GEF, 2013):

- Gender mainstreaming and capacity building within GEF staff to improve socio-economic understanding of gender issues

- A designated focal point for gender issues to support development, implementation, monitoring and strategy on gender mainstreaming internally and externally

- Working with experts in gender issues to utilize their expertise in developing and implementing GEF projects

Notwithstanding, this is not to be misinterpreted that the GEF will finance activities that promote gender equality.  This is not an eligible use of GEF finance, but rather a new requirement of the strategic design of GEF-financed projects since April 2011.

Gender issues will be one of the social issues that will be monitored throughout project implementation.  The project design and implementation will ensure both an adequate balance of participation in the project, and the equitable distribution of benefits.  Additionally, to help ensure that gender does not become a marginalized issue, gender sensitive indicators to be monitored per good practice (Demetriades, 2007; Moser, 2007).  This gender monitoring and special consideration is in line with other gender initiatives in the Liberia, such as the Convention on the Elimination of all Forms of Discrimination against Women which the Liberia ratified in 1980.

At the time of project initiation, UNDP gender markers will be tracked.  These will be tracked on an annual basis as part of the Annual Progress Report/Project Implementation Review.  Other gender-relevant markers will be identified and tracked as appropriate:

- Total number and percentage of full-time project staff that are women

- Total number and percentage of Project Steering Committee members that are women

- The number and percentage of jobs created by the project that are held by women

- Total number and percentage of women that actively engaged in substantively in learning-by-doing workshops, dialogues, and key consultations and meetings

## D.4	South-South and Triangular Cooperation

This project’s approach to South-South and Triangular Cooperation is to encourage and strengthen shared self-reliance among developing countries through the exchange of experiences, best practices, and lessons learned.  This will be achieved by coordinating with on-going projects in the area, such as the Adapting to climate change induced coastal risks management in Sierra Leone project, or the Strengthening the resilience of vulnerable coastal areas and communities to climate change in Guinea Bissau project.  Like this CCCD project, these projects will promote policy and institutional development, the transmission of technology, and generating scientific knowledge and access to information.  During implementation, other related initiatives will be identified and lessons learned will be incorporated.

Sharing knowledge between nations will help achieve and sustain outcomes under this project by allowing for this project to a) preemptively address known problems, b) reduce the learning curve, and c) limit wasted resources by focusing efforts on proven techniques.

In addition to learning from other projects, best practices and lessons learned from this CCCD project will be disseminated so that other countries may benefit from Liberia’ experience.  For example, the tools on information and knowledge management and integrating the three Rio Conventions in national strategies and plans, the training courses on the environmental database and management information system software, and the training programme for mainstreaming the Rio Conventions could serve as models for other countries facing similar challenges.

This approach is in line with UNDP’s approach, which is to support South-South and Triangular Cooperation in order to maximize the impact of development, hasten poverty eradication, and accelerate the achievement of Sustainable Development Goals.

# E.	Feasibility

A project’s feasibility is assessed according to the following criteria: a) sustainability and scaling up, b) social and environmental safeguards, c) cost efficiency and effectiveness, and d) risk management.  This section covers risk management and social and environmental safeguards.  Sustainability and scaling up is covered in B.7, whereas the project’s cost efficiency and effectiveness appears in I.3.

## E.1	Risk Management

Notwithstanding that the project’s risks and association assumptions were assessed at a preliminary stage, one purpose of the project preparation phase is to undertake an in-depth assessment of these risks based on a more extensive set of consultations and review of the background documentation.  A more accurate assessment of the risks was therefore possible at the end of the project document preparation phase.

| Project risks |  |  |  |  |
| --- | --- | --- | --- | --- |
| Description | Type | Impact & Probability | Management Measures | Owner |
| Weak inter-institutional coordination | Operational Organizational | Given the multi-faceted nature of the project, engagement of a multitude of stakeholders is required. I=3 P=3 | To mitigate this risk, the project includes several approaches. During the proposal formulation, consultations were organized with key stakeholders to increase their understanding of the project and establish networks of collaboration. Once implementation of the project begins, key stakeholders will meet on a regular basis through the Project Steering Committee so that they are aware of the progress of the project and contribute to the project. Additionally, the project will have select activities to strengthen institutional mechanisms for improved coordination and collaboration. These include items like negotiating best consultative processes and memoranda of agreements. | Project Manager |
| Lack of absorptive capacity of national institutions to implement activities | Operational | A lack of absorptive capacity could undermine the achievement of outcomes, or lead to delays. I=3 P=3 I=2 P=2 | This risk will be managed by taking a learn-by-doing approach to project execution. The best way to raise absorptive capacities is for government staff to learn skills through critical thinking exercises such as early implementation of the EKMS. All project activities, including those that target systemic, institutional and individual capacities, will be designed through a comprehensive multi-stakeholder consultation to ensure they are implementable, including provisions for additional dedicated project staff. | Project Manager |
| Internal resistance to change | Political Operational | Internal resistance to change can undermine implementation and lead to delays. I=2 P=2 | - The activities of this project were strategically selected and designed to take into account these existing “business-as-usual” approaches, and to facilitate a process by they could be improved incrementally. Most, if not all, of the activities under this project call for such incremental modifications to be made. This approach serves to strengthen the ownership and legitimacy of the decisions reached in these stakeholder consultations, workshops, or other project exercises. | Project Manager |
| Financial limitations | Financial | Without continued financing, there may be insufficient commitment to implement project recommendations for post-project activities I=2 P=2 | Given that project results emerge through external financing and support, key project results must be sufficiently institutionalized if the larger outcomes are to be sustainable. The project includes a specific output on resource mobilization to address the issue of financial sustainability. Another project design feature to address this issue is that the demonstrated value of the project may strengthen the Government’s greater appreciation of the recommendations, and therefore more likely to support their approval for post-project implementation. | Project Manager |

As per standard UNDP requirements, the Project Manager will monitor risks quarterly and report on the status of risks to the UNDP Country Office.  The UNDP Country Office will record progress in the UNDP ATLAS risk log.  Risks will be reported as critical when the impact and probability are high (i.e., when impact is rated as 5, or when impact is rated as 4 and probability is rated at 3 or higher).  Management responses to critical risks will also be reported to the GEF in the Annual Progress Report.

## E.2	Social and Environmental Safeguards

The UNDP Social and Environmental Screening was completed and no risks were identified.  A project categorization is based on the highest level of significance of identified risks.  Since there are no identified risks in this project, the overall risk categorization of the project is low.  See Annex 4 for UNDP Social and Environmental Screening.  As a Low Risk project, no further social and environmental assessments are required.

During PPG, consultations were held to gain a better understanding of potential social and environmental impacts so that the project strategy would address these considerations, resulting in a more feasible project strategy.  The Project steering committee will negotiate any environmental and social grievances. Environmental and social grievances will be reported to the GEF in the APR.

# F.	Project Results Framework

Annex 3 is a plan that provides the additional information of frequency and responsibility for data collection as an additional tool to monitor the project results framework.

This project will contribute to the following Sustainable Development Goal (s): s): SDG 13, SDG 14, and SDG 15

This project will contribute to the following country outcome included in the UNDAF/Country Programme Document: UNDAF and Country Programme Outcome 2: Inclusive and sustainable economic transformation informed by evidence-based macro-economic policy promoting access to livelihood, innovative and competitive private sector and efficient natural resource management. UNDAF and Country Programme Outcome 4: Liberian governance systems strengthened to ensure consolidation of peace and stability supported by effective and well-functioning institutions that foster inclusive participation of stakeholders, especially women and youth, with enhanced service delivery at local levels.

This project will be linked to the following output of the UNDP Strategic Plan: Output 1.3: Solutions developed at national and sub-national levels for sustainable management of natural resources, ecosystem services, chemicals and waste. Output 2.5: Legal and regulatory frameworks, policies and institutions enabled to ensure the conservation, sustainable use, and access and benefit sharing of natural resources, biodiversity and ecosystems, in line with international conventions and national legislation.

|  | Objective and Outcome Indicators | Baseline | End of Project Target | Means of Verification | Assumptions |
| --- | --- | --- | --- | --- | --- |
| Project Objective To strengthen a targeted set of national capacities to deliver and sustain global environmental outcomes within the framework of sustainable development priorities. | Indicator 1: Number of new partnership mechanisms with funding for sustainable management solutions of natural resources, ecosystem services, chemicals and waste at national and/or subnational level. | Despite the presence of a number of capacity development interventions, absorptive capacity in Liberia is so low and insufficiently institutionalized that almost all solutions for the sustainable management of natural resources are only available within the construct of externally-funded projects. | A high quality integrated Environmental Knowledge Management System is institutionalized | - Meeting Minutes - Working group and workshop reports and products - UNDP quarterly progress reports - Annual Project Implementation Reports - Independent final evaluation report - GEF Cross-Cutting Capacity Development Scorecard - RMS - EKMS - Training programme | - The project will be executed in a transparent, holistic, adaptive, and collaborative manner - Government ministries and authorities maintain political commitment to the formulation and early implementation of the EKMS - Non-state stakeholder representatives, in particular project champions, remain active participants in the project - Policy and institutional reforms and modifications recommended by the project are politically, technically, and financially feasible |
|  | Indicator 2: Number of countries with legal, policy and institutional frameworks in place for conservation, sustainable use, and access and benefit sharing of natural resources, biodiversity and ecosystems | The baseline of this indicator is qualitatively measured as inadequate, reflected by the inadequacy of existing policy and legal instruments to guarantee the realization of Rio Convention obligations. While the baseline consists of various environmental and development policies and laws, their inadequacy lies in their sectoral and thematic construct, insufficient awareness and understanding of how to reconcile competing policies and laws, and inadequate guidance on the strategic operationalization of this policy framework. | - One consultative and coordinating mechanism that catalyzes the mainstreaming of global environmental obligations within national development planning and policy formulation - At least one by-law or legal instrument has been developed or strengthened to catalyze compliance with standards to support the realization of Rio Convention obligations - At least one sectoral plan effectively integrated with criteria and indicators that reinforce Rio Convention obligations achievements. |  |  |
|  | Indicator 3: 500 direct project beneficiaries | The baseline for this project is set at zero, to be compared with the number of unique stakeholders benefitting from the project’s activities. | At least 500 stakeholders have benefitted from an integrated EKMS |  |  |
|  | Indicator 4: Sectoral plans and policies include targets that measure progress toward achieving global environmental obligations | - Liberia has degraded and limited infrastructure. When combined with low technical and institutional capacity, the result is a severely limited environmental governance framework. The civil war led to the displacement of individuals and unprecedented amounts of resource exploitation. - Requirements of the Rio Conventions are not adequately incorporated in sectoral development planning | - There is an increase in the appreciation of the Rio Conventions among the general public - Rio Convention obligations are being better implemented through an integrated system of data and information management - Increased capacity within relevant stakeholder groups to handle data and information relevant to the Rio Convention - There is an increase in coordination between government groups and other stakeholders |  |  |
| Component 1 Establishment of an integrated environmental knowledge management system (EKMS) to meet global environment and sustainable development priorities | Indicator 5: All stakeholders agree by consensus on a key set of higher-order indicators to monitor the progress the country is making towards meeting and sustaining Rio Convention obligations. Indicator 6: A data protocol system is developed and tested that allows data, information, and knowledge to be tracked through the life cycle of their creation to informing policy and plans to the latter’s adaptive management. Indicator 7: Key existing databases, management information systems, and monitoring systems are strategically networked into an integrated system (the EKMS) Indicator 8: A pilot project to test the application of the EKMS is carried out on a high value sector development plan at the local self-governing authority. Indicator 9: A long-term training programme is developed and institutionalized on Rio Convention mainstreaming based on lessons learned from the project’s learning-by-doing workshops and related exercises | - Key data and information is not readily shared among agencies - Data and information does not sufficiently inform development decision-making - Systems for data and information management is are outdated and inadequate | - Stakeholders (including at least 40% women) are trained on how to manage the EKMS - Institutional mapping and analysis of an optimal knowledge management system is completed by month 6 - Integrated environmental knowledge management system designed and reviewed by month 12 - Existing information and knowledge management systems networked - Technologies to create cost-effective synergies updated - Global environmental indicators are integrated into select sectoral development plan(s) - Learning-by-doing training on improved methodologies and analytical skills for interpreting global environmental trends and understanding their relevance to sectoral development - Integrated environmental knowledge management system piloted through a select sectoral plan by month 39 | - Analysis of an optimal knowledge management system - EKMS - Operational procedures - Feasibility study - Pilot sector development plan - Meeting minutes - Indicators - Technology updates - Report with recommended revisions - Operational manual - Lessons learned report | - Design and assessment is deemed legitimate, relevant, and valid among all key stakeholder representatives and project champions - Expert peer reviewers follow through with quality reviews - EKMS is politically, technically, and financially feasible |
| Component 2 Enhanced institutional and technical capacities to mainstream, develop, and utilize policies and/or legislative frameworks for effective implementation of the three Rio Conventions | Indicator 10: Operational by-laws are developed to improve and legitimize Rio Convention mainstreaming into sector development plans. Indicator 11: A resource mobilization strategy for the long-term operation (e.g., 15 years) of the EKMS is developed and approved by the Government Apparatus Indicator 12: Memoranda of agreement must be negotiated and signed among government and non-state stakeholders on the sharing of data and information. Indicator 13: Liaison protocols between key government agencies must be updated and signed to strengthen sharing of data and information and proactive collaboration in the operation of the integrated EKMS. Indicator 14: The project facilitates broad-based stakeholder workshops to negotiate and institutionalize best practice consultative and decision-making processes to access best available data, information and knowledge. | - The government agencies responsible for the Rio Conventions have limited budgetary funds - The availability of significant resources from the international donor community to address environmental issues has led to the deleveraging of government budgetary allocations to address environmental priorities | - SWOT and gap analysis completed by month 6 - Operational interpretation, enforcement tools, and by-laws created and distributed by month 43 - Strengthened consultative and decision-making processes - Mandates harmonized by month 39 - Monitoring and compliance arrangements enhanced by month 39 - Environmental-development best practices demonstrated and piloted - Resource mobilization strategy finalized by month 40 | - SWOT and gap analysis - Resource mobilization strategy - By-laws - Memoranda of agreement - Working group meeting minutes - Updated mandates and operational plans | - Strategy developed by the project is politically, technically, and financially feasible - Institutional reforms and modifications recommended by the project and the EKMS are politically, technically, and financially feasible and approved by the Project Steering Committee - Institutions and working groups are open to change |
| Component 3 Improving awareness of global environmental values | Indicator 15: Education module on the importance of the global environment to national sustainable development is adopted and integrated within teaching curricula at the secondary school level Indicator 16: Collectively and over the three years of project implementation, the awareness-raising workshops engage over 700 unique stakeholders Indicator 17: A government-based website is created to network existing sources of electronic data and information | - The general public remains generally unaware or unconcerned about the contribution of the Rio Conventions to meeting and satisfying local and national socio-economic priorities - Awareness of Rio Convention mainstreaming is limited, and stakeholders do not fully appreciating the value of conserving the global environment. | - Public Service Announcement (PSA) - Environmental awareness module prepared - Project Launch and Results Conference held by months 3 and 44 - Private sector and media sensitization panel discussions held - Articles on linkages between the global environment and socio-economic issues | - Panel discussion minutes - Meeting minutes - Awareness and sensitization workshop reports - Training programme, curricula, materials and training modules - Attendance list - PSA - Brochures and articles - Facebook page | - Public dialogues attract people that are new to the concept of Rio Convention mainstreaming, as well as detractors, with the assumption that dialogues will help change attitudes in a positive way - The right representation from the various government ministries, departments, and agencies participate in project activities - There is sufficient commitment from policy-makers to maintain long-term support to public awareness raising activities - Development partners implementing parallel public awareness campaigns are willing to modify, as appropriate, their activities to supporting the awareness activities of the present project to create synergies and achieve cost-effectiveness - Articles published in the popular media will be read and not skipped over - Brochures will be read and the content absorbed |
| Component 4 NCSA is updated to reflect post 2015-SDGs and current opportunities to strengthen priority foundational capacities for the global environment | Indicator 18: NCSA Final Report and Capacity Development Action Plan is completed | - The previous NCSA was completed in 2006 - Since the NCSA, Liberia has undertaken several initiatives to address barriers in the NCSA. Despite the important contributions from various bilateral and multilateral development agencies however, Liberia continues to face a number of difficulties in meeting global environmental objectives. | - Assessments of capacity challenges completed by month 33 - Cross-cutting analysis completed by month 36 - Capacity Development Strategy and Action Plan, developed - NCSA Final Report finalized by month 45 | - Working Group and workshop reports and products - Survey results - Interviews - Thematic assessments - Cross-cutting analysis report - Meeting minutes - Draft Action Plan - NCSA Final Report and Action Plan | - Survey respondents contribute their honest attitudes and values - The right representation from the various government ministries, departments, and agencies participate in project activities - Assessments are deemed legitimate, relevant, and valid among all key stakeholder representatives and project champions - Best practices and lessons learned from other countries are appropriately used - Expert peer reviewers follow through with quality reviews - Action Plan politically, technically, and financially feasible - Final Report is deemed legitimate, relevant, and valid among all key stakeholder representatives and project champions - The approval process is transparent and deemed valid by all stakeholders |

# G.	Monitoring and Evaluation Plan

The project results as outlined in the project results framework (chapter F) will be monitored annually and evaluated periodically during project implementation to ensure the project effectively achieves these results.  Supported by Component Three on awareness-raising and knowledge management, the project monitoring and evaluation plan will also facilitate learning and ensure that knowledge is shared and widely disseminated to support the scaling up and replication of project results.

Project-level monitoring and evaluation will be undertaken in compliance with UNDP requirements as detailed in the UNDP Programme and Operations Policies and Procedures  and UNDP Evaluation Policy.  The UNDP Country Office will work with the relevant project stakeholders to ensure UNDP M&E requirements meet high quality standards in a timely fashion.  Additional mandatory GEF-specific M&E requirements (as outlined below) will be undertaken in accordance with the GEF M&E policy and other relevant GEF policies.

In addition to these mandatory UNDP and GEF M&E requirements, other M&E activities deemed necessary to support project-level adaptive collaborative management will be agreed on during the Project Inception Workshop and will be detailed in the Inception Report.  This will include the exact role of project target groups and other stakeholders in project M&E activities including the GEF Operational Focal Point and national/regional institutes assigned to undertake project monitoring.  The GEF Operational Focal Point will strive to ensure consistency in the approach taken to the GEF-specific M&E requirements (notably the Capacity Development Scorecard) across all GEF-financed projects in the country.

M&E Oversight and monitoring responsibilities:

Project Manager:  This project will recruit a part-time Project Manager who will be responsible for day-to-day project management and regular monitoring of project results and risks, including social and environmental risks.  The Project Manager will ensure that all project staff maintains a high level of transparency, responsibility and accountability in M&E and reporting of project results.  The Project Manager will inform the Project Steering Committee, the UNDP Country Office, and the UNDP/GEF RTA of any delays or difficulties as they arise during implementation so that appropriate support and corrective measures can be adopted.

The Project Manager will develop annual work plans based on the multi-year work plan included in Annex 2, including annual output targets to support the efficient implementation of the project.  The Project Manager will ensure that the standard UNDP and GEF M&E requirements are fulfilled to the highest quality.  This includes, but is not limited to, ensuring the results framework indicators are monitored annually in time for evidence-based reporting in the Annual Progress Report, and that the monitoring of risks and the various plans/strategies developed to support project implementation (e.g., the gender strategy or the knowledge management strategy) occur on a regular basis.

Project Steering Committee:  The Project Steering Committee will take corrective action as needed to ensure the project achieves the desired results.  The Project Steering Committee will hold project reviews to assess the performance of the project and appraise the Annual Work Plan for the following year.  In the project’s final year, the Project Steering Committee will hold an end-of-project review to capture lessons learned and discuss opportunities for scaling up and to highlight project results and lessons learned with relevant audiences.  This final review meeting will also discuss the findings outlined in the project terminal evaluation report and the management response.

Project Implementing Partner:  The Implementing Partner is responsible for providing any and all required information and data necessary for timely, comprehensive, and evidence-based project reporting, including results and financial data, as necessary and appropriate.  The Implementing Partner will strive to ensure project-level M&E is undertaken by national institutes, and is aligned with national systems so that the data used and generated by the project supports national systems.

UNDP Country Office:  The UNDP Country Office will support the Project Manager as needed.  The UNDP Country Office will initiate and organize key GEF M&E activities including the annual progress report and the independent terminal evaluation.  The UNDP Country Office will also ensure that the standard UNDP and GEF M&E requirements are fulfilled to the highest quality.

The UNDP Country Office is responsible for complying with all UNDP project-level M&E requirements as outlined in the UNDP POPP.  This includes: a) the UNDP Quality Assurance Assessment; b) the ATLAS risk log; c) the UNDP gender markers; and d) the development, monitoring, and reporting of annual targets.  Any quality concerns flagged during these M&E activities must be addressed by the UNDP Country Office and the Project Manager.

The UNDP Country Office will retain all M&E records for this project for up to seven years after project financial closure in order to support ex post evaluations undertaken by the UNDP Independent Evaluation Office and/or the GEF Independent Evaluation Office.

UNDP/GEF Unit:  Additional M&E and implementation quality assurance and troubleshooting support will be provided by the UNDP/GEF Regional Technical Advisor and the UNDP/GEF Directorate as needed.

Audit: The project will be audited according to UNDP Financial Regulations and Rules and applicable audit policies on nationally implemented projects (NIM).

Additional GEF monitoring and reporting requirements:

Inception Workshop and Report:  A project inception workshop will be held within three months after the project document has been signed by all relevant parties.  Other key monitoring and reporting requirements will include:

- Re-orient project stakeholders to the project strategy and discuss any changes in the overall context that influence project strategy and implementation;

- Discuss the roles and responsibilities of the project team, including reporting and communication lines and conflict resolution mechanisms;

- Review the results framework and finalize the indicators, means of verification and monitoring plan;

- Discuss reporting, monitoring and evaluation roles and responsibilities and finalize the M&E budget; identify national/regional institutes to be involved in project-level M&E; discuss the role of the GEF Operational Focal Point in M&E;

- Update and review responsibilities for monitoring the various project plans and strategies, including the risk log; Environmental and Social Management Plan and other safeguard requirements; the gender strategy; the knowledge management strategy, and other relevant strategies;

- Review financial reporting procedures and mandatory requirements, and agree on the arrangements for the annual audit; and

- Plan and schedule Project Steering Committee meetings and finalize the first year annual work plan.

The Project Manager will prepare the inception report no later than one month after the inception workshop.  The inception report will be cleared by the UNDP Country Office and the UNDP/GEF Regional Technical Adviser, and will be approved by the Project Steering Committee.

GEF Annual Progress Report:  The Project Manager and the UNDP Country Office will prepare an annual progress report (APR) covering the reporting period July (previous year) to June (current year) for each year of project implementation.  This report will be submitted to the UNDP/GEF Regional Technical Advisor who will provide objective input prior to its finalization.  The Project Manager will ensure that the indicators included in the project results framework are monitored annually in advance of the APR submission deadline so that progress can be reported in the APR.  Any environmental and social risks and related management plans will be monitored regularly, and progress will be reported in the APR.

The APR will be shared with the Project Steering Committee.  The UNDP Country Office will coordinate the input of the GEF Operational Focal Point and other stakeholders into the APR as appropriate.  The quality rating of the previous year’s APR will be used to inform the preparation of the subsequent APR.

Lessons learned and knowledge generation:  Results from the project will be disseminated within and beyond the project intervention area through existing information sharing networks and forums.  The project will identify and participate, as relevant and appropriate, in scientific, policy-based and/or any other networks, which may be of benefit to the project.  The project will identify, analyze, and share lessons learned that might be beneficial to the design and implementation of similar projects and disseminate these lessons widely.  There will be continuous information exchange between this project and other projects of similar focus in the same country, region and globally.

GEF Focal Area Tracking Tools:  The Capacity Development Scorecard (Annex 1) is the GEF Tracking Tool that will be used to monitor the capacities developed.  The capacities developed under the scorecard will be assessed a second time at the end of the project, and used to infer the extent to which the project contributed towards their strengthening.  This final scorecard will not be completed by the Project Manager or Project Team, but rather by the independent consultant contracted to undertake the terminal evaluation.  The final Scorecard will be submitted to the GEF as part of the terminal evaluation report.

Terminal Evaluation:  An independent terminal evaluation will take place upon completion of all major project outputs and activities.  The terminal evaluation process will begin three months before the operational closure of the project, allowing the evaluation mission to proceed while the project team is still in place, yet ensuring the project is close enough to completion for the evaluation team to reach conclusions on key aspects such as capacities developed and the sustainability of project outcomes.  The Project Manager will remain on contract until the terminal evaluation report and the companion management response have been finalized.  The terms of reference, the evaluation process, and the terminal evaluation report will follow the standard templates and guidance prepared by the UNDP Independent Evaluation Office for GEF-financed projects available on the UNDP Evaluation Resource Center.  As noted in this guidance, the evaluation will be ‘independent, impartial, and rigorous’.

The consultants (international and national) that will be hired to undertake the assignment will be independent from organizations that were involved in designing, executing, or advising on the project to be evaluated.  The GEF Operational Focal Point and other stakeholders will be involved and consulted during the terminal evaluation process.  Additional quality assurance support will be available from the UNDP/GEF Directorate.  The terminal evaluation report will be cleared by the UNDP Country Office and the UNDP/GEF Regional Technical Adviser, and will be approved by the Project Steering Committee.

The UNDP Country Office will include the planned project terminal evaluation in the UNDP Country Office evaluation plan, and will upload the final terminal evaluation report and the corresponding management response to the UNDP Evaluation Resource Centre’s website.  Once uploaded, the UNDP Independent Evaluation Office will undertake a quality assessment, validate the findings and ratings in the terminal evaluation report, and rate the quality of the report.  The UNDP Independent Evaluation Office assessment report will be sent to the GEF Independent Evaluation Office.

Final Project Report Package: The project’s final APR along with the terminal evaluation report and corresponding management response will serve as the final project report package.  The final project report package will be discussed with the Project Steering Committee during an end-of-project review meeting to discuss lessons learned and opportunities for replication and scaling up.

Mandatory GEF M&E Requirements and M&E Budget:

| GEF M&E requirements | Primary responsibility | Indicative costs to be charged to the Project Budget (US$) |  | Time frame |
| --- | --- | --- | --- | --- |
|  |  | GEF grant | Co-financing |  |
| Inception Workshop and Report | Project Manager, Project Team, EPA, UNDP Country Office | US$ 5,000 | US$ 3,000 | Within three months of project document signature |
| Standard UNDP monitoring and reporting requirements as outlined in the UNDP Programme and Operations Policies and Procedures | UNDP Country Office | None | None | Quarterly, annually |
| Monitoring of indicators in project results framework (EPA) | Project Manager | Per year: US$ 1,000 | Per year: US$ 1,000 | Annually |
| UNDP Annual Progress Report | Project Manager and UNDP Country Office and UNDP/GEF team | None | None | Annually |
| NIM Audit as per UNDP audit policies | UNDP Country Office | Per year: US$ 1,000 | Per year: US$ 1,000 | Annually or other frequency as per UNDP audit policies |
| Lessons learned and knowledge generation | Project Manager | Per year: US$ 5,000 | Per year: US$ 6,000 | Annually |
| Monitoring of environmental and social risks, and corresponding management plans as relevant | Project Manager UNDP CO | None | Per year: US$ 6,000 | On-going |
| Addressing environmental and social grievances | Project Manager UNDP Country Office | None for time of Project Manager, and UNDP CO | Per year: US$ 2,000 | Costs associated with missions and workshops can be charged to the project budget. |
| Project Steering Committee meetings | Project Steering Committee UNDP Country Office Project Manager | Per year: US$ 500 | Per year: US$ 1,000 | Twice per year |
| Supervision missions | UNDP Country Office | None | None | No supervision missions are required for this project |
| Oversight missions | UNDP/GEF team | None12 | None | Troubleshooting as needed |
| GEF Secretariat learning missions/site visits | UNDP Country Office and Project Manager and UNDP/GEF team | None | To be determined | To be determined during project implementation |
| Terminal GEF Tracking Tool | Project Manager International Evaluation Consultant | US$ 1,000 | US$ 1,000 | As part of the terminal evaluation mission |
| Independent Terminal Evaluation included in UNDP evaluation plan, and management response | UNDP Country Office and project team and UNDP/GEF team | US$ 24,000 | US$ 15,000 | At least four months before operational closure |
| Project Terminal Report | Project Manager and Team, UNDP CO | None | None | At least two months before the end of project implementation |
| TOTAL indicative COST Excluding project team staff time, and UNDP staff and travel expenses |  | US$ 60,000 | US$ 87,000 |  |

-----

## G.1	Evaluation Schedule

| Evaluation Title | Planned start date Month/year | Planned end date Month/year | Included in the Country Office Evaluation Plan | Budget for consultants | Other budget (i.e., travel, site visits etc…) | Budget for translation |
| --- | --- | --- | --- | --- | --- | --- |
| Terminal Evaluation | February 2021 | June 2021 | Yes | US$ 20,000 | US$ 5,000 | N/A |
| Total evaluation budget |  |  |  | US$ 25,000 |  |  |

# H.	Implementation and Management Arrangements

Roles and responsibilities of the project’s implementation arrangements:  The project will be implemented following UNDP’s national implementation modality, according to the Standard Basic Assistance Agreement between UNDP and the Government of Liberia, and the Country Programme.

The Implementing Partner for this project is the Environmental Protection Agency (EPA).  The Implementing Partner is responsible and accountable for managing this project, including the monitoring and evaluation of project interventions, achieving project outcomes, and for the effective use of UNDP resources.  The project organization structure is as follows:

Project Management Unit

National Project Director

Executive Director, EPA

Project Steering Committee

Senior Beneficiary:

Ministry of Lands, Mines & Energy Ministry of Internal Affairs, Ministry of Finance and Development Planning, regional government; and local communities

Senior Supplier:

UNDP

Project Assurance

UNDP Country Office

Project Organization Structure

TEAM 3

Improved environmental attitudes and updated NCSA

(Component 3 and 4)

Executive:

Environmental Protection Agency

TEAM 1

Environmental knowledge management system

(Component 1)

Project Assistant

Project Manager

TEAM 2

Enhanced institutional and technical capacities

(Component 2)

National Project Director:  A senior government official will be designated at the National Project Director (NPD) and will be responsible for management oversight of the project.  The NPD will devote a significant part of his/her working time on the project.  In the fulfilment of his/her responsibilities, the NPD will be supported by the Project Board and a part-time Project Manager.

The Project Steering Committee is responsible for making by consensus, management decisions when guidance is required by the Project Manager, including recommendation for UNDP/Implementing Partner approval of project plans and revisions.  In order to ensure UNDP’s ultimate accountability, Project Steering Committee decisions should be made in accordance with standards that shall ensure management for development results, best value money, fairness, integrity, transparency and effective international competition.  In case a consensus can not be reached within the Project Steering Committee, the final decision will rest with the UNDP Programme Manager.  The terms of reference for the Project Steering Committee are contained in Annex 7.

The Project Manager will run the project on a day-to-day basis on behalf of the EPA as the project’s implementing partner and within the constraints laid down by the Project Steering Committee.  The Project Manager’s functions will end when the final project report package (which includes the terminal evaluation report and corresponding management response), and other documentation as required by the GEF and UNDP, has been completed and submitted to UNDP (including operational closure of the project).

The organization and execution of project activities will be by components.  Under the oversight of the Project Manager, three teams of technical consultants will be organized to carry out project activities – one team for each of components 1 and 2, and a third team to carry out components 3 and 4.  The timely and cost-effective execution of the project activities will be facilitated by the holding project management at all levels for high quality management practices, such as timely communication with execution and implementing partners, timely preparation of quality reports, and timely responses to electronic communications.  A Chief Technical Advisor (see below) will be recruited to provide regular guidance to the technical execution of project activities, including advising on the adaptive collaborative management of the project.

Project assurance refers to the oversight of the project that will be provided by the UNDP Country Office, currently Mr. Moses Massah who is the UNDP Liberia Programme Officer at the time of this project document’s writing.  Additional quality assurance will be provided by the UNDP Regional Technical Advisor as needed.

Senior Supplier: The primary function of the Senior Supplier is to provide guidance regarding the technical feasibility of the project.  This includes technical guidance on designing, developing, facilitating, procuring, and implementing the project.

Senior Beneficiary: These individuals represent the interests of those who will ultimately benefit from the project.  The Senior Beneficiary’s primary function is to ensure the realization of project results from the perspective of project beneficiaries.  These individuals will validate the needs and monitor the proposed solutions to ensure that those needs are met within the provisions of the project.

Project Management Unit: In consultation with the Ministry of Finance and Development Planning, Ministry of Lands, Mines, and Energy, and the Environmental Protection Agency, UNDP will establish a Project Management Unit for the day-to-day management of project activities and subcontract specific components of the project to specialized government agencies, research institutions, as well as qualified NGOs.  The PMU will be administered by a part-time Project Manager and supported by a part-time Project Assistant.  The PMU will be based at the offices of the EPA, which will provide in-kind support in the form of office space, furniture, and transportation.

National Consultants:  The project will contract national experts/specialists as consultants to provide specialized expertise to carrying out project activities outlined in components 1, 2, 3, and 4.  This will include drafting technical texts that serve as discussion material for the learning-by-doing workshops, as well as being presenters and resource persons for the awareness-raising dialogues.  Annex 7 outlines the indicative Terms of References for these national consultants.

International Consultants: The project will contract two international consultants.  An independent evaluation expert to undertake a final evaluation of the project four (4) months prior to project closure will be recruited.  Critically, the project will recruit a part-time chief technical advisor to provide technical guidance during project implementation.  He/she will be recruited for the full duration of the four year project.

Capacity Development Activities:  The project will take an adaptive collaborative management approach to implementation.  That is, UNDP and EPA will manage project activities in order that stakeholders are involved early and throughout project implementation, providing regular input of the performance of project activities.  This will help signal unforeseen risks and contribute to the timely modification and realignment of activities within the boundaries of the project's goal and objectives.

Technical Working Groups:  Three working groups will be established.  The groups will be led by a specialist contracted under the project, and each group will be made up of a team of independent consultants, technical government agency representatives, as well as representatives from stakeholder groups.  Consultants will facilitate the implementation of the relevant activities under their respective component.

UNDP Direct Project Services as requested by Government (if any):  The GEF Council has adopted rules and issued guidance on when and how Direct Project Costs may be recovered for projects financed by the GEF Trust Fund.   In concert with these guidelines, the UNDP Country Office will provide a range of support services for the implementation of this project, and recover the actual direct and indirect costs (per the Universal Price List) incurred by the Country Office in delivering such services as stipulated in the Letter of Agreement (LOA) between the Government of Liberia and UNDP (Annex 6).  These services include, but are not limited to the following:

- Payments, disbursements and other financial transactions

- Recruitment of staff, project personnel, and consultants

- Procurement of services and equipment, including disposals

- Organization of training activities, conferences, and workshops, including fellowships

- Travel authorization, Government clearances ticketing, and travel arrangements

Agreement on intellectual property rights and use of logo on the project’s deliverables and disclosure of information:  In order to accord proper acknowledgement to the GEF for providing grant funding, the GEF logo will appear together with the UNDP logo on all promotional materials, other written materials like publications developed by the project, and project hardware.  Any citation on publications regarding projects funded by the GEF will also accord proper acknowledgement to the GEF.  Information will be disclosed in accordance with relevant policies notably the UNDP Disclosure Policy and the GEF policy on public involvement.

The Harmonized Approach to Cash Transfers (HACT) Framework represents a common operational framework for UN agencies’ transfer of cash to government and non-governmental implementing partners.  For this cross-cutting capacity development project, the Implementing Partner is the Environmental Protection Agency (EPA).  The micro-assessment was carried out in June 2016 through a process of consultations, observations, and walk-through tests of transactions.  This exercise provides an overall assessment of the EPA’s programme, financial and operations management policies, procedures, systems, and internal controls necessary to implement agreed work plans and agreements with the United Nations agencies.  The HACT micro-assessment is available as a separate report.

# I.	Project Financing

## I.1	Co-financing

The GEF financing will be used to finance project goods and services that require procurement, such as the recruitment of experts and specialists and the renting of workshop venues.  The total estimated co-financing to this project is US$ 1.5 million, most of which is in-kind and estimated by the active engagement of sufficiently large numbers of government staff and other stakeholders in various project activities, among other in-kind contributions such as the administrative and overhead costs incurred by partner and participating organizations.

Although not costed, the sustainable development baseline is significant and reflected by the important number of projects and activities that are outlined in the section on project linkages (D.2).  No GEF financing will be used, directly or indirectly, for overseas study tours as this is not a cost-effective use of resources.

UNDP Liberia will make available US$ 200,000 as cash co-financing to the above-mentioned project over the period 2017 to 2021.  These funds are being available from Target Resources for Assignment from the Core (TRAC) in the amount of US$ 50,000 per year as this project is a strategic element of interventions that will contribute to meeting expected UNDAF outcomes 2.1 and 4.3.

Co-financing is also being provided by the government to the order of US$ 1,300,000 in the form of in-kind contribution.  This funding will be made available through the extensive engagement of government and other national stakeholders in the cross-cutting capacity development (CCCD) project, as well as aligning various project activities with other key capacity development projects in Liberia.  Government in-kind co-financing will include the provision of office space, furniture, and transportation.

The main project with which this CCCD project will align is the Liberia Forest Sector Project (LFSP), which is receiving a grant of US$ 37.5 million from the Government of Norway.  Among the capacity development activities of the LFSP are a series of assessments, consultations, and working group meetings to improve the Environmental Protection Agency’s institutional and technical capacities to pursue sustainable forest management.  These activities align well with the CCCD project’s work to strengthen Liberia’s ability to formulate better sector development plans and make more informed decisions that help the country better adapt to the impacts of climate change, reduce the loss of critical biodiversity, and stem the expansion of land degradation.

Another important project from which this CCCD project will align is the European Union-Liberia Climate Change Alliance Project (LCCA) that is financed with € 6 million.   Among the activities of the LCCA project with which the CCCD project will align as the learning-by-doing exercises to mainstream climate change mitigation strategies in waste management and carrying out piloting and up-scaling of recycling and composting programmes in targeted communities.

## I.2	Incremental Cost Reasoning

The incremental cost of this project is determined on the basis of the main criterion that the co-financing achieves an equal share of the GEF increment will be negotiated with potential donors.  The nature of the capacity development activities of this project does not lend itself to clearly distinguish those activities that will deliver global environmental benefits and those that should be undertaken in the country’s own sustainable development interest.  Unless such a distinction can be made, the average cost of project activities will be equally shared by both sources of funds.

The technical portion of the GEF increment of this project will be used to strengthen the global environmental character of the indicators to monitor progress towards meeting Rio Convention objectives and strengthening coordination and decentralization of environmental governance.  The GEF increment will also be used to remove the policy and institutional barriers that limit the integration of Rio Convention criteria and indicators into the formulation and implementation of communal development planning frameworks.

The above-mentioned intervention logic already indicates what can be expected with and without GEF assistance.  The baseline provides a number of policy, program and institutional changes that have already strengthened the way in which the Union of the Liberia deals with environmental governance.

The baseline also provides a number of initiatives that already exist in the Liberia.  The financial contribution of the GEF will be added to parallel and additional funds provided by various other sources of funding obtained through an allocation of national budgets or support for the programme by traditional and new development partners, such as the UNDP, EU, AfDB, FAO and AFD.  In-kind contributions will be mobilized, particularly at the level of local communes and the competent ministries and their decentralized support services.  The GEF funding will focus on the harmonization of these efforts in the area of intervention through a collaborative approach and therefore to ensure a more effective and intelligent system for adaptive management.

## I.3	Cost-Effectiveness

The cost-effectiveness of this project is crucial part of the project strategy.  One design feature that will ensure cost-effectiveness is the project’s strategy to build upon a significant baseline of commitment to participate in training and learning-by-doing exercises on Rio Convention mainstreaming. Additionally, by seeking to use existing environmental and natural resource management legislation to implement Rio Convention obligations, this project builds upon an existing baseline of legislation and institutional capacities.  The key to success will be in reducing bureaucratic inefficiencies by improving coordination amongst line ministries.  Promoting inter-institutional collaboration will also allow for opportunities to realize synergies and reduce inefficiencies associated with duplication of effort or contradictions in approaches.

The cost-effectiveness of this project is also demonstrated in efficient allocation and management of financial resources.  The recruitment of consultants under the project will be financed by the GEF contribution, reducing the transaction costs associated when contracting consultants through multiple sources of finances.

Another important indicator of cost-effectiveness is the very low percentage of the GEF grant being used for project management, which is approximately 9.5%.  The project will also ensure cost-effectiveness through integrating project activities with those of development partners to achieve cost-effectiveness and capitalize on synergies.  Given the number of ongoing projects in the country, careful attention will be given to coordinating project activities in such a way that activities are mutually supportive and opportunities capitalized to realize synergies and cost-effectiveness.  Working with existing organizations (especially NGOs) as delivery mechanisms for project support to local stakeholders will allow the project to capitalize on their expertise and their relationship with the community.

Finally, lessons learned from baseline projects will be incorporated into the project implementation so that GEF resources can be used in the most efficient manner.  Cost-effectiveness was initially increased during the PPG Phase by incorporating lessons learned to inform the project design.

## I.4	Financial Planning and Management

Budget Revision and Tolerance:  As per UNDP requirements outlined in the UNDP POPP, the Project Steering Committee will agree on a budget tolerance level for each plan under the overall annual work plan allowing the project manager to expend up to the tolerance level beyond the approved project budget amount for the year without requiring a revision from the Project Steering Committee.  Should the following deviations occur, the Project Manager and UNDP Country Office will seek the approval of the UNDP-GEF team as these are considered major amendments by the GEF:

- Budget re-allocations among components in the project with amounts involving 10% of the total project grant or more;

- Introduction of new budget items/or components that exceed 5% of original GEF allocation.

Any over-expenditure incurred beyond the available GEF grant amount will be absorbed by non-GEF resources (e.g., UNDP TRAC or cash co-financing).

Refund to Donor:  Should a refund of unspent funds to the GEF be necessary, this will be managed directly by the UNDP-GEF Unit in New York.

Operational completion: The project will be operationally completed when the last UNDP-financed inputs have been provided and the related activities have been completed.  This includes the final clearance of the Terminal Evaluation Report and the corresponding management response, and the end-of-project review Project Steering Committee meeting.  The Implementing Partner through a Project Steering Committee decision will notify the UNDP Country Office when operational closure has been completed.  At this time, the relevant parties will have already agreed and confirmed in writing on the arrangements for the disposal of any equipment that is still the property of UNDP.

Project Closure:  Project closure will be conducted as per UNDP requirements outlined in the UNDP POPP.  On an exceptional basis only, a no-cost extension beyond the initial duration of the project will be sought from in-country UNDP colleagues and then the UNDP-GEF Executive Coordinator.

Financial completion:  The project will be financially closed when the following conditions have been met:

(a) The project is operationally completed or has been cancelled;

(b) The Implementing Partner has reported all financial transactions to UNDP;

(c) UNDP has closed the accounts for the project;

(d) UNDP and the Implementing Partner have certified a final Combined Delivery Report (which serves as final budget revision).

The project will be financially completed within 12 months of operational closure or after the date of cancellation.  Between operational and financial closure, the implementing partner will identify and settle all financial obligations and prepare a final expenditure report.  The UNDP Country Office will send the final signed closure documents including confirmation of final cumulative expenditure and unspent balance to the UNDP-GEF Unit for

## I.5	Project Outcome Budget

| Activity | Description | Year 1 | Year 2 | Year 3 | Year 4 | Total | GEF | Co-Financing |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Total Project Budget | 725,000 | 720,000 | 680,000 | 875,000 | 3,000,000 | 1,500,000 | 1,500,000 |
| Component 1 | Establishment of an integrated environmental knowledge management system (EKMS) to meet global environment and sustainable development priorities | 270,000 | 215,000 | 120,000 | 215,000 | 820,000 | 420,000 | 400,000 |
| Output 1.1 | Institutional mapping and analysis of an optimal knowledge management system | 65,000 | - | - | - | 65,000 | 40,000 | 25,000 |
| Output 1.2 | Design of an integrated environmental knowledge management system | 65,000 | - | - | - | 65,000 | 40,000 | 25,000 |
| Output 1.3 | Targeted technological networking of existing information and knowledge management systems. | 40,000 | 60,000 | - | - | 100,000 | 45,000 | 55,000 |
| Output 1.4 | Selected updating of technologies to create cost-effective synergies for knowledge management. | - | 75,000 | 40,000 | 75,000 | 190,000 | 125,000 | 65,000 |
| Output 1.5 | Integration of new and improved global environmental indicators into select sectoral development plan(s) | 60,000 | - | - | 60,000 | 120,000 | 60,000 | 60,000 |
| Output 1.6 | Learning-by-doing training on improved methodologies and analytical skills for interpreting global environmental trends and understanding their relevance to sectoral development | 40,000 | 20,000 | 20,000 | 20,000 | 100,000 | 35,000 | 65,000 |
| Output 1.7 | Early implementation and piloting of the integrated environmental knowledge management system through a select sectoral plan. | - | 60,000 | 60,000 | 60,000 | 180,000 | 75,000 | 105,000 |
| Component 2 | Enhanced institutional and technical capacities to mainstream, develop, and utilize policies and/or legislative frameworks for effective implementation of the three Rio Conventions | 235,000 | 265,000 | 265,000 | 285,000 | 1,050,000 | 500,000 | 550,000 |
| Output 2.1 | In-depth SWOT and gap analysis of existing environmental policies and legislation, and the effectiveness of their enforcement | 60,000 | - | - | - | 60,000 | 30,000 | 30,000 |
| Output 2.2 | Strengthened policy and regulatory framework through improved operational interpretation, enforcement tools, and by-laws | - | 60,000 | 60,000 | 60,000 | 180,000 | 90,000 | 90,000 |
| Output 2.3 | Strengthened consultative and decision-making processes for mainstreaming of Rio Convention obligations. | 40,000 | 30,000 | 30,000 | 30,000 | 130,000 | 50,000 | 80,000 |
| Output 2.4 | Targeted updating and streamlining of institutional mandates to facilitate and catalyze long-term action to meet global environmental obligations | 50,000 | 50,000 | 50,000 | 50,000 | 200,000 | 100,000 | 100,000 |
| Output 2.5 | Enhanced monitoring and compliance arrangements, e.g., environmental impact and strategic environmental assessments | 60,000 | 40,000 | 40,000 | 45,000 | 185,000 | 90,000 | 95,000 |
| Output 2.6 | Demonstration and piloting of integrated environmental-development best practices that reflect global environmental priorities and the Post-2015 Sustainable Development Goals. | - | 60,000 | 60,000 | 60,000 | 180,000 | 90,000 | 90,000 |
| Output 2.7 | Resource mobilization strategy | 25,000 | 25,000 | 25,000 | 40,000 | 115,000 | 50,000 | 65,000 |
| Component 3 | Improving awareness of global environmental values and knowledge management | 115,000 | 175,000 | 125,000 | 135,000 | 550,000 | 250,000 | 300,000 |
| Output 3.1 | Stakeholder dialogues on the value of Rio Conventions | 60,000 | 40,000 | 40,000 | 55,000 | 195,000 | 80,000 | 115,000 |
| Output 3.2 | Brochures and articles on the Rio Conventions | 20,000 | 20,000 | 20,000 | 20,000 | 80,000 | 40,000 | 40,000 |
| Output 3.3 | Public service announcement(s) on globally sensitive and environmentally friendly behavior | - | 60,000 | 10,000 | 10,000 | 80,000 | 40,000 | 40,000 |
| Output 3.4 | Improved environmental educational curricula and youth civic engagement | - | 45,000 | 45,000 | 40,000 | 130,000 | 55,000 | 75,000 |
| Output 3.5 | Internet visibility of integrated approaches to meet Rio Convention obligations and national sustainable development priorities. | 35,000 | 10,000 | 10,000 | 10,000 | 65,000 | 35,000 | 30,000 |
| Component 4 | NCSA is updated to reflect post 2015-SDGs and current opportunities to strengthen priority foundational capacities for the global environment | 25,000 | - | 100,000 | 125,000 | 250,000 | 200,000 | 50,000 |
| Output 4.1 | Updated assessments of capacity challenges to meet and sustain Rio Convention obligations, building upon GEF focal area enabling activities | - | - | 40,000 | - | 40,000 | 30,000 | 10,000 |
| Output 4.2 | Integrated cross-cutting analysis of systemic, institutional, and individual capacity development priorities | 25,000 | - | 35,000 | 25,000 | 85,000 | 70,000 | 15,000 |
| Output 4.3 | Capacity Development Strategy and Action Plan, building on action plans of GEF focal area enabling activities | - | - | 25,000 | 40,000 | 65,000 | 50,000 | 15,000 |
| Output 4.4 | Update NCSA Final Report | - | - | - | 60,000 | 60,000 | 50,000 | 10,000 |

|  | Activity | Year 1 | Year 2 | Year 3 | Year 4 | Total | GEF | Co-Financing |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Project Management |  | 80,000 | 65,000 | 70,000 | 115,000 | 330,000 | 130,000 | 200,000 |
| A | Project Manager | 20,000 | 20,000 | 20,000 | 20,000 | 80,000 | 80,000 | - |
| B | Independent Terminal Evaluation | - | - | - | 50,000 | 50,000 | 30,000 | 20,000 |
| C | Project Board Meetings | 2,000 | 2,000 | 2,000 | 2,000 | 8,000 | 2,000 | 6,000 |
| D | Project Support Staff | 7,500 | 7,500 | 7,500 | 7,500 | 30,000 | - | 30,000 |
| E | Travel | 6,000 | 6,000 | 6,000 | 6,000 | 24,000 | 4,000 | 20,000 |
| F | Audio Visual & Print Prod Costs | 3,500 | 3,500 | 3,500 | 3,500 | 14,000 | 4,000 | 10,000 |
| G | Equipment and Furniture | 20,000 | 5,000 | 10,000 | 5,000 | 40,000 | - | 40,000 |
| H | Rental & Maintenance-Premises | 15,000 | 15,000 | 15,000 | 15,000 | 60,000 | - | 60,000 |
| I | Miscellaneous Expenses | 2,500 | 2,500 | 2,500 | 2,500 | 10,000 | - | 10,000 |
| J | Professional Services: Audit | 2,000 | 2,000 | 2,000 | 2,000 | 8,000 | 4,000 | 4,000 |
| K | Direct Project Costs | 1,500 | 1,500 | 1,500 | 1,500 | 6,000 | 6,000 | - |

## I.6	Total Input Budget and Work Plan

| Atlas Proposal or Award ID: | TBD | Atlas Primary Output Project ID: | TBD |
| --- | --- | --- | --- |
| Atlas Award Title: | Strengthening National Capacities to Meet Global Environmental Obligations with the Framework of Sustainable Development Priorities |  |  |
| Atlas Business Unit | LBR10 |  |  |
| Atlas Primary Output Project Title | Strengthening National Capacities to Meet Global Environmental Obligations with the Framework of Sustainable Development Priorities |  |  |
| UNDP/GEF PIMS No. | 5796 |  |  |
| Implementing Partner | Ministry of Finance and Development Planning/EPA |  |  |

| GEF Component/Atlas Activity | Responsible Party | Fund ID | Donor Name | Atlas Budgetary Account Code | ATLAS Budget Description | Amount Year 1 (USD) | Amount Year 2 (USD) | Amount Year 3 (USD) | Amount Year 4 (USD) | Total (USD) | See Budget Note: |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| COMPONENT 1: Establishment of an integrated environmental knowledge management system (EKMS) to meet global environment and sustainable development priorities | MFDP/EPA |  |  | 71400 | Contractual Services – Individ. | 65,000 | 30,000 | 20,000 | 35,000 | 150,000 | 1 |
|  |  |  |  | 71200 | International Consultant | 10,000 | 10,000 | 10,000 | 10,000 | 40,000 | 2 |
|  |  |  |  | 71600 | Travel | 5,000 | 5,000 | 2,500 | 5,000 | 17,500 | 3 |
|  |  | 62000 | GEF | 75700 | Training, Workshops and Conferences | 32,000 | 32,000 | 12,000 | 32,000 | 108,000 | 4 |
|  |  |  |  | 72300 | Materials & Goods | 5,000 | 5,000 | 5,000 | 5,000 | 20,000 | 5 |
|  |  |  |  | 72800 | Information Technology Equipment | 28,000 | 28,000 | 5,500 | 23,000 | 84,500 | 7 |
|  |  |  |  |  | GEF Sub-total Outcome 1 | 145,000 | 110,000 | 55,000 | 110,000 | 420,000 |  |
|  |  |  |  | 71600 | Travel | 5,000 | 5,000 | 5,000 | 5,000 | 20,000 | 3 |
|  |  |  |  | 74200 | Audio Visual & Print Prod Costs | 1,000 | 1,000 | 1,000 | 1,000 | 4,000 | 6 |
|  |  | 04000 | UNDP | 75700 | Training, Workshops and Conferences | 6,000 | 7,000 | 6,000 | 6,000 | 25,000 | 4 |
|  |  |  |  |  | UNDP Sub-total Outcome 1 | 12,000 | 13,000 | 12,000 | 12,000 | 49,000 |  |
|  |  |  |  |  | Total Outcome 1 | 157,000 | 123,000 | 67,000 | 122,000 | 469,000 |  |
| COMPONENT 2: Enhanced institutional and technical capacities to mainstream, develop, and utilize policies and/or legislative frameworks for effective implementation of the three Rio Conventions |  |  |  | 71400 | Contractual Services: Individual | 65,000 | 70,000 | 70,000 | 75,000 | 280,000 | 1 |
|  |  |  |  | 71200 | International Consultant | 10,000 | 10,000 | 10,000 | 10,000 | 40,000 | 2 |
|  |  |  |  | 71600 | Travel | 5,000 | 10,000 | 15,000 | 15,000 | 45,000 | 3 |
|  | MFDP/EPA | 62000 | GEF | 75700 | Training, Workshops and Conferences | 27,000 | 27,000 | 27,000 | 27,000 | 108,000 | 4 |
|  |  |  |  | 72300 | Materials & Goods | 2,000 | 2,000 | 3,000 | 2,000 | 9,000 | 5 |
|  |  |  |  | 72800 | Information Technology Equipment | 6,000 | 6,000 | - | 6,000 | 18,000 | 7 |
|  |  |  |  |  | GEF Sub-total Outcome 2 | 115,000 | 125,000 | 125,000 | 135,000 | 500,000 |  |
|  |  |  |  | 71600 | Travel | 5,000 | 5,000 | 3,000 | 3,000 | 16,000 | 3 |
|  |  |  |  | 74200 | Audio Visual & Print Prod Costs | 2,000 | 2,000 | 1,000 | 1,000 | 6,000 | 6 |
|  |  | 04000 | UNDP | 75700 | Training, Workshops and Conferences | 9,000 | 9,000 | 2,000 | 2,000 | 22,000 | 4 |
|  |  |  |  |  | UNDP Sub-total Outcome 2 | 16,000 | 16,000 | 6,000 | 6,000 | 44,000 |  |
|  |  |  |  |  | Total Outcome 2 | 131,000 | 141,000 | 131,000 | 141,000 | 544,000 |  |
| COMPONENT 3: Improving awareness of global environmental values and knowledge management |  |  |  | 71400 | Contractual Services: Individual | 25,000 | 35,000 | 20,000 | 25,000 | 105,000 | 1 |
|  |  |  |  | 71200 | International Consultant | 10,000 | 10,000 | 10,000 | 10,000 | 40,000 | 2 |
|  |  |  |  | 71600 | Travel | 5,000 | 5,000 | 5,000 | 5,000 | 20,000 | 3 |
|  | MFDP/EPA | 62000 | GEF | 75700 | Training, Workshops and Conferences | 13,000 | 25,000 | 18,000 | 18,000 | 74,000 | 4 |
|  |  |  |  | 72300 | Materials & Goods | 2,000 | 5,000 | 2,000 | 2,000 | 11,000 | 5 |
|  |  |  |  |  | GEF Sub-total Outcome 3 | 55,000 | 80,000 | 55,000 | 60,000 | 250,000 |  |
|  |  |  |  | 71600 | Travel | 5,000 | 5,000 | 5,000 | 5,000 | 20,000 | 3 |
|  |  |  |  | 74200 | Audio Visual & Print Prod Costs | 1,000 | 3,000 | 1,000 | 1,000 | 6,000 | 6 |
|  |  | 04000 | UNDP | 75700 | Training, Workshops and Conferences | 6,000 | 8,000 | 6,000 | 6,000 | 26,000 | 4 |
|  |  |  |  |  | UNDP Sub-total Outcome 3 | 12,000 | 16,000 | 12,000 | 12,000 | 52,000 |  |
|  |  |  |  |  | Total Outcome 3 | 67,000 | 96,000 | 67,000 | 72,000 | 302,000 |  |
| COMPONENT 4: NCSA is updated to reflect post 2015-SDGs and current opportunities to strengthen priority foundational capacities for the global environment |  |  |  | 71400 | Contractual Services: Individuals | 10,000 |  | 40,000 | 60,000 | 110,000 | 1 |
|  |  |  |  | 71200 | International Consultant | 5,000 | - | 10,000 | 10,000 | 25,000 | 2 |
|  |  |  |  | 71600 | Travel | 1,500 | - | 15,000 | 15,000 | 31,500 | 3 |
|  | MFDP/EPA | 62000 | GEF | 75700 | Training, Workshops and Conferences | 3,000 | - | 14,000 | 14,000 | 31,000 | 4 |
|  |  |  |  | 72300 | Materials & Goods | 500 | - | 1,000 | 1,000 | 2,500 | 5 |
|  |  |  |  |  | GEF Sub-total Outcome 4 | 20,000 | - | 80,000 | 100,000 | 200,000 |  |
|  |  |  |  | 71600 | Travel | 1,000 | - | 5,000 | 5,000 | 11,000 | 3 |
|  |  |  |  | 74200 | Audio Visual & Print Prod Costs | 1,000 | - | 2,000 | 2,000 | 5,000 | 6 |
|  |  | 04000 | UNDP | 75700 | Training, Workshops and Conferences | 3,000 | - | 8,000 | 8,000 | 19,000 | 4 |
|  |  |  |  |  | UNDP Sub-total Outcome 4 | 5,000 | - | 15,000 | 15,000 | 35,000 |  |
|  |  |  |  |  | Total Outcome 4 | 25,000 | - | 95,000 | 115,000 | 235,000 |  |
|  |  |  |  | 71300 | Local Consultants | 20,000 | 20,000 | 20,000 | 20,000 | 80,000 | 9 |
|  |  |  |  | 74200 | Audio Visual & Print Prod Costs | 1,000 | 1,000 | 1,000 | 1,000 | 4,000 | 6 |
|  |  |  |  | 71200 | International Consultant | - | - | - | 30,000 | 30,000 | 10 |
|  |  |  |  | 75700 | Training, Workshops and Conferences | 500 | 500 | 500 | 500 | 2,000 | 4 |
| PROJECT MANAGEMENT | MFDP/EPA/UNDP | 62000 | GEF | 71600 | Travel | 1,000 | 1,000 | 1,000 | 1,000 | 4,000 | 11 |
|  |  |  |  | 74100 | Professional Services | 1,000 | 1,000 | 1,000 | 1,000 | 4,000 | 12 |
|  |  |  |  | 74596 | Services to projects - GOE for CO | 1,500 | 1,500 | 1,500 | 1,500 | 6,000 | 13 |
|  |  |  |  |  | GEF Sub-total Project Management | 25,000 | 25,000 | 25,000 | 55,000 | 130,000 |  |
|  |  |  |  | 75700 | Training, Workshops and Conferences | 250 | 250 | 250 | 250 | 1,000 | 4 |
|  |  |  |  | 74200 | Audio Visual & Print Prod Costs | 500 | 500 | 500 | 500 | 2,000 | 6 |
|  |  | 04000 | UNDP | 71600 | Travel | 1,250 | 1,250 | 1,250 | 1,250 | 5,000 | 14 |
|  |  |  |  | 74500 | Miscellaneous Expenses | 2,000 | 2,000 | 2,000 | 2,000 | 8,000 | 15 |
|  |  |  |  | 74100 | Professional Services | 1,000 | 1,000 | 1,000 | 1,000 | 4,000 | 12 |
|  |  |  |  |  | UNDP Sub-total Project Management | 5,000 | 5,000 | 5,000 | 5,000 | 20,000 |  |
|  |  |  |  |  | Total Project Management | 30,000 | 30,000 | 30,000 | 60,000 | 150,000 |  |
|  |  |  |  |  | GEF TOTAL | 360,000 | 340,000 | 340,000 | 460,000 | 1,500,000 |  |
|  |  |  |  |  | UNDP TOTAL | 50,000 | 50,000 | 50,000 | 50,000 | 200,000 |  |
|  |  |  |  | PROJECT TOTAL |  | 410,000 | 390,000 | 390,000 | 510,000 | 1,700,000 |  |

| Budget Notes: |  |
| --- | --- |
| 1 | National consultants to prepare technical analyses |
| 2 | Chief Technical Advisor to provide technical backstopping |
| 3 | Travel for stakeholder consultations |
| 4 | Meetings and workshop venue costs: Consultations with expert informants on policy issues; Venues for learning-by-doing workshops, exercises, and related stakeholder gatherings; Learning-by-doing workshops on resource mobilization strategies; Technical training workshops on the EKMS operation |
| 5 | Securing and preparation of technical materials |
| 6 | Equipment needed for presentations at workshops and meetings |
| 7 | Procurement of information communication technology necessary to set up the EKMS |
| 8 | Collection of baseline and end-of-year survey responses |
| 9 | Part-time Project Manager |
| 10 | Independent consultant to conduct the terminal evaluation |
| 11 | Travel for the international consultant |
| 12 | Audit of project finances |
| 13 | Direct Project Services Cost: per Letter of Agreement ANNEX 6. DPC are the costs of administrative services (such as those related to human resources, procurement, finance, and other functions) provided by UNDP in relation to the project. Direct project costs will be charged based on the UNDP Universal Price List or the actual corresponding service cost, in line with GEF rules on DPCs. The amounts indicated here are estimations. DPCs will be detailed as part of the annual project operational planning process and included in the yearly budgets. DPC costs can only be used for operational cost per transaction. DPCs are not a flat fee. |
| 14 | Local transportation for project team |
| 15 | Miscellaneous expenses |

| Summary of Funds | Amount |  |  |  | Total (US$) |
| --- | --- | --- | --- | --- | --- |
|  | Year 1 | Year 2 | Year 3 | Year 4 |  |
| GEF | 360,000 | 340,000 | 340,000 | 460,000 | 1,500,000 |
| UNDP | 50,000 | 50,000 | 50,000 | 50,000 | 200,000 |
| Government: Ministry of Finance and Development Planning | 315,000 | 330,000 | 290,000 | 365,000 | 1,300,000 |
| TOTAL | 725,000 | 720,000 | 680,000 | 875,000 | 3,000,000 |

# J.	Legal Context

This document together with the CPAP signed by the Government and UNDP which is incorporated by reference constitute together a Project Document as referred to in the Standard Basic Assistance Agreement (or other appropriate governing agreement) and all CPAP provisions apply to this document.  Consistent with the Article III of the Standard Basic Assistance Agreement, the responsibility for the safety and security of the implementing partner and its personnel and property, and of UNDP’s property in the implementing partner’s custody, rests with the implementing partner.

The implementing partner will put in place an appropriate security plan and maintain the security plan, taking into account the security situation in the country where the project is being carried; as well as assume all risks and liabilities related to the implementing partner’s security, and the full implementation of the security plan.

UNDP reserves the right to verify whether such a plan is in place, and to suggest modifications to the plan when necessary.  Failure to maintain and implement an appropriate security plan as required hereunder shall be deemed a breach of this agreement.

The implementing partner agrees to undertake all reasonable efforts to ensure that none of the UNDP funds received pursuant to the Project Document are used to provide support to individuals or entities associated with terrorism and that the recipients of any amounts provided by UNDP/GEF hereunder do not appear on the list maintained by the Security Council Committee established pursuant to Resolution 1267 (1999).  This provision must be included in all sub-contracts or sub-agreements entered into under this Project Document The list can be accessed via:

http://www.un.org/Docs/sc/committees/1267/1267ListEng.htm.

Any designations on maps or other references employed in this project document do not imply the expression of any opinion whatsoever on the part of UNDP concerning the legal status of any country, territory, city or area or its authorities, or concerning the delimitation of its frontiers or boundaries.

# K.	Required Annexes

Annex 1:	Capacity Development Scorecard

Annex 2:	Total Input Budget and Work Plan (Detailed)

Annex 3:	Provisional Multi-year Work Plan

Annex 4:	Monitoring Plan

Annex 5:	UNDP Social and Environmental and Social Screening Template (SESP)

Annex 6:	UNDP Project Quality Assurance Report

Annex 7:	Standard letter of agreement between UNDP and Government

Annex 8:	Capacity assessment results: implementing partner and HACT micro assessment

Annex 9:	Terms of Reference

Annex 10:	References

## Annex 1:	Capacity Development Scorecard

Project Name:	Strengthening of institutional and legal capacities to enable improvement of the national monitoring system and management of environmental information

Project Cycle Phase:	PPG					Date: April 2017

| Capacity Result / Indicator | Staged Indicators |  | Rating | Score | Comments | Next Steps | Contribution to which Outcome |
| --- | --- | --- | --- | --- | --- | --- | --- |
| CR 1: Capacities for engagement |  |  |  |  |  |  |  |
| Indicator 1 – Degree of legitimacy/ mandate of lead environmental organizations | Organizational responsibilities for environmental management are not clearly defined | 0 |  |  | The EPA has the statutory mandate for management of the environmental sector but doesn’t have the full capacity/expertise to carry out this mandate. Other ministries and agencies have more relevant expertise in particular disciplines to complement that of the EPA. | The project will improve the ability of key environmental organizations to carry out their mandates and other responsibilities focusing on integrating global environmental objectives into national and sub-national policy and planning frameworks. The awareness and sensitization of social actors in the non-environmental sectors, decision-makers, non-state stakeholders, and civil society in general will be targeted in component 3 in order to increase the recognition of environmental organizations’ mandates and legitimacy. | 2, 3 |
|  | Organizational responsibilities for environmental management are identified | 1 |  |  |  |  |  |
|  | Authority and legitimacy of all lead organizations responsible for environmental management are partially recognized by stakeholders | 2 |  | 2 |  |  |  |
|  | Authority and legitimacy of all lead organizations responsible for environmental management recognized by stakeholders | 3 |  |  |  |  |  |
| Indicator 2 – Existence of operational co-management mechanisms | No co-management mechanisms are in place | 0 |  |  | There is some level of collaborative management between some governmental agencies and the private sector within the country. | Notwithstanding the current set of cooperative agreements among certain government bodies, the project will assess their effectiveness and lessons learned in order to facilitate the development of new agreements and/or the updating and operationalization of current MOUs. Importantly, the project will develop liaison protocols among partner agencies and Memoranda of Agreement with other non-state stakeholder organizations. | 2 |
|  | Some co-management mechanisms are in place and operational | 1 |  |  |  |  |  |
|  | Some co-management mechanisms are formally established through agreements, MOUs, etc. | 2 |  | 2 |  |  |  |
|  | Comprehensive co-management mechanisms are formally established and are operational/functional | 3 |  |  |  |  |  |
| Indicator 3 – Existence of cooperation with stakeholder groups | Identification of stakeholders and their participation/involvement in decision-making is poor | 0 |  |  | Currently, just about all national institutions have mandates that are driven towards stakeholder involvement. Some mechanisms are ad hoc or implicit arrangements. | The learning-by-doing approach of this project is intended to allow stakeholders to actively participate and build long-term technical capacities to better understand and apply global environmental indicators to mainstream the Rio Conventions and MEAs into decision-making. Particular attention will be given to demonstrating the value of teamwork among government agencies and other stakeholders with a view to integrating global environmental priorities into development plans at the national and sub-national levels. The project will also promote awareness and agreement on the various comparative advantages of different stakeholder organizations to promote global environment values and make stakeholders more influential in decision-making. | 1, 2, 3, 4 |
|  | Stakeholders are identified but their participation in decision-making is limited | 1 |  |  |  |  |  |
|  | Stakeholders are identified and regular consultations mechanisms are established | 2 |  | 2 |  |  |  |
|  | Stakeholders are identified and they actively contribute to established participative decision-making processes | 3 |  |  |  |  |  |
| CR 2: Capacities to generate, access and use information and knowledge |  |  |  |  |  |  |  |
| Indicator 4 – Degree of environmental awareness of stakeholders | Stakeholders are not aware about global environmental issues and their related possible solutions (MEAs) | 0 |  |  | While stakeholders are aware of global environmental issues, most stakeholders are not willing to participate because of their self- interest; they believe result based solutions are lacking. | The project will carry out a number of awareness-raising activities, as well as to institutionalize an EKMS. | 1, 3 |
|  | Stakeholders are aware about global environmental issues but not about the possible solutions (MEAs) | 1 |  | 1 |  |  |  |
|  | Stakeholders are aware about global environmental issues and the possible solutions but do not know how to participate | 2 |  |  |  |  |  |
|  | Stakeholders are aware about global environmental issues and are actively participating in the implementation of related solutions | 3 |  |  |  |  |  |
| Indicator 5 – Access and sharing of environmental information by stakeholders | The environmental information needs are not identified and the information management infrastructure is inadequate | 0 |  |  | International experts hired on certain projects do not share findings from their research with their Liberian counterparts and require fees to be paid for assessing data from the Liberian experts. Line ministries and agencies are just starting to have environmental databases available; they were completely absent in the past. | An EKMS will be developed and implemented. The project will also provide training on the use of the EKMS. Targeted management arrangements for sharing information will also be developed, and the project will develop information-sharing and collaborative agreements, to agree on priority channels of environmental information exchange across sectors and ministries. | 1, 2 |
|  | The environmental information needs are identified but the information management infrastructure is inadequate | 1 |  | 1 |  |  |  |
|  | The environmental information is partially available and shared among stakeholders but is not covering all focal areas and/or the information management infrastructure to manage and give information access to the public is limited | 2 |  |  |  |  |  |
|  | Comprehensive environmental information is available and shared through an adequate information management infrastructure | 3 |  |  |  |  |  |
| Indicator 6 – Existence of environmental education programmes | No environmental education programmes are in place | 0 |  |  | Some institutions have begun to undertake environmental awareness programs as part of their activities. WASH awareness is being promoted by the WASH secretariat through regular radio talk shows, newsletters, and stakeholder meetings. | - The project will work with partner institutions to strengthen education. An environmental awareness module for schools will be developed. Stakeholders will learn best practices on data access and interpretation for environmental management and evidence-based development planning using modules developed under the project. The project will coordinate with other similar training workshops carried under other related projects and the training being developed and carried out by the stakeholders. | 3 |
|  | Environmental education programmes are partially developed and partially delivered | 1 |  | 1 |  |  |  |
|  | Environmental education programmes are fully developed but partially delivered | 2 |  |  |  |  |  |
|  | Comprehensive environmental education programmes exist and are being delivered | 3 |  |  |  |  |  |
| Indicator 7 – Extend of the linkage between environmental research/science and policy development | No linkage exist between environmental policy development and science/research strategies and programmes | 0 |  | 0 | Research institutions are severely lacking in their capacity to carry out basic research to influence policy making. | As part of the EKMS development, the importance of using data for decision-making will be part of the training and sensitization workshops. Additionally, the project has demonstration and piloting of plans with integrated environmental-development best practices that reflect global environmental priorities and the Post-2015 Sustainable Development Goals. | 1, 3 |
|  | Research needs for environmental policy development are identified but are not translated into relevant research strategies and programmes | 1 |  |  |  |  |  |
|  | Relevant research strategies and programmes for environmental policy development exist but the research information is not responding fully to the policy research needs | 2 |  |  |  |  |  |
|  | Relevant research results are available for environmental policy development | 3 |  |  |  |  |  |
| Indicator 8 – Extend of inclusion/use of traditional knowledge in environmental decision-making | Traditional knowledge is ignored and not taken into account into relevant participative decision-making processes | 0 |  |  | Traditional knowledge is mostly ignored and not taken into account | Stakeholder representatives, in particular staff from government, NGOs, academia, and the research community, will be brought together to discuss and agree on best practicable approaches to collaborate and coordinate their respective activities with a view to maximizing the utility of high quality data, information and knowledge. | 1, 3 |
|  | Traditional knowledge is identified and recognized as important but is not collected and used in relevant participative decision-making processes | 1 |  | 1 |  |  |  |
|  | Traditional knowledge is collected but is not used systematically into relevant participative decision-making processes | 2 |  |  |  |  |  |
|  | Traditional knowledge is collected, used and shared for effective participative decision-making processes | 3 |  |  |  |  |  |
| CR 3: Capacities for strategy, policy and legislation development |  |  |  |  |  |  |  |
| Indicator 9 – Extent of the environmental planning and strategy development process | The environmental planning and strategy development process is not coordinated and does not produce adequate environmental plans and strategies | 0 |  |  | No action has been taken on key recommendations from the 1st National Communication, which detailed the state of the country’s environment. Projects identified in the NAPA have not been taken on. The country’s Agenda for Transformation have plans that are adequate but are mostly not implemented. | The project will build upon Liberia’s political commitment to reform its environmental sector in support of provisions under the Rio Conventions. Through learning-by-doing workshops and exercises, participants will review, revise, and develop appropriate legislative and regulatory instruments to better reflect and support global environmental objectives within the framework of socio-economic policies. | 2 |
|  | The environmental planning and strategy development process does produce adequate environmental plans and strategies but there are not implemented/used | 1 |  |  |  |  |  |
|  | Adequate environmental plans and strategies are produced but there are only partially implemented because of funding constraints and/or other problems | 2 |  | 2 |  |  |  |
|  | The environmental planning and strategy development process is well coordinated by the lead environmental organizations and produces the required environmental plans and strategies; which are being implemented | 3 |  |  |  |  |  |
| Indicator 10 – Existence of an adequate environmental policy and regulatory frameworks | The environmental policy and regulatory frameworks are insufficient; they do not provide an enabling environment | 0 |  |  | Liberia is very good at making laws and policies but very poor in implementing them (e.g., the wetlands, wildlife, climate change, and Integrated Water Management laws are all “hanging”). There are no national policies on some of the Conventions signed by the government. | The project will focus on key reforms in policy, legislation, and implementation in accordance with the provisions under the Rio Conventions through by-laws and/or associated operational guidance. For these to have a meaningful impact, they will need to be formally approved. This project will also strengthen targeted organizational relationships, promoting and forging stronger partnerships and commitments. These will be directed towards improved collaboration and coordination that will increase the effectiveness of existing capacities to monitor and formulate better planning frameworks for the global environment. | 2 |
|  | Some relevant environmental policies and laws exist but few are implemented and enforced | 1 |  | 1 |  |  |  |
|  | Adequate environmental policy and legislation frameworks exist but there are problems in implementing and enforcing them | 2 |  |  |  |  |  |
|  | Adequate policy and legislation frameworks are implemented and provide an adequate enabling environment; a compliance and enforcement mechanism is established and functions | 3 |  |  |  |  |  |
| Indicator 11 – Adequacy of the environmental information available for decision-making | The availability of environmental information for decision-making is lacking | 0 |  |  | The 14 year civil war greatly stunted the strives made by the various institutions in gathering data on the environment. However, post-war Liberia has seen a renewed interest in environmental issues. The EPA now has the defined mandate of oversight responsibility of the environment. However, the issue of some lingering/conflicting responsibilities of other line ministries & agencies still exist. Limited allocation of national funding to the enormous task of environmental research, monitoring & evaluation is greatly hampering the ability of acquiring environmental data. | The project will assess and strengthen existing consultative and decision-making structures and mechanisms to make more effective and integrated decisions on the global environment. Moreover, the project includes an EKMS that will serve to increase access to data, information and knowledge, as well as a robust training programme that will strengthen critical thinking and impart new and improved analytical tools and processes. A public awareness campaign will increase the number of stakeholders that understand the relationship between local action and the global environment, with particular attention to strengthening the consensus on the impacts of local action on the global environment. | 1, 2, 3 |
|  | Some environmental information exists but it is not sufficient to support environmental decision-making processes | 1 |  | 1 |  |  |  |
|  | Relevant environmental information is made available to environmental decision-makers but the process to update this information is not functioning properly | 2 |  |  |  |  |  |
|  | Political and administrative decision-makers obtain and use updated environmental information to make environmental decisions | 3 |  |  |  |  |  |
| CR 4: Capacities for management and implementation |  |  |  |  |  |  |  |
| Indicator 12 – Existence and mobilization of resources | The environmental organizations do not have adequate resources for their programmes and projects and the requirements have not been assessed | 0 |  |  | The country is being greatly assisted in its developmental agenda with the environment being no exception. However, the co-financing component which is a part of most financing arrangements is difficult to achieve as the government struggles to spread the limited financial resources it has amongst competing projects | In order to alleviate financial barriers to the implementation of the Conventions, the project will organize a resource mobilization strategy to perform a set of resource mobilization activities in a coordinated manner. | 2 |
|  | The resource requirements are known but are not being addressed | 1 |  |  |  |  |  |
|  | The funding sources for these resource requirements are partially identified and the resource requirements are partially addressed | 2 |  | 2 |  |  |  |
|  | Adequate resources are mobilized and available for the functioning of the lead environmental organizations | 3 |  |  |  |  |  |
| Indicator 13 – Availability of required technical skills and technology transfer | The necessary required skills and technology are not available and the needs are not identified | 0 |  |  | Over the years, highly trained young professionals have been added to the available scientific workforce with high competencies. The international donor community (United Nations, EU, GIZ, USAID, etc.,) has been extremely helpful in assisting the country in the environmental sector | A key feature of the project is the learning-by-doing workshops and exercises in order to foster greater critical thinking among a sufficiently large number of social actors and stakeholders of environmental management and governance. The institutionalization of these skills will also be addressed by the development of an extensive programme of training, information dissemination and advocacy, as well as a resource mobilization strategy to implement this programme over the long-term. | 1, 2, 3, 4 |
|  | The required skills and technologies needs are identified as well as their sources | 1 |  | 1 |  |  |  |
|  | The required skills and technologies are obtained but their access depend on foreign sources | 2 |  |  |  |  |  |
|  | The required skills and technologies are available and there is a national-based mechanism for updating the required skills and for upgrading the technologies | 3 |  |  |  |  |  |
| CR 5: Capacities to monitor and evaluate |  |  |  |  |  |  |  |
| Indicator 14 – Adequacy of the project/programme monitoring process | Irregular project monitoring is being done without an adequate monitoring framework detailing what and how to monitor the particular project or programme | 0 |  |  | All projects now have a monitoring and evaluation component attached to them, however, feedback is not forthcoming. | The project will set up mechanism to monitor implementation and piloting. Additionally, the project will work to strengthen technical capacities for mainstreaming and monitoring of the Rio Conventions. The project also includes a Monitoring and Evaluation plan. | 1, 2, 3, 4 |
|  | An adequate resourced monitoring framework is in place but project monitoring is irregularly conducted | 1 |  | 1 |  |  |  |
|  | Regular participative monitoring of results in being conducted but this information is only partially used by the project/programme implementation team | 2 |  |  |  |  |  |
|  | Monitoring information is produced timely and accurately and is used by the implementation team to learn and possibly to change the course of action | 3 |  |  |  |  |  |
| Indicator 15 – Adequacy of the project/programme evaluation process | None or ineffective evaluations are being conducted without an adequate evaluation plan; including the necessary resources | 0 |  |  | Feedbacks from evaluations of different projects are readily available to the relevant managers/heads of entities. However, implementation/execution of feedback is the greatest default in the M & E process | - For evaluating the adequacy of project/programme monitoring, progress reports will be prepared periodically. Also, an independent final evaluation report will be prepared. - Programme evaluation is a critical part of the project, reflected by the learning-by-doing workshops and exercises to mainstream the global environment into development planning frameworks. - A very important part of programme evaluation is the capacity to interpret data and information leading to the creation and use of knowledge to better inform more holistic, resilient, and institutionally sustainable development constructs, i.e., policies, plans, programmes, legislative and regulatory frameworks, and natural resource management regimes. | 1, 2, 3, 4 |
|  | An adequate evaluation plan is in place but evaluation activities are irregularly conducted | 1 |  |  |  |  |  |
|  | Evaluations are being conducted as per an adequate evaluation plan but the evaluation results are only partially used by the project/programme implementation team | 2 |  | 2 |  |  |  |
|  | Effective evaluations are conducted timely and accurately and are used by the implementation team and the Agencies and GEF Staff to correct the course of action if needed and to learn for further planning activities | 3 |  |  |  |  |  |
| …. Add your own indicator(s) |  |  |  |  |  |  |  |

## Annex 2:	Provisional Multi-year Work Plan

| Provisional Work Plan |  | Year 1 |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Activity | Description | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 |
| Component 1 | Establishment of an integrated environmental knowledge management system (EKMS) to meet global environment and sustainable development priorities |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 1.1 | Institutional mapping and analysis of an optimal knowledge management system |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.1.1 | Undertake a SWOT and gap analysis of the institutional requirements to use best available and innovation data, information and knowledge |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.1.2 | Carry out an assessment of stakeholders' awareness and absorptive capacities to manage and monitor environmental information relevant to the Rio Conventions |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.1.3 | Organize and convene MEA technical committee meetings to discuss and recommend best practices for collecting and managing environmental data, information, and knowledge |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 1.2 | Design of an integrated environmental knowledge management system |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.2.1 | Convene stakeholder workshops on the management of information and knowledge for planning and policy-making |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.2.2 | Design the technological requirements for collecting, storing, and sharing data and information. |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.2.3 | Undertake an independent peer review of the EKMS feasibility study, finalize, and secure stakeholder validation and the required official approvals |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 1.3: | Targeted technological networking of existing information and knowledge management systems. |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.3.1 | Negotiate and facilitate the formulation and adoption of networking cooperative agreements on information and knowledge management with key institutions. |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.3.2 | Institute targeted management arrangements for sharing information. |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 1.4: | Selected updating of technologies to create cost-effective synergies for knowledge management. |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.4.1 | Procure and install the technological hardware and software of the EKMS as recommended in the approved feasibility study |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 1.5: | Integration of new and improved global environmental indicators into select sectoral development plan(s) |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.5.1 | Identify a set of best applicable indicators for measuring global environmental trends within the context of planning and policy-making in Liberia. |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.5.2 | Prepare technical guidance material for planners and other users of indicators relevant to the monitoring of the global environment. |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 1.6: | Learning-by-doing training on improved methodologies and analytical skills for interpreting global environmental trends and understanding their relevance to sectoral development |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.6.1 | Undertake a comprehensive assessment of training needs to manage data and information. |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.6.2 | Prepare a training programme and curriculum that builds on the earlier analyses. |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.6.3 | Carry out training workshops on the management of existing and new data and information through the EKMS. |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 1.7: | Early implementation and piloting of the integrated environmental knowledge management system through a select sectoral plan. |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.7.1 | Select one high value sectoral development plan for early implementation and piloting through a broad-based consultative process. |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.7.2 | Convene learning-by-doing workshops to use the EKMS to demonstrate its value at improving a more holistic and resilient construct of the selected sectoral plan in keeping with Rio Convention obligations. |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.7.3 | Facilitate dialogues on the EKMS and its implementation with decision- and policy-makers to enhance their understanding and secure their support and championship. |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.7.4 | Prepare lessons learned study on the use of the EKMS to mainstream Rio Convention obligations into sectoral plans and policies. |  |  |  |  |  |  |  |  |  |  |  |  |
| Component 2 | Enhanced institutional and technical capacities to mainstream, develop, and utilize policies and/or legislative frameworks for effective implementation of the three Rio Conventions |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 2.1 | In-depth SWOT and gap analysis of existing environmental policies and legislation, and the effectiveness of their enforcement |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.1.1 | Undertake an in-depth analysis of Liberia's policy, legislative, and regulatory framework on environmental governance |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.1.2 | Undertake a SWOT and gap analysis of sector policies to ascertain the extent to which they support or work against meeting and sustaining Rio Convention obligations. |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 2.2 | Strengthened policy and regulatory framework through improved operational interpretation, enforcement tools, and by-laws |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.2.1 | Carry out learning-by-doing training workshops to understand and reconcile weaknesses and gaps in key environmental policies and legal instruments |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.2.2 | Formulate appropriate by-laws and operational guidance to mainstream Rio Conventions. |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.2.3 | Secure approval of by-laws and any other amended policy, legislative, or regulatory texts |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.2.4 | Distribute updated codes, laws and relevant texts pertaining to Rio Convention implementation. |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 2.3 | Strengthened consultative and decision-making processes for mainstreaming of Rio Convention obligations. |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.3.1 | Convene working group meetings to negotiate best consultative and decision-making processes. |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.3.2 | Draft the memoranda of agreement on consultative and decision-making processes |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 2.4 | Targeted updating and streamlining of institutional mandates to facilitate and catalyze long-term action to meet global environmental obligations |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.4.1 | Reconcile and harmonize the various mandates and operational plans of the relevant national commissions, local and regional authorities, and other key institutions to integrate Rio Convention obligations. |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 2.5 | Enhanced monitoring and compliance arrangements, e.g., environmental impact and strategic environmental assessments |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.5.1 | Assess current data collection and generation methods of key agencies with attention to harmonization and metrics, relevance, validity, and quality. |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.5.2 | Recommend improved monitoring and compliance reforms based on learning-by-doing exercises to formulate best practices and guidelines. Draft and validate guidelines for coordinated monitoring and compliance. Develop quality control/validation procedures and identify responsible scientific and institutional correspondents. |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 2.6 | Demonstration and piloting of integrated environmental-development best practices that reflect global environmental priorities and the Post-2015 Sustainable Development Goals. |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.6.1 | Structure technical working groups for each of the three Rio Conventions on legislative responses and amendments. |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.6.2 | Identify and select the environmental-development best practices that are to be piloted through the use of the EKMS for a high value sectoral development plan |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.6.3 | Undertake an assessment of lessons learned and best practices through the early implementation and piloting of the EKMS for Rio Convention mainstreaming. |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 2.7 | Resource mobilization strategy |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.7.1 | Undertake a financial and economic analysis of monitoring, enforcement, and compliance of Rio Convention implementation |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.7.2 | Undertake a series of learning-by-doing workshops to draft a resource mobilization strategy. |  |  |  |  |  |  |  |  |  |  |  |  |
| Component 3 | Improving awareness of global environmental values and knowledge management |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 3:1 | Stakeholder dialogues on the value of Rio Conventions |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.1.1 | Organize and convene a one-day Kick-Off Conference and a one-day Project Results Conference |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.1.2 | Develop and validate public awareness and communication campaign plan. |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.1.3 | Convene three (3) public policy dialogues |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.1.4 | Convene national and sub-national awareness workshops |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.1.5 | Convene private sector sensitization panel discussions on the global environmental issues |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.1.6 | Convene workshops targeted to media professionals to improve environmental reporting |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 3.2 | Brochures and articles on the Rio Conventions |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.2.1 | Prepare and publish articles on linkages between the global environment and socio-economic issues |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 3.3 | Public service announcement(s) on globally sensitive and environmentally friendly behavior |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.3.1 | Prepare and air a public service announcement on Rio Convention mainstreaming |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 3.4 | Improved environmental educational curricula and youth civic engagement |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.4.1 | Develop and apply an awareness module for institutions on Rio Conventions mainstreaming and monitoring |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.4.2 | Prepare and integrate an environmental awareness module into school curricula |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 3.5 | Internet visibility of integrated approaches to meet Rio Convention obligations and national sustainable development priorities. |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.5.1 | Convene working group meetings among key agencies that have websites relevant to environmental governance and negotiate opportunities to improve the design and content of their respective webpages. |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.5.2 | Create a Facebook page on environmental information and Rio Convention mainstreaming. Upload relevant content at least twice per week. |  |  |  |  |  |  |  |  |  |  |  |  |
| Component 4 | NCSA is updated to reflect post 2015-SDGs and current opportunities to strengthen priority foundational capacities for the global environment |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 4:1 | Updated assessments of capacity challenges to meet and sustain Rio Convention obligations, building upon GEF focal area enabling activities |  |  |  |  |  |  |  |  |  |  |  |  |
| 4.1.1 | Prepare and validate the methodology to update the NCSA and integrate the post-2015 SDGs. |  |  |  |  |  |  |  |  |  |  |  |  |
| 4.1.2 | Design and carry out a survey to assess public awareness of the importance of the Rio Conventions to catalyzing sustainable development. |  |  |  |  |  |  |  |  |  |  |  |  |
| 4.1.3 | Conduct individual interviews to gather additional inputs on national priorities and constraints for improved and sustained environmental governance. |  |  |  |  |  |  |  |  |  |  |  |  |
| 4.1.4 | Draft thematic assessments of the challenges and opportunities to meet obligations under three Rio Conventions |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 4.2 | Integrated cross-cutting analysis of systemic, institutional, and individual capacity development priorities |  |  |  |  |  |  |  |  |  |  |  |  |
| 4.2.1 | Synthesize the findings and assessments of output 4.1 into a synthesis of the systemic, institutional, and individual capacity development challenges, priorities, and opportunities to meet and sustain Rio Convention obligations within the framework of national sustainable development priorities. |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 4.3 | Capacity Development Strategy and Action Plan, building on action plans of GEF focal area enabling activities |  |  |  |  |  |  |  |  |  |  |  |  |
| 4.3.1 | Review the action plans of GEF focal area enabling activities (such as the national strategies and actions plans under the three Rio Conventions) as well as other national sustainable development strategies. |  |  |  |  |  |  |  |  |  |  |  |  |
| 4.3.2 | Formulate a capacity development strategy and action plan. |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 4.4 | Update NCSA Final Report |  |  |  |  |  |  |  |  |  |  |  |  |
| 4.4.1 | Draft and validate the updated NCSA Final Report. |  |  |  |  |  |  |  |  |  |  |  |  |
| 4.4.2 | Convene a roundtable for donors to present the NCSA and Action Plan in order to leverage financial support from development partners |  |  |  |  |  |  |  |  |  |  |  |  |
| 4.4.3 | Finalize and present the NCSA Final Report and Action Plan at the Project Result Conference |  |  |  |  |  |  |  |  |  |  |  |  |
| Project Management |  |  |  |  |  |  |  |  |  |  |  |  |  |
| A | Project Administration |  |  |  |  |  |  |  |  |  |  |  |  |
| B | Independent Terminal Evaluation |  |  |  |  |  |  |  |  |  |  |  |  |
| C | Project Board Meetings |  |  |  |  |  |  |  |  |  |  |  |  |

| Provisional Work Plan |  | Year 2 |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Activity | Description | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 |
| Component 1 | Establishment of an integrated environmental knowledge management system (EKMS) to meet global environment and sustainable development priorities |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 1.1 | Institutional mapping and analysis of an optimal knowledge management system |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.1.1 | Undertake a SWOT and gap analysis of the institutional requirements to use best available and innovation data, information and knowledge |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.1.2 | Carry out an assessment of stakeholders' awareness and absorptive capacities to manage and monitor environmental information relevant to the Rio Conventions |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.1.3 | Organize and convene MEA technical committee meetings to discuss and recommend best practices for collecting and managing environmental data, information, and knowledge |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 1.2 | Design of an integrated environmental knowledge management system |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.2.1 | Convene stakeholder workshops on the management of information and knowledge for planning and policy-making |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.2.2 | Design the technological requirements for collecting, storing, and sharing data and information. |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.2.3 | Undertake an independent peer review of the EKMS feasibility study, finalize, and secure stakeholder validation and the required official approvals |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 1.3: | Targeted technological networking of existing information and knowledge management systems. |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.3.1 | Negotiate and facilitate the formulation and adoption of networking cooperative agreements on information and knowledge management with key institutions. |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.3.2 | Institute targeted management arrangements for sharing information. |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 1.4: | Selected updating of technologies to create cost-effective synergies for knowledge management. |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.4.1 | Procure and install the technological hardware and software of the EKMS as recommended in the approved feasibility study |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 1.5: | Integration of new and improved global environmental indicators into select sectoral development plan(s) |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.5.1 | Identify a set of best applicable indicators for measuring global environmental trends within the context of planning and policy-making in Liberia. |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.5.2 | Prepare technical guidance material for planners and other users of indicators relevant to the monitoring of the global environment. |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 1.6: | Learning-by-doing training on improved methodologies and analytical skills for interpreting global environmental trends and understanding their relevance to sectoral development |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.6.1 | Undertake a comprehensive assessment of training needs to manage data and information. |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.6.2 | Prepare a training programme and curriculum that builds on the earlier analyses. |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.6.3 | Carry out training workshops on the management of existing and new data and information through the EKMS. |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 1.7: | Early implementation and piloting of the integrated environmental knowledge management system through a select sectoral plan. |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.7.1 | Select one high value sectoral development plan for early implementation and piloting through a broad-based consultative process. |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.7.2 | Convene learning-by-doing workshops to use the EKMS to demonstrate its value at improving a more holistic and resilient construct of the selected sectoral plan in keeping with Rio Convention obligations. |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.7.3 | Facilitate dialogues on the EKMS and its implementation with decision- and policy-makers to enhance their understanding and secure their support and championship. |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.7.4 | Prepare lessons learned study on the use of the EKMS to mainstream Rio Convention obligations into sectoral plans and policies. |  |  |  |  |  |  |  |  |  |  |  |  |
| Component 2 | Enhanced institutional and technical capacities to mainstream, develop, and utilize policies and/or legislative frameworks for effective implementation of the three Rio Conventions |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 2.1 | In-depth SWOT and gap analysis of existing environmental policies and legislation, and the effectiveness of their enforcement |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.1.1 | Undertake an in-depth analysis of Liberia's policy, legislative, and regulatory framework on environmental governance |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.1.2 | Undertake a SWOT and gap analysis of sector policies to ascertain the extent to which they support or work against meeting and sustaining Rio Convention obligations. |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 2.2 | Strengthened policy and regulatory framework through improved operational interpretation, enforcement tools, and by-laws |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.2.1 | Carry out learning-by-doing training workshops to understand and reconcile weaknesses and gaps in key environmental policies and legal instruments |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.2.2 | Formulate appropriate by-laws and operational guidance to mainstream Rio Conventions. |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.2.3 | Secure approval of by-laws and any other amended policy, legislative, or regulatory texts |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.2.4 | Distribute updated codes, laws and relevant texts pertaining to Rio Convention implementation. |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 2.3 | Strengthened consultative and decision-making processes for mainstreaming of Rio Convention obligations. |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.3.1 | Convene working group meetings to negotiate best consultative and decision-making processes. |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.3.2 | Draft the memoranda of agreement on consultative and decision-making processes |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 2.4 | Targeted updating and streamlining of institutional mandates to facilitate and catalyze long-term action to meet global environmental obligations |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.4.1 | Reconcile and harmonize the various mandates and operational plans of the relevant national commissions, local and regional authorities, and other key institutions to integrate Rio Convention obligations. |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 2.5 | Enhanced monitoring and compliance arrangements, e.g., environmental impact and strategic environmental assessments |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.5.1 | Assess current data collection and generation methods of key agencies with attention to harmonization and metrics, relevance, validity, and quality. |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.5.2 | Recommend improved monitoring and compliance reforms based on learning-by-doing exercises to formulate best practices and guidelines. Draft and validate guidelines for coordinated monitoring and compliance. Develop quality control/validation procedures and identify responsible scientific and institutional correspondents. |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 2.6 | Demonstration and piloting of integrated environmental-development best practices that reflect global environmental priorities and the Post-2015 Sustainable Development Goals. |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.6.1 | Structure technical working groups for each of the three Rio Conventions on legislative responses and amendments. |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.6.2 | Identify and select the environmental-development best practices that are to be piloted through the use of the EKMS for a high value sectoral development plan |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.6.3 | Undertake an assessment of lessons learned and best practices through the early implementation and piloting of the EKMS for Rio Convention mainstreaming. |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 2.7 | Resource mobilization strategy |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.7.1 | Undertake a financial and economic analysis of monitoring, enforcement, and compliance of Rio Convention implementation |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.7.2 | Undertake a series of learning-by-doing workshops to draft a resource mobilization strategy. |  |  |  |  |  |  |  |  |  |  |  |  |
| Component 3 | Improving awareness of global environmental values and knowledge management |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 3:1 | Stakeholder dialogues on the value of Rio Conventions |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.1.1 | Organize and convene a one-day Kick-Off Conference and a one-day Project Results Conference |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.1.2 | Develop and validate public awareness and communication campaign plan. |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.1.3 | Convene three (3) public policy dialogues |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.1.4 | Convene national and sub-national awareness workshops |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.1.5 | Convene private sector sensitization panel discussions on the global environmental issues |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.1.6 | Convene workshops targeted to media professionals to improve environmental reporting |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 3.2 | Brochures and articles on the Rio Conventions |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.2.1 | Prepare and publish articles on linkages between the global environment and socio-economic issues |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 3.3 | Public service announcement(s) on globally sensitive and environmentally friendly behavior |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.3.1 | Prepare and air a public service announcement on Rio Convention mainstreaming |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 3.4 | Improved educational curricula and youth civic engagement |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.4.1 | Develop and apply an awareness module for institutions on Rio Conventions mainstreaming and monitoring |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.4.2 | Prepare and integrate an environmental awareness module into school curricula |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 3.5 | Internet visibility of integrated approaches to meet Rio Convention obligations and national sustainable development priorities. |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.5.1 | Convene working group meetings among key agencies that have websites relevant to environmental governance and negotiate opportunities to improve the design and content of their respective webpages. |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.5.2 | Create a Facebook page on environmental information and Rio Convention mainstreaming. Upload relevant content at least twice per week. |  |  |  |  |  |  |  |  |  |  |  |  |
| Component 4 | NCSA is updated to reflect post 2015-SDGs and current opportunities to strengthen priority foundational capacities for the global environment |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 4:1 | Updated assessments of capacity challenges to meet and sustain Rio Convention obligations, building upon GEF focal area enabling activities |  |  |  |  |  |  |  |  |  |  |  |  |
| 4.1.1 | Prepare and validate the methodology to update the NCSA and integrate the post-2015 SDGs. |  |  |  |  |  |  |  |  |  |  |  |  |
| 4.1.2 | Design and carry out a survey to assess public awareness of the importance of the Rio Conventions to catalyzing sustainable development. |  |  |  |  |  |  |  |  |  |  |  |  |
| 4.1.3 | Conduct individual interviews to gather additional inputs on national priorities and constraints for improved and sustained environmental governance. |  |  |  |  |  |  |  |  |  |  |  |  |
| 4.1.4 | Draft thematic assessments of the challenges and opportunities to meet obligations under three Rio Conventions |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 4.2 | Integrated cross-cutting analysis of systemic, institutional, and individual capacity development priorities |  |  |  |  |  |  |  |  |  |  |  |  |
| 4.2.1 | Synthesize the findings and assessments of output 4.1 into a synthesis of the systemic, institutional, and individual capacity development challenges, priorities, and opportunities to meet and sustain Rio Convention obligations within the framework of national sustainable development priorities. |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 4.3 | Capacity Development Strategy and Action Plan, building on action plans of GEF focal area enabling activities |  |  |  |  |  |  |  |  |  |  |  |  |
| 4.3.1 | Review the action plans of GEF focal area enabling activities (such as the national strategies and actions plans under the three Rio Conventions) as well as other national sustainable development strategies. |  |  |  |  |  |  |  |  |  |  |  |  |
| 4.3.2 | Formulate a capacity development strategy and action plan. |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 4.4 | Update NCSA Final Report |  |  |  |  |  |  |  |  |  |  |  |  |
| 4.4.1 | Draft and validate the updated NCSA Final Report. |  |  |  |  |  |  |  |  |  |  |  |  |
| 4.4.2 | Convene a roundtable for donors to present the NCSA and Action Plan in order to leverage financial support from development partners |  |  |  |  |  |  |  |  |  |  |  |  |
| 4.4.3 | Finalize and present the NCSA Final Report and Action Plan at the Project Result Conference |  |  |  |  |  |  |  |  |  |  |  |  |
| Project Management |  |  |  |  |  |  |  |  |  |  |  |  |  |
| A | Project Administration |  |  |  |  |  |  |  |  |  |  |  |  |
| B | Independent Terminal Evaluation |  |  |  |  |  |  |  |  |  |  |  |  |
| C | Project Board Meetings |  |  |  |  |  |  |  |  |  |  |  |  |

| Provisional Work Plan |  | Year 3 |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Activity | Description | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 |
| Component 1 | Establishment of an integrated environmental knowledge management system (EKMS) to meet global environment and sustainable development priorities |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 1.1 | Institutional mapping and analysis of an optimal knowledge management system |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.1.1 | Undertake a SWOT and gap analysis of the institutional requirements to use best available and innovation data, information and knowledge |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.1.2 | Carry out an assessment of stakeholders' awareness and absorptive capacities to manage and monitor environmental information relevant to the Rio Conventions |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.1.3 | Organize and convene MEA technical committee meetings to discuss and recommend best practices for collecting and managing environmental data, information, and knowledge |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 1.2 | Design of an integrated environmental knowledge management system |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.2.1 | Convene stakeholder workshops on the management of information and knowledge for planning and policy-making |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.2.2 | Design the technological requirements for collecting, storing, and sharing data and information. |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.2.3 | Undertake an independent peer review of the EKMS feasibility study, finalize, and secure stakeholder validation and the required official approvals |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 1.3: | Targeted technological networking of existing information and knowledge management systems. |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.3.1 | Negotiate and facilitate the formulation and adoption of networking cooperative agreements on information and knowledge management with key institutions. |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.3.2 | Institute targeted management arrangements for sharing information. |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 1.4: | Selected updating of technologies to create cost-effective synergies for knowledge management. |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.4.1 | Procure and install the technological hardware and software of the EKMS as recommended in the approved feasibility study |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 1.5: | Integration of new and improved global environmental indicators into select sectoral development plan(s) |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.5.1 | Identify a set of best applicable indicators for measuring global environmental trends within the context of planning and policy-making in Liberia. |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.5.2 | Prepare technical guidance material for planners and other users of indicators relevant to the monitoring of the global environment. |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 1.6: | Learning-by-doing training on improved methodologies and analytical skills for interpreting global environmental trends and understanding their relevance to sectoral development |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.6.1 | Undertake a comprehensive assessment of training needs to manage data and information. |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.6.2 | Prepare a training programme and curriculum that builds on the earlier analyses. |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.6.3 | Carry out training workshops on the management of existing and new data and information through the EKMS. |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 1.7: | Early implementation and piloting of the integrated environmental knowledge management system through a select sectoral plan. |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.7.1 | Select one high value sectoral development plan for early implementation and piloting through a broad-based consultative process. |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.7.2 | Convene learning-by-doing workshops to use the EKMS to demonstrate its value at improving a more holistic and resilient construct of the selected sectoral plan in keeping with Rio Convention obligations. |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.7.3 | Facilitate dialogues on the EKMS and its implementation with decision- and policy-makers to enhance their understanding and secure their support and championship. |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.7.4 | Prepare lessons learned study on the use of the EKMS to mainstream Rio Convention obligations into sectoral plans and policies. |  |  |  |  |  |  |  |  |  |  |  |  |
| Component 2 | Enhanced institutional and technical capacities to mainstream, develop, and utilize policies and/or legislative frameworks for effective implementation of the three Rio Conventions |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 2.1 | In-depth SWOT and gap analysis of existing environmental policies and legislation, and the effectiveness of their enforcement |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.1.1 | Undertake an in-depth analysis of Liberia's policy, legislative, and regulatory framework on environmental governance |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.1.2 | Undertake a SWOT and gap analysis of sector policies to ascertain the extent to which they support or work against meeting and sustaining Rio Convention obligations. |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 2.2 | Strengthened policy and regulatory framework through improved operational interpretation, enforcement tools, and by-laws |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.2.1 | Carry out learning-by-doing training workshops to understand and reconcile weaknesses and gaps in key environmental policies and legal instruments |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.2.2 | Formulate appropriate by-laws and operational guidance to mainstream Rio Conventions. |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.2.3 | Secure approval of by-laws and any other amended policy, legislative, or regulatory texts |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.2.4 | Distribute updated codes, laws and relevant texts pertaining to Rio Convention implementation. |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 2.3 | Strengthened consultative and decision-making processes for mainstreaming of Rio Convention obligations. |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.3.1 | Convene working group meetings to negotiate best consultative and decision-making processes. |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.3.2 | Draft the memoranda of agreement on consultative and decision-making processes |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 2.4 | Targeted updating and streamlining of institutional mandates to facilitate and catalyze long-term action to meet global environmental obligations |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.4.1 | Reconcile and harmonize the various mandates and operational plans of the relevant national commissions, local and regional authorities, and other key institutions to integrate Rio Convention obligations. |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 2.5 | Enhanced monitoring and compliance arrangements, e.g., environmental impact and strategic environmental assessments |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.5.1 | Assess current data collection and generation methods of key agencies with attention to harmonization and metrics, relevance, validity, and quality. |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.5.2 | Recommend improved monitoring and compliance reforms based on learning-by-doing exercises to formulate best practices and guidelines. Draft and validate guidelines for coordinated monitoring and compliance. Develop quality control/validation procedures and identify responsible scientific and institutional correspondents. |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 2.6 | Demonstration and piloting of integrated environmental-development best practices that reflect global environmental priorities and the Post-2015 Sustainable Development Goals. |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.6.1 | Structure technical working groups for each of the three Rio Conventions on legislative responses and amendments. |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.6.2 | Identify and select the environmental-development best practices that are to be piloted through the use of the EKMS for a high value sectoral development plan |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.6.3 | Undertake an assessment of lessons learned and best practices through the early implementation and piloting of the EKMS for Rio Convention mainstreaming. |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 2.7 | Resource mobilization strategy |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.7.1 | Undertake a financial and economic analysis of monitoring, enforcement, and compliance of Rio Convention implementation |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.7.2 | Undertake a series of learning-by-doing workshops to draft a resource mobilization strategy. |  |  |  |  |  |  |  |  |  |  |  |  |
| Component 3 | Improving awareness of global environmental values and knowledge management |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 3:1 | Stakeholder dialogues on the value of Rio Conventions |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.1.1 | Organize and convene a one-day Kick-Off Conference and a one-day Project Results Conference |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.1.2 | Develop and validate public awareness and communication campaign plan. |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.1.3 | Convene three (3) public policy dialogues |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.1.4 | Convene national and sub-national awareness workshops |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.1.5 | Convene private sector sensitization panel discussions on the global environmental issues |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.1.6 | Convene workshops targeted to media professionals to improve environmental reporting |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 3.2 | Brochures and articles on the Rio Conventions |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.2.1 | Prepare and publish articles on linkages between the global environment and socio-economic issues |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 3.3 | Public service announcement(s) on globally sensitive and environmentally friendly behavior |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.3.1 | Prepare and air a public service announcement on Rio Convention mainstreaming |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 3.4 | Improved environmental educational curricula and youth civic engagement |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.4.1 | Develop and apply an awareness module for institutions on Rio Conventions mainstreaming and monitoring |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.4.2 | Prepare and integrate an environmental awareness module into school curricula |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 3.5 | Internet visibility of integrated approaches to meet Rio Convention obligations and national sustainable development priorities. |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.5.1 | Convene working group meetings among key agencies that have websites relevant to environmental governance and negotiate opportunities to improve the design and content of their respective webpages. |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.5.2 | Create a Facebook page on environmental information and Rio Convention mainstreaming. Upload relevant content at least twice per week. |  |  |  |  |  |  |  |  |  |  |  |  |
| Component 4 | NCSA is updated to reflect post 2015-SDGs and current opportunities to strengthen priority foundational capacities for the global environment |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 4:1 | Updated assessments of capacity challenges to meet and sustain Rio Convention obligations, building upon GEF focal area enabling activities |  |  |  |  |  |  |  |  |  |  |  |  |
| 4.1.1 | Prepare and validate the methodology to update the NCSA and integrate the post-2015 SDGs. |  |  |  |  |  |  |  |  |  |  |  |  |
| 4.1.2 | Design and carry out a survey to assess public awareness of the importance of the Rio Conventions to catalyzing sustainable development. |  |  |  |  |  |  |  |  |  |  |  |  |
| 4.1.3 | Conduct individual interviews to gather additional inputs on national priorities and constraints for improved and sustained environmental governance. |  |  |  |  |  |  |  |  |  |  |  |  |
| 4.1.4 | Draft thematic assessments of the challenges and opportunities to meet obligations under three Rio Conventions |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 4.2 | Integrated cross-cutting analysis of systemic, institutional, and individual capacity development priorities |  |  |  |  |  |  |  |  |  |  |  |  |
| 4.2.1 | Synthesize the findings and assessments of output 4.1 into a synthesis of the systemic, institutional, and individual capacity development challenges, priorities, and opportunities to meet and sustain Rio Convention obligations within the framework of national sustainable development priorities. |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 4.3 | Capacity Development Strategy and Action Plan, building on action plans of GEF focal area enabling activities |  |  |  |  |  |  |  |  |  |  |  |  |
| 4.3.1 | Review the action plans of GEF focal area enabling activities (such as the national strategies and actions plans under the three Rio Conventions) as well as other national sustainable development strategies. |  |  |  |  |  |  |  |  |  |  |  |  |
| 4.3.2 | Formulate a capacity development strategy and action plan. |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 4.4 | Update NCSA Final Report |  |  |  |  |  |  |  |  |  |  |  |  |
| 4.4.1 | Draft and validate the updated NCSA Final Report. |  |  |  |  |  |  |  |  |  |  |  |  |
| 4.4.2 | Convene a roundtable for donors to present the NCSA and Action Plan in order to leverage financial support from development partners |  |  |  |  |  |  |  |  |  |  |  |  |
| 4.4.3 | Finalize and present the NCSA Final Report and Action Plan at the Project Result Conference |  |  |  |  |  |  |  |  |  |  |  |  |
| Project Management |  |  |  |  |  |  |  |  |  |  |  |  |  |
| A | Project Administration |  |  |  |  |  |  |  |  |  |  |  |  |
| B | Independent Terminal Evaluation |  |  |  |  |  |  |  |  |  |  |  |  |
| C | Project Board Meetings |  |  |  |  |  |  |  |  |  |  |  |  |

| Provisional Work Plan |  | Year 4 |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Activity | Description | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 |
| Component 1 | Establishment of an integrated environmental knowledge management system (EKMS) to meet global environment and sustainable development priorities |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 1.1 | Institutional mapping and analysis of an optimal knowledge management system |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.1.1 | Undertake a SWOT and gap analysis of the institutional requirements to use best available and innovation data, information and knowledge |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.1.2 | Carry out an assessment of stakeholders' awareness and absorptive capacities to manage and monitor environmental information relevant to the Rio Conventions |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.1.3 | Organize and convene MEA technical committee meetings to discuss and recommend best practices for collecting and managing environmental data, information, and knowledge |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 1.2 | Design of an integrated environmental knowledge management system |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.2.1 | Convene stakeholder workshops on the management of information and knowledge for planning and policy-making |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.2.2 | Design the technological requirements for collecting, storing, and sharing data and information. |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.2.3 | Undertake an independent peer review of the EKMS feasibility study, finalize, and secure stakeholder validation and the required official approvals |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 1.3: | Targeted technological networking of existing information and knowledge management systems. |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.3.1 | Negotiate and facilitate the formulation and adoption of networking cooperative agreements on information and knowledge management with key institutions. |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.3.2 | Institute targeted management arrangements for sharing information. |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 1.4: | Selected updating of technologies to create cost-effective synergies for knowledge management. |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.4.1 | Procure and install the technological hardware and software of the EKMS as recommended in the approved feasibility study |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 1.5: | Integration of new and improved global environmental indicators into select sectoral development plan(s) |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.5.1 | Identify a set of best applicable indicators for measuring global environmental trends within the context of planning and policy-making in Liberia. |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.5.2 | Prepare technical guidance material for planners and other users of indicators relevant to the monitoring of the global environment. |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 1.6: | Learning-by-doing training on improved methodologies and analytical skills for interpreting global environmental trends and understanding their relevance to sectoral development |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.6.1 | Undertake a comprehensive assessment of training needs to manage data and information. |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.6.2 | Prepare a training programme and curriculum that builds on the earlier analyses. |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.6.3 | Carry out training workshops on the management of existing and new data and information through the EKMS. |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 1.7: | Early implementation and piloting of the integrated environmental knowledge management system through a select sectoral plan. |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.7.1 | Select one high value sectoral development plan for early implementation and piloting through a broad-based consultative process. |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.7.2 | Convene learning-by-doing workshops to use the EKMS to demonstrate its value at improving a more holistic and resilient construct of the selected sectoral plan in keeping with Rio Convention obligations. |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.7.3 | Facilitate dialogues on the EKMS and its implementation with decision- and policy-makers to enhance their understanding and secure their support and championship. |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.7.4 | Prepare lessons learned study on the use of the EKMS to mainstream Rio Convention obligations into sectoral plans and policies. |  |  |  |  |  |  |  |  |  |  |  |  |
| Component 2 | Enhanced institutional and technical capacities to mainstream, develop, and utilize policies and/or legislative frameworks for effective implementation of the three Rio Conventions |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 2.1 | In-depth SWOT and gap analysis of existing environmental policies and legislation, and the effectiveness of their enforcement |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.1.1 | Undertake an in-depth analysis of Liberia's policy, legislative, and regulatory framework on environmental governance |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.1.2 | Undertake a SWOT and gap analysis of sector policies to ascertain the extent to which they support or work against meeting and sustaining Rio Convention obligations. |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 2.2 | Strengthened policy and regulatory framework through improved operational interpretation, enforcement tools, and by-laws |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.2.1 | Carry out learning-by-doing training workshops to understand and reconcile weaknesses and gaps in key environmental policies and legal instruments |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.2.2 | Formulate appropriate by-laws and operational guidance to mainstream Rio Conventions. |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.2.3 | Secure approval of by-laws and any other amended policy, legislative, or regulatory texts |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.2.4 | Distribute updated codes, laws and relevant texts pertaining to Rio Convention implementation. |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 2.3 | Strengthened consultative and decision-making processes for mainstreaming of Rio Convention obligations. |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.3.1 | Convene working group meetings to negotiate best consultative and decision-making processes. |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.3.2 | Draft the memoranda of agreement on consultative and decision-making processes |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 2.4 | Targeted updating and streamlining of institutional mandates to facilitate and catalyze long-term action to meet global environmental obligations |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.4.1 | Reconcile and harmonize the various mandates and operational plans of the relevant national commissions, local and regional authorities, and other key institutions to integrate Rio Convention obligations. |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 2.5 | Enhanced monitoring and compliance arrangements, e.g., environmental impact and strategic environmental assessments |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.5.1 | Assess current data collection and generation methods of key agencies with attention to harmonization and metrics, relevance, validity, and quality. |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.5.2 | Recommend improved monitoring and compliance reforms based on learning-by-doing exercises to formulate best practices and guidelines. Draft and validate guidelines for coordinated monitoring and compliance. Develop quality control/validation procedures and identify responsible scientific and institutional correspondents. |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 2.6 | Demonstration and piloting of integrated environmental-development best practices that reflect global environmental priorities and the Post-2015 Sustainable Development Goals. |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.6.1 | Structure technical working groups for each of the three Rio Conventions on legislative responses and amendments. |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.6.2 | Identify and select the environmental-development best practices that are to be piloted through the use of the EKMS for a high value sectoral development plan |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.6.3 | Undertake an assessment of lessons learned and best practices through the early implementation and piloting of the EKMS for Rio Convention mainstreaming. |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 2.7 | Resource mobilization strategy |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.7.1 | Undertake a financial and economic analysis of monitoring, enforcement, and compliance of Rio Convention implementation |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.7.2 | Undertake a series of learning-by-doing workshops to draft a resource mobilization strategy. |  |  |  |  |  |  |  |  |  |  |  |  |
| Component 3 | Improving awareness of global environmental values and knowledge management |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 3:1 | Stakeholder dialogues on the value of Rio Conventions |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.1.1 | Organize and convene a one-day Kick-Off Conference and a one-day Project Results Conference |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.1.2 | Develop and validate public awareness and communication campaign plan. |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.1.3 | Convene three (3) public policy dialogues |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.1.4 | Convene national and sub-national awareness workshops |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.1.5 | Convene private sector sensitization panel discussions on the global environmental issues |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.1.6 | Convene workshops targeted to media professionals to improve environmental reporting |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 3.2 | Brochures and articles on the Rio Conventions |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.2.1 | Prepare and publish articles on linkages between the global environment and socio-economic issues |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 3.3 | Public service announcement(s) on globally sensitive and environmentally friendly behavior |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.3.1 | Prepare and air a public service announcement on Rio Convention mainstreaming |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 3.4 | Improved environmental educational curricula and youth civic engagement |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.4.1 | Develop and apply an awareness module for institutions on Rio Conventions mainstreaming and monitoring |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.4.2 | Prepare and integrate an environmental awareness module into school curricula |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 3.5 | Internet visibility of integrated approaches to meet Rio Convention obligations and national sustainable development priorities. |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.5.1 | Convene working group meetings among key agencies that have websites relevant to environmental governance and negotiate opportunities to improve the design and content of their respective webpages. |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.5.2 | Create a Facebook page on environmental information and Rio Convention mainstreaming. Upload relevant content at least twice per week. |  |  |  |  |  |  |  |  |  |  |  |  |
| Component 4 | NCSA is updated to reflect post 2015-SDGs and current opportunities to strengthen priority foundational capacities for the global environment |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 4:1 | Updated assessments of capacity challenges to meet and sustain Rio Convention obligations, building upon GEF focal area enabling activities |  |  |  |  |  |  |  |  |  |  |  |  |
| 4.1.1 | Prepare and validate the methodology to update the NCSA and integrate the post-2015 SDGs. |  |  |  |  |  |  |  |  |  |  |  |  |
| 4.1.2 | Design and carry out a survey to assess public awareness of the importance of the Rio Conventions to catalyzing sustainable development. |  |  |  |  |  |  |  |  |  |  |  |  |
| 4.1.3 | Conduct individual interviews to gather additional inputs on national priorities and constraints for improved and sustained environmental governance. |  |  |  |  |  |  |  |  |  |  |  |  |
| 4.1.4 | Draft thematic assessments of the challenges and opportunities to meet obligations under three Rio Conventions |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 4.2 | Integrated cross-cutting analysis of systemic, institutional, and individual capacity development priorities |  |  |  |  |  |  |  |  |  |  |  |  |
| 4.2.1 | Synthesize the findings and assessments of output 4.1 into a synthesis of the systemic, institutional, and individual capacity development challenges, priorities, and opportunities to meet and sustain Rio Convention obligations within the framework of national sustainable development priorities. |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 4.3 | Capacity Development Strategy and Action Plan, building on action plans of GEF focal area enabling activities |  |  |  |  |  |  |  |  |  |  |  |  |
| 4.3.1 | Review the action plans of GEF focal area enabling activities (such as the national strategies and actions plans under the three Rio Conventions) as well as other national sustainable development strategies. |  |  |  |  |  |  |  |  |  |  |  |  |
| 4.3.2 | Formulate a capacity development strategy and action plan. |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 4.4 | Update NCSA Final Report |  |  |  |  |  |  |  |  |  |  |  |  |
| 4.4.1 | Draft and validate the updated NCSA Final Report. |  |  |  |  |  |  |  |  |  |  |  |  |
| 4.4.2 | Convene a roundtable for donors to present the NCSA and Action Plan in order to leverage financial support from development partners |  |  |  |  |  |  |  |  |  |  |  |  |
| 4.4.3 | Finalize and present the NCSA Final Report and Action Plan at the Project Result Conference |  |  |  |  |  |  |  |  |  |  |  |  |
| Project Management |  |  |  |  |  |  |  |  |  |  |  |  |  |
| A | Project Administration |  |  |  |  |  |  |  |  |  |  |  |  |
| B | Independent Terminal Evaluation |  |  |  |  |  |  |  |  |  |  |  |  |
| C | Project Board Meetings |  |  |  |  |  |  |  |  |  |  |  |  |

## Annex 3:	Monitoring Plan

This plan provides the additional information of frequency and responsibility for data collection as an additional tool to monitor the project results framework (See Section F).

| Monitoring | Indicators | Description | Means of Verification/Data source | Frequency | Responsible for data collection | Assumptions and Risks |
| --- | --- | --- | --- | --- | --- | --- |
| Project Objective To strengthen a targeted set of national capacities to deliver and sustain global environmental outcomes within the framework of sustainable development priorities. | Indicator 1: Number of new partnership mechanisms with funding for sustainable management solutions of natural resources, ecosystem services, chemicals and waste at national and/or subnational level. | A high quality integrated Environmental Knowledge Management System is institutionalized | - Meeting Minutes - Working group and workshop reports and products - UNDP quarterly progress reports - Annual Project Implementation Reports - Independent final evaluation report - GEF Cross-Cutting Capacity Development Scorecard - RMS - EKMS - Training programme | Annually and at project end | - EPA - UNDP - PMU | - Internal resistance to change - The project will be executed in a transparent, holistic, adaptive, and collaborative manner - Government ministries and authorities maintain political commitment to the formulation and early implementation of the EKMS - Non-state stakeholder representatives, in particular project champions, remain active participants in the project - Policy and institutional reforms and modifications recommended by the project are politically, technically, and financially feasible |
|  | Indicator 2: Number of countries with legal, policy and institutional frameworks in place for conservation, sustainable use, and access and benefit sharing of natural resources, biodiversity and ecosystems | - One consultative and coordinating mechanism that catalyzes the mainstreaming of global environmental obligations within national development planning and policy formulation - At least one by-law or legal instrument has been developed or strengthened to catalyze compliance with standards to support the realization of Rio Convention obligations - At least one sectoral plan effectively integrated with criteria and indicators that reinforce Rio Convention obligations achievements. |  | Annually and at project end | - EPA - UNDP - PMU |  |
|  | Indicator 3: 500 direct project beneficiaries | - At least 500 stakeholders have benefitted from an integrated EKMS |  | Annually and at project end | - EPA - UNDP - PMU |  |
|  | Indicator 4: Sectoral plans and policies include targets that measure progress toward achieving global environmental obligations | - There is an increase in the appreciation of the Rio Conventions among the general public - Rio Convention obligations are being better implemented through an integrated system of data and information management - Increased capacity within relevant stakeholder groups to handle data and information relevant to the Rio Convention - There is an increase in coordination between government groups and other stakeholders |  | Annually and at project end | - EPA - UNDP - PMU |  |
| Component 1 Establishment of an integrated environmental knowledge management system (EKMS) to meet global environment and sustainable development priorities | Indicator 5: All stakeholders agree by consensus on a key set of higher-order indicators to monitor the progress the country is making towards meeting and sustaining Rio Convention obligations. Indicator 6: A data protocol system is developed and tested that allows data, information, and knowledge to be tracked through the life cycle of their creation to informing policy and plans to the latter’s adaptive management. Indicator 7: Key existing databases, management information systems, and monitoring systems are strategically networked into an integrated system (the EKMS) Indicator 8: A pilot project to test the application of the EKMS is carried out on a high value sector development plan at the local self-governing authority. Indicator 9: A long-term training programme is developed and institutionalized on Rio Convention mainstreaming based on lessons learned from the project’s learning-by-doing workshops and related exercises | - Institutional mapping and analysis of an optimal knowledge management system - Integrated environmental knowledge management system designed and reviewed - Existing information and knowledge management systems networked - Technologies to create cost-effective synergies updated - Global environmental indicators are integrated into select sectoral development plan(s) - Learning-by-doing training on improved methodologies and analytical skills for interpreting global environmental trends and understanding their relevance to sectoral development - Integrated environmental knowledge management system piloted | - Analysis of an optimal knowledge management system - EKMS - Operational procedures - Feasibility study - Pilot sector development plan - Meeting minutes - Indicators - Technology updates - Report with recommended revisions - Operational manual - Lessons learned report | Annually and at project end | - EPA - UNDP - PMU | - Design and assessment is deemed legitimate, relevant, and valid among all key stakeholder representatives and project champions - Expert peer reviewers follow through with quality reviews - EKMS is politically, technically, and financially feasible |
| Component 2 Enhanced institutional and technical capacities to mainstream, develop, and utilize policies and/or legislative frameworks for effective implementation of the three Rio Conventions | Indicator 10: Operational by-laws are developed to improve and legitimize Rio Convention mainstreaming into sector development plans. Indicator 11: A resource mobilization strategy for the long-term operation (e.g., 15 years) of the EKMS is developed and approved by the Government Apparatus Indicator 12: Memoranda of agreement must be negotiated and signed among government and non-state stakeholders on the sharing of data and information. Indicator 13: Liaison protocols between key government agencies must be updated and signed to strengthen sharing of data and information and proactive collaboration in the operation of the integrated EKMS. Indicator 14: The project facilitates broad-based stakeholder workshops to negotiate and institutionalize best practice consultative and decision-making processes to access best available data, information and knowledge. | - SWOT and gap analysis - Operational interpretation, enforcement tools, and by-laws created and distributed Strengthened consultative and decision-making processes - Monitoring and compliance arrangements enhanced - Environmental-development best practices demonstrated and piloted - Resource mobilization strategy | - SWOT and gap analysis - Resource mobilization strategy - By-laws - Memoranda of agreement - Working group meeting minutes - Updated mandates and operational plans | Annually and at project end | - EPA - UNDP - PMU | - Strategy developed by the project is politically, technically, and financially feasible - Institutional reforms and modifications recommended by the project and the EKMS are politically, technically, and financially feasible and approved by the Project Steering Committee - Institutions and working groups are open to change |
| Component 3 Improving awareness of global environmental values and knowledge management | Indicator 15: Education module on the importance of the global environment to national sustainable development is adopted and integrated within teaching curricula at the secondary school level Indicator 16: Collectively and over the three years of project implementation, the awareness-raising workshops engage over 700 unique stakeholders Indicator 17: A government-based website is created to network existing sources of electronic data and information | - Public Service Announcement (PSA) - Environmental awareness module prepared - Project Launch and Results Conference - Private sector and media sensitization panel discussions held - Articles on linkages between the global environment and socio-economic issues | - Panel discussion minutes - Meeting minutes - Awareness and sensitization workshop reports - Training programme, curricula, materials and training modules - Attendance list - PSA - Brochures and articles - Facebook page | Annually and at project end | - EPA - UNDP - PMU | - Public dialogues attract people that are new to the concept of Rio Convention mainstreaming, as well as detractors, with the assumption that dialogues will help change attitudes in a positive way - The right representation from the various government ministries, departments, and agencies participate in project activities - There is sufficient commitment from policy-makers to maintain long-term support to public awareness raising activities - Development partners implementing parallel public awareness campaigns are willing to modify, as appropriate, their activities to supporting the awareness activities of the present project to create synergies and achieve cost-effectiveness - Articles published in the popular media will be read and not skipped over - Brochures will be read and the content absorbed |
| Component 4 NCSA is updated to reflect post 2015-SDGs and current opportunities to strengthen priority foundational capacities for the global environment | Indicator 18: NCSA Final Report and Capacity Development Action Plan is completed | - Assessments of capacity challenges - Cross-cutting analysis completed - Capacity Development Strategy and Action Plan, developed - NCSA Final Report | - Working Group and workshop reports and products - Survey results - Interviews - Thematic assessments - Cross-cutting analysis report - Meeting minutes - Draft Action Plan - NCSA Final Report and Action Plan | Annually and at project end | - EPA - UNDP - PMU | - Survey respondents contribute their honest attitudes and values - The right representation from the various government ministries, departments, and agencies participate in project activities - Assessments are deemed legitimate, relevant, and valid among all key stakeholder representatives and project champions - Best practices and lessons learned from other countries are appropriately used - Expert peer reviewers follow through with quality reviews - Action Plan politically, technically, and financially feasible - Final Report is deemed legitimate, relevant, and valid among all key stakeholder representatives and project champions - The approval process is transparent and deemed valid by all stakeholders |

## Annex 4:	UNDP Social and Environmental and Social Screening Template (SESP)

| Project Information |  |
| --- | --- |
| Project Title | Strengthening national capacities to meet global environmental obligations with the framework of sustainable development priorities |
| Project Number | 5796 |
| Location (Global/Region/Country) | Liberia |

Part A.  Integrating Overarching Principles to Strengthen Social and Environmental Sustainability

QUESTION 1: How does the project integrate the overarching principles in order to strengthen social and environmental sustainability?

Briefly describe in the space below how the project mainstreams the human-rights based approach

The project mainstreams the human-rights based approach through significant participation and engagement of all stakeholders beginning with project design, and including implementation, monitoring and adaptive collaborative management of the project. Stakeholders will be invited to participate in capacity development activities and the project will cultivate an enabling environment for active stakeholder engagement in natural resource management. As part of the project formulation phase, consultations were held with a broad group of stakeholders to build an understanding of the challenges and barriers to strong environmental policy, compliance, data and information management, and more effective decision-making for the global environment, (i.e., the baseline of the project). One assumption of the project strategy is that these in-depth consultations will enhance the transparency and legitimacy of the proposed activities. Furthermore, component3, which focuses on improving awareness of global environmental values and knowledge management, allows for a multi-dimensional approach that includes stakeholder engagement and awareness programs with the private sector, the media, civil society, academia and local organizations.

Briefly describe in the space below how the Project is likely to improve gender equality and women’s empowerment

The project design has taken into account gender equality concerns, and as a result, the monitoring of key indicators, such as the gender balance in capacity development activities and the extent to which gender issues shape workshop deliberations and recommendations, are included in the project. The project will promote gender parity, including the promotion of gender equality in environmental management, and the empowerment and participation of women in environmental management.

Briefly describe in the space below how the Project mainstreams environmental sustainability

This project directly responds to the GEF-funded 2006 National Capacity Self-Assessment (NCSA). Additionally, the project responds to national priorities, policies, and strategies such as the 2013-2017 UNDAF, the National Action Plan for Climate Change Adaptation, the NBSAP II, the medium-term Poverty Reduction Strategy II (2012-2018), and Liberia RISING 2030. This project is also aligned with the post-2015 Sustainable Development Goals. - The expected outcomes of the project from a GEF perspective are improved capacities to meet and sustain global environmental priorities, the expected outcomes from a national socio-economic development perspective are improved capacities to plan and make decisions that will meet and sustain sustainable development priorities. This will be achieved by mainstreaming global environment into planning and decision-making process (i.e., integrating environmental-development best practices that reflect global environmental priorities and the Post-2015 Sustainable Development Goals into planning). The Rio Conventions will serve as analytical frameworks for identifying global environmental criteria and indicators and will be linked to sustainable development objectives and other indicators. Through learning-by-doing training, a national sustainable development strategy which fully integrates Rio Convention obligations, an Environmental Knowledge Management System, and improved institutional structures and mechanisms for mainstreaming and enforcing Rio Conventions, environmental sustainability will be mainstreamed.

Part B.  Identifying and Managing Social and Environmental Risks

| QUESTION 3: What is the level of significance of the potential social and environmental risks? Note: Respond to Questions 4 and 5 below before proceeding to Question 6 |  |  |  | QUESTION 6: What social and environmental assessment and management measures have been conducted and/or are required to address potential risks (for Risks with Moderate and High Significance)? |  |
| --- | --- | --- | --- | --- | --- |
| Impact and Probability (1-5) | Significance (Low, Moderate, High) | Comments |  | Description of assessment and management measures as reflected in the Project design. If ESIA or SESA is required note that the assessment should consider all potential impacts and risks. |  |
| QUESTION 4: What is the overall Project risk categorization? |  |  |  |  |  |
| Select one (see SESP for guidance) |  |  |  |  | Comments |
| Low Risk |  |  | √ |  | Two risks have been identified: 1) a risk that duty-bearers do not have the capacity to meet their obligations in the Project, and 2) a risk that there will be indigenous peoples present in the Project area. These risks are minimal and will be mitigated by the project design of inclusion, engagement, and appropriate grievance mechanisms. |
| Moderate Risk |  |  | ☐ |  |  |
| High Risk |  |  | ☐ |  |  |
| QUESTION 5: Based on the identified risks and risk categorization, what requirements of the SES are relevant? |  |  |  |  |  |
| Check all that apply |  |  |  |  | Comments |
| Principle 1: Human Rights |  |  | ☐ |  | None required |
| Principle 2: Gender Equality and Women’s Empowerment |  |  | ☐ |  | None required |
| 1. Biodiversity Conservation and Natural Resource Management |  |  | ☐ |  | None required |
| 2. Climate Change Mitigation and Adaptation |  |  | ☐ |  | None required |
| 3. Community Health, Safety and Working Conditions |  |  | ☐ |  | None required |
| 4. Cultural Heritage |  |  | ☐ |  | None required |
| 5. Displacement and Resettlement |  |  | ☐ |  | None required |
| 6. Indigenous Peoples |  |  | ☐ |  | None required |
| 7. Pollution Prevention and Resource Efficiency |  |  | ☐ |  | None required |

Final Sign off

| Signature | Date | Description |
| --- | --- | --- |
| QA Assessor Moses Massah Programme Specialist & Environment Focal Point UNDP Liberia | 20 April 2017 | UNDP staff member responsible for the Project, typically a UNDP Programme officer. Final signature confirms they have “checked” to ensure that the SESP is adequately conducted. |
| QA Approver |  | UNDP senior manager, typically the UNDP Deputy Country Director (DCD), Country Director (CD), Deputy Resident Representative (DRR), or Resident Representative (RR). The QA Approver cannot also be the QA Assessor. Final signature confirms they have “cleared” the SESP prior to submittal to the PAC. |
| PAC Chair |  | UNDP chair of the PAC. In some cases PAC Chair may also be the QA Approver. Final signature confirms that the SESP was considered as part of the project appraisal and considered in recommendations of the PAC. |

SESP Attachment 1:  Social and Environmental Risk Screening Checklist

| Checklist Potential Social and Environmental Risks |  |
| --- | --- |
| Principles 1: Human Rights | Answer (Yes/No) |
| 1. Could the Project lead to adverse impacts on enjoyment of the human rights (civil, political, economic, social or cultural) of the affected population and particularly of marginalized groups? | No |
| 2. Is there likelihood that the Project would have inequitable or discriminatory adverse impacts on affected populations, particularly people living in poverty or marginalized or excluded individuals or groups? | No |
| 3. Could the Project potentially restrict availability, quality of and access to resources or basic services, in particular to marginalized individuals or groups? | No |
| 4. Is there likelihood that the Project would exclude any potentially affected stakeholders, in particular marginalized groups, from fully participating in decisions that may affect them? | No |
| 5. Are there measures or mechanisms in place to respond to local community grievances? | No |
| 6. Is there a risk that duty-bearers do not have the capacity to meet their obligations in the Project? | Yes |
| 7. Is there a risk that rights-holders do not have the capacity to claim their rights? | No |
| 8. Have local communities or individuals, given the opportunity, raised human rights concerns regarding the Project during the stakeholder engagement process? | No |
| 9. Is there a risk that the Project would exacerbate conflicts among and/or the risk of violence to project-affected communities and individuals? | No |
| Principle 2: Gender Equality and Women’s Empowerment |  |
| 1. Is there likelihood that the proposed Project would have adverse impacts on gender equality and/or the situation of women and girls? | No |
| 2. Would the Project potentially reproduce discriminations against women based on gender, especially regarding participation in design and implementation or access to opportunities and benefits? | No |
| 3. Have women’s groups/leaders raised gender equality concerns regarding the Project during the stakeholder engagement process and has this been included in the overall Project proposal and in the risk assessment? | No |
| 3. Would the Project potentially limit women’s ability to use, develop and protect natural resources, taking into account different roles and positions of women and men in accessing environmental goods and services? For example, activities that could lead to natural resources degradation or depletion in communities who depend on these resources for their livelihoods and well being | No |
| Principle 3: Environmental Sustainability: Screening questions regarding environmental risks are encompassed by the specific Standard-related questions below |  |
| Standard 1: Biodiversity Conservation and Sustainable Natural Resource Management |  |
| 1.1 Would the Project potentially cause adverse impacts to habitats (e.g., modified, natural, and critical habitats) and/or ecosystems and ecosystem services? For example, through habitat loss, conversion or degradation, fragmentation, hydrological changes | No |
| 1.2 Are any Project activities proposed within or adjacent to critical habitats and/or environmentally sensitive areas, including legally protected areas (e.g., nature reserve, national park), areas proposed for protection, or recognized as such by authoritative sources and/or indigenous peoples or local communities? | No |
| 1.3 Does the Project involve changes to the use of lands and resources that may have adverse impacts on habitats, ecosystems, and/or livelihoods? (Note: if restrictions and/or limitations of access to lands would apply, refer to Standard 5) | No |
| 1.4 Would Project activities pose risks to endangered species? | No |
| 1.5 Would the Project pose a risk of introducing invasive alien species? | No |
| 1.6 Does the Project involve harvesting of natural forests, plantation development, or reforestation? | No |
| 1.7 Does the Project involve the production and/or harvesting of fish populations or other aquatic species? | No |
| 1.8 Does the Project involve significant extraction, diversion or containment of surface or ground water? For example, construction of dams, reservoirs, river basin developments, groundwater extraction | No |
| 1.9 Does the Project involve utilization of genetic resources? (e.g., collection and/or harvesting, commercial development) | No |
| 1.10 Would the Project generate potential adverse transboundary or global environmental concerns? | No |
| 1.11 Would the Project result in secondary or consequential development activities which could lead to adverse social and environmental effects, or would it generate cumulative impacts with other known existing or planned activities in the area? For example, a new road through forested lands will generate direct environmental and social impacts (e.g., felling of trees, earthworks, potential relocation of inhabitants). The new road may also facilitate encroachment on lands by illegal settlers or generate unplanned commercial development along the route, potentially in sensitive areas. These are indirect, secondary, or induced impacts that need to be considered. Also, if similar developments in the same forested area are planned, then cumulative impacts of multiple activities (even if not part of the same Project) need to be considered. | No |
| Standard 2: Climate Change Mitigation and Adaptation |  |
| 2.1 Will the proposed Project result in significant greenhouse gas emissions or may exacerbate climate change? | No |
| 2.2 Would the potential outcomes of the Project be sensitive or vulnerable to potential impacts of climate change? | No |
| 2.3 Is the proposed Project likely to directly or indirectly increase social and environmental vulnerability to climate change now or in the future (also known as maladaptive practices)? For example, changes to land use planning may encourage further development of floodplains, potentially increasing the population’s vulnerability to climate change, specifically flooding | No |
| Standard 3: Community Health, Safety and Working Conditions |  |
| 3.1 Would elements of Project construction, operation, or decommissioning pose potential safety risks to local communities? | No |
| 3.2 Would the Project pose potential risks to community health and safety due to the transport, storage, and use and/or disposal of hazardous or dangerous materials (e.g., explosives, fuel and other chemicals during construction and operation)? | No |
| 3.3 Does the Project involve large-scale infrastructure development (e.g., dams, roads, buildings)? | No |
| 3.4 Would failure of structural elements of the Project pose risks to communities? (e.g., collapse of buildings or infrastructure) | No |
| 3.5 Would the proposed Project be susceptible to or lead to increased vulnerability to earthquakes, subsidence, landslides, and erosion, flooding or extreme climatic conditions? | No |
| 3.6 Would the Project result in potential increased health risks (e.g., from water-borne or other vector-borne diseases or communicable infections such as HIV/AIDS)? | No |
| 3.7 Does the Project pose potential risks and vulnerabilities related to occupational health and safety due to physical, chemical, biological, and radiological hazards during Project construction, operation, or decommissioning? | No |
| 3.8 Does the Project involve support for employment or livelihoods that may fail to comply with national and international labor standards (i.e. principles and standards of ILO fundamental conventions)? | No |
| 3.9 Does the Project engage security personnel that may pose a potential risk to health and safety of communities and/or individuals (e.g., due to a lack of adequate training or accountability)? | No |
| Standard 4: Cultural Heritage |  |
| 4.1 Will the proposed Project result in interventions that would potentially adversely impact sites, structures, or objects with historical, cultural, artistic, traditional or religious values or intangible forms of culture (e.g., knowledge, innovations, practices)? (Note: Projects intended to protect and conserve Cultural Heritage may also have inadvertent adverse impacts) | No |
| 4.2 Does the Project propose utilizing tangible and/or intangible forms of cultural heritage for commercial or other purposes? | No |
| Standard 5: Displacement and Resettlement |  |
| 5.1 Would the Project potentially involve temporary or permanent and full or partial physical displacement? | No |
| 5.2 Would the Project possibly result in economic displacement (e.g., loss of assets or access to resources due to land acquisition or access restrictions – even in the absence of physical relocation)? | No |
| 5.3 Is there a risk that the Project would lead to forced evictions? | No |
| 5.4 Would the proposed Project possibly affect land tenure arrangements and/or community based property rights/customary rights to land, territories and/or resources? | No |
| Standard 6: Indigenous Peoples |  |
| 6.1 Are indigenous peoples present in the Project area (including Project area of influence)? | Yes |
| 6.2 Is it likely that the Project or portions of the Project will be located on lands and territories claimed by indigenous peoples? | No |
| 6.3 Would the proposed Project potentially affect the rights, lands and territories of indigenous peoples (regardless of whether Indigenous Peoples possess the legal titles to such areas)? | No |
| 6.4 Has there been an absence of culturally appropriate consultations carried out with the objective of achieving FPIC on matters that may affect the rights and interests, lands, resources, territories and traditional livelihoods of the indigenous peoples concerned? | No |
| 6.5 Does the proposed Project involve the utilization and/or commercial development of natural resources on lands and territories claimed by indigenous peoples? | No |
| 6.6 Is there a potential for forced eviction or the whole or partial physical or economic displacement of indigenous peoples, including through access restrictions to lands, territories, and resources? | No |
| 6.7 Would the Project adversely affect the development priorities of indigenous peoples as defined by them? | No |
| 6.8 Would the Project potentially affect the traditional livelihoods, physical and cultural survival of indigenous peoples? | No |
| 6.9 Would the Project potentially affect the Cultural Heritage of indigenous peoples, including through the commercialization or use of their traditional knowledge and practices? | No |
| Standard 7: Pollution Prevention and Resource Efficiency |  |
| 7.1 Would the Project potentially result in the release of pollutants to the environment due to routine or non-routine circumstances with the potential for adverse local, regional, and/or transboundary impacts? | No |
| 7.2 Would the proposed Project potentially result in the generation of waste (both hazardous and non-hazardous)? | No |
| 7.3 Will the proposed Project potentially involve the manufacture, trade, release, and/or use of hazardous chemicals and/or materials? Does the Project propose use of chemicals or materials subject to international bans or phase-outs? For example, DDT, PCBs and other chemicals listed in international conventions such as the Stockholm Conventions on Persistent Organic Pollutants or the Montreal Protocol | No |
| 7.4 Will the proposed Project involve the application of pesticides that may have a negative effect on the environment or human health? | No |
| 7.5 Does the Project include activities that require significant consumption of raw materials, energy, and/or water? | No |

## Annex 5:	UNDP Project Quality Assurance Report

| Project Monitoring QA Assessment Guidance |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Overall Project |  |  |  |  |  |  |  |
| Exemplary (5) |  | High (4) | Satisfactory (3) | Needs Improvement (2) | Inadequate (1) |  |  |
| At least three criteria are rated Exemplary, and all criteria are rated High or Exemplary. |  | All criteria are rated Satisfactory or higher, and at least three criteria are rated High or Exemplary. | At least six criteria are rated Satisfactory or higher, and only one may be rated Needs Improvement. The SES criterion must be rated Satisfactory or above. | At least three criteria are rated Satisfactory or higher, and only four criteria may be rated Needs Improvement. | One or more criteria are rated Inadequate, or five or more criteria are rated Needs Improvement. |  |  |
| DECISION |  |  |  |  |  |  |  |
| - APPROVE – the project is of sufficient quality to continue as planned. Any management actions must be addressed in a timely manner. - APPROVE WITH QUALIFICATIONS – the project has issues that must be addressed before the project document can be approved. Any management actions must be addressed in a timely manner. - DISAPPROVE – the project has significant issues that should prevent the project from being approved as drafted. |  |  |  |  |  |  |  |
| RATING CRITERIA |  |  |  |  |  |  |  |
| Strategic |  |  |  |  |  |  |  |
| - Does the project’s Theory of Change specify how it will contribute to higher level change? (Select the option from 0-4 that best reflects the project): - 4: The project has a theory of change backed by credible evidence specifying how the project will contribute to higher level change through the programme outcome’s theory of change. The project document clearly describes why the project’s strategy is the best approach at this point in time. - 3: The project has a theory of change, specifying how the project will contribute to higher level change through the programme outcome’s theory of change, but this backed by relatively limited evidence. The project document clearly describes why the project’s strategy is the best approach at this point in time. - 2: The project has a theory of change describing how the project intends to contribute to development results, but it is not supported by evidence nor linked to higher level results through the programme outcome’s theory of change. There is some discussion in the project document that describes why the project’s strategy is the best approach at this point in time. - 1: The project does not have a theory of change, but the project document describes in generic terms how the project will contribute to development results. It does not make an explicit link to the programme outcome’s theory of change. The project document does not clearly specify why the project’s strategy is the best approach at this point in time. - 0: The project does not have a theory of change, and the project document does not specify how the project will contribute to higher level change, or why the project’s strategy is the best approach at this point in time. *Note: Management Action or strong management justification must be given for scores of 0 or 1 |  |  |  |  |  | Rating Score |  |
|  |  |  |  |  |  | 3 |  |
| Evidence The project strategy (extensive learning-by-doing, pilot exercise, adaptive collaborative management approach to implementation, and targeted institutional reforms to name a few) will facilitate larger scale and long-term changes. See B.3 Theory of Change. The project aims to remove the barriers identified in the 2006 NCSA so that Liberia can make more informed decisions and implement resilient, environmentally-friendly and sustainable development plans. This project is a continuation of a process of capacity building initiatives undertaken in Liberia with the support of other development partners. |  |  |  |  |  |  |  |
| - Is the project is aligned with the UNDP Strategic Plan? (select the option from 0-4 that best reflects the project): - 4: The project responds to one of the three areas of development work (1. Sustainable development pathways; 2. Inclusive and effective democratic governance; 3. Resilience building) as specified in the Strategic Plan; it addresses at least one of the proposed new and emerging areas (sustainable production technologies, access to modern energy services and energy efficiency, natural resources management, extractive industries, urbanization, citizen security, social protection, and risk management for resilience); an issues-based analysis has been incorporated into the project design; And the project’s RRF includes at least one SP output indicator. - 3: The project responds to one of the three areas of development work (1. Sustainable development pathways; 2. Inclusive and effective democratic governance; 3. Resilience building) as specified in the Strategic Plan; an issues-based analysis has been incorporated into the project design; and the project’s RRF includes at least one SP output indicator. - 2: The project responds to one of the three areas of development work (1. Sustainable development pathways; 2. Inclusive and effective democratic governance; 3. Resilience building) as specified in the Strategic Plan. The project’s RRF includes at least one SP output indicator, if relevant. - 1: While the project responds to one of the three areas of development work (1. Sustainable development pathways; 2. Inclusive and effective democratic governance; 3. Resilience building) as specified in the Strategic Plan, none of the relevant SP indicators are included in the RRF. - 0: The project does not respond to one of the three areas of development work (1. Sustainable development pathways; 2. Inclusive and effective democratic governance; 3. Resilience building) as specified in the Strategic Plan |  |  |  |  |  | Rating Score |  |
|  |  |  |  |  |  | 4 |  |
| Evidence This project responds to all three areas of development work per the UNDP Strategic Plan. The evidence for this is through the various project activities that will integrate global environmental criteria and indicators in national sustainable development planning frameworks. The project also the proposed new and emerging area of natural resources management. The project’s results framework includes at least one Strategic Plan output indicator. |  |  |  |  |  |  |  |
| Relevant |  |  |  |  |  |  |  |
| - Does the project have strategies to effectively identify and engage targeted groups/areas? (select the option from 0-4 which best reflects this project): - 4: The target groups/areas are appropriately specified. The project has an explicit strategy to identify and engage specified target groups/areas throughout the project. Beneficiaries will be identified through a rigorous process based on evidence (if applicable.) The project plans to solicit feedback from targeted groups regularly through project monitoring. Representatives of the target group/area will be included in the project’s governance mechanism (i.e., project board.) - 3: The target groups/areas are appropriately specified. The project has an explicit strategy to identify and engage the target groups/areas throughout the project. Beneficiaries will be identified through a rigorous process based on evidence (if applicable.) The project plans to solicit feedback from targeted groups through project monitoring. Representatives of the target group, will contribute to the project’s decision making, but will not play a role in the project’s formal governance mechanism. - 2: The target groups/areas are appropriately specified and engaged in project design. The project document is clear how beneficiaries will be identified and engaged throughout the project. Collecting feedback from targeted groups has been incorporated into the project’s RRF/monitoring system, but representatives of the target group will not be involved in the project’s decision making. - 1: The target groups/areas are specified, but the project does not have a written strategy to identify or engage the target groups/areas throughout the project. - 0: The project has not specified any target group/area that is the intended beneficiary of the project’s results. *Note: Management Action must be taken for scores of 0 or 1 |  |  |  |  |  | Rating Score |  |
|  |  |  |  |  |  | 4 |  |
| Evidence Targeted groups are clearly identified in the project document. See Section D. The GEF CCCD Strategy emphasizes the requirement that stakeholder representatives actively engage in the full project life cycle in order to facilitate the strategic adaptation of project activities in keeping with project objectives. Periodic monitoring of implementation progress will be undertaken by the UNDP/CO. Additionally, specific meetings may be scheduled between the PMU, the UNDP/CO and other pertinent stakeholders as deemed appropriate. |  |  |  |  |  |  |  |
| - Have knowledge, good practices, and past lessons learned of UNDP and others informed the project design? (select the option from 0-4 which best reflects this project): - 4: Knowledge and lessons learned backed by credible evidence from evaluation, analysis and monitoring have been explicitly used, with appropriate referencing, to develop the project’s theory of change and justify the approach used by the project over alternatives. - 3: The project design references knowledge and lessons learned backed by credible evidence from evaluation, analysis, monitoring and/or other sources, but these references have not been explicitly used to develop the project’s theory of change or justify the approach used by the project over alternatives. - 2: The project design mentions knowledge and lessons learned backed by relatively limited evidence/sources, but these references have not been explicitly used to develop the project’s theory of change or justify the approach used by the project over alternatives. - 1: There is only scant mention of knowledge and lessons learned informing the project design. These references are not backed by evidence. - 0: There is no evidence that knowledge and lessons learned have informed the project design. *Note: Management Action or strong management justification must be given for scores of 0 or 1 |  |  |  |  |  | Rating Score |  |
|  |  |  |  |  |  | 4 |  |
| Evidence This project design is rooted in a credible assessment of needs (the NCSA) and it responds directly to identified barriers and recommendations. The use of best practices also informs several project activities such as the comprehensive assessment of technical training needs and the awareness raising material in component 3. Moreover, the project calls for stakeholders to discuss and agree on best practices for several other activities. |  |  |  |  |  |  |  |
| - Does the project use gender analysis in the project design and includes special measures/ outputs and indicators to address gender inequities and empower women? - 4: Gender analysis has been conducted on the differential impact of the project’s development situation on gender relations, women and men, with constraints identified and clearly addressed in the design of gender-specific measures/outputs and indicators, where appropriate - 3: Gender analysis has been conducted on the differential impact of the project’s development situation on gender relations, women and men, with constraints identified but only partially addressed in the design of gender-specific measures/outputs and indicators, where appropriate - 2: Partial gender analysis has been conducted on the differential impact of the project’s development situation on gender relations, women and men with constraints identified, but these have not been explicitly addressed in the design of gender-specific measure/outputs and indicators. - 1: The project design mentions information and/or data on the differential impact of the project’s development situation on gender relations, women and men but the constraints have not been identified and gender-specific intervention has not been considered. - 0: No gender analysis has been conducted on the differential impact of the project’s development situation on gender relations, women and men. |  |  |  |  |  | Rating Score |  |
|  |  |  |  |  |  | 2 |  |
| Evidence A partial gender analysis has been conducted and is included in the project document. The results framework has specific indicators to address the identified gender issues, while others are expected to be identified and monitored during project implementation. See section D.3. |  |  |  |  |  |  |  |
| - Does UNDP have a clear advantage to engage in the role envisioned by the project vis-à-vis national partners, other development partners, and other actors? (select from options 0-4 that best reflects this project): - 4: An analysis has been conducted on the role of other partners in the area that the project intends to work, and credible evidence supports the proposed engagement of UNDP and partners through the project. Options for south-south and triangular cooperation have been considered, as appropriate. - 3: An analysis has been conducted on the role of other partners in the area that the project intends to work, and relatively limited evidence supports the proposed engagement of UNDP and partners through the project. Options for south-south and triangular cooperation have been considered, as appropriate. - 2: Some analysis has been conducted on the role of other partners in the area that the project intends to work, and relatively limited evidence supports the proposed engagement of UNDP and partners through the project. Options for south-south and triangular cooperation have not been explicitly considered. - 1: No clear analysis has been conducted on the role of other partners in the area that the project intends to work, and relatively limited evidence supports the proposed engagement of UNDP and partners through the project. Options for south-south and triangular cooperation have not been considered. - 0: No analysis has been conducted on the role of other partners in the area that the project intends to work to inform the design of the role envisioned by UNDP and other partners through the project. *Note: Management Action or strong management justification must be given for scores of 0 or 1 |  |  |  |  |  | Rating Score |  |
|  |  |  |  |  |  | 4 |  |
| Evidence UNDP’s mandate, relationship with government and long-standing engagement in the area gives it a comparative advantage in facilitating government partnerships. The project has considered options for south-south and triangular cooperation. See Section D.4. |  |  |  |  |  |  |  |
| Management & Monitoring |  |  |  |  |  |  |  |
| - Does the project have a strong results framework? (select from options 0-4 that best reflects this project): - 4: The project’s selection of outputs and activities are an appropriate level and relate in a clear way to the project’s theory of change. Outputs are accompanied by SMART, results-oriented indicators that measure all of the key expected changes identified in the theory of change, each with credible data sources, and populated baselines and targets, including gender sensitive, sex-disaggregated indicators where appropriate. - 3: The project’s selection of outputs and activities are an appropriate level and are consistent with the project’s theory of change. Outputs are accompanied by SMART, results-oriented indicators, with specified data sources. Most baselines and targets populated. Some use of gender sensitive, sex-disaggregated indicators. - 2: The project’s selection of outputs and activities are at an appropriate level, but do not reference the project’s theory of change. Outputs are accompanied by SMART, results-oriented indicators, but baselines, targets and data sources are not fully specified. Some use of gender sensitive, sex-disaggregated indicators. - 1: The project’s selection of outputs and activities are not at an appropriate level. Outputs are not accompanied by SMART, results-oriented indicators that measure the expected change, and have not been populated with baselines and targets. Data sources are not specified. No gender sensitive, sex-disaggregation of indicators is used. - 0: The project’s selection of outputs and activities are not accompanied by appropriate indicators that measure the expected change. *Note: Management Action or strong management justification must be given for scores of 0 or 1 |  |  |  |  |  | Rating Score |  |
|  |  |  |  |  |  | 3 |  |
| Evidence Project outcomes will be measured through a set of output, process, and performance indicators which have been constructed using SMART design criteria. These indicators were developed to correspond with major project activities/outputs. A few gender sensitive indicators are included in the results framework. |  |  |  |  |  |  |  |
| 8. Is there a comprehensive and costed M&E plan with specified data collection sources and methods to support evidence-based management and monitoring of the project? |  |  |  |  |  | Yes (2) | No (0) |
| 9. Is the project’s governance mechanism clearly defined in the project document, including planned composition of the project board? - 4: The project’s governance mechanism is fully defined in the project composition. Individuals have been specified for each position in the governance mechanism (esp. all members of the project board), and full terms of reference of the project board has been attached to the project document. A conversation has been held with each board member on their role and responsibilities, and all members agree on the terms of reference. - 3: The project’s governance mechanism is almost fully defined in the project document. Individuals have been specified for each position in the governance mechanism (esp. all members of the project board). While full terms of reference of the project board may not be attached, the project document describes the responsibilities of the project board, project director/manager and quality assurance roles. - 2: The project’s governance mechanism is partially defined in the project document; specific institutions are noted as holding key governance roles, but individuals have not yet been specified. The project document lists the most important responsibilities of the project board, project director/manager and quality assurance roles, but full terms of reference are not included. - 1: The project’s governance mechanism is loosely defined in the project document, only mentioning key roles that will need to be filled at a later date. No information on the responsibilities of key positions in the governance mechanism. - 0: The governance mechanism is not clearly defined in the project document *Note: Management Action or strong management justification must be given for scores of 0 or 1 |  |  |  |  |  | Rating Score |  |
|  |  |  |  |  |  | 3 |  |
| Evidence The governance mechanism is almost fully defined in the project document. See Section H. Terms of references for project structures, mechanisms and specialists assigned to implement the project are outlined in Annex 7. . |  |  |  |  |  |  |  |
| 10. Have the project risks been identified with clear plans stated to manage and mitigate each risk? (select from options 0-4 that best reflects this project): - 4: Project risks fully described in the project risk log, based on comprehensive analysis which references key assumptions made in the project’s theory of change. Clear and complete plan in place to manage and mitigate each risk. - 3: Project risks identified in the project risk log. Clear plan in place to manage and mitigate risks. - 2: Some risks identified in the initial project risk log. While some general mitigation measures have been identified, they do not adequately and fully address all the identified risks. - 1: Some risks identified in the initial project risk log, but no clear risk mitigation measures identified. - 0: Risks not clearly identified. No initial project risk log included with the project document. *Note: Management Action must be taken for scores of 0 or 1 |  |  |  |  |  | Rating Score |  |
|  |  |  |  |  |  | 4 |  |
| Evidence Risks and assumptions have been fully identified in the project. Measures to mitigate the risk have been consider and addressed in the project document. See section E.1. The risks were based on an in-depth assessment and an extensive set of consultations and review of the background documentation. |  |  |  |  |  |  |  |
| Efficient |  |  |  |  |  |  |  |
| 11. Have specific measures for ensuring cost-efficient use of resources been explicitly mentioned as part of the project design? This can include using the theory of change analysis to explore different options of achieving the maximum results with the resources available. |  |  |  |  |  | Yes (2) | No (0) |
| 12. Are plans in place to ensure the project links up with other relevant on-going projects and initiatives, whether led by UNDP, national or other partners, to achieve more efficient results (including, for example, through sharing resources or coordinating delivery?) |  |  |  |  |  | Yes (2) | No (0) |
| 13. Is the budget justified and supported with valid estimates? |  |  |  |  |  | Yes (2) | No (0) |
| 14. Is the Country Office fully recovering its costs involved with project implementation? |  |  |  |  |  | Yes (2) | No (0) |
| Effective |  |  |  |  |  |  |  |
| 15. Is the chosen implementation modality most appropriate? (select from options 0-4 that best reflects this project): - 4: The required implementing partner assessments (capacity assessment, HACT micro assessment) have been conducted, and there is evidence that options for implementation modalities have been thoroughly considered. There is a strong justification for choosing the selected modality, based on the development context. - 3: The required IP assessments (capacity assessment, HACT micro assessment) have been conducted, and there is evidence that options for implementation modalities have been considered. There is justification for choosing the selected modality, based on the development context. - 2: The capacity of the IP has been assessed, but the HACT micro assessment has not been done due to external factors outside of UNDP’s control. There is evidence that options for implementation modalities have been considered. There is justification for choosing the selected modality, based on the development context. - 1: The required assessments have not been conducted, but there is evidence that options for implementation modalities have been considered. - 0: The required assessments have not been conducted, and there is no evidence that options for implementation modalities have been considered. *Note: Management Action or strong management justification must be given for scores of 0 or 1 |  |  |  |  |  | Rating Score |  |
|  |  |  |  |  |  | N/A |  |
| Evidence This project will be executing through the National Implementation Modality (NIM) by UNDP Country Office (as the GEF Implementing Agency). The choice of modality is based on agreement between the Government of Liberia and UNDP. The HACT micro-assessment was completed in June 2016. |  |  |  |  |  |  |  |
| 16. Have targeted groups, including marginalized populations that will be affected by the project, been engaged in the design of the project? |  |  |  |  |  | Yes (2) | No (0) |
| 17. Does the project have explicit plans for evaluation or other lesson learning, timed to inform course corrections if needed during project implementation? |  |  |  |  |  | Yes (2) | No (0) |
| 18. The project budget at the output level reflects adequate financial investments contributing to the advancement of gender equality. This can include outputs that have adequately mainstreamed gender (GEN2), and/or outputs for gender specific or stand-alone intervention (GEN3). - 4: The project budget reflects outstanding financial investments contributing to gender equality as evidenced by 100% of the project budget at the output level with the gender marker score GEN2+GEN3. - 3: The project budget reflects adequate financial investments contributing to gender equality as evidenced by at least 75% of the project budget at the output level with the gender marker score GEN2+GEN3. - 2: The project budget reflects partial investments contributing to gender equality as evidenced by at least 50% of the project budget at the output level with the gender marker score GEN2+GEN3. - 1: The project budget reflects limited financial investments contributing to gender equality as evidenced by at least 25% of the project budget at the output level with the gender marker score GEN2+GEN3. - 0: The project budget reflects no financial investments contributing to gender equality *Note: Management Action or strong management justification must be given for scores of 0 or 1 |  |  |  |  |  | Rating Score |  |
|  |  |  |  |  |  | 0 |  |
| Evidence There is no budget allocation made to specifically address gender equality as gender inequality does not represent a barrier to meeting Rio Convention obligations. The GEF Instrument also clearly states the criteria for the use of GEF financial resources, and these must be directed to activities that deliver global environmental benefits as defined under the three Rio Conventions. Even if there is a desire and/or expectation that financial resources be directed to gender equality, not only must they must come from non-GEF financial resources, they can not benefit from an allocation of a GEF increment because gender inequality does not represent a barrier to delivering global environmental benefits under the project strategy, nor would it be appropriate to tack it on. |  |  |  |  |  |  |  |
| 19. Is there a realistic multi-year work plan and budget to ensure outputs are delivered on time and within allotted resources? (select from options 0-4 that best reflects this project): - 4: The project has a realistic multi-year work plan and multi- year budget at the activity level to ensure outputs are delivered on time and within the allotted resources. - 3: The project has a multi-year work plan at the activity level and multi-year budget at the output level. - 2: The project has a multi-year work plan and a multi-year budget at the output level. - 1: The project has an output level multi-year work plan, but not a multi-year budget - 0: The project does not yet have a multi-year work plan. |  |  |  |  |  | Rating Score |  |
|  |  |  |  |  |  | 3 |  |
| Evidence The project has a detailed multi-year work plan at the activity level, and a multi-year budget at the output level. See section I.5 and I.6 and Annex 2. |  |  |  |  |  |  |  |
| Social & Environmental Standards |  |  |  |  |  |  |  |
| 20. Has the project ensured that both women and men have equitable access to project resources and comparable social and environmental benefits? (select from options 0-4 that best reflects this project): - 4: Credible evidence that the project fully reflects a consistent strategy that provides equitable access to and control over project resources and social and environmental benefits (e.g., security, health, water, and culture) through project rationale, strategies and results framework. - 3: Credible evidence that the project partially reflects a strategy that provides equitable access to and control over project resources and social and environmental benefits (e.g., security, health, water, and culture) through project strategies and the results framework. - 2: Credible evidence that the project design includes a set of activities that provide equitable access to and control over project resources and social and environmental benefits (e.g., security, health, water, and culture) although project activities are not part of a consistent strategy. - 1: Credible evidence that the project design includes some scattered activities that provide equitable access to and control over project resources and social and environmental benefits (e.g., security, health, water, and culture) - 0: The project has no interventions to ensure a fair share of opportunities and benefits for women and men or reduce gender inequalities in access to and control over resources and social and environmental benefits (e.g., security, health, water, and culture) *Note: Management Action or strong management justification must be given for scores of 0 or 1 |  |  |  |  |  | Rating Score |  |
|  |  |  |  |  |  | 3 |  |
| Evidence Gender considerations have been taken into account in the formulation of the project. During implementation, every effort will be made to incorporate gender issues. Roles of men and women to participate in activities of the project will be equally assigned without any discrimination. The project also includes several validation measures and gender sensitive indicators to help ensure equal access and benefits. |  |  |  |  |  |  |  |
| 21. Did the project apply a human rights based approach? - 4: Credible evidence that opportunities to integrate human rights in the project and prioritize the principles of accountability, meaningful participation, and non-discrimination were fully considered. Any potential adverse impacts on enjoyment of human rights were rigorously assessed and identified with appropriate mitigation and management measures incorporated into project design and budget. - 3: Partial evidence that opportunities to integrate human rights in the project and the principles of accountability, meaningful participation, and non-discrimination were considered. Potential adverse impacts on enjoyment of human rights were assessed and identified and appropriate mitigation and management measures incorporated into the project design and budget. - 2: Limited evidence that opportunities to integrate human rights in the project and the principles of accountability, meaningful participation and non-discrimination were considered. Potential adverse impacts on enjoyment of human rights were assessed and identified and appropriate mitigation and management measures incorporated into the project design and budget. - 1: No evidence that opportunities to integrate human rights in the project and the principles of accountability, meaningful participation and non-discrimination were considered. Limited evidence that potential adverse impacts on enjoyment of human rights were considered. - 0: No evidence that opportunities to integrate human rights in the project were considered. No evidence that the potential adverse impact on the enjoyment of human rights have been considered. *Note: Management action or strong management justification must be given for scores of 0 or 1 |  |  |  |  |  | Rating Score |  |
|  |  |  |  |  |  | 4 |  |
| Evidence The project supports the meaningful participation and inclusion of all stakeholders, during the design, implementation, monitoring, and adaptive collaborative management of the project. Stakeholders will participate in capacity development activities and the project will support the development of an enabling environment conducive to the active engagement of stakeholders in the management of natural resources. During the project formulation phase, consultation sessions and meetings were undertaken with a diverse group of stakeholders in order to construct as holistic as possible an understanding of the challenges and barriers related to the management of data and information for improved decision-making on the global environment, i.e., the project baseline. The project design makes the assumption that the extensive consultations during project formulation strengthens the transparency and legitimacy of the proposed project activities, notwithstanding that during project implementation, activities can and should be adapted to ensure that the human rights of stakeholders are preserved and/or reinforced. The extensive stakeholder consultations, learning-by-doing workshops, and awareness-raising dialogues are intended to engage as many people as possible in order to reduce the risks of marginalizing stakeholders and incorporating their diverse perspectives in as many project activities as possible. |  |  |  |  |  |  |  |
| 22. Did the project consider potential environmental opportunities and adverse impacts, applying a precautionary approach? - 4: Credible evidence that opportunities to enhance environmental sustainability and integrate poverty-environment linkages were fully considered. Identified opportunities fully integrated in project strategy and design. Credible evidence that potential adverse environmental impacts identified and rigorously assessed with appropriate management and mitigation measures incorporated into project design and budget. - 3: Limited evidence that opportunities to enhance environmental sustainability and poverty-environment linkages were considered. Credible evidence that potential adverse environmental impacts identified and assessed and appropriate management and mitigation measures incorporated into project design and budget. - 2: No evidence that opportunities to strengthen environmental sustainability and poverty-environment linkages were considered. Credible evidence that potential adverse environmental impacts assessed and appropriate management and mitigation measures incorporated into project design and budget. - 1: No evidence that opportunities to strengthen environmental sustainability and poverty-environment linkages were considered. Limited evidence that potential adverse environmental impacts were adequately considered. - 0: No evidence that potential adverse environmental impacts have been considered. Note: Management action or strong management justification must be given for scores of 0 or 1 |  |  |  |  |  | Rating Score |  |
|  |  |  |  |  |  | 4 |  |
| Evidence This project is consistent with Liberia’s current United Nations Development Assistance Framework (UNDAF) 2013-2017, and relates to national initiatives to achieve sustainable management of energy, environment and natural resources. This project will carry out workshops that learn new tools and methodologies to achieve environmental sustainability by strengthening the linkages between global environmental and national socio-economic priorities. Socio-economic benefits would be demonstrated in the medium-term through better indicators and planning decisions being made that will enhance more environmentally-friendly and sustainable development. |  |  |  |  |  |  |  |
| 23. If the project is worth $500,000 or more, has the Social and Environmental Screening Procedure (SESP) been conducted to identify potential social and environmental impacts and risks? |  |  |  |  |  | Yes | No |
|  |  |  |  |  |  | N/A |  |
| Sustainability & National Ownership |  |  |  |  |  |  |  |
| 24. Have national partners led, or proactively engaged in, the design of the project? (select from options 0-4 that best reflects this project): - 4: National partners have full ownership of the project and led the process of the development of the project. - 3: The project has been developed jointly by UNDP and national partners, with equal effort. - 2: The project has been developed by UNDP in close consultation with national partners. - 1: The project has been developed by UNDP with limited engagement with national partners. - 0: The project has been developed by UNDP with no engagement with national partners. |  |  |  |  |  | Rating Score |  |
|  |  |  |  |  |  | 3 |  |
| Evidence National stakeholders led the development of the PIF, the project document, the PPG initiation mission, and the Capacity Development Scorecard. National stakeholders also held consultations with stakeholders that reaffirmed the validity of the project strategy to work with other projects and help strengthen the global environmental character, in particular to strengthen the synergies and institutional sustainability of capacities (systemic, institutional, and individual) for more informed and holistic planning and decision-making. |  |  |  |  |  |  |  |
| 25. Are key institutions and systems identified, and is there a strategy for strengthening specific/ comprehensive capacities based on capacity assessments conducted? (select from options 0-4 that best reflects this project): - 4: The project has a comprehensive strategy for strengthening specific capacities of national institutions based on a systematic and detailed capacity assessment that has been completed. - 3: A capacity assessment has been completed, although it is not systematic or detailed. The project document has identified activities that will be undertaken to strengthen capacity of national institutions, but these activities are not part of a comprehensive strategy. - 2: A capacity assessment is planned after the start of the project. There are plans to develop a strategy to strengthen specific capacities of national institutions based on the results of the capacity assessment. - 1: There is mention in the project document of capacities of national institutions to be strengthened through the project, but no capacity assessments or specific strategy developments are planned. - 0: Capacity assessments have not been carried out and are not foreseen. There is no strategy for strengthening specific capacities of national institutions. |  |  |  |  |  | Rating Score |  |
|  |  |  |  |  |  | 3 |  |
| Evidence Although the comprehensive capacity assessment for this project is rooted in the NCSA, this is supported by subsequent assessments. Notwithstanding, this CCCD project calls for capacity assessments to be undertaken at the beginning of project implementation tailored to integrate and reconcile the Rio Conventions with the post-2015 Sustainable Development Goals and green growth indicators, among other relevant indicators that may contribute to environmental resilience and sustainability. Additional project activities such as the design of the EKMS, and training programmes are based on the assessments. Project activities are designed to increase the capacity of key institutions. Through a learning-by-doing and adaptive collaborative management approach, the project will strengthen targeted institutional and technical capacities to create and access better data, information, and knowledge for improved monitoring of global environmental trends. |  |  |  |  |  |  |  |
| 26. Is there is a clear plan for how the project will use national systems, and national systems will be used to the extent possible? |  |  |  |  |  | Yes (2) | No (0) |
| 27. Is there a clear transition arrangement/ phase-out plan developed with key stakeholders in order to sustain or scale up results (including resource mobilization strategy)? |  |  |  |  |  | Yes (2) | No (0) |

## Annex 6:	Standard Letter of Agreement between UNDP and Government of Liberia

STANDARD LETTER OF AGREEMENT BETWEEN UNDP AND THE GOVERNMENT of LIBERIA FOR THE PROVISION OF SUPPORT SERVICES

D R A F T

Dear ________,

1.	Reference is made to consultations between officials of the Government of Liberia (hereinafter referred to as “the Government”) and officials of UNDP with respect to the provision of support services by the UNDP Country Office for nationally managed programmes and projects.  UNDP and the Government hereby agree that the UNDP Country Office may provide such support services at the request of the Government through its institution designated in the relevant programme support document or project document, as described below.

2.	The UNDP Country Office may provide support services for assistance with reporting requirements and direct payment.  In providing such support services, the UNDP Country Office shall ensure that the capacity of the Government-designated institution is strengthened to enable it to carry out such activities directly.  The costs incurred by the UNDP Country Office in providing such support services shall be recovered from the administrative budget of the office.

3.	The UNDP Country Office may provide, at the request of the designated institution, the following support services for the activities of the programme/project:

(a)	Identification and/or recruitment of project and programme personnel;

(b)	Identification and facilitation of training activities; and

(c)	Procurement of goods and services;

4.	The procurement of goods and services and the recruitment of project and programme personnel by the UNDP Country Office shall be in accordance with the UNDP regulations, rules, policies and procedures.  Support services described in paragraph 3 above shall be detailed in an annex to the programme support document or project document, in the form provided in the Attachment hereto.  If the requirements for support services by the Country Office change during the life of a programme or project, the annex to the programme support document or project document is revised with the mutual agreement of the UNDP resident representative and the designated institution.

5.	The relevant provisions of the UNDP Standard Basic Assistance Agreement with Government of Liberia of 1977 (the “SBAA”), including the provisions on liability and privileges and immunities, shall apply to the provision of such support services. The Government shall retain overall responsibility for the nationally managed programme or project through its designated institution.  The responsibility of the UNDP Country Office for the provision of the support services described herein shall be limited to the provision of such support services detailed in the annex to the programme support document or project document.

6.	Any claim or dispute arising under or in connection with the provision of support services by the UNDP Country Office in accordance with this letter shall be handled pursuant to the relevant provisions of the SBAA.

7.	The manner and method of cost-recovery by the UNDP Country Office in providing the support services described in paragraph 3 above shall be specified in the annex to the programme support document or project document.

8.	The UNDP Country Office shall submit progress reports on the support services provided and shall report on the costs reimbursed in providing such services, as may be required.

9.	Any modification of the present arrangements shall be effected by mutual written agreement of the parties hereto.

10.	If you are in agreement with the provisions set forth above, please sign and return to this office two signed copies of this letter.  Upon your signature, this letter shall constitute an agreement between your Government and UNDP on the terms and conditions for the provision of support services by the UNDP Country Office for nationally managed programmes and projects.

Yours sincerely,

________________________

Signed on behalf of UNDP

Pa Lamin Beyai (Ph.D.)

Country Director

_____________________

For the Government

Hon. Boimah S. Kamara, Minister

Ministry of Finance and Development Planning

Attachment

DESCRIPTION OF UNDP COUNTRY OFFICE SUPPORT SERVICES

D R A F T

1.	Reference is made to consultations between Ministry of Finance and Development Planning, the institution designated by the Government of Liberia and officials of UNDP with respect to the provision of support services by the UNDP Country Office for the nationally managed programme or project entitled Strengthening National Capacities to Meet Global Environmental Obligations with the Framework of Sustainable Development Priorities, hereinafter referred to as the Project (Award ID: XXXXXXX/Project ID: XXXXXX/UNDP/GEF PIMS Number 5796).

2.	In accordance with the provisions of the letter of agreement signed on [insert date of agreement] and the project document, the UNDP Country Office shall provide support services for the Project as described below.

3.	Support services to be provided:

| Support services (insert description) | Schedule for the provision of the support services | Cost to UNDP of providing such support services (where appropriate) | Amount and method of reimbursement of UNDP (where appropriate) |
| --- | --- | --- | --- |
| 1. Identification and/or recruitment of project personnel * Project Manager * Project Assistant | On-going throughout implementation when applicable | As per the UPL or according to actual cost | UNDP will directly charge the project upon receipt of request of services from the Implementing Partner |
| 2. Procurement of goods: * Data show * PCs * Printers | On-going throughout implementation when applicable | As per the UPL or according to actual cost | As above |
| 3. Procurement of Services Contractual services for companies | On-going throughout implementation when applicable | As per the UPL or according to actual cost | As above |
| 4. Payment Process | On-going throughout implementation when applicable | As per the UPL or according to actual cost | As above |
| 5. Ticket request (booking, purchase) | On-going throughout implementation when applicable | As per the UPL or according to actual cost | As above |
| 6. F10 settlement | On-going throughout implementation when applicable | As per the UPL or according to actual cost | As above |
|  |  | Total: up to USD 6,000 from GEF grant |  |

Line item in project budget

| Atlas Budgetary Account Code | ATLAS Budget Description | Amount Year 1 (US$) | Amount Year 2 (US$) | Amount Year 3 (US$) | Amount Year 4 (US$) | Total (US$) | See Budget Note: |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 74596 | Services to projects - GOE for CO | 1,500 | 1,500 | 1,500 | 1,500 | 6,000 | a |

Budget note

a.  Recuperation of key project administrative costs

4.         Description of functions and responsibilities of the parties involved:

Functions and responsibilities of Ministry of Lands, Mines and Energy and Responsible parties shall be to:-

- Prepare TORs and Specifications for procurement of services, goods and equipment and request UNDP to procure the International / Local Consultants,

- Prepare Job descriptions and request UNDP to advertise and recruit Project staff,

- Set up Grant management committees and request UNDP to disburse grants/ procure equipment,

- Request UNDP to procure services for some events,

- Request UNDP to procure some communication equipment

Functions and responsibilities of UNDP

- Procurement of services, goods and equipment and request UNDP to procure the International / Local Consultants,

- Advertise and recruit Project staff,

- disburse grants, monitor and evaluate them/ procure equipment,

- Procure services for some events,

- Procure some communication equipment

## Annex 7:	Terms of References

The following Terms of Reference outlines the general responsibilities to be carried out by consultants contracted under the project.  With the exception of the international consultants that will be recruited for the independent evaluation of the project and the Chief Technical Advisor that would provide technical backstopping, the project consultants should ideally be Liberian nationals.  However, experts from the region may be recruited in the event that a suitable national consultant could not be found.  Rates will be based on UNDP Liberia standards for the recruitment of regional consultants, but ideally at a rate that is not significantly greater than that of the national consultant rates in order for the project to remain cost-effective.

Background

- Liberia has made significant progress since the end of the civil war by investing in infrastructure, revising existing policies and laws, and reviewing the mandates of political institutions to reduce duplication.  One area of progress is updating the mandates and restructuring Government ministries and agencies to improve effectiveness and efficiency. Liberia has also established new agencies like the Rural and Renewable Energy Agency to promote the sustainable development strategy. Reforms in Liberia have been undertaken on an institution-by-institution basis and have not been considered on a holistic basis, nor have they increased coordination and harmonization.

- Despite this progress, Liberia is struggling to fulfill many of the objectives set forth in the Rio Conventions.  Many of the developed frameworks and plans for action face limited implementation due to limited government resources, limited human capacity, and a lack of appropriate technologies. Liberia struggles with an inadequate system for information and knowledge management and the poor information sharing between or within sectors. Additionally, the country’s degraded and limited infrastructure combined with a low technical and institutional capacity severely limit Liberia’s environmental governance framework and thus its potential to conserve the natural environment, let alone secure long-term benefits from it. The civil war only exacerbated the situation, leading to displacement of individuals and unprecedented amounts of resource exploitation.

Project Goal and Objectives

- The goal of this project is for Liberia to make better decisions to meet and sustain global environmental obligations.  This requires the country to have the capacity to coordinate efforts, as well as best practices for integrating global environmental priorities into planning, decision-making, and reporting processes.  To that end, the objective of this project is to strengthen a targeted set of national capacities to deliver and sustain global environmental outcomes within the framework of sustainable development priorities.

Project Strategy

- This project will lead to change by addressing the barriers that limit Liberia’s ability to meet obligations under the three Rio Conventions and other MEAs.  By systematically targeting the key barriers, the project will help Liberia make incremental improvements. These short-term changes will in turn lead to long-term improvements; while the project develops capacities, it also lays groundwork for improved systems and frameworks to sustain outcomes.

- This CCCD project creates an institutional space to remove certain key barriers to mainstreaming global environmental obligations into national, county, and district information systems, development policies, and planning frameworks.  The project is also designed to help Liberia sustain these outcomes and realize long-term change.  Specifically, the project will transform how Liberia pursues socio-economic development that integrates global environmental objectives and priorities within decision-making and improved knowledge management.  The project will also contribute to change by catalyzing Liberia’s road to self-reliance and environmental sustainability, assuming that the capacities developed will be institutionalized, thereby resulting in an incrementally reduced dependency on external funding.

The United Nations Development Programme (UNDP), acting as an implementing agency of the Global Environment Facility (GEF), is providing assistance to the Environmental Protection Agency of Liberia in the preparation of the GEF Medium Size Project (MSP) “Strengthening National Capacities to Meet Global Environmental Obligations with the Framework of Sustainable Development Priorities.”

- This project is in line with the GEF-6 CCCD Strategy objective 1, 3, and 5 which call for countries to: a) integrate global environmental needs into management information systems and monitoring, b) integrate MEA provisions into national policy, legislative, and regulatory frameworks, and c) update NCSAs, respectively.

Project Outcomes and Components

At the end of the project, the project will have resulted in improved capacities for meeting global environmental priorities.  This general outcome will be measured by a variety of indicators, characterized as outputs, process, and performance indicators.  Output indicators include the actual installation of the integrated EKMS.  Process indicators include the very important collaboration among government agencies and authorities to share data and information through an agreed sharing protocol and data flow system, legitimized by the necessary approvals, e.g., Memoranda of Agreements.  This project is organized into four linked components:

- Establishment of an integrated environmental knowledge management system to meet global environment and sustainable development priorities

- Enhanced capacities to mainstream, develop, and utilize policies and/or legislative frameworks for effective implementation of the three Rio Conventions.

- Improved environmental attitudes and values for the global environment.

- NCSA is updated to reflect post 2015-SDGs and current opportunities to strengthen priority foundational capacities for the global environment

Responsibilities

National Project Director (NPD)

The Government of Liberia will appoint a national director for this UNDP-supported project.  The National Project Director supports the project and acts as a focal point on the part of the Government.  This responsibility normally entails ensuring effective communication between partners and monitoring of progress towards expected results.

The National Project Director is the party that represents the Government’s ownership and authority over the project, responsibility for achieving project objectives and the accountability to the Government and UNDP for the use of project resources.

In consultation with UNDP, the Committee on Environmental Protection as the concerned ‘ministry’ will designate the National Project Director from among its staff at not lower than the Deputy Minister or Head of Department level.  The National Project Director (NPD) will be supported by a full-time National Project Manager (NPM).

Duties and Responsibilities of the NPD

The NPD will have the following duties and responsibilities:

- Assume overall responsibility for the successful execution and implementation of the project, accountability to the Government and UNDP  for the proper and effective use of project resources)

- Serve as a focal point for the coordination of projects with other Government agencies, UNDP and outside implementing agencies;

- Ensure that all Government inputs committed to the project are made available;

- Supervise the work of the National Project Manager and ensure that the National Project Manager is empowered to effectively manage the project and other project staff to perform their duties effectively;

- Select and arrange, in close collaboration with UNDP, for the appointment of the National Project Manager (in cases where the NPM has not yet been appointed);

- Supervise the preparation of project work plans, updating, clearance and approval, in consultation with UNDP and other stakeholders and ensure the timely request of inputs according to the project work plans;

- Represent the Government institution (national counterpart) at the tripartite review project meetings, UNDP Outcome Board, and other stakeholder meetings.

Remuneration and entitlements:

The National Project Director may not receive monetary compensation from project funds for the discharge of his/her functions.

Project Manager

A part-time Project Manager will be recruited to oversee the project implementation under the guidance of the NPD, the Project Steering Committee, and with the support of UNDP Liberia.  He/she will hold a separate contract as the Public Administration Expert.   In addition to overseeing the implementation of the project’s capacity development activities, the project management will carry out the monitoring and evaluation procedures per UNDP agreed policies and procedures.  These include:

- Oversee the day-to-day monitoring of project implementation

- In consultation with stakeholders, recommend modifications to project management to maintain project’s cost-effectiveness, timeliness, and quality project deliverables (adaptive collaborative management) to be approved by the Project Advisory Board

- Prepare all required progress and management reports, e.g., APR/PIR and project initiation report

- Support all meetings of the Project Advisory Board

- Maintain effective communication with project partners and stakeholders to dissemination project results, as well as to facilitate input from stakeholder representatives as project partners

- Support the independent terminal evaluation

- Ensure full compliance with the UNDP and GEF branding policy

Project Assistant

The Project Assistant will be recruited to support the Project Manager in the carrying out of his/her duties, which will include:

      - Organizational and logistical issues related to project execution per UNDP guidelines and procedures

      - Record keeping of project documents, including financial in accordance with audit requirements

      - Ensure all logistical arrangements are carried out smoothly

      - Assist Project Manager in preparation and update of project work plans in collaboration with the UNDP Country Office

      - Facilitate timely preparation and submission of financial reports and settlement of advances, including progress reports and other substantial reports

      - Report to the Project Manager and UNDP Programme Officer on a regular basis

      - Identification and resolution of logistical and organizational problems, under the guidance of the Project Manager

The Project Assistant will have at least five (5) years’ experience in supporting the implementation of UNDP implemented projects, with preference in environment and natural resource management projects.

Specialist on the Convention on Biological Diversity

This national consultant will be responsible for those project activities that require expertise on interpreting and translating CBD obligations into national programmable activities.  The consultant will prepare the appropriate technical background studies, as well as also serve as a facilitator in the trainings on using data and information relevant to meeting biodiversity conservation objectives, with particular emphasis on endangered endemic species and their ecosystems.

The CBD national consultant will have at least 10 years of work experience in biodiversity conservation programming and project implementation.  At least the last two (2) years of experience include active involvement in CBD negotiations   He/she will have a PhD in natural resource management, with a specialization directly related to biodiversity conservation in Liberia and/or the surrounding region.  Under the supervision of the Project Manager, the specialist will coordinate his/her work with that of other national experts and specialists. This includes coordinating activities with those under implementation by the development partners.

Specialist on the Convention on Desertification and Drought

This national consultant will be responsible for those project activities that require expertise on interpreting and translating CCD obligations into national programmable activities.  The national consultant will prepare the appropriate technical background studies, as well as also serve as a facilitator in the trainings on using data and information relevant to meeting land degradation objectives, with particular emphasis on sustainable land management and land degradation.

The CCD national consultant will have at least 10 years of work experience, of which at least the last two (2) years include active involvement in CCD programming and project implementation.  He/she will have a PhD in natural resource management, with a specialization directly related to land management issues in Liberia and/or the surrounding region.  Under the supervision of the Project Manager, the specialist will coordinate his/her work with that of other national experts and specialists.  This includes coordinating activities with those under implementation by the development partners.

Specialist on the Framework Convention on Climate Change

This national consultant will be responsible for those project activities that require expertise on interpreting and translating FCCC obligations into national programmable activities.  The national consultant will prepare the appropriate technical background studies, as well as also serve as a facilitator in the trainings on using data and information relevant to meeting climate change mitigation and mitigation objectives, with particular emphasis on endangered endemic species and their ecosystems.

The FCCC national consultant will have at least 10 years of work experience, of which at least the last two (2) years include active involvement in FCCC programming and project implementation.  He/she will have a PhD in a field directly relevant to climate change science, with a specialization directly related to mitigation and adaptation strategies relevant to Liberia and/or the surrounding region.  Under the supervision of the Project Manager, the specialist will coordinate his/her work with that of other national experts and specialists. This includes coordinating activities with those under implementation by the development partners.

Information Technology Specialist

An information technology specialist will be recruited to oversee the technical design of the EKMS, including the procurement of the technological hardware and software for its installation.  Under the supervision of the Project Manager, he/she will work with the national Rio Convention specialists, as well as with the relevant information technology managers in the different departments to network the EKMS with their information systems.  The specialist will apply technical expertise to the implementation, monitoring, and maintenance of the EKMS.  With at least five (5) years’ of work experience, the specialist will have at least a Master’s degree in information technology, including network analysis, system administration, security and information assurance, IT audit, database administration, and web administration.

Environmental Sociologist

The Environmental Sociologist will be support the project by contributing to the identification and assessment of best practices and innovations for mainstreaming, paying close attention to socio-economic implications.  This includes the analyses related to the feasibility study and public awareness plan.  He/she will take the lead in developing and implementing the survey as well as undertaking a statistical analysis of survey results.  This specialist will also help design the awareness material and serve as a resource person for the private sector and district level dialogues and workshops.

The Environmental Sociologist will have a PhD in environmental sociology, with demonstrated experience in constructing and implementing surveys, as well as their statistical analysis on trends in environmental values and attitudes.

Public Administration Expert

The individual recruited as the Public Administration Expert will hold an additional separate contract as the Project Manager.  He/she will work with the national and international specialists as well as with the information technology specialist to assess and institutionalize the EKMS as well as with the partner government departments and other stakeholder organizations’ information systems.  He/she will work with the information technology specialist to undertake the in-depth baseline assessment of the current management information systems in Liberia as well as to design the institutional architecture of the EKMS.  This expert will also work with the legal expert to assess and recommend institutional and associated regulatory reforms to be submitted for legislative approval, as well as work of the Rio Convention experts through the expert working groups, as well serve as a resource person and facilitator for the training and learn-by-doing working groups.

The Public Administration Expert will have a post-graduate degree in public administration or related field, and have a minimum of ten (10) years’ experience in progressively responsible and substantive areas in environmental and natural resource governance programming and planning.

Policy/Legal Specialist

The Policy/Legal expert will contribute to the substantive work under the project by assessing the policy and legal implications of instituting the EKMS, in particular the collaboration among key agencies and other stakeholder organizations.  The expert will work with the Public Administration expert as well as with the others, as appropriate to draft and negotiate the Memoranda of Agreement to share data and information, as well as draft the bills that need legislative approval.

The policy/legal expert will have a post-graduate degree in law, with a specialization on environmental law and policy of Liberia.  S/he will have to have a minimum of ten (10) years’ experience in progressively responsible and substantive areas in environmental and natural resource governance programming and planning.

Financial Analyst

The Financial Analyst will take the lead on developing the resource mobilization strategy.  He/she will also provide support, along with other national consultants, in other project activities such as early implementation of the EKMS.  He/she will work under the supervision of the Project Manager.

- The Finance Analyst will have a post-graduate degree in finance or accounting, with preference being a certified or charted public accountant.  He/she will have five years or more experience with the accounting, financial management and auditing of environmental, as well as with the fiscal administration of the government’s agencies that have an environmental stake.  He/she will also have experience in research government statutes, legislation, regulation, and directives that govern public finance management.

Environmental Education Specialist

The Environmental Education Specialist will work with other project consultants to undertake a number of key project analyses, as well as support the other project consultants to construct deliverables such as the public awareness and communication campaign, assessment of training needs, and the secondary school curricula.  He/she will also design the learning-by-doing workshops to ensure that they are structured to foster critical thinking among workshop participants.

The Environmental Education Specialist will have a post-graduate degree in K-12 education, preferably a PhD, with demonstrated experience in developing national education policies, programmes, and plans as well as the development of secondary school curricula on environmental studies.  He/she will have experience in facilitating expert and stakeholder working groups in the collaborative drafting of sector policies.

Technical Working Groups

The Technical Working Groups will be constituted by a diverse set of national experts and other key stakeholders with comparative knowledge and/or experience on a wide range of Rio Convention issues related to the project.  Three such groups will be constituted – one for each of the three Rio Conventions.  Membership of these groups can be rotating in order that each meeting of the group contains as complete as possible the breadth of stakeholder views and expertise.  These groups will convene to review and validate the technical analyses prepared by the individual consultants, and serve as a form of peer review group.  They should meet as a group in order to be more effective in discussing and exchange views of the particular issues to be discussed.  Each working group should contain at least 12 stakeholder members and represent all key stakeholder groups, NGOs, and civil society.  Outside of the technical workshop groups, other experts and stakeholders should be encouraged to provide input and peer review input of analyses and recommendations prepared under the project.

The Technical Working Groups will also meet collectively to reconcile the different perspectives from the three Rio Conventions with a view to producing a consolidated set of recommendations.  The consolidated Technical Workshop Groups are to be considered as the stakeholder validation workshops for each of the key deliverables under the project, such as the technical analyses, Rio Convention monitoring indicators, memoranda of agreement, and by-laws.

Chief Technical Advisor

Critically, the project will recruit a part-time chief technical advisor who will be recruited for the full duration of the four year project.  The Chief Technical Advisor will provide necessary technical advisory services on the implementation of key project activities, in particular the review of recommendations to integrate and institutionalize Rio Convention obligations within the EKMS, among other substantive activities, as appropriate.  These services will be provided over the course of the three-year implementation period to provide technical backstopping to help ensure the timely and high quality project delivery.

International Evaluation Consultant

The international evaluation consultant will be an independent expert that is contracted to assess the extent to which the project has met project objectives as stated in the project document and produced cost-effective deliverables.  The consultant will also rate capacities developed under the project using the Capacity Development Scorecard.

The Terms of Reference for the International Evaluation Consultant will follow the UNDP/GEF policies and procedures, and together with the final agenda will be agreed upon by the UNDP/GEF RCU, UNDP Country Office and the Project Team.  The final report will be cleared and accepted by UNDP (Country Office and Regional Coordination Unit) before being made public.

## Annex 8:	References

Bellamy, J.-J., & Hill, K. (2010). Monitoring Guidelines of Capacity Development in Global Environment Facility Projects. New York: Global Support Programme, Bureau for Development Policy, United Nations Development Programme.

Bellamy, J.-J., & Hill, K. (2010), National Capacity Self-Assessments: Results and Lessons Learned for Global Environmental Sustainability. New York: Global Support Programme, Bureau for Development Policy, United Nations Development.

Demetriades, J. (2007). Gender Indicators: What, Why and How? . BRIDGE.

DESA. (2011). Capacity Development Strategy. New York.

Dorliae, K. (2012). 2012 National Sustainable Development Report.

Environmental Protection Agency of Liberia. (2013). Liberia Initial National Communication. GEF, UNEP.

GEF. (2013). Mainstreaming Gender at the GEF. Washington, D.C.: Global Environment Facility.

Global Support Programme. (2005). National Capacity Self-Assessment: Resource Kit. Global Environment Facility/United Nations Development Programme/United Nations Environment Programme.

Government of Liberia (2011), EPA Five-Year Strategic Implementation Plan 2011-2016

Government of Liberia (2012), National Sustainable Development report 2012

Government of Liberia (2013), Liberia Constraints Analysis

Government of Liberia (2016), Liberia's National Vision 2030

Greijn, H. (2013, January). Dilemas of inter-organisational learning. Capcity.org.

Hassani, K. S. (2012). Final Report Establish a Institutional Mechanism for Multi-Sectoral Coordination for Sustainable Development National Commission for Sustainable Development CNDD. UNDP.

Hill, K., Rife, M. J., & Twining-Ward, T. (2015), The Strategic Value of GEF-Funded Cross-Cutting Capacity Development. New York: United Nations Development Programme.

Human Rights and Protection Service of the United Nations Mission in Liberia. (2016). Addressing Impunity for Rape in Liberia. Office of the United Nations High Commissioner for Human Rights.

Ministry of Planning and Economic Affairs (MPEA). (2011). Liberia National Capacity Development Strategy. UNDP.

Moser, A. (2007). Gender and Indicators Overview Report. BRIDGE, UNDP, Institute of Development Studies.

OECD. (2012). Greening Development: Enhancing Capacity for Environmental Management and Governance.

OECD. (2015). Social Institutions and Gender Index (SIGI). Retrieved April 24, 2015, from Indonesia.

Organisation for Economic Cooperation and Development. (2006). The Challenge of Capacity Development: Working Towards Good Practices. OECD.

Republic of Liberia. (2004). Liberia's National Biodiversity Strategy and Action Plan. Monrovia: Republic of Liberia.

Republic of Liberia. (2013). Agenda for Transformation 2012-2017: STEPS TOWARDS LIBERIA RISING 2030.

Republic of Liberia. (2014). Fifth National Report.

Republic of Liberia. (2017). Liberia’s Second National Biodiversity Strategy and Action Plan II 2017-2025.

The Office of the Executive Mansion. (2012). Women’s Participation Increases in President Sirleaf’s New Government; Representation in Legislature Still Below Proposed 30 Percent Threshold. Press Release, Monrovia. Retrieved from http://www.emansion.gov.lr/2press.php?news_id=2264&related=7&pg=sp

UNDP. (2010). Capacity Assessment Methodology: User's Guide. New York: Capacity Development Group/Bureau for Development Policy, United Nations Development Programme.

UNDP. (2010). Measuring Capacity. Capacity Development Group, Bureau for Development Policy.

UNDP. (2015). Human Development Report 2015.Briefing note for countries on the 2015 Human Development Report. Liberia.

UNEP. (2010). National Environmental Summary.

UNEP. (2011). Towards a Green Economy: Pathways to Sustainable Development and Poverty Eradication .

United Nations. (2011). Partnering with countries to integrate global develpoment knowledge into national development strategies.

United Nations. (2014). Empowering Women in Liberia Joint Programme on Gender Equality And Women's Empowerment. Government of Liberia.

United Nations Development Programme. (2014). UNDP gender equality strategy 2014-2017.

World Bank Institute Capacity Development and Results Practice. (2011). Steps for Designing a Results-Focused Capacity Development Strategy A Primer for Development Practitioners Based on the Capacity Development and Results Framework.

Whereas the global environmental challenges refer to the environmental issues such as climate change, habitation degradation, loss of loss of endemic species, and land degradation, capacity barriers refer to underlying causes of global environment degradation, such as a lack of awareness of the value of the environment.

This medium-size project was implemented by UNDP between 2008 and 2014, the aim of which was to strengthen the country’s institutional and human resource capacity on sustainable land management planning and implementation.  A particular feature of the project was to facilitate the wider adoption of sustainable land management practices across sectors.

This is the abbreviation in English.

See GEF Council Paper GEF/C.40/10, 26 April 2011 on GEF Policies on Environmental and Social Safeguards and Gender Mainstreaming as well as the Instrument for the Establishment of the Restructured Global Environment Facility, October 2011.

Changed from mitigate to manage. Projects cannot mitigate risks, they can only manage them.

Meeting minutes includes records of key meetings such as local, regional and national consultations regarding inputs on the design and implementation of the relevant output and associated activities.  Meetings may be individual or group meetings, with government officials or non-state stakeholders.

These will include a list of all workshop and working group participants

See https://www.thegef.org/gef/policies_guidelines

See https://www.thegef.org/gef/gef_agencies

See guidance here:  https://info.undp.org/global/popp/frm/pages/financial-management-and-execution-modalities.aspx

Excluding project team staff time and UNDP staff time and travel expenses

The costs of UNDP Country Office and UNDP/GEF Unit’s participation and time are charged to the GEF Agency Fee

The budget will vary depending on the number of consultants required (for full size projects should be two consultants); the number of project sites to be visited; and other travel related costs.  Average # total working days per consultant not including travel are between 22-25 working days.

See http://www.undp.org/content/undp/en/home/operations/transparency/information_disclosurepolicy/

See https://www.thegef.org/gef/policies_guidelines

Meeting minutes includes records of key meetings such as local, regional and national consultations regarding inputs on the design and implementation of the relevant output and associated activities.  Meetings may be individual or group meetings, with government officials or non-state stakeholders.

These will include a list of all workshop and working group participants

Prohibited grounds of discrimination include race, ethnicity, gender, age, language, disability, sexual orientation, religion, political or other opinion, national or social or geographical origin, property, birth or other status including as an indigenous person or as a member of a minority.  References to “women and men” or similar is understood to include women and men, boys and girls, and other groups discriminated against based on their gender identities, such as transgender people and transsexuals.

In regards to CO2, ‘significant emissions’ corresponds generally to more than 25,000 tons per year (from both direct and indirect sources).  [The Guidance Note on Climate Change Mitigation and Adaptation provides additional information on GHG emissions.]

Forced evictions include acts and/or omissions involving the coerced or involuntary displacement of individuals, groups, or communities from homes and/or lands and common property resources that were occupied or depended upon, thus eliminating the ability of an individual, group, or community to reside or work in a particular dwelling, residence, or location without the provision of, and access to, appropriate forms of legal or other protections.

This Letter of Agreement is on-going at the time of project document formulation, and expected to be signed by June 2017.

This Letter of Agreement is on-going at the time of project document formulation, and expected to be signed by June 2017.

Ibid

To qualify as an expert, this individual must demonstrate a higher standard of expertise and must possess significant skills and experience.