GEF-6 Project Identification Form (PIF)

Project Type:  Medium-Sized Project

Type of Trust Fund: GEF Trust Fund

For more information about GEF, visit TheGEF.org

PART I: Project Information

| Project Title: | Strengthening national capacities to meet global environmental obligations with the framework of sustainable development priorities |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Country(ies): | Liberia | GEF Project ID: |  |  |  | 9390 |
| GEF Agency(ies): | UNDP | GEF Agency Project ID: |  |  |  | 5796 |
| Other Executing Partner(s): | EPA | Submission Date: |  |  |  | 1 Apr 2016 |
| GEF Focal Area(s): | Multi-focal Areas | Project Duration (Months) |  |  |  | 36 |
| Integrated Approach Pilot | IAP-Cities IAP-Commodities IAP-Food Security |  |  | Corporate Program: SGP |  |  |
| Name of parent program: | Cross-Cutting Capacity Development |  | Agency Fee ($) |  | 142,500 |  |

A.  indicative Focal Area  Strategy Framework and Other Program Strategies

| ### Objectives/Programs (Focal Areas, Integrated Approach Pilot, Corporate Programs) | ### Trust Fund | ### (in $) |  |
| --- | --- | --- | --- |
|  |  | ### GEF Project Financing | ### Co-financing |
| CCCD-1 | GEFTF | 545,000 | 550,000 |
| CCCD-3 | GEFTF | 625,000 | 700,000 |
| CCCD-5 | GEFTF | 200,000 | 50,000 |
| Project Management | GEFTF | 130,000 | 200,000 |
| Total Project Cost |  | 1,500,000 | 1,500,000 |

B.  indicative Project description summary

| ### Project Objective: To strengthen a targeted set of national capacities to deliver and sustain global environmental outcomes within the framework of sustainable development priorities |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| ### Project Component | ### Financing Type | ### Project Outcomes | ### Project Outputs | ### Trust Fund | ### (in $) |  |
|  |  |  |  |  | ### GEF Project Financing | ### Co-financing |
| Component 1: Establish an integrated environmental knowledge management system that catalyzes the application of best practices and innovations for the global environment | TA | CD-1: Environmental knowledge management system is created through networking, use of best practices and innovations, updating technology, and linkage to planning and decision-making | 1.1: Institutional mapping and analysis of an optimal knowledge management system for the global environment 1.2: Integrated environmental knowledge management system designed 1.3: Targeted networking of existing information and knowledge management systems 1.4: Selected updating of technologies to create cost-effective synergies for knowledge management and monitoring of the global environment 1.5: Development of new and improved global environmental indicators for select high priority sector(s) 1.6: Learning-by-doing training on improved methodologies and analytical skills for interpreting global environmental trends and formulating integrated environmental-sectoral development 1.7: Pilot implementation of the integrated environmental knowledge management system through a select sectoral plan (with 2.6) | GEF TF | 420,000 | 400,000 |
| Component 2: Enhanced institutional and technical capacities to mainstream, develop, and utilize policies and/or legislative frameworks for effective implementation of the three Rio Conventions | TA | CD-3: Capacities to develop and implement integrated policies, plans and programmes are enhanced | 2.1: In-depth SWOT and Gap analysis of existing environmental policies and legislation, and the effectiveness of their enforcement 2.2: Strengthened policy and regulatory framework through improved operational interpretation, enforcement tools, and by-laws 2.3: Strengthened consultative and decision-making processes for sector mainstreaming of Rio Convention obligations. This will include, among others, information-sharing and collaborative agreements, inter-ministerial committee(s) on MEAs; and non-state consultative committee(s) 2.4: Targeted updating and streamlining of institutional mandates to facilitate and catalyze long-term action to meet global environmental obligations 2.5: Enhanced monitoring and compliance arrangements, e.g., environmental impact and strategic environmental assessments 2.6: Demonstration and piloting of integrated environmental-development best practices that reflect global environmental priorities and the Post-2015 Sustainable Development Goals (with 1.7) 2.7: Resource mobilization strategy to replicate and institutionalize Rio Convention mainstreaming | GEF TF | 500,000 | 550,000 |
| Component 3: Enhancing awareness on the value of the global environment to meet socio-economic priorities | TA | CD-1 & CD-3: Improved environmental attitudes and values for the global environment | 3.1: Stakeholder dialogues on the socio-economic value of the Rio Conventions 3.2: Brochures and articles on the Rio Conventions 3.3: Public service announcement(s) on globally sensitive and environmentally friendly behavior 3.4: Improved educational curricula and youth civic engagement 3.5: Internet visibility of integrated and streamlined environmental legislation and valuation tools | GEF TF | 250,000 | 300,000 |
| Component 4: Updated NCSA | TA | CD-5: NCSA is updated to reflect post 2015-SDGs and current opportunities to strengthen priority foundational capacities for the global environment | 4.1: Updated assessments of capacity challenges to meet and sustain Rio Convention obligations, building upon GEF focal area enabling activities 4.2: Integrated cross-cutting analysis of systemic, institutional, and individual capacity development priorities 4.3: Capacity Development Strategy and Action Plan, building on action plans of GEF focal area enabling activities 4.4: Update NCSA Final Report | GEF TF | 200,000 | 50,000 |
| Subtotal |  |  |  |  | 1,370,000 | 1,300,000 |
| Project Management Cost (PMC) |  |  |  | GEFTF | 130,000 | 200,000 |
| Total Project Cost |  |  |  |  | 1,500,000 | 1,500,000 |

If Multi-Trust Fund project: PMC in this table should be the total and enter trust fund PMC breakdown here (     )

C.  Indicative sources of  Co-financing for the project by name and by type, if available

| Sources of Co-financing | Name of Co-financier | Type of Co-financing | Amount ($) |
| --- | --- | --- | --- |
| Recipient Government | Government of Liberia | Grant | 100,000 |
| Recipient Government | Government of Liberia | In-Kind | 400,000 |
| GEF Agency | United Nations Development Programme | Grant | 50,000 |
| GEF Agency | United Nations Development Programme | In-Kind | 150,000 |
| Others | To be determined | In-Kind | 800,000 |
| Total Co-financing |  |  | 1,500,000 |

D.  Indicative Trust Fund  Resources Requested by Agency(ies),  Country(ies) and the Programming of Funds a)

| GEF Agency | Trust Fund | Country/ Regional/ Global | Focal Area | Programming of Funds | (in $) |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | GEF Project Financing (a) | Agency Fee (b)b) | Total (c)=a+b |
| UNDP | GEFTF | Liberia | Multi-Focal Area | Cross-Cutting Capacity | 1,500,000 | 142,500 | 1,642,500 |
|  |  |  |  |  |  |  | 0 |
|  |  |  |  |  |  |  | 0 |
|  |  |  |  |  |  |  | 0 |
|  |  |  |  |  |  |  | 0 |
| Total GEF Resources |  |  |  |  | 1,500,000 | 142,500 | 1,642,500 |

- Refer to the Fee Policy for GEF Partner Agencies.

E.  Project preparation grant (ppg)

Is Project Preparation Grant requested? Yes    No  If no, skip item E.

PPG  Amount requested by agency(ies), Trust Fund,  country(ies) and the Programming  of funds

| Project Preparation Grant amount requested: $50,000 PPG Agency Fee: $4,750 |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| GEF Agency | Trust Fund | Country/ Regional/Global | Focal Area | Programming of Funds | (in $) |  |  |
|  |  |  |  |  | PPG (a) | Agency Fee (b) | Total c = a + b |
| UNDP | GEF TF | Liberia | Multi-focal Areas | Cross-Cutting Capacity | 50,000 | 4,750 | 54,750 |
|  |  |  |  |  |  |  | 0 |
|  |  |  |  |  |  |  | 0 |
| Total PPG Amount |  |  |  |  | 50,000 | 4,750 | 54,750 |

F.  Project’s Target Contributions to Global Environmental Benefits

Provide the expected project targets as appropriate.

| Corporate Results | Replenishment Targets | Project Targets |
| --- | --- | --- |
| - Maintain globally significant biodiversity and the ecosystem goods and services that it provides to society | Improved management of landscapes and seascapes covering 300 million hectares | hectares |
| - Sustainable land management in production systems (agriculture, rangelands, and forest landscapes) | 120 million hectares under sustainable land management | hectares |
| - Promotion of collective management of transboundary water systems and implementation of the full range of policy, legal, and institutional reforms and investments contributing to sustainable use and maintenance of ecosystem services | Water-food-ecosystems security and conjunctive management of surface and groundwater in at least 10 freshwater basins; | Number of freshwater basins |
|  | 20% of globally over-exploited fisheries (by volume) moved to more sustainable levels | Percent of fisheries, by volume |
| - 4. Support to transformational shifts towards a low-emission and resilient development path | 750 million tons of CO2e mitigated (include both direct and indirect) | metric tons |
| - Increase in phase-out, disposal and reduction of releases of POPs, ODS, mercury and other chemicals of global concern | Disposal of 80,000 tons of POPs (PCB, obsolete pesticides) | metric tons |
|  | Reduction of 1000 tons of Mercury | metric tons |
|  | Phase-out of 303.44 tons of ODP (HCFC) | ODP tons |
| - Enhance capacity of countries to implement MEAs (multilateral environmental agreements) and mainstream into national and sub-national policy, planning financial and legal frameworks | Development and sectoral planning frameworks integrate measurable targets drawn from the MEAs in at least 10 countries | Number of Countries: 1 |
|  | Functional environmental information systems are established to support decision-making in at least 10 countries | Number of Countries: 1 |

PART II:  Project Justification

1.  Project Description.  Briefly describe: 1) the global environmental and/or adaptation problems, root causes and barriers that need to be addressed; 2) the baseline scenario or any associated baseline projects, 3) the proposed alternative scenario, with a brief description of expected outcomes and components of the project, 4) incremental/additional cost reasoning and expected contributions from the baseline, the GEFTF, LDCF, SCCF,  and co-financing; 5) global environmental benefits (GEFTF) and/or adaptation benefits (LDCF/SCCF); and 6) innovation, sustainability and potential for scaling up.

1) Liberia is located on the southwest coast of Africa, and boarders the Ivory Coast, Guinea, and Sierra Leone. Although Liberia is a rather small country, it has significant biodiversity. There are 600 bird species, 150 mammals, 75 reptiles and over 2000 flowering plants.   Some notable species in Liberia include western chimpanzees, forest elephants, and leopards.   Liberia also has rich forests; around 42% of the Upper Guinea Forest of West Africa is contained within Liberia.  Liberia also has numerous natural resources such as timber, rubber, gold diamonds, and iron ore.  Economically, the forestry and agriculture sectors are two of the most important sectors in Liberia.

Liberia faces numerous environmental problems including land degradation, fragmentation, deforestation, soil erosion, and pollution.  Between 1990 and 2005, Liberia lost 22.3% of its forest cover.  Deforestation rates have increased since 2000.   Increases in deforestation and land degradation are largely due to displaced people clearing land.   Also contributing to these threats is the method of farming, poaching and hunting, unregulated timber extraction.   These threats stem from logging, farming, mining, charcoal production, invasive species, and a lack of public education and awareness, and inadequate law enforcement.  Liberia has struggled to address these environmental issues.   The civil wars, which lasted for more than 10 years, significantly contributed to environmental problems in the country. There has been slow progress in establishing protected areas, and conservation is hampered by limited data, a lack of land-use planning.  Additionally, the absence of public electricity has led to an increase in charcoal production.

Liberia has undertaken numerous initiatives to address environmental issues.  Despite the achievements Liberia made, Liberia continues to face important challenges to meeting environmental goals.  The NCSA identified the following barriers (i.e., drivers of global environmental degradation) that cut across the three Rio Conventions:

- Inadequate public awareness and education/training

- Inadequate institutions and institutional frameworks

- Inadequate political commitment

- Inadequate planning skills and resources, as well as incomplete structures at all levels of policy implementation

- Inadequate financial resources and economic framework

- Inadequate strategic plans and implementation

- Inadequate access to information

- Inadequate policies and legal frameworks

- Low level of involvement of civil society

- Inadequate natural resources management systems

- Lack of institutional capacities

- Lack of effective mechanism for information processing and sharing

- Poor governance

Liberia’s Agenda for Transformation 2012-2017 confirmed many of the barriers identified in the NCSA.  Specifically, the agenda noted the following barriers:

- Weak technical, administrative and managerial capacities

- Weak institutional coordination

- Unclear policies and mechanisms to enable effective participation by especially non-state actors at the national and local levels

- Limited stakeholder participation in planning and decision-making processes

- Limited dissemination of key information

2) Liberia is struggling to fulfill many of the objectives set forth in the Rio Conventions.  Many of the developed frameworks and plans for action face limited implementation due to limited government resources, limited human capacity, and a lack of appropriate technologies. Liberia struggles with an inadequate system for information and knowledge management and the poor information sharing between or within sectors. Additionally, the country’s degraded and limited infrastructure combined with a low technical and institutional capacity severely limit Liberia’s environmental governance framework and thus its potential to conserve the natural environment, let alone secure long-term benefits from it. The civil war only exacerbated the situation, leading to displacement of individuals and unprecedented amounts of resource exploitation.

The country has demonstrated a desire to improve the environmental policy framework with the preparation of multiple new policies including the National Environmental Protection and Management Law (2003), the National Environmental Policy (2003), the establishment of an Environmental Protection Agency, in 2003, the National Forestry Law (2000), and the New Mineral and Mining Laws (2000).

Multilateral donor agencies currently working in Liberia now include the African Development Bank, GEF, IFAD, UNDP, and the World Bank.  Bilateral donor agencies are also very important development partners from, Norway, and the United States (USAID), as well as other inter-governmental organizations such as the CARE International, Conservation International, and the Society for the Conservation of Nature in Liberia.

National environmental NGOs, with assistance from Conservation International, organized themselves into the Alliance for Conservation in Liberia. The goal of this body is to ensure that all local NGOs who are or would like to be involved in conservation of biodiversity can do so without overlapping efforts or functions.

Liberia has made significant progress since the end of the civil war by investing in infrastructure, revising existing policies and laws, and reviewing the mandates of political institutions to reduce duplication.  One area of progress is updating the mandates and restructuring Government ministries and agencies to improve effectiveness and efficiency. Liberia has also established new agencies like the Rural and Renewable Energy Agency to promote the sustainable development strategy. Reforms in Liberia have been undertaken on an institution-by-institution basis and have not been considered on a holistic basis, nor have they increased coordination and harmonization.

In the first Poverty Reduction Strategy, the environment was considered a cross-cutting issue.  Some achievements made during implementation of this strategy include passage of the Community Rights Law, which established a system for community harvesting of forests. Efforts were also undertaken to improve protected areas management and increase the size/number of protected areas.

In Liberia’s medium-term Poverty Reduction Strategy II (2012-2018) there is a fifth pillar: Cross-Cutting Issues which includes the environment. Additionally, environmental issues have been integrated into other pillars of the strategy specifically the economic pillar.

During the Liberia Rio+20 National Consultative Workshop, Liberia identified five issues that are essential for accomplishing its development goals and objectives.  Additionally, Liberia has also developed a National Capacity Development Strategy (2010), which calls for investing in areas needed to achieve development goals.

During the PPG, the extent to which capacities to meet and sustain Rio Convention obligations will build on national sustainable development priorities will be explored, and help to better delineate the project’s system boundary.

3) GEF Cross-Cutting Capacity Development is a programme that does not lend itself readily to programme indicators, such as reduction of greenhouse gas emissions over a baseline average for the years 1990 to 1995, or percentage increase of protected areas containing endangered endemic species.  Instead, CCCD projects are measured by output, process, and performance indicators that are proxies to the framework indicators of improved capacities for the global environment.  To this end, CCCD projects look to strengthen cross-cutting capacities in the five major areas of stakeholder engagement, information and knowledge, policy and legislation development, management and implementation, and monitoring and evaluation (Hill, Rife, & Twining-Ward, 2015).  This project also conforms to the GEF CCCD Strategy in that the project will take a learn-by-doing approach to mainstream and integrate global environmental priorities within targeted existing monitoring, evaluation and decision-making processes, thus further ensuring sustainability.  These capacities would be institutionalized by taking an adaptive collaborative management approach that engages stakeholders as collaborators in the design and implementation of project activities that take into account unintended consequences arising from policy interventions. This approach of pursuing socio-economic and environmental improvements through capacity building, reformed policies, technological innovation, knowledge management, increased efficiency, financial mobilization, and enhanced awareness at a national and sub-national level is in line with many of the strategies discussed in the International Resource Panel Report on Policy Coherence of the Sustainable Development Goals.

Based on Liberia’s key policy and programme frameworks outlined above, a number of priority capacity development recommendations could be undertaken within the construct of a Cross-Cutting Capacity Development (CCCD) project.  The proposed project would develop a targeted set of systemic, institutional, and individual capacities to strengthen the country’s underlying capacities to meet and sustain global environmental obligations.  The objective is to strengthen targeted national capacities to deliver and sustain global environmental outcomes within the framework of sustainable development priorities.  This project will be implemented through four components:

Component 1

CCCD-1:	Establishment of an integrated environmental knowledge management system to meet global environment and sustainable development priorities

This first component will focus on the establishment of an environmental knowledge management system by integrating and reconciling relevant existing systems.  A key feature of this system is that it seeks to use the latest tools and innovations, including technological, to access and create new knowledge that would allow for better decisions to be made to protect the global environment.  Not only will this component seek to develop this institutional mechanism, it will also provide the learning-by-doing training so that stakeholders make best use this system (output 1.6)

1.1:  Institutional mapping and analysis of an optimal knowledge management system

1.2:  Integrated environmental knowledge management system designed

1.3:  Targeted networking of existing information and knowledge management systems

1.4:  Selected updating of technologies to create cost-effective synergies for knowledge management

1.5: Development and integration of new and improved global environmental indicators into select sectoral development plan(s)

1.6: Learning-by-doing training on improved methodologies and analytical skills for interpreting global environmental trends and understanding their relevance to sectoral development

Component 2

CCCD-3:	Enhanced capacities to mainstream, develop, and utilize policies and/or legislative frameworks for effective implementation of the three Rio Conventions

Components 1 and 2 are important complements of each other.  Whereas the first component will establish and provide training on the how substantive content of the integrated environmental knowledge management system, component 2 follows with a set of institutional capacity development actions to use this system for improved mainstreaming and monitoring.  This will include systemic capacity building by strengthening the enabling environment, i.e., relevant policies and legislative frameworks, to make legitimize the long-term use of this system.  Capacity development actions will also focus on strengthen institutional arrangements in order to embed this system within existing management structures and operational procedures.  A third set of capacity development activities will include learning-by-doing use of the system to formulate policy responses and programme interventions and to test these in the field.  Participants in this second set of trainings will go through the first set of trainings under component 1 where they will learn new and improved methodologies and skills to understand global environmental metrics and their impacts on socio-economic development.   Through learning-by-doing workshops and exercises, participants will review, revise, and develop appropriate legislative and regulatory instruments to better reflect and support global environmental objectives within the framework of socio-economic policies.  An important set of activities under this component will be to demonstrate and pilot mainstreamed best practices.

2.1:  In-depth SWOT and Gap analysis of existing environmental policies and legislation, and the effectiveness of their enforcement

2.2:  Strengthened policy and regulatory framework through improved operational interpretation, enforcement tools, and by-laws

2.3:  Strengthened consultative and decision-making processes for sector mainstreaming of Rio Convention obligations, including information-sharing and collaborative agreements, inter-ministerial committee on MEAs; and non-state consultative committee

2.4:  Targeted updating and streamlining of institutional mandates to facilitate and catalyze long-term action to meet global environmental obligation

2.5:  Enhanced monitoring and compliance arrangements and policy responses, e.g., environmental impact and strategic environmental assessments

2.6:  Demonstration and piloting of integrated environmental-development best practices the reflect global environmental priorities and the Post-2015 Sustainable Development Goals (with 1.7)

Component 3

CCCD-1 & CCCD-3:  Improved environmental attitudes and values for the global environment

This component will focuses on a set of activities designed to strengthen awareness and understanding of the wider population of the project.  This component is critical to addressing the institutional sustainability of project outputs by raising an overall understanding and greater value of how addressing global environmental obligations under the Rio Convention contribute to addressing important and immediate socio-economic development priorities.  Project outputs include:

3.1:  Stakeholder dialogues on the socio-economic value of the Rio Conventions

3.2:  Brochures and articles on the Rio Conventions

3.3:  Public service announcement(s) on globally sensitive and environmentally friendly behavior

3.4:  Improved educational curricula and youth civic engagement

3.5:  Internet visibility of integrated and streamlined environmental legislation and valuation tools

3.6:  Resource mobilization to replicate and institutionalize Rio Convention mainstreaming

Component 4

CCCD-5:	NCSA is updated to reflect post 2015-SDGs and current opportunities to strengthen priority foundational capacities for the global environment

This fourth component will update Liberia’s NCSA that was prepared in 2005.  This will serve to reinvigorate the consultative and collaborative approach developed under the NCSA to reconcile and integrate the capacities necessary to strengthen global environmental outcomes.  Key outputs include:

4.1:  Updated assessments of capacity challenges to meet and sustain Rio Convention obligations, building upon GEF focal area enabling activities

4.2:  Integrated cross-cutting analysis of systemic, institutional, and individual capacity development priorities

4.3:  Capacity Development Strategy and Action Plan, building on action plans of GEF focal area enabling activities

4.4:  Updated NCSA Final Report and Action Plan

4) UNDP will contribute cash from its core funds to this project.  UNDP will also provide significant in-kind support to the project.  Its technical and administrative staff will provide ongoing advice and logistical support to the project when needed.  It will provide meeting facilities, communication facilities, transport facilities, as requested and as necessary.  UNDP will further use its role as the UN Resident Coordinator to make sure the project is aligned with all UN system work.  UNDP senior management will play a key role in advocacy, and in awareness raising by attending key public events.

The incremental cost of this project is determined on the basis of the main criterion that the co-financing achieves an equal share of the GEF increment will be negotiated with potential donors.  The nature of the capacity development activities of this project do not lend itself to clearly distinguish those activities that will deliver global environmental benefits and those that should be undertaken in the country’s own sustainable development interest.  Unless such a distinction can be made, the average cost of project activities will be equally shared by both sources of funds.

5) This project responds to three main categories of articles under the three Rio Conventions, demonstrating both the global environmental value of the project and its cross-cutting capacity development strategy.  The first set of Rio Convention articles refer to stakeholder engagement, where the three Rio Conventions call for the building of capacities of relevant individuals and organizations (resource users, owners, consumers, community and political leaders, private and public sector managers and experts) to engage proactively and constructively with one another to manage a global environmental issue (FCCC: Articles 4 & 6; CBD: Articles 10 &13; and CCD: Articles 5, 9, 10 &19).  The second set of articles call for countries to develop capacities of individuals and organizations to plan and develop effective environmental policy and legislation, related strategies, and plans based on informed decision-making processes for global environmental management (FCCC: Article 4 & 6; CBD: Articles 8, 9, 16 &17); and CCCD: Articles 4, 5, 13, 17, 18, and 19).  The third set of capacities refer to strengthening environmental governance, in particular to strengthen capacities of individuals and organizations to enact environmental policies or regulatory decisions, as well as plan and execute relevant sustainable global environmental management actions and solutions (FCCC: Article 4; CBD: Articles 6, 14, 19 & 22); and CCD: 4, 5, 8, 9 & 10).  In particular, article 7 of the CBD, article 16 of the CCD, and article 5 of the FCCC specifically call for strengthening monitoring, data and information management, and sharing.

The GEF support to this CCCD project will be instrumental in building the country's capacities to secure national assets and also to protect the global environment and biodiversity.  The proposed actions will generate global environmental benefits by bringing into operation effective, integrated programs that conserve and sustain Liberia’s natural environment and resources, including marine and forest biodiversity.  The global significance stems from the fact that Liberia has rich biodiversity including marine species, mangroves, and large terrestrial species.  Additionally, the Upper Guinean Forest, which Liberia has over 40% of, is a world biological diversity hotspot. The project's actions will support outcomes relevant to each of the major MEAs to which Liberia is signatory.

6) The innovativeness of this project stems from its strategy of engaging stakeholders from the local level to the top decision-making level.  The transformative nature of this project rests largely on negotiating coordination and collaboration agreements among agencies and non-state stakeholders to share data, information, and knowledge.  The project seeks to facilitate improved collaboration and engagement of stakeholders with comparative expertise and knowledge that is intended to yield better quality data, information and knowledge to apply best practices.

The project’s fundamental approach to sustainability lies in building the underlying capacities to make more informed decisions on best practice approaches for integrated global environmental and sustainable development.  All levels of government are responsible for taking on the challenges of global environment and meeting the convention guidelines as part of this project.  The onus is every level of government to use the best available data, information and knowledge to make more informed decisions.  This project is strategically designed to meet the Rio Convention priorities through a targeted set of capacity building activities that seeks to engage stakeholders at all levels in Liberia responsible for planning and make decisions that affect the global environment.  Activities should therefore be implemented to involve as many and as diverse stakeholders in order to ensure a more comprehensive and holistic approach to creating, accessing, and using the best available data and information.  Stakeholder engagement should also be as early as possible, allowing for increased ownership and thus sustainability.  Notwithstanding, decisions must be negotiated in a way that also ensure that all stakeholders receive satisfactory levels of benefits and equity, which are also critical to sustainability.

Sustainability is further enhanced by undertaking an extensive set of awareness-raising activities targeted at a broad range of stakeholders, including the general public and particularly youths where the addition of appropriately framed information can have an important impact on the early stages of value formation.  Another approach to ensuring sustainability is to align multilateral environmental agreements with key national development priorities.  Aligning global environmental priorities with high value sector development priorities should help strengthen the legitimacy of both priorities if they are reconciled through thoughtful and transparent consultative and decision-making processes, as well as being based on widely accepted data, information, knowledge and best practices.  The project will also undertake targeted awareness-raising activities to secure high-level commitment from key decision-makers, such as parliamentarians, and foster a sufficient number of project champions to sustain project outcomes following project completion.

As a medium-size project, this intervention has certain limitations, namely in being able to reconcile and undertake all the necessary institutional and legislative reforms identified as needed during project implementation.  Instead, this project serves as catalyst of a more long-term approach for improved decision-making for the global environment through a system for knowledge management, institutional environmental evaluation, and integrating global environmental obligations into sector development plans at the sub-national level.  By strengthening the institutional and technical capacities, the replicability and extension of the project strategy through future pilot projects will be greatly enhanced and the learning curve greatly reduced.

The replication and extension of project activities is further strengthened by the large number of stakeholders that the project envisages engaging.  This includes working with NGOs and civil society associations that have a strong presence and extensive reach in local communities and/or are actively supporting related capacity development work.  Replication will also be supported by raising awareness of the project throughout Liberia.  This project will facilitate this through awareness-raising workshops with key stakeholders from the local and regional government, the private sector, academia, civil society and the media with the purpose of helping them to write articles about the environment.  The public service announcements on radio and television also serve the purpose of popularizing the project with the public in order to generate greater support and demand for replication activities.

The potential for scaling up project outcomes is significant given that demonstrative value of improved decision-making capacities for the global environment; specifically, lessons learned from applying the valuation tools and knowledge management system.  It is also conceivable that the improved knowledge management system could be a catalyst for Liberia to increasingly integrate global environmental indicators into the development decision making processes.  These and other opportunities for scaling up will be carefully considered on the basis of political, financial, socio-economic and environmental expediency during project implementation and not to inappropriately raise expectations.

2.  Stakeholders.  Will project design include the participation of relevant stakeholders from civil society and indigenous people?  (yes  /no ) If yes, identify key stakeholders and briefly describe how they will be engaged in project design/preparation.

The main project stakeholders are the government ministries and agencies who are responsible for key sectoral policies and legislation.  During the preparation of the project document, the complete list of ministries that will participate in the project will be confirmed.  Key national ministries and agencies that are likely to be involved are:

Ministry of Internal Affairs

Ministry of Lands, Mines & Energy

Ministry of Agriculture

Ministry of Transport

Ministry of Planning & Economic Affairs

Ministry of Rural Development

Ministry of Commerce and Industry

Ministry of Justice

Ministry of Education

Ministry of Gender and Development

Ministry of Public Work

Environmental Protection Agency

Stakeholders are not only present at the national level, but at the field level, i.e., sub-national and provincial levels.  A number of government bodies operating at both the national and local levels are responsible natural resource and environmental management, working with local community organizations and in some cases partnering with NGOs to undertake particular activities.  Other stakeholders include the private sector and academic institutions that are important to ensuring the long-term sustainability of the project, such as the University of Liberia.  The private sector is a particular important stakeholder to environmental issues.  This is of particular importance in that a high value capacity development activity is to mainstream global environmental obligations into development projects.  Other key stakeholders are those from the rural areas in that they have a major stake in the sustainable management of natural resources.  For the most part, these stakeholders are most at risk from land degradation as well as contributing to it through poor and unsustainable land management practices.  They are also contributing to the loss of important species through the degradation of their natural habitats.  Thus, the project will also support consultation, engagement and coordination of programmes with the number of national and international NGOs, academia, and with the private sector.

The project will be implemented in line with established Government of Liberia’s and UNDP procedures in Liberia.  The Environmental Protection Agency will take overall responsibility for implementation of the project, and for the project success.  It will establish the necessary planning and management mechanisms to oversee project inputs, activities and outputs.  The UNDP CO will support the Ministry as requested and as necessary.  The PPG process will be used to further define the management, coordination and consultation mechanisms.  Stakeholders will be involved in all stages of the project and will be involved in the validation activities, design of outputs and will be included in trainings.  Activities should be implemented to involve as many and as diverse stakeholders as possible.

3.  Gender Considerations.  Are gender considerations taken into account? (yes  /no ).  If yes, briefly describe how gender considerations will be mainstreamed into project preparation, taken into account the differences, needs, roles and priorities of men and women.

As in many countries, there are important gender inequalities in Liberia.  The project will make every effort to incorporate gender issues in the implementation.  Roles of men and women to participate in activities of the project will be equally assigned without any discrimination.  The project also includes several validation measures and gender sensitive indicators to help ensure equal access and benefits.  Notwithstanding these efforts, there is no budget allocation made to specifically address gender equality as gender inequality does not represent a barrier to meeting Rio Convention obligations.  The GEF Instrument also clearly states the criteria for the use of GEF financial resources, and these must be directed to activities that deliver global environmental benefits as defined under the three Rio Conventions for which the GEF is the financial mechanism.

Gender considerations for this project are informed by the 2014 report on Mainstreaming Gender at the GEF.  During the PPG phase, the design of project implementation arrangements will include the structuring of consultative and decision-making mechanisms that will mobilize the unique perspectives of Rio Convention implementation from the lens of gender priorities and differences.  Project preparation will apply UNDP guidelines that call for measuring the following indicators:

-	Total number of full-time project staff that are women

-	Total number of full-time project staff that are men

-	Total number of Project Board members that are women

-	Total number of Project Board members that are men

# 4.   Risks: Indicate risks, including climate change, potential social and environmental risks that might prevent the project objectives from being achieved, and, if possible, propose measures that address these risks to be further developed during the project design (table format acceptable).

One high risk is weak inter-institutional coordination.  Given the multi-faceted nature of the project, engagement of a multitude of stakeholders is required.  There is a real risk that coordination will be challenging.  To mitigate this risk, the project includes several approaches.  During the proposal formulation, consultations will be organized with key stakeholders to increase their understanding of the project and establish networks of collaboration.  Once implementation of the project begins, key stakeholders will meet on a regular basis through the Project Board so that they are aware of the progress of the project and contribute to the project.  Additionally, the project will have select activities to strengthen institutional mechanisms for improved coordination and collaboration.  These include items like negotiating best consultative processes and memoranda of agreements.

Related to these risks is an equally important risk: internal resistance to change.  This is a natural human condition and reflects people’s comfort with known policies and procedures.  However, the basis for this project is that these policies and procedures could be improved.  The activities of this project were strategically selected and designed to take into account these existing “business-as-usual” approaches, and to facilitate a process by they could be improved incrementally.  Most, if not all, of the activities under this project call for such incremental modifications to be made.  These will not be dictated by external expertise, but rather facilitated by experts and independent advisors so that stakeholders discuss and come to consensus agreements themselves.  This approach serves to strengthen the ownership and legitimacy of the decisions reached in these stakeholder consultations, workshops, or other project exercises.  For this reason, the project makes the implicit assumption that stakeholders will give the benefit of the doubt to the design of the project activities, be open to new and opposing perspectives, and actively participate in the project to negotiate issues and recommendations towards a consensus.

Another risk is inadequate funding.  There is a risk of having disrupted allocation of sufficient resources in implementation of the project.  The risk could lead to limited absorptive capacity to carry out the extensive mainstreaming .  Inadequate funding also risks institutional and organizational continuity as well as potential realization of opportunities to scale.  However, this risk is obviated by spreading roles and responsibilities to numerous partner ministries, each of which would take the lead, in consultation with the Environmental Protection Agency, as executing agency, and independent expert non-state organizations to provide additional technical expertise.  During the preparation phase of the project, careful consideration and negotiation with the respective line ministries will be undertaken to identify incentives and secure long-term commitment to active project participation and project deliverables The implementing agency and the project team will constantly seek for additional resources, mobilizing them from internal and external sources.

5.  Coordination.  Outline the coordination with other relevant GEF-financed and other initiatives.

There are a number of projects under implementation or planned that the proposed CCCD project would take into account to ensure the latter’s strategic value.  These include:

GEF Enhancing Resilience to Climate Change by Mainstreaming Adaption Concerns into Agricultural Sector Development in Liberia (Ending September 2015)

GEF/UNDP Strengthening Liberia’s capability to provide climate information and services to enhance climate resilient development and adaptation to climate change

This project is also in line with Liberia’s UNDAF 2013-2017.  The UN Country Team decided that the new UNDAF would also take into account the requirements of Delivering as One. Thus, in addition to the Strategic Framework and Results Matrix, the UNDAF is accompanied by a detailed Costed Action Plan. Together they constitute the One Programme. The four pillars of the One UN Programme are:

1. Peace, Security, Rule of Law

2. Sustainable Economic Transformation

3. Human Development

4. Inclusive Governance and Public Institutions

The UNDAF (One Programme) also aligns with Liberia’s National medium-term strategy, known as the Agenda for Transformation.  The Agenda for Transformation is based on five pillars:

1. Peace, Security and Rule of Law

2. Economic Transformation

3. Human Development

4. Governance and Public Institutions

5. Cross-cutting issues

The Agenda contains a specific goal to improve management of the environment to safeguard sustained economic development and growth. Specific actions called for in this agenda include: a) developing environmental quality standards and regulatory tools; b) harmonizing environmental laws and policies to ensure improved environmental management; c) undertake a gap analysis of sectoral environmental laws and policies; d) create environmental awareness; e) create training and education programs; f) develop a public awareness strategy and campaign; g) train professionals in effective environmental management;  strengthen environmental units in ministries through training and improved coordination; and h) develop a system to collect and disseminate environmental information/data.

The design and implementation of the proposed CCCD project would also take into account the development plans of other bilateral and multilateral donors in Liberia to ensure appropriate alignment as well as to leverage the necessary co-financing.

During the PPG phase, further discussions will be held with partner donor agencies, such as the World Bank and the Government of Norway,  that are supporting similar capacity building activities to determine the extent to which current and planned programmes and projects are complementary to the proposed CCCD project.  In 2015 Liberia accepted $150 million in aid from Norway.  This aid is ensure that by the year 2020 Liberia will stop legal logging, build up protection infrastructure, and make 30% or more of forest under protected area.  Additionally, the Government of Liberia has pledged to place a moratorium on new logging contracts, increase support and training for community based management of forests, and respect the rights of rural landowners, ensuring that decisions are made with their free, prior and informed consent.

A project board will be created to facilitate active participation in project activities from these stakeholders and that recommendations and agreements negotiated will be deemed legitimate by the respective institutions of the participating stakeholder.  During the PPG phase, these coordination arrangements will be further discussed and elaborated.  These donor consultations will also serve to confirm the amount of co-financing to support project activities.

6.  Consistency with National Priorities.  Is the project consistent with the National strategies and plans or reports and assessments under relevant conventions? (yes  /no ).  If yes, which ones and how:  NAPAs, NAPs, ASGM NAPs, MIAs, NBSAPs, NCs, TNAs, NCSAs, NIPs, PRSPs, NPFE, BURs, etc.

As a Rio Convention mainstreaming project, the proposed strategy sets out to meet barriers identified in Liberia’s 2009 NCSA.  Thus, the proposed strategy is consistent with the findings of the NCSA.  Liberia undertook its National Capacity Assessment (NCSA) in 2009 through a consultative process and participatory approach that involved numerous stakeholders from various sectors.   Through the inclusive and consultative process of the NCSA, stakeholders identified a number of areas that explain the difficulty in fulfilling the obligations of the Rio Conventions.

The project will assist the Government of Liberia to achieve the national priorities it has set in Liberia RISING 2030.  The aim of this is to transform Liberia through a new development strategy, which was launched in December 2012. The overall objective is to turn Liberia into a middle income country by 2030.

This project is designed to build the capacity of the agencies to engage effectively together in the series of concurrent national assessment and planning exercises, the subsequent development and implementation of policies and substantial programs, and the monitoring of results and strengthening of future planning and actions.  The agencies that will be included work in the following areas: forestry, agriculture, fisheries, biodiversity, water resources, eco-tourism, renewable energies, and environmental protection.

The project is also in line with Liberia’s NBSAP which aims to, as part of Liberia’s commitment to the Millennium Development Goals, and in line with the National Environmental Policy of Liberia, assist the people of Liberia to acknowledge and exercise responsible stewardship over biological resources to meet the needs of the present without endangering the ability of future generations to meet their own needs.  Some of the goals are to protect critical ecosystems, create biodiversity awareness, and increase commitment to sustainable use of biological diversity.

Liberia’s 2008 NAPA aligns with National Environmental Policy which calls for the sustainable management of Liberia’s environment and natural resources.  The NAPA also aims to establish synergies between adaptation and national development plans, such as the National Reconstruction and Development Plan, Millennium Development Goals, and the National Biodiversity and Strategy Action Plan.  The NAPA identifies key adaptation needs and list priority actions, such as enhancing resilience to increasing rainfall variability through agriculture, to address the needs.

Between 2010 and 2012, UNEP implemented a global project, entitled “Piloting Integrated Processes and Approaches to Facilitate National Reporting to Rio Conventions” that included Liberia as a beneficiary country.  This project focused on helping Liberia (among other countries) to better organize modalities for accessing and preparing their national reports.  Notwithstanding the capacities developed, a number of important capacities remained to be developed, such as the standardization of data collection and information analysis, improved coordination and collaboration to facilitate streamlined national reporting, and increased awareness and stakeholder engagement in the national reporting process.  During the project implementation, activities under component 4 will undertake an updated assessment of the systemic, institutional, and individual capacities that remain a priority to be developed in order to meet and sustain Rio Convention obligations.

7.  Knowledge Management.  Outline the knowledge management approach for the project, including, if any, plans for the project to learn from other relevant projects and initiatives, to assess and document in a user-friendly form, and share these experiences and expertise with relevant stakeholders.

This project is part of capacity building in the country that encourages regional cooperation and knowledge and information exchanges.  Partnerships and collaboration will also catalyze the transfer of knowledge and competencies among actors and stakeholders.  Lessons learned from other projects will be included, as appropriate (for example, in the training programmes and the knowledge management system).  This project also contains specific activities to increase the use and sharing of knowledge such as brochures, youth engagement, and learning-by-doing training to strengthen individual and institutional capacities to use knowledge in decision making.  The project also contains an entire component on strengthening a knowledge management system that aims to catalyze the application of best practices and innovations for the global environment. The project’s approach to knowledge management is consistent with the International Resource Panel Report on Policy Coherence of the Sustainable Development Goals which emphasizes the need for developing widespread awareness and creating and disseminating decision support tools.

part iii:  approval/endorsement by gef operational focal point(s) and GEF agency(ies)

A.  Record of Endorsement of GEF Operational Focal Point (s) on Behalf of the Government(s):  
      (Please attach the Operational Focal Point endorsement letter(s) with this template.  For SGP, use this SGP OFP 
      endorsement letter).

| Name | Position | Ministry | Date (MM/dd/yyyy) |
| --- | --- | --- | --- |
| Hon.Anyaa Vohiri | Executive Director of EPA and GEF Operational Focal Point | Environmental protection Agency | 02/03/2016 |

B.  GEF Agency(ies) Certification

This request has been prepared in accordance with GEF policies and procedures and meets the GEF criteria for project identification and preparation under GEF-6.

| Agency Coordinator, Agency name | Signature | Date (MM/dd/yyyy) | Project Contact Person | Telephone | Email |
| --- | --- | --- | --- | --- | --- |
| Adriana Dinu Executive Coordinator and Director UNDP-GEF |  | 02/09/2016 | Tom Twining-Ward UNDP Green-LECDRS | +90 8502 882 612 | tom.twining-ward@undp.org |

GEF_PIF_60

C.  Additional GEF Project Agency Certification (Applicable Only to newly accredited GEF Project Agencies)

For newly accredited GEF Project Agencies, please download and fill up the required GEF Project Agency Certification of Ceiling Information Template to be attached as an annex to the PIF.

Project ID number will be assigned by GEFSEC and to be entered by Agency in subsequent document submissions.

When completing Table A, refer to the excerpts on GEF 6 Results Frameworks for GETF, LDCF and SCCF.

Financing type can be either investment or technical assistance.

For GEF Project Financing up to $2 million, PMC could be up to10% of the subtotal;  above $2 million, PMC could be up to 5% of the subtotal.  PMC should be charged proportionately to focal areas based on focal area project financing amount in Table D below.

PPG requested amount is determined by the size of the GEF Project Financing (PF) as follows: Up to $100k for PF up to $3 mil; $150k for PF up to $6 mil; $200k for PF up to $10 mil; and $300k for PF above $10m.  On an exceptional basis, PPG amount may differ upon detailed discussion and justification with the GEFSEC.

PPG fee percentage follows the percentage of the Agency fee over the GEF Project Financing amount requested.

Provide those indicator values in this table to the extent applicable to your proposed project.  Progress in programming against these targets for the projects per the Corporate Results Framework in the GEF-6 Programming Directions, will be aggregated and reported during mid-term and at the conclusion of the replenishment period.  There is no need to complete this table for climate adaptation projects financed solely through LDCF and/or SCCF.

For regional and/or global projects in which participating countries are identified, OFP endorsement letters from these countries are required 
  even though there may not be a STAR allocation associated with the project.

GEF policies encompass all managed trust funds, namely: GEFTF, LDCF, and SCCF