Project Identification Form (PIF)

Project Type:

Type of Trust Fund:

PART I: Project Identification

| Project Title: | Shire Natural Ecosystems Management Project |  |  |
| --- | --- | --- | --- |
| Country(ies): | Malawi | GEF Project ID: | 4625 |
| GEF Agency(ies): |  | GEF Agency Project ID: | P117617 |
| Other Executing Partner(s): | Government of Malawi | Submission Date: | 2011-09-13 |
| GEF Focal Area (s): |  | Project Duration (Months) | 66 |
| Name of parent program (if applicable): - For SFM/REDD+ | N/A | Agency Fee ($): | 657,800 |

A.  Focal AREA STRATEGY Framework:

| ### Focal Area Objectives | ### Expected FA Outcomes | ### Expected FA Outputs | ### Trust Fund | ### Indicative ### Grant Amount ### ($) | ### Indicative Co-financing ### ($) |
| --- | --- | --- | --- | --- | --- |
|  | 1.1: Improved management effectiveness of existing protected areas. | 100,000 ha of protected areas under improved management |  | 2,727,000 | 7,265,000 |
|  | 1.2: Improved agricultural management. | 40,000 ha under under effective land and water management practices / under agro-forestry tree cover |  | 0 | 23,484,000 |
|  | 3.1: Enhanced enabling environments between sectors in support of SLWM. | Government agencies collaborating on SLWM in the Shire Basin through establishment of Basin management plan and structures based on comprehensive land cover and hydrological information |  | 1,082,000 | 15,134,000 |
|  | 1.2: Good management practices developed and applied in existing forests. | 37,000 ha of forest land under sustainable community-based management |  | 1,269,000 | 7,400,000 |
|  | 1.2: Reduced vulnerability to climate change (lives and damage saved through integrated flood management) | 3 types of integrated flood management measures (community preparedness, small-scale infrastructure, wetland management) introduced in lower Shire |  | 1,500,000 | 9,935,000 |
|  | Others |  |  |  |  |
| Sub-Total |  |  |  | 6,578,000 | 63,218,000 |
| Project Management Cost |  |  |  | 0 | 5,096,000 |
| Total Project Cost |  |  |  | 6,578,000 | 68,314,000 |

- Project Framework

| ### Project Objective: to develop a strategic planning and development framework for the Shire River Basin and support targeted investments to improve land and water resources management, and associated ecological services and livelihoods in the Basin. |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| ### Project Component | ### Grant Type | ### Expected Outcomes | ### Expected Outputs | ### Trust Fund |  | ### Indicative ### Grant Amount ($) | ### Indicative Cofinancing ### ($) |
| Component A: Shire Basin Planning A.1: Develop Shire Basin Plan |  | Natural habitats knowledge base for the Shire basin greatly improved Natural ecosystem services in Shire basin evaluated Natural ecosystem management priorities included within basin planning | Basin-wide maps of ecosystems and biodiversity [GEF funded] Site-level biodiversity survey reports for focal areas [GEF funded] Economic analysis of ecosystem services, including incorporation of natural habitats in to hydrological modelling Shire basin management framework and policies with integrated natural habitat management priorities Policy proposals for management of charcoal industry |  |  | 700,000 | 8,161,000 |
| A.2: Build institutional capacity for coordinated basin management |  | Capacity of Shire Basin management agencies strengthened | Ecological/biodiversity databases and partnerships with external reaserch institutes established and maintained within forest and ecological research institutes[GEF funded] Enhanced capacity of other Basin management agencies to understand and integrate biodiversity management |  |  | 382,000 | 6,973,000 |
| Component B: Catchment Management B.1: Build institutional capacity for sub-catchment planning and monitoring |  | Capacity for participatory watershed planning strengthened Improved coordination of lower Shire protected areas cluster | 40 community microwatershed management plans prepared Coordination structure and management framework established |  |  | 0 | 10,645,000 |
| B.2: Rehabilitate targeted sub-catchments |  | Enhanced hydrological function within 40 microwatersheds | Improved SLWM technologies applied to 40,000 ha |  |  | 0 | 22,484,000 |
| B.3: Alternative rural livelihoods |  | Low impact and nature-based livelihoods provide incentives to reduce unsustainable exploitation of protected areas | Alternative livelihoods grants provided to 20 communities surrounding protected areas |  |  | 0 | 3,020,000 |
| B.4: Sustainable management of lower shire forests and wetlands B4.1 Investments for sustainable management of Lengwe National Park |  | Improved Park infrastructure producing higher revenues and more effective management | Lengwe management plan updated, including feasibility study for concession management [GEF funded] Provision of tourism infrastructure, water points, and patrolling & monitoring equipment [GEF funded] |  |  | 2,727,000 | 1,000,000 |
| B4.2: Community-based forest management in Mtandwe & Thanbani Forest Reserves |  | Community-based sustainable forest management established in two Forest Reserves following national model piloted by EU forestry project | Commuity-based mangement systems operating in 20 group villages [GEF funded] 5 sustainable charcoal production licenses granted [GEF funded] |  |  | 1,269,000 | 1,000,000 |
| Component C: Water Related Infrastructure C.2: Flood Management |  | Community adaptation capacity enhanced in lower Shire Flood Basin Physical flood mitigation infrastructure in place Physical infrastructure complemented by ecological flood mitigation and resilient livelihoods resrouce base through co-management of 120,000ha Elephant Marshes | "Last mile" flood warning and community response systems established covering 40,000 households Small-scale infrastructure (polders, gabions, cuverts, protective vegetation) established along 200km stretch of Shire River Elephant Marshes management strategy & pilot community management activities in 10 communities completed [LDCF funded] |  |  | 1,500,000 | 9,935,000 |
| Sub-Total |  |  |  |  |  | 6,578,000 | 63,218,000 |
| Project Management Cost |  |  |  |  |  | 0 | 5,096,000 |
| Total Project Costs |  |  |  |  |  | 6,578,000 | 68,314,000 |

- Indicative Co-financing for the project by source and by name if available, ($)

| Sources of Cofinancing | Name of Cofinancier | Type of Cofinancing | Amount ($) |
| --- | --- | --- | --- |
|  | World Bank (IDA) |  | 62,314,000 |
|  | Government of Malawi |  | 5,000,000 |
|  | Local communities |  | 1,000,000 |
| Total Cofinancing |  |  | 68,314,000 |

- GEF/LDCF/SCCF  Resources Requested by Agency, Focal Area and Country1

| GEF Agency | Type of Trust Fund | Focal Area | Country Name/Global | Grant Amount (a) | Agency Fee (b)2 | Total c=a+b |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Malawi | 2,727,000 | 272,700 | 2,999,700 |
|  |  |  | Malawi | 1,082,000 | 108,200 | 1,190,200 |
|  |  |  | Malawi | 1,269,000 | 126,900 | 1,395,900 |
|  |  |  | Malawi | 1,500,000 | 150,000 | 1,650,000 |
|  |  |  |  |  |  | 0 |
|  |  |  |  |  |  | 0 |
|  |  |  |  |  |  | 0 |
|  |  |  |  |  |  | 0 |
|  |  |  |  |  |  | 0 |
|  |  |  |  |  |  | 0 |
| Total Grant Resources |  |  |  | 6,578,000 | 657,800 | 7,235,800 |

1  In case of a single focal area, single country, single GEF Agency project, and single trust fund project, no need to provide 
    information for this table

2   Please indicate fees related to this project.

part ii:  project JustiFication

- Description of the consistency of the project with:

A.1.1   the GEF focal area strategies:

The project will mainstream natural habitat and biodiversity management within the Shire River Basin Management Project (SRBMP), a $100+ million IDA credit, which will form the first 5-year stage of a larger Adjustable Programmatic Loan. GEF-funded activities within the project will strengthen knowledge on the natural ecosystems of the basin, in order to allow this to be fully integrated into basin planning and management activities, and will strengthen the management of remaining natural habitat blocks in a cluster of National Parks, Wildlife Reserves, Forest Reserves and a wetland complex in the lower Shire Basin. Alongside the parent project, this comprises a comprehensive catchment restoration approach that combines protection of natural habitats with improved land management in production landscapes. The project is therefore entirely consistent with: - the Biodiversity Focal Area strategy (BD#1) in that it will directly improve the sustainability of protected areas , forest reserves and floodplain wetlands covering roughly 2,460 km2 (2.46 million hectares) and much of the remaining lowland forest and wetland habitats in the lower Shire, and globally significant biodiversity; - the Land Degradation Focal Area strategy (LD#3) through supporting a cross-sectoral basin planning and management approach that integrates management of natural habitat blocks and responsible agencies including the Department of Parks and Wildlife and the Department of Forestry, and (LD#1) through the substantial investments being made in improved land and water management within agricultural landscapes within the parent project; and - the Sustainable Forest Management Focal Area strategy (SFM#1) through establishing community-based management within Forest Reserves in the lower Shire, following a nationally developed model. The project will also mainstream biodiversity conservation into landscape planning at both the basin and PA cluster levels.

A.1.2.   For projects funded from LDCF/SCCF:  the LDCF/SCCF eligibility criteria and               priorities:

Many of the project activities are consistent with national adaptation priorities, including reforestation, increasing agricultural productivity and resilience through SLWM technologies, strengthening hydromet monitoring systems and upgrading water infrastructure for increased storage and flow regulation capacity. More specifically, LDCF funds will co-finance investments in integrated community flood resilience in the lower Shire floodplain through a combination of “last mile” connectivity with flood warning systems, capacity building for community flood response, small scale infrastructure and co-management of the 120,000ha Elephant Marshes. These activities are fully consistent with the LDCF (CCA#1) objective through reducing vulnerability to extreme climate events. Malawi is eligible for LDCF funding, and has developed a NAPA (see below).

A.2.   national strategies and plans or reports and assessments under relevant conventions, if applicable, i.e. NAPAS, NAPs, NBSAPs, national communications, TNAs, NIPs, PRSPs, NPFE, etc.:

The constitution of Malawi requires the State to conserve and enhance biological diversity in the country, prevent the degradation of the environment and accord full recognition of the rights of the future generations by means of environmental protection and the achievement of sustainable development. The Environmental Affairs Department of the Ministry of Energy, Mines and Natural Resources published a National Biodiversity Strategy and Action Plan in October 2006. This sets out five strategic priorities, three of which would be addressed by this project: a) Enhancement of protected areas management, b) Enhancing the governance of biodiversity, and c) Strengthening infrastructure and human capacity for biodiversity conservation. The 1997 Forestry Act recognizes the need to promote community-based management of forest resources, including co-management of forest reserves. A locally appropriate model is elaborated within the 2005 Standards and Guidelines for Participatory Forestry in Malawi, which have since been applied through a number of pilots. In particular, the EU Improved Forest Management for Sustainable Livelihoods Program has engaged communities in active management of a number of forest reserves, and is currently beginning a second phase. Malawi’s NAPA identified 5 key areas for action – (i) community resilience through sustainable rural livelihoods, (ii) improving agricultural production under erratic rains and changing climatic conditions, (iii) restoring forests in the Upper and Lower Shire Valleys and other catchments to reduce siltation and associated water flow problems, (iv) improving preparedness to cope with droughts and floods, and (v) climate monitoring to enhance Malawi’s early warning capability and decision making and sustainable utilization of Lake Malawi and lakeshore areas resources. The SRBMP will contribute to all five of these priority areas: to (i), (ii) & (iii) through community land management and agro-forestry activities under Component B; to (iv) through flood preparedness activities under Component C; and to (v) through upgrading hydromet systems under Component A (see below for more details on structure of components). The LDCF-financed activities will address NAPA priority areas (i) and (v) by enhancing flood protection measures under subcomponent C2 with co-management of important wetlands in the lower Shire, enhancing natural flood mitigation services and resilient livelihoods of some of Malawi’s most climate-vulnerable people. Since the Malawi NAPA was produced in 2006, the importance of flood management has been reinforced by recurrent flooding in the lower Shire. The multi-donor supported National Program for Management Climate Change in Malawi is refining and detailing adaptation priorities, with considerable emphasis on the assessment options for improving climate resilience through improved land use.

- Project Overview:
B.1. Describe the baseline project and the problem that it seeks to  address:

The Shire River Basin Management Project (SRBMP) would: (a) strengthen the institutional capacities and mechanisms for Shire Basin monitoring, planning, management and decision support systems; (b) invest in water related infrastructure that sustainably improves water resources management and development; (c) reduce erosion in priority catchments and sedimentation and flooding downstream, while enhancing agricultural productivity and improving livelihoods; and (d) improve flood management in the Lower Shire and provide community level adaptation and mitigation support. The objective of GEF support will be to strengthen sustainable management of remaining natural systems as part of the basin planning and catchment management approach in the Shire Valley to conserve globally important biodiversity and protect forests and wetlands essential for livelihoods, climate resilience and economic development. Project components: Component A: Shire Basin Planning will support (A1) basin survey and planning, (A2) institutional capacity development of various basin management agencies, (A3) improved hydrological monitoring systems, and (A4) overall project management. Component B: Catchment Management will include (B1) development of sub-catchment management plans, guidelines and monitoring systems, (B2) SLWM investments in targeted sub-catchments, and (B3) technical assistance and community grants for more sustainable livelihood activities. Component C: New Water Investments will include (C1) upgrading of the Kamuzu Barrage for improved regulation of flows in the Shire River, (C2) community flood management in the lower Shire floodplain, and (C3) identification of major new water infrastructure investments. The Shire River originates from the southern end of Lake Malawi and flows south into the Zambezi shortly beyond the boundary of the country. The Shire Basin occupies most the southern half of the country and delivers 95% of hydroelectric production (from cataracts in the middle Shire), supports extensive smallholder agriculture and the country’s largest sugar and tea estates. The population of the Shire basin is growing rapidly – from less than 4 million in the mid 1960s to nearly 13 million by 2008. The basin’s natural resources have been rapidly depleted, and today, most areas outside of wildlife and forest reserves have been deforested, and even some reserves have been extensively denuded. Soil fertility has decreased, and sedimentation and eutrophication from agricultural run-off has reduced effective hydropower generation capacity, and disrupted fisheries and irrigation systems. Hydrological flows have also become more erratic, and the basin has experienced several severe drought and flooding episodes within the last 20 years. The SRBMP has a duration of five and a half years and is organized in three components: (i) Shire Basin Planning, which would strengthen the institutional capacities and mechanisms for Shire Basin monitoring, planning, management and decision support systems; (ii) Catchment Management, which would reduce erosion in priority catchments and sedimentation and flooding downstream, while enhancing agricultural productivity and improving livelihoods; and (iii) Water Related Infrastructure, which would invest in water related infrastructure that sustainably improves water resources management and development, and improves flood management in the Lower Shire, providing community level adaptation and mitigation support. Of the total value of the IDA credit, approximately $62m is expected to be utilized as co-financing of investments and technical assistance for the GEF-sponsored activities.

B. 2. incremental /Additional cost reasoning:

The incremental GEF- and LDCF-funded activities would provide for the management of ecological infrastructure (in particular natural ecosystems and biodiversity) to be fully mainstreamed within the SRBMP. High rural population densities and almost universal reliance on wood fuels have placed high pressure on natural resources in the Shire Basin. Larger wildlife and extensive areas of natural terrestrial habitat have virtually disappeared outside of reserves, even some forest reserves have been effectively cleared, and most remaining forest and wildlife reserves are affected by agricultural encroachment. Extensive wetlands in the lower Shire attenuate the floods that affect the area, and have historically provided rich fish and bird resources for the local population, but these areas too are under pressure from environmental and anthropogenic changes to hydrological flows, and increasing pressure on land and biological resources. Change to the physical environment of the Shire Basin also accentuate vulnerability to climate change through erosion of the resource base for climate-resilient livelihoods and of the buffering of extreme weather events. In particular, the population within the lower Shire Floodplain is perhaps the most climate-vulnerable in Malawi, having been subjected to successive floods and droughts. Their resilience is undermined both by upstream changes to hydrological and sediment flows, and by degradation of local floodplain resources and habitats. Natural ecosystems are critical to the overall functioning of the Shire Basin. In all cases, GEF financing will support incremental natural habitat knowledge or field management activities that will complement, enhance and leverage baseline investments in river basin management, laying the foundation for additional IDA investments in ecological infrastructure during the second phase of the APL. Incremental activities would: (i) address the current dearth of precise and systematic information on the ecological assets of the Shire Basin, allowing ecological infrastructure to be fully incorporated into basin-wide hydrological modeling, economic analysis and management planning; and (ii) provide proof of concept by investing in sustainable management of a number of habitat areas (especially Lengwe National Park, Thanbani & Mtandwe Forest Reserves and a the Elephant Marshes wetland system – see fig. 1 above) which combine key biodiversity and watershed functions. Fig 1. Map of lower Shire, showing natural habitat blocks targeted under GEF activities. Component A of the SRBMP: Shire Basin Planning. Incremental GEF resources will provide for systematic natural habitat and biodiversity surveys and mapping under subcomponent A1, which will allow the watershed services flowing from ecological infrastructure to be properly evaluated and reflected in the IDA-funded hydrological modeling, economic analyses and basin planning under that subcomponent. The Ministry of Irrigation and Water Development are highly receptive to integrating these elements, but currently lack the information base in order to do so. This will recognize and integrate the role of natural habitat management agencies (particularly the Department of National Parks and Wildlife and the Department of Forestry) within a comprehensive basin management program. GEF resources under subcomponent A2 will also extend capacity building to technical and academic bodies, such as the National Herbarium and the Forest Research Institute of Malawi, which will provide for long-term management and development of the ecological knowledge base for the Shire Basin. Project management costs will be entirely covered from IDA resources. Component B: Catchment Management. Incremental GEF resources will support a fourth subcomponent (B4) which will strengthen management of remaining natural habitat blocks in the lower Shire, including planning and infrastructure investments in Lengwe National Park, and establishment of community forest management in two Thanbani and Mtandwe Forest Reserves according to a proven co-management model already endorsed and field-tested by the Department of Forestry. These activities will form part of an integrated landscape management approach alongside the IDA-funded SLWM investments in predominantly agricultural lands under B2. The GEF investments will leverage additional component B IDA resources in support of cluster-based management planning for lower Shire wildlife and forest reserves from B1, and support for low impact or nature-based livelihood activities around the target reserves from B3. Component C: New Water Investments. GEF resources from the LDCF will establish participatory management planning for the 1200km2 Elephant Marshes, including pilot community resource management activities. This will pave the way for further investments, not least through the second phase SRBMP and potentially gazettement of the wetlands within the Malawian protected areas system. The Marshes occupy a significant proportion of the lower Shire floodplain, and are important both for their hydrological function within the floodplain in absorbing floodwaters, and also for their potential for supporting enhanced climate-resilient livelihoods in the form of fisheries and tourism. Management of the wetlands will complement IDA-funded community preparedness and protective infrastructure investments within subcomponent C2 to form a comprehensive flood resilience program that integrates community preparedness, physical and ecological infrastructure investments and enhancement of natural-resource dependent livelihoods. The GEF investments will leverage additional IDA resources from subcomponent B3 in support of complementary livelihood activities around the Marshes. Component A will be implemented by the Ministry of Irrigation and Water Resources, which has overall management responsibility for the project, but with technical input and coordination of all line agencies involved in river basin management. Component B & C activities will be implemented by agencies with mandates covering the specific project sites. For the GEF-financed activities, this will particularly involve the Department of National Parks and Wildlife, and the Department of Forestry. More detailed implementation arrangements will be specified during preparation. GEF investments will significantly contribute to the river basin management objectives of the SRBMP and therefore hydrological regulation of an important branch of the Zambezi river system. They will provide additional global environmental benefits in the form of conservation of globally significant biodiversity, development of a promising and largely indigenous model for community management of East African forests, and maintenance of substantial carbon stocks, particularly the intact natural habitats of the cluster of sites that would be targeted in the lower Shire – comprising 2,460 km2 (2.46 million hectares) of carbon-rich forests and wetlands which might otherwise be lost or degraded through land clearance, encroachment and erosion. The GEF investments represent particular value for money in that they will mainstream an ecological infrastructure approach within a much larger project, leveraging phase 1 project resources and laying the groundwork for additional support under phase 2 of the intended APL. Project M&E will include key performance indicators on the changes in vegetation cover, hydrological parameters, as well as mandatory GEF tracking tools, such as the METT.

B.3. 	Describe the socioeconomic benefits to be delivered by the Project at the national and local levels, including consideration of gender dimensions, and how these will support the achievement of global environment benefits (GEF Trust Fund) or adaptation benefits (LDCF/SCCF). As a background information, read Mainstreaming Gender at the GEF.":

Primary project beneficiaries will be the rural populations living in and around the project sites, both those benefiting from SLWM investments in agricultural and agro-forestry systems targeted under subcomponent B2, and those living in and around the natural habitat blocks targeted under subcomponents B4 and C2, who will benefit from the maintenance of the natural resource base and ecological services, and ultimately from related livelihood opportunities based on eco-tourism, fisheries, sustainable charcoal, etc. Shire floodplain inhabitants will additionally gain from increased flood protection. Ultimately, more sustainable natural resource-based industries will benefit the entire population of the Shire Basin, if not the country, through increased production of crops, wood fuels, fish and hydropower, and increased tourism. At the basin level, the project would identify areas of natural habitats scattered within broader productive landscapes where smallholder agriculture predominates. These remnant areas still deliver ‘free’ environmental services for local communities, including watershed protection, provision of forest products and clean water and they are also a key source of biomass energy for local populations - over 90% of household energy comes from biomass fuels. Firewood and charcoal trade to urban centers generates significant revenue flows and demand is growing significantly. Wetland areas also contribute to local livelihoods through provision of fish and other wetland products, and attenuation of flooding. The project would seek to identify appropriate management prescriptions for these natural habitat areas - with the goal of sustaining and enhancing the environmental services they provide – both locally and globally, and by engaging local communities in their sustainable management. For example, at Mtandwe and Thanbani Forest Reserves there is strong local demand to end current and ineffective state management of these forest blocks and replace this with community-based forest management using experience from recent and successful pilots elsewhere in Malawi. At cluster site level in the lower Shire, the project will seek to increase revenues on a sustainable basis so that Lengwe National Park authorities can implement plans to invest in local communities and contribute to local socio-economic development in the longer term. Park authorities also want to develop ways of better engaging local communities in park management, including through enforcement efforts, tourism guiding, habitat management and through construction and maintenance of trails, check dams and other infrastructure. Taken together, these approaches should contribute to improved relationships between Park authorities and local communities, will introduce new livelihood options for local residents around the Park boundary and ultimately should reduce pressures on the Park’s natural resources. The project will also focus on community-based planning in and around the Elephant marshes, including substantial investments in sustainable livelihoods – to diversify the range of economic activities available, especially during prolonged dry seasons. As appropriate, community livelihood development funds from the parent project can be mobilized to support livelihood options that would either reduce pressure on natural resources or increase the value of sustainable resource management. Women play a key role in management of a number of natural resources, including water and fuel wood collection and transport. Improved management of these resources will therefore be particularly beneficial to women, and the GEF activities will follow gender-sensitive approaches developed under the main project.

B.4	Indicate risks, including climate change risks that might prevent the project objectives from being achieved, and if possible, propose measures that address these risks to be further developed during the project design:

Institutional capacity and coordination – capacity to undertake surveys and collate and manage information on the Basin’s natural habitats and biodiversity is currently limited. The project will specifically invest in capacity development of those key institutions that have a mandate for biodiversity and broader environmental management in the Shire River Basin. This will enable these organizations to engage more effectively in the proposed Shire River Basin management organization and in planning and implementation work on landscape restoration and management. Key institutions are specified in Section B5 (below). The proposed Shire River basin management plan and organization should also help improve institutional coordination at basin level. Economic risks – any sustained reductions in tourist arrivals and/or international donor budget support to Malawi may constrain the ability of GoM to sustain current levels of public financing for national parks and forest reserves. This could limit engagement of state authorities and reduce public investment in these areas. Revenues from tourism comprise a substantial component of financing for protected areas elsewhere, e.g. Liwonde national Park and Majete Wildlife Reserve. There is considerable scope for increasing revenues from tourism at Lengwe National Park and this will need to be realized if the park’s finances are to be placed on a more sustainable footing. Environmental risks – the Kamuzu barrage and hydro development in the middle Shire cataracts means that hydrological flows along the Shire are already highly managed. Growing demand for power and irrigation may reduce low and mean flows in the lower Shire and could therefore impact further on the Elephant marshes. Proposed interventions in the Elephant marshes will include studies that will improve understanding of the hydrology of the system and its impact on the ecology and hydro-morphology of the marshes. Subsequent community-based planning will be responsive to these findings. The most likely scenarios for climate change suggest warmer mean and maximum temperatures and more variable rainfall. This could contribute to more frequent forest fires - especially in the dry miombo woodlands of Lengwe National Park, Thanbani and Mtandwe Forest Reserves with resultant impacts on forest quality and biodiversity. Dry season farming on islands within the marshes is also more extensive during prolonged dry seasons as farmers search for soil moisture. Investments in small-scale irrigation and other options for livelihood diversification should help address this issue whilst also providing alternative options for farmers.

B.5. Identify key stakeholders involved in the project including the private sector, civil society organizations, local and indigenous communities, and their respective roles, as applicable:

At national level, the SRBMP will be implemented by the Ministry of Irrigation and Water Management – the agency with state management responsibility for water resources. They will coordinate closely with the Environmental Affairs Department (EAD) of the Ministry of Natural Resources, Energy and Environment which has overall responsibility for environment and biodiversity policy and is also the GEF focal point. The Forest Department has responsibility for forest reserves –including both natural forests and plantations. The Department of Disaster Management Affairs is mandated with coordinating disaster response and resilience, but must work with other agencies on the ground in areas such as infrastructure and natural resource management. The Department of National Parks and Wildlife (DNPW) has responsibility for protected areas (including national parks and wildlife reserves) and also has responsibility for implementing the Convention on Wetlands of International Importance (the Ramsar Convention). For this reason, DNPW is expected to have a major role in managing sub-components of GEF support for sites in the lower Shire, including Lengwe National Park and the Elephant Marshes. DNPW’s regional presence and mandate will also allow them to facilitate cross-support across different sites in the lower Shire – including Mwabvi and Majete protected areas, for example on training, use of spatial imagery, marketing and deployment of equipment. Institutions with a mandate for research and inventory - and with potential for hosting knowledge centers, include the Forest Resources Institute of Malawi (FRIM) and the National Botanical Gardens and Herbarium. There are also a number of relevant and capable non-governmental organizations working on sustainable management of biodiversity both nationally and within the Shire basin. These include the Mulanje Mountain Conservation Trust, LEAD International, the World Fish Center and the Wildlife Conservation Society of Malawi (the BirdLife International partner in Malawi). The main stakeholders at local level will include communities that depend on forest and wetland resources in and around the two forest reserves (Thanbani and Mtandwe), Lengwe National Park and the Elephant marshes. These communities are mostly smallholder farmers with high dependency on natural resources and with limited access to basic services. Forest users around Thanbani and Mtandwe will benefit from local participation and benefit sharing arrangements from these forest reserves and it is anticipated that this will include licensed charcoal production. This should create an incentive for investment in sustainable and more efficient charcoal production and will also enable charcoal producers and local forest management groups to retain the share of revenues from charcoal that would normally be lost through informal payments to enforcement agencies. It is envisaged that Mwabvi and Majete Wildife Reserves (the latter already succeeding in attracting increasing numbers of tourists) will benefit indirectly since the project should diversify the options available for wildlife-based tourism in the lower Shire Valley. Shire floodplain communities around the Elephant Marshes are particularly vulnerable due to the impact of recurrent floods. A number of NGOs are already working in this area, providing largely palliative support in the face of flood impacts. The project should help to direct this effort towards longer term solutions based on flood and livelihood resilience. Private sector investors in wildlife-based tourism, including tour operators in Blantyre and concession holders such as African Parks (who manage Majete Wildlife Reserve adjacent to Lengwe) see this as an opportunity and are expected to contribute guidance and expertise. The approach in Lengwe will be to provide the basic tourist infrastructure (e.g. visitor information center, access tracks, water points) that will attract co-investment from the private sector in accommodation and tour facilities, and potentially even pave the way for a park management concession, as has been successfully implemented at Majete. Private sector partners should also provide means through which Lengwe National Park and the Elephant Marshes can be better marketed to regional, national and international visitors.

B.6. Outline the coordination with other related initiatives:

Component 1 of the SRBMP will support the establishment of a basin management entity on which the key central line ministries will be represented, and which will engage other key stakeholders, including traditional authorities, local authorities at district and regional level and civil society organizations. The precise design of this entity will be detailed during early project implementation, but its duties will include ensuring alignment of government policies and plans with overarching Shire Basin management plans, and complementarity of donor-supported activities, through establishing more systematic site-selection protocols and sharing of lessons. There are several current and planned rural livelihoods and environmental management projects within the Shire Basin, including the UNDP Sustainable Land Management Project, the FAO Food Security and Sustainable Rural Livelihoods Project, the EU Improved Forest Management for Sustainable Livelihoods Program, the JICA Community Vitalization and Afforestation project, and planned watershed management investments in the upper Shire by the Millennium Challenge Account. A coordination structure for the lower Shire protected areas (wildlife and forest reserves) cluster will also be established to improve collaboration between the Department of Parks and Wildlife and the Department of Forestry, as well as with NGO and private sector entities involved in protected areas management, such as the Mulanje Mountain Conservation Trust, the Malawi Environmental Endowment Trust, and African Parks. A number of related activities focus more specifically on climate change within Malawi. Management planning for the Elephant Marshes will learn lessons from the ongoing Lake Chilwa Basin Climate Change Adaptation Program, which covers the only part of southern Malawi outside of the Shire Basin, and includes community management of extensive wetland resources. DfID and IrishAID are developing a community climate resilience fund, which will be national and demand-driven in scope, but (given the population’s vulnerability) is expected to focus largely on the lower Shire Floodplain, and should help to align the efforts of locally active NGOs with the longer-term community resilience approach being pursued under the SRBMP. The project will also coordinate with the upcoming Climate Adaptation for Rural Livelihoods and Agriculture, financed through the AfDB. More broadly, the preparation of the SRBMP is closely coordinated with assessment of land use options and strengthening of the climate information base under the National Program for Management Climate Change in Malawi (CCP). The CCP (along with UNDP’s related activities under the Africa Adaptation Program) is coordinating key climate agencies (primarily the Ministries of Development Planning & Cooperation, Natural Resources, Energy & Environment, and Irrigation and Water Development) and develop partners (UNDP, WB, FAO, DfID, Norway) to identify more detailed and actionable adaption and mitigation investment, and potentially lay the basis for a climate SWAp. Coordination will ensure that the SRBMP and LDCF-funded activities responds to the most up-to-date national adaptation priorities. The coordination of hitherto piecemeal land, natural resources and biodiversity management projects into an integrated basin management approach is a key outcome of the SRBMP, and critical to the subsequent scale-up of catchment management to effect significant impact on the hydrology of the Shire. Before the long-term basin management entity is established, coordination between agencies and with other projects and programs will be the responsibility of the project coordination unit in the Ministry of Irrigation and Water Development, supported by the World Bank task team. The locally-based Bank team will also ensure synergy with other IDA irrigation and community investments in southern Malawi, e.g. ensuring that any irrigation investments in the lower Shire provide an alternative to agricultural expansion within the Elephant Marshes, without causing undue disruption to their hydrology. The same team is also working on related climate change and disaster risk management programs in Malawi.

C.   describe the GEF agency’s comparative advantage to implement this project:

GEF-funded activities will be managed by the World Bank’s Africa Environment and Natural Resources Management Unit which has extensive and long standing experience in managing biodiversity and river basin management projects in Sub-Saharan Africa, including a large GEF portfolio. The Unit already manages to GEF-funded protected areas projects in Malawi at Nyika and Nkhotkhota, and also completed a successful GEF project to support management of the Mulanje Massif within the Shire Basin, and is developing a similar integrated land, water and biodiversity approach to the management of the Lake Malawi basin, which is likely to involve blended GEF funding. Overall, the World Bank has extensive project experience in the broad range of fields – governance, infrastructure, agriculture, water resources, land use planning, forestry and rural energy – needed for large-scale integrated river basin management projects, and also in the mainstreaming of biodiversity within larger development programs. The World Bank has an active relationship with both GoM agencies and local civil society organizations working in various aspects of natural resources management, and can also provide links to related Bank activities in climate change and disaster risk management. The Bank’s convening power; it’s unique ability to execute technically complex and politically delicate programs; it’s high fiduciary standards; and it’s international visibility and reputation all make it the only international financial institution able to assume the role as implementing agency for this project.

C.1   Indicate the co-financing amount the GEF agency is bringing to the project:

The IDA credit for the “Shire River Basin Management Project” is estimated to be about US$105m. Of this amount, approximately US$ 62 million is expected to be used as direct co-financing for the GEF activities, comprising basin management planning and capacity building activities, policy analysis related to the charcoal industry, SLWM investments in agricultural landscapes, inputs from the community livelihoods fund, community-level flood resilience activities in and around the area of the Elephant Marshes, and project management and monitoring overheads. This IDA credit will serve as a flagship project for the Bank in Malawi, laying the foundation for sustainable development based on integrated natural resources management throughout most of the southern half of the country and the largest part of its economy. It is also anticipated that the project will lead to a second phase investment of similar size as part of the APL, and which would be informed by the ecosystem valuation and pilot management activities funded by GEF. Through establishment of basin-wide coordination and monitoring mechanisms, it is also expected to be influence the direction of related land management projects, including investments by the Millennium Challenge Account, UNDP and Japan.

C.2  How does the project fit into the GEF agency’s program (reflected in  documents such as UNDAF, CAS, etc.) and staff capacity in the country to follow up project implementation:

The Shire River Basin Management Project is consistent with the Bank’s fifth Country Assistance Strategy (CAS) for Malawi, 2011–2016. The project focuses on safeguarding and ameliorating the environment and natural resource base in the Shire River Basin to ensure local and global environmental services, including biodiversity conservation, climate resilience and carbon sequestration, and to improve sustainable livelihoods, food security, water supply and electrical energy generation; essential elements to support sustainable economic growth and poverty alleviation efforts. Project investments are primarily aligned with: CAS Theme 1 Promoting sustainable, diversified and inclusive growth, Results Area 1.3 Strengthening productivity in a diversified economy, Outcome 2 Improved capacity to plan, manage and develop water resources for multipurpose use; and CAS Theme 2 Enhancing human capital and reducing vulnerabilities, Results Area 2.2 Lowering vulnerability and enhancing resilience, Outcome 3 Sustained rural livelihoods and improved protection of investments dependent on the resource base, and Outcome 4 Enhanced capacity to respond to current and future climate and disaster risks. The GEF-funded activities within the project are particularly aligned with Outcome 3under Results Area 2.2. Along with the Bank’s other biodiversity projects in Malawi, they will help to conserve of resources that are important to rural livelihoods, as well as providing watershed services and the basis for most of Malawi’s tourism industry. The project is also closely related to climate and disaster resilience activities under Outcome 4. The World Bank has a well staffed office in Malawi, as well as the ability to draw on pre-eminent global expertise. It is anticipated that four natural resources technical staff will be based in Malawi during the project, covering water, environment, forests and climate change, in addition to agriculture, private sector, procurement and financial management specialists. The task team for the Shire Project also includes some of the most experienced experts within the Bank in river basin management, and in environmental and social safeguards.

part iii:  approval/endorsement by gef operational focal point(s) and GEF agency(ies)

A.   Record of Endorsement of GEF Operational Focal Point (S) on Behalf of the Government(S): (Please attach the Operational Focal Point endorsement letter(s) with this template. For SGP, use this OFP endorsement letter).

| Name | Position | Ministry | Date (MM/dd/yyyy) |
| --- | --- | --- | --- |
| Dr. Aloysius Kamperewera | Deputy Director, Environmental Affairs Department | Ministry of Natural Resources, Environment & Energy | 08/22/2011 |

B.  GEF Agency(ies) Certification

| This request has been prepared in accordance with GEF/LDCF/SCCF policies and procedures and meets the GEF/LDCF/SCCF criteria for project identification and preparation. |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Agency Coordinator, Agency name | Signature | Date (MM/dd/yyyy) | Project Contact Person | Telephone | Email Address |
| Karin Shepardson, GEF Agency Executive Coordinator |  | August 30, 2011 | Paola Agostini, Regional Coordinator, Africa Region | 202 473 7620 | pagostini@worldbank.org |

PIF_WITHOUT_MACROS

1.0

It is very important to consult the PIF preparation guidelines when completing this template.

Project ID number will be assigned by GEFSEC.

Refer to the reference attached on the Focal Area Results Framework when filling up the table in item A.

GEF will finance management cost that is solely linked to GEF financing of the project.

Same as footnote #3.

Remaining forest and wetland areas in the Shire basin continue to support biodiversity of global significance and there are seven Important Bird Areas (IBAs) listed by BirdLife International for the basin, and a center of globally important endemism in the form of the Mulanje massif. Both Liwonde National Park and Majete Wildife Reserve now support re-introduced populations of critically-endangered Black rhino Diceroa bicornia – part of efforts to restore the ecological integrity of these two protected areas. Liwonde National Park supports a significant population of the endangered African elephant Loxodonta africana and these continue transfrontier migration cycles into Niassa province,  Mozambique (via Mangochi Forest Reserve and forest areas on customary village land). An elephant population has also been re-established in its former range at Majete Wildlife Reserve with translocated stock from Liwonde NP. Red bush squirrel Paraxerus palliates and Spotted-necked otter Lutra maculicollis – both categorized as ‘vulnerable’ are found in the forests and wetlands of the middle and lower Shire. Threatened birds include Blue swallow Hirundo atrocaerluea, categorized as endangered and which is documented as breeding on the montane grasslands of Mulanje mountain and perhaps other upland areas in the Shire basin, Thyolo alethe Alethe choloensis, atrocareulea (both considered vulnerable) and the endangered Spotted ground thrush Zoothera guttata – a very rare resident of the southeastern montane forests. The White-winged Apalis Apalis chariessa also considered vulnerable is found in the low and mid altitude of the Shire highlands. The Elephant Marshes are also likely to fulfill Ramsar criteria as an internationally important wetland by supporting waterbird populations of international significance – although comprehensive surveys have yet to be undertaken.