Malaysia

Sustainable Management of Peatland Ecosystems in Malaysia (SMPEM)

Final project design report

Main Report and Appendices

Contents

List of Figures	ii

List of Tables	ii

Currency Equivalents	iii

Weights and Measures	iii

Abbreviations and Acronyms	iv

Map of the Project Area	vi

Executive Summary	vii

Logical Framework	xxii

I.	Strategic Context and Rationale	1

A.	Country and rural development context	1

B.	Rationale	7

II.	Project Description	10

A.	Project Area and Target Group	12

B.	Development objective and impact indicators	13

C.	Outcomes/Components	13

D.	Lessons Learned and Adherence to IFAD Policies, GEF policies and the SECAP	21

III.	Project Implementation	24

A.	Approach	24

B.	Organizational Framework	25

C.	Planning, M&E, Learning and Knowledge Management	28

D.	Financial Management, Procurement and Governance	31

E.	Supervision	34

F.	Risk identification	34

IV.	Project Costs, Financing, Benefits and Sustainability	36

A.	Project Costs	36

B.	Benefits	40

C.	Socio-economic benefits	44

D.	Sustainability	45

List of Figures

Figure 1: Percentage Share to GDP by Kind of Economic Activity, 2015	2

Figure 2: Distribution of World Peat Map (source: Parish et al, 2008)	3

List of Tables

Table 1: Parts of NSPSF within various forest reserves	xi

Table 2: Permanent Reserved Forest by Size	xii

Table 3: The area (ha) of peatlands and land uses in Peninsula Malaysia, Sabah and Sarawak	3

Table 4: State level Agencies and their Duties/Relevant Responsibilities	5

Table 5: Staffing of project management offices	29

Table 6: Project Risk and Risk Mitigation Analysis	34

Table 7: Project Components by Financier (USD '000)	37

Table 8: Expenditure Categories by Financiers (USD'000)	38

Table 9: Project Management Costs (USD '000)	38

Table 10: Co-financing levels by source / amount	39

Table 11: Key biodiversity associated with Project sites	40

Table 12: Estimated Emission reduction linked to project activities	43

Currency Equivalents

| Currency Unit | = | Malaysian Ringgit |
| --- | --- | --- |
| US$1.0 | = | MYR 4.3 (August 2017) |

Weights and Measures

| 1 kilogram | = | 1000 g |
| --- | --- | --- |
| 1 000 kg | = | 2.204 lb. |
| 1 kilometre (km) | = | 0.62 mile |
| 1 metre | = | 1.09 yards |
| 1 square metre | = | 10.76 square feet |
| 1 acre | = | 0.405 hectare |
| 1 hectare | = | 2.47 acres |

| Abbreviations and Acronyms |  |  |
| --- | --- | --- |
| AATHP | ASEAN Agreement on Transboundary Haze Pollution |
| ACC | ASEAN Coordinating Centre for Transboundary Haze Pollution Control |
| APFP | ASEAN Peatland Forests Project |
| APMS | ASEAN Peatland Management Strategy |
| APSMPE | ASEAN Programme for Sustainable Management of Peatland Ecosystems (2014-2020) |
| AWPB | Annual Work Plan and Budget |
| BBP | Biodiversity and Forestry Management Division (Bahagian Pengurusan Biodiversiti dan Perhutanan) |
| BPASPI | Environmental Management and Climate Change Division (Bahagian Pengurusan Alam Sekitar dan Perubahan Iklim) |
| BPEN CEO | Bahagian Perancang Ekonomi Negeri Pahang (State Economic Planning Division, Pahang) Chief Executive Officer |
| CIG | Common Interest Group |
| CPMT | Country Programme Management Team (IFAD) |
| CSO | Civil Society Organization |
| DDR | Detailed Design Report |
| DO | District Office |
| DPMO | District Project Management Office |
| DTM | Digital terrain model |
| FD | Forest Department |
| FDPM | Forestry Department Peninsula Malaysia |
| FDR | Final Project Design Report |
| FDRS | Fire Danger Rating System |
| FPIC | #### Free, Prior and Informed Consent |
| FR | #### Forest Reserve |
| GCF | Green Climate Fund |
| GEF | Global Environment Facility |
| GEFSEC | GEF Secretariat |
| GOM | Government of Malaysia |
| GHG | Greenhouse Gases |
| IFAD | International Fund for Agricultural Development |
| IUCN | International Union for Conservation of Nature |
| LiDAR | Light Detection and Ranging |
| MAHFSA | Measurable Action for Haze Free Sustainable Land Management in Southeast Asia |
| M&E | Monitoring and Evaluation |
| MRV | Measuring, Reporting and Verification |
| NAPP | National Action Plan for Peatlands |
| NGO | Non-Governmental Organization |
| NPBD | National Policy on Biological Diversity |
| NPMO | National Project Management Office |
| NPSC | National Peatland Steering Committee |
| NPWD | National Park and Wildlife Department |
| NPWC | National Peatland Working Committee |
| NRE | Ministry of Natural Resources and the Environment |
| NRO | Natural Resources Office |
| NTFP | Non Timber Forest Product |
| PIM | Project Implementation Manual |
| PMO | Project Management Office |
| PP | Procurement Plan |
| PRF | Permanent Reserved Forest |
| PSF | Peat Swamp Forest |
| PWG | Project Working Group |
| QE | Quality Enhancement |
| REDD+ | Reduction of Emissions from Deforestation and forest Degradation and the role of conservation, sustainable management of forests and enhancement of forest carbon stocks |
| SCC | Site Coordination Committee |
| SEApeat | Sustainable management of peatland forests in South East Asia (SEApeat) Project |
| SFD | State Forestry/Forest Department |
| SAO | State Administration Office |
| SEA | South East Asia |
| SPMO | State Project Management Office |
| SPPL SSC | Southeast Pahang Peatland Landscape State Steering Committee |
| SPU | State Planning Unit, Sarawak |
| UNDP | United Nations Development Programme |
| UNEP | United Nations Environmental Programme |
| UPEN | Unit Perancang Ekonomi Negeri (State Economic Planning Unit) |
| WB | World Bank |
| WG | Working Group |

Map of the Project Area

1

2

3

4

5

Location of Project Sites (1: North Selangor Peat Swamp Forest; 2: South Selangor Peatland Landscape; 3: Southeast Pahang Peatland Landscape; 4: Klias Peninsula Peatland Landscape; and 5: Maludam Peninsula Peatland Landscape)

# Executive Summary

Background

- Building on the success of the Malaysian component of the Global Environment Facility (GEF)-IFAD funded ASEAN Peatland Forests Project (APFP) -– a regional IFAD/GEF/ASEAN project implemented between 2009 and 2014 – IFAD has worked with the Government of Malaysia to develop the Sustainable Management of Peatland Ecosystems in Malaysia (SMPEM) project. The GEF project identification form (PIF) for the SMPEM was developed through a multi-stakeholder process in 2014-2015 and endorsed by Malaysia’s National Peatland Steering Committee (NPSC) and its National Peatland Working Committee (NPWC) in December 2014. The PIF was subsequently endorsed by the Malaysian GEF Focal Point and approved by the GEF Council in May 2016.

- Preparation of the present Detailed Design Report (DDR) and the GEF CEO Endorsement document began in October 2016 with preparation of a background report on the project sites. An IFAD Detailed Design Mission visited Malaysia from 1 to 15 May 2017 and included extensive meetings at federal and state levels together with visits to the project sites, i.e. 48 consultation meetings (8 meetings at national level, 14 meetings at sub-national level and 26 multi-stakeholder meetings) and 40 community and village group discussions. An Appraisal Mission took place from 31 July-10 August 2017 and included extensive meetings at federal and state levels and made significant progress in confirming the design and elaborating the institutional, financing and administrative procedures related to the project.

Rationale

- Increasing pressures for land development (e.g. agriculture, infrastructure) and timber extraction have heavily affected peat swamp forests in Malaysia over the past 50 years. Land conversion for primarily agricultural and plantation purposes has generated economic benefits; however, management of these lands is creating major challenges and substantial environmental, and in some cases economic, losses. As of 2015, more than 1.5 million hectares of peatlands in Malaysia have been developed for oil palm, agriculture and urban areas. However, some of these developments have faced challenges such as subsidence, fire, low productivity etc,. In addition, peatland landscapes have been fragmented, drained and degraded, and the fragility of these ecosystems has grown due to the increasing frequency of severe droughts. In recent decades, peatland fires have been growing in extent and severity in parts of Malaysia. Peatland drainage and fires are also major contributors of greenhouse gas (GHG) emissions thus creating a positive feedback loop between climate change and further peatland degradation.

- Malaysia has recognised the significance of peatland ecosystems and has outlined a broad range of actions to maintain them in its National Action Plan on Peatlands (NAPP), which was adopted in 2011 and which covers the period of the 10th and 11th Malaysia Plans (i.e. 2011- 2020). The importance of conserving and restoring peatland ecosystems has also been highlighted in the National Policy on Biological Diversity 2016-2025. Malaysia has also recognised the increasing extent and frequency of peatland fires and associated smoke haze pollution and updated its National Haze Action Plan in 2013. In 2015, NRE adopted a Standard Operating Procedure for Prevention of Peatland Fires. The government has also introduced measures to enhance the sustainable management of production landscapes in peat through establishing a target for mandatory certification of all plantations and smallholder production on peat (and other soils) under the Malaysian Standard on Palm Oil (MSPO) by 31 December 2019 as well as other measures to enhance sustainability of agriculture and forest management. Integrated management plans have been developed for large peatland complexes in Selangor and Pahang States as well as management plans for selected peatland sites in Sabah and Sarawak. However, there remains much work to complete to achieve the targets under the NAPP for ensuring the protection and sustainable management of all of Malaysia’s peatlands.

Project Approach and Objectives

- Theory of Change: The project’s theory of change is based on the assumption that addressing the complex challenge of sustainable peatland management (SPM) requires coordinated and complementary actions in several key thematic areas, at multiple geographic levels, and systematically over time. Malaysia has 2.7 million ha of peatlands, which originally were all covered with peat swamp forest and providing critical ecosystem services for water resource management, climate regulation and biodiversity conservation. Over the past fifty years, the majority of peatlands have been cleared and drained for agriculture and plantation purposes. While such uses have been important for economic development, there have been significant challenges including land subsidence,, disruption of water supply and increased flooding, loss of biodiversity, peatland fires and GHG emissions.

- In some states, government expenditure for peatland fire-fighting is higher than that for peatland management and fire prevention (whereas international experience indicates that more than 80% of the resources should be allocated to fire prevention rather than fire suppression).   Management of peatlands is also fragmented between Forestry Departments managing those portions remaining under forest cover, and agriculture departments and plantation agencies, local government, private sector and communities managing those areas which have been developed outside forest reserves. A significant area (especially those outside of forest reserves with no active agriculture or plantations) has no clear management and is increasingly prone to fire. A further complexity is that policy is set at a national level, but all land is managed at the state level. At state level, there are relatively limited resources for active management or rehabilitation of degraded peatlands outside of forest reserves. Even within forest reserves and protected areas, there are often insufficient management resources.

- The project’s theory of change thus operates along three distinct dimensions: thematic, geographic and time. The thematic aspect considers the complementary roles of planning, capacity building, policy reform, demonstration and uptake, knowledge and financial resource allocation. The geographic dimension takes into account how these themes operate and interact at local, state and national levels, and, as part of ASEAN Programme on Sustainable Management of Peatland Ecosystems 2014-2020 (APSMPE), at ASEAN level. The temporal aspect relates to the development of an investment framework that straddles two national planning and budgeting cycles extending up to 2030. The project will drive elements of change within each individual theme and geography over time, while encouraging synergies amongst and between the elements that further magnify the individual changes.

- Given the complexity of each of the above dimensions, they are presented separately below. In each case, the direct project actions and outputs are highlighted in bold as the root causes of the subsequent changes that are expected.

- In thematic terms, the project supports multi-sectoral policy dialogue based on the multi-sectoral nature of peatland management challenges, including forest, plantation and agricultural sectors along with the cross-cutting issues of water resource management. A quick look at the long list of institutional stakeholders (see Paras 52-54 below) should suffice to indicate the importance and complexity of this theme. Policy dialogue through multiple mechanisms depending on geographic level, together with targeted supporting analysis, is expected to lead to enhanced enabling environments at local, state and national levels based on harmonized policy and regulatory changes and reflecting better understanding of cross-sectoral needs and concerns. Multi-sectoral dialogue will also help to ensure effective private sector and local community participation in the process.

- Policy work will be closely complemented by support to planning, which has two facets. First, the project will help to mainstream SPM into multiple policy and planning documents, e.g. Malaysia National Plan, REDD+ land use planning and agriculture development policies, wetland policies, etc. to ensure that such guidance is contributing to sustainable peatland objectives. In addition, peatland-specific planning documents, including support for revision of the National Action Plan on Peatlands (NAPP), development of new State Action Plans on Peatlands (SAPPs) and preparation of landscape-level Integrated Management Plans (IMPs), will define clear agendas for achieving SPM.

- The above policy and planning efforts would likely suffer at the implementation stage without efforts to enhance institutional capacities for implementation. Efforts in this area will be targeted at individuals and units responsible for key areas, particularly those where new mandates and responsibilities may be emerging in connection with the above policy and planning reforms.

- A closely related factor underpinning SPM is ensuring an adequate flow of financial resource allocations for operations and investment, and this brings in the temporal aspect of the work, as sustained efforts and financing will be necessary for changes on the ground to manifest themselves. Without dedicated financial allocations to priority activities, capacities will remain unused while plans and policies will not be implemented. Underpinning the project’s financial resource strategy is a two-pronged effort, first, to produce an overarching cost-benefit analysis demonstrating the economic costs of mismanaged peatlands and the corresponding benefits of investing in SPM and, second, work to assess the potential of landscape-level financing options based on Payment for Ecosystem Services (PES) generated by peatlands and leveraged co-investments on the part of those benefiting from the use of peatlands. These areas of work will underpin the development of a 10-year investment framework (2021 - 2030). The framework will straddle two 5-year Malaysia National Plans (12th and 13th MNPs) and will identify a hierarchy of priorities targeting all levels, to be financed by public, private and development cooperation financing, as well as international climate change and environmental funds. The project will build capacity for mainstreaming the investment framework into the 12th MNP. It is furthermore expected that this work will be replicated during the development of the 13th MNP. Taken together, these activities and outputs will ensure that the substantial investment and operating costs of achieving and maintaining SPM are well resourced financially over the medium-term. The project will also work to enhance the level of funding support from the private sector for NAPP implementation, as well as helping to secure regional and international resources to sustain efforts after the SMPEM project.

- Demonstration activities will allow the project both to create direct, tangible impacts at site and broader state levels while, as the term implies, demonstrating, and raising awareness of, effective approaches to SPM - thereby providing tested approaches for scaling up. Key demonstration / learning themes include, landscape level planning and water management, fire prevention, peatland agro-forestry, sustainable agriculture and plantation management, community empowerment and private sector engagement.

- Altogether, the above-described thematic and temporal elements of the project’s theory of change argue that integrated support to planning, policy, capacity building, financial resource allocation and demonstrations will lead to well-coordinated and rationalized implementation over the medium-term of plans and related actions at national, state and site levels. Change will emerge from a combination of regulatory efforts and enhanced recognition of financial feasibility. These actions, in turn, will generate positive impacts in terms of GHG emission reductions, biodiversity conservation and reduced land degradation, together with an extensive array of socio-economic benefits (see Section IV.C. Benefits).

- The geographic dimension of the theory of change involves support at four geographic levels. Working from bottom up, the project assigns a significant portion of its resources to the landscape level. Integrated management will be supported in five key peatland sites in four states. These areas have been selected based on the concept of peatland landscapes (or peatland basin/hydrological unit). This has been done as a result of the natural inter-connectivity of peatland hydrological systems, which transcend the artificial administrative boundaries of say -  forest reserves and plantations. In addition to site-level benefits, particularly for biodiversity conservation, ecosystem restoration and GHG mitigation, work at the landscape level will address hydrological integrity, flood control and fire prevention as well as balancing development and conservation approaches.

- At state level, the project aims to expand the scope and scale of impacts generated at site level to additional peatland areas. In developing State Action Plans for Peatlands (SAPPs), the states will follow a common methodology aimed at ensuring sustainable peatland management targets at state level. This work will focus on sustainability aspects of existing forestry, agriculture and plantations on peatlands, as well as, fire prevention and associated contingency planning. Lessons learning among states, both from work on these two issues and from landscape-level work, will be an important state-level activity.

- At national level, change is designed to flow from the enhanced enabling policy, regulatory and financing environment, national-level plans and investment planning support, and enhanced capacities, together with coordination and support for knowledge management. Finally, the national-level component will serve as a connector to ASEAN-level work through the APSMPE.  The linkages will be supported by IFAD's US$3.5 million regional grant to the ASEAN Secretariat for the project on Measurable Action for Haze-Free Sustainable Land Management in Southeast Asia (MAHFSA).

- The Project Goal: To sustainably manage peatlands in Malaysia in an integrated manner to conserve resources, prevent degradation and fires, and generate benefits for current and future generations. The goal is derived from the Malaysian National Action Plan on Peatlands (NAPP) adopted in 2011. The project will also support Malaysia’s contribution to the six targets of the ASEAN Programme on Sustainable Management of Peatland Ecosystems 2014-2020 (APSMPE).

- The Project Objective: is to strengthen national policy and institutional capacity for implementing peatland-related strategies and plans and to enhance integrated peatland management in targeted landscapes.

- Target populations and expected benefits: Peatlands play a critical role in the socio-economic well-being of the country, particularly by generating ecological and hydrological values, timber and non-timber forest products, water supply, flood control and many other social, environmental and economic benefits. Target populations include communities in identified peatland landscapes, especially poor and marginalised local communities.

- Geographical Targeting. The project includes a national-level component, state-level work in Pahang, Sabah Sarawak and Selangor, and work at the five sites described below.

- North Selangor Peat Swamp Forest

Peatland Area: North Selangor Peat Swamp Forest (NSPSF) is located in northwest Selangor State and covers an area of 81,304 ha mainly within various forest reserves – as seen in Table 1, as well as a 15,000 ha buffer zone.

##### Table 1: Parts of NSPSF within various forest reserves

| Number | Forest Reserve | Size (ha) |
| --- | --- | --- |
| 1 | Raja Musa Forest Reserve | 35,656 |
| 2 | Sungai Karang Forest Reserve | 37,417 |
| 3 | Part of Bukit Belata (Extension) Forest Reserve | 3,140 |
| 4 | Sungai Dusun Wildlife Reserve / Sungai Dusun Forest Reserve | 5,091 |
|  | Total | 81,304 |

Significant Value of Site: The NSPSF harbours a variety of plants including 107 types of trees, 60 types of herbs, 32 types of orchids, 14 types of mosses and lycophytes, 24 types of ferns and others. Some of the important tree species found within this PSF are Ramin melawis (Gonystylus bancanus), Meranti bakau (Shorea uliginosa) and Keranji paya (Dialium patens). This forest is also home for many species of endangered fauna which are restricted to the PSF, such as Sun bear (Helarctos malayanus), Clouded leopard (Neofelis nebulosa), Tapir (Tapirus indicus), and False Gharial (Tomistoma schlegelii). It is home to at least 46 species of mammals, 173 species of birds, 17 species of amphibians, 16 species of reptiles, 47 species of dragonflies and damselflies, 17 species of spiders and more than 100 fish species are found in this forest including 6 endemic species found nowhere else in the world. In addition, the site provides a number of ecosystem services, including water supply, flood control, eco-tourism, fishing sites for local peoples and climate regulation.

Disturbances and Threats: The main threat is fire with more than 6,000 ha within the forest reserve severely degraded by fires. 500 km of ex-logging canals drain much of the forest. The southern portion of the site is affected by sub-surface drainage linked to extensive sand and tin mining. More than 2,000 ha have been encroached in the past for agriculture and oil palm activities. A buffer zone covering 15,000 ha has recently been designated but 90% of this area has been developed for agriculture and oil palm plantations. Appropriate land and water management strategies need to be implemented in this land.

Proposed Actions Through SMPEM: Updating the Integrated Management Plan and scaling up implementation with focus on fire prevention and control, improved water management, implement buffer zone management, local communities participatory and forest rehabilitation.

- South Selangor Peatland Landscape

Peatland Area: The South Selangor Peatland Landscape covers 60,000 ha in Southern Selangor State near Kuala Lumpur International Airport in Kuala Langat and Sepang District. There are two peat swamp forests (PSF), namely the North and South Kuala Langat FRs, covering an area of 958 ha and 8,339 ha respectively (as recorded in Selangor State Forest Management Planning, 2011-2020). There are an additional 52,227 ha in the surrounding peatland landscape

Significant Value of Site: Meranti bunga (Shorea teysmanniana), a Critically Endangered tree species found inside the forest reserves. Local peat swamp species such as Mersawa paya (Anisoptera marginata) and Meranti bakau (Shorea uliginosa) as well as lowland forest species such as Jelutong (Dyera costulata) are also found in the forest reserves. There is a 130 ha Virgin Jungle Reserve (VJR) located within the Kuala Langat South Forest Reserve (FR). High value species such as Kempas (Koompasia malaccensis), Meranti bunga (Shorea teysmanniana), Punah (Tetramerista glabra) and Ramin melawis (Gonystylus bancanus) are found within the VJR area.

Disturbances and Threats: The main threats are increasing development activities adjacent to the forest reserves – oil palm plantations and housing and infrastructure development projects increase pressure on the land, inadequate enforcement by the relevant agencies on encroachment into forested area from adjacent private land for agriculture, abandonment of degraded peatland leads to peat fires caused by land clearing, hunters and fishers.

Proposed Actions through SMPEM Project: Management of peatland landscape including sustainable agricultural practices (e.g. best management practices) and enhanced urban and infrastructure management approaches. Within the forest conservation areas, focus will be on rehabilitation and maintenance of forest, fire prevention and engagement with local and indigenous communities.

- Southeast Pahang Peatland Landscape (SEPPL)

Peatland Area: The 230,000 ha peatland landscape includes 108,920 ha of PSF in Permanent Reserved Forests (PRFs) and 122,000 ha of private plantations, village and state land.

##### Table 2: Permanent Reserved Forest  in SEPPL by Size

| Number | Forest Reserve | Area (Ha) |
| --- | --- | --- |
| 1 | Pekan Forest Reserve | 44,148 |
| 2 | Pekan Forest Reserve (Extension) Forest Reserve | 19,123 |
| 3 | Nenasi Forest Reserve | 20,546 |
| 4 | Nenasi Forest Reserve (Extension) | 5,140 |
| 5 | Kedondong Forest Reserve | 1,818 |
| 6 | Resak Forest Reserve | 2,280 |
| 7 | Resak Forest Reserve (Extension) | 15,864 |
| Total |  | 108,920 |

Significant Values of Site: Important habitat for threatened species such as Malayan sun bear, Flat-headed cat, White-handed gibbon, Small-clawed otter and Malayan porcupine animal species Critically Endangered: Painted terrapin, Malayan tiger, Asian elephant, Sunda otter civet, Hairy-nosed otter, Panther, Leopard, Lesser adjutant stork, Wrinkled hornbill, Large green pigeon, Short-toed coucal, Wallace’s hawk- eagle, False gharial and Malayan giant turtle. The forests also includes valuable timber species such as Meranti paya (Shorea platycarpa), Mersawa paya (Anisoptera marginata), Bintangor (Calopyhllum spp.) and Ramin melawis (Gonystylus bancanus) and commercial fish species such as Tapah, Toman and Baung.

The Orang Asli (aboriginal peoples), from the Jakun subgroup, known as Proto Malays represent a key community in the SEPPSF. A total of 19 Orang Asli villages are found near the SEPPSF. A significant portion of the Orang Asli community is still dependent on forest products for their sustenance and livelihood.

Disturbances and Threats: Fire has been impacting more of the landscape in recent years because of drainage and fragmentation. Fire has impacted more than 10,000 ha in recent years and has needed up to US$37 million a year in fire control costs, in addition to significant environmental and economic losses. The principal drivers are large-scale drainage of portions of the state land around the forest reserves and conflicting land and water use strategies.

Proposed Actions Through SMPEM Project: Development and implementation of an Integrated Management Plan for the Landscape including action on fire prevention and control, forest rehabilitation, development of buffer zone plan and cooperative land uses, promotion of sustainable management for existing oil palm plantation on peat (best management practices), and enhanced sustainable livelihoods for indigenous communities.

- Maludam Peninsula Peatland Landscape

Area: The Maludam National Park covers 53,568 ha. This peatland landscape includes an additional 25,000 ha of private, community and state land that is outside the national park and has been used for agriculture and plantations.

Significant Value of Site: There are 61 species of mammals recorded in Maludam, which include 15 species of bats and 5 species of diurnal primates. The Maludam National Park is the only site globally for the conservation of the Red-banded langur (Presbytis melalophos cruciger) which number less than 200, and are now restricted to the remnant patches of tall forest. One of only about five viable populations, in Sarawak, of Proboscis monkey (Nasalis larvatus), occurs in the park. There are 201 species and 24 families of birds including 5 species of Hornbills (including Black, Pied and Rhinoceros hornbills), and the rare Storm's stork. There are at least 218 species of flora recorded from various groups of plants.

Disturbances and Threats: The main impacts on the National Park include encroachment and illegal logging and the development of oil palm plantations adjacent to national park.

Proposed Actions Through SMPEM Project: Enhanced National Park protection and management, buffer zone management, including sustainable water supply to local settlement, expansion of conservation area, regulation on land clearing and conversion in buffer zone/adjacent land.

- Klias Peninsula Peatland Landscape

Area: The Klias Peninsula comprises about 45% of the pristine PSFs in Sabah with an estimated 12,500 ha within 25,511 ha of forest reserves in a larger landscape of 69,579 ha of peatlands including cultivated for agriculture and oil palm as well as portions degraded by fire.

Significant Value of Site: Globally threatened mammal, reptiles and trees: including endangered Proboscis monkey (Nasalis larvatus) and Meranti bunga (Shorea tesysmanniana); and Vulnerable Pig-tailed macacque (Macaca nemestrina), Malayan sun bear (Helarctos malayanus), Asiatic softshell turtle (Amyda catilaginea) and Critical trees such as Giam (Hopea pentanervia) and Meranti paya (Shorea platycarpa).

Disturbances and Threats: The main threats to the Klias Peninsula peatlands are the land-use conversion, drainage of adjacent lands for oil palm, flooding during wet season and serious fire risks.

Proposed Actions Through SMPEM Project: Landscape management and best management practices on water as well as control on land clearing, rehabilitation of degraded forests and enhanced community and private sector engagement.

- Project Components: The following summarizes the project components, outcomes and outputs. A more complete description is provided in Section I.C. of the main text. Full details, including implementation responsibilities, are provided in Appendix 2.

Component 1: Enhanced policy dialogue and improved institutional capacity for development and implementation of peatland related strategies and plans

Outcome 1. Enhanced resources, multi-stakeholder involvement and capacity for implementing the National Action Plan on Peatlands and other policies and plans up to 2030

- Component 1 will focus on strengthening national frameworks and capacities for the sustainable management of peatlands and peatland ecosystems in Malaysia, with an emphasis on multi-sectoral aspects of peatland management and rationalization of resource use. Institutional capacity will be strengthened to effectively implement the relevant national policies and actions particularly those identified in the National Action Plan on Peatlands (NAPP). Work under this component will enable key agencies to review and mainstream peatland issues into national policies that are peat-relevant. The component will support establishment of a multi-stakeholder network of government agencies, as well as the private sector, civil society and local communities to enhance collaboration and joint action to sustainably manage Malaysia’s peatlands. Finally, it will develop a longer-term investment and financing framework to support sustainable peatland management in the country.

- A key targeted outcome of this component is a 30% increase in total funding for sustainable peatland management. Increased funding allocations will also be better coordinated—particularly between public and private sectors—and focused on priority issues as identified by the NAPP and associated policy frameworks. Finally, enhanced capacities will help to ensure that financial resources, once mobilized, are effectively disbursed and monitored.

Output 1.1 Policies, guidelines, institutional arrangements, and capacity for sustainable peatland management enhanced

- The main activities will include: i) Strengthen and support operations of the National Peatland Steering Committee (NPSC) and the associated National Peatland Working Committee (NPWC); ii) Provide a package of strategic technical support for the SPMEM Project implementation; iii) Review implementation of existing National Action Plan on Peatlands (NAPP) and develop the NAPP 2021 – 2030; iv) Support capacity building and implementation of the NAPP and  peatland-related aspects of the National Policy on Biological Diversity (2016-2025); v) Mainstream peatland issues into relevant national policies and plans; vi) Develop and promote use of guidelines for sustainable management of peatland landscapes; and  vii) prepare a National Peatland Directory.

Output 1.2 Investment framework for NAPP 2021 – 2030 developed and adopted

- This output will focus on developing, and obtaining commitments to implement, a ten-year investment framework to channel financial resources for the implementation of the new NAPP (2021-2030).

- Main Activities will include: i) Undertake an economic analysis of the long-term costs and benefits of existing land-use systems and future scenarios of peatland quality in a changing climate; ii) Develop models of co-investment mechanisms for peatland users; iii) Identify the required costs for the NAPP priorities and implementation by relevant actors (including government institutions, private sector, and other partners) and prepare an investment framework for the NAPP 2021-2030; iv) Mainstream NAPP investments into the 12th Malaysia Plan (2021-2025) and relevant state development plans; v) mobilise supplementary finance from private sector, international environmental and climate funds, and bilateral and multilateral sources in line with the NAPP investment framework.

Output 1.3: Knowledge management and exchange enhanced to support scaling-up of sustainable peatland management

- Knowledge management is key to building capacity for sustainable management of peatland ecosystems. A knowledge management system will be established to document and synthesize successful approaches and technologies for sustainable peatland management, and to make use of dissemination pathways for scaling up best practice and for informing evidence-based policy dialogue. This work will help to secure broader adoption of sustainable peatland management approaches especially by the private sector and state governments.

- Main Activities include: i) Develop a knowledge management (KM) strategy for peatlands targeting relevant stakeholders at all levels; ii) Establish a knowledge management system by strengthening knowledge repositories and pathways for dissemination; iii) collate existing materials as well as develop and share knowledge and lessons learned from state and site level activities through outreach programmes; iv) Awareness raising on sustainable peatland management; v) Engage in knowledge sharing and coordination activities at regional and international levels; vi)  Support collation and analysis of information on GHG emissions from peatlands; and viii) Monitoring and Evaluation (M&E) of the project implementation.

Component 2: Enhanced Management framework and practices for sustainable management of peatlands in Pahang, Sabah, Sarawak and Selangor.

Outcome 2. Improved sustainable management of peatlands in target states

- As noted above, peatland is the most important of Malaysia’s wetland types in terms of biodiversity, area and biogeography, accounting for approximately seventy-five percent of total wetland area. As shown in Table 2 below, Malaysia possesses about 2.717 million ha of peatland, more than sixty percent of which is located in the state of Sarawak. Sarawak’s estimated 1,645,580 ha of peatland cover fourteen percent of the state’s total land area. In the state of Sabah, remaining peatland areas are smaller, covering about 192,000 ha. Some 880,389 ha of peatland remain in Peninsular Malaysia, the majority of which (506,631 ha) is found in the states of Pahang and Selangor. About 373,758 ha of peatland are situated in the states of Johor, Kelantan, Perak and Terengganu. About 70% of peatlands by area have been developed for oil palm and other agricultural uses, while most of the remainder is in forest reserves and protected areas. Some areas in forest reserves are zoned for conservation while others are for forestry production.

- A key targeted outcome of this component is a 30% increase in the area implementing good management practices for peatland management as compared to the baseline. In addition, important health and economic benefits for local populations from enhanced sustainable management and reduced peatland fires as well as global benefits in terms of GHG emissions reductions (projected to reach 3.06 million MT of CO2e. This target will be achieved through a combination of support to best management practices in the agricultural and fire prevention and control. In both cases, work will be guided by the SAPPs, with similar benefits from planning as those described at national level under Component 1, i.e. enhanced co-ordination and prioritization due to multi-stakeholder engagement.

Output 2.1 State Action Plan for Peatlands (SAPP) developed and adopted by Pahang, Sabah, Sarawak and Selangor.

- The states selected for the development of SAPPs are Pahang, Sabah, Sarawak and Selangor. Together, these four states account for 86% of Malaysia’s peatlands and more than 90% of the permanent reserved forest (PRF) and protected areas on peat. Each is managed and utilised under quite different legal and administrative structures

- Main Activities will include the following actions: i) Develop a workable methodology and approach for developing the SAPP including common scope, format, and sub studies for defining necessary actions, institutional responsibilities and budgetary requirements for sustainable peatland management in the respective states; ii) Establish an institutional framework and develop SAPPs through multi-stakeholder consultation, iii) Conduct comprehensive peatland inventory and economic analysis; and v) undertake an assessment on Peatland Fire Prevention and Control in targeted states.

Output 2.2 Best management practices introduced in agriculture and plantation sectors in Pahang, Sabah, Sarawak and Selangor.

- More than 60% of peatland area in Malaysia is used for agriculture and oil palm plantations. Drainage and development of plantations and agriculture on peat, lead over time, to the loss of the peat soil through oxidation and compaction leading to subsidence and GHG emissions. Peatland drainage increases the risk of fire within the development areas and in adjacent lands. This output will provide support and guidance to improve agriculture products and / or yields in existing agriculture and oil palm plantations on peat and to address issues related to drainage development, water management, fires, GHG emissions, subsidence and other impacts that affect the potential sustainability of agriculture and oil palm plantation on peatlands.

- The following are the main activities: i) Review and enhance capacity for sustainable management of oil palm plantations on peat; ii) Review and enhance capacity for  sustainable agriculture on peat; iii) Work in partnership with private sector to document the BMP sites for oil palm on peatland and improve practices of existing oil palm plantations on peat; iv) Empower local communities for sustainable peatland management through training modules and TOT workshops and farmer field schools;  v) Support certification of oil palm plantations and smallholders under MSPO; and vii)  Explore options for agro-forestry on peat.

Output 2.3 Best management practices for peatland fire prevention and control for reducing GHG emissions in four states

- In recent years, peatland fires have increasingly occurred in Pahang, Sabah, Sarawak and Selangor particularly during the prolonged dry weather between the months of February to May and July to October each year. The associated haze and pollution have had severe socio-economic, ecological and environmental impacts, especially on the public health of local populations. Ministry of Natural Resources and Environment (NRE), through the Department of Environment (DOE), launched the National Peatland Fire Prevention Programme in 2009 to overcome peatland fire and haze. A total of US$ 10 million has been spent between 2009-2016 for construction of facilities and upgrading of infrastructure for peatland fire prevention and operation. Although the National Peatland Fire Prevention Programme has initiated prevention actions, peatland fires have continued to occur because the fire prevention measures/ approaches need to be fine-tuned and also scaled up to cover all fire prone peatlands.

- The Main Activities include: i)  Review, enhance and promote the use of the National Standard Operating Procedures (SOP) on Peatland Fire Prevention; ii) Strengthen stakeholder engagement in peatland fire control; iii) Enhance the effectiveness of the Fire Danger Rating System (FDRS) and stakeholders' preparedness in fire prevention and control

Component 3: Development and implementation of Integrated Management Plans (IMPs) for targeted, peatland landscapes

Outcome 3: Integrated Peatland Management Plans (IMPs) adopted and implementation initiated in five peatland landscapes

- Component 3 is focused on the conservation and integrated management of selected critical peatland landscapes of key importance for biodiversity. Project interventions will seek to reduce threats to the critical biodiversity sites through various alternatives to baseline land management practices, including sustainable agriculture and plantation management, buffer zone establishment and management, ecotourism, hydrology management, fire prevention, and forest and land rehabilitation. Work will be undertaken through partnerships between government agencies, local communities and private sector. The interventions will take a landscape approach linking the management of the peat swamp forests with the adjacent peatland areas under agriculture, plantation and other land uses.  The Component will work in five peatland landscapes located in four states (Pahang, Sabah, Sarawak and Selangor).

- A key targeted outcome of this component is that biodiversity-rich peatland landscapes covering a total of 518,004 ha and containing critical peatland ecosystems (which are mainly peat swamp forests) covering 268,643 ha. will be brought under the aegis of integrated management plans operating at landscape level. This will ensure more sustainable agricultural development in these areas, benefits to local communities and enhanced conservation of these critical ecosystems. Resources that will flow from SAPPs (see Component 2) and under the overall co-ordination of the NAPP (Component 1), will help to ensure the medium-term implementation of these landscape-level plans, and thus achievement of the above benefits.

Output 3.1 Review, update and implement existing Integrated Management Plan (IMP) for North Selangor Peat Swamp Forest (NSPSF), and develop a new IMP for South Selangor Peatland Landscape

- North Selangor Peat Swamp Forest (NSPSF) is the largest remaining PSF (81,304 ha) on the west coast on Peninsular Malaysia. It is of international significance for biodiversity with a broad range of rare and endangered flora and fauna. In the past, the site has been subject to heavy pressure from logging due to the previous status as stateland forest. More than 6,000 ha of the forest have burnt over the past 20 years linked to drainage associated with timber extraction, plantations, mining and agriculture on adjacent lands.

- The peatlands in southern Selangor State occur primarily in a peatland hydrological unit covering 61,524 ha. Significant portions of these peatlands were included in forest reserves gazetted starting in 1927 and were mainly forested until 1974 after which they were progressively converted for agriculture, plantation and urban development purposes There still remains about 9,000 ha of forest reserve which is still of significant importance for conservation of biodiversity as well as maintaining the hydrology of the surrounding areas. Fires have significant socio-economic impacts on local community and on Kuala Lumpur International Airport, which lies mainly within the landscape.

- The Main activities in North Selangor Peat Swamp Forest will be: i) Assess the progress of the existing IMP and update as necessary; ii) Develop an implementation plan and budget for the IMP-NSPSF for the period 2019-2023; iii)  Support active implementation of and reporting on IMP-NSPSF plan including forest and hydrology rehabilitation measures, iv) community engagement  and community based fire prevention and rehabilitation as well as sustainable agriculture and ecotourism; v) Strengthen capacity of State Forestry Department and other stakeholders; vi) Promote sustainable agriculture and plantation practices in the buffer zone; and vii) Support further development of the existing Centre of Excellence.

- The main activities in South Selangor Peatland Landscape (SSPL) will include: i) undertake assessment for South Selangor Peatland Landscape/ Hydrological Unit;  ii) Develop  the IMP for the SSPL to include community and stakeholder participation plan and sustainable landscape management plan (includes rehabilitation sub-plan, buffer zone management sub-plan, cooperative fire prevention sub-plan); iii) Initiate implementation of the SSPL IMP including, support  for implementation of the fire management plan for Kuala Langat North and South Forest reserves; iv) introduce community-based forest rehabilitation and canal blocking / rewetting;   v) Support community-based ecotourism; and vi) Promote best management practices for smallholder agriculture and plantations.

Output 3.2 Review existing Integrated Management Plans (IMP) for Southeast Pahang Peat Swamp Forest, and update and expand the scope to cover the Southeast Pahang Peatland Landscape

- Southeast Pahang Peat Swamp Forest (SEPPSF) is the largest peatland forest in Peninsular Malaysia. In the 1980s, it used to cover more than 300,000 ha but now the remaining forest is just over 100,000 ha primarily within Permanent Reserved Forests (PRF).  Peatland forest outside the PRF has been mainly logged and cleared or burnt and converted into plantation or agricultural land or remains under shrub or degraded forest. The site is still of international significance for the conservation of biodiversity. Increasing portions of the landscape have been affected by large-scale fires because of extensive drainage and disruption of hydrology in the state-land outside the forest reserves because of log extraction canals and oil palm plantation development.

- The Main Activities will include the following: i) Establish and support operation of a multi-stakeholder forum and governance mechanism for integrated management of Southeast Pahang Peatland Landscape (SPPL); ii) Undertake a comprehensive assessment of the SPPL; iii) Review the previous IMP (2008-2015), and revise it to cover the whole peatland landscape; iv) Implementation of priority fire prevention measures, demarcation of outer boundary of forest reserve and buffer zones, and enhancing capacity of plantations and other landowners in fire prevention and control; v) Work with targeted communities to enhance sustainable peatland management; vi) Rehabilitation of degraded PSF through restoring  water levels and preventing fire, enhancement and development of tree nurseries, enhancing natural regeneration, and development of a Centre of Excellence; and vii) Enhance the management of agriculture and oil palm on peat in the landscape, working with mills and refineries to enhance the sustainability and certification of the supply chain.

Output 3.3 Develop and implement new landscape level IMP for Klias Peninsula Peatland Landscape in Sabah

- In Sabah, the project will focus on the Klias Peninsula Peatland Landscape (KPPL) that includes Klias FR, Padas Damit FR and Binsulok FR, as well as large areas of plantations and community land between them. The landscape has been seriously affected by fire that has degraded 1,500 ha of forest reserve and 3,300 ha on the border of the forest reserve in 2016. Most of the rest of the landscape has been converted to agriculture and plantations.

- The Main Activities are the following: i) Undertake a detailed assessment of Klias Peninsula Peatland Landscape; ii) develop a comprehensive IMP for Klias Peninsula Peatland Landscape including, cooperative fire prevention and management plan, water management plan, and alternative livelihood development; iii) Support priority management measures including, promoting fire prevention and risk reduction in agriculture and plantation lands; iv) Restore natural hydrology and regeneration of degraded portions of Binsuluk FR; v)Protect corridors for wildlife; vi) Engage local community groups to improve their livelihoods at the same time protecting and rehabilitating the degraded peatland areas; and vii) Enhance management practices on smallholder plantations and agriculture on peat, and; viii) enhance community-based ecotourism.

Output 3.4 Develop and implement a landscape level IMP in the Maludam Peninsula, Sarawak

- In Sarawak, the project will focus on developing an IMP for the Maludam Peninsula Peatland Landscape (MPPL) that includes the 53,568 ha Maludam National Park and the community and plantation land (about 25,000 ha) surrounding it. The park is of key importance for biodiversity including endemic species.

- The Main Activities include: i) Undertake detailed assessment and gap analysis of Maludam Peninsula Peatland Landscape; ii) Develop IMP for Maludam Peninsula including, revised National Park Management Plan, Buffer Zone Management Plan; Community Sustainable Development Plan; iii) Support priority management measures including, delineation and patrolling of National Park boundary and monitoring of management issues and wildlife; promotion of Maludam National Park and community ecotourism packages, enhancement of water management to maintain forest hydrology and reduce fire risks, promote sustainable land and forest management, engage local community groups to improve livelihoods while at the same time rehabilitating peatland areas, and enhance management practices of agriculture and plantations on peat .

Project Management and Costs

- Project management: At the national level, the Project will be managed by a National Project Management Office (NPMO) hosted by the Forestry Department of Peninsula Malaysia (FDPM) in Kuala Lumpur and under the guidance of a National Peatland Steering Committee (NPSC) and National Peatland Working Committee (NPWC). The Project Director will be the Senior Director of Forest Management Division of FDPM, supported by the Wetlands Forest Management Section. The Secretary General of the Ministry of Natural Resources and the Environment (NRE) of the Federal Government will chair the NPSC. NRE will also play a role in various aspects of project management and implementation, including policy dialogue, reporting to relevant national and international processes, financial oversight, supporting engagement of other government ministries and State governments, as well as, support and guidance to the NPMO. The NPMO will be responsible for overall project (all components) planning and implementation including consolidation of the Annual Work Plan and Budget (AWPB) and procurement plan, coordination of implementation, monitoring across different levels of government, knowledge management, consolidating financial statements of expenditures, and reporting to IFAD in line with agreed procedures.

- At the sub-national level, four State Project Management Offices (SPMOs) will be established and based respectively at the State Forestry Departments in Selangor, Pahang, and Sabah, and either the Sarawak Forest Department. The SPMOs will work under the guidance of respective State Steering Committees (SSC) chaired by UPEN (State Economic Planning Unit) in Sabah and Selangor, the State Economic Planning Division (BPEN) of Pahang, and the State Planning Unit of Sarawak, to guide the project at state level (Component 2). SPMOs will also be responsible to coordinate and provide necessary assistance for the success of project implementation at landscape level (Component 3).

- In Sarawak, for component 2, Output 2.1 will be facilitated by the state Ministry of Urban Development and Natural Resources; The state Department of Agriculture will facilitate Output 2.2 and the Natural Resources and Environment Board will facilitate state level activities for Output 2.3. The Sarawak Forest Department is appointed as the lead agency to coordinate and implement Output 3.4 for the Maludam Landscape. The Forestry Department is still finalising arrangements for the field office.

- For implementation at site level in Pahang, Sabah and Selangor, project activities will be managed from each corresponding SPMO in consultation with Landscape Working Groups (LWG) at district/landscape level. In Sabah, a landscape level working group will also support the implementation work.

- Project Costs: Total project costs are estimated at USD 62.14 million. GEF financing is USD 9.43 million. Anticipated co-financing of approximately USD 52.71 million is expected to come from various sources, including Federal and State governments, the private sector, IFAD and Civil Society Organisations (CSOs). Further Information on Project costs and co-financing is given  below and in Appendix 7.

Logical Framework

| Results Hierarchy | Indicators |  |  |  |  | Means of Verification |  |  | Assumptions (A) / Risks (R) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Name | Baseline | YR1 | Mid-Term | End Target | Source | Frequency | Responsibility |  |
| Goal: To sustainably manage peatlands in Malaysia in an integrated manner to conserve resources, prevent degradation and fires, and generate benefits for current and future generations |  |  |  |  |  |  |  |  |  |
| Development Objective: Strengthen national policy and institutional capacity for implementing peatland-related strategies and plans and to enhance integrated peatland management in targeted landscapes | - National Action Plan on Peatlands 2021-2030 - Number of tonnes of GHG emissions (CO2e) avoided and / or sequestered - Number of households (HH) benefiting from sustainable peatland management (with> 50% women) | None None None |  | Prepared 1.0 million MT CO2e mitigated 300HH | Adopted, resourced and under implementation 3.06 million MT CO2e mitigated 1000HH | NPMO annual reports, GHG monitoring reports Report on community engagement | Annual Biennial (every two years) Annual | NPMO BPASPI SPMO/NPMO |  |
| Outcome 1: Enhanced resources, multi-stakeholder involvement and capacity for implementing the National Action Plan on Peatlands and other policies and plans up to 2030 | % increase in financial resources (from public, private and external) specifically channelled for sustainable peatland management | To be calcu-lated at project start up |  |  | 30% increase in total financing | Report on funding allocations for 2021-25 NAPP investment priorities | annual | NRE, NPMO |  |
| Outputs: 1.1 Policies, guidelines, institutional arrangements and capacity for sustainable peatland management enhanced | - Number of new or revised laws, regulations, policies, plans or strategies proposed to national-level policy makers for approval, ratification or amendment | 0 | 0 | 3 | 5 | NPMO annual reports, NPSC meeting minutes | Annual report and NPSC meeting minutes | NRE, NPMO | Multiple sectors work with NRE to incorporate peatland issues into policies (A) |
| 1.2 Investment framework for NAPP 2021 – 2030 developed and adopted | - NAPP investment framework adopted by national and state-level stakeholders and mainstreamed into national development plan 2021-2025 | No | None | Under preparation | Adopted | NPMO annual reports, NPSC meeting minutes | Annual report and NPSC meeting minutes | NPMO | National development planning agencies will recognise importance of peatlands (A) |
| 1.3 Knowledge management and exchange enhanced to support scaling-up of sustainable peatland management | - Peatland Knowledge management system established and being used. | No | Under prepa-ration | Estab-lished | Being used by more than x stakeholders | NPMO annual reports, SPMO reports | PMO reports | PMOs | Different agencies and sectors willing to share knowledge (A) |
| Outcome 2: Improved sustainable management of peatlands in target states | Increase in the use of sustainable management practices in agriculture and plantations located on peatlands | To be deter-mined during inception phase |  | Baseline + 100,000 ha | Baseline + 300,000 ha | Monitoring reports on application of best management practices | Annual | SPMO, NPMO |  |
| 2.1 State Action Plan on Peatlands (SAPP) developed and adopted by Pahang, Sabah, Sarawak and Selangor | - Adoption of SAPPs | none | Prepa-ration initiated | 2 prepared | 4 adopted | NPMO annual reports, SSC, NPSC meeting minutes | Annual | NPSC and SSC | All key stakeholders in targeted states support development of SAPP (A) |
| 2.2 Best management practices introduced in agriculture and plantation sectors in Pahang, Sabah, Sarawak and Selangor | - BMP guidelines and training materials reviewed and enhanced and ≥ 500 persons trained (with >25% being women) | limited | Train-ing mate-rials deve-loped | 250 participants in 9 pro-grammes | 500 participants in 18 programmes (with >25% being women) | NPMO annual reports, NPSC meeting minutes, SPMO reports | Annual | NPSC and SSC | All targeted smallholders and commercial plantations on peat agree to be certified with MSPO Standard (A) MPIC, MPOB, MPOCC support capacity building and certification process for plantations and smallholders on peat in targeted areas (A) |
| 2.3 Best management practices for peatland fire prevention and control in four states | - BMP guidelines and training materials reviewed and enhanced and ≥ 300 persons trained | limited | Train-ing mate-rials deve-loped | 130 participants in 5 pro-grammes | ≥ 300 participants in 10 programmes | NPMO annual reports, NPSC meeting minutes, SPMO reports | Annual | NPMO and SPMO | Effort on peat fire prevention would reduce expenses for fire-fighting and suppression on peatland and more resources will be allocated to prevention (A) |
| Outcome 3: Integrated Peatland Management Plans (IMPs) adopted and implementation initiated by multiple sectors in five peat landscapes | Area of peatland-dominated landscapes with IMP adopted and being implemented by multiple sectors | 80,000 ha |  | 150,000 ha | 450,000 ha | NPMO reports NPSC meeting minutes | Annual | NPMO |  |
| 3.1. Review, update and implement existing Integrated Management Plan (IMP) for North Selangor Peat Swamp Forest (NSPSF), and develop a new IMP for South Selangor Peatland Landscape | - IMPs for NSPSF and SSPL adopted and implemented | IMP for NSPSF | Preparatory work | IMP for north Selangor updated and under implementation | IMP for south Selangor adopted and under implementation | Selangor SPMO reports and SSC meeting minutes | Semi-annual | SPMO and SSC | IMP-SSPL adopted by the State Government and sufficient resources allocated to implement the IMP (A) |
| 3.2. Review existing IMP for Southeast Pahang Peat Swamp Forest, and update and expand the scope to cover the Southeast Pahang Peatland Landscape | - IMP for SEPPSF reviewed and to be included in IMP for SPPL | IMP for SEPPSF | Preparatory work | Expanded IMP prepared | Revised IMP adopted and under implementation | Pahang SPMO reports and SSC meeting minutes | Semi-annual | SPMO and SSC | Active engagement and support from broad stakeholders for development and adoption of IMP (A) |
| 3.3. Develop and implement new landscape level IMP for Klias Peninsula Peatland Landscape in Sabah | - IMP for KPPL developed, adopted and implemented by the State Government |  | Preparatory work | IMP under preparation | IMP adopted and under implementation | Sabah SPMO reports and SSC meeting minutes | Semi-annual | SPMO and SSC | Active engagement and support from broad stakeholders for development and adoption of IMP (A) |
| 3.4. Develop and implement a landscape level IMP in the Maludam Peninsula, Sarawak | - IMP for MPPL developed, adopted and implemented by the State Government | Mgmt. plan for National Park | Existing NP management plan reviewed | IMP under preparation | IMP adopted and under implementation | Sarawak SPMO reports and SSC meeting minutes | Semi-annual | SPMO and SSC | Active engagement and support from broad stakeholders for development and adoption of IMP (A) Land conflict between Oil palm plantation and local community cannot be resolved disrupting work (R) |

# Strategic Context and Rationale

### Country and rural development context

- Demographics and population: As of its 2010 census, Malaysian population was 28,334,135 and ranked as the 43rd most populated country. The total number of households in the 2010 census was 6.35 million compared to 4.8 million households in the 2000 census, which indicated a 32 percent increase or an average annual increase of 3.2% during the period of 2000 and 2010. According to the Department of Statistics, the total population of Malaysia in 2016 was 31.7 million persons, with 16.4 million males and 15.3 million females. Population by age structure is the following: 24.5% 0-14 years; 69.5% 15-64 years (working age); and 6% 65 years and above. Malaysian citizens consist of Bumiputera, Chinese, Indians, and other minority groups.

- Poverty level: In May 2017, the Government of Malaysia announced that, the poverty rate had declined from 3.8% in 2009 to just 0.6% in 2014, while hard-core poverty was almost completely eradicated.

- Agriculture and Agri-business: Malaysia’s agricultural sector consists of a mix of large plantations (state-owned, government-linked and private) and smallholder farms. The large plantations tend to focus on commodities that are important export products (particularly palm oil and rubber), while the smallholder farmers’ focus on rice, fruit, vegetables, and oil palm, and others. Based on information from the Department of Statistics, agriculture/plantation/forestry sector expanded in 2015 with a contribution of 8.9% to 2015 Gross Domestic Product (GDP), of which oil palm contributed 46.9%, livestock 10.7%, rubber 7.2%, fishing 10.7%, forestry and logging 6.9% and other agriculture 17.7% (see Figure 1 below). Malaysia was ranked the second largest world palm oil producer in 2014 with approximately 19.7 million tonnes, after Indonesia (29 million tonnes).

- The Agriculture sector (see Figure 1) comprising of forestry, rubber, oil palm, fishery, livestock and other agriculture is expected to transform and modernise its operation to achieve the 11th Malaysian Plan’s target to become a sector that generates high and sustainable income. In 2015 the agriculture sector, contributed approximately MYR 94 billion or 8.9% of the Gross Domestic Products (GDP) of Malaysia. As included as one of the twelve National Key Economic Areas (NKEA). The agriculture sector is expected to provide significant contribution to the economic growth of the country. The agriculture sector (excluding oil palm and rubber) is also expected to have 3.5% annual increase of development and contribute to 7.8% of the GDP by 2020. It is expected to create 75,000 additional jobs, especially in rural areas, and a target has been set to increase farmers’ income by the range of double to quadruple.

###### Figure 1: Percentage Share to GDP by Kind of Economic Activity, 2015

(Constant 2010 prices) (Source: Department of Statistics, Malaysia)

- Agriculture sector challenges and trends: One of the challenges for the oil palm sector is the stigma associated with the commodity in international markets, especially Europe and USA, because of concerns related to deforestation, biodiversity loss, and climate change. This is driving certification schemes in Malaysia. Currently male workers dominate the agriculture sector with 75.7% employment, while the remaining 24.3 % are female workers. For oil palm and other agriculture commodities, salaries for workers are low and as such, do not attract much interest among the local communities.  As a result, foreign workers dominate the plantation sector, which is also leading to social tensions.

- Another challenge faced by the local communities is access to markets, and farmer and fisher folk are constrained to sell their products/yields to an intermediary at low prices. Local communities also have little capacity to produce value added goods that could generate additional income. Introduction of more processing and value added products could enhance the participation of women. Furthermore, in some vulnerable agriculture areas, flood and drought have also become a major threat particularly for smallholder farmers.

- Peatlands: Malaysia has approximately 0.7% of the global peatland area and 12% of the tropical peatlands in Southeast Asia, covering about 2.7 million ha, with the largest peatland areas found in Sarawak. Peatlands - formed from partially decomposed plant material accumulated over thousands of years under waterlogged conditions - sequester as much as 30 per cent of global soil carbon (equivalent to double the total carbon in the biomass of all the world’s forests). Peatland swamp forests are critical habitat for a significant number of threatened and endangered species, both flora and fauna. Approximately 28% of Malaysia’s peatlands remain under forest cover (see Table 3), the balance, totalling some 1.96 million ha, having been cleared and drained for agriculture, plantations and other development, leading to high greenhouse gas (GHG) emissions and loss of biodiversity.

###### Figure 2: Distribution of World Peat Map (Source: Parish et al, 2008)

- According to NRE (2016), based on a study in 2014 and further information from the Sabah and Sarawak State Governments in 2017, the estimated total peatland area in Malaysia is 2,717,969 ha. Pahang, Sabah, Sarawak and Selangor contain a total of 2,344,211 ha or approximately 86% of the total peatlands in the country.

##### Table 3: The area (ha) of peatlands and land uses in Peninsula Malaysia, Sabah and Sarawak

| Area | Total peatland | Peat swamp forest | Oil palm (on peat)^^ | Other (incl. other agric., settlements, etc) |
| --- | --- | --- | --- | --- |
| Peninsular Malaysia | 880,389 | 270,176 | 207,458 | 402,755 |
| Sabah | 192,000* | 27,665^ | 21,406 | 142,929 |
| Sarawak | 1,645,580** | 459,000*** | 437,174 | 749,406 |
| TOTAL | 2,717,969 | 756,841 | 666,038 | 1,295,090 |

* Information from Department of Agriculture, Sabah (data of 2009)

** Information from State Planning Unit of Sarawak (data from Department of Agriculture, 2015)

*** Information from Sarawak Forest Department, 2015

^ Information Sabah Forestry Department (area of peat swamp forest in Forest Reserve), 2016

^^ Wahid, MPOB, 2010

Source: NRE 2016

- Drainage of tropical peatlands for agriculture and plantations causes long-term subsidence rates in the range of 2 – 6 cm/yr, and long term emission rates in the range of 50–55 tCO2/ha/yr; excluding the emissions spike shortly after drainage. Intense peatland fires can release up to 1,000 tCO2/ha during the fire season. In general, peatland fires in Southeast Asia undermine national economies and public health through premature deaths from respiratory disease, and affect about 50 million people in five countries in the region, in particular, Indonesia, Singapore and Malaysia.

- Key national policies and regulations affecting peatland use and management include the following:

- National Forestry Act 1984 (Amended 1993)

- National Forestry Policy 1978 (Revised 1992)

- Third National Physical Plan 2016-2020

- Fourth National Agriculture Policy (National Agro-Food Policy) 2011-2020

- National Policy on Biological Diversity 2016-2025

- National Action Plan on Peatland 2011-2020

- National Policy on Climate Change 2010

- National Wetland Policy 2005

- State Forestry Enactments

- Various state level enactments, ordinances, laws and regulations relevant to peatlands are listed in Appendix 3.

- Climate Change: Rising temperatures and sea levels have implications for Malaysia’s peatlands. As biological processes drive long-term rates of subsidence in drained peatlands, they are strongly temperature dependent. Some researchers (e.g., Ise et al, 2008) have concluded that peatlands will quickly respond to the warming expected during this century by losing additional soil organic carbon during dry periods. This would significantly increase rates of subsidence. Not only would this result in significant increases in GHG emissions from peatlands but also, increase flood risks and salinity intrusion. In extreme cases, land surfaces will settle below sea level.

- Key government institutions: At Federal level, the following ministries and agencies have important roles related to peatland management:

  - The Ministry of Natural Resources and the Environment (NRE). Lead agency to oversee and coordinate implementation of policies/regulations at national level, such as National Policy on Biological Diversity 2016-2025 (NPBD), National Wetlands Policy (2005), National Action Plan on Peatlands (NAPP)(2011) and the National Forestry Policy 1978 (Revised 1992). The Department of Environment (DOE) of the NRE is the national focal point for the ASEAN Agreement on Transboundary Haze Pollution (AATHP), which meets annually to update on country’s progress on smoke haze prevention measures. DOE has also been a leading agency for peatland fire prevention nationwide primarily through channelling resources for infrastructure such as fire towers, check dams, water piping, retention ponds and tube wells as well as facilitating enhanced monitoring through the National Peatland Fire Prevention Programme. The Forestry Department of Peninsula Malaysia (FDPM) and respective State Forestry Departments (SFD) play an important role in the rehabilitation and protection of the peatland forests.

  - The Ministry of Agriculture (MOA). The Ministry legislates, plans and implements policies and strategies for agriculture and development programmes. The Ministry also evaluates, coordinates and ensures the implementation of agro-food development projects/programmes, as well as conduct research and development, and innovation to enhance productivity and competitiveness in the agro-food sector. The current policy under the Ministry is the Fourth National Agriculture Policy, also known as National Agro-food Policy 2011-2020.

  - The Ministry of Plantation Industry and Commodities (MPIC). The Ministry formulates policies and strategies for the overall development of the plantation and the commodity sectors, supervises departments and agencies under the Ministry on financial management and implementation of plantation and commodities development programmes. It is spearheading work to enhance the management and sustainability of the oil palm plantation sector through the Malaysian Palm Oil Board (MPOB) and the Malaysian Palm Oil Certification Council (MPOCC).

  - The Ministry of Urban Wellbeing, Housing and Local Government. The Ministry plans and implements the ministry’s policies to achieve primary national development goals; provide adequate housing for all citizens, particularly for the low-income group; sets up local authorities which are strong and able to contribute to the establishment of a progressive society and a clean and healthy environment; provides efficient Fire and Rescue Services for the safety of life and property; and strengthens and implements physical, social, economic, and town and country planning in accordance with the Town and Country Planning Act 1976. The Fire and Rescue Department (BOMBA) comes under the Ministry, and is a key agency in suppression of peatland fires.

  - The Ministry of Science, Technology and Innovation (MOSTI). The Ministry aims to improve the competitiveness in the fields of science and technology through the generation of knowledge and sustainable development. The identified departments/agencies from the Ministry are the Malaysian Meteorological Department (MMD) and Malaysian Remote Sensing Agency (MRSA).

- At state level, the following agencies and stakeholders have important roles related to peatland management (further information is given in Appendix 3):

##### Table 4: State level Agencies and their Duties/Relevant Responsibilities

| Agency | Duties/ Relevant responsibilities |
| --- | --- |
| State Economic Planning Unit (UPEN) for Selangor and Sabah/ State Economic planning Division of Pahang/ State Planning Unit of Sarawak | - Responsible for economic planning at state level and budgetary management and disbursement of funding allocations, including coordination of Government co-financing and in-kind contributions. - To be effective, the planned activities in the state peatland will be coordinated with development proposals and plan, for example for land development in the state land. |
| State Forestry Department (SFD) | - Administer and manage the state's forest resources based on sustainable forest management (SFM) concept in order to benefit the social, economic and environment to the people. - Act as the implementing agency for policies and enforcement of laws and forestry regulations. - Act as the implementing agency's development efforts, rehabilitation and reforestation through proper silvicultural practices for optimum and sustainable production of forest produce |
| Fire and Rescue Department (BOMBA) | - BOMBA is responsible for suppressing fire and provides training for the stakeholders on firefighting operations |
| Department of Agriculture (DOA) | - Provide consultation services and technical support in a package format to entrepreneurs, private organizations and agriculture development agencies. - Development of trained and skilled workforce to cater to the needs of the agriculture industry. - Develop Agriculture Food and Soil Information Centres for planning purposes and implement development programmes for the agriculture sector. - Conduct training at the agriculture Institute and Training Centre to fulfill the requirements for skilled workforce within the agriculture sector. - Monitor and control the quality of the country's agriculture resource and seedlings. - Assessing land and crop suitability classification and soil survey - Promoting sustainability agriculture and advisory services to smallholders - Implementing government agricultural policy - Promoting and implementing the Good Agriculture Practices |
| Department of Irrigation and Drainage (DID) | - Conserve, manage and develop water resources, land and related resources across all sectors within a river basin. - Implement erosion control plans across the country. - Integrated River Basin Development and Integrated Flood Management for flood management plans. - Provide Standards and Procedure for Urban Drainage Design for Peninsular Malaysia. |
| Department of Environment (DOE) | - To administer and enforce the Environmental Quality Act, 1974 including section 29(A), and Section IV of the Exclusive Economic Zone Act, 1984. - To ensure and sustain sound environmental management in the process of nation building. - A key activity is to study and assess development projects subject to the Environmental Impact Assessment order. - DOE also provides environmental inputs to state agencies to ensure that use of land and other natural resources is carried out in a manner that complies with the concept of sustainable development. |
| Department of Land and Survey | - Ensuring proper land administration by recording alienation and land-use changes - Determine exact boundaries of different land uses and ensuring their legal status |
| Department of Town and Country Planning (DTCP) | - Act as the principal adviser to the State Government on all matters of planning, including the preservation of land use and development. - Act as advisors to local authorities on town and country planning, and development and land use. - Implement and coordinate the standardization of the full implementation of the Town and Country Planning Act 1976 (Act 172) in all local planning authorities in Selangor. - Coordinate the preparation of the development plan of the State Structure Plan, Local Plan and Special Area Plan and research / special projects either ordered or on the initiative of the department based on ESA component adoption. - Provide advice to departments / agencies of the town and country planning. |
| Department of Minerals and Geoscience (DMG) | - To undertake systematic investigations in various geoscience disciplines such as geological mapping, groundwater resources, engineering geology, geological hazards, environmental geology, marine geology, geophysics, and others. - To collect, analyse and disseminate data and information pertaining to mineral exploration, mining and related activities. - To provide technical advisory and expertise services in the fields of mineral, geoscience, mining and quarrying. - To ensure that mining of minerals and related activities are carried out safely, efficiently and systematically. |
| Department of Wildlife and National Parks (PERHILITAN) | - Conservation measures and monitoring of wildlife - Coordinate the enforcement of wildlife protection - Objectives of department: - Protection, management and preservation of biodiversity for production benefits. - Protection and development of protected areas for the purpose of research, education, economic, aesthetic, recreation and ecological purposes. - Enhancement of knowledge, awareness and public support on the importance of biodiversity conservation. |
| Department of Veterinary Services | - Control, prevent and eradicate animal and zoonotic diseases. - Production of livestock, livestock produce and animal feed. - Training for the livestock and domestic animal industries. - Expand livestock production and animal health as well as general veterinary health. |
| Department of Health (DOH) | - DOH is responsible for a healthy community through:- - Provision of high quality, affordable and accessible healthcare service - Prevention and control disease - Protection of health of the population - Sustainable and continual health promotion in smart partnership with various agencies, organizations and the community |
| Department of Orang Asli Development / Jabatan Kemajuan Orang Asli (JAKOA). | - Responsible for the welfare and development of the various Orang Asli communities in Peninsular Malaysia - The Department provides welfare assistance, skills training and other human development programmes and social services such as childcare, community halls, etc. It is also responsible for the planning and development of Orang Asli Resettlement Schemes |
| District Offices/ District Land Offices | - Management development and disposal of land. - Provides technical services and enforcement. - Management of land title registration. - Management of land revenue. - Management Services include administration, human resources, finance and information technology. - Management of socio-economic development and the implementation of small-scale rural infrastructure projects. - Management of Disaster Management Committee at District level |
| District Municipality / Council | - Their functions are as local government of respective areas including provision and management of services such as waste disposal. - Enforcement and monitoring of development at the district level - Implementation of the local district plan |
| State Government linked corporation | - Responsible for the development of farming and agro-based industry to improve the socio-economic and development. - Involved with commercial agricultural projects, palm plantation development, mining (clay, quarry and sand) and tourism |
| Other relevant stakeholders | - Interested parties (NGOs, JKK kampong, Head of Village, CBOs) - Work together with government and others agencies to protect and support the government in creating national and local awareness of the importance of conserving the ecosystems - Land owners, local community involvement and support is important for a successful management programme that will involve the protection, monitoring, development, conservation and promotion in the buffer zone |
| Research institutions and universities (government and private) | - Undertaking fundamental and applied ecosystem research using federal funds adding to the overall understanding of these systems - Provision of expert opinions on issues related to peatland and water conservation management - Providing a pool of scientific expertise to undertake research and monitoring development and application (R,D & A) |

- Stakeholders at the landscape level include state agencies, local authorities, private sector, local communities and CSOs. Further information is given in Appendix 2, Annex A2-5.

### Rationale

- Peatlands are a fragile and unique ecosystem with important ecological functions and values. In addition to acting as repositories for biodiversity, peatlands in Southeast Asia are of global importance because of their ability to store an estimated 69 billion tonnes of carbon or approximately 3.6% of the world’s terrestrial carbon store. Malaysia’s peatlands contribute significantly to the global carbon store in this region with estimated storage of more than 9 billion tonnes38. Peatlands also play a critical role in the socio-economic wellbeing of the country, particularly for their biodiversity and hydrological values, timber and non-timber forest products, water supply, flood control and many other social, environmental and economic benefits.

- In Malaysia, peatlands are the most widespread type of wetlands occurring in more than eight (Johor, Kelantan, Perak, Pahang, Sabah, Sarawak, Selangor and Terengganu) of the 13 states. They cover an area of about 2.72 million ha (approximately 8% of the total land area). The largest area of peat — over 1.645 million ha — is found in Sarawak. Approximately 30% of the total peatland area in Malaysia is found in forest reserves. The remaining areas have been converted for other uses, while some are still designated as stateland forests. Peatlands are recognized as environmentally sensitive areas (ESA) under Section 6B of the Town and Country Planning 1976 (Act 172) in the National Physical Plan (NPP).

- The uses and values of peatlands in Malaysia can be categorized into those that pertain to socio-economics (e.g. forest resources, agriculture, infrastructure, community livelihood, etc.) and those that pertain to protective or conservation purposes (e.g. biodiversity conservation, forest, flood mitigation, water supply and climate regulation).

- Increasing pressures for land development (e.g. agriculture, infrastructure) and timber extraction have heavily affected peatlands in Malaysia over the past 50 years. Land conversion for primarily agricultural purposes has generated economic benefits; however, the management of these lands is creating major challenges. As of 2015, more than 1.5 million ha of peatlands in Malaysia have been developed for oil palm, agriculture and urban areas. However some of these developments have faced challenges such as subsidence, fire, low productivity etc,. In addition, peatland landscapes have been fragmented, drained and degraded and serious droughts have increased in frequency. As a result, peatland fires have been growing in extent and severity over the last few decades. Peatland drainage and fires are a major contributor of greenhouse gas (GHG) emissions thus creating a positive feedback loop between climate change and further peatland degradation.

- While the management of peatland areas in Malaysia comes under the jurisdiction of the State Government wherein the peatland is found, the following barriers often face sustainable peatland management:

- Inadequate Policies and Weak Institutional Framework - Currently, there is a lack of specific policies and guidelines related to sustainable peatland management in Malaysia. Existing policies and guidelines do not provide proper guidance, which further contributes to the unsustainable use and degradation of peatlands and their resources. Lack of field-level coordination among key government institutions level has led interventions related to sustainable peatland management to be inefficient and sporadic.

- Inadequate Information on Peatland Management - There is inadequate information available on sustainable peatland management methods and practices. This is due in part to limited information sharing by the respective government agencies, departments and ministries, related to peatlands and their resources.

- Historical legacy of unsustainable agricultural production or timber harvesting in peatlands - Peat soils — particularly those exceeding 2 m in depth — are generally marginal to poor for agriculture. Poor or unsustainable practices and the abandonment of agricultural projects leave peatlands vulnerable and susceptible to further degradation. Timber harvesting also impacts peatlands, especially when tracked excavators were introduced for the canal extraction system (i.e. large canals were constructed to drain water from peat swamp forests to facilitate easier access for heavy vehicles and for the extraction of timber). This system induces over-drainage and lowers the naturally high water table when the area is abandoned. This results in subsidence, soil compaction, drying out and fire susceptibility. While this system has now been replaced in some sites with more environment-friendly Reduced Impact Logging (RIL) methods such as Railway, Kuda-kuda system and Long haulage Cable Logging system. To a certain extent, the negative effects of the previous extraction systems continue to impact peatlands.

- Over-drainage from Forestry and Agricultural Practices - One of the prominent natural characteristics of peatlands is their high water table. This naturally occurring high water table is an important factor in their formation and stability. Over-drainage of peatlands can have detrimental effects on the ecosystem. The threats of over-drainage stem from forestry and agricultural practices in peatlands. Agricultural and forestry practices often involve poor water management practices in peatlands, which significantly lower the water table and lead to the drying and breakdown of peat soils, i.e. peat subsidence. This in turn affects biodiversity. In severe cases of over-drainage, subsidence of up to 5 m have been recorded over a period of 40 years. Such negative impacts tend to be exacerbated during the dry season or periods of drought.

- Peatland Fires and Associated Haze Pollution - Peatland fires in Malaysia and in the Southeast Asian region as a whole have been a common phenomenon over the past 20 years. They are often associated with periodic drought occurrences and closely linked with forest clearance and drainage activities by the forestry and agricultural sectors. The El Niño Southern Oscillation (ENSO) cycles also play a significant role in peatland fire incidents. Detrimental impacts associated with peatland fire incidences are the negative effects on the socio-economy of local communities who are dependent on peatland resources, atmospheric pollution and the significant decrease or loss of important floral and faunal populations. Peatland fires are a major source of GHGs, with annual emissions estimated at 94 million tonnes CO2eq from Malaysia. The impacts of climate change are further increasing the incidences and intensity of peatland fires in Malaysia. The incidence of peatland fires in Malaysia has increased significantly in recent years, with the cumulative hotspot count for Peninsular Malaysia in 2014 exceeding all other years on record.

- Malaysia has recognised the significance of peatland ecosystems and has outlined a broad range of actions to maintain them in its National Action Plan on Peatlands, which was adopted in 2011 and which covers the period 2011-2020. The importance of conserving and restoring peatland ecosystems has also been highlighted in the National Policy on Biological Diversity 2016-2025. Malaysia has also recognised the increasing extent and frequency of peatland fires and associated smoke haze pollution, and updated its National Haze Action Plan in 2013. In 2015, NRE adopted a Standard Operating Procedure for Prevention of Peatland Fires. The government has also introduced measures to enhance the sustainable management of production landscapes in peat through establishing a target for mandatory certification of all plantations and smallholder production on peat (and other soils) under the Malaysian Sustainable Palm Oil (MSPO) Standard by 31 December 2019 as well as other measures to enhance sustainability of agriculture and forest management. Integrated management plans have been developed for large peatland complexes in Selangor and Pahang States as well as management plans for selected peatland sites in Sabah and Sarawak. However, there remains much work to complete to achieve the targets under the national plans for ensuring the protection and sustainable management of all of Malaysia’s peatlands.

# Project Description

- The project’s theory of change is based on the assumption that addressing the complex challenge of sustainable peatland management (SPM) requires coordinated and complementary actions in several key thematic areas, at multiple geographic levels, and systematically over time. Malaysia has 2.7 million ha of peatlands which originally were all covered with peat swamp forest and providing critical ecosystem services for water resource management, climate regulation and biodiversity conservation. Over the past fifty years, the majority of peatlands have been cleared and drained for agriculture and plantation purposes. While such uses have been important for economic development, there have been significant challenges including land subsidence,, disruption of water supply and increased flooding, loss of biodiversity and increasing peatland fires and GHG emissions.

- In some states, government expenditure for peatland fire-fighting is higher than that for peatland management and fire prevention (whereas international experience indicates that more than 80% of the resources should be allocated to fire prevention rather than fire suppression).   Management of peatlands is also fragmented between forestry departments managing those portions remaining under forest cover, and agriculture departments and plantation agencies, local government, private sector and communities managing those areas outside forest reserves, which have been developed. A significant area (especially those outside of forest reserves with no active agriculture or plantations) has no clear management and is increasingly prone to fire. A further complexity is that policy is set at a national level, but all land is managed at the state level. At state level, there are relatively limited resources for active management or rehabilitation of degraded peatlands outside of forest reserves. Even within forest reserves and protected areas, there are often insufficient management resources.

- The project’s theory of change thus operates along three distinct dimensions: thematic, geographic and time. The thematic aspect considers the complementary roles of planning, capacity building, policy reform, demonstration and uptake, knowledge and financial resource allocation. The geographic dimension takes into account how these themes operate and interact at local, state and national levels, and, as part of ASEAN Programme on Sustainable Management of Peatland Ecosystems 2014-2020 (APSMPE), at ASEAN level. The temporal aspect relates to the development of an investment framework that straddles two national planning and budgeting cycles extending up to 2030. The project drives elements of change within each individual theme and geography over time, while encouraging synergies amongst and between the elements that further magnify the individual changes.

- Given the complexity of each of the above dimensions, they are presented separately below. In each case, the direct project actions and outputs are highlighted in bold as the root causes of the subsequent changes that are expected.

- In thematic terms, the project supports multi-sectoral policy dialogue based on the multi-sectoral nature of peatland management challenges (including forest, plantation, agriculture and water resource management). A quick look at the long list of institutional stakeholders (see Paras. 52-54 above) should suffice to indicate the importance of this theme. Policy dialogue through multiple mechanisms depending on geographic level (see below), together with targeted analysis, is expected to lead to enhanced enabling environments (local, state, national) - based on harmonized policy and regulatory changes and reflecting better understanding of cross-sectoral needs and concerns. Multi-sectoral dialogue will also help to ensure effective private sector participation in the process.

- Policy work will be closely complemented by support to planning, which has two facets. First, the project will help to mainstream SPM into multiple policy and planning documents, e.g. Malaysia National Plan, National Physical Plan, REDD+ policies, wetland policies, etc. to ensure that such plans are contributing to sustainable peatland objectives. In addition, peatland-specific planning documents, including support for revision of the National Action Plan on Peatlands (NAPP), new State Action Plans on Peatlands (SAPPs) and landscape-level Integrated Management Plans (IMPs), will define clear agendas for achieving sustainable use of this land type.

- The above policy and planning efforts would likely suffer at the implementation stage without efforts to increase institutional capacities for implementation. Efforts in this area will be targeted at individuals and units responsible in key areas, particularly those where new mandates and responsibilities may be emerging in connection with the above policy and planning reforms.

- A closely related factor is ensuring SPM involves the flow of financial resource allocations for operations and investment, and this brings in the temporal aspect of the work, as sustained efforts will be necessary for changes on the ground to manifest itself. Without dedicated financial allocations to priority activities, capacities will remain unused while plans and policies will not be implemented. Underpinning the project’s financial resource strategy is a two-pronged effort to produce an overarching cost-benefit analysis demonstrating the economic costs of mismanaged peatlands and the corresponding benefits of investing in SPM, along with work to assess the potential of landscape-level financing options based on Payment for Ecosystem Services (PES) generated by peatlands and co-investments from those benefiting from the use of peatlands. These areas of work will help to build support for a 10-year investment framework to be developed by the project. The 10-year investment framework (2021 – 2030) will straddle two 5-year Malaysia National Plans (12th and 13th MNPs), and will identify a hierarchy of priorities targeting all levels, to be financed by public, private and development cooperation financing, as well as, international climate change and environmental funds. SMPEM will build capacity for mainstreaming the investment framework into the 12th MNP and it is expected that this work will be replicated during the development of the 13th MNP. Taken together, these activities and outputs will ensure that the substantial investment and operating costs of achieving and maintaining SPM are well resourced financially over the medium-term.

- Demonstration activities will allow the project both to create direct, tangible impacts at site and broader state levels while, as the term implies, demonstrating, and raising awareness of, effective approaches to SPM and thereby providing tested approaches for scaling up. Multi-stakeholder consultation forums will be created to engage local communities, Orang Asli, private sector actors and government agencies to develop effective solutions for SPM. Gender equity and socio-economic / community empowerment will be important themes at each demonstration site. Additional key demonstration / learning themes will include: landscape level planning and water management, fire prevention, peatland agro-forestry, sustainable agriculture and plantation management and private sector engagement.

- Altogether, the project’s thematic theory of change argues that integrated support to planning, policy, capacity building, financial resource allocation and demonstrations will lead to well-coordinated and rationalized implementation of plans and related actions at national, state and site levels. Change will emerge from a combination of regulatory efforts and enhanced recognition of financial feasibility. These actions, in turn, will generate positive impacts in terms of GHG emission reductions, biodiversity conservation and reduced land degradation, together with an extensive array of socio-economic benefits (see Section IV.C. Benefits).

- The geographic dimension of the theory of change is based on four geographic levels. Working from bottom up, the project assigns a significant portion of its resources to the landscape level. Five key demonstration sites will be supported across the four states. The site definitions themselves are an important aspect of the project’s theory of change, as they are based on peatland landscapes (or peatland basin/hydrological unit). This choice is based on an acknowledgement of the inter-connectivity of peatland hydrological systems, which are in no way reduced by administrative boundaries between, for example, forest reserves and surrounding productive landscapes. In addition to site-level benefits, particularly for biodiversity and GHG mitigation, work at the project landscapes will be important for generating lessons learned, which will be carefully assessed and shared at each of the project’s higher geographic levels.

- At state level, the project aims to expand the scope and scale of impacts generated at site level to additional peatland areas. In developing State Action Plans for Peatlands (SAPPs), the states will follow a common methodology aimed at ensuring overall SPM results. State-level work will focus on sustainability aspects of existing forestry, agriculture and plantations on peatlands, as well as, fire prevention and associated contingency planning. Lesson learning among states, both from work in these two areas and from site-level work, will be an important state-level activity.

- At national level, change is designed to flow from the enhanced enabling policy, regulatory and financing environment, national-level plans and investment planning support, and enhanced capacities, together with coordination and support for knowledge management. Finally, the national-level component will serve as a connector to ASEAN-level work through the APSMPE.  The linkages will be supported by IFAD's US$3.5 million regional grant to the ASEAN Secretariat for the project on Measurable Action for Haze-Free Sustainable Land Management in Southeast Asia (MAHFSA).

### Project Area and Target Group

- Geographical targeting: The project includes a national-level component as well as state and site-level components in Pahang, Sabah, Sarawak and Selangor. Further details of the targeted landscapes are given in Annex A2-5 in Appendix 2.

- Target population and expected benefits: Peatlands play a critical role in the socio-economic well-being of the country, particularly by generating ecological and hydrological values, timber and non-timber forest products, water supply, flood control and many other social, environmental and economic benefits. Target populations include communities in identified peatland hydrological landscapes, especially poor and marginalised indigenous communities.

### Development objective and impact indicators

- The project goal: To sustainably manage peatlands in Malaysia in an integrated manner to conserve resources, prevent degradation and fires, and generate benefits for current and future generations .

- The goal is derived from the Malaysian National Action Plan on Peatlands (NAPP) adopted in 2011. The project will also support Malaysia’s contribution to the six targets of the ASEAN Programme on Sustainable Management of Peatland Ecosystems 2014-2020 (APSMPE).

- The project’s development objective is to strengthen national policy and institutional capacity for implementing peatland-related strategies and plans and to enhance integrated peatland management in targeted landscapes

- The project’s outcome or impact indicators are shown in the above logical framework matrix. They are as follows:

- 3.06 million metric tons of CO2eq mitigated;

- 30% increase in total financing for sustainable peatland management;

- 390,000 ha of peatland currently under agriculture and plantations, implement sustainable  management practices to reduce peatland degradation;

- At least 450,000 ha of peatland landscapes under integrated management plan (IMP) implementation

### Outcomes/Components

Component 1: Enhanced policy dialogue and improved institutional capacity for development and implementation of peatland related strategies and plans

Outcome 1. Enhanced resources, multi-stakeholder involvement and capacity for implementing the National Action Plan on Peatlands and other policy and plans up to 2030

- Component 1 will focus on strengthening national frameworks and capacities for the sustainable management of peatlands and peatland ecosystems in Malaysia, with an emphasis on multi-sectoral aspects of peatland management. Institutional capacity needs to be strengthened to effectively implement the relevant national policies and actions particularly those identified in the National Action Plan on Peatlands (NAPP), which was approved by the Malaysian Cabinet in 2011 (see Annex A2-2). Similar capacities will be needed for implementing the State Action Plans on Peatlands (SAPPs) being produced under Output 2.1.

- Work under this component will enable key agencies to review and mainstream peatland issues into national policies that are peat-relevant. These include the Third National Physical Plan, National Agro-Food Policy (replaced National Agriculture Policy since 28 September 2011), National Forestry Policy, National Wetlands Policy, National REDD+ Policy, National Policy on Biological Diversity, among others.

- The component will support establishment of a multi-stakeholder network of government agencies across sectors and levels, as well as the private sector, civil society and local communities to enhance collaboration and joint action to sustainably manage Malaysia’s peatlands. Finally, it will develop a longer-term investment and financing framework to support sustainable peatland management in the country.

- A key targeted outcome of this component is a 30% increase in total funding for sustainable peatland management. Increased funding allocations will also be better coordinated—particularly between public and private sectors—and focused on priority issues as identified by the NAPP and associated policy frameworks. Finally, enhanced capacities will help to ensure that financial resources, once mobilized, are effectively disbursed and monitored.

Output 1.1 Policies, guidelines, institutional arrangements, and capacity for sustainable peatland management enhanced

- The main activities will include: i) Strengthen and support operations of the National Peatland Steering Committee (NPSC) and the associated National Peatland Working Committee (NPWC); ii) Provide a package of strategic technical support for the SPMEM Project implementation; iii) Review implementation of existing National Action Plan on Peatlands (NAPP) and develop the NAPP 2021 – 2030; iv) Support capacity building and implementation of the NAPP and peatland-related aspects of the National Policy on Biological Diversity (2016-2025); v) Mainstream peatland issues into relevant national policies and plans; vi) Develop and promote use of guidelines for sustainable management of peatland landscapes; and  vii) prepare a National Peatland Directory.

- By the end of the project, key agencies will benefit from enhanced capacities to coordinate and contribute to multi-stakeholder efforts to conserve and rehabilitate Malaysia’s peatland ecosystems through, among others, the NAPP, SAPPs and landscape-level plans.

Output 1.2 Investment framework for NAPP 2021 – 2030 developed and adopted

- This output will focus on developing, and obtaining commitments to implement, a ten-year investment framework to channel financial resources for the implementation of the new NAPP (2021-2030). The investment framework will be split between activities at national and state levels, the latter to include landscape/site-level actions. A multi-stakeholder platform at national level will guide and monitor implementation of the framework, which will enable predictable funding flows and potential for joint programmes and project development among States. This collaborative approach will reduce duplication and parallel initiatives and generate more synergistic action, as well as helping to secure funding from private sector and international sources. The project will also help establish mechanisms to track fund flows and monitor implementation progress.

- Main Activities include the following: i) Undertake an economic analysis of the long-term costs and benefits of existing land-use systems and future scenarios of peatland quality in a changing climate; ii) Develop models of co-investment mechanisms for peatland users; iii) Identify the required costs for the NAPP priorities and implementation by relevant actors (including government institutions, private sector, and other partners) and prepare an investment framework for the NAPP 2021-2030; iv) Mainstream NAPP investments into the 12th Malaysia Plan (2021-2025) and relevant state development plans; v) mobilise supplementary finance from private sector, international environmental and climate funds, and bilateral and multilateral sources in line with the NAPP investment framework.

Output 1.3: Knowledge management and exchange enhanced to support scaling-up of sustainable peatland management

- The Project will establish a knowledge management (KM) system to document and synthesize successful approaches and technologies for sustainable peatland management that have been implemented in the country, and for sharing experiences with other countries. This will include, but not be limited to, experience and lessons gained from the project’s own demonstration activities. The KM system will identify dissemination pathways for scaling up best practice and for informing evidence-based policy dialogue at all levels. This work will help to speed up broader adoption / uptake of demonstrated sustainable peatland management approaches, especially by the private sector and state governments.

- The project will support the organization of workshops, trainings and peer learning programmes to enhance the capacity and awareness of relevant stakeholders, including government agencies, private sector, civil society organisations (CSOs) and local community groups. This country-based knowledge management system will be linked to a regional platform established within the framework of the ASEAN Programme on Sustainable Management of Peatland Ecosystems (APSMPE) thereby helping to ensure that lessons from other countries’ experience are also taken into account.

- Main Activities include: i) Develop a knowledge management (KM) strategy for peatlands targeting relevant stakeholders at all levels; ii) Establish a knowledge management system by strengthening  knowledge repositories and pathways for dissemination; iii) collate existing materials as well as develop and share knowledge and lessons learned from state and site level activities through outreach programmes; iv) Awareness raising on sustainable peatland management; v) Engage in knowledge sharing and coordination activities at regional and international levels; vi)  Support collation and analysis of information on GHG emissions from peatlands to support government assessing progress on national GHG reduction targets and reporting; and viii) Monitoring and Evaluation (M&E) of the project implementation.

Component 2: Enhanced Management framework and practices for sustainable management of peatlands in Pahang, Sabah, Sarawak and Selangor.

Outcome 2. Improved sustainable management of peatlands in target states

- Peatlands are the most important of Malaysia’s wetland types in terms of biodiversity, area and biogeography, accounting for approximately seventy-five percent of total wetland area. Malaysia has approximately 2.7 million ha of peatland. In Malaysia, land management is under the exclusive jurisdiction of state governments. As such, the development of State Action Plans for Peatlands (SAPPs), including investment frameworks, is necessary for effective conservation of peatland resources and ecosystem services and thus for ensuring long-term viability of productive investments on peatlands. In Malaysia, about 60% of the peatlands have been developed for oil palm and other agricultural uses, while most of the remainder is in forest reserves,  protected areas and some stateland forests or stateland.

- Component 2 focuses on sustainable management of peatlands at the state level to reduce GHG emissions, and generate biodiversity and sustainable land, water and forest management benefits. It will focus on management of all peatlands, including promoting best agriculture, plantation, forest and land management practices across peatland landscapes as well as a shift from fire suppression to fire prevention.

- A key targeted outcome of this component is a 300,000 ha increase in the area implementing good management practices for peatland management as compared to the baseline. In addition important health and economic benefits for local populations from enhanced sustainable management and reduced peatland fires as well as global benefits in terms of GHG emissions reductions (projected to reach 3.06 million MT of CO₂e. This target will be achieved through a combination of support to best management practices in the agricultural and fire prevention and control. In both cases, work will be guided by the SAPPs, with similar benefits from planning as those described at national level under Component 1, i.e. enhanced co-ordination and prioritization due to multi-stakeholder engagement.

Output 2.1 State Action Plan for Peatlands (SAPP) developed and adopted by Pahang, Sabah, Sarawak and Selangor.

- The states selected for the development of SAPPs are Pahang, Sabah, Sarawak and Selangor. Together, these four states account for 86% of Malaysia’s peatlands and more than 90% of the Permanent Reserved Forest (PRF) and protected areas on peat. Each is managed and utilised under quite different legal and administrative structures. As a group, the four states represent a good cross-section of the ecological, legal, administrative and socio-economic conditions found in peatlands in Malaysia.

- Under this output, State Action Plans for Peatlands (SAPP) will be developed, covering the period 2019-2030. The SAPPs will complement the National Action Plan (NAPP) for Peatlands developed by NRE, which was adopted by the Malaysian Cabinet in 2011, as well as contribute to the updating of the NAPP for the period 2021-2030. Each SAPP will set down a vision, values and principles to guide state government policy and actions on peatlands in the respective state.

- To ensure consistency and a harmonised approach, SAPP development will be guided by a methodology and approach agreed at national level. A consultative process at the respective state levels will facilitate preparation of the SAPPs. The SAPPs will include a specific emphasis on enhancing the sustainability of existing production on peatland through improved sustainable land and water management practices as well as fire prevention and control. They will identify a hierarchy of priority actions, institutional responsibilities and budgetary requirements for sustainable peatland management in the respective states.

- Main Activities will include the following actions: i) Develop a workable methodology and approach for developing the SAPP including common scope, format, and sub studies for defining necessary actions, institutional responsibilities and budgetary requirements for sustainable peatland management in the respective states; ii) Establish institutional framework and develop SAPPs through multi-stakeholder consultation;, iii) Organise a consultative process in respective states to identify key management issues, agencies’ responsibilities and gaps; iv) Conduct comprehensive peatland inventory, land-use (change and trend) analysis, peatland hydrological assessment and economic analysis; improvement of sustainability of peatland use; and v)  undertake an assessment on Peatland Fire Prevention and Control in targeted states.

Output 2.2 Best management practices introduced in agriculture and plantation sectors in Pahang, Sabah, Sarawak and Selangor.

- Forestry, agriculture and plantation sectors are essential to the wellbeing of Malaysia’s population and economy. These sectors rely on peatlands, while simultaneously placing multiple pressures on them. Drainage and development of plantations and agriculture on peat, lead over time, to the loss of the peat soil through oxidation and compaction leading to subsidence and GHG emissions. Peatland drainage also increases the risk of fire within the development areas and in adjacent lands. More than 60% of peatland area in Malaysia is used for agriculture and oil palm plantations.

- This output will provide support and guidance to improve agriculture products and / or yields in existing agriculture and oil palm plantation on peat and to address issues related to drainage development, water management, fires, GHG emissions, subsidence and other impacts that affect the potential sustainability of agriculture and oil palm plantation on peatlands.

- The output will develop and promote sustainable peatland management and best management practices for the agriculture and plantation sectors, in close coordination with the Ministry of Plantation Industries and Commodities (MPIC) and the Ministry of Agriculture (MOA), together with respective departments, local communities and the private sector.

- The project will support the development of guidelines for sustainable management of existing plantations (building on RSPO and MPOB requirements for plantations on peatlands), agriculture (building on Malaysian Good Agriculture Practice Standards – MyGAP) and agroforestry on peatlands. The project will also support the target of the Malaysian Government to certify under the Malaysian Sustainable for Palm Oil (MSPO) all plantations in Malaysia before 30 June 2019 and all smallholders by the end of December 2019.

- An emerging approach for peatland management in the region is that of agroforestry. The project will explore options of new tree crops and agro-forestry options as an alternative to current oil palm or agriculture practices on peat.

- The following are the main activities: i) Review and enhance capacity for sustainable management of oil palm plantations on peat; ii) Review and enhance capacity for  sustainable agriculture on peat; iii) Work in partnership with private sector to identify and document the BMP sites for oil palm on peatland and improve practices of existing oil palm plantations on peat. iv) Empower local communities for sustainable peatland management  through training modules and TOT workshops and farmer field schools; v) Support certification of oil palm plantations and smallholders under MSPO; and vi)  Explore options for agro-forestry on peat.

Output 2.3 Best management practices for peatland fire prevention and control for reducing GHG emissions in four states

- In recent years, peatland fires have increasingly occurred in Pahang, Sabah, Sarawak and Selangor particularly during the prolonged dry weather between the months of February to May and July to October each year. The associated haze and pollution have had severe socio-economic, ecological and environmental impacts, especially on the public health of local populations. Many of these peatland fires are known to have occurred in degraded peatlands, logged-over forest reserves, secondary state-land areas, private sector lands and smallholder areas.  With comprehensive planning, adoption of innovative approaches and commitment will ensure success in peatland fire prevention and control.

- The NRE, through the Department of Environment (DOE), launched the National Peatland Fire Prevention Programme in 2009 to overcome peatland fire and haze. A total of US$ 10 million has been spent between 2009-2016 in seven states (Selangor, Pahang, Sabah, Sarawak, Johor, Terengganu and Kelantan) for construction of facilities and upgrading of infrastructure for peatland fire prevention and operation. Although the National Peatland Fire Prevention Programme has initiated prevention actions, nevertheless peatland fires have continued to occur because the fire prevention measures/ approaches need to be fine-tuned based on experience and also scaled up to cover all fire prone peatlands.

- In order to address this challenge, this output will support the development of best management practices (BMP) for peatland fire prevention and control guidelines. These BMP will be based on the four elements of the fire management cycle:  fire prevention, preparedness, response (suppression) and recovery.

- The Main Activities will include: i) Review, enhance and promote the use of the National Standard Operating Procedures (SOP) on Peatland Fire Prevention ii) Strengthen stakeholder engagement in peatland fire control and  iii) Enhance the effectiveness of the Fire Danger Rating System (FDRS) and stakeholders' preparedness in fire prevention and control

Component 3: Development and implementation of Integrated Management Plans (IMPs) for targeted, peatland landscapes

Outcome 3: Integrated Peatland Management Plans (IMPs) adopted and implementation initiated in five peatland landscapes

- This component is focused on the conservation and integrated management of selected critical peatland landscapes of key importance for biodiversity. Project interventions will seek to reduce threats to the critical biodiversity sites through various alternatives to baseline land management practices, including sustainable agriculture and plantation management, buffer zone establishment and management, ecotourism, hydrology management, fire prevention, and forest and land rehabilitation. Work will be undertaken through partnerships between government agencies, local communities and private sector. The interventions will take a landscape approach linking the management of the PSFs with the adjacent peatland areas under agriculture, plantation and other land uses. The Component will work in five peatland landscapes located in four states (Pahang, Sabah, Sarawak and Selangor).

- A key targeted outcome of this component is that at least 450,000ha of biodiversity-rich peatland landscapes covering a total of 537,643 ha and containing critical peatland ecosystems (which are mainly PSFs) covering 276,542 ha will be brought under the aegis of integrated management plans operating at landscape level. This will ensure more sustainable agricultural and plantation development in these areas, benefits to local communities and enhanced conservation of these critical ecosystems. Funding that will flow from SAPPs (see Component 2) and under the overall co-ordination of the NAPP (Component 1), will help to ensure the medium-term implementation of these landscape-level plans, and thus achievement of the above benefits

Output 3.1 Review, update and implement existing Integrated Management Plan (IMP) for North Selangor Peat Swamp Forest (NSPSF), and develop a new IMP for South Selangor Peatland Landscape

- North Selangor Peat Swamp Forest (NSPSF) is the largest remaining PSF on the west coast on Peninsular Malaysia. It is of international significance for biodiversity with a broad range of rare and endangered flora and fauna including six endemic fish species. In the past, the site has been subject to heavy pressure from logging due to the previous status as stateland forest. More than 6,000 ha of the forest have been burnt over the past 20 years, linked to drainage associated with a network of canals constructed for timber extraction, as well as active development of adjacent lands for plantations, mining and agriculture.

- The peatlands in southern Selangor State occur primarily in a peatland hydrological unit covering 50,000 ha. Significant portions of these peatlands were included in FRs gazetted starting in 1927 and were mainly forested until 1974, after which they were progressively converted for agriculture, plantation and urban development purposes. There still remains about 9,000 ha of PRF, which is still of significant importance for conservation of biodiversity as well as maintaining the hydrology of the surrounding areas. The site has been fragmented in recent years and subsidence, fires and land degradation have increased. Fires have significant socio-economic impacts on local community and on Kuala Lumpur International Airport, which lies mainly within the landscape.

- The main activities in North Selangor Peat Swamp Forest (NSPSF) will be: i) Assess the progress with implementation of the existing  IMP and update as necessary; ii) Develop an implementation plan and budget for the IMP-NSPSF for the period 2019-2023; iii)  Support active implementation of and reporting on IMP-NSPSF plan including forest and hydrology rehabilitation measures, (iv) community engagement and community based fire prevention and rehabilitation as well as sustainable agriculture and ecotourism; iv) Strengthen capacity of State Forestry Department and other stakeholders to monitor and protect forests and biodiversity and prevent fires in NSPSF; v) Strengthen capacity of State Forestry Department and other stakeholders; vi) Promote sustainable agriculture and plantation practices in the buffer zone, and vii) Support further development of the existing Centre of Excellence and related facilities for education, training, research and ecotourism purposes.

- The main activities in South Selangor Peatland Landscape (SSPL) will include the following: i) undertake detailed assessment for South Selangor Peatland Landscape/ Hydrological Unit;  ii) develop IMP for the SSPL to include community and stakeholder participation plan and sustainable landscape management plan (includes rehabilitation sub-plan, buffer zone management sub-plan, cooperative fire prevention sub-plan); iii) initiate implementation of the SSPL IMP including support  for implementation of the fire management plan for Kuala Langat North and South FRs; iv) introduce community-based forest rehabilitation and canal blocking/ rewetting and support community-based ecotourism; and v) promote best management practices for smallholder agriculture and plantations.

Output 3.2 Review existing Integrated Management Plans (IMP) for Southeast Pahang Peat Swamp Forest, and update and expand the scope to cover the Southeast Pahang Peatland Landscape

- Southeast Pahang Peat Swamp Forest (SEPPSF) is the largest peatland forest in Peninsular Malaysia. In the 1980s, it used to cover more than 300,000 ha but now the remaining forest is just over 100,000 ha primarily within the PRF. Peatland forest outside the PRF has mainly been logged and cleared or burnt and converted into plantation or agricultural land or remains under shrub or degraded forest. The SEPPSF is still of international significance for the conservation of biodiversity. An Integrated Management Plan (IMP) was developed in 2008 (with support from UNDP-GEF) for the period 2008-2015, for four separate forest reserves, which covered 90,000 ha of SEPPSF at the time. Pahang State Government through Executive Council Meeting in 2008 had approved 12,950 ha area from state land in between the SEPPSF to be gazetted as forest reserve to ensure stability and connectivity of South-East Pahang Peat Swamp Forest. Since 2008, almost all the forest outside the PRF as well as much of the buffer zones have been cleared and developed for plantations and/or degraded by fire. Large-scale fires have affected increasing portions of the landscape. One of the main root causes of the fire has been extensive drainage and disruption of hydrology in the state-land outside the forest reserve because of log extraction canals, oil palm plantation and infrastructure development.

- The project will focus on the Southeast Pahang Peatland Landscape (SPPL), which includes the 108,000 ha within forest reserves and approximately 122,000 ha of peatland on private or state-land surrounding it. Only by addressing the whole peatland landscape will it be possible to implement an integrated management approach, which can restore the natural hydrology and prevent expanding peatland fires and degradation.

- The Main Activities will include the following: i) Establish and support operation of a multi-stakeholder forum and governance mechanism for integrated management of SPPL; ii) Undertake a comprehensive assessment of the SPPL; iii) Review the previous IMP (2008-2015), and revise it to cover the whole peatland landscape and include new sub-plans on: landscape hydrology management; fire management; forest rehabilitation; community and stakeholder participation; plantation and agriculture management; and budget and implementation plan; iv) Implementation of priority fire prevention measures including improved water management in the peatland landscape; promotion of fire danger rating system and associated SOP in targeted communities and plantations; demarcation of forest reserve and buffer zones; enhancing capacity of plantations and other landowners in fire prevention and control; v) Work with targeted communities to enhance sustainable peatland management including community based peatland fire prevention and control; community-based peatland rehabilitation; enhancing livelihoods related to peatland products and ecotourism; vi) Rehabilitation of degraded peat swamp forest through enhanced natural regeneration techniques focusing on restoring natural water levels and preventing fire in portions of forest reserves affected by drainage and fire; development of tree nurseries for primary and secondary peatland forest species in collaboration with local communities; monitoring and enhancing where necessary natural regeneration; and development of Centre of Excellence and related facilities for education, training, research and ecotourism purposes; and vii) Enhance the management of agriculture and oil palm on peat in the landscape in particular by local communities and private sector; working with mills and refineries utilizing palm oil from the landscape to enhance the sustainability and certification of the supply chain.

Output 3.3 Develop and implement new landscape level IMP for Klias Peninsula Peatland Landscape in Sabah

- In Sabah, the project will focus on the Klias Peninsula Peatland Landscape (KPPL) that includes Klias FR, Padas Damit FR and Binsuluk FR, as well as large areas of plantations and community land between them. The Klias Peninsula in Southwest Sabah contains one of the largest areas of pristine PSF in Sabah covering an area of 12,504 ha within a peatland landscape of about 77,000 ha (and representing about 45% of total estimated pristine PSFs in the state). The landscape has been seriously affected by fire that has degraded 1,500 ha of forest reserve and 3,300 ha on the border of the forest reserve in 2016. Most of the rest of the landscape has been converted to agriculture and plantations.

- The Main Activities will involve the following: i) Undertake a detailed assessment of Klias Peninsula Peatland Landscape; ii) develop a comprehensive IMP for Klias Peninsula Peatland Landscape including cooperative fire prevention and management plan, water management plan, and alternative livelihood development; iii) Support priority management measures including promote fire prevention and risk reduction in agriculture and plantation lands, restore natural hydrology and support natural regeneration of degraded portions of Binsuluk FR, protect and enhance corridors for wildlife across Klias Peninsula Peatland Landscape, engage local community groups to improve their livelihoods at the same time protecting and rehabilitating the degraded peatland areas, enhance management practices on smallholder plantations and agriculture on peat, and enhance community-based ecotourism.

Output 3.4 Develop and implement a landscape level IMP in the Maludam Peninsula, Sarawak

- In Sarawak, the project will focus on developing an IMP for the Maludam Peninsula Peatland Landscape (MPPL) that includes the 53,568 ha Maludam National Park and the community and plantation land (about 25,000 ha) surrounding it. The park is of key importance for biodiversity including endemic species. The main management issues being faced at the site are: forest clearance and drainage along the boundaries of the National park by oil palm plantations and community agriculture; fire associated with agriculture and land clearing; conflicts over land rights between oil palm companies and communities; disruption of water supply to communities due to changes in hydrology due to the plantations; lack of clear delineation of park boundaries; illegal logging; and inadequate capacity of the National Park management to patrol and manage the National Park.

- The Main Activities will include the following: i) Undertake detailed assessment and gap analysis of Maludam Peninsula Peatland Landscape; ii) Develop IMP for Maludam Peninsula including revised National Park Management Plan, Buffer zone management plan, and community sustainable development plan; iii) Support priority management measures including delineation and patrolling of National Park boundary and monitoring of management issues and wildlife, development and promotion of Maludam National Park and community ecotourism packages, enhancement of water management to maintain forest hydrology and reduce fire risks, promote sustainable land and forest management in buffer zone including fire prevention, engage local community groups to improve their livelihoods at the same time rehabilitating the degraded peatland areas and protecting the National Park, and enhance management practices of agriculture and plantations on peat.

### Lessons Learned and Adherence to IFAD Policies, GEF policies and the SECAP

- Specific lessons learned on peatland management

- The APFP, implemented between 2009 and 2014, including pilot activities in Malaysia, provided the following main lessons:

- Integrated peatland management is a complex undertaking requiring an effective framework for cooperation and coordination among stakeholders and an associated integrated multi-stakeholder consultation approach;

- Private enterprises are key partners in sharing good management practices (e.g. fire prevention measures including water management and plantation BMPs);

- Capacity building and institutional strengthening on fire prevention, suppression and control, sustainable peatland agriculture and alternative livelihood options is essential for communities living within the peatland buffer zones;

- Community development and rural finance programmes supporting public infrastructure and alternative livelihoods programmes are important for sustainable management of peatlands;

- Water management at landscape level is a critical factor in peatland management;

- Sustainable peatland development. Effective options for community engagement in sustainable peatland management include:

      - Household-based land use entitlement and linked performance-based grants for peatland restoration;

      - Seedling buy-back system involving small grants to set up village nurseries with seedlings purchased for government and Corporate Social Responsibility (CSR) rehabilitation / replanting activities;

      - Haze-free village development, as pioneered in Harapan Jaya Village under the APFP/SEApeat Project, which provides a model for effectively engaging key stakeholders in achieving this key outcome.

- Under the APFP and the subsequent APSMPE, demonstration sites for peatland rehabilitation have been established in Indonesia (Mentangai River Peatlands, Central Kalimantan), Malaysia (North Selangor Peat Swamp Forest), Thailand (Pru To Daeng) and Viet Nam (U Minh Thoung). Experiences and lessons learned from these sites can be used to support design of rehabilitation measures in Malaysia.

- In particular, experience from North Selangor Peat Swamp Forest in Malaysia is very relevant to the project. The extent and severity of peatland fires was significantly reduced and forest started to recover following a combination of hydrological restoration in fire prone sites, multi-stakeholder coordination through district governments, involvement of local community members in patrolling fire prone sites along forest boundaries and building partnerships with private sector plantations along the forest boundaries. This work was the basis for an integrated management plan that was adopted by the state government covering the forest reserves and a buffer zone on state and private land. Adoption of the plan by the State Government has been key to mainstream the issues into the state planning processes and to start the steps to scale up implementation. However, further work is needed to secure the necessary investment to complete these actions.

- The project design builds on the following lessons learned in the following areas: a) implementation of environmental and social standards in line with the legislation of Malaysia (Application of environmental impact assessments at the project level do not address the cumulative and landscape impacts in peatland landscapes although regulations have been recently strengthened to address environmentally sensitive areas); b) implementation of the National Action Plan on Peatlands NAPP (Responsibilities for peatland management are divided across many different ministries and agencies and levels (federal, state and site) and dedicated resources to implement NAP have not been provided – so in future a more integrate approach is needed and specific responsibility and resource allocations are needed to ensure successful implementation); and c) addressing barriers to sustainable peatland management (Policy conflicts between different sectors (agriculture, plantation, forestry and environment) need to be addressed; private sector and local communities must be better engaged; Integrated landscape approach is required; level of resources for sustainable peatland management need to be enhanced).

- Finally, a growing body of research suggests a number of key conclusions for peatland conservation and management efforts:

- Loss of peat carbon (GHG emissions) and land subsidence are inevitable once drainage starts. Eventually, subsidence will bring the land surface to an elevation where flood risk is high. In extreme cases, as seen in other parts of the world (e.g., Netherlands, UK, USA), the land surface can end up below sea level. Therefore, subsidence and flood analysis should be undertaken as a standard part of land use and economic planning in lowland tropical peatlands.

- Peat loss is not dependent on water table depth alone. In agricultural areas, a combination of several factors, including fertilizer application, higher top soil temperature after removal of the original vegetation cover, and greater air entry into the soil after it is disturbed also enhance peat loss and may together have an effect on peat decomposition rates that is as strong as that of water table depth alone. Peat loss in tropical peatlands that have been developed for agriculture/plantations will always be substantial; it may be reduced but not stopped in cases where water levels are brought up close to the surface. To stop peat loss, it is necessary both to raise water levels and also to reduce these other disturbances as well as restore forest cover.

- The current bottlenecks for resolving the peat / forest / fire problems do not include a significant lack of basic knowledge. From a technical perspective, it is clear what needs to be done and most of the issues are well researched. The challenges are getting this knowledge reflected in legislation and planning, mobilizing adequate sources of financing and ensuring that laws and plans are effectively implemented by diverse sets of stakeholders.

- The project adheres to the following IFAD policies (see Appendix 9 for details):

- IFAD Strategic Framework 2016-2025

- Environmental Natural Resource Management (ENRM) Policy

- IFAD’s Climate Change Strategy

- IFAD’s Policy for Gender Equality and Women’s Empowerment

- IFAD’s Policy for Indigenous People

- IFAD’s Policy to Improve Access to Land and Security of Tenure

- IFAD’s Knowledge Management Strategy.

- In addition to the above, the project has undertaken a review in light of IFAD’s Social, Environmental and Climate Procedures (SECAP), as provided in Appendix 1. The project has been assessed to have a medium-level Potential Social and Environmental Impact (Category B).  Mitigation measures to address to potential impacts have been identified. In addition, the project areas are judged to have high vulnerability to climate change related risks – such as increased flooding and droughts, which may disrupt peatland hydrology, lead to increased fires and disrupt livelihood activities for targeted communities. Adaptation measures have been proposed. Much of the project interventions at site level will work to reduce climate-related risks.

- The Project is aligned to and conforms to the following GEF focal area strategies and programmes:

- CCM-2 Programme 4: The project is fully aligned with Program 4 to promote conservation and enhancement of carbon stocks in forest and other land use, and support climate smart agriculture. The project will aim to reduce GHG emissions related to drainage and burning of peatland forest, improve management of plantation and agriculture systems in the targeted landscapes and at national level through implementation and updating of the National Action Plan on Peatlands and other related strategies, policies and action plans.

- SFM-2 Program 5: The project will support the increased application of good management practices by relevant government, local community and private sector actors within the proposed landscapes. These areas include those that have been burned during dry season especially within the forest reserves and national parks and the adjacent plantations and buffer zones. This engagement of private sector and local communities in the restoration of peat swamp forests will be enhanced through technical support and incentive mechanisms.

- Relevant Aichi targets that the project will contribute to include the following:

- Target 1. Awareness of the values of biodiversity increased by 2020

- Target 2. Biodiversity integrated into national and local development and poverty reduction strategies and planning process

- Target 3: By 2020, incentives (including subsidies) harmful to biodiversity are eliminated, phased out or reformed, and positive incentives for the conservation and sustianable use of biodiversity are developed and applied

- Target 4. Government/business/stakeholders taken steps to achieve/implement plans for sustainable production and consumption within safe ecological limits

- Target 5. The rate of loss of all natural habitats is at least halved by 2020

- Target 7. By 2020, areas under agriculture, aquaculture and forestry managed sustainably, ensuring conservation of biodiversity

- Target 11. By 2020, at least 17% of terrestrial and inland water, especially areas of particular importance for biodiversity and ecosystem services are conserved/managed effectively

- Target 12: By 2020, the extinction of known threatened species has been prevented and their conservation status, particularly of those most in decline, has been improved and sustained.

- Target 14. By 2020, ecosystems that provide essential services are restored and safeguarded taking into account the needs of women, indigenous and local communities, and the poor and vulnerable

- Target 15. By 2020, ecosystem resilience and the contribution of biodiversity to carbon stocks has been enhanced

- Target 17: By 2020, each Party has developed, adopted as a policy instrument, and has commenced implementing an effective, participatory and updated national biodiversity strategy and action plan

- Target 20. By 2020, the mobilization of financial resources for effectively implementing the Strategic Plan for Biodiversity 2011-2020 from all sources should increase substantially from the current level.

# Project Implementation

### Approach

- The main approaches that the project will take include:

- Working with existing national structures such as the National Peatland Steering Committee (NPSC) and the National Peatland  Working Committee (NPWC)

- Building on experience and lessons learned of the previous IFAD-GEF supported ASEAN Peatland Forest Project (2010-2014) and the UNDP-GEF supported Conservation of Peatland Ecosystems in Malaysia Project (2002-2007)

- Work with multiple sectors and stakeholders and at multiple levels including Government, Private sector, CSOs and community stakeholders, agriculture, plantation, forestry and conservation sectors, and national state and local levels

- Introducing a landscape based approach to peatland management to include the entire peatland hydrological units and where relevant adjacent lands to ensure a fully integrated approach that can address all stakeholders in the landscape and recognise the interconnectedness of peatland hydrology.

- Ensure a significant portion of the funds is allocated for practical action on the ground.

- Ensure the effective engagement of indigenous and local communities.

- Links will be made with other regional and national initiatives as follows. The Investment Plan under Output 1.2 will be linked to a regional investment framework for implementation of the APSMPE and APMS being developed under ASEAN through the IFAD-supported MAHFSA Project (2018-2022). This regional investment framework, with an indicative value of US$1.5 billion, is expected to lead to significant engagement of regional and international funders (including GCF and other climate related funding mechanisms)

- The project will directly link to and support implementation of key Malaysian government policies, such as the Malaysian National Action Plan on Peatlands (NAPP) as well as the associated ASEAN Peatland Management Strategy 2006-2020 (APMS). The project also seeks to achieve the APSMPE targets as detailed under the Goal. Strategy, Action Plan and Programme are being undertaken under framework of ASEAN Agreement on Transboundary Haze Pollution, the first regional arrangement in the world that binds a group of neighbouring states to tackle transboundary haze pollution caused by land and forest fires.

- The Malaysian National Policy on Biological Diversity 2016-2025 includes peatlands as an element under the chapter of Terrestrial Habitats – “it is the edaphic forests that grow in specialized soil conditions, such as the peat swamp, mangrove, freshwater swamp and limestone that are critically threatened by land conversion and extractive activities. Freshwater swamps and peatlands are important habitats for a variety of plants and animals…”. It is also covered under Goal 3 Target 7 Key Indicator 7.3 where the Policy targets 10,000 ha of degraded peat swamp forests to be rehabilitated by 2025 and Action 7.3, which requires the implementation of the National Action Plan on Peatlands (NAPP).

### Organizational Framework

- Project Management: At the national level, the Project (Component 1) will be managed by a National Project Management Office (NPMO) hosted by the Forestry Department of Peninsula Malaysia (FDPM) in Kuala Lumpur and under the guidance of a National Peatland Steering Committee (NPSC) and NPWC. The Project Director will be the Senior Director of Forest Management Division of FDPM, supported by the Wetlands Forest Management Section. The Secretary General of the Ministry of Natural Resources and the Environment (NRE) of the Federal Government will chair the NPSC. NRE will also play a key role in different aspects of project management and implementation including leadership in policy dialogue, reporting to relevant national and international processes, financial oversight, supporting engagement of other government ministries and State governments, as well as, support and guidance to the NPMO.

- The NPMO will be responsible for the overall project (all components) planning and implementation including consolidation of the Annual Work Plan and Budget (AWPB) and procurement plan, coordination of implementation, monitoring across different levels of government, knowledge management, consolidating financial statements of expenditure, and reporting to IFAD in line with agreed procedures.

- At the sub-national level, four State Project Management Offices (SPMOs) will be established and based respectively at the State Forestry/Forest Departments in Pahang, Sabah, Sarawak and Selangor. The SPMOs will work under the guidance of respective State Steering Committees (SSC) chaired by UPEN (State Economic Planning Unit) in Sabah and Selangor, the State Economic Planning Division (BPEN) of Pahang, and the State Planning Unit of Sarawak, to guide the project at state level (Component 2). SPMOs will be also responsible to coordinate and provide necessary assistance for the success of project implementation at landscape level (Component 3).

- In Sarawak, for component 2, Output 2.1 will be facilitated by the state Ministry of Urban Development and Natural Resources; The state Department of Agriculture will facilitate Output 2.2 and the Natural Resources and Environment Board will facilitate state level activities for Output 2.3. The Sarawak Forest Department has been appointed as the lead agency to coordinate and implement Output 3.4 for the Maludam Landscape.

- For implementation at site level in Selangor and Pahang, project activities will be managed from each corresponding SPMO in consultation with Landscape Working Groups (LWG) at district/landscape level. In Sabah, a landscape level working group will also support the implementation work.

- The project will be implemented over a period of 48 months. An initial inception period of 3 months (after the signing of the Grant Agreement) will be used for project staff appointment, preparation of the AWPB and any necessary fine-tuning of the indicators and M&E Plan and institutional co-financing arrangements. A Gantt chart for project implementation is given in Appendix 3.

- Project Organisational Chart

- Implementation Arrangements: The project will be primarily implemented by the relevant government agencies with support from technical service providers and partners. It is expected that the government agencies will combine project activities with their regular work and where necessary make available agency resources such as results of previous analytical work, hyperspectral data, maps and other materials useful for advancing project activities. To ensure buy-in by local communities, a mechanism for direct fund disbursement to communities and local NGOs will be facilitated.

- In order for government to access the IFAD resources, in the last quarter of each year, each SPMO will prepare an AWPB and PP for the coming year and submit it to NPMO for review, revision and endorsement through a consultative process. The NPMO will then compile the state-level AWPBs and PPs, together with the national level AWPB and PP, for submission to IFAD for review, revisions if necessary, and clearance. The respective draft final state and national AWPBs and PPs will then be submitted to the SSC, and subsequently to NPSC, for clearances. Once cleared, the complete AWPB and PP package will be officially submitted to IFAD for No Objection.

- In light of substantial technical assistance (TA) being included in support of national and state-level activities, effort will need to be taken to ensure quality, coherence, and responsiveness of the TA support. To avoid fragmented individual TA activities, and heavy workload associate with contract management for the NPMO/SPMO, bundling similar TA activities into work packages for recruiting expert and credible TA institutions will be necessary.

- In order to ensure effective linkage between different sectors at national level and between national-state and landscape level it is important that common and compatible guidance and frameworks for national action plans, state action plans and Integrated management plans are developed.  Similarly, it is important that effective engagement of stakeholders including federal and state governments, CSOs, Private sector, and community it is important that there is effective outreach and engagement.  To ensure this provision has been made to appoint an experienced organization with a track record in facilitating multi-level peatland policy, institutional and stakeholder engagement action. Such an organization will provide a package of core technical support to support the NPMO and NRE in the development and implementation of the NAPP/SAPP/IMP frameworks, multi-stakeholder engagement policy mainstreaming and outreach. Further information is provided in the Project description (Appendix 2) and TORs in Appendix 3.

- Other stakeholders. The success of the SMPEM depends on the active engagement of multiple stakeholders, including local communities, NGOs and private sector and government-linked companies (GLCs). In order to enable active engagement of local communities in particular, a mechanism for direct fund disbursement to communities, CSOs, Common Interest Groups (CIGs), and local NGOs will be facilitated.

- Stakeholder Engagement Plan: A Stakeholder Engagement Plan (SEP) is given in Appendix 3, Annex A3-1. The SEP describes the engagement mechanism and role of stakeholders for the following six main groups of stakeholders: i) Federal Government agencies; ii) State government Agencies; iii) Civil society organisations; iv) Indigenous peoples and local communities; v) Private sector; vi) Academic and research bodies.

- The SEP also indicates the approach through which the project will consult and engage with indigenous and local peoples in planning and decision making processes. Specific resource allocations are made in the budget for the landscape assessments for each of the targeted landscapes for detailed assessments of the socio-economic situation and resource use practices and rights of indigenous and local communities living in the respective landscapes.  This will include a process for free prior and informed consent (FPIC) in line with the requirements of IFAD’s Policy on Engagement with Indigenous Peoples.  Representatives of stakeholders including indigenous and local people will also be included in consultations in relation to the development of State Action Plans on Peatlands (SAPPs) and National Action plan on Peatlands (NAPP).  The engagement strategy for local communities and indigenous people will be elaborated in the TORs/methodologies for the preparation of NAPP/SAPP/IMP.

- Gender The project will mainstream gender issues into the project implementation, based on the understanding that women play an important role in peatland management and livelihoods, and as such, their equal participation in the project needs to be facilitated through a set of specific measures. The project will focus on activities and outputs which ensure equal participation of women, developing their capacities, building awareness and creating opportunities in sustainable peatland livelihoods, especially rehabilitation, ecotourism, agroforestry and paludiculture. The gender mainstreaming opportunities include: i) gender equality concept to be adequately introduced to Project Staff as well as women and men from Project communities as much as possible during the project inception and implementation; ii) Measures to ensure participation of women in the peatland planning, management and implementation of the project activities in the targeted peatland landscapes; iii) Promotion of economic empowerment of women, especially through identification of traditional- and non-traditional livelihood activities that will benefit female workers/producers and processors; and iv) Provide equal opportunities to female community and stakeholder representatives to participate in training programmes undertaken by the project.

- Project Implementation Manual. A Project Implementation Manual (PIM) will be developed prior to the project start up, with support from IFAD. The PIM will provide detailed guidance on planning, monitoring, evaluation, financial management arrangements, procurement methods (including flow of funds), audit systems, and knowledge management functions to be used by the project (see Appendix 8 for the indicative contents of the PIM).

### Planning, M&E, Learning and Knowledge Management

Planning

- The Annual Work Plan and Budget (AWPB) will be the key management tool for planning, monitoring and reporting on implementation of activities. The AWPBs will be based on the design report and informed by operational experiences and supervision mission reports. The Project Logical Framework will be used as the main reference for formulating the AWPB, to create clear linkages between proposed activities and budget requirements and expected outputs, outcomes and impacts (annual targets vs. achievements).

- The Project will follow a participatory planning approach in the targeted areas to ensure that the interventions closely reflect the needs of the target groups and the local context. The participatory planning approach will be led by the SPMO at the state level and the outcome of this process will be integrated into the AWPB to be consolidated by the NPMO. The AWPB will cover detailed activities and will be used as a tool to promote a results-oriented and performance-based approach.

- Building on participatory planning processes undertaken in other IFAD-supported projects/ programmes, the planning process will be based on consultations with beneficiaries at the village level, implemented through the Site Coordination Committee.

Monitoring and Evaluation

- The SMPEM Monitoring and Evaluation (M&E) system is designed to provide reliable information to facilitate results-based management of the Project. The main objectives of the Project’s M&E system are to:

- Steer project implementation: provide Project stakeholders with the information and analysis required to measure Project outputs and outcomes; assess Project effects on the sustainable management of targeted peatlands, the engagement and capacity of government, community and private sector partners, livelihoods of participating households; assess the relevance of the Project’s implementation strategy and processes; identify lags; and support overall decision-making to improve Project performance;

- Support policy-making: the M&E system will provide government with information to measure Project contribution to the implementation of overall national peatland management policy and plans.

- The M&E system will have three levels of monitoring: output, outcomes and impact. Where appropriate, outcome and impact indicators will be disaggregated by poverty quintile and by gender, particularly under Component 3, which will be working with local communities at landscape level. This will include benefits to women and the poor arising from activities like community-based fire prevention, peatland rehabilitation and ecotourism services. Information gathering and consultations will be needed to establish robust baselines to support M&E in these areas.

- Apart from the three levels of monitoring, the project will also monitor processes leading to outputs and outcomes. Specific areas where progress monitoring will be applied include the provision of technical services, the execution of participatory village peatland planning and management and the implementation of group activities.

- While SMPEM’s M&E system will respond to the reporting requirements of GEF/IFAD, it will also make an effort to harmonize its data collection processes and templates to that of the GOM.

- Staffing: The project team will consist of members as in the table below:

##### Table 5: Staffing of project management offices

| - National Project Management Office (NPMO) |  |
| --- | --- |
| - Project Director | - Senior Director of Forest Management Section of the Forestry Department of Peninsula Malaysia |
| - National Project Coordinator | - Head of Wetland Forest Management Section, Forestry Department of Peninsula Malaysia |
| - Assistant National Project Coordinator | - Staff of Wetland Forest Management Section, Forestry Department of Peninsula Malaysia |
| - Project Manager | - Recruited with GEF funding |
| - Project Finance Officer | - Recruited with GEF funding |
| - Project Administration Officer(s) | - Recruited with GEF funding |
| - Knowledge Management/Communication Specialist | - Recruited with GEF funding |
| - Support staff as required | - Allocated by Government of Malaysia |
| - State Level Project Management Offices ( 4 states) |  |
| - a) State Project Coordinators | - Senior staff of State government |
| - b) State Project Technical Officers | - Recruited with GEF funding |
| - c) State Project Admin/Finance Officer | - Recruited with GEF funding |
| - Support and field staff as required* | - Allocated by respective states |

- *One field technical officer position is being supported with GEF funds at Maludam landscape in Sarawak in light of the remoteness of the site location.

- Additional details on M&E are provided in Appendix 4.

Learning and Knowledge Management

- The Project’s learning system will comprise quarterly state-level meetings and national bi-annual and annual review meetings, capturing information on progress, lessons and finding solutions for implementation constraints. A consolidated Annual Project Review will be carried out towards the end of each fiscal year, in addition to the bi-annual reviews at national level. It will assess performance in the achievement of physical and financial progress against annual targets. Furthermore, reviews of progress towards development objectives as reflected in the Outcome Surveys will be done to assess success and failures and reasons thereof and lessons learned.

- Mid-Term Review (MTR). The Government of Malaysia and IFAD will jointly undertake a mid-term review at the end of year 2 of the Project lifecycle to review Project achievements and implementation constraints.

- Project Completion Review. As the Project reaches completion, the NPMO will prepare a draft Project Completion Report (PCR). IFAD and the Government will then carry out a Project Completion Review based on the information in the PCR.

- Knowledge management is key to building capacity for sustainable management of peatland ecosystems. The Project will establish a knowledge management (KM) system to document and synthesize successful approaches and technologies for sustainable peatland management that have been implemented in the country and for exchanging experiences with other countries. This will include, but not be limited to, experience and lessons gained from the project’s own demonstration activities. The KM system will identify dissemination pathways for scaling up best practice and for informing evidence-based policy dialogue at all levels. This work will help to speed up broader adoption / uptake of demonstrated sustainable peatland management approaches, especially by the private sector and state governments.

- Knowledge Management will be undertaken systematically and continuously throughout the Project. To enable effective knowledge management and sharing, results and lessons from the Project will be documented through special studies and knowledge products commissioned by the NPMO. The M&E system will be one of the most important sources of knowledge. In addition, innovations observed during the implementation process will also be documented.

- The Project will share best management practice (BMP) concerning, inter alia: (i) the participatory development and implementation of integrated peatland management plans, including agriculture, forestry, plantations, conservation, water management, infrastructure development, fire prevention and control; (ii) development of National and State Action Plans on Peatlands (NAPP/SAPP) and associated investment plans; (iii) development of BMPs for oil palm and agricultural and for fire prevention and control on peat. The project will also support national workshops on peatland management and policy dialogue at local state and national levels on the application of landscape management approaches to peatlands.

- The NPMO M&E staff will be responsible for disseminating knowledge documents through dedicated websites and occasional workshops and seminars. Knowledge management efforts will be led by NRE with support from the National Biodiversity Centre (NBC) on the development and operationalisation of the knowledge management system and with additional support from the NPMO / FDPM, FRIM and other stakeholders. Knowledge management efforts will be closely monitored by the National Peatland Steering Committee (NPSC) and, in particular, its National Peatland Working Committee (NPWC).

- This country-based knowledge management system will be linked to a regional platform established within the framework of the ASEAN Programme on Sustainable Management of Peatland Ecosystems (APSMPE) and the ASEAN Agreement on Transboundary Haze Pollution, thereby helping to ensure that lessons from other countries’ experience are also taken into account and Malaysia’s lessons likewise shared. Participation in regional and international meetings and exchange programmes for knowledge sharing and enhancement will also be supported.

### Financial Management, Procurement and Governance

- Fiduciary Risk: Malaysia’s inherent risk is medium as measured by Transparency International’s Corruption Perceptions Index (CPI or TI). The country’s annual CPI has been slightly lowered from 52 in 2014 to 50 in 2015 to 49 in 2016 (scale 0- high risk and 100 - low risk). Safeguard measures will therefore be put in place to reduce risk.

- Financial Management: SMPEM will engage similar financial management systems to those used under APFP project, including use of the National Accounting Software known as Government Financial Management and Accounting Software (GFMAS). Both the NPMO and the SPMOs will recruit project specific finance / accounting staff.

- Accounting System: Government of Malaysia (GoM) has adopted the Malaysian Public Sector Accounting Standards (MPSAS), which are consistent with International Public Sector Accounting Standards (IPSAS). The GoM accounting system is in compliance with IPSAS- Modified Cash Basis and GOM intends to adopt Accrual Basis in 2018. The Accounting System currently in place is an Access-based computer system that captures double entries of all financial transactions.

- Budgetary System: The budgetary cycle begins in stages from budget formulation, approval and execution, to audit and performance assessment and evaluation. Government budgeting remains on a Modified Cash Basis and GoM may adopt accrual budgeting system to bring more coherence in decision-making.

- Reporting: FDPM will be responsible to prepare a summary financial statement of the project. The expenditure tracking system used for financial reporting by the Malaysian Component of the APFP project may be used for reporting purposes. The financial statements will be shared with IFAD within four months after the end of the fiscal year.

- Auditing: The Government shall have the financial statements relating to SMPEM audited each Fiscal Year by the Auditor General of Malaysia and supplemented (if required) by an external Auditor in order to meet established audit submission requirements and deadlines. The external audits will be carried out in accordance with the International Standards on Auditing and the Fund's "Guidelines on Programme Audits", as may be amended from time to time. In addition to the audit report on the financial statements, the auditors shall provide: (i) an opinion on the certified statements of expenditure and the operation of the Designated Account; and (ii) a separate management letter, addressing the adequacy of the accounting and internal control systems: and (iii) response to the management letter of the auditors. The Government shall deliver the above-mentioned items to the Fund within six months of the end of each such Fiscal Year

- Disbursement: Transaction-based disbursement procedures will be used. Other methods of disbursement may include direct payments and reimbursements. Details concerning disbursement methods will be indicated in the Letter to the Recipient (LTR) and the Project Financing Agreement. Subsequently, the cost centers will submit their Statements of Expenditure (SOEs) to the NPMO, which will forward the Withdrawal Applications (WAs) to IFAD for subsequent transfer of funds into the Designated Account.

- Flow of Funds: For the purpose of Designated Account, the NRE or Ministry of Finance will open a bank account in USD to receive funds from IFAD. GOM will maintain a bank account system operated in local currency. Treasury will record in the Trust Account Ledger, all project transactions. NPMO will manage the National Trust Account and respective SPMOs will manage respective State Trust Accounts. The NPMO will authorise the transfer of an initial Deposit to the State Trust Accounts on the basis of approved Annual Work Plans and Budgets (AWPBs). All payments are through Electronic Fund Transfer and can be made to government agencies, NGOs and CBOs. In case any recipients do not have a bank account, payments may be made through intermediaries such as Jawatankuasa Kemajuan dan Keselamatan Kampong (JKKK-Village Committee).

- A Project Trust Deed will be issued by the Ministry of Finance (Treasury) to facilitate the operation and governance of the Project Trust Accounts by the NPMO and the respective SPMOs. The Project Trust Accounts are Specific Ledger Accounts in Malaysian Ringgit (MYR) which will record receipts and disbursements of project funds. The National and State Trust Deeds should be consistent in their terms and conditions for use of funds by including, among others, the following clauses:

  - transfer of funds to other Federal and State Agencies

  - transfer of funds at State level to State agencies

  - payments to CSOs, CIGs and communities

  - reporting against disbursement categories specified in the IFAD Grant Agreement

  - return of outstanding balances at end of project to IFAD by MOF.

- In order to facilitate a rapid and smooth initiation of the project activities at the start of the project period, it will be possible for the GOM, after signing the Financing Agreement, to request an advance of up to US$300,000 from the project grant in order to start the recruitment and appointment processes for key project staff and setting up of the project offices.

- Fund flow diagram

- Procurement: Procurement will be undertaken in accordance with the provisions of the National/ State Procurement Regulations and its implementation arrangements which also includes the use of e-procurement systems, in so far as it does not conflict with IFAD's Project Procurement Guidelines and its Project Procurement Handbook. The procurement methods, prior review arrangements, cost and estimates, and risk mitigation measures will be defined in the Letter to the Recipient and reflected in the procurement plan. The procurement of goods, works and services will be managed by the respective implementing agencies and their partners.

- Governance: The Project’s governance arrangement will be the responsibility of NRE through the National Peatland Steering Committee and the Biodiversity and Forestry Management Division. This will ensure overall monitoring of the project at all levels, including NPMO, SPMOs, and landscape levels.

- It should be noted that IFAD applies a zero-tolerance approach in cases where investigation determines that fraudulent, corrupt, collusive, or coercive actions have occurred in projects financed through its grants.

- Further details on financial management and disbursement arrangements are found in Appendix 5, while details on procurement are given in Appendix 6.

### Supervision

- The Project will be supervised by IFAD. Annual supervision missions will be organised jointly with the GOM and will include the main implementing agencies and Project stakeholders. Implementation support missions will be fielded based on specific needs. Supervision will not be conducted as a general inspection or evaluation, but rather as an opportunity to assess achievements and lessons jointly, to review innovations, to reflect on improving implementation measures, and to make any course corrections if necessary. Missions will therefore be an integral part of the knowledge management and learning cycle, with mission members playing a supportive and coaching role. To ensure continuity in this process, missions will be carried out by a core team of resource persons, joined by specialists to address specific needs of a given year.

- Mid-term review: Government and IFAD will organize a joint mid-term review after 30 months from project start-up (mid-2020), in close collaboration with the above-mentioned agencies and stakeholders. It will be carried out by consultants not involved in supervision missions to bring a fresh look at 2.5 years of Project achievements and learning. The MTR will: (i) assess Project achievements and interim impact, the efficiency and effectiveness of SMPEM management, and the continued validity of SMPEM design; (ii) identify key lessons learnt and good practices; and (iii) provide recommendations for the second half of Project implementation.

- Completion review: A Project Completion Review (PCR) will be undertaken by NRE in the final Project year to document achievements, challenges experienced, lessons learned, and to make recommendations for ensuring the sustainability of Project achievements beyond Project completion. Subsequent to the PCR, IFAD will coordinate an independent Terminal Evaluation in line with GEF and IFAD procedures.

### Risk identification

- Table 6 identifies the main risks and mitigation measures, as well as sensitivity to risk occurrence.

##### Table 6: Project Risk and Risk Mitigation Analysis

| Risk | Impact and probability | Mitigation Measure |
| --- | --- | --- |
| Weak enforcement of policies and regulations related to peatland management | Medium impact Medium probability | Awareness-raising on the impacts of peatland degradation Enhancement of monitoring and enforcement measures through capacity building of responsible government units and clarifying the roles and responsibilities in the governance structure |
| Lack of political will or poor governance | Medium Impact Low probability | Linking project activities closely with The National Action Plan on Peatlands, (2011) government policies—including the Five year development Plans—and plans developed under international conventions will help avoid barriers related to lack of political will by ensuring that implementation is in many cases ‘obligatory’. In addition, the project will conduct various sensitization campaigns to ensure buy-in of decision-makers in various ministries and departments. |
| Lack of engagement of state governments | High impact Low probability | Relevant Components (Component 2 and 3) will be anchored with the four participating state governments and guided by a State Working Group chaired by the State Economic Planning Unit. In particular, Component 2 will be focused on the development of SAPPs, development and implementation of which will be driven by each respective state, with only methodological guidance from Federal level. SAPPs will also be mainstreamed into state budget and development plan processes. This approach to project design is intended, inter alia, to ensure state government engagement in implementation. |
| Poor participation by oil palm plantations and private sector | Medium Impact. Low probability | The project will link with and support the new Malaysian government plan to have all plantation companies and smallholders certified under the Malaysian Sustainable Palm Oil (MSPO) Standard by 31 December 2019. This will facilitate the engagement of the Ministry of Plantation Industries and Commodities and related agencies as well as ensuring the participation of existing private sector plantations cultivating on peat. The project will also work with the selected state governments to ensure private sector plantations on peat in the targeted landscapes will be involved. Finally, the project will support the establishment of multi-stakeholder consultation platforms at key demonstration sites, as well as the development of financial mechanisms based on the principle of User/polluter pays or payment for ecosystem services (PES). |
| Potentially slow implementation of multi stakeholder integrated management strategies | Medium impact; Medium probability | Careful selection of project partners (this will include local government agencies and community groups with demonstrated commitment to addressing peatland issues) and through close monitoring and guidance of project activities |
| Climate change risk including intensification of the periodic El Nino drought is anticipated to occur at some time during implementation of the project and could affect some aspects of project implementation | Medium impact medium probability | The project will promote sustainable peatland management including enhanced water management and fire prevention as well as community stewardship. This will reduce fire risk during El Nino related droughts. The project will focus on enhancing the resilience of peatlands to current and anticipated climate change scenarios The project will work closely with the Malaysian Meteorological Department (MMD) to detect any early warning signs of El Nino and use the information to adjust the planning of activities especially in the fire prone regions to minimize disruption The project will work closely with DOE and BOMBA to upgrade SOPs for peatland fire prevention and control, which will include SOPs related to drought or El Nino years. |

# Project Costs, Financing, Benefits and Sustainability

### Project Costs

- The total cost for the SMPEM is estimated at USD 62.14 million. GEF financing is USD 9.43 million. Anticipated co-financing of approximately USD 52.71 million is expected to come from various sources, including Federal and State governments, the private sector, IFAD and Civil Society Organisations (CSOs). The exchange rate of RM 4.3/USD has been applied for the SMPEM costing. The breakdown of project costs by component and financier is shown in Table 7 and by expenditure category in Table 8. The project management cost is detailed in Table 9. Further Information on GEF allocations for project costs is given in Appendix 7.

##### Table 7: Project Components by Financier (USD '000)

##### Table 8: Expenditure Categories by Financiers (USD'000)

##### Table 9: Project Management Costs (USD '000)

- Co-financing

- Information on co-financing is given in Table 10. The main co-financier is the Government of Malaysia, which will make funding available through a variety of agencies and ministries at the national/Federal level and state levels. IFAD will provide some co-financing in-kind (primarily support for project management and coordination) as well as in cash (through the IFAD funded MAHFSA project) – primarily for knowledge and information management and capacity building.  Co-financing in-kind will also be provided by the four participating state governments through various agencies.

##### Table 10: Co-financing levels by source

| Sources of Co-financing | Name of Co-financier | Type of Co-financing | Amount (USD’000) |
| --- | --- | --- | --- |
| GEF Agency | IFAD | In-kind | 500 |
|  | IFAD | cash | 250 |
| Recipient Government | Federal Government* | In-kind | 12,007 |
|  | Federal Government** | cash | 5,000 |
|  | State governments*** | In-kind | 31,658 |
| CSO | GEC and others | cash | 465 |
| Private Sector | Agriculture, plantation and housing development sector | In-kind | 2,831 |
| Total Co-financing |  |  | 52,711 |

*Including Ministry of Natural Resources and the Environment (NRE), Ministry of Plantation Industries and Commodities, Malaysian Meteorological Department, and Fire and Rescue Department.

** Development funds through NRE to support specific policy measures, peatland management and restoration, fire prevention and monitoring activities

*** The four targeted state governments of Pahang, Sabah, Sarawak and Selangor

- In addition to the co-financing given in the table above, it is anticipated that additional co-financing will be confirmed before the start of project implementation or during implementation. In particular IFAD is in the process of finalising a Malaysia country grant of up to US$1 million to support community based livelihood and peatland management activities under SMPEM. The European Union and The German Government have committed Euro 24 Million under the framework of the EU-ASEAN SUPA project to support peatland management and fire prevention in the region. Part of these funds will be allocated for peatland management in Malaysia and will be able to co-finance or support activities under SMPEM. It is understood that the SUPA project will be initiated in the second half of 2017 and resource allocations to countries may be made in early 2018.

- The Co-financing from civil society organisations is currently consisting of co-financing from the Global Environment Centre (GEC) which has been supporting sustainable peatland management in Malaysia since 1998. The committed co-financing from 2018-2021 is specifically to support peatland restoration and management costs in Selangor state under the framework of an MOU between GEC and the Selangor State government from 2016-2023.

- The co-financing from the private sector included in the above table includes initial estimated commitments of support from companies working in the plantation and property development sectors with active landholdings in the peatland landscapes in Selangor. It is anticipated that significant additional private sector co-financing will be leveraged in other landscapes during the course of implementation of the project – particularly from plantation companies in the oil palm sector.

### B. Benefits

- Global environmental benefits: The SMPEM Project is expected to generate key global environmental benefits in terms of biodiversity conservation, increased sustainable land management and GHG mitigation through the protection, rehabilitation and sustainable management of key peatland areas. These actions will contribute towards the fulfillment of Malaysia's obligations under the Convention on Biological Diversity (CBD), United Nations Convention to Combat Desertification (UNCCD), United Nations Framework Convention on Climate Change (UNFCCC) and the Ramsar Convention on Wetlands of International Importance.

Biodiversity conservation

- The project will contribute to protection of globally significant peat swamp forests, associated carbon stocks and biodiversity. The tropical PSFs feature some of the highest freshwater biodiversity of any habitat in the world and are home to threatened fauna such as Tiger, Sun bear, False gharial and a range of endemic fish species. Information on endangered flora and fauna species at proposed project sites is shown in Table 11 below (also see Appendix 2, Annex 5 for further details on target landscapes).

##### Table 11: Key biodiversity associated with Project sites

| Name of site | North Selangor Peat Swamp Forest | Southeast Pahang Peatland Landscape | Maludam National Park | Klias Peninsula Peatland Landscape | South Selangor Peat Swamp Forest |
| --- | --- | --- | --- | --- | --- |
| Area | 81,000 ha | 230,000 ha incl. 108,000 ha in ten designated forest reserves | 53,568 ha | 23,635 ha of forest reserves in a broader landscape of 70,000ha | 8,108 ha with 1,200ha of Kuala Langat North Forest Reserve and 6,908 of Kuala Langat South Forest Reserve |
| Signifi-cant value of the sites | The site supports many specialized species of plants and animals, as well as provides a number of ecosystem services, including water supply, flood control and climate regulation. Unique habitat for 107 tree species, 173 species of birds, over 100 species of fishes and rare and endangered mammals such as the Sun Bear, Clouded Leopard, Tapir, and False Gharial. | Provide valuable timber species such as Kempas (Koompassia malaccensis) and Ramin melawis (Gonystylus bancanus) and commercial fish species such as Tapah, Toman and Baung. Important habitat for threatened species such as Malayan sun bear, Flat-headed cat, White-handed gibbon, Small-clawed otter and Malayan porcupine animal species critically endangered: Painted terrapin, Malayan tiger, Asian elephant, Sunda otter civet, Hairy-nosed otter, Panther, Leopard, Lesser adjutant stork, Wrinkled hornbill, Large green pigeon, Short-toed coucal, Wallace’s hawk-eagle, False gharial and Malayan giant turtle. The Orang Asli, from Jakun subgroup, known as Proto Malays represent a key community in the SEPPSF. A total of 19 Orang Asli villages are found in the vicinity of the SPPL. Many of the Orang Asli are still dependent on the forest products. | There are 61 species of mammals recorded in Maludam, which include 15 species of bats and five species of diurnal primates. The Maludam National Park is the only site globally for the conservation of the Red-banded langur (Presbytis melalophos cruciger) which number less than 200, and are now restricted to the remnant patches of tall forests. One of only about five viable populations of Proboscis monkey (Nasalis larvatus) in Sarawak, occurs in the park. There are 201 species and 24 families of birds including 5 species of Hornbills (including Black, Pied and Rhinoceros hornbills), and the rare Storm's stork. There are at least 218 species of flora from various groups of plants are recorded. | (1) Globally threatened mammals (IUCN): ENDANGERED: Proboscis Monkey Nasalis larvatus; VULNERABLE: Pig-tailed macaque (Macaca nemestrina); Malayan sun bear (Helarctos malayanus) NEAR THREATENED: Long-tailed macaque (M. fascicularis), Pangolin manis javanica, Oriental Small-clawed otter (Amblonyx cinereus); (2) Globally threatened reptiles VU: Asiatic Softshell Turtle (Amyda cartilaginea) (3) Globally threatened plants: CR: Hopea pentanervia, Shorea platycarpa; EN: Shorea teysmanniana; VU: Combretocarpus rotundatus, Calophyllum havilandii, Gonystylus bancanus, Nepenthes bicalcarata. | Meranti bunga, a Critically Endangered tree species was recorded at this site. Local peat swamp species such as Mersawa paya and Meranti bakau are also found at the forest reserves. Lowland forest species such as Jelutong are also recorded in the forest reserve. There is a 130ha of Virgin Jungle Reserve located within the Kuala Langat South FR. High value timber species such as Kempas (Koompasia malaccensis), Meranti bunga (Shorea teysmanniana), Punah (Tetramerista glabra) and Ramin melawis (Gonystylus bancanus) within the VJR area |
| Disturbances and threats | The main threat is fire with more than 6000ha within the forest reserve severely degraded by fires in the past. Much of the site is affected by sub-surface drainage linked to extensive sand and tin mining to the SE of the site. 500km of drainage canals cut for log extraction remain. A buffer zone covering 14,000 ha has recently been designated but 90% of this area has been developed for agriculture and oil palm plantations. Appropriate land and water management strategies need to be implemented in this land. | The core portion of the landscape is within 10 forest reserves covering 108,000ha. About 3000ha of the land in the forest reserves has been severely degraded by fires linked to drainage, logging and land development. The principal threats to the integrity of the landscape are ongoing reclamation for agriculture as well as large scale plantation development. Fire has impacted more than 10,000ha of the landscape in recent years. | The main threats include encroachment and illegal logging and the development of oil palm plantations adjacent to national park that have affected the hydrology of the peatland system. | Frequent fires caused by the drainage and conversion of the landscape for oil palm and agriculture, which disturbs regional hydrology, affect forest in the Klias Peninsula. | The main threats are: (i) peat fires linked to land clearing,; ii) land-use pressure from increasing development activities adjacent to the forest reserves – oil palm plantations and housing development projects, and (iii) encroachment into forested area from adjacent private land for agriculture. |
| Indicative actions through project | Fire prevention and control, improved water management, implement buffer zone management and forest rehabilitation | Fire prevention and control, forest rehabilitation, development of integrated peatland landscape plan, promotion of sustainable land management for oil palm plantations on peat adjacent to forest, active engagement of indigenous peoples | Enhanced management of the National park and control of illegal logging and fires. Buffer zone management including sustainable water supply to local settlement, regulation on land clearing and conversion in buffer zone/adjacent land | Protection and rehabilitation of remaining forests, Fire prevention and control in the landscape, Buffer zone management and good management practices on water as well as regulations on land clearing and conversion in the landscape, creation of wildlife corridors | Buffer zone management include sustainable agricultural practices, Restoration and protection of remaining forest areas; regulation on urban land development in buffer zone/adjacent land |
| Anticipated result | Further reduction in extent of fires, Increase in area of rehabilitated forest, maintenance and increase in biodiversity | Significant reduction in extent of fires and initial rehabilitation of degraded sites in partnership with local communities. maintenance and increase in biodiversity | Reduction in illegal logging and fire risk and drainage along boundaries. | Enhanced water management and rehabilitation of degraded forests and enhanced connectivity between forest patches | Significant reduction in extent of fires and initial rehabilitation of degraded sites |

- Rehabilitation and sustainable management of the 250,000 ha of globally important peatland ecosystems within the targeted landscapes will enable them to support the above-mentioned species in the longer term. Preventing the degradation of peatlands and encouraging rehabilitation, conserving globally important biodiversity and taking action to promote sustainable land and forest management as stated in the National Action Plan on Peatlands will reduce occurrences of fires on peatlands and land-use pressure, which are key threats to those species in the project areas. These actions will contribute significantly to achieving the targets under the National Policy on Biological Diversity (2016-2025).

- The SMPEM will also contribute significantly to meeting the obligations under the Ramsar Convention especially in relation to wise use of wetlands in Malaysia.  Peatlands are the largest wetland ecosystem in Malaysia comprising more than 70% of the wetland area in the country. Peatlands also occur in several of the Ramsar Sites in Malaysia. The work on the NAPP and SAPP will support the national wetland policy implementation. All outputs of the project will contribute towards the goals in the Ramsar Strategic Plan.

Sustainable Land Management

- The project will play a significant role in reducing the degradation of peatlands that are recognized in the National Action Plan for UNCCD as a fragile habitat subject to land degradation in Malaysia. The project will work in line with the GEF Focal Area Strategy and National strategies to address land degradation. It will specifically support enhanced water management, landscape level rehabilitation and fire prevention measures, which are expected to significantly reduce peatland degradation in the approximately 500,000 ha of peatlands within the targeted landscapes as well as the broader area of more than 2 million ha of peatlands covered by the SAPPs.

GHG emission reduction

- Enhanced management of peatlands through the project (through fire prevention, water management, rehabilitation and avoided forest conversion) will reduce net GHG emissions. The project is expected to mitigate approximately 3.06 million metric tons of CO2eq from targeted peatlands. In order to be conservative, the project has only targeted direct emissions during the project period rather than direct/indirect emissions over a 20 year period.

- The GHG emission reduction for SMPEM has been calculated through application of the IPCC 2013 Supplement to the 2006 Guidelines for National Greenhouse Gas Inventories: Wetlands (the Wetlands Supplement). The Wetlands Supplement was developed upon the request of UNFCCC to undertake further methodological work on wetlands, focusing on the rewetting and restoration of peatland.

- The selection of GHG emission assessment methodology for SMPEM followed the GEF Guidelines for GHG emissions accounting and reporting (May 2015). As a project that develops policy, and capacity development for peatland use, and that influences oil palm and forest land management areas in peatlands in targeted landscapes, SMPEM incorporated the Wetlands Supplement for CO2 and non-CO2 emissions from fires on drained inland organic soils. In addition for the calculation of emission reductions related to enhanced water management in peatlands – the project has adopted the methodology approved by the Emission Reduction Working Group of the Round Table on Sustainable Palm Oil (RSPO 2016) which addresses the differential emissions from drainage according to the average water table.

- The following assumptions were applied to the GHG emissions reduction assessment of the SMPEM:

- The methodology is based on the IPCC 2013 Wetlands Supplement  and RSPO PalmGHG Calculator.

- All GHG emissions are converted to tonnes of CO2e for the project

- The CO2e reductions reported are cumulative reductions, estimated for the project period only and not the  lifetimes of the investments

- There is no discounting for future risks and changes in  GHG emissions.

- Given the characteristics of the soil type in the project areas of SMPEM (i.e. soil organic/wet, non-flooded land, not constructed for wastewater treatment, non-coastal land), the assessment refers to Drained Inland Organic Soils (Chapter 2) and Rewetted Organic Soils (Chapter 3) of the Wetlands Supplement. The land-use categories applied are thus organic wet soil and organic drained soil.

- These calculations are based on the following assumptions and detailed methodologies

- Fire prevention emission reduction  is based on an estimated reduction of 7,000 ha (30%) of fires in the five targeted landscapes. This is a reduction from a baseline of about 21,000 ha of land that have been burnt over recent years. The emission reduction factor of 310 tCO2/ha is a conservative estimate based on i) the RSPO default values for peatland carbon stock of 7.05 tC/cm  of peat depth over an area of one ha multiplied by ii) the carbon to carbon dioxide conversion factor of  3.67 tCO2/tC multiplied by iii) an estimated burning depth of 12 cm  (which is conservative compared to an estimated average burning depth of 33 cm recorded by Balhorn et al (2009) in Indonesia). Summary: (7.05 tC/cm depth/ha x 3.67 tCO2/tC x 12 cm depth burnt = 310 tCO2/ha)

- The emission reductions associated with improved water management are based on a target of improved water management in 14,000 ha of plantations in the five landscapes leading to a 20 cm average rise in water table, multiplied by the factor of 0.91 tCO2/cm drainage depth/ha/year (Reference: Hooijer et al 2010 and RSPO Emission Reduction Working Group, 2016). This is multiplied by two years assuming that the enhanced water levels would on average be in place for two years out of the four years of the project implementation. Summary: (20 cm x 0.91 tCO2/cm drainage/ha/year x 2 years = 36 tCO2/ha)

- The emission reduction/sequestration related to rehabilitation assumes that there will be on average a 20 cm increase in water levels for an average of two years over the four years of the project.  This will be multiplied by the factor of x 0.91 tCO2/cm drainage depth/ha/year x 2 years to get an emission reduction of 36 tCO2/ha.  In addition, sequestration is estimated as 1.5 tC/ha/year for two years multiplied by the conversion factor of carbon to carbon dioxide of 3.67 to get a sequestration of 11 tCO2/ha making a total emission reduction factor of 47 tCO2/ha.  The estimated area to be rehabilitated over the project period is 2,150 ha. Summary: ((20 cm x 0.91 tCO2/cm drainage/ha/year x 2 years = 36 tCO2/ha) + (1.5 tC/ha/year x 2 years x 3.67 tCO2/tC = 11 tCO2/ha) = 47 tCO2/ha)

- The emissions reduced from avoided forest conversion is based on an estimated 350 ha of peat swamp forest not converted over the project period.  The emission reduction factor is based on avoiding Above Ground Biomass (AGB) carbon stock loss from secondary forest/logged over forest of  estimated 75 tC/ha (275 tCO2/ha), plus avoided emission from drainage of 60cm  x 0.91 tCO2/cm drainage depth/ha/year x 10 years (546 tCO2/ha) to give an emission reduction factor of 821 tCO2/ha. Summary: ((75 tC/ha x 3.67 tCO2/tC = 275 tCO2/ha) + (60 cm x 0.91 tCO2/cm drainage/ha/year x 10 years = 546 tCO2/ha) = 821 tCO2/ha)

- The estimated reduction of CO2eq through the project activities in the five targeted landscapes is shown  in Table 12 below.

Table 12: Estimated emission reduction linked to project activities*

| Mitigation measures | Peatland Landscape (ha) |  |  |  |  | Total Ha | Emission reduction factor tCO2eq/ha | Total Emission reduction tCO2eq |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | NSPSF | SSPL | SEPPL | KPPL | MPPL |  |  |  |
| Fire prevention | 800 | 500 | 3000 | 2500 | 200 | 7,000 | 310 | 2,170,000 |
| Improved water management | 2500 | 3000 | 3500 | 3000 | 2000 | 14,000 | 36 | 504,000 |
| Rehabilitation | 250 | 300 | 500 | 600 | 500 | 2,150 | 47 | 101,050 |
| Avoided forest conversion | 50 | 50 | 100 | 50 | 100 | 350 | 821 | 287,350 |
| TOTAL |  |  |  |  |  |  |  | 3,062,400 |

*updated during appraisal, based on confirmed site-based activities

C. Socio-economic benefits

- The Project is expected to generate significant long-term socio-economic benefits and reduce substantial negative socio-economic impacts from current peatland management. The most important ecosystem services delivered on peatlands are livelihood provisions, biodiversity conservation and hydrological services. For livelihood provisions, the project will focus on enhanced sustainable production of agriculture, and peatland ecotourism and associated activities of handicrafts. For biodiversity conservation, the project will enable plantations and agroforestry in sites to adopt best management practices. For improved hydrological services, maintenance or enhancement of surface and subsurface water supply for agriculture, domestic and industrial use will be done. The project is also expected to reduce, in targeted landscapes, negative socio-economic impacts including i) peatland fires and associated smoke haze and related health impacts; iii) economic losses of NTFP extraction; ii) peatland subsidence and degradation and related increased risk of flooding.

### D. Sustainability

- Sustainability of the project investment is ensured by the following key approaches: (i) pursuit of multi-stakeholder engagement in developing integrated approaches for addressing peatland degradation issues – this is the main innovative aspects of the project as the engagement of private sector, civil society and local communities working in partnership with local and national government agencies will be more effective compared to conventional sectoral approaches of Malaysia; (ii) project implementation partnership with private sector plantation and urban development companies at selected sites (e.g. North Selangor Peat Swamp Forest, South Selangor Peatland Landscape and Southeast Pahang Peatland Landscape); (iii) demonstration of an integrated landscape approach to peatland management including those areas where private sector will enhance their land and plantation management; and (iv) maintaining the integrity and hydrology of the peatland landscapes  to prevent fire and minimize drying and degradation.

- IFAD has developed a Complaints Procedure for “Alleged Non-Compliance with its Social and Environmental Policies and Mandatory Aspects of Its Social Environmental and Climate Assessment Procedures”. Parties adversely or potentially adversely affected by IFAD-funded projects and programmes may bring issues to the Fund’s attention using SECAPcomplaints@ifad.org. The IFAD website provides a clear summary of the steps involved and guidance on how to report issues.

- To ensure scaling-up of SMPEM, it would be important to strengthen institutional and financial aspects of sustainability. This model is developed based on experience from the previous GEF-funded ASEAN Peatland Forests Project (APFP), where the key stakeholders and relevant line agencies have built up "Smart Partnerships" to tackle peatland-related issues. The two sustainability frameworks of the project are detailed as follows:

Institutional Sustainability

- Ensuring full national ownership of the project and of the processes that it sets in motion. This will include seeking high-level, multi-sectoral political support for the project, and most particularly for the NAPP. This will be a key aspect of the project’s exit strategy.

- Capacity building of National Peatland Steering Committee (NPSC) and National Peatland Working Committee (NPWC): The project will work under the guidance and support from the NPSC and its associated NPWC. The NPWC was specifically formed with the support of the previous GEF-supported APFP to coordinate and facilitate efforts of the different agencies to manage the country’s peatlands in a sustainable manner. The current project will further work to enhance the capacity and functions of these groups as well as the capacity of the agencies involved in them

- Support to the implementation of National Action Plans on Peatlands and to expand the scope of peatland-related activities to be covered under respectively the 12th and 13th Malaysian Plans (2021-2025; 2026 - 2030).

- Strengthening institutional capacities at multiple levels (national, State and site level) including through the development of State Action Plans on Peatlands and Integrated Management Plans for peatland landscapes that will bring together and enhance capacity of diversity stakeholders including government agencies, private sector and local communities.

- Linking closely with the implementation and review of the Malaysian national policies and strategies for agriculture, forestry, water resources, land use planning as well as implementation of national plans and strategies for CBD, UNFCCC and UNCCD.

- Supporting the collaborative work between Malaysia and other ASEAN Member States in the framework of the ASEAN Peatland Management Strategy 2006-2020 and its proposed extension to 2030 as well as the ASEAN Programme for Sustainable Management of Peatland Ecosystems 2014-2020 (APSMPE) under the framework of the ASEAN Agreement of Transboundary Haze Pollution (AATHP).

Financial Sustainability

- Mainstreaming sustainable peatland management into the mid-term and long-term national development planning frameworks as well as the internal budget planning processes of related ministries and agencies.

- Developing an investment framework for the implementation of the NAPP 2021-2030 in collaboration with broad range of institutions to secure an appropriate level of national budget allocation and of co-financing from the private sector (See Output 1.2). Based on the investment framework, clear roles of the private sector and incentive mechanisms will be developed.

- Developing budgets and investment requirements at the state level (as part of the SAPP (Output 2.1) and at landscape level for the project sites (Component 3), to help secure the resources and commitments to implement the respective plans.

- Demonstrating effectiveness and efficiency of fire prevention and sustainable peatland management approaches at a landscape level in contrast to high current expenditures and economic losses on ineffective peatland firefighting.

- Linking with strategies, investment plans and capacity development related to the Nationally Determined Contributions (NDCs) for emission reduction for 2020-2030 under the Paris Agreement of UNFCCC.

- Output 1.2 will be linked to a regional investment framework for implementation of the APSMPE and APMS being developed under ASEAN through the IFAD-supported MAHFSA Project (2018-2022) This regional framework with an indicative value of US$1.5 billion is expected to lead to significant engagement of regional and international funders (including Green Climate Fund (GCF) and other climate related funding mechanisms).

Mr. Christopher E. Cosslett, Mission Team Leader; Mr. Faizal Parish, Peatland Management Specialist; Mr. Roshan Cooke, IFAD Lead Technical Climate and Environment Specialist; Ms. Sunae Kim, IFAD GEF Portfolio Officer; Mr. Candra Samekto, IFAD Environment Officer and Water Management Specialist; Mr. Nagarajan Rengasamy, Fire Management Specialist; Ms. Lew Siew Yan (Serena), Policy and Institutional Specialist; and Ms. Firoza binti Yusoff, Financial Management Specialist. The design team was accompanied on its state visits by: Mr. Hamdan Napiah, Head of Wetlands Section, FDPM (in Selangor and Pahang) and Ms. Regina Mariah Jong, FDPM (in Sabah and Sarawak).

Schedule of the Design Mission is in Appendix 1 Annex A1-1.

Mr. Christopher E. Cosslett, Mission Team Leader; Mr. Faizal Parish, Peatland Management Specialist; Mr. Roshan Cooke, IFAD Lead Technical Climate and Environment Specialist; Mr. Shankar Achuthan Kutty, IFAD Procurement Specialist; Mr. Candra Samekto, IFAD Environment Officer and Water Management Specialist; Mr. Nagarajan Rengasamy, Fire Management Specialist; Ms. Lew Siew Yan (Serena), Social and Institutional Specialist; Ms. Firoza Parvin binti M N Mohd Yusoff, Financial Management Specialist, and; Ms. Titie Hadiyati, COSTAB Specialist. The design team was accompanied on its state visits by: Mr. Yusoff Muda, Deputy Director of Forest Management Division, FDPM (in Sabah and Sarawak) and Mr. Hamdan Napiah, Head of Wetlands Forest Management Section, FDPM (in Selangor).

Schedule of the Appraisal Mission is in Appendix 1 Annex A1-2

Yap, C.L. (1964). A mechanised method of log extraction in peat swamp forest. Malayan Forester 28: 34 – 36.

Miettinen, J , Shi CH. & SC Liew (2016) Land cover distribution in the peatlands of Peninsular Malaysia, Sumatra and Borneo in 2015 with changes since 1990 Global Ecology and Conservation 6 (2016) 67–78

Tonks, A.J., Aplin, P., Beriro, D.J., Cooper, H., Evers, S., Vane, C.H. & Sjogersten, S. (2017) Impacts of conversion of tropical peat swamp forest to oil palm plantation on peat organic chemistry, physical properties and carbon stocks, Geoderma, 39, 36-45

Jamaludin bin Jaya (2012) Sarawak: peat agricultural use StraPeat Project

Koh, LP., Miettinen, J. , Liew, SC.  & J. Ghazoula (2011) Remotely sensed evidence of tropical peatland conversion to oil palm PNAS, vol. 108, no. 12:pp 5127–5132

http://www.nre.gov.my/ms-my/PustakaMedia/Penerbitan/National%20Action%20Plan%20for%20Peatlands.pdf

National Policy on Biological Diversity 2016-2025, NRE, 2016

National plan in response to the ASEAN Haze Action Plan

which outlines infrastructure support to be provided to state governments facing challenges of peatland fires including support for observation towers, check dams, tube wells and other support to prevent or control peatland fires

NRE 2016

A. Hooijer,  S. Page , J. Jauhiainen , W. A. Lee , X. X. Lu , A. Idris & G. Anshari.(2012) Subsidence and carbon loss in drained tropical peatlands Biogeosciences, 9, 1053–1071,

# J.H.M. Wösten,..A.BIsmail & A.L.Mvan Wijka (1997) Peat subsidence and its practical implications: a case study in Malaysia.  Geoderma. Volume 78, Issues 1–2, pp 25-36

For example US$37 million was spent in Pahang state along in 2014 to fight peatland fires

See ASEAN Guidelines on Peatland Fire Management 2015

Different terms are used by different institutions and regions. The concept of peatland drainage basins to denote a single peatland unit connected by surface and subsurface water flows has been developed in Sarawak State. The concept of peatland hydrological units has been developed and defined in Indonesia as the main framework for peatland management and refers to the peatland area and all areas connected hydrologically with it between the peatland and the adjacent rivers and sea. The term peatland landscape encompasses both of these concepts and is used in this proposal

Including Orang Asli and Orang Asal

Ismail, P., Nizam, M.S., Latiff, A., Faridah Hanum, I. & Shamsudin, I. 2011. Phenology of Gonystylus bancanus in Pahang, Peninsular Malaysia.  Journal of Tropical Forest Science 23(2): 143–151 (2011).

Miettinen, J , Shi CH, SC Liew, (2016) Land cover distribution in the peatlands of Peninsular Malaysia, Sumatra and Borneo in 2015 with changes since 1990 Global Ecology and Conservation 6 (2016) 67–78

A. Hooijer,  S. Page , J. Jauhiainen , W. A. Lee , X. X. Lu , A. Idris , and G. Anshari.(2012) Subsidence and carbon loss in drained tropical peatlands Biogeosciences, 9, 1053–1071

Stateland forest is land outside of the permanent forest reserves that may either be converted for development purposes or designated at a later date as forest reserve or conservation area.

Ismail, P., Khali Aziz, H. & Grippin, A. 2007. Restoring the Wetland Ecosystem: Experience in Peat Swamp Forest Restoration Trials In Peninsular Malaysia. Conference on Forestry & Forest Products Research (CFFPR) 2007. Forest Research Institute Malaysia (FRIM). Pp. 233–242.

Note women comprise 24% of the agricultural, plantation, forestry and fishery workforce in Malaysia.

Information from official website of Malaysian Government, https://www.malaysia.gov.my/public/cms/article/page/304/

Information from Department of Statistics Malaysia released by 29 January 2014, https://www.dosm.gov.my/v1/images/stories/files/LatestReleases/population/Web_Release_Ciri_IR2010.pdf

Information released by the Department of Statistics, Malaysia on 22 September 2016, https://www.dosm.gov.my/v1/index.php?r=column/cthemeByCat&cat=397&bul_id=WVVQUnYrZkRwK1k1QXZMbEpuV1hNUT09&menu_id=L0pheU43NWJwRWVSZklWdzQ4TlhUUT09#

Bumiputera refers to Malay, Peranakan, Kristang and indigenous ethnic groups such as Jakun, Iban, Kadazan, Dusun, Bisaya, Murut, Kedayan and others.

New Straits Time, 24 May 2017, page 1 and 8

Information from the Department of Statistics, Malaysia, released on 30 December 2016, https://www.dosm.gov.my/v1/index.php?r=column/pdfPrev&id=T2Z3NkhLSFk2VjZ5dkdUL1JQUGs4dz09

ibid

Twelve National Key Economic Areas are: 1) Oil, gas and energy; 2) palm oil; 3) Financial Service; 4) Tourism; 5) Business Service; 6) Electronic and Electrical; 7) Wholesale and retail; 8) Education; 9) Health care; 10) Content and communications infrastructure; 11) Agriculture; and 12) Greater Kuala Lumpur/ Klang Valley.

See Table 3

Information from NRE, 2016 (unpublished, based on information from ASEAN Peatland Forests Project, 2014) and updated information from Sabah and Sarawak States 2017

Rates as published in numerous scientific papers and summarized by IPCC (2013).  Actual measurements in Acacia and oil palm plantations in SE Asia (Hoojier et al, 2012) found subsidence in the first 5 years after drainage to be 142 cm, of which 75 cm occurred in the first year. After 5 years, the subsidence rates remained constant at around 5 cm/yr with water table depth at 0.7 m. The average rate of carbon loss over the first 5 years was 178 tCO2/ha/yr., which reduced to 73 tCO2/ha/yr over subsequent years, potentially resulting in an average loss of 100 tCO2/ha/yr. over 25 years.

For further details, see Appendix 3.

Susan Page, John O’Neil Rieley, Christopher Banks. Global and regional importance of the tropical peatland carbon pool. Global Change Biology, Wiley, 2010, 17 (2), pp.798.

Jörn PW Scharlemann, Edmund VJ Tanner, Roland Hiederer & Valerie Kapos (2014) Global soil carbon: understanding and managing the largest terrestrial carbon pool, Carbon Management, 5:1, 81-91, DOI: 10.4155/cmt.13.77

Through regulation of release of Greenhouse gasses ( CO2, N2O, CH4 ) and uptake and storage of carbon

Yap, C.L. (1964).  A mechanised method of log extraction in peat swamp forest.  Malayan Forester 28: 34 – 36.

Miettinen, J , Shi CH, SC Liew, (2016) Land cover distribution in the peatlands of Peninsular Malaysia, Sumatra and Borneo in 2015 with changes since 1990 Global Ecology and Conservation 6 (2016) 67–78

Tonks, A.J., Aplin, P., Beriro, D.J., Cooper, H., Evers, S., Vane, C.H. and Sjogersten, S., (2017), Impacts of conversion of tropical peat swamp forest to oil palm plantation on peat organic chemistry, physical properties and carbon stocks, Geoderma, 39, 36-45;

Jamaludin bin Jaya, (2012). Sarawak: peat agricultural use StraPeat Project

Koh, LP., Miettinen, J. , Liew, SC.  and J. Ghazoula (2011) Remotely sensed evidence of tropical peatland conversion to oil palm PNAS, vol. 108, no. 12:pp 5127–5132

Such as in Southwest Johor, Malaysia  ( see Wösten J H, Ismail A B and vanWijk A L M 1997 Peat subsidence and its practical implications: a case study in Malaysia Geoderma 78 25–36;    Hooijer A et al 2012 Subsidence and carbon loss in drained tropical peatlands Biogeosciences 91053–71)

Jukka Miettinen, Aljosja Hooijer, Ronald Vernimmen, Soo Chin Liew & Susan E Page (2017) From carbon sink to carbon source: extensive peat oxidation in insular Southeast Asia since 1990.  Environmental Research Letters, Volume 12, Number 2

Hotspots counts are based on fire hotspots detected using NOAA weather satellite (as determined by the ASAEAN Specialised Meteorological Centre). Data on cumulative hotspots in report by Malaysia to Committee to Conference of Parties of ASEAN Agreement on Transboundary Haze Pollution (AATHP) in 2014.

http://www.nre.gov.my/ms-my/PustakaMedia/Penerbitan/National%20Action%20Plan%20for%20Peatlands.pdf

National Policy on Biological Diversity 2016-2025, NRE, 2016

National plan in response to the ASEAN Haze Action Plan

NRE 2016

A. Hooijer, S. Page, J. Jauhiainen, W. A. Lee, X.X. Lu, A. Idris & G. Anshari (2012) Subsidence and carbon loss in drained tropical peatlands Biogeosciences, 9, 1053–1071,

# J.H.M. Wösten, A. BIsmail & A.L. Mvan Wijka (1997) Peat subsidence and its practical implications: A case study in Malaysia. Geoderma. Volume 78, Issues 1–2, pp 25-36

For example US$37 million was spent in Pahang state along in 2014 to fight peatland fires

See ASEAN Guidelines on Peatland Fire Management (2015)

Different terms are used by different institutions and regions. The concept of peatland drainage basins to denote a single peatland unit connected by surface and subsurface water flows has been developed in Sarawak State. The concept of peatland hydrological units has been developed and defined in Indonesia as the main framework for peatland management and refers to the peatland area and all areas connected hydrologically with it between the peatland and the adjacent rivers and sea. The term peatland landscape encompasses both of these concepts and is used in this proposal

See Table 3 above

Miettinen, J , Shi CH, SC Liew, (2016) Land cover distribution in the peatlands of Peninsular Malaysia, Sumatra and Borneo in 2015 with changes since 1990 Global Ecology and Conservation 6 (2016) 67–78

NRE 2016 updated as in Table 3

Note in some policy and economic analyses – the agriculture sector includes forestry, plantations, crops, livestock and fisheries.

A. Hooijer, S. Page, J. Jauhiainen, W.A. Lee, X.X. Lu, A. Idris & G. Anshari (2012) Subsidence and carbon loss in drained tropical peatlands Biogeosciences, 9, 1053–1071

Miettinen, J, Shi CH & SC Liew (2016) Land cover distribution in the peatlands of Peninsular Malaysia, Sumatra and Borneo in 2015 with changes since 1990 Global Ecology and Conservation 6 (2016) 67–78

Stateland forest is land outside of the Permanent Reserved Forests that may either be converted for development purposes or designated at a later date as forest reserve or conservation area.

The APFP was working at the macro scale, enhancing capacity and stakeholder engagement, developing plans and strategies, and documenting best management practices. Its focus was primarily on biodiversity and land degradation issues.

Sustainable management of peatland forests in South east Asia (SEAPeat) Project

ASEAN Programme on Sustainable Management of Peatland Ecosystems 2014-2020

For examples, see: www.biogeosciences.net/9/1053/2012/; www.deltares.nl/app/uploads/2015/12/Plantation-Impacts-Kampar-Peatland-DELTARES-2015.pdf; www.deltares.nl/app/uploads/2015/06/Rajang-Delta-Peatland-Subsidence-Flooding-Deltares-2015.pdf; www.peatsociety.org/document/effect-hydrological-restoration-degraded-tropical-peat-carbon-fluxes; www.deltares.nl/app/uploads/2015/03/QANS-Peat-mapping-report-final-with-cover.pdf

Measurable Action for Haze Free land management in Southeast Asia

Sarawak Forest Department will lead the component 3 and the newly approved National Park and Wildlife Department (NPWD) will support implementation especially at the level of the targeted project site

https://www.ifad.org/documents/10180/14e50d95-2c58-423e-8ac6-3023359173b6

To be based at FDPM and NRE

Consideration may need to be given for GEF support in cases where government procedures preclude appointment of additional government staff.

Consideration may need to be given for GEF support in cases where government procedures preclude appointment of additional government staff.

NBC is expected to be in full operation by 2018.

It is expected that the project’s knowledge management system will be established in 2018-19 with the support from the NBC and other key agencies including FRIM (current national Clearing House on Biodiversity and focal centre for REDD+), MARDI, MPOB and NGOs such as GEC (Technical and Operational Support Partner for ASEAN Programme on Sustainable Management of Peatland Ecosystems) and MNS (Malaysia CEPA focal point for Ramsar Convention)

See Output 1.1.

Reference has been made to the Transparency International Corruption Perceptions Index as the Public Expenditure and Financial Accountability (PEFA) assessments is not available for Malaysia .

To be confirmed prior to the signing of the Grant Agreement

For example: Tasek Bera in Pahang and Lower Kinabatangan -Segama Wetlands in Sabah

The estimate of fire-related emissions has been made with reference to the methodology specified in the  2013 Supplement to the 2006 IPCC Guidelines for National Greenhouse Gas Inventories: Wetlands (Wetlands Supplement) (IPCC 2013) which specifies the following calculation for emissions from peat fires: Amount of CO2 emissions in tonnes = Total area burned annually (ha) * Soil fuel consumption value (t dry matter/ha) * Emission factor for each gas (tCO2/t dry matter).  However in line with normal tier 3 methodology this can be modified with country or region based information. Hence the calculation of solid fuel consumption value (global default) has been modified by using information on peatland carbon content from SE Asia and burn scar depth from the region.

Roundtable on Sustainable Palm Oil (RSPO). RSPO GHG Assessment Procedure for New Development (Version 3, 30th October 2016). RSPO, Kuala Lumpur. Here the default value of the carbon stock per ha of peatland is 2,115 tC/ha assuming the peat depth of 3m (300cm). This means peatland carbon stock of 7.05tC/cm per ha (2,115 tC/ha * 1cm/300cm = 7.05 tC/cm depth/ha).

A conservative figure of 12cm for burn scar depth has been adopted since the estimate of Balhorn et al is based on fires during El Nino drought in Indonesia.  Fires during El Nino droughts are more severe than at other times and skew the estimates. For obtaining a realistic estimate a more conservative figure of 12 cm was used to reflect the average.  During the project period information will be gathered on burn scar depth in Malaysian peats to better calibrate the estimates of emission reductions.

Balhorn, U., Siegert, F. Mason, M. & Limin, S. 2009. Derivation of burn scar depths and estimation of carbon emissions with LIDAR in Indonesian peat soils. Proceedings National Academy of Sciences, 106, 21213-21218.

The calculation of the emission reduction associated with improved water management in Oil palm plantations  have been made based on the PalmGHG calculator  (see https://rspo.org/certification/palm-ghg-calculator ) developed by the Emission Reduction Working Group of the Roundtable on Sustainable Palm Oil (RSPO)  as the sole official methodology ( since 2011) for calculating emissions for improved water management on peat by RSPO member companies.

The proposed 20cm rise in water levels is based on the difference in the default level in the RSPO PalmGHG calculator of 80 cm drainage representing poor water management and 60 cm representing good management.

Hooijer et al 2010. Current and future CO2 emissions from drained peatlands in Southeast Asia. Biogeosciences 7: 1505-1514 ). Table 1. pg 1508. This emission factor has been adopted in 2011 by the Emission Reduction Working Group (ERWG) for the PalmGHG calculator.

The EF of 1.5 tC/ha/year for sequestration for forest rehabilitation comes from the RSPO PalmGHG calculator.

Conservative compared to RSPO default Carbon stock for secondary forest of 128 tC/ha.

Assuming that the area of peat swamp forest converted is also drained to a depth of 60 cm in line with the default level for good management practice under the RSPO Palm GHG Calculator.

It is assumed that any area converted will continue to be drained for at least 10 years.

Measurable Action for Haze-Free Sustainable Land Management in Southeast Asia