-Project Identification Form (PIF)

Project Type: Full-sized Project

Type of Trust Fund: GEF Trust Fund

PART I: Project Identification

| Project Title: | Strengthening the resilience of multiple-use protected areas to deliver multiple global environmental benefits |  |  |
| --- | --- | --- | --- |
| Country(ies): | Nicaragua | GEF Project ID: | TBD |
| GEF Agency(ies): | UNDP | GEF Agency Project ID: | 5125 |
| Other Executing Partner(s): | Ministry of Environment and Natural Resources (MARENA) | Submission Date: | 18 Jan 2013 |
| GEF Focal Area (s): | Multi-Focal Area | Project Duration (Months): | 60 |
| Name of Parent program (if applicable): For SFM/REDD+ |  | Agency Fee ($): | 588,288 |

- Focal Area strategy Framework:

| ### Focal Area Objectives | ### Expected FA Outcomes | ### Expected FA Outputs | ### Trust Fund | ### Indicative Financing from the GEF TF ($)* | ### Indicative Cofinancing ### ($) |
| --- | --- | --- | --- | --- | --- |
| BD-1 | Outcome 1.1: Improved management effectiveness of 11 existing and 0 new protected areas | Output 1.1: New protected areas (0) and coverage (0) of unprotected ecosystems (11 existing multiple-use PAs covering 125,669 ha) | GEFTF | 1,823,527 | 6,964,000 |
| LD-3 | Outcome 3.2: Integrated landscape management practices adopted by local communities | Output 3.1: Integrated land management plans developed and implemented | GEFTF | 729,411 | 2,188,813 |
| CCM-5 | Outcome 5.1: Good management practices in LULUCF adopted both within the forest land and in the wider landscape | Output 5.2: Forests and non-forest lands under good management practices | GEFTF | 1,870,285 | 5,612,331 |
| SFM/ REDD-1 | Outcome 1.2: Good management practices applied in existing forests | Output 1.2: Forest area (hectares) under sustainable management, separated by forest type | GEFTF | 1,474,408 | 4,424,380 |
| Sub-total |  |  |  | 5,897,631 | 19,189,524 |
| Project management cost |  |  | GEFTF | 294,881 | 959,476 |
| Total project cost |  |  |  | 6,192,512 | 20,149,000 |

* Applying the STAR flexibility mechanism of GEF-5 resources a total of US$230,900 of BD STAR allocation is being channeled to other focal areas as follows: US$161,310 for CCM-5 and US$69,590 for LD-3 inclusive of the corresponding contribution of each focal area to Project Management cost.  Thus, for the FSP a total amount of US$1,914,704 of BD resources, US$765,881 of LD resources and US$1,963,799 of CC resources are being allocated. Amounts including fees are shown in Table D.

- Project Framework

| ### Project Objective: Strengthened management effectiveness of multiple-use protected areas and the sustainable use of dry and humid forests in the wider landscape in western and north-central Nicaragua to ensure the flow of multiple ecosystem services, ensuring BD conservation, sustainable land management, and CC mitigation from land use change. |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| ### Project Component | ### Type ### (TA / INV) | ### Expected Outcomes | ### Expected Outputs | ### Trust Fund | ### Indicative Financing from GEF TF ($) | ### Indicative Cofinancing ### ($) |
| 1. Strengthened capacity and financial sustainability of the multiple-use protected areas (MUPAs) in dry forest and humid, semi-humid, and cloud forest landscapes of western and north-central Nicaragua | TA | - Improved management effectiveness of eleven (11) existing multiple-use PAs in two dry forest landscapes (Chinandenga-Rivas Dry Forest Corridor and Cumaica Cerro Cerro Alegre–Mombachito Cerro La Vieja–Sierra Amerrisque Biological Corridor), the Lake Nicaragua islands, and a humid, semi-humid, and cloud forest landscape (Peñas Blancas–Kuskawas–Kilambé Corridor) (measured by METT). METT scores increase from current average of 40 to at least 50*. (*baseline and target values to be confirmed during project preparation) - The threats facing 11 multiple-use PAs (non-sustainable agriculture and cattle ranching, illegal logging, trade of vulnerable and endangered species, and forest fires) are reduced across an area of 125,669 hectares (ha)**. a) Reduction by at least 10% in area converted annually from forest to land used for agriculture and pastures. b) Levels of illegal logging of high value timber reduced by at least 10%. c) The trade of vulnerable and endangered species) reduced by one third. d) Forest fires in tropical dry forest landscapes reduced by half. (** baseline and target values to be confirmed during project preparation) - Reduced vulnerability of threatened BD: a) 104,233 ha of dry forest habitat secured. b) 21,436 ha of humid, semi-humid, and cloud forest secured. c) Stable numbers of key species of biological groups (mammals, birds, and plants; targeted species for each group will be defined during the PPG). | - Planning and monitoring strengthened in 11 multiple-use PAs (MUPA) through: a) Approved management plans for 11 existing MUPA, defining conservation measures to address threats; defining sustainable off-takes limits and specifying management targets, and indicators of success and needs for delivering PA functions b) Procedures, roles and responsibilities defined for monitoring, surveillance, and enforcement of sustainable off-takes for forest products, and land use prescriptions for grazing, agriculture, and other acceptable production activities. c) Information system for sustainable use and management (forest products, agriculture, and grazing) and conservation in MUPAs strengthens decision-making processes and facilitates compliance and monitoring of threats to BD. - Management and enforcement framework in place for 11 MUMPAs: a) Capacity built within MARENA to effectively deliver PA management functions across MUPAs in dry forest and humid, semi-humid, and cloud forest landscapes. b) Multi-sectoral collaborative agreements for shared management of MULAs define access areas for sustainable use of forest products and offtakes, BD-friendly production methods, agreed-to management measures, and monitoring and enforcement mechanisms. c) Strengthening of enforcement (targeting illegal logging, trade of vulnerable and endangered species, uncontrolled slash-and-burn); improved national and local PA authorities’ information systems for monitoring threats; protocols for patrolling and reporting malfeasance; capacity to sanction infractions. - Finance in place for 11 multiple-use PAs: a) New financial resources available for PA management derived from government and private funds (i.e., PAs visitors’ entry fees – Law 200/2012), REDD+ incentives, and funds leveraged by multiple-use PA management partners (NGOs, private sectors, local governments), among other sources. b) Effective deployment of funds and human resources to address threats to multiple-use PAs. c) Cost-effective administration (including financial management and personnel administration) at MARENA’s Headquarters and in Local Territorial Delegations. | GEFTF | 1,823,527 (BD) | 6,964,000 |
| 2. Multiple global environmental benefits generated through sustainable forest and land management outside multiple-use PAs (MUPAs) | TA | - Ecosystem structure and functionality of tropical dry, humid, semi-humid, and cloud forests strengthened through the consolidation of 4 biological corridors (see Table 1) improved through: a) Connectivity between remnants of endangered tropical forest habitat outside multiple-use PAs is increased by 10% (baseline to be determined during the PPG phase), improving ecosystem resilience to CC, and providing refuge for globally important BD (tropical dry forests, at least 25,000 ha; humid, semi-humid, and cloud forests, at least 30,000 ha outside MUPAs). b) A stable population of indicator species as a result of enhanced connectivity facilitated by the biological corridor (baselines to be established during the PPG phase) c) Restored C stocks of threatened tropical forest over a 5-year period (i.e., project length): - Tropical dry forest: 102,760 tCO2-eq sequestered (1,000 ha; aboveground biomass). - Humid, semi-humid, and cloud forests: 330,300 tCO2-eq sequestered (1,000 ha; aboveground biomass). d) Sustained water flows in 10 watersheds (baseline of stream flows will be established during the PPG phase). - At least 25% reduction in humid, semi-humid, and cloud forests deforestation: 568,315 tCO2-eq over a 5-year period (i.e., project length) (baseline area = 30,000 ha; areal biomass). - Increase of 10% in the management and technical capacity of 270 municipal officials and local communities in dry and humid forest landscapes as measured by capacity development indicators (baseline will be determined during the PPG phase). | - Land use planning, monitoring and enforcement strengthened in landscapes around MUPAs: a) Strengthened institutional capacity of national and regional officials and field personnel to support the sustainable management and conservation of dry and humid forest production landscapes, the use of SFM/REDD+ methodologies, the quantification and evaluation of carbon (C) flows, and the development of strategies to conserve BD. b) Training and logistical support provided to municipal environment authorities, for implementing SFM, SLM, and CC mitigation measures, as well as their enforcement capabilities: compliance monitoring with land use planning structures; spatial and field surveys and other surveillance measures to assess compliance; and improved policing and capacity to sanction infractions. c) Municipal-level GIS mapping tool of SFM/SLM and BD benefits guide the development and implementation of land use plans and ecological zoning for the consolidation of biological corridors connecting MUPAs. d) Municipal-level monitoring and enforcement systems facilitate decision-making and the assessment of SFM/SML and BD benefits in dry and humid forest landscapes - Integrated farm management delivers multiple global environmental benefits: a) Integrated farm management plans specifying the spatial and temporal arrangements of different land uses across farms in dry and humid forest landscapes allow farmers to improve on-farm sustainability (including the implementation of agroforestry and silvopastoral systems) and improved ecosystem connectivity: b) Two thousand hectares (2,000) of dry and humid forests set asides enhanced through natural rehabilitation of degraded areas. - Financial mechanism for the wider landscape in place: a) One performance-based compensation mechanism for the generation of income in multiple-use PA landscapes by means of ENDE/REDD+ provide a utilitarian incentive for the conservation of humid forest blocks covering 30,000 ha. | GEFTF | 4,074,104 LD: 729,411 CCM: 1,870,285 SFM/REDD: 1,474,408 | 12,225,524 |
| Sub-Total |  |  |  |  | 5,897,631 | 19,189,524 |
| Project Management Cost |  |  |  | GEFTF | 294,881 | 959,476 |
| Total Project Costs |  |  |  |  | 6,192,512 | 20,149,000 |

- Indicative Co-financing for the project by source and by name if available, ($)

| Sources of Co-financing | Name of Cofinancier | Type of Co-financing | Amount ($) |
| --- | --- | --- | --- |
| GEF Agency | UNDP | Grant | 285,000 |
| GEF Agency | UNDP | In kind | 50,000 |
| National Government | Ministry of Environment and Natural Resources (MARENA) | In-kind | 250,000 |
| National Government | Ministry of Environment and Natural Resources (MARENA) - Land Administration Project (PRODEP) Additional Financing (Component Demarcation and Consolidation of Protected Areas) | Grant | 900,000 |
| National Government | Nicaraguan Tourism Institute (INTUR) | Grant | 15,600,000 |
| Local Government | Municipal Governments | In-kind | 350,000 |
| Bilateral Aid Agency (ies) | U.S. Agency for International Development (USAID) - Regional Program for the Management of Aquatic Resources and Economic Alternatives | Grant | 264,000 |
| Bilateral Aid Agency (ies) | European Union - EcoFishery Project | Grant | 1,500,000 |
| Private Sector | Cooperatives or producer associations and tourism companies associated with PAs. | In-kind | 350,000 |
| CSO | Non-governmental organizations (FFI, FUNDAR, LIDER, CUCULMECA, , Amigos de la Tierra, PASO PACIFIC, etc.), and universities (UCA, UNAN-León, UNA and BICU-URACCAN) | In-kind | 350,000 |
| Private Sector | Private Natural Reserve Network | In-kind | 250,000 |
| (select) |  | (select) |  |
| (select) |  | (select) |  |
| Total Co-financing |  |  | 20,149,000 |

- GEF/LDCF/SCCF/NPIF Resources Requested by Agency, Focal Area and Country1:

| GEF Agency | Type of Trust Fund | Focal area | Country name/Global | Project amount (a) | Agency Fee (b) | Total c=a+b |
| --- | --- | --- | --- | --- | --- | --- |
| UNDP | GEF TF | BD | Nicaragua | 1,914,704 | 181,897 | 2,096,601 |
| UNDP | GEF TF | LD | Nicaragua | 765,881 | 72,759 | 838,640 |
| UNDP | GEF TF | CCM | Nicaragua | 1,963,799 | 186,561 | 2,150,360 |
| UNDP | GEF TF | SFM/REDD+ | Nicaragua | 1,548,128 | 147,071 | 1,695,199 |
| Total Grant Resources |  |  |  | 6,192,512 | 588,288 | 6,780,800 |

part ii:  project justification

- Description of the consistency of the project with:

A.1.1. The GEF Focal Area strategies:

- The proposed project is in line with GEF’s strategy and the results framework for STAR 5 for Nicaragua. The project will contribute to reducing the degradation and loss of the dry and humid forests in Nicaragua through the strengthening of multiple-use protected areas (PAs) management; the consolidation of biological corridors that promote ecological connectivity between existing multiple-use PAs and forest remnants of dry, semi-humid, and humid forests; the implementation of ENDE-REDD+ pilot projects; and the sustainable management of tropical dry forests and dry lands in Nicaragua. These and other actions will help to remove barriers related to the lack of institutional capacity and technical knowledge that have limited the effective conservation of biodiversity (BD) through multiple-use PAs, and the sustainable use of forests and the land within their surrounding landscapes. The project will deliver multiple global environmental benefits including BD conservation, reduction of desertification, increase in carbon (C) stocks and reduction of greenhouse gas (GHG) emissions, and increase in forest cover and sustainable flows of ecosystem services.

- The project’s objective is framed within the Focal Areas of Biodiversity (BD), Land Degradation (LD), and Climate Change Mitigation (CCM), as well as Sustainable Forestry Management/REDD Plus (SFM/REDD+). Specifically, the project addresses the BD-1 objective: Improve Sustainability of Protected Area Systems. The project will improve the management effectiveness of  eleven (11) existing PAs to reduce the threats that these face from land use within and outside their boundaries (e.g., non-sustainable agriculture and cattle ranching, illegal logging, trade of vulnerable and endangered species, and forest fires), and will thereby reduce vulnerability of threatened  biodiversity in selected dry forest landscapes and in  humid, semi-humid, and cloud forest core habitats (Component 1). The project will also address the LD-3: Integrated Landscapes: Reduce pressures on natural resources from competing land uses in the wider landscape. The project will facilitate the development of landscape management practices by local farmers that will result in stable dry forest and humid forest covers and sustainable ecosystem services, including sustained water flows in key watersheds (Component 2). The project will also address the CCM-5: LULUCF: Promote conservation and enhancement of carbon stocks through sustainable management of land use, land-use change, and forestry. The project will use landscape management tools (e.g., natural rehabilitation of degraded areas, agroforestry, and silvopastoral systems) in selected dry forest and humid forest of western and north-central Nicaragua, resulting in improved ecosystem structure and functionality and enhanced C stocks (Component 2). The project also addresses the SFM/REDD-1: Forest Ecosystem Services objective, which seeks to Reduce pressures on forest resources and generate sustainable flows of forest ecosystem services. The project has been designed in accordance with GEF investment guidelines for the SFM/REDD+ and will reduce the pressure on forest resources and to generate sustainable flows of ecosystem services by implementing SFM/REDD+ measures to reduce threats to the tropical dry forest and the humid/semi-humid forests, buffering and connecting existing PAs where deforestation rates are high principally due to the expansion of agriculture and extensive cattle ranching.

- The project will contribute to the implementation of the 2011-2020 Strategic Plan of the Convention on Biological Diversity (i.e., Aichi Targets). More specifically, the project will contribute to achieving Targets 1, 5, 7, 11, 12, 14, and 15.

A.2. National Strategies and Plans or Reports and Assessments under Relevant Conventions, if applicable

- The project advances the 2010-2020 National Plan for Human Development (PNDH) of the Government for Reconciliation and National Unity in its Objectives 2 and 8: “To care for and defend protected areas” and “To care for and restore environmentally degraded and eroded areas through adaptive, agroforestry, and silvopastoral systems,” respectively. The project is equally consistent with the National Environmental and Climate Change Strategy-NECCS (2010) and its Plan of Action, particularly under two of the five guidelines: a) Environmental Defense and Protection of Natural Resources, which proposes to “strengthen the mechanisms for protection of the current protected areas” and “restore and conserve corridors of life” as steps toward “the integral restoration of the country’s existing ecosystems;” and b) Sustainable Land Management, which proposes “the appropriate land use and planning in rural and urban areas, in harmony with nature, ensuring its preservation” and the promotion of best agricultural practices for the improved management of agricultural land use. It will contribute to the NECCS Plan of Action 2010-2015 which guarantees the participation of the organized community and government institutions in developing conservation actions and preserving Nicaragua’s natural resources. In particular the project is in line with the strategy for mitigation, adaptation, and risk management with regard to CC.

- The project has been designed to address the National Biodiversity Strategy NBS (2002) and the National Plan to Combat Desertification and Drought (2002), which establishes lines of action for the restoration of ecosystems, the protection of BD, and reversing the process of soil degradation in the dry areas of Nicaragua. The proposed project will have a relevant and pioneering role in Nicaragua with regard to NBS’s Objective 8, which was agreed to in 2010 during the Convention on Biological Diversity (CBD) (To maintain ecosystems’ capacity to deliver goods and services and lend support to livelihoods). The Fourth National Report to the CBD (2010) indicates that complying with this objective depends upon connectivity through biological corridors. In addition, the Biodiversity Conservation Gap Analysis (BCGA) of Nicaragua indicates that these corridors ensure the protection of water resources, the genetic exchange between species and ecosystems, and should contribute to increasing agricultural productivity. The project will make an important contribution to the consolidation of biological corridors and the promotion of ecosystem connectivity, providing refuge for species of global importance against the effects of CC.

- The project also addresses the Gender Policy of the Government for Reconciliation and National Unity of Nicaragua and the Equal Rights and Opportunities Law (No. 648, 2008) and its Regulation, which states that with regard to the environment, it will ensure the adoption of Equal Opportunities by incorporating a gender focus into the country's environmental policy with awareness and training programs that address equity and the equality between women and men involved in environmental activities. Similarly, through the formulation and implementation of educational programs, control, protection, and management of natural resources; the environment and biodiversity, in gender statistics and indicators, funding for women for the implementation of projects for the protection, conservation and rational use of the natural resources that alleviate the workload of women and family poverty, and the participation of women and men in decision-making processes that involve them and their families.

- Project Overview:

B.1. The Baseline of the Project and the Problem that it seeks to Address:

- Nicaragua is the largest country in Central America, with an area of 130,370 square kilometers (km2). Home to most of the Central American Volcanic Arc, the geographical variation in the country, from the Pacific Lowlands to the Amerrique Mountains and the Mosquito Coast along the Atlantic Lowlands, has contributed to Nicaragua’s status as a BD hotspot. Nicaragua has 68 types of ecosystems and plant forms, which is equivalent to 60% of the ecosystems in the Central American region. Nicaragua has more than 6,014 identified plant species, of which 105 (1.75%) are endemic; and 11,589 species of wildlife (mollusks, arthropods, fish, reptiles, amphibians, and mammals), of which 102 (1.75%) are endemic. In addition, the country provides habitat to 704 resident and migratory bird species.

- PAs are an essential component of the strategies for BD conservation in Nicaragua. A total of 72 areas comprise the National System of Protected Areas (SINAP), which is administered by the Ministry of the Environment and Natural Resources (MARENA). Sixty-six (66) of these areas (comprising 2,093,747.38 ha) are terrestrial and five are marine-coastal (comprising 113,551.65 ha). The PAs are classified into nine management categories and cover 17% of the country’s territory. In addition, Nicaragua has three reserves recognized by the UNESCO Man and the Biosphere Programme (MAB), including the Bosawás Biosphere Reserve, and nine wetlands that are of global importance for aquatic and migratory birds and are recognized and named by the RAMSAR Convention. Seven of these wetlands are found within the boundaries of legally declared PAs. Fifty-six (56) private natural reserves (comprising 9,276.7 ha) and 17 municipal ecological parks (comprising 8,621.63 ha) are also part of SINAP and make an important contribution to the conservation of BD. The PAs and forested areas play a fundamental hydrometeorological role in risk reduction, providing increased stability to natural cycles and processes (mainly hydrological), since most of the country’s upper watersheds are included in PAs as recognized by Decree 42-91, which declares all mountains, volcanoes, and river headwaters as PAs. Locally, PA governance is through MARENA’s Territorial Delegations

- There are 28 documented forest types in Nicaragua. Among these, Nicaragua’s tropical dry forests and tropical humid forests are critical for the delivery of multiple environmental benefits. Nicaragua’s tropical dry forests are home to globally important plant species such as the oak (Quercus oleoides), the gourd (Crescentia alata), the boxwood (Phyllostylon brasiliensis), Holywood Lignum-vita (Guaiacum sanctum), and the Brazilwood (Haematoxylum brasiletto). Wildlife species include endangered species such as the spider monkey (Ateles geoffroyi), various cats including Felis onca, F. concolor, F. pardalis, F. wiedi, and F. yaguaroundi, the Baird's tapir (Tapirus bairdii), and the Mexican anteater (Tamandua mexicana). Notable bird species are the White-throated Magpie-Jay (Calocitta formosa) and the Turquoise-browed Motmot (Eumomota superciliosa), species that are limited to the tropical dry forest, as well as a wide variety of migratory birds (e.g., Chlidonias niger, Tyrannus tyrannus, Petrochelidon pyrrhonota, Hylocichla mustelina, Vireo olivaceu. Tropical dry forests provide multiple environment services including the maintenance of soil fertility and the recycling of nutrients, providing habitat to BD adapted to low and seasonal water availability, water regulation and storage critical for agriculture, firewood, timber, and flood control during rainy seasons. The tropical dry forest ecosystem is one of the least represented in the SINAP. According to the BCGA, only 123,280 ha are contained within PAs and the protection of an additional 124,105 ha of tropical dry forest is required to comply with national conservation goals.

- The tropical humid forests of north-central Nicaragua are globally important since it is the point where North and South American flora and fauna mix; these forests are valued as one of 11 priority conservation areas in Central America due to their high BD (370 species of trees and shrubs; 278 species of birds, 36 of which are migratory birds; 85 species of mammals; and 15 species of poisonous snakes). These forests are dominated by Dialium guianensis, Ampelocera hottlei, and Pseudolmedia oxyphyllaria; pre-montane tropical very humid forest, which includes species such as Dialium guianensis, Pouroma bicolor, and Ocotea paulli; and low montane very humid forest. Among the bird species present is the harpy eagle (Harpia harpyja) and the scarlet macaw (Ara macao). Mammals include the cougar (Felis concolor), the jaguar (Felis onca), the two-toed sloth (Choloepus hoffmanni), and the tapir (Tapirus bairdii), the latter being an endangered species. In addition to providing habitat for BD, these forests also play a central role as a climate regulator for the region, are important reservoirs of C, and provide multiple goods and services to the people who inhabit them, including food, timber, control of erosion and maintenance of soil productivity, and water regulation.

- Despite the fact that Nicaragua still maintains considerable forest cover (3,398,000 ha or 26.1% of the national territory), it is currently undergoing a process of severe soil degradation caused by unregulated activity and exploitation of forest resources and due to the effects of drought in a large part of the country. The rate of deforestation is approximately 74,663 ha/year (2.1%) leading to an accelerated loss of BD and forest cover, the reduction of surface and ground waters, and soil erosion. An analysis of changes in land use and forest cover, which was developed as part of the Readiness Preparation Proposal (R-PP) of Nicaragua (2011), determined that the principal historical causes for the conversion of forests to other land uses (deforestation) in the Pacific region are agriculture (55.9%), cattle ranching (34.4%), and agroforestry (9.8%). For the north-central region of the country, the expansion of cattle ranching has resulted in the conversion of 45.5% of original forest cover, with agriculture and agroforestry at 39.5% and 15.1%, respectively. In the central-southern and Atlantic regions the tendency towards conversion of forest cover from cattle ranching is 74% and 56.2%, respectively. For the year 2008 it was estimated that 68.7% of the total area of the country’s original forest cover had been converted to other uses.

- The BCGA identified the tropical dry forest as one of the most threatened ecosystems in Nicaragua. According to the National Forestry Institute (INAFOR, 2009), the current dry forest cover in the country is 156,930 ha (3,553,128 tC; 22.6 tC/ha); it is estimated that 77% of the original dry forest has been converted to other uses. The expansion of agriculture and unsustainable land use practices (e.g., the excessive use of fertilizer, extensive farming, intense timber extraction, slash-and-burn agriculture, among others) have been among the main factors for the loss and degradation of this ecosystem. In addition, the high population density in the Pacific, northern, and central regions of the country, which are where the dry areas are located (80% of the Nicaraguan population is concentrated in these regions), and infrastructure development are also sources of pressure. It is common for the rural population in these areas to use forest remnants for timber extraction or for establishing subsistence farming plots, thereby promoting desertification. The tropical dry forest region of Nicaragua strongly depends on the services and functions of the tropical dry forest ecosystem, namely as soil and water resources, for economic development and daily subsistence of the region’s native communities. The dry region’s agricultural production supports the entire country, offering more than 60% of the country’s jobs and 55.8% of total exports. This region produces 49% of the bean crop, 33% of corn, 100% of the nation’s sorghum, and 80% of the beef. Despite the fertility of the volcanic soils in the region, this area’s severe degradation during the last decades has led to a 30% to 50% reduction in national agricultural production.

- Nicaragua is highly vulnerable to climate variability. According to the modeling work conducted by the Water Center for the Humid Tropics of Latin America and the Caribbean (CATHALAC), Central America will be significantly affected by CC by the 2020s and the areas that will be most affected are those currently classified as dry lands. Furthermore, by the 2080s, in terms of the “comfort zone” of climatic niches that species and ecosystems have become tolerant to, if worst-case scenario conditions prevail, all of the ecosystems and species of Central America will be subjected to conditions well outside of their traditional “comfort zones.” CATHALAC also concluded that the potential CC impact on the ecosystems and species most likely to be affected are already within PAs, and they may find it difficult to adapt to the forecasted climatic changes. Among the countries most affected is Nicaragua: the Pacific region, where over 65% of the population lives and which presents high levels of extreme rural poverty and low precipitation rates, is the most vulnerable. Additionally, Nicaragua is extremely susceptible to hurricanes, earthquakes, volcanic eruptions, and landslides. It is believed that CC will result in an increase in the frequency and severity of natural disasters.

- The degradation of the land in dry areas because of the impacts of CC and unsustainable production practices has contributed to desertification. Climatic phenomena such as El Niño, which is exacerbated by CC, prolonged drought, and the presence of hurricanes, has caused a loss of basic grain crops in consecutive production cycles and contributed to the near disappearance of surface and ground water resources. These losses, together with increasing poverty, has led small producers (i.e., owners of farms less than 17 ha in size, representing 80% of all producers in the country) to intensify the use of non-sustainable land use strategies such as extensive grazing and slash-and-burn agriculture, or to invade existing forests to extract timber as a means of generating alternative sources of income. The consequences of this sequence of events have led to increased land degradation along with a reduction of BD in PAs and the loss of ecosystem connectivity. Land and natural resources use planning and management outside PAs is the responsibility of the municipal governments. These are also responsible for delivery of technical support to farmers. In areas where soils present high levels of degradation or are threatened, the Ministry of Agriculture and Livestock, in coordination with MARENA and the Municipal Councils, may establish soil conservation areas and define management standards to prevent their degradation and ensure their protection and recovery. The Office of the Environmental Attorney ensures compliance with environmental laws. Approximately 60% of the land in Nicaragua has some form of title, and farm sizes vary considerably and include small (less than 17 ha), medium (18 to 100 ha), and large holdings (over 100 ha).

- The following baseline was developed for each of the four focal areas addressed by this project: 1) Biodiversity: the problem that the baseline activities seek to address is the loss of dry and humid forests and BD and their ability to generate goods and services (water generation, BD habitat, and C sequestration). Investments for PA management are expected to be on the order of $7 million USD/year for the period of 2013-2018. Additionally, through the Program for the sustainable management of natural resources and promotion of entrepreneurial capacities (MASRENACE, Phase III; 2011-2013) an investment of $3.1 million USD, with support from the German Agency for Technical Cooperation (GIZ), will contribute to BD conservation in municipalities of the southwest and in the North Atlantic Autonomous Region (RAAN), including the BBR, through the administration, conservation, and sustainable management of natural resources in and around forests by rural communities and relevant public agencies in selected municipalities. 2) Land degradation: the problem that the baseline activities seek to address is the loss of soil productivity and desertification in arid and semi-arid zones. Through the Integrated management of watersheds, water and sanitation project (PIMCHAS - MARENA), the Government of Nicaragua (GoN), with financial support from the Government of Canada, will aim to improve the quality of life and economic welfare of the residents of the semi-arid areas of northern Nicaragua through the improved management and use of water resources. Phase 3 of PIMCHAS (2012-2015) includes an investment of $2.3 million USD in highly vulnerable environmental and social areas in the Estelí River and Old River sub-basins, and the Black River and Estero Real River basins, specifically in the areas of aquifer recharge and catchment sites that supply water to the towns of 11 municipalities. 3) Climate change: the baseline activities aim to promote good practices for land and forest cover management as well as the restoration and enhancement of C stocks in dry ecosystems and humid forests. The Environmental program for disaster risk and climate change management, with an investment of $13 million USD for the period of 2011-2015 and financial support from the Inter-American Development Bank (IADB) and the Nordic Development Fund (NDF), is under implementation in the Río Viejo and Lake Apanás sub-basins (upper San Juan River Basin, southeastern Nicaragua). This investment will allow: a) increased tree cover, improved soil conservation areas by ensuring the efficient water use, increased infiltration, topsoil conservation, reduced erosion, and stabilized slopes to limit the risk of landslides during the rainy season; b) enhanced water capture through water-harvesting systems that will increase water supply for household and production during the crop cycle; c) construction works in critical areas for climate-related risk reduction that will benefits an estimated 34,329 vulnerable people; and d) increased knowledge among the population about the risk and vulnerability to extreme events, climate variability and change, and the development of municipal plans for risk management and CC adaptation. In addition, the project Reducción de la Vulnerabilidad y Adaptación al Cambio Climático en la Región de Las Segovias, with an investment of $3.2 million USD (2012-2015) and support from the Swiss Cooperation and the UNDP, will contribute to reducing poverty by increasing the resilience of vulnerable populations and their livelihoods to CC in northern Nicaragua. 4) Forests/REDD+: the baseline activities seek to address the problem of increased C emissions from deforestation and forest degradation. Through MARENA, the GoN developed the R-PP to implement the ENDE and REDD+ activities. The ENDE/REDD+ aims to integrate actions at national, sub-national, and local levels for reversing the main causes of deforestation and forest degradation. The expected key results from the R-PP implementation process are: a) sufficient local, territorial, regional, and national knowledge to design the ENDE and implement REDD+; b) local, territorial, regional and national capacity-building, acquiring and sharing techniques and technology among the stakeholders involved in carrying out the REDD+ mechanism in Nicaragua; c)  a national and regional revised ENDE/REDD+ forest monitoring system; and d) key local, territorial, regional and national stakeholders are aware of the importance of the ENDE/REDD+ and have participated in the design and/or consultations of each R-PP component, as well as in the planning and execution of the activities in the preparatory stage of the ENDE/REDD+. The R-PP will be implemented between 2012 and 2015 and has a total budget of $10.27 million USD, of which $3.4 million USD are expected to be obtained from the Forest Carbon Partnership Facility (FCPF). Local government contributions are estimated at $250,000 USD (the GoN’s contribution has yet to be tallied, but it is estimated to be between 5 and 10% of the current budget), and $1 million USD is anticipated through the REDD Central American Commission on Environment and Development−German Technical Cooperation agency (CCAD-GIZ) project (2010-2016). In addition, investments on the order of $2.5 million USD over the next 5 years will be made through the National Forest Development Fund (FONADEFO/INAFOR) to be used in promoting reforestation for the conservation of natural resources and the development of markets for payments for environmental services (PES).

- The baseline investments although significant are neither coordinated across the landscape nor sufficient enough to sustain the flow of multiple ecosystems services. The long-term solution is to overcome these deficiencies through strengthened multiple-use PA management that conserve core areas nested in a wider landscape where multiple environmental benefits are delivered by sustainable forest and land management in western and north-central Nicaragua. A PA management approach that successfully integrates BD conservation and the sustainable use of natural resources in the landscape will effectively reduce threats originating outside of the PAs and will contribute to the reduction of deforestation and desertification, enhance C stocks, and maintain forest cover between PAs. Currently, there are two barriers which prevent this objective from being achieved:

| Weak institutional capacity framework for the effective management of multiple-use PAs | Government officials and members of local organizations and communities have limited capacity to effectively manage multiple-use PAs in dry forest and humid forest landscapes of the western and north-central regions of Nicaragua in order to maximize BD conservation benefits. There is limited capacity to integrate multiple-use PA management with the wider landscape, reducing opportunities to maximize the delivery of ecosystems services, including quality habitat for BD. According to the Regulation of Protected Areas of Nicaragua (Decree No. 01-2007), multiple-use PAs are administered by MARENA and can be given in co-management. Activities allowed in multiple-use PAs include research, technical studies, monitoring, environmental education and interpretation, sustainable tourism and recreation, and sustainable agricultural production activities under silvopastoral and agroforestry systems. However, MARENA has limited capacity to articulate the geographical and technical scope of these activities, including procedures, roles and responsibilities, in the context of community-based management plans. In addition, multiple-use PAs have a weak governance framework and limited technical, monitoring and enforcement capacity. MARENA has not developed efficient coordination and cooperation mechanisms with municipal authorities to reduce threats emerging from outside PAs and this has prevented the achievement of the PAs’ management goals, including the sustainable delivery of environmental goods and services (e.g., water, energy, timber, and outdoor recreation). PA officials and potential local partners for conservation, including municipalities, lack the knowledge and skills to design biological corridors in adjacent production landscapes that contribute to reducing threats and increase connectivity. An approach to BD conservation that considers the wider landscape needs to be incorporated into the management plans for existing multiple-use PAs. Similarly, there is absence of information and monitoring systems that employ indicators to assess the impact of strategies that are designed to reduce vulnerability and enhance BD conservation and to facilitate decision-making. Finally, multiple-use PA management must be strengthened not only with new financial resources from government and private sources but also with specialized financial and management staff that ensures cost-effective administration procedures. |
| --- | --- |
| Limited planning and management capacities and mechanisms for generating global environmental benefits through sustainable forest and land management in the wider landscape (corridors) between multiple-use PAs | The generation of environmental benefits through sustainable forest and land management between multiple-use PAs requires effective cooperation between national and local environmental authorities, and the involvement of local communities and farm owners. Cooperation between municipal authorities responsible for land use planning and for verifying compliance with the environmental standards established by law (i.e., Municipalities Act, No. 40/1988) at the local level, and the national environmental authorities, is limited by the lack of tools and skills that would enable them to align land and natural resources use within the municipality with conservation objectives of the surrounding PAs. Similarly, the ability of municipal officials to provide land use planning support to landowners to implement sustainable production systems and land use plans with environmental benefits within their properties is limited. In addition, environmental information and monitoring mechanisms to facilitate decision-making, the assessment of the benefits of sustainable forest and land management, and enforcement at the municipal level are lacking. In turn, national environmental authorities do not have the required skills to support their municipal counterparts to implement strategies for sustainable forest and land management or for the conservation of biodiversity. National authorities have limited knowledge about methodologies for implementing SFM/REDD+, LULUCF, and the quantification and evaluation of C flows to assess changes in C stocks. Finally, there is a lack of financial incentives for landowners to carry out integrated farm management practices and conserve forest patches within their farms, which would contribute to improving ecosystem connectivity through biological corridors. Land owners lack farm management plans that would improve on-farm sustainability through agroforestry and silvopastoral systems and that would enhance ecosystem connectivity. |

B.2. Incremental /Additional Cost Reasoning (describe the incremental (GEF Trust Fund) activities requested for GEF/LDCF/SCCF financing) and Associated Global Environmental Benefits (GEF Trust Fund):

- The project’s objective is to strengthen the management effectiveness of 11 multiple-use PAs and the sustainable use of tropical dry forests and humid, semi-humid, and cloud forests in the wider landscape that surrounds them to ensure the flow of multiple forest ecosystem services, including BD habitat, C storage, water regulation and supply, and the control of erosion and protection of soils. The project’s incremental approach consists of two main components summarized as follows: Component 1 will strengthen the management effectiveness of the 11 multiple-use PAs and Component 2 will deliver multiple global environmental benefits through sustainable forest and land management practices implemented in the wider landscape around these PAs. Component 2 activities will facilitate connectivity between the 11 multiple-use PAs in order to constitute 4 biological corridors listed in Table 1.

- Component 1 will improve the management effectiveness of 11 existing multiple-use PAs in tropical dry forest and humid/semi-humid/cloud forest landscapes. PA management effectiveness will be assessed using METT (the baseline will be established during the PPG phase). To this end, the project will develop management plans for existing PAs (e.g., the Mombachito-La Vieja NR) and will update existing  management plans to include a landscape approach to BD conservation. More specifically, management plans will include designs to improve ecological connectivity between the multiple-use PAs and the surrounding landscape, and a management framework for monitoring, surveillance, and enforcement as well guidelines for allowable production activities within and between the PAs. Improved governance mechanisms will also include the establishment of multi-sectoral collaborative management committees and management agreements for the administration of 11 existing multiple-use PAs that specify access areas for the sustainable use of forest products and offtakes, BD-friendly production methods, agreed-to management measures, and monitoring and enforcement mechanisms. A monitoring and information system will be put into place under the supervision of MARENA officials and in coordination with local environmental authorities to strengthen decision-making processes and facilitate compliance and monitoring of threats to BD in 11 existing multiple-use PAs. The management of the multiple-use PAs will be strengthened through government funding derived from the application of the Law of Conservation and Sustainable Use of Biodiversity (No. 200/2012), which outlines financial mechanisms for the financial sustainability of the SINAP (including country and PAs’ visitors entry fees), REDD+ incentives, collaborative management agreements, and other sources identified as part of the financial strategies developed for the SINAP. Component 1 will also improve the capacity of MARENA to effectively deliver PA management functions across multiple-use PAs in dry forest and in humid, semi-humid, and cloud forest landscapes. More specifically, by the project’s end MARENA will have strengthened enforcement and control capacity, a more effective deployment of funds and human resources to address threats to multiple-use PAs, and improved administration at its Headquarters and in its Local Territorial Delegations. A total of 30 national-level officials and 30 PA staff will be trained. As a result, the threats facing 11 multiple-use PAs (such as non-sustainable agriculture and cattle ranching, illegal logging, trade of vulnerable and endangered species, and forest fires) will be reduced across an area of 125,669 ha and encompass the reduction of the vulnerability of threatened BD.

- Component 2 will allow the delivery of multiple global environmental benefits through sustainable forest and land management between multiple-use PAs. The project will improve the ecosystem structure and functionality of tropical dry forests and in humid, semi-humid, and cloud forests by promoting connectivity between existing multiple use PAs and the forest remnants between them in order to consolidate 4 biological corridors (Chinandenga-Rivas Dry Forest Corridor, Cumaica Cerro Cerro Alegre–Mombachito Cerro La Vieja–Sierra Amerrisque Biological Corridor, Lake Nicaragua Islands Corridor, and Peñas Blancas–Kuskawas–Kilambé Corridor). The institutional capacity for supporting the sustainable management and conservation of the wider landscape between multiple-use PAs will be strengthened, including: a) the capacity of national and regional officials and field personnel to support the use of SFM/REDD+ methodologies, the quantification and evaluation of carbon (C) flows, and the development of strategies to conserve BD; and b) the capacity for municipal authorities to implement  SFM, SLM, and CC mitigation measures, as well as for effective monitoring and enforcement. In addition, municipal authorities will be equipped with GIS mapping tools to implement SFM and SLM, including the implementation of land use plans and ecological zoning for the consolidation of biological corridors connecting multiple-use PAs. At the farm level integrated farm management plans specifying the spatial and temporal arrangements of different land uses across farms will be in place, allowing farmers to improve on-farm sustainability, including the implementation of agroforestry and silvopastoral systems, and to improve ecosystem connectivity within and between farms. To facilitate the implementation of sustainable production practices, the project will train 40 municipal technical staff and 500 farmers/community members in the use of SFM, SLM, and BD conservation tools.

- One performance-based compensation (payments) mechanisms for the generation of income in multiple-use PA landscapes through ENDE/REDD+ will provide the incentives required for the conservation of tropical humid forest blocks within the landscape. ENDE/REDD+ actions will reduce GHG emissions in a 30,000-ha humid, semi-humid, and cloud forest landscape through 25% reduction in deforestation, respectively. The methodology for the implementation of the ENDE-REDD+ activities for avoided emissions will be selected from among the nearly 15 methodologies approved under the Verified Carbon Standard (VCS). The selected methodology will be adjusted according to local conditions and will include a proposal for performance-based compensation mechanisms (i.e., payments) through sources such as FONADEFO, other government funds, and international funding mechanisms that will be identified during the project’s PPG phase. Payments from these funds will continue after project completion to guarantee the sustainability of the SFM/REDD+ activities. According to Cancun’s COP decision 4/CP.15, the scope of a REDD+ project includes reducing emissions from deforestation and forest degradation, conserving and enhancing forest C stocks, and ensuring the sustainable management of forests. Additionally, an activity for coordination with the FCPF will be included as part of the PPG and the specifics will be determined at the time of the CEO Endorsement and included as part of the incremental cost analysis. During the PPG phase, actions will be coordinated with national stakeholders to determine the added value of this proposal in the development of Nicaragua’s R-PP for the FCPF, which may include contributions to capacity-building, the development of ENDE-REDD+ related payment, the development of the National Forest monitoring system of the R-PP; the design of an information system for multiple benefits and other impacts, governance, and safeguards; and  to the development of a baseline or reference level for ENDE-REDD+ at the sub-national level.

- Ecosystem connectivity will be further enhanced through the natural rehabilitation of 2,000 ha of degraded dry forest and humid forest areas. Finally, municipal-level monitoring and enforcement systems will facilitate decision-making and the assessment of SFM/SML and BD benefits. The development of the monitoring systems to assess project benefits will make use of existing initiatives, including those being carried out as part of the GEF-funded project Integrated Watershed Management in Lakes Apanás to assess C flows (PPG activities will include the assessment of existing monitoring systems) and will be linked to existing platforms such as the SINIA, the SIAM, and the ENDE’s monitoring system. The monitoring system will include gender-based indicators used to assess the equitable distribution of projects benefits among women and men, as well as indicators for youth and the elderly.

- Table 1. List of biological corridors consolidated by the 11 multiple-use landscape in the wider landscape:

| Corridor Name | Ecosystems | Location | Ecosystems status | Protected areas |
| --- | --- | --- | --- | --- |
| Dry Forest Corridor | - Tropical dry forest - Transitional humid forest - Mangroves, coastal lagoons, and beaches (coastal areas) | Chinandega and Rivas departments (Pacific region) | - Large degraded areas - Some natural regeneration areas - Some areas need to be restored | - Volcán Cosigüina NR - Estero Padre Ramos NR - Estero Real NR - Apacunca Genetic Reserve |
| Lake Nicaragua Island Corridor | - Humid and cloud forests. - Gallery and dry forests - Wetland ecosystems | Ometepe Island Biosphere Reserve, Lake Nicaragua | - Dry forests and wetlands threatened by agricultural expansion and habitat fragmentation and degradation - Water pollution - Poaching of wildlife and timber extraction - Uncontrolled tourism and the development of coastal properties | - Volcán Concepción NR - Volcán Maderas NR |
| Cumaica Cerro Cerro Alegre–Mombachito Cerro La Vieja–Sierra Amerrisque Biological Corridor | - Tropical dry forest - Sub-humid forest | Boaco and Chontales departments (central region) | - PAs have low ecosystem coverage and are fragmented - Some areas need to be restored - Unstable/steep slope areas vulnerable to landslides | - Cerro Cumaica - Cerro Alegre NR - Cerro Mombachito– La Vieja NR - Sierra Amerrisque NR |
| Peñas Blancas–Kuskawas–Kilambé Corridor | - Tropical humid forest - Sub-tropical humid forest - Tropical montane forest | Jinotega department (north-central region) | - Deforestation - Agriculture and cattle ranching | - Macizos de Peñas Blancas NR - Cerro Kilambé NR |

- The global environmental benefits to be delivered through project are presented below:

| - Current Practice (Baseline) | - Alternative to be Put in Place by the Project | - Global Environmental Benefits |
| --- | --- | --- |
| - Component 1: - Limited capacity of PA officials at the national and local levels to effectively manage PAs - Inadequate allocation of funds and human resources to address threats to multiple-use PAs and BD | - New and updated multiple-use PA management plans include a landscape approach to BD conservation. - New financial resources available for PA management derived from government and private funds. - Information system facilitates decision-making regarding multiple-use PA management and facilitates monitoring of threats to BD. - Multi-sectoral collaborative agreements for shared management of multiple-use PAs and the reduction of threats. - Improved skills and knowledge of MARENA officials to effectively deliver PA management functions across multiple-use PAs. | - 1. Improved effectiveness of eleven (11) existing multiple-use PAs management. - 2. Threats facing 11 multiple-use PAs (non-sustainable agriculture and cattle ranching, illegal logging, trade of vulnerable and endangered species, and forest fires) are reduced across an area of 125,669 ha. - 3. 104,233 ha of dry forest habitat and 21,436 ha of humid, semi-humid, and cloud forest secured. - 4. Stable numbers of key species of biological groups (mammals, birds, and plants), including the protection of 27 endangered wildlife and plant species such as Cocodrilos acutus, Lepidochelys olivácea, Chelonia mydas agassizii, Eretmochelys imbricata, Dermochelys coriácea, Pharomachrus mocinno, Cebus capucinus, Ara macao, Amazona auropalliata, and Ateles geoffroyi. |
| - Component 2: - Fractured connectivity between dry forest patches and between humid, semi-humid, and cloud forest patches outside existing multiple-use PAs. - Nonsustainable agricultural and cattle ranching practices promote soil degradation, desertification, and deforestation. - Overexploitation of dry forest resources (timber and firewood extraction) reduces water generation and retention capacity. - Overexploitation of humid, semi-humid, and cloud forest resources, including extraction of timber and firewood. | - Improved ecological connectivity between existing multiple-use PAs and dry forest patches in a 25,000 ha productive landscape. - Improved ecological connectivity between existing multiple-use PAs and humid, semi-humid, and cloud forest patches in a 30,000-ha productive landscape. - 2,000 ha of dry and humid forests restored through natural rehabilitation of degraded areas. - Improved management of 10 watersheds to maintain forest cover and water flows. - Information and monitoring systems allow environmental authorities to assess SFM/REDD+, LULUCF, CC, and BD benefits and facilitate decision-making. | - 1. Ecosystem connectivity: - 25,000 ha of dry forest in biological corridors improve ecosystem resilience to CC and provide refuge for globally important BD in dry forest landscapes. - 30,000 ha of humid, semi-humid, and cloud forests in biological corridors improve ecosystem resilience to CC and provide refuge for globally important BD in humid/semi-humid/cloud forest landscapes. - 2. C sequestration: - 1,000 ha of dry forests restored over a 5-year period (i.e., project length): 102,760 tCO2-eq (1,000 ha x 28 tC ha/yr[] x 5 years x 3.67 CO2 conversion factor). - 1,000 ha of humid/semi-humid/cloud forest restored over a 5-year period (i.e., project length): 330,300 tCO2-eq (1,000 ha x 90 tC ha/yr[2] x 5 years x 3.67 CO2 conversion factor). 3. Avoided emissions: - Emissions reduction from deforestation (average deforestation rate of 1.84%/yr) of 30,000 ha of tropical humid forests: 568,315 tCO2 over a 5-year period (# of ha x annual deforestation rate x 212 tC ha/y [] x 3.67 CO2 conversion factor). 4. Sustained water flows and forest cover in 10 watersheds. |

B.3. Socioeconomic Benefits to be delivered by the Project at the national and local levels, including consideration of gender dimensions, and how these will support the achievement of global environment benefits (GEF Trust Fund)

- The majority of the population residing in the dry region of Nicaragua is economically disadvantaged, particularly the rural communities where 63.3% are classified as impoverished. The project will benefit 1,500 families, 250 of whom have women as heads of households, and 25 families from indigenous communities in the multiple-use PA landscapes. This will be achieved through: a) the equitable distribution of economic benefits derived from compensation for forest credits through national funds such as FONADEFO, which could increase net income from $4 to $5 USD per tCO2-eq/year); the training of local community members, including women, in the implementation of ENDE-REDD+ practices, sustainable forest management and conservation, and sustainable use of biodiversity; c) improved agroecological conditions in multiple-use  PA landscapes that will contribute to improving production systems and restoring degraded soils in cultivation areas; and d) the restoration and enhancement of 2,000 ha of tropical forest with native species that will serve as energy and timber sources for local use and income generation for the communities. Promoting the use of firewood-saving kitchen stoves and establishing and managing species as an energy source will specifically involve the participation of groups of women. To ensure that gender and indigenous issues are fully incorporated throughout the project proposed herein, a gender/indigenous specialist will be hired during the PPG phase to specifically address these topics. Gender-based indicators will be included in the project’s results framework to assess the equitable distribution of projects benefits among women, men, youth, and the elderly.

- Through the protection and improvement of tropical forest cover and the promotion of activities geared towards implementing land use best practices, the project will help to reduce the vulnerability of local communities to extreme natural events that are related to CC and variability. Members from at least 30 communities and local government authorities will also benefit from training for the implementation of landscape management tools (i.e., agroforestry and silvopastoral systems) in the prioritized tropical dry forest and humid/semi-humid forest corridors. Finally, the development of sustainable management plans for the tropical dry forest area in 10 watersheds will help to reverse the population’s current and future deficit of available water and improve the economy of the Pacific region of Nicaragua.

B.4. Risks, including climate change risks that might prevent the project objectives from being achieved, and if possible, propose measures that address these risks to be further developed during the project design:

| Risk | Level* | Risk Mitigation Strategy |
| --- | --- | --- |
| Limited benefits to farmers from conservation and sustainable forest and land management sustain pressures on PAs from competing land uses | M | To mitigate this risk, the project will make use of conservation-based and sustainable forest management-based incentives (including performance-based payment plans) to promote the implementation of sustainable production practices. Farmers participating in these activities will be properly informed about the benefits of conservation and sustainable forest and land management and will benefit from related training. In addition, famers will receive project assistance for the development of integrated farm management plans that will specify the spatial and temporal arrangements of different land uses across farms, allowing farmers to improve on-farm sustainability. |
| Failures in the functioning of relations between PA staff and municipal authorities limits the integration of PA management with conservation efforts in the wider landscape | L | To promote collaboration between PA staff and municipal authorities, the project will make use of collaborative agreements that allow the joint management of PAs. By doing so, municipal authorities will be able to more easily integrate conservation efforts within and from outside of PAs, while PA authorities will have a chance to buffer PAs more effectively. Both PA staff and the municipal authorities will have access to information and monitoring systems that will facilitate the exchange of information and enable joint decision-making. Furthermore, the project will involve both parts in all stages of the project design phase as a way to promote early collaboration and to build trust. During project implementation, the joint development and application of work plans and indicators will be promoted. |
| Poorly developed tenure conditions limit producers’ eligibility for REDD+ and other incentives | M | In order to reduce the risk related to the lack of clarity regarding land property and use rights, the project will work closely with local governments to coordinate land titling, respecting all existing forms and regulations that guarantee those rights. In the cases where there is little clarity or conflict exists regarding property and use rights, the project will assume a conciliatory approach in order to arrive at the best solution possible for all parties without compromising the achievement of the project’s outcomes. |
| Degradation of the tropical dry forest and loss of forest coverage as a consequence of extreme climatic events | L | The risks related to CC may include more intense dry seasons and/or torrential rains associated with tropical storms and hurricanes. This could lead to increased forest degradation, including changes to plant communities or forest/ecosystem cover due to landslides, accelerated loss of soils, and desertification. The project’s actions for sustainable forest and ecosystem management will translate into more solid and increased coverage, as well as healthier forests (for example, diversity of age classes and greater regenerative capacity) that are resilient to climate variability. In addition, there will be greater protection of the soils and regulation of hydric cycles that generate stable microclimatic conditions with benefits for their associated species and forests, as well as a reduction of vulnerability of local communities to CC. |

*L= low; M = medium; H = high

B.5. Key Stakeholders involved in the project including the private sector, civil society organizations, local and indigenous communities, and their respective roles, as applicable:

| Stakeholders | Project Implementation Role |
| --- | --- |
| Ministry of Environment and Natural Resources (MARENA) | Lead agency for environmental management in Nicaragua (e.g., GoN representative to the UNFCCC, Natural Heritage, and PAs). It will guide the actions for SFM, BD conservation, PA management, reduction of land degradation, and CC mitigation. |
| Municipalities | The municipalities will participate actively in the planning and management of multiple-use PAs and biological corridors, which will bring local benefits through BD conservation and a sustainable flow of goods and services. The municipalities will be direct beneficiaries of the project in terms of training in REDD+, sustainable forest and land use management, and BD conservation. |
| Civil Society Organizations (CSOs) | NGOs will contribute to multiple-use PA management, consolidation of biological corridors, and the mobilization of resources (financial, technical, and training). They will be involved in providing technical assistance for the implementation of the project and some may serve as co-financiers. The NGOs working in the project multiple-use PAs include: FFI, FUNDAR, LIDER, CUCULMECA, AMIGOS DE LA TIERRA, PASO PACIFIC, and others. Universities include: UCA, UNAN-León, UNA and BICU-URACCAN |
| Private sector | Cooperatives or producer associations and tourism companies associated with PAs. |
| Ministry of Agriculture and Forestry (MAGFOR) and the National Forestry Institute (INAFOR) | Coordination of actions with the MAGFOR and INAFOR will promote sustainable forest management and improve the management effectiveness of buffer zones of multiple-use PAs. |

B.6. Coordination with other Related Initiatives:

- Actions will be coordinated with the 5-year (2011-2016) GEF-funded project Integrated Watershed Management in Lake Apanás, with support from the IADB. In particular, coordination mechanisms will be established for the development of a C monitoring system. This project has MARENA as one of its implementing partners, which will facilitate the exchange of information and/or lessons learned between the two projects. Discussion groups will be formed by the projects’ coordinators and team members and will meet periodically in person or virtually to share ideas and experiences. The directors of MARENA and the technical team from the Environmental Program and Development Unit will ensure that the lessons learned are taken into consideration during the implementation of the project proposed herein, including the development of a C monitoring system to assess C flows and benefits. The project will also coordinate actions with the recently approved Special Climate Change Fund (SFFC)-funded project Adaptation of Nicaragua's Water Supplies to Climate Change, with support from the Word Bank. The SFFC-funded project aims to enhance climate resilience of investments in Nicaragua’s rural water supply sector to cope with both increasing climate variability and the expected adverse impacts of CC in selected areas. Special consideration will be given to climate-related aspects for water resource management in the prioritized project watersheds. Additionally, experiences and lessons learned will also be exchanged with the project financed by the Adaptation Fund, Reduction of Risks and Vulnerability Based on Flooding and Droughts in the Estero Real River Watershed, with support from the UNDP, particularly in terms of the development of agroecological practices that are resilient to climate change. Similarly, actions will be coordinated with the Environmental program for disaster risk and climate change management (2011-2015), which is currently under implementation in the Río Viejo and Lake Apanás sub-basins (upper San Juan River Basin, southeastern Nicaragua) with support from the IADB and the NDF. Given the multiple climate-related initiatives in Nicaragua, as part of the PPG activities, coordination mechanisms between all projects will be clearly defined and lessons learned will be assessed for their effective incorporation into the final project design. In additional, team members of all related projects currently under implementation will be invited to participate in PPG activities, including the inception and results framework workshops.

- Lessons learned from the implementation of the GEF-funded project Strengthening and Catalyzing the Sustainability of Nicaragua's Protected Areas System will also be incorporated. This PA project has support from the UNDP and has as its objective the effective management of the Nicaraguan SINAP through legal reform, strengthened institutions, sustainable financing, and partnerships. The project’s is reaching completion. Added value through this new GEF investment to multiple-use PAs that benefited from the SINAP project include joint PA management through multi-sectoral collaborative agreements, implementation of financial mechanisms to support PA management developed through the SINAP projects (e.g., visitors’ entry fees), and a PA management approach that successfully integrates BD conservation and the sustainable use of natural resources in buffer zones to reduce threats originating outside of the PAs. Similarly, lessons learned from the GEF-funded project Sustainable Land Management in Drought Prone Areas of Nicaragua, implemented between 2006 and 2011 with support from the UNDP, will be incorporated, particularly: a) the importance of incorporating gender considerations into the project design to ensure the equitable distribution of benefits; b) the necessity of establishing mechanisms for the replication of successful BMPs and experiences with the participation of beneficiary groups to facilitate the extension of these benefits to other local groups; and c) the importance of having flexible mechanisms to facilitate adaptive management. Lessons learned will also be incorporated from the GEF- funded project Conservation of Dry Forest and Coastal Biodiversity of the Pacific Coast of Southern Nicaragua: Building Private-Public Partnerships regarding the establishment of lasting relationships between government agencies and civil society, which will be instrumental for the consolidation of biological corridors and effective PA management. This project was finalized in 2010 and was supported in part by UNDP.

- Coordination mechanisms will also be established with the ENDE/REDD+ strategy for Nicaragua, which has partial funding from the FCPF and support from the World Bank (NITF 099264) (2011-2013). In particular, coordination will be sought for the exchange of information and lessons learned regarding the reduction of emission from deforestation, the conservation and restoration of C stocks, and sustainable forest management.

- Finally, actions will be coordinated with the following projects: a) the Program for the sustainable management of natural resources and promotion of entrepreneurial capacities (MASRENACE) financed by the German Government through the GIZ Agency (2011-2013), under implementation in the RAAN and the BBR; and b) the project Local Governance in the Catchment Area of Lake Cocibolca, financed by the European Union (2011-2015), whose objective is to strengthen environmental management and to protect the natural resources of the Lago Cocibolca (or Lago de Nicaragua) watershed.

C.   describe the GEF agency’s comparative advantage to implement this project:

- The comparative advantage of the UNDP for GEF lies in its global network of Country Offices, its experience in the formulation of integral development policies, institutional strengthening, and the participation of the non-governmental sector and communities, as specified in the document Comparative Advantage of the GEF Agencies (GEF/C.31/5rev.1). UNDP currently supports SFM and REDD+ activities in over 25 countries around the world. Under the UN/REDD, UNDP is currently working in five countries in Latin America and the Caribbean (Bolivia, Panama, Ecuador, Paraguay, and Mexico) on SFM and REDD+ readiness projects with a total investment of over $30 million USD. In addition, the UNDP has a long history providing assistance to the GoN in the promotion, design, and implementation of activities that are consistent with GEF mandates as well as with national plans for conservation and sustainable development. The UNDP has been identified by MARENA as the appropriate GEF Implementing Agency for this initiative, given its development experience with multiple GEF projects in BD, land degradation, CC, and sustainable forest use. The project proposed herein is consistent with UNDP’s Biodiversity and Ecosystems Global Framework 2012-2020, which has an overall strategic objective to “Maintain and enhance the goods and services provided by biodiversity and ecosystems in order to secure livelihoods, food, water and health, enhance resilience, conserve threatened species and their habitats, and increase carbon storage and sequestration.”

C.1.Indicate the Co-financing amount the GEF agency is bringing to the project:

- UNDP will contribute co-finance of $320,000 USD.

C.2.How does the project fit into the GEF agency’s program (reflected in documents such as UNDAF, CAS, etc.) and staff capacity in the country to follow up project implementation:

- The project is aligned with the United Nations Development Assistance Framework (UNDAF) for Nicaragua 2008-2012. Specifically, the project is consistent with UNDAF Product 3.1.1, which seeks to strengthen the capacity of public, community, civil society, and private sector institutions in developing and implementing policies, legal frameworks, and programs related to the environment, natural resources, energy, and water. This project will be under the supervision of the Regional Technical Advisor for GEF and UN-REDD projects in Latin America and the Caribbean, who has a Ph.D. and M.Sc. in Environmental Policy and Economics with emphasis on the economic valuation of forests. The UNDP Country Office will assign five key staff to manage and monitor project implementation. The project will be managed by the Programme Officer of the Department of Environment, Energy, and Risk Management, who has more than 12 years of experience in the formulation and monitoring of environmental and biodiversity projects, and will receive support from the Area Coordinator. Administrative support will be provided by the Area Manager. Project monitoring and evaluation will be led by the Monitoring and Evaluation Analyst and, when required, will receive support from the Procurement Unit.

part iii:  approval/endorsement by gef operational focal point and GEF agency

- Record of Endorsement of GEF Operational Focal Point(s) on Behalf of the Government:

| Name | Position | Ministry | Date (MM/DD/YYYY) |
| --- | --- | --- | --- |
| Roberto Araquistain Cisneros | Vice Minister | Ministry of Environment and Natural Resources | 01/13/2013 |

- GEF Agency(ies) Certification

| This request has been prepared in accordance with GEF/LDCF/SCCF policies and procedures and meets the GEF/LDCF/SCCF criteria for project identification and preparation. |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Agency Coordinator, Agency name | Signature | Date (MM/DD/YYYY) | Project Contact Person | Telephone | Email Address |
| Yannick Glemarec GEF Executive Coordinator, UNDP |  | January 18, 2013 | Santiago Carrizosa, Senior Technical Advisor, EBD | +507 302-4510 | Santiago.carrizosa@undp.org |

PPG resources will be used for updating the condition of project corridors and related multiple-use PAs.

Based on Kanninen, M. 2002. Secuestro de Carbono en los Bosques: El papel de los bosques en el Ciclo Global de Carbono. Available at http://www.fao.org/wairdocs/lead/x6366s/x6366s09.htm#P0_0. Accessed 11/20/2012.

Average deforestation rate for Nicaragua. It was assumed the rate of deforestation for year 1 will remain equal to the baseline (2.1%) and that it will decrease by 0.13% each year for the remaining 4 years (average deforestation rate = 1.84%).

Based on Intergovernmental Panel on Climate Change. 2000. Special Report on Land Use, Land-Use Change, and Forestry.