request for

Project Type:

Type of Trust Fund:

For more information about GEF, visit TheGEF.org

part i: project information

| Project Title: Generating Global Environmental Benefits from Improved Decision Making Systems and Local Planning in Pakistan |  |  |  |
| --- | --- | --- | --- |
| Country(ies): | Pakistan | GEF Project ID: | 5326 |
| GEF Agency(ies): |  | GEF Agency Project ID: | 4939 |
| Other Executing Partner(s): | Federal Climate Change Division | Submission Date: | 17 February 2015 |
| GEF Focal Area (s): |  | Project Duration(Months) | 36 |
| Name of Parent Program (if applicable): - For SFM/REDD+ - For SGP - For PPP |  | Project Agency Fee ($): | 94,572 |

- Focal Area Strategy framework

| ### Focal Area Objectives | ### Expected FA Outcomes | ### Expected FA Outputs | Trust Fund | Grant Amount ($) | ### Cofinancing ### ($) |
| --- | --- | --- | --- | --- | --- |
|  | 2.1: Institutions and stakeholders have skills and knowledge to research acquire and apply information collective actions 2.3: Public awareness raised and information management improved | 1. Institutions and stakeholders trained how to use different tools available to manage information 2. Knowledge platform established to share lessons learned among CBOs and CSOs across SGP participating countries 3. Public awareness raised through workshops and other activities |  | 345,500 | 472,000 |
|  | 3.1: Enhanced institutional capacities to plan, develop policies and legislative frameworks for effective implementation of global conventions | 4. Institutional capacities enhanced in recipient countries to implement global conventions |  | 559,500 | 196,350 |
|  |  | Project Management |  | 90,500 | 271,700 |
| Total project costs |  |  |  | 995,500 | 940,050 |

- Project Framework

| ### Project Objective: Generating global environmental benefits from improved decision making systems in Pakistan. |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| ### Project Component | ### Grant Type | ### Expected Outcomes | ### Expected Outputs | ### Trust Fund | ### Grant Amount ($) | ### Confirmed Cofinancing ### ($) |
| Enhanced Information management systems for global environment issues |  | 1: Availability of Consistent and Reliable Environmental Data 2: A Coordinated and Robust Environmental Information Management System | 1.1: A Unified Collection, Storage and Access System for Primary Data 1.2: An Established List of Priorities for Data Gathering and Reporting 1.3: A Report of Bench Marking of Environmental Statistics of Pakistan with the NEMIS Identified Environmental Data Requirement 1.4: An Agreement between the Climate Change Division (CCD) and Pakistan Bureau of Statistics (PBS) 1.5: Reformed Data Collection Tools and Approaches 1.6: Environment Statistics of Pakistan 1.7: Mandate for Collecting Residual Data 1.8: Protocols of Quality Assurance of Environment Data 2.1: An Effectively Operating National Environmental Information Management System 2.2: Policy Research and Analysis 2.3: Pakistan’s State of Environment Report(s) 2.4: Provincial State of Environment Reports 2.5: Bench Marking Pakistan State of Environment Report with Provincial Environment Reports 2.6: Country Reports under Multilateral Agreements 2.7: Harnessing Research Capacity and Opportunities in Universities |  | 345,500 | 472,000 |
| Strengthened capacities for policy and legislation development for achieving global benefits. |  | 3: Enhanced commitment and capacity for sustainable development planning and legislation | 3.1. Exposure and Training of Civil Service 3.2. Enhanced Access of Planning Functions to Environmental Expertise 3.3: An Engaged Polity 3:4: Supportive Public Opinion 3.5: Media Support |  | 559,500 | 196,350 |
| Subtotal |  |  |  |  | 905,000 | 668,350 |
| Project management Cost (PMC) (including Direct Project Services Cost 24,888) |  |  |  |  | 90,500 | 271,700 |
| Total project costs |  |  |  |  | 995,500 | 940,050 |

- sources of confirmed Cofinancing for the project by source and by name ($)

Please include letters confirming cofinancing for the projeSct with this form

| Sources of Co-financing | Name of Co-financier (source) | Type of Cofinancing | Cofinancing Amount ($) |
| --- | --- | --- | --- |
|  | UNDP |  | 217,700 |
|  | Environment Protection Agency, Climate Change Division (Through Parallel Projects Financing) |  | 488,850 |
|  | Environment Protection Agency, Climate Change Division |  | 50,000 |
|  | Provincial Government, Khayber Pakhtun Khwa (KPK) - (Through Parallel Projects Financing) |  | 73,750 |
|  | Provincial Government, Khayber Pakhtun Khwa (KPK) |  | 18,000 |
|  | Provincial Government, Punjab - (Through Parallel Projects Financing) |  | 73,750 |
|  | Provincial Government, Punjab |  | 18,000 |
| Total Co-financing |  |  | 940,050 |

- trust fund Resources Requested by agency, Focal Area  and country1

| GEF Agency | Type of Trust Fund | Focal Area | Country Name/ Global | (in $) |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | Grant Amount (a) | Agency Fee (b)2 | Total c=a+b |
|  |  |  | Pakistan | 995,500 | 94,572 | 1,090,072 |
|  |  |  |  |  |  | 0 |
|  |  |  |  |  |  | 0 |
|  |  |  |  |  |  | 0 |
|  |  |  |  |  |  | 0 |
|  |  |  |  |  |  | 0 |
|  |  |  |  |  |  | 0 |
|  |  |  |  |  |  | 0 |
|  |  |  |  |  |  | 0 |
|  |  |  |  |  |  | 0 |
| Total Grant Resources |  |  |  | 995,500 | 94,572 | 1,090,072 |

1  In case of a single focal area, single country, single GEF Agency project, and single trust fund project, no need to provide information for this
    table.  PMC amount from Table B should be included proportionately to the focal area amount in this table.

2   Indicate fees related to this project.

- Consultants working for technical assistance components:

| ### Component | ### Grant Amount ($) | ### Cofinancing ($) | ### Project Total ($) |
| --- | --- | --- | --- |
| ### International Consultants |  | 30,000 | 30,000 |
| ### National/Local Consultants | 401,500 | 77,000 | 478,500 |

- Does the project include a “non-grant” instrument?

(If non-grant instruments are used, provide in Annex D an indicative calendar of expected reflows to your Agency 
       and to the GEF/LDCF/SCCF/NPIF Trust Fund).

part ii:  project justification

A. describe any changes in alignment with the project design of the original pif

A.1 National strategies and plans or reports and assessments under relevant conventions, if applicable, i.e. NAPAS, NAPs, NBSAPs, national communications, TNAs, NCSA, NIPs, PRSPs, NPFE, Biennial Update Reports, etc.N/A

A.2. GEF focal area and/or fund(s) strategies, eligibility criteria and priorities.N/A

A.3 The GEF Agency’s comparative advantage: N/A

A.4. The baseline project and the problem that it seeks to address:  N/A

A. 5. Incremental /Additional cost reasoning:  describe the incremental (GEF Trust Fund/NPIF) or additional (LDCF/SCCF) activities  requested for GEF/LDCF/SCCF/NPIF  financing and the associated global environmental benefits  (GEF Trust Fund) or associated adaptation benefits (LDCF/SCCF) to be delivered by the project: N/A

A.6  Risks, including climate change, potential social and environmental risks that might prevent the project objectives from being achieved, and measures that address these risks: N/A

A.7. Coordination with other relevant GEF financed initiativesN/A

B. additional information not addressed at Pif stage:

B.1 Describe how the stakeholders will be engaged in project implementation. In the broader sense, the entire environment and development community is the stakeholder for this project for easy access to reliable environmental information is a common need and the integration of environment and development a shared goal. However, for the purpose of the project design and implementation, key stakeholders have been identified as those with specific direct contributions to make or particular role to play in the project implementation. The direct stakeholders will be in this case the governments divisions and departments influencing MEAs implementation. Attention has been paid to gender analysis and the prospects of mainstraeming gender under the project. The indirect stakeholders may be other government departments, academia, NGOs , private sector and the public at large. Currently, stakeholders’' efforts are little coordinated. This project will help better address this imperative. Under NEMIS (baseline project “National Environmental Management Information System “at federal Climate Change Division), did not include the agencies collecting primary data such as the departments of forestry, agriculture, irrigation, public health and others. This gap will be filled under this project and the fold of key stakeholders expanded to include them as well. The member organizations will be encouraged to continue their research and analysis, enabled in part by the unified data gathering, storage and access system under outcome one, and continue pooling it with others on the EMIS platform. The success of the EMIS will reside in keeping stakeholders engaged, contributing and supportive. It will be important for the project management to continue to cultivate deeper ownership of the project and its outcomes, among the relevant direct stakeholders, during the course of implementation. This will enhance the effective involvement of stakeholders (federal ministries and divisions, provincial line departments, thinks tanks, NGOs and other information providers) by giving them, among other things, due recognition and value addition. The project will also seek the involvement of broader stakeholders' groups through invitation to participate in media events, filed visits and other such activities.

B.2 Describe the socioeconomic benefits to be delivered by the Project at the national and local levels, including consideration of gender dimensions, and how these will support the achievement of global environment benefits (GEF Trust Fund/NPIF) or adaptation benefits (LDCF/SCCF): In countries like Pakistan, development without focusing on global environmental concerns would result in further degradation of environment. Keeping in view the environment and poverty nexus, and impact of degraded environment on socioeconomic situation, ill planned economic developments will make poor and especially the women worse off.  A successful implementation of the project, involving mainstreaming of environment, will improve the quality of economic development and enhance its contribution to sustainable livelihoods. Interventions such as this are not just needed but essential.

A market based approach to capacity development and awareness-raising will help increasing involvement of NGOs and civil society in development planning. The civil society in Pakistan has been playing a key role filling in institutional and development gaps the government programs left behind. Strengthening NGOs through their participation in this project will expand the safety net, especially for the marginalized women groups in rural areas that quietly suffer from bad projects undertaken in the name of development. It will also enhance opportunities for them to participate and influence these developments in the long term.

The project will improve the country’s ability to undertake targeted monitoring, verification, and reporting on each of the Rio Conventions by removing the  underlying deficiencies (lack of consistent and reliable data of adequate quality) that limit a more comprehensive analysis of environmental and development policies, plans and programmes.  Capacity development activities under this project will serve to catalyze a long-term approach to generation and use of knowledge that cut across the three Rio Conventions. By providing strategic inputs to making the Environmental Information Management System (EMIS) operational and sustainable over the long term, this project will remove some of the key barriers to informed decision-making for sustainable development in the country, and thus enhance its ability for greater contribution to global environmental benefits. .

The goal of this project is to deliver global environmental benefits by enhancing Pakistan’s capacities and tools to plan, monitor and measure progress in meeting its global obligations.  To that end, the objective of this project is to target both the environmental data and information systems (generation, flow, storage, access and sharing of data and information) as well as employing this information to improve economic planning and implementation by integrating environment and development.

Eventually, the project activities are expected to result in a set of improved institutional and technical capacities to meet and sustain global environmental objectives.  New and innovative mechanisms are envisaged to create effective long term capacities, premised on market approach than continued expansions in government infrastructure that many developing countries find hard to finance and sustain. Likewise, engaging media and mobilizing public opinion are strategic project interventions that, together with direct engagement of polity, will further enhance and sustain political commitment for mainstreaming the Rio Conventions implementation in Pakistan. Such a sustained commitment is essential for securing the Pakistan’s natural resource base that underwrites its economic development, more so than any other country. In fact the success of this project in Pakistan, as outlined in the main document, will yield dividends both regionally and globally in terms of international trade and its impact on both exporting and importing economies.

Poject interventions are mostly gender-neutral and, by themselves, are unlikely to aggravate the gender issues facing the country. In contrast, they offer an opportunity to highlight the gender issues and cretae space for affirmative action to mainstream gender in sustainable development in some small, albeit important ways.   The project will harness these opportunities by seeking to: (a)	Involve in the EMIS organization that hold and produce information on gender issues; (b)	Design data collection tools that  report gender segregated information as much as possible; (c)	Ensure eligible women participants are actively enlisted for participation in various training and awareness raising workshops; (d)	Engage women experts, where possible, for delivering the required training and educational lectures and workshops; (e)	National and Provincial State of Environment reports carry relevant gender data; (f)	Ensure research and policy components include addressing some key gender issues under the three Rio conventions; and, (g)	Engage eligible women researchers and policy professional for undertaking policy research studies under the project;

B.3.Explain how cost-effectiveness is reflected in the project design: The project design is based on the acute awareness that the available resources are limited and has therefore sought to follow the most cost effective approach to achieving the planned outcomes. Foremost, while PIF talked about an EMIS as the essential backbone for integrating environment and development, the design team has refrained from creating another EMIS initiative and has instead opted to leverage the investments and outputs under the NEMIS project concluded two years ago that the Government of Pakistan is following up. Some marginal investments under this project, mainly in terms of facilitation and stimulation, will enable taking the NEMIS key outputs and outcomes to fruition that wasn’t possible due to closure of the project before their completion. Cost effectiveness is also manifest in the approach of implementing the project through existing organizations and structures and avoiding the creation of new additional ones as much as possible. It will enable takeing the project off the ground swiftly that wouldn’t be possible if too many of new staff had to be recruited, inducted and trained. The additional human resources contemplated under the project are essentially only for the additional coordination capacity that the project implementation will require during its implementation. Emphasis on adapting a market based approach to sourcing and generating information will bring the market efficiencies into play, and is premised on drawing on existing capacities, as much as possible, and on using the available fiscal and human resources effectively. Equally important is the approach to capacity building and enhancing public understanding and support for environment-development integration. The capacity building activities would entail bringing resource persons to the work environment of the target audience than to take the target beneficiaries away to other locations at considerable expense of time and funds. Using the popular TV programs to bolster public and political opinion and support for mainstreaming sustainability would be the most cost effective way to reach masses. The alternative approach of workshops, seminars and advertisements in press would be limited in its reach and far more expensive. It is only with carefully choosing such cost effective approaches that it would be possible to achieve what the project is set out to do with limited funds available to it.

C.  describe the budgeted m &e plan:The design of the M&E framework has been guided by the essential requirements of UNDP-GEF for similar projects. It is premised on the M&E being conducted according to the established UNDP and GEF procedures. The overall responsibility will rest with project team represented by the leads of the different components and coordinated by the Project Coordinator. UNDP Country Office and UNDP/GEF Regional Coordination Unit will provide the requisite support from their end.

A detailed budgeted M&E Plan in Project Document reflects a total M&E budget of USD 43,000.

Following activities are envisaged in Project's M&E Plan:

1. Inception Workshop (IW)

2. Inception Report

3. Measurement of Means of Verification for Project Progress and Performance (measured on an annual basis)

4. Quarterly/Half Yearly progress reports and operational reports

5. Annual Progress Report (APR)/PIR

6. Tripartite Review (TPR) and TPR report

7. Project Executive Committee meetings

8. Technical and periodic status reports

9. Mid-term Evaluation

10. Final External Evaluation

11. Terminal Report

12. Audit

13. Visits to field sites (UNDP staff travel costs to be charged to IA fees)

The overall objective of the monitoring and evaluation process is to ensure successful and quality implementation of the project by:( i) tracking and reviewing project activities execution and actual accomplishments; (ii) providing recurrent visibility into implementation progress as the project proceeds so that the management team can take early corrective action if performance deviates significantly from original plans; and (iii) adjust and update project strategy and implementation plan to reflect possible changes on the ground, results achieved and corrective actions taken.

PART iII: Approval/endorsement by gef operational focal point(s) and gef agency(ies)

- Record of Endorsement of GEF Operational Focal Point(s) on Behalf of the Government(s):): (Please attach theOperational Focal Point endorsement letter(s) with this form. For SGP, use this OFP endorsement letter).

| Name | Position | Ministry | Date(MM/dd/yyyy) |
| --- | --- | --- | --- |
| Muhamad AIi Gardezi | GEF Operational Focal point | Climate Change Division | 06/11/2013 |

B.  GEF agency(ies) certification

This request has been prepared in accordance with GEF/LDCF/SCCF/NPIF policies and procedures and meets the GEF/LDCF/SCCF/NPIF criteria for CEO endorsement/approval of project.

| Agency Coordinator, Agency Name | Signature | Date (Month, day, year) | Project Contact Person | Telephone | Email Address |
| --- | --- | --- | --- | --- | --- |
| Adriana Dinu, Executive Coordinator UNDP-GEF |  | 01/27/2015 | Tom Twining-Ward, Senior Technical Advisor, UNDP (GLECRDs) |  | tom.twining-ward@undp.org |

GEF_CEOENDR_52

ANNEX A:  PROJECT RESULTS FRAMEWORK (either copy and paste here the framework from the Agency document, or provide reference to the page in the project document where the framework could be found).

The project results framework can be found at Annex 1 to the Project Document.

ANNEX B:  RESPONSES TO PROJECT REVIEWS (from GEF Secretariat and GEF Agencies, and Responses to Comments from Council at work program inclusion and the Convention Secretariat and STAP at PIF).

N/A

Annex C:  status of implementation of project preparation activities and the use of funds

A.  provide detailed funding amount of the ppg activities financing status in the table below:

| PPG Grant Approved at PIF: 30,000 |  |  |  |
| --- | --- | --- | --- |
| Project Preparation Activities Implemented | GEF/LDCF/SCCF/NPIF Amount ($) |  |  |
|  | Budgeted Amount | Amount Spent Todate | Amount Committed |
| Preparation of work plan, and design of stakeholders’ consultations and validation workshops | 7,350 | 7,350 |  |
| Field mission including international and in-country travel, organization and facilitation of stakeholders consultations and validation workshops. | 7,350 | 7,350 |  |
| Preparation of project documents including various annexes, revision of drafts to incorporate feedback , and assistance with co-financing opportunities. | 10,290 | 10,290 |  |
| Assistance with responses to GEF Secretariat comments (if any). | 4,410 | 0 | 4,410 |
| other unforeseenexpenses | 600 | 0 | 600 |
| Total | 30,000 | 24,990 | 5,010 |

annex D:  calendar  of expected reflows (if non-grant instrument is used)

Provide a calendar of expected reflows to the GEF/LDCF/SCCF/NPIF  Trust Fund or to your Agency (and/or revolving fund that will be set up)

No non-grant instrument is used.

Project ID number will be assigned by GEFSEC.

Refer to the Focal Area Results Framework and LDCF/SCCF Framework when completing Table A.

PMC should be charged proportionately to focal areas based on focal area project grant amount in Table D below.

For questions A.1 –A.7 in Part II, if there are no changes since PIF and if not specifically requested in the review sheet at PIF  stage, then no need to respond, please enter “NA” after the respective question.

If at CEO Endorsement, the PPG activities have not been completed and there is a balance of unspent fund, Agencies can continue undertake the activities up to one year of project start.  No later than one year from start of project implementation, Agencies should report this table to the GEF Secretariat on the completion of PPG activities and the amount spent for the activities.