GEF-6 Project Identification Form (PIF)

Project Type: Full-sized Project

Type of Trust Fund: GEFTF

For more information about GEF, visit TheGEF.org

PART I: Project Information

| Project Title: | Pakistan Snow Leopard and Ecosystem Protection Program |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Country(ies): | Pakistan | GEF Project ID: |  |  |  |  |
| GEF Agency(ies): | UNDP | GEF Agency Project ID: |  |  |  | 5716 |
| Other Executing Partner(s): | Ministry of Climate Change, Snow Leopard Foundation | Submission Date: Resubmission Date: |  |  |  | 31 July 2015 26 April 2016 |
| GEF Focal Area(s): | Multi-focal Areas | Project Duration (Months) |  |  |  | 48 |
| Integrated Approach Pilot | IAP-Cities IAP-Commodities IAP-Food Security |  |  | Corporate Program: SGP |  |  |
| Name of parent program: | Global Snow Leopard and Ecosystem Conservation Program |  | Agency Fee ($) |  | 441,229 |  |

A. indicative Focal Area  Strategy Framework and Other Program Strategies

| ### Objectives/Programs (Focal Areas, Integrated Approach Pilot, Corporate Programs) | ### Trust Fund | ### (in $) |  |
| --- | --- | --- | --- |
|  |  | ### GEF Project Financing | ### Co-financing |
| BD-1 Program 2: Nature’s Last Stand: Expanding the Reach of the Global Protected Area Estate | GEFTF | 2,211,676 | 6,167,141 |
| LD-3 Program 4: Scaling-up sustainable land management through the Landscape Approach | GEFTF | 884,671 | 2,466,858 |
| SFM-1 Program 1: Integrated land use planning. | GEFTF | 700,000 | 1,951,913 |
| SFM-1 Program 2: Identification and maintenance of high conservation value forests. | GEFTF | 248,174 | 692,020 |
| SFM-3 Program 7: Building technical and institutional capacities to identify degraded forest landscapes and monitor forest restoration. | GEFTF | 600,000 | 1,673,068 |
| Total Project Cost |  | 4,644,521 | 12,951,000 |

B. indicative Project description summary

| Project Objective: To promote a landscape approach for the survival of the snow leopard and its prey species by reducing threats and applying sustainable land and forest management in critical habitats in northern Pakistan. |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| ### Project Components | ### Financing Type | ### Project Outcomes | ### Project Outputs | ### Trust Fund | ### (in $) |  |
|  |  |  |  |  | ### GEF Project Financing | ### Co-financing |
| 1. Landscape-level approach for snow leopard conservation | TA | Landscape management plans developed for the three model snow leopard landscapes covering 4,100,000 ha that integrate and sustainable forest and land management and snow leopard conservation compatible practices. Appropriate SLM and SFM technologies implemented by local communities (in at least 250,000 ha), resulting in: i) reduced land degradation (measured by decrease in extent of degraded areas); ii) improved productivity (measured by Net Primary Productivity and increase in rain use efficiency); iii) maintenance of ecosystem services (e.g. water availability and increased carbon sequestration); iv) restoration/regeneration of degraded rangelands, including 1,000 ha juniper forest. This reduces threats from land and forest degradation (competition for grazing, soil erosion, degradation of hydrological functions) and leads to improved habitat integrity and connectivity across the model landscapes. Baselines, means of measurement and targets will be established and confirmed during the PPG. | 1.1. Three model landscape level management plans covering a total area of approx. 4,100,000 ha that integrate sustainable forest and rangeland management and reconcile needs of snow leopard ecosystem conservation and development. 1.2. Ten valley plans covering 250,000 ha developed and implemented that integrate sustainable forest and land management practices and snow leopard conservation compatible measures in line with the landscape level plans, and provided with training and extension support on appropriate technologies. 1.3. Improved SLM and SFM practices applied by local communities in and surrounding PAs to improve community skills base and support sustainable livelihoods, including: rehabilitation of degraded rangelands and improving management (e.g. providing adequate rest through rotational grazing regimes), improved shrub land management (e.g. sustainable fuelwood collection, use of fuel efficient stoves and reduced shrub land grazing), silvopastoral practices, community forestry, sustainable fodder cultivation. | GEFTF | 1,500,000 | 4,182,670 |
| 2. PA expansion and strengthening |  | Increased representation of snow leopard habitat in the PA network, including 7,000 ha of forests. Increased management effectiveness of critical existing National Parks and newly established PAs (measured by METT). Enhanced capacity of key local stakeholders including wildlife managers and local communities on assessment, monitoring and enforcement of sustainable snow leopard friendly forest and landscape management practices (as measured by increase in UNDP Capacity Scorecard) Baselines, means of measurement and targets will be established and confirmed during the PPG. | 2.1. At least 20,000 ha of priority snow leopard habitat (including 7,000 ha of forests important for biodiversity) gazzetted as PAs. 2.2. PA management and financing plans for critical existing National Parks and new PAs are developed/aligned and operationalized. 2.3. At least 100 forest and wildlife managers (PA staff and community organizations) trained and equipped for monitoring and enforcement. 2.4. Improved anti-poaching, surveillance measures (including involvement of local communities in anti-poaching efforts; information sharing and management systems) to reduce incidences of wildlife poaching and illegal trade. | GEFTF | 1,000,000 | 2,788,447 |
| 3. Participatory conservation in snow leopard Model Landscapes through sustainable community development | TA | Reduced human-snow leopard conflicts in target landscapes through a comprehensive strategy aimed at off-setting losses, preventing crop and livestock depredation and increasing benefits to local communities resulting in: (i) number of snow leopards and other key wildlife (e.g. brown bear) remain stable or increase; (ii) at least 20% increase in income of participating households from schemes such as livestock insurance, improved corrals and vaccination. Reduced threats to snow leopards and their ecosystems as evidenced by: (i) reduced incidences of retaliatory killings; (ii) local communities’ attitude towards SL and SL ecosystem conservation are positive; (iii) reduced incidences of poaching and illegal wildlife trade. Baselines, means of measurement and targets will be established and confirmed during the PPG. | 3.1. Community-run livestock insurance services are established and accessed by at least 10,000 households in the model landscapes. 3.2. Improved wildlife deterrent systems (corral improvements) piloted and better livestock management (e.g. vaccination for disease control) in 20 valleys comprising minimum of 10,000 households (over baseline of 10). 3.3. Community based conservation education and outreach strategy focused on: (a) ecological, socio-economic importance of snow leopards and their ecosystems; (b) greater awareness of conservation laws are developed and implemented: (i) information centers developed, one in each model landscape; (ii) school-based Nature Clubs initiated in 20 new schools that engage young students to promote behaviour change in conservation. | GEFTF | 1,523,354 | 4,247,791 |
| 4. Support for international cooperation and conservation and management actions informed by knowledge on snow leopard ecology and ecosystem dynamics | TA | Enhanced scientific knowledge on snow leopards, prey species, and habitat leads to better conservation and management decisions. This consists of: (i) GIS database for model landscapes; (ii) monitoring system for identifying threats; (iii) climate change impacts and adaptation measures are incorporated into 3 landscape management plans (linking with global SL project and GSLEP as well as with national and regional initiatives). Effective development of mechanisms and improved capacities for international cooperation on snow leopard conservation, control of illegal trade and improved information management. Baselines, means of measurement and targets will be established and confirmed during the PPG. | 4.1. Model snow leopard ecosystem GIS based monitoring system established for model landscapes, integrating: (i) systematic surveys of snow leopard and wild prey, (ii) research and surveys on the status of snow leopard ecosystems, including vegetative cover and juniper forests, (iii) system for assessing status of and trend in threats in snow leopard ecosystems established; and monitoring information used to develop measures for management and restoration of habitats. 4.2. Systematic assessment of climate change impacts on snow leopard ecosystems; adaptation measures integrated into management plans (output 1.1) 4.3. Targeted support to participation of Pakistan in the Global Snow Leopard Ecosystem Protection Plan process. | GEFTF | 400,000 | 1,115,378 |
| Subtotal |  |  |  |  | 4,423,354 | 12,334,286 |
| Project Management Cost (PMC) |  |  |  |  | 221,167 | 616,714 |
| Total Project Cost |  |  |  |  | 4,644,521 | 12,951,000 |

C. Indicative sources of  Co-financing for the project by name and by type, if available

| Sources of Co-financing | Name of Co-financier | Type of Co-financing | Amount ($) |
| --- | --- | --- | --- |
| Recipient Government | Government of Pakistan (GoP) | Grants | 1,506,500 |
| Recipient Government | Government of Pakistan (GoP) | In-kind | 5,599,100 |
| Recipient Government | Government of Khyber Pakhtoonkhwa (KPK) | In-kind | 2,000,000 |
| Recipient Government | Government of Gilgit Baltistan (GB) | In-kind | 838,500 |
| Recipient Government | Government of Gilgit Baltistan | Grants | 1,576,900 |
| Recipient Government | Government of Azad Jammu and Kashmir (AJK) | In-kind | 840,000 |
| CSO | Snow Leopard Trust | Grants | 500,000 |
| Other | EvK2 CNR | In-kind | 90,000 |
| Total Co-financing |  |  | 12,951,000 |

D. Indicative Trust Fund  Resources Requested by Agency(ies),  Country(ies) and the Programming of Funds a)

| GEF Agency | Trust Fund | Country/ Regional/ Global | Focal Area | Programming of Funds | (in $) |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | GEF Project Financing (a) | Agency Fee (b)b) | Total (c)=a+b |
| UNDP | GEFTF | Pakistan | Biodiversity |  | 2,211,676 | 210,109 | 2,421,785 |
| UNDP | GEFTF | Pakistan | Land Degradation |  | 884,671 | 84,044 | 968,715 |
| UNDP | GEFTF | Pakistan | SFM |  | 1,548,174 | 147,076 | 1,695,250 |
| Total GEF Resources |  |  |  |  | 4,644,521 | 441,229 | 5,085,750 |

- Refer to the Fee Policy for GEF Partner Agencies.

E.  Project preparation grant (ppg)

Is Project Preparation Grant requested? Yes    No  If no, skip item E.

PPG  Amount requested by agency(ies), Trust Fund,  country(ies) and the Programming  of funds

| Project Preparation Grant amount requested: $150,000 PPG Agency Fee: $14,250 |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| GEF Agency | Trust Fund | Country/ Regional/Global | Focal Area | Programming of Funds | (in $) |  |  |
|  |  |  |  |  | PPG (a) | Agency Fee (b) | Total c = a + b |
| UNDP | GEFTF | Pakistan | Biodiversity |  | 71,429 | 6786 | 78,215 |
| UNDP | GEFTF | Pakistan | Land Degradation |  | 28,571 | 2714 | 31,285 |
| UNDP | GEFTF | Pakistan | SFM |  | 50,000 | 4750 | 54,750 |
| Total PPG Amount |  |  |  |  | 150,000 | 14,250 | 164,250 |

F.  Project’s Target Contributions to Global Environmental Benefits

Provide the expected project targets as appropriate.

| Corporate Results | Replenishment Targets | Project Targets |
| --- | --- | --- |
| - Maintain globally significant biodiversity and the ecosystem goods and services that it provides to society | Improved management of landscapes and seascapes covering 300 million hectares | 20,000 hectares |
| - Sustainable land management in production systems (agriculture, rangelands, and forest landscapes) | 120 million hectares under sustainable land management | 250,000 hectares |
| - Promotion of collective management of transboundary water systems and implementation of the full range of policy, legal, and institutional reforms and investments contributing to sustainable use and maintenance of ecosystem services | Water-food-ecosystems security and conjunctive management of surface and groundwater in at least 10 freshwater basins; | Number of freshwater basins |
|  | 20% of globally over-exploited fisheries (by volume) moved to more sustainable levels | Percent of fisheries, by volume |
| - 4. Support to transformational shifts towards a low-emission and resilient development path | 750 million tons of CO2e mitigated (include both direct and indirect) | 548,187 tCO2-eq |
| - Increase in phase-out, disposal and reduction of releases of POPs, ODS, mercury and other chemicals of global concern | Disposal of 80,000 tons of POPs (PCB, obsolete pesticides) | metric tons |
|  | Reduction of 1000 tons of Mercury | metric tons |
|  | Phase-out of 303.44 tons of ODP (HCFC) | ODP tons |
| - Enhance capacity of countries to implement MEAs (multilateral environmental agreements) and mainstream into national and sub-national policy, planning financial and legal frameworks | Development and sectoral planning frameworks integrate measurable targets drawn from the MEAs in at least 10 countries | Number of Countries: |
|  | Functional environmental information systems are established to support decision-making in at least 10 countries | Number of Countries: |

PART II: Project Justification

1. Project Description.

1. Global environmental problems, root causes and barriers that need to be addressed:

Spread across 130,000 square kilometers of the Hindu Kush, Karakoram, Pamir and Western Himalayan mountain ranges, northern Pakistan (Gilgit-Baltistan (GB), Khyber Pakhtunkhwa (KPK), and Azad Jammu and Kashmir (AJK) administrative units) is rich in global biodiversity. These mountain complexes provide connectivity for high altitude fauna, acting as a bridge for the biota of Afghanistan, China, and India. Khunjerab National Park in Karakorams is considered a high-altitude biodiversity hotspot (WWF 2009).

Northern Pakistan supports 113 mammal species against Pakistan’s total of 174 species (Roberts, 1997).  It supports 525 species of birds, which represents 80% of the avifauna of the country (Roberts, 1991; 1992). Of the 177 fish species reported from Pakistan, 90 (51%) occur in the Himalayas. Fifty species of reptiles and 15 of amphibians have been recorded from the region, representing 33% of Pakistan’s herpetofauna (Akbar and Anwar, 2011).  Similarly, 90 fish species (51%) have been reported from the Himalayas out of the 177 native freshwater fish species in Pakistan, of which 29 are endemic to the country. Noteworthy are the nine species of snow trout occurring in rivers of the northern mountains. The Northern Pakistan region includes elements of four phytogeographic regions (Sino Himalayan, Indian, Euro-Siberian and Mediterranean), and almost 80% of Pakistan’s endemic flowering plants are confined to these mountains. The Kashmir Himalayas, in particular, are identified as a global center of plant diversity and endemism.

A higher coverage of protected areas (PAs) in northern Pakistan (19 %, as opposed to 11% in the country) reflects the disproportionally greater importance of the area. Currently there are 61 PAs established, comprising: 9 wildlife sanctuaries; 15 national parks; and 37 game reserves. Pakistan is one of the most important countries in the world for the conservation of the sub-family Caprinae (Shackleton 1997) because most of the taxa present in the country are threatened. Northern Pakistan is a particularly important stronghold for the globally Endangered snow leopard (Panthera uncia, EN on the IUCN Red List; Appendix I of CITES; Appendix II on CMS/Bonn Convention). An estimated 200–420 snow leopards exist in Northern Pakistan, which constitutes among the world’s largest concentrations of the species. A national-level assessment deemed the snow leopard Critically Endangered (Sheikh and Molur, 2004). Total snow leopard habitat available in Pakistan is c. 80,000 km2 (Annexure A) with the majority (>60%) located in GB. The snow leopard plays an important ecological role in controlling the populations and health of wild ungulate species and is an important indicator species of healthy mountain ecosystems. The snow leopard is also an important cultural icon for the peoples of Pakistan. Over nine million people live in northern Pakistan; cultural diversity is immense and includes one of the world’s oldest known civilizations in the Kelash valleys. Other important species within northern Pakistan include: markhor (Capra falconeri; globally Near Threatened); Marco Polo sheep (Ovis ammon polii); alpine musk deer (Moschus chrysogaster; globally Endangered); Himalayan lynx (Lynx lynx); blue sheep (Pseudois nayaur); brown bear (Ursus arctos); Indian wolf (Canis lupus); and Himalayan ibex (Capra sibirica). Ibex, markhor and wild sheep are all key prey species of snow leopard and are therefore important to the species’ survival.

KPK, AJK and GB account for over 60% of the country’s forests, estimated at 2,625,000 ha (Forestry Sector Master Plan). Forests play a vital role in protecting the Indus River watershed, supporting a rich diversity of flora and fauna, and serving as an important source of forage and pasture for livestock populations, timber and firewood, and non-timber forest products (NTFPs). Juniper forests in particular play a significant role in soil and water conservation in dry mountain ecosystems where water is the limiting factor. Juniper forests support ground vegetation cover that protects soil from water and wind erosion, lessens runoff, and regulates the flow of streams. Juniper trees reduce aridity by maintaining higher humidity and intercepting clouds for rain. Junipers provide grazing material not only to the large number of sheep and goats but also to wildlife by supplying much needed browse for important wild ungulates like markhor, ibex, blue sheep and musk deer in winter when ground vegetation is covered with heavy snow and provide shelter for other wildlife in the harsh winters. Many medicinal plants and threatened wildlife species occur in juniper patches throughout northern Pakistan.

The Karakorams have the greatest concentration of high mountains and the longest glaciers in the world. Overall the country’s northern mountains provide water to half the nation and 70% of summer flow into the Indus River watershed; the Indus River in turn discharges some 200 cubic kilometers of water and 450 million tons of suspended sediment annually. Indus Flyway and adjacent high altitude lakes, streams, marshlands, peatlands and bogs are used as temporary and permanent staging, feeding and breeding grounds by migratory water birds, including several endangered aquatic bird species. Rangelands occupy over 22% of Pakistan’s mountainous areas (GoP and IUCN, 2003) and provide critical grazing areas for wild and domestic ungulates. In northern Pakistan, approximately 60-80% of the population is engaged in subsistence agriculture and an estimated livestock population of 4.56 million is dependent on alpine pastures (GoP and IUCN, 2003) alongside wild prey species. The livestock sector’s contribution to the GDP of the country is more than 11%, and more than 60% of livestock feed requirements are met from the rangelands (National Rangelands Policy, 2010). Rangelands, and their sustained functioning, are therefore hugely important ecologically, socially and economically to this region.

Pakistan ranks 146th out of 187 countries on the United Nations Development Programme's 2013 Human Development Index – a comparative measure of life expectancy, literacy, education and standards of living for countries worldwide. The average income of rural pastoral communities in northern Pakistan is estimated to be PKR 4,000–6,000 which is far below the national average for Pakistan (PKR 9,170 PKR, Ehlers and Kreutzmann, 2000).  Poverty means no or limited means of income from industry or employment, thus poverty increases reliance and dependence on fragile natural resources, including pressure on herders to increase and protect stocking density. Agriculture is at the heart of the rural economy and accounts for roughly one fifth of the national economy. Most of the land is arid, semi-arid or rugged, and not easily cultivated. Water resources are scarce in most of the country, and finding water for irrigation is a critical challenge for the agriculture sector – particularly in remote areas.

Project target landscapes: The project target area is located in northern Pakistan and spans snow leopard habitat in GB, KPK and AJK. This region encompasses permanent snowfields and cold desert in the northern most areas and highest altitudes (Karakoram Mountains), extensive sub-alpine scrub (including juniper), dry temperate coniferous forest (including morinda spruce, Himalayan pine), and mixed deciduous and coniferous forest (Himalayan moist temperate forest, including Himalayan poplar and Indian maple). The project will establish three ‘model’ snow leopard landscapes, covering a total area of 4,100,000 ha (refer to Annexure A). These model landscapes include important PAs (e.g. Central Karakoram National Park , CKNP and Khunjerab National Park, KNP) as well as hunting regions, community lands, unprotected critical wildlife corridors and rangelands that include juniper forest. The composition of each model landscape is detailed in Annexure B. Considered together the three landscapes in total include: 676,000 ha of rangelands (including alpine meadows and sub-alpine scrub with juniper), 1.47 million ha agriculture, 67,000 ha of coniferous and mixed deciduous and coniferous forest, with the rest comprising rivers, lakes, rock and snow covered areas.

Threats: Despite their global and national importance to endangered wildlife and the pastoral communities that inhabit them, the high rangelands of this region face a number of increasing threats, described below.

Climate change impacts: The Greater Himalayas as a whole is very sensitive to global climate change. Progressive increases in warming at high elevations are already occurring at approximately 3 times the global average (IPCC, 2007). The Intergovernmental Panel on Climate Change (IPCC) has projected that average annual mean warming will be about 3 °C by the 2050s and about 5 °C in the 2080’s over the Asian land mass, with temperatures on the Tibetan Plateau rising substantially more. Given that current discussions about dangerous climate change are centered on increases of 2–3 °C, these temperatures are potentially catastrophic for Greater Himalayan peoples and ecosystems. Ongoing climate change over succeeding decades will likely have additional negative impacts across these mountains, including significant cascading effects on river flows, groundwater recharge, natural hazards, and biodiversity; ecosystem composition, structure, and function; and human livelihoods. A recent study indicates that about 30% of snow leopard habitat in the Himalaya may be lost and heavily fragmented (Forrest et al., 2012).

Overgrazing within rangelands is the cause of the most widespread land degradation in upland areas, causing considerable damage to the integrity of ecosystems and provision of essential ecosystem services – from soils, trees, water and biodiversity. Overgrazing has resulted in a high composition of less palatable forage species, including wide-spread weeds and poisonous plants. Grazing also impacts Juniper forests as young seedlings are susceptible to the browsing and trampling of livestock. The livestock census indicates an annual growth rate of 3.5% in Gilgit-Baltistan since 1976 (Khan 2003).  Based on the livestock census of 1996, Khan (2003) estimated stocking rate at 5.2 ha/animal unit, which was three times more than the FAO’s (1987) recommended critical stocking rate (i.e. 16 ha/animal unit for low potential range). Thus the rangelands that were assessed as burdened and overgrazed 20 years ago are experiencing even higher degradation due to progressively increasing livestock numbers. This has also led to high disturbance to wild ungulates such as markhor and ibex. Competition with livestock for forage is one of the most widespread causes of ungulate decline (Khan 2003).

Illegal timber harvesting and unsustainable gathering of fuel wood and NTFPs by local people dependent on this resource for fuel in rural areas, have led to widespread deforestation and degradation and diminishing forest resources. Deforestation rates in Pakistan are among the highest in the world. The total natural forest cover has reduced from 3.59 million hectares to 3.32 million hectares at an average rate of 27,000 hectares annually. Sedimentation following the loss of forests brings enormous social costs as a result of reduced storage capacity of reservoirs, loss of fertile soils, increased maintenance cost of irrigation infrastructure, reduction in agricultural production and increased vulnerability. Growing human and livestock populations, coupled with government control over forests in northern Pakistan and erosion of traditional systems of forest resource management has led to overuse of timber and NTFPs. Local communities rely on forests, particularly juniper, for construction material, fuel wood, thatch, fencing material, grazing ground for livestock and household medicine/remedies. Collection of wood and NTFPs in juniper forests has resulted in severe degredation of, causing reduction of juniper forests from 640,000 ha to an estimated 295,000 ha (or reduced by 46 percent) over the past 20 years in Gilgit-Baltistan translated into 14,750 ha per year. Juniper have endured long periods of heavy human use, primarily for grazing of livestock and gathering.

Illegal hunting and killing of wildlife and human-wildlife conflict: While poverty has a direct connection to increased reliance on rangelands and overgrazing, it is also responsible for much of the illegal hunting and killing of wildlife in northern Pakistan. Degraded rangelands, reduced abundance of wild herbivores, and increased prevelance of domestic livestock culminate in increased conflict between local communities and predators. Economic hardship is one of the root causes prompting herders to kill snow leopards to protect their livestock, and retribution killing of snow leopards in response is considered a high threat to the species (SLSS 2014). In addition, to compensate for livestock losses and supplement their incomes, herders in the region have also relied on poaching of snow leopard and wild prey to sell on the black market. International net trade in snow leopard between 1975 and 2000, as reported by CITES Parties, is 1042 items (skins 53, specimens 570, garments 3, trophies 3, bodies 9, skeletons 2).

The long-term vision of the project is to promote a landscape approach for the survival of the snow leopard. There are four key barriers to conservation and sustainable management of snow leopard landscapes in northern Pakistan, outlined below:

Barrier 1: Absence of a landscape-level approach to snow leopard conservation Forest and rangelands ecosystems in the wider landscape, outside PAs, are extensively used in the local economy. Over-grazing and excessive extraction of timber and fuelwood is leading to widespread degradation of rangelands and forests in northern Pakistan. Use of large areas of forests and alpine and sub-alpine meadows in northern Pakistan does not adequately account for conservation principles. Current management regimes - where existent within PAs and at the valley level – do not take into account the ecological requirements of flagship species such as snow leopard. They do not cover snow leopard migration corridors and juniper forests and often do not reflect the actual state of threats of snow leopard and its prey species, nor the actual state of snow leopard ecosystems, extraction rates of timber and NTFPs. Corridors providing for wildlife passage to key habitats outside Protected Areas are lacking. Juniper forests and grasslands in many of these areas are severely degraded beyond natural regeneration rates and buffer zones are not effectively managed to restrict biodiversity-incompatible uses. The status of locally migrating mammals depends on a landscape-level approach to conservation, combining strict conservation in core areas with sustainable use in wildlife passage/ forage areas. The snow leopard requires a large range as it migrates locally with the changing seasons, movements of markhor and ibex, and during the propagation season, and therefore none of the existing PAs alone are adequate to sustain viable populations of snow leopard. Local communities living in the project landscapes rely on the land and natural resources for their livelihoods. As described above, multiple pressures, including over-exploitation of rangelands and forest resources combined with climate change is resulting in increasing degradation of land and natural resources, threatening to trap local people into a cycle of resource degradation, vulnerability to variability and insecurity. Local communities need to be actively involved in stewarship of natural resources and improving production and management practices effectively, if the results are to be sustained. Most land users have limited capacities to adopt SLM and SFM technologies that can address this problem, while improving the management of important areas for biodiversity. At the same time, existing efforts by government (national and provincial), NGOs, educational institutions, and community organizations working on independent conservation initiatives inside and outside of PAs are largely uncoordinated.

Barrier 2: Inadequate representation and protection of important habitats, including forests, in the existing PA network Although there are over 20 established PAs in snow leopard habitat (Annexure A), these have not been assessed for their effectiveness to conserve snow leopard. A broad gap assessment of the national PA system of Pakistan showed that forest ecosystems in general are either inadequately represented or not represented at all, particularly in KPK and AJK. There has been no detailed gap assessment of the PA system in this northern region of Pakistan, nor in current conservation programs to ensure they are working effectively or efficiently, and to determine areas for improved synergy. Skills and abilities of wildlife and forest managers within PAs for law enforcement are reduced due to lack of training and equipment and the management capability of the PAs needs to be built in order to effectively conserve snow leopard and facilitate community engagement. Currently there is no system in place in the country for evaluating management effectiveness of Protected Areas.

Barrier 3: Insufficient involvement and support of local communities towards conservation solutions Historically, the presence of a large resident and migratory human community that has formal and usufruct rights has received little attention from managers and policymakers. The process of establishing a large number of PAs in the country have tended to completely ignore local communities. A lack of social safety nets and workable strategies to protect livelihoods and/or compensate for wildlife-caused damages has exacerbated the root causes of human-wildlife conflicts (e.g. families face average annual livestock losses to predation of 3-13% in snow leopard habitat, often equivalent to up to one month’s salary). Communities often claim compensation for predation, hold protests, and try to influence political and administrative leadership in resolving conflict. The lack of workable solutions undermines their ability to engage in wildlife conservation efforts. A recent survey in Musk Deer National Park (in AJK) - where there are no ongoing carnivore oriented conservation efforts - indicated that the majority of people (72-86%) wanted to reduce or eliminate populations of snow leopard, brown bear and wolf. This is further exacerbated by a general lack of awareness among natural resource users and managers in northern Pakistan towards both the importance of biodiversity and forest conservation and laws protecting wildlife and forests in the region. Materials and activities have previously been developed, but largely without a supporting strategy to ensure their effectiveness. Past efforts have either not been sustained, or have not been reinforced in order to create a strong understanding among local people of the value of protecting wildlife and associated forests and ecosystems. The role of community members as co-managers is recognized under Pakistan’s National Snow Leopard and Ecosystem Protection Priorities (NSLEP) and supported by new legislation (i.e. the provincial Model Wildlife Law). AJK has approved the Model Wildlife Law while GB and KPK are heading in the same direction. This shows positive interest and intent on behalf of the Government, however the adoption of mechanisms for sharing of responsibility and benefits with local communities have not been widely implemented as part of national policy. NGOs working in northern Pakistan have developed workable models for community conservation but these models need greater support from national policy and broader application.

Barrier 4: Lack of knowledge and skills necessary for effective conservation decision-making The vastness of northern Pakistan’s mountains, coupled with extreme ruggedness and poor accessibility, have limited systematic field-based research. Government and NGOs are hindered by a general lack of information as minimal systematic studies, if any, exist to assess distribution and basic ecology of snow leopards and prey species (even within PAs) and there is limited understanding of current juniper coverage and climate change impacts. Baselines for all major wildlife in northern Pakistan are severely limited; in fact, rigorous studies for snow leopard and wild snow leopard prey are lacking across Central Asia. Restoration measures for different degraded Juniper forest sites under different ecological and socio-cultural environments are little understood. Drivers of, and vulnerabilities to, climate change in northern Pakistan are little understood. Contributing to this, the technical surveillance capacities for conservation of signature species such as snow leopard and Juniper are weak and basic equipment and training for personnel is lacking. The current operational budget (US$ 4.8 million) of the three snow leopard range provinces is not adequate given the vastness of the area, rugged terrain, and diversity of issues each department is dealing with. In many PAs in northern Pakistan, staff numbers, capacities, and operating costs are far below the requirements for even basic operational management. International cooperation on snow leopard conservation to explore possibilities for coordinated management of habitat, cooperation on research on gene flow and on control of illegal trade have been identified as priorities for Pakistan under the Global Snow Leopard Ecosystem Programme, but have not yet been advanced.

2) Baseline scenario and associated baseline projects

The strategic framework for this project is the four-year National Strategy and Action Plan for the Conservation of Snow Leopard, 2014 – 2020. The main goal of the strategy and action plan is to prevent the decline of the Snow Leopard population in Pakistan. The plan defines the following critical areas for intervention: reducing habitat loss and degradation; reducing livestock impact on wild prey base; reducing retaliatory killing of snow leopard; improving institutional capacity; improving awareness; and addressing climate change.

Northern Pakistan is a major focus of conservation efforts by the government and leading conservation organizations like IUCN, WWF-P, Himalayan Wildlife Foundation (HWF), the Snow Leopard Trust (SLT), and the Wildlife Conservation Society (WCS).  Although the snow leopard was not the prime focus in the majority of large projects undertaken in northern Pakistan in the past, they have contributed to the cause of snow leopard conservation in various ways ranging from enhancing awareness to improving habitat quality and prey base.

There are a number of projects funded through the federal and provincial budgets. The annual operational budget of the three snow leopard range provinces is $4.82 million US$ (KPK 3.5, GB 0.78, AJK 0.54), which is being spent in controlling wildlife crime, maintaining watch and ward, management of protected areas, and species and habitat management. These departments also have developmental budgets, almost equivalent to the operational budget, which has been used for building infrastructure in snow leopard range, including offices, check posts, information centers and field stations.  Existence of the infrastructure and staff movement imparts surveillance necessary to control wildlife poaching, and has promoted awareness on wildlife legislation in rural communities.

The Mountain Areas Conservancy Fund (MACF) – established to support conservation-related activities of Valley Conservation Committees (VCC) – has a capital value of US$ 3.28 million.  The profit generated through term deposits (currently estimated at US$ 1.18 million) will provide financial support to snow leopard conservation initiatives undertaken by VCCs in northern Pakistan.

The Mountain and Markets Project (MMP, 2010-2015) is a US$ 3.293 million project implemented by UNDP in collaboration with the Ministry of Climate Change and the provincial forest and wildlife departments of Khyber Pakhtunkhwa and Gilgit-Baltistan. The MMP is using voluntary certification of non-timber forest products (NTFP) as a tool to promote biodiversity conservation and strengthen existing conservation efforts with innovative market-based mechanisms. The MMP will assist in organizing communities in the snow leopard range, and building their capacity for collective conservation actions. It will facilitate the development of  Sustainable Resource Use (SRU) agreements with communities, including snow leopard conservation.

More than 70% of the trophy hunting quota in the country is allocated to the snow leopard range. Local communities will benefit directly from the 80-90% share of the legal hunting of snow leopard prey species—markhor, ibex, blue sheep—which delivers an annual cash income of at least US$0.7 million in permit fees.

Limited scale community-based conservation is ongoing through a variety of organizations - including Snow Leopard Trust (SLT), Snow Leopard Foundation (SLF), WWF-Pakistan, and Baltistan Wildlife Conservation and Development Organization (BWCDO). These organizations are working with several communities, in collaboration with the wildlife departments in KPK and GB. Through these initiatives, basic data on snow leopard distribution and conflicts with humans are being collected, and snow leopard focused conservation models are being developed and piloted.

Degradation of land and forest exacerbates climate change impacts and potential disaster risks. This proposed project complements the UNDP supported “Disaster Risk Management Support” project (2013-2017), which is working at the national and provincial levels to formulate a programme of disaster risk management. The project is in the process of providing technical support to districts across Pakistan and is expected to enhance national, provincial and district capacities in prevention, assessment, management and reduction of risks. It is also expected to support vulnerable populations to benefit from improved and sustainable environmental management practices and improved prevention, risk reduction and response mechanisms.

These initiatives in the baseline scenario are significant insofar as they provide basic support to northern Pakistan and a framework for the socio-economic development for local communities. However, there is no overall approach at a suitable landscape scale to effectively conserve snow leopard and address the threats and drivers of ecosystem degradation identified above.

3) Proposed alternative scenario, with a brief description of expected outcomes and components of the project

The alternative scenario will promote a landscape-level approach which seeks to address major threats to snow leopard survival, while supporting communities to adopt sustainable land and forest management practices and implementing priority snow leopard conservation activities identified in the national strategy and action plan, in priority habitats of northern Pakistan. Four components have been designed to address the barriers described above:

Component 1. Landscape-level approach for snow leopard conservation: This project will establish three ‘model’ landscapes (refer to Annexure B). The project will guide comprehensive and participatory landscape-level management planning at two levels. At the first level model landscapes will be evaluated as a whole, and their management plans will be developed providing guidelines and structure for the overall management of these landscapes. This will include an assessment of PAs and PA operations and resources/needs within each landscape (taking into consideration existing PA Management Plans). The landscape plans will identify biological corridors (inside and outside of PAs) and develop plans to manage and operationalize them for sustainable use. The plans will also identify priority areas for rehabilitation (inside and outside of PAs) and define areas for improved forest and rangeland management. A sustainable livelihoods development plan that scopes and identifies options for reducing pressures within the landscapes through improved SLM and SFM production practices will also be developed under the landscape plans. This first level will be completed following a multi-stakeholder and cross-sectoral approach involving all relevant stakeholders and government departments (Stakeholder table section 2 list most prominent stakeholders, but others can be added as deemed appropriate during PPG). Following the development of landscape management plans, valley-specific management plans for conservation and improved SLM and SFM activities will be developed and implemented through extensive community consultation and in cooperation with local organizations. These valley plans will include the following: (i) areas for application of improved SLM and SFM technologies and restoration/regeneration; (ii) restoration/regeneration of degraded rangelands and at least 1,000 ha juniper forest, (iii) co-management agreements with local communities for delineated areas that describe prescriptions for sustainable natural resource use (such as off-take of fuelwood and NTFPs); (iv) define appropriate management, monitoring and enforcement to be implemented. Socio-economic and ecological studies will be carried out in targeted valleys to generate data for informed management planning. Communities within the valleys and in important biodiversity areas surrounding/adjacent to the PAs, such as in corridors and buffer zones, will be supported to adopt improved climate resilient and biodiversity friendly SLM and SFM practices (the exact measures to be determined during the PPG and appropriate to each target model landscape), such as rehabilitation of degraded rangelands and improving management (e.g. providing adequate rest through rotational grazing regimes), improved shrub land management (e.g. promoting sustainable fuelwood collection, use of fuel efficient stoves and reduced shrub land grazing), silvopastoral practices, community forestry using only native tree species (e.g. Himalayan poplar) to provide sustainable fuelwood, sustainable fodder cultivation. Training and extension support on appropriate technologies will be provided.

Component 2. PA expansion and strengthening: Within the model landscapes identified in component 1, the project will support the identification of priority areas for PA expansion and support implementation of measures to enhance management of these critical PAs and more broadly within the existing network, to strengthen the PA system will be improved through improving thereby contributing to expansion and strengthening of the PA system. In order to do so, the project will assess existing PAs in model landscapes for their adequacy to protect snow leopards, conserve remaining forests and identify candidate sites for additional PAs, with 20,000 ha of priority snow leopard habitat (including 7,000 ha of forests important for biodiversity) identified, mapped and gazetted as PAs by the end of the project. PA management and financing plans for critical existing National Parks (to be selected during the PPG) and new PAs in the model landscapes will be developed/aligned and operationalized to provide for: (i) PAs zoned for protection and sustainable use of natural resources by local communities; (ii) management of natural resources within PAs (including sustainable use by communities); (iii) effective monitoring and law enforcement governing wildlife poaching; shrub harvesting and other natural resource use; (iv) PA governance, including co-management and conflict resolution mechanisms; (v) monitoring systems in place for targeted species and ecosystems, establishing thresholds for resource use and informing PA management. The project will provide an opportunity to pilot the implementation of METT (Management Effectiveness Tracking Tool) in order to evaluate the current efficiency of the PAs. The results will develop a METT baseline for PAs in northern Pakistan, which will help to track progress in coming years. Support will also be provided for capacity building and training of PA staff (withing model landscapes and more broadly), community organizations and other relevant personnel to support effective PA management and operationalization, including for law enforcement and working with communities, in line with the above. The project will also improve the monitoring, enforcement and research capacity of wildlife and forest management staff and community organizations. The project will train and equip forest and wildlife managers (PA staff and community organizations) for implementing monitoring and enforcement systems to reduce violations. The project will also put in place improved anti-poaching and surveillance measures (including involvement of local communities in anti-poaching and surveillance/wildlife monitoring efforts), supported by information sharing and management systems to reduce incidences of wildlife poaching and illegal trade. Overall, the aim of this cross-training and co-involvement between PA staff and community organizations/local communities will improve efforts not only within PAs, but also coordination and integration of these efforts across the larger landscape, including corridor and rehabilitation zones spanning both PA and non-PA regions.

Component 3: Participatory conservation in snow leopard Model Landscapes through sustainable community development. Deep conservation engagement is necessary to reduce negative sentiment and provide families with the economic and emotional tools necessary to engage in and support wildlife and forest conservation initiatives. This component will reduce human-wildlife conflicts through community-based programs, in snow leopard model landscapes (Annexure B). In order to remain focused, this component will primarily consider livestock-based options for economic development, and rangeland improvements and social forestry that may help strengthen agriculture income. During the PPG the feasibility to include other forms of non-livestock income-generation activities such as NTFP based enterprise will be explored. In this regard, lessons from the GEF funded mountains and markets project in working with the private sector on product development and marketing of NTFP products will be useful.. The community-based models currently proposed are i) reduce economic losses to herder communities due to snow leopard predation ii) enhance economic gains by herder communities; and iii) enhance tolerance towards snow leopards and associated wildlife, and understanding of sustainable forest management.

Reducing economic losses to herder community because of snow leopard predation: Work under this output will be focused on facilitating the initiation of community-managed livestock insurance schemes that are closely linked to corral improvements. Livestock insurance schemes involve pooled community resources (cash) that can then be used to repay families who have lost livestock to predation. The initial pool—or insurance corpus—comes from a combination of participant premiums matched by outside donations (in this case NGO co-financing to this project), the premiums based on what families feel they can afford and the match as an incentive for families to contribute. Repayment rates and claims management are determined in collaboration with the community to protect against false claims, promote transparency, and ensure the insurance fund can grow towards self-sufficiency. NGO partners have experience running insurance programs of this nature, which work much better than compensation programs and compensate for their weaknesses. To complement this scheme, the project will support corral improvements  to protect goats and sheep when not grazing.  In many areas, livestock lost inside poorly constructed corrals can be quite high; one study reported 50 %. This is reduced considerably by proofing the corral from all sides with wire mesh on the roof, a single/strong wooden door, and by reinforcing walls with stones/cement.

Enhance economic gains by herder communities: The project will support vaccination of livestock. Research shows that 3–5 animals die of disease for every one killed by a wild predator (SLF, unpub. data). Vaccination is a conservation-based incentive in which herders are more willing to tolerate occasional losses to wild predators if fewer domestic animals are lost to disease. Most families in northern Pakistan cannot afford vaccines.  In addition, trained vaccinators are limited, making delivery inefficient.  To overcome these obstacles, vaccination programs make vaccines readily available to rural communities and train local vaccinators. Vaccination programs have been shown to reduce livestock losses to disease by up to 50%, increasing herd productivity and health (with related improvements to livestock products e.g. milk, dairy), and leading to a concomitant increase in income of up to $117 USD per participating family/year from selling animals at market.  Through conservation agreements with the participating communities, it is ensured that they will maintain their herd size and sell extra animals so that the decline in mortality does not result in increased herd sizes and thus increased competition for the wild ungulates.

Enhanced tolerance towards snow leopards and associated wildlife and understanding of sustainable forest management: A comprehensive environmental education (EE) program will be initiated to i) encourage a change in attitude towards snow leopards by enhancing awareness on the ecological, socio-economic importance of snow leopards and their ecosystems as well as measures that can reduce predation incidences; and ii) revive traditional understanding towards the value, importance and means of sustainably managing forests and rangelands. The EE program will unify and expand outwards from existing resources. As a part of EE program, wildlife and forest-focused EE strategies will be developed with concomitant resource materials and EE activities will be initiated catering to the needs of wildlife/forest staff and school children. Visitor information centers will be established in each model landscape, utilizing existing infrastructure of the wildlife departments, which will educate visitors and tourists to the area. The project’s strategy is that enhanced awareness and understanding among local communities on importance of conservation of snow leopard ecosystems combined with proven insurance and livestock management systems leads to higher tolerance  and increased stewardship of snow leopards and other wildlife and reduced threats.

Component 4. Support for international cooperation and conservation and management actions informed by knowledge on snow leopard ecology and ecosystem dynamics. This component will focus on addressing information gaps on the snow leopard population, its prey species and habitat. The first step will be a review of available data from past initiatives and it relevance/support to this project (e.g. GEF funded wetlands project; the Mountain Areas Conservation Programme and the on-going GEF funded Mountains and Markets project). A model snow leopard ecosystem information system will be developed that integrates and consolidates relevant data collected previously with data more specific to this project: i) systematic surveys to establish reliable snow leopard and prey abundance estimates (using camera traps, double-observer prey surveys, and genetic sampling); ii) research and surveys on the status of snow leopard ecosystems, including vegetative cover and juniper forests; iii) undertaking research on the impacts on snow leopard and prey habitats and the development of  techniques to rehabilitate and/or restore these habitats; and iii) undertaking research on the effects of climate change in high mountain systems and the vulnerability of snow leopard and prey to these climate change induced effects. A comprehensive GIS-based database of baseline and monitoring information for the entire snow leopard range in northern Pakistan will be developed and made available to researchers, conservations and decision makers. This component will also increase international cooperation by making concrete links with established relevant global and regional programmes such as linkages with the Global Snow Leopard Ecosystem Protection Programme (GSLEP) and other relevant initiatives. Targeted support will be provided for Pakistan’s participation in the Global Snow Leopard Ecosystem Protection Programme, including for partnership development and trans-boundary coordination. For example, Pakistan’s participation in international meetings and to inter-governmental cooperation on snow leopard conservation (e.g. for inter-governmental control of illegal trade), international collaboration and joint learning on research on snow leopard (e.g. gene flow and connectivity of populations) and good practices for snow leopard conservation. Opportunities for transboundary cooperation on coordinated management of snow leopard habitat will be further explored and considered during the PPG.

Global environmental benefits and Incremental/additional cost reasoning

The project centers on conservation of the globally Endangered snow leopard, and key ecosystems and landscapes of global value, including the Pamir-Karakoram which has been proposed as an UNESCO Biosphere Reserve. The Karakoram Mountains harbor the most heavily glaciated part of the world outside the Polar Regions and the Indus Flyway and adjacent high altitude lakes, streams, marshlands, peat lands and bogs are used as temporary and permanent staging, feeding and breeding grounds by migratory water birds, including several endangered aquatic bird species. The project will also benefit other significant and threatened species, including globally Endangered musk deer and key prey species such as Near Threatened markhor. The project will directly result in securing 3 snow leopard landscapes covering an area of about 4,100,000 ha, and improve the national ecological infrastructure of Pakistan through training and capacity building of PA staff, improved coordination across government sectors via cross-cutting management planning, and improved resources and knowledge base for effective decision-making.

| Summary of baseline scenario | Summary of GEF Scenario |  |  | Increment |
| --- | --- | --- | --- | --- |
| Sustainable landscape planning and management |  |  |  |  |
| -Lack of landscape-level approach that provides for effective conservation of large ranging flagship globally endangered snow leopard, resulting in fragmentation, increasing threats and degradation of land, forest and other natural resources on which communities rely -Communities living in valleys surrounding PAs, corridors and buffer zones lack capacity to implement SLM and SFM technologies and define sustainable resource use, resulting in degradation and over-exploitation of natural resources. |  | -Comprehensive management plans for three model landscapes developed along with valley plans that integrate sustainable forest and land management practices and snow leopard conservation compatible practices. - Appropriate SLM and SFM technologies implemented by local communities (in at least 250,000 ha) in areas adjacent to PAs, corridors and buffer zones. | -Landscape management plans developed covering 4,100,000 ha of key habitat for globally endangered snow leopard and that integrate and sustainable forest and land management and snow leopard conservation compatible practices. LD Benefits Reduced land degradation and enhanced ecosystem service provision in 250,000 ha of important SL ecosystems, indicated by: i) reduced land degradation (measured by decrease in extent of degraded areas); ii) improved productivity (measured by Net Primary Productivity and increase in rain use efficiency); iii) maintenance of ecosystem services (e.g. water availability and increased carbon sequestration); iv) restoration/regeneration of degraded rangelands, including 1,000 ha juniper forest. |  |
| PA expansion and strengthening |  |  |  |  |
| -Current PA network alone is not adequate to conserve viable populations of snow leopard. Gaps exist, particularly in representation of forests. -No assessment of management in the current PA system to ensure they are working effectively or efficiently. -Forest and wildlife managers lack capacity to apply, monitor and enforce sustainable landscape management measures. |  | -At least 20,000 ha of priority snow leopard habitat (including 7,000 ha of forests important for biodiversity) identified, mapped and submitted for gazettment as PAs. -PA management and financing plans for critical National Parks and new PAs are developed/aligned and operationalized. -At least 100 forest and wildlife managers (PA staff and community organizations) trained and equipped for monitoring and enforcing application of sustainable management measures that span inside and outside PAs for integrated, landscape-level coverage. |  | BD and SFM Benefits Increased representation of snow leopard habitat in the PA network, and avoided loss of 7,000 ha of forests, resulting in avoided emissions of 548,187 tCO2-eq Increased management effectiveness of existing National Parks and newly established PAs (measured by METT). Enhanced capacity of key local stakeholders including wildlife managers and local communities on assessment, monitoring and enforcement of sustainable snow leopard friendly forest and landscape management practices. |
| Human-cat conflict management |  |  |  |  |
| -Insufficient involvement and support of local communities towards conservation solutions -Lack of social safety nets and workable strategies to protect livelihoods and/or compensate for wildlife-caused damages -Threats to snow leopards in terms of retribution killing and/or poaching of snow leopard and wild prey -Lack of understanding among local people towards the importance of protecting endangered wildlife as important towards overall environmental health |  | -Livestock insurance schemes established to reduce predation-related economic burden on communities Improvements made to existing corrals to reduce predation losses -Livestock vaccination schemes implemented to reduce mortalities in livestock -Enhanced EE efforts implemented to increase awareness and enhance tolerance towards snow leopards and reintroduce traditional values towards forest management |  | BD Benefits -Reduced threats to globally endangered snow leopard as indicated by: number of snow leopards and other key wildlife (e.g. brown bear) remain stable or increase; -Local communities better off as result of enhanced measures, indicated by: at least 20% increase in income of participating households from schemes such as livestock insurance, improved corrals and vaccination. Reduced threats to globally endangered snow leopards as evidenced by: (i) reduced incidences of retaliatory killings; (ii) local communities’ attitude towards SL and SL ecosystem conservation are positive; (iii) reduced incidences of poaching and illegal wildlife trade. |
| Knowledge management and international cooperation |  |  |  |  |
| -Systematic field-based research in northern Pakistan is extremely limited -Baseline information for conservation planning is lacking, limiting ability of wildlife managers, forest managers, and conservationists to efficiently and effectively target solutions and develop programs to address current and emerging threats, including climate change. - International cooperation on snow leopard conservation identified as priorities for Pakistan under the Global Snow Leopard Ecosystem Programme, but not yet fully advanced. |  | -Review of relevant existing data -Systematic surveys completed of snow leopard and wild prey in model landscapes -Research to assess the status of existing SL ecosystems in northern Pakistan -Database platform for consolidation of new and old data -Monitoring system for rehabilitating/restoring rangelands within snow leopard habitats developed -Vulnerability of snow leopard ecosystems to the effects of climate change assessed -Targeted support to participation of Pakistan in the Global Snow Leopard Ecosystem Protection Plan process. |  | -Enhanced scientific knowledge on snow leopards, prey species, and habitat leads to better conservation and management decisions and improved stewardship of globally endangered SL and their ecosystems. -Effective development of mechanisms and improved capacities for international cooperation on snow leopard conservation, control of illegal trade and improved information management. -Enhanced scientific knowledge used to guide and improve conservation of wildlife, forests, and rangelands in northern Pakistan |

Innovation, sustainability and potential for scaling up

Innovative aspects: The community-based programs advanced through this project are innovative models that will generate important lessons for wider application, particularly the role of compensation/incentive programs for conservation of large carnivores in Pakistan. Involvement of local institutions, such as the VCCs, in landscape level management planning is novel in northern Pakistan. New structures will also be established by the project to further facilitate local stakeholder dialogue and input. This project will also take advantage of new advances in research to improve the efficiency and effectiveness of snow leopard and prey surveying and monitoring activities.

Sustainability: Current wildlife and conservation governance is characterized by devolution and decentralization of responsibilities. In this context, the proposed project will provide mechanisms for harmonized conservation and management strategies and the determination of roles and responsibilities at provincial and federal level, without reducing the authority of the provincial and other territory governments. Federal, provincial and sector departments have endorsed the NSLEP, and formal structures are being developed within the government and at the community level to implement the NSLEP, thus providing a solid foundation for future sustainability.  The project aims to empower local stakeholders to become custodians of local wildlife, and builds in sustainability by ensuring development schemes have full community buy-in and are community-managed.  The capacity building component of the project will improve skills of the PA staff in management, monitoring, law enforcement and research. They will be trained in systematically recording and reporting the species inventories, sightings, conflicts and wildlife crimes. Collecting and maintaining such data on PAs is cost-effective if it is done by the wildlife/forest staff, and the park management will be able to maintain this data after the project period. Wildlife staff will also maintain information centers (developed as part of EE component) over the long-term.

Potential to scale-up:  On a national level, best practices from this project will be replicated in other parts of snow leopard range in Pakistan, as well as applied to other wildlife conservation activities. Many of the innovative activities supported through this project for reducing threats to snow leopard, including livestock insurance, vaccination programmes and corral improvements are highly scalable. Lessons learned through the project’s on the ground and landscape level interventions in the target ‘model’ landscapes will be used to promote replication and scaling of the interventions, including the landscape conservation models and participatory conservation mechanisms, at the national, regional and global levels through knowledge management and dissemination activities under component four of this project. The engagement of Pakistan in the international GSLEP, namely by joining the international standards in the monitoring and research of snow leopard, as well as by participating in high level negotiations on the future policy and land use improvements aiming at conservation of this species, will ensure the longevity of the results in the areas of monitoring, research, community engagement, and policy making.

2. Stakeholders. Will project design include the participation of relevant stakeholders from civil society and indigenous people?  (yes  /no )

The project will follow a participatory approach, requiring involvement of community based organizations, conservation organizations, relevant public institutes whose roles and responsibilities are summarized in the table below.

| Stakeholders | Project Implementation Role |
| --- | --- |
| Local Communities of model landscapes | The primary beneficiary of project’s assistance. Local communities will be consulted during the development of the landscape management plans, with particular focus on issues related to pastures and livestock health and husbandry measures. Communities shall be mobilized proactively using monetary as well as social incentives, including livestock insurance, livestock corrals and livestock vaccination schemes. Local communities, particularly children, are considered a direct beneficiary of EE efforts under this project. |
| Local and district administration | Will be consulted during preparation of landscape management plans, and other project interventions. They will benefit from advice and training and will be able to use data and experiences generated by the project for improvements of the economic and social sections of their District Development plans. |
| The Ministry of Climate Change (MoCC) | MoCC is the lead ministry and focal point for the NSLEP. It is a key ministry for policy formulation regarding biodiversity and also acts as National Focal point to the CBD. The office of the Director Biodiversity shall be involved during the monitoring and implementation of the project. |
| Forest and Wildlife Department of Gilgit-Baltistan; Wildlife Department of Khyber Pakhtunkhwa; Fisheries and Wildlife Department of Azad Jammu Kashmir | The departmental field staff shall be trained in community-based wildlife management as well as population monitoring and innovative participatory conservation. Staff shall be actively involved in implementation of the project activities. |
| Livestock Department, Gilgit-Baltistan; Livestock Department, Khyber-Pakhtunkhwa Livestock Department, Azad Jammu Kashmir | Will be consulted during preparation of landscape management plans. Staff shall be actively involved in implementation of the project activities. |
| Pakistan Tourism Development Corporation | Will be consulted during preparation of landscape management plans. |
| Agricultural Department, Gilgit-Baltistan Agricultural Department, Khyber-Pakhtunkhwa Agricultural Department, Azad Jammu Kashmir | Will be consulted during preparation of landscape management plans. |
| Pakistan Museum of Natural History (PMNH) | PMNH is the lead institution for carrying out biodiversity inventories. It shall support the implementation of key species and prey species baseline assessments and monitoring. It will also assist in any other related biodiversity survey and monitoring work undertaken in the project. |
| Zoological Survey department (ZSD) | ZSD shall be actively engaged during the habitat analysis and surveys. |
| GSLEP Working Secretariat, Bishkek | GSLEP is planning to implement a global project for all the 12 range countries and during its implementation shall actively involve Pakistan. The strategies, innovations and lessons learnt globally shall be used in implementing the current project. |
| WWF-Pakistan | WWFs experience of environmental education and awareness raising shall be utilized in all the project areas. |
| Snow Leopard Trust (SLT), USA | The SLT will continue to provide technical support in implementation of the project, and will also provide co-financing to implement certain conservation components of the project |
| Panthera | Will provide co-financing to implement tested conservation models in selected valleys of the model landscapes. |
| Wildlife Conservation Society WCS | WCS experience of community based management of natural resources shall be utilized in project areas in a collaborative fashion. |
| The World Conservation Union- IUCN - Pakistan | IUCN has been quite active in Gilgit Baltistan in implementing MACP and preparation of Northern Areas Conservation Strategy. The expertise of IUCN shall be actively involved in implementation of the project and its initiatives in the project areas shall be synergized |
| Agha Khan Rural Support Programme (AKRSP) | The communities developed by AKRSP in the project areas shall be proactively engaged. The AKRSP community outreach program shall be utilized. |
| Himalayan Wildlife Foundation (HWF) | HWF shall be involved in implementation of the project in the areas of its work in AJK |
| Everest–K2-National Research Council (Ev-K2-CNR) | Ev-K2-CNR shall be involved in implementation of the project in the areas of its work in GB. |
| Baltistan Wildlife Conservation and Development Organization (BWCDO) | BWCDO shall be involved in implementation of the project in the areas of its work in AJK |
| Universities (Quaid-i-Azam University, Karakoram International University, Shaheed Benazir Bhutto University, Sheringal, AJK University, Muzaffarabad) | Students will be engaged in data collection and habitat assessment studies |

3. Gender Considerations. Are gender considerations taken into account? (yes  /no ).

This project recognizes that in rural Northern Pakistan, women of all ages play a critical role in managing natural resources. Women work in fields and may spend as much as 60 percent of their time in productive gender roles during the growing season. Women collect fuel, medicinal plants, and water and are responsible for storing grain. Women maintain family gardens and storing of vegetables. Women are most often in charge of livestock health care, shed cleaning, feeding and care of pregnant and lactating animals, milk processing and preparation of milk products such as butter oil (ghee) and buttermilk (lassi). Handicrafts, such as making woolen mats, knitting and embroidery, are also a source of income for women, particularly during the winter months when they are less involved in agriculture. Overall, they have a great deal of indigenous knowledge that should be utilized towards conservation. Men and women have different roles within the family, village and larger socio-political arena. Women are primary caregivers for children and the elderly and have a greater burden for maintaining the health of the family unit. Women are physically removed from men in society at large, and in rural communities women’s roles in governance and decision-making are negligible, and in some areas restricted to adult. Female literacy rates lag behind males, for example in GB female literacy is estimated at 38% vs 64% for males. There is also an indication that women’s perceptions towards wildlife may be different than men, due to their differing social roles, e.g. research findings from India indicate that women have more negative attitudes towards predators than men, most likely due to their role as family caregivers and the economic impact of livestock depredation upon family income.

This context has been taken into consideration in the design of this project and will be mainstreamed into its implementation in the following ways:

- Dedicated female staff at partner NGOs will be selected and trained to engage with, and collect data and information from, community women to feed into planning, strategies, and decision-making;

- EE courses and resources developed through this project will be made available to men and women and will confer information relevant to developing conservation strategies for men and women

- Where possible, opportunities will be developed specifically for women

- Knowledge gained through this project and shared back with communities will be conveyed to women in ways that are the most culturally and socially relevant

- Community-based programs will take into account the role of women in livestock rearing and livestock production, and ways for women to engage and benefit (particularly economically) from these programs will be devised; if necessary, women’s groups will be developed specifically to guide these initiatives

- Data collected for project monitoring and evaluating will be disaggregated by gender

At the same time, efforts will be taken to ensure women do not suffer adverse effects during the development process. In the development of management plans, special consideration will be taken by stakeholders to ensure the needs and roles of women are fully considered and accounted for. For example, management plans should consider the different ways in which men and women utilize natural resources within model landscapes to ensure that planned activities will not have disproportionate impact on women’s social and economic needs.

# 4. Risks.

| Risks | Rating | Preventive Measures |
| --- | --- | --- |
| Security situation may -delay project implementation | Medium | Insecure areas will be avoided for the selection of target areas. By adopting a participatory approach and involving all local stakeholders, risks related to social instability is reduced. In addition the project’s reliance on local institutions to implement field level activities ensures that much of project implementation can continue under moderate security threats. |
| Resistance or low levels of participation of local communities | Medium | The project will be implemented with full community participation, using existing built-in structures to facilitate community engagement wherever possible, and with recognition for meeting economic/social needs of communities. Programs such as insurance, vaccination, corral improvements, etc. will be coupled with outreach and education to simultaneously build economic security and a greater foundation of understanding and awareness. Insurance in particular is a well-tested model working successfully in multiple snow leopard range countries. These programs have found that when implemented as a repayment (and not compensation) system, with norms decided and managed at the community level, community buy-in and contributions are high and false claims and corruption are low. |
| Natural disasters (including those linked to climate change) in model landscapes slows or prevents implementation of some project activities | Medium | The project is designed to contribute to increasing the resilience of the target landscapes to disasters. In the event of a natural disaster making work untenable in one landscape, the project will focus resources and activities in the other 2 ‘model landscapes’ until there is some recovery evident in the area affected. |
| Insufficient data to produce knowledge for improved programs and policies | Low | Proven methods are in place and have been tested in Pakistan for most of the information needs in this project. Increasing capacity through inter-agency cross training and training of wildlife department staff should improve the ability to collect larger, more thorough data sets and repeat surveys as necessary. |

# 5. Coordination. Outline the coordination with other relevant GEF-financed and other initiatives.

The project will integrate experiences and good practices both in Pakistan and other countries by linking to relevant initiatives at the local, national, regional and global levels. The Global Snow Leopard and Ecosystem Protection Program (GSLEP) is a comprehensive global approach to conserve the endangered snow leopards and unique heritage and fragile mountain ecosystems of which is it an important icon. The GSLEP was formally endorsed by the 12 range countries (including Pakistan) at the Global Snow Leopard Conservation Forum held in Bishkek, Kyrgyzstan on October 22-26, 2013.  Subsequent to the endorsement of the GSLEP, a working secretariat of the program has been established in Bishkek, with the support of the government of Kyrgyzstan, which will facilitate implementation of the GSLEP. The working secretariat convened a workshop of 12 range countries on June 5-11, 2014, Issyk-Kul Region, Kyrgyz Republic. The objectives of the workshop were to identify 20 model snow leopard landscapes, and define National Priority Activities NPAs and Global Priority Activities (GPAs) for the first two-year Implementation Plan, develop Key Performance Indicators (KPIs) to measure progress toward the goal and advance preparation of specific project proposals for the relevant funding partners. The three model landscapes (see Annnexure B) focused on in this project are part of the 20 model lnadscapes identified in GSLEP, and the outcomes of this  proposed project are developed following the KPIs set under GSLEP. Recently, on March 19-20, 2015, snow leopard range countries gathered again in Bishkek, and agreed to form a high-level Steering Committee to guide Program implementation, regularly review its progress, and maintain a strong political commitment to its objectives. Pakistan’s Federal Minister of Climate Change has been elected Chair of the steering committee for two years, and he will also provide patronage to the proposed project. The project will therefore complement the GSLEP by implementing national targets, and will coordinate with the GSLEP secretariat on regional activities and global goals, through its NPD (national project director) who is also a focal person for GSLEP in Pakistan. In fact the GSLEP Secretariat has developed a “Standard Management System for Information Sharing”, which will be adopted for periodic reporting to the GSLEP.

The project has been designed to complement and build on several past and on-going projects in Pakistan, including:

The proposed project is complementary to the GEF supported project "Mountains and Markets: Biodiversity  and Business in Northern Pakistan" (GoP, GEF, UNDP, 2011-2015) which is promoting the development of ecosystem based enterprises in the northern territories of Pakistan and key partners of this project participate in the proposed GEF project. The proposed project also builds on the IUCN implemented "Mountain Areas Conservancy Project MACP" that was implemented from 1999-2006 in Gilgit-Baltistan and Khyber Pakhtunkhwa. In this project the communities in both these provinces were organized proactively for biodiversity conservation and trophy hunting from community based conservation areas was used as an incentive to mobilize communities. The project also established a Mountain Areas Conservancy Fund MACF that is currently being managed under the auspices of Ministry of Climate Change. Some of the project areas falling in the jurisdiction of MACF shall also be proactively involved through MACF.

The Sustainable Land Management Programme to Combat Desertification in Pakistan (GoP, GEF, UNDP, 2013-14 – 2018-19) is a two-phased programme focused on creating an enabling environment for SLM and information systems and capacity building for SLM at national and provincial levels. The second phase will focus on scaling up SLM and climate resilient practices, developing a planning and decision support system. Guidelines, standards, training products and lessons learned developed under this initiative will provide important resources for this proposed project to apply in the target landscapes, and will be integrated into project design and the development of the landscape and valley plans and SLM activities. The SLM project has successfully used various community engagement and governance mechanisms that will be used by this project, such as village level agreements, alternative livelihoods development and inter-sectoral mechanisms at provincial level. The Sustainable Forest Management to Secure Multiple Benefits in Pakistan's High Conservation Value Forests (GoP, GEF, UNDP, 2014-2019) project will promote an integrated approach at landscape level for the management of high conservation value forests that will deliver global biodiversity, carbon benefits and ecosystem services to local communities and enhance resilience across 3 target landscapes totaling 55,600 ha. The proposed snow leopard project will coordinate closely with the SFM project to ensure complementarity in the project target areas and activities.

The UNDP supported “Disaster Risk Management Support” project (2013-2017) recently began working at the national and provincial levels to formulate a programme of disaster risk management. The project will build national, provincial and district capacities for prevention, assessment, management and reduction of risks and support vulnerable populations to benefit from improved and sustainable environmental management practices and improved prevention, risk reduction and response mechanisms. This project should also be engaged in the preparation of the snow leopard project to leverage synergies and links to this work and ensure that relevant guidelines and lessons learned are incorporated in development of the project design and landscape plans.

This project has been designed to complement the above described initiatives. Mechanisms for coordination with the on-going initiatives described above will be developed during the PPG and integrated into project development to ensure effective integration of lessons learned and coordination throughout implementation of this project.

6. Consistency with National Priorities. Is the project consistent with the National strategies and plans or reports and assessments under relevant conventions? (yes  /no ).  If yes, which ones and how:  NAPAs, NAPs, ASGM NAPs, MIAs, NBSAPs, NCs, TNAs, NCSAs, NIPs, PRSPs, NPFE, BURs, etc.

Sustainable natural resource management, benefit sharing, and biodiversity conservation are the cornerstones of the proposed project and they are recognized as crucial elements by Pakistan's policies for sustainable development. The "Vision 2030" elaborated by the Pakistan Planning Commission in 2007, aims for equitable sharing of environmental benefits, increasing community management of national resources, and integrating environmental issues into socio-economic planning to achieve sustainable development. Pakistan's National Conservation Strategy (1992) recommends measures for sustainable management of wildlife and habitat, by emphasizing; (a) the introduction of incentives to safeguard conservation areas and divert pressures on threatened wildlife habitats and species, (b) promotion of community-based management systems so that local people participate in the protection and conservation of habitats and related species, (c) enforcement of existing legislation strictly in support of ecosystem protection and wildlife conservation and support to appropriate higher penalties for breaches.

In addition, the project will contribute to achievement of the Aichi Targets, in particular under the strategic goal B: Reduce the direct pressures on biodiversity and promote sustainable use, Target 5: By 2020, the rate of loss of all natural habitats, including forests, is at least halved and where feasible brought close to zero, and degradation and fragmentation is significantly reduced; Target 7: By 2020 areas under agriculture, aquaculture and forestry are managed sustainably, ensuring the conservation of biodiversity; Target 11: By 2020, at least 17 per  cent of terrestrial and inland water, and 10 per cent of coastal and marine area, especially areas of particular importance for biodiversity and ecosystem services, and conserved through effectively and equitably managed, ecologically representative and well-connected systems of protected areas and other effective area-based conservation measures, and integrated into the wider landscapes and seascapes.

Being signatory to Convention on Biological Diversity, Pakistan developed a Biodiversity Action Plan (BAP, 2000), which has been updated as the National Biodiversity Strategy and Action Plan (NBSAP) in 2016).  In order to address geographic variation in biodiversity potential and challenges, the KP and GB also have recently drafted provincial biodiversity strategies and action plans (KP-BSAP 2016 and GB-BSAP 2016).  These are important policy instruments to conserve biodiversity in the country. The project’s Components 1 & 2 are built upon targets 11 and 14 of the NBSAP, and targets 11-12-14 in KP-BSAP, and targets 1-3 (under section on Ecosystems, Habitats, and Species) in GB-BSAP.  The PA expansion and strengthening activities in the proposed project cover 10 PAs considered important in NBSAP/KP-BSAP/GB-BSAP (Ghamot NP, Musk Deer NP, Desoai NP, Central Karakoram NP, Khunjerab NP, Qurambar NP, Broghil NP, Chitral Gol NP, Shandoor and Kalash Areas).  The snow leopard is considered important and target species for recovery under NBSAP/KP-BSAP/GB-BSAP, therefore the project Component 3 supports target 12 in NBSAP and KP-BSAP, and target 4 (under section on Ecosystems, Habitats, and Species) in GB-BSAP, as it entails measures that will conserve important 14 fauna (Brown bear, black bear, Himalayan lynx, grey wolf, Eurassian otter, wooly flying squirrel, Kashmir flying squirrel, grey langur, common leopard, Marcopolo sheep, blue sheep, ladakh urial, markhor, musk deer) and 8 flora species (Juniper, kuth, Nag chhatri, marsh orchid , aconite, Himalayan mayapple, Primula, gugul) identified in NBSAP/KP-BSAP/GB-BSAP, besides recovery of the snow leopard.  The environmental education (EE) program proposed under Component 3 of the project is in line with target 1 in NBSAP/KP-BSAP.  The knowledge enhancement on snow leopards and ecosystems under Component 4 of the project supports target 19 in NBSAP/KP-BSAP, and targets 2 (under Forest sector and Ecosystems, Habitats, and Species) in GB-BSAP.  The project Component 3 also addresses target 5 in KP-BSAP, which aims at reducing pressure on biodiversity and loss of habitat.

The project is also consistent with the recommendations of the GSLEP process and has been designed to respond to the four-year National Strategy and Action Plan for the Conservation of Snow Leopard, 2014 – 2020, including the following critical areas for intervention: reducing habitat loss and degradation; reducing livestock impact on wild prey base; reducing retaliatory killing of snow leopard; improving institutional capacity; improving awareness; and addressing climate change.

7. Knowledge Management.

This project recognizing the importance of KM and will take the following approach towards managing and sharing information:

- Data and experiences (facts, observations, survey results, field notes, stories, etc.) will be collected and stored by executing partners with specific, relevant expertise in these areas following their established protocols. Each agency will be responsible for seeking out and coordinating inter-agency learning for better use of resources when most appropriate.

- Data will be accessible to anyone within or outside this project wishing to use it for the purpose of further research. It is the role and responsibility of the executing partners to ensure proper storage of data for future reference and use.  Through this project, efforts will be taken to increase capacity towards data collection among wildlife department staff; data collected will be stored and become part of the database managed by whichever agency is providing the training and overseeing the study.

- Data will be analyzed to produce information by experts with relevant experience from within an established base of NGO stakeholders already involved in project design.  This will include assistance or mentoring of wildlife/PA staff where possible. Information will be open to all executing partners within this project. Information will be reviewed and, when possible, developed into knowledge products that can be used for decision-making, including recommendations and publications.

- Relevant publications will be submitted to peer-reviewed journals, shared with the Program Steering Committee (PSC) and provided open access through Snow Leopard Network, which maintains an online bibliography. Recommendations will be shared with PSC and then with Program Management Committees (PMCs). It will fall under the responsibility of the PMCs to more broadly disseminate information to communities.

- Knowledge produced through this project - either directed or 'organically' via lessons learned - will be documented by the SLF and, where possible, re-incorporated into Pakistan's NSLEP and to the wider GSLEP. At the same time, this project will benefit from an influx of knowledge via the GSLEP and other snow leopard range countries conducting similar projects.

part iii:  approval/endorsement by gef operational focal point(s) and GEF agency(ies)

A. Record of Endorsement of GEF Operational Focal Point (s) on Behalf of the Government(s):  
      (Please attach the Operational Focal Point endorsement letter(s) with this template. For SGP, use this SGP OFP 
      endorsement letter).

| Name | Position | Ministry | Date (MM/dd/yyyy) |
| --- | --- | --- | --- |
| Mr. Aftab Ahmad Maneka | Joint Secretary (Development) Cabinet Secretariat, Climate Change Division | ministry of climate change | 07/28/2015 |

B. GEF Agency(ies) Certification

This request has been prepared in accordance with GEF policies and procedures and meets the GEF criteria for project identification and preparation under GEF-6.

| Agency Coordinator, Agency name | Signature | Date (MM/dd/yyyy) | Project Contact Person | Telephone | Email |
| --- | --- | --- | --- | --- | --- |
| Adriana Dinu Executive Coordinator UNDP – GEF |  | 26 April 2016 | Doley Tsehering Regional Technical Advisor, EBD | +66 (0)2 304 9100 | doley.tshering@undp.org |

C. Additional GEF Project Agency Certification (Applicable Only to newly accredited GEF Project Agencies)

For newly accredited GEF Project Agencies, please download and fill up the required GEF Project Agency Certification of Ceiling Information Template to be attached as an annex to the PIF.

ANNEXURES

Annexure A: Protected areas located in the snow leopard range in Pakistan

Annexure B: Snow Leopard Model Landscapes targeted for project activities

Project target landscapes:

This project will establish three model landscapes, covering a total area of 4,100,000ha: Karakoram Pamir Landscape (2,546,600 ha; including 324,000 ha of rangeland, 850,000 ha of agriculture, 8,000 ha of coniferous forest, as well as rivers, lakes, rock, debris and snow covered areas), Hindukush Landscape (1,047,280 ha; including 172,000ha of rangeland, 460,000 ha of agriculture, 15,000 ha of forest, as well as rivers, lakes, rock, debris and snow covered areas) and Himalaya Landscape (508,320 ha; including 180,000 ha of rangeland, 160,000 ha of agriculture, 44,000 ha of forest, as well as rivers, lakes, rock, debris and snow covered areas).

Annexure C: Literature Cited

Akbar, G. and Anwar, M. (eds.). 2011. Wildlife of Western Himalayan Region of Pakistan (Northern Pakistan). Instant Print System (Pvt.) Ltd. Islamabad

Ehlers, E. and Kreutzmann, H. (eds.). 2000. High Mountain Pastoralism in Northern Pakistan. Stuttgart.

FAO. 1987. Pakistan’s experience in rangeland rehabilitation and improvement. Food and Agriculture Organization of the United Nations. Rome, pp70.

Forest, Wildlife and Environment Department, GB 2012. Draft Rangeland Policy for GB. Forest Complex, Jutial, Gilgit

Forrest, J.L., Wikramanayake, E., Shrestha, R., Areendran, G., Gyeltshen, K., Maheshwari, A., Mazumdar, S., Naidoo, R., Thapa, G.J., Thapa, K., 2012. Conservation and climate change: Assessing the vulnerability of snow leopard habitat to treeline shift in the Himalaya. Biological Conservation 150, 129–135.

GoP and IUCN, 2003. Northern Areas Strategy for Sustainable Development. IUCN Pakistan, Karachi.

GoP and. IUCN. 1992. National Conservation Strategy.

GoP. 2010. Draft National Rangeland Policy, Ministry of Environment. Islamabad, Pakistan, pp16

GoP/WWF/IUCN. 2000. Biodiversity action plan for Pakistan: A framework for conserving our natural wealth. Karachi: IUCN Pakistan, Government of Pakistan and World Wide Fund for Nature, Pakistan.

Jackson, R. and Wangchuk, R. 2004. A Community-Based Approach to Mitigating Livestock Depredation by Snow Leopards. Human Dimensions of Wildlife, 9:307–315.

Khan, M. I. 2003. NASSD background paper: Communication for sustainable development. Gilgit: NACS Support Project, IUCN Pakistan.

Roberts, T. J. 1991. The Birds of Pakistan, Volume 1. Oxford University Press.

Roberts, T. J. 1992. The birds of Pakistan, Volume 2. Oxford University Press.

Roberts, T.J. 1997. The Mammals of Pakistan, Ernest Benn Limited, London.

Shackleton, D.M. (ed.). 1997. Wild Sheep and Goats and their Relatives: Status Survey and Conservation Action Plan for Caprinae. IUCN, Gland, Switzerland, and Cambridge, UK.

Sheikh, K. M. and Molur, S. (Eds.). 2004. Status and Red List of Pakistan’s Mammals. Based on the Conservation Assessment and Management Plan Workshop: IUCN Pakistan.

Shrestha, A. B., Wake, C.P., Mayewski, P.A. and Dibb, J. E. 1999. Maximum temperature trends in the Himalaya and its vicinity: an analysis based on temperature records from Nepal for the Period 1971–94. Journal of Climate, 12: 2775–2787.

Snow Leopard Network. 2014. Snow Leopard Survival Strategy. Revised 2014 Version Snow Leopard Network, Seattle, Washington, USA.

WWF-P. 2009. Boundary Delineation of Khunjerab National Park. Boundary Demarcation and Renotification of Protected Areas Project.

Annexure D: Carbon Calculations:

7,000 ha of (high conservation value) forest identified and gazzetted within protected areas and avoided GHG emissions of  548,187 tCO2-eq over a 10 year period

Gazzettment of 7,000 ha of forest within PAs through this project will change the regime from use to protection and this will halt deforestation in these areas. Deforestation rates in Pakistan are estimated at 2.2 per cent per year according to FAO Forest Resources Assessment (2010). As a result of the project, 154 ha of deforestation will be prevented annually, amounting to 1,540 ha over a 10 year period.  The Ex-Ante Carbon-balance Toll (EX-ACT) Tier ONE Edition, developed by FAO was used for the calculations. Based on avoided loss of 1,540 ha of forest with the project’s intervention, estimate of sequestration is 548,187 tCO2eq over a 10 year period. This will be studied in more detail during the PPG stage.

See FAO EX-ACT Calculations below.

Project ID number will be assigned by GEFSEC and to be entered by Agency in subsequent document submissions.

When completing Table A, refer to the excerpts on GEF 6 Results Frameworks for GETF, LDCF and SCCF.

Financing type can be either investment or technical assistance.

For GEF Project Financing up to $2 million, PMC could be up to10% of the subtotal;  above $2 million, PMC could be up to 5% of the subtotal. PMC should be charged proportionately to focal areas based on focal area project financing amount in Table D below.

PPG requested amount is determined by the size of the GEF Project Financing (PF) as follows: Up to $100k for PF up to $3 mil; $150k for PF up to $6 mil; $200k for PF up to $10 mil; and $300k for PF above $10m. On an exceptional basis, PPG amount may differ upon detailed discussion and justification with the GEFSEC.

PPG fee percentage follows the percentage of the Agency fee over the GEF Project Financing amount requested.

Provide those indicator values in this table to the extent applicable to your proposed project.  Progress in programming against these targets for the projects per the Corporate Results Framework in the GEF-6 Programming Directions, will be aggregated and reported during mid-term and at the conclusion of the replenishment period. There is no need to complete this table for climate adaptation projects financed solely through LDCF and/or SCCF.

This is a minimum figure based on the new area of PA to be gazette through the project. The project will also strengthen critical PAs (to be selected during PPG) within the model landscapes.

UNDP/GEF’s MACP project (1999-2006) laid a positive foundation of awareness and appreciation for conservation in GB, KPK, and AJK communities; however, MACP only reached about 60% of the region covered by this project and in the past 10 years the motivation of MACP communities has been gradually diluted, due to limited post-project follow up and weak interaction by the government and IUCN with those communities.

The MACF was established by the now completed UNDP-GEF Mountain Areas Conservancy Project (MACP). The project facilitated the establishment of 47 VCCs, 31 of which are implementing valley conservation plans with the financial support of the MACF.

Unless managed carefully, many compensation programs tend to result in aggravating conflicts rather than mitigating them (Nyhus et al. 2003). State-run compensation programs often fail to address conflicts due to several factors such as low compensation rates, false claims or corruption, depletion of funds, bureaucratic apathy, and the time and effort required in securing compensation (Mishra 1997; Nyhus et al. 2003; Madhusudan 2003; Maclenan et al. 2009).

(Jackson and Wangchuk 2004)

For regional and/or global projects in which participating countries are identified, OFP endorsement letters from these countries are required 
  even though there may not be a STAR allocation associated with the project.

GEF policies encompass all managed trust funds, namely: GEFTF, LDCF, and SCCF