GEF-6 REQUEST FOR PROJECT ENDORSEMENT/APPROVAL

Project Type: Full-sized Project

Type of Trust Fund: GEF Trust Fund

For more information about GEF, visit TheGEF.org

part i: project information

| Project Title: Snow Leopard and Ecosystem Protection Program |  |  |  |  |
| --- | --- | --- | --- | --- |
| Country(ies): | Pakistan | GEF Project ID: |  | 9231 |
| GEF Agency(ies): | UNDP | GEF Agency Project ID: |  | 5716 |
| Other Executing Partner(s): | Ministry of Climate Change and Snow Leopard Foundation | Submission Date: Re-submission Re-submission Re-submission |  | 08 Nov. 2017 9 Jan 2018 26 Feb 2018 9 April 2018 |
| GEF Focal Area (s): | Multi-focal area | Project Duration (Months) |  | 60 |
| Integrated Approach Pilot | IAP-Cities IAP-Commodities IAP-Food Security |  | Corporate Program: SGP |  |
| Name of Parent Program | NA | Agency Fee ($) |  | 441,229 |

- Focal Area  Strategy Framework and Other Program Strategies

| ### Focal Area Objectives/Programs | ### Focal Area Outcomes | ### Trust Fund | ### (in $) |  |
| --- | --- | --- | --- | --- |
|  |  |  | ### GEF Project Financing | ### Co-financing |
| BD-1 Program 2 | Nature’s Last Stand: Expanding the Reach of the Global Protected Area Estate | GEFTF | 2,211,676 | 6,817,000 |
| LD-3 Program 4 | Scaling-up Sustainable Land Management through the Landscape Approach | GEFTF | 884,671 | 3,079,000 |
| SFM-1 Program 1 | Integrated Land Use Planning | GEFTF | 700,000 | 2,550,000 |
| SFM-1 Program 2 | Identification and Maintenance of High Conservation Value Forests | GEFTF | 248,174 | 784,000 |
| SFM-3 Program 7 | Building Technical and Institutional Capacities to Identify Degraded Forest Landscape and Monitor Forest Restoration | GEFTF | 600,000 | 1,900,000 |
| Total project costs |  |  | 4,644,521 | 15,130,000 |

- Project description summary

| ### Project Objective: To promote a landscape approach for the survival of snow leopard and its prey species by reducuing threats and applyiong sustainable land and forest management in critical habitats in Northern Pakistan |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| ### Project Components/ ### Programs | ### Financing Type | ### Project Outcomes | ### Project Outputs | ### Trust Fund | ### (in $) |  |
|  |  |  |  |  | ### GEF Project Financing | ### Confirmed Co-financing |
| Component 1: Landscape level approach for snow leopard conservation | TA/INV | Outcome 1: Improved management of snow leopard landscapes that integrates sustainable forest and land management and compatible conservation practice. Key outcome indicators are: (i) At least 1,500,000 hectares of critical snow leopard landscapes effectively managed under integrated participatory management landscape approaches (ii) Increase in institutional capacity (by 50%) as measured by UNDP Capacity Development Scorecard baseline values of: National level-18; GB-18; AJK-15: and KP-18. (iii) Stable or improved snow leopard (from existing baseline of + 200) and associated species baseline populations in Northern Pakistan as follows: Karakoram-Pamir LS: Himalayan Ibex-4,900 Markhor -230 Blue Sheep – 750 Ladakh Urial -50 Hindu Kush LS: Markhor – 3,400 Himalaya LS: Musk Deer, Brown bear | 1.1: Functional multi-sector and multi-stakeholder coordination and governance mechanisms developed and supported to facilitate convergence of planning, manpower and financial resources for three multiple use snow leopard landscapes. 1.2 Landscape level management strategies that integrates biodiversity, ecosystem services, climate mitigation, sustainable community resource use and socio-economic considerations developed, approved and implemented following: (a) biological and socio-economic mapping to identify conservation (HCVFs, KBAs and corridors) and multiple use areas for sustainable natural resources management and community resource use; (b) negotiation of shared vision among relevant stakeholders for each landscape, including options for zoning; (c) defining prescriptions for each management zone; and (d) developing partnership arrangements with government agencies and CSOs for collaboration in these landscapes. 1.3 Participatory monitoring for snow leopard and other endangered species, including prey species developed and implemented to inform management responses through (a) design of monitoring framework and implementation plan; (b) enhanced capacity of field staff and local volunteers; (c) validation of existing baselines and monitoring changes in snow leopard and key species populations; (d) assessing diversity and gene flows in snow leopard populations across landscapes; and (e) improving understanding of human-wildlife conflict and wildlife trade. 1.4 Replication strategy developed and implemented to facilitate up-scaling of integrated landscape planning and management model by (a) improving dialogue with provincial authorities; (b) strengthening awareness and improving capacity; (c) developing best practice manuals and handbooks and (d) mobilization of external and internal funding for replication. | GEFTF BD 0.39m; LD 0.05m; SFM 0.20m | 642,000 | 3,610,000 |
| Component 2: Protected Area expansion and strengthening | TA/INV | Outcome 2: Increased representation of priority snow leopard ecosystems in Protected Area network. Key outcome indicators are: (i) At least 200,000 ha of additional priority snow leopard habitat, including 10,000 ha of high conservation value forests legally defined and included in PA resulting in 2.96 million tCO2e sequestrated over 10-year period (ii) Increase in METT score by at least 30 points for the following PAs from baseline values of: – Chitral Gol NP-30; Broghil NP – 12; Central Karokoram NP – 22; Qurumba NP- 13; Khunjerab NP -25; Musk Deer NP- 18; Ghamot NP –16 (iii) At least 17 management and financing plans for existing PAs (mainly CMCAs) developed, approved by government and operationalized with adequate financial support. (iv) At least 200 forest and wildlife staff trained and actively enforce environmentally friendly management practices and wildlife crime prevention measures in snow leopard habitats (vi) At least 60 community members trained and actively engaged in wildlife crime monitoring and surveillance resulting in 25% decrease in incidents of wildlife crime from current baseline | 2.1 Protected area network in the snow leopard range expanded through identification, mapping and gazettal of new protected areas to be achieved through (a) assessment of coverage and effectiveness of existing PA network; (b) improving PA networks by establishing new community managed conservation areas (CMCAs) to enhance connectivity and improve protection of key species and habitats; (c) development of METT baselines for PAs; and (d) improving management of CMCAs 2.2 Management and financial plans for priority protected areas developed, discussed with stakeholders and approved by the government. Priority activities include: (a) preparation/update of management plans for existing and new PAs; (b) site-specific investment for restoration of degraded alpine pastures and sub-alpine forests; (c) improving protocols for conservation of snow leopard and associated species; (d) improved management prescriptions for CMCAs; and (e) improved coordination with development agencies to mainstream biodiversity conservation principles in sector plans within the landscapes 2.3 Capacity of forest and wildlife staff in the demonstration sites enhanced/strengthened to improve conservation outcomes and combat wildlife crime entailing (a) undertaking capacity needs assessment of wildlife and forest staff; (b) development of training modules/manuals for rangeland management, forest and pasture restoration, wildlife and protected areas management, wildlife crime management etc.; (c) trainings in wildlife management, assessment and monitoring techniques; and (d) development of syllabus and conduct of diploma course for the selected field staff of the wildlife and forest departments. 2.4 Wildlife agencies have information on hotspots and pathways of Illegal Wildlife Trade (IWT) to organize targeted ant-poaching surveillance operations against wildlife crime. This will entail (a) detailed intelligent information gathering on poaching and wildlife trade; (b) mapping hotspots and pathways of illegal activities; (c) training of wildlife, army and local police staff on crime scene investigation and basic forensic science; and (d) use of data by law enforcement agencies for enabling surveillance and monitoring operations against wildlife trade. | GEFTF BD 0.60m; LD 0.38m; SFM 0.17m | 808,107 | 2,505,000 |
| Component 3: Participatory conservation in snow leopard model landscapes through sustainable community development | TA/INV | Outcome 3: Participatory conservation in the targeted landscape enhanced to reduce human-snow leopard conflicts and improve livelihoods of community. Outcome indicators are: (i) Valley conservation plans implemented in at least 17 valleys funded by GEF grant (ii) Implementation of sustainable livelihood, NRM and wildlife deterrents systems ensures at least 15% average increase in incomes of participating communities from current levels, of which at least 30 % of households include women beneficiaries (iii) At least 25% decrease in baseline livestock predation of 0.6 individuals /household/year, and at least 50% decrease in retaliatory killings of snow leopards and other predators | 3.1 Site-specific integrated valley conservation management plans designed and implemented in areas of high biodiversity value areas through (a) establishment/strengthening existing valley conservation committees; (b) ecological and socio-economic mapping of valleys to determine scale of and impact of resource use; (c) institution of a participatory community-based planning process to define options for improving conservation, sustainable natural resource use and livelihood outcomes; and (d) preparation of multi-year valley conservation plans (VCPs). 3.2 Projects on sustainable community based natural resources management, sustainable livelihood and solutions to reduce wildlife-human conflicts developed and implemented through grant allocation to selected Valley Conservation Committees and beneficiary households for VCP implementation. 3.3 Community-based surveillance, monitoring and wildlife crime prevention system developed and implemented through (a) design of community surveillance, monitoring and crime detection plans; (b) mobilization of community groups for wildlife crime surveillance and monitoring; (c) training of community groups and provision of equipment and other relevant support for surveillance and monitoring; (d) development of communication and reporting formats and communication systems for information flow and management; and (e) designing of long-term plan for sustaining community surveillance and monitoring system beyond the project. | GEFTF BD 0.80m; LD 0.68m; SFM 0.90m | 2,382,647 | 6,665,000 |
| Component 4: Support for international cooperation and conservation and management actions informed by knowledge, awareness and monitoring and evaluation | TA/INV | Outcome 4: Implementation, upscaling and replication of project approaches supported by effective knowledge management and gender mainstreaming. Outcome indicators are: (i) At least 10 best practices of sustainable grazing and forest use, ecotourism, human-wildlife conflict management, financial instruments for livestock predation resolution, and gender mainstreaming documented and replicated in at least 5 additional valleys with non-GEF resources (ii) At least 50% of participating households (of which 40% of households include women beneficiaries) in landscapes are aware of conservation, sustainable resource use and wildlife crime prevention benefits (iii) At least 3 inter-provincial collaborative agreements negotiated, joint patrolling and information regarding poaching and IWT shared to improve species conservation and reduce poaching, and trans-boundary agreements reached with at least two neighboring countries for sharing of information on IWT and genetic composition of snow leopard populations. | 4.1 Communication, gender mainstreaming and monitoring and evaluation strategies developed and implemented at national, provincial and local levels. This will be achieved through (a) development and conduct of communication plan for awareness and outreach activities in each landscape; (b) implementation of gender mainstreaming action plan; (c) development of partnerships with the corporate sector for social responsibility; (d) awareness programs at schools and educational facilities; (e) branding of the snow leopard products and services; and (f) best practices and monitoring and evaluation data integrated into the existing database of the Snow Leopard Foundation. 4.2 Replication of project approaches by effective knowledge management and gender mainstreaming through (a) studies to identify and document gaps in the existing policies and legislative framework including wildlife crime and trade; (b) policy-level workshops and seminars; (c) technical assistance support to sector agencies to inform policy and practice; and (d) upscaling to additional valleys with non-GEF resources. 4.3 Knowledge management is coordinated with global, regional and national programs to improve cooperation and research on snow leopard conservation to be achieved through (a) improving mechanism for coordination, information sharing and collaboration at regional, national and international level to fight wildlife crime and improve species conservation; and (b) improving collaboration with information and knowledge sharing networks in neighboring countries through GSLEP and other regional programs. | GEFTF BD 0.28m; LD 0.12m; SFM 0.20m | 590,600 | 1,527,593 |
| Subtotal |  |  |  |  | 4,423,354 | 14,307,593 |
| Project Management Cost (PMC) |  |  |  | GEFTF | 221,167 | 822,407 |
| Total project costs |  |  |  |  | 4,644,521 | 15,130,000 |

- confirmed sources of Co-financing for the project by name and by type

Please include evidence for co-financing for the project with this form.

| Sources of Co-financing | Name of Co-financier | Type of Cofinancing | Amount ($) |
| --- | --- | --- | --- |
| Recipient Government | Ministry of Climate Change | In kind | 2,000,000 |
| Recipient Government | Provincial Government of Gilgit Baltistan | In kind | 6,400,000 |
| Recipient Government | Provincial Government of Khyber Pakhtunkhwa | In kind | 3,200,000 |
| Recipient Government | Provincial Government of Azad Jammu and Kashmir | In kind | 1,600,000 |
| Recipient Government | Museum of Natural History, Ministry of Science and Technology | Grant | 200,000 |
| Recipient Government | Museum of Natural History, Ministry of Science and Technology | In kind | 460,000 |
| CSO | Wildlife Conservation Society | Grant | 240,000 |
| CSO | Wildlife Conservation Society | In kind | 260,000 |
| CSO | Snow Leopard Foundation | Grant | 720,000 |
| CSO | Snow Leopard Conservancy | Grant | 50,000 |
| Total Co-financing |  |  | 15,130,000 |

- Trust Fund  Resources Requested by Agency(ies),  Country(ies), Focal Area and the Programming of Funds

| GEF Agency | Trust Fund | Country Name/Global | Focal Area | Programming of Funds | (in $) |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | GEF Project Financing (a) | Agency Fee a) (b)2 | Total (c)=a+b |
| UNDP | GEFTF | Pakistan | Biodiversity |  | 2,211,676 | 210,109 | 2,421,785 |
| UNDP | GEFTF | Pakistan | Land Degradation |  | 884,671 | 84,044 | 968,715 |
| UNDP | GEFTF | Pakistan | SFM |  | 1,548,174 | 147,076 | 1,695,250 |
| Total Grant Resources |  |  |  |  | 4,644,521 | 441,229 | 5,085,750 |

a ) Refer to the Fee Policy for GEF Partner Agencies

- Project’s Target Contributions to Global Environmental Benefits

Provide the expected project targets as appropriate.

| Corporate Results | Replenishment Targets | Project Targets |
| --- | --- | --- |
| - Maintain globally significant biodiversity and the ecosystem goods and services that it provides to society | Improved management of landscapes and seascapes covering 300 million hectares | 1.5 million hectares |
| - Sustainable land management in production systems (agriculture, rangelands, and forest landscapes) | 120 million hectares under sustainable land management | 200,000 hectares |
| - 4. Support to transformational shifts towards a low-emission and resilient development path | 750 million tons of CO2e mitigated (include both direct and indirect) | 2.96 million tCO2e sequestrated over 10-year period |
| - f. Does the project include a “non-grant” instrument? NA |  |  |  |

part ii:  project justification

A. describe any changes in alignment with the project design with the original pif

A.1. Project Description.

There are no significant changes in alignment with the project design of the original PIF. During the PPG stage, certain Outcomes and Outputs have been modified and strengthened to improve the design of the project.  These are further detailed in Section A.1. 3 and Annex E of this document.

1) Global environmental problems, threats, root causes and barriers to be addressed.

There are no significant changes from the PIF, but through the PPG process, threats, impacts, barriers presented in the original PIF are further refined and elaborated through consultations. Please refer to Section II Development challenge in the UNDP Project Document for details.

2) Baseline scenario or any associated baseline projects.

There are no significant changes from the PIF. However, Section II Development challenge, baseline scenario and Section IV Results and Partnerships of the UNDP Project Document identifies a wider range of partners that would be involved in project implementation; and in addition included baseline initiatives (with baseline budget estimates) that will contribute to the results of the project.

3) Proposed alternative scenario, with brief description of expected outcomes and components of the project

The Outcomes and Outputs of the project have been slightly modified from the PIF to provide better clarify and improved sequencing of activities.  The four project Outcomes are as follows:

Outcome 1: Improved management of snow leopard landscapes that integrates sustainable forest and land management and compatible conservation practice focuses on the establishment of coordination and governance mechanisms for landscape planning and the preparation of integrated landscape management plans for the three project landscapes; strengthening monitoring of snow leopard and associated species; and the development of a sustainability strategy to ensure replication and scaling up of project investments. The latter was included in accordance with the recommendation of STAP to specifically addresses replication and scaling up of integrated landscape models (Output 1.4).

Outcome 2: in alignment with the PIF, the Outcome focuses on expansion and strengthening of the protected area network. It entails the establishment of new protected areas to improve species conservation and connectivity; improve PA management and financial planning; strengthen capacity of field staff for wildlife management; and improve understanding of hotspots and pathways of illegal wildlife trade (IWT) to be able to better target surveillance and monitoring of wildlife crime.

Outcome 3:  Participatory conservation in the targeted landscape enhanced to reduce human-snow leopard conflicts and improve livelihoods of community, includes all activities related to community engagement. This necessitated a shift of output on preparation of 17 Valley Conservation Management Plans (moved from PIF Output 1.2 to GEF CEO ER Output 3.1) and its implementation (GEF CEO ER Output 3.2), as well as implementation of SLM and SFM practices (originally as Output 1.3 in PIF is now part of GEF CEO ER Output 3.2).

Outcome 4: Conservation and management approaches at national and international level is supported by effective knowledge management and gender mainstreaming is focuses on communication and outreach, gender mainstreaming and monitoring and evaluation.

Specific changes from the original PIF is further detailed in Annex E (Changes and Rationale for Changes from Project Information Form) to this document.

The relevance and feasibility of the proposed outcomes and outputs have been confirmed (Refer Figure 2 for Theory of Change and Section IV, Part I of UNDP Project Document) through additional expert review and through extensive consultations during the preparation phase of the project (Refer Section IV Results and Partnerships, Part (iii) Stakeholder engagement of the UNDP Project Document). Project indicators and targets have been refined to reflect on-ground practicalities and ecological considerations. The project will be implemented over a 5-year period, as against the 4-year project duration identified in the PIF.

Cost Efficiency and Effectiveness

The project is designed primarily to ensure that investments are the most cost-effective so that project approaches and institutional mechanisms can be easily replicated and scaled up using existing budgetary constraints that operate within the states and country.  Removing the barriers that impede sustainable and efficient conservation of high Himalayan areas will increase the conservation dividend of the resources and provide a real incentive for local communities to engage in sustainable management and conservation of the resource.  A number of options were considered in determining the most cost efficient approach that would be the most viable and socially acceptable. Declaring and managing the majority of the snow leopard landscape as protected areas would provide the most conservation dividend, but this was considered neither practical nor cost effective given the large dependency on grazing and NTFP collection, as well as the remoteness and accessibility for effective management. In addition, instead of investing in reforestation of Juniper forests as envisaged at the PIF stage, the project will now support community protection of existing forests and meadows (through declaration of CMCAs) as a more cost-effective measure. Similarly, given the limited budgetary and manpower resources, it would have been impractical to develop sustainable livelihoods and natural resources management interventions in all the villages that are located in the landscape within the allocations of the project.  The alternative was to seek a balanced approach to conservation and livelihood development in a limited and manageable number of villages through a multi-stakeholder and multi-sectoral institutional coordination mechanism that sought to facilitate a convergence of planning, manpower and financial resources as a cost-effective and demonstration approach with replication potential using existing state and national level budgetary resources. As a measure of cost-effectiveness and collective action, the project will enhance collaboration with CSO/NGO partners namely Wildlife Conservation Society (WCS), Baltistan Wildlife Conservation and Development Organization (BWCDO), Himalayan Wildlife Foundation (HWF); and World Wildlife Fund (WWF) to ensure sharing of responsibilities for planning and implementation of project activities. This is aimed at promoting a broad based partnership for conservation and sustainable management of snow leopard habitats at the landscape level and develop a “whole” of Northern Pakistan approach to conserving snow leopards and their habitats.  This partnership arrangement will facilitate a broad-based effort that extends beyond the project itself, bringing a range of partners and resources for collective action.

At the community level, the project will work through existing local institutions to the extent feasible, but will institute a local level planning process to plan and deliver activities that are related to community natural resource use, grazing and livestock management and community livelihood investments, as well as help coordinate other socio-economic development investments available at the provincial, district and local level and facilitate convergence through the landscape and state level coordinating committees. The planning process will be instituted under existing government policy rather than creating new systems that are not cost-effective. It will work with sectors and partners outside the conservation sector to collectively reduce threats to globally significant biodiversity by enhancing incomes and diversifying livelihoods of people in the landscapes who are currently depended on biological resources. The intent of the project is to demonstrate the viability of a multi-sectoral and integrated approach to conservation and resource use, and in the process help develop and demonstrate tools and techniques and enhance capacity in participatory conservation. This is a cost effective approach as it does not add significant additional resources to conservation, but intends to use existing national, provincial, private sector, CSOs and community resources to demonstrate a new approach to conservation that meets both conservation and local community needs and aspirations.

Sustainability and Scaling Up

The project will address sustainability as follows:

Financial sustainability will be achieved by a number of means, including: (i) through the integrated landscape and valley planning exercises, the provincial coordinating committees (that will include representative from key sector agencies) will facilitate the convergence of provincial government financial resources to support conservation and sustainable community livelihoods that would help financially sustain activities beyond the life of the project; (ii) a partnership arrangement between provincial and CSO partners within the snow leopard landscapes will ensure complementarity and cost-effectiveness of multiple partners and investments; (iii) develop new business models for landscape conservation, livelihood and value chains that recognize the full range of environmental ecosystem services provided by Pakistan’s high Himalayan ecosystems. Developing market linkages for sustainable forest and livestock products and services, ecotourism and local handicrafts and establishment of “Himalayan” labels will ensure financial sustainability of local livelihoods; and; (iv) support for establishment of valley level conservation revolving funds that will help to financially sustain and expand investments beyond the project period. Implementation of such models through carefully developed business plans could lead to a diversification of funding base from sources such as ecotourism, NTFPs and other mechanisms. In addition, the project would seek to evaluate the potential of extending the current Protected Areas Conservation Trust Fund established under a previous GEF World Bank funded Protected Area Management Project that currently operates in 3 PAs in the country (2 within Northern Pakistan), as well as potential for extending the currently very successful trophy hunting program that channels 80% of the earnings from this program to local communities. The project will work with the Provincial and National Governments to expand the successful livestock insurance scheme to non-project areas using provincial and national government budgetary support as a means to build community support for conservation of the snow leopard. These activities will result in long-term sustainability of Pakistan’s Himalayan ecosystems that currently rely on government and international donor support.

Institutional sustainability will be improved through systematic capacity development of capacity of existing public (particularly the Forest and Wildlife Departments) and civil society organizations (Snow Leopard Foundation and other CSOs that operate in the snow leopard landscapes), valley and village level institutions, other relevant sectors and the local communities in the project landscape and beyond. By engaging these stakeholders in conservation and livelihood investment planning, the project will help establish alliances for conservation and sustainable use of the high Himalayan resources that is expected to continue beyond the project period. Capacity building measures will be improved by integrating these programs into the curricula of training institutes. Carefully tailored training and capacity building to enhance the skills of the NTFP and other local producers. The project’s institutional arrangements will further help build coordination structures at the national (SC) and provincial level (PCCs) with representation from different development sectors and stakeholders (including CSOs and private sector) states and the private sector to implement joint landscape planning and to ensure that development plans mainstream biodiversity and biosecurity policies. To ensure sustainability of institutional arrangements for landscape planning and ensuring mainstreaming of biodiversity and biosecurity policies into development plans, the Government of Pakistan will work towards institutionalization of these coordination mechanisms as part of its long-term strategy to streamline and support biodiversity goals. Formalization of these coordination arrangements will enable sustaining and scaling up of benefits of the project in terms of landscape planning and management and biodiversity mainstreaming.  The implementation of the project through SLF (and its partnership arrangements with other CSOs) will further strengthen this arrangement.

Social sustainability will be improved through the development/strengthening of stakeholder participation mechanisms for the target snow leopard landscapes. A Knowledge Management and Communication strategy has been developed to facilitate awareness and enhance stakeholder participation. Frameworks for Participatory Landscape Conservation (Annex 3 of UNDP Project Document) and Valley Participatory community planning (Annex 5 of UNDP Project Document) was designed during PPG stage to ensure adequate consultation and participatory decision making to ensure that project activities are detailed in collaboration with local communities, so that extensive consultation including all affected groups is undertaken prior to delineation of areas to be set aside, so as to avoid excessive community resource use areas or to improve the management of such uses.  Social sustainability will also be achieved by strengthening community institutions, ensuring their active participation in planning and implementation of conservation and sustainable natural resources management, improving community capacity for management of valley conservation plans and for improving grievance redressal mechanisms that will ensure social sustainability.

Environmental sustainability will be achieved through a coordinated approach involving improved protected area management approaches; sustainable natural resources and pasture management; securing improved forest restoration and sustainable NTFP use;  improve incentives for conservation and community participation. It would also help reducing external threats on PAs and wildlife through landscape level partnerships; enhance controls on the wildlife trade and poaching; and improve inter-provincial and transboundary collaboration. This work at landscape level is aimed at ensuring environmental and socio-economic sustainability through improved institutional capacity, policies and legislation.

Innovation: The project design is innovative in several ways. First, it proposes to pilot the first program in Pakistan for integrated planning and management of snow leopard landscapes and to mainstream biodiversity conservation outcomes into sectoral planning.  This approach would involve multi-stakeholder planning and inter-sectoral coordination approach to landscape level. A landscape would be viewed as a system in itself, comprised of various natural, cultural and socio-economic components. In turn, it is part of the bigger national, regional, thematic, and global networks of BRs; (ii) The snow leopard landscapes would be appropriately re-zoned by ecological-based planning using a patch-corridor-matrix model for biodiversity conservation, taking account of landscape ecology, inter-connectedness, vegetation zoning, regional land-use planning, nature and cultural landscape integration, etc. (i.e. landscape planning); (iii) bringing actors from the provinces, development sectors and civil society sectors together to achieve mutual understanding and negotiate and implement mutually agreeable plans, combining top-down and bottom-up approaches and promotion of community participation (i.e. intersectoral coordination); and (iv) promoting a conservation-based economy in landscapes, with value creation and increased economic benefits for local people; labelling of goods and services from landscapes (e.g. tourism products and services; sustainable agricultural products; NTFPs, etc.); consumption and production in line with sustainable development; fair distribution; and awareness of conservation of nature and culture. Lessons learned on collaboration with the tourism sector can be shared with other BRs in the region. Secondly, it is innovative because it would seek to link “set-asides” or new conservation areas (CMCAs) and forest restoration as part of a larger effort to improve biodiversity conservation outcomes in HCVFs and improve connectivity of individual parts of the landscapes. Thirdly, it would develop and test sustainable financing mechanisms at the local level (valley level) to improve incentive for community engagement in conservation, including establishment of community revolving funds, tourism concession fees, accommodation surcharges, etc.).

Scaling-Up: The project is designed to provide demonstration models for up-scaling in Pakistan. In particular, the capacity building and the development of guidelines and regulations for each aspect of the project will strongly support up-scaling. By communicating and disseminating project’s results widely, will help in generating demand for similar initiatives in the country. The involvement of NGOs and the private sector (particularly in ecotourism development, value addition and marketing of forest-based and agricultural products) can lead to further up-scaling of the project’s intervention. Improvement in capacity, awareness and regulatory framework will ensure post-project sustainability and encourage investments from public and private sector and hence, can contribute to up-scaling. The project anticipates close collaboration with CSOs, NGOs and Provincial agencies to further replicate participatory models in at least 5 additional valleys beyond the 17 proposed under the project as a means to test replication and scaling up models.

The practicability of replicating landscape conservation and livelihood models, governance and capacity building programs will be the basis for the success of this project. The project’s approach of integrated conservation and livelihood planning and management including the introduction of new planning and monitoring guidelines specifically for sustainable pasture and forest management will provide the basis for application in other regions of the country as well. The project will introduce a participatory planning process by engaging community members and tapping into their local knowledge. Hence, the process will enable the project to test the acceptability and replicability of such models elsewhere in the country. The Project’s investment component will seek to develop synergies among rural development actors and programs with an objective of raising additional investments that will fund and expand models of resource use and alternative livelihood activities within and outside of the targeted landscapes. This component will also seek to catalyze a process whereby regional and local NGOs, CSOs and forest and wildlife development agencies seek to obtain commitments from provincial budgets for sustainable resource management and related community actions.

On a national level, best practices from this project will be replicated in other parts of snow leopard range in Pakistan, as well as applied to other wildlife conservation activities. Many of the proposed innovative activities in this project aimed at reducing threats to snow leopard, including livestock insurance, vaccination programs and corral improvements are highly scalable. Lessons learned through the project’s on-the-ground and landscape level interventions in the target ‘model’ landscapes will be used to promote replication and scaling of the interventions at the national, regional and global levels through knowledge management and dissemination (Component 4). Pakistan’s engagement in the GSLEP through its commitment to the international standards in the monitoring and research of snow leopard, as well as by participating in high level negotiations on the future policy improvements aiming at conservation of this species will ensure sustainability of the results.

In summary, it can be clearly stated that the long-term sustainability of these approaches are assured considering the level of commitment at various levels of the government, community and CSO partners with programs and resources committed to the high Himalayan landscapes. The promotion of value chains and market driven approach to create sustainable solutions can outlive the life of the project. The project’s focus on developing business models that will allow local farmers and other inhabitants to participate and benefit from the economic systems - that facilitates productive enhancement and marketing, promotes local entrepreneurs, and development of ecotourism potentials to become tourist hubs and use local resources to develop products such as handlooms, crafts, etc. The project includes a specific Output (1.4) to facilitate replication and scaling up of project approaches.

4) Incremental/additional cost reasoning

There are no changes from the PIF in the incremental reasoning. Baseline projects as well as other contributions to the project´s baseline and co-financing are given in UNDP Project Document Section IV (Results and Partnerships) for each project component, and Section IX (Financial Planning and Management).

The indicative co-financing for the project has been confirmed, reaching a slightly higher total (USD15.08 million) from the PIF targets (see Table C above). Significant parallel co-financing investments have been proposed by the key partners (including provincial governments) to all four components covered by the project (integrated landscape planning and management, PA expansion, participatory conservation and knowledge management and gender mainstreaming). These investments will mainly be allocated to complementary activities related to forest conservation and management; community development; sustainable management of pastures and livestock development. In addition, in-kind contributions have been assigned to meet staff cost for activities such as - coordinating committees; staffing of conservation areas; monitoring and assessment; institutional information management; project monitoring and evaluation; and project management.

GEF resources will be used to address efforts in developing an enabling framework for - integrated landscape planning and management approach in the snow leopard areas; development of plans and strategies that aim to strengthen inter-sectoral coordination; engagement of stakeholders at all levels from local to provincial in planning and sustainable resource uses; capacity development for provincial government and key sector agencies;  promotion of sustainable livelihood practices; extension of the PA system and improvement of PA management effectiveness; and provision of information systems, spatial analysis and decision support tools. This will be done through the provision of incremental funding to add on to investments already being made by the project partners. The project preparation phase has engaged key stakeholders in developing a shared vision and initiated steps towards the removal of barriers for effective implementation.

5) Global Environmental Benefits.

The project centers on the conservation of snow leopard, and key ecosystems and landscapes of global value including the Pamir-Karakoram which has been proposed as a UNESCO Biosphere Reserve. The Karakoram Mountains harbors the most heavily glaciated part of the world outside the Polar Regions. Indus Flyway and adjacent high altitude lakes, streams, marshlands, peat lands and bogs are used as temporary and permanent staging, feeding and breeding grounds by migratory water birds, including several endangered aquatic bird species. The project will also benefit other significant and threatened species, including globally endangered musk deer and key prey species such as near threatened markhor. The project will directly result in securing 3 snow leopard landscapes covering an area of about 6 million hectares, and improve the national ecological infrastructure of Pakistan through training and capacity building of PA staff, improved coordination across government sectors via cross-cutting management planning, and improved resources and knowledge base for effective decision-making.

| Summary of baseline scenario | Summary of GEF Scenario |  |  | Increment |
| --- | --- | --- | --- | --- |
| Sustainable landscape planning and management |  |  |  |  |
| -Lack of landscape-level approach that provides for effective conservation of large ranging globally endangered snow leopard, resulting in fragmentation, increasing threats and degradation of land, forest and other natural resources on which communities rely for their livelihoods. -Communities living in valleys surrounding PAs, corridors and buffer zones lack capacity to implement SLM and SFM technologies and define sustainable resource use, resulting in degradation and over-exploitation of natural resources. |  | -Comprehensive landscape management plans for three model landscapes developed along with valley plans that integrate sustainable forest and land management practices and snow leopard conservation compatible practices. - Appropriate SLM and SFM technologies implemented within Community managed conservation areas adjacent to existing PAs. | -Landscape management strategies developed covering 6 million ha of key habitat for globally endangered snow leopard that integrate - sustainable forest and land management and snow leopard conservation compatible practices. LD Benefits Competitive pressures on 190,000 ha in sub-alpine and alpine meadows of important Snow Leopard ecosystems (established within 200,000 ha of new and existing CMCAs) reduced through improved community protection and herding practices indicated by: i) reduced land degradation (measured by improved condition of vegetation in currently degraded areas); ii) maintenance of ecosystem services (e.g. increased carbon sequestration of 2.96 million tCO2e sequestrated over 10-year period) through sustainable management of 10,000 ha of sub-alpine forests and 190,000 ha of sub-alpine and alpine meadows within critical snow leopard habitat set-aside of 200,000 ha as community managed conservation areas (CMCAs) |  |
| PA expansion and strengthening |  |  |  |  |
| -Current PA network alone is not adequate to conserve viable populations of snow leopard. Gaps exist, particularly in representation of forests. -No assessment of management in the current PA system to ensure they are working effectively or efficiently. -Forest and wildlife managers lack capacity to apply, monitor and enforce sustainable landscape management measures. |  | -At least 200,000 ha of priority snow leopard habitat identified, mapped and submitted for gazettement as PAs (CMCAs) to improve connectivity -PA management and financing plans for new and existing CMCAs are developed/aligned and operationalized. -At least 200 forest and wildlife managers (PA staff and community organizations) trained and equipped for monitoring and enforcing application of sustainable management measures that span inside and outside PAs for integrated, landscape-level coverage. |  | BD and SFM Benefits Increased representation of snow leopard habitat in the PA network, and avoided loss of 200,000 ha of priority Snow Leopard habitat Increased management effectiveness of existing National Parks (measured by METT). Enhanced capacity of key local stakeholders including wildlife managers and local communities on assessment, monitoring and enforcement of sustainable snow leopard friendly forest and landscape management practices. |
| Human-Snow Leopard conflict management |  |  |  |  |
| -Insufficient involvement and support of local communities towards conservation solutions -Lack of social safety nets and workable strategies to protect livelihoods and/or compensate for wildlife-caused damages -Threats to snow leopards in terms of retribution killing and/or poaching of snow leopard and wild prey -Lack of understanding among local people towards the importance of protecting endangered wildlife as important towards overall environmental health |  | -Livestock insurance schemes established to reduce predation-related economic burden on communities -Improvements made to existing corrals to reduce predation losses -Livestock vaccination schemes implemented to reduce mortalities in livestock -Improved livestock herding practices -Enhanced education efforts implemented to increase awareness and enhance tolerance towards snow leopards and reintroduce traditional values towards forest management |  | BD Benefits Reduced threats to globally endangered snow leopard as indicated by: number of snow leopards and other key wildlife (e.g. Musk deer, Markhor, Himalayan Ibex, Blue Sheep, Ladakh Urial, Brown Bear and other species) remain stable or increase; Local communities better off as result of enhanced measures, indicated by: at least 15% increase in income of participating households from schemes such as livestock insurance, improved corrals, vaccination, and improved livelihoods Reduced threats to globally endangered snow leopards as evidenced by: (i) reduced incidences of retaliatory killings; (ii) local communities’ attitude towards Snow Leopards and ecosystem conservation are positive; (iii) reduced incidences of poaching and illegal wildlife trade. |
| Knowledge management and international cooperation |  |  |  |  |
| -Systematic field-based research in northern Pakistan is extremely limited -Baseline information for conservation planning is lacking, limiting ability of wildlife managers, forest managers, and conservationists to efficiently and effectively target solutions and develop programs to address current and emerging threats, including climate change. - International cooperation on snow leopard conservation identified as priorities for Pakistan under the Global Snow Leopard Ecosystem Programme, but not yet fully advanced. |  | -Systematic surveys completed for snow leopard and wild prey in model landscapes -Assessment of status of existing Snow Leopard ecosystems in Northern Pakistan -Improved database platform for consolidation of new and old data -Monitoring system for rehabilitating/restoring rangelands within snow leopard habitats developed -Vulnerability of snow leopard ecosystems to the effects of climate change assessed -Targeted support to participation of Pakistan in the Global Snow Leopard Ecosystem Protection Plan process. |  | Enhanced scientific knowledge on snow leopards, prey species, and habitat leads to better conservation and management decisions and improved stewardship of globally endangered SL and their ecosystems. Effective development of mechanisms and improved capacities for inter-provincial and international cooperation on snow leopard conservation, control of illegal trade and improved information management. Enhanced scientific knowledge used to guide and improve conservation of wildlife, forests, and rangelands in northern Pakistan Knowledge management improves replication of valley conservation efforts in 5 additional valleys with non-GEF funding |

# A.2. Child Project.	N/A

A.3.  Stakeholders. The project conducted a thorough consultations with relevant stakeholders both at the PIF and during the design of the project. During the PPG stage, the stakeholder analysis was updated and elaborated following consultations undertaken by international and national consultants at the landscape sites and with the provincial governments addressing both institutional stakeholders in the context of their statutory involvement in the project, and more broadly for non-governmental stakeholders including NGOs and natural resource dependent communities. Stakeholder workshops were conducted at the provincial level from April-June 2017 to obtain the perspective of different stakeholders and, a national validation workshop in Islamabad on July 13, 2017 to discuss the project design and obtain consensus on project outcomes, outputs, activities and institutional arrangements for the project. The list of stakeholders consulted and report is annexed separately (Annexes 26 and 29 of UNDP Project Document).

Identification of Potential Stakeholders and taking their views

The SIP was prepared through the identification of the stakeholders at national, provincial, district and local levels including CSOs and local communities who would be involved as partners in project implementation. Thorough consultations were conducted to incorporate stakeholders’ views, interests and concerns into the development of the project components, outcomes, outputs, project sites, implementation mechanism and other relevant issues. Moreover, it involved analyzing whether key stakeholders are willing and able to engage in a joint, collaborative process (which also include joint fact finding, dialogue, negotiation, social mobilization and preparation of plans) for project implementation and to resolve the issues.

Role and responsibilities of key stakeholders and their Involvement Mechanisms and Strategies

Mechanisms and strategies for stakeholder involvement will ensure that the relevant shareholders receive and share information and provide their inputs in the planning, design, implementation, monitoring and evaluation of project initiatives and play a role in sustaining the initiatives during and after the closure of the project. It describes the process of representation of stakeholders in the project steering and coordination committees, identification of their decision-making authority, resources needed by the stakeholders and how these will be arranged. Roles and responsibilities of key stakeholders of the project are summarized in the stakeholder involvement plan (Table 4 of stakeholder engagement in the UNDP project document).

A.4. Gender Equality and Women's Empowerment.  Gender analysis has been conducted, and gender considerations have been integrated into the project design and the Gender Analysis and Mainstreaming Action Plan (Please refer to Annex 9 of UNDP Project Document). The landscape planning component will have significant long-term impacts on both gender and social groups, and thus the Gender Mainstreaming Action Plan includes specific actions for applying a gender and socially inclusive lens to every decision, expanding representation, filling in gender and social-based research gaps, and investing in approaches to gather and share information among major groups. It is the intent of this project to be a model for improving gender and social mainstreaming into government and planning processes. In particular, the project has taken into consideration gender in the design of this project and it will be mainstreamed into its implementation as outlined in table below:

Proposed Gender Mainstreaming Actions for Project Implementation

| Gender Mainstreaming Objective | Gender Mainstreaming Activity | Gender mainstreaming Target |
| --- | --- | --- |
| To strengthen women based institutions and ensure women’s participation and leadership | Support to strengthen Community Conservation Committees, community/village organizations and valley conservation committees and district conservation committees ensuring women participation. In some cases, it would entail establishing separate women community-based committees with the village to facilitate work that are largely women’s responsibility, as well as set up women’s self-help group | At least 40% of project beneficiaries are women in the target households and these are associated with community-based institutions and participate in the project initiatives. Thi will include in some cases establishing separate women community-based committees. |
| Improve understanding of gender issues, capacity building needs of women and policy issues | Support action research to identify the issues related to gender so that capacity building and policy interventions can be planned in a specific manner. | Specific gender related issues and capacity gaps are identified and taken up as part of the planning process in all the three landscapes of the project. |
| To enhance capacity, skills and competence of women in technical aspects related to conservation and livelihood promotion | Technical training programs, study tours/exposure visits and other skills development activities involving women | At least 30% of technical and front-line staff and women leaders of grassroots institutions are trained. |
| To reduce drudgery of the women and enhance conservation through technological interventions | Promote fodder demonstration plots and fodder seed banks, soil and water conservation, forest trees plantation, improvement of grasslands near to the houses, etc. | Drudgery of at least 25% of women members of CBOs reduced due to project interventions |
| To promote pro-women livelihood activities, alternative technologies to improve environment, biodiversity and health of women | Focus on women-dominant livelihoods and value chain activities like snow leopard enterprises, livestock management, home gardens, on-farm water management, sea buckthorn and ecotourism activities. | At least 5 alternative technologies introduced to reduce the workload of women, improve environment and household income. |
| To monitor and evaluate women’s participation and their empowerment through the project interventions | Incorporating gender-sensitive indicators and collection of sex-disaggregated data for monitoring and evaluating project results | Gender disaggregated data included in monitoring and evaluation formats of the project interventions. |
| To enhance role of women in project implementation. | Engaging local women community mobilizers for social mobilization to encourage greater participation of women from local communities | At least 30% of the community mobilisers engaged in the project are women, preferably locals. |
| To enhance awareness about access and ownership of land and other productive resources by women | Interventions to enhance awareness related to policy issues through communication strategy and knowledge sharing initiatives | At least 30 % women members of CBOs among the target households are aware of their rights and contribute to the policy issues |
| To ensure high participation of women in project activities through innovative communication strategy and methods | Including specific efforts to encourage women’s role in outreach and communication strategy of the project Keeping gender focus in awareness and communication campaigns | At least 50 % of the communication methods used in the project will be focused towards women |
| Improve women’s role in decision-making | Promote adequate representation and active participation of women decision-making bodies. | At least 25% women representation in project specific committees at landscape, valley & grassroots levels or separate women committees at valley or village level |

# A.5 Risk. The main risks and mitigation measures have been further elaborated from the PIF. Please refer to Section V Feasibility, Part (ii) Risk management of the UNDP Project Document. As per standard UNDP requirements, the Project Manager will monitor risks quarterly and report on the status of risks to the UNDP Country Office. The UNDP Country Office will record progress in the UNDP ATLAS risk log.  Risks will be reported as critical when the impact and probability are high (i.e. 5). Management responses to critical risks will also be reported in annual Project Implementation Reports. Updated project risks are reflected in the Table below:

Risk Management Matrix

| Project Risks |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Description | Type | Impact, Probability and Risk Level | Mitigation Measures | Owner | Status |
| Risk 1 - Conflicts between public institutions and local communities regarding access to natural resources, including pasture resources. | Social | P3, I3 | Restrictions, if any, on access and use of resources would not be imposed on communities, but evolve through a collective decision-making process and complemented by alternative livelihoods and resources measures to compensate for such losses. A grievance redress system will also ensure that any conflicts are addressed and amicably settled (refer Section (V) Part (iii) Social and Environmental Safeguards of UNDP Project Document regarding grievance redress procedures | NPM (SLF) | Implementation phase |
| Risk 2: Lack of capacity in government and communities to meet obligations related to project | Institutional/ Operational | P3, I3 | Capacity need assessment of government and local communities will inform project on capacity development needs. Training activities will be tailored to meet specific requirements of the different stakeholders to ensure that they have the skills to participate in relevant aspects of the project. Communities participating in the livelihood, sustainable natural resource management and wildlife monitoring activities will be provided training, and training programs would be evaluated and adjusted as appropriate to ensure their effectiveness. | NPM (SLF) | Planning and Implementation Phase |
| Risk 3: Limited capacity within Snow Leopard Foundation as Executing Agency to manage risks associated with the project | Institutional | P2, I 3 | The SLF has been in the project landscapes since its inception in 2008 on conservation, capacity development and HWC management and has been rated as “Low risk” for implementation of the project by EY Ford Rhodes on behalf of UNDP. Further, SLF project activities are being supported by (i) high level National and provincial level coordinating committees that are chaired by senior government officials that will provide oversight and serve as advisory role to SLF; (ii) forest and wildlife staff are part of the project landscape planning and implementation teams to support SLF; and (iii) MOUs will be signed with provincial wildlife departments and other CSOs to share implementation responsibilities as a measure to manage any risks. These CSOs will undertake specific activities in selected valleys | MOCC and Provincial Governments (through the National and Provincial Coordinating Committees | Implementation Phase |
| Risk 4: The spread of the project landscapes across mountain areas of three provinces and many districts may cause coordination difficulties affecting implementation and hinder landscape approach to biodiversity conservation. | Operational | P2, I3 | This risk will be managed by establishing specific landscape planning and implementation teams for each valley and involving a range of local stakeholders in establishing/strengthening district and valley conservation committees and developing communication strategy. | NPM (SLF) | Implementation phase |
| Risk 5: Intra and inter community conflicts and conflict between public institutions and communities for natural resource use may hamper landscape level management planning process | Social | P2, I2 | Training of the staff and community representatives in conflict management and promoting collective decision making process by engaging all potential stakeholders and making the community realize that their resource use rights will remain intact. Further, compensating the resource loss, if occurred, through alternative livelihood and resource measures as indicated in Outcome 3 of the project. | NPM (SLF) | Implementation phase |
| Risk 6: Indigenous people and vulnerable groups may be excluded from participation in project planning and investments related to livelihoods and sustainable use practices | Operational | P3, I3 | Participatory process indicated in the project document will ensure that all households in village/valley (including indigenous and vulnerable people) will be part of the investment planning, be trained and have capacity for implementation of livelihood activities and benefit directly from project activities | NPM (SLF) | Planning and Implementation Phase |
| Risk 7: Efforts to engage women folk in the project activities may be resisted by the communities, resulting in gender bias and insufficient focus being given to the needs and priorities of women. | Operational | P3, I3 | Focus activities initially in those areas where gender relations support women’s involvement in planning and management, and where actively functioning women organizations exist. Where possible the project will ensure to establish separate women conservation committees as well as promote specific livelihood options for women with the intent of strengthening women’s participation. The success of such efforts may in turn serve as a catalyst for work in other areas. A gender analysis and mainstreaming action plan (Annex 9) prepared for the project will be implemented | NPM (SLF) | Planning and Implementation Phase |
| Risk 8: Natural disasters and climate change may affect the implementation and results of project initiatives | Environmental | P2, I2 | Measures to reduce impacts of natural disasters and climate change will be initiated, including improved water management, soil and water conservation, crop and livelihood diversification, and training in risk management (refer Annex 5 Valley Level Participatory Community Planning Framework and Annex 7 Indicative list of possible valley conservation plan investments and livelihoods) | RPM (SLF) | Planning and Implementation Phase |
| Risk 9- Long gestation periods for alternative livelihoods, value chain activities and restoration of pasture resources can undermine community participation | Operational | P2, I2 | Valley Conservation Plan activities will entail a menu of options (including activities with short-term gestation periods as buffer until longer-term investments generate sustainable benefits) to help diversify the livelihood and resource base, including linkage with on-going governmental and NGO programs to supplement and complement project activities. | RPM (SLF) | Planning and Implementation Phase |

Green: Low Risk; Yellow: Moderate Risk

A.6. Institutional Arrangement and Coordination.   Please refer to Section VIII Governance and Management Arrangements and Annex 14 of the UNDP Project Document for further details.

The Implementing Partner for this project is Snow Leopard Foundation (SLF) in cooperation with Ministry of Climate Change (MoCC). The Implementing Partner is responsible and accountable for managing this project, including the monitoring and evaluation of project interventions, achieving project outcomes, and for the effective use of UNDP resources. Capacity assessment of SLF was undertaken during the project preparation, and the overall risk rating was identified as ‘low’.  A standard Project Cooperation Agreement (PCA) will be signed with SLF constituting the legal agreement between UNDP and SLF on the implementation of the project. SLF will work very closely with the provincial government agencies during the implementation of the project, ensuring that technical and extension support are solicited from the respective provincial government agencies.  This agreement and the roles and responsibilities of the respective Provincial Wildlife Departments have been agreed to (during the numerous national and provincial consultations at PPG stage) and will be formalized through Memorandum of Agreements that will be signed before the project inception workshop. Contractual agreements will be executed between SLF and the 4 CSOs/NGOs (namely WCS, BWCDO, WWF and HWF) to implement project interventions on-the-ground in the 10 valleys out of the 17 valleys identified for project intervention. MoUs will be agreed and finalized before the project inception workshop.

# The Project Board will be chaired by the Secretary, MoCC. The Board will have high level cross-sectoral representation including representatives from MoCC. As the key governmental agency in charge of natural resources and environment, MoCC will ensure that other governmental ministries are duly consulted and involved as per their mandate (such as the Ministry of Planning and Development, Ministry of Finance, and Ministry of Science and Technology). The Board may also include representatives of participating provinces, in particular its Departments of Planning and Development, and Department of Forest/Wildlife, non-government organizations, experts and community representatives.

- The National Program Management Unit (PMU) will be established in the Snow Leopard Foundation. It will comprise of a National Program Manager (NPM), Finance and Admin Officer, Finance and Admin Assistant and Office Assistant. The PMU in collaboration with the MoCC and Landscape Coordination committees will have overall management and administrative responsibility for facilitating stakeholder involvement and ensuring increased provincial level ownership of the project.  The PMU staff will be located in Islamabad to ensure coordination among key stakeholders at the federal level and with provincial Forest and Wildlife Departments supported by the Landscape Coordination Committees during the project period.

- Each province will establish a Provincial Coordinating Committee that will be chaired by the Additional Chief Secretary (Development)/Secretary (Planning and Development Department) in GB and AJK, whereas the District Nazim will Chair the committee in Khyber Pakhtunkhwa as the project will cover part of Chitral district. Its composition may include relevant line departments and key NGOs working in the area, Secretary of committee will be Regional Project Manager of Snow Leopard and Ecosystem Protection Program.  Through the Provincial Coordinating Committees, the Provincial Governments will play a central role in advising, overseeing, planning and monitoring project activities as well as in facilitating coordinating development activities with relevant sector agencies in the snow leopard landscapes. It will guide and oversee the implementation of the project, approve work plans, monitor progress and manage any risks associated with SLF implementation.

- At the provincial level, oversight and coordination will be the responsibility of a Regional Program Manager of the Snow Leopard Foundation. At the landscape level, there will be a Landscape Planning and Implementation team (LPIT) consisting of a Landscape Planning Facilitator on full time basis supported by Social Organizers, Natural Resource Management Specialist and Livelihood/Participatory Specialist (consultants). Forest and Wildlife Rangers will be part of the Landscape Level Planning and Implementation teams while the interventions are undertaken in the areas under their respective jurisdictions. The forest and wildlife staff will guide the identification of CMCAs, revision of CMCA management plans, support livestock-wildlife conflict resolution and support the implementation of predator proof corrals, livestock insurance schemes and community based surveillance and monitoring of wildlife poaching and illicit wildlife trade. In addition, sector agency technical staff at the Tehsil (sub-district) level will be engaged as and when required to provide technical and extension support for planning and implementation of Valley Conservation Plans.  The LPITs will be responsible for planning, implementation and the monitoring of valley conservation plans. Valley Conservation Committees will be involved in the planning and implementation of the valley conservation plans.

# Additional Information not well elaborated at PIF Stage:

A.7 Benefits. The socio-economic benefits of the project will be seen at the individual household and at the collective community level through the community groups like livestock groups, self-help groups, producer groups and cooperatives in the following manner:

- At least 4,000 households in 17 valleys to be targeted by the project will directly benefit through improved livelihoods and incomes.  (This is based on a figure of 1/3 of total number beneficiary households within the valleys).

- As a result of participatory landscape management processes and related project investments, about 25,000 people (about 40% women beneficiaries) will directly benefit from improved management of the project landscapes and the sustainable management of natural resources.

- Implementation of valley conservation plans will result in improved agriculture, pasture and livestock management practices, better water conservation and management and improved livelihood and value chain products and services. This will collectively result in better conservation and livelihoods outcomes.

- Improved access to basic goods and technical services, technology and improved grazing and pastoral practices - a shift from extensive low nutrition productive systems to semi-intensive high nutrition ones, as well as the complementary diversification of livelihoods in agriculture and non-farm sector including tourism and agri-based products will ensure more livelihood options and better prices and income for the community in the target landscapes.

- An increase in community incomes from sustainable livelihood activities (calculated for each community) of around 15% wherein around 30% of beneficiaries will be women;

- Reduction of livestock losses from predation by around 25%;

- The focus on addressing gender inequality through various initiatives such as technological interventions for drudgery reduction in livelihood and household based activities, promotion of alternative energy options like solar cookers, LPGs etc., fodder plots and fodder banks, participation of women in conservation committee and strengthening of SHG are proposed. The project envisages more gender equality in context of sex ratio, decision making powers, ownership and control of resources, reduction in drudgery as well as working hours of women and women leadership, and participation. At least 30% women participation in the conservation committee will be ensured in the project, or a separate women conservation committees will be established to address the specific needs of women;

- A reduction in the natural resource conflicts and increase in effective implementation of sustainable practices. There will be at least 10 such practices that would be forthcoming from the project for potential replication within and outside the participating landscapes;

- Incremental funding from existing government and local development programs and also linkage with other funding sources will improve sustainable natural resource outcomes and improvement in livelihoods and incomes, thus resulting in sustainability of such investments beyond the life of the project.

- Enhanced community participation in wildlife crime monitoring and surveillance in community battalions (At least 60 persons participating);

- Reduced human-wildlife conflicts leading to reduction in retaliatory killing of snow leopards and other species;

- Stable or improved populations of snow leopard (by reducing competition for habitat and snow leopard prey species) and improved conservation management practices.

A.8 Knowledge Management.

The project has a knowledge management component to ensure special emphasis is paid to delivering effective outreach and communications campaigns; training and education to strengthen awareness and support for landscape conservation; reducing unsustainable livestock grazing and forest product extraction practices; improving awareness and prevention of human-wildlife conflict; reducing wildlife related crime and illegal trade. The project has developed a communication strategy that will be tailored to each landscape and implemented adopting user-friendly outreach materials like posters, booklets and other products to communicate key information to target audiences. The project will establish a social media platform to promote interactions with stakeholders (on project related activities such as workshops, trainings, community outreach). Members of the national and provincial level coordination mechanisms established through the project will be encouraged to take a lead in participating and sharing information widely. Well recognized communication/media firms will be hired for the design and implementation of provincial-specific communication plans. Knowledge management materials and products will facilitate replication of valley conservation plans to 5 additional valleys with non-GEF funding. Refer Outcome 4 of the project and Annex 12 in the UNDP Project Document for further details of the knowledge management and communication activities that will be supported under the project.

B. Description of the consistency of the project with:

B.1 Consistency with National Priorities. Sustainable natural resource management, benefit sharing, and biodiversity conservation are the cornerstones of the proposed project and they are recognized as crucial elements by Pakistan's policies for sustainable development. The "Vision 2030" elaborated by the Pakistan Planning Commission in 2007, aims for equitable sharing of environmental benefits, increasing community management of national resources, and integrating environmental issues into socio-economic planning to achieve sustainable development. Pakistan's National Conservation Strategy (1992) recommends measures for sustainable management of wildlife and habitat, by emphasizing (a) the introduction of incentives to safeguard conservation areas and divert pressures on threatened wildlife habitats and species, (b) promotion of community-based management systems so that local people participate in the protection and conservation of habitats and related species, (c) enforcement of existing legislation strictly in support of ecosystem protection and wildlife conservation.

In addition, the project will contribute to achievement of Aichi Targets, in particular under the strategic goal B: Reduce the direct pressures on biodiversity and promote sustainable use:

- Target 5: By 2020, the rate of loss of all natural habitats, including forests, is at least halved and where feasible brought close to zero, and degradation and fragmentation is significantly reduced;

- Target 7: By 2020 areas under agriculture, aquaculture and forestry are managed sustainably, ensuring the conservation of biodiversity;

- Target 11: By 2020, at least 17 per cent of terrestrial and inland water, and 10 per cent of coastal and marine area, especially areas of importance for biodiversity and ecosystem services, conserved through effectively and equitably managed, ecologically representative and well-connected systems of protected areas and other effective area-based conservation measures, and integrated into the wider landscapes and seascapes.

Being signatory to the Convention on Biological Diversity, Pakistan developed a Biodiversity Action Plan (BAP, 1999), which has been updated as the National Biodiversity Strategy and Action Plan (NBSAP) in 2015).  In order to address geographic variation in biodiversity potential and challenges, the two provinces of KP and GB have recently drafted provincial biodiversity strategies and action plans (Khyber Pakhtunkhwa (KP)–Biodiversity Strategy and Action Plan (BSAP) 2016 and Gilgit-Baltistan (GB) -BSAP 2016).  These are important policy instruments to conserve biodiversity in the country. The project’s Component 1 & 2 are built on: targets 11 and 14 of the NBSAP; targets 11-12-14 of KP-BSAP; and targets 1-3 of GB-BSAP. The PA expansion and strengthening activities in the proposed project cover 10 PAs identified in NBSAP/KP-BSAP/GB-BSAP (Ghamot NP, Musk Deer NP, Desoai NP, Central Karakoram NP, Khunjerab NP, Qurambar NP, Broghil NP, Chitral Gol NP, Shandoor and Kalash Areas).  The snow leopard is identified as an important target species for recovery under NBSAP/KP-BSAP/GB-BSAP. Therefore Component 3 supports target 12 of NBSAP and KP-BSAP, and target 4 of GB-BSAP as it entails measures to conserve 14 important fauna specie (Brown bear, black bear, Himalayan lynx, grey wolf, Eurassian otter, wooly flying squirrel, Kashmir flying squirrel, grey langur, common leopard, Marcopolo sheep, blue sheep, ladakh urial, markhor, musk deer) and 8 flora specie (Juniper, kuth, Nag chhatri, marsh orchid , aconite, Himalayan mayapple, Primula, gugul), besides recovery of the snow leopard.  The environmental education (EE) program proposed under Component 3 of the project is in line with target 1 in NBSAP/KP-BSAP. The knowledge enhancement on snow leopard and ecosystems under Component 4 of the project supports target 19 in NBSAP/KP-BSAP, and targets 2 of GB-BSAP.  Component 3 also addresses target 5 of KP-BSAP, which aims at reducing pressure on biodiversity and loss of habitat.

The project is also consistent with the recommendations of the GSLEP and has been designed to respond to the four-year National Strategy and Action Plan for the Conservation of Snow Leopard (2014–2020), including the following critical areas for intervention: reducing habitat loss and degradation; reducing livestock impact on wild prey base; reducing retaliatory killing of snow leopard; improving institutional capacity; improving awareness; and addressing climate change.

The project will also contribute to achieving the following Sustainable Development Goals (SDGs) in Pakistan:

- Goal 2: end hunger, achieve food security and improved nutrition and promote sustainable agriculture

- Goal 15: to protect, restore and promote sustainable use of terrestrial ecosystems, sustainably manage forests, combat desertification, and halt and reverse land degradation and halt biodiversity loss.

- Target 15.4: By 2030, ensure the conservation of mountain ecosystems, including their biodiversity, in order to enhance their capacity to provide benefits that are essential for sustainable development

- Target 15.5: Take urgent and significant action to reduce the degradation of natural habitats, halt the loss of biodiversity and, by 2020, protect and prevent the extinction of threatened species

- Target 15.7: Take urgent action to end poaching and trafficking of protected species of flora and fauna and address both demand and supply of illegal wildlife products

- Target 15.9: By 2020 integrate ecosystem and biodiversity values into national and local planning, development processes, poverty reduction strategies and accounts

- Target 15.c: Enhance global support for efforts to combat poaching and trafficking of protected species, including by increasing the capacity of local communities to pursue sustainable livelihood opportunities

C.  Describe the budgeted m &e plan:

| GEF M&E requirements | Primary responsibility | Indicative costs to be charged to the Project Budget (US$) |  | Time frame |
| --- | --- | --- | --- | --- |
|  |  | GEF grant | Co-financing |  |
| Inception Workshop (one national and 3 provincial) | UNDP Country Office | 6,000 | 5,000 | Within three months of project document signature |
| Inception Report | Project Manager | None |  | Within two weeks of inception workshop |
| Standard UNDP monitoring and reporting requirements as outlined in the UNDP POPP | UNDP Country Office | None |  | Quarterly, annually |
| Monitoring of indicators in project results framework | M&E Specialist | 20,000 | 50,000 | Annually |
| GEF Project Implementation Report (PIR) | Project Manager and UNDP Country Office and UNDP-GEF team | None |  | Annually |
| NIM Audit as per UNDP audit policies | UNDP Country Office | 15,000 (5 x 3,000) |  | Annually or other frequency as per UNDP Audit policies |
| Lessons learned and knowledge generation | Project Manager | 46,500 | 25,000 | Annually |
| Monitoring of environmental and social risks, and corresponding management plans as relevant | Project Manager UNDP CO | None |  | On-going |
| Addressing environmental and social grievances | Project Manager UNDP Country Office BPPS as needed | None |  | Costs associated with missions, workshops, BPPS expertise etc. can be charged to the project budget. |
| Project Board meetings | Project Board UNDP Country Office Project Manager | None | 10,000 | At minimum annually |
| Supervision missions | UNDP Country Office | None | 20,000 | Annually |
| Oversight missions | UNDP-GEF team | None11 |  | Troubleshooting as needed |
| Knowledge management as outlined in Outcome 4 | Project Manager | 22,500 |  | On-going |
| GEF Secretariat learning missions/site visits | UNDP Country Office and Project Manager and UNDP-GEF team | None |  | To be determined. |
| Mid-term GEF Tracking Tool to be updated by | Project Manager | Covered under M&E above | 10,000 | Before mid-term review mission takes place. |
| Independent Mid-term Review (MTR) and management response | UNDP Country Office and Project team and UNDP-GEF team | 30,000 | 10,000 | Between 2nd and 3rd PIR. |
| Terminal GEF Tracking Tool to be updated by BCA | Project Manager | Covered under M&E above | 10,000 | Before terminal evaluation mission takes place |
| Independent Terminal Evaluation (TE) included in UNDP evaluation plan, and management response | UNDP Country Office and Project team and UNDP-GEF team | 40,000 | 20,000 | At least three months before operational closure |
| Translation of MTR and TE reports into English | UNDP Country Office | 5,000 |  | As required. GEF will only accept reports in English. |
| TOTAL INDICATIVE COSTS Excluding project team staff time, and UNDP staff and travel expenses |  | 185,000 | 160,000 |  |

iII:  certification by gef partner agency(ies)

- GEF Agency(ies) certification

This request has been prepared in accordance with GEF policies and procedures and meets the GEF criteria for CEO endorsement under GEF-6.

| Agency Coordinator, Agency Name | Signature | Date (MM/dd/yyyy) | Project Contact Person | Telephone | Email Address |
| --- | --- | --- | --- | --- | --- |
| Adriana Dinu UNDP-GEF Executive Coordinator |  | 08 Nov 2017 | Tashi Dorji UNDP-GEF Regional Technical Adviser | +66 098 659 9975 | tashi.dorji@undp.org |

ANNEX A:  PROJECT RESULTS FRAMEWORK

|  | Objective and Outcome Indicators | Baseline | Mid-term Target | End of Project Target | Assumptions and Risks |
| --- | --- | --- | --- | --- | --- |
| Project Objective: To promote a landscape approach for the survival of snow leopard and its prey species by reducuing threats and applying sustainable land and forest management in critical habitats in Northern Pakistan | Indicator 1: Area of snow leopard habitat under integrated landscapes management | Approximately 10,000 hectares currently managed effectively in protected areas | At least 100,000 hectares of additional snow leopard habitat brought under participatory conservation management approaches | At least 1,500,000 hectares of critical snow leopard landscapes effectively managed under integrated participatory management landscape approaches | Assumptions: -Local communities understand livelihood benefits and ecological security of sustainable management of landscape resources through cooperation. Thus, they will participate in sustainable management and ecosystem restoration work. -The National and Provincial Governments consider their priority to support integrated planning of the landscape areas and implement target oriented activities with local communities to improve conservation and sustainable use of the resources. -The Provinces, CBOs and communities will work in close collaboration to prepare the landscape management frameworks Risks: -Natural disaster may affect the restoration work. -Lack of capacity in government and communities to meet obligations related to project. -Livelihood benefits from sustainable management may be low to give up current unsustainable practices -Conflicts over issues related to jurisdiction and mandate between provincial and sectoral entities could undermine efforts in promoting integrated planning approaches. |
|  | Mandatory Indicator 1.3.2: Number of additional people benefiting from strengthened livelihoods through solutions for improved management of natural resources and provision of ecosystem services | Fragmented and stand-alone community managed activities currently exists in the 3 landscapes | At least 500 households are directly benefiting from improved sustainable grazing management and diversified and alternative livelihoods and incomes | At least 4,000 households, (approximately 25,000 people, of which 40% will be women) directly benefit through sustainable resource management approaches |  |
|  | Mandatory indicator 2.5.1: Extent to which Institutional frameworks are in place for integration of conservation, sustainable natural resource use, control and management of wildlife crime and illegal wildlife trade and improved livelihoods into landscape planning and management | Multiple use landscape planning and management approaches absent or limited within Northern Pakistan. | Multiple use landscape frameworks agreed with key stakeholders and under review for official approval | Multiple use and sustainable landscape approaches institutionalized through national legislative, policy, and institutional arrangements in the three provinces |  |
| Outcome 1 Improved management of snow leopard landscapes that integrates sustainable forest and land management and compatible conservation practice | Indicator 4: Level of institutional capacity of provincial government agencies for planning, implementation and monitoring of integrated landscape plans as measured by UNDP capacity development scorecard | Limited institutional capacities for planning, implementation and monitoring of multiple use landscape as indicated by the capacity development baseline scores for: (i) National level-18 (ii) GB -18 (iii) AJK- 15 (iv) KP - 18 | 20% Increase in institutional capacity from baseline | 50% increase in institutional capacity from the baseline | Assumption: -The national government will develop appropriate legislative, policy, institutional and technical measures that facilitate integrated landscape planning and management in a timely manner. -The Provinces will take active part in developing the strategies and implementation using new knowledge and skills provided by the project -Local communities are convinced that mainstreaming biodiversity into key development sectors is for their long-term interests Risks: -Priorities of provincial governments and local communities might shift if development benefits take long to manifest -Capacity of provincial stakeholders and communities may pose a challenge and constraint in taking forward the initiatives. |
|  | Indicator 5: Status of snow leopard and associated endangered species populations in the landscapes | Snow leopard population estimate at + 200 individuals in Northern Pakistan with associated species baselines as: Karakoram-Pamir LS: Himalayan Ibex-4,900 Markhor -230 Blue Sheep – 750 Ladakh Urial -50 Hindu Kush LS: Markhor – 3,400 Himalaya LS: Musk Deer, Brown bear | Snow leopard and associated species baselines validated and monitoring showing stable or improving population trends | Stable or increase in snow leopard and associated species populations in Northern Pakistan from existing baselines | Assumptions: -SLF and provincial wildlife departments give high priority to monitoring of snow leopard and associated species -Adequate technical capacity and resources available for undertaking species monitoring Risks: -Catastrophic climatic events may greatly impact on snow leopard and associated species populations -Large-scale transboundary infrastructure developments would seriously impact on snow leopard and associated species habitat and species. |
| Outcome 2 Increased representation of priority snow leopard ecosystems in Protected Area network | Indicator 6: Increase in extent of snow leopard habitat under PA network | 3,100,000 ha of snow leopard areas under existing PA network (national parks, sanctuaries, game reserves and community managed conservation areas, but with exception of around 10,000 ha under National Parks and/or CMCAs, other areas lack appropriate management | At least 100,000 ha of additional priority snow leopard habitat, including 2,000 ha of high conservation value forests legally defined and included in PA network | At least 200,000 ha of additional priority snow leopard habitat, including 10,000 ha of high conservation value forests legally defined and included in PA network resulting in 2.96 million tCO2e sequestrated over 10-year period | Assumption: -Adequate technical capacity available for undertaking preparation of management plans - Management plans will be officially approved by Provincial governments on time with allocation of appropriate funding for their implementation -The Provinces will take active part in developing the strategies and implementation using new knowledge and skills provided by the project -Local communities are convinced that critical habitats in their vicinities will benefit livelihoods and ecological security to them and they will participate in conservation and restoration work. -Community-based institutions would establish an effective institutional mechanism to facilitate conservation outcomes Risk: -Administrative/political changes may undermine the implementation of the management plan strategies -Lack of capacity in government and communities to meet obligations related to project -Conflicts between national, provincial and local communities regarding management and access to natural resources may undermine integrated planning approaches -External factors, like major climatic events might negate positive impacts of integrated approaches |
|  | Indicator 7: Effectiveness in management of protected areas within the landscape as measured by METT (Management Effectiveness Tracking Tool). | Current METT baseline scores for PAs are as follows: Chitral Gol NP-30; Broghil NP – 12; Central Karokoram NP – 22; Qurumba NP- 13; Khunjerab NP -25; Musk Deer NP- 18; Ghamot NP – 16 | Average increase by at least 10 points in METT from the baseline | Increase in METT score by at least 30 points from the baseline values |  |
|  | Indicator 8: Number of management and financing plans for protected areas with adequate financial resources developed and approved by the provincial government. | 4 PA management plans approved, but lack adequate budgetary provisions | Guidelines for improved management of CMCAs developed and approved by government and at least 5 additional management and financing plans agreed with local communities | At least 17additional management and financing plans for existing and new critical protected areas (mainly CMCAs) developed, approved by government and operationalized with adequate financial support |  |
|  | Indicator 9: Number of forest and wildlife staff and community members actively engaged in wildlife crime monitoring and surveillance to reduce incidence of wildlife crime. | Limited and uncoordinated training programs currently implemented and incidents of wildlife crime in landscapes | (i) At least 50 forest and wildlife trained and actively enforcing environmentally friendly management practices and wildlife crime prevention measures in snow leopard habitats; (ii) At least 20 community members actively engaged in wildlife crime monitoring and surveillance in community battalions | (i) At least 200 forest and wildlife trained and actively enforcing environmentally friendly management practices and wildlife crime prevention measures in snow leopard habitats (ii) At least 60 community members trained and actively engaged in wildlife crime monitoring and surveillance resulting in 25% decrease in incidents of wildlife crime from Year 1 baseline | Assumption: -Adequate capacity and resources available for effective management -Capacities of the community groups will be adequate after the training to execute the task. -Local communities have economic interest in reducing wildlife crime Risks: -Partner Organizations (NGOs) are unable to mobilize adequate manpower and technical resources to support sustainable actions |
| Outcome 3 Participatory conservation in the targeted landscape enhanced to reduce human-snow leopard conflicts and improve livelihoods of community. | Indicator 10: Number of valley conservation plans developed and under implementation. | Lack of integrated landscape planning approaches and the current planning process is mostly at sectoral level | At least 8 valley conservation plans developed and approved | At least 17 valley conservation plans developed, endorsed and under implementation | Assumptions: -The Provinces will take active part in developing the strategies and implementation using new knowledge and skills provided by the project -Local communities are convinced that critical habitats in their vicinities will benefit livelihoods and ecological security and they will participate in conservation and restoration work. -Local community based institutions would establish an effective institutional mechanism to facilitate conservation outcomes -Project interventions will focus on short to mid-term benefits to avoid long gestation period that would not be conducive to win community support for conservation Risk: -Lack of capacity in government and communities to meet obligations related to project -Conflicts between national, provincial and local communities regarding management and access to natural resources may undermine integrated planning approaches -Sufficiently trained and committed personnel unavailable to provide adequate coverage -Natural calamities may affect the ability of local communities to respond positively to holistic approaches to sustainable management of resources. |
|  | Indicator 11: Average increase in income of communities from sustainable livelihood and resource management activities | Baseline incomes to be established in Year 1 through the valley conservation planning process | At least 5% increase in average incomes from sustainable livelihoods, natural resource management and business activities (At least 30% of beneficiaries are women) | Implementation of sustainable livelihood, natural resource management and wildlife deterrents systems ensures at least 15% average increase in incomes of participating communities from the baseline established in Y1, of which at least 30 % of households include women beneficiaries |  |

|  | Indicator 12: Decreased incidences of human-wildlife conflict as indicated by: - Decrease in livestock lost to snow-leopard and other predators; - Reduce incidence of retaliatory killing of snow leopard and other predators | (i) Average livestock lost to wildlife estimated at 0.6 head/HH/Year (ii) Number of incidences of retaliatory killings of snow leopard and other predators to be assessed in Year 1 | (i) At least 10% decrease in livestock lost/year to wildlife (ii) At least 10% decrease in retaliatory killings of snow leopard and other predators | (i) At least 25% decrease in livestock lost/year to wildlife (ii) At least 50% decrease in retaliatory killings of snow leopard and other predators | Assumption: -Communities are willing to subscribe to livestock compensation programs and improved herding practices. Risks: -Delays in payment of compensation may result in community disengagement from such programs |
| --- | --- | --- | --- | --- | --- |
| Outcome 4 Conservation and management approaches at national and international level is supported by effective knowledge management and gender mainstreaming. | Indicator 13: Number of knowledge products reflecting best practices and lessons learned documented and disseminated and up-scaled. | No concerted effort exists in promoting best practices | A majority of best practice and lessons identified and at least 3 under documentation | At least 10 best practices of sustainable grazing and forest use, ecotourism, human-wildlife conflict management, financial instruments for livestock predation resolution, and gender mainstreaming documented and replicated in at least 5 additional valleys with non-GEF resources | Assumption: -Stakeholders willing to actively participate in the review process. -Project management will be able to identify, document and disseminate the best practices -Mid Term Review and End of Project Evaluation of the project will also contribute to identifying the best practices -Best practices on sustainable resource management readily available to resource users -Gender and social inclusion plan followed and benefits distributed equitably -Political climate is conducive to promote trans-boundary collaboration Risks: -Government priorities may change from due to political pressure from resource users -Actions among the assorted agencies and NGOs remain uncoordinated -Community diversity will be a hindrance to outreach activities -Vulnerable groups are left out and continue using poor practices -Changing international political climate may constraint trans-boundary collaboration |
|  | Indicator 14: Increase in the level of awareness of communities in the target landscapes on conservation and sustainable use and threats to snow leopard and biodiversity | Baseline to be established in Year 1 | At least 20% of participating households (at least 40% of households include women beneficiaries) have good awareness of conservation, sustainable natural resource use and wildlife crime prevention benefits | At least 50% of participating households (at least 40% of households include women beneficiaries) in landscapes aware of conservation, sustainable resource use and wildlife crime prevention benefits |  |
|  | Indicator 15: Number of effective inter-provincial/trans-boundary collaboration mechanisms negotiated and implemented | No concerted efforts in trans-boundary and inter-provincial collaboration exists | At least 2 effective collaborative inter-provincial agreements negotiated and protocols agreed to | Collaborative agreements negotiated, joint patrolling and information regarding poaching and IWT shared to improve species conservation and reduce poaching, and trans-boundary agreements reached with at least two neighboring countries for sharing of information on IWT and genetic composition of snow leopard populations. |  |

ANNEX B:  RESPONSES TO PROJECT REVIEWS (from GEF Secretariat and GEF Agencies, and Responses to Comments from Council at work program inclusion and the Convention Secretariat and STAP).

ANNEX B.1: RESPONSES TO PIF COMMENTS

| Comment | Response | Relevant Section of UNDP Project Document and - GEF CEO ER. |
| --- | --- | --- |
| GEFSEC Review Comments |  |  |
| 1. Considering involvement of indigenous peoples, please make sure to develop a relevant indigenous peoples plan | The project includes a valley level participatory community planning framework that outlines the procedures and mechanisms that would be followed to ensure participation of local communities, including indigenous and marginalized communities. This approach would allow an informed, transparent and inclusive process in the planning and implementation of activities of the project, so that a self-managed and governed system sustains even after completion of the project. A grievance redressal mechanism is also proposed to ensure that all communities including indigenous and marginalized communities have equal access to benefit from the project. A gender mainstreaming action plan details specific arrangements to ensure that women and disadvantaged groups actively participate in project related decisions and benefits. | Please refer to the following annexes in UNDP Project Document: Annex 5 (Valley Level Participatory Framework) Annex 9 (Gender Analysis and Mainstreaming Action Plan) |
| 2. The carbon figure seems low for a targeted project area of 4 million ha under better planned SFM and SLM management. Please review the figure by using appropriate tools and provide updated figure by CEO endorsement | The figures have been revised as follows: The total carbon sequestration from the project intervention is estimated at ~2,960,760 million tCO2 equivalent over a 10-year period. The estimate has been derived as indicated below: Protection of 10,000 ha of temperate mountain forests will yield 805,447 tCO2 over a 10 year period. Protection and sustainable management of 190,000 ha of sub-alpine and alpine grasslands that are currently in “severely” degraded condition will be converted into “moderately” degraded condition within the 10-year period resulting in 2,155,313 tCO2 sequestration over a 10-year period. | Refer Annex 25 of UNDP Project Document |
| STAP Comments |  |  |
| 3. STAP welcomes this initiative addressing the conservation needs of an iconic and critically endangered species, Snow Leopard (Panthera unica), across its range in Northern Pakistan, while concomitantly addressing critical land management and socio-economic issues in the same region. It is an ambitious undertaking in a challenging region both from a socio-economic and bio-physical perspective. | While this is an ambitious undertaking, the project has tried to address these concerns through the following actions: - Being selective with project interventions and the number of valleys to be covered under the project. The project particularly focused in those valleys of high snow leopard habitat suitability. - Establishing collaborative arrangements with a number of NGOs and CSOs who are already active in community-based snow leopard conservation work in the landscape in order to complement and coordinate the activities. - Ensuring that future expansion of the PA network will largely concentrate on the more cost-effective and successful community managed conservation area approach rather than on traditional PAs. - The project will be executed through the Snow Leopard Foundation that has been active in snow leopard conservation work in Northern Pakistan since 2006 and has already established regional offices in the 3 landscapes with staff and other resources that will help implement the project, so establishment of new offices are not envisaged. SLF has already been active with the local communities which would greatly facilitate community interaction and planning. SLF has also established an extensive program of livestock immunization and compensation that has helped build good relationships with the local people. - SLF will collaborate with sector agencies for delivery of additional technical expertise and resources to the area. - The landscape coordinating committees will facilitate improved interaction and collaboration with sector agencies and other partners in the landscape | Section III “Strategy” of UNDP Project Document |
| 4. For instance, the imperative for developing sustainable financing schemes over the life of the project is noted on a number of occasions in the PIF, and is closely associated with long term project success. However, this seemly important project component has not been developed in this document. Given the obvious importance of this component to project success and sustainability, it is insufficient at PIF stage to effectively leave sustainable financing as an inherent assumption that will emerge successfully during project implementation. STAP urges that particular care is taken to fully develop this component of the project during the development phase. | The project now includes a separate Output 1.4 (Replication strategy developed and implemented to facilitate up-scaling of integrated landscape planning and management model to other sites) to help develop a replication strategy and financial instruments for replication and scaling up during the implementation phase of the project. | Refer to Section IV “Results and Partnerships” Part i “Expected Results” Output 1.4 of UNDP Project Document. |
| 5. Another inherent assumption in this document is the notion that improvements to SLM and SFM and associated practices will largely lead to reduction in pressure on Snow Leopard habitat. Little evidence of past success in this regard has been provided. This is surprising, given the level of effort from past and ongoing initiatives noted in the baseline analysis. | SLM and SFM alone cannot by itself lead to reduction of pressure on Snow Leopard habitat, but when combined with a number of complementary measures, such as: (i) mainstreaming biodiversity conservation into sector planning, (ii) ensuring an overall integrated planning and coordination mechanism at the landscape level, (iii) improving community conservation through establishment of additional Community Managed Conservation Areas (CMCAs) particularly in key biodiversity areas and corridors, (iv) improved community management of alpine pastures through better herding practices, (v) reduction livestock related deaths through immunization and wildlife deterrent systems (corrals); (vi) establishing compensatory mechanisms for wildlife related livestock losses and others. These interventions are expected to collectively result in improved conservation outcomes. | Section IV “Results and Partnerships” Part i “Expected Results” provides the range on conservation related activities to be implemented by the project |
| 6. The likely future impacts of climate change in Northern Pakistan have been outlined in the document and included in the results table, however it is peculiar that climate change has not been considered in the project risk table. The impacts of climate change will almost certainly ensure that current bio-physical and socio-economic conditions which exist on the ground will not exist within 20 years. The PIF correctly notes that Snow Leopard habitat is expected to contract by 30% by mid-century (highlighted in IPCC AR5 WGII). Probability is high that temperatures will increase by 3ï‚°C in the northern reaches of Pakistan over a similar time period. Great care will need to be taken in the project planning phase to address this dynamic, particularly in PA identification and development, establishment of corridors, and including in the identification and use of appropriate SLM and SFM practices which build resilience to climate change. | Project design includes specific means to address climate change adaptation in planning of landscape planning and valley conservation planning processes. | Refer Section V of GEF CEO ER |
| 7. The project Knowledge Management strategy should include how data will be managed post project and where these data will reside. STAP urges that data access also be made available beyond the circle of project stakeholders. | The Snow Leopard Foundation will have enhanced its existing database with updated information on best practices and improved mapping, monitoring and evaluation data that would be made available beyond project staff and SLF. | Section IV “Results and Partnerships” Part i “Expected Results” Outcome 4 of UNDP Project Document |
| 8. Project proponents should consider including the IUCN Species Survival Commission "Big Cat Specialist Group" among project stakeholders | Noted and included in the SIP. | Table 3 “Stakeholder Involvement Plan” of UNDP Project Document. |
| Comments from Germany |  |  |
| 9. Germany has concerns that particularly provincial governments are in the position to co-finance the planned projects with the indicated amounts. | The PPG Team undertook extensive consultations with Provincial Governments as well as reviewed on-going and proposed programs at the provincial level to ascertain realistic co-financing figures as reflected in Table C of the GEF CEO ER. This has been confirmed and the co-financing letter has been issued by the provincial governments indicating their full commitment to the project. | Table C of GEF CEO ER |
| 10. Furthermore Germany suggests that component 1 landscape level approach for snow leopard conservation is further developed using a multi-stakeholder and cross-sectoral approach involving all relevant stakeholders and government departments (not just the Wildlife Departments). | Agreed. Output 1.1 specifically deals with the establishment of multi-sectoral, multi-stakeholder coordination and governance mechanism at each landscape to facilitate the integration and/or mainstreaming of biodiversity conservation in sector plans and programs at the landscape level | Section IV “Results and Partnerships” Part i “Expected Results” Outcome 1 of UNDP Project Document |
| 11. Germany also recommends clarifying interlinkages between component 1 and 2 to ensure a coherent overall approach. | Component 2 which entails expanding the PA network in Snow Leopard ranges will build on the assessment and mapping to be undertaken under Component 1 namely Output 1.2 and baseline monitoring of snow leopard and prey species populations, habitats and threats (Output 1.3) that will inform identification of high value areas outside the existing PA network for potential creation of new PAs, extension of existing PAs as well as improving management effectiveness of existing ones, thereby contributing to overall strengthening of the PA system. | Section IV “Results and Partnerships” Part i “Expected Results” Outcome 1 and 2 of UNDP Project Document |
| 12. In the development of the final project proposal it should be assessed if component 3 can comprise activities to encourage alternative sources of income (other than livestock). | The local communities in the snow leopard landscapes are mainly herder communities depending primarily and solely on livestock rearing. To preserve this focus, the component will primarily consider livestock-based options for economic development, and rangeland improvements and social forestry that may help strengthen agriculture income. However, it is anticipated that valley level planning (Output 3.1) will bring in a more holistic approach to community participation (beyond addressing livestock development and sustainable pasture management) to conservation, sustainable natural resources management (forest, land and pasture management) and alternative and diversified livelihood and income generation activities, including options for NTFP based enterprises. In this regard, lessons from the GEF funded mountains and markets project in working with the private sector on product development and marketing of NTFP products will be useful and adopted during implementation. | Section IV “Results and Partnerships” Part i “Expected Results” Outcome 3 of UNDP Project Document |
| 13. Activities implemented under component 4 should take into account existing initiatives when developing GIS-based information systems in Pakistan. | To ascertain and assess information gaps on snow leopard population, its prey species and habitat, a snow leopard ecosystem information data management system will be developed that integrates and consolidates relevant data collected previously with data specific to this project. This system will make use of all existing initiatives including those set up under the Ministry of Climate Change and other agencies. | Section IV “Results and Partnerships” Part i “Expected Results” Outcome 4 of UNDP Project Document |
| 14. Germany further suggest that the final project proposal takes into account the information available in the regional Biodiversity and Action Plan for KP (KPBSAP) as well as the revised NBSAP and uses these strategies as orientation. | The PPG Team took into consideration information available from all relevant programming documents including the NBSAP, the KPSAP and also provincial documents and had number of consultative meetings at the national and provincial levels to ensure that project design complements existing programs and initiatives. Project design ensures that collaborative mechanism (through MOUs and Landscape Conservation Committees) would be established with other NGOs and CBOs already undertaking conservation related work in Northern Pakistan to ensure that landscape planning and management becomes a very complementary, collaborative and seamless effort. | Section III “Strategy” and Section IV “Results and Partnerships” Part i “Expected Results” Outcome 3 of UNDP Project Document |
| 15. The final project proposal should clearly address all the concerns and issues raised in the STAP review. | Refer response to STAP review comments 3 through 8 above. | See above |

Annex C:  status of implementation of project preparation activities and the use of funds

A.  Provide detailed funding amount of the PPG activities financing status in the table below:

| PPG Grant Approved at PIF: |  |  |  |
| --- | --- | --- | --- |
| Project Preparation Activities Implemented | GETF/LDCF/SCCF/CBIT Amount ($) |  |  |
|  | Budgeted Amount | Amount Spent To date | Amount Committed |
| Component A: Technical Review | 80,000.00 | 49,246.00 | 30,754.00 |
| Component B: Institutional Arrangements, Monitoring and Evaluation | 35,000.00 | 21,545.00 | 13,455.00 |
| Component C: Financial Planning and Co-financing Investments | 10,000.00 | 6,156.00 | 3,844.00 |
| Component D: Validation Workshop | 15,000.00 | 9,234.00 | 5,766.00 |
| Component E: Completion of Final Document | 10,000.00 | 6,156.00 | 3,844.00 |
| Total | 150,000.00 | 92,337.00 | 57,663.00 |

annex D:  calendar  of expected reflows (if non-grant instrument is used)

Provide a calendar of expected reflows to the GEF/LDCF/SCCF/CBIT Trust Funds or to your Agency (and/or revolving fund that will be set up)

N/A

Annex E: changes and rationale of changes from original project concept

The Table below summarizes the changes made to the outcomes and outputs from the original PIF, and the rationale for the changes. Most of the changes have been made with the intent of developing a more coherent strategy for the project and reducing the complexity and scattered nature of the activities based on the recommendation of STAP. The main changes relate to changing the order and elaboration of the outcome/output descriptions.

|  | PIF | GEF CEO ER | Rationale |
| --- | --- | --- | --- |
| Project Components | Support for international cooperation and conservation and management actions informed by knowledge on snow leopard ecology and ecosystem dynamics | Component 4: Support for international cooperation and conservation and management actions informed by knowledge, awareness and monitoring and evaluation | Revised to provide additional emphasis on awareness, monitoring and evaluation |
| Project Outcomes | Outcome 1.1: Landscape management plans developed for the three model snow leopard landscapes covering 4,100,000 ha that integrate and sustainable forest and land management and snow leopard conservation compatible practices. Outcome 1.2: Appropriate SLM and SFM technologies implemented by local communities (in at least 250,000 ha), resulting in: i) reduced land degradation (measured by Net Primary Productivity and increase in rain use efficiency); iii) maintenance of ecosystem services (e.g. water availability and increased carbon sequestration); and iv) restoration/regeneration of degraded rangelands, including 1,000 ha juniper forest. | Outcome 1: Revised as a single Output: Developed framework for improved management of snow leopard landscapes that integrates sustainable forest and land management and compatible conservation practice | Outcome 1 is now specifically focused on the development of a coordination and institutional framework for integrated landscape planning. The Outcome relating to SLM and SFM in PIF has been moved to Output (3.2) under Outcome 3 that specifically deals with community activities. This Outcome now excludes restoration of 1,000 ha of juniper forests as this activity is expensive and not a viable proposition. Instead the project aims to set-aside 200,000 ha of new PAs (in the form of 17 CMCAs) as against a PIF target of 20,000 ha with improved community protection and sustainable land management as a more cost-effective option. |
|  | Outcome 4.1: Enhanced scientific knowledge on snow leopards, prey species, and habitat leads to better conservation and management decisions. This consists of: (i) GIS database for model landscapes; (ii) monitoring system for identifying threats; (iii) climate change impacts and adaptation measures are incorporated into 3 landscape management plans (linking with global SL project and GSLEP as well as with national and regional initiatives). Outcome 4.2: Effective development of mechanisms and improved capacities for international cooperation on snow leopard conservation, control of illegal trade and improved information management. | Outcome 4: Implementation, upscaling and replication of project approaches supported by effective knowledge management and gender mainstreaming. | This Outcome focuses on communication, gender mainstreaming, inter-provincial and transboundary collaboration and M&E. Aspects relating to monitoring (is now a new Output 1.3), while climate change and adaptation mainstreaming are integrated into Valley Conservation Management Planning and Implementation (Outputs 3.1 and 3.2), as well as IWT management (Output 3.3) as these directly involve community participation (Outcome 3) |
| Outputs | None | New Output 1.1: Functional multi-sector and multi-stakeholder coordination and governance mechanisms developed, discussed with stakeholders and supported | A new Output with emphasis on establishment of a functional institutional arrangement to facilitate coordination across sectors and stakeholders that is recognized as a pre-requisite for successful broad-based regional planning has been proposed. |
|  | Output 1.1: Three model landscape level management plans covering a total area of approx. 4,100,000 ha that integrate sustainable forest and rangeland management and reconcile needs of snow leopard ecosystem conservation and development. | Output 1.2: Landscape level spatial zoning and management strategies integrates biodiversity, ecosystem services, climate mitigation, sustainable community resource use and socio-economic considerations developed, approved and implemented in snow leopard landscapes | Modified to improve clarity and provide more realistic assessment of impacts as requested by STAP |
|  | Output 1.2: Ten valley plans covering 250,000 ha developed and implemented that integrate sustainable forest and land management practices and snow leopard conservation compatible measures in line with the landscape level plans, and provided with training and extension support on appropriate technologies. | Moved to Output 3.1: Site-specific integrated valley conservation management plans designed and implemented in areas of high biodiversity value areas under community governance, management and enforcement regimes. | As discussed previously, all community activities are now part of Outcome 3 and covers 17 valley plans that will be supported through the project fund. |
|  | Output 1.3: Improved SLM and SFM practices applied by local communities in and surrounding PAs to improve community skills base and support sustainable livelihoods, including: rehabilitation of degraded rangelands and improving management (e.g. providing adequate rest through rotational grazing regimes), improved shrub land management (e.g. sustainable fuelwood collection, use of fuel efficient stoves and reduced shrub land grazing), silvopastoral practices, community forestry, sustainable fodder cultivation. | Reconfigured as Output 3.2: projects on sustainable community based natural resources management, sustainable livelihood and solutions to reduce wildlife-human conflicts developed and implemented. | As discussed previously, all community activities are now part of Outcome 3 and sustainable land and forest conservation activities are integrated into the Valley Conservation Plans. |
|  | None | New Output 1.3: Participatory monitoring for snow leopard, other endangered species and prey species developed and implemented to inform management responses | Moved from PIF Output 4.1 as this Output is specific to the entire snow leopard range in Northern Pakistan and has implications on the management of landscapes. |
|  | None | New Output 1.4: Replication strategy developed and implemented to facilitate up-scaling of integrated landscape planning and management model to other sites | Included as a separate output based on STAP recommendation to ensure sustainability considerations during the project implementation. |
|  | Output 2.1: At least 20,000 ha of priority snow leopard habitat (including 7,000 ha of forests important for biodiversity) gazzetted as PAs. | Output 2.1: Expanded protected area network in the snow leopard range through identification, mapping and government approval of new protected areas in priority snow leopard habitat | Revised to provide better clarity as PIF output is presented as an outcome rather than an output. |
|  | Output 2.3: At least 100 forest and wildlife managers (PA staff and community organizations) trained and equipped for monitoring and enforcement. | Output 2.3: Forest and wildlife staff have technical support and enhanced capacities for improving conservation outcomes and combatting wildlife crime | Revised to provide clarity of the output statement. |
|  | Output 2.4: Improved anti-poaching, surveillance measures (including involvement of local communities in anti-poaching efforts; information sharing and management systems) to reduce incidences of wildlife poaching and illegal trade. | Reconstituted as Output 3.3: Community-based surveillance, monitoring and wildlife crime prevention system developed and implemented | This is in keeping with the decision to move all community based activities to Outcome 3 |
|  | None | Output 2.4: Wildlife agencies have information on hotspots and pathways of Illegal Wildlife Trade (IWT) to organize targeted operations against wildlife crime. | This is a new output as good understanding of hotspots and pathways of organized IWT operations is required to enable the planning and implementation of effective surveillance and monitoring operations against wildlife crime. |
|  | Output 3.1: Community-run livestock insurance services are established and accessed by at least 10,000 households in the model landscapes. | Now Output 3.2: Projects on sustainable community based natural resources management, sustainable livelihood and reduced wildlife-human conflicts developed, tested and implemented. | Community participation in conservation requires a more holistic approach to manage the totality of interactions between communities and their environment rather than just focus on a single activity. |
|  | Output 3.2: Improved wildlife deterrent systems (corral improvements) piloted and better livestock management (e.g. vaccination for disease control) in 20 valleys comprising minimum of 10,000 households (over baseline of 10). | Output 3.2: Projects on sustainable community based natural resources management, sustainable livelihood and reduced wildlife-human conflicts developed, tested and implemented. | As mentioned above, livestock management and deterrent systems are now considered within a more holistic program that includes conservation, sustainable natural resources management, livelihood improvement and management of wildlife-human conflicts. |
|  | Output 3.3: Community based conservation education and outreach strategy focused on: (a) ecological, socio-economic importance of snow leopards and their ecosystems; (b) greater awareness of conservation laws are developed and implemented: (i) information centers developed, one in each model landscape; (ii) school-based Nature Clubs initiated in 20 new schools that engage young students to promote behaviour change in conservation. | Now reconstituted as Output 4.1: Communication, gender mainstreaming and monitoring and evaluation strategies developed and implemented at national, provincial and local levels. | Necessitated based on decision to move awareness to Outcome 4, and it is now expanded to include the implementation of gender mainstreaming action plan |
|  | Output 4.1: Model snow leopard ecosystem GIS based monitoring system established for model landscapes, integrating: (i) systematic surveys of snow leopard and wild prey, (ii) research and surveys on the status of snow leopard ecosystems, including vegetative cover and juniper forests, (iii) system for assessing status of and trend in threats in snow leopard ecosystems established; and monitoring information used to develop measures for management and restoration of habitats. | New Output 1.3: Participatory monitoring for snow leopard, other endangered species and prey species developed and implemented to inform management responses | See response above (PIF Output 1.3) |
|  | Output 4.2: Systematic assessment of climate change impacts on snow leopard ecosystems; adaptation measures integrated into management plans (output 1.1) | Integrated into Output 3.2 | See response above (GEFCEO ER Output 3.2) |
|  | Output 4.3: Targeted support to participation of Pakistan in the Global Snow Leopard Ecosystem Protection Plan process. | Now constituted as Output 4.3: Knowledge management is coordinated with global, regional and national programs to improve cooperation and research on snow leopard conservation | New output goes beyond just participation in GSLEP, instead includes the establishment of inter-provincial and transboundary partnerships, to the extent of improving species conservation and addressing IWT issues. |
|  | None | New output 4.2: Replication of project approaches by effective knowledge management and gender mainstreaming | Additional emphasis on replication through policy and legislation reforms being informed by best practices and experiences generated by the project. |
| Component Budget Changes | Component 1: USD 1.5m Component 2: USD1.0 m Component 3: USD 1.52 m Component 4: USD 0.4 m | Component 1: USD 0.642 m Component 2: USD 0.808 m Component 3: USD 2.38 m Component 4: USD 0.59 m | Changes in GEF budget for Components have been made, in particular in Component 3, on account that all community related activities are now moved to Component 3. This includes preparation of Valley Conservation Plans (moved from Output 1.2 to Outputs 3.1 and 3.2) and consequently implementation of SLM and SFM activities are envisaged to be planned and implemented by communities through the Valley Conservation plans under Component 3. Concurrently there has been a reduction of budget allocation in Component 1 as a consequence of moving SLM and SFM activities to Component 3. Other reductions are associated with the creation of a new Component 4. |
| Project Duration | 4 years | 5 years | Inclusion of an additional year given the time required for planning in the remote landscapes of Northern Pakistan |
| Co-financing | 12,951,000 | 15,130,000 | Co-financing figures have slightly increased due to better alignment of co-financing from National and Provincial Government and CSOs |

This includes around 1,500,000 ha in the target 17 valley conservation areas and other PAs (CMCAs and NPs and WLS), which constitutes about 25% of the total area of the 3 landscapes

Baselines to be developed in Year 1 for Himalaya LS

Baselines METTs for two National Parks not available would be assessed in Year 1

Baselines values unreliable, so would be assessed in Year 1

Baselines to be developed in Year 1 for each landscape

This figure is calculated on the basis that 95% of 200,000 ha of new CMCAs established in 17 valleys will be sub-alpine and alpine pastures that will be targeted under the project for SLM (improved grazing and herding practices, soil and water conservation, etc.) and the balance 10,000 ha will be sub-alpine forests under community protection

For questions A.1 –A.7 in Part II, if there are no changes since PIF , no need to respond, please enter “NA” after the respective question.

The landscape spatial zoning and management strategies developed for the entirety of the 3 landscapes, although direct actions at community level will focus on 17 valleys covering 1.5 million ha.

Excluding project team staff time and UNDP staff time and travel expenses.

The costs of UNDP Country Office and UNDP-GEF Unit’s participation and time are charged to the GEF Agency Fee.

GEF policies encompass all managed trust funds, namely: GEFTF, LDCF, SCCF and CBIT

As measured by (i) Effective and functional Provincial Coordination Committee with sector representation; (ii) Landscape Management Plans formalized and validated at provincial level; (iii) landscape effectively zoned with creation of CMCAs; (iv) community institutional arrangements in place for management of CMCAs; (v) partnership arrangements established with CSOs for collaborative actions in landscape.

Including in particular Chitral Gol National Park and few CMCAs

This includes areas brought under CMCAs following completion of the landscape management and valley conservation planning process

This includes around 1,500,000 ha in the target 17valley conservation areas and other PAs (CMCAs and NPs and WLS), which constitutes about 25% of the total area of the 3 landscapes

This constitutes about 30% of the HHs in the 17 target valleys

Representing around 25,000 people

Outcomes are short to medium term results that the project makes a contribution towards, and that are designed to help achieve the longer term objective.  Achievement of outcomes will be influenced both by project outputs and additional factors that may be outside the direct control of the project.

Associated species where indicated will be verified and validated in Year 1, and where baseline values are unavailable (Himalaya LS) these will be determined in Year 1, and monitored subsequently

Current number of wildlife crime incidents in 3 landscapes not accurate. Numbers to be validated in Year 1.

Based on 2017 Survey undertaken by SLF in 49 valleys and 2,798 households surveyed predation rates in snow leopard ranges in Northern Pakistan to be validated in Year 1 on landscape basis

If at CEO Endorsement, the PPG activities have not been completed and there is a balance of unspent fund, Agencies can continue to undertake the activities up to one year of project start.  No later than one year from start of project implementation, Agencies should report this table to the GEF Secretariat on the completion of PPG activities and the amount spent for the activities.  Agencies should also report closing of PPG to Trustee in its Quarterly Report.