GEF-6 Project Identification Form (PIF)

Project Type: Full Size Project

Type of Trust Fund:GEF Trust fund

PART I: Project Information

| Project Title: | Sixth Operational Phase of the GEF Small Grants Program in Pakistan |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Country: | Pakistan | GEF Project ID: |  |  |  | 9331 |
| GEF Agency: | UNDP | GEF Agency Project ID: |  |  |  | 5734 |
| Other Executing Partner: | UNOPS | Submission Date: Resubmission Date: |  |  |  | 22 Oct 2015 26 January 2016 |
| GEF Focal Area(s): | Multifocal Area | Project Duration (Months) |  |  |  | 36 |
| Integrated Approach Pilot | IAP-Cities IAP-Commodities IAP-Food Security |  |  | Corporate Program: SGP X |  |  |
| Name of parent program: |  |  | Agency Fee ($) |  | 252,674 |  |

A. indicative Focal Area  Strategy Framework and Other Program Strategies

| ### Objectives/Programs | ### Trust Fund | ### (in $) |  |
| --- | --- | --- | --- |
|  |  | ### GEF Project Financing | ### Co-financing |
| BD-4 Program 9 | GEF | 177,315 | 200,000 |
| CCM-2 Program 3 | GEF | 1,595,836 | 1,825,000 |
| LD-2 Program 3 | GEF | 886,575 | 1,000,000 |
| Total Project Cost |  | 2,659,726 | 3,025,000 |

B. indicative Project description summary

| ### Project Objective: to enable community organizations in Pakistan to take collective action for adaptive management for socio-ecological resilience - through design, implementation and evaluation of grant projects for global environmental benefits and sustainable development in key landscapes and rural/urban communities |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| ### Project Components | ### Financing Type | ### Project Outcomes | ### Project Outputs | ### Trust Fund | ### (in $) |  |
|  |  |  |  |  | ### GEF Project Financing | ### Co-financing |
| 1.0. Resilient rural landscapes and seascapes of Pakistan’s Indus Delta for sustainable development and global environmental protection | TA | 1.1 Multistakeholder partnerships develop and execute participatory adaptive management plans to enhance socio-ecological landscape resilience in the Indus Delta area. 1.2. Community organizations in landscape level networks build their adaptive management capacities by implementing community level projects and collaborating in managing landscape resources and processes to achieve landscape resiliency. 1.3: Strategic projects are developed and implemented by multistakeholder partnerships that catalyze broader adoption of specific successful SGP-supported technologies, practices or systems to a wider area and/or groups of stakeholders. 1.4: Potential financial partners, policy makers and their national/ subnational advisors and institutions, as well as the private sector, engage in designing, planning and monitoring dissemination and replication of successful technologies, practices or systems. 1.5. Alternative livelihoods developed or enhanced in the Indus Delta through the promotion of high value livestock breeds and development of innovative products and market access | 1.1.1. Maps and analysis of inter-institutional governance frameworks and stakeholder constituencies produced 1.1.2 Civil society representation gap analysis and proposals for amendments to existing governance structures to improve community and local CSO participation, and dialogues with government officials 1.1.3 Participatory research and planning processes instituted and comprehensive socio-ecological baseline assessments carried out 1.1.3 Multistakeholder governance platform(s) in the Indus Delta develop and execute adaptive landscape management plans and policies through strategic community actions. 1.2.1 Community level small grants projects that conserve biodiversity and restore ecosystem services in the Indus Delta 1.2.2 Community level small grant projects that enhance productivity and sustainability of smallholder agroecosystems 1.2.3 Community level small grant projects for alternative livelihood options and improved market access 1.3.1 Detailed analysis of successful grant project portfolios and lines of work (e.g. community agro-forestry) from previous phases to identify lessons learned/best practice and market opportunities 1.3.2 Engagement of potential financial partners and public sector institutions as viable in analysis and planning 1.4.1 Based on detailed analysis, identification of upscaling requirements and opportunities and development of a strategy(ies) to enable and facilitate upscaling 1.4.2 Conservation and water management through rainwater harvesting systems, gulley plugs gabions, and small dams as well as drip irrigation and better management of livestock watering systems and fishponds. 1.5.1 High value local livestock breeds introduced and promoted 1.5.2 Innovative products and services such as micro-mills, fruit collection and/or processing factories (e.g. Moringa olifera products, seed oil), sustainable tourism services, etc., identified and supported. 1.5.3 Strengthened market links for CSO agroecological products through organic fairs, fair-trade, solidarity markets (local, regional, national and international), and organic and/or sustainable certification schemes. | GEF | 1,013,229 | 1,167,857 |
| 2.0. Demonstration, deployment and transfer of renewable energy and energy efficient technologies and approaches and promote conservation and enhancement of carbon stocks | TA | 2.1: Potential financial partners, policy makers and their national/subnational advisors and institutions, as well as the private sector form multistakeholder partnerships to engage in designing, planning and monitoring dissemination and replication of energy efficient technologies 2.2: Multistakeholder partnerships develop and implement strategic projects to expand adoption of energy efficient stoves, kilns and housing to a larger number of communities and community organizations. 2.3. Multistakeholder partnerships, local policy makers and subnational/ national advisors organized in policy and innovation platforms discuss potential policy innovations based on analysis of project experience and lessons learned. | 2.1.1 Detailed analysis of successful grant project portfolios and lines of work from previous phases and from the current phase (e.g. fuel efficient stoves, efficient kilns and energy efficient housing) to identify lessons learned/best practice, new market opportunities, and feasibility, and upscaling requirements 2.1.2 Engagement of potential financial partners and public sector institutions as viable in analysis and planning 2.2.1 Based on the detailed analysis, identification of upscaling requirements and opportunities and development of a strategy(ies) to enable and facilitate upscaling 2.2.2. Community level renewable energy and fuel-efficient technologies piloted in a sub-program in the Indus Delta and elsewhere in the country based on identified feasiblity 2.3.1 Multisectoral policy and innovation platforms organized in the Indus Delta and nationally 2.3.2 Relevant project and portfolio experiences systematized and codified for dissemination to policy and innovation platform participants as well as community organizations and networks and second level organizations | GEF | 1,519,843 | 1,714,286 |
| Subtotal |  |  |  |  | 2,533,072 | 2,882,143 |
| Project Management Cost (PMC) |  |  |  |  | 126,654 | 142,857 |
| Total Project Cost |  |  |  |  | 2,659,726 | 3,025,000 |

C. Indicative sources of  Co-financing for the project by name and by type, if available

| Sources of Co-financing | Name of Co-financier | Type of Co-financing | Amount ($) |
| --- | --- | --- | --- |
| CSOs | Grantee Organizations | Cash | 750,000 |
| CSOs | Grantee Organizations | In-kind | 750,000 |
| GEF Agency | UNDP | In-kind | 400,000 |
| GEF Agency | UNDP | Cash | 100,000 |
| Private Sector | Shantech | In-kind | 25,000 |
| Corporate sector | Pakistan Petroleum Limited | Cash | 500,000 |
| Govt. Department | Commissioner Karachi | In-kind/ cash | 500,000 |
| Total Co-financing |  |  | 3,025,000 |

D. Indicative Trust Fund  Resources Requested by Agency,  Country and Programming of Funds

| GEF Agency | Trust Fund | Country/ Regional/ Global | Focal Area | Programming of Funds | (in $) |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | GEF Project Financing (a) | Agency Fee (b) | Total (c)=a+b |
| UNDP | GEF | Pakistan | Biodiversity | na | 177,315 | 16,845 | 194,160 |
| UNDP | GEF | Pakistan | Climate change | na | 1,595,836 | 151,604 | 1,747,440 |
| UNDP | GEF | Pakistan | Land degradation | na | 886,575 | 84,225 | 970,800 |
| Total GEF Resources 1 |  |  |  |  | 2,659,726 | 252,674 | 2,912,400 |

E.  Project preparation grant (ppg)

Is Project Preparation Grant requested? Yes X  No

PPG  Amount requested by agency, Trust Fund,  country and the Programming  of funds

| Project Preparation Grant amount requested: $ 80,000 PPG Agency Fee: $ 7,600 |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| GEF Agency | Trust Fund | Country/ Regional/Global | Focal Area | Programming of Funds | (in $) |  |  |
|  |  |  |  |  | PPG (a) | Agency Fee (b) | Total c = a + b |
| UNDP | GEF | Pakistan | Biodiversity | na | 5,333 | 507 | 5,840 |
| UNDP | GEF | Pakistan | Climate change | na | 48,000 | 4,560 | 52,560 |
| UNDP | GEF | Pakistan | Land degradation | na | 26,667 | 2,533 | 29,200 |
| Total PPG Amount |  |  |  |  | 80,000 | 7,600 | 87,600 |

F.  Project’s Target Contributions to Global Environmental Benefits

| Corporate Results | Replenishment Targets | Project Targets |
| --- | --- | --- |
| - Maintain globally significant biodiversity and the ecosystem goods and services that it provides to society | Improved management of landscapes and seascapes covering 300 million hectares | TBD Hectares |
| - Sustainable land management in production systems (agriculture, rangelands, and forest landscapes) | 120 million hectares under sustainable land management | TBD Hectares |
| - Promotion of collective management of transboundary water systems and implementation of the full range of policy, legal, and institutional reforms and investments contributing to sustainable use and maintenance of ecosystem services | Water-food-ecosystems security and conjunctive management of surface and groundwater in at least 10 freshwater basins; | Number of freshwater basins |
|  | 20% of globally over-exploited fisheries (by volume) moved to more sustainable levels | Percent of fisheries, by volume |
| - 4. Support to transformational shifts towards a low-emission and resilient development path | 750 million tons of CO2e mitigated (include both direct and indirect) | TBD metric tons |
| - Increase in phase-out, disposal and reduction of releases of POPs, ODS, mercury and other chemicals of global concern | Disposal of 80,000 tons of POPs (PCB, obsolete pesticides) | metric tons |
|  | Reduction of 1000 tons of Mercury | metric tons |
|  | Phase-out of 303.44 tons of ODP (HCFC) | ODP tons |
| - Enhance capacity of countries to implement MEAs (multilateral environmental agreements) and mainstream into national and sub-national policy, planning financial and legal frameworks | Development and sectoral planning frameworks integrate measurable targets drawn from the MEAs in at least 10 countries | Number of Countries: |
|  | Functional environmental information systems are established to support decision-making in at least 10 countries | Number of Countries: |

part ii:  project JustiFication

1. Project Description.

Pakistan is divided into three broad physiographical units: the northern mountains, the western highlands and the Indus plain. Around 80% of Pakistan’s land is arid and semi-arid, 12% dry sub-humid, and 8% humid. Agriculture employs more than 45% of the country’s total workforce, and deforestation and forest degradation have caused a reduction in carbon stocks (Forest Resource Assessment 2010 (FAO). Irrigation uses 90-95% of freshwater resources of the country and unsustainable water management practices, e.g. traditional flood irrigation, is contributing to water logging and salinity in farming areas causing a decline in land productivity (Government of Pakistan, 2014).

During the last century the average annual temperature in the country increased by 0.6o Celsius and, according to projections, the average temperature will increase in the range of 1.3-1.5o Celsius by 2020 (Government of Pakistan, 2010, Climate Change Task Force). Climate change will increase variability of monsoon rains and cause an increase in extreme weather events, which result in frequent floods and droughts in Pakistan (Climate Change Policy, 2013).

In Pakistan, high poverty levels and population growth, together with uncontrolled urbanization, are challenges for the country’s sustainable development. Pakistan’s population has grown at a rate of 2.5 percent per year over the last decades in rural areas and 3.5 percent per year in urban areas (UNHABITAT, 2012). On average, population growth in urban areas is estimated to be 1 - 1.5 times faster than that of rural areas. By 2030, Pakistan’s population is expected to reach 260 million people with half the population projected to live in urban areas. Pakistan is a large importer of both exhaustible and renewable natural resources and a large consumer of fossil fuels. Environmental degradation has been acknowledged as a key factor contributing to poverty in the country, affecting livelihoods and health and increasing the vulnerability of the poor to disasters and related risks. The poor are dependent on natural resources, and repeated floods as well as other internal and external factors have exacerbated their vulnerability. Environmental degradation in the country is also linked to inadequate institutional capacities.

The Indus Delta is the world’s seventh largest. Occupying an area of about 600,000 ha with mudflats and mangrove forests between Karachi and the Desert of Kutch, the Indus Delta is rich in biodiversity and natural resources including mangrove forests, fisheries, wetlands, coastal creek systems, flora and fauna as well as cultural and historical heritage. Socio-economic and environmental indicators of the Indus Delta are low, with low levels of education and health care, high food insecurity and shrinking community livelihood sources characterized by the loss of critical ecosystem services due to ongoing degradation. The total population in the three deltaic districts including Badin, Sujawal and Thatta is over 3 million in addition to one million more from the indigenous coastal communites of Karachi. These communities have been coping with the natural as well as man-made disatsers for the last two decades.

There are Six Ramsar Sites, protected under the Ramsar Convention on Wetlands of International Importance, in the Indus Delta region. Aside from the Indus Delta itself, there are five other Ramsar Sites in the region including Jubho Lagoon, Nuriri Lagoon, the Rann of Kutch, Haleji and Hadero Lake. These Ramsar sites suffer from a process of progressive degradation and a number of threats stemming from unsustainable land and resource use: agriculture; fuelwood harvesting for cooking; poaching and overhunting; salt extraction; cattle grazing; habitat destruction (particularly mangroves); and overfishing.

The Indus Deltaic region has also been the traditional home of various indigenous communities including Muhannas, Rebaries, Jats, Samees, Joagis and Bheel. These isolated and marginalized communities have suffered more in the wake of disasters and have often been displaced, with corresponding harm to their culture and livelihood practices. The Indus Deltaic Districts of Thatta and Badin are considered among the poorest districts of Pakistan.

The Government of Pakistan (GoP) recognizes the importance of creating the conditions and incentives for biodiversity conservation at the local community level, but community-based PA management and the mainstreaming of biodiversity management into local strategic land and resource use has been weak. Few funds are spent on local community-based PA management.

The GEF SGP Country Program

The GEF Small Grants Program has been a fundamental part of the GEF’s support to the production of global environmental benefits and the implementation of the UNFCCC, UNCBD, UNCCD and other multilateral environmental agreements since 1993 when the Pakistan SGP Country Program was first established. By supporting community level initiatives in the focal areas of the GEF, the Country Program has assisted Pakistani civil society over the years to become more aware of the global environmental problems in the country, how these affect them concretely and what can be done to mitigate or address them through local community based initiatives that produce global environmental benefits.

Over the past two decades, the SGP Pakistan Country Program has followed a trajectory of greater and greater strategic focus. In the early stages of Country Program implementation, grants were provided for a wide variety of community and NGO projects. As experience was gained and knowledge acquired regarding efficiency and effectiveness of project interventions and community capacities, the Country Program Strategy has become more focused on specific areas of action, aligning sustainable development objectives with national priorities, global environmental commitments and emerging institutional capacities. Several key lines of work that have been developed over the years of implementation are replication of energy efficient technologies and products that have generated local and national level benefits - especially the successful work in energy efficient housing and cooking technologies - biodiversity conservation and community protected/conserved areas, reintroduction of medicinal plant species, and land rehabilitation. Since 2007 the SGP National Steering Committee chose to concentrate SGP’s work in the Indus Delta, focusing on reforestation, recovery and sustainable use of mangroves and gallery forests, rehabilitation of wetlands, promotion of sustainable fishing practices, and general conservation of flora and fauna.

Since the Programme was initiated it has supported NGOs and CBOs to implement 273 projects covering all GEF focal areas. SGP Pakistan devised its first country programme strategy (CPS) for 1996-1998 followed by the second for 1999-2001. These strategies emphasized the importance of building long-term partnerships with all key stakeholders and providing community-based continuity to national initiatives. The key thrusts of these early strategies were clustering of partner CSOs in five specific geographic zones and the development of an integrated approach to developing synergies among projects, for example, in the salt range of Punjab. The CPS formulated for 2004-2009 called for greater participation of women and enhancing programme impacts and strengthening the monitoring and evaluation system. The strategy developed for the period 2006-2011 consolidated previous experience with the aim of creating economies of scale, enhancing programme sustainability and improving knowledge management. In GEF5 the SGP Pakistan Country Program focused on supporting the testing, demonstration and dissemination of innovations in cooking and housing technologies to reduce reliance on fuelwood as well as reduce associated costs and drudgery. Provincial and district governments have expressed interest in partnering with SGP in support of wider application of these technologies. Innovations have included fuel efficient cookstoves, energy efficient brick kilns and energy efficient housing. A complementary focus of the GEF5 Programme was ecosystem restoration in the Delta with reforestation of mangroves and gallery forests.

To enhance knowledge and impact, the Pakistan Country Program’s National Steering Committee has promoted collaborative arrangements with NGOs and government programs and institutions to strengthen effectiveness of community-based components in its specific initiatives. It has collaborated with government institutions and supported, for example, early recovery from floods by communities for the restoration of their livelihoods and rehabilitation of damaged infrastructure. Over fifty local community based organizations received first-ever grants from the SGP and have gradually emerged as capable of acting at the national level. These organizations were a vital local tool for the international humanitarian organizations and the government during the search, rescue and early recovery phases in the wake of the 2010-2011 floods.

The SGP Country Programme has partnered with key NGOs to ensure that community organizations are supported effectively throughout the project cycle. Initially, the SGP Country Program Manager discusses and analyzes key program directions in the Country Program Strategy with National Steering Committee members, the majority of whom are from civil society. Potential thematic and geographic areas of action are confirmed, and the Country Program Manager visits specific areas to meet with NGOs and community organizations to identify promising ideas and concepts. In dialogue with community organizations and the supporting NGOs, proposals are identified and developed for submission to the National Steering Committee for review and approval. NGOs selected by the community organizations and the NSC, provide technical assistance, organizational strengthening and monitoring support.

As implementation finalizes, community based projects are evaluated and modifications made to the design and implementation of the next generation of projects. This adaptive management approach has produced periodic modifications to the Country Program Strategy in keeping with emerging opportunities, new knowledge, greater capacities, and changing environment and development priorities. In particular, there is ongoing recognition of the need to continuously sharpen Country Program focus thematically to maximize efficiency and effectiveness in strengthening CSO capacities to address their environmental priorities as well as knowledge for sustainable resilient development in their areas.

The lessons learned from different lines of work are disseminated through the SGP Country Program’s network of NGOs and their own networks and to government programs and institutions. This web of collaborative relationships helps to promote best practice and provides the material and credibility for policy discussions and development. These relationships have led to the development of multistakeholder partnerships in specific geographic or thematic areas in support of longer term, multi-project efforts and creates the foundation for SGP’s work in GEF6.

During GEF 5 SGP Pakistan emerged as a provider of solutions to provincial and district governments - particularly those of Balochistan and Sindh - who sought assistance and technical facilitation on several occasions. SGP furthermore achieved breakthroughs in research and building capacities in regard to low-carbon housing, cooking and lighting.

Innovations in GEF 5

Development and mainstreaming of low-carbon cooking and housing technologies:

The “Ultimate” cook stove: During the floods of 2010-11 the biggest problem for flood victims was cooking food, and traditional mud cookstoves were not withstanding the new weather conditions. SGP supported development of a new metallic, portable, energy efficient stove by using heat entrapping technology. The prototype was further tested and ultimately over 7000 cookstoves were manufactured and distributed through 12 projects all over the country benefitting 49,000 people. This smokeless, portable and insulated invention was intended to benefit women who suffer various cooking related problems ranging from fuel-wood collection to smoke-inhalation from traditional stoves.

The “Ultimate” brick-kiln: Brick kilns are key contributors to Pakistan’s greenhouse gas emissions, primarily as a result of kiln design. The innovative design of the “Ultimate” kiln conserves heat, substantially reduces heat emissions and causes uniform combustion.  This results in an average improvement of 18 percent in energy efficiency and a decline in air pollution emissions of 40 perent. The Pakistan Brick Kiln Association is currently discussing adoption of the design with SGP.

Reintroduction of Indigenous Energy Efficient Housing Design: In the late Mughul period house design was highly energy efficient. Key features were wind-catchers and duct systems and use of energy efficient housing material. SGP has supported successful development of a prototype house using this kind of construction design and materials. Institutions including Karachi’s Mehdia Township and Mehran University of Engineering and Technology have used this experience in teaching civil engineering students. Over 200,000 compressed earth blocks (CEBs) were manufactured and utilized in construction during GEF 5 bringing the total number of blocks to 1.2 million since Aug 2009.

Other highlights of GEF 5:

- Partnership with Awaran district (Balochistan province) administration in constructing 16,000 houses in the earthquake-affected area.

- Pilot project with Karachi district administration to convert Karachi solid waste into bricks as well as to clean the polluted fish harbor and Karachi beaches.

- Over 3,500 solar lanterns and other products provided to over 24,500 people.

- Over 65,000 people from 17 tributaries in the Indus Delta have been mobilized to plant and conserve mangroves on 4,500 acres.

- Amendment to the 1980 Fisheries Act by the Sindh government as a result of an SGP project to control unsustainable fishing practices.

Communities have been able to highlight issues like industrial pollution, illegal fishing and degradation of RAMSAR sites, resulting in stricter measures from government, revision of existing laws like the Sindh Fisheries Act and community level rehabilitation of portions of RAMSAR lakes and lagoons. Similarly, communities have successfully launched reforestation and afforestation in the highly desertified area to control and minimize the impacts of land degradation and loss of habitats of significant biodiversity. To increase the scope of such community based adapatation and mitigation activites and enhance resilience, this project envisages additional interventions of similar kinds. From the perspective of climate change mitigation and adaptation, SGP Pakistan’s low-carbon, energy efficient housing, cooking and lighting technologies and products which have been developed and promoted with SGP Pakistan support, need to be further mainstreamed. In a country like Pakistan with a very high population and a record low forest cover, changing cooking habits through SGP’s Ultimate energy efficient cookstove as well as shifting housing design to greater energy efficiency supports bottom-up social transformation. The government of Sindh’s replication and upscaling of SGP supported housing technologies with a USD 2.3 million project in 2009 or the Awaran district government’s adoption of SGP-supported housing technology and training highlight the role SGP can play in devising community based solutions.

The problem to be addressed

Strengthening the resilience of communities is built primarily on climate change mitigation and adaptation and optimization of ecosystem services through biodiversity conservation and sustainable land management, including integrated water resources management, among other things. Community organizations need to act in synergy to achieve impacts of collective action at the scale of rural or urban landscapes, progressively addressing prioritized measures for adaptation and innovation. To act effectively, these organizations need the capacities, knowledge, administrative tools financing and enabling elements and opportunities to work individually and collectively. Using SGP funding, community organizations and NGOs build their capacities through learning by doing i.e. through analysis of their priorities and problems; identification of potential innovations to address them; and project design, implementation, monitoring, and evaluation of results and performance. To date, while the Pakistan Country Program has supported community organizations individually, it has also organized them in informal networks for broader knowledge sharing and information exchange. SGP Pakistan’s experience with different successful lines of work has laid the foundation for upscaling of specific technologies, practices and broader systems. A significant enabling factor for the success of the SGP Pakistan Country Programme over the years and a concrete basis for upscaling has been the establishment of long-lasting multistakeholder partnerships in specific regions and around specific themes. Partners include governmental, non-governmental and private sector actors who provide support (technical assistance, strategic guidance, financing) to community level initiatives.

The Pakistan Country Programme has built extensive porfolios in the GEF thematic areas, testing and adapting a variety of approaches in successful project implementation with community organizations with different levels of capacity. As part of its continual development of thematic and geographic lines of work based on lessons learned over time, the Country Program has been working to consolidate its more successful community approaches with a focus on upscaling to achieve economic, social and ecological sustainability. Nevertheless, community organizations still often labor under significant difficulties including underdeveloped strategic vision, weak planning and organizational skills, lack of adaptive management capabilities, limited capacities for sustained and systematic innovation, and ineffective linkages with other organizations for collective action across landscapes and sectors.

The essential problem to be addressed by this project is that the necessary collective action in Pakistan for adaptive management of resources and ecosystem processes, as well as technology development and application, for sustainable development and global environmental benefits is hindered by the organizational weaknesses of the communities living and working in affected urban and rural landscapes to act strategically and collectively in building social and ecological resilience.

The solution to the problem is for community organizations in rural landscapes of the Indus Delta and the urban landscapes of towns to develop and implement adaptive landscape management strategies that build resilient sustainable development based on the production of global environmental and local sustainable development benefits. At the same time, community organizations and NGOs can identify, test and adapt technologies that address housing, cooking and production needs in a more energy efficient or climate friendly manner in strategic locations across Pakistan. To achieve the outcomes of these integrated landscape and sustainable development plans, community organizations will implement grant projects reviewed and approved by the SGP National Steering Committee, supported by multi-stakeholder agreements involving local government, the private sector, NGOs and other partners, and evaluated as part of the broader collective process of adjusting management strategies to new information, knowledge sharing and strengthened capacity.

Barriers to achieving this solution include:

Barrier 1: Community organizations in rural landscapes, as well as community organizations in urban areas, lack a larger, more long-term vision and strategy for ecosystem and resource management and suffer from weak management capacities i.e. to innovate, test alternatives, monitor and evaluate results, and adjust practices and techniques to meet challenges and lessons learned:

SGP Pakistan in its previous operational phases, especially OP4 and OP5, focused particularly on work with CBOs in remote areas. While there have been notable successes on the ground, the fact is in most cases these interventions remain isolated and lack holistic impact or vision. The geographic or landscape approach, however, works with communities to create critical mass. Communities lack of knowledge of ecosystem function and sustainable natural resources management underpins land and resource degradation and the loss of biodiversity. Also, extreme climate variability is affecting these landscapes. The communities’ lack of knowledge of the threats and the benefits to be gained from potential new techniques, taking advantage of tangible and intangible ecosystem assets, can be offset or improved by networking among peers and also providing regular capacity building through dialogue with subject specialists and organizations with the required expertise. Communities also hold indigenous knowledge which is equally beneficial, especially when combined or enhanced with scientific knowledge.

Barrier 2: Community organizations have insufficient organizational capacities to efficiently and effectively plan, manage and implement initiatives and actions of their own design in favor of resilience objectives in urban and rural areas;

Project initiatives need to be disseminated and adapted by other smallholder communities throughout the landscape to create a critical mass of practitioners that will tip production in the landscape to a new standard of sustainable use of biodiversity. As such, it will be necessary to strengthen the capacities of community organizations to innovate, experiment, evaluate results, identify lessons and best practice, and use this knowledge to adapt to changing circumstances and information.

In GEF 5 SGP Pakistan successfully introduced innovative practices and systems that bolster landscape resilience, including agro-forestry and reintroduction of the indigenious “Hurri” system. The Hurri is a sustainable forest management system for timber and fodder. Community organizations are encouraged to adopt new approaches or adapt older indigenous practices for resilience. Networking among peers in a landscape can dynamize this process, as well as through capacity building and showcasing successful pilots.

Barrier 3: Community organizations lack coordination with other community organizations to pursue collective action for global environmental and landscape management outcomes at a landscape scale:

To achieve long term impacts on natural resource management it is crucial that community organizations act collectively and in synergy. This requires coordination among communities within an agreed strategic framework as well as recognition of the importance of developing social capital through organizational interactions within networks. Creating an enabling environment for community-driven landscape management must be supported by multistakeholder partnerships across sectors, involving community organizations and networks, local governments, the private sector, and NGOs. The Pakistan SGP Country Program has successfully networked partners from the pilot phase through GEF 5 in a Small Grants Action Network (SGAN). The network has its own elected body and mandate which focuses on identification and discussions of problems and challenges, analysis of potential solutions and identification of synergies with each other’s work. This network has emerged as an effective platform but needs further capacity building and support. In addition to this, multistakeholder partnerships in the critical landscapes addressed by this project require further strengthening, particularly in regard to new communities receiving support from SGP for the first time.

Barrier 4: Knowledge from project experience with innovation/experimentation is not systematically analyzed, recorded or disseminated to policy makers or other communities, organizations and programs

The SGP Country Program secretariat has undertaken several post-project activities to disseminate knowledge originating from successful innovations and project experience. However, at the level of communities in the landscape, dissemination and analysis is considerably lacking. The conclusions generated from analyses of project experience by communities are rarely disseminated to other communities or to policy makers or opinion leaders, and practice-based evidence for policy development related to sustainable natural resource management is rarely synthesized. The community organizations and their members may experience solid success with innovative practices and systems, but the knowledge gained should provide the foundation for entrepreneurship. The analytical capacities of community organizations should be strengthened to increase understanding of the problems and challenges facing them and build their abilities to identify potential innovations and associated risks, and test them.

Barrier 5: Community organizations lack sufficient financial resources to lower the risks associated with innovating land and resource management practices and sustaining or scaling up successful experiences.

Community organizations rarely have sufficient financial capital to take risks with innovations of untested or un-experienced technologies, methods or practices. In most cases assets in the form of personal and/or communal property have served as an often tenuous form of security, however, the risk to community organizations is lowered through the strengthening of their human capital, both individual and organizational. Grants to community organizations cover essential inputs to innovations in the form of training and capacity building, as well as necessary equipment and materials.  Successful innovations that build the capacities of community organizations through learning by doing provide the foundation for entrepreneurship and small business development. This also enables them to seek micro-credit and other commercial lendings available with formal and informal financial institutions.

Barrier 6: Community-level constraints to producing, testing, adapting, purchasing and/or using less energy intensive and more energy efficient technologies mean that significant energy and emissions savings from using climate friendly technologies are not well known at the community-level in Pakistan, resulting in inefficient use of energy and unnecessary GHG emissions in the land use and construction sectors.

Community organization usually lack the capacity to identify and adapt new technologies for energy generation or efficient use. However, the growing burden of energy and fuelwood prices is motivating communities to look for energy efficient systems and technologies. Energy efficient products supported by SGP for cooking, housing and lighting have already been very successfully introduced and replicated in areas of the country in addition to the focused thrust in the Indus Delta area. For example, in GEF 5 the newly innovated metallic portable energy efficient cookstove was successfully tested by a significant number of users. To make such solutions available for broader adoption at the grass-roots level, entrepreneurs in strategic locations around the country need to manufacture and market them as a business proposition.

A.1.2 The baseline scenario and associated baseline projects

Component 1: Resilient rural landscapes and seascapes of Pakistan’s Indus Delta for sustainable development and global environmental protection

A number of projects currently supported by UNDP (e.g. the GEF funded Sustainable Land Management and Mountain and Market projects), USAID, IUCN and WWF, among others, implement community-based interventions in certain areas of the country, but there are currently no rural socio-ecological landscape management initiatives underway in Pakistan that have an integrated, participatory, community-based approach. The Government of Pakistan does implement a number of sectoral initiatives that pursue specific objectives in regard to rural energy, irrigation and water management, and agricultural production, and ADB is also working on water resource development, but there is no integrated community-driven approach that brings these initiatives together at the landscape level to produce synergistic benefits aimed at enhancing social and ecological resilience based on global environmental benefits and sustainable development goals. The focus of project initiatives is on individual project interventions without empowering community organizations in the country to take a lead role in decision making in determining strategic land management priorities, which technologies or practices to adopt, how production systems should be designed, how they should be adapted to prevailing community conditions and how to monitor and evaluate the work and ensure efficiency of the interventions.

In summary, there are currently no other specifically focused small grants programmes in Pakistan aimed at building the capacities of rural communities in the Indus Delta to plan and manage their landscapes for sustainable development and global environmental benefits. SGP, over the past two decades, has developed strong multistakeholder partnerships in different parts of the country. These partnerships have facilitated support to community organizations implementing projects, while at the same time, SGP has been able to match community initiatives with government priorities and programmes. These partnerships and long term collaborative arrangements around sectoral initiatives in the rural landscapes constitute a dynamic baseline of programmes and relationships on which further GEF investment will be built.

Component 2: Demonstration, deployment and transfer of renewable energy and energy efficient technologies and approaches and promote conservation and enhancement of carbon stocks

At the current time, there are currently no other small grants programmes in Pakistan specifically focused on testing, demonstrating, deploying and adapting renewable energy and energy efficient technologies at the community level using a participatory approach that builds capacities for community-driven innovation.  SGP, over the past two decades, has developed strong multistakeholder partnerships in different parts of the country in relation to cooking and housing technologies.

SGP partnerships and long term collaborative arrangements around sectoral initiatives in the rural landscapes constitute a dynamic baseline of programmes and relationships on which further GEF investment will be built. More specific, additional information is as follows:

Indus Delta

Focused SGP work in the Indus Delta area since 2006 has paved the way for further innovation on energy efficient, low carbon and disaster resistant housing. A prototype house produced in 2007 with SGP support was selected by the government of Sindh for a pilot project to upscale its design and technology. The government invested $2.3 million in 2009 for the Benazir Housing Project. In GEF 5 the government of Balochistan partnered with the SGP for housing technology transfer and training of master trainers – the project was shortlisted for the UN-HABITAT award. These kinds of partnerships have facilitated support to community organizations to implement projects, while at the same time, SGP has been able to match community initiatives with government priorities and programmes.

SGP Pakistan is known for its support to innovation, especially in regard to housing and cooking technologies. The recent GEF National Portfolio Formulation Exercise held in April 2015 featured SGP-supported innovations, especially low-carbon energy efficient housing and cooking technologies which sparked discussions among media and delegates. In GEF 5, the “Ultimate EE stove” was a key successful technology. After the prototype, over 9,000 units were manufactured and distributed for use and testing by users in different parts of the country. Another technology – energy efficient low carbon housing as a practical housing solution for poor and vulnerable communities - has been supported in partnership with the government of Pakistan, who provided US$ 2.3 million to UNDP for pilot production of 400 housing units. In GEF5 - apart from design improvements and re-introducing indigenous energy efficient housing technologies - training and mechanization of the production of energy efficient housing materials have been carried out. Changes to the design of conventional brick kilns have made them much more efficient and have contributed to decreasing carbon intensity of housing material production.

In a country where forest cover has dropped to around five percent, and where 80 percent of cooking depends on fuelwood, highly efficient cook stoves and reduced timber use in housing promise to produce a significant environmental impact, if broader adoption can be leveraged.

### A.1.3 The proposed alternative scenario

Component 1:  Resilient rural landscapes and seascapes of Pakistan’s Indus Delta for sustainable development and global environmental protection

GEF financing and co-financing will be applied to overcome the barriers mentioned above and to add value, where appropriate and possible, to existing initiatives by the government, NGOs and/or the private sector in the Indus Delta. It will contribute to the long-term solution of adaptive management for social, economic and ecological resilience. GEF funding will provide small grants to NGOs and community organizations to develop integrated land use management plans and implement community projects in pursuit of strategic landscape level outcomes related to resource management for biodiversity conservation, climate change mitigation and adaptation and integrated water resources management.

Funding will also be available for initiatives to build the organizational capacities of specific community groups as well as landscape level organizations to plan and manage complex initiatives and test, evaluate and disseminate community level innovations. Resources will be made available through the SGP strategic grant modality to upscale proven land and resource use systems or practices based on knowledge gained from analysis of community innovations from past experience during previous phases of the SGP Pakistan Country Programme.

The alternative to be carried out by this project will be based on a mix of community-driven projects within the landscape with the aim of developing synergies among initiatives within a strategic planning framework that expedites adaptive landscape management to enhance social and ecological resilience.  The alternative will build on previous successful experience and lessons learned from sustainable land and resource management for conservation, livelihoods and income. Strategic projects will be financed that enhance these impacts.

Consistent with the overall GEF guidelines, the general approach or strategy for BD has been to identify and fund community projects that are simple yet innovative in addressing the challenges to conserve and sustainably use biodiversity in different ecosystems and ecological complexes of the Indus Delta, in particular in regard to the Narerri Jabbo Lagoon Complex; degraded watersheds of the deltaic districts; and the Sir, Kajhar and Warri creek mangroves.

These three areas have been identified in the PIF at this pre-preparation stage and will be assessed in more detail, in a participatory approach, during the PPG-financed project preparation phase for more specific global environmental values, threats to biodiversity and potential solutions.  The exact boundaries of the landscapes to be addressed during GEF 6 will be delineated with more precision during this time.

SGP has over the past 15-20 years supported communities in demonstrating good practices that have yielded tangible results in conservation, reducing the loss of biodiversity and establishing the link of biodiversity to local economies and livelihoods of targeted communities. The recent GEF-UNDP Joint Evaluation case study for Pakistan, and the project Terminal Evaluation Report both indicate the Country Program’s success in its approach to community level actions. This approach is consistent with an ongoing process of adaptive management and will be further sharpened during OP-6.

The good practices developed and identified – many with SGP support – include mangrove reforestation, reforestation of gallery forests along the Indus and its tributaries, stakeholder managed natural regeneration of arid and semi-arid vegetation complexes, eradication or control of invasive species, establishment of community conservation areas, sustainable use of deltaic habitats for small scale ecotourism, reestablishment of wetland ecosystems through small-scale infrastructure, use agreements and protocols, etc.  The essential ingredient in the success of these measures is to establish or consolidate the link between conservation and sustainable use of the Indus Delta’s biodiversity and the livelihoods and income generation activities of the local population.

Central to the approach will be sensitizing, equipping and capacitating communities to own and manage their rights and access to resources in an equitable way and to clearly identify the value and benefits of biodiversity to the sustainability of their livelihoods.

By refining its geographic focus in the Indus Delta, the SGP approach will generate impacts across a defined area with significant BD. A geographically defined cluster of projects (10-12) will be able to create significant impact on habitats, e.g. the rehabilitation of the degrading Ramsar sites present in the Indus Delta region.

The Indus delta contains the largest desert climate mangrove forests in the world. Fish, crustaceans and invertebrates reproduce and fish fry shelter among the aerial roots. The Indus mangroves are also home to large numbers of waterbirds, including Greater flamingos and Dalmatian pelicans, and as many as 60,000 migratory birds arrive each year as part of the Indus flyway.

The Indus river is habitat for Marsh Crocodiles (Crocodylus palustris), Smooth Coated River Otter (Lutrogale perspicillata), Fishing Cats (Prionailurus viverrinus) and Indus River Dolphin (Platanista gangetica minor), among several other species. In addition, the Indus delta is home to high value indigenous breeds of Kamori goat, Richhi Sheep and Deltaic Kharai Camel. At least eight types of cobra and an indigenous endemic snake species, the Sind krait (Bungarus sindanus), are also found in the delta.

GEF Biodiversity resources, although relatively small in sum, will be supplemented with Land Degradation resources in this landscape, as the geographic focus is the same and the LD benefits will spillover to impact BD.

The project will also address land degradation, deforestation and desertification by promoting good practices in sustainable land management such as stakeholder managed natural regeneration, improved integration of livestock-cropping systems, reforestation of gallery forests, use of windbreaks, field contouring, small-scale water management  infrastructure, and other elements, as well as scaling-up successful interventions. The proposed strategies and projects in sustainable land management are expected to lead to increasing land productivity, reductions in soil erosion and deforestation and adoption of sustainable agroecological practices (e.g. agroforestry, rain-water harvesting, and crop diversification). An important focus under LD will be to identify and support opportunities for agroforestry, improved livestock management, and forest restoration that create local and national socio-economic benefits as well as contribute towards global environmental benefits. These projects will also complement some of the work under BD focal area.

Although subject to confirmation during the project preparation phase of this initiative, three landscapes in the Indus Delta will be targeted in particular in GEF 6:

Narerri-Jabbo Lagoon Complex

Both Narerri and Jabbo lagoons were granted Ramsar status because of their rich biodiversity. The lagoons formed a natural barrier between the sea and fertile agriculture lands, however, both lagoons have begun facing gradual degradation after the massive 1999 cyclone. A portion of the Narerri lagoon was successfully rehabilitated with the support of a SGP project in 2009. However, the unprecedented floods and heavy rains of 2010-11 augmented degradation because of the loss of protective dykes and barriers that impeded industrial pollution of the lagoons. The successful rehabilitation pilot of 2009 will be scaled up throughout the Lagoon Complex with the aim of aim of making a comprehensive contribution to the conservation of biodiversity in the Indus Delta.

Degraded watersheds of deltaic areas of Thatta and Badin districts

There are over a dozen small and medium lakes and lagoons in the coastal belt of Thatta and Badin districts, which used to be major fresh water reservoirs. However, the 1999 cyclone affected these lakes and lagoons through siltation. These waterbodies’ capacities to retain rainwater or flood runoff has decreased dramatically. These same bodies can again be rehabilitated to enhance rainwater harvesting. As a pilot supported in GEF 5, the Shaikh Kirhio Dhoro watershed was successfully rehabilitated. Rehabilitation of the lakes and lagoons not only regenerates biodiversity but also provides a natural buffer against sea intrusion.

Mangroves along Sir, Kajhar and Warri creeks

In previous operational phases and also in GEF 5 SGP supported the successful reforestation and conservation of thousands of acres of mangroves. These creek mangrove ecosystems, of the 17 creeks of the Indus Delta, have been neglected in the past. Several small and medium size canals and runoff drains bring fresh water to these creeks, and the area has proven to be apt for mangrove reforestation.

Strategic lines of work to be supported in these three areas may include:

Agro-afforestation and improved ecosystem services

SGP in GEF 5 successfully tested a model of agro-afforestation and encouraged farmers to start planting trees in semi-fertile lands. Pakistan has very low forest cover, and the price of fuelwood and timber is rising at an alarming rate. Trees like Acacia nilotica or Moringa oleifera are both a good source of food for humans and animals, in addition to biomass and fuelwood. Agro-afforestation combines agricultural and forestry technologies to create more diverse, productive, profitable, and sustainable land-use systems.  Agroforestry systems will be encouraged as a means of optimizing ecosystem services and raising productivity and sustainability of agroecosystems in the Indus Delta landscape.

Ecotourism and sustainable tourism

In Pakistan the attractive wetlands, beaches, hill stations and archaeological sites receive thousands of tourists, but the industry lacks a strategic direction and a regulatory framework, thus leading to often severe damage to these resources. For example, Keenjhar lake in Thatta district receives over 17,000 tourists every weekend. There is no proper solid waste management system, and tons of waste generated by these visitors sinks to the bottom of the lake. In many contexts, development of sustainable tourism has helped to recover, add value, and revitalize lost or disappearing local and indigenous cuisines, traditions, and knowledge about culture and biodiversity, as well as generating green jobs and developing entrepreneurial capacities while reducing pressure on biodiversity, land and water. Ecotourism pilots will be supported in areas where there is tourism potential in the Indus Delta.

Rare and endangered livestock breeds

In areas of the Indus Delta many high value indigenous breeds of livestock have either vanished or fast declining. In previous phases of the GEF, SGP focused on recovering rare indigenous goat, camel and horse breeds through sustainable use and improved productivity through better animal husbandry. In GEF 6 the SGP will support the conservation of rare and endangered livestock breeds and will encourage the pursuit or development of market incentives to sustain improved animal husbandry practices.

Water resource management

Extreme weather conditions alternate in the Indus Delta area. Extreme drought is followed by floods and heavy rains. Because of several natural and man-made disasters, small and medium lakes and lagoons characteristic of the area have become shallow and degraded. Rainwater harvest and storage by enhancing natural vegetation and sustainable agroecosystems in these watersheds and increasing the retention capacity of wetlands will not only encourage potential new ways of generating income but also create a buffer against sea intrusion and recharge the areas’ aquifers.

Identification of potential upscaling initiatives will take place during project preparation based on analysis of previous experience, lessons learned and prospects for sustainability. Preliminary possibilities include expansion of programs for land management (soil conditioning through improved productivity and sustainability of agroecosystems, agroforestry plantations); water resource management (rainwater harvesting and treatment); and sustainable use of biodiversity (medicinal plants, farmer managed natural regeneration,  ecotourism).

Formal multistakeholder groups will be consolidated that will incorporate governmental and non-governmental actors. These partnerships will provide technical assistance, strategic guidance and financial support, where possible, to community organizations for individual community initiatives, as well as landscape level projects and strategic upscaling projects.

Project experiences will be systematized and knowledge generated for discussion and dissemination to local policy makers and national/subnational advisors, as well as landscape level organizations, NGOs and other networks.

More precise integrated land use management strategies will be developed based on analysis of the landscapes, their ecosystem characteristics and potential community organizations. Elements to be analyzed will include biodiversity value, land use trends and patterns, opportunities for application of innovative agroecological practices and systems, previous SGP supported initiatives, poverty and inequality levels, disposition of communities and local authorities, potential partnerships with NGOs, the private sector and others, and other factors.

Component 2: Demonstration, deployment and transfer of renewable energy and energy efficient technologies and approaches and promotion of carbon stock enhancement and conservation

The SGP has developed partnerships over the past decade and a half that permit it to quickly identify community level needs, potential innovations, and collaborative institutions from both the public and private sectors. This project will strengthen multistakeholder partnerships involving private and public sectors to engage in design and implementation of initiatives for broader adoption.  The SGP will provide strategic project funding (up to USD 150,000) to support these partnerships and initiatives.

The SGP’s attention to introducing and implementing workable solutions that are environmentally sustainable, economically feasible and technologically appropriate is well-recognized by civil society, government and private sector entities in Pakistan. It is especially appreciated for its preparedness and access to diverse stakeholders for swift implementation in communities that government finds hard to reach.

The SGP Pakistan Country Program has over a decade of experience supporting the development, innovation and promotion of energy efficient technologies and systems for communities, many of which are remote and isolated.  It has produced manuals and brochures detailing the technologies whose development it has supported. See in particular https://www.dropbox.com/sh/4kok54buwidg5g9/AACBJjm8wXKpajmumiDQshnQa?dl=0

Of the SGP Upgrading Country Programs, worldwide, SGP Pakistan is the leader in direct involvement in development of community level technologies like fuel-efficient stoves, fuel-efficient brick kilns, and energy efficient housing.  SGP has directly supported the development of these technologies through on-the-ground consultations and collaboration with innovators from both academic institutions and the private sector.  The innovations are tested under field conditions and piloted through grants in communities with the aim of upscaling through private sector and/or government programs for broader adoption.

The Ultimate efficient fuel stove is an example of a technology developed, prototyped, tested, and then piloted through 12 community level projects utilizing 9,000 units and benefitting around 49,000 people. Similar processes can be described for efficient brick kilns and housing.

SGP has been successful in supporting the development, testing, manufacture and broader adoption of these technologies for the following reasons:

- A continuous focus on identifying workable solutions to community-identified local problems through diverse products and systems built through a process of consultation, participatory research and development and technological innovation

- Testing and piloting workable models (e.g. EE products and technologies) across diverse landscapes and with diverse target groups

- Close interaction with and cultivation of strong partnerships with key industry players (particularly the private sector and academia) for technological developments and refinements as well as for mobilizing external financial resources

- Replication and broader adoption of SGP-introduced products and technologies, often to remote and underserved communities, through grants complemented by co-financing from communities and micro-credit groups.

- Demonstrations of the technologies on the ground have resulted in requests by provincial and city governments (e.g. Punjab, Karachi) for extension, training and replication of specific technologies to their constituent communities.

- SGP has supported the training of artisans and small enterprises in the manufacture of the technologies and is discussing potential financing options for broader application with credit institutions and government agencies.

GEF incremental funding and co-financing will be applied to replicate and mainstream successfully tested technologies whose development SGP has supported in previous Operational Phases, in a strategically designed programmatic approach to maximize the impacts and sustainability of upscaling. These upscaling initiatives will overcome the barriers mentioned above, and add value, where appropriate and possible, to any existing sectoral initiatives by government or the private sector in two districts of Pakistan.

The UNDP SE4ALL initiative in Pakistan will provide a foundation for this component’s activities and the Rapid Assessment and Gap Analysis of the Energy Sector  conducted by the project provides baseline information regarding the energy situation in the country.

CBOs and NGOs will receive 90% of the overall GEF allocation earmarked for Climate Change to implement energy efficiency projects utilizing the tested technologies as well as for their systematic dissemination.  Projects will be aimed at adapting proven technologies to community needs, using past experience with technology adoption projects as a guide. Funding will also be available for initiatives to build the organizational capacities of specific community groups as well as allied organizations to plan and manage complex initiatives and test and evaluate community level innovations and disseminate best practices. Such resources will be made available through the SGP strategic grant modality to upscale proven technologies, systems or practices based on knowledge gained from analysis of community innovations from past experience gained during previous phases of the SGP in Pakistan. The selection of specific technologies for upscaling will take place during project preparation. Likely candidates for upscaling include solar water heaters, solar powered lighting, efficient water resource management, and energy efficient housing, lighting and brick production. The PPG activities for this component consist of a broad scoping exercise that will help identify the viability and prospects of adoption of the potential technologies and prototypes developed and tested during OP-5, in specific contexts and potential locations/communities where no prior SGP experience exists. This exploration under the PPG will involve obtaining feedback from communities and will cater to their specific requirements on a region-by-region basis.

This project component will be carried out in two urban areas (towns) of the Indus Delta, to be defined more precisely during the project preparation phase. GEF SGP has supported construction of 900 units of an energy efficient earthquake resistant low cost model house since 2008 in Pakistan. The potential for sustainable energy efficiency in towns in Pakistan is high. Other partners include Local Governorates; National Council for Women; Ministry of Climate Change; Business Sector; Ministry of Water and Power. Towns suffer from ineffective systems of solid waste and water management and energy use and supply. SGP has supported communities and NGOs in the implementation of more than 20 projects addressing a variety of issues in urban areas. These organizations include Comprehensive Development Association – NGO; Business Association in the National Council for Women; Ministry of Electricity; Aga Khan Foundation. The biggest towns are strongly integrated into the production landscape matrix and causes of some urban environmental problems are linked directly to local land use (water, solid waste management, biomass energy). SGP has developed the capacity of more than 18 NGOs and CBOs in energy efficient practices and systems during GEF 5.

Criteria for further confirmation regarding urban landscape or neighborhood selection will include poverty and inequality levels, disposition of neighborhood communities and local authorities, land use trends and patterns, opportunities for application of renewable energy, energy efficiency and water efficiency technologies, potential partnerships with NGOs, the private sector and others, and other factors. Selection of urban landscape or neighborhoods will take place as part of project preparation to be funded by the PPG requested here.

### A.1.4. Global environmental benefits

Global environmental benefits (GEB) generated by the SGP Upgrading Country Programme as a result of the project proposed here can be estimated simplistically over the short term as a result of potential aggregated impacts from hypothetical future individual grant projects. However, overall benefits over the longer term will be a function of the synergies created between projects through programmatic approaches such as the integrated landscape management and sustainable development strategies proposed here. Under these approaches, community groups, local authorities and NGOs form multistakeholder partnerships and develop and implement landscape (three) and neighborhood (two) resilience strategies based on outcomes linked to biodiversity conservation and ecosystem services, sustainable land management, climate change mitigation, and adaptation, all of which are shaped and defined by their relation to local priorities for food security, income generation and the development of social capital for the global environment and socio-ecological resilience.

These strategies will define the types and numbers of community projects required to meet the selected outcomes; at that point, once the strategies have been developed by the communities a more credible, detailed accounting of potential global environmental benefits will be possible. At the same time, the project’s multistakeholder partnerships will explicitly develop strategic projects to upscale successful SGP-supported technologies, practices or systems identified from previous phases of the SGP Pakistan Country Programme. As such, GEB from these initiatives will be more precisely defined during project preparation and validated during implementation.

The Pakistan Upgrading Country Programme will focus on two specific strategic directions:

Component 1: Resilient rural landscapes and seascapes of Pakistan’s Indus Delta for sustainable development and global environmental protection

This line of work is expected to result in landscapes under adaptive management for global environmental benefits and local sustainable development. A reasonably precise measure of the area (in hectares) to be brought under integrated management for global environmental benefits will be made as a result of project preparation. Greater food security and/or generation of employment and income for resource-dependent communities from sustainable management of ecosystem processes and services of biodiversity (ecotourism) and other resources will provide the primary economic incentive to these communities, individually and collectively, to conserve biodiversity and optimize ecosystem services. Community organizations will build their capacities to plan and manage resources adaptively and in synergy with each other, thus contributing to the sustainability of biodiversity conservation, land management and climate mitigation. The knowledge obtained from analysis of project experiences and lessons learned will be disseminated through SGP's national network of stakeholders and used in upscaling successful initiatives. Prospective candidates thus far for upscaling include energy efficient stoves (for their effect on forest integrity), land management (agroecological systems and practices; agroforestry) and water resource management (water harvesting, efficient irrigation). Multistakeholder landscape level policy and innovation platforms will be established to analyze lessons learned from projects and to monitor and evaluate progress towards project and landscape level outcomes. The Country Programme team, including the  National Steering Committee, will identify and discuss potential policy applications with local policy makers and national/subnational advisors.

Component 2: Demonstration, deployment and transfer of renewable energy and energy efficient technologies and approaches and carbon stock enhancement and conservation

This line of work is expected to result in greater grassroots support for the development and maintenance of integrated low-emission urban/village systems. Concrete experience by community groups on the ground with neighborhood planning and management of the urban environment will be gained through projects addressing energy efficiency, land use planning and green infrastructure, solid waste management, and renewable energy generation and applications. Sustainable development strategies will identify outcomes related to the GEF focal areas, aligning them with neighborhood priorities for income generation/savings, security, development of social capital, health improvement/maintenance, and other priorities. The knowledge obtained from the ongoing analysis of project experiences and lessons learned as proposed in Output 2.1.1 will be disseminated through knowledge networks and used to adjust the technologies as needed, to inform policies, and in upscaling successful initiatives from previous phases and from this phase; prospective candidates for upscaling include energy efficient cookstoves and brick-kilns, energy efficient housing material and construction, solid waste bricks, and land and resource management aimed at enhancing biomass and soil carbon. Multistakeholder neighborhood or district level networks will be established to analyze lessons learned from project and programme performance and discuss potential policy applications with local policy makers and national/subnational policy advisors.

Finally, the Country Programme will, as part of its OP6 strategy and in continuation of its OP5 strategy, link community organizations to larger government and non-governmental organizations and initiatives (including FSPs financed by the GEF) involved in implementing Pakistan’s policies related to development of low emissions urban systems, sustainable rural energy and landscape management for climate resilience based on biodiversity conservation and optimization of ecosystem function. As such, SGP will continue to work with GEF Full-sized Projects, especially in the fields of land management and biodiversity conservation, to promote community-based approaches and help to deliver local development benefits (UNDP’s Sustainable Land Management II and Mountain and Markets projects). SGP will collaborate closely with various national NGO networks to promote global environmental values and their integration with sustainable development priorities. NGOs and CBOs will play increasingly significant roles in efforts to achieve national priorities and the relevant global benefits during this phase of the SGP. These include:

- Strengthening the linkages between NGOs and CBOs, GEF projects, the government counterparts and already existing networks working in the field of environment and sustainable development to facilitate exchange of experience, engage technical support, monitor and disseminate successful experiences and knowledge, which will help to replicate or upscale successful lessons in different areas;

- Establishing new networks of NGOs implementing projects in the same focal and/or geographic areas to strengthen their cooperation, coordination and networking through a strategy on integrated land use management and sustainable development;

- Establishing a link between national and global NGO communities to share good practices internationally and ensure the dissemination of experiences and lessons learnt.

### A.1.5. Innovativeness, sustainability and potential for scaling up

Innovativeness - This project proposes to carry out participatory, multistakeholder, landscape management in rural and urban areas aimed at enhancing social and ecological resilience through community-based, community-driven projects to conserve biodiversity, strengthen ecosystem services, manage land and water sustainably, and mitigate and adapt to climate change. Taking advantage of the knowledge and experience gained from global and national landscape level initiatives delivered by SGP through its various landscape management initiatives, this project will build on previous work in the Indus Delta to pilot landscape planning and management in one or more sites of the Delta. Building on experience and lessons learned from previous SGP operational phases in Pakistan, the Pakistan Upgrading Country Program will assist community organizations to carry out and coordinate projects in pursuit of outcomes they have identified in the landscape plan and sustainable development strategies. This will build community ownership of individual initiatives and capacity of multistakeholder organizations for landscape management overall. Coordinated community projects in the landscape will generate ecological, economic and social synergies that will produce greater and potentially longer-lasting global environmental benefits, as well as increased social capital and resilient sustainable development benefits. In particular, capacities of community organizations will be strengthened through a learning-by-doing approach in which the project itself is a vehicle for acquiring practical knowledge and strengthening organizational skills in a longer term adaptive management process. The project will also take prior years’ experience and identify and implement a number of potential upscaling opportunities during this project’s lifetime.

Sustainability – The sustainability of landscape management processes and community initiatives is predicated on the principle – based on SGP experience - that global environmental benefits can be produced and maintained through appropriately designed community-based sustainable development projects. Previous phases of the SGP Pakistan Country Programme have identified and promoted clear win-win opportunities with community initiatives and clusters of initiatives in areas such as sustainable use of biodiversity and genetic resources (agro-biodiversity, watershed protection, ecotourism), agro-ecological production practices and systems, sustainable land and water management, energy efficiency and sustainable forest management. For example in phases 2 to 4, the smokeless energy efficient mud stoves were introduced in the remotest parts of Pakistan. These brought changes to cooking practice. However, in GEF 5 SGP Pakistan took this effort further with the production of energy efficient, metallic, portable smokeless stoves. SGP believes that the likelihood of sustainability with respect to community adoption of the smokless stove is high on the following grounds: (i) the non-perishable, portable, detachable and flexible metallic stoves being introduced are more resilient and convenient as compared with the traditional mud-stoves; and, (ii) the vanishing forest cover and the high cost of fuel wood in Pakistan (ranging between USD4-7 per 10kgs) makes it unaffordable for an ordinary household and provides the incentive for households to look after the fuel-efficient stoves.

Similarly, initial experiences with energy efficient housing material and design in GEF 3 led to testing in GEF 4 and entry level commercial applications in GEF 5; upscaling of this experience will be supported in GEF 6.

Sustainability of landscape planning and management processes will be enhanced through the formation of multistakeholder partnerships, involving local government, national agencies and institutions, NGOs, the private sector and others at the landscape level and the adoption of multistakeholder partnership agreements to pursue specific landscape level outcomes related to biodiversity conservation, water management, etc. NGO networks will be called upon for their support to community projects and landscape planning processes, and technical assistance will be engaged through government, NGOs, universities, academic institutes and other institutions.

Market assessments, which are essential for sustainability and upscaling, will be carried out at different levels: market assessment of individual EE technologies will be carried out by the SGP Secretariat and the National Steering Committee members with support from specialist organizations and the private sector with which SGP has longstanding partnerships; market assessments required by CSOs/CBOs grant proposals with market-based components will be the responsibility of the project proponents at the proposal submission stage and refined upon review by the SGP Secretariat and the NSC that is responsible for ensuring project quality at entry.

Upscaling potential - Based on earlier experience, there is evidence that small individual grants lead to demonstrable impact and generate interest at various levels for upscaling to take place. This is illustrated by the impact created under OP-5 where three provincial governments and other entities showed interest in upscaling SGP introduced products and technologies (energy efficient housing, brick kilns and cook-stoves) for which technical manuals were developed and distributed to the interested parties by the SGP Pakistan Country Program. The upscaling and associated national level actions are primarily the responsibility of governmental entities represented in the NSC, i.e., the Ministry of Climate Change (MoCC), the SGP Secretariat and the NSC. A recent example of this is the upscaling initiative carried out by the MoCC’s recommendation to the Punjab government to adopt the SGP’s energy efficient brick-kiln model.

An essential output of this project is the upscaling of initiatives that have been piloted successfully during previous phases of the SGP Pakistan Country Program. The premise of upscaling in this context is that the aggregate of community adopters of successful SGP-supported technologies, practices and systems from previous SGP phases has been slowly acquiring critical mass to reach a tipping point of adoption more broadly by rural constituencies of adaptive practice and innovation. Multistakeholder partnerships in the Indus Delta and in specific sectors or areas (e.g. housing, brick production) to be addressed by this Upgrading Country Programme will analyze the prospective critical mass of community adopters required to reach the tipping point in each of the landscapes for specific technologies, practices or systems and design and implement a program of action to reach it.

Resources will be made available through the SGP strategic grant modality to finance key elements of the upscaling initiative to reduce the risk to other donors and investors. The multistakeholder partnerships will identify potential upscaling opportunities, analyze and plan upscaling processes, engage established microcredit and revolving fund mechanisms to finance upscaling components, design and implement the upscaling programme, and evaluate its performance and impacts for lessons learned for adaptive management, policy discussion and potential extension of the model to other areas of the country. Identification/confirmation of specific potential upscaling initiatives will take place during project preparation.

# 2.  Stakeholders. Will project design include the participation of relevant stakeholders from civil society and indigenous people?  (yes X /no )

The primary stakeholders of the Pakistan GEF-SGP are the community-based organizations and local communities who will receive grants to produce benefits to local sustainable development and the global environment and ultimately to the social and ecological resilience of their communities and landscapes. Women, ethnic minorities and youth will be especially invited to participate in the landscape planning and management processes as well as to submit project proposals for specific initiatives. Stakeholder organizations will be identified first based on the experience of SGP over 20 years, and with more precision through a participatory process of planning and consultation to take place during the process of project formulation and during implementation of the project itself.

The bulk of SGP’s work over the years has been with marginalized and poor communities, many of which are indigenous, through small community based organizations. The proposed project places particular importance on reaching out to indigenous communities, both participating and those new to the SGP. SGP has been working with a number of indigenous peoples including Kalash, Jat Cameleers, Koochis, Muhannas, Rebaries, Kabootras and Rawiras.

SGP has supported the recuperation of local/traditional knowledge as a foundation for enhanced technical assistance. The preservation and documentation of this indigenous knowledge has also remained a key focus under the knowledge products developed under earlier GEF cycles, including GEF 5.

# During the project preparation phase financed by the PPG, an analysis will be carried out of IP conditions and capacities which will be used to develop a strategy for greater and more effective engagement of SGP with the identified IPs.

NGOs, whose work has been to support CBOs and communities in pursuing local sustainable development, are also important stakeholders. These will include those NGOs who have the interest and capacities to provide key support services to community-based projects, including technical assistance and capacity development. These NGOs will be identified during the process of project formulation and implementation to initiate with approval of this proposal.

Project stakeholders can be identified and categorized as follows:

# Community organizations: Principal participants in landscape planning exercises; first-order partners in the multistakeholder partnerships for each landscape; implementing agents of community and landscape level projects. The project will favor organizations run by and for women, ethnic minorities and youth.

Second level organizations: Landscape level: primary participants in landscape planning exercises; first-order partners in the multistakeholder partnerships for each landscape; implementing agents of landscape level projects; participants in landscape level policy platforms. Potential partners and stakeholders include Rural Elevation Services Society, Sindh Agriculture Development Association, Bahar-al-Sindh Foundation (BASF), Sindh Radiant Organization (SRO), Kuchlak Welfare Society (KWS), Quetta, SCOPE, RDHR, Green Circle Organization Lahore, GODH Lahore.

SGP National Steering Committee: Functions as the Project Steering Committee. The  NSC is composed of government and non-government organizations with a non-government majority, a UNDP representative, and individuals with expertise in the GEF Focal Areas, in compliance with the SGP Strategic Operational Guidelines. The NSC is responsible for grant selection and approval and for determining the overall strategy of the SGP in the country. NSC members serve without remuneration and rotate periodically in accordance with its rules of procedure. The Government is usually represented by the GEF Operational Focal Point or by another high level representative of relevant ministries or institutions. The NSC assesses the performance of the Country Programme Manager with input from the UNDP CO and the UNDP-GEF Global Coordinator of the Upgrading Country Programs. The NSC also contributes to bridging community-level experiences with national policy-making.

# SGP Country Programme Manager (National Coordinator), and team: Responsible for the overall implementation and operations of the SGP, acting as secretary to the National Steering Committee, mobilizing cofinancing, organizing strategic partnerships with government and non-governmental organizations, and in general for managing the successful achievement of country programme objectives as described in the Project Document.

# NGOs:	Lead and facilitate participatory baseline assessments and landscape planning processes, as needed; partners in multistakeholder partnerships; signatories to community level partnership agreements; provide technical assistance to community organizations for implementation of their projects; potential participant on policy platforms. Potential NGO stakeholders will include those with experience in the specific areas of action.

Local, provincial governments, including districts, tehsils and union councils: Participate in baseline assessments and landscape planning processes; partners in multistakeholder partnerships; signatories to community level partnership agreements; primary participant on policy platforms.

# National entities, including the Ministries of Climate change, Food Security and Research, Water and Power, Commerce and Textile Industry, Pakistan Environmental Protection Agency and others. Partners in multistakeholder partnerships; selected members of National Steering Committee; as relevant or appropriate, provide technical assistance to community organizations for implementation of their projects; primary participant on policy platforms.

# Private sector: Partners in multistakeholder partnerships; signatories to community level partnership agreements, as appropriate; potential participant on policy platforms. Potential collaborators include enterprises with social responsibility components, chambers of commerce, Regional Micro and Small Enterprises and certification enterprises. These entities include Shaan Technologies, Enerdynamic Canada, and Bahria Foundation

# Academic institutions, both public and private: Assist in participatory baseline assessments and landscape planning processes; partners in multistakeholder partnerships for each landscape; signatories to community level partnership agreements, as appropriate; provide technical assistance to community organizations for implementation of their projects; potential participant on policy platforms. These entities could include  Mehran University of Engineering and Technology, Jamshoro, Sindh Pakistan, Waterloo University Canada, University of Toronto, Canada and  York University Canada.

# 3. Gender Consideration. Are gender considerations taken into account? (yes X /no ).

# Gender will be considered throughout this project’s design and implementation. The project will prioritize work with women’s groups.  The Country Programme team, as part of project preparation, will formulate a specific strategy to engage women’s groups as primary actors in landscape/neighborhood management. Gender will be taken into account in the project to better understand how women’s empowerment can strengthen communities. The project will mainstream gender into all activities, for example, new  technologies to be tested and experienced will be analyzed by women’s discussion/training groups. The Country Programme team will work with the gender focal point on the National Steering Committee to identify potential project ideas for initial discussions with women’s groups.  Gender-sensitive NGOs will be engaged to support women’s groups in defining grant project objectives and designing grant project activities.  Women/girls groups will evaluate their projects’ performance to identify lessons and knowledge for adaptive management as well as gender specific policy recommendations.

A specific gender analysis at the design stage will be key to tailoring well-defined interventions. It will serve as an important input to ensure that gender considerations are applied in a consistent manner across the entire project cycle and in the preparation of a gender mainstreaming strategy that will form part of all the grants for the IPs. This detailed gender analysis will be carried out as part of project preparation financed by the PPG.

Moreover, for effective mainstreaming, appropriate gender related outputs and outcomes will be reflected under all other outcomes and outputs and not treated as a stand-alone outcome/output. Sex-disaggregated indicators for tracking and monitoring purposes will be developed.  The gender analysis, among other aspects, will explore women and men’s power relations and their access to and control over resources in specific areas, changes in gender roles and division of labor, changes in rights, decision making and empowerment at different levels etc., and the likely impacts on different groups of men and women in the geographic focus area of the SGP Country Program as well in relation to different thematic elements e.g. energy efficient stoves, kilns, housing.

The analysis will include a focus on specific groups of beneficiaries and interest groups. Some categories of interest are likely to include female business owners/entrepreneurs, female single household heads, small farmers, etc.

The women based organizations that have been supported by SGP include 1) Trust for Rural Uplift, Culture and Environment (Truce) 2) Pakistan Hoslamand Khawateen Network (PHKN), and 3) Alqaim Women’s Development Organization, among others.

# 5. Risks

# Table 2. Risks, rating and proposed mitigation measures.

| Identified risks | Potential consequence | Risk rating L: Likelihood I: Impact | Mitigation measures | Risk category |
| --- | --- | --- | --- | --- |
| Communities may not perceive the benefits of proposed projects and view them as conflicting with their own livelihood development initiatives. | Perceiving the project activities as conflicting may have a negative impact on project implementation. | L:Low I:Medium | Grant proposals will not be approved if they cannot demonstrate the full support of local communities. | Organizational |
| Continuation of the country’s instability in terms of security | Instability may have a negative impact on resource mobilization, on the implementation of SGP funded projects’ activities and may also affect the sustainability/accessibility of the project’s activities. | L: Medium I: High | Insecure areas will be avoided for the selection of target landscapes. By adopting a participatory approach and involving all local stakeholders, risks related to social instability will be reduced. In addition the project will mainly work through local organizations and provincial authorities to coordinate and implement field level activities. | Contextual |
| Low capacity and awareness of local NGOs and CBOs to address global environmental problems in selected geographical areas. | Low capacity and awareness of local NGOs and CBOs may decrease demand for community driven projects as well as influence implementation of grant projects once approved. | L: medium I: medium | Risk mitigation systems in place will be strengthened to maintain or improve CBO and NGO performance. The Pakistan SGP Country Programme works with all grantees to help build capacities by learning from each other (peer-to-peer), and working in a way that responds to the strengths and comparative advantages of grantees. The SGP Country Program adapts the lessons learned from previous SGP OPs and good practices applied. The National Steering Committee (NSC), provides support for effective design and implementation of SGP-financed projects. | Programmatic |

# 8. Coordination

# The National Steering Committee of the Pakistan SGP Country Programme has consistently promoted the collaboration of the Country Programme with other GEF-funded and government-financed projects and programmes for many years. The SGP has provided technical assistance to community components of selected GEF FSPs to increase the efficiency of uptake by community stakeholders of project-promoted technologies and practices. Members of the National Steering Committee endorse collaborative arrangements and partnerships to maximize the efficiency of the GEF SGP investment, as well, with SGP-sponsored technologies, experience and lessons learned disseminated by government programmes and institutions.  As part of project preparation, the Pakistan Country Programme will analyze and confirm potential and/or continued cooperation with the following initiatives, programmes or institutions:

# IUCN-The World Conservation Union. IUCN will provide policy and technical support to the project’s biodiversity, forest and livelihood related activities, along with specialized technical assistance in regeneration and preservation of coastal mangroves of Pakistan.  IUCN in an international organization whose work focuses on valuing and conserving nature, ensuring effective and equitable governance of its use, and deploying nature-based solutions to global challenges in climate, food and development. Mangroves for the Future (MFF) is a an initiative that was begun in recognition of the important role that mangrove forests played in reducing the impact of the 2004 Indian Ocean tsunami and it embraces all coastal ecosystems, including coral reefs, estuaries, lagoons, wetlands, beaches and seagrass beds. IUCN will provide technical knowledge and support to the project grantees in coastal ecosystem conservation.

# ENERCON. National Energy Conservation Centre (ENERCON) is as an independent authority under the proposed ENERCON Bill 2011. ENERCON serves as national focal point for energy conservation/energy efficiency in all sectors of the economy. ENERCON undertakes pilot projects to demonstrate new technologies, generates information and outreach materials, conducts training and education, and develops plans and policies to promote energy efficiency. ENERCON will provide technical knowledge and support to the project grantees in utilizing energy efficient technology and methods to be used in reducing carbon emissions in energy construction.

# Forest Department (FD) at Provincial levels. The FD will provide technical support to various project activities as related to afforestation and reforestation. The FD will play an important supporting role in any grant approved by SGP dealing with re- or afforestation.

# Federal and Provincial Environment Protection Agencies. The EPAs are the mandated federal bodies to set national environmental emission standards, monitor compliance, approve EIAs, energy audits, and enforce environmental law. The EPAs will provide technical knowledge and support to project grantees in terms of measurement of energy and emission reduction estimations of various energy efficiency products, as well as in setting up bio-composting systems.

# WWF. WWF will provide technical and capacity building support to project partners in biodiversity, forest and livelihood related activities.

# Women’s organizations: Pakistan Hoslamand Khawateen Network, Trust for Rural Uplift Culture and Environment, Bakhtawar Women’s Development Organization and Shirkat Gah Women’s Resource Center Karachi. SGP will continue its partnership with national women’s organizations through community based initiatives like mangroves reforestation and conservation. The SGP network of its CBOs and NGOs has strong representation by women in addition to SGP’s proactive interventions in cookstoves, lighting and water.

The project will cooperate with the following UNDP/UNEP/GEF projects:

Sustainable Land Management for Combating Desertification (Phase II) (UNDP-GEF). This FSP aims to mainstream and harmonize SLM within the national development priorities and integration of desertification/deforestation prevention and control measures into national development programmes. This proposed project will complement emphasis on local community level action of the project.

Mountains and Markets: Biodiversity and Business in Northern Pakistan (UNDP-GEF). This FSP aims to strengthen sustainable production of biodiversity goods and services through community ecosystem-based enterprises. This proposed project will gather important future lessons for community-based conservation work and scale up best practices.

Pakistan Sustainable Transport Project (UNDP-GEF).This FSP aims to reduce the growth of energy consumption and related greenhouse gas emissions from the transport sector in Pakistan. The project proposed here will explore possibilities to cooperate in regard to relevant energy efficiency work.

IISD – Italian Government / Study impacts of climate change on the water sector in Pakistan

The Project aims to improve decision-making in Pakistan’s water sector by developing a fuller picture of current knowledge regarding the exposure of Pakistan’s water resources to the impacts of climate change and the potential socio-economic ramifications of these impacts. The study will also identify priority research gaps and barriers to be overcome to fill these gaps. The proposed project will cooperate with the research team to integrate the latest information on the water sector and climate challenges in Pakistan into its own work.

# 9. Consistency with GEF Policy and Programming.

GEF Policy on Upgrading SGP Country Programmes and Strategic Directions

The project proposed here is in full conformity with the policy for upgrading of SGP Country Programmes as first described in GEF/C.36/4 Small Grants Programme Execution Arrangements and Upgrading Policy for GEF-5 and then in GEF/C.46/13 GEF Small Grants Programme: Implementation Arrangements for GEF-6, approved by GEF Council in Cancun 2014.  This GEF SGP Upgrading Country Programme will continue to follow the SGP’s Operational Guidelines to ensure compliance with longstanding best practice and GEF policy for the SGP.

At the same time, the outcomes of the project proposed here are fully aligned with the SGP Strategic Directions for GEF 6 found on pages 200-206 of GEF/R.6/20/Rev.04, GEF Programming Directions, approved by GEF Council in March 2014.

# 10. Consistency with National Priorities. Is the project consistent with the National strategies and plans or reports and assessments under relevant conventions? (yes X /no )

Pakistan is signatory to several multilateral agreements in environment including the three major Rio1992 agreements of Conventions on Biological Diversity (CBD) , United Nations Framework Convention on Climate Change (UNFCCC), and the Convention to Combat Desertification (UNCCD). Pakistan has developed a Biodiversity Action Plan (BAP, 2000) which emphasizes in-situ conservation; sustainable use; strengthening human capacity in biodiversity conservation and management; and public education and awareness. Sustainable natural resource management and biodiversity conservation are in the centre of the proposed project and they are recognized as crucial elements by Pakistan's policies for sustainable development. The "Vision 2030" elaborated by the Pakistan Planning Commission in 2007, aims for equitable sharing of environmental benefits, increasing community management of natural resources, and integrating environmental issues into socio-economic planning to achieve sustainable development. The Government of Pakistan (GoP) ratified the National Climate Change Policy (NCCP) in 2012, which aims to ensure that climate concerns are mainstreamed in the economically and socially vulnerable sectors of the economy, and to steer Pakistan towards climate-resilient development. In 2015, the Ministry of Climate Change (MCC) finalized a Climate Public Expenditure and Institutional Review (CPEIR) to assess the level at which the GoP has so far been able to respond to the challenges of climate change and to identify opportunities for further strengthening its response.

The National Biodiversity Action Plan (Draft, 2015) explicitly mentions the Indus Delta for its degraded and vulnerable state resulting from pollution, salt-water intrusion and loss of essential biodiversity. Target 14 and 14.2 illustrate the consistency of the SGP with national strategies and plans: “the Indus Delta will be sustainably managed through collaborative management to conserve biodiversity and make sustainable use to safeguard the livelihood and well-being of local communities.” Moreover, the NBSAP emphasizes the importance of recognizing and involving communities in different proposed critical areas and conservation plans (e.g. forests, fisheries, species conservation, and mangroves.

The capacity development, integration and role of communities in sustainable land management and biodiversity conservation is also reflected in the different strategies and actions proposed in the NBSAP for the implementation of the CBD Programme and the Aichi targets. Of particular importance are the ones articulated for coastal and marine biodiversity resources through capacity development of coastal fishing communities.

Contribution of the project to the Aichi targets

A central feature of this project is the development of management strategies aimed at strengthening the socio-ecological resilience of rural communities based on the conservation and sustainable use of biodiversity and ecosystem services in the Indus Delta. The vast majority, if not all, of small grant projects financed by the project proposed here will achieve global environmental benefits as a consequence of activities that also produce economic benefits related to food security, disaster risk reduction, and other goals. These landscape strategies will also include activities related to rural landscape governance, thus beginning to formalize development and poverty reduction as part of landscape management.

The project is also consistent with the Aichi Biodiversity Targets, and in particular: Targets 5, 7 and 18

Target 5: By 2020, the rate of loss of all natural habitats, including forests, is at least halved and where feasible brought close to zero, and degradation and fragmentation is significantly reduced

Target 7: By 2020 areas under agriculture, aquaculture and forestry are managed sustainably, ensuring conservation of biodiversity.

Target 18: By 2020, the traditional knowledge, innovations and practices of indigenous and local communities and their customary use, are respected.

The quantification of proposed landscape level targets and indicators will take place during the planning phases of each landscape strategy with the direct involvement of landscape stakeholders. A baseline assessment will be carried out in each landscape prior to outcome definition and target identification. More specific definition of the contribution of this project to the Aichi targets will be provided after the project planning phase financed by the PPG.

10. Knowledge Management

Knowledge management, including the dissemination of best practices and lessons learned, will remain an important element of the GEF SGP Pakistan Country Programme during its 6th Operational Phase. In the Pakistan Country Program, each grant project is designed to produce three things: global environmental and local sustainable development benefits; organizational capacities (technical, analytical, etc.) from learning by doing; and knowledge from evaluation of the innovation experience.

Each grant project will have as a primary product a case study and summary of lessons learned based on evaluation of implementation results and their contributions to GEB, local development objectives and landscape level outcomes, including the development of social capital. This knowledge will be further systematized and codified for dissemination at the landscape level through policy and innovation platforms, community landscape management networks and multistakeholder partnerships, knowledge fairs and other exchanges; at the national level through the National Steering Committee, strategic partnerships and their networks, and national knowledge fairs where appropriate; and globally through the SGP global network of SGP Country Programs and UNDP’s knowledge management system.

A primary product of the knowledge management approach will be a detailed case study summarizing lessons learned and best practices from the target landscapes based on evaluation of implementation results and their contributions to GEB, local development objectives and landscape level outcomes, including the development of social capital. At the same time, sub-programs focused on development and application of energy efficient and renewable energy technologies will be studied to identify lessons and best practices for further dissemination to policy and innovation platforms and onward transmission to the network of communities, NGOs and government stakeholders.

Knowledge products will focus on sharing land restoration processes; know-how to convert and enhance productivity while contributing to sustainable landscapes; how to strengthen community participation in governance schemes in areas vulnerable to climatic variability and climate change; water management practices; soil management practices; construction and use of innovative energy efficient and renewable energy technologies, access to micro-credit in a community context; scaling up innovative businesses, etc.

part iii:  approval/endorsement by gef operational focal point and GEF agency

A. Record of Endorsement of GEF Operational Focal Point on Behalf of the Government:  
      (Please find attached the Operational Focal Point endorsement letter).

| Name | Position | Ministry | Date (MM/dd/yyyy) |
| --- | --- | --- | --- |
| Aftab Ahmad Maneka | GEF Operational Focal Point | Ministry of Climate Change | 07/28/2015 |

B. GEF Agency Certification

This request has been prepared in accordance with GEF policies and procedures and meets the GEF criteria for project identification and preparation under GEF-6.

| Agency Coordinator, Agency name | Signature | Date (MM/dd/yyyy) | Project Contact Person | Telephone | Email |
| --- | --- | --- | --- | --- | --- |
| Adriana Dinu Executive Coordinator UNDP-GEF |  | 01/25/2016 | Stephen Gold | 212-906-5452 | stephen.gold@undp.org |

GEF_PIF_60