United Nations Development Programme

Country: Paraguay

PROJECT DOCUMENT

Project Title: Capacity development for improved decision-making for the global environment

UNDAF Outcome: 3) Paraguay will make advances in the protection of nature, the reduction of environmental degradation, and disaster risk management supported by the participation of local communities and indigenous populations UNDP Strategic Plan Environment and Sustainable Development Primary Outcome: 1) Growth and development are inclusive and sustainable, incorporating productive capacities that create employment and livelihoods for the poor and excluded UNDP Strategic Plan Secondary Outcome: 5) Countries are able to reduce the likelihood of conflict, and lower the risk of natural disasters, including from climate change

Expected CP Outcome: Outcome 3.2) Paraguay will make significant advances in the reduction of deforestation and desertification, best practices for environmental conservation and sustainable use of biodiversity, and climate change mitigation and adaptation Expected CPAP Outputs: 3.2.1: Strategies and systems to reduce greenhouse gas emissions are designed and implemented by 2019 3.2.2 Productive practices for the conservation and sustainable use of biodiversity are designed and implemented by 2019

Executing Entity/Implementing Partner: Secretariat of the Environment (SEAM)

Implementing Entity/Responsible Partners: Secretariat of the Environment (SEAM), United Nations Development Programme

Brief Description: The goal of this project is to improve decision-making for the global environment in Paraguay by strengthening capacities to create and access better data and information, as well as develop analytical skills to implement Rio Convention obligations within the framework of sub-national planning frameworks.  The project’s strategy emphasizes a long-term approach to institutionalizing capacities to meet MEA obligations through a set of learning-by-doing activities that lay the foundation for effective decision-making and policy-making regarding global environmental benefits.  Specifically, the project will undertake a comprehensive review of the data and information management needs and strengthen systemic, institutional, and technical capacities to formulate more holistic and resilient development plans, with particular reference to protecting the global environment.  In particular, project activities will target the improvement of global environmental indicators and the analytical procedures in order to create more relevant knowledge.  The project will also strengthen key consultative and decision-making mechanisms necessary to legitimize implementation of more resilient land-use planning.  Active participation of stakeholders in the full project life cycle will facilitate adaptive collaborative management.  The learning-by-doing approach of the project will facilitate the institutionalization of the capacities developed to conceptualize more complex, holistic, and resilient social systems of improved governance for the conservation of the global environment.

Programme Period:	2013-2017

Atlas Award ID:	00084609

Project ID:	00092545

PIMS #	4925

Start date:	April 2015

End Date:	April 2018

Management Arrangements: NIM

PAC Meeting Date: 	   TBD		.

Total resources required		US$ 1,880,000

Total allocated resources	US$ 1,880,000

- UNDP (In-kind)		US$    200,000

- Other:

  - GEF			US$    880,000

  - Government (In-kind))	US$    640,000

  - Government (Cash)	US$    160,000

| Agreed by: |  |  |
| --- | --- | --- |
| Secretariat of the Environment (SEAM) | __________________________________ María Cristina Morales Palarea Minister | _______________ Date/Month/Year |
| United Nations Development Programme (UNDP) | __________________________________ Cecilia Ugaz Resident Representative UNDP Paraguay | _______________ Date/Month/Year |

Table of Contents

PART I - PROJECT	5

A.  	Project Summary	5

A.1	Project Rationale, Objectives, Outcomes/Outputs, and Activities	5

A.2	Key Risks, Assumptions, and Indicators	7

B.	Country Ownership	8

B.1	Country Eligibility	8

B.2	Country Drivenness	8

B.2.a	National Capacity Self-Assessment	9

B.2.b	Sustainable Development Context	10

B.2.c	Global Environmental Values	11

B.2.d	Policy and Legislative Context	12

B.2.e	Institutional Context	13

B.2.f	Barriers to Achieving Global Environmental Objectives	16

C.	Programme and Policy Conformity	17

C.1	GEF Programme Designation and Conformity	17

C.1.a	Guidance from the Rio Conventions	19

C.1.b	Project’s Target Contribution to Global Environmental Benefits	20

C.2  	Project Design: GEF Alternative	20

C.2.a	Project Rationale	20

C.2.b	Project Goal and Objective	21

C.2.c	Expected Outcomes	23

C.2.d	Project Components, Outputs, and Activities	23

C.3	Sustainability and Replicability	36

C.3.a	Sustainability	36

C.3.b	Replicability and Lessons Learned	37

C.3.c	Risks and Assumptions	38

C.4	Stakeholder Involvement	39

C.5	Monitoring and Evaluation	39

D.	Financing	44

D.1	Financing Plan	44

D.2	Cost-Effectiveness	45

D.3	Co-financing	46

D.4	Total GEF Budget and Work Plan	46

E.	Institutional Coordination and Support	48

E.1	Core Commitments and Linkages	48

E.2	Implementation and Execution Arrangements	50

F.	Legal Context	53

PART II:	ANNEXES	54

Annex 1:	Capacity Development Scorecard	55

Annex 2:	Logical Framework	61

Annex 3:	Provisional Work Plan	75

Annex 4:	Outcome Budget (GEF Contribution and Co-financing)	81

Annex 5:	Total GEF Budget and Work Plan	83

Annex 6:	Environmental and Social Review Criteria	87

Annex 7:	Terms of References	96

Annex 8:	Paraguay UN REDD+ Programme and Forest Carbon Partnership Facility	102

Annex 9:	Standard letter of agreement between UNDP and Government of Paraguay	103

Annex 10: 	References	107

Annex 11:	Unofficial translation of Government Co-financing letter from SEAM	108

PART III:	GEF Letters of Endorsement and Co-Financing	109

Acronyms and Abbreviations

| ACM | Adaptive Collaborative Management |
| --- | --- |
| APR | Annual Progress Report |
| CBD | Convention on Biological Diversity |
| CCA | Common Country Assessment |
| CCCD | Cross-Cutting Capacity Development |
| CCD | Convention to Combat Desertification and Drought |
| CO | Country Office |
| CONAM | National Environmental Council |
| CPAP | Country Programme and Action Plan |
| DSP | Directorate of Strategic Planning |
| FCCC | Framework Convention on Climate Change |
| GEF | Global Environment Facility |
| GIZ | German Society for International Cooperation |
| GNI | Gross National Income |
| IDEA | Institute for Environmental Law and Economics |
| IFAD | International Fund for Agricultural Development |
| INFONA | National Institute of Forestry |
| MAG | Ministry of Agriculture |
| M&E | Monitoring and Evaluation |
| MDG | Millennium Development Goal |
| MEA | Multilateral Environmental Agreement |
| MECIP | Standard Model of Internal Control for Public Institutions |
| MIC | Ministry of Industry and Commerce |
| MOU | Memorandum of Understanding |
| MSP | GEF Medium Size Project |
| NCSA | National Capacity Self-Assessment |
| NGO | Non-Governmental Organization |
| NPD | National Project Director |
| NPM | National Project Manager |
| PIF | Project Identification Form |
| PIR | Project Implementation Review |
| PMU | Project Management Unit |
| RCU | Regional Coordinating Unit |
| REDD+ | Reducing Emissions from Deforestation and Forest Degradation |
| SBAA | Standard Basic Assistance Agreement |
| SEAM | Secretariat of the Environment |
| SISNAM | National System of the Environment |
| STP | Technical Secretariat of Planning |
| TRAC | Target for Resource Assignment from the Core |
| UGR | Risk Management Unit |
| UNDAF | United Nations Development Assistance Framework |
| UNDP | United Nations Development Programme |

# PART I - PROJECT

# A.  	Project Summary

## A.1	Project Rationale, Objectives, Outcomes/Outputs, and Activities

Paraguay completed its National Capacity Self-Assessment (NCSA) in 2010, identifying the challenges to implementing the Rio Conventions and other multilateral environmental agreements (MEAs).  These included insufficient technical capacities among government staff, inadequate stakeholder and institutional collaboration and coordination, and insufficient access to best practice knowledge for improved environmental governance.  Although there is national expertise in Paraguay, it is not sufficiently institutionalized within government institutions.  The National Environmental Council (CONAM) is an important consultative and decision-making mechanism that has the mandate to approve policies that are intended to catalyze advances in environmental conservation.  However, CONAM has not convened sufficiently frequently to carry out this mandate.  Instead, the implementation of conservation efforts have largely operated within the framework of existing policy frameworks and carried out within the construct of externally funded projects.  The latter have been largely thematic, and largely focused on capacity assessments, e.g., Paraguay’s UN REDD+ Programme, which includes the strengthening of a national forest inventory and an information network mechanism.  A number of other environmental projects are innovative in that they seek to demonstrate and catalyze action to meet Rio Convention obligations through market instruments, such as the Mainstreaming Biodiversity Conservation and Sustainable Land Management into Production Practices in all Bioregions and Biomes.

Since 2010, Paraguay has developed a number of important laws, policies, and strategies to strengthen its environmental policy and programming framework.  For example, Paraguay’s Economic and Social Strategic Plan 2008-2018 calls for strengthening institutional capacities to carry out local actions to manage environmental issues, with particular attention to meeting obligations under multilateral environmental agreements.  The Law on the Real Rights of Forest Area (2013) aims to encourage reforestation by integrating forest values and conservation principles into developmental obligations.  The Zero Deforestation Law established a moratorium on conversion of forest land to other uses (agriculture and pasture) as a means to encourage the conservation of the remaining forests.  The National Policy and Programme on Agricultural and Forest Biotechnology is another policy instrument that was developed in order to promote access and facilitate the availability of knowledge and production technologies that benefit society as a whole.  Other key strategic developments include the Agrarian Strategic Framework (2009-2018) and the Strategic Plan and National Plan of Afforestation / Reforestation (2009-2015).

These policies and strategic frameworks demonstrate Paraguay’s commitment to meeting environmental conservation goals that also have important global environmental values.  The strategic design of this Cross-Cutting Capacity Development (CCCD) project responds to a number of the principles outlined in the above-mentioned policy instruments and strategic frameworks, and complements the more specific global environmental priorities that out outlined in Paraguay’s Rio Convention strategies and Action Plans.  These include the National Biodiversity Strategy and Action Plan (NBSAP), the National Environment Policy, the National Action Plan of Land Degradation, the National Climate Change Policy, the Second National Communication to the FCCC.  A particular feature of synergies between the NBSAP and this CCCD project is through the development of capacities to track progress towards meeting the Aichi Targets.

Paraguay has also made commitments to meeting sustainable development goals through their active participation and preparation of Rio+20 reports.  The formulation of environmental conservation projects in Paraguay call for a review of their contribution to these goals, which are also embodied within the current Millennium Development Goals, in particular Goal 7 on environmental sustainability.  Similarly, Paraguay’s national development priorities are outlined in the United Nations Development Assistance Framework (UNDAF), which also call for directing investments to promoting environmentally sound and sustainable development.

This CCCD project will be an important complement to the portfolio of programmes and projects planned and underway in Paraguay to meet these shared goals.  The CCD strategy is to do so by strengthening improved planning and decision-making that integrates best practices for formulating and implementing sub-national development plans that integrate global environmental criteria as well as meeting national socio-economic development priorities.

This project conforms to the GEF-5 Cross-Cutting Capacity Development (CCCD) Strategy, Programme Framework CD-2, strengthening capacities to generate, access, and use information and knowledge, CD-3 strengthening capacities to develop policy and legislative frameworks, and CD-4, building capacities to implement and manage global convention guidelines.  The capacities developed under this project will also contribute to monitoring environmental trends, which along with capacities to evaluate environmental impacts, is an objective of CD-5.

The expected outcome of this project is that a key set of foundational capacities will have been improved to help Paraguay meet and sustain global environmental benefits as defined under the three Rio Conventions.  To this end, the project will build Paraguay’s capacity to implement NCSA priority actions with a practicable approach towards meeting MEA objectives and achieving environmental sustainability. This will be achieved through three inter-linked project components.  The first focuses on strengthening data and information management for the global environment. The second focuses on enhancing institutional arrangements to catalyze Rio Convention implementation. The third focuses on strengthening technical capacities to manage and implement Rio Convention obligations.

The project will take an adaptive collaborative management (ACM) approach to implementation, which calls for stakeholders to take an early and proactive role in identifying best applicable practices for monitoring and evaluating environmental indicators, identifying and solving unexpected implementation barriers and challenges, and integrating these within consultative and decision-making processes.  By taking an ACM approach, project activities and outputs can be more legitimately modified and adapted to maintain timely and cost-effective project performance and delivery.

This project is innovative and transformative in that it serves to catalyze a readjustment of the traditional status quo.  That is, instead of the traditional sectoral approach to decision-making, a more holistic and participatory approach to decision-making will include academia, civil society and local municipalities.  This process will increase the likelihood that more robust, resilient, and legitimate decisions could be made in the name of the global environment.  Institutional capacities to create and access new and improved data, information, and knowledge will be strengthened, along with technical capacities to absorb and use these to use innovation and best practices to formulate and implement more holistic and resilient land-use and development plans that reflect global environmental values.

The replication value of this approach is that it will empower social actors and other stakeholders at the sub-national level to make more relevant and timely decisions to that reflect better or best practices to deliver global environmental benefits.  Importantly, these social actors will have more tools and resources to adapt to changing political, economic, social and environmental contexts in a way that reduces the risks associated with unintended consequences because of the adaptive collaborative management approach employed.  This will be embodied within the construct of an integrated network of environmental and management information systems that are reinforced by streamlined consultative and decision-making processes as well as a sufficiently large number of individuals that are trained in new knowledge management methodologies and analytical skills.  These will be tested at the municipal and district level, with institutional linkages to national decision-making to validate their value as well as iron out kinks in the broader consultative and decision-making process.  The financial and institutional sustainability will be address through the formulation of a replication strategy and a resource mobilization strategy.

The Secretariat of the Environment (SEAM) is the Implementing Partner for this project, and the project was developed in accordance with agreed policies and procedures between the Government of Paraguay and UNDP.  With the support of UNDP, Paraguay will establish the necessary planning and management mechanisms and facilitate government decision-making to catalyze implementation of project activities and timely delivery of project outputs.  The project was designed to be complementary to other related projects under implementation in Paraguay, in particular those supported by the Global Environment Facility (GEF).  This includes the Asunción Green Cities project under formulation, the preparation of the National Communication to the Framework Convention on Climate Change, and the National Biodiversity Strategy and Action Plan.  These, among other capacity development projects, are undertaking similar though thematic approaches to strengthening systemic, institutional, and individual capacities to meet global and national environmental commitments and priorities.  The strengthening of CONAM is a critical feature of this project that will require coordination with other related projects.  Not only will the Project Board and Project Steering Committee established under this project coordinate activities in such a way that they are mutually supportive and opportunities capitalized to realize synergies and cost-effectiveness with other projects, but it will also serve as a critical institutional arrangement to inform and catalyze the work of CONAM.

## A.2	Key Risks, Assumptions, and Indicators

There are three main risks associated with this project.  The first is the high risk of project implementation delays due to bureaucratic processes  and weak coordination between national and sub-national (district and municipal) authorities and key stakeholder institutions.  A second risk that is ranked medium is the overall weak cooperation between Paraguay’s line ministries and SEAM that could result in poor quality project outputs.   A third but nominal risk to the project is political change.  This risk is ranked low given that a change in political leadership is unlikely to alter the strategic value of the project to meeting Paraguay’s national environmental and development policies.

One of the project’s assumption is that higher quality of data and information, as well as capacities to create new knowledge and innovation, will result in better planning and decision-making.  The project also makes the assumption that project stakeholders other than SEAM will value the expected benefits of a strengthened networking of environmental management information systems, even if they are satisfied with their current level of capacities and efforts.  It follows from that assumption that project stakeholders will remain engaged throughout the project, actively participating  in project activities.  A final main assumption is that no new policies, legislation, or regulation is needed, but rather that improved awareness and understanding of how best to implement and comply with the current set of policies and legal instruments.

Project outcomes will be measured through a set of output, process, and performance indicators.  Each project activity includes a number of target indicators that were constructed using SMART design criteria.  Performance indicators will include an assessment of knowledge gained over the course of project implementation.  These include the carrying out two surveys on awareness and understanding of the global environment, one at the beginning of the project, and another at the end of the project.  A statistical and sociological analysis will help assess the extent to which awareness has increased (and hoping that awareness will not have decreased), over the three years of project implementation.  This would be indicated by a percentage differential on the scoring of the surveys, and complemented by important assumptions of validity.  For example, increased awareness of global environmental issues can be attributable to projects other than the CCCD project.

One of the project’s performance indicators is the independent peer review and quality ranking exercise of analytical reports prepared by the relevant lead national experts.  An example of a process indicator of the project is the diversity and number of participants in the learning-by-doing workshops, strengthened by, for example, tracking staff participation and engagement at the beginning, middle and end of daily workshops.  Process indicators include workshops that contain technical staffs from all key departments and agencies as well as the very important collaboration among government authorities and non-state stakeholders to share data and information through an agreed sharing protocol and data flow system, legitimized by the necessary approvals, e.g., memoranda of agreements.

# B.	Country Ownership

## B.1	Country Eligibility

Paraguay is eligible to receive technical assistance from UNDP, and is thus eligible for support under the Global Environment Facility (GEF).  Paraguay ratified the Convention on Biological Diversity (CBD) on 24 February 1994, the Convention to Combat Desertification and Drought (CCD) on 15 January 1997, and the Framework Convention on Climate Change (FCCC) on 24 February 1994.  Paraguay ratified important protocols under the Rio Conventions in later years, namely:

  - The Cartagena Protocol on Biological Safety on 8 June 2004 to protect biodiversity from the potential risks posed by genetically modified organisms that are the product of biotechnology.

  - The Kyoto Protocol on 27 August 1999, committing to stabilize greenhouse gas emissions for the period 2008-2012 at the 1990 level.

In addition to the three Rio Conventions above, Paraguay has also demonstrated its commitment as to the global environment through the accession or ratification of several other international treaties and protocols that call for the protection and sustainable use of natural resources.  These MEAs include:

- Ramsar Convention on Preservation of Wetlands

- Convention on International Trade in Endangered Species of Wild Fauna and Flora (CITES)

- Vienna Convention and Montreal Protocol to protect the ozone layer

- Basel Convention on the Control of Hazardous Wastes and their transfer across borders

- Rotterdam Convention on the prior approval of the transfer of hazardous chemicals

- Stockholm Convention on Persistent Organic Pollutants

- Convention on the Conservation of Migratory Species of Wild Animals

- International Treaty for Genetic Resources in Food and Agriculture

- Minamata Convention on Mercury

Fit with the GEF-5 CCCD Strategy: The GEF Strategy for Cross-Cutting Capacity Development projects serves to provide resources for reducing, if not eliminating, the institutional bottlenecks and barriers to the synergistic implementation of the Rio Conventions.  This particular project has three components, each of which will target one of the Capacity Development Strategic Programme.  The first component will target CD-2, which is to strengthen capacities to generate, access, and use information and knowledge.  Component 2 will contribute to meeting CD-3 by strengthening capacities to develop policy and legislative frameworks.  Component 3 will focus on CD-4, building capacities to implement and manage global convention guidelines.  Although not expressly structured as such, the capacities developed under this project will also contribute to monitoring environmental trends, which along with capacities to evaluate environmental impacts is an objective of CD-5.

## B.2	Country Drivenness

The proposed project is consistent with Paraguay’s national development priorities as well as those of the UN as identified in the United Nations Development Assistance Framework (UNDAF).  Drawing from the Country Assessment, the UNDAF identified “Environmental Rights” as one of the three strategic priority areas for UN activities with Outcome 3 stating: “Paraguay will make advances in the protection of nature, the reduction of environmental degradation, and disaster risk management supported by the participation of local communities and indigenous populations” (UN, 2014).  Specifically, Output 3.2 calls for Paraguay to make significant advances in: the reduction of deforestation and desertification, best practices for environmental conservation and sustainable use of biodiversity, and climate change mitigation and adaptation (UN, 2014).

The project is also consistent with the Economic and Social Strategic Plan 2008-2018 of the Government of Paraguay, in particular to strengthen decentralized environmental governance.  The Plan calls for strengthening institutional capacities to carry out local actions to manage environmental issues, with particular attention to meeting obligations under multilateral environmental agreements.  A related priority of the Plan is to strengthen monitoring and evaluation mechanisms to assess the performance and impacts of conservation efforts.

Paraguay is part of the Open Working Group on Sustainable Development Goals, which in July 2014, proposed 17 specific goals with 169 associated targets. (United Nations, Open Working Group on Sustainable Development Goals, 2014).  The strategy to achieve these goals includes: financing, development of technology, science, and innovation, and investing in sustainable development capacities.  Some additional essential steps to integrate these goals include addressing the drivers of climate change and its consequences, basing analysis in credible data and evidence, enhancing data capacity, availability, disaggregation, literacy, and sharing. (United Nations, 2014).  Given these strategies, this CCCD project will complement Paraguay’s future work to achieve the SDGs.

This CCCD project will also contribute to the existing National Biodiversity Strategy and Action Plan (NBSAP), which will include building capacities to meet the Aichi targets, in particular the development of a national roadmap of programmatic actions.  Special emphasis will be placed on mainstreaming biodiversity into development plans, incorporating protected area networks and sustainable production systems into ecosystem-based climate adaptation and resilience plans, and creating sustainable finance for biodiversity conservation.

This CCCD project is also consistent with the national priorities outlined in the National Environment Policy, the National Action Plan of Land Degradation, and with the National Climate Change Policy and the Second National Communication to the FCCC.  Collectively, they call for strengthening Paraguay’s technical capacities to understand environmental trends and to formulate best practice conservation responses.

This project is also in line with the commitments made by the GEF for the United Nations Conference on Sustainable Development (Rio+20), specifically:

  - Seek to expand opportunities for joint implementation of the Rio Conventions through GEF-funded projects and programmes by promoting synergies in the generation of global environmental benefits.

  - Continue to support capacity development in recipient countries as well as addressing their needs through funding of enabling activities and the GEF Country Support Programme, together with other national and regional consultation processes.

### B.2.a	National Capacity Self-Assessment

Paraguay´s environmental management issues are mainly due to insufficient technical capacities, inadequate collaboration and coordination, and insufficient involvement of relevant stakeholders and institutions for improved and sustained environmental governance that yields global environmental benefits.  Notwithstanding the work being undertaken by a small number of non-State social actors, there remains an insufficiency of national expertise available to catalyze effective decision-making for the global environment.  While some applied research is underway, much remains to be undertaken to integrate higher quality data and information into management information systems.  The work that a number of universities and research institutes have been doing is isolated and needs to be unified with the appropriate application of standards and the efficient coordination of the institutions involved.

Secondly, the need for clearer mandates and structures for organizational environment is a core element of the present proposal lead by the Secretariat of the Environment (SEAM).  SEAM oversees the development, coordination, and implementation of Paraguay’s environmental policies.  It hosts the three Rio Convention Focal Points.  It is the entity in charge of coordination, monitoring and enforcement of the environmental action plans, programmes and projects under the National Development Plan pertaining to the preservation and conservation, restructuring and management of natural resources and the ecological environment in general.  Furthermore, the SEAM is tending to a constant improvement of the living conditions of the various sectors of Paraguayan society to ensure and enable favourable conditions for economic growth, social equity and ecological sustainability in the long term.  Other institutions are also involved in environmental policy implementation, environmental protection and effective management of natural resources (see relevant stakeholder listing below).  Even though there are continuous efforts in Paraguay to enhance institutional capacities to plan and develop policies and legislation to implement with success environmental commitments, there are main environmental governance issues in the country.  Therefore, this project is directed at the integration of environmental policy in sectoral and local policies: such integration will be foreseen in the National Development Plans.

Furthermore, the SEAM will act as a coordination body for strategic planning, implementation and monitoring of cross-sectoral and regional integration.  This CCCD project will enhance and create capacity in order for civil servants to be able to effectively manage issues of environmental policy integration.  As a result, policy, institutional and educational framework of the project activity will promote strengthening of environmental governance in Paraguay.  Strategic planning of integrated environmental activity would lead to cost-effective and sustainability for joint environmental activities that help in meeting national and global environmental priorities, since such planning is intended to promote prevention of environmental degradation and mitigations of possible conflicts between economic development and nature conservation in Paraguay.  Cross-sectoral coordination leading to improvement of environmental policies and programmes is a task that the Government has tried to implement.  This project will enable the Government of Paraguay to strengthen capacity and performance, to share experiences with the civil society, as well as the inclusion of local cultures and traditions into environmental issues to engage Paraguayan communities across the country.

### B.2.b	Sustainable Development Context

Paraguay is a landlocked country in the center of South America; bordered by Argentina (to the South, East and West), Brazil (to the North and East), and Bolivia (to the North and West).  The Paraguay River divides the country’s 406,762 km2 into two clearly distinct natural regions: the Oriental Region and the Western Region.  The terrain east of the river is mostly grassy plains and wooded hills and contains the 97% of the country’s inhabitants.  On the other hand, the western region, known as the Gran Chaco, is sparsely populated with 61% of the land area, but only 3% of the population; this area is characterized by mostly low marshlands near the river and dry forests and thorny scrub elsewhere (SEAM, 2013).

Paraguay has a diverse and rich cultural history.  Guaraní, an indigenous language, is spoken by approximately 85% of the country, and along with Spanish is one of the two official languages of the country (SEAM, 2013).  Although Paraguay has made significant progress in recent years, it still lags behind other Latin American countries in terms of multiple socioeconomic indicators such as access to water and sanitation, secondary school enrollment, and rates of immunization.  Deficiencies in infrastructure present another barrier to the country’s long-term development, and political instability limits not only the country’s economic development, but also the number of immigrants coming into the country (CIA, 2014).

Paraguay’s economy has a high level of volatility due in part to its large dependence on agriculture and foreign trade.  In general, the country suffers from a shortage of skilled workers in the processing and service sectors, and there is a large informal sector that entails re-exporting imported consumer goods to nearby countries.  The agricultural sector plays an indispensable role in Paraguay’s economy and nearly half the country’s population works in this sector, many on a subsistence basis (SEAM, 2013).  Small-scale producers generate approximately 75% of the country’s food supply, though these family-run operations only own about 4% of the arable land in Paraguay.  In contrast, around 1,000 large businesses own 90% of the arable land (GIZ, 2014).

On a related note, Paraguay Gini coefficient places it at the 11th most unequal country in the world with regard to income distribution.  Despite high rates of economic growth, over 13% in 2013 and an estimated 5% in 2014, Paraguay is nonetheless characterized by income inequities and poverty.  Approximately 23.8% of the country’s 6.8 million people live below the poverty line, and 18% live in extreme poverty, while the country’s 2% indigenous population have minimal livelihood security.  Poverty is especially high in rural regions which host approximately 33% of the population (CIA, 2014).  Overall, per capita GNI is just over US$4,000 and falls considerably below the average of US$9,500 for the rest of Latin America and the Caribbean (GIZ, 2014; World Bank, 2014).

As the Gini coefficient would suggest, there are great disparities between the rich and the poor, and corruption only exacerbates the issue.  Corruption in the legal and judicial system is a particularly is a pressing challenge to the country’s development.  Recently, corruption scandals have started to gain media attention, leading to public protests and legal proceedings against officials suspected of corruption.

Paraguay has significant and complex environmental challenges due to the current drivers of economic growth that rely heavily on the natural environment, namely primary production and agro-industry.  The need to expand the agricultural frontier, along with the internal and external demand for wood, has resulted in a process of indiscriminate deforestation that is also linked with soil erosion, contamination of freshwater sources.  Although the country has taken measures such as the Law of Zero Deforestation of 2005 in the Eastern Region to limit deforestation, it is estimated that each year at least 130, 000 hectares of forest are converted to farmland in the Occidental (Western) Region (UN, 2014).  Furthermore, inadequate waste disposal poses health risks and negatively impacts the quality of life (CIA, 2014).  Soil quality is also degraded by unsustainable agricultural practices such as the excessive use of pesticides, mono-cultivation practices, and slash-and-burn techniques.  In addition such practices also have deleterious effects on the country’s biodiversity (SEAM, 2013).

### B.2.c	Global Environmental Values

While Paraguay does not have a complete inventory of flora and fauna within its territory, it is nonetheless an important source of an invaluable proportion of the world’s biodiversity.  For example, around 69% of the country’s 13,000 plants are endemic.  The country is also host to some 250 fish species; 76 amphibians; 135 reptiles; as many as 685 bird species; and 167 mammal species.  Issues such as land use change, deforestation, urban encroachment, and overexploitation of wildlife all negatively impact the country’s biodiversity.  Numerous species are currently  listed as threatened including 279 plant species as well as eight reptile, 86 bird, and 38 mammal species (CBD, 2014)

In order to better preserve the natural environment, Paraguay has steadily increased the national territory under protection.  In 1993, 2.79% of the country was protected, while today approximately 16% of the national territory enjoys some form of management under the country’s protected areas system.  Furthermore, the country also has one Biosphere Reserve and four Ramsar sites with an additional two areas that will potential Biosphere Reserve sites (CBD, 2014).

Paraguay has a rather unique situation with regard to its energy production and consumption; nearly 100% of its electricity is generated through hydroelectric dams thus its carbon footprint is exceptionally low.  Per capita CO2 emissions in 2010 amounted to 0.8 metric tons, half that of other lower middle income countries, and negligible compared to the emissions of the developed world (World Bank, 2014).  In addition, the country is also one of the world’s largest exporters of energy.  Of the approximately 54,000 GWh of electricity the country produced in 2010, nearly 80% was exported to nearby countries (International Energy Agency, 2014).

While hydroelectric dams, offer a much cleaner source of energy when compared with tradition fossil fuel based generation, Paraguay still has a number of issues affecting its air and water quality.  For example, there are a number of point and non-point sources of pollution that threaten the air and water by producing toxic gases and particulate matter, as well as greenhouse gases (SEAM, 2013).

Paraguay has an extraordinary environmental richness including surface and groundwater conditions, as well as favorable weather.  Currently however, Paraguay faces several environmental problems threatening this richness, including soil erosion, degradation, salinization, compaction, depletion, and drought.  These problems are a result of improper practices in agriculture, infrastructure, and production.  Risk of drought and flooding are increasing as reflected by their increased intensity in recent years, and the increase in the number of people directly exposed to deleterious effects on the food supply, health, and environment infrastructure.  The traditional un-environmentally friendly land management activity of slash and burn for ranching is expanding, contributing further to land degradation.  The Western Region or Paraguayan Chaco is considered the most susceptible to land degradation.  The Northeast region is characterized as an area of low precipitation and therefore extremely fragile to productive human activities.  This area is largely unregulated (SEAM, 2013).  While Paraguay lacks adequate land management and land-use policies, the government has and is implementing a number of national and international projects and programmes that include activities aimed at combatting land degradation, such as environmental education and awareness-raising dialogues and workshops.

### B.2.d	Policy and Legislative Context

Paraguay’s commitment to the environment begins at the highest legal level, through its Constitution that was reformed in 1992.  Declaring the preservation, conservation and improvement of the environment, and their reconciliation with human development as a social interest, the Constitution defines the rights of citizens of Paraguay to life in a healthy and ecologically balanced environment (Articles 7 and 8).  A few key government institutions have mandates to help meet this goal, established through Law No.  1561/00 that created the National System of the Environment (SISNAM), which comprises the National Environmental Council (CONAM) and the Secretariat of the Environment (SEAM).

Key national policies related to environmental governance include the National Environmental Policy, the National Forest Policy, and National Policy and Programme on Agricultural and Forest Biotechnology.  The National Environmental Policy (2005) aims to conserve and manage the use of natural and cultural heritage of Paraguay in order to ensure sustainable development, equitable distribution of benefits, environmental justice and livelihoods of the population.  This policy also sets its operational instruments: strategic environmental assessment, environmental audit, quality standards, control and surveillance, citizenship and economic-financial and promotional instruments.

The National Forest Policy (2009) has the overall objective of improving the contribution of forestry to sustainable economic development through institutional strengthening adaptive legislation, sustainable management of forests, afforestation and reforestation, financing and incentives, competitiveness in industry, control, research, training and awareness.

The National Policy and Programme on Agricultural and Forest Biotechnology (2011) was developed in order to promote access and facilitate the availability of knowledge and production technologies that benefit society as a whole.  Other key strategic developments include the National Biodiversity Strategy SEAM and Plan of Action (2003), the Agrarian Strategic Framework 2009-2018 and the Strategic Plan and National Plan of Afforestation / Reforestation 2009-2015.

There are a number of laws establishing the legal framework for the protection and management of the environment in the productive landscape and have a direct relationship with forests.  The Forestry Law (1973) is one of the first legal instruments adopted in order to protect, conserve, enhance, restore and use the country's forest resources sustainably, and the ecosystem services provided by forests.  Reforestation Act (1996) established financial incentives funded by the State for afforestation / reforestation.  Given the high rates of deforestation in the Eastern Region since the 1960s, the so-called Zero Deforestation Law was passed in 2004 establishing a moratorium on conversion of forest land to other uses (agriculture and pasture) as a means to encourage the conservation of the remaining forests.  The law was extended successively in 2006, 2008 and 2013 and is currently in force until 2018.

The Law of Agrarian (2002) guarantees private property, identifies the social, economic and environmental function of land, and establishes criteria for land use for land reform.  The Law on Environmental Impact Assessment (1993) governs the procedure for impact assessment of projects that could have a significant impact on the environment, including among others farming, livestock and forestry.  The Environmental Crimes Act (1996) aims to protect the environment and the livelihoods of activities that threaten the ecosystem balance, sustainability of natural resources and quality of life.

The Valuation and Compensation Act Environmental Services No.  3001 (2006) was adopted with the aim to promote the conservation, protection, recovery and sustainable development of the country's biodiversity and natural resources through payments for ecosystem services.  The Law on Fire Prevention and Control (2010) and the Law on the Restoration of Forests for Water Channels (2010), the first sets standards for the management and control of fire use in productive activities, while the second seeks to conserve and restore protective forests in the Eastern Region and compliance with environmental protection measures of water resources in the Western Region (Chaco).

The recent Law of Real Rights of Forest Area (2013) aims to encourage reforestation offering legal guarantees for forestry investments included in property of third parties not owned by the investor.  These laws are administrative in nature, the SEAM and INFONA act as enforcement authorities, except for the Agrarian Act, which falls within the authority of the National Institute of Rural Development and Land (INDERT).  The Ecological Crimes Act is the only criminal law and falls under the jurisdiction of the Public Ministry.

Paraguay is presently looking at two additional laws to be considered at the territorial level are Departmental Government Act (1994) and the Municipal Government Act (2010).  Both laws establish the roles and responsibilities of departmental and municipal governments, particularly in the productive sectors and the environment.

### B.2.e	Institutional Context

The National Environmental System (SISNAM) in Paraguay is made up by the SEAM and the CONAM, which was created with the purpose of facilitating collaboration among key stakeholders to address Paraguay’s environmental problems.  CONAM is consultative body that serves to   inform decision-making on environmental issues.  CONAM is chaired by SEAM, with membership comprised of representatives of environmental units from various line ministries, sub-national governments, as well as representatives from the private sector and NGOs.  The Act that established CONAM called for meetings to be held three times per year although in practice periodicity is not ensured.  Instead, communication and collaboration is done through a more ad hoc approach through specific projects

The same law that created CONAM also established the Secretariat of Environment, whose purpose is to regulate the functioning of the institutions responsible for the development, standardization, coordination, implementation and monitoring of the environment.  SEAM is also the institution responsible for the focal points of the three Rio Conventions and the Global Environment Facility (GEF).

SEAM oversees the National Environmental Policy as well as monitoring and enforcing environmental standards under the National Development Plan.  The SEAM is composed of four General Directorates:  The General Directorate of Environmental Management is made up of the Directorate of Management and the Environmental Information.  This Department formulates, coordinates and oversees policies, programmes and projects including intergovernmental environmental education programmes and awareness campaigns, issues of international relations and the National Environmental Information System.

SEAM’s General Directorate of Quality Control and Natural Resources is composed of the Department of Control of Environmental Quality and the Evaluation of Environmental Impact Assessment.  The role of this department is to develop, coordinate, monitor, evaluate and implement, in partnership with governments and municipalities, a number of programmes, projects and activities, including impact assessment and management of environmental quality.

The General Directorate for the Protection and Biodiversity Conservation is formed by the Wildlife Department, the Department of Biological Research / National Museum of Natural History of Paraguay, the Directorate of Fisheries and Aquaculture and Management of Protected Areas.  It deals with creating, managing, manage and monitor protected areas, and to establish strategies for the conservation of biodiversity, including hunting, farming, trade and marketing of wildlife.  It is also responsible for implementing the Wildlife Act, including in the government sector and the private sector.

The General Directorate for the Protection and Conservation of Water Resources is composed of the Office of Management and Watershed Water Resources, is responsible for developing and monitoring the health of watersheds, proposing and promoting regulatory regimes.  This directorate is also responsible for developing institutional mechanisms and actions for sustainable use of water resources through integrated management of watersheds.  The directorate is also mandated to promote cross-sectoral cooperation and jurisdictional watershed level approach to implement the national, as well as to propose and promote standards and parameters related to the quality and availability of water resources policy indicators.

The National Office for Climate Change (ONCC) of SEAM manages the National Climate Change Programme and oversaw the implementation of the Five-Year Plan on Climate Change (2008-2012) that included, among others, promoting the regeneration of natural forests with the aim of covering 10% of the land area.

The Directorate of Strategic Planning (DSS) in SEAM is in charge of guiding the development of institutional strategies as inputs for national development plans as well as of supervising the execution of national and international projects and programmes.

Besides the SEAM there other government institutions involved in the implementation of environmental policy, environmental protection and sustainable management of natural resources.  These are linked to the economic, social and cultural development of Paraguay, the agro-production, industry, research, innovation, tourism, cooperation, among others.

The Ministry of Agriculture and Livestock (MAG) is responsible for promoting sustainable agricultural development, implementing various programmes and projects, including the National Programme for the Management, Conservation and Reclamation of Land, the National Support Programme for Family Agriculture, and the Sustainable Agriculture and Rural Development Project that is supported by the World Bank and IFAD under the Agricultural Strategic Framework (2009 – 2018).

MAG uses risk analysis as a process of adaptation of agriculture to climate change in rural areas.  The Risk Management Unit (UGR) publishes a bimonthly newsletter, facilitates meetings with producers at the beginning of each crop, produces maps, databases, simulation results and recommendations, and accompanied weather forecasts for crops, connected by a geographic information system (GIS) that allows spatial vulnerability studies from the national to the local level.  Also, the UGR has developed the agricultural zoning of 12 crops from the East, by departments and districts, plus four pilot projects for safe harvesting crops of cotton, soybean, sesame, and plantain or banana.  UGR also supports producers with quarterly information based on weather predictions about the risks of production.

The National Forestry Institute (INFONA) is responsible for the national forest policy and mandate encompassing conservation of forest resources.  Specific responsibilities include national forest inventory, approval of forest management plans and land use under the Forest Act 422/73, and supervision and control of management plans.

The Public Ministry is the body of independent prosecutors in charge of the defense of justice.  With regard to environmental issues the MP is responsible for investigating complaints and prosecuting violators of the Environmental Crimes Law 716/96.  A specialized in Environmental Crimes Unit was established in 2009.

The Ministry of Industry and Commerce (MIC) is responsible for the development of industry, trade and services, as well as promoting investment and national and international export.  One of the key initiatives of the MIC is the Investment and Export Network, through which the government and the private sector work together to promote investment and exports.  The network comprises several sectoral programmes, including forestry and meat.  The Ministry of Public Works and Communications (MOPC) is responsible for policies and regulations on public works, infrastructure, transport, communications and energy.

The National Council of Science and Technology (CONACYT) is responsible for formulating and proposing national policies and strategies for science, technology and innovation and quality for the country in accordance with the policy of economic and social development of the State.  The council works in coordination with related institutions to monitor and evaluate the implementation of these policies and strategies.

The Technical Secretariat of Planning (STP) is responsible for coordinating and promoting the design, implementation, monitoring and evaluation of national development processes.  The strategic objectives of the STP is to contribute to the reduction of extreme poverty, coordinate the design and implementation of the National Development Plan, and promote the development of public-private partnership (PPP) and investment in infrastructure and services.  The National Secretariat of Tourism (SENATUR) is responsible for implementing national policy on tourism, as well as promoting and developing domestic tourism.

The Ministry of Foreign Affairs is responsible for implementing the foreign policy of Paraguay, including coordination with other government institutions to determine national policy on environmental issues.  The Ministry also participates and monitors the bilateral and multilateral meetings on environmental issues, such as the Conference of the Parties of the three Rio Conventions.  Another relevant government institution is the Secretary of National Emergency whose mandate is the strengthening of coordination capabilities and advancing the formulation of the National Policy Management and Disaster Risk Reduction.

The Ministry of Finance is an important government institution that is responsible for a number of key policy decisions and with institutional mandates that affect action to meet Rio Convention obligations and sustainable development overall.  Indeed, a major challenge in achieving these goals is due to the insufficiency of financial resources to staff important government bodies and finance critical consultative and decision-making mechanisms.  Among a key function of the Ministry of Finance that also has a bearing on the project is the Standard Model of Internal Control in Paraguay (MECIP).  This programme includes strengthening the development of efficiency indicators, integrity and transparency to promote the human, social and economic development.

Local governments and comprised of departments/districts and municipalities.  The main responsibilities of the departmental governments (governorates) are to coordinate with national institutions and municipalities activities will be pursued within its territory, and the formulation of Departmental Development Plan.  The governorates are organized secretariats, including environmental and development departments, which have the responsibility to promote environmental and industrial policies.  Governorates depend on the funds transferred by the National Budget.  The municipalities are in charge of responsibilities for the environment and the productive sectors, namely, the development of sustainable development plans and zoning of the land, as well as conservation and restoration of natural resources and the application of national regulations (through agreements with national authorities).  The degree of strengthening of municipalities is directly related to its ability to raise taxes, which are generally stronger in areas where agricultural production is highly developed.

The country is composed of 17 administrative divisions known as departments, as well as the capital city of Asunción.  The departments are then further divided into 218 districts throughout the country (SEAM, 2013).  For example, the involvement of indigenous peoples in a consultative process is in part being addressed through the REDD+ project underway in with the support of UNDP.  One of the REDD+ project’s outputs is the development of a Protocol for Consultation and Consent Process with the Indigenous Peoples of Paraguay.  This protocol details a process that is to apply to all social actors that have work interests and carry out activities that affect the territories, land, natural resources and human rights of indigenous peoples.

Paraguay has undertaken numerous actions to increase coordination and collaboration between groups.  In 2013, the Supreme Court, the Office of the Special Envoy of the United Nations Environmental Justice, and the Institute for Environmental Law and Economics (IDEA) signed an inter-institutional cooperation.  One goal of this agreement is for various groups to work together to achieve the finished performance of the functions to ensure the right of people to live in a healthy and ecologically balanced environment.  One aim of Paraguay’s National Development Policy is to increase coordination between institutions and strengthen monitoring and evaluation mechanisms.  Paraguay’s Supreme Court also ruled that environmental authority/ jurisdiction should be shared between national, departments, and municipal governments.

### B.2.f	Barriers to Achieving Global Environmental Objectives

Despite the many efforts undertaken by Paraguay to protect the country’s natural environment and pursue sustainable development, there are many hurdles to overcome.  One main hurdle is the insufficient institutional and absorptive capacity of the government to meet these challenges due to very limited financial resources.  Notwithstanding, development partners in Paraguay have and continue to play an important catalytic role in advancing efforts to meet these challenges through individual projects.  SEAM and other government ministries and bodies have and are currently benefiting from investments in Paraguay’s public administration.  However, these are targeted to relatively narrow constructs of the ministries’ institutional mandate.

Whether by design or unintended, by filling capacity gaps institutions have taken on additional functions that overlap with those of other institutions, further allowing them is operate with less communication, coordination, or collaboration.  Despite the creation of SISNAM and CONAM to address these issues, institutional coordination and collaboration remain within the narrow constructs of externally funded and thematically focused projects.  Often, the approaches to improve coordination are piecemeal and project specific.

An important weakness in Paraguay is the relatively weak cooperation between the private sector and SEAM.  This is in part due to the perception of weak legitimacy of SEAM by the private sector, which is in part due to the relatively low investment in strengthening SEAM’s institutional capacities, including updating the technology needed for more efficient and timely provision of services.  In the absence of private sector champions to support cooperation with SEAM, there is minimal exchange of information.

Through a number of assessments carried by capacity assessment projects, such as the NCSA, the National Communications, and the NBSAP, much of Paraguay’s data and information needs have been identified.  However, there remain gaps, and more importantly the tools by which to collect and manage this information, as well as analytical skills to create knowledge and apply best practices.  This, coupled with the insufficiency of financial and human resources, helps explain why environmental plans and strategies are only partially implemented.  Even in the instances when the resource requirements are known, these are not efficiently managed (SEAM, 2013).

These capacity development challenges are exacerbated by the relatively low level of compliance to environmental legislation.  As with the partial implementation of environmental plans and strategies, non-compliance is due in large part from the insufficiency of resources for adequate monitoring.

# C.	Programme and Policy Conformity

## C.1	GEF Programme Designation and Conformity

This project conforms primarily to Capacity Development Programme Framework CD-2 of the GEF-5 Cross-Cutting Capacity Development (CCCD) Strategy, which calls for the strengthening of capacities generate, access and use of information and knowledge to help meet and sustain global environmental objectives.  These capacities will be reinforced by strengthening appropriate policy and legislative instruments, which is consistent with CD-3.  In line with CD-4, a third component will strengthen individual capacities needed to manage and transform data and information into new and improved knowledge to implement provisions of the Rio Conventions.  Although not expressly structured as such, the capacities developed under this project will also contribute to monitoring environmental trends, which along with capacities to evaluate environmental impacts is an objective of CD-5.

- The project is also consistent with the programmatic objectives of the three GEF thematic focal areas of biodiversity, climate change and land degradation, the achievement and sustainability of which is dependent on the critical development of capacities (individual, organizational and systemic).  Through the successful implementation of this project, these focal area projects will have better access to data and information to improve the implementation and monitoring of the National Biodiversity Strategy and Action Plan, the National Communication on climate change, and national reports on land degradation.  Table 2 summarizes the project's conformity with the 11 operational principles of capacity development identified in the GEF Strategic Approach to Capacity Building.

Table 1: Conformity with GEF capacity development operational principles

| Capacity Development Operational Principle | Project Conformity |
| --- | --- |
| Ensure national ownership and leadership | The essence of this project is rooted in the belief that global environmental issues can best be addressed if local people are involved and direct community benefits and ownership are generated. Thus, the development of the present project includes consultations with relevant stakeholders of the following sectors: NGOs, academia, the Government, the Civil Society, among others. These consultations included a dialogue on the capacity development needs: a basic consensus on assumptions and the capacity development strategy of the Project, as well as the clarity on the sequence and timing of its activities. The government has allocated US$ 1,000,000 to complement project activities. These funds will be used to ensure active engagement of local stakeholders throughout project implementation to ensure on-going legitimacy, ownership, leadership, and collaborative management of the project strategy. |
| Ensure multi-stakeholder consultations and decision-making | Input from all levels of government, NGOs and community leaders is expected, encouraged, accommodated, and accounted for in order to ensure stakeholder support and assistance in maintaining long-term and self-sustaining results. Project implementation may require Memoranda of Agreement to ensure multi-stakeholder participation and collaboration. |
| Base capacity building efforts in self-needs assessment | This project is in response to Paraguay’s NCSA which identified the major environmental management limitations as: weak technical and institutional capacities; insufficient involvement of relevant stakeholders and institutions at national and, especially, at local levels; lack of coordination between various sectors on environmental policies and programmes; and poor monitoring and evaluation. The many and diverse stakeholders at the project validation workshop reaffirmed the project objectives and strategy as meeting a top priority needs. The project will strengthen a policy dialogue process to catalyze effective consultation and collaboration in a cost-effective manner. This project will strengthen capacities of the SEAM, as well as institutions, to effectively coordinate the policy decisions and catalyze implementation pertaining to the three Rio Conventions. |
| Adopt a holistic approach to capacity building | This project takes a holistic approach by involving as many stakeholders as possible. Only this holistic approach can cost-effectiveness and synergies be created. These stakeholders will also participate in the training and learn-by-doing exercises to see the value of taking a holistic approach to data and information management, i.e., by sharing comparative advantages and expertise. The project balances a bottom-up and top-down approach with stakeholder involvement by encouraging capacity building at individual, institutional and systemic levels. |
| Integrate capacity building in wider sustainable development efforts | The project will include a set of activities to strengthen awareness and knowledge among a wider audience and at all levels on the complex relationship between global environmental values and national development priorities. This will be undertaken through a learn-by-doing approach to strengthen the legitimacy of integrated global environmental and sustainable development plans. Implementation of capacity building will be instituted and coordinated within existing structures and mechanisms. The project’s training and learn-by-doing will be directly targeted to using the improved indicators to screen and assess (“sustainable”) development policies, programmes, plans and project from a Rio Convention lens, using the Rio Convention-coded indicators. |
| Promote partnerships | Stakeholder representatives from NGOs, communities, the private sector, academia, among others, will be encouraged to actively engage with government representatives as partners in carrying out project activities or components thereof. This will help capitalize on stakeholders’ comparative advantages, as well as to create synergies, strengthen a more accurate holistic and resilient construct of policy interventions, and improve legitimacy. These partnerships will also help ensure a more equitable distribution of benefits. The comparative expertise among the diverse stakeholders will be demonstrated through the learn-by-doing integration of improved environmental indicators into municipal planning and decision-making, which will seek to foster stronger partnerships, both between government departments as well as with non-state organizations, including NGOs, academia and civil society. |
| Accommodate the dynamic nature of capacity building | Recognizing that capacity building requires flexibility, this project will take an adaptive collaborative management approach to its implementation, and to that extent will call upon the Project Steering Committee to meet at least four (4) times per year. These meetings will be immediately preceded by project stakeholder review meetings to review project progress and report on recommended modification to project execution. This will allow project activities to be appropriately and legitimately modified to take into account unforeseen events or consequences of project implementation. Although modifications can be made, these will be made within the existing system boundary and objectives of the project. |
| Adopt a learning-by-doing approach | The core of the project's capacity development activities is via a learning-by-doing approach. Mobilization of representatives of diverse positions, special interests, responsibilities, capacities and social location such as NGOs, local communities, academia, the private sector and government will all be encouraged to actively participate in the actual mainstreaming exercises and pilot activities, including the development and institutionalization the indicators for the global environment. Their active involvement in these exercises and activities will require critical thinking to determine best practices and approaches applicable to Paraguay. |
| Combine programmatic and project-based approaches | By definition, the activities will be implemented through a project-based approach. However, these capacity development activities are structured to support sustainable development, which can best be programmed within broader sustainable development programmes. |
| Combine process as well as product-based approaches | The transformative value of this project is indeed through the integration of its process with the products to be delivered. Whereas the product of this project is strengthened capacity for improving decisions for the global environment, which is manifest by networks management information systems, associated training, and reports, the process of active stakeholder engagement that will demonstrate the value of breaking down traditional barriers environmental management. The adaptive collaborative management and learn-by-doing approaches are both reflective of the integration of process and product-based approaches to capacity development. |
| Promote regional approaches | One strategic objective established in this plan is decentralized regional development. The project will convene stakeholder workshops to reconcile mandates among local and regional authorities for streamlined environmental information management and impact assessment within the context of Rio Convention implementation in the selected pilot sector development plan. The project also includes learn-by-doing training through targeted implementation of sectoral recommendations at the regional level. |

### C.1.a	Guidance from the Rio Conventions

This CCCD project will contribute to strengthening the capacities of Paraguay that cut across the three Rio Conventions: in particular, the global environmental benefits of this project refer to “Capacities of individuals and organizations to research, acquire, communicate, educate and make use of pertinent information to be able to diagnose and understand global environmental problems and potential solutions”.  These refer specifically to articles 4 and 5 of the FCCC, articles 12, 14, 17 and 26 of the CBD and articles 9, 19 and 16 of the CCD.  More specifically the project, directly or indirectly, addresses the following articles under the Conventions: FCCC (Articles 4 and 5); CBD (Articles 6, 7, 8, 9, 10, 12, 14, 17, 19, 22 and 26), and CCD (Articles 4, 5, 8, 9, 10, and 16).

Table 2: Capacity development requirements of the Rio Conventions

| Type of Capacity | Convention Requirements | FCCC | CBD | CCD |
| --- | --- | --- | --- | --- |
| Stakeholder Engagement | Capacities of relevant individuals and organizations (resource users, owners, consumers, community and political leaders, private and public sector managers and experts) to engage proactively and constructively with one another to manage a global environmental issue. | Article 4 Article 6 | Article 10 Article 13 | Article 5 Article 9 Article 10 Article 19 |
| Organizational Capacities | Capacities of individuals and organizations to plan and develop effective environmental policy and legislation, related strategies, and plans based on informed decision-making processes for global environmental management. | Article 4 Article 6 | Article 8 Article 9 Article 16 Article 17 | Article 4 Article 5 Article 13 Article 17 Article 18 Article 19 |
| Environmental Governance | Capacities of individuals and organizations to enact environmental policies or regulatory decisions, as well as plan and execute relevant sustainable global environmental management actions and solutions. | Article 4 | Article 6 Article 14 Article 19 Article 22 | Article 4 Article 5 Article 8 Article 9 Article 10 |
| Information Management and Knowledge | Capacities of individuals and organizations to research, acquire, communicate, educate and make use of pertinent information to be able to diagnose and understand global environmental problems and potential solutions. | Article 4 Article 5 | Article 12 Article 14 Article 17 Article 26 | Article 9 Article 10 Article 16 |
| Monitoring and Evaluation | Capacities in individuals and organizations to effectively monitor and evaluate project and/or programme achievements against expected results and to provide feedback for learning, adaptive management and suggesting adjustments to the course of action if necessary to conserve and preserve the global environment. | Article 6 | Article 7 |  |

### C.1.b	Project’s Target Contribution to Global Environmental Benefits

The project’s contribution to implementing MEAs lies at the core of the project strategy.  The obligations as defined by the three Rio Conventions, their associated protocols, as well as decisions from their respective Conference of the Parties will inform the set of criteria and indicators that will be integrated into networked management information systems.  The project will also facilitate learning-by-doing training to learn and apply new analytical skills to create better knowledge for delivering global environmental benefits within the framework of national development plans.  The project will demonstrate this contribution through two sub-national development plans (district and municipal) as well as integrating these into a targeted set of economic instruments.

Cross-cutting capacity development projects are not the type of projects that will directly yield global environmental benefits as they focus on strengthening the underlying capacities of programme activities.  Instead, this project, like other CCCD projects, will provide Paraguay with additional tools and strengthen institutional arrangements to facilitate effective and sustained action to meet Rio Convention obligations.  This includes strengthening the appropriate legal instruments to legitimize improved decision-making and institutional mandates to operationalize more resilient land-use planning that meets both national and global environmental priorities.

- CCCD projects are measured by output, process, and performance indicators that are proxies to the framework indicators of improved capacities for the global environment.  To this end, CCCD projects look to strengthen cross-cutting capacities in the five major areas of stakeholder engagement, information and knowledge, policy and legislation development, management and implementation, and monitoring and evaluation.  Project indicators will include output indicators such as the systematic identification of data needs for all three Rio Conventions, process indicators such as workshops that include technical staffs from all key departments and agencies.

- Performance indicators will include an assessment of knowledge gained over the course of project implementation.  This project will implement capacity development activities through an adaptive collaborative management approach to engage stakeholders as collaborators in the design and implementation of project activities that take into account unintended consequences arising from policy interventions.

## C.2  	Project Design: GEF Alternative

### C.2.a	Project Rationale

The rationale for this project is based on the best practice of meeting Rio Convention obligations by mainstreaming these priorities within high value national planning frameworks.  In recent years, Paraguay’s capacities to manage information for decision-making have diminished as technical skills and technology requirements have not kept pace with the need for making decisions that are informed by latest science and best practices.

The project’s baseline is defined by the existing management information systems, as well as the technical capacities available in Paraguay to formulate and implement municipal land-use plans that promote local sustainable development.  However, this baseline is very low.  The technology in SEAM is outdated by at least ten years, with much data and information still only found in hard copy documents.  Most of these require digitization, which is being undertaken by SEAM.  The REDD+ programme is another baseline project that strengthening institutional and technical capacities to measure and assess reductions of greenhouse gas emissions from deforestation and forest degradation.  There are a number of non-state organizations, programmes, and projects that are carrying out important capacity building activities, such as awareness-raising and training on the formulation, implementation, and evaluation of public policies, as well as applied research for territorial development.

In particular, the success of improved coordination of multi-sectoral environment programmes is expected to result in greater effectiveness and efficiency of the Government of Paraguay to meet its obligations under the three Rio Conventions.  It will also ensure that overlap, ambiguities, and competing management responsibilities and accountabilities across agencies and stakeholder organizations are reconciled, with mandates modified to create management synergies and an appropriate level of redundancies that are necessary to create resilience of operational procedures in face of attrition staff and turnover that may lead to institutional memory loss.

A strategic value of this project lies in strengthening the consultative process of decision-making in Paraguay.  While these mechanisms exist (CONAM), thy have been Building on the existing capacities and those developed as part of the NCSA consultative process, the project will strengthen a dialogue process to catalyze effective consultation and collaboration in a cost-effective manner.  The proposed project is transformative in that it serves to catalyze a readjustment of the traditional status quo.  That is, instead of the traditional sectoral approach to decision-making, a more holistic and participatory approach to decision-making by including academia, civil society and local municipalities, more robust, resilient, and legitimate decisions could be made in the name of the global environment.  The replication value of this approach is that it will empower academia, civil society and local municipalities to take more concerted efforts to meeting global environmental objectives.  Through this project, local environmental agencies would be strengthened, setting the bases for its replication in other local agencies.  Thus, enhancing and strengthening the information system and planning at grassroots level.

The project will ensure that a proper use and dissemination of the knowledge, created during the implementation, is done.  In this regard, the project will develop and implement a communication strategy, already defined in the NCSA Action Plan, which will enable to disseminate project results and lessons to a wider audience of environmental managers and practitioners across Paraguay.  The project will set a steady platform for effective and efficient political dialogue, creating cross-institutional alliances that will strengthen the national environmental management at national and local levels

### C.2.b	Project Goal and Objective

The goal of this project is to improve decision-making for the global environment in Paraguay.  To this end, the project will focus on strengthening capacities to create and access better data and information, as well as develop analytical skills to implement Rio Convention obligations within the framework of sub-national planning frameworks.  The project’s objective is to build Paraguay’s capacity to implement NCSA priority actions with a practicable approach towards meeting MEA objectives and achieving environmental sustainability.

Specifically, this will be carried out by strengthening the methodologies for collecting and analyzing data and information, learning-by-doing training on the creation and sharing of new knowledge, and institutionalizing best practices using knowledge to formulate and implement resilient planning frameworks that deliver global environmental benefits.  These will be organized around three project components that are outlined in Figure 1.  Annex 4 provides a logical framework of the project that deconstructs the project objective into component outputs and activities.

Component 2: 	Enhancing institutional arrangements to catalyze Rio Convention implementation

Institutional arrangements and associated policy, legislative, and/or regulative instruments will be strengthened to operationalize and legitimize sub-national level planning frameworks that reflect a more holistic construct of inter-related global and local environmental and sector development priorities.  Technical committees will transform scientific and technical knowledge into policy recommendations that will be acted upon by appropriate participatory decision-making processes on the global environment.  Two municipal land-use plans and economic instruments that reflect global environmental priorities will be piloted.

Key Activities

- Strengthen targeted institutional arrangements and agreements for improved collaborative and coordinated planning between national and municipal planners, decision-makers, and stakeholders, in particular universities and research institutions

- Review and develop updated operational guidance and by-laws to more effectively interpret, implement, and enforce national environmental policies and legislation

- Pilot two municipal-level projects to test up streamlined communication, coordination, and collaborative efforts for municipal-level implementation of sectoral development planning that integrates global environmental indicators.  This will be undertaken through key municipal-level land-use and development plans.

- Develop and implement a pilot project to test the appropriate application of existing economic instruments to catalyze Rio Convention implementation using improved data, information and knowledge

- Building on the two municipal pilot projects and the lessons learned to apply economic instruments to catalyze Rio Convention implementation, develop a national programme for replicating and scaling up integrated global environment 0and sector development plans in all municipalities.

- Develop a resource mobilization strategy to strengthen the financial sustainability of sub-national institutional arrangements to catalyze Rio Convention implementation.

Figure 1: Project design.

Component 3: 	Strengthening technical capacities to manage and implement Rio Convention obligations

Technical capacities of staff, decision-makers, and key stakeholders to think critically of best practices and innovations to implement Rio Conventions will be improved through targeted trainings and learning-by-doing piloting activities.  New tools and methodologies will be identified to diagnose, understand, and transform information and knowledge into local actions to meet and sustain global environmental objectives.  Awareness-raising exercises will build up the long-term absorptive capacity and sustainability of more complex decision-making.  Improved technical capacities will help replicate the best practices piloted under component 2.

Key Activities

- Prepare a targeted set of training and awareness-raising material, building on best practices from neighboring countries in South America, among other countries.

- Carry out learning-by-doing exercises for improved technical capacities to collect, analyze and transform information and knowledge into local action.  In addition to government staff at both the national and municipal levels, this will include stakeholder representatives from NGOs, civil society, private sector, academia, and research institutions

- Organize and carry out awareness-raising workshops with government staff, in particular decision-makers, in planning and budget departments on the intrinsic value of global environmental indicators to national socio-economic priorities

- Develop and implement a communication campaign using the Internet, social media, and public service announcements to share data and information with the broader public on global environmental indicators affecting social and economic issues, e.g., daily ozone concentrations in major municipal areas.

1

3

2

Component 1: 	Strengthening data and information management for the global environment

This component will focus on strengthening information management systems in order for more informed decision-making regarding the global environment.  New and improved data management methodologies, including monitoring and reporting procedures will improve access to more data and information, which will also be integrated into target economic instruments.  Management information systems will be networked for more cost-effective sharing of data and information.  Data sharing protocols will be developed to reduce unnecessary redundancy, raise standards, and streamline access to data, information, and knowledge.  A tracking mechanism for monitoring, reporting, and disseminating environmental information for policy formulation and development planning will be developed.

Key Activities

- Develop a comprehensive set of indicators to inform and measure national and sub-national development and global environmental priorities within the construct of the Rio Conventions

- Develop an integrated/networked environmental management information system to carry out data collection and analysis.  This includes strengthening the intra- and internet-based clearinghouse mechanisms

- Structure a vertically and horizontally integrated Rio Convention monitoring and evaluation system  that is institutionalized within planning and decision-making, including mechanisms for accountability

- Identify, collate, and update a comprehensive yet targeted set of guidance materials and best practices as learning resources for improved data and information management and knowledge creation.

### C.2.c	Expected Outcomes

- At the end of the project, activities will have resulted in a set of improved capacities to meet and sustain Rio Convention objectives.  This project will undertake a set of targeted activities to improve methodologies and standards for creating data, information and knowledge for developing and implementing more resilient land-use planning frameworks that integrate criteria and indicators for meeting Rio Convention obligations.  Institutional linkages and collaborative arrangements will be strengthened to create synergies and allow for the streamlined application of new and improved standards and methodologies.  They will be reinforced by negotiated agreements among partnering institutions to share data, information and knowledge for improved planning and decision-making.  As appropriate, institutional mandates will be updated and by-laws amended and/or developed to strengthen the long-term legitimacy and sustainability of project outcomes.

- Particular attention will be given to strengthening these institutional and associated individual capacities at the sub-national level where much of the custodianship of environmental and natural resources are best adaptively managed.  Two sub-national pilot projects will test the development and application of improved indicators for the global environment in land-use planning frameworks.  The project will take a learn-by-doing approach to reinforce the individual and institutional capacities developed under the project.  This approach will also serve to demonstrate the value of the project, as well as to learn lessons for its replication to other municipal development plans.

- SEAM will serve as the central body to coordinate the management of new and improved data, information and knowledge among partnering ministries, agencies.  This includes non-state organizations that are undertaking activities that are complementary to those to be implemented by this project.

- Particular attention will be given to gender equality.  Paraguay benefits from having a Ministry on Women with the mandate to conduct policy analysis and facilitate the integration of gender equality in national development policies.  Building on this mandate and past efforts, the project will actively integrate gender issues (as well as indigenous rights issues) into consultative and decision-making processes.

### C.2.d	Project Components, Outputs, and Activities

This project will be implemented in three inter-linked components, with activities and outputs in one component informing and building on those of the other two components.  During the project preparation phase, consultations served to further refine and tailor the project activities.

Component 1:	Strengthening data and information management for the global environment

Component 2:	Enhancing institutional arrangements to catalyze Rio Convention implementation

Component 3:	Strengthening technical capacities to implement Rio Convention obligations

Component 1:	Strengthening data and information management for the global environment

Outcome 1:	By the end of the project, better data and information will be more easily available and accessible to inform planners and decision-makers when formulating and implementing sector development plans

Component 1 focuses on strengthening existing environmental data and information management systems in order for Paraguay to undertake more informed decision-making regarding the global environment.  New and improved data management methodologies, including monitoring and reporting procedures and best practices, will be identified to create and access global environmental data and information.  This data will be integrated into targeted economic instruments to raise the perceived value of global environmental benefits.  Among others, the project will strengthen key data and information gaps and weaknesses on assessing air and water quality, energy consumption and greenhouse gas emissions, soil and land quality as related to agricultural productivity, indicators of disaster risk, and population levels of endemic endangered species.

Relevant existing management information systems will be networked for more cost-effective sharing of data and information, as well as to catalyze collaboration to create new knowledge.  An output under this activity will be the development and institutionalization of data sharing protocols for reducing unnecessary redundancy, raising standards, and streamlining access to data, information, and knowledge.  The development and institutionalization of a tracking mechanism for monitoring, reporting, and disseminating environmental information for policy formulation and development planning will be undertaken as part of this component.

Activities under this component will require important cooperation and coordination with a number of institutions that are custodians of data and information needed for effective environmental governance.  Importantly, project activities must be organized and coordinated with a number of other related projects currently under implementation (See section E.1.a).  Whereas this component will include training to improve the administrative operation of the networked management information systems, the learning-by-doing training activities under component 3 will strengthen the technical capacities of social actors to use tools and methodologies to diagnose, understand, and transform information and knowledge into local actions.

Output 1.1	Develop comprehensive set of indicators

In coordination with stakeholder organizations and projects currently undertaking similar activities to develop environmental indicators, activities under this project will help fill gaps in the set of environmental indicators that are available for better planning and decision-making to meet and sustain Rio Convention objectives.

- Activities

    - Contract an in-depth baseline assessment of the current management information systems with particular attention on the data, information, best practices, and knowledge gaps and weaknesses that prevent effective measurement of global environmental impacts and trends.  This includes an assessment of the institutional structures and mechanisms to manage data, information, and knowledge as well as recommendations on priority capacity development activities at the systemic, institutional, and technical levels.

Target indicator:	Assessment report drafted and peer reviewed by month 5 and finalized by month 6

Target indicator:	Baseline assessment is rated as high quality

    - Convene expert working group meetings to select best appropriate indicators with representation from the Rio Convention Focal Points and key regulatory agencies.  This working group is comprised of technical experts and other specialists who will discuss and agree on the specific data, information and knowledge needs to operationalize the information sharing policy and associated regulatory and legislative requirements.  This group will identify and agree on priority channels of environmental information exchange across sectors and ministries through the inter-ministerial council.

Target indicator:	Expert committee composition agreed by the Project Steering Committee in its first meeting by month 4

Target indicator:	Expert committee meets every three (3) months for the first 12 months, and every quarter for the rest of the project

Target indicator:	Appropriate sets of national standards of environmental data and information are identified, as well as regulation necessary for improving coordination and communication at the national level for better reporting system by month 23

Output 1.2	Strengthen networking of environmental management information systems

This output comprises activities to assess and design the best appropriate networking of existing environmental management information systems, in coordination with projects and activities currently underway to strengthen existing information systems.  This output seeks to reduce the overlap in data and information management systems, the unintended consequence of which allows institutions to without collaborating with other institutions with complementary expertise.

- Activities

1.2.1	Convene three expert working groups, one for each of the Rio Conventions to review best practices for data and information sharing and collection.  This will include identifying best practice institutional arrangements for collecting technical data and information and the preparation of a comprehensive set of data and information needs for each lead agency responsible for collecting the data.  The needs of will be described according to the respective measurement metrics and methodologies.  Building on assessment under activity 1.1.1, undertake a targeted study of best practice web-based tools for environmental data and metadata sharing, storage, and management at all levels as part of the design of an integrated environment management information system.

Target indicator:	All three expert working groups convened by month 4

Target indicator:	Undertake a targeted study of best practice web-based tools for environmental data and metadata sharing and storage management at all levels as part of the design of an integrated environment management information system, completed by month 6.

Target indicator:	Data and information needs for each line agency compiled by month 6

Target indicator:	Best practices report on data collection methods drafted, reviewed, and finalized and distributed to relevant stakeholders by month 7.

1.2.2	Convene expert workshops and stakeholder meetings to select the best institutional arrangements to manage data and information.  Agree on recommended institutional reforms detailing the specific institutional requirements necessary to ensure the steady flow of data and information through the data flow system developed under output 1.2.1.  An expert working group for each of the three Rio Conventions will be established.

Target indicator:	All three expert working groups convened by month 5

Target indicator:	Expert working groups presents a consensus agreement on prioritized recommendations by month 12.

Target indicator:	Prepare parliamentary brief to recommend and approve, as appropriate, institutional reforms by month 19.

1.2.3	Negotiate and facilitate networking cooperative agreements on data and information management with key institutions to facilitate and secure improved communication, coordination and collaboration amongst stakeholders.

Target indicator:	Convene inter-ministerial council including representatives from each stakeholder organization formed by month 7and meets four (4) times to discuss and approve recommendations for data and information collection and management as well as the associated training programmes before month 8

Target indicator:	Council meets twice (2) per year to update and revise cooperative agreements and associated training or awareness programmes

Target indicator:	Memorandum of Agreement among partner agencies and other stakeholder organizations to pilot the sharing of data and information during the project is signed by month 8

Target indicator:	At least five (5) different channels of environmental data and information flow through the environmental management information system are agreed upon by month 28

Target indicator:	Electronic information-sharing mechanism on identified priority activities in the context of the Rio Convention is identified by the MEA technical committee and approved by the inter-ministerial council by month 28

Target indicator:	New Memorandum of Agreement is signed by partner agencies and key non-state stakeholder organizations to share data and information per institutional reforms signed by month 32

1.2.4	Strengthen targeted institutional architectures for sharing data and information.  Taking into account the results of activities 1.2.2 and 1.2.3, re-design the institutional arrangements and data and information pathways for realizing a more integrated environmental management information system.  Prepare an operational plan for implementing re-designed architectures, including technological updates and improved electronic information-sharing (both Inter- and Intranet).  This set of activities will be informed by activity 1.2.2.

Target indicator:	Designs for integrated environmental management information system drafted by month 9, distributed to stakeholders for review by month 10, and finalized by month 11

Target indicator:	Feasibility study conducted by month 13, verified by stakeholders and finalized by month 14

Target indicator:		Environmental management information system infrastructure installation begins by month 20 and ends by month 29

Output 1.3	Training programme and materials on improved data and information management

This training programme under this component will focus on the administrative operation and networking of the environmental management information system, emphasizing the collection of data and information, their storage, and sharing protocols.  This training programme will complement that of output 3.2, which focuses on strengthen analytical skills to transform data and information into applied research, knowledge, and other innovations.

- Activities

1.3.1	Undertake a comprehensive assessment of training needs to manage data and information.  This will include administrative operation and networking, sharing protocols, storage, data collection methods and metrics, and knowledge management tools to integrate data, information and knowledge into an environmental management information system in a way that Rio Conventions obligations are also being satisfied.  The assessment will cover national and sub-national training needs for data access, interpretation and use in national development projects and programmes.

Target indicator:	Training needs report drafted by month 6 and finalized and endorsed by Project Steering Committee by month 8

Target indicator:	Training report is rated as high quality

1.3.2	Building on the earlier analyses (activities 1.1.1, 1.2.2, and 1.3.1), prepare a comprehensive training programme and curriculum that includes training materials and modules that incorporate best practices for the sharing, collection and use of environmental data and information.  Participants in the training programme will include all technical government staff that have responsibilities related to the collection and use of environmental data as well as relevant stakeholders from civil society including universities and research institutions.

Target indicator:	Convene expert workshop to review best practices for data collection (activity 1.2.1) and ways of incorporating best practices into training curricula by month 9

Target indicator:	Review training curricula in national training institutions, and develop comprehensive training programme with curricula drafted by month 10, peer-reviewed, and finalized by month 11

Target indicator:	The training programme is rated as high quality

1.3.3	Carry out training courses and workshops on best practices and innovations for the collection and management of data and information.  At the beginning of each course each participant will be tested on their prior knowledge of materials to be taught.  A follow-up test will also be administered at the end of each course to measure each participant’s knowledge of the material taught.  The final results will be statistically analyzed to show incremental learning.  Carry out learn-by-doing exercises to formulate and apply data collection best practices and data quality guidelines for key agencies.  Data quality guidelines will be improved based on the results of this experiment and shared with key government data managing agencies.  This activity will be completed with the training activities of output 3.2 and awareness-raising activities of output 3.3.

Target indicator:	Training programme developed under activity 1.3.2 commences by month 12

Target indicator:	Four (4) training workshops and related exercises begin by month 13

Target indicator:	The average test score of all attendees will be no lower than 80%.

Target indicator:	Learn-by-doing training workshops (at least ten), the first held no earlier than month 14 and the final workshop held no later than month 19

Target indicator:	Collect feedback evaluations from trainees on course effectiveness, 90% response rate for each course following its implementation.  Analyze results by month 23

Target indicator:	At least 250 officials drawn from national, provincial and district level offices of the 16 key technical agencies and other key stakeholder representatives training.

Target indicator:	All technical government staff that have responsibilities related to the collection and use of environmental data participate in all training courses.  A minimum of 100 government staff have participated in training courses by month 28

1.3.4 	Building on the previous training activities, draft replication strategy to expand learning on how to better share and collect information.

Target indicator:	Training program is revised and strengthened on lessons learned by month 27

Target indicator:	New training manual is created and tested by month 30

Component 2:	Enhancing institutional arrangements to catalyze Rio Convention implementation

Outcome 2:	By the end of the project, institutional mechanisms and structures will allow for best practices for Rio Convention implementation to be mainstreamed into sector development plans

Component 2 will focus on institutionalizing the use of best practices to meet and sustain global environmental objectives.  Activities under this component will focus on strengthening targeted institutional arrangements and associated policy, legislative, and/or regulative instruments,  including the formulation of appropriate by-laws and regulation at the national and sub-national levels, as necessary.  The immediate objective of these activities is to operationalize and legitimize sub-national level planning frameworks that reflect a more holistic formulation of inter-related global and local environmental and sector development priorities and obligations.

A key output under this component is the strengthening of existing technical committees (inclusive of stakeholders from academia, civil society, local municipalities, and the private sector) to transform scientific and technical knowledge into policy recommendations that will be acted upon by appropriate participatory decision-making processes on the global environment.  These committees, which are currently operating under other projects, will be expanded to create synergies and achieve cost-effectiveness.  They will submit recommendations to CONAM for endorsement and appropriate follow-up.  This strengthening also requires that consultative and decision-making processes be inclusive, transparent, and streamlined.

The value and viability of using global environmental criteria and indicators to inform planning and decision-making on national priorities will be tested through two sub-national pilot projects – one at the municipal level and the other at the regional government level, i.e., district. This component will also include an activity to pilot the integration of global environmental criteria into economic instruments, which will then be tested through the two pilot municipal land-use plans and the testing of economic instruments that have been improved by the global environmental data created under Component 1.

Output 2.1	Assessment of policy and legislative barriers to Rio Convention mainstreaming

The activities under this component will address the key policy and legislative barriers to implementing the Rio Conventions within the framework of sectoral development and planning frameworks.  This output will involve expert stakeholders to validate the barriers and collectively agree on how best to reconcile the overlaps and fill the gaps.  This will be undertaken through expert and learning-by-doing workshops.  These will help planners and decision-makers to identify potential adjustments of the existing policy and legislative frameworks, including the formulation of appropriate by-laws.  Activities under this output will be coordinated with other similar activities currently being undertaken by other projects, to create synergies across the set of multiple policies and legislation, as well as to reinforce the collaboration among stakeholder institutions to share data and information.

- Activities

2.1.1	Using the Rio Convention legal and policy analytical framework, undertake an analysis of Paraguay’s environmental policy and legislation and their compliance from a Rio Convention perspective.  This activity will be informed by the parallel activity of 1.1.1.  Particular attention must be given to socio-economic impacts, including impacts differentiated by gender and youth.  The review will also consider knowledge gaps and weaknesses that prevent effective mainstreaming of Rio Conventions.  Each Rio Convention will have its own analysis, and a fourth analysis will reconcile the three analyses into one synthesized report.

Target indicator:	The three (3) in-depth thematic analyses (CBD, CCD, and FCCC) of Paraguay’s environmental governance are drafted by month 6.

Target indicator:	The analytical report that synthesizes all three Rio Conventions is drafted and endorsed by the MEA technical working groups by month 8.

Target indicator:	MEA working groups draft policy recommendations for Project Steering Committee approval by month 8.

2.1.2	Prepare a comprehensive learning-by-doing training programme to reconcile weaknesses and gaps in key environmental policies and legal instruments, as well as weaknesses and gaps in trainings for planners and decision-makers to understand and think critically about them.  This exercise will be informed by the baseline analysis of information needs carried out under activity 2.1.1 and carried out in coordination with other relevant programmes and projects.  The trainings proposed will also be informed by the learning-by-doing and pilot exercises under output 2.3.  This activity will inform the preparation of the public awareness campaign of 3.1.3 and the awareness-raising module of 3.3.1.  This training will include best applicable practices on monitoring and compliance.

Target indicator:	Identify and collect new guidelines, tools, and other resources and make available through the electronic platform by month 12

Target indicator:	Comprehensive training programme drafted by month 16 and endorsed by the MEA working groups by month 17

2.1.3	Formulate appropriate by-laws and operational guidance to mainstream Rio Conventions.  This activity focuses on the negotiating among key planners, legal experts, decision-makers, and policy-makers on how to strategically implement and comply with Paraguay’s environmental and related legal instruments.  This activity is heavily based on the results of activity 2.1.2 as well as 2.2.1 that will facilitate consultations and negotiations on designing the best practicable mechanisms for consulting and taking decisions at the highest level.  This activity also calls for addressing the bottlenecks and loopholes in monitoring and compliance that were identified in activity 2.1.1 and legitimizing the recommended best practices identified in activity 2.1.2.

Target indicator:	Operational guidelines are drafted and finalized by month 18.

Target indicator:	Guidelines are validated in stakeholder workshop by month 24

Target indicator:	Policy recommendations to legitimize these guidelines, as appropriate, are prepared, submitted, and approved by the inter-ministerial council by month 30

Output 2.2	Consultative and decision-making processes on Rio Convention implementation

This output will take an objective approach to assessing and strengthening the most appropriate and sustainable consultative and decision-making processes.  Notwithstanding that role of CONAM as the mechanism that brings together decision-makers on environmental matters, other consultative processes, such as the policy committee under the Forest Carbon Partnership Facility project, serve as important opportunities to create cost-effective synergies for sharing data, information, and knowledge.  In collaboration with the related programmes and projects currently underway (See Section E.1), this output will facilitate a more comprehensive approach to structuring and streamlining the consultative and decision-making processes with a view to lowering the transaction costs to high quality data, information and knowledge.  This output will also seek to remove barriers for the access of high quality data, information and knowledge, which is large due to cost, technology, and sharing policies.  This output is also key to invigorating the most appropriate mechanism to legitimize and therefore sustain strengthened capacities to formulate and implement best practice resilient development and territorial plans that catalyze achievement of both sustainable development and Rio Convention goals.

- Activities

2.2.1	Convene working groups to negotiate best consultative and decision-making processes.  Expert working group meetings made up of SISNAM members will be convened to agree on the methodology for the formulation of two sub-national development plans with a Rio Convention character and related indicators and targets.

Target indicator:	The first meeting of the working group will review and discuss the preliminary findings of the institutional assessments of 2.1.1, provide input to finalize the assessment on environmental governance in Paraguay, as well as the formulation of the two sub-national pilot projects (activity 2.3.1) by month 5

Target indicator:	The second meeting of the working group will review the final reports and provide policy recommendations to be incorporated into the drafting of the Memorandum of Agreement of 2.2.2 by month 9.

Target indicator:	The third working group meeting will convene by month 18 to facilitate consultative and decision-making on the two pilot sub-national projects.

Target indicator:	The fourth working group meeting will convene by month 28 to review project findings to date and endorse recommendations for approval by the Project Steering Committee.

2.2.2	Draft memoranda of agreements to formalize agreed consultative and decision-making processes

Target indicator:	Memorandum of Agreement among partner agencies and other stakeholder organizations to pilot the sharing of data and information during the project is drafted by month 10

Target indicator:	Memorandum of Agreement is signed by partner agencies and key non-state stakeholder organizations to share data and information per institutional reforms signed by month 13

Output 2.3	Pilot two sub-national projects

The output is critical to testing and validating the project strategy by using the best practice methodologies to create data and information and the analytical skills to formulate integrated and resilient sub-national development plans for the Chaco region.  This output will include the preparation of lessons learned from these two demonstration projects to inform the preparation of a replication strategy (output 2.4).

- Activities

2.3.1	Finalize the selection of the municipality and district, as well as the specific type of development plan for the pilot activities.  Prepare a project document for the implementation of the two pilot projects for formulating integrated development plans that reflect strong and measurable criteria and indicators for meeting Rio Convention obligations.

Target indicator:	The municipality and district for piloting Rio Convention mainstreaming activities are selected by month 3.

Target indicator:	Sub-national pilot project document is prepared and finalized by month 7.

2.3.2	Implement sub-national pilot projects identified in 2.3.1.  This activity will consist of multiple learning-by-doing workshops with the widest diversity of stakeholders

Target indicator:	Projects are implemented by month 24.

2.3.3	Prepare lessons learned study on sub-national Rio Convention mainstreaming

Undertake a comprehensive review of the lessons learned on sub-national Rio Convention mainstreaming.

Target indicator:		Lessons learned study is not initiated until after the sub-national pilot projects have been completed or by month 25.  Lessons learned study is to be completed by month 32. The lessons learned study will be peer-reviewed and validated at the sub-national and national levels.

Output 2.4	Replication strategy for sub-national Rio Convention mainstreaming

The institutional sustainability of the capacities developed under the project will rely on structuring a long-term programme to replicate key project activities in other districts and municipalities.  This strategy is also informed by the results of output 2.5, which focuses on the financial sustainability of managing the networked environmental management information systems, the functioning of CONAM to support planning at both the national and sub-national levels.

- Activities

2.4.1	Based on lessons learned of output 2.3, prepare a programme to integrate Rio Convention criteria and indicators into the formulation of sub-national development plans throughout Paraguay.

Target indicator:	Convene expert working group to review best practice replication strategies by month 20

Target indicator:	Building on lessons learned of activity 2.3.3, draft replication strategy by month 26

Target indicator:	Draft replication strategy is peer-reviewed and finalized by month 28

Target indicator:	Draft replication strategy is formally approved by CONAM by month 32.

Target indicator:	The training programme is rated as high quality

2.4.2	Carry out regional workshops to inform and validate replication strategy.  This activity calls for sub-national workshops to prepare sub-national specific replication strategies to integrate Rio Convention criteria and indicators into the formulation of municipal and district level development plans.  These workshops will include representatives from local government officials, NGOs, private sector, and civil society to ensure local legitimacy and validity, with particular attention to address local socio-economic priorities.

Target indicator:	Six (6) sub-national workshops are convened between months 22 and 24to provide input into the draft replication strategy.

Target indicator:	Sub-national workshops are convened review draft replication strategy by month 26 and to validate final replication strategy by month 30.

Output 2.5	Resource mobilization strategy for Rio Convention mainstreaming

The resource mobilization strategy is a key companion to the replication strategy (output 2.4).  This strategy will be drafted by nationally contracted experts, but in close coordination with other capacity development projects and institutions.  The preparation of sub-national development plans (output 2.3) will include a resource mobilization component that builds upon project results.

- Activities

2.5.1	Undertake an in-depth financial and economic analysis associated with the long-term financing of the environmental management information system.  Particular attention will be paid to identifying indicators that provide some metric on Rio Convention achievements and outcomes.

Target indicator:	Analytical report drafted, peer reviewed, and completed by month 10

2.5.2	Identify best practice and innovative financial and economic instruments for piloting.  This will build on the results of the expert workshops on best practice indicators of 1.1.2 and take the form of a feasibility study and broad consultations on the strategic choice of instruments to pilot and implement through the learning-by-doing activities of the pilot sub-national projects of output 2.2.

Target indicator:	Feasibility study on financial and economic instruments to pilot within the framework of output 2.2 sub-national pilot projects.  This feasibility study will be completed by month 18 and address Rio Convention mainstreaming in the formulation of sub-national development plans as well as monitoring and evaluation capacities.

2.5.3	Establish expert group of finance and economic experts for the peer review of activities 2.5.1 and 2.5.2, as well as to champion resource mobilization efforts.  This group will also meet to discuss the financial implications of the environmental governance activity 1.1.2.  Experts will be government finance and economic experts, as well as independent experts working in the private and non-profit sectors.

Target indicator:	Expert working group is made up of at least 20 rotating members, who will undertake a desk review of the drafts of the analytical report and feasibility study, and meet at least once to discuss the findings of each within one month of their completion, i.e., by months 15 and 19

2.5.4	Draft a resource mobilization strategy that takes into account Paraguay’s national development framework.  This strategy will be informed by best practices and lessons learned from other similar national environmental funds, including activity 2.5.2 and 2.5.3.  An expert working group will be convened to guide the collaborative formulation and peer-review of a resource mobilization strategy.

Target indicator:	Expert drafts resource mobilization strategy by month 19

Target indicator:	Resource mobilization strategy includes good practices for raising and allocating funds to achieve global environmental targets through decentralized decision-making

Target indicator:	Expert working group reviews and guides the revision and finalization of the resource mobilization strategy by month 25

Target indicator:	Resource mobilization strategy approved by month 28

2.5.5	Formulate operational procedures for the allocation of resources to finance decentralized resource management that delivers global environmental benefits through the national communications.  These will be based on 2.5.4, and tested through the construct of the two sub-national development plans (output 2.3).

Target indicator:	Operational procedures drafted by month 22

Target indicator:	Operational procedures tested and piloted in two (2) sub-national development plans by month 26.

Target indicator:	By month 35, the independent final evaluation determines that the national communications is on solid ground to raise and allocate funds

Component 3:	Strengthening technical capacities to implement Rio Convention obligations

Outcome 3:	By the end of the project, the awareness and knowledge of social actors and other stakeholders to formulate and implement environmentally sound and sustainable development plans is greatly enhanced

Component 3 focuses on strengthening the technical capacities of key stakeholders, technical staff, and decision-makers that directly and indirectly affect obligations under the Rio Conventions.  More specifically, this component focuses on strengthening individual technical capacities to create and use better data, information and knowledge to inform the formulation and implementation of sub-national (municipal and district) land-use and development plans.  Best practices and innovations from this component’s activities, along with those from Component 1 and Component 2 will form the basis of trainings and learning-by-doing piloting activities related to environmental evaluation with particular focus on meeting global environment priorities.  Proactive participation in the learning-by-doing exercises will train participants to think more critically when undertaking their role and responsibilities.  The trainings will be carried out in conjunction with the piloting activities of Component 2 and include government staff, civil society and NGO representatives that carry out similar or related activities, and whom may in the near future be responsible for drafting and implementing development plans.

Awareness-raising exercises are also part of this component, which will be targeted to an extended set of social actors and other stakeholders to build up the long-term absorptive capacity and sustainability of projects outcomes.  This component will help minimize the impact of staff turnover by raising awareness and training people that could more readily replace vacancies.  The sustainability of the project also rests on ensuring that a sufficient baseline of stakeholders value the project and has the support of champions.  Activities are therefore directed to raising the public profile of the project, convening targeted awareness-raising workshops and developing related materials, as well as developing a resource mobilization strategy to address the financial sustainability of project results.

Output 3.1	Public awareness campaign

This output includes a number of activities that are designed to strategically raise project awareness.  This will include convening a project launch conference to showcase the value of addressing Rio Convention obligations in helping Paraguay meet and sustain national development priorities.  A public awareness campaign will be developed to elaborate on the best appropriate practices to help modify the general attitudes in Paraguay on the Rio Conventions.  In order to make some assessment as to awareness raised by carrying out a survey at both the beginning and end of the project.  A public service announcement will be prepared and aired to reach an even larger audience of the general public.  The strengthening of the website of SEAM (among other appropriate institutional websites, as appropriate), will serve to facilitate access of unique data, information, and knowledge to users.  The project will close with a project results conference to showcase the lessons learned throughout the project and thus reinforce its strategic value.

Activities

3.1.1	Organize a one-day conference at the beginning of the project to raise awareness of the project goal and objectives.  This conference will focus on presentations and panel discussions on the challenges of meeting Rio Convention obligations through decentralized governance and the opportunities of this approach.  Organize and convene a one-day conference at the end of the project to promote the value of decentralized environmental governance to deliver global environmental benefits at the same time as meeting socio-economic development priorities.  This conference will focus on presentations and panel discussions on the lessons learned during project implementation, with particular attention given to opportunities for replication to other prefectures and sharing with other South America countries and beyond.  This conference should take place after the second broad-based survey and statistical analysis of activity 1.3.3.

Target indicator:	One-day Kick-Off Conference held within three (3) months of project initiation

Target indicator:	Over 100 participants attend Kick-Off Conference.

Target indicator:	One-day Project Results Conference is held by month 32

Target indicator:	Over 100 participants attend Conference

3.1.2	Design and carry out a broad-based survey to assess public awareness of global environmental issues as well as understanding of Rio Convention mainstreaming.  This activity would be implemented in at the beginning and six months prior to the closing of the project.  This survey will serve as an assessment of baseline awareness for assessing project outcomes.

Target indicator:	Two broad-based surveys carried out by month 4 and by month 33 (N>250 for each survey).

Target indicator:	Baseline awareness report prepared by month 6

Target indicator:	Project end awareness report prepared by month 34.

3.1.3	Develop and validate an over-arching public awareness campaign and implementation plan for environmental awareness, education, and training to the benefit of the territorial communities, their administrations, private sector partners, NGOs and projects intervening on the local level.

Target indicator:	Undertake a comprehensive assessment environmental awareness, education and training needs, completed by month 7

Target indicator:	Environmental awareness, education and training plan is endorsed by CONAM and SEAM by month 9

Target indicator:	Environmental awareness, education and training plan includes a detailed action and financial plan developed in cooperation with partner development agencies

3.1.4	Promote the linkages between local action and global environmental outcomes under the Rio Conventions through social media and on the webpages on the Secretary of Environment.  The website (which may include an electronic discussion forum) will serve as a clearinghouse on up-to-date information about Paraguay’s national implementation of the Rio Conventions.  Use social media, e.g., Facebook, twitter, Instagram, to popularize Rio Convention mainstreaming.

Target indicator:	SEAM website includes new webpage and introductory articles on Rio Convention mainstreaming by month 6

Target indicator:	Memoranda of agreements signed with owners of relevant websites to collaborate and coordinate website content by month 6.

Target indicator:	Website is regularly updated, at least once a month with new information, articles, and relevant links on Rio Convention mainstreaming.

Target indicator:	Number of unique visits to the SEAM Rio Convention mainstreaming webpages has increased by at least 10% between months 6 and 33.

Target indicator:	Facebook page created by month 6, with 750 likes by month 19 and 1,000 likes by month 33

3.1.5	Prepare and air a public service announcement (PSA) on the legislative links between local socio-economic issues and the global environment on television or radio.  This activity will involve the conceptualization of the message, the story-boarding, filming, post-production and distribution.  This will be followed by its airing at strategic intervals.  Special consideration will be made to translate the audio version of the PSA into key indigenous language for the radio version.

Target indicator:	One PSA completed for television or radio by month 12, with the first airing by month 15.

Target indicator:	At least 50 airings of the PSA on television or at least 100 airings of the PSA on radio, by month 34.

Output 3.2	Training programme and knowledge materials

The training programme under this component focuses on strengthening the technical abilities of social actors in Paraguay to formulate and implement integrated and resilient sub-national development plans.  This will complement the training programme in component 1 (output 1.3), which focuses on the administrative operation of the networked environmental information system.  Training activities will be structured as learning-by-doing exercises and in conjunction with the sub-national development plans.

Activities

3.2.1	Assess the training necessary to integrate data, information and knowledge into national planning frameworks in a way that Rio Conventions obligations are also being satisfied.  The assessment will cover national and sub-national training needs for data access, interpretation and use in national development projects and programmes.

Target indicator:	Training needs report drafted by month 6, and finalized and endorsed by Project Steering Committee by month 8

3.2.2	Prepare training programme and curriculum, and collate knowledge materials on strengthening the technical abilities of social actors to formulate and implement integrated and resilient sub-national development plans.  This programme will be informed by the baseline analysis of information needs carried out under activity 3.2.1.

Target indicator:	Comprehensive training programme drafted by month 9 and endorsed by the MEA technical committees by month 11

Target indicator:	At least 80 government staff members that are directly implicated in the planning and decision-making process to monitor and enforce environmental legislation have participated in training workshops by month 32

3.2.3	Undertake learning-by-doing training workshops on Rio Convention-resilient planning frameworks.  Stakeholders (government agencies, academia, public, and NGOs) will be learn best practices on data access and interpretation for environmental management and evidence-based development planning using modules developed under activity 3.2.2.  This activity will be coordinated with other similar training workshops carried under other related projects (See Section E.1).

Target indicator:	Ten (10) learning-by-doing training workshops for public are convened by month 14

Target indicator:	At least 250 unique stakeholders (planners and decision-makers from government bodies as well as other key non-state organizations) at the national and sub-national level actively participate in training workshops.

Target indicator:	Gather feedback evaluations after training programme and workshops on module effectiveness and participants’ recommendations for strengthening training programme and modules with a 90% response rate.  Analyze results by month 32

3.2.4	Prepare articles on linkages between the global environment and local socio-economic issues

These articles will be targeted to the general population and published in print media with a high circulation.  Articles will also be printed as separate brochures for targeted distribution at special events.

Target indicator:	At least 12 articles on the relevancy of the Rio Conventions to Paraguay’s national socio-economic development will be written and published in popular literature with high circulation.  Articles are to be published at least every three (3) months.  First article is to be published by month 6.

Target indicator:	Each article is published as a brochure, at least 100 copies each and distributed to at least two high value special events for greatest impact.

3.2.5	Prepare a five-year training programme to replicate and scale up trainings undertaken in the CCCD project.  This programme will build on the training programmes developed under activities 1.3.2 and 3.2.2, the lessons learned from their respective training workshops, as well as the results of two sub-national pilot projects.  The programme will also take into account the training programmes developed under related parallel projects.

Target indicator:	Training programme drafted by month 28 and peer reviewed and finalized by month 30

Target indicator:	Project Steering Committee approves training programme by month 32.

Output 3.3	Awareness-raising workshops and dialogues

The awareness workshops and dialogues will be elaborated through the public awareness campaign of output 3.1.  As many as possible stakeholders and other social actors will be invited to participate in the workshops and dialogues.  This is intended to increase substantially the number of individuals that are more conscious of the inherent value and need to more environmentally friendly and sustainable development, in particular the value of meeting Rio Convention obligations.  Stakeholders will include a broad cross-section of media representatives, teachers, civil society leaders and champions, private sector, NGO representatives, academic and research institutions, as well as government representatives from all ministries, both at the national and sub-national levels.

Activities

3.3.1	Develop an awareness-raising module on Rio Conventions mainstreaming for institutional representatives within the framework of the public awareness campaign of 3.1.3.  This module does not provide the in-depth training that would be carried out under output 3.2, but rather be tailored to a more general and wider audience of stakeholders.  This awareness-raising module will structure the awareness-raising activities to be carried out under activities 3.3.2 – 3.3.5.

Target indicator:	Module is drafted by month 8, peer reviewed and finalized by month 9

3.3.2	Convene national and sub-national awareness-raising workshops on Rio Convention mainstreaming.  These workshops will be structured and organized on the basis of the public awareness campaign developed by under output 3.1, and use the module prepared by activity 3.3.1.  Target participants will include representatives of all institutional members of SISNAM, as well as district and municipal government planners and decision-makers, among other stakeholder representatives (e.g., NGOs, private sector, and academia).

Target indicator:	Two (2) national workshops with >25 participants are convened by month 12.  Four (4) sub-national workshops with > 25 participants are convened by month 23.  A national workshop and a regional workshop with >25 participants each are convened between months 25 and 32.

Target indicator:	At least 200 unique stakeholders participate in these awareness-raising workshops by month 32.

3.3.3	Convene panel discussions and public dialogues on environmental information management relevant to the Rio Conventions.  These will be held nationally and sub-nationally to reinforce the policy and institutional linkages between the two.

Target indicator:	Four (4) national dialogues on environmental data/information availability and access with at least 30 unique participants attending each dialogue (for a total of 120 participants) every six (6) months beginning by month 12 and ending by month 30

Target indicator:	Three (3) sub-national dialogues on environmental data/information availability and access with at least 90 participants total held by months 12, 18, and 24.

3.3.4	Organize and convene private sector sensitization panel discussions.  These panel discussions will raise the understanding among the private sector of Rio Convention and other environmental indicators.  Particular attention will be given to promoting the value of meeting Rio Convention and other environmental objectives within the framework of socio-economic development.

Target indicator:	Three (3) panel discussions, with at least 30 private sector representatives, one held each year, the first by month 12.

3.3.5		Organize and convene workshops for media professionals to better enable them to report on the environmental information as well as environmental monitoring results (e.g., atmospheric conditions) from the perspectives of the global environmental issues and their relevance to Paraguay.  Particular attention will be given to the implications of global environmental issues and local socio-economic issues in Paraguay.  The project will invite the media from print and audio-visual media to two workshops per year.  The first workshop will introduce the value of an environmental management information system.   Subsequent workshops will be based on the tailored module of activity 3.3.1.

Target indicator:	Six (6) media awareness workshops held (twice per year), each with at least 20 participating media representatives, the first by month 7.

Target indicator:	Articles in the popular press and literature on the Rio Conventions and their implications to local socio-economic priorities have increased 10% over the baseline indicator assessed as part of the activity 3.1.2.

## C.3	Sustainability and Replicability

### C.3.a	Sustainability

- The project’s fundamental approach to sustainability relies on strengthening the underlying technical and institutional capacitates to make more informed decisions on best practice approaches for integrated global environmental and sustainable development.  Sustainability of the project will be ensured by institutionalizing key reforms technical and institutional reforms, which will be project-based and legitimized through Memoranda of Agreement, as well as the formulation and implementation of sub-national planning frameworks.  The latter will be through the integration of global environmental criteria and indicators into the formulation and testing of two sub-national (district and municipal) development plans in the Chaco region.

- The project will take a vertical integration approach to involving government institutions from the local to the national level to take on board the challenges of addressing global environmental challenges.  This requires all government institutions and authorities to use new information and improved mechanisms to make more informed decisions.  This project is strategically designed to meet the Rio Convention priorities by helping stakeholders at all levels in Paraguay to have more ownership and proactively engage in conservation efforts.  The project will actively encourage both a bottom-up and top-down approach in order to achieve traction with as many stakeholder representatives as possible, i.e., governments, private sector, NGOs, civil society, academia, and farmers.

- Another critical feature of the project’s sustainability is its cost-effective strategy.  Making more informed decisions on the global environmental will be based on a more clear understanding of Paraguay’s existing environmental and natural resource management legislation.  Workshops and dialogues carried out under the project will serve to clarify and help reconcile the conflicting requirements of the legislative instruments, as well as demonstrate the use of new methodologies to formulate and implement sub-national planning frameworks.  A critical feature of sustainability is strengthening the value of re-energized consultative and decision-making procedures and reducing bureaucratic inefficiencies by streamlining and catalyzing improved collaboration and coordination.

- An institutional feature of the project’s sustainability is the improved Intra- and Internet-based mechanisms that will be strengthened through networked information systems to lower the transaction costs and catalyze the sharing of information.  These mechanisms will be complemented by a communication campaign to raise awareness and understanding of the value that local actions for the global environment will have on local socio-economic priorities.

- A final feature of the project’s sustainability strategy is through the implementation arrangements.  Most of the project activities are constructed as learning-by-doing activities in order to instill critical thinking by social actors that are responsible for various aspects of environmental monitoring, planning, decision-making, enforcement, and implementation of conservation efforts.   This project will take an adaptive collaborative management approach in order that the mistakes that may occur be used as opportunities for learning better practices.  The project’s sustainability also depends on the success and replicability of the pilot and demonstration projects.

### C.3.b	Replicability and Lessons Learned

- As a medium-size project, this project has certain limitations, namely in being able to undertake institutional and legislative reforms as needed during project implementation.  Instead, this project will serve as catalyst of a more long-term approach to Rio Convention implementation by strengthening key underlying capacities.  This approach will be tested through two sub-national pilot projects, one a municipal land-use plan in the municipality of Filadelfia and the second a district development plan for the Department of Boquerón.  By developing the institutional and technical capacities through pilot and demonstration activities, the replicability of the project is significantly enhanced as the learning curve is greatly reduced.  The project will further support reducing the learning curve by undertaking an assessment of lessons learned and best practices, not only from the pilot and demonstration activities, but from the project overall.

- Lessons learned from these two pilots will inform the development of a replication and resource mobilization strategy that will be used to inform the formulation and financing of new plans in other districts and municipalities.  This strategy will also serve to ensure the sustainability of other technical and institutional capacities developed under the project.

- The replication of project activities is further strengthened by the project implementation arrangements, which will involve numerous stakeholder representatives, many of whom have a strong presence in communities and/or are actively supporting related capacity development work.  Research and academic institutions also play an important role in identifying new and innovative interpretations and policy responses to improve environmental management.  The pilot project to integrate global environmental indicators into economic instruments will also serve to inform future decisions on the global environment.

- Replication will also be supported by raising awareness of the project throughout Paraguay.  This project will facilitate this through awareness-raising workshops with key stakeholders from the local and regional government, the private sector, academia, civil society and the media with the purpose of helping them to write articles about the environment.  The public service announcements on radio and television also serve the purpose of popularizing the project with the public in order to generate greater support and demand for replication activities.

### C.3.c	Risks and Assumptions

There are three main risks associated with this project.  The first is the high risk that project implementation delays due to bureaucratic processes  and weak coordination between national and sub-national (district and municipal) authorities and key stakeholder institutions.  There are many institutionalized procedures that have not been modified as a result of insufficient resources to undertake comprehensive structural reforms, and as a result, administrative reforms are undertaken largely through projects in more manageable increments.  SEAM is particularly challenged in that it does not benefit for sufficient levels of resources, in particular financial and staff, to effectively implement and absorb streamlined operations.

A medium risk of the project is the overall weak cooperation between Paraguay’s line ministries and SEAM.  Despite the important work being undertaken by SEAM, the work of the environment remains largely seen as a sector in of itself, with other government bodies focusing on their own sectoral mandates.  This is rationalized by the perception that the added value of cooperation, e.g., better planning frameworks, is not worth the cost of cooperation.  Due to insufficiently high monitoring and quality control standards, these outputs are deemed sufficient to meet agencies’ development objectives.

A third risk to the project is political change.  This risk is ranked low given that a change in political leadership is unlikely to alter the strategic value of the project to meeting Paraguay’s national environmental and development policies, in particular the National Economic and Social Strategic Plan 2008-2018 of the Government of Paraguay.

There are a number of assumptions that the project makes in its design.  The first assumption pertains to the inherent value of the project.  By strenghtening the quality of data and information, as well as capacities to create new knowledge and innovation, there is an implicit assumption that this will be recognized at all levels of planning and decision-making.  There is a risk that this assumption may prove false, given that past investments and equity have been squandered.  The transaction costs of improving these technical and institutional capacities should be seen as relatively low and a good return on investment with the assumption that they will result in more resilient, inclusive and environmentally friendly development, in particular global environmental benefits.

A second assumption follows from the first in that other government bodies outside of SEAM as well as non-state institutions will benefit from a strengthened networking of their respective environmental management information systems.  While some redundancy is necessary to ensure resilience of the system, the project will help reduce unnecessary overlaps as well as improve critical thinking among planners and decision-makers on the creation and use of better quality data, information and knowledge.

A corollary to this assumption is that project stakeholders will remain engaged throughout the project, actively participating  in project activities.  This includes the sub-national government authorities, i.e., municipalities and district governments, the private sector, academia, media representatives, non-governmental organizations, civil society, and expert research institutions such as Instituto Desarollo.  Through the awareness-raising activities, the project assumes that stakeholders’ values and attitudes towards the environment will be improved.  Part of this same assumption is that members of SISNAM remain committed to supporting environmental governance through the government’s various national environmental strategies, such as the NBSAP.  The project will pay particular attention to strengthening the membership of SISNAM and functionality of key consultative  processes to catalyze, legitimize and institutionalize the project strategy of cross-cutting capacity development.

A third assumption pertains to the policy and legislative framework on environmental governance.  The project makes the assumption that despite the weaknesses among the current set of legal instruments, no new policies, legislation, or regulation is needed.  Instead, the project makes the assumption that building consensus among key decision-makers on how best to reconcile existing instruments can be a cost-effective approach to promoting sustainable development that reflects Rio Convention obligations.  To this end, the project will develop operational by-laws to guide implementation, monitoring, and enforcement of existing legal instruments to guide the formulation and implementation of municipal land-use plans and district development plans (which will be piloted by the project).

## C.4	Stakeholder Involvement

The project will be carried out in a participative and systematic way, including a wide range of multi-stakeholder participants, strengthening community participation, and including the indigenous peoples in the process.  This project will be executed by the Secretariat of the Environment (SEAM), bringing together all the technical and coordination efforts aimed at managing environmental actions and guiding sustainable development processes.  The project will also have the participation of other Ministries and Secretariats, NGOs, academic institutions, private sector representatives, and representatives of civil society.  These include, but are not limited to the Ministry of Agriculture (MAG). Ministry of Finance (MoF), Ministry of Woman (MoM), Ministry of Foreign Affairs (MRE), Ministry of Education and Culture (MEC), Secretariat of Technical Planning (STP), Secretariat of National Emergencies (SEN), Department of Boquerón, Municipality of Filadelfia, Paraguay Indigenous Institute (INDI), Environment Network of NGOs of Paraguay (ROAM), and National University of Asunción (UNA).  These stakeholders will be invited from the very beginning and in all stages of project activities.

Gender:  Paraguay enjoys relatively high gender parity, which is reinforced by the Civil Code of Paraguay (1992) and Article 2 of the Constitution that guarantees women’s access to land.  The latter specifically calls for the government to promote women’s access to land ownership and to guarantee that ownership through access to title deeds.  This ownership is also reinforced by the Agrarian Act (2002) that defines a set of protections for the rights of women to own and manage land.  The Latin American and Caribbean Committee for the Defense of Women’s Rights (CLADEM) in Paraguay, a non-governmental organization, reported in 2004 that women make up only 9 percent of land owners and own only 8 percent of the land surface.

Rural women in Paraguay play an important role in the management of natural resources.  This role and its links to biodiversity conservation remain to be more specifically analyzed.  Previous biodiversity planning processes have not taken gender issues more specifically into consideration.  This will be corrected in the current round.  The project coordination team will ensure that that gender considerations become an integral part of this project.

## C.5	Monitoring and Evaluation

Project monitoring and evaluation will be conducted in accordance with established UNDP and GEF procedures.  The project team and the UNDP Country Office (UNDP/CO) will undertake monitoring and evaluation activities, with support from UNDP/GEF, including by independent evaluators in the case of the final evaluation.  The logical framework matrix in Annex 2 provides a logical structure for monitoring project performance and delivery using SMART indicators during project implementation.  The output budget and the work plan in the UNDP project document provide additional information for the allocation of funds, both the GEF and co-financing, for expected project deliverables and the timing of project activities to produce these deliverables.  Annex 4 provides a breakdown of the total GEF budget by outcome, project management costs, and allocated disbursements on a per year basis.  A GEF tracking tool for CCCD will be used as part of monitoring and evaluation activities to assess project delivery.  The work plan is provisional, and is to be reviewed and endorsed by the Project Steering Committee and during the initiation phase within the first three (3) months of project implementation.

The following sections outline the principle components of monitoring and evaluation.  The project’s monitoring and evaluation approach will be discussed during the project’s initiation report so as to fine-tune indicators and means of verification, as well as an explanation and full definition of project staff M&E responsibilities.

Within the first 2 months of project start, a project initiation workshop will be conducted with the full project team, including the National Project Director, relevant government counterparts, co-financing partners, the UNDP/CO, with representation from the UNDP/GEF Regional Coordinating Unit as appropriate.  Non-governmental stakeholders should be represented at this workshop.

A fundamental objective of this initiation workshop will be to further instill an understanding and ownership of the project’s goals and objectives among the project team, government and other stakeholder groups.  The workshop also serves to finalize preparation of the project’s first annual work plan on the basis of the project’s log-frame matrix.  This will include reviewing the log frame (indicators, means of verification, assumptions), imparting additional detail as needed, and on the basis of this exercise, finalize the Annual Work Plan with precise and measurable performance (process and output) indicators, and in a manner consistent with the expected outcomes for the project.

Specifically, the project initiation workshop will: (i) introduce project staff to the UNDP/GEF expanded team that will support the project during its implementation, namely the CO and responsible Project Management Unit (PMU) staff; (ii) detail the roles, support services and complementary responsibilities of UNDP/CO and PMU staff with respect to the project team; (iii) provide a detailed overview of UNDP/GEF reporting and monitoring and evaluation (M&E) requirements, with particular emphasis on the combined Annual Project Reports - Project Implementation Reviews (APR/PIRs), Project Steering Committee meetings, as well as final evaluation.  The initiation workshop will also provide an opportunity to inform the project team on UNDP project-related budgetary planning, budget reviews, and mandatory budget re-phasing.

The initiation workshop will also provide an opportunity for all parties to understand their roles, functions, and responsibilities within the project’s decision-making structures, including reporting and communication lines, and conflict resolution mechanisms.  The Terms of Reference for PMU staff and associated decision-making structures will be discussed again, as needed, in order to clarify for all, each party’s responsibilities during the project’s implementation phase.

The initiation workshop will present a schedule of M&E-related meetings and reports.  The National Project Manager in consultation with UNDP will develop this schedule, and will include: (i) tentative time frames for Project Steering Committee meetings, and the timing of near-term project activities, such as the in-depth review of literature on natural resource valuation; and (ii) project-related monitoring and evaluation activities.  The provisional work plan will be approved in the first meeting of the Project Steering Committee.

Day-to-day monitoring of implementation progress will be the responsibility of the National Project Manager based on the project’s Annual Work Plan and its indicators.  The National Project Manager will inform the UNDP/CO of any delays or difficulties faced during implementation so that the appropriate support or corrective measures can be adopted in a timely and remedial fashion.

The National Project Manager will fine-tune outcome and performance indicators in consultation with the full project team at the initiation workshop, with support from UNDP/CO and assisted by the UNDP/GEF.  Specific targets for the first year implementation performance indicators, together with their means of verification, will be developed at the initiation workshop.  These will be used to assess whether implementation is proceeding at the intended pace and in the right direction and will form part of the Annual Work Plan.  Targets and indicators for subsequent years would be defined annually as part of the internal evaluation and planning processes undertaken by the Project Team, and agreed with the Implementing Partner (SEAM) among other key project partners sitting on the Project Board and Project Steering Committee.

Periodic monitoring of implementation progress will be undertaken by the UNDP/CO through the provision of quarterly reports from the National Project Manager.  Furthermore, specific meetings may be scheduled between the PMU, the UNDP/CO and other pertinent stakeholders as deemed appropriate and relevant (particularly the Project Steering Committee members).  Such meetings will allow parties to take stock and to troubleshoot any problems pertaining to the project in a timely fashion to ensure smooth implementation of project activities.

Annual Monitoring will occur through the Annual Project Board meeting.  This is the highest policy-level meeting of the parties directly involved in the implementation of a project.  The project will be subject to Project Steering Committee meetings four (4) times per year.  The first such meeting will be held within the first twelve months following the initiation workshop.  For each annual meeting of the Project Board, the National Project Manager will prepare harmonized Annual Project Report / Project Implementation Reviews (APR/PIR) and submit it to UNDP/CO, the UNDP/GEF Regional Coordination Unit, and all Project Steering Committee members at least two weeks prior to the meeting for review and comments.

The APR/PIR will be used as one of the basic documents for discussions in the annual Project Board meeting.  The National Project Manager will present the APR/PIR to the Project Board members, highlighting policy issues and recommendations for the decision of the Committee participants.  The National Project Manager will also inform the participants of any agreement(s) reached by stakeholders during the APR/PIR preparation, on how to resolve operational issues.  Separate reviews of each project output may also be conducted, as necessary.  Details regarding the requirements and conduct of the APR/PIR and Project Board meetings are contained with the M&E Information Kit available through UNDP/GEF.

The terminal review meeting is held by the Project Board, with invitation to other relevant Government and municipal stakeholders as necessary, in the last month of project operations.  The National Project Manager is responsible for preparing the terminal review report and submitting it to UNDP/COs, the UNDP/GEF Regional Coordinating Unit, and all participants of the terminal review meeting.  The terminal review report will be drafted at least one month in advance of the terminal review meeting, in order to allow for timely review and to serve as the basis for discussion.  The terminal review report considers the implementation of the project as a whole, paying particular attention to whether the project has achieved its stated objectives and contributed to the broader environmental objective.  The report also decides whether any actions remain necessary, particularly in relation to the sustainability of project outputs and outcomes, and acts as a vehicle through that lessons learned can be captured to feed into other projects under implementation or formulation.  The terminal review meeting should refer to the independent final evaluation report, conclusions and recommendations as appropriate.

The UNDP/CO, in consultation with the UNDP/GEF Regional Coordinator and members of the Project Board, has the authority to suspend disbursement if project performance benchmarks are not met as per delivery rates, and qualitative assessments of achievements of outputs.

A project initiation report will be prepared immediately following the initiation workshop, but no later than four (4) months after project implementation.  This report will include a detailed First Year Work Plan divided in quarterly time-frames as well as detailed activities and performance indicators that will guide project implementation (over the course of the first year).  This Work Plan will include the proposed dates for any visits and/or support missions from the UNDP/CO, the UNDP/GEF Regional Coordinating Unit, or consultants, as well as time-frames for meetings of the project decision-making structures (e.g., Project Board and Project Steering Committee).  The report will also include the detailed project budget for the first full year of implementation, prepared on the basis of the Annual Work Plan, and including any monitoring and evaluation requirements to effectively measure project performance during the targeted 12 months’ time-frame.

The initiation report will include a more detailed narrative on the institutional roles, responsibilities, coordinating actions and feedback mechanisms of project related partners.  In addition, a section will be included on progress to date on project establishment and start-up activities and an update of any changed external conditions that may affect project implementation, including any unforeseen or newly arisen constraints.  When finalized, the report will be circulated to project counterparts who will be given a period of one calendar month in that to respond with comments or queries.

The combined Annual Progress Report (APR) and Project Implementation Review (PIR is prepared to monitor progress made since project start and in particular for the previous reporting period (30 June to 1 July).  The APR/PIR combines both UNDP and GEF reporting requirements. As a self-assessment report by project management to the Country Office, the APR/PIR is a key input to the annual Project Board meetings.  As a joint combined reporting requirement, the APR/PIR is essential management and monitoring tool for National Project Managers and offers the main vehicle for extracting lessons from on-going projects.

An APR/PIR is to be prepared on an annual basis by June/July, but should be completed well before this deadline (at least one month) in order to be considered at the Project Board meeting (preferably convened around June).  The purpose of the APR/PIR is to reflect progress achieved in meeting the project’s Annual Work Plan and assess performance of the project in contributing to intended outcomes through outputs and partnership work.  The APR/PIR is discussed by the Project Board, so that the resultant report represents a document that has been agreed upon by all of the key stakeholders.

A standard format/template for the APR/PIR is provided by UNDP/GEF.  This includes, but is not limited to reporting on the following:

- Annual Work Plans, related expenditure reports, and ATLAS Quarterly Progress Reports;

- The constraints and barriers (materialized risks) experienced in the progress towards achieving results and the adaptive collaborative management approach to keep the project on track;

- An analysis of project performance over the reporting period, in particular project performance using SMART indicators (project logical framework);

- Lessons learned on best practices and project contribution to institutionalizing sustainability of global environmental outcomes;

- Clear recommendations for future orientation in addressing key problems in lack of progress; and

- An assessment of the portfolio level indicators through the GEF CCCD Capacity Development Scorecard.

UNDP will analyze the individual APR/PIRs by focal area, theme and region for common issues/results and lessons.  The APR/PIRs are also valuable for the independent evaluators who can utilize them to identify any changes in the project’s structure, indicators, work plan, among others, and view a past history of delivery and assessment.

Quarterly:

  - Progress made shall be monitored in the UNDP New Enhanced Results Based Management Platform.

  - Based on the initial risk analysis submitted, the risk log shall be regularly updated in ATLAS.  Risks become critical when the impact and probability are high.  Note that for UNDP GEF projects, all financial risks associated with financial instruments such as revolving funds, microfinance schemes, or capitalization of ESCOs are automatically classified as critical on the basis of their innovative nature (high impact and uncertainty due to no previous experience justifies classification as critical).

  - Based on the information recorded in Atlas, a Project Progress Reports (PPR) can be generated in the Executive Snapshot.

  - Other ATLAS logs can be used to monitor issues, lessons learned etc...  The use of these functions is a key indicator in the UNDP Executive Balanced Scorecard.

During the last three months of the project, the PMU will prepare the Project Terminal Report.  This comprehensive report will summarize all activities, achievements and outputs of the project, lessons learned, the extent to which objectives have been met, structures and mechanisms implemented, capacities developed, among others.  Together with the independent final evaluation, the project terminal report is one of two definitive statements of the project’s activities during its lifetime.  The project terminal report will also recommend further steps, if necessary, in order to ensure sustainability and replicability of the project outcomes and outputs.

An independent Final Evaluation will take place three months prior to the final Project Board meeting and will be undertaken in accordance with UNDP and GEF guidance.  The final evaluation will focus on the delivery of the project’s results as initially planned (and as corrected after the mid-term evaluation, if any such correction took place).  The final evaluation will look at impact and sustainability of results, including the contribution to capacity development and the achievement of global environmental benefits/goals. The Terms of Reference for this evaluation will be prepared by the UNDP CO based on guidance from the Regional Coordinating Unit and UNDP-GEF in consultation with the SEAM.

The Terminal Evaluation should also provide recommendations for follow-up activities and requires a management response which should be uploaded to PIMS and to the UNDP Evaluation Office Evaluation Resource Center (ERC).

Learning and knowledge sharing:

  - Results from the project will be disseminated within and beyond the project intervention zone through existing information sharing networks and forums.

  - The project will identify and participate, as relevant and appropriate, in scientific, policy-based and/or any other networks, which may be of benefit to project implementation though lessons learned. The project will identify, analyze, and share lessons learned that might be beneficial in the design and implementation of similar future projects.

  - Finally, there will be a two-way flow of information between this project and other projects of a similar focus.

Communications and visibility requirements:

  - Full compliance is required with UNDP’s Branding Guidelines.  These can be accessed at http://intra.undp.org/coa/branding.shtml, and specific guidelines on UNDP logo use can be accessed at: http://intra.undp.org/branding/useOfLogo.html. Amongst other things, these guidelines describe when and how the UNDP logo needs to be used, as well as how the logos of donors to UNDP projects needs to be used.  For the avoidance of any doubt, when logo use is required, the UNDP logo needs to be used alongside the GEF logo.   The GEF logo can be accessed at: http://www.thegef.org/gef/GEF_logo.   The UNDP logo can be accessed at http://intra.undp.org/coa/branding.shtml.

  - Full compliance is also required with the GEF’s Communication and Visibility Guidelines (the “GEF Guidelines”).  The GEF Guidelines can be accessed at: http://www.thegef.org/gef/sites/thegef.org/files/documents/C.40.08_Branding_the_GEF%20final_0.pdf.  Amongst other things, the GEF Guidelines describe when and how the GEF logo needs to be used in project publications, vehicles, supplies and other project equipment.  The GEF Guidelines also describe other GEF promotional requirements regarding press releases, press conferences, press visits, visits by Government officials, productions and other promotional items.

  - Where other agencies and project partners have provided support through co-financing, their branding policies and requirements should be similarly applied.

The National Project Manager will provide the UNDP Resident Representative with certified periodic financial statements and an annual audit of the financial statements relating to the status of project funds according to the established procedures set out in UNDP’s Programming and Finance manuals.  The audit on project will follow UNDP Financial Regulations and Rules and applicable Audit policies.

Monitoring and Evaluation Work Plan

| Type of M&E activity | Responsible Parties | Budget US$ Excluding project team staff time | Time frame |
| --- | --- | --- | --- |
| Inception Workshop and Report | - Project Manager - UNDP CO, UNDP GEF | Indicative cost: US$ 5,000 | Within first two months of project start up |
| Measurement of Means of Verification of project results. | - UNDP GEF RTA/Project Manager will oversee the hiring of specific studies and institutions, and delegate responsibilities to relevant team members. | To be finalized in Inception Phase and Workshop. | Start, mid and end of project (during evaluation cycle) and annually when required. |
| Measurement of Means of Verification for Project Progress on output and implementation | - Oversight by Project Manager - Project team | To be determined as part of the Annual Work Plan's preparation. | Annually prior to ARR/PIR and to the definition of annual work plans |
| ARR/PIR | - Project manager and team - UNDP CO - UNDP RTA - UNDP EEG | None | Annually |
| Project Board/ Project Steering Committee Meetings | - National Project Manager - UNDP-CO - GoP representatives | US$ 1,000 per year | Two times per year |
| Periodic status/ progress reports | - Project manager and team | None | Quarterly |
| Mid-term Review | - Project manager and team - UNDP CO - UNDP RCU - Evaluation team | None | Not applicable |
| Independent Final Evaluation | - Project manager and team, - UNDP CO - UNDP RCU - Evaluation team | Indicative cost : US$20,000 | At least three months before the end of project implementation |
| Lessons Learned | - Project manager and team - UNDP CO - Local consultant | None | Yearly |
| Project Terminal Report | - Project manager and team - UNDP CO - Local consultant | 0 | At least three months before the end of the project |
| Audit | - UNDP CO - Project manager and team | US$2,000 per year | Yearly |
| Visits to field sites | - UNDP CO - UNDP RCU (as appropriate) - Government representatives | For GEF supported projects, paid from IA fees and operational budget | Yearly |
| Total indicative cost (Excluding project team staff time and UNDP staff and travel expenses) |  | US$ 34,000 |  |

# D.	Financing

## D.1	Financing Plan

The financing of this project will be provided by the GEF, with co-financing from the Secretariat of SEAM and parallel projects being implemented by UNDP.  During the first year of the project, most of the financing is being directed to assessing the current weaknesses and gaps in data, information, and knowledge.  During this first phase, the project will finance expert analyses and consensus building to reconcile the overlapping and conflicting information.  Financing in the second year will be directed to using extensive learning-by-doing exercises to formulate more resilient territorial development plans (at the municipal and district levels) using stronger global environmental indicators and associated analytical methodologies.  A key set of activities in the first year is to strengthen the technological and information management system architecture to ease and track the flow of data and information to their target users in a timely manner.

Financing during this second year will also be directed to strengthening the associated consultative and decision-making processes to catalyze and ensure the legitimacy of the strengthened sub-national development plans.  The third year of the project is largely directed to learning lessons from pilot activities and to focus capacity building activities on awareness-raising and technical training (although these will be carried out in years 1 and 2).  Financing will be directed to facilitating the institutionalization of the capacities developed under the project, in particular to develop a replication strategy and a robust resource mobilization strategy and action plan.

Table 3: Project costs (US$)

| Total Project Budget by Component | GEF (US$) | Co-Financing (US$) | Project Total (US$) |
| --- | --- | --- | --- |
| Component 1: Data and information | 205,000 | 136,000 | 341,000 |
| Component 2: Institutional capacities | 320,000 | 373,000 | 693,000 |
| Component 3: Management capacities | 275,000 | 251,000 | 526,000 |
| Project Management | 80,000 | 240,000 | 320,000 |
| Total project costs | 880,000 | 1,000,000 | 1,880,000 |

Table 4: Estimated project management budget/cost (estimated cost for the entire project)

| Component | Estimated Staff weeks | GEF (US$) | Co-Financing (US$) | Project Total (US$) |
| --- | --- | --- | --- | --- |
| Locally recruited personnel: Project Manager | 34 | 30,000 | 0 | 30,000 |
| Locally recruited personnel: Project Assistant | 33 | 33,000 | 0 | 33,000 |
| Internationally recruited consultants* | 4 | 10,000 | 26,000 | 36,000 |
| Office facilities and communications |  | 0 | 126,000 | 126,000 |
| Project Steering Committee Meetings |  | 0 | 29,000 | 29,000 |
| Travel |  | 3,000 | 59,000 | 62,000 |
| UNDP Cost Recovery – Bills |  | 4,000 | 0 | 4,000 |
| Total project management cost |  | 80,000 | 240,000 | 320,000 |

* Local and international consultants in this table are those who are hired for functions related to the management of project.  Please see Table 7 below for consultants providing technical assistance for special services.

An internationally recruited consultant will be contracted to undertake the independent final evaluation towards the end of the project.  The travel budget includes the costs of DSA, TE and return airfare for the international consultant.  The travel budget also includes financing to cover the cost of local consultant travel to and from the Chaco district, where the two pilot projects will be taking place.  Travel to other districts and municipalities will also serve to validate the applicability of replicating and scaling up project outcomes.

Table 5: Consultants for technical assistance components (estimated for entire project)

| Local Consultants | Estimated Staff weeks | GEF (US$) | Project Total (US$) |
| --- | --- | --- | --- |
| National CBD Specialist | 23 | 57,500 | 57,500 |
| National CCD Specialist | 23 | 57,500 | 57,500 |
| National FCCC Specialist | 23 | 57,500 | 57,500 |
| Public Administration Expert (1) | 126 | 111,000 | 111,000 |
| Policy/Legal Expert | 15 | 38,500 | 38,500 |
| IT and Knowledge Management Expert | 19 | 47,500 | 47,500 |
| Environmental Sociologist | 14 | 34,500 | 34,500 |
| Environmental Economist | 13 | 32,500 | 32,500 |
| Sub-total |  | 436,500 | 436,500 |
| International Consultants |  |  |  |
| International Technical Specialist | 12 | 30,000 | 30,000 |
|  |  | 30,000 | 30,000 |
| Total |  | 466,500 | 466,500 |

As a capacity development project, over half of the GEF allocation is targeted to using national consultants to carry out the technical and policy assessments, as well as to facilitate the numerous learning-by-doing and awareness raising workshops and dialogues.  A small amount of resources are set aside to provide technical advisory services to help the project technical activities remain relevant and timely.

No UNDP Implementing Agency Project Cycle Management services are being charged to the project budget.  All such costs are being charged to the Implementing Agency fee.  The Government of Paraguay has requested UNDP to provide a few implementation services (including procurement and recruitment) under the National Implementation Modality (NIM), and these will be charged to the project management budget per the agreement on direct projects costs (See Annex 9).  Details of such charges can be provided at the time these services are requested.

## D.2	Cost-Effectiveness

The cost-effectiveness of the project is in part realized through the significant leveraging of SEAM’s investment to improve decision-making for improved global environmental governance.  Six (6) percent of the GEF allocation is available for project management, which is insufficient to recruit a full-time project management team.   Synergies in project management will be achieved by coordinating implementation of this project with other parallel projects being implemented by UNDP and SEAM.

Table 8: Project costs (%)

| Project Budget Component by Contribution Type | Contribution (US$) | Percentage (%) |
| --- | --- | --- |
| Component 1: GEF | 205,000 | 11 |
| Component 1: Co-Financing | 136,000 | 7 |
| Component 2: GEF | 320,000 | 17 |
| Component 2: Co-Financing | 373,000 | 20 |
| Component 3: GEF | 275,000 | 15 |
| Component 3: Co-Financing | 251,000 | 13 |
| Project Management: GEF | 80,000 | 4 |
| Project Management: Co-Financing | 240,000 | 13 |
| Total | 1,880,000 | 100 |

## D.3	Co-financing

This CCCD project takes an incremental approach to developing the foundational capacities needed to meet and sustain Rio Convention objectives.  SEAM is very committed to strengthening these capacities, and is making available significant inputs to co-financing project activities.  This includes updating the institutional infrastructure for managing data and information, facilitating the active participation of SEAM staff at both the national and sub-national levels to formulate and implement more holistic and resilient municipal land-use plans, and coordinating improved technical, consultative, and decision-making arrangements on improved environmental governance for the global environment.

The GEF contribution will be targeted to activities that provide demonstrable global environmental benefits.  Co-financing plays an important role to ensure that the global increment is fully institutionalized within national environmental structures and mechanisms.  GEF financing will be complemented by important co-financing from the Government of Paraguay and UNDP.  Although not specifically identified as co-financing, other development partners will participate in project activities, such as Instituto Desarrollo.  Co-financing will ensure as well that improved decision-support mechanisms, local planning and development processes allow governmental bodies to reduce overlap in the management of data and information, as well as to create innovation and synergies that arises from the sharing of expertise and experience across institutions and agencies.

The incremental approach of this project lies in building upon existing technical and institutional capacities for managing data and information, as well as for the formulation and implementation of sub-national planning frameworks.  The baseline of the project is related to the on-going work of Paraguay to pursue sustainable development, but also includes inadequate capacities to that end.  For this reason, leveraged co-financing is needed to strengthen capacities to raise the sustainable development baseline.  An estimated US$ 1 million has been leveraged by the project, of which US$ 800,000 is from SEAM and US$ 200,000 from UNDP.

Table 9: Co-financing sources

| Name of Co-financier | Classification | Type | Amount |  |
| --- | --- | --- | --- | --- |
|  |  |  | Confirmed (US$) | Unconfirmed (US$) |
| Secretariat of the Environment | Government | Grant | 160,000 | N/A |
| Secretariat of the Environment | Government | In-Kind | 640,000 | N/A |
| UNDP | GEF Implementing Agency | In-Kind | 200,000 | N/A |
| Total Co-financing |  |  | 1,000,000 | N/A |

## D.4	Total GEF Budget and Work Plan

The total outcome budget is based on cash inputs from the GEF contribution.  UNDP’s contribution is being provided as in-kind through non-GEF parallel projects (please see Section E.1), that are and will be undertaking complementary and leveraged capacity development activities.  Further details are provided in Annex 5.

Table 10:  GEF Outcome Budget

| Award ID: |  |  |  | 00084609 |  |  | Project ID: | 00092545 |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Award Title: |  |  |  | Capacity development for improved decision-making for the global environment |  |  |  |  |  |  |  |  |  |
| Business Unit: |  |  |  | PRY10 |  |  |  |  |  |  |  |  |  |
| Project Title: |  |  |  | Capacity development for improved decision-making for the global environment |  |  |  |  |  |  |  |  |  |
| PIMS No: |  |  |  | 4925 |  |  |  |  |  |  |  |  |  |
| Implementing Partner (Executing Agency): |  |  |  | SEAM |  |  |  |  |  |  |  |  |  |
| GEF Outcome/Atlas Activity | Responsible Party/ Implementing Agent | Fund ID | Donor Name |  | Atlas Budgetary Account Code | ATLAS Budget Description |  |  | Amount Year 1 (USD) | Amount Year 2 (USD) | Amount Year 3 (USD) | Total (USD) | Budget Notes |  |
| COMPONENT 1: Strengthened data and information management for the global environment | SEAM | 62000 | GEF |  | 71300 | Local consultants |  |  | 65,000 | 18,000 | 16,500 | 99,500 | 1 |  |
|  |  |  |  |  | 71200 | International consultants |  |  | 3,500 | 3,000 | 3,500 | 10,000 | 2 |  |
|  |  |  |  |  | 72100 | Contractual services: Companies |  |  | 42,000 | 33,500 | 20,000 | 95,500 | 3 |  |
|  |  |  |  |  |  | Sub-total GEF |  |  | 110,500 | 54,500 | 40,000 | 205,000 |  |  |
|  |  |  |  |  |  | Total Outcome 1 |  |  | 110,500 | 54,500 | 40,000 | 205,000 |  |  |
| COMPONENT 2: Enhanced institutional capacities to catalyze Rio Convention implementation | SEAM | 62000 | GEF |  | 71300 | Local consultants |  |  | 61,500 | 69,500 | 37,000 | 168,000 | 1 |  |
|  |  |  |  |  | 71200 | International consultants |  |  | 3,500 | 3,000 | 3,500 | 10,000 | 2 |  |
|  |  |  |  |  | 72100 | Contractual services: Companies |  |  | 34,500 | 85,500 | 22,000 | 142,000 | 3 |  |
|  |  |  |  |  |  | Sub-total GEF |  |  | 99,500 | 158,000 | 62,500 | 320,000 |  |  |
|  |  |  |  |  |  | Total Outcome 2 |  |  | 99,500 | 158,000 | 62,500 | 320,000 |  |  |
| COMPONENT 3: Strengthened capacities for management and implementation on convention guidelines | SEAM | 62000 | GEF |  | 71300 | Local consultants |  |  | 76,000 | 35,500 | 57,500 | 169,000 | 1 |  |
|  |  |  |  |  | 71200 | International consultants |  |  | 3,500 | 3,000 | 3,500 | 10,000 | 2 |  |
|  |  |  |  |  | 72100 | Contractual services: Companies |  |  | 39,500 | 19,500 | 31,000 | 90,000 | 3 |  |
|  |  |  |  |  | 74100 | Professional Services |  |  | 2,000 | 2,000 | 2,000 | 6,000 | 8 |  |
|  |  |  |  |  |  | Sub-total GEF |  |  | 121,000 | 60,000 | 94,000 | 275,000 |  |  |
|  |  |  |  |  |  | Total Outcome 3 |  |  | 121,000 | 60,000 | 94,000 | 275,000 |  |  |
| Project Management | SEAM/UNDP | 62000 | GEF |  | 71300 | Local consultants |  |  | 21,000 | 21,000 | 21,000 | 63,000 | 4 |  |
|  |  |  |  |  | 71200 | International consultants |  |  | 0 | 0 | 10,000 | 10,000 | 5 |  |
|  |  |  |  |  | 71600 | Travel |  |  | 0 | 0 | 3,000 | 3,000 | 6 |  |
|  |  |  |  |  | 74599 | UNDP cost recovery charges |  |  | 1,500 | 1,500 | 1,000 | 4,000 | 7 |  |
|  |  |  |  |  |  | Sub-total GEF |  |  | 22,500 | 22,500 | 35,000 | 80,000 |  |  |
|  |  |  |  |  |  | Total Project Management |  |  | 22,500 | 22,500 | 35,000 | 80,000 |  |  |
| Total Project |  |  |  |  |  | Total Project |  |  | 353,500 | 295,000 | 231,500 | 880,000 |  |  |

| Budget Notes |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | GEF financing for eight (8) local specialists |  |  |  |  |  |  |  |  |
| 2 | GEF financing for an international technical specialist |  |  |  |  |  |  |  |  |
| 3 | GEF financing for various contractual services, such as meeting expenses and publications |  |  |  |  |  |  |  |  |
| 4 | GEF will finance the cost of a part-time Project Manager and part-time Project Assistant |  |  |  |  |  |  |  |  |
| 5 | GEF will finance the cost of an international consultant to conduct terminal evaluation |  |  |  |  |  |  |  |  |
| 6 | GEF will finance the travel of an international consultant to conduct the terminal evaluation |  |  |  |  |  |  |  |  |
| 7 | UNDP cost recovery charges (See Annex 9) |  |  |  |  |  |  |  |  |
| 8 | Audit fee |  |  |  |  |  |  |  |  |

# E.	Institutional Coordination and Support

## E.1	Core Commitments and Linkages

This project constitutes an important support to strengthening Paraguay’s national capacities to meet and sustain Rio Convention obligations.  Many of the activities among these projects are similar, and will involve many of the same stakeholders.  However, this CCCD project fills a number of important data and information gaps needed for Paraguay to take more holistic approaches to ensuring the institutional sustainability of development actions that will also yield global environmental benefits.  The project will be strategically linked to these programmes and projects in a number of ways.

The first linkage is through the strengthening of Paraguay’s consultative and decision-making process, in particular the network of environmental organizations (SISNAM) that have key comparative advantages in environmental conservation.   The project will re-energize a high-level consultative and decision-making mechanism on the environment, building on the lessons learned through the implementation of CONAM and other associated mechanisms in Paraguay.

The project will also create synergies by building upon the existing technical committees established by other projects to carry out CCCD-specific project work.  For example, the technical committees under the National Biodiversity Strategy and Action Plan that is working on Aichi targets could also contribute to helping to reconcile CBD-related indicators with those under the CCD and FCCC.  The Project Steering Committee of this project will comprise many of the same individuals that are members of the Project Steering Committees of other projects.  Synergies can also be created by combining meetings of the Project Steering Committee, which will also facilitate a cross-fertilization of issues, and more importantly help strengthen the coherence of the multiple project strategies and activities.

Other opportunities for creating synergies among projects include the learning-by-doing workshops.  This project will convene a number of these, and to the extent that similar workshops of other projects will involve most of the same participants as well as cover similar issues, workshops can be appropriately integrated.  This is particular true for the awareness-raising workshops and dialogues that will be convened by other projects.

When initiated, the CCCD project will review the current state of play with the current portfolio of programmes and projects to develop a more detailed work plan that identifies CCCD activities and their coordination with activities of other projects and programmes.  This exercise will be particularly important to identify and coordinate the work related to identifying gaps and weaknesses of existing data and information management system.  This work will also include coordinating with other projects for the formulation of the integrated sub-national development projects, i.e., the municipal land-use plans and the district development plan.  Activities under this CCCD project will be tied to specific activities of Paraguay’s REDD+ programme and the human security project.

Paraguay UN REDD+ Programme and Forest Carbon Partnership Facility.  Under implementation since 2011, this is a US$ 4.7 million project under implementation by SEAM, the National Forest Service (INFONA), and the Federation for the Self-Determination of Indigenous Peoples (FAPI), with the support from FAO, UNDP and UNEP.  The aim of this programme is to strengthen institutional and technical capacity of government and civil society organizations to manage REDD+ activities, with particular attention to implementation capacities at the local level.  Activities under this programme will be important complements to the CCCD project, in particular the programme’s preparation of a National Forestry Inventory, a National REDD+ Plan, and an information network mechanism.

Strengthening of human security in central districts of the Paraguayan Chaco:  With funding from the Government of Japan and a budget of US$ 3 million, this project is being implemented by UNDP jointly with the World Food Programme (WFP) and the World Health Organization (WHO).  The objective of this project is to strengthen the capacities of local institutions to overcome health, food, environmental and economic insecurities of vulnerable communities.  This will include the strengthening technical capacities of local government representatives as well as other local social actors to formulate more holistic and resilient local development plans.  The CCCD project will work with this project to co-organize related working group meetings and dialogues, to strengthen the inclusion of global environmental criteria, indicators, and best practices.

E.1.a	Linkages to other activities and programmes

The adaptive collaborative management of the project will help ensure that collaboration and coordination serve mutually beneficial objectives.  In order to secure these arrangements, the CCCD Project Steering Committee and senior officials of SEAM will work closely with their respective counterparts to identify and work out the appropriate cooperative arrangements.

The Ministry of Foreign Affairs, through the Internal Control Committee (ICC) is carrying out the implementation and execution of the Standard Model of Internal Control for Public Institutions (MECIP).  This aim of this project is to improve the efficiency, effectiveness, transparency and effectiveness of the government’s public administration.  Activities under this project include the strengthening of a communication process to improve transparency and disclosure of information to various stakeholders in the public sector

Updating the National Biodiversity Strategy and Developing the Action Plan to Support the Implementation of the CBD 2011-2020 Strategic Plan: This is a GEF-funded enabling activity that will carry out consultative and technical exercises to integrate obligations under the CBD into national development and sectoral planning processes.  Whereas this project focuses on biodiversity, the CCCD project will carry out additional activities to reconcile and strengthen the data and information needs to support the work of the NBSAP project.  The CCCD project will also serve as a mechanism to reconcile the strategic planning for biodiversity with the strategic planning for the two other conventions on climate change and land degradation.

Mainstreaming Biodiversity Conservation and Sustainable Land Management into Production Practices in all Bioregions and Biomes: This project aims to ensure that the biodiversity and ecosystem functions of the Atlantic Forest ecoregion is protected from existing and emerging threats from multi-sectoral production practices and is a model for replication across the country’s bioregions and biomes, will provide a basis for key strategies within the Atlantic Forest ecoregion, and will provide an opportunity for synergies in developing protected area-based climate resilience and adaptation strategies.

The Sustainable Forest Management in the Transboundary Gran Chaco American Ecosystem is a regional project that aims at reversing desertification processes in the Gran Chaco, anchored within SEAM and centralized at local level in the Department of Boquerón.  The national component bears a number of important complementary activities, such as the strengthening of inter-institutional coordination mechanisms among key stakeholders.  Whereas the regional project focuses on sustainable forest management, the CCCD project will have a larger focus on reconciling data, information, and knowledge that takes a wider landscape approach to formulate municipal and district level.

Improving the Conservation of Biodiversity in Atlantic Forest of Eastern Paraguay: This project aims to assist the government of Paraguay in its efforts to reduce the deforestation rate and associated biodiversity loss within the productive landscape of the Paraguayan Atlantic Forest through development of connectivity within a conservation corridor, improving the protected area system, and strengthening of the policy framework and enforcement mechanisms, will also provide the basis for developing a comprehensive protection strategy within the Atlantic Forest ecoregion and will provide the basis for achieving Aichi Target 5 (reducing the rate of loss of natural habitats, including forests).

Biodiversity Conservation and Sustainable Use in the Mbaracayú Natural Reserve: This project aims to conserve globally significant biodiversity in the highly threatened Interior Atlantic Forest of Paraguay by supporting the effective protection and consolidation of the Mbaracayú Natural Reserve and promoting conservation, sustainable use, and land-use planning in the Upper Jejuí River Watershed, will help provide lessons for improving the integration of conservation, sustainable use and land-use planning.

Forest Preservation Programme: This programme is funded with a grant of US$ 7 million from the Japan International Cooperation Agency, the objective of which is to reduce impacts from climate change, with a special emphasis on adaptation and mitigation of climate change as well as access to clean energy, based on the strengthening of forest in protected areas.

Third National Communication on Climate Change and First Biennial Update Report.  SEAM has worked on the creation of the National Climate Change Office (ONCC), and on the design of the National Climate Change Programme in 2001 and the 2008-2012 Climate Change Five- Year Plan, which includes - among others - the promotion of natural regeneration of forests with the aim of covering 10% of the country's surface area.  The ONCC has worked on the preparation and presentation of the First and Second National Communications to the UNFCCC, as well as on generating proposals that deal with the different aspects of climate change, which includes the above-mentioned REDD programme and the Forest Preservation Programme.

## E.2	Implementation and Execution Arrangements

The project will be implemented according to UNDP’s National Implementation Modality (NIM), as per the NIM project management implementation guidelines agreed by UNDP and the Government of Paraguay.

UNDP’s comparative advantage lies first as a global leader to promote countries’ implementation of MEAs, and for Paraguay specifically through its strong country presence and relationship with SEAM and other government bodies to support national development and consensus-building.  UNDP is currently developing and implementing a number capacity development projects, such as the GEF-financed Mainstreaming Biodiversity Conservation and Sustainable Land Management into Production Practices in all Bioregions and Biomes, National Biodiversity Strategy and Action Plan, Third national Communication to the FCCC, and the Regional Sustainable Forest Management in the Transboundary Gran Chaco American Ecosystem.  UNDP supported the Government of Paraguay with a number of other responses to national environmental challenges.  With particular reference to the proposed CCCD project, UNDP in Paraguay will facilitate stakeholder collaboration and help create programmatic synergies and links with other MEA and related development efforts.

The UNDP Country Office in Asunción has developed strong working relationships with the key project stakeholders, and is staffed with two professional officers that manage the Environment and Energy portfolio, and are in turn supported by other operational, senior management and support staff.

Taking an adaptive and collaborative management approach to execution, the project will ensure that key stakeholders are involved early and throughout project execution as partners for development.  This includes their participation in the Project Steering Committee, review of project outputs such as recommendations for amendments to policies, plans, programmes and legislation, as well as participation in monitoring activities.

UNDP is the GEF Implementing Agency for this project, with the UNDP Country Office responsible for transparent practices, appropriate conduct and professional auditing.  The Implementing Agency is the Secretariat of the Environment, which houses the focal points for the CBD, CCD, FCCC and GEF.  SEAM will assign a National Project Director (NPD) and provide its staff and network of experts as support to Project Management Unit (as part of government co-financing).  The basic implementation and execution framework is as follows:

Project Board and Project Steering Committee: The Project Board is specifically established by the project to provide management oversight of project activities as well as to secure the necessary commitments from their respective institutions.  The Project Board will also be an important consultative and decision-making intermediary to the CONAM.  The Board will review progress and evaluation reports, and approve programmatic modifications to project execution, as appropriate and in accordance to UNDP procedures.  Policy recommendations will be discussed and recommended for consideration by the Cabinet of Ministers and Parliament.  Taking into account that the Project Board is a high level mechanism and chaired by SEAM’s highest authority, i.e., Minister, the board will only meet once per year.  In Paraguay, a subsidiary project coordination mechanism, i.e., Project Steering Committee will be created with delegated authority by the Project Board to oversee more regular execution oversight and ensure the project’s adaptive collaborative management.  The Project Steering Committee will meet every three (3) months to this end and chaired by the GEF Operational Focal Point in SEAM.  Given that project activities will require close coordination with other projects, as well as having similar if not identical membership, the Project Steering Committees of multiple GEF project may be convened at back-to-back meetings, facilitating synergies between policy decisions and allowing for cost-effectiveness.

Additionally, the Governor of the Department of Boquerón and the Major of the Municipality of Filadelfia will be a part of this board, representing interests from the local level.  At the local level, the Department of Boquerón and the Municipality of Filadelfia are the Senior Beneficiaries of the project on the basis that the project will be strengthening and integrating Rio Convention provisions into their local sectoral policies, legislation, policies and plans and institutional mandates.  UNDP will be the Senior Supplier, providing technical guidance and support for the cost-effective procurement and implementation of project services and activities, including project implementation oversight through regular monitoring and reporting.

National Project Director:  The SEAM will designate a National Project Director (NPD) from the Directorate of Strategic Planning (DSP) who will be responsible for management oversight of the project.  The NPD may devote a significant part of his/her working time on the project.  Duties and responsibilities of the NPD are described in Annex 7.  In the fulfillment of his/her responsibilities, the NPD will be supported by the Project Board, the Project Steering Committee, and the Project Manager.

Project Management Unit: A Project Management Unit (PMU) will be established for the day-to-day management of project activities and to subcontract and supervise specific components of the project to specialized government agencies, research institutions, as well as qualified NGOs.  This PMU lodged within SEAM’s Directorate of Strategic Planning (DSP) will be supervised by the Director of the DSP or a duly appointed government staff acting as National Project Director operating on a part-time basis. The NPD will be supported by a part-time Project Manager and part-time administrative assistant financed with Project’s funds.

National Consultants: The project will contract eight (8) national experts as consultants to carry out both project management and technical activities.  Annex 7 below outlines for indicative Terms of References for these national consultants.

Capacity Development Activities: The project will take an adaptive collaborative management (ACM) approach to implementation.  That is, UNDP, SEAM and both local governments will manage project activities in order that stakeholders are involved early and throughout project implementation, providing regular input of the performance of project activities.  This will help signal unforeseen risks and contribute to the timely modification and realignment of activities within the boundaries of the project's goal and objectives.

Technical Working Groups:  Working groups will be created to review and discuss the technical and institutional analyses drafted by the experts, as well as to make recommendations to the Project Board.   They may be called upon to undertake targeted drafting exercises.  Three technical working groups will be organized, one for each of the Rio Conventions, and a fourth technical working group that will synthesize and reconcile the results of the three thematic working groups.  These working groups will pay particular attention to making recommendations to the Project Board on the institutionalization of best practices to integrate Rio Convention criteria and indicators into planning, consultative and decision-making processes.  The working groups will be comprised of representatives from the Secretariat of Technical Planning, the Department of Boquerón, the Municipality of Filadelfia, as well as experts from academia, NGOs, among other stakeholder groups.

Stakeholder Consultations: Whereas the technical working groups will focus on discussion and negotiating consensus on a range of technical issues, the stakeholder consultations are the individual consultations with key stakeholders to work out particular issues.

GEF Visibility: Visibility of GEF financial support will be ensured by using the global GEF branding in all electronic and printed materials.  The GEF logo will appear on all relevant project publications, including amongst others, project hardware and other purchases with GEF funds.  Any citation in publications regarding projects funded by GEF will acknowledge the GEF.  Logos of the Implementing Agencies (e.g., UNDP) and the Implementing Partner (i.e., SEAM) will also appear on all publications.  Where other agencies and project partners have provided support (through co-financing) their logos may also appear on project publications.  Full compliance will be made with the GEF’s communication and visibility guidelines and UNDP’s branding guidelines.

Project Steering Committee

Technical Working Groups

(Biodiversity, Climate Change, Land Degradation)

Mayor of the Municipality of Filadelfia

Governor of the Department of Boquerón

Technical Planning Secretariat

Department of Boquerón

Technical representative

Municipality of Filadelfia

Technical representative

Figure 2:  National implementation arrangements

Strategic Planning Directorate

(National Project Director)

Project Board

Ministry of the Environment

UNDP Resident Representative

Project Assurance

(UNDP)

Project Organization Structure

Project Management Unit

(Project Manager, Administrative Assistant, Consultants)

# F.	Legal Context

- This document together with the CPAP signed by the Government and UNDP which is incorporated by reference constitute together a Project Document as referred to in the SBAA (or other appropriate governing agreement) and all CPAP provisions apply to this document.  Consistent with the Article III of the Standard Basic Assistance Agreement, the responsibility for the safety and security of the implementing partner and its personnel and property, and of UNDP’s property in the implementing partner’s custody, rests with the implementing partner.

- The implementing partner will put in place an appropriate security plan and maintain the security plan, taking into account the security situation in the country where the project is being carried; as well as assume all risks and liabilities related to the implementing partner’s security, and the full implementation of the security plan.

- UNDP reserves the right to verify whether such a plan is in place, and to suggest modifications to the plan when necessary.  Failure to maintain and implement an appropriate security plan as required hereunder shall be deemed a breach of this agreement.

- The implementing partner agrees to undertake all reasonable efforts to ensure that none of the UNDP funds received pursuant to the Project Document are used to provide support to individuals or entities associated with terrorism and that the recipients of any amounts provided by UNDP/GEF hereunder do not appear on the list maintained by the Security Council Committee established pursuant to resolution 1267 (1999).  This provision must be included in all sub-contracts or sub-agreements entered into under this Project Document The list can be accessed via:

http://www.un.org/Docs/sc/committees/1267/1267ListEng.htm.

# PART II:	ANNEXES

Annex 1:	Capacity Development Scorecard	55

Annex 2:	Logical Framework	61

Annex 3:	Provisional Work Plan	75

Annex 4:	Outcome Budget (GEF Contribution and Co-financing)	81

Annex 5:	Total GEF Budget and Work Plan	83

Annex 6:	Environmental and Social Review Criteria	87

Annex 7:	Terms of References	96

Annex 8:	CCCD Co-financed activities	102

Annex 9:	Standard letter of agreement between UNDP and Government of Paraguay	103

Annex 10:	References	107

Annex 11:	Unofficial translation of Government Co-financing Letter	108

## Annex 1:	Capacity Development Scorecard

Project/Programme Name: Capacity development for improved decision-making for the global environment

Project/Programme Cycle Phase:	Project preparation 						Date:	December 2014

| Capacity Result / Indicator | Staged Indicators | Rating | Score | Comments | Next Steps | Contribution to which Outcome |
| --- | --- | --- | --- | --- | --- | --- |
| CR 1: Capacities for engagement |  |  |  |  |  |  |
| Indicator 1 – Degree of legitimacy mandate of lead environmental organizations | Institutional responsibilities for environmental management are not clearly defined | 0 |  | SEAM oversees the development, coordination, and implementation of Paraguay’s environmental policies. It hosts the three Rio Convention Focal Points. However, participating officials mention that SEAM is not currently recognized as a leading instance in aspects of natural resource conservation and sustainable management. Its image is greatly affected by inefficient management in large part because there is significant overlapping of roles and competencies. | The capacity of lead environmental organizations and individual capacities will be strengthened. By the end of project, Paraguay will have reconciled and strengthened collaborative arrangements to reconcile institutional mandates to manage data and information and create synergies for the national implementation of the Rio Conventions. The project will also pay particular attention to using and managing data and information to improve monitoring and enforcement. | 1, 2 |
|  | Institutional responsibilities for environmental management are identified | 1 | 1 |  |  |  |
|  | Authority and legitimacy of all lead organizations responsible for environmental management are partially recognized by stakeholders | 2 |  |  |  |  |
|  | Authority and legitimacy of all lead organizations responsible for environmental management recognized by stakeholders | 3 |  |  |  |  |
| Indicator 2 – Existence of operational co-management mechanisms | No co-management mechanisms are in place | 0 |  | Paraguay’s current system of environmental governance is not very effective, with inadequate information and knowledge being used to formulate high quality and resilient sectoral and regional development plans and strategies. This is due in large part from the poor communication and weak collaboration among stakeholder institutions, notably SISNAM. Despite its existence, CONAM does not meet as mandated. | The project will place significant emphasis on consensus building and collaboration on the shared access to data and information. This will be reinforced by negotiated memoranda of agreements. Particular attention will be given to strengthening the role and meetings of CONAM. | 1,2 |
|  | Some co-management mechanisms are in place and operational | 1 | 1 |  |  |  |
|  | Some co-management mechanisms are formally established through agreements, MOUs, etc. | 2 |  |  |  |  |
|  | Comprehensive co-management mechanisms are formally established and are operational/functional | 3 |  |  |  |  |
| Indicator 3 – Existence of cooperation with stakeholder groups | Identification of stakeholders and their participation/involvement in decision-making is poor | 0 |  | There is limited stakeholder involvement in the consultative process that informs policy-making. Inter-governmental cooperation, mainly with the SEAM is virtually non-existent, despite the existence of SISNAM and CONAM. Experts from academic institutions and NGOs are involved in environmental decision-making but their participation is limited. This is particularly the case with the involvement of the private sector. | Through the stakeholder dialogues and learning-by-doing workshops, stakeholder organizations will gain a better understanding of best practices for data and information management, and improved collaborative arrangements. This will also inform improved consultative and decision-making arrangements, including CONAM. | 2 |
|  | Stakeholders are identified but their participation in decision-making is limited | 1 | 1 |  |  |  |
|  | Stakeholders are identified and regular consultations mechanisms are established | 2 |  |  |  |  |
|  | Stakeholders are identified and they actively contribute to established participative decision-making processes | 3 |  |  |  |  |
| CR 2: Capacities to generate, access and use information and knowledge |  |  |  |  |  |  |
| Indicator 4 – Degree of environmental awareness of stakeholders | Stakeholders are not aware about global environmental issues and their related possible solutions (MEAs) | 0 |  | Environmental awareness is generally low among all stakeholders. The general public in Paraguay is generally unaware or unconcerned about the environment or the Rio Conventions, in particular about the contribution of the Rio Conventions to meeting local and national socio-economic priorities. Although a number of key stakeholders are aware of global environmental issues, they do not have sufficient information by which to carry out substantive analyses. While a number of stakeholders do help raise awareness, this is limited. | The project will carry out a number of awareness-raising activities, as well as to facilitate and institutionalize cooperative and collaborative arrangements to raise awareness on meeting Rio Conventions obligations. These will focus on demonstrating the value of better networked environmental management information systems. In addition to the three Rio Conventions, this project will respond to data and information management needs under other multilateral environmental agreements. | 2, 3 |
|  | Stakeholders are aware about global environmental issues but not about the possible solutions (MEAs) | 1 | 1 |  |  |  |
|  | Stakeholders are aware about global environmental issues and the possible solutions but do not know how to participate | 2 |  |  |  |  |
|  | Stakeholders are aware about global environmental issues and are actively participating in the implementation of related solutions | 3 |  |  |  |  |
| Indicator 5 – Access and sharing of environmental information by stakeholders | The environmental information needs are not identified and the information management infrastructure is inadequate | 0 |  | The exchange of data, information, and knowledge as they relate to making better decisions that reflect global environmental criteria in sectoral development plans is minimal. Although environmental information is partially available, the sharing is limited to a handful of partner stakeholders, and usually undertaken within the construct of projects. The sharing of information to municipal and district authorities is particularly limited, in large part because of the absorptive capacities of the receiving institutions. | The project will facilitate collaborative arrangements among stakeholders to secure low cost and barrier-free access and sharing of information, reinforced through memoranda of agreement. The networked information systems will include an Internet-interface that is user-friendly for access data and information relevant to the three Rio Conventions, among other MEAs. | 1, 2 |
|  | The environmental information needs are identified but the information management infrastructure is inadequate | 1 | 1 |  |  |  |
|  | The environmental information is partially available and shared among stakeholders but is not covering all focal areas and/or the information management infrastructure to manage and give information access to the public is limited | 2 |  |  |  |  |
|  | Comprehensive environmental information is available and shared through an adequate information management infrastructure | 3 |  |  |  |  |
| Indicator 6 – Existence of environmental education programmes | No environmental education programmes are in place | 0 |  | Outside of externally funded projects, environmental education programmes are virtually non-existent. There are a few programmes that seek to raise awareness on sustainable forest management with the active participation of stakeholders, but these are only developed and implemented. | The project will work with partner institutions to strengthen their environmental education programmes as well as to increase participation. | 1, 2, 3 |
|  | Environmental education programmes are partially developed and partially delivered | 1 | 1 |  |  |  |
|  | Environmental education programmes are fully developed but partially delivered | 2 |  |  |  |  |
|  | Comprehensive environmental education programmes exist and are being delivered | 3 |  |  |  |  |
| Indicator 7 – Extent of the linkage between environmental research/science and policy development | No linkage exist between environmental policy development and science/research strategies and programmes | 0 |  | Although there has been a limited amount of applied research that has informed the formulation of environmental, forest and agricultural policy, this is not sufficiently taken to the point informing their strategic implementation. This includes an insufficiency of expertise and use of applied research to inform the formulation of integrated land-use and development plans at the sub-national level. | As part of the information management system, the importance of using data for decision-making will be part of the training and sensitization workshops. This will be strengthened by building the capacity of staff to manage data for policy and strategy formulation. | 1, 2 |
|  | Research needs for environmental policy development are identified but are not translated into relevant research strategies and programmes | 1 | 1 |  |  |  |
|  | Relevant research strategies and programmes for environmental policy development exist but the research information is not responding fully to the policy research needs | 2 |  |  |  |  |
|  | Relevant research results are available for environmental policy development | 3 |  |  |  |  |
| Indicator 8 – Extent of inclusion/use of traditional knowledge in environmental decision-making | Traditional knowledge is ignored and not taken into account into relevant participative decision-making processes | 0 | 0 | Traditional and indigenous knowledge is recognized as important, but not collected and used in the relevant processes of participatory decision-making. Notwithstanding, this is currently being addressed through a number of parallel projects, including the UN-REDD+ project recently underway. | Traditional and indigenous knowledge figure among the set of data, information, and knowledge to be collected and used through strengthened collaboration and improved data sharing mechanisms. | 1 |
|  | Traditional knowledge is identified and recognized as important but is not collected and used in relevant participative decision-making processes | 1 |  |  |  |  |
|  | Traditional knowledge is collected but is not used systematically into relevant participative decision-making processes | 2 |  |  |  |  |
|  | Traditional knowledge is collected, used and shared for effective participative decision-making processes | 3 |  |  |  |  |
| CR 3: Capacities for strategy, policy and legislation development |  |  |  |  |  |  |
| Indicator 9 – Extent of the environmental planning and strategy development process | The environmental planning and strategy development process is not coordinated and does not produce adequate environmental plans and strategies | 0 |  | Suitable environmental strategies and plans are partially produced but only partially implemented due to various constraints. These include the insufficient knowledge of best practices or skills to formulate more resilient and integrated land-use and development plans, as well as inadequate financial resources. | This project will undertake a set of targeted activities to improve and showcase methodologies and standards for creating data, information and knowledge and funding for developing and implementing more resilient land-use planning frameworks that integrate criteria and indicators for meeting Rio Convention obligations. This will be carried out through learning-by-doing exercises and the pilot demonstration projects. | 1, 2 |
|  | The environmental planning and strategy development process does produce adequate environmental plans and strategies but there are not implemented/used | 1 |  |  |  |  |
|  | Adequate environmental plans and strategies are produced but they are only partially implemented because of funding constraints and/or other problems | 2 | 2 |  |  |  |
|  | The environmental planning and strategy development process is well coordinated by the lead environmental organizations and produces the required environmental plans and strategies; which are being implemented | 3 |  |  |  |  |
| Indicator 10 – Existence of an adequate environmental policy and regulatory frameworks | The environmental policy and regulatory frameworks are insufficient; they do not provide an enabling environment | 0 |  | The regulatory framework for environmental, forest, and agricultural policy, as well as environmental laws and regulations in force can be considered adequate. However, they are not effectively enforced. | This project will undertake a review policy and legislative weaknesses limiting Rio Convention mainstreaming, training workshops to reconcile policy and legislative weaknesses and gaps and formulate appropriate by-laws and operational guidance to mainstream Rio Conventions. | 2 |
|  | Some relevant environmental policies and laws exist but few are implemented and enforced | 1 |  |  |  |  |
|  | Adequate environmental policy and legislation frameworks exist but there are problems in implementing and enforcing them | 2 | 2 |  |  |  |
|  | Adequate policy and legislation frameworks are implemented and provide an adequate enabling environment; a compliance and enforcement mechanism is established and functions | 3 |  |  |  |  |
| Indicator 11 – Adequacy of the environmental information available for decision-making | The availability of environmental information for decision-making is lacking | 0 |  | Some relevant environmental information is available for environmental decision making, but this remains insufficient for the purposes of making best practice decisions. There are a number of websites that cover the environment, but they are of varying quality and none adequately ensure flow of adequate environmental information management, nor do they clearly articulate best practices for Rio Convention mainstreaming. | The project will train government staff and other stakeholders on how to collect and interpret data and information decision-making. This will include deconstructing Rio Convention obligations into measurable indicators. Improved networking and sharing agreements will facilitate access to high quality data and information, and best practice knowledge. | 1, 2 |
|  | Some environmental information exists but it is not sufficient to support environmental decision-making processes | 1 |  |  |  |  |
|  | Relevant environmental information is made available to environmental decision-makers but the process to update this information is not functioning properly | 2 |  |  |  |  |
|  | Political and administrative decision-makers obtain and use updated environmental information to make environmental decisions | 3 |  |  |  |  |
| CR 4: Capacities for management and implementation |  |  |  |  |  |  |
| Indicator 12 – Existence and mobilization of resources | The environmental organizations don’t have adequate resources for their programmes and projects and the requirements have not been assessed | 0 |  | Although the resource requirements are known they are very limited, and those resources that are available are not being managed effectively. Although a high priority, managers that are responsible for budget are not sufficiently engaged in resource mobilization. | The project will identify new and innovative financial and economic instruments for formulating and implementing integrated land-use and development plans. These will be negotiated and legitimized in consultation with decision-makers, including through CONAM. Particular attention will be given to ensuring the financial sustainability of the work of the municipal and district level development plans. | 2 |
|  | The resource requirements are known but are not being addressed | 1 | 1 |  |  |  |
|  | The funding sources for these resource requirements are partially identified and the resource requirements are partially addressed | 2 |  |  |  |  |
|  | Adequate resources are mobilized and available for the functioning of the lead environmental organizations | 3 |  |  |  |  |
| Indicator 13 – Availability of required technical skills and technology transfer | The necessary required skills and technology are not available and the needs are not identified | 0 |  | The integration of global environment of environmental issues in sectoral and regional planning is not systematic and rarely carried out. Some training is provided, but none on the integration of Rio Convention provisions into sectoral and regional planning. Sometimes, even when technology transfer takes place, there are no national experts to operationalize the activities (as they lack the capacity to do so). | The project will support an extensive programme of training, information dissemination and advocacy to ensure adherence and involvement of concerned stakeholders in the policy and institutional reforms. | 1, 2, 3 |
|  | The required skills and technologies needs are identified as well as their sources | 1 |  |  |  |  |
|  | The required skills and technologies are obtained but their access depend on foreign sources | 2 | 2 |  |  |  |
|  | The required skills and technologies are available and there is a national-based mechanism for updating the required skills and for upgrading the technologies | 3 |  |  |  |  |
| CR 5: Capacities to monitor and evaluate |  |  |  |  |  |  |
| Indicator 14 – Adequacy of the project/programme monitoring process | Irregular project monitoring is being done without an adequate monitoring framework detailing what and how to monitor the particular project or programme | 0 |  | Monitoring is undertaken within the construct of externally funded programmes and projects, but not systematically within corporate programmes due to insufficient absorptive capacities, including clear and enforceable monitoring procedures as well as financial resources. | The project will support an extensive programme of learning-by-doing training and awareness-raising dialogues. These will serve to raise the absorptive and foundational capacities in Paraguay to monitor and assess the national implementation of Rio Conventions. | 1, 2, 3 |
|  | An adequate resource monitoring framework is in place but project monitoring is irregularly conducted | 1 |  |  |  |  |
|  | Regular participative monitoring of results in being conducted but this information is only partially used by the project/programme implementation team | 2 | 2 |  |  |  |
|  | Monitoring information is produced timely and accurately and is used by the implementation team to learn and possibly to change the course of action | 3 |  |  |  |  |
| Indicator 15 – Adequacy of the project/programme monitoring and evaluation process | None or ineffective evaluations are being conducted without an adequate evaluation plan; including the necessary resources | 0 |  | Although there are evaluation programmes, they do not include criteria or indicators to assess their impact on the global environment. These programmes are also only being implemented irregularly. | The learning-by-doing training undertaken by the project will engage government staff to think critically on the use of data and information to assess trends and impacts of policy decisions on the global environment. | 1, 2, 3 |
|  | An adequate evaluation plan is in place but evaluation activities are irregularly conducted | 1 | 1 |  |  |  |
|  | Evaluations are being conducted as per an adequate evaluation plan but the evaluation results are only partially used by the project/programme implementation team | 2 |  |  |  |  |
|  | Effective evaluations are conducted timely and accurately and are used by the implementation team and the Agencies and GEF Staff to correct the course of action if needed and to learn for further planning activities | 3 |  |  |  |  |

## Annex 2:	Logical Framework

| Project Strategy | Objectively verifiable indicators |  |  |  |  |  |  | Sources of verification |  |  |  | Risks and Assumptions |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Indicator |  | Baseline value |  | Target value and date |  |  |  |  |  |  |  |  |  |
| Long-term goal: Paraguay will undertake improved decision-making for the global environment |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Project objectives: A. Strengthen technical capacities to develop and integrate global environmental criteria and indicators into more holistic and resilient planning frameworks. | Outcome indicators: - An strengthened integrated environmental information management system for monitoring and reporting of Paraguay’s MEA targets and indicators - Capacity to use the information management system for monitoring and reporting of Paraguay’s MEA targets and indicators - Institutional and technical capacities are strengthened to create knowledge and mainstream Rio Conventions within national development frameworks - Awareness and environmental education on the linkages between Rio Conventions and national sustainable development objectives |  | - Paraguay has taken steps to integrate environmental considerations into planning, such as the creation of SISNAM and CONAM but the positive results are limited - Paraguay has limited capacity for handling data and information for reporting on MEA including the Rio Conventions - There are gaps in information and the tools by which to collect and manage this information, as well as analytical skills to create knowledge and apply best practices. - Environmental plans and strategies are only partially implemented. |  | By the end of the project: - Rio Convention obligations are being better implemented through an integrated system of data and information managements system. - Increased capacity within relevant stakeholder groups to handle data and information relevant to the Rio Convention |  |  | - Strategic documents within CONAM will indicate that the new system is institutionalized. - The increased reports produced by relevant staff using scientifically credible data and information - Meeting Minutes - Working Group meeting reports - UNDP quarterly progress reports - Independent final evaluation reports - Rio Convention national reports and communications - Inter-Ministerial Task Force decisions - GEF Cross-Cutting Capacity Development Scorecard - Statistical analyses of surveys carried out under activity 1.3.3 |  |  |  | - Involvement of the UNDP will ensure, the lack of absorptive capacity does not undermine project - The project will be executed in a transparent, holistic, adaptive, and collaborative manner - Government staff and non-state stakeholder representatives are actively engaged in the project - Higher quality of data and information, as well as capacities to create new knowledge and innovation, will result in better planning and decision-making - Project stakeholders will remain engaged throughout the project, actively participating in project activities - No new policies, legislation, or regulation is needed. Building consensus among key decision-makers on how best to reconcile existing instruments can be a cost-effective approach to promoting sustainable development that reflects Rio Convention obligations. |  |  |
| Project Strategy | Objectively verifiable indicators |  |  |  |  |  |  | Sources of verification |  |  |  | Risks and Assumptions |  |  |
|  | Indicator |  | Baseline value |  | Target value and date |  |  |  |  |  |  |  |  |  |
| Outcome 1: By the end of the project, better data and information will be more easily available and accessible to inform planners and decision-makers when formulating and implementing sector development plans |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 1.1: Develop comprehensive set of indicators | - Sets of national standards of environmental data are identified - Frequency of working group meetings |  | - Paraguay has several entities that are in charge of monitoring however there is an insufficiency of resources for adequate monitoring - Indicators are incomplete and methods, metrics, and technology are outdated and/or inefficient |  | - Baseline assessment of the current management information systems finalized by month 6 - Expert working group to select best appropriate indicators with representation from the Rio Convention Focal Points and key regulatory agencies meets every three (3) months for the first 12 months, and every quarter for the rest of the project - Appropriate sets of national standards of environmental data and information are identified, as well as regulation necessary for improving coordination and communication at the national level for better reporting system by month 23 |  |  | - Baseline report - Meeting minutes - Sets of national standards |  |  |  | - New indicators lead to environmental improvements - Paraguay has adequate methods, technology, and capacities to measure indicators - Expert peer reviewers follow through with quality reviews |  |  |
| Project Strategy | Objectively verifiable indicators |  |  |  |  |  |  | Sources of verification |  |  |  | Risks and Assumptions |  |  |
|  | Indicator |  | Baseline value |  | Target value and date |  |  |  |  |  |  |  |  |  |
| Output 1.2: Strengthen networking of environmental management information systems Output 1.2: Strengthen networking of environmental management information systems (continued) Output 1.2: Strengthen networking of environmental management information systems (continued) | - Cooperative agreements on data and information management - Installation of environmental management information system infrastructure - Electronic information--sharing mechanism - Frequency of MEA technical committee meetings |  | - Paraguay has barriers to the access of high quality data, information and knowledge, which is due to cost, technology, and sharing policies - Although environmental information is partially available, the sharing is limited to a handful of partner stakeholders, and usually undertaken within the construct of projects. - The sharing of information to municipal and district authorities is particularly limited, in large part because of the absorptive capacities of the receiving institutions. - Eternally funded projects have been largely thematic, and largely focused on capacity assessments |  | - Three expert working groups to review best practices for data and information sharing and collection convened by month 4 - Targeted study of best practice web-based tools for environmental data and metadata sharing and storage management completed by month 6. - Data and information needs for each line agency compiled by month 6 - Best practices report on data collection methods drafted, reviewed, and finalized and distributed to relevant stakeholders by month 7. - Expert workshops and stakeholder meetings to select the best institutional arrangements to manage data and information convened by month 5 - Expert working groups presents a consensus agreement on prioritized recommendations by month 12. - Negotiate and facilitate networking cooperative agreements on data and information management with key institutions - Inter-ministerial convened council by month 7, meets four (4) times to discuss and approve recommendations for data and information collection and management as well as training programmes before month 8 - Memorandum of Agreement among partner agencies and other stakeholder is signed by month 8, new Memorandum is singed by month 32 - At least five (5) different channels of environmental data and information flow through the environmental management information system are agreed upon by month 28 - Electronic information--sharing mechanism on identified priority activities in the context of the Rio Convention is identified by the MEA technical committee and approved by the inter-ministerial council by month 28 - Designs for integrated environmental management information system drafted by month 9, distributed to stakeholders for review by month 10, and finalized by month 11 - Feasibility study conducted by month 13, finalized by month 14 - Environmental management information system infrastructure installation begins by month 20 |  |  | - Memorandum of Agreement - Information needs report - Meeting Minutes - Working Group meeting reports |  |  |  | - The various government authorities maintain commitment to negotiate and agree best practices - Best practices are appropriately used - Government bodies outside of SEAM as well as non-state institutions will benefit from a strengthened networking of their respective members - Members of SISNAM remain committed to supporting environmental governance through the government’s various national environmental strategies environmental management information systems. |  |  |
| Project Strategy |  | Objectively verifiable indicators |  |  |  |  |  |  | Sources of verification |  | Risks and Assumptions |  |  |
|  |  | Indicator |  | Baseline value |  |  | Target value and date |  |  |  |  |  |  |
| Output 1.3: Training programme and materials on improved data and information management Output 1.3: Training programme and materials on improved data and information management (continued) |  | - Survey data on training needs - New training manual is created |  | - The exchange of data, information, and knowledge as they relate to making better decisions that reflect global environmental criteria in sectoral development plans is minimal. - Environmental information is partially available and the sharing is limited - The sharing of information to municipal and district authorities is particularly limited, in large part because of the absorptive capacities of the receiving institutions. - Existing training is limited |  |  | - Comprehensive assessment of training needs to manage data and information finalized by month 6 - Expert workshop to review best practices for data collection (activity 1.2.1) and ways of incorporating best practices into training curricula convened by month 9 - Comprehensive training programme and curriculum finalized by month 11 - Training programme commences by month 12 - Four (4) training workshops and related exercises begin by month 13 - Learn-by-doing training workshops held no earlier than month 14 and the final workshop held no later than month 19 - Feedback collected from evaluations from trainees on course effectiveness. Results analyzed by month 23 - At least 250 officials drawn from national, provincial and district level offices of the 16 key technical agencies and other key stakeholder representatives training. - A minimum of 100 government staff have participated in training courses by month 28 - Ten (10) one-day sensitization workshops to raise awareness by at least 150 mid-level and senior decision-makers and planners by month 32 - New training manual is created and tested by month 30 |  | - Assessment of needs - Report - Meeting minutes - Evaluations |  | - Survey respondents contribute their honest attitudes - Agencies will allow their staff to attend all trainings - The right representation from the various government ministries, departments, and agencies participate in project activities - Analyses are deemed legitimate, relevant, and valid among all key stakeholder representatives and project champions |  |  |
| Outcome 2: By the end of the project, institutional mechanisms and structures will allow for best practices for Rio Convention implementation to be mainstreamed into sector development plans |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Project Strategy |  | Objectively verifiable indicators |  |  |  |  |  |  | Sources of verification |  | Risks and Assumptions |  |  |
|  |  | Indicator |  | Baseline value |  |  | Target value and date |  |  |  |  |  |  |
| Output 2.1: Assessment of policy and legislative barriers to Rio Convention mainstreaming Output 2.1: Assessment of policy and legislative barriers to Rio Convention mainstreaming (continued) |  | - Endorsed policy recommendations to legitimize guidelines - Thematic reports - Frequency of MEA technical committee meetings |  | - The regulatory framework for environmental, forest, and agricultural policy, as well as environmental laws and regulations in force is adequate, however, they are not effectively enforced. - Paraguay’s current system of environmental governance is not very effective, with inadequate information and knowledge being used to formulate high quality and resilient sectoral and regional development plans and strategies. |  |  | - The three (3) in-depth thematic analyses (CBD, CCD, and FCCC) of Paraguay’s environmental governance are drafted by month 6. - The analytical report that synthesizes all three Rio Conventions is drafted and endorsed by the MEA technical working groups by month 8. - MEA working groups draft policy recommendations for CONAM by month 8. - Comprehensive learning-by-doing training programme to reconcile weaknesses/gaps in key environmental policies and legal instruments - Identify and collect new guidelines, tools, and other resources and make available through the electronic platform by month 12 - Comprehensive training programme drafted by month 16 and endorsed by the MEA working groups by month 17 - At least 80 government staff members have participated in training workshops by month 30 - Formulate appropriate by-laws and operational guidance to mainstream Rio Conventions, drafted and finalized by month 18, validated in stakeholder workshop by month 24 - Policy recommendations to legitimize these guidelines are prepared, submitted, and approved by the inter-ministerial council by month 30 |  | - Analyses of governance - Analytical report - Policy recommendations for CONAM |  | - Policy and institutional recommendations are politically, technically, and financially feasible and approved by the CONAM - No new policies, legislation, or regulation is needed. Building consensus among key decision-makers on how best to reconcile existing instruments can be a cost-effective approach to promoting sustainable development that reflects Rio Convention obligations. |  |  |
| Output 2.2: Consultative and decision-making processes on Rio Convention implementation Output 2.2: Consultative and decision-making processes on Rio Convention implementation (continued) |  | - Memorandum of Agreement among partner agencies and other stakeholder organizations to pilot the sharing of data and information - Frequency of working group meetings |  | - There is poor communication and weak collaboration among stakeholder institutions, notably SISNAM. Despite its existence, CONAM does not meet as mandated. - The exchange of data, information, and knowledge as they relate to making better decisions that reflect global environmental criteria in sectoral development plans is minimal. Although environmental information is partially available, the sharing is limited to a handful of partner stakeholders, and usually undertaken within the construct of projects. - The sharing of information to municipal and district authorities is particularly limited, in large part because of the absorptive capacities of the receiving institutions. |  |  | - Four working groups meetings: the first meeting of the working group will review and discuss the preliminary findings of the institutional assessments, provide input to finalize the assessment on environmental governance in Paraguay, as well as the formulation of the two sub-national pilot projects by month 5 - The second meeting of the working group will review the final reports and provide policy recommendations to be incorporated into the drafting of the Memorandum of Agreement of 2.2.2 by month 9. - The third working group meeting will convene by month 18 to facilitate consultative and decision-making on the two pilot sub-national projects. - The fourth working group meeting will convene by month 28 to review project findings to date and endorse recommendations for CONAM uptake. - Memorandum of Agreement among partner agencies and other stakeholder organizations to pilot the sharing of data and information during the project is drafted by month 10, signed by partner agencies and key non-state stakeholder organizations to share data and information per institutional reforms by month 13 |  | - Memorandum of Agreement - Working groups meeting minutes |  | - Members of SISNAM remain committed to supporting environmental governance through the government’s various national environmental strategies |  |  |
| Output 2.3: Pilot two sub-national projects |  | - Project document for the implementation of the two pilot projects for formulating integrated development plans that reflect strong and measurable criteria and indicators for meeting Rio Convention obligations. - Prepare lessons learned study on sub-national Rio Convention mainstreaming. |  | - Suitable environmental strategies and plans are partially produced but only partially implemented due to various constraints such as insufficient knowledge of best practices or skills to formulate more resilient and integrated land-use and development plans, as well as inadequate financial resources. - The integration of global environment of environmental issues in sectoral and regional planning is not systematic and rarely carried out. |  |  | - Finalize the selection of the municipality and district, as well as the specific type of development plan for the pilot activities. Prepare a project document for implementation. - The municipality and district for piloting Rio Convention mainstreaming activities are selected by month 3. - Sub-national pilot project document is prepared and finalized by month 7. - Implement sub-national pilot projects identified in 2.3.1. This activity will consist of multiple learning-by-doing workshops with the widest diversity of stakeholders - Projects are implemented by month 24. - Prepare lessons learned study on sub-national Rio Convention mainstreaming - Undertake a comprehensive review of the lessons learned on sub-national Rio Convention mainstreaming. - Lessons learned study completed by month 32 |  | - Peer reviewer comments - Project document for implementation - Lessons learned report |  | - Strategy and plan developed by the project are politically, technically, and financially feasible - Best practices and lessons learned are appropriately used |  |  |
| Output 2.4: Replication strategy for sub-national Rio Convention mainstreaming Output 2.4: Replication strategy for sub-national Rio Convention mainstreaming (continued) |  | - Final replication strategy |  | - Paraguay has number of environmental projects that seek to demonstrate and catalyze action to meet Rio Convention obligations through market instruments, such as the Mainstreaming Biodiversity Conservation and Sustainable Land Management into Production Practices in all Bioregions and Biomes. - CONAM has the mandate to approve policies that are intended to catalyze advances in environmental conservation. However, CONAM has not convened sufficiently frequently to carry out this mandate. - The implementation of conservation efforts have largely operated within the framework of existing policy frameworks and carried out within the construct of externally funded projects. - Projects have been largely thematic, and largely focused on capacity assessments. |  |  | - Convene expert working group to review best practice replication strategies by month 20 - Draft replication strategy by month 26, peer-reviewed and finalized by month 28 - Draft replication strategy is formally approved by CONAM by month 32. - Six (6) sub-national workshops are convened between months 22 and 24to provide input into the draft replication strategy. - Sub-national workshops are convened review draft replication strategy by month 26 and to validate final replication strategy by month 30. |  | - Draft and final strategy - Meeting minutes |  | - Implementation delays due to bureaucratic processes and weak coordination between national and sub-national (district and municipal) authorities and key stakeholder institutions - Political change will not lead to lack of support for project in future - Government bodies outside of SEAM as well as non-state institutions will benefit from a strengthened networking of their respective members - Members of SISNAM remain committed to supporting environmental governance through the government’s various national environmental strategies environmental management information systems. - Project stakeholders will remain engaged throughout the project, actively participating in project activities |  |  |
| Output 2.5: Resource mobilization strategy for Rio Convention mainstreaming Output 2.5: Resource mobilization strategy for Rio Convention mainstreaming (continued) |  | - Baseline analysis of financing needs for environmental management information system - Feasibility study on financial and economic instruments to pilot |  | - Although the resource requirements are known, they are very limited, and those resources that are available are not being managed effectively. - Managers that are responsible for budget are not sufficiently engaged in resource mobilization. |  |  | - In-depth financial and economic analysis associated with the long-term financing of the environmental management information system, analytical report drafted, peer reviewed, and completed by month 10 - Identify best practice and innovative financial and economic instruments for piloting. - Feasibility study on financial and economic instruments to pilot completed by month 18 - Establish expert group of finance and economic experts for the peer review of activities 2.5.1 and 2.5.2, as well as to champion resource mobilization efforts. This group will also meet to discuss the financial implications of the environmental governance activity 1.1.2. Experts will be government finance and economic experts, as well as independent experts working in the private and non-profit sectors. - Expert working undertake a desk review of the drafts of the analytical report and feasibility study, and meet at least once to discuss the findings of each within one month of their completion, i.e., by months 15 and 19 - Resource mobilization strategy drafted by month 19 - Expert working group reviews and guides the revision and finalization of the resource mobilization strategy by month 25 - Resource mobilization strategy approved by month 28 - Formulate operational procedures for the allocation of resources to finance decentralized resource management drafted by month 22 - Operational procedures tested and piloted in two (2) sub-national development plans by month 26. |  | - Analysis of needs - Resource mobilization strategy - Meeting minutes - Feasibility study report |  | - Global financial and economic pressures do have significantly adverse impacts on the opportunities to mobilize resources from national sources, such as raising park entrance fees, increased enforcement and collection of fees and fines. - Compliance with environmental legislation can be politically and expediently pursued in tandem with socio-economic development plans and programmes, in particular green economy policies - Champions for innovative approaches to finance the enforcement and compliance of environmental legislation are not outdone by champion detractors - Expert peer reviewers follow through with quality reviews |  |  |
| Outcome 3: By the end of the project, the awareness and knowledge of social actors and other stakeholders to formulate and implement environmentally sound and sustainable development plans is greatly enhanced |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Project Strategy | Objectively verifiable indicators |  |  |  |  |  |  |  | Sources of verification | Risks and Assumptions |  |  |
|  | Indicator |  | Baseline value |  |  | Target value and date |  |  |  |  |  |  |
| Output 3.1: Public awareness campaign | - Facebook page created - PSA on television or radio - One-day Kick-Off Conference to raise high profile of project - One-day Project Results Conference to showcase lessons learned and best practices - Survey data on environmental attitudes and values |  | - The general public in Paraguay is generally unaware or unconcerned about the environment or the Rio Conventions, in particular about the contribution of the Rio Conventions to meeting local and national socio-economic priorities |  |  | - Baseline awareness report prepared by month 6. - Project end awareness report prepared by month 34. - Over 100 participants attend Kick-Off and Results Conference - One PSA completed for television or radio by month 12, with the first airing by month 15. - At least 50 airings of the PSA on television or at least 100 airings of the PSA on radio, by month 34. - Number of unique visits to the SEAM Rio Convention mainstreaming webpages has increased by at least 10% between months 6 and 33. - Facebook page created by month 6, with 750 likes by month 19 and 1,000 likes by month 33 |  |  | - Memoranda of agreements - Meeting minutes - Tracking and progress reports - Baseline awareness report - Project end awareness report - Facebook ‘likes’ - Website and unique site visits using site meters | - Workshops and dialogues will further enhance support for Rio Convention mainstreaming - Participation to the public dialogues attracts people that are new to the concept of Rio Convention mainstreaming, as well as detractors. - Interest in environmental issues can be distinguished from rising interest on Rio Convention mainstreaming - Survey respondents contribute their honest attitudes and values |  |  |
| Output 3.2: Training programme and knowledge materials | - Articles on the relevancy of the Rio Conventions to Paraguay’s national socio-economic development - Five-year training programme |  | - Some training is provided, but none on the integration of Rio Convention provisions into sectoral and regional planning. - When technology transfer takes place, there are no national experts to operationalize the activities (as they lack the capacity to do so). - Although there has been a limited amount of applied research that has informed the formulation of environmental, forest and agricultural policy, this is not sufficiently taken to the point informing their strategic implementation. This includes an insufficiency of expertise and use of applied research to inform the formulation of integrated land-use and development plans at the sub-national level. - There are gaps in information and the tools by which to collect and manage this information, as well as analytical skills to create knowledge and apply best practices. - Constraints such as insufficient knowledge of best practices or skills to formulate more resilient and integrated land-use and development plans exist in Paraguay |  |  | - Training needs report drafted by month 6, and finalized and endorsed by Project Board by month 8 - At least 80 government staff members have participated in training workshops on strengthening the technical abilities of social actors by month 3 - Ten (10) learning-by-doing training workshops on Rio Convention-resilient planning frameworks for public are convened by month 14 - Project board approves a five-year training programme by month 32. - Analyze results by month 32 of feedback from learning-by-doing training workshops on Rio Convention-resilient - At least 12 articles on the relevancy of the Rio Conventions to Paraguay’s national socio-economic development are written and published |  |  | - Training needs report - Published articles - Feedback from Evaluations after learning-by-doing training workshops on Rio Convention-resilient planning frameworks - Meeting minutes - Awareness and sensitization workshop reports | - Articles published in the popular media will be read and not skipped over - Expert peer reviewers follow through with quality reviews - Best practices from neighboring countries in South America are used appropriately |  |  |
| Output 3.3: Awareness-raising workshops and dialogues Output 3.3: Awareness-raising workshops and dialogues (continued) | - Three (3) expert panel discussions on Rio Convention sub-themes - Articles in the popular press and literature on the Rio Conventions and their implications to local socio-economic priorities have increased 10% over the baseline indicator |  | - Paraguay has been carrying out a number of activities to promote environmental consciousness. However, they are thematic. - Articles on the Rio Conventions are being published, but in specialized literature that is largely read by environmental supporters or in the popular literature during crisis events, with few exceptions - The private sector is primarily focused on traditional approaches to maximizing profits, seeing environmental issues as an added transaction cost that reduces profits |  |  | - Awareness-raising module on Rio Conventions mainstreaming for institutional representatives is finalized by month 9 - Two (2) national awareness-raising workshops on Rio Convention mainstreaming with >25 participants are convened by month 12, and another one between month 25-32 - Four (4) sub-national awareness-raising workshops on Rio Convention mainstreaming with > 25 participants are convened by month 23, another regional workshop with >25 participants convened between months 25 and 32. - Four (4) national dialogues on environmental data/information availability and access with at least 30 unique participants attending each dialogue every six (6) - Three (3) sub-national dialogues on environmental data/information availability and access with at least 90 participants held by months 12, 18, and 24. - Three private sector sensitization panel discussions with at least 30 private sector representatives, one held each year, the first by month 12. - Six (6) media awareness workshops held (twice per year), each with at least 20 participating media representatives, the first by month 7. - Articles in the popular press and literature on the Rio Conventions and their implications to local socio-economic priorities have increased 10% over the baseline indicator assessed as part of the activity 3.1.2. |  |  | - Workshop and dialogue registration lists - Awareness-raising module - Meeting minutes - Tracking and progress reports - Participant registration lists - Awareness and sensitization workshop reports - Public dialogue meeting reports | - Articles published in the popular media will be read and not skipped over - Media representatives and private sector representatives are open to learn about Rio Convention values and opportunities, and will actively work to support project objectives - Participation to the public dialogues attracts people that are new to the concept of Rio Convention mainstreaming, as well as detractors, with the assumption that dialogues will help convert their attitudes in a positive way - Public attitudes towards environment are not too negative and socio-economic pressures not too great that they are willing to participate in awareness raising activities - Expert peer reviewers follow through with quality reviews |  |  |

## Annex 3:	Provisional Work Plan

| WORK PLAN |  | Year 1 |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Project Components, Outputs, and Activities |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 |
| Component 1 | Strengthened data and information management for the global environment |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 1.1 | Comprehensive set of Rio Convention indicators |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.1.1 | Assess data and information indicators, weaknesses, and best practices |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.1.2 | Convene expert meetings to select best appropriate indicators |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 1.2 | Strengthened networking of environmental management information systems |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.2.1 | Review and design institutional arrangements for collecting and sharing data |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.2.2 | Convene expert workshops on data and information management arrangements |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.2.3 | Negotiate networking agreements on data and information management |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.2.4 | Strengthen targeted institutional architectures for sharing data and information |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 1.3 | Training programme and materials on data and information management |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.3.1 | Undertake assessment of training needs on data and information management |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.3.2 | Prepare training programme and curriculum |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.3.3 | Carry out training workshops on data and information management |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.3.4 | Develop long-term training programme on data and information management |  |  |  |  |  |  |  |  |  |  |  |  |
| Component 2 | Enhanced institutional capacities to catalyze Rio Convention implementation |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 2.1 | Assessment of policy and legislative barriers to Rio Convention mainstreaming |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.1.1 | Review policy and legislative weaknesses limiting Rio Convention mainstreaming |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.1.2 | Learn-by-doing workshops to reconcile policy and legislative weaknesses and gaps |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.1.3 | Formulate appropriate by-laws and operational guidance to mainstream Rio Conventions |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 2.2 | Consultative and decision-making processes on Rio Convention implementation |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.2.1 | Working group meetings to negotiate best consultative and decision-making processes |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.2.2 | Draft memoranda of agreements on consultative and decision-making processes |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 2.3 | Two pilot sub-national projects |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.3.1 | Finalize selection of sub-national plans to pilot and formulate project document |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.3.2 | Implement pilot projects (municipal and district) |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.3.3 | Prepare lessons learned study on sub-national Rio Convention mainstreaming |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 2.4 | Replication strategy for sub-national Rio Convention mainstreaming |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.4.1 | Draft strategy to replicate and scale up pilot projects |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.4.2 | Conduct regional workshops to draft, tailor, and validate replication strategy |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 2.5 | Resource mobilization strategy for Rio Convention mainstreaming |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.5.1 | Assess effectiveness of financial sustainability and relevant economic instruments |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.5.2 | Identify best practice and innovative financial and economic instruments for piloting |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.5.3 | Establish expert group of finance and economic experts for peer review activities |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.5.4 | Draft, review, and approve resource mobilization strategy |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.5.5 | Formulate and approve decentralized resource allocation procedures |  |  |  |  |  |  |  |  |  |  |  |  |
| Component 3 | Strengthened capacities for management and implementation on convention guidelines |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 3.1 | Public awareness campaign |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.1.1 | Organize and convene a Kick-Off and Project Results Conference |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.1.2 | Design and carry out survey to assess understanding of Rio Convention mainstreaming |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.1.3 | Develop and validate public awareness campaign and implementation plan |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.1.4 | Increase use of Internet and social media to disseminate data and information |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.1.5 | Prepare and air a public service announcement on Rio Convention mainstreaming |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 3.2 | Training programme and knowledge materials |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.2.1 | Undertake a comprehensive assessment of technical training needs |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.2.2 | Prepare training programme and curriculum, and collate knowledge materials |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.2.3 | Undertake training workshops on Rio Convention-resilient planning frameworks |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.2.4 | Prepare articles on linkages between the global environment and local socio-economic issues |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.2.5 | Prepare a training programme to replicate and scale up technical trainings |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 3.3 | Awareness-raising workshops |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.3.1 | Develop an awareness-raising module on Rio Conventions mainstreaming |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.3.2 | Convene national and sub-national awareness workshops |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.3.3 | Convene panel discussions and public dialogues on environmental values |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.3.4 | Organize and convene private sector sensitization panel discussions |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.3.5 | Convene workshops for media professionals to improve environmental reporting |  |  |  |  |  |  |  |  |  |  |  |  |
| Project Management |  |  |  |  |  |  |  |  |  |  |  |  |  |
| A | Locally recruited personnel: Project Manager |  |  |  |  |  |  |  |  |  |  |  |  |
| B | Locally recruited personnel: Project Assistant |  |  |  |  |  |  |  |  |  |  |  |  |
| C | International Evaluation Consultant: Terminal Evaluation |  |  |  |  |  |  |  |  |  |  |  |  |
| D | Office facilities and communications |  |  |  |  |  |  |  |  |  |  |  |  |
| E | Project start-up: Organize project team and review work plan |  |  |  |  |  |  |  |  |  |  |  |  |
| F | Technical Oversight Committee Meetings (every three months) |  |  |  |  |  |  |  |  |  |  |  |  |

| WORK PLAN |  | Year 2 |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Project Components, Outputs, and Activities |  | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 |
| Component 1 | Strengthened data and information management for the global environment |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 1.1 | Comprehensive set of Rio Convention indicators |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.1.1 | Assess data and information indicators, weaknesses, and best practices |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.1.2 | Convene expert meetings to select best appropriate indicators |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 1.2 | Strengthened networking of environmental management information systems |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.2.1 | Review and design institutional arrangements for collecting and sharing data |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.2.2 | Convene expert workshops on data and information management arrangements |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.2.3 | Negotiate networking agreements on data and information management |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.2.4 | Strengthen targeted institutional architectures for sharing data and information |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 1.3 | Training programme and materials on data and information management |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.3.1 | Undertake assessment of training needs on data and information management |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.3.2 | Prepare training programme and curriculum |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.3.3 | Carry out training workshops on data and information management |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.3.4 | Develop long-term training programme on data and information management |  |  |  |  |  |  |  |  |  |  |  |  |
| Component 2 | Enhanced institutional capacities to catalyze Rio Convention implementation |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 2.1 | Assessment of policy and legislative barriers to Rio Convention mainstreaming |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.1.1 | Review policy and legislative weaknesses limiting Rio Convention mainstreaming |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.1.2 | Learn-by-doing workshops to reconcile policy and legislative weaknesses and gaps |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.1.3 | Formulate appropriate by-laws and operational guidance to mainstream Rio Conventions |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 2.2 | Consultative and decision-making processes on Rio Convention implementation |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.2.1 | Working group meetings to negotiate best consultative and decision-making processes |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.2.2 | Draft memoranda of agreements on consultative and decision-making processes |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 2.3 | Two pilot sub-national projects |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.3.1 | Finalize selection of sub-national plans to pilot and formulate project document |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.3.2 | Implement pilot projects (municipal and district) |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.3.3 | Prepare lessons learned study on sub-national Rio Convention mainstreaming |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 2.4 | Replication strategy for sub-national Rio Convention mainstreaming |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.4.1 | Draft strategy to replicate and scale up pilot projects |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.4.2 | Conduct regional workshops to draft, tailor, and validate replication strategy |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 2.5 | Resource mobilization strategy for Rio Convention mainstreaming |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.5.1 | Assess effectiveness of financial sustainability and relevant economic instruments |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.5.2 | Identify best practice and innovative financial and economic instruments for piloting |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.5.3 | Establish expert group of finance and economic experts for peer review activities |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.5.4 | Draft, review, and approve resource mobilization strategy |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.5.5 | Formulate and approve decentralized resource allocation procedures |  |  |  |  |  |  |  |  |  |  |  |  |
| Component 3 | Strengthened capacities for management and implementation on convention guidelines |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 3.1 | Public awareness campaign |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.1.1 | Organize and convene a Kick-Off and Project Results Conference |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.1.2 | Design and carry out survey to assess understanding of Rio Convention mainstreaming |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.1.3 | Develop and validate public awareness campaign and implementation plan |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.1.4 | Increase use of Internet and social media to disseminate data and information |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.1.5 | Prepare and air a public service announcement on Rio Convention mainstreaming |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 3.2 | Training programme and knowledge materials |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.2.1 | Undertake a comprehensive assessment of technical training needs |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.2.2 | Prepare training programme and curriculum, and collate knowledge materials |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.2.3 | Undertake training workshops on Rio Convention-resilient planning frameworks |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.2.4 | Prepare articles on linkages between the global environment and local socio-economic issues |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.2.5 | Prepare a training programme to replicate and scale up technical trainings |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 3.3 | Awareness-raising workshops |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.3.1 | Develop an awareness-raising module on Rio Conventions mainstreaming |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.3.2 | Convene national and sub-national awareness workshops |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.3.3 | Convene panel discussions and public dialogues on environmental values |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.3.4 | Organize and convene private sector sensitization panel discussions |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.3.5 | Convene workshops for media professionals to improve environmental reporting |  |  |  |  |  |  |  |  |  |  |  |  |
| Project Management |  |  |  |  |  |  |  |  |  |  |  |  |  |
| A | Locally recruited personnel: Project Manager |  |  |  |  |  |  |  |  |  |  |  |  |
| B | Locally recruited personnel: Project Assistant |  |  |  |  |  |  |  |  |  |  |  |  |
| C | International Evaluation Consultant: Terminal Evaluation |  |  |  |  |  |  |  |  |  |  |  |  |
| D | Office facilities and communications |  |  |  |  |  |  |  |  |  |  |  |  |
| E | Project start-up: Organize project team and review work plan |  |  |  |  |  |  |  |  |  |  |  |  |
| F | Technical Oversight Committee Meetings (every three months) |  |  |  |  |  |  |  |  |  |  |  |  |

| WORK PLAN |  | Year 3 |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Project Components, Outputs, and Activities |  | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 |
| Component 1 | Strengthened data and information management for the global environment |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 1.1 | Comprehensive set of Rio Convention indicators |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.1.1 | Assess data and information indicators, weaknesses, and best practices |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.1.2 | Convene expert meetings to select best appropriate indicators |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 1.2 | Strengthened networking of environmental management information systems |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.2.1 | Review and design institutional arrangements for collecting and sharing data |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.2.2 | Convene expert workshops on data and information management arrangements |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.2.3 | Negotiate networking agreements on data and information management |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.2.4 | Strengthen targeted institutional architectures for sharing data and information |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 1.3 | Training programme and materials on data and information management |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.3.1 | Undertake assessment of training needs on data and information management |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.3.2 | Prepare training programme and curriculum |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.3.3 | Carry out training workshops on data and information management |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.3.4 | Develop long-term training programme on data and information management |  |  |  |  |  |  |  |  |  |  |  |  |
| Component 2 | Enhanced institutional capacities to catalyze Rio Convention implementation |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 2.1 | Assessment of policy and legislative barriers to Rio Convention mainstreaming |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.1.1 | Review policy and legislative weaknesses limiting Rio Convention mainstreaming |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.1.2 | Learn-by-doing workshops to reconcile policy and legislative weaknesses and gaps |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.1.3 | Formulate appropriate by-laws and operational guidance to mainstream Rio Conventions |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 2.2 | Consultative and decision-making processes on Rio Convention implementation |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.2.1 | Working group meetings to negotiate best consultative and decision-making processes |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.2.2 | Draft memoranda of agreements on consultative and decision-making processes |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 2.3 | Two pilot sub-national projects |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.3.1 | Finalize selection of sub-national plans to pilot and formulate project document |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.3.2 | Implement pilot projects (municipal and district) |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.3.3 | Prepare lessons learned study on sub-national Rio Convention mainstreaming |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 2.4 | Replication strategy for sub-national Rio Convention mainstreaming |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.4.1 | Draft strategy to replicate and scale up pilot projects |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.4.2 | Conduct regional workshops to draft, tailor, and validate replication strategy |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 2.5 | Resource mobilization strategy for Rio Convention mainstreaming |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.5.1 | Assess effectiveness of financial sustainability and relevant economic instruments |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.5.2 | Identify best practice and innovative financial and economic instruments for piloting |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.5.3 | Establish expert group of finance and economic experts for peer review activities |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.5.4 | Draft, review, and approve resource mobilization strategy |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.5.5 | Formulate and approve decentralized resource allocation procedures |  |  |  |  |  |  |  |  |  |  |  |  |
| Component 3 | Strengthened capacities for management and implementation on convention guidelines |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 3.1 | Public awareness campaign |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.1.1 | Organize and convene a Kick-Off and Project Results Conference |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.1.2 | Design and carry out survey to assess understanding of Rio Convention mainstreaming |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.1.3 | Develop and validate public awareness campaign and implementation plan |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.1.4 | Increase use of Internet and social media to disseminate data and information |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.1.5 | Prepare and air a public service announcement on Rio Convention mainstreaming |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 3.2 | Training programme and knowledge materials |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.2.1 | Undertake a comprehensive assessment of technical training needs |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.2.2 | Prepare training programme and curriculum, and collate knowledge materials |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.2.3 | Undertake training workshops on Rio Convention-resilient planning frameworks |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.2.4 | Prepare articles on linkages between the global environment and local socio-economic issues |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.2.5 | Prepare a training programme to replicate and scale up technical trainings |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 3.3 | Awareness-raising workshops |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.3.1 | Develop an awareness-raising module on Rio Conventions mainstreaming |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.3.2 | Convene national and sub-national awareness workshops |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.3.3 | Convene panel discussions and public dialogues on environmental values |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.3.4 | Organize and convene private sector sensitization panel discussions |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.3.5 | Convene workshops for media professionals to improve environmental reporting |  |  |  |  |  |  |  |  |  |  |  |  |
| Project Management |  |  |  |  |  |  |  |  |  |  |  |  |  |
| A | Locally recruited personnel: Project Manager |  |  |  |  |  |  |  |  |  |  |  |  |
| B | Locally recruited personnel: Project Assistant |  |  |  |  |  |  |  |  |  |  |  |  |
| C | International Evaluation Consultant: Terminal Evaluation |  |  |  |  |  |  |  |  |  |  |  |  |
| D | Office facilities and communications |  |  |  |  |  |  |  |  |  |  |  |  |
| E | Project start-up: Organize project team and review work plan |  |  |  |  |  |  |  |  |  |  |  |  |
| F | Technical Oversight Committee Meetings (every three months) |  |  |  |  |  |  |  |  |  |  |  |  |

## Annex 4:	Outcome Budget (GEF Contribution and Co-financing)

The budget allocations serve as a general indication of the funding to be made available to carry out project activities and tasks, and overall project delivery.

## Annex 5:	Total GEF Budget and Work Plan

| Award ID: | 00084609 |  | Project ID: | 00092545 |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Award Title: | Capacity development for improved decision-making for the global environment |  |  |  |  |  |  |  |
| Business Unit: | PRY10 |  |  |  |  |  |  |  |
| Project Title: | Capacity development for improved decision-making for the global environment |  |  |  |  |  |  |  |
| PIMS No: | 4925 |  |  |  |  |  |  |  |
| Implementing Partner (Executing Agency): | SEAM |  |  |  |  |  |  |  |

## Annex 6:	Environmental and Social Review Criteria

QUESTION 1:

Has a combined environmental and social assessment/review that covers the proposed project already been completed by implementing partners or donor(s)? Select answer below and follow instructions: X NO Continue to Question 2 (do not fill out Table 1.1) - YES No further environmental and social review is required if the existing documentation meets UNDP’s quality assurance standards, and environmental and social management recommendations are integrated into the project. Therefore, you should undertake the following steps to complete the screening process: 1. Use Table 1.1 below to assess existing documentation. (It is recommended that this assessment be undertaken jointly by the Project Developer and other relevant Focal Points in the office or Bureau). 2. Ensure that the Project Document incorporates the recommendations made in the implementing partner’s environmental and social review. 3. Summarize the relevant information contained in the implementing partner’s environmental and social review in Annex A.2 of this Screening Template, selecting Category 1. 4. Submit Annex A to the PAC, along with other relevant documentation.

| TABLE 1.1: CHECKLIST FOR APPRAISING QUALITY ASSURANCE OF EXISTING ENVIRONMENTAL AND SOCIAL ASSESSMENT | Yes/No |
| --- | --- |
| 1. Does the assessment/review meet its terms of reference, both procedurally and substantively? |  |
| 2. Does the assessment/review provide a satisfactory assessment of the proposed project? |  |
| 3. Does the assessment/review contain the information required for decision-making? |  |
| 4. Does the assessment/review describe specific environmental and social management measures (e.g., mitigation, monitoring, advocacy, and capacity development measures)? |  |
| 5. Does the assessment/review identify capacity needs of the institutions responsible for implementing environmental and social management issues? |  |
| 6. Was the assessment/review developed through a consultative process with strong stakeholder engagement, including the view of men and women? |  |
| 7. Does the assessment/review assess the adequacy of the cost of and financing arrangements for environmental and social management issues? |  |
| Table 1.1 (continued) For any “no” answers, describe below how the issue has been or will be resolved (e.g., amendments made or supplemental review conducted). |  |

QUESTION 2:

Do all outputs and activities described in the Project Document fall within the following categories? - Procurement (in which case UNDP’s Procurement Ethics and Environmental Procurement Guide need to be complied with) - Report preparation - Training - Event/workshop/meeting/conference (refer to Green Meeting Guide) - Communication and dissemination of results Select answer below and follow instructions: X NO Continue to Question 3 - YES No further environmental and social review required. Complete Annex A.2, selecting Category 1, and submit the completed template (Annex A) to the PAC.

QUESTION 3:

Does the proposed project include activities and outputs that support upstream planning processes that potentially pose environmental and social impacts or are vulnerable to environmental and social change (refer to Table 3.1 for examples)? (Note that upstream planning processes can occur at global, regional, national, local and sectoral levels) Select the appropriate answer and follow instructions: - NO Continue to Question 4. X YES Conduct the following steps to complete the screening process: 1. Adjust the project design as needed to incorporate UNDP support to the country(ies), to ensure that environmental and social issues are appropriately considered during the upstream planning process. Refer to Section 7 of this Guidance for elaboration of environmental and social mainstreaming services, tools, guidance and approaches that may be used. 2. Summarize environmental and social mainstreaming support in Annex A.2, Section C of the Screening Template and select ”Category 2”. 3. If the proposed project ONLY includes upstream planning processes then screening is complete, and you should submit the completed Environmental and Social Screening Template (Annex A) to the PAC. If downstream implementation activities are also included in the project then continue to Question 4.

| TABLE 3. 1 EXAMPLES OF UPSTREAM PLANNING PROCESSES WITH POTENTIAL DOWNSTREAM ENVIRONMENTAL AND SOCIAL IMPACTS | Check appropriate box(es) below |
| --- | --- |
| - Support for the elaboration or revision of global-level strategies, policies, plans, and programmes. For example, capacity development and support related to international negotiations and agreements. Other examples might include a global water governance project or a global MDG project. |  |
| - Support for the elaboration or revision of regional-level strategies, policies and plans, and programmes. For example, capacity development and support related to transboundary programmes and planning (river basin management, migration, international waters, energy development and access, climate change adaptation etc.). | X |
| 3. Support for the elaboration or revision of national-level strategies, policies, plans and programmes. For example, capacity development and support related to national development policies, plans, strategies and budgets, MDG-based plans and strategies (e.g., PRS/PRSPs, NAMAs), sector plans. | X |
| 4. Support for the elaboration or revision of sub-national/local-level strategies, polices, plans and programmes. For example, capacity development and support for district and local level development plans and regulatory frameworks, urban plans, land use development plans, sector plans, provincial development plans, provision of services, investment funds, technical guidelines and methods, stakeholder engagement. | X |

QUESTION 4:

Does the proposed project include the implementation of downstream activities that potentially pose environmental and social impacts or are vulnerable to environmental and social change? To answer this question, you should first complete Table 4.1 by selecting appropriate answers. If you answer “No” or “Not Applicable” to all questions in Table 4.1 then the answer to Question 4 is “NO.” If you answer “Yes” to any questions in Table 4.1 (even one “Yes” can indicated a significant issue that needs to be addressed through further review and management) then the answer to Question 4 is “YES”: - NO No further environmental and social review and management required for downstream activities. Complete Annex A.2 by selecting “Category 1”, and submit the Environmental and Social Screening Template to the PAC. X YES Conduct the following steps to complete the screening process: 1. Consult Section 8 of this Guidance, to determine the extent of further environmental and social review and management that might be required for the project. 2. Revise the Project Document to incorporate environmental and social management measures. Where further environmental and social review and management activity cannot be undertaken prior to the PAC, a plan for undertaking such review and management activity within an acceptable period of time, post-PAC approval (e.g., as the first phase of the project) should be outlined in Annex A.2. 3. Select “Category 3” in Annex A.2, and submit the completed Environmental and Social Screening Template (Annex A) and relevant documentation to the PAC.

| TABLE 4.1: ADDITIONAL SCREENING QUESTIONS TO DETERMINE THE NEED AND POSSIBLE EXTENT OF FURTHER ENVIRONMENTAL AND SOCIAL REVIEW AND MANAGEMENT |  |
| --- | --- |
| 1. Biodiversity and Natural Resources | Answer (Yes/No/ Not Applicable) |
| 1.1 Would the proposed project result in the conversion or degradation of modified habitat, natural habitat or critical habitat? | No |
| 1.2 Are any development activities proposed within a legally protected area (e.g., natural reserve, national park) for the protection or conservation of biodiversity? | No |
| 1.3 Would the proposed project pose a risk of introducing invasive alien species? | No |
| 1.4 Does the project involve natural forest harvesting or plantation development without an independent forest certification system for sustainable forest management (e.g., PEFC, the Forest Stewardship Council certification systems, or processes established or accepted by the relevant National Environmental Authority)? | No |
| 1.5 Does the project involve the production and harvesting of fish populations or other aquatic species without an accepted system of independent certification to ensure sustainability (e.g., the Marine Stewardship Council certification system, or certifications, standards, or processes established or accepted by the relevant National Environmental Authority)? | No |
| 1.6 Does the project involve significant extraction, diversion or containment of surface or ground water? For example, construction of dams, reservoirs, river basin developments, groundwater extraction. | No |
| 1.7 Does the project pose a risk of degrading soils? | No |
| 2. Pollution | Answer (Yes/No/ Not Applicable) |
| 2.1 Would the proposed project result in the release of pollutants to the environment due to routine or non-routine circumstances with the potential for adverse local, regional, and transboundary impacts? | No |
| 2.2 Would the proposed project result in the generation of waste that cannot be recovered, reused, or disposed of in an environmentally and socially sound manner? | No |
| 2.3 Will the propose project involve the manufacture, trade, release, and/or use of chemicals and hazardous materials subject to international action bans or phase-outs? For example, DDT, PCBs and other chemicals listed in international conventions such as the Stockholm Convention on Persistent Organic Pollutants, or the Montreal Protocol. | No |
| 2.4 Is there a potential for the release, in the environment, of hazardous materials resulting from their production, transportation, handling, storage and use for project activities? | No |
| 2.5 Will the proposed project involve the application of pesticides that have a known negative effect on the environment or human health? | No |
| 3. Climate Change |  |
| 3.1 Will the proposed project result in significant greenhouse gas emissions? Annex E provides additional guidance for answering this question. | No |
| 3.2 Is the proposed project likely to directly or indirectly increase environmental and social vulnerability to climate change now or in the future (also known as maladaptive practices)? You can refer to the additional guidance in Annex C to help you answer this question. For example, a project that would involve indirectly removing mangroves from coastal zones or encouraging land use plans that would suggest building houses on floodplains could increase the surrounding population’s vulnerability to climate change, specifically flooding. | No |
| 4. Social Equity and Equality | Answer (Yes/No/ Not Applicable) |
| 4.1 Would the proposed project have environmental and social impacts that could affect indigenous people or other vulnerable groups? | No |
| 4.2 Is the project likely to significantly impact gender equality and women’s empowerment? | No |
| 4.3 Is the proposed project likely to directly or indirectly increase social inequalities now or in the future? | No |
| 4.4 Will the proposed project have variable impacts on women and men, different ethnic groups, social classes? | No |
| 4.5 Have there been challenges in engaging women and other certain key groups of stakeholders in the project design process? | No |
| 4.6 Will the project have specific human rights implications for vulnerable groups? | No |
| 5. Demographics | No |
| 5.1 Is the project likely to result in a substantial influx of people into the affected community(ies)? | No |
| 5.2 Would the proposed project result in substantial voluntary or involuntary resettlement of populations? For example, projects with environmental and social benefits (e.g., protected areas, climate change adaptation) that impact human settlements, and certain disadvantaged groups within these settlements in particular. | No |
| 5.3 Would the proposed project lead to significant population density increase which could affect the environmental and social sustainability of the project? For example, a project aiming at financing tourism infrastructure in a specific area (e.g., coastal zone, mountain) could lead to significant population density increase which could have serious environmental and social impacts (e.g., destruction of the area’s ecology, noise pollution, waste management problems, greater work burden on women). | No |
| - Culture |  |
| 6.1 Is the project likely to significantly affect the cultural traditions of affected communities, including gender-based roles? | No |
| 6.2 Will the proposed project result in physical interventions (during construction or implementation) that would affect areas that have known physical or cultural significance to indigenous groups and other communities with settled recognized cultural claims? | No |
| 6.3 Would the proposed project produce a physical “splintering” of a community? For example, through the construction of a road, powerline, or dam that divides a community. | No |
| - Health and Safety |  |
| 7.1 Would the proposed project be susceptible to or lead to increased vulnerability to earthquakes, subsidence, landslides, erosion, flooding or extreme climatic conditions? For example, development projects located within a floodplain or landslide prone area. | No |
| 7.2 Will the project result in increased health risks as a result of a change in living and working conditions? In particular, will it have the potential to lead to an increase in HIV/AIDS infection? | No |
| 7.3 Will the proposed project require additional health services including testing? | No |
| - Socio-Economics |  |
| 8.1 Is the proposed project likely to have impacts that could affect women’s and men’s ability to use, develop and protect natural resources and other natural capital assets? For example, activities that could lead to natural resources degradation or depletion in communities who depend on these resources for their development, livelihoods, and well-being? | Yes |
| 8.2 Is the proposed project likely to significantly affect land tenure arrangements and/or traditional cultural ownership patterns? | No |
| 8.3 Is the proposed project likely to negatively affect the income levels or employment opportunities of vulnerable groups? | No |
| 9. Cumulative and/or Secondary Impacts | Answer (Yes/No/ Not Applicable) |
| 9.1 Is the proposed project location subject to currently approved land use plans (e.g., roads, settlements) which could affect the environmental and social sustainability of the project? For example, future plans for urban growth, industrial development, transportation infrastructure, etc. | N/A |
| 9.2 Would the proposed project result in secondary or consequential development which could lead to environmental and social effects, or would it have potential to generate cumulative impacts with other known existing or planned activities in the area? For example, a new road through forested land will generate direct environmental and social impacts through the cutting of forest and earthworks associated with construction and potential relocation of inhabitants. These are direct impacts. In addition, however, the new road would likely also bring new commercial and domestic development (houses, shops, businesses). In turn, these will generate indirect impacts. (Sometimes these are termed “secondary” or “consequential” impacts). Or if there are similar developments planned in the same forested area then cumulative impacts need to be considered. | Yes |

ANNEX A.2:  ENVIRONMENTAL AND SOCIAL SCREENING SUMMARY

(To be filled in after Annex A.1 has been completed)

Name of Proposed Project:	Capacity development for improved decision-making for the global environment

A. Environmental and Social Screening Outcome

Select from the following:

- Category 1. No further action is needed

X

Category 2.  Further review and management is needed.  There are possible environmental and social benefits, impacts, and/or risks associated with the project (or specific project component), but these are predominantly indirect or very long-term and so extremely difficult or impossible to directly identify and assess.

- Category 3. Further review and management is needed, and it is possible to identify these with a reasonable degree of certainty. If Category 3, select one or more of the following sub-categories:

- Category 3a: Impacts and risks are limited in scale and can be identified with a reasonable degree of certainty and can often be handled through application of standard best practice, but require some minimal or targeted further review and assessment to identify and evaluate whether there is a need for a full environmental and social assessment (in which case the project would move to Category 3b).

- Category 3b: Impacts and risks may well be significant, and so full environmental and social assessment is required. In these cases, a scoping exercise will need to be conducted to identify the level and approach of assessment that is most appropriate.

B. Environmental and Social Issues (for projects requiring further environmental and social review and management)

In this section, you should list the key potential environmental and social issues raised by this project. This might include both environmental and social opportunities that could be seized on to strengthen the project, as well as risks that need to be managed.  You should use the answers you provided in Table 4.1 as the basis for this summary, as well as any further review and management that is conducted.

There are no real negative social impacts of this project, which is largely about facilitating a broad engagement of stakeholders from key government departments and agencies, as well as other non-state actors to agree on environmental indicators, the sharing of data and information, and recommendations to address policy and legislative barriers to Rio Convention mainstreaming.  The project will provide technical training on good/best practices to collect and manage data, and undertake learning-by-doing exercises to encourage critical thinking on the use of data and information in the assessment of development policies and plans from a stronger global environmental perspective.  Additionally, this project will pilot two sub-national projects to test the value and viability of using global environmental criteria and indicators to inform planning and decision-making on national priorities.  Women will be encouraged to participate in the training workshops and learn-by-doing exercises.

C. Next Steps (for projects requiring further environmental and social review and management):

In this section, you should summarize actions that will be taken to deal with the above-listed issues. If your project has Category 2 or 3 components, then appropriate next steps will likely involve further environmental and social review and management, and the outcomes of this work should also be summarized here. Relevant guidance should be obtained from Section 7 for Category 2, and Section 8 for Category 3.

Further environmental and social review and management is recommended to ensure that the project is being adaptively and collaboratively managed, as this is critical to project success.  Although there is an official network of environmental organizations (SISNAM) and a formal consultative mechanism to facilitative decision-making on environmental issues (CONAM) in Paraguay, communication and coordination remains relatively low between stakeholders.  This project therefore targets the underlying barriers to the management of environmental data and information by getting stakeholders and key decision-makers to proactively collaborate to reduce the risk of pursuing actions that work against the goals of global environmental conservation and sustainable development.  Memoranda of agreements to share information will help strengthen opportunities to formulate more resilient and environmentally friendly sustainable development.

One risk to this project is that stakeholders do not have strong environmental values and become disinterested.  The project will manage this risk by convening numerous training and awareness-raising meetings and workshops, among other means to actively engage stakeholders.  Incentives for their active participation will be sought.

The project’s design also sets out to shorten the divide between protecting the environment and socio-economic priorities.  This is to be achieved through mainstreaming.  That is, a country that pursues priority socio-economic development could also be pursuing global environmental priorities that science has shown to be inherently fundamental to sustaining development.  It is through the training and learn-by-doing exercises that stakeholders will learn how to reconcile priority socio-economic priorities with global environmental obligations

The project will take an adaptive collaborative management approach to ensure that project activities remain appropriate to meeting long-term objectives.  This approach is designed to strengthen the legitimacy of project activities throughout its implementation with stakeholders.

The Local Project Appraisal Committee (LPAC) for this project will be convened after CEO endorsement.

D. Sign Off

Project Manager								Date___________

Date___________

Date: 18 Dec. 2014

## Annex 7:	Terms of References

The following Terms of Reference outlines the general responsibilities to be carried out by ten (10) consultants contracted under the project.

Background

The United Nations Development Programme (UNDP), acting as an implementing agency of the Global Environment Facility (GEF), is providing assistance to the Secretariat of the Environment (SEAM) under the Government of Paraguay in the preparation of the GEF Medium Size Project (MSP) “Capacity development for improved decision-making for the global environment.”

A central barrier to meeting Rio Convention obligations in Paraguay is the relatively low institutional and technical capacities for managing environmental data and information that is critical for understanding the current status and dynamic changes in the state of environment.  Developing and applying high quality data and information is critical to making better decisions for environmental governance that will not only meet national socio-economic priorities, but also ensure their long-term sustainability by incorporating criteria and indicators that reflect Rio Convention obligations.

- Paraguay´s environmental management issues are mainly due to insufficient technical capacities, inadequate collaboration and coordination, and insufficient involvement of relevant stakeholders and institutions for improved and sustained environmental governance that yields global environmental benefits.  Notwithstanding the work being undertaken by a small number of non-State social actors, there remains an insufficiency of national expertise available to catalyze effective decision-making for the global environment.  While some applied research is underway, much remains to be undertaken to integrate higher quality data and information into management information systems.  The work that a number of universities and research institutes have been doing is isolated and needs to be unified with the appropriate application of standards and the efficient coordination of the institutions involved.

Project Goal and Objectives

The goal of this project is for Paraguay to make better planning decisions that will help protect the global environment within the framework of sustainable development.  Better decisions to meet and sustain global environmental objectives will be made as a result of better access to existing data and information as well as new knowledge.  To this end, the project’s objective is to strengthen technical capacities to develop and integrate global environmental criteria and indicators into more holistic and resilient planning frameworks.  New and improved data collection methodologies and learning-by-doing workshops will be undertaken to formulate holistic land-use and environmental management plans.  Collaboration and coordination will be increased through a network of institutions and social actors, each with their own comparative advantages.  The project will test and demonstrate the strengthened capacities through two sub-national planning frameworks, for example, municipal land-use plans.

Project activities will be carried out through learning-by-doing workshops to encourage critical thinking and to reaffirm the strategic and transformative value of the project strategy.  The project will also help institutionalize the improved decision-making for the global environment by facilitating the increased awareness and understanding on best practices to operationalize existing legislative instruments, including the formulation of targeted by-laws to catalyze the implementation of municipal land-use plans that integrate global environmental criteria and indicators.

Strategically, the project includes activities that will call upon all stakeholder organizations to meet and negotiate sharing protocols, based on the data and information that each needs.  Memoranda of Agreement, as appropriate, would be signed to facilitate this sharing, which would then be institutionalized through appropriate legal pathways.

Project Outcomes and Components

At the end of the project, activities will have resulted in a set of improved capacities to meet and sustain Rio Convention objectives.  This general outcome will be measured by a variety of indicators, characterized as outputs, process, and performance indicators.  Output indicators include the municipal land-use management plans that reflect global environmental priorities.  Process indicators include the very important collaboration among government authorities and non-state stakeholders to share data and information through an agreed sharing protocol and data flow system, legitimized by the necessary approvals, e.g., memoranda of agreements.  This project is organized into three linked components.

Component 1:	Strengthening data and information management for the global environment

Component 1 focuses on strengthening existing environmental data and information management systems in order for more informed decision-making regarding the global environment.  New and improved data management methodologies, including monitoring and reporting procedures and best practices, will be identified to create and access global environmental data and information.  This data will be integrated into targeted economic instruments to raise the value of global environmental benefits.  Relevant existing management information systems will be networked for more cost-effective sharing of data and information, as well as to catalyze collaboration to create new knowledge.  An output under this activity will be the development of data sharing protocols for reducing unnecessary redundancy, raising standards, and streamlining access to data, information, and knowledge.  A tracking mechanism for monitoring, reporting, and disseminating environmental information for policy formulation and development planning will be developed.

Component 2:	Enhancing institutional arrangements to catalyze Rio Convention implementation

Component 2 will strengthen targeted institutional arrangements and associated policy, legislative, and/or regulatory instruments, as necessary, to operationalize and legitimize sub-national level planning frameworks that reflect a more holistic construct of inter-related global and local environmental and sector development priorities and obligations.  Two key outputs under this component is the strengthening of existing technical committees (inclusive of stakeholders from academia, civil society, local municipalities, and the private sector) to transform scientific and technical knowledge into policy recommendations that will be acted upon by appropriate participatory decision-making processes on the global environment.  These will validate the development and implementation of two pilot municipal land-use plans and the testing of economic instruments that have been improved by the global environmental data created under Component 1.

Component 3: Strengthening technical capacities to manage and implement Rio Convention obligations

Component 3 focuses on strengthening the technical capacities of key stakeholders, technical staff, and decision-makers that directly and indirectly affect obligations under the Rio Conventions.  Best practices and innovations from this component’s activities, along with those from Component 1 and Component 2 will form the basis of trainings and learning-by-doing piloting activities related to environmental evaluation with particular focus on meeting global environment priorities.  This component will catalyze the use of new tools and methodologies to diagnose, understand, and transform information and knowledge into local actions to meet and sustain global environmental objectives.  Awareness-raising exercises for an extended set of social actors and other stakeholders will build up the long-term absorptive capacity and sustainability of more complex decision-making.  Improved technical capacities will also help replicate the best practices piloted and tested in component 2.  Proactive participation in the learning-by-doing exercises will train participants to think more critically when undertaking their role and responsibilities.

Responsibilities

- National Project Director (NPD)

The Government of Paraguay will appoint a National Project Director (NPD) for this UNDP-supported project.  He/she will support the project and act as a focal point on behalf of the Government.  This responsibility entails ensuring effective communication between partners and monitoring of progress towards expected results.  The National Project Director is the party that represents the Government’s ownership and authority over the project, responsibility for achieving project objectives and the accountability to the Government and UNDP for the use of project resources.

In consultation with UNDP, the Secretariat of the Environment (SEAM) as the concerned ‘ministry’ will designate the National Project Director from among its staff at not lower than the Deputy Minister or Head of Department level.  He/she will be supported by a National Project Manager (NPM) who will be contracted to implement the CCCD project.

Duties and Responsibilities of the NPD

The NPD will have the following duties and responsibilities:

- Assume overall responsibility for the successful execution and implementation of the project, accountability to the Government and UNDP  for the proper and effective use of project resources

- Serve as a focal point for the coordination of projects with other Government agencies, UNDP and other development partners

- Ensure that all Government inputs committed to the project are made available

- Select and arrange, in close collaboration with UNDP, the appointment of the National Project Manager

- Supervise the work of the NPM and ensure that he/she is empowered to effectively manage the project and other project staff to perform their duties effectively

- Supervise the preparation of project work plans, progress reports, project modifications, and budget clearance and approval in consultation with UNDP and other stakeholders, and ensure the timely request of inputs according to the project work plans

- Represent the Government institution at the tripartite review project meetings, Project Steering Committee, and other stakeholder meetings

Remuneration and entitlements:

The National Project Director may not receive monetary compensation from project funds for the discharge of his/her functions.

- Project Manager

A Project Manager will be recruited to oversee the project implementation under the guidance of the NPD, the Project Steering Committee, and with the support of UNDP Paraguay.  He/she will be recruited for project management activities and will also hold a separate contract as the Public Administration Expert.  The Project Manager will be held accountable for the delivery of project services and outputs.  In addition to overseeing the implementation of the project’s capacity development activities, the project management will carry out the monitoring and evaluation procedures per UNDP agreed policies and procedures.  These include:

- Oversee the day-to-day monitoring of project implementation

- In consultation with stakeholders, recommend modifications to project management to maintain project’s cost-effectiveness, timeliness, and quality project deliverables (adaptive collaborative management) to be approved by the Project Steering Committee

- Prepare all required progress and management reports, e.g., APR/PIR and project initiation report

- Support all meetings of the Project Steering Committee

- Maintain effective communication with project partners and stakeholders to dissemination project results, as well as to facilitate input from stakeholder representatives as project partners

- Support the independent terminal evaluation

- Ensure full compliance with the UNDP and GEF branding policy

- Project Assistant

The Project Assistant will support the National Project Manager in the carrying out of his/her duties, which will include:

      - Organizational and logistical issues related to project execution per UNDP guidelines and procedures

      - Record keeping of project documents, including financial in accordance with audit requirements

      - Ensure all logistical arrangements are carried out smoothly

      - Assist the NPM in preparation and update of project work plans in collaboration with the UNDP Country Office

      - Facilitate timely preparation and submission of financial reports and settlement of advances, including progress reports and other substantial reports

      - Report to the Project Manager and UNDP on a regular basis

      - Identification and resolution of logistical and organizational problems, under the guidance of the Project Manager

The Project Assistant will have at least five (5) years’ experience in supporting the implementation of UNDP implemented projects, with preference in environment and natural resource management projects.

- Public Administration Expert (National)

The individual recruited as the Public Administration Expert will also hold an additional separate contract as the Project Manager.  He/she will work with the national consultants as well as with the information technology specialist to assess and institutionalize networked information systems and collaborative arrangements with partner government agencies and other stakeholder organizations.  He/she will work with the information technology specialist to structure appropriate data sharing protocols as well as the harmonization of methodologies and standards.  This expert will also work with the legal expert to assess and recommend institutional and associated regulatory reforms requiring approval, as well as work of the Rio Convention experts through the expert working groups, and will serve as a resource person and facilitator for the training and learning-by-doing working groups.  The Public Administration Expert will have a post-graduate degree in public administration or related field, and have a minimum of ten (10) years’ experience in progressively responsible and substantive areas in environmental and natural resource governance programming and planning in Paraguay

- National Consultant on the Convention on Biological Diversity

This national consultant will be responsible for undertaking those project activities that require expertise on interpreting and translating CBD obligations into national programmable activities.  The consultant will prepare the appropriate technical background studies, as well as also serve as a facilitator in the trainings on the using data and information relevant to meeting biodiversity conservation objectives, with particular emphasis on endangered endemic species and their ecosystems.

The CBD consultant will have at least 10 years of work experience biodiversity conservation programming and project implementation, of which at least the last two (2) years include active involvement in CBD negotiations.  He/she will have a PhD in natural resource management, with a specialization directly related to biodiversity conservation in Paraguay and/or the surrounding region.  Under the supervision of the NPM, the consultant will coordinate his/her work with that of other national experts and specialists.  This includes coordinating activities with those under implementation by the development partners.

- National Consultant on the Convention on Desertification and Drought

This national consultant will be responsible for undertaking those project activities that require expertise on interpreting and translating CCD obligations into national programmable activities.  The consultant will prepare the appropriate technical background studies, as well as also serve as a facilitator in the trainings on the using data and information relevant meeting land degradation objectives, with particular emphasis on sustainable land management and land degradation.

The CCD consultant will have at least 10 years of work experience, of which at least the last two (2) years include active involvement in CCD negotiations, programming, and project implementation.  He/she will have a PhD in natural resource management, with a specialization directly related to land management issues in Paraguay and/or the surrounding region.  Under the supervision of the NPM, the consultant will coordinate his/her work with that of other national experts and specialists.  This includes coordinating activities with those under implementation by the development partners.

- National Consultant on the Framework Convention on Climate Change

This national consultant will be responsible for undertaking those project activities that require expertise on interpreting and translating FCCC obligations into national programmable activities.  The consultant will prepare the appropriate technical background studies, as well as also serve as a facilitator in the trainings on the using data and information relevant to meeting climate change mitigation and mitigation objectives, with particular emphasis on endangered endemic species and their ecosystems.

The FCCC national consultant will have at least 10 years of work experience, of which at least the last two (2) years include active involvement in FCCC negotiations, programming, and project implementation.  He/she will have a PhD in a field directly relevant to climate change science, with a specialization directly related to mitigation and adaptation strategies relevant to Paraguay and/or the surrounding region.  Under the supervision of the NPM, the consultant will coordinate his/her work with that of other national experts and specialists.  This includes coordinating activities with those under implementation by the development partners.

- Information Technology and Knowledge Management Specialist (National)

An information technology specialist will be recruited to oversee the technical networking of existing information systems, including the procurement of the appropriate hardware and software.  Under the supervision of the NPM, he/she will work with the national Rio Convention consultants, as well as with the relevant information technology managers in the different departments to network the information systems.  The specialist will provide training on the use of data management software and the maintenance of networked information systems.  With at least five (5) years’ of work experience, the specialist will have at least a Master’s degree in information technology, including network analysis, system administration, security and information assurance, IT audit, database administration, and web administration.

- Policy/Legal Expert

The policy/legal expert will contribute to the substantive work under the project by assessing the policy and legal implications of Rio Convention instituting the networking of information systems, harmonization of standards and methodologies, and the piloting of the two municipal land-use plans and the economic instruments.  He/she will pay particular attention to reducing, if not removing, legal barriers to collaboration among key agencies and other stakeholder organizations.  The expert will work with the public administration expert, among others as appropriate, to draft and negotiate memoranda of agreement to share data and information, as well as draft appropriate legislative instruments that are to be approved.  He/she will have a post-graduate degree in law, with a specialization in environmental law and policy.  S/he will have to have a minimum of ten (10) years’ experience in progressively responsible and substantive areas in environmental and natural resource governance programming and planning in Paraguay.

- Environmental Sociologist

A critical aspect of this project is to integrate environmental data with socio-economic issues in order to interpret data and information to understand the social and other human dimensions of environmental degradation and impacts.  These dimensions are also critical to determining how to improve environmental values and attitudes that influence environmental friendly behaviour.  To these ends, the Environmental Sociologist will be recruited to support a number of activities that call for, among others, assessing stakeholders’ understanding and awareness of environmental issues and survey analyses.  He/she will work with the Public Administration Expert to structure the learning-by-doing trainings, the training curricula, as well as to develop the public awareness campaign.  The Environmental Sociologist will have a post-graduate degree in environmental sociology, preferably a PhD, with demonstrated experience in constructing and implementing surveys, as well as their statistical analysis on trends in environmental values and attitudes.

- Environmental Economist

An environmental economist will be recruited to strengthen the economic dimensions of environmental data and information, in particular to understand opportunities for strengthening values of ecosystem services.  Working with the other experts, this specialist will support of number of activities that call for identifying weaknesses and gaps in environmental data and information, in particular analytical methodologies for assessing the economic impacts and implications of environmental degradation.  To this end, the national consultant will provide input into the learning-by-doing trainings as well as awareness-raising dialogues.  He/she will work with the Public Administration Expert to develop the two sub-national pilot projects and the replication strategy.  The Environmental Economics will have a post-graduate degree in environmental economics, preferably a PhD, with demonstrated experience in analyzing and developing national economic policies and development programmes.  He/she will have experience in facilitating expert and stakeholder working groups in the collaborative drafting of sector policies.

- International Technical Specialist

The International Technical Specialist will be retained on a part-time basis to provide necessary technical advisory services on the implementation of key project activities, in particular the review of recommendations to integrate and institutionalize Rio Convention obligations within the EMIS, among other substantive activities, as appropriate.  These services will be provided over the course of the three-year implementation period to provide technical backstopping to help ensure the timely and high quality project delivery.

- International Evaluation Consultant

The international evaluation consultant will be an independent expert that is contracted to assess the extent to which the project has met project objectives as stated in the project document and produced cost-effective deliverables.  The consultant will also rate capacities developed under the project using the Capacity Development Scorecard.  The Terms of Reference for the International Evaluation Consultant will follow the UNDP/GEF policies and procedures, and together with the final agenda will be agreed upon by the UNDP/GEF, UNDP Country Office and the Project Team.  The final report will be cleared and accepted by UNDP.

## Annex 8:	Paraguay UN REDD+ Programme and Forest Carbon Partnership Facility

Under implementation since 2011, this is a US$ 4.7 million project under implementation by SEAM, the National Forest Service (INFONA), and the Federation for the Self-Determination of Indigenous Peoples (FAPI), with the support from FAO, UNDP and UNEP.  The aim of this programme is to strengthen institutional and technical capacity of government and civil society organizations to manage REDD+ activities, with particular attention to implementation capacities at the local level.  Activities under this programme will be important complements to the CCCD project, in particular the programme’s preparation of a National Forestry Inventory, a National REDD+ Plan, and an information network mechanism.  There are three outcomes and various outputs for the programme:

Outcome 1:	Institutional and technical capacities of government and civil society organizations to manage REDD+ activities in Paraguay are improved

To this end, the programme will facilitate the development of four main outputs, namely: a) National Action Plan for Reduction of Emissions due to Deforestation and Degradation of Forests (REDD-Plan); b) a National Environmental (SEAM) and Forest (INFONA) Information System to measure and evaluate reduction of emissions from deforestation and degradation of forests; c) a national system of carbon accounting and data management; and d) an equitable and transparent system of payments and benefit-sharing.  These outputs will contribute to the development of national capacities to design and implement the necessary measures to reconcile and integrate key environmental, forest, social, rural development and economic policies.  These capacities will include generating new and improved data to better monitor measurable and sustainable reductions in deforestation and forest degradation rates.  Capacities developed under this component also include the development of key incentives associated with the REDD+ mechanism, receiving payments and distributing such payments at local level.

Outcome 2:	Capacities to implement REDD+ at local level are strengthened through a REDD+ Demonstration project and REDD+ project proposals for other forest areas.

Activities under this outcome will develop local capacities to design and implement REDD+ activities and demonstrate best practice approaches to reduce deforestation and forest degradation that conform to local development priorities.  Activities also include strengthening management capacities of local authorities and the empowerment of local stakeholders to undertake these best practice approaches.  A local REDD+ committee established under the programme will work with representatives of the district governments, the municipalities, the REDD+ Technical Team, government agencies, NGOs, as well as representatives of regional/local private sector organizations.

Outcome 3:	Knowledge and related technical capacities on REDD+ for forest dependent communities, in particular indigenous peoples and other relevant stakeholders in the country, are improved

The third set of activities and outputs of the REDD+ programme center on the strengthening of awareness and understanding among social actors to broaden heightened values and attitudes towards REDD+ principles and strategies.  In so doing, the expected result is increased support and action that is both consistent with and that which catalyzes sustainable best practice approaches for minimizing deforestation and forest degradation.  Outputs include the preparation of a national awareness campaign on REDD+, training and consultation on REDD+ with indigenous peoples, and training and consultation on REDD+ with small-, medium-, and large-scale producers and other stakeholders.  To this end, activities under this component will work with SEAM and other partner stakeholder organizations and agencies.  The UN-REDD+ programme is collaborating with the Forest Carbon Partnership Facility (FCPF) on a wide range of initiatives including: harmonized guidelines on stakeholder engagement, a common ‘readiness template’, technical review process, joint country missions, back-to-back board meetings, cooperation on safeguards and joint secretariat support to the REDD+ Partnership.

## Annex 9:	Standard letter of agreement between UNDP and Government of Paraguay

Letter of agreement between UNDP and the Secretariat of the Environment of Paraguay for the provision of services to support the implementation of the "Capacity development for improved decision-making for the global environment” award 00084609 in the context of the national implementation modality

1.	Within the framework of the " Capacity development for improved decision-making for the global environment”, the UNDP and the Ministry of Environment of Paraguay (hereinafter the counterparty) express their agreement for UNDP to provide support services to the aforementioned project implementation, in accordance with the counterpart and the project document signed by the parties.

2.	The UNDP country office may provide support services for assistance with reporting requirements and direct payment.  In providing such support services, the UNDP country office shall ensure that the capacity of the Government-designated institution is strengthened to enable it to carry out such activities directly.  The costs incurred by the UNDP country office in providing such support services shall be recovered from the administrative budget of the office.

3.	The UNDP country office may provide, at the request of the designated institution, the following support services for the activities of the programme/project:

(a)	Identification and/or recruitment of project and programme personnel;

(b)	Identification and facilitation of training activities;

(c)           Procurement of goods and services;

4.	The procurement of goods and services and the recruitment of project and programme personnel by the UNDP country office shall be in accordance with the UNDP regulations, rules, policies and procedures.  Support services described in paragraph 3 above shall be detailed in an annex to the programme support document or project document, in the form provided in the Attachment hereto.  If the requirements for support services by the country office change during the life of a programme or project, the annex to the programme support document or project document is revised with the mutual agreement of the UNDP resident representative and the designated institution.

5.	The relevant provisions of the Special Standard Agreement between the Government of Paraguay and the United Nations Development Programme signed on October 10th, 1977 (the “SSA”), including the provisions on liability and privileges and immunities, shall apply to the provision of such support services. The Government shall retain overall responsibility for the nationally managed programme or project through its designated institution.  The responsibility of the UNDP country office for the provision of the support services described herein shall be limited to the provision of such support services detailed in the annex to the programme support document or project document.

6.	Any claim or dispute arising under or in connection with the provision of support services by the UNDP country office in accordance with this letter shall be handled pursuant to the relevant provisions of the SSA and the project document.

7.	The manner and method of cost-recovery by the UNDP country office in providing the support services described in paragraph 3 above shall be specified in the annex to the programme support document or project document.

8.	The UNDP country office shall submit progress reports on the support services provided and shall report on the costs reimbursed in providing such services, as may be required.

9.	Any modification of the present arrangements shall be effected by mutual written agreement of the parties hereto.

10.	If you are in agreement with the provisions set forth above, please sign and return to this office three signed copies of this letter.  Upon your signature, this letter shall constitute an agreement between your Government and UNDP on the terms and conditions for the provision of support services by the UNDP country office for nationally managed programmes and projects.

Yours sincerely,

________________________

Signed on behalf of UNDP Paraguay

Cecilia Ugaz

Resident Representative

_____________________

María Cristina Morales Palarea

For the Government Paraguay

Minister

Secretary of the Environment

Attachment: Description of UNDP Country Office Support Services

1.	Reference is made to consultations between the Ministry of Ecology and Natural Resources, the institution designated by the Government of Paraguay and officials of UNDP with respect to the provision of support services by the UNDP country office for the nationally managed programme or project “Capacity development for improved decision-making for the global environment” AWARD 00084609.

2.	In accordance with the provisions of the letter of agreement signed and the programme support document (project document), the UNDP country office shall provide support services for the Programme as described below.

3.	Support services to be provided:

| Support services (insert description) | Schedule for the provision of the support services | Cost to UNDP of providing such support services (where appropriate) | Amount and method of reimbursement of UNDP (where appropriate) |
| --- | --- | --- | --- |
| - Payments, disbursements and other financial transactions | During project implementation | Universal Price List | Support Services |
| - Recruitment of staff, project personnel, and consultants | During project implementation | Universal Price List | Support Services |
| - Procurement of services and equipment, and disposal/sale of equipment | During project implementation | Universal Price List | Support Services |
| - Organization of training activities, conferences, and workshops, including fellowships | During project implementation | Universal Price List | Support Services |
| - Travel authorizations, visa requests, ticketing, and travel arrangements | During project implementation | Universal Price List | Support Services |
| - Shipment, custom clearance, vehicle registration, and accreditation | During project implementation | Universal Price List | Support Services |
|  |  | Total: up to USD 4,000 from GEF grant |  |

4.	Description of functions and responsibilities of the parties involved:

The project will be conducted through the National Implementation Modality (NIM). The Secretariat of Environment (SEAM) will act as a partner in the National Implementation with the support of UNDP as GEF Implementing Agency. The SEAM will be responsible for directing and managing the project and monitor the compliance of project work plans as a basis for its implementation.

UNDP will provide technical and operational support necessary for the implementation of the activities and results of this project and shall ensure that all consultant contracts, purchase orders and service contracts for the project are in accordance with UNDP rules and procedures.

Project authorities will undertake contracts and procurement for all purchases of less than USS 10,000. These minor operations will comply with the rules and procedures contained in the for National Implementation projects Manual. The Manual can be viewed on the UNDP website: www.py.undp.org. According to the above, the ownership of equipment, spare parts and other goods financed with project funds will be of the UNDP. The transfer of property rights will be determined in accordance with the policies and procedures of UNDP. All goods will be considered property of UNDP until its transfer to the SEAM.

UNDP will assist in the administration of the funds provided by GEF. UNDP will be able to support the management of any additional funds for co-financing of this project. These measures shall be included in the corresponding project document or Memorandum of Understanding. The contributions will be subject to audit established in the UNDP financial regulations rules.

*****

## Annex 10: 	References

CBD. (2014). Paraguay Overview. Retrieved from Convention on Biological Diversity: http://www.cbd.int/countries/profile/default.shtml?country=py#nbsap

CIA. (2014). Paraguay. Retrieved from CIA World Factbook: https://www.cia.gov/library/publications/the-world-factbook/geos/pa.html

GIZ. (2014). Sustainable natural resource management. Retrieved from GIZ: http://www.giz.de/en/worldwide/23423.html

International Energy Agency. (2014). Paraguay: Electricity and Heat for 2010. Retrieved from International Energy Agency: http://www.iea.org/statistics/statisticssearch/report/?country=PARAGUAY&product=electricityandheat&year=2010

SEAM. (2013). National Capacity Self-Assessment.

UN. (2014). UNDAF 2015-2019. UN.

United Nations. (2014). The Road to Dignity by 2030: Ending Poverty, Transforming All Lives and Protecting the Planet Synthesis Report of the Secretary-General On the Post-2015 Agenda.

United Nations, Open Working Group on Sustainable Development Goals. (2014). Proposal of the Open Working Group on Sustainable. New York.

World Bank. (2014). Paraguay country data. Retrieved from World Bank: http://data.worldbank.org/country/paraguay

## Annex 11:	Unofficial translation of Government Co-financing letter from SEAM

Ms. Adriana Dinu
Executive Director UNDP / GEF
304 East 45th Street, NY 10017, USA

Ms. Cecilia Ugaz
UNDP Resident Representative Paraguay

24 December 2014

Reference:  Capacity development for improved decision-making for the global environment

I am pleased to express to you the support of the Ministry of Environment for the above-mentioned project, in compliance with the institutional mandate of policy formulation, coordination, monitoring, and enforcement of environmental actions, plans, programmes and projects under the National Development Plan as they relate to the preservation, conservation, restructuring and management of natural resources.

Co-financing for this project will be US $ 160,000 (one hundred and sixty thousand US dollars) in cash and US $ 640,000 (six hundred and forty thousand US dollars) in kind.

Without further ado, I avail myself of this opportunity to greet them with the assurance of my highest esteem and consideration.

[signed]

Ms. Cristina Morales

Minister

# PART III:	GEF Letters of Endorsement and Co-Financing

Annex A    GEF Endorsement Letter	56

Annex B    Letters of Co-Financing	62

As of December 2014

Further details of the project’s indicators are provided in the project document narrative and the logical framework.  For further information please see http://www.thegef.org/gef/Policies_and_Guidelines

This project was approved under the GEF-5 Cross-Cutting Capacity Development Strategy.

Primary produce accounts for 80% of the country’s exports (GIZ, 2014).

Ratings will be based on a set of 12 criteria on a scale of 1 to 5.

These information systems are tied to the planning bodies within their respective institutions, and activities 1.2.3, 1.2.4, and 2.2.1 focus on strengthening the management of data, information, and knowledge for planning purposes.

Also referred to as MEA working groups.

This activity will include operational tools for transmitting data and information among stakeholder organizations in their original format.  This activity will not finance the preparation of national reports to the Rio Conventions.

Ratings will be based on a set of 12 criteria on a scale of 1 to 5

Ibid.

Ratings will be based on a set of 12 criteria on a scale of 1 to 5.

The choice of television or radio will be decided at project inception.

For example, in the past SEAM did not make available sufficient resources to maintain operational vehicles purchased through project funds, the result of which these vehicles have deteriorated to the point of having nominal value.

See http://www.thegef.org/gef/sites/thegef.org/files/documents/C.40.08_Branding_the_GEF%20final_0.pdf.

See http://intra.undp.org/coa/branding.shtml and http://intra.undp.org/branding/useOfLogo.html

Meeting minutes includes records of key meetings such as local, regional and national consultations regarding inputs on the design and implementation of the relevant output and associated activities.  Meetings may be individual or group meetings, with government officials or non-state stakeholders.

Significant corresponds to CO2 emissions greater than 100,000 tons per year (from both direct and indirect sources). Annex E provides additional guidance on calculating potential amounts of CO2 emissions.

Women are often more vulnerable than men to environmental degradation and resource scarcity. They typically have weaker and insecure rights to the resources they manage (especially land), and spend longer hours on collection of water, firewood, etc. (OECD, 2006).  Women are also more often excluded from other social, economic, and political development processes.

UNDP direct project support services will be defined yearly, and for those executed during the period, direct project costs will be charged at the end of each year based on the UNDP Universal Pricelist (UPL) or the actual corresponding service cost.