United Nations Development Programme

Countries:  Cook Islands, Federated States of Micronesia, Fiji, Kiribati, Marshall Islands, Nauru, Niue, Palau, Papua New Guinea, Samoa, Solomon Islands, Tonga, Tuvalu, Vanuatu.

PROJECT DOCUMENT

Project Title: Enhancing Capacity to Develop Global and Regional Environmental Projects in the Pacific.

UNDAF Outcome(s): UNDP Strategic Plan Environment and Sustainable Development Primary Outcome: UNDP Strategic Plan Secondary Outcome:

Expected CP Outcome(s):

Executing Entity/Implementing Partner: Secretariat of the Pacific Regional Environment Programme.

Implementing Entity/Responsible Partners: United Nations Development Programme (UNDP).

Brief Description: The goal of this project is to build national capacities of 14 Pacific Island Countries to access GEF resources through strengthening of the Secretariat of the Pacific Regional Environment Programme (SPREP).  SPREP was established to enhance the technical and policy capacity of Pacific countries to meet their national and international obligations to MEAs. This includes the Rio Conventions, Stockholm, Basel, and Rotterdam Conventions, under which the GEF provides financial assistance to these Pacific Island Countries.  This project will focus on strengthening SPREP's capacity to obtain GEF accreditation and assist Pacific Island Countries to meet their international obligations to the Rio Convention.  The first project objective is to build SPREP's institutional capacity to satisfy minimal accreditation standards of the GEF, in-order to become accredited as a GEF Project Agency. To achieve this, the project will aim to strengthen internal control frameworks of SPREP to perform fiduciary functions expected of a GEF Project Agency. In addition, SPREP's policies will be enhanced to integrate environmental and social safeguards including a gender mainstreaming strategy for the organization as a whole. Management systems and procedures will be revised and improved at the organizational level to deliver GEF projects in accordance with GEF policies. It is expected that this project will be implemented through a learning-by-doing approach. The active participation of national GEF Operational Focal Points and SPREP Focal Points from all 14 Pacific Island Countries in the full project life cycle will facilitate the strategic focus of project activities in keeping with the project objectives.

Total resources required         US$ 2,914,502.60

Total allocated resources:       US$ 2,914,502.60

- Other:

  - GEF		        US$ 1,000,000.00

  - Australian Government   US$ 180,000.00

  - Chinese Government      US$ 150,000.00

  - SPREP (In-Kind)          US$ 1,484,502.60

  - UNDP (In-Kind)	            US$ 100,000.00

Programme Period:	2013-2017

Atlas Award ID:		00081135

Project ID:		00090570

PIMS #			             5160

Start date:	1st October 2014

End Date:	31st December 2015

Management Arrangements:	IGO

PAC Meeting Date:                     2 May 2014

Agreed by (Country):

Date/Month/Year

Agreed by (Executing Entity/Implementing Partner):

Date/Month/Year

Agreed by (UNDP):

Date/Month/Year

Table of Contents

Acronyms and Abbreviations	4

PART I - PROJECT	6

A Project Summary	6

A.1	Project Rationale, Objectives, Outcomes/Outputs, and Activities	6

A.2	Key Indicators, Assumptions, and Risks	9

B	Country ownership	10

B.1	Country Eligibility	10

B.2	Country Ownership	11

B.2.a	National Capacity Self-Assessment (NCSA)	12

B.2.b	Sustainable Development Context	14

B.2.c	Policy and Legislative Context	17

B.2.d	Institutional Context	18

B.2.e	Barriers to Achieving Global Environmental Objectives	18

C.	Programme and policy conformity	18

C.1	GEF Programme Designation and Conformity	18

C.1.a	Guidance from the Rio Conventions	21

C.2  Project Design	22

C.2.a	GEF Alternative	22

C.3	Sustainability and Replicability	40

C.3.a	Sustainability	40

C.4	Stakeholder Involvement	41

D.	Financing	48

D.1	Financing Plan	48

D.2	Cost Effectiveness	54

D.3	Co-financing	54

E.	Institutional Coordination and Support	54

E.1	Core Commitments and Linkages	54

E.1.a	Linkages to other activities and programmes	54

E.2	Management Arrangements	55

F.	Legal Context	57

PART II:	ANNEXES	59

Annex 1:	TREATY TO ESTABLISH SPREP	60

Annex 2:	Logical Framework	61

Annex 3:	Outcome Budget (GEF Contribution and Co-financing)	72

Annex 4:	Provisional Work Plan	74

Annex 5: UNDP Risk Log	77

Annex 6:	Terms of References	78

Annex 7:	Letter of Agreement for recovery of Direct Project Costs	86

Annex 8: Letter of Endorsement	87

# Acronyms and Abbreviations

ACM - Adaptive Collaborative Management

APR - Annual Project Reports

AusAID - Australian AID

AWP - Annual Work plan

AWPID - Annual Work Programme Implementation Database.

CCCD - Cross Cutting Capacity Development

CMCA - Common Multi-Country Analysis

CPAP - Country Programme Action Plan

CROP - Council of Regional Organizations of the Pacific

CO2- Carbon Dioxide

COSO - Cadbury and CoCo

DPC - Direct Project Cost

DSA - Daily Subsistence Allowance

ESIA - Environmental and Social Impact Assessment

FAO - Food and Agriculture Organization

FMIS - Financial Management Information System

FSM - Federated States of Micronesia

GDP - Gross Domestic Product

GEF EA - Global Environment Facility Executing Agency

GEF IA - Global Environment Facility Implementing Agency

GEF PAS - Global Environment Facility Pacific Alliance for Sustainability

HR  - Human Resources

ICF - Internal Control Framework

ICT - Information, Communication and Technology

IFAC - International Federation of Accountants

IFRS -International Financial Reporting Standards

IIA - Institute of Internal Auditors

ISA - International Standards on Auditing

LoA - Letter of Agreement

M & E - Monitoring and Evaluation

MEA - Multilateral Environmental Agreement

MoU - Memorandum of Understanding

NCSA - National Capacity Needs Self-Assessment

OEPPC - Office of Environmental Planning and Policy Coordination

OERC - Office of Environmental Response and Coordination

PB - Project Board

PD - Project Director

PIR - Project Implementation Report

PICs - Pacific Island Countries

PICTs - Pacific Island Countries and Territories

PIFACC - Pacific Island Framework for Action on Climate Change

PM - Project Manager

PMERs- Performance and Monitoring and Evaluation Review

PMS - Project Management System

PMU - Project Management Unit

PNG- Papua New Guinea

PRMS - Pacific Regional Support Mechanism

POPs - Persistent Organic Pollutants

PTS - Persistent Toxic Substances

RMI - Republic of the Marshall Islands

SBAA - Standard Basic Assistance Agreement

TE - Terminal Allowance

ToR - Terms of Reference

UNCBD - United Nations Convention on Biological Diversity

UNCCD - United Nations Convention to Combat Desertification

UNCT - United Nations Country Team

UNDAF - United Nations Development Assistance Framework

UNDP - United Nations Development Programme

UNEP - United Nations Environment Programme

UNFCCC - United Nations Framework Convention for Climate Change

UNDP MCO - United Nations Development Programme Multi-Country Office

(UNDP GEF) RCU - Regional Coordination Unit

# PART I - PROJECT

# A Project Summary

## A.1	Project Rationale, Objectives, Outcomes/Outputs, and Activities

- The decision for SPREP to seek accreditation to the GEF is based on instructions from SPREP's member countries, including all 14 Pacific Island Countries eligible for GEF funding. These countries noted this would provide an additional option for accessing GEF resources and further noted that this decision reflects the fact that SPREP is part of their national capacities and should be strengthened to support nationally driven development programmes. In essence, countries account for SPREP as extensions of their national ministries or departments of environment and climate change, and therefore justify seeking financial support from the GEF to build the institutional, systemic and individual capacities of SPREP to meet the GEF minimal standards for accreditation.

- By specifically investing in building SPREP's capacity to become a GEF Project Agency, the Pacific Island Countries' national capacities to develop and manage GEF projects will invariably be built through SPREP's support.  This is due primarily to the countries having national ownership of SPREP and also how the secretariat has been structured to supplement national capacities as part of Government agencies’ internal structures.

- The SPREP Agreement signed by Pacific Island Governments in 1993 determines the legal standing and purpose of SPREP, as an intergovernmental environmental organization working in the Pacific region. SPREP is headquartered in Apia, Samoa and has 26 Members with direct interests in the region including American Samoa, Australia, Commonwealth of the Northern Mariana Islands, Cook Islands, Federated States of Micronesia, Fiji, France, French Polynesia, Guam, Kiribati, Marshall Islands, Nauru, New Caledonia, New Zealand, Niue, Palau, Papua New Guinea, Samoa, Solomon Islands, Tokelau, Tonga, Tuvalu, United Kingdom, United States of America, Vanuatu, and Wallis and Futuna.

- SPREP’s funding sources include its member countries and other sources, including the GEF. SPREP finances its projects though grants and operates in its Pacific member countries. SPREP’s mission is to promote cooperation in the Pacific region and provide assistance in order to protect and improve the region’s environment and to ensure sustainable development for present and future generations.

- SPREP has been assisting the Pacific Island Countries (PICs) with their national and regional applications to the GEF since the inception of GEF. In addition, SPREP is a partner for the PICs in the GEF-Pacific Alliance for Sustainability (GEF-PAS), established in 2006 between the GEF CEO and the PICs. SPREP has been the Executing Agency on a number of regional and multi-country projects under the auspices of GEF PAS and other GEF Initiatives.

- Under the National Capacity Self–Assessment (NCSA), all 14 Pacific Island Countries have prepared their National Action Plans, which reflect the principles and provisions of the three Rio Conventions.  These Action Plans are providing countries with frameworks for internal and external coordination to streamline planning and implementation of cross-cutting capacity building initiatives. SPREP supported all 14 Pacific Island Countries through a joint collaborative effort with the United Nations University and the Department of Environment and Heritage in Australia to provide technical backstopping for each phases of the NCSA process. This suite of support was delivered to countries formally under the Pacific Regional Support Mechanism (PRMS) for NCSA. The PRSM provided support during the NCSA exercises to some of the countries in the region, in addition to the technical and operational support provided by the Implementing Agency (UNDP for 13 countries and UNEP for 1 country).

- The Secretariat introduced document GEF/C.42/09/Rev.01, Secretariat Recommendations of Project Agencies for Accreditation, reviewing the two-stage screening process to be followed during 2012, in which during Stage I, entities are screened for their possible value-added to the GEF, and those approved by the Council are passed on to Stage II, where an external panel reviews their compliance with GEF standards and policies. 11 agencies received passing scores in Stage I: five national, two regional and four CSOs. The GEF CEO noted that while the Secretariat of the Pacific Regional Environment Programme (SPREP) did not receive an overall passing score, the GEF Secretariat recommended providing capacity building for one year and allowing them to reapply in 2013.  The GEF CEO stressed that the Secretariat is not advocating a special capacity-building project for SPREP, but rather working with the UN Development Programme (UNDP) on a normal GEF project that would involve SPREP and include capacity building designed in a way that would prepare them to become a GEF Agency in GEF-6.

- SPREP's Stage I application to the GEF had identified the need for countries to build SPREP's institutional capacity to meet minimal accredited standards as part of their efforts to strengthen national capacities to access GEF resources. The independent accreditation panel review concluded in its value added review for stage I, that SPREP has demonstrated its mission aligns very well with the GEF’s mission, and that it has extensive regional experience in the areas of climate change and biodiversity with the ability to engage in both medium- and full-size GEF projects, as well as the capacity to leverage co-financing. Additionally, the review noted 3 areas that required strengthening in-order to be reconsidered for Stage II. These are (1) Demonstration of Environmental or Climate Change Adaptation Results; (2) Institutional Efficiency; and (3) Network and Contacts. These areas shape the key priorities of this proposed medium-sized project. The essential components will be designed around building fiduciary capacity, setting up of an organizational social and environmental safeguard policy and a gender mainstreaming policy.

- SPREP's Stage II application was prepared in parallel to developing its PIF and project document for this MSP. The intention was to allow for these 2 processes to occur side by side and eventually converge at a later stage where the MSP will inform the contents of the Stage II application. Unfortunately, while SPREP was preparing its Stage II application which was sent to the GEF accreditation panel on the 21 May 2012, a decision was taken by both the GEF accredited panel and SPREP to resubmit its Stage I and II application after the MSP has upgraded many of SPREP's policies, procedures, systems and tools that will enable it to meet the GEF's minimum accredited standards.  Subsequent advice sought from the GEF noted that the current first round of the accreditation process will end by the 31st December 2014. Therefore, it is envisage that this MSP will not be completed in time to prepare and re-submit SPREP's Stage I and  II application. SPREP may need to wait for the GEF Council to take a decision on when a second round of application will take place.

- In 2011, the SPREP Governing Council Meeting held in Apia, Samoa, inter alia, endorsed the proposal that the Secretariat apply for accreditation as a GEF Project agency to provide Members with another choice of GEF Agency; and noted that the aim of this application is to implement more effectively t the SPREP Strategic Plan 2011-2015, to support the priorities of Pacific Island Countries”. The rationale behind the 2011 directive given to SPREP by its member countries was to assist Pacific Island Countries to improve access to multilateral financing for sustainable development, in particular through the Global Environmental Facility.

- SPREP has been making positive advances towards improving its governance structure and initiated a comprehensive change management process in 2010. This process has ensured a more focused and strategic approach within SPREP to deliver key results under the 4 areas (Climate Change, Biodiversity and Ecosystem Management, Waste Management and Pollution Control, and Environmental Monitoring and Governance) in a new SPREP Strategic Plan (2011-2015).   These priorities of SPREP for 2011–2015 address the fundamental environmental concerns of the Pacific region that have become increasingly evident over the past two decades. As well as responding to Members’ priorities, this Strategic Plan sets clear targets and performance indicators, and strengthens environmental monitoring as a basis for regional and national decision making. At the same time, SPREP engaged the Frankfurt School of Finance and Management to perform a baseline assessment of SPREP’s institutional capacity to access multilateral funding directly.  The assessment was broad in scope, covering an analysis of SPREP’s performance in both programmed delivery and compliance with GEF Fiduciary Standards. It noted that while some aspects of SPREP’s organizational practices were in compliance with the various GEF standards and requirements, there were areas in which improvement was needed. In particular, the report identified compliance with the GEF’s fiduciary standards and its project development, monitoring and evaluation capacities as key areas in which SPREP, and the region as a whole, require strengthening.

- Taken together, these studies provide the baseline and justification for the proposed project. Both outline the institutional functions in need of further development in order to comply with the requirements for direct access to GEF financing. The project is structured to coherently consider the institutional conditions at SPREP and its ability to meet Pacific Island Countries’ needs and requirements, and thereby address institutional policy development to meet the GEF Project Agency criteria. For the purposes of this proposal, the baseline reasoning in relation to the principal accreditation requirements regarding institutional efficiency is summarized below noting that each of these requirements will be taken through a rigorous analysis to ensure compliance with GEF criteria.

- This project responds directly to the Stage I review of the independent accreditation panel of the GEF.  It had identified multitudes of capacity gaps that SPREP must strengthen before proceeding forward to Stage II accreditation. These are: (1) Internal audit and financial management and control frameworks; (2) Separation of SPREP’s implementation functions from existing execution activities; (3) Financial disclosure; (4) Project appraisal processes and standards; (5) Procurement processes; (6) Investigation function and whistleblower protection;  (7) Environmental and social safeguards; and (8) Gender mainstreaming policy.

- Internal audit and financial management and control frameworks: SPREP has recently established an Internal Audit function at SPREP. However, further work is required to meet the GEF Policies and Procedures. In particular, further work is required on the operational policies necessary to ensure that the Internal Auditing function is operationally independent from Executive management. Under the baseline scenario, SPREP would continue to lack the internal audit function and additional strengthening is required. The project will develop a comprehensive system for internal audit at the organization to oversee risk areas such as Fraud, Whistleblower Protection and Procurement.

- Separation of SPREP’s implementation functions from existing execution activities: Under the baseline scenario, the current SPREP institutional framework lacks a clear separation (firewall) between project implementation and project execution functions. This is based entirely on the executing agency role that SPREP is suited for and has been performing in the last 20 years for the GEF in the Pacific region. However, as a GEF Project Agency, SPREP would be required to have such a firewall if it was to continue to perform EA functions. The proposed project would develop this division at the operational level in accordance with the GEF Separation of Implementation and Executing Functions in GEF Partner Agencies [unless SPREP decides to be only an EA for projects, which are managed by a different GEF IA]. This will ensure that there is a clear separation between project implementation (identification, preparation of project concept, appraisal, preparation of detailed project document, project approval and start-up, project supervision, and project completion and evaluation) and execution (management and administration of the day-to day activities of projects in accordance with specific project requirements). Alternatively, SPREP may consider adopting a policy that stipulates it will never seek to engage both roles in one project at any time. Thus the status quo remains where SPREP will work with another GEF IA to secure its role as an EA - as it always has been with UNDP, UNEP and FAO. Conversely, SPREP may wish to engage a project as a GEF IA (should it received accreditation) and collaborate with separate and independent organizations as the EA for any one project.

- Financial Disclosure: As mentioned previously, the Value Added Review Panel identified weaknesses in SPREP’s institutional efficiency. For example, in the VAR, as a primary weakness the Panel identified a lack of clarity in the way project and administrative costs are defined by the organization. Under the proposed project, this would be addressed by enhancing SPREP’s current classification of project costs to meet that required by the GEF. The project will enable SPREP to develop these classifications further with the objective of increased transparency in its financial procedures. Under the baseline scenario, there has been little incentive to change the way project and administration costs are defined.

- Project appraisal processes and standards: Another major institutional weakness cited in the Value Added Review was that, at present, it is unclear how long it takes SPREP, on an average basis, to guide a project from concept to terminal evaluation; this was instrumental to the low score obtained by SPREP for institutional efficiency. The proposed project will develop internal policies and procedures for project cycle management that are compliant with the 2010 GEF Monitoring and Evaluation Policy and the 2008 Policies and Procedures for the GEF Project Cycle. Under the baseline, while rigorous project cycle management is an important best practice for any institution, GEF-specific policies and procedures have not been applied.

- Procurement processes: The Value Added Review (VAR)process concluded that SPREP’s Policies and Procedures in Procurement were GEF-compliant; however, the issue of sustained oversight over procurement processes was raised as a concern to be addressed. In this area, the proposed project will fully integrate oversight of SPREP’s procurement processes into the internal audit function and institute the appropriate procedures to ensure that outside agencies are in full compliance with SPREP’s Procurement Processes.

- Investigation function and whistleblower protection: In a similar vein to the finding on Procurement, the Value Added Panel was satisfied with SPREP’s Policy on Zero Tolerance Fraud and Investigation. However, at the present time, a detailed operational framework related to whistleblower protection and related issues, is yet to be developed. The proposed project will develop these policies and integrate them at all levels of the organisation in order to meet the Recommended Minimum Fiduciary Standards for GEF Implementing and Executing Agencies.

- Gender mainstreaming policy: As per GEF policy, SPREP will endeavor to develop its policy for gender sensitization both within the organization and at project/programme design stage. This is an additional requirement that has recently been introduced by the GEF Council for all GEF Project Agencies.

- This project is eligible for funding under the GEF-5 Cross-Cutting Capacity Development (CCCD) Strategy, Programme Framework C, which calls for the strengthening of capacities to develop policy and legislative frameworks to meet Rio Convention objectives.  It does so by strengthening SPREP's capacity to assist Pacific Island Countries to access MEA funding through the GEF.

## A.2	Key Indicators, Assumptions, and Risks

- There are a few risks and assumptions associated with the design of this project.  The first risk is associated with meeting the GEF' council deadline for the GEF 5 Pilot on Accrediting GEF Project Agencies. The Accreditation Pilot began in January 2012 after 16 agencies submitted Stage I applications to the Secretariat by December, 31, 2011. SPREP was one of these agencies.  Based on the outcome of the Stage I Value-Added Review, SPREP was identified as a key partner that required capacity building for which this project aims to bridge before it can proceed to Stage II. Stage II review process for the first round began in June 2012and is expected that this first round will be completed in December 2014. Therefore, there is a significant risk that this MSP will not be able to be completed by December 2014 unless the GEF Council extends the deadline or approve a second round of accreditation.

- This is a management project as opposed to the traditional development type project that would require a longer time period for results to be achieved. This project requires management expertise for capacity building activities that meets the GEF and/or World Bank fiduciary standards. Therefore, the recruitment of management experts that could deliver the key outputs of this project may take some time. This could prove counter-productive to any efforts to expedite the delivery of outputs before the December 2014 deadline.

- There is also the risk that the capacity building activities of this MSP may not be adequate or sufficient to meet the expectations of the accreditation panel. The progress report submitted to the GEF council GEF/C.42/09/Rev.01 May 8, 2012 provided limited guidance on exactly what needs to be done with the exception of identifying 3 key areas of capacity, which did not receive a pass mark. These are demonstration of environmental and climate change adaptation results, institutional efficiency, networks and contacts. Additional guidance can be sourced from GEF policy papers on social and environmental policy including gender mainstreaming policy that all GEF Project Agency must comply with. Together, these papers inform the initial designing of ' what we think constitutes a bridging activity to meet the GEF's minimum accredited standards.

- The  difficulty in the identification of what is a GEF minimal accredited standard has hampered any discussions to define clearly the benchmarks for fiduciary standards that will need to be built into the enhanced functions and procedures of SPREP under this MSP. However, guidance sourced from the GEF policy paper (2007) 'Recommended Minimum Fiduciary Standards for GEF Implementing and Executing Partners' has been helpful. UNDP as the GEF Implementing Agency is placed appropriately to use its extensive experience working with the GEF, and with SPREP, since 1991,and will provide strategic guidance in the project design for minimal accredited standards.

- This risk makes the assumption that the commitment of the GEF Council and its Secretariat to the project will not wane during its formulation and implementation or beyond, jeopardizing the institutional sustainability of project outcomes.  For this reason, this project will take an adaptive collaborative management (ACM) approach to implementation, which calls for key partners involved (i.e. SPREP Senior Management Team, UNDP Samoa, and GEF) to take an early and proactive role in the delivery of key outputs, as well as to help identify and solve unexpected implementation barriers and challenges.  By taking an ACM approach, project activities and outputs can be more legitimately modified and adapted to maintain timely and cost-effective project performance and delivery.

- Annex 5 identifies key risks and proposed mitigation for this MSP. The overall level of risk is considered moderate primarily due to the real probability that this MSP will not be completed in time before the first round of accreditation ends in December 2014. All other risks identified are deemed manageable with the appropriate mitigation proposed to alleviate concerns that may hamper the progress of the MSP.

# B	Country ownership

## B.1	Country Eligibility

- Fourteen (14) of the Pacific Island Countries that are members of SPREP are signatories to the Rio Conventions on Climate Change, Biological Diversity and Land Desertification. Additionally, these same countries are also eligible to receive technical assistance from UNDP, and therefore eligible for support under the Global Environment Facility (GEF). The 14 Pacific Island Countries eligible for GEF funding are all members of the SPREP with equal ownership of the organization. SPREP as an intergovernmental organization, by default, provides technical extension of the Ministries /Departments of Environment and Climate Change of these Pacific countries. The SPREP Secretariat is accountable to its member countries and receives instructions annually through its SPREP Governing Council Meeting. At the 22nd SPREP Meeting in 2010, Apia, Samoa, all 14 Pacific Island Countries requested the Secretariat to seek accreditation as a GEF Project Agency as soon as possible. The meeting;

  - Endorsed the proposal that the Secretariat apply for accreditation as a GEF Project Agency to provide Members with another choice of GEF Agency.

  - Noted the aim of this application is to more effectively implement the SPREP Strategic Plan 2011-15, to support the priorities of Pacific Island Countries and Territories; and

  - Directed the Secretariat to provide an update to the 2012 SPREP Meeting on the status of this application.”

- Though not an eligibility requirement, SPREP has demonstrated its commitment to regional environmental priorities through various environmental agreements in the Pacific that complements the GEF's work such as the Apia, Noumea and the Waigani Conventions for which SPREP is the secretariat. Others include the Convention on Conservation of Nature in the South Pacific, 1976; Convention for the Protection of the Natural Resources and Environment of the South Pacific Region, 1986 (and related Protocols); and Convention to Ban the Importation into Forum Island Countries of Hazardous and Radioactive Wastes and to Control the Trans-boundary Movement and Management of Hazardous Wastes within the South Pacific Region, 1995. SPREP has also been designated by the leaders of the Pacific as the regional focal point for the 3 Rio Conventions namely: United Nations Framework Convention on Climate Change; United Nations Convention on Biological Diversity; and United Nations Convention to Combat Desertification.  SPREP also provides technical and policy support to Pacific Islands Countries in meeting their international obligations under the Stockholm Convention, Basel Convention and Rotterdam Convention, including through the Waigani Convention.

- Fit with the GEF-5 CCCD Strategy:  The GEF strategy for Cross-Cutting Capacity Development projects serves to provide resources for reducing, if not eliminating, the institutional bottlenecks and barriers to the synergistic implementation of the Rio Conventions. This particular project is in line with CCCD Programme Framework C, which calls for countries to strengthen capacities for developing policy and legislative frameworks.  Through a learning-by-doing process, this project will improve sectoral policies, plans and programmes by integrating provisions of the three Rio Conventions (sub-programme framework C1)through the strengthening of SPREP's capacity to support national and regional capacities.  The project will help build SPREP's institutional capacity and to support the Pacific Island Countries national efforts to meet their national and international obligations under the Rio Conventions (sub-programme) C2 including the Stockholm, Basel, and Rotterdam Conventions.

## B.2	Country Ownership

- The Pacific Regional UN Development Assistance Framework (UNDAF) 2013-2017 was approved in 2012. The United Nations Development Assistance Framework (UNDAF) for the Pacific Sub-Region is a five-year strategic programme framework that outlines the collective response of the UN system to development challenges and national priorities in 14 Pacific Island Countries and Territories (PICTs), namely Cook Islands, Fiji, Federated States of Micronesia, Kiribati, Nauru, Niue, Palau, Marshall Islands, Samoa, Solomon Islands, Tokelau, Tonga, Tuvalu and Vanuatu for the period 2013-2017. Its overarching ambition is to promote sustainable development and inclusive economic growth to address the social, economic and environmental vulnerabilities affecting society at all levels and to ensure human security in the Pacific, with a focus on the most vulnerable groups.

- The Framework is the result of broad consultations with PICTs and partners around a number of development challenges identified in a Common Multi-Country Analysis (CMCA) developed by the UN Country Teams (UNCT) based in Fiji, Samoa and Papua New Guinea in consultation with national and regional stakeholders and partners. Among these challenges, the analysis highlighted physical isolation, small economies of scale, limited governance structures, small populations and markets, limited natural resources (in most cases), uneven infrastructure, the impact and variability of climate change, natural hazard risks, and the vulnerability to economic shocks. There are significant gaps with regard to service delivery capacity and gender equality, including limited political participation by women. Nearly a fifth of the region’s total population is young, which is both a challenge and an opportunity for governments to ensure access to quality education and health services, employment and the types of support services that will guide their transition to productive adulthood. Cultural heritage and diversity is at risk due to increasing urbanization and, in some countries, significant outmigration.

- With the UNDAF 2013-2017 the UN system in the Pacific will draw on its comparative advantage to continue its work to address these challenges, build on the progress achieved during the previous programming cycle and reflect on the development needs beyond 2015. In line with the global imperatives and opportunities detailed in the UN Secretary-General’s Five Year Action Agenda of 2012, the UN system in the Pacific will focus its programming and advocacy efforts on five inter-related outcomes areas:

1. Environmental management, climate and disaster risk management, in support of an integrated approach to environmental sustainability and efforts by PICT governments and communities to adapt to climate change and reduce and manage disaster risk.

2. Gender equality, with the aim of fostering gender equality, women’s political and economic empowerment and participation, and enhance safety for women and children across the Pacific.

3. Poverty reduction and inclusive economic growth, where the UN system will promote the capacity to stimulate equitable growth, create economic opportunities and decent work especially for the youth, and promote sustainable livelihoods and social protection systems.

4. Basic services (health and education). The UN system aims to building capacity throughout society to improve the quality of and access to basic services in health, education, and protection; and strengthening the accountability of duty bearers.

5. Governance and human rights, where the aim is to improve the quality of governance, including the inclusion of vulnerable groups in decision-making processes in the political and economic spheres and advance compliance with international human rights norms and standards.

### B.2.a	National Capacity Self-Assessment (NCSA)

- All 14 Pacific Island Countries eligible for GEF funding have received and completed their National Capacity Needs Self-Assessment Exercises. Their National Action Plans have highlighted capacity constraints commonly shared in the Pacific Region. The UNDP and UNEP synopsis in 2010 titled 'National Capacity Self-Assessments: Results and Lessons Learned for Global Environmental Sustainability' was undertaken to identify the results generated by applying the NCSA methodology around the world. This analysis	 revealed that the top five capacity development	needs expressed by countries to achieve and sustain global environmental outcomes are:

(1) public awareness	and environmental	education; (2)  information management and exchange; (3) development and enforcement of policy and regulatory	frameworks; (4) strengthening organizational mandates and structures; and (5) economic instruments and sustainable financing mechanisms.

- The problems related to global environmental management and how the Pacific Island Countries are contributing to this problem are rooted in an overall institutional weakness of governance, including environmental governance. The NCSA identified the following major shortfalls.

- Lack of awareness amongst the Ministries and/or Departments and other state bodies on the international conventions and of the opportunities they provide, as well as of the steps required from national Governments to fulfill its commitments;

- Weak institutional arrangements for the implementation of the Conventions;

- Poor financing and lack of appropriate human resources in governmental institutions;

- Lack of consistency and insufficient sharing of information between key stakeholders. There is currently little communication across agencies responsible for the Conventions with individual Pacific Island Governments. This is linked to the low commitment to follow up on identified priorities, and to the lack of a strong policy framework and political commitment to implementation; and

- The weak capacity of the government to carry out strategic planning that reflects an integration of international objectives into local and national action plans. This is primarily related to two factors: first, the lack of up-to-date social, economic and environmental data to support the strategic planning process; and second, lack of communication and coherent regulations establishing the framework for preparing and implementing integrated sustainable planning.

- Based on the global analysis (inclusive of the Pacific Island Countries) for lessons learned from the NCSA process, the following 5 main types of capacities gaps were identified to meet and sustain global environmental objectives are;

  - Stakeholder Engagement: A sense of readiness is necessary from all parties involved, including at the political level, in order to achieve and sustain  global environmental objectives; Achieving environmental sustainability necessitates  the engagement of stakeholders; which in turn is predicated on their level of awareness and understanding, as well as having the skills to take action; Best Practice methodologies are needed to engage stakeholders; and that the NCSA process was innovative, benefitting from broad and interactive participation of stakeholders, which made the assessments highly relevant.

  - Information Management and Knowledge: Although not complete, environmental information exists; however, the capacities to access and manage this information including coordination with other management information systems remain weak;

There is	 a need to incorporate traditional/indigenous knowledge into the environmental management information system.

  - Organizational Capacities: Many countries lack clarity in their	 organizational arrangements to adequately finance environmental management.

  - Environmental Governance:	Many countries continue to lack comprehensive	 and adequate set of environmental policies, with missing or unenforced legislative and regulatory instruments that further hinder environmental management.

  - Monitoring and Evaluation:	Regulatory instruments that further hinder environmental	management.

- SPREP conducted a regional analysis of 10 Pacific Island Countries' NCSA Action Plans in 2012.

This review summarizes the vulnerabilities and challenges identified in these countries' National Capacity Self-Assessment reports (NCSAs). It then identifies two strategies for addressing them: a) a set of questions to help stakeholders prioritize among various environmental problems and b) guidelines for designing better environmental policies. The report concludes by proposing five specific tasks that national governments might request SPREP to assist them with, as follows:

- Identify “no regrets” policies that generate non-environmental co-benefits while also fostering environmental progress.

- Develop a “citizen science” program to simultaneously collect and organize data, promote education, raise awareness, and prompt more environmentally-friendly behavior.

- Further develop “regional expert networks” to promote “learning exchanges” among SPREP countries.

- Develop new and enhance existing “traditional knowledge and the environment” programs.

- Enhance SPREP’s policy coordination and facilitation among member states.

### B.2.b	Sustainable Development Context

- The Pacific Island Region is diverse in terms of size and features of the island countries, although there are many shared characteristics that have a substantial influence on the potential impacts sustainable development vis–a-vis environmental protection and conservation:

- Geographical isolation – the large expanses of water and small areas of land, create numerous challenges including difficulties of transport and communications both within and between countries, and to the international community;

- Rapid population growth, and high population densities – the rapid growth in population that many PICs have experienced in past decades along with increasing commercialization of traditional, subsistence-based economies has been associated with rapid increases in rates of natural resource exploitation, especially land, forests and living marine resources;

- Limited land resources – many PICs are characterized by extremely small land area and limited land resources, such as soil and forest, making many terrestrial and near-shore resources quite vulnerable to overexploitation and pollution from poorly planned waste disposal;

- Dependence on marine resources – all PICs have a traditional dependence on marine resources for subsistence, and as the region's ocean resources contain the highest marine biodiversity in the world, it represents almost the sole opportunity for substantial economic development for many of the small island nations;

- Low topographic elevation – many of Pacific islands, especially atolls, have very low topography, some reaching only a few meters above sea level at their highest point;

- Vulnerability and resilience – PICs often experience enormously damaging extreme weather events, suffer severely from global economic pressures and fluctuations, and have a heavy reliance on the productivity of one or two economic sectors, resulting in many PICs adopting a no regrets‟ approach to resource management ; and

- Small, highly integrated environmental and economic systems – the small size of islands result in the interactions between components of natural systems and the sectors of economic activity being rapid and strong, which demands that sustainable development be holistic and balanced.

- The Pacific Islands region includes 14 nation states and eight territories scattered over one third of the globe, covering an area of around 30 million km2. Of the total area, only 0.4% is covered by land, made up of between 20,000-30,000 small islands, with Papua New Guinea (PNG) covering 83% of the region’s land area.

- The Pacific Islands is a place of enormous diversity in physical geography, culture, languages, social-political organization, size and natural resource endowment. The area is also extremely vulnerable to environmental changes because its predominantly small islands and fragile environment are susceptible to natural and human-induced geologic and climatic hazards such as cyclones, droughts, and tsunamis, resulting from the global rise in greenhouse gas emissions, increasing populations, and unsustainable exploitation of its biodiversity and natural resources.

- The Pacific Islands region is one of the richest areas of terrestrial and marine ecosystems on earth, with habitats ranging from mountain forest ecosystems to volcanic islands and low lying coral atolls and extensive coral reef systems. The New Guinea Islands (the west is part of Indonesia and the east is part of Papua New Guinea) alone is home to over 5% of global terrestrial biodiversity, with two thirds found nowhere else in the world, despite being less than 1% of the global landmass. The Western Pacific, which includes Melanesian countries and Palau, is recorded as having the highest marine biodiversity along with the most extensive coral reef system in the world. The region’s isolated islands provide ideal conditions for the evolution of new species. As a consequence, Pacific islands have high numbers of "endemic" species, including more than 400 endemic bird species.

- The Pacific Islands, with large spans of untouched forests, mangroves and pristine inshore reefs, provide great carbon sequestration values, but are also the most vulnerable to human-induced and natural climate change and sea level rise. This is despite the countries of the region emitting the least amount of carbon into the atmosphere.

- Climate change is already disproportionally affecting the islands of the Pacific. Although islanders have done little to contribute to the cause – less than 0.03% of current global greenhouse gas emissions – they are among the first to be affected. Most islands are experiencing climate change impacts on communities, infrastructure, water supply, coastal and forest ecosystems, fisheries, agriculture, and human health as well as tourism.

- Agriculture, which is mostly rain-fed in the region, is susceptible to changes in rainfall distribution. Intense and prolonged rainfall could damage seedlings, resulting in greater run-off and soil erosion and encourage conditions that promote pests and diseases. Droughts combined with higher temperatures would cause added thermal stress on plants. Projected increases in sea surface temperatures combined with increased ocean acidification (from increased CO2 concentrations in the atmosphere) are likely to put pressure on the marine food chain (particularly reef systems and other calcifying organisms such as planktons) which in turn potentially threatens aspects of marine food supply and associated livelihoods. The incidence of vector-borne disease such as malaria and dengue fever, and water-borne diseases such as dysentery and diarrhea are likely to increase and shift in distribution (malaria is likely to extend further southwards).

Table 1: SPREP Countries’ Key Statistics

| Countries |  | Land Area (km2) | Exclusive economic Zone(EEZ) Area (km2) |  |  | Population (est. mid-2009) | GDP/capita (USD) |  |  | GDP Growth Rate 2007 (est.) | Human Development Index |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Cook Islands |  | 237 | 1,830,000 |  |  | 15,636 | 10,007 |  |  | 0.4 | .829 |
| FSM |  | 701 | 2,978,000 |  |  | 110,899 | 2,1830 |  |  | .10 | .716 |
| Fiji Islands |  | 18,272 | 1,290,000 |  |  | 843,8833 | 3182 |  |  | -3.90 | .718 |
| Kiribati | 811 |  |  | 3,550,000 | 98,989 |  |  | 656 | 0.597 |  |  |  |
| RMI |  | 181 | 2,131,000 |  |  | 54,065 | 2,851 |  |  | 2 | .708 |
| Nauru |  | 21 | 310,000 |  |  | 9,771 | 2,820 |  |  | 0.20 | .637 |
| Niue | 259 |  |  | 390,000 | 1,514 |  |  | 5,854 | 0.821 |  |  |  |
| Palau |  | 444 | 616,000 |  |  | 20,397 | 8,423 |  |  | 5.5 | 0.810 |
| Papua New Guinea |  | 462,840 | 3,120,000 |  |  | 6,609,745 | 1,062 |  |  | 6.2 | 0.437 |
| Samoa |  | 2,935 | 120,000 |  |  | 182,578 | 2,860 |  |  | 4.7 | 0.762 |
| Solomon Islands |  | 28,370 | 1,340,000 |  |  | 535,007 | 1,100 |  |  | 6.3 | 0.579 |
| Tonga |  | 650 | 700,000 |  |  | 103,023 | 1,874 |  |  | -3.5 | 0.737 |
| Tuvalu |  | 26 | 900,000 |  |  | 11,093 | 1,563 |  |  | 3 | 0.691 |
| Vanuatu |  | 12,190 | 680,000 |  |  | 238,903 | 1,908 |  |  | 4.7 | 0.640 |

- As reflected in Table 1, the Pacific Island nations range in size and population, from Papua New Guinea, which is spread over 400,000 km2 with a population of over 5 million, to Nauru with a population of less than 9,800 and a land mass of only 21 km2, and Niue with a population of roughly 1,500 residing on a land area of 259km2. Solomon Islands and Fiji have populations above 500,000, while Vanuatu, Samoa, Tonga, Kiribati, and Micronesia have populations of between 100,000 and 230,000. The remaining smaller island states of Nauru, Palau, Cook Islands, Niue, Tuvalu, and Marshall Islands have populations ranging from around 60,000 down to 1,400. The population growth rates for the region are relatively high, averaging 2.2% per annum. Countries that have high emigration rates such as Tonga, Samoa, and Tuvalu normally have less than 1% growth rates, while Niue and Cook Islands with New Zealand citizenship have had negative growth rates for the last 10 years.

- With the exception of PNG, the Pacific’s populations predominantly reside in rural coastal areas, thus making them even more vulnerable to sea level rise, extreme weather events and tsunamis.  The Pacific economies are primarily dependent on agriculture (20-40% of GDP), fishing (10% of GDP) and tourism (up to 40%) of GDP in some countries.2 For countries like Samoa and Tonga, remittances account for 25% and 32% of their respective GDPs. The continental high islands of the Melanesian group have extractive industries such as logging and mining as additional major contributors to their economies.

- The resource-rich Melanesian states have higher GDPs than the Polynesian and Micronesian states. PNG has a GDP of USD$7906 million, Fiji a GDP of USD$3061 million, Solomon Islands a USD$715 million GDP, and Vanuatu a USD$729 million GDP. The rest of the region – which includes Samoa, Tonga, Niue, Cook Islands, Tuvalu, Federated States of Micronesia, Palau, Kiribati, Nauru, and the Marshall Islands – have GDPs ranging from USD$523 million in Samoa to USD$54 million in Nauru.

- The 14 Pacific Island nation states have all signed and either ratified or acceded to UNFCCC, UNCBD, UNCCD, and Stockholm Convention on POPs for which GEF is the financial mechanism.

- To have individual countries undertake national efforts to combat the environmental challenges is a difficult task due to small populations, limited economies, lack of technical knowledge base, and trans-boundary conditions. It is for these reasons that the Pacific Island countries established the Secretariat of the Pacific Regional Environment Programme (SPREP) to coordinate regional efforts and support the countries’ environment and sustainable development efforts.

- SPREP was established by Pacific Island governments and territories under the Agreement Establishing SPREP in 1993, “… to promote co-operation, and provide assistance in order to protect the environment and to ensure the sustainable development for present and future generations.”3 SPREP has four Focal Areas: climate change; biodiversity and ecosystem management; waste management and pollution control; and environmental monitoring and governance.

### B.2.c	Policy and Legislative Context

- The Pacific Plan: The Plan is the overarching strategy for regional integration and coordination in the Pacific.  Building on the Pacific Island Forum Leaders’ Vision, it is the  highest regional policy framework that guides the work of national governments, regional agencies and development partners in support of the aspirations of the Pacific Island Countries and their people.  The Plan was endorsed by the Pacific Island Forum Leaders at their meeting in Port Moresby, Papua New Guinea in October 2005.The primary goal of the Pacific Plan is to enhance and stimulate economic growth, sustainable development, good governance and security for Pacific countries through regionalism. The Plan is made up of four strategic pillars: (i) Economic Growth; (ii) Sustainable Development; (iii) Good Governance; and (iv) Security.  Two of these pillars, sustainable development and good governance, are areas directly relevant to the outcomes of this project and for which regional agencies such as SPREP have been granted a strong mandate to provide technical support for sustainable environmental management in the Pacific.

The Pacific Plan is based on a strong sense of regionalism where Pacific Island Countries recognise the value and the potential co-benefits of regional cooperation that can bring in decreased transaction costs and broader geographical coverage in areas where extensive geographical cooperation is required.

- Council of Regional Organizations of the Pacific Agencies (CROP): The Forum Leaders established the Council of Regional Organisations in the Pacific (formerly the South Pacific Organisations Coordinating Committee) in 1988 with the mandate to improve cooperation, coordination and collaboration among the various intergovernmental organisations to work toward achieving the common goal of sustainable development in the Pacific region. CROP functions as (i) a coordination mechanism between the heads of the regional organisations in the Pacific, and (ii) a high-level advisory body to provide policy advice and facilitate policy formulation at the national, regional and international levels.  CROP provides a forum to enable CROP heads to collectively review progress with their respective organisations’ contributions to the Pacific Plan.

- SPREP Strategic Plan 2011-2015: The SPREP Strategic Plan was adopted by the 2010 SPREP Meeting.  The Strategic Plan is a single, integrated plan that identifies the priorities, strategies and actions for addressing a number of environmental and sustainable development challenges within SPREP’s regional mandate. As a result of extensive consultation with SPREP’s Member Countries, Secretariat programme staff and partner organisations, the plan establishes four strategic priorities:

- Climate Change;

- Biodiversity and Ecosystem Management;

- Waste Management and Pollution Control; and

- Environmental Monitoring and Governance

These priorities of SPREP for 2011-2015 address the fundamental environmental concerns of the region that have become increasingly evident over the past two decades.  As well as responding to Members’ priorities, the Strategic Plan sets clear targets and performance indicators, and strengthens environmental monitoring as a basis for regional and national decision making. Whilst identifying the fundamental underlying environmental and sustainable development concerns, the Strategic Plan also recognises the need for strengthening SPREP in order to execute its functions effectively. SPREP’s ability to execute projects effectively is directly correlated with its institutional capacity and this project primarily aims to address this.

### B.2.d	Institutional Context

### B.2.e	Barriers to Achieving Global Environmental Objectives

- For many years, Pacific Island Countries relied on the GEF for financial support to establishing enabling frameworks for sustainable environment management in-country. With the establishment of national architectures in the form of environmental departments/ministries and conservation policies, Pacific Island Countries have increased implementation of their environmental policies. Through support from existing GEF Implementing Agencies in the Pacific region, national efforts are gaining momentum to meet both national and international obligations to MEAs. Despite this, the Pacific region historically lags behind other regions in accessing their GEF allocations. National capacities vis a vis institutional, systemic and individual barriers in addition to GEF IA and EA internal procedures are often causing delays to developing projects quickly and effectively for GEF funding. This translates directly to delays in generating global environment benefits for Pacific Island Countries. Breaks between parent and offspring projects and prolonged project cycles can also hinder the continuity of sustaining environmental outcomes in linear form.

- The barriers to achieving global environmental objectives are in large part a reflection of the challenges faced by Pacific Island Countries. Since1991, certain experiences and practices in the area of sustainable environmental management has been gained.  However, at the same time, limitations to environmental governance, high staff turnover, weak information systems, national budgetary constraints, inadequate science programmes, and limited research capabilities have all had a negative impact on the quality of development and implementation of environmental management policies.

- Barriers to achieving global environmental objectives in Pacific Island Countries are largely the result of the lack of awareness and understanding of the Rio Conventions' and their value. While some Pacific Island Countries are advanced in their mainstreaming agenda through the adoption of sector wide approaches, there are many still experiencing difficulties of transitioning to greater mainstreaming at the national and local levels. The traditional sectoral approach to development coupled with seriously limited financial resources means that line ministries will follow the path of least resistance.  This is exacerbated by the complex bureaucratic structures that are a disincentive for ministries and agencies to override institutional and regulatory directives.

# C.	Programme and policy conformity

## C.1	GEF Programme Designation and Conformity

- This project conforms to the GEF-5 Cross-Cutting Capacity Development (CCCD) Strategy, Programme Framework C, which calls for the strengthening of capacities to develop policy and legislative frameworks to meet Rio Convention objectives.  More precisely, this CCCD framework provides the vision for CCCD projects to integrate and mainstream Rio Convention (among other MEA) obligations into a country's policy and legislative frameworks, and to underpin these strengthened capacities with strengthening improved management and compliance.

- Taking into account SPREP's Integrated Strategic Plan 2011-2015, as well as Regional and National Sustainable Development Plans of Pacific Island Countries, the project activities will focus on a collaborative and expert analysis of capacity gaps within SPREP which affects its ability to support national capacities of Pacific Island Countries to further integrate provisions of the Rio Convention into sectoral policies, plans and programmes.  This will be accompanied by targeted training on how to better operationalize recommended modifications by undertaking capacity building priority exercises.  For example, the project could look at the set of guiding policy documents of the GEF for accessing funds as a Project Agency. By doing so, SPREP's internal management frameworks will be enhanced with the flow-on effects to Pacific Island Countries to be realized through expedited processes of applying for GEF funds. Fast-tracking GEF resources to Pacific Island Countries will inevitably create stronger capacities to generate both national and global environmental benefits and thereby meeting international obligations of countries to MEAs. This will be achieved in-countries through deeper and meaningful mainstreaming into national planning, policy and budgetary frameworks.

- National Sustainable Development Plans (NSDP) of Pacific Island Countries are in place.  The achievement of national sustainable environmental management goals are supported by SPREP alongside other development partners of the Pacific region. Invariably, individual countries' NSDP are in different degrees of operationalization, although all are tailored to national circumstances. SPREP works within these levels of variance to ensure quality environmental protection and conservation goals are being met and aligned to MEAs. Specific collaborations target biodiversity conservation, climate change adaptation and mitigation, sustainable land management, chemical management (i.e. POPs &PTS). Owing much to SPREP's mandate, it is expected that similar support from the secretariat will be demanded by the Pacific Island Countries who sign on to the recently approved Minamata Convention. In essence, SPREP provides technical and policy assistance through programmatic support that includes the GEF inter alia.

- Given the holistic construct of sustainable development and its foundations based on the principles of environmental conservation (of both national and global significance), economic growth, and social needs (which includes culture), continuous support to Pacific Island Countries' efforts to implement their National Sustainable Development Plans are imperative to generating national and global environmental benefits. SPREP's ability to support national capacities for more entrenched integration of the three GEF focal areas is vital for sustaining meaningful and longer lasting outcomes for environmental protection and conservation in Pacific Island Countries. Therefore, the outcomes of this project center on an improved systemic, institutional, and individual capacities to meet and sustain global environmental objectives.  Project outcomes will be measured against building SPREP's capacity as a key contribution to building national capacities of Pacific Island Countries to better understand and reinforce the linkages between the national sectoral policies and global environmental objectives.

- This project will implement management development capacity activities in SPREP through an adaptive collaborative management approach to engage stakeholders of SPREP, namely the 14 national GEF operational focal points as collaborators in the design and implementation of project activities that take into account unintended consequences arising from this project. The SPREP Governing Council Meeting Chairperson provides the overall voice and input of the 14 Pacific Island Countries throughout the lifespan of this project.

- The project is also consistent with the programmatic objectives of the three GEF thematic focal areas of biodiversity, climate change and land degradation, the achievement and sustainability of which is dependent on the critical development of capacities (individual, organizational and systemic) of Pacific Island Countries through SPREP.  Through the successful implementation of this project, recommendations and amendments will be made on the institutional, systemic and individual capacity of SPREP, which will in turn will support National Sustainable Development policies and programmes that fully reflect Rio Convention principles and obligations. Table summarizes the project's conformity with the 11 operational principles of capacity development identified in the GEF Strategic Approach to Capacity Building.

Table 2:  Conformity with GEF Capacity Development Operational Principles

| Capacity Development Operational Principle | Project Conformity |
| --- | --- |
| Ensure national ownership and leadership | The development of this project benefitted from consultations with all 14 Pacific Island Countries National Operational Focal Points and SPREP National Focal Points. The Chairperson of the SPREP Governing Council Meeting will provide the overall leadership on behalf of the Pacific Island Countries. |
| Ensure multi-stakeholder consultations and decision-making | The project will use multi-stakeholder and expert consultative reviews of the analysis of SPREP's institutional, systemic and individual capacity and make recommendations towards defining capacity building outcomes and outputs for meeting GEF's minimal accredited standards. Project implementation will take an adaptive collaborative management approach, which includes stakeholder representatives in the project decision-making structures. |
| Base capacity building efforts in self-needs assessment | SPREP's Regional NCSA analysis from 10 Pacific Island Countries' NCSA action plans have identified capacity needs for supporting policy coordination, expert networks, citizen science programmes and no regrets policies. Overall, it conforms with UNDP's analysis where countries NCSA needs fall under 5 thematic areas for targeted capacity development support. These are stakeholder engagement, information management and knowledge, organization capacities, environmental governance, and monitoring and evaluation. |
| Adopt a holistic approach to capacity building | The project's strategy is to focus on building 14 Pacific Island Countries' national capacity to meet MEA's obligations through strengthening of SPREP management policies, systems and procedures to deliver GEF funds directly to them. All 14 departments/ministries of environment and climate change functions and roles in-country will apply a sector wide approach will be supported by building SPREP's capacity to support their national functions. |
| Integrate capacity building in wider sustainable development efforts | By integrating Rio Convention provisions into Pacific Island Countries' socio-economic policies and plans, this project will directly implement capacity building activities (e.g., training and learn-by-doing exercises) towards strengthening SPREP's capacity to assist its member countries eligible for GEF funding to meet sustainable development goals so that they deliver both national and global environmental benefits. |
| Promote partnerships | By its very nature, this project requires collaboration and coordination among Pacific Island Countries and SPREP. SPREP's extensive network of partnerships with international and regional NGOs and development partners in the Pacific region may also be used to garner ideas for strengthening SPREP's role as a GEF Project Agency. |
| Accommodate the dynamic nature of capacity building | The project's implementation arrangements include the creation of a Project Board that will convene regularly (once every four months and as needed should the need arise) to oversee the performance of capacity development activities, manage risks, and to approve appropriate modifications to the project activities. |
| Adopt a learning-by-doing approach | The core of the project's capacity development activities are via a learning-by-doing approach. SPREP staff involved in performing fiduciary functions, mainstreaming gender and implementing the organization's environmental and social safeguard policy will be target for training. The learning-by-doing will also be instituted through the development and implementation of recommended policy reforms in SPREP. |
| Combine programmatic and project-based approaches | This project takes a bottom-up and top-down approach to Rio Convention mainstreaming. This project effectively began with the NCSA, which was a bottom-up approach to develop national action plan for cross-cutting capacity development. The NCSA Action Plans provide the analytic framework for defining recommendations to build national capacities of Pacific Island Countries' to comply with the Rio Conventions. The focus of this project is consistent with the programmatic framework for the holistic pursuit of Rio Convention outcomes and sustainable development of Pacific Island Countries through strengthening SPREP's support to them. |
| Combine process as well as product-based approaches | The project’s execution process is the adaptive collaborative management approach, which is organized to ensure that representatives from all 14 GEF operational focal points and SPREP focal point inclusive of the SPREP Governing Council Meeting Chairperson is in the decision-making process. This process effectively began with the NCSA, which identified this project's objective, whose commitment was maintained through the instructions from all 14 Pacific Island Countries to seek GEF accreditation as a way for countries to quickly access GEF funds to implement their NCSA action plans inter alia. |
| Promote regional approaches | The project will test recommendations for reforms and amendments in SPREP. This will allow for the ground-truthing of the recommendations, and inform modifications in SPREP's policies, systems and procedures to enhance its regional role in supporting NSDPs. |

### C.1.a	Guidance from the Rio Conventions

- This project will address the shared obligations under the three Rio Conventions, which call for countries to strengthen their national capacities for effective national environmental management frameworks.  In the long run, this project will address a set of Rio Convention articles that call for improved stakeholder engagement to address global environmental issues in Pacific Island Countries.  In-directly, the project will strengthen national environmental governance of 14 Pacific Island Countries for the global environment by integrating Rio Convention provisions into their respective sectoral development policies, legislation, plans and programmes, all organized under the rubric of a National Sustainable Development Plans.  This responds to the Article 4(f) of the FCCC, which calls for Parties to "Take climate change considerations into account, to the extent feasible" in their relevant social, economic and environmental policies and actions…"  Similarly, Article 6(b) of the CBD calls for Parties to "Integrate, as far as possible and as appropriate, the conservation and sustainable use of biological diversity into relevant sectoral or cross-sectoral plans, programmes and policies."  Article 4(a) of the CCCD calls for Parties to "Adopt an integrated approach addressing the physical, biological and socio-economic aspects of the processes of desertification and drought."

- The project will also strengthen organizational capacities, which include individual capacities to carry out actions for improved decision-making on the global environment.  For example, Article 19 of the CCD calls for "institution building, training and development of relevant local and national capacities in efforts to combat desertification and mitigate the effects of drought."  Article 17(2) of the CBD calls for "information on training and surveying programmes, specialized knowledge, indigenous and traditional knowledge" to be shared in order to facilitate the conservation and sustainable use of biodiversity.  Article 6(a)(iv) of the FCCC calls for the "Training of scientific, technical, and managerial personnel."

- Stakeholder engagement is similarly called for in the three Rio Conventions.  Articles 6(a)(ii) and (iii) of the FCCC expressly call for Parties to promote and facilitate public access to information on climate change and its effects, as well as for public participation in addressing climate change.  Article 10(d) calls for Parties to "support local populations to develop and implement remedial action in degraded areas where biodiversity has been reduced."  Article 5(d) of the CCD calls for Parties to "promote awareness and facilitate the participation of local populations, particularly women and youth, with the support of NGOs, in efforts to combat desertification and mitigate the effects of drought."

Table 2:  Capacity Development Requirements of the Rio Conventions

| Type of Capacity | Convention Requirements | FCCC | CBD | CCD |
| --- | --- | --- | --- | --- |
| Stakeholder Engagement | Capacities of relevant individuals and organizations (resource users, owners, consumers, community and political leaders, private and public sector managers and experts) to engage proactively and constructively with one another to manage a global environmental issue. | Article 4 Article 6 | Article 10 Article 13 | Article 5 Article 9 Article 10 Article 19 |
| Organizational Capacities | Capacities of individuals and organizations to plan and develop effective environmental policy and legislation, related strategies, and plans based on informed decision-making processes for global environmental management. | Article 4 Article 6 | Article 8 Article 9 Article 16 Article 17 | Article 4 Article 5 Article 13 Article 17 Article 18 Article 19 |
| Environmental Governance | Capacities of individuals and organizations to enact environmental policies or regulatory decisions, as well as plan and execute relevant sustainable global environmental management actions and solutions. | Article 4 | Article 6 Article 14 Article 19 Article 22 | Article 4 Article 5 Article 8 Article 9 Article 10 |

- Environmental governance is a centerpiece of this project, wherein the project will strengthen national policy frameworks for catalyzing Rio Convention implementation through integrated sectoral policies, plans and programmes in Pacific Island Countries.  The institutional sustainability of the project's strengthened capacities of an integrated global environmental and sustainable development strategy would be supplemented through SPREP's on-going programmes for training and awareness-raising activities.  Table 3 identifies the Rio Convention articles to which this project will help address.

## C.2  Project Design

### C.2.a	GEF Alternative

- This project takes a GEF incremental approach to sustainable development, where the co-financed baseline is SPREP's work to pursue sustainable development in Pacific Island Countries' national interest, and the GEF adds or modifies this baseline, as appropriate, to create synergies in development actions that provide global environmental benefits.  This project builds upon SPREP's commitment to sustainable development, in particular sustainable environmental management, to take a bottom-up approach to mainstreaming Rio Convention provisions into sectoral development policies, plans, programmers, and legislation of its member countries that will in turn inform a more robust and integrated global environmental and sustainable development strategy.

- All 26 member countries of SPREP are key partners in the implementation of this project through their annual budgetary support to SPREP. This project also builds upon the review of SPREP by the Frankfurt School of Finance and Management, which assessed internal capacity to access multi-lateral funding abroad. More importantly, this project will directly respond to bridging gaps identified in the Value Added Review by the GEF's independent accreditation panel in 2012.

#### C.2.a.1	Project Rationale

- The project has been developed in accordance with the guidance on GEF policies, programme priorities and eligibility criteria for requesting medium size project funds. The rationale for this project comes out of the need to build SPREP's internal capacity to support expedited access of GEF resources by 14 Pacific Island Countries who are both eligible to receive GEF support and are SPREP member countries. The historical constraints faced by the pacific region with regards to drawing down on GEF funding has been chronic and at times affecting the continuity of project succession. Important development gains can be reversed due to lapses in post project funding. Pacific Island Countries have limited national budgets to sustain key results when project funding cease and thereby underpins the importance for continuity of parent to offspring project from one GEF programme cycle to another.

- In addition to the three Rio Conventions, this project will enhance SPREP's capacity to assist the Pacific region to access GEF funds including other multilateral funding to assist Pacific Island Countries meet their international obligations under various MEAs. It will also allow SPREP to strengthen its coordination role in leveraging technical assistance and funding for its own work to meet its core mandate as reflected in its 2011-2015 Strategic Plan. Aside from this Plan, other regional plans that have been approved by Pacific Island Countries will also be targeted for additional support as these all contribute to achieving GEF's core mandate in the Pacific region. These  include: (1)Pacific Island Framework for Action on Climate Change (PIFACC) 2006-2015, (2) Pacific Regional Solid Waste Management Strategy 2010-2015, (3) Regional Wetlands Action Plan for the Pacific 2011-2013, (4) Regional Marine Species Action Plans, and the (5) new regional framework for nature conservation and protected areas 2014-2020.

- Despite the success of implementing NCSA projects, Pacific Island Countries'(see section B.2.a) continue to encounter barriers to implementation as a result of limited funding to support NCSA Action Plans. Evaluation reports of capacity development suggest the importance of integrating capacity development with specific areas of activities along with increasing the scale of support for sound economic development and environmental sustainability. Thus, a central part of GEF’s approach to capacity development is to develop capacity through regular Focal Area projects and programs. However, recently eight Pacific Island Countries (Samoa, Fiji, Solomon Islands, Papua New Guinea, Kiribati, Palau, Tonga and Vanuatu) are in the process of developing national project under GEF’s Cross-Cutting Capacity Development (CCCD) funding window to address national capacities identified in NCSA Action Plans. By achieving GEF accreditation as a project agency, SPREP will work complement this work, and support coordination with other key development partners of the region to deepen integration of development activities that target specific recommendations arising out NCSA Action Plans.

- The GEF and UNDP will partner with SPREP's technical assistance programmes to provide incremental support to mainstreaming global environmental provisions under the three Rio Conventions.  This project will also coordinate with existing programmes funded by SPREP's metropolitan countries such as Australia, New Zealand, France, United Kingdom, and the USA to mainstream environmental priorities into regional and national planning and decision-making processes of Pacific Island Countries.

#### C.2.a.2	Project Goal and Objectives

- The long term objective of the project is to enable SPREP to support 14 Pacific Island Countries

to more effectively achieve global environmental benefits by strengthening their key institutional and individual capacities. The support given by SPREP to its member countries that are eligible for GEF funding includes technical and policy support and facilitating access to funding to strengthen the design, adoption and implementation of environmental policies and programs.

- Key results will be measured by the work undertaken by SPREP to develop project proposals for Pacific Island Countries to expedite access to GEF resources inter alia. Projects that are approved will be targeting capacity development to achieve deeper integration of project activities to NCSA action plans and ultimately contributing to generating global environmental benefits. Public awareness campaigns and wider consultation with relevant stakeholders on the role of SPREP as a GEF Project Agency will be unfolded either separately in SPREP conferences and workshops or during PPG planning. This will contribute to effective policy formulation and implementation in PIC member countries.

- The goal of this project is to strengthen SPREP's capacity to assist Pacific Island Countries' implementation of the three Rio Conventions. To this end, the project will focus on enhancing 3 key areas: internal control framework, environmental and social safeguard policy, and a gender mainstreaming policy and guidelines.

SPREP's Accreditation as a GEF Project Agency Application

Baseline Analysis of SPREP's capacity to meet minimal GEF accreditation Standards

- Recommendations for developing SPREP's Gender Mainstreaming Policy & Guideline

Recommendations for developing SPREP's Environmental and Social Safeguard Policies

Recommendations for strengthening SPREP Internal Control Frameworks

GEF SPREP Medium Size Project for Enhancing Capacity to Develop Global and Environmental Projects in the Pacific

C.2.a.3	Expected Outcomes and Outputs

- At the end of the project, activities will have resulted in a set of improved capacities within SPREP to meet GEF minimum accreditation standards. This project will have strengthened and helped institutionalize commitments required to meet SPREP's Stage II application for accreditation. Indirectly, it will also help Pacific Island Countries efforts to meet their obligations under the Rio Conventions in the long run.

- This project will be implemented in four linked components:

  - Enhancing Internal Control Frameworks to meet GEF Minimum Fiduciary Standards;

  - Develop Environmental and Social Safeguard Policy;

  - Develop Gender Mainstreaming Policy and Guideline; and

  - Strengthening Information, Communication and Technology Systems.

Component 1:  Enhancing Internal Control Frameworks to meet GEF Fiduciary Requirements

Outcome 1: SPREP has the policies, mechanisms, procedures and standards in place to perform GEF fiduciary functions.

- As a way of understanding the existing baseline in SPREP, Table 3 summarizes the GEF minimum fiduciary standards and what is needed to be achieved by this project. The project outputs and activities inadvertently shape the direction for the desired capacity to be achieved.

Table 3: GEF Fiduciary requirements and envisaged project outputs and activities

| Recommended Minimum Fiduciary Standards | Related Project Output and Activities |
| --- | --- |
| The external financial audit function ensures an independent (as defined by the International Federation of Accountants (IFAC)) review of financial statements and internal controls. | Already standard SPREP practice. Required by the SPREP Governing Council Meeting. Internal Auditor established in 2011. Reports directly to the SPREP Director General. Additionally, the Internal Auditor works through the Independent Audit committee comprising of non-SPREP staff . External audits are outsourced to reputable audit firms within the Pacific Region. An external audit opinion is sought annually for discussions in the SPREP Governing Council Meeting. Project outputs: 2.1 |
| An internal control framework, as defined by internationally recognized frameworks such as COSO, Cadbury and CoCo, is a risk-based process designed to provide reasonable assurance and feedback to management regarding the achievement of objectives in the following categories: - Effectiveness and efficiency of operations - Reliability of financial reporting and financial management frameworks - Compliance with applicable policies and procedures. | Strengthened to meet GEF standards under project output 2.5. This output covers also the requirements formulated in the note “GEF Minimum Fiduciary Standards: Separation of Implementation and Execution Functions in GEF Partner Agencies”. |
| The financial disclosure policy delineates the process surrounding mandatory financial disclosures of possible or apparent conflicts of interest by identified parties. | SPREP does not have a financial disclosure policy. Uses International Financial Reporting Standards that are World Bank compliant. The procurement manual requires financial disclosures or conflict of interests. Project Output 1.1. |
| A code of ethics for agency staff promotes responsible governance and ethical behavior. | There is an existing SPREP Code of Ethics in place. Analysis will assess the adequacy of the existing code of conduct against the GEF accredited standards for Ethics. Project Output 2.4 |
| Internal auditing is an independent, objective activity designed to add value and improve an organization's operations. It helps an organization to accomplish its objectives by bringing a systematic, disciplined approach to evaluate and improve the effectiveness of risk management, control, and governance processes. | Internal auditor recruited since 2011. Reports directly to the Director General on operational matters. Reports to the independent audit committee (comprising on Non-SPREP staff) on matters pertaining to the Director General. Project Output 2.5 |
| Project appraisal functions include the establishment of standards and appropriate safeguards that are used to determine whether projects and activities will meet their stated goals before funds are disbursed. | Project appraisal undertaken through compliance with GEF project M&E rules within the approved project documents. These include reviews done through evaluation (mid-term and terminal) including updates received through PMU and Steering Committee/Project Board meetings. Project Outputs 2.6 and 2.7 |
| Agency procurement processes covering both internal/administrative procurement and procurement by recipients of funds include written standards based on widely recognized processes and an internal control framework to protect against fraudulent and corrupt practices (using widely recognized definitions such as those agreed by the International Financial Institutions Anti-Corruption Task Force and waste. | Procurement Manual guides all procurement of goods and services in SPREP. Project Output 3.2 |
| The GEF monitoring and evaluation policy, adopted by the Council in February 2006, establishes minimum requirements based on widely recognized, best practice norms and standards for monitoring in the GEF. From a fiduciary perspective, the monitoring function detects, assesses, and provides management information about risks related to projects and/or activities, particularly those deemed to be at risk. | SPREP follows the GEF and UNDP Monitoring and Evaluation Frameworks reflected in approved project documents. Project Output 2.7 |
| The evaluation function assesses the extent to which projects, programs, strategies, policies, sectors, focal areas, or other activities achieve their objectives. The goals of evaluation are to provide an objective basis for assessing results, to provide accountability in the achievement of agency objectives, and to learn from experience. The GEF monitoring and evaluation policy, adopted by the Council in February 2006, establishes minimum requirements based on widely recognized, best practice norms and standards for monitoring in the GEF, including impartiality, professionalism, and a high degree of independence. | GEF funded projects evaluations are managed through GEF Implementing Agencies such as UNDP and UNEP. GEF IA recruits the independent evaluator and manages the process to completion. Project Outputs 2.6 and 2.7 |
| The investigation function provides for independent, objective investigation of allegations of fraudulent and corrupt practices (using widely recognized definitions such as those agreed by the International Financial Institutions Anti-Corruption Task Force) in agency operations, and of allegations of possible agency staff misconduct. | Zero tolerance policy on fraud and corruption in place. Project Outputs 2.8 and 2.9 |
| Agency policies provide avenues for reporting suspected ethics violations and protections for individuals reporting such violations. | Whistleblower arrangements are in place. Project Outputs 2.8 and 2.9. |

- In general, all minimum fiduciary standards apply across SPREP operations, rather than to project- or GEF-specific activities. These include external and internal audit, financial management and controls, financial disclosure, codes of ethics, investigation, hotline and whistleblower protection. Project appraisal standards, procurement processes, and project-at-risk systems may vary to some degree, depending on the type of programs and activities, in terms of the appropriate criteria and objectives used. However, the core principles are consistent across different types of operations and activities.

- In the specific context of an agency’s GEF work, any assessment must examine whether GEF activities are fully covered by institution-wide standards. In addition, institutional standards designed to cover core business activities must be assessed to ensure that their application to GEF work is effective. This proposal assumes that SPREP's activities undertaken are consistent with the recommendations of the GEF policy on Comparative Advantages of the GEF Agencies; in any case, if SPREP's management and control frameworks are focused on different kinds of activities than those undertaken for the GEF, there must be an examination of whether the frameworks achieve their intended purposes for GEF activities as well. This may apply to existing or future operations.

- SPREP's finance comprises of 10 staff with 5 programme staff and 5 support staff; responsible for projects financial reporting; conference and travel arrangements; financial operations and procurement; financial reporting & administration services. The budget of the organisation has increased from 7 million to 22 million during the last 5 years and the number of projects has increased from 22 to 50 and the volume of transactions has increased tremendously. The current accounting system (ACCPAC) is not capable to meet the ever increasing (specific) reporting requirements of different donors to SPREP.  The procurement function has not been fully integrated into the current system and the human resources and payroll systems have a standalone system which needed to be integrated into one system for the efficiency of operations. The need for project managers to keep track of their expenditures throughout the lifespan of their projects is an additional pressing need for SPREP finance team to come up with an enabling system and environment that allows for better management of project finances.

- This section specifies the recommended minimum fiduciary standards. The first subsection comprises of an overarching audit, financial management and controls areas: (1) external financial audit, (2) financial management and control frameworks, (3) financial disclosure, (4) code of ethics, and (5) internal audit. The second subsection covers the project/activity cycle: (1) project appraisal standards, including safeguards, (2) procurement processes, (3) project monitoring and project-at-risk systems, and (4) evaluation. The final subsection comprises the investigation function, including hotline and whistleblower protection.

Output 1.1:	Audit, Financial Management and Control Framework

- This output comprises a set of activities that are aligned directly to the GEF Policy Paper on Recommended Minimum Fiduciary Standards for GEF Implementing and Executing Agencies that was approved by the GEF Council in 2007. Therefore, the desired capacities to be built are shaped around specific requirements stipulated by this policy.

Activities: Strengthen External Financial Audit Functions

The external financial audit function ensures an independent {as defined by the International Federation of Accountants (IFAC)}  review of financial statements and internal controls.

1.1.1:	SPREP has appointed an independent external audit firm or organization that works according to the International Standards on Auditing (ISA).

Target: External Auditor Appointed.

Target indicator: Contract with External Auditor signed by senior management

1.1.3:	Prepare Financial Statements in accordance with recognized accounting standards such as 	International Financial Reporting Standards (IFRS).

Target: SPREP Financial Statements adopt IFRS.

Target indicator:	Financial Statements are in accordance with IFRS.

1.1.4:	Issue and make public an annual audit opinion on the financial statements, and/or, as appropriate,

on all GEF funds received from the Trustee and administered by the SPREP.

Target: SPREP External Audit Completed.

Target indicator:	External Audit Opinions on Financial Statements for all GEF funds are uploaded on the SPREP website.

1.1.5:	Appoint an independent audit committee, or comparable body to oversees the work of the

external audit firm or organization as it relates to the audit of the financial statements. The audit

committee or comparable body has written terms of reference that address its membership

requirements, duties, authority, accountability and regularity of meetings. The main duty of the

Audit Committee is to undertake regular external audit reports of observations with respect to

accounting systems, 	internal financial controls, and administration and  management of the

organization. Auditor and 	management progress reports are reviewed by the audit committee or

comparable body annually.

Target: SPREP Independent Audit Committee Established.

Target indicator:	Terms of Reference of the Independent Audit Committee is developed and approved by the SPREP Governing Council Meeting.

Target indicator:  Operational Budget for the Independent Audit Committee Secured.

Target indicator:	Opinions of the Independent Audit Committee to be made public.

Output 1.2:	Financial Management and Control Frameworks

Activities: Strengthen Financial Management and Control Frameworks

An internal control framework, as defined by internationally recognized frameworks such as COSO, Cadbury and CoCo, is a risk-based process designed to provide reasonable assurance and feedback to management regarding the achievement of objectives in the following categories:

• Effectiveness and efficiency of operations

• Reliability of financial reporting and financial management frameworks

• Compliance with applicable policies and procedures.

1.2.1:	Develop and adopt an internal control framework that includes clearly defined roles for 	management, internal auditors, the board of directors or comparable body, and other 	personnel. The control framework covers the control environment (“tone at the top”), risk 	assessment, internal control activities, monitoring, and procedures for information sharing.

Demarcate roles and responsibilities in the internal control framework pertaining to	accountability of fiscal agents and fiduciary trustees. The control framework guides the financial 	management framework

Target: SPREP's Internal Control Framework Established.

Target indicator:	SPREP's Internal Control Framework Document approved by Senior Management Team and uploaded on SPREP's Website.

1.2.2:	Establish risk-assessment processes at the institutional level to identify, assess, analyze and 	provide a basis for proactive risk responses in each of the financial management areas. Risks are 	assessed at multiple levels, and plans of action are in place for addressing risks that are deemed 	significant or frequent.

Target: SPREP's Internal Control Framework Established.

Target indicator:	Action Plans for Addressing Risks are Developed where necessary.

1.2.3:	Establish procedures for identifying internal controls and assessing controls details annually in 	core financial management areas, including budgeting; accounting; internal control; funds flow 	(including disbursements, cash management, unused fund closeout); financial reporting; and	auditing arrangements.

Target: SPREP's Internal Control Framework Established.

Target indicator: Procedures for Identifying Internal Controls and Assessing Control Details in

place.

1.2.4:	Segregate duties that are incompatible. Related duties are subject to a regular review by 	management; response is required when discrepancies and exceptions are noted; and segregation 	of duties is maintained between: settlement processing; procurement processing; risk 	management/reconciliations; and accounting.

Target: SPREP's Internal Control Framework Established.

Target indicator: Related Duties regularly Reviewed and Appropriate Management responses are

Documented when necessary.

Output 1.3:       Financial Disclosure

Activities: Enhance SPREP's Financial Disclosure Policy

The financial disclosure policy delineates the process surrounding mandatory financial disclosures of

possible or apparent conflicts of interest by identified parties.

1.3.1:	Document financial disclosure policy covering identified parties and defines conflicts of interest 	arising from personal financial interests that require disclosure, including actual, perceived and 	potential conflicts. The policy specifies prohibited personal financial interests. The policy 	describes the principles under which conflicts of interests are reviewed and resolved by SPREP. It 	describes sanction measures for parties that do not self-disclose where a conflict of interest is 	identified. Parties covered by the policy are provided a way to disclose personal financial	interests annually to an administrative function within the agency.

Target: SPREP's Financial Disclosure Policy in Operation.

Target indicator:	SPREP's Financial Disclosure Policy Document approved by the Senior

Management Team.

1.3.2:	Establish processes in the policy for the administration and review of financial disclosure 	interests of the defined parties, as well as resolution of identified conflicts of interests, under an 	independent monitoring/administration function.

Target: Processes for Financial Disclosure Approved.

Target indicator:	SPREP's Financial Disclosure Policy Documented and submitted to the Senior

Management Team for Approval.

Output 1.4:       Code of Ethics

Activities:  Enhance SPREP's Code of Ethics

A code of ethics for SPREP staff promotes responsible governance and ethical behavior.

1.4.1:	Document code of ethics to define ethical standards to be upheld, including protecting SPREP	and trust fund assets. The code lists parties required to adhere to the standards including 	employees, consultants, and independent experts. It describes disciplinary and enforcement 		actions for violations, and provides for appropriate flexibility in application and implementation 	in local environments. An ethics or related function provides administrative support for the code,	including distributing the code, monitoring compliance, and authority to refer alleged 	violations to the agency’s investigation function.

Target: SPREP's Code of Ethics Updated.

Target indicator:	SPREP's Code of Ethics Updated and submitted to Senior Management Team

for Approval.

1.4.3:	Establish multiple avenues for confidentially reporting compliance and/or other business conduct 	concerns such as a hotline and contact information for functional/department options (e.g. 	human resources and internal audit) are readily available (e.g. on the agency's intranet and 	external websites).

Target indicator: SPREP's Code of Ethics Updated.

Target indicator: Hotline set up including Code of Ethics portal for submitting complaints on the

SPREP website.

Output 1.5:        Internal Audit

Activities:    Strengthen SPREP's Internal Audit Functions

Internal auditing is an independent, objective activity designed to add value and improve an organization's operations. It helps an organization to accomplish its objectives by bringing systematic, disciplined approach to evaluate and improve the effectiveness of risk management, control, and governance processes.

1.5.1:	Internal audit activity carried out in accordance with internationally recognized standards such 	as those prescribed by the Institute of Internal Auditors (IIA).

Target: SPREP's Internal Auditor is IIA certified.

Target indicator:	SPREP's Internal Auditor using IIA standards

1.5.2:  Auditors and entities that provide internal auditing services adhere to ethical principles of integrity, 	objectivity, confidentiality and competency.

Target: Auditors complies with SPREP's Updated Code of Ethics.

Target indicator: SPREP's Code of Ethics Updated

1.5.3:	 The internal audit entity is functionally independent and objective in the execution of its 	respective duties. There is an officer designated to head the internal audit function. The chief 	audit officer reports to a level of the organization that allows the internal audit activity to fulfill 	its responsibilities objectively.

Target: Internal Auditor Position Fully Operational.

Target indicator:	Internal Auditor Recruited and Terms of Reference uploaded onto SPREP's

Website.

1.5.4:	Document the internal audit function Terms of Reference/charter that outlines its purpose, 	authorized functions, and accountability.

Target: Internal Auditor Terms of Reference Approved.

Target indicator: Internal Auditor Terms of Reference uploaded on SPREP's website.

1.5.5:	Description of the annual audit planning process in the internal audit function, including a risk-based methodology for preparing an audit plan. The audit plan outlines the priorities of the function and is consistent with the agency's goals. Share of audit information and coordination of activities with relevant internal and external parties (including external financial statement auditors) tonsure proper coverage and minimize duplication of efforts.

Target: SPREP's Internal Control Framework Established.

Target indicator: SPREP's Audit Plan uploaded on SPREP's website.

1.5.6:	Disseminate internal audit findings to the corresponding senior and business management units, 	who are responsible for acting on and/corresponding to recommendations.

Target: Internal Audit Findings Report.

Target indicator:	Audit findings shared with SPREP's Senior Management Team.

1.5.8:  Establish process for internal audit function to be in place to monitor the response to its	recommendations. Establish process to monitor and assess the overall effectiveness of the internal	audit functions 	including periodic internal and external quality assessments.

Target: Process for monitoring internal audit function established.

Target indicator: SPREP's audit plan policy and risk management plan updated.

Output 1.6:        Project/Activity Processes and Oversight

Activities:    Enhance Project Appraisal Standards

Project appraisal functions include the establishment of standards and appropriate safeguards that are used to determine whether projects and activities will meet their stated goals before funds are disbursed.

1.6.1:	Establish a project and/or activity appraisal process with the purpose of examining whether proposed projects and/or activities meet appropriate technical, economic, financial, fiduciary, environmental, social, institutional and/or other relevant criteria, including GEF-mandated criteria, and whether they are reasonably likely to meet stated objectives and outcomes. Incorporate project and/or activity development objectives and outcomes into key performance indicators with baseline and targets into the project/activity design.

Target: SPREP's Project Management Policy and Guideline.

Target indicator:	SPREP's Project Management Policy and Guideline submitted to Senior Management Team for Approval.

1.6.2:	Set-up policies and risk-assessment procedures that specify the criteria and circumstances under which environmental, social, institutional and/or fiduciary assessments must be conducted to incorporate environmental, social or other relevant considerations into a proposed project or activity.

Target: SPREP's organizational policies revised to include Environmental, Social and Fiduciary

Assessments and Consideration.

Target indicator:	SPREP's Project Management Policy and Guideline Developed to include these

considerations.

1.6.3:	Set-up guidelines or policies for appraisal by technical advisors, who assess whether or not a proposed project or activity is eligible for GEF funding, based on the GEF-mandated criteria; is likely to achieve GEF focal goals; and is aligned with scientifically sound principles.

Target: Guidelines for Project Appraisal Developed.

Target indicator:	SPREP's Project Management Policy and Guideline Developed and includes

risk management, social, environmental and gender aspects..

Target indicator: Operational Project Appraisal Criteria for Panel of Assessors.

1.6.4:	 Set-up appropriate fiduciary oversight procedures to guide the appraisal process and ensure its quality and monitoring of follow-up actions during implementation.

Target: SPREP's Fiduciary Oversight Procedures Established.

Target indicator:	SPREP's Project Management Policy and Guideline Developed.

Activities:       Procurement Processes and Guidelines

SPREP's procurement processes covering both internal/administrative procurement and procurement by recipients of funds include written standards based on widely recognized processes and an internal control framework to protect against fraudulent and corrupt practices(using widely recognized definitions such as those agreed by the International Financial Institutions Anti-Corruption Task Force2) and waste.

1.6.6:	Specific agency directives promote economy and efficiency in procurement through written 	standards and procedures that specify procurement requirements, accountability, and authority to 	take procurement actions. Specific procurement guidelines are in place with respect to different 	types of procurement 	managed by the agency, such as consultants, contractors and service	providers. Specific procedures, guidelines and methodologies of assessing the procurement	procedures of beneficiary institutions are in place. Procurement performance in implemented 	projects is monitored at periodic intervals, and there 	are processes in place requiring a response 	when issues are identified. Procurement records are easily accessible to procurement staff, and 	procurement policies and 	awards are publicly disclosed.

Target: SPREP's Procurement Guidelines, Procedures and Methodologies revised to include

GEF Accreditation Standards.

Target indicator: SPREP's revised Procurement Manual approved by senior management.

Activities:         Enhancing Monitoring and Project-at-Risk Systems

The GEF monitoring and evaluation policy, adopted by the Council in February 2006, establishes minimum requirements based on widely recognized, best practice norms and standards for monitoring in the GEF and Project Agencies. From a fiduciary perspective, the monitoring function detects, assesses, and provides management information about risks related to projects and/or activities, particularly those deemed to be at risk.

1.6.7:	Align monitoring functions, policies and procedures of SPREP to be consistent with the 	requirements of the GEF monitoring and evaluation policy. Articulate roles and responsibilities of the monitoring function at both the project/activity and 	entity/portfolio levels. Separate the monitoring function at the entity/portfolio level from the 	project and/or activity origination and supervision functions.

Target: SPREP's Monitoring and Evaluation Policy and Guideline Approved.

Target indicator: SPREP's Monitoring and Evaluation Policy and Guideline are aligned to GEF

Accredited Standards.	  .

Target indicator: Enterprise Risk Management Framework Adopted in SPREP.

1.6.8:	Establish a process or system, such as a project-at-risk system, to flag when project 	has 	developed problems that may interfere with the achievement of its objectives, and to respond 	accordingly to redress the problems.

Target: SPREP's Monitoring and Evaluation Policy and Guideline Approved.

Target indicator:	SPREP's Monitoring and Evaluation Policy and Guideline approved.

Target indicator: Enterprise Risk Management Framework adopted in SPREP.

Target indicator: Monitoring Reports prepared.

1.6.9:	Establish a process or system, such as a project-at-risk system, to flag when project 	has 	developed problems that may interfere with the achievement of its objectives, and to respond 	accordingly to redress the problems.

Target: SPREP's Monitoring and Evaluation Policy and Guideline includes a system covering

projects-at-risk..

Target indicator:	SPREP's Monitoring and Evaluation Policy and Guideline approved.

1.6.10:	Set-up adequate fiduciary oversight procedures to guide the project risk management process 	and to ensure its quality and monitoring of follow-up actions during implementation. This process 	or system is subject to independent managerial oversight.

Target: SPREP's Monitoring and Evaluation Policy and Guideline Approved.

Target indicator:	SPREP's Monitoring and Evaluation Policy and Guideline approved.

Target indicator: Enterprise Risk Management Framework adopted in SPREP.

Target indicator: Monitoring Reports prepared.

Output 1.7:        Evaluation Function

Activities:      Strengthened Evaluation Function

The evaluation function assesses the extent to which projects, programs, strategies, policies, sectors, focal areas, or other activities achieve their objectives. The goals of evaluation are to provide an objective basis for assessing results, to provide accountability in the achievement of agency objectives, and to learn from experience. The GEF monitoring and evaluation policy, adopted by the Council in February 2006, establishes minimum requirements based on widely recognized, best practice norms and standards for monitoring in the GEF, including impartiality, professionalism, and a high degree of independence.

1.7.1:	Align evaluation function to follow impartial, widely recognized, documented and professional standards and methods. Structure SPREP evaluations function to be independent from the organization’s operations, consistent with the structure of the SPREP, reporting directly to the board of directors. Develop an evaluation disclosure policy. Evaluation reports are disseminated as widely as possible, and at a minimum to all parties directly or indirectly involved with the project. To enhance transparency, to the extent possible, reports are available to the public.

Target: SPREP's Evaluations Systems and Procedures Enhanced.

Target indicator:	SPREP's Monitoring and Evaluation Policy and Guideline Aligned to GEF

Accredited Standards.

Target indicator: Evaluation Reports prepared.

Output 1.8:         Investigations

Activities:      Strengthen Investigation Functions.

The investigation function provides for independent, objective investigation of allegations of fraudulent and corrupt practices (using widely recognized definitions such as those agreed by the International Financial Institutions Anti-Corruption Task Force) in SPREP's operations, and of allegations of possible SPREP staff misconduct.

1.8.1:	Disseminate terms of reference of SRPEP's investigation functions publicly. This should outline the purpose, authority, and accountability of the function. To ensure functional independence, the investigations function is headed by an officer who reports to a level of the organization that allows the investigation function to fulfill its responsibilities objectively. Publish guidelines of SPREP's investigation functions for processing cases, including standardized procedures for handling complaints received by the function and managing cases before, during and after the investigation process.

Target: SPREP's Investigative Capacity Enhanced.

Target indicator: SPREP's Fraud Policy Updated and Aligned to the GEF Accredited Standards.

Target indicator: Investigation Guidelines and Procedures and ToRs Approved and Uploaded on

SPREP's website.

1.8.2:	Define a process for periodically reporting case trends as part of SPREP's investigation functions. To enhance accountability and transparency, to the extent possible, case trend reports and other information are made available to senior management and relevant business functions.

Target: SPREP's Investigative Capacity Enhanced.

Target indicator:	SPREP's Monitoring and Evaluation Policy and Guideline approved.

Target indicator: Enterprise Risk Management Framework adopted in SPREP.

Target indicator: Case Trend Reports prepared for SPREP Senior Management Team.

Output 1.8:     Hotline and Whistleblower Protection

Agency policies provide avenues for reporting suspected ethics violations and protections for individuals reporting such violations.

1.8.1:	Develop a whistleblower protection policy that specifies who is protected and defines protected disclosures, including violations of law, rule or regulation, abuse of authority, gross waste of funds, gross mismanagement or a substantial and specific danger to public health and safety. The policy defines the standard of protection from retaliation, including placing the burden on the agency to provide evidence that alleged acts of retaliation would have taken place absent the protected disclosure.

Target: SPREP Hotline and Whistleblower Protection Established.

Target indicator: SPREP's Whistleblower Policy submitted to Senior Management Team

for Approval.

1.8.2:	Coordinate the reporting of hotline information at the intake function point including compliance and/or other business concerns from internal and external sources. The intake function maintains an appropriate level of autonomy from the investigations function.

Target: SPREP Hotline and Whistleblower Protection Established.

Target indicator:	SPREP's Fraud Policy Updated and uploaded on the SPREP website.

Target indicator: Periodical Reports of Intake information prepared for SPREP senior

management team.

1.8.3:	Set up a SPREP hotline or comparable mechanism to ensure the capacity to take in reports of suspected unethical, corrupt, fraudulent or similar activity as defined by SPREP policies.

Target: SPREP Hotline and Whistleblower Protection Established.

Target indicator: Telephone Hotline and Web-based Applications for Reporting Fraud in place.

1.8.4:	Set up procedures for the periodic review of hotline, whistleblower and other reported information to determine whether it is handled effectively and whether processes for protecting whistleblowers and witnesses are consistent with best international practice.

Target: SPREP Hotline and Whistleblower Protection Established.

Target indicator:	SPREP's Fraud Policy Updated and uploaded on the SPREP website.

Target indicator:  SPREP's Whistleblower Policy submitted to Senior Management Team for

Approval.

Target indicator: Periodic reports on the management of whistleblower information

- SPREP will hire consultants who are experts in financial and administrative management, human resource management and legal matters pertaining to ethics, fraud and whistle-blowing to review the existing baseline capacity of SPREP and make recommendations and actions to improve SPREP's capacity in these areas. The PMU will seek assistance from the GEF secretariat, in particular the accreditation team leader on recommended consultants who have done similar work with other organizations who are seeking accreditation or have received accreditation to the GEF.

Component 2:	Develop Environmental and Social Safeguard Policy and Guideline

Outcome 2:	Environmental and Social Safeguard Policy and Guideline effectively applied and managed in both corporate and programme divisions of SPREP.

- In order to be accredited as a GEF Project Agency, SPREP will need to demonstrate to the GEF Accreditation Panel that it has policies and systems that comply with the criteria of all eight minimum standards stipulated for the environmental and social safeguard policy of the GEF.

- The eight minimum standards are:  (1) Environmental and Social Impact Assessment; (2) Natural Habitats; (3) Involuntary Resettlement; (4) Indigenous Peoples; (5) Pest Management; (6) Physical Cultural Resources; (7) Safety of Dams, and (8) Accountability and Grievance Systems. The paper also provides background on the GEF Secretariat- level Conflict Resolution System.

- In keeping with GEF policy, SPREP will comply with the mandatory prerequisite for safeguard standards 1 (Environmental and Social Impact Assessment), 2 (Natural Habitats), and 8 (Accountability and Complaint). The rationale for making Safeguard 1 compulsory for all GEF Partner Agencies is that Environmental and Social Impact Assessment is the umbrella policy framework within which application of the other safeguard standards occurs. The reason for requiring compliance with Safeguard 2 in all cases is that it is in keeping with the GEF’s long-standing policy that GEF projects in one focal area do not cause harm in another focal area. In this case, GEF projects in other focal areas should not harm natural habitats, which are critical to the preservation of biodiversity and ecosystem function.

- In the context of the review of the GEF Agencies, SPREP may consider requesting the GEF Council to by-pass non-compulsory standards. The GEF policy C41.Rev 10 on environmental and social safeguard provides opportunity for such a request to be made - i.e. ...'inapplicability for Minimum Standards 3 through 7 if it is found that SPREP would not reasonably need to apply such a safeguard in the context of its GEF operations, as defined by the type of projects it will implement or execute, or its agreed comparative advantage'. The Accreditation Panel would have the ability to make a similar finding for agencies that apply for accreditation as a GEF Project Agency, taking into account the types of projects they would be expected to implement according to its comparative advantage in the GEF network. The GEF Secretariat will not screen GEF Partner Agency1 compliance with this policy on a project-by-project basis.

- SPREP will need to hire consultants with significant expertise in the area of environmental and social safeguard standards to assess whether it complies with the minimum standards. These consultants will also assess compliance with the Policy on Gender Mainstreaming. The assessment will be implemented in a transparent manner. Terms of References of these consultancies and the assessment process in general will be discussed with the UNDP as the GEF IA for this project. The consultants will consolidate the results of this assessment in a report to SPREP, which will clearly indicate those areas in which it needs to meet the relevant criteria (e.g. on the different safeguards and the gender mainstreaming policy) and where the Agency does not. SPREP shall use the recommendations of this assessment report to shape capacity building activities to develop such as policy within SPREP but also to have the capacity to implement such policy. This project will therefore contribute directly through bridging activities that target a wholesale approach to institutionalizing an environmental and social safeguard policy in SPREP.

Output 2.1:	SPREP's Environmental and Social Safeguard Policy and Guideline

Activities:	Formulate SPREP's Environmental and Social Safeguard Policy and Guideline

2.1.1:	Formulate SPREP's Environmental and Social Impact Assessments Policy that ensure proposed projects are of environmental and social soundness and sustainability.

Target: SPREP's Environmental and Social Impact Assessment Policy.

Target indicator: Consultant recruited to develop SPREP's Environmental and Social Impact  Assessment Policy and Guideline.

Target indicator:	SPREP's Environmental and Social Impact Policy approved by SPREP senior

management team.

2.1.2:	Formulate guidelines for the administration of SPREP's Environmental and Social Impact Policy in compliance with the prescribed minimum requirements in the GEF ESIA policy paper C41. Rev 10.

Target: SPREP's Environmental and Social Safeguard Guidelines.

Target indicator:	SPREP's Environmental and Social Guidelines approved by SPREP senior

management team.

2.1.3:	Undertake training and transfer of knowledge activities for SPREP staff responsible for administering the Environmental and Social Impact Policy and Safeguard Guidelines.

Target: SPREP staff trained.

Target indicator:	Training undertaken for all relevant SPREP staff.

Target indicator: Regular training plans for ESIA Policy and Guideline prepared.

Component 3:	Gender Mainstreaming Policy and Guideline

Outcome 3:    Gender Mainstreaming Policy and Guideline effectively applied and managed in both

corporate and programme divisions of SPREP.

- In order to be eligible to receive GEF financing for GEF projects, SPREP will be required to have established either (a) policies, (b) strategies, or (c) action plans that promote gender equality;

- The policies, strategies, or action plans of SPREP will need to satisfy the minimum criteria on gender mainstreaming that are included in the GEF policy GEF/PL/SD/0 for systems to be assessed as adequate.

- To support the application of the gender policy, the GEF Secretariat will coordinate the development of corporate-wide guidance for use by the GEF Agencies and GEF Secretariat program managers on the inclusion of gender aspects in the design of projects and on the monitoring and evaluation of gender dimensions in the context of its projects. Such guidance will take into account that not all GEF projects involve gender aspects in equal measure, depending on the focal area and scope of the project.

- SPREP shall incorporate such guidance into their project and program proposals submitted to the Secretariat for review.

Output 3.1:    SPREP's Gender Mainstreaming Policy and Guideline

Activities:    Formulate SPREP's Gender Mainstreaming Policy and Guideline

In order to implement GEF-financed projects, SPREP will be required to establish either a policy or policies (this may include relevant laws, regulations, and guidelines), a strategy, or an action plan that requires SPREP to design and implement projects in such a way that both women and men (a) receive culturally compatible social and economic benefits; (b) do not suffer adverse effects during the development process; and that (c) fosters full respect for their dignity and human rights.

The policies, strategy, or action plan of SPREP comply with the minimum requirements listed in GEF policy GEF/PL/SD/0 paragraphs 13 – 19.

This project will allow SPREP to demonstrate sufficient institutional capability to develop and implement its policies, strategy, or action plan and apply the provisions of each to GEF financed projects.

3.1.1: Formulate SPREP's Gender Mainstreaming Policy that ensure proposed projects are gender sensitized.

Target: SPREP's Gender Mainstreaming Policy.

Target indicator: SPREP's Gender Mainstreaming Policy approved by SPREP senior

management team.

3.1.2:	Formulate guidelines for the administration of SPREP's Gender Mainstreaming Policy in compliance with the prescribed minimum requirements in the GEF/PL/SD/0 paragraphs 13 – 19.

Target: SPREP's Gender Mainstreaming Guideline.

Target indicator:	SPREP's Gender Mainstreaming Guideline approved by SPREP Senior

Management Team.

3.1.3:	Undertake training and transfer of knowledge activities for SPREP staff responsible for administering the Gender Mainstreaming Policy and Guideline.

Target: SPREP staff trained.

Target indicator:	Training undertaken for all relevant SPREP staff.

Target indicator: Regular training plans for Gender Mainstreaming Policy and Guideline

prepared.

Component 4:	Strengthening Information, Communication and Technology (ICT) Systems

Outcome 4:   SPREP's ICT upgraded to support a web-based project management and regional repository for lessons learned on project cycle implementation and management.

- The expected outcome under this component is the increased ability of SPREP to act as a regional repository and resource for lessons learned on project cycle implementation and management, in particular, the development, design and implementation of sustainable development projects throughout the Pacific region, followed by project monitoring and evaluation, and institutional requirements in SPREP and Member countries to enable optimal access and use of GEF resources in the region. Member countries will have access to knowledge of best practice across institutional policy and procedures, project monitoring and evaluation and in financial management processes. It will provide the basis for SPREP to eventually target assistance at the national level to facilitate national institutional accreditation as executing agencies.

- The proposed project strategy of building the capacity of SPREP at the regional level and then using this capacity to, in turn, strengthen the capacities of national institutions is highly cost-effective. The initial GEF investment will permit SPREP to achieve GEF Project Agency accreditation, which will allow it to subsequently assist countries directly in accessing and executing GEF funding. SPREP will build the capacities of national institutions in project design and implementation as a regular part of its assistance programme, but also particularly in the development of GEF project proposals and their ensuing implementation.

- SPREP will hire an IT specialist to work with its IT team. The IT specialist/expert will provide additional support to the existing SPREP IT team in developing appropriate systems for the web-based project management system. The SPREP IT team will lead the improvement works on its intranet to incorporate new features on its AWPID and setting up new features for external interface to be used by project officers/managers.

Output 4.1:    SPREP's Information, Communication and Technology Systems

Activities:    Strengthen SPREP's Information, Communication and Technology Systems

4.1.1:  Develop SPREP's web-based project management information system to include clear 	indicators for measuring its efficiency and effective use for analyzing staff performance over time.

Target: Improved performance of SPREP's Web-base Project Management Information System.

Target indicator: SPREP's Web-based Project Management Information System (PMIS)

Operating Online.

Target indicator: Project Progress and Financial Reports Generated from PMIS.

4.1.2:	Enhance the AWPID tool to be an online project management database. To incorporate a 	dashboard providing historical and current synopsis of projects, progress, financial status, 	reporting deadlines and alerts, and an executive management snapshot(etc).

Target: AWPID Upgraded and Operating Online.

Target indicator: Staff using Project Management Dashboard and Related Functions to Track 		 Progress and Assist with Decision Making.

4.1.3:    Re-build SPREP intranet structure incorporating an external interface to the various information 	systems and repositories required by staff and GEF funded project managers.

Target:  SPREP Intranet Upgraded with New Features for External Interface and 			Repositories for Lessons Learned from Project Cycle Implementation and Management.

Target indicator: Functionalities installed and use by staff of national partners and others

## C.3	Sustainability and Replicability

### C.3.a	Sustainability

- This project’s fundamental approach to sustainability is to create incentives for continued development and application of the fiduciary capacities developed by the project.  The project’s exit strategy is dependent on the continuation of particular commitments and activities without the need of long-term international financing.  These include:

- High-level political commitment to sustainable development by Pacific Leaders and SPREP's Governing Council;

- Successive SPREP Strategic Plans;

- On-going commitment and accountability for CROP inter-agency collaboration in decision-making and planning processes;

- Cost-effective and well-functioning coordination structure to deliver GEF support services within SPREP;

- Regular trainings for SPREP staff on accredited standards and application of updated systems, procedures, and mechanisms to maintain accredited performance;

- Long-term implementation of SID's Samoa Roadmap,

- On-going raising of public awareness on linkages of the global environment to national socio-economic development priorities; and

- Increasing the ownership of project benefits within SPREP and its 14 Pacific Island Countries eligible for GEF funding.

- The project has considered four key aspects of sustainability, which are institutional sustainability, financial sustainability, social sustainability, and environmental sustainability. Moreover, entrenched sustainability will be achieved through the 'learning by doing approach' which will ensure transfer of knowledge or the acquisition of new knowledge through experiential learning. These are described below in details.

- Institutional Sustainability: The project builds primarily upon existing institutional structure and mandates of SPREP and as per expressed policies of the SPREP Governing Council Meeting. This is expected to be sustainable as long as the Pacific Island Government's find it useful. Thus no extra investments are envisaged to maintain the institutional structures by SPREP post project completion. The capacity building of SPREP staff and others are expected to be institutionalized within the secretariat's training programme in addition to on-demand training for emerging needs as the year progresses. Securing the institutional sustainability of the project’s impacts will be promoted by developing the technical capacities at relevant levels such as finance, human resource, IT,  senior management team, and programme divisions. Capacity building is a major thrust of the project, so both short-term and long-term plans to strengthen technical expertise and capability for all involved, have been recommended.

- Financial Sustainability: The project will develop a very clear strategy and action plan for delivering the project activities during implementation as well as a long term plan for sustaining accredited capacity. Every step will be taken to identify resources that will sustain core development and maintenance of SPREP's fiduciary capacity. The financial sustainability of the project’s impacts will be further assured by the project’s focus to build SPREP's capacity to assist its member countries to access their GEF funding. This will naturally reinforce commitments to maintain and develops SPREP's capacity to function as an accredited GEF Project Agency by the member countries sitting in the SPREP's Governing Council Meeting. Future financial support sourced both within the secretariat and externally will be considered whenever possible.

- Social Sustainability: The capacity building activities, networking and continuous on the job training will help achieve social sustainability of the project. The build-up of trust between SPREP and its member countries will be addressed through long term capacity development triggered by the project and will ultimately assist in achieving this long-term objective. The strong focus on building on local knowledge, capacities and incentives and ensuring gender equity are expected to lead to social sustainability. The development of SPREP's Gender Mainstreaming Policy will also guide the equitable distribution and use of resources both within the secretariat but also in countries through development projects executed by SPREP.

- Environmental Sustainability: The primary purpose of this project is to achieve environmental sustainability in the Pacific Region. The environmental sustainability of the project’s impacts will be assured by the development of an environmental safeguard policy that will guide the operation of the secretariat and work in-country. This should flow naturally from SPREP's own mandate which seeks to promote cooperation in the Pacific Region and provide assistance in order to protect and improve its environment and to ensure sustainable development for present and future generations.

- Learning By Doing Approach: SPREP staff will attend specialized training for all new upgrades introduced by this MSP. Staff responsible for financial management, procurement, human resource management, IT, audit, legal for whistle blower protection and fraud, communication and outreach, project management, and evaluation will receive on-the-job training by consultants. Training modules and schedules will be developed including contingency planning for support services to continue for existing  GEF  funded projects such as PACC and PIGGAREP  so that work is not affected by staff having to undergo training. It is expected that these training will strengthen operational and technical support to all projects executed by SPREP and thus will have a positive impact on the overall support and delivery to existing and future GEF funded projects in SPREP.

C.3.b	Replicability and Lessons Learned

- The project has been designed to ensure that its actions can be widely replicated within any organization that is seeking GEF accreditation. The cost effectiveness, as well as institutional, social and environmental sustainability mentioned above are expected to contribute to the replication of the project's approaches. In addition, the project will develop a clear communication strategy to ensure that project activities, impacts and lessons learnt are recorded and disseminated widely among SPREP member countries who are eligible for GEF funding.

- An adaptive learning and knowledge management webpage will be introduced and built upon existing virtual mechanisms within SPREP's website. This will store lessons learned and best practices generated from the project including all other projects executed by SPREP and shall be accessible by the public. Furthermore, this project will also ensure that all lessons and best practices generated from every project executed by SPREP shall be incorporated into project designs of all future projects and programmes.

## C.4	Stakeholder Involvement

- The project was developed on the basis of consultations with SPREP member countries through the SPREP Governing Council Meeting held annually. This is the starting point of stakeholder consultation as the meeting itself provided comments from all 14 Pacific Island Countries eligible for GEF funding. The ensuing stages of developing the PIF was undertaken in consultation with Pacific GEF operational focal points. Countries were invited to endorse the PIF and SPREP received Palau's Letter of Endorsement first. The second consultative stage with Pacific Island Countries (GEF Operational Focal Points and Political Focal Points) was addressed through the development of the present project document benefitted from input solicited from UNDP, the Frankfurt School of Finance and Management, and SPREP staff. The letter of endorsement required from all 14 Pacific Island Countries eligible for GEF funding was sourced from the chair of the 22 SPREP Governing Council Meeting and accepted by the GEF.

- Taking an adaptive and collaborative management approach to execution, the project will ensure that key stakeholders are involved early and throughout project execution as partners for development.  This includes their participation in the Project Board, review of project outputs such as recommendations for amendments to policies, plans, programmes and legislation, as well as participation in monitoring activities.

- The background studies prepared as part of the development of the project included baseline assessment of SPREP’s institutional capacity to access multilateral funding directly by the Frankfurt School of Finance and Management. The assessment was broad in scope, covering an analysis of SPREP’s performance in both programme delivery and compliance with GEF Fiduciary Standards.  Evidently, this assessment links SPREP's capabilities with countries' ability to access funding to meet international obligation to the Rio Conventions. Additional analyses were undertaken internally to identify gaps on the current fiduciary capacity of SPREP along with a gender, environmental and social safeguard components.

- The first set of government stakeholders is the 14 ministries/departments of pacific island countries accessing GEF funding to which this project will assist their efforts. These are the national frontline for delivering future GEF projects that will come out of SPREP's accreditation application. The heads of these ministries and departments are also their respective countries' national GEF operational focal points. These include:

•	Cook Islands: National Environment Service

•	Federated States of Micronesia: Office of Environment and Emergency Management

•	Fiji: Department of Environment

•	Kiribati: Environment and Conservation Division

•	Marshall Islands: Office of Environmental Planning and Policy Coordination (OEPPC)

•	Nauru: Department of Commerce, Industry Environment

•	Niue: Department of Environment

•	Palau: Office of Environmental Response and Coordination (OERC)

•     Papua New Guinea: Department of Environment and Conservation

•     Samoa: Ministry of Natural Resource and Environment

•     Solomon Islands: Ministry of Environment, Climate Change, Disaster Management and

Meteorology

•     Tonga: Ministry of Lands, Environment, Climate Change & Natural Resources

•     Tuvalu: Department of Environment

•     Vanuatu: Department of Environmental Protection and Conservation

- In addition to the above, a key group of stakeholders that form the SPREP GEF Advisory Group shall also participate in the management of the project through oversight and advisory supervisions when the project is implemented. The group works within the secretariat to effectively coordinate and streamline GEF support services to its member countries and thus, shall act as an additional advisory organ to the project management unit.

- Every measure will be undertaken to share information about this project with member countries through other regional trainings and workshops that SPREP is involved in. Various networks that SPREP participates in and provides leadership roles such as the Asia Pacific Adaptation Network, Pacific Climate Change Roundtable Resource (Finance) Working Group, Pacific Invasive Learning Network, and the Pacific Island Roundtable for Nature Conservation and other relevant Networks.

C.5	Monitoring and Evaluation

- Project monitoring and evaluation will be conducted in accordance with established UNDP and GEF procedures.  The project team and the UNDP Multi-Country Office (UNDP-MCO) in Samoa will undertake monitoring and evaluation activities, with support from UNDP-GEF, including by independent evaluators in the case of the final evaluation.  The logical framework matrix in Annex 2provides a logical structure for monitoring project performance and delivery using SMART indicators during project implementation. The output budget and the work plan in the UNDP project document provide additional information for the allocation of funds, both the GEF and co-financing, for expected project deliverables and the timing of project activities to produce these deliverables. Annex 3 provides a breakdown of the total GEF budget by outcome, project management costs, and allocated disbursements on a per year basis.  A GEF tracking tool for CCCD will be used as part of monitoring and evaluation activities to assess project delivery.  The work plan is provisional, and is to be reviewed during the first project board and endorsed at the project initiation workshop.

- The following sections outline the principle components of monitoring and evaluation.  The project’s monitoring and evaluation approach will be discussed during the project’s initiation report so as to fine-tune indicators and means of verification, as well as an explanation and full definition of project staff M&E responsibilities.

- A project initiation workshop will be conducted within the first two (2) months with SPREP, UNDP-MCO, and with representation from the UNDP-GEF Regional Coordinating Unit as appropriate. A fundamental objective of this initiation workshop will be to further instill the understanding and ownership of the project’s goals and objectives among the project team at SPREP and UNDP.  The workshop also serves to finalize preparation of the project’s first annual work plan on the basis of the project’s log-frame matrix.  This will include reviewing the log frame (indicators, means of verification, assumptions), imparting additional detail as needed, and on the basis of this exercise, finalize the Annual Work Plan (AWP) with precise and measurable performance (process and output) indicators, and in a manner consistent with the expected outcomes for the project.

- Specifically, the project initiation workshop will: (i) introduce project staff to the UNDP-GEF expanded team that will support the project during its implementation, namely the MCO and responsible Project Management Unit (PMU) staff; (ii) detail the roles, support services and complementary responsibilities of UNDP-MCO and PMU staff with respect to the project team; (iii) provide a detailed overview of UNDP-GEF reporting and monitoring and evaluation (M&E) requirements, with particular emphasis on the combined Annual Project Reports - Project Implementation Reviews (APR/PIRs), Project Board (PB) meetings, as well as final evaluation.  The initiation workshop will also provide an opportunity to inform the project team on UNDP project-related budgetary planning, budget reviews, and mandatory budget re-phasing.

- The initiation workshop will provide an opportunity for all parties to understand their roles, functions, and responsibilities within the project’s decision-making structures, including reporting and communication lines, and conflict resolution mechanisms.  The Terms of Reference for PMU staff and associated decision-making structures will be discussed again, as needed, in order to clarify for all, each party’s responsibilities during the project’s implementation phase.

- The initiation workshop will also present a schedule of M&E-related meetings and reports.  The Project Manager in consultation with UNDP will develop this schedule, and will include: (i) tentative time frames for PB meetings, and the timing of near-term project activities, such as the in-depth review of literature on natural resource valuation; and (ii) project-related monitoring and evaluation activities.  The provisional work plan will be approved in the first meeting of the PB.

- Day-to-day monitoring of implementation progress will be the responsibility of the Project Manager based on the project’s Annual Work Plan and its indicators.  The Project Manager will inform the UNDP-MCO of any delays or difficulties faced during implementation so that the appropriate support or corrective measures can be adopted in a timely and remedial fashion.

- The Project Manager will fine-tune outcome and performance indicators in consultation with the full project team at the initiation workshop, with support from UNDP-MCO and assisted by the UNDP-GEF.  Specific targets for the first year implementation performance indicators, together with their means of verification, will be developed at the initiation workshop.  These will be used to assess whether implementation is proceeding at the intended pace and in the right direction and will form part of the Annual Work Plan.  Targets and indicators for subsequent years would be defined annually as part of the internal evaluation and planning processes undertaken by the Project Team, and agreed with the UNDP MCO, among other key project partners sitting on the PB.

- Periodic monitoring of implementation progress will be undertaken by the UNDP-MCO through the provision of quarterly reports from the Project Manager.  Furthermore, specific meetings may be scheduled between the PMU, the UNDP-CO and other pertinent stakeholders as deemed appropriate and relevant (particularly the PB members).  Such meetings will allow parties to take stock and to troubleshoot any problems pertaining to the project in a timely fashion to ensure smooth implementation of project activities.

- Annual Monitoring will occur through the Annual Project Board meeting.  This is the highest policy-level meeting of the parties directly involved in the implementation of a project.  The project will be subject to PB meetings at least twice per year.  The first such meeting will be held within the first 3 months following the initiation workshop.  For each year-end meeting of the PB, the Project Manager will prepare harmonized Annual Project Report / Project Implementation Reviews (APR/PIR) and submit it to UNDP-MCO, the UNDP-GEF Regional Coordination Unit, and all PB members at least two weeks prior to the meeting for review and comments.

- The APR/PIR will be used as one of the basic documents for discussions in the PB year-end meeting.  The Project Manager will present the APR/PIR to the PB members, highlighting policy issues and recommendations for the decision of the Committee participants.  The Project Manager will also inform the participants of any agreement(s) reached by stakeholders during the APR/PIR preparation, on how to resolve operational issues.  Separate reviews of each project output may also be conducted, as necessary.  Details regarding the requirements and conduct of the APR and PB meetings are contained with the M&E Information Kit available through UNDP-GEF.

- The terminal review meeting is held by the PB in the last month of project operations.  The Project Manager is responsible for preparing the terminal review report and submitting it to UNDP-MCO, the UNDP-GEF Regional Coordinating Unit, and all participants of the terminal review meeting.  The terminal review report will be drafted at least one month in advance of the terminal review meeting, in order to allow for timely review and to serve as the basis for discussion.  The terminal review report considers the implementation of the project as a whole, paying particular attention to whether the project has achieved its stated objectives and contributed to the broader environmental objective.  The report also decides whether any actions remain necessary, particularly in relation to the sustainability of project outputs and outcomes, and acts as a vehicle through that lessons learned can be captured to feed into other projects under implementation or formulation.  The terminal review meeting should refer to the independent final evaluation report, conclusions and recommendations as appropriate.

- The UNDP-MCO, in consultation with the UNDP-GEF Regional Coordinator and members of the PB, has the authority to suspend disbursement if project performance benchmarks are not met as per delivery rates, and qualitative assessments of achievements of outputs.

- A project inception report will be prepared immediately following the initiation workshop.  This report will include a detailed First Year Work Plan divided in quarterly time-frames as well as detailed activities and performance indicators that will guide project implementation (over the course of the first year).  This Work Plan will include the proposed dates for any visits and/or support missions from the UNDP-MCO, the UNDP-GEF Regional Coordinating Unit, or consultants, as well as time-frames for meetings of the project decision-making structures (e.g., PB).  The report will also include the detailed project budget for the first full year of implementation, prepared on the basis of the Annual Work Plan, and including any monitoring and evaluation requirements to effectively measure project performance during the targeted 12 months 'time-frame.

- The initiation report will include a more detailed narrative on the institutional roles, responsibilities, coordinating actions and feedback mechanisms of project related partners.  In addition, a section will be included on progress to date on project establishment and start-up activities and an update of any changed external conditions that may affect project implementation, including any unforeseen or newly arisen constraints.  When finalized, the report will be circulated to project counterparts who will be given a period of one calendar month in that to respond with comments or queries.

- Quarterly Progress Reports are short reports outlining the main updates in project performance, and are to be provided quarterly to the UNDP Multi-Country Office.  UNDP-MCO will provide guidelines for the preparation of these reports, which will be shared with the UNDP-GEF RCU:

- Progress made shall be monitored in the UNDP Enhanced Results Based Management Platform.

- Based on the initial risk analysis submitted, the risk log shall be regularly updated in ATLAS.  Risks become critical when the impact and probability are high.  Note that for UNDP GEF projects, all financial risks associated with financial instruments such as revolving funds, microfinance schemes, or capitalization of ESCOs are automatically classified as critical on the basis of their innovative nature (high impact and uncertainty due to no previous experience justifies classification as critical).

- Based on the information recorded in Atlas, a Project Progress Reports (PPR) can be generated in the Executive Snapshot.

- Other ATLAS logs can be used to monitor issues, lessons learned etc...  The use of these functions is a key indicator in the UNDP Executive Balanced Scorecard..

- The combined Annual Project Report (APR) and Project Implementation Review (PIR) is a UNDP requirement and part of UNDP’s  Multi-Country Office central oversight, monitoring and project management.  As a self-assessment report by project management to the Multi-Country Office, the APR/PIR is a key input to the year-end Project Board meetings.  The PIR is an annual monitoring process mandated by the GEF.  It has become an essential management and monitoring tool for project managers and offers the main vehicle for extracting lessons from on-going projects.  These two reporting requirements are very similar in input, purpose and timing that they have now been amalgamated into a single APR/PIR Report.

- An APR/PIR is to be prepared on an annual basis for the previous reporting period (30 June to 1 July), but well in advance (at least one month) in order to be considered at the PB meeting.  The purpose of the APR/PIR is to reflect progress achieved in meeting the project’s Annual Work Plan and assess performance of the project in contributing to intended outcomes through outputs and partnership work.  The APR/PIR is discussed by the PB, so that the resultant report represents a document that has been agreed upon by all of the key stakeholders.

- A standard format/template for the APR/PIR is provided by UNDP-GEF.  This includes, but not limited to, the following:

- Progress made toward project objective and project outcomes - each with indicators, baseline data and end-of-project targets (cumulative)

- Project outputs delivered per project outcome (annual).

- Lesson learned/good practice.

- AWP and other expenditure reports

- Risk and adaptive management

- ATLAS QPR

- Portfolio level indicators (i.e. GEF focal area tracking tools) are used by most focal areas on an annual basis as well.

- UNDP will analyze the individual APR/PIRs by focal area, theme and region for common issues/results and lessons.  The APR/PIRs are also valuable for the independent evaluators who can utilize them to identify any changes in project structure, indicators, work plan, etc., and view a past history of delivery and assessment.

- During the last three months of the project, the PMU will prepare the Project Terminal Report.  This comprehensive report will summarize all activities, achievements and outputs of the project, lessons learned, the extent to which objectives have been met, structures and mechanisms implemented, capacities developed, among others.  Together with the independent final evaluation, the project terminal report is one of two definitive statements of the project’s activities during its lifetime.  The project terminal report will also recommend further steps, if necessary, in order to ensure sustainability and reliability of the project outcomes and outputs.

- An independent final evaluation will take place three months prior to the terminal tripartite review meeting, and will focus on: a) the cost-effectiveness, efficiency and timeliness of project implementation and performance; b) highlight issues requiring decisions and actions; and c) present initial lessons learned about project design, implementation and management.  Findings of this evaluation will be incorporated as lessons learned, and recommendations for improvement addressed to ensure the institutional sustainability of project outputs, particular for the replication of project activities.  The final evaluation will also look at project outcomes and their sustainability.  The final evaluation should also provide recommendations for follow-up activities, as appropriate.  The terms of reference for the final evaluation will be prepared in consultation with UNDP-MCO based on guidance from the UNDP-GEF Regional Coordinating Unit.

- The Project Manager will provide the UNDP Resident Representative with certified periodic financial statements and an annual audit of the financial statements relating to the status of UNDP (including GEF) funds according to the established procedures set out in UNDP’s Programming and Finance manuals. The audit on project will be conducted according to UNDP financial regulations and rules and applicable audit policies.The audit will be conducted by the legally recognized auditor of UNDP Samoa.

- Learning and knowledge sharing will be enhanced through the dissemination of project results within and beyond the project intervention zone through existing information sharing networks and forums.  The project will identify and participate, as relevant and appropriate, in scientific, policy-based and/or any other networks, which may be of benefit to project implementation though lessons learned. The project will identify, analyze, and share lessons learned that might be beneficial in the design and implementation of similar future projects.  Finally, there will be a two-way flow of information between this project and other projects of a similar focus.

- Communications and visibility requirements: Full compliance is required with UNDP’s Branding Guidelines.  These can be accessed at http://intra.undp.org/coa/branding.shtml, and specific guidelines on UNDP logo use can be accessed at:http://intra.undp.org/branding/useOfLogo.html.  Amongst other things, these guidelines describe when and how the UNDP logo needs to be used, as well as how the logos of donors to UNDP projects needs to be used.  For the avoidance of any doubt, when logo use is required, the UNDP logo needs to be used alongside the GEF and SPREP logos.   The GEF logo can be accessed at: http://www.thegef.org/gef/GEF_logo. The UNDP logo can be accessed at: http://intra.undp.org/coa/branding.shtml.

- Full compliance is also required with the GEF’s Communication and Visibility Guidelines (the “GEF Guidelines”).  The GEF Guidelines can be accessed at:

http://www.thegef.org/gef/sites/thegef.org/files/documents/C.40.08_Branding_the_GEF%20final_0.pdf. Amongst other things, the GEF Guidelines describe when and how the GEF logo needs to be used in project publications, vehicles, supplies and other project equipment.  The GEF Guidelines also describe other GEF promotional requirements regarding press releases, press conferences, press visits, visits by Government officials, productions and other promotional items.  Where other agencies and project partners have provided support through co-financing, their branding policies and requirements should be similarly applied.

Table 5: Monitoring Workplan and Budget

| Type of M&E activity | Responsible Parties | Budget US$ Excluding project team staff time | Time frame |
| --- | --- | --- | --- |
| Initiation Workshop and Report | - Project Manager - Project Coordinator - Technical Advisor - UNDP CO, UNDP GEF | Indicative cost: 5,000 | Within first two months of project start up |
| Measurement of Means of Verification of project results. | - UNDP GEF RTA/Project Manager will oversee the hiring of specific studies and institutions, and delegate responsibilities to relevant team members. | To be finalized in the Initiation Workshop. | Start, mid and end of project (during evaluation cycle) and annually when required. |
| Measurement of Means of Verification for Project Progress on output and implementation | - Oversight by Project Manager - Project team | To be determined as part of the Annual Work Plan's preparation. | Annually prior to ARR/PIR and to the definition of annual work plans |
| ARR/PIR | - Project manager and team - UNDP MCO - UNDP GEF RCU | None | Annually |
| Periodic status/ progress reports | - Project manager and team | None | Quarterly |
| Mid-term Evaluation | - Project manager and team - UNDP MCO - UNDP GEF RCU - External Consultants (i.e. evaluation team) | Indicative cost : 10,000 | At the mid-point of project implementation. |
| Final Evaluation | - Project manager and team, - UNDP MCO - UNDP GEF RCU - External Consultants (i.e. evaluation team) | Indicative cost : 25,000 | At least three months before the end of project implementation |
| Project Terminal Report | - Project manager and team - UNDP MCO - local consultant | 0 | At least three months before the end of the project |
| Audit | - UNDPMCO - Project manager and team | Indicative cost per year: 10,000 | Yearly |
| Visits to field sites | - UNDP MCO - UNDP GEF RCU (as appropriate) - Government representatives | For GEF supported projects, paid from IA fees and operational budget | Yearly |
| TOTAL indicative COST Excluding project team staff time and UNDP staff and travel expenses |  | US$ 50,000 (+/- 5% of total budget) |  |

# D.	Financing

## D.1	Financing Plan

- The financing of this project will be provided by the GEF, with co-financing from SPREP.  The allocation of these two sources of finances is structured by the four main project outputs, as described in section C.2.a.3 above. The Total Budget and Work plan budget for the GEF contribution is provided below;

Total budget and workplan

| Award ID: | 00081135 | Project ID(s): | 00090570 |
| --- | --- | --- | --- |
| Award Title: | Country Name Project Title: Enhancing Capacity to Develop Global and Regional Environmental Projects in the Pacific. |  |  |
| Business Unit: | WSM10 |  |  |
| Project Title: | Country Name Project Title: Enhancing Capacity to Develop Global and Regional Environmental Projects in the Pacific. |  |  |
| PIMS no._______ | 5160 |  |  |
| Implementing Partner (Executing Agency) | Secretariat of the Pacific Regional Environment Programme (SPREP) |  |  |

| GEF Outcome/Atlas Activity | Responsible Party/ Implementing Agent | Fund ID | Donor Name | Atlas Budgetary Account Code | ATLAS Budget Description | Amount Year 1 (USD) | Total (USD) | Budget Note |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| OUTCOME 1: SPREP FUDICIARY CAPACITY ENHANCED | UNDP | 62000 | GEF | 71200 | International Consultants | $350,000 | $350,000 | International specialist/experts to strengthen policies, procedures and tools for SPREP's internal control framework, code of ethics, evaluation functions, whistle-blowing, project management guidelines, procurement, financial disclosure, and audit (internal and external). |
|  |  |  |  | 71300 | Local Consultants | $150,000 | $150,000 | Local fiduciary consultants to help programs and strengthening plans - transferring of knowledge to in-country consultants for availability of services locally. Also paid for the remaining balance of salaries for the local project coordinator and technical coordinator performing technical support to the project. |
|  |  |  |  | 71400 | Contractual services - Individuals | $217,430 | $217,430 | Consultants fees/services for fiduciary stocktaking of fiduciary capacity practices and capacity building. include finance service of a consultant for a period of one year. |
|  |  |  |  |  | sub-total GEF | $717,430 | $717,430 |  |
|  |  | 001880 | SPREP | 74100 | Professional Services | $94,866 | $94,866 | Annual Operational Costs for the Internal Auditor plus 70% of staff time ($71,834) dedicated to supporting the evaluation outputs of this project. Also include 20% of staff time from SPREP legal adviser to support ethics, whistle-blowing outputs of this project and other policy work that will need legal guidance. |
|  |  |  |  |  | sub-total SPREP | $94,866 | $94,866 |  |
|  |  |  |  |  | Total Outcome 1 | $812,296 | $ 812,296 |  |
| OUTCOME 2: ENV & SOCIAL SAFEGUARD POLICY & GUIDLEINES DEVELOPED | UNDP | 62000 | GEF | 71200 | International Consultants | $50,000 | $50,000 | International specialist to develop SPREP's organizational policy on environmental and social safeguards including training of SPREP staff on the application (implementation and M &E) of this policies. |
|  |  |  |  |  | sub-total GEF | $50,000 | $50,000 |  |
|  |  | 001880 | SPREP | 74100 | Professional Services | $36,062 | $36,062 | 20 percent technical and policy support provided by the SPREP Planning and Capacity Development Adviser and the Environment Planning Officer to the international consultant. |
|  |  |  |  |  | sub-total SPREP | $ 36,062 | $36,062 |  |
|  |  |  |  |  | Total Outcome 2 | $86,062 | $86,062 |  |
| outcome 3: GENDER MAINSTREAMING POLICY & GUIDELINES DEVELOPED | UNDP | 62000 | GEF | 71200 | International Consultants | $50,000 | $50,000 | International specialist to develop SPREP's organizational policy on gender mainstreaming including training of SPREP staff on the application (implementation and M &E) of this policy. |
|  |  |  |  |  | sub-total GEF | $50,000 | $50,000 |  |
|  |  |  |  |  | Total Outcome 3 | $50,000 | $50,000 |  |
| OUTCOME 4: IFORMATION, COMMUNICATION, TECHNOLOGY SYSTEMS EHANCED | UNDP | 62000 | GEF | 71200 | International Consultants | $50,000 | $50,000 | International IT specialist to provide technical (web-based) expertise for upgrading SPREP web-based project management information system, financial management information system, and human resource information system. |
|  |  |  |  | 71400 | Contractual services - Individuals | $50,000 | $50,000 | Local consultant to help with backstopping and strengthening program. Local IT service provider will be recruited to assist with transfer of knowledge. Important to source local IT providers who can offer trouble shooting assistance. |
|  |  |  |  |  | sub-total GEF | $100,000 | $100,000 |  |
|  |  | 001880 | SPREP | 71400 | Contractual services - Individuals | $1,094,466 | $1,094,466 | Total $ from combining budgets for Annual Operational Costs for SPREP's Financial Management Information Systems ($663,465); Annual Operational Costs for Administering Procurements ($84,623); and the Annual Operational Costs for SPREP's Human Resource Information System ($346,378). |
|  |  |  |  | 74100 | Professional Services | $80,000 | $80,000 | Annual IT Software licences fees |
|  |  |  |  |  | sub-total SPREP | $ 1,174,466 | $1,174,466 |  |
|  |  |  |  |  | Total Outcome 4 | $1,274,466 | $1,274,466 |  |
| Project management unit | UNDP |  |  | 71200 | International Consultant | $11,000 | $11,000 | Payment costs for an independent evaluator for both the mid-term and terminal evaluation. |
|  |  | 62000 | GEF | 71300 | Local Consultants | $21,570 | $21,570 | Salary for a local project coordinator ($36,285) and the technical adviser ($13,285) will be primarily source din this budget-line for carrying out project management functions only. Technical functions of both posts will be paid out of components 1-3 depending of the role(s) carried out by the local project coordinator and the technical adviser. |
|  |  |  |  | 71600 | Travel | $15,000 | $15,000 | Supporting travel for the independent evaluator. Also payment made for 2 country representatives to attend project board meetings. |
|  |  |  |  | 74599 | UNDP cost recovery charges- Bills | $25,000 | $25,000 | Direct Project Costs (DPC) are costs that are incurred by UNDP for the delivery of project inputs. These execution-related costs are completely separate and distinct from General Management Support (GMS) costs that are incurred by UNDP regardless of the implementation modality chosen for the project. The Letter of Agreement (LoA) specifies the support services that would be considered as DPCs. |
|  |  |  |  | 74100 | Professional Services (Audit Fee) | $10,000 | $10,000 | Payment costs for the audit, considering an estimated budget based on audit quotations of other similar projects with SPREP, UNDP and GEF. |
|  |  |  |  |  | sub-total GEF | $82,570 | $82,570 |  |
|  |  | 001880 | SPREP | 71400 | Contractual Services - Individuals | $361,241 | $ 361,241 | 20 percent of 14 SPREP professional staff providing management, technical and policy support to the project. These include Director General, Deputy Director General, Director of Environment Monitoring and Governance Division, Finance and Administration Adviser, Procurement Officer, Human Resources Adviser, GEF Support Adviser, Executive Officer, Biodiversity Officer, Invasive Species Adviser, IT Manager, Solid Waste Management Adviser, Internal Auditor and Legal Adviser. |
|  |  |  |  | 72100 | Contractual Services - Companies | $147,868.60 | $147,867.60 | Includes 6 months of electricity bill worth $60,000 plus Office space for the PMU and SPREP staff who are supporting this project (include water, furniture, administration support etc) totalling $87,939.60. |
|  |  |  |  |  | sub-total SPREP | $ 509,108.6 | $509,108.60 |  |
|  |  |  |  |  | Total Management | $591,678.60 | $591,678.60 |  |
|  |  |  |  | PROJECT TOTAL |  | $2,814,502.60 | $2,814,502.60 |  |

| Summary of Funds: |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  |  |  | Amount Year 1 |  | Total |
|  |  |  |  |  |  | GEF |  |  | $1,000,000 |  | $1,000,000 |
|  |  |  |  |  |  | Donor 2 - In Kind (SPREP) |  |  | $1,814,502.60 |  | $1,814,502.60 |
|  |  |  |  |  |  | Donor 3 – In-kind (UNDP) |  |  | $100,000.00 |  | $100,000.00 |
|  |  |  |  |  |  | TOTAL |  |  | $2,914,502.60 |  | $2,914,502.60 |

h

- Direct project costs (DPC) are costs that are incurred by UNDP that are execution-driven and are incurred for, and can be traced in full to, the delivery of project inputs.  These execution-related costs are completely separate and distinct from General Management Support (GMS) costs that are incurred by UNDP regardless of the implementation/execution modality chosen for the project and that are distributed to UNDP from the 9.5% GEF implementation fee.  The DPCs will be used to reimburse the UNDP Multi-Country Office for supporting national project implementation through, for example, the recruitment of an independent evaluator for a mid-term evaluation or/and terminal evaluation.  Over the period of planned project implementation, this cost is estimated at US$ 25,000 although the actual or transacted costs will be fully reimbursed as part of the standard UNDP financial management procedures. SPREP will request UNDP to provide service procurement for the independent evaluator only and this will be charged to the Project Management Budget.  The letter of agreement between UNDP and SPREP for providing Direct Project Services with the estimation of anticipated cost and identification of type of service and method of reimbursement is included as Annex 7.

- An internationally recruited consultant will be contracted to undertake the independent final evaluation towards the end of the project.  The travel budget includes the costs of DSA, TE and return airfare for the international consultant.  The travel budget also includes financing for to cover the cost of local consultant travel to the regions where they will be facilitating the negotiations and drafting of sectoral policy, programmes, plans, or legislation. Arrangements for the full recovery of DPCs will be provided upon the request of and in agreement between UNDP as the implementing partner and the SPREP.

- No UNDP Implementing Agency Project cycle management services are being charged to the Project Budget. All such costs are being charged to the IA fee.

- A menu of international specialists/experts will be recruited to provide technical services and policyformulation support on an as needed basis over the course of project implementation to ensure high quality interventions.This includes technical backstopping on the project’s work to strengthen SPREP's fiduciary capacity as well as supporting the development of key organizational policies, procedures, tools and mechanism required to establish an environmental and social safeguar policy and a gender mainstreaming policy.

Table 8:  Consultants for technical assistance components (estimated for entire project)

| Consultants | Estimated Staff weeks | GEF ($) | Co-Financing ($) | Project Total ($) |
| --- | --- | --- | --- | --- |
| Finance Specialist/Expert | 6.0 | 50,000 | 13,500 | 63,500 |
| Management and Procurement Specialist/Expert | 6.0 | 50,000 | 13,500 | 63,500 |
| Ethics Specialist/Experts | 6.0 | 50,000 | 13,500 | 63,500 |
| Audit Specialists/Expert | 6.0 | 50,000 | 27,000 | 77,000 |
| Project Management Specialist/Expert | 6.0 | 50,000 | 30,000 | 80,000 |
| Environmental Specialist/Expert | 6.0 | 50,000 | 13,500 | 63,000 |
| Social Scientist | 6.0 | 50,000 | 13,500 | 63,500 |
| Gender Specialist/Expert | 6.0 | 50,000 | 13,500 | 63,500 |
| IT &Network Specialist/Expert | 6.0 | 50,000 | 13,500 | 63,500 |
| Total | 54 | 450,000 | 242,500 | 692,500 |

## D.2	Cost Effectiveness

- The financing of this project is inherently cost-effective through its design.  The financing of this project is also cost-effective in that the GEF contribution has leveraged almost twice the amount of resources from SPREP as co-financing.

## D.3	Co-financing

- The co-financing to this project is estimated at US$ 1,914,502.60. These funds are divided as both cash contribution and in-kind.  Cash injections are provided by the Commonwealth Government of Australia's Aid programme (formerly known as AusAID) in the amount of USD 180,000 including an additional USD 150,000 from the People's Republic of China's Government. Total cash contributions is USD 330,000.This will be combined together with SPREP's in-kind contribution of USD 1,484,502.60 plus UNDP’s in kind contribution of UD 100,000 and bringing the total co-financing package to USD 1,914,502.60. While most of the project’s co-financing is in-kind, these funds represent real funds that are paid to SPREP staff or contracted consultants that will help execute project activities. It should be mentioned in the first instance that the current co-financing ratio is near (GEF) 1:2 with SPREP providing significantly more resources through key staff support and operational costs in addition to corporate upgrades of existing systems for finance and HR. Annex 9 depicts SPREP's co-finance letter and breakdown of parallel costing to supplement the MSP funds.

- The Australian cash contribution is provided as starting capital (USD 80,000) for upgrades on the existing Human Resource Information System that runs the payroll and managing contractual obligations between the organization and its staff. Additionally, these funds (USD 100,000) plus the (USD 150,000) cash contribution from the Chinese Government will be channeled to support upgrading works for the existing Financial Management Information System which will be a vital component of this MSP in-order to meet GEF fiduciary standards.

Table 10:  Co-financing Sources

| Name of Co-financier | Classification | Amount(US$) |
| --- | --- | --- |
| Secretariat of the Pacific Environment Programme | Regional Inter-Governmental Agency | $1,814,502.60 USD |
| UNDP |  | $100,000.00 USD |
| Total Co-financing |  | $1,914,502.60 USD |

# E.	Institutional Coordination and Support

## E.1	Core Commitments and Linkages

### E.1.a	Linkages to other activities and programmes

- A few programmes and projects under implementation sets the baseline capacity for which this project will build on. This includes improvements undertaken for various operating systems in finance and HR.  These improvements will provide the springboard and entry points for synergies to take place. The overall goal for this is to implement a new Financial Management Information System (FMIS) solution that allows for more effective and efficient financial management; improved business processes through automation (reduce greatly paperwork to support  SPREP's mandate of protecting the environment) introduce  a new integrated business solution at SPREP that streamlines business processes and enables users to operate more effectively. The project's capacity building outputs aimed at strengthening SPREP's overall fiduciary capacity will be complemented through FMIS by establishing viable platforms for synergies. The project will enhance and expand on the FMIS success to match what is expected from SPREP to achieve GEF minimum fiduciary standards.

- SPREP engaged the Frankfurt School of Finance and Management to perform a baseline assessment of SPREP’s institutional capacity to access multilateral funding directly.  The assessment was broad in scope, covering an analysis of SPREP’s performance in both programme delivery and compliance with GEF Fiduciary Standards. It noted that while some aspects of SPREP’s organizational practices were in compliance with the various GEF standards and requirements, there were areas in which improvement was needed. In particular, the report identified compliance with the GEF’s fiduciary standards and its project development, monitoring and evaluation capacities as key areas in which SPREP, and the region as a whole, require strengthening.

- Taken together, this study together with gap analysis exercises undertaken by the SPREP GEF Advisory Group provides the baseline and justification for the proposed project. Both outline institutional functions in need of further development in order to comply with the requirements for direct access to GEF financing, in particular. The project is structured to coherently consider the institutional conditions at SPREP and its ability to meet Pacific Island Countries needs and requirements, and thereby address institutional policy development to meet the GEF Project Agency criteria.

- SPREP's Performance Monitoring and Evaluation Reporting System (PMERs). The Annual Work Programme implementation database system records events/activities carried out by staff and links projects results to SPREP's Annual Work Plan software called AWPID. These activities are recorded against established indicators in the Annual Work Plan. A report by projects can then be extracted from the information captured which has been used for the PMER. We also have the MOU/LOA database system which captures information on MOU's, critical dates for reporting, lessons learnt etc. SPREP is planning activities to re-develop/enhance the AWPID to be an online project management database similar to UNDP's ATLAS project management dashboard and reporting tools. The project will build on this work in-order to incorporate a project management dashboard that provides current snapshot on projects' summary, progress, financial status, reporting deadlines and alerts, etc.

- SPREP will be rolling out it's  strengthening IT support by specifically aiming to rebuild SPREP intranet structure to incorporate the following 2 components: external interface to the various information systems and repositories required by staff; and incorporating Project Manager functions online. This will address concerns raised in the Value-Added Review around the issue of Network and Contacts which improvements to IT services will be needed.

## E.2	Management Arrangements

- UNDP, as the responsible party for this project, with the UNDP Multi-Country Office in Samoa responsible for transparent practices, appropriate conduct and professional auditing. The Implementing Partner is the Secretariat of the Pacific Regional Environment Programme (SPREP), which will assign a Project Director (PD) and provide its staff and network of experts as support to Project Management Unit (as part of co-financing).

- This project will be implemented under the agreement reached by the GEF Council, the GEF Secretariat, UNDP and SPREP. The project aims to support to capacity development of 14 Pacific Island Countries eligible for GEF funding to access MEA resources in-order to meet their international obligations under the Rio Conventions. It does this through strengthening SPREP's capacity to obtain GEF accreditation and thus allowing these countries to expedite access to GEF funds. SPREP is an extension of national ministries/departments of environment and thereby is considered as part of national capacities of these 14 Pacific Island Countries.

- Figure 3:  Project execution

Project Board:  This Board is specifically established by the project to provide management oversight of project activities and is to be chaired by the Director General of SPREP.  The Board will review progress and evaluation reports, and approve programmatic modifications to project execution, as appropriate and in accordance to UNDP procedures.  The Project Board will meet regularly and as deemed necessary for important decisions to be made. The composition of the PB is as follows:

The Director General of SPREP assumes the Executive role, which will reinforce senior

local ownership over the project;

The Senior Supplier role will be represented by 2 offices:

o UNDP, as the body which provides guidance regarding the technical feasibility and substantive focus of the Project and is responsible for supporting operational aspects of implementation and quality assurance of the project;

o Deputy Director General of SPREP as the Project Manager;

The Senior Beneficiary on the Board is responsible for providing advice on the realization of project benefits from the perspective of project beneficiaries. This role will be assumed by three representatives of the 14 Pacific Island Countries, as follow:

o Chief Executive Officer for the Ministry of Natural Resource and Environment for Samoa  (representing the Polynesian Sub-Region);

o  Permanent Secretary of the Ministry of Local Government, Urban Development, Housing and Environment for Fiji (representing the Melanesian Sub-Region); and

o  Permanent Secretary of the Ministry Commerce, Industry and Environment (representing the Micronesia Sub-Region);

- The 14 Pacific Island Countries are Senior Beneficiaries of the project on the basis that the project will be strengthening and integrating their access to funds in-order to meet obligations under the Rio Convention. The region will be represented by 3 members from each sub-region: Polynesia (Ministry of Natural Resource and Environment from Samoa), Melanesia (Ministry of Local Government, Urban Development, Housing and Environment from Fiji), and Micronesia (Ministry Commerce, Industry and Environment from Nauru). The rationale for selecting these 3 countries are based on both political, practical and costs premises. Samoa's inclusion will not involve any travel costs while Fiji's inclusion is based on its regional hub status and a relatively low cost for funding its participation in meetings either (most probably) in Samoa or Fiji. Nauru is the current chair of the SPREP Governing Council Meeting 2013 and is extended the courtesy first to represent the Micronesia sub-region. Ultimately, all GEF projects channeled through SPREP will work to deepen integration of the Rio Conventions' provisions into national sectoral policies, legislation, policies and plans and institutional mandates.  UNDP will be the Senior Supplier, providing technical guidance and support for the cost-effective procurement and implementation of project services and activities, including project implementation oversight through regular monitoring and reporting.

- Project Director:  The Director General of SPREP will be designated at the Project Director (PD), and will be responsible for management oversight of the project.  The PD will devote a significant part of his working time on the project.  Duties and responsibilities of the PD are described in Annex 8.  In the fulfillment of his responsibilities, the PD will be supported by the Project Board and a full-time Project Manager (PM).

- Project Management Unit:  SPREP will establish a Project Management Unit (PMU) for the day-to-day management of project activities and subcontract specific components of the project to specialized consultants.  The PMU will be administered by a full-time Project Manager (NPM) and supported by a the SPREP GEF Advisory Group and other key staff from finance, IT, and human resource.

- International Consultants:  The project will contract a number of specialists and/or experts as consultants to undertake the analysis and development of key organizational policies, procedures, tools and mechanism arising from having to upgrade in-order to meet GEF minimum accredited standards. These consultants will be experts in all IT, human resources, audit, evaluation, ethics, gender, social and environmental safeguards, procurement among other things.

- Capacity Development Activities:  The project will take an adaptive collaborative management (ACM) approach to implementation.  That is, UNDP and SPREP will manage project activities in order that stakeholders are involved early and throughout project implementation, providing regular input of the performance of project activities.  This will help signal unforeseen risks and contribute to the timely modification and realignment of activities within the boundaries of the project's goal and objectives.

- SPREP GEF Advisory Group:  A working group comprised of SPREP technical officers with experience and knowledge on the GEF will act as an additional organ advising the PMU throughout the implementation of the project and may play an internal quality assurance function in-order to comply with UNDP and GEF programmatic rules and policies. The group will also work with other key SPREP staff in finance, HR and IT to deliver all 4 components  of the project. The Group is chaired by the Director of the Environmental Monitoring and Governance Divisions with representatives from the Climate Change Divisions, Waste Management and Pollution Control Divisions, and the Biodiversity and Ecosystem Management Divisions.

- Stakeholder Consultations:  The consultation programme for the project will target audiences such as SPREP staff, UNDP MCO Samoa, UNDP GEF RCU, and Pacific Island Countries. Countries will receive updates through various SPREP networks including workshops and trainings around the Pacific Region.  Key inputs will be sourced from UNDP in the implementation stages of the project while updates shall form the basis for communicating with SPREP member countries.

# F.	Legal Context

This project forms part of an overall programmatic framework under which several separate associated country level activities will be implemented. When assistance and support services are provided from this Project to the associated country level activities, this document shall be the “Project Document” instrument referred to in: (i) the respective signed SBAAs for the specific countries; or (ii) in the Supplemental Provisions attached to the Project Document in cases where the recipient country has not signed an SBAA with UNDP, attached hereto and forming an integral part hereof.

This project will be implemented by the agency (name of agency) (“Implementing Partner”) in accordance with its financial regulations, rules, practices and procedures only to the extent that they do not contravene the principles of the Financial Regulations and Rules of UNDP. Where the financial governance of an Implementing Partner does not provide the required guidance to ensure best value for money, fairness, integrity, transparency, and effective international competition, the financial governance of UNDP shall apply.

The responsibility for the safety and security of the Implementing Partner and its personnel and property, and of UNDP’s property in the Implementing Partner’s custody, rests with the Implementing Partner. The Implementing Partner shall: (a) put in place an appropriate security plan and maintain the security plan, taking into account the security situation in the country where the project is being carried; (b) assume all risks and liabilities related to the Implementing Partner’s security, and the full implementation of the security plan. UNDP reserves the right to verify whether such a plan is in place, and to suggest modifications to the plan when necessary. Failure to maintain and implement an appropriate security plan as required hereunder shall be deemed a breach of this agreement.

The Implementing Partner agrees to undertake all reasonable efforts to ensure that none of the UNDP funds received pursuant to the Project Document are used to provide support to individuals or entities associated with terrorism and that the recipients of any amounts provided by UNDP hereunder do not appear on the list maintained by the Security Council Committee established pursuant to resolution 1267 (1999). The list can be accessed via http://www.un.org/Docs/sc/committees/1267/1267ListEng.htm. This provision must be included in all sub-contracts or sub-agreements entered into under this Project Document.

# PART II:	ANNEXES

Annex 1: SPREP Agreement

Annex 2:Logical Framework

Annex 3:Outcome Budget (GEF Contribution and Co-financing)

Annex 4:Provisional Work Plan

Annex 5: UNDP Risk Log

Annex 6:Terms of References

Annex 7:Letter of Agreement for the recovery of Direct Project Costs

Annex 8: SPREP Chair's Letter of Endorsement for MSP

Annex 9: SPREP's Letter of Co-Finance

Annex 10: Environmental and Social Screening Summary

## Annex 1:	TREATY TO ESTABLISH SPREP

Provided as a separate document to this project document. Marked clearly as TREATY.

## Annex 2:	Logical Framework

| Project Strategy | Objectively verifiable indicators |  |  | Sources of verification | Risks and Assumptions |
| --- | --- | --- | --- | --- | --- |
|  | Indicator | Baseline value | Target value and date |  |  |
| Long-term goal: To enable SPREP to support 14 Pacific Island Countries to more effectively achieve global environmental benefits by strengthening their key institutional and individual capacities. |  |  |  |  |  |
| Project objectives: A. To strengthen SPREP's capacity to assist Pacific Island Countries' implementation of the three Rio Conventions. B. To enable pacific island countries to expedite access to GEF resources through SPREP. | Outcome indicators: - Number of Pacific Island countries enabled to implement the three Rio Conventions - Extent to which SPREP’s policies, procedures &core functions pertaining direct access to GEF resources (including fiduciary capacity, social & environmental safeguard policy, gender mainstreaming…)have been met. - Number of Pacific Island countries strengthened their relevant Government functions that expedite access to GEF resources through SPREP | - SPREP’s fiduciary capacity is limited, and its policies and procedures are not aligned to GEF’s social (including gender mainstreaming)& environmental safeguard - All Pacific island countries are slow in accessing MEAs funding. | By the end of the project: - 14 Pacific countries successfully implemented the three Rio Conventions - SPREP accredited as a GEF Project Agency by the end of the project. - All of the 14 Pacific island countries will have fast track access to MEA funding such as the GEF. | - Meeting Minutes - Working Group meeting reports - UNDP quarterly progress reports - Independent mid-term and final evaluation reports - Social and environmental policy. - Gender mainstreaming policy. - GEF Cross-Cutting Capacity Development Scorecard - SPREP Stage II application. - Implementation of 14 Pacific Countries NCSA Action Plans and other GEF Projects. | - Pacific island government's and the GEF maintain deep commitment to SPREP's accreditation application. - The project will be executed in a transparent, holistic, adaptive, and collaborative manner - Policy and institutional reforms and modifications recommended by the project are correct and match GEF's minimum accreditation standards. |
| Project Strategy | Objectively verifiable indicators |  |  | Sources of verification | Risks and Assumptions |
|  | Indicator | Baseline value | Target value and date |  |  |

| Outcome 1: MEA funding access fast tracked. |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Output 1.1 Stage I &II application for GEF accreditation completed and submitted. | - Status of accreditation of Stage II applications | - SPREP Stage I application submitted, while stage II has not been submitted yet. - Stage I Value-Added Review noted 3 areas need strengthening: (1) Demonstration of Environmental or Climate Change Adaptation Results; (2) Institutional Efficiency; and (3) Network and Contacts. | - Stage II applications finalized and received by the GEF Secretariat by 31 December 2014. | - Final Stage II application form. - GEF Secretariat acknowledgement of receipt. | - GEF Council maintains support to SPREP's application. - The MSP is not completed in time the accreditation deadline expires by the 31st December 2014. Assume that the GEF Council will approve a second or third round of accreditation. - New Policies introduced through this project will need time to be tested and reported back to the GEF; Stage II application will be affected from the lack of evidence to testify the success of new policies that would meet GEF minimum accredited standards. |

| Outcome 2: SPREP Fiduciary Capacity strengthened and met GEF’s accreditation standards |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Project Strategy | Objectively verifiable indicators |  |  | Sources of verification | Risks and Assumptions |
|  | Indicator | Baseline value | Target value and date |  |  |
| Output 2.1: SPREP’s financial management/controls (including external audit function) strengthened and become adequate/in compliance with financial regulation & procedures. | - Appointment/contracting an External Auditor firm . - Financial control mechanisms/types of audit - Number of external audits of audits financial control | - Existing SPREP Independent Audit Committee. - Audit committee to oversee management of issues raised by the internal auditor. - Limited SPREP fiduciary capacity. - EU audit in 2008, 2011, and end of 2014. | - Adequate financial control (including external audit) in place and operational External Audit Firms recruited biennial under the financial regulations | - External auditor ToR - Meeting minutes - Tracking and progress reports - Audit Reports - SPREP Governing Council Meeting approval of external auditor reports. | - Independent external auditor has always been recruited annual and audit opinion reports are submitted to the SPREP Governing Council Meeting for discussions and approval. - Management response and action plans for every audit are channeled through the independent audit committee consisting of Non-SPREP staff. - New Policies introduced through this project will need time to be tested and reported back to the GEF; Stage II application will be affected from the lack of evidence to testify the success of new policies that would meet GEF minimum accredited standards. |
| Project Strategy | Objectively verifiable indicators |  |  | Sources of verification | Risks and Assumptions |
|  | Indicator | Baseline value | Target value and date |  |  |
| Output 2.2: Financial Management and Control Frameworks strengthened and meet GEF’s accreditation standards. | - Extent to which SPREP has functioning internal control framework - Extent to which Roles and responsibilities pertaining to accountability of fiscal agents and fiduciary trustees are functioning at SPREP. - Availability of procedures for identifying internal controls and assessing control details annually for core financing management. - Incompatible duties segregated. | - Limited internal control framework. SPREP Financial Regulations. - Procurement Manual. - Financial Manual of Procedures. - Travel Policy. | - SPREP's internal control framework and procedures are revised/developed and meet GEF Minimum accreditation standards. - Strong ICF achieved through the efficient and effective use of resources; the safeguard of assets; the reliability of financial and other information, the compliance with regulations, rules and established policies; the effectiveness of risk management; and the adequacy of organizational structures, systems and processes. | - SPREP Internal Control Framework Approved. - Meeting minutes - Tracking and progress reports | - Internal control frameworks will consolidate all of SPREP's operational and management procedures and policies including upgrades where necessary to meet GEF minimum accredited standards. - New Policies introduced through this project will need time to be tested and reported back to the GEF; Stage II application will be affected from the lack of evidence to testify the success of new policies that would meet GEF minimum accredited standards. |
| Project Strategy | Objectively verifiable indicators |  |  | Sources of verification | Risks and Assumptions |
|  | Indicator | Baseline value | Target value and date |  |  |
| Output 2.3: SPREP's Financial Disclosure Capacity strengthened and met international Financial Reporting Standards. | - Availability of Policy and procedures for financial disclosure. - Extent to which SPREP’s financial reporting meets international standards | - Financial disclosure policy not available. SPREP’s financial reporting does not meet international standards or not compliant to World Bank. | - SPREP's Financial Disclosure Policy and Procedures Approved. - Procedures for financial disclosure in place and operational. - Financial reporting meets international standards (is World Bank compliant) | - SPREP's internal control framework documented. - SPREP's Financial Disclosure Policy. Financial Disclosure Procedures documented and practiced. | - New Policies introduced through this project will need time to be tested and reported back to the GEF; Stage II application will be affected from the lack of evidence to testify the success of new policies that would meet GEF minimum accredited standards. |
| Project Strategy | Objectively verifiable indicators |  |  | Sources of verification | Risks and Assumptions |
|  | Indicator | Baseline value | Target value and date |  |  |
| Output 2.4: Strengthens SPREP's Code of Ethics. | - Status of documentation and functionality of SPREP's internal control framework addressing ethics. - Approval and application status SPREP's Code of Ethics . - Availability of Procedures for administering the Code of Ethics . | - Internal Control Framework not documented. - SPREP's Code of Conduct and Organizational Value Pamphlet. - SPREP Staff Regulations Booklet. | - Internal control framework that includes ethics available and functional - SPREP's Code of Ethics approved and applied. - Procedures for administering the Code of Ethics prepared and applied | - SPREP's internal control framework documented. | - Current Code of Ethics are appropriate but may need revision to meet GEF minimum accredited standards. - New Policies introduced through this project will need time to be tested and reported back to the GEF; Stage II application will be affected from the lack of evidence to testify the success of new policies that would meet GEF minimum accredited standards. |
| Project Strategy | Objectively verifiable indicators |  |  | Sources of verification | Risks and Assumptions |
|  | Indicator | Baseline value | Target value and date |  |  |
| Output 2.5: Strengthens SPREP's internal audit functions. | - SPREP's internal control framework documented. - IIA standards applied. - Terms of Reference revised. - Audit Plan | - Internal Auditor post established and filled since 2011. - Terms of Reference. - Independent Audit Committee. | - Revised Terms of Reference - IIA compliance. | - SPREP's internal control framework. - Revised Terms of Reference. - Audit Plan. - Meeting Minutes | - Current Terms of Reference may need revisions to meet GEF minimum accredited standards. - New Policies introduced through this project will need time to be tested and reported back to the GEF; Stage II application will be affected from the lack of evidence to testify the success of new policies that would meet GEF minimum accredited standards. |
| Project Strategy | Objectively verifiable indicators |  |  | Sources of verification | Risks and Assumptions |
|  | Indicator | Baseline value | Target value and date |  |  |
| Output 2.6: Strengthens SPREP Project Management through Results Based Management. | - Extent which SPREP's Project and activity appraisal process fulfils GEF guideline. - SPREP's Project Management Guideline in place. - SPREP's Risk Management Plan in place. - SPREP's Environmental and Social Safeguard Policy and Procedures in place. - SPREP's Gender Mainstreaming Policy and Procedures in place. - SPREP's Monitoring and Evaluation Policy and Guidelines in place. - Enterprise Risk Management Framework adopted in SPREP. | - No SPREP Project Management Guidelines. | - SPREP's Project Management Guideline. - SPREP Risk Management Plan. - SPREP's Environmental and Social Safeguard Policy. - SPREP's Gender Mainstreaming Policy. - Enterprise Risk Management | - SPREP's internal control framework. - SPREP's project appraisal process. - SPREP's Project Management Guideline. - SPREP's Risk Management Plan. - SPREP's Environmental Social Safeguard Policy and Procedures. - SPREP's Gender Mainstreaming and Procedures. - SPREP's Monitoring and Evaluation Policy and Guidelines. - Enterprise Risk Management Framework | - New Policies introduced through this project will need time to be tested and reported back to the GEF; Stage II application will be affected from the lack of evidence to testify the success of new policies that would meet GEF minimum accredited standards. |
| Project Strategy | Objectively verifiable indicators |  |  | Sources of verification | Risks and Assumptions |
|  | Indicator | Baseline value | Target value and date |  |  |
| Output 2.7: Performance and accountability improved by integrating M&E information system policy, guideline, framework and plan into SPREP project/programme management.. | - Availability and functionality of SPREP's internal control framework - Availability of SPREP's Monitoring and Evaluation Policy and Guidelines. - Adoption of Enterprise Risk Management Framework in SPREP. - Number of Evaluation Reports produced | - NO functional internal control framework - No M&E policy and guideline - No enterprise risk management | - SPREP's Monitoring and Evaluation Policy and Guidelines prepared and operational. - Enterprise Risk Management Framework available and used. - Evaluation Reports. | - SPREP's internal control framework. - SPREP's Monitoring and Evaluation Policy and Guidelines. - Enterprise Risk Management Framework. - .Evaluation Reports | - New Policies introduced through this project will need time to be tested and reported back to the GEF; Stage II application will be affected from the lack of evidence to testify the success of new policies that would meet GEF minimum accredited standards. |
| Project Strategy | Objectively verifiable indicators |  |  | Sources of verification | Risks and Assumptions |
|  | Indicator | Baseline value | Target value and date |  |  |
| Output 2.8: Strengthens SPREP's Investigative Capacity. | - SPREP's Fraud Policy Updated. - SPREP's investigation guidelines, procedures and Terms of Reference approved. - SPREP's Monitoring and Evaluation Policy and Guidelines in place. - Enterprise Risk Management Framework adopted in SPREP. - Case Trends Reports | - SPREP's Fraud Policy. - Staff Regulation. - Financial Regulation. - Risk Management Plan. | - SPREP's Updated Fraud Policy. - SPREP's investigation guidelines, procedures and Terms of Reference. - SPREP's Monitoring and Evaluation Policy and Guidelines. - Enterprise Risk Management Framework adopted in SPREP. - Case Trends Reports. | - SPREP's Fraud Policy. - SPREP's investigation guidelines, procedures and Terms of Reference. - SPREP's Monitoring and Evaluation Policy and Guidelines. - SPREP's Enterprise Risk Management Framework. - Case Trends Reports. | - New Policies introduced through this project will need time to be tested and reported back to the GEF; Stage II application will be affected from the lack of evidence to testify the success of new policies that would meet GEF minimum accredited standards. |
| Project Strategy | Objectively verifiable indicators |  |  | Sources of verification | Risks and Assumptions |
|  | Indicator | Baseline value | Target value and date |  |  |
| Output 2.9: SPREP's Whistleblower Protection function strengthened. | - Status of SPREP's Fraud Policy and Procedures. - Status of SPREP's Whistleblower Policy and Procedures - Availability of Telephone Hotline. - Status of SPREP webpage dedicated for reporting fraud - Availability of Periodical Reports of intake information available. | - SPREP's Fraud Policy outdated. - SPREP’s Whistleblower Policy and Procedure not available - No telephone hotline - Risk Management Plan not available. - Email address for public complaints not available. | - SPREP's Fraud Policy and Procedures updated. - SPREP's Whistleblower Policy and Procedures approved. - Hotline Number available and operational. - SPREP Website includes webpage for whistle-blowing/reporting fraud operational. - Periodical Reports of intake information available and used | - SPREP's Fraud Policy and Procedures. - SPREP's Whistleblower Policy and Procedures. - Telephone Hotline Number. - SPREP webpage dedicated for reporting fraud. - Periodical Reports of intake information. | - New Policies introduced through this project will need time to be tested and reported back to the GEF; Stage II application will be affected from the lack of evidence to testify the success of new policies that would meet GEF minimum accredited standards. |

| Outcome 3: SPREP's Environmental and Social Safeguard Policy and Guideline Developed. |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Project Strategy | Objectively verifiable indicators |  |  | Sources of verification | Risks and Assumptions |
|  | Indicator | Baseline value | Target value and date |  |  |

| Output 3.1: Develop SPREP's Environmental and Social Safeguard Policy and Guideline. | - Recruitment of an Environmental Specialist/Expert. - Recruitment of a Social Scientist. - SPREP Environmental and Social Safeguard Policy and Guideline. | - SPREP does not have an Environmental and Social Safeguard Policy and Guideline per se. | - Environmental Specialist/Expert. - Social Scientist. - SPREP Environmental and Social Safeguard Policy and Guideline. | - Consultancy Contracts. - Meeting minutes - Tracking and progress reports - SPREP Environmental and Social Safeguard Policy and Guideline. | - New Policies introduced through this project will need time to be tested and reported back to the GEF; Stage II application will be affected from the lack of evidence to testify the success of new policies that would meet GEF minimum accredited standards. |
| --- | --- | --- | --- | --- | --- |
| Outcome 4: SPREP's Mainstreaming Policy and Guideline Developed. |  |  |  |  |  |
| Project Strategy | Objectively verifiable indicators |  |  | Sources of verification | Risks and Assumptions |
|  | Indicator | Baseline value | Target value and date |  |  |
| Output 4.1: Develop SPREP's Gender Mainstreaming Policy and Guideline. | - Recruit Gender Specialist/Experts. - SPREP's Gender Mainstreaming Policy and Guideline approved. - SPREP Procedures and Tools in place for gender mainstreaming in the secretariat and project designs. - Gender mainstreaming training undertaken for key staff. | - Gender mainstreaming considered at project levels but no such policy exists for the organizations as a whole. | - SPREP's Gender Mainstreaming Policy and Guideline. - SPREP Procedures and Tools. - Gender mainstreaming training. | - SPREP's Gender Mainstreaming Policy and Guideline. - SPREP Procedures and Tools. - Gender mainstreaming training. | - New Policies introduced through this project will need time to be tested and reported back to the GEF; Stage II application will be affected from the lack of evidence to testify the success of new policies that would meet GEF minimum accredited standards. |
| Outcome 5: SPREP's Information, Communication and Technology Systems Enhanced. |  |  |  |  |  |
| Project Strategy | Objectively verifiable indicators |  |  | Sources of verification | Risks and Assumptions |
|  | Indicator | Baseline value | Target value and date |  |  |
| Output 5.1: Strengthen SPREP's Information, Communication and Technology Systems. | - SPREP Intranet upgraded for including new functions and features to support policy implementation introduce - SPREP Financial Management Information (FMIS) and Human Resource Information(HRIS) Systems upgraded with project management interface functions. | - SPREP Intranet. - CC Portal - Pacific Environment Information Network (PEIN). - SPREP's FMIS and HRIS systems. | - SPREP web-based project management information system. - Ethics/Fraud/Whistle-blowing web-page. - SPREP's FMIS and HRIS systems upgraded. | - SPREP web-based project management information system. - SPREP's FMIS and HRIS systems upgraded. | - New Policies introduced through this project will need time to be tested and reported back to the GEF; Stage II application will be affected from the lack of evidence to testify the success of new policies that would meet GEF minimum accredited standards. |

## Annex 3:	Outcome Budget (GEF Contribution and Co-financing)

|  |  | Year |  | Co- | Total |
| --- | --- | --- | --- | --- | --- |
| Activity | Description | 1 | GEF | financing |  |
| Component 1: Enhancing Internal Control Frameworks to meet GEF Fiduciary Standards |  | 717,430 | 717,430 | 94,866 | 812,296 |
| Output 2.1 | Strengthening of External Financial and Audit Function | 90,000 | 90,000 | 10,500 | 100,500 |
| Output 2.2 | Strengthen Financial Management and Control Frameworks | 187,430 | 187,430 | 10,866 | 198,296 |
| Output 2.3 | Enhance SPREP's Financial Disclosure Capacity. | 20,000 | 20,000 | 10,500 | 30,500 |
| Output 2.4 | Strengthens SPREP's Code of Ethics. | 90,000 | 90,000 | 10,500 | 100,500 |
| Output 2.5 | Strengthens SPREP's internal audit functions. | 50,000 | 50,000 | 10,500 | 60,500 |
| Output 2.6 | Strengthens SPREP Project Management. | 100,000 | 100,000 | 10,500 | 110,500 |
| Output 2.7 | Strengthens SPREP's Evaluation Function. | 80,000 | 80,000 | 10,500 | 90,500 |
| Output 2.8 | Strengthens SPREP's Investigations. | 50,000 | 50,000 | 10,500 | 60,500 |
| Output 2.9 | Strengthens SPREP's Whistleblower Protection function. | 50,000 | 50,000 | 10,500 | 60,500 |
| Component 2: Develop Environmental and Social Safeguard Policy |  | 50,000 | 50,000 | 36,062 | 86,062 |
| Output 3.1 | Develop SPREP's Environmental and Social Safeguard Policy and Guideline | 50,000 | 50,000 | 36,062 | 86,062 |
| Component 3: Develop Gender Mainstreaming Policy |  | 50,000 | 50,000 | 0.00 | 50,000 |
| Output 4.1 | Develop SPREP's Gender Mainstreaming Policy and Guideline. | 50,000 | 50,000 | 0,00 | 50,000 |
| Component 4: Strengthening SPREP's ICT Systems |  | 100,000 | 100,000 | 1,174,466 | 1,274,466 |
| Output 5.1 | Strengthen SPREP's Information, Communication and Technology Systems. | 100,000 | 100,000 | 1,174,466 | 1,274,466 |

|  |  | Year 1 | GEF | Co-Fin | Total |
| --- | --- | --- | --- | --- | --- |
| Project Management |  | 691,678.60 | 82,570 | 609,108.60 | 691,678.60 |
| A | Project Director | 72,000 | 0.00 | 72,000 | 72,000 |
| B | Project Manager | 70,000 | 0.00 | 70,000 | 70,000 |
| C | Project Coordinator | 36,285 | 36,285 | 0.00 | 36,285 |
| D | Technical Adviser | 13,285 | 13,285 | 0.00 | 13,285 |
| E | International Evaluation Consultant Fee (1) | 28,000 | 28,000 | 0.00 | 28,000 |
| F | Office facilities and communications (2) | 467,108.60 | 0.00 | 467,108.60 | 367,108.60 |
| G | Travel (meetings) | 5,000 | 5,000 | 0.00 | 5,000 |

Notes

(1)   The International Consultant will conduct an independent evaluation of the project and recruited by UNDP MCO Samoa.

(2)  In addition to office space for the project team, this budget will cover the cost of Project Board meetings.

## Annex 4:	Provisional Work Plan

|  |  | Year 1 |  |  |  |  |  |  |  |  |  |  |  | Year 2 |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 |
| Activity | Description |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| A | Project start-up: Organize project team and review work plan. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| B | Policy Board Meetings. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 1.1 | Stage II application for GEF accreditation completed and submitted |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.1.1 | Desktop review of Stage II application submitted in May 2012. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.1.2 | Undertake gap analysis: fiduciary, environmental and social safeguard, and gender mainstreaming. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.1.3 | Collation of baseline information and built capacity through the MSP project. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.1.4 | Complete revision of Stage II application. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 2.1 | Strengthening of External Financial and Audit Function. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.1.1 | Desktop review of external audit opinions undertaken for SPREP in the last 10 years. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2..1.2 | Descriptive analysis of existing procedures for recruiting an independent external auditor. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.1.3 | Recruit an independent audit specialist/expert to identify gaps to meet GEF minimum accredited standards for external auditing. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.1.4 | Develop report with recommendations and submit to SPREP SMT for approval. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.1.5 | Implement recommendations for actions to meet GEF minimum accredited standards for audit. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 2.2 | Strengthen Financial Management and Control Frameworks |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.2.1 | Recruit Management and Finance Specialist/Expert. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.2.2 | Identify institutional, systemic and individual gaps for capacity building in-order to meet GEF minimum accredited standards for financial management and control frameworks (also including the HACT assessment) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.2.3 | Develop SPREP Internal Control Framework (ICF). |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.2.4 | Develop procedures and tools for effective use and compliance of SPREP ICF. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.2.5 | Undertake an assessment of training needs. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.2.6 | Capacity building training of SPREP staff on the new ICF. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.2.7 | Submit Internal Control Framework Document to SPREP SMT for approval. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 2.3 | Enhance SPREP's Financial Disclosure Capacity |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.3.1 | Recruit Financial Management Specialist/Expert. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.3.2 | Develop SPREP Financial Disclosure Policy. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.3.3 | Develop Procedures and Tools for administering the new SPREP Financial Disclosure Policy. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.3.4 | Submit Financial Disclosure Policy to SPREP SMT for approval. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 2.4 | Strengthens SPREP's Code of Ethics |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.4.1 | Recruit an Ethics Specialist/Expert |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.4.2 | Update Code of Ethics to meet GEF minimum accredited standards. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.4.3 | Develop/Update procedures for administering the Code of Ethics. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.4.4 | Submit Code of Ethics to SPREP SMT for approval. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 2.5 | Strengthens SPREP 's Internal Audit Functions |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.5.1 | Same as Output 2.1.3. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.5.2 | Gap analysis of internal audit functions to meet GEF minimum accredited standards. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.5.3 | Provide report with recommendations for capacity building activities to meet GEF accredited standards to SPREP SMT for approval. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.5.4 | Implement SMT approved recommendations. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 2.6 | Strengthens SPREP Project Management |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.6.1 | Recruit Project Management Specialist/Expert. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.6.2 | Develop Project Management Guideline and Procedures for SPREP SMT approval. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.6.3 | Established SPREP's Project and Activity Appraisal Process. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.6.4 | Develop SPREP's Risk Management Plan for SPREP SMT approval. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.6.5 | Develop Enterprise Risk Management Framework (ERMF) for SPREP SMT approval. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.6.6 | Same as Output 3.1.2 and Output 4.1.2 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.6.7 | Capacity building training for SPREP staff on the ERMF. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 2.7 | Strengthens SPREP's Monitoring and Evaluation Function |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.7.1 | Recruit Monitoring &Evaluation Specialist/Expert |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.7.2 | Develop SPREP's Monitoring and Evaluation Policy and Guideline for SMT approval. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.7.3 | Same as Output 2.6.5 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.7.4 | Capacity building training for SPREP staff on the M&E Policy and Guideline. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 2.8 | Strengthens SPREP's Investigative Capacity |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.8.1 | Recruit Legal Specialist/Expert |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.8.2 | Review and Update SPREP's Fraud Policy to meet GEF minimum accredited standards. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.8.3 | Submit revised Fraud Policy to SPREP SMT for approval. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.8.4 | Capacity building training for SPREP staff on the revised Fraud Policy. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 2.9 | Strengthens SPREP's Whistleblower Protection Function. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.9.1 | Same as Output 2.8.1 and Output 2.4.1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.9.2 | Develop SPREP's Whistleblower Policy and Procedures for SMT approval. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.9.3 | Set-up Hotline number |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.9.4 | Develop new webpage within the SPREP website dedicated for reporting fraud and unethical behavior by SPREP staff. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.9.5 | Capacity building training for SPREP staff on the Whistleblower Policy and Procedures. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 3.1 | Develop SPREP's Environmental and Social Safeguard Policy and Guideline |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.1.1 | Recruit Environmental Specialist/Expert. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.1.2 | Develop SPREP's Environmental and Social Safeguard Policy and Guideline (ESSPG) for SMT approval. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.1.3 | Set up Procedures and Tools for administering the ESSPG. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.1.4 | Capacity building training for SPREP staff on the ESSPG. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 4.1 | Develop SPREP's Gender Mainstreaming Policy and Guideline |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 4.1.1 | Recruit Gender Specialist/Expert. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 4.1.2 | Develop SPREP's Gender Mainstreaming Policy and Guideline (GMPG) for SMT approval. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 4.1.3 | Set up Procedures and Tools for administering the GMPG. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 4.1.4 | Capacity building training for SPREP staff on the GMPG. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 5.1 | Strengthen SPREP's Information, Communication and Technology Systems. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| C | Project final evaluation and wrap-up |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

## Annex 5: UNDP Risk Log

| # | Key risk | Level of risk | Comments and mitigation responses |
| --- | --- | --- | --- |
| 1 | The “learning by doing approach” cannot be implemented because SPREP staff do not have time to engage in this capacity building project | Low to moderate | SPREP staff have limited time to invest in learning and capacity building and may not be available for the objectives set out in this project document. The solution is to carefully plan how SPREP personnel can receive support in their daily workload to be able to contribute to the assigned tasks in this project document. Using ongoing GEF-projects as objects of learning in the activities of the project is also a good model for saving time. |
| 2 | First Round of GEF Accreditation ends on the 31st December 2014 | High | The MSP will not be completed in time to submit applications for Stage I & II by the end of 2014. As a way forward, the GEF council may wish to decide for a second round of accreditation which will allow sufficient time for SPREP to prepare submissions for accreditation. |
| 3 | Regional Participation in the Project Board. | Low to Moderate | Regional participation of all 14 Pacific Island Countries on the project board is not plausible due to the high transportation costs of funding all 14 national representation in the project board. The solution is to replicate management models of existing GEF funded regional projects such as PIGGAREP and PACC where 1 country will represent one of the 3 sub-region in the Pacific. Samoa for Polynesia, Fiji for Melanesia, and Nauru for Micronesia. Nauru is the current chair of the SPREP Governing Council Meeting and may also sit in as the whole of Pacific regional representative. |
| 4 | Limited Consultancy Pool in the Pacific Region. | Low | There is a limited pool of consultants in the Pacific Region who have experience to support this MSP. Additionally, the risk of recruiting consultants that do not have expertise with the GEF accreditation process or any of the International Financial Institutions such as the World Bank, Asian Development Bank, International Monetary Fund etc will affect the quality of deliverables that may negatively impact on SPREP's application to be a GEF Project Agency. It is important to procure the appropriate consultant that can put in place the necessary and correct upgrades to meet the GEF's minimum accredited standards. The solution is to source advice from the GEF accreditation panel and the GEF secretariat of appropriate consultants who have supported other agencies' applications for accreditation to the GEF. |
| Overall risk |  |  | Moderate |

The overall level of risk is considered Moderate due the probability of this MSP not being completed in the current first round of accreditation which will end in December 2014.  Other risks are managed appropriately through the proposed solutions that will mitigate their adverse effects on the project.

## Annex 6:	Terms of References

The following Terms of Reference outlines the general responsibilities to be carried out by the project team and consultants contracted under the project.

Background

This project is borne out of the necessity to expedite access of Pacific Island Countries to MEA funding, in particular from the GEF. 14 Pacific Island Countries eligible for GEF funding are members of the SPREP Governing Council Meeting who instructed its secretariat to seek GEF accreditation in 2011. Since then, SPREP has submitted its Stage I and Stage II applications in the hope of proceeding to the final Stage III. However, with the support of the GEF Governing Council, SPREP was invited to submit its request for medium size project of USD 1 million to assist with its own capacity building initiatives to upgrade and match the GEF minimum accredited standards.

This medium size project is designed in partnership between the GEF secretariat and SPREP working with the UN Development Programme (UNDP) on a normal GEF project that would involve SPREP and include capacity building designed in a way that would prepare SPREP to become a GEF Agency in GEF-6.

Project Goal and Objectives

The goal of this project is To enable SPREP to support 14 Pacific Island Countries to more effectively achieve global environmental benefits by strengthening their key institutional and individual capacities. To this end, the project will focus on enhancing 3 key areas: internal control framework, environmental and social safeguard policy, and a gender mainstreaming policy and guidelines.

Key results will be measured by the work undertaken by SPREP to develop project proposals for Pacific Island Countries to expedite access to GEF resources inter alia. Projects that are approved will be targeting capacity development to achieve deeper integration of project activities to NCSA action plans and ultimately contributing to generating global environmental benefits. Public awareness campaigns and wider consultation with relevant stakeholders on the role of SPREP as a GEF Project Agency will be unfolded either separately in SPREP conferences and workshops and during PPG planning. This will contribute to effective policy formulation and implementation in PIC member countries.

The goal of this project is to strengthen SPREP's capacity to assist Pacific Island Countries' implementation of the three Rio Conventions. To this end, the project will focus on enhancing 3 key areas: internal control framework, environmental and social safeguard policy, and a gender mainstreaming policy and guidelines.

Project Strategy

The project’s strategy is to take a partnership approach between SPREP and UNDP to this exercise by focusing on a key set of outputs required to be implemented in-order for SPREP to meet GEF minimum accreditation standards. In this way, SPREP will be guided and benefited from UNDP's experience as a seasoned GEF IA, especially in the designing of appropriate desired capacity that SPREP should build to meet GEF minimum accreditation standards.

The delivery of outputs depends heavily on the outsourced work of consultants who will be recruited to implement activities to upgrade SPREP's capacity to carry out GEF fiduciary functions expected from a GEF Project Agency. Additionally, consultants will work to put in place environmental and social safeguard and gender mainstreaming policies along with their procedures and tools for the effective and efficient administration of these new policies.

Project Outcomes and Components

- At the end of the project, activities will have resulted in a set of improved capacities within SPREP to meet GEF minimum accreditation standards. This project will have strengthened and helped institutionalize commitments required to meet SPREP's application II for accreditation. Indirectly, it will also help Pacific Island Countries efforts to meet their obligations under the Rio Conventions in the long run.

- This project will be implemented in four linked components:

  - Enhancing Internal Control Frameworks to meet GEF Minimum Fiduciary Standards;

  - Develop Environmental and Social Safeguard Policy;

  - Develop Gender Mainstreaming Policy and Guideline; and

  - Strengthening Information, Communication and Technology Systems.

Responsibilities

- Project Director (PD)

The Director General of SPREP shall be the project director for this UNDP-supported project.  The National Project Director supports the project and acts as a focal point on the part of SPREP.  This responsibility normally entails ensuring effective communication between partners and monitoring of progress towards expected results.

The Project Director is the party that represents SPREP's ownership and authority over the project, responsibility for achieving project objectives and the accountability to the SPREP Governing Council Meeting and UNDP for the use of project resources.

Duties and Responsibilities of the PD

The PD will have the following duties and responsibilities:

- Assume overall responsibility for the successful execution and implementation of the project, accountability to the SPREP Governing Council Meeting and UNDP for the proper and effective use of project resources;

- Serve as a focal point for the coordination of projects with Pacific Island Governments and UNDP;

- Supervise the work of the Project Manager and ensure that the Project Manager is empowered to effectively manage the project and other project staff to perform their duties effectively;

- Supervise the preparation of project work plans, updating, clearance and approval, in consultation with UNDP and other stakeholders and ensure the timely request of inputs according to the project work plans;

- Represent the SPREP Governing Council Meeting at the tripartite review project meetings, and other stakeholder meetings.

- Project Manager (PM)

The Deputy Director General of SPREP will also act as the Project Manager. Twenty  (20) percent of the Project Manager's time will be spent carrying out a number of activities, namely:

- Oversees the establishment of the Project Management Unit;

- Develop and manage the project's work plan and budget;

- Finalize ToR for consultants;

- Coordinates the recruitment of consultants;

- Manages consultants work and reporting.;

- Reports to the project board on the progress and financial statements of the project;

- Submit as required the progress and financial statements to UNDP MCO Samoa;

- Submit, as required the Annual Performance Review (APR) to Tri-Partite Review Meetings; and

- Oversee the implementation of the Project Board's directives.

- Project Coordinator (PC)

The PC will report to the PM and work under the supervision of the PM and UNDP management. The PC will lead the Project Team through the planning, implementation, and delivery of policies, reports, knowledge products, and other results approved in the project document and annual work plans. S/he will provide overall operational management for the successful execution and implementation of the programmed. S/he will be responsible for financial management and disbursements, with accountability to the SPREP and UNDP. In carrying out her/his responsibilities, s/he will advocate and promote the work of this project.

Tasks:

- Facilitate the day-to-day functioning of the PMU;

- Manage human and financial resources, in consultation with the project’s senior management, to achieve results in line with the outputs and activities outlined in the project document;

- Lead the preparation and implementation of the annual results-based work plans and logical frameworks as endorsed by the management;

- Coordinate project activities with related and parallel activities both within SPREP and with external implementing partner agencies;

- Monitor project activities, including financial matters, and prepare monthly and quarterly progress reports, and organize monthly and quarterly progress reviews;

- Support the PM in organizing PB meetings;

- Coordinate the distribution of responsibilities amongst Project Team members and organize the monitoring and tracking system of all cluster services;

- Report and provide feedback to UNDP-GEF and the PB on project strategies, activities, progress and barriers; and

- Organizational and logistical issues related to project execution per UNDP guidelines and 	procedures;

- Record keeping of project documents, including financial in accordance with audit 	requirements;

- Ensure all logistical arrangements are carried out smoothly;

- Assist Project Manager in preparation and update of project work plans in collaboration 	with the UNDP MCO Samoa;

- Facilitate timely preparation and submission of financial reports and settlement of 	advances, including progress reports and other substantial reports;

- Report to the Project Manager and UNDP Programme Officer on a regular basis; and

- Identification and resolution of logistical and organizational problems, under the 	guidance of the Project Manager.

The SPREP Executive Officer and the GEF Support Adviser will provide on-demand support to the Project Coordinator for delivering on the project's work plan and results.

- Technical Adviser

SPREP will recruit a Technical Adviser who will provide overall technical backstopping to the Project Coordinator. Specific functions include but not necessarily limited to:

(i) Coordination and Management Functions

- Assist with the development of a detailed work plan and budget, assist with project oversight and implementation, assist with the monitoring work progress, reporting and communication, and timely delivery of relevant;

- Ensure stakeholders consultations related to activities for these outputs are carried out; and

(ii) Strategic Planning and Technical Support

- Support consultants work to review existing SPREP policies and procedures and ensure appropriate actions are carried out to build capacity in-order to meet GEF accredited standards;

- Prepare issues and risks logs for PM and PC.

- Ensure overall technical support and assistance is available and provided to support project implementation.

(iii) Capacity building and training

- Ensure project capacity building, awareness, educational and training programmes are developed and implemented; and

- Ensure resources are available to conduct training, including offering technical support.

- Finance Specialist/Expert

The Finance Specialist/Expert is one of nine Lead Consultants that will work together in a team environment to deliver the key outputs of this project.  The Finance Specialist/Expert will be recruited to carry out a number of activities, namely:

- Comparative analysis of SPREP's existing capacity against GEF minimum fiduciary standards;

- Prepare report with recommendations for capacity building activities to respond to gaps identified from the comparative analysis.

- Present report findings to the SPREP Senior Management Team (SMT);

- Incorporate SMT and others review commentary for report finalization;

- Design and implement activities to build SPREP's financial capacity to meet GEF minimum accreditation standards.

- Carry out capacity building training of SPREP staff on improvements to SPREP's financial capacity.

- Provide the project manager with a progress report write up both electronically and hard copy.

The Finance Specialist/Expert will have will have a post graduate degree on management and administration  and/or an internationally recognized procurement certification with a minimum of 15 years of experience in the management and administration field. Preferably, this person should have demonstrable experience working in international financial institutions such as the World Bank, IMF, ADB, and the GEF itself. Additionally, we would prefer a person who has successfully supported another organization's efforts to obtain GEF accreditation.

- Management and Procurement Specialist/Expert

The Management and Procurement Specialist/Expert is one of nine Lead Consultants that will work together in a team environment to deliver the key outputs of this project.  The Specialist/Expert will be responsible for the following activities:

- Undertake a gap analysis of SPREP's existing management and procurement capacity against GEF minimum fiduciary standards;

- Prepare report with recommendations for capacity building activities to respond to gaps identified from the comparative analysis.

- Present report findings to the SPREP Senior Management Team (SMT);

- Incorporate SMT and others review commentary for report finalization;

- Design and implement activities to build SPREP's management and procurement capacity to meet GEF minimum accreditation standards.

- Carry out capacity building training of SPREP staff on improvements to SPREP's management and procurement capacity.

The Management and Procurement Specialist/Expert will have will have a post graduate degree on management and administration and/or an internationally recognized procurement certification with a minimum of 15 years of experience in the management and administration field. Preferably, this person should have demonstrable experience working in international financial institutions such as the World Bank, IMF, ADB, and the GEF itself. Additionally, we would prefer a person who has successfully supported another organization's efforts to obtain GEF accreditation.

- Ethics Specialist/Expert

The Ethics Specialist/Expert is one of nine Lead Consultants that will work together in a team environment to deliver the key outputs of this project.  The Specialist/Expert will be responsible for the following activities:

- Undertake a gap analysis of SPREP's existing ethics management capacity against GEF minimum fiduciary standards;

- Prepare report with recommendations for capacity building activities to respond to gaps identified from the comparative analysis.

- Present report findings to the SPREP Senior Management Team (SMT);

- Incorporate SMT and others review commentary for report finalization;

- Design and implement activities to build SPREP's financial capacity to meet GEF minimum accreditation standards.

- Carry out capacity building training of SPREP staff on improvements to SPREP's Ethics capacity.

The Ethics Specialist/Expert will have will have a post graduate degree on management and administration; Law;  and/or an internationally recognized ethics certification with a minimum of 15 years of experience in the management and administration field. Preferably, this person should have demonstrable experience working in international financial institutions such as the World Bank, IMF, ADB, and the GEF itself. Additionally, we would prefer a person who has successfully supported another organization's efforts to obtain GEF accreditation.

- Audit Specialist/Expert

The Audit Specialist/Expert is one of nine Lead Consultants that will work together in a team environment to deliver the key outputs of this project.  The Specialist/Expert will be responsible for the following activities:

- Undertake a gap analysis of SPREP's existing management and procurement capacity against GEF minimum fiduciary standards;

- Prepare report with recommendations for capacity building activities to respond to gaps identified from the comparative analysis.

- Present report findings to the SPREP Senior Management Team (SMT);

- Incorporate SMT and others review commentary for report finalization;

- Design and implement activities to build SPREP's financial capacity to meet GEF minimum accreditation standards.

- Carry out capacity building training of SPREP staff on improvements to SPREP's audit capacity.

The Audit Specialist/Expert will have will have a post graduate degree on management and accounting and/or an internationally recognized audit certification with a minimum of 15 years of experience in the management and accounting field. Preferably, this person should have demonstrable experience working in international financial institutions such as the World Bank, IMF, ADB, and the GEF itself. Additionally, we would prefer a person who has successfully supported another organization's efforts to obtain GEF accreditation.

- Project Management Specialist/Expert

The Project Management Specialist/Expert is one of nine Lead Consultants that will work together in a team environment to deliver the key outputs of this project.  The Specialist/Expert will be responsible for the following activities:

- Undertake a gap analysis of SPREP's existing project management capacity against GEF minimum fiduciary standards;

- Prepare report with recommendations for capacity building activities to respond to gaps identified from the comparative analysis.

- Present report findings to the SPREP Senior Management Team (SMT);

- Incorporate SMT and others review commentary for report finalization;

- Design and implement activities to build SPREP's project management capacity to meet GEF minimum accreditation standards.

- Carry out capacity building training of SPREP staff on improvements to SPREP's project management capacity.

The Project Management Specialist/Expert will have will have a post graduate degree on management and administration and/or an internationally recognized project management certification (i.e. PRINCE Practitioner/Examiner) with a minimum of 15 years of experience in the management and accounting field. Preferably, this person should have demonstrable experience working in Multi-lateral Organizations such as the World Bank, ADB, UNDP, and the GEF itself. Additionally, we would prefer a person who has successfully supported another organization's efforts to obtain GEF accreditation.

- Environmental Specialist/Expert

The Environmental Specialist/Expert is one of nine Lead Consultants that will work together in a team environment to deliver the key outputs of this project.  The Specialist/Expert will be responsible for the following activities:

- Undertake a gap analysis of SPREP's existing environmental safeguard policy capacity against GEF minimum fiduciary standards;

- Prepare report with recommendations for capacity building activities to respond to gaps identified from the comparative analysis.

- Present report findings to the SPREP Senior Management Team (SMT);

- Incorporate SMT and others review commentary for report finalization;

- Design and implement activities to build SPREP's environmental safeguard and management capacity to meet GEF minimum accreditation standards.

- Carry out capacity building training of SPREP staff on improvements to SPREP's environmental safeguard and management capacity.

The Environmental Specialist/Expert will have a post graduate degree on environmental planning, policy and management, and/or an internationally recognized environmental management certification; and/or EIA training with a minimum of 15 years of experience in the environmental management field. Preferably, this person should have demonstrable experience working in Multi-lateral Organizations such as the World Bank, ADB, UNDP, UNEP, and the GEF itself. Additionally, we would prefer a person who has successfully supported another organization's efforts to obtain GEF accreditation.

- Social Scientist

The Social Scientist is one of nine Lead Consultants that will work together in a team environment to deliver the key outputs of this project.  The Specialist/Expert will be responsible for the following activities:

- Undertake a gap analysis of SPREP's existing policy and capacity to administer social safeguard against GEF minimum fiduciary standards;

- Prepare report with recommendations for capacity building activities to respond to gaps identified from the comparative analysis.

- Present report findings to the SPREP Senior Management Team (SMT);

- Incorporate SMT and others review commentary for report finalization;

- Design and implement activities to build SPREP's social safeguard capacity to meet GEF minimum accreditation standards.

- Carry out capacity building training of SPREP staff on improvements to SPREP's social safeguard capacity.

The Social Scientist will have a post graduate degree either in social science, anthropology, sociology, or any relevant field, and/or an internationally recognized social science certification; with a minimum of 15 years of experience in the social science field. Preferably, this person should have demonstrable experience working in Multi-lateral Organizations such as the World Bank, ADB, UNDP, UNEP, and the GEF itself.  Additionally, we would prefer a person who has successfully supported another organization's efforts to obtain GEF accreditation.

- Gender Specialist/Expert

The Gender Specialist/Expert is one of nine Lead Consultants that will work together in a team environment to deliver the key outputs of this project.  The Specialist/Expert will be responsible for the following activities:

- Undertake a gap analysis of SPREP's existing gender mainstreaming policy and capacity against GEF minimum fiduciary standards;

- Prepare report with recommendations for capacity building activities to respond to gaps identified from the comparative analysis.

- Present report findings to the SPREP Senior Management Team (SMT);

- Incorporate SMT and others review commentary for report finalization;

- Design and implement activities to build SPREP's gender mainstreaming policy and capacity to meet GEF minimum accreditation standards.

- Carry out capacity building training of SPREP staff on improvements to SPREP's gender mainstreaming policy and capacity.

The Gender Mainstreaming Specialist/Expert will have a post graduate degree on gender mainstreaming, and/or an internationally recognized gender mainstreaming certification; with a minimum of 15 years of experience in the gender mainstreaming/equality/equity field. Preferably, this person should have demonstrable experience working in Multi-lateral Organizations such as the World Bank, ADB, UNDP, UNEP, and the GEF itself.  Additionally, we would prefer a person who has successfully supported another organization's efforts to obtain GEF accreditation.

- IT & Network Specialist/Expert

The IT & Network Specialist/Expert is one of nine Lead Consultants that will work together in a team environment to deliver the key outputs of this project.  The Specialist/Expert will be responsible for the following activities:

- Undertake a gap analysis of SPREP's existing IT & Network capacity against GEF minimum fiduciary standards;

- Prepare report with recommendations for capacity building activities to respond to gaps identified from the comparative analysis.

- Present report findings to the SPREP Senior Management Team (SMT);

- Incorporate SMT and others review commentary for report finalization;

- Design and implement activities to build SPREP's IT and Network capacity to meet GEF minimum accreditation standards.

- Carry out capacity building training of SPREP staff on improvements to SPREP's gender IT and Network capacity.

The IT and Network Specialist/Expert will have a post graduate degree on IT and Network, and/or an internationally recognized IT & Network certification; with a minimum of 15 years of experience in the IT and Network field. Preferably, this person should have demonstrable experience working in Multi-lateral Organizations such as the World Bank, ADB, UNDP, UNEP, and the GEF itself.  Additionally, we would prefer a person who has successfully supported another organization's efforts to obtain GEF accreditation.

## Annex 7:	Letter of Agreement for recovery of Direct Project Costs

LETTER OF AGREEMENT (LOA) BETWEEN UNDP AND SPREP

FOR THE PROVISION OF SUPPORT SERVICES

Mr. David Sheppard,

1.	Reference is made to consultations between officials of the Secretariat of the Pacific Regional Environment Programme (hereinafter referred to as “SPREP”) and officials of UNDP with respect to the provision of support services by the UNDP Multi-Country Office for programmes and projects implemented by SPREP. UNDP and SPREP hereby agree that the UNDP Multi-Country Office may provide such support services at the request of SPREP through its division designated in the relevant programme support document or project document, as described below.

2.	The UNDP Multi-Country Office may provide support services for assistance with reporting requirements and direct payment.  In providing such support services, the UNDP Multi-Country Office shall ensure that the capacity of SPREP is strengthened to enable it to carry out such activities directly.  The costs incurred by the UNDP Multi-Country Office in providing such support services shall be recovered from the administrative budget of the office.

3.	The UNDP Multi-Country Office may provide, at the request of the designated institution, support services for the activities of the programme/project, including:

(a)	Identification and/or recruitment of project and programme personnel;

(b)	Identification and facilitation of training activities;

(c)	Procurement of goods and services;

4.	The procurement of goods and services and the recruitment of project and programme personnel by the UNDP Multi-Country Office shall be in accordance with the UNDP regulations, rules, policies and procedures.  Support services described in paragraph 3 above shall be detailed in an annex to the programme support document or project document, in the form provided in the Attachment hereto.  If the requirements for support services by the Multi-Country Office change during the life of a programme or project, the annex to the programme support document or project document is revised with the mutual agreement of the UNDP Resident Representative and the designated institution.

5.	The relevant provisions of the UNDP Standard Basic Assistance Agreement with the Government of Samoa (the “SBAA” of 5th of September 2008), including the provisions on liability and privileges and immunities, shall apply to the provision of such support services. SPREP shall retain overall responsibility for the project. The responsibility of the UNDP Multi-Country Office for the provision of the support services described herein shall be limited to the provision of such support services detailed in the annex to the project document.

6.	Any claim or dispute arising under or in connection with the provision of support services by the UNDP Multi-Country Office in accordance with this letter shall be handled pursuant to the relevant provisions of the Project Cooperation Agreement for the project signed by UNDP and SPREP.

David Sheppard

Director General

Secretariat of the Pacific Regional Environment Programme (SPREP)

19 May 2014

7.	The manner and method of cost-recovery by the UNDP Multi-Country Office in providing the support services described in paragraph 3 above shall be specified in the annex to the project document.

8.	The UNDP Multi-Country Office shall submit progress reports on the support services provided and shall report on the costs reimbursed in providing such services, as may be required.

9.	Any modification of the present arrangements shall be effected by mutual written agreement of the parties hereto.

10.	If you are in agreement with the provisions set forth above, please sign and return to this office two signed copies of this letter.  Upon your signature, this letter shall constitute an agreement between SPREP and UNDP on the terms and conditions for the provision of support services by the UNDP Multi-Country Office for nationally managed programmes and projects.

Yours sincerely,

________________________

Signed on behalf of UNDP

Lizbeth Cullity

UN Resident Coordinator and UNDP Resident Representative

UNDP MCO Cook Islands, Niue, Samoa and Tokelau

_____________________

David Sheppard

Director General

Secretariat of the Pacific Regional Environment Programme (SPREP)

19 May 2014

Attachment

# DESCRIPTION OF UNDP MULTI-COUNTRY OFFICE SUPPORT SERVICES FOR THE PROJECT “ENHANCING CAPACITY TO DEVELOP GLOBAL AND REGIONAL ENVIRONMENTAL PROJECTS IN THE PACIFIC”

1.	Reference is made to consultations between officials of the Secretariat of the Pacific Regional Environment Programme (SPREP) and the United Nations Development Programme (UNDP) with respect to the provision of support services by the UNDP Multi-Country Office based in Samoa for the following project implemented by SPREP: “Enhancing Capacity to Develop Global and Regional Environmental Projects in the Pacific”.

2.	In accordance with the provisions of the Letter of Agreement and Project Cooperation Agreement, both signed on the 19th of May 2014, and the project document, the UNDP Multi-Country Office shall provide support services for the project as described below.

3.	Support services to be provided:

This project aims to build the national capacities of 14 Pacific Island Countries through strengthening SPREP and, in particular, its institutional capacity to satisfy minimal accreditation standards of the GEF. To achieve this, UNDP will closely work with SPREP, transferring the required knowledge and providing additional support when required, in order to facilitate SPREP’s accreditation as a GEF Project Agency.

## SPREP may request operational, administrative and technical services (Direct Project Costs) from UNDP Multi-Country Office (MCO) to support the implementation of this project. These services shall be consider Direct Project Costs and, as indicated on the Operational Guidelines for Implementation of new Cost Recovery methodology, Utilization of Multiple-funding lines for posts, and Direct Project Costing (hereinafter referred to as “Cost Recovery Policy”), may include the involvement of the following UNDP MCO’s units:

- Communications Unit staff time spent on communication of development results and outcomes in the context of the specific project.

- Human Resources staff time spent on the recruitment, selection, hiring, contracting, and/or contract administration of project personnel.

- Procurement Unit staff time spent on the procurement of goods or services on behalf of the project, covering the entire procurement cycle tasks, transport, storage, distribution, on-site receipting of goods, customs clearance, logistics, etc.

- Finance Unit staff time spent on undertaking direct project payment requests, disbursements and other finance transactions related to the project.

- Programme staff time and any other MCO staff time spent directly on programme implementation and directly contributing to development results.

Recovery of costs for such services shall be calculated based on actual costs, in accordance with UNDP’s Cost Recovery Policy. When determining actual costs is not possible, the Universal Price List / Local Price List may be applied.

In addition, Direct Project Costs may include standard fees related to the access of personnel of the Implementing Partner to existing UNDP tools and platforms, such us the Learning Management System (including courses for international certifications) or the external access to ATLAS.

The following table includes the specific details of the estimated services:

| Support services | Schedule for the provision of the support services | Cost to UNDP of providing such support services | Amount and method of reimbursement of UNDP |
| --- | --- | --- | --- |
| 1. Provision of technical advice (which may include support to gap analysis, provision of examples, templates and best practices, review of ToR, reports and other documents, training sessions, etc.) on the following areas: - External Financial Audit Functions - Financial Management and Control Frameworks - Financial Disclosure - Code of Ethics - Internal Audit Functions - Project Appraisal Standards - Procurement Processes and Guidelines - Monitoring and Project-at-Risk Systems - Evaluation Functions - Investigation Functions - Hotline and Whistleblower Protection - Environmental and Social Safeguard Policy & Guidelines - Gender Mainstreaming Policy and Guidelines | As defined on the Annual Work Plan or requested ad-hoc. Tentatively, an average of two working days per month has been estimated, but it will depend on the specific needs of support. | For UNDP staff from Pacific Center or Regional Services Center coming to Samoa: 600 USD/day For UNDP MCO personnel and online support: Actual cost of staff will be calculated with the timesheet, in accordance with UNDP’s Cost Recovery Policy and tools | 15,000 USD (estimated amount) The actual or transactional based costs will be charged to a separate account code (74599 – UNDP cost recovery charges-Bills) within the budget for Project Management Costs |
| 2. Provision of transactional services, which may include: - Recruitment, selection, hiring, contracting, and/or contract administration of consultants and project personnel - Procurement of goods or services on behalf of the project, covering the entire procurement cycle tasks, transport, storage, distribution, on-site receipting of goods, customs clearance, logistics, etc. - Direct project payment requests, disbursements and other finance transactions related to the project. - Standard fees related to the access of personnel of the Implementing Partner to existing UNDP tools and platforms, such us the Learning Management System or the external access to ATLAS. | These services will be provided when requested by the IP. | Recovery of costs for such services shall be calculated based on actual costs, in accordance with UNDP’s Cost Recovery Policy. When determining actual costs is not possible, the Universal Price List / Local Price List may be applied. | 5,000 USD (estimated amount) The actual or transactional based costs will be charged to a separate account code (74599 – UNDP cost recovery charges-Bills) within the budget for Project Management Costs |
| 3. Miscellaneous, which may include support on communications, publications or other expenditures related to the support services provided to this project. | These services will be provided when requested by the IP and may be associated to the provision of technical advisory services. | Recovery of costs for such services shall be calculated based on actual costs, in accordance with UNDP’s Cost Recovery Policy. When determining actual costs is not possible, the Universal Price List / Local Price List may be applied. | 5,000 USD (estimated amount) The actual or transactional based costs will be charged to a separate account code (74599 – UNDP cost recovery charges-Bills) within the budget for Project Management Costs |

4.         Description of functions and responsibilities of the parties involved:

The Project will be implemented through UNDP’s Inter-Governmental Organization (IGO) Implementation Modality, with the SPREP as the designated executing agency (“Implementing Partner”) of the project. SPREP will have the technical and administrative responsibility for applying Global Environment Facility (GEF) inputs in order to reach the expected Outcomes/Outputs as defined in this project document. SPREP is responsible for the timely delivery of project inputs and outputs, and in this context, for the coordination of all other responsible parties, including other line ministries, local government authorities and/or UN agencies.

UNDP will serve as the Implementing Agency and Responsible Party for this project. Services that UNDP will provide to the Implementing Partner in support of achieving project Outcomes will be provided by staff in the UNDP Multi-Country Office in Samoa, UNDP Asia Pacific Regional Centre in Bangkok (with a Regional Technical Advisor on Adaptation out-posted in Samoa) as well as UNDP Headquarters (New York).

_____________________

David Sheppard

Director General

Secretariat of the Pacific Regional Environment Programme (SPREP)

19 May 2014

## Annex 8: Letter of Endorsement

Annex 9: SPREP's and UNDP’s Letters of Co-Finance

PO Box 240, Apia, Samoa 
E: sprep@sprep.org
T: +685 21929
F: +685 20231
W: www.sprep.org

The Pacific environment, sustaining our livelihoods and natural heritage in harmony with our cultures.

LETTER OF CO-FINANCE

23 May 2014

The UN Resident Coordinator

& UNDP Resident Representative

Apia, Samoa

The UNDP GEF Coordinator

304 E 45th St.

9th Floor New York, NY 10017

United States of America

Dear Sir/Madam,

LETTER OF SUPPORT FOR CO-FINANCING OF ‘ENHANCING CAPACITY TO DEVELOP GLOBAL AND REGIONAL ENVIRONMENTAL PROJECTS IN THE PACIFIC’ PROJECT

As indicated in the Project Document, this letter serves to reaffirm our co-financing through in-kind assistance to the value of US$ 1,484,502.60 for the above mentioned project. This amount is estimated based on the human resources allocated for this project, transportation, office space, internet and communication costs, and utilities over the lifetime of the project. In addition, we have secured USD 180,000 from the Commonwealth Government of Australia and USD 150,000 from the Government of the People's Republic of China for this project. This brings a total co-financing amount of USD 1,814,502.60.

We look forward to early implementation of the above project.

Yours sincerely,

David Sheppard

Director General

## Annex 10:	Environmental and Social Screening Summary

National Climate Finance Institutions Support Programme: SPREP. Draft Report, 16 May 2012.

From: Recommended Minimum Fiduciary Standards for GEF Implementing and Executing Agencies

National Climate Finance Institutions Support Programme: SPREP. Draft Report, 16 May 2012.

The Project Management Unit (PMU) will be an administrative extension of the MENR, with technical and administrative support from the UNDP-MCO Samoa and the UNDP GEF Regional Coordination Unit (RCU).

Summary table should include all financing of all kinds: GEF financing, co-financing, cash, in-kind, etc...

National Climate Finance Institutions Support Programme: SPREP. Draft Report, 16 May 2012.

Meeting minutes includes records of key meetings such as local, regional and national consultations regarding inputs on the design and implementation of the relevant output and associated activities.  Meetings may be individual or group meetings, with government officials or non-state stakeholders.

Internal Control Framework describes staff member accountabilities with reference to their role in the office. For simplicity, the ICF and guideline focuses on those roles considered most significant to internal control. An understanding of these roles is essential to understanding the internal controls described herein. It includes sections such as the ‘Definition of roles,’ describes specific roles and responsibilities, their authority, and their assigned user/management/approval profiles within the overall management procedures and processes for different aspects of SPREP's administration. The ICF also includes control checkpoints for procurement inter alia.

Direct Project Costs (DPC) are costs that are incurred by UNDP that are execution-driven and are incurred for, and can be traced in full to, the delivery of project inputs. These execution-related costs are completely separate and distinct from General Management Support (GMS) costs that are incurred by UNDP regardless of the implementation/execution modality chosen for the project.

In case of consultants, those tasks can be developed by the Procurement Unit (procurement of services).

This rate corresponds to the current standard “Travel Equalization Scheme” (TES) fee for the Regional Bureau for Asia and the Pacific. This fee aims to equalize the indifferences of financial costs of support services from the Regional Center in Bangkok and the Pacific Center in Fiji. This fee may be reviewed.