West Africa Regional Fisheries Program

Experiences and Selected Lessons from the First Phase of one of the World’s Largest Tropical Fisheries Governance Reform Programs

Discussion Paper for the Regional Workshop on Lessons Learned from the First Phase and Strategic Directions for Phase Two

February 13 and 14, 2017

Saly, Senegal

Prepared by: John Virdin

Nicholas Institute for Environmental Policy Solutions

Duke University

This paper was prepared as a basis for discussion at the regional workshop on the West Africa Regional Fisheries Program. The findings, interpretations, and conclusions expressed in this paper do not necessarily reflect the views of the World Bank. The World Bank does not guarantee the accuracy of the data included in this work.

Table of Contents

Executive Summary	3

I. Introduction and Objectives of the Paper	9

1.1 Introduction: The need for large-scale and context-specific governance reforms in the tropics to meet the SDG 14 target to reduce overfishing in the ocean	9

1.2 Objectives	11

II. Methodology	12

III. The Context for the WARFP in 2009	14

3.1 The Ecological Systems of West Africa’s Fisheries in 2009	14

3.2 The Social Systems of West Africa’s Fisheries in 2009	16

3.3 The Governance Systems for West Africa’s Fisheries in 2009	23

3.4 Outcomes from West Africa’s Fishery Systems in 2009	24

IV. The Fisheries Governance Reforms Introduced through the WARFP	32

4.1 Entry points for proposed governance reforms	32

4.2 Description of the fisheries governance reforms to be financed by the WARFP	33

V. Experiences with Fisheries Governance Reforms Supported by the WARFP	43

5.1 Cabo Verde	43

5.2 Guinea-Bissau	45

5.3 Liberia	47

5.4 Senegal	51

5.5 Sierra Leone	54

5.6 Regional – Sub-Regional Fisheries Commission (CSRP)	56

VI. Outcomes from Reforms and Some Key Lessons Learned	58

6.1 Outputs	58

6.2 Outcomes	61

6.3 Some Lessons Learned	62

VII. Considerations for the Future	67

Appendix I. WARFP Phase One Targets and Outputs	68

# Executive Summary

Introduction, objectives and methodology of the paper

The current level of ‘overfishing’ by commercial fleets in the global ocean is considered one of the major environmental problems of our time – with 31 percent of commercially targeted fish stocks that have been assessed considered as biologically overexploited by FAO. Overfishing is not only an environmental problem, but costs the world’s food supply an estimated 16.5 million tons of fish per year and the world’s economy an estimated $50 billion per year in foregone profits.  Critically, overfishing threatens an estimated 73.6 to 92.0 million jobs dependent upon fishing in the ocean – the ocean economy’s largest employer.

In 2013, experts estimated that reducing overfishing and rebuilding fish stocks will require a reduction in fishing effort by 36 to 43 percent from 2008 levels.  While there is certainly no single determinant of fishing behavior, a wide body of literature has identified failures in governance – defined here as the policies, rules and organizations that control or influence fishing activity – as one of the primary causes of current levels of overfishing. Where fishing rules have been strengthened and firm limits enforced, countries have shown that it is possible to reduce fishing rates and restore fish stocks, as emphasized in FAO’s 2016 State of World Fisheries and Aquaculture (SOFIA). However to date, most of these rebuilding efforts and successes have occurred in the more temperate waters under the jurisdiction of developed countries, while overfishing has increased the most in the tropical waters of developing countries – notably in Africa and Asia.  Relatively smaller scale cases of reform have shown success throughout these regions, but to date there are far fewer examples of tropical fisheries governance reform at a large spatial scale – and certainly no blueprints for states to follow, in fisheries that are incredibly diverse and complex systems.

This paper aims to document the experiences of arguably one of the largest (in terms of the spatial scale) tropical fisheries governance reform efforts to date: the West Africa Regional Fisheries Program (WARFP). While all fisheries are context-specific, the intention is to help add to the growing body of knowledge in the empirical literature on large-scale initiatives to reduce tropical overfishing, and particularly to support West African states in taking stock of progress made after completion of the first phase, some lessons learned and opportunities for further reform.

To achieve this objective, the paper draws upon reviews and periodic monitoring and trip reports prepared by staff of the Sub-Regional Fisheries Commission (CSRP) and the World Bank, in order to provide a historical description of the events that were documented during the first phase of the WARFP in the initial countries to participate: Cabo Verde, Guinea-Bissau, Liberia, Senegal and Sierra Leone. The paper synthesizes available data on outputs attributed to these events. Admittedly, this describes the events from the perspective of the CSRP and the World Bank, however these reflections were periodically documented and form the largest available data set to understand what occurred. Based on this data the paper suggests some key lessons learned from the first phase, as well as some considerations for the design of reforms to be supported in the next phase of the program. Of course care must be taken in drawing conclusions from the series of events in West Africa during the first phase of the WARFP and the historical explanation given to make connections between them, and the paper aims to make all assumptions explicit.

The context of West Africa’s fisheries in 2009 and rationale for the WARFP

The waters off of the coast of West Africa – defined here as the region from Mauritania to Ghana inclusive – have long been known as some of the most productive fishing grounds in the world. The full spectrum of vessels fish commercially in these waters, from small dugout canoes without motors, to larger motorized canoes that travel long distances, to industrial trawl and tuna fleets that are often foreign and rove between countries.  In the decades after independence the region integrated rapidly into international markets with harvests increasing exponentially between the 1960s and 2000.  By 2009 available data suggested annual harvests from West African waters on the order of 1.2 to 1.6 million tons annually. With an estimated wholesale value of some $2.5 billion in 2009, these harvests were also estimated at the time to support over 3 million direct and indirect jobs in the region, in several countries where fish contributed over half of per capita animal protein intake (Gambia, Ghana, Senegal and Sierra Leone) and between 5 to 10 percent of GDP (Guinea, Guinea-Bissau, Mauritania, Senegal and Sierra Leone). In particular, the small-scale fishing operations supported a majority of the jobs, with several countries’ fleets since estimated to support fishers and dependents equivalent to over 8 percent of the labor force in some countries (Ghana, Mauritania, Senegal and Sierra Leone).

While data was limited, all available information at the time suggested that despite rising production levels, most of the region’s commercially important stocks were considered as fully or overexploited (i.e. at a biomass lower than necessary to support the maximum sustainable yield), with the demersal fish in the northern countries the most severely overexploited. At the same time, World Bank analyses showed a consistent pattern of increasing fleets and costs, and often declining catch rates, with profitability in many of the fisheries also declining. Another prevalent though harder to measure outcome was the high levels of resources lost to illegal, unregulated and unreported fishing – estimated to be equivalent to 18 percent of the total harvest.

Given increasing fishing effort in the region and estimates for decreasing resources and economic benefits, the Sub-Regional Fisheries Commission (CSRP) established by seven of the countries facilitated discussions among the governments and stakeholders, with World Bank support, on the potential for a shared program of governance reforms to reduce overfishing and increase both the resource base and the benefits it could provide to the region. These discussions led to agreement among the CSRP’s member governments in 2007 and 2008 on a reform program with grant and concessional loan financing from the World Bank, entitled the West Africa Regional Fisheries Program (WARFP). Subsequently, as observers to the CSRP, both Liberia and Ghana expressed interest to participate in the program, particularly given the presence of some of the same industrial trawl fleets in their waters. For the World Bank, the WARFP would be one of the organization’s earliest and largest pilots in supporting countries to rebuild tropical fish resources at such a large spatial scale, with a design based on ‘learning by doing’ rather than any fixed blueprint.

Given the expected long timeframe for fisheries governance reform, the WARFP was designed as a multi-phase program, with each phase lasting for five years. Additionally, countries could begin when ready and participate on a rolling basis, rather than all having to begin at the same time. The first five countries to begin the program were Cabo Verde, Liberia, Senegal and Sierra Leone after the financing was approved by the World Bank in late 2009, and subsequently Guinea-Bissau in 2011.  Ghana, Guinea and Mauritania would subsequently begin as well, bringing the total financing provided to be on the order of over $140 million.

The WARFP program of fisheries governance reforms and experiences to date

The WARFP’s objective was articulated as a reform program to “sustainably increase the overall wealth generated by the exploitation of the marine fisheries resources of West Africa, and the proportion of that wealth captured by West African countries.”  The target for this increase over a ten-year period would subsequently be set as “the initial recovery of at least 7 overexploited fisheries in the region” and “at least a 25 percent increase in the net economic benefits to the region from the fisheries targeted by the program.” The program consisted of essentially a ‘clear-hold-build’ approach to fisheries governance reform for the region’s coastal fishery systems:

- Clear out illegal fishing by providing immediate support to West African countries to eliminate illegal fishing activities in their waters, stop the loss of products and economic returns as well as its contribution to overfishing;

- Hold these gains through governance reforms to reduce fishing effort to levels sufficient to allow the stocks to recover to sizes capable of supporting the maximum sustainable yield; and

- Build the infrastructure necessary to capture the benefits of reform locally through increased the domestic value added to the fish captured in the region’s waters at the processing, wholesaling and retail stages.

With this overall approach, the first phase of financing was approved by the World Bank for Cabo Verde, Liberia, Senegal and Sierra Leone at the end of 2009 for a period of five years, with at least a second phase of another five years of financing envisaged for each, as well as a grant to the CSRP to support the countries. Subsequently, the first phase of funding for Guinea-Bissau was approved in early 2011. The objective of the first round of WARFP-financed reforms was to strengthen the capacity of each country to govern and manage targeted fisheries (focused principally the coastal demersal fisheries), reduce illegal fishing and increase local value added to fish products – though admittedly each country introduced these reforms into a different and specific context.  In the final project documents and plans, the three components of the first phase of the program and its financing in these five countries were listed as:

- Good governance and sustainable management of the fisheries, including support to strengthen or reform state-level governance institutions (e.g. policy and legal frameworks, agency capacity to administer and monitor access), pilots in community management of coastal fisheries, and transition assistance for alternative livelihoods to fishing, where reforms were expected to reduce fishing effort;

- Reduction of illegal fishing, including increased sea and aerial surveillance patrols, establishment of satellite-based vessel monitoring systems and functioning fisheries monitoring centers; and

- Increasing the contribution of the marine fish resources to the local economies, through public investments in local fish landing infrastructure and competent authorities to regulate food quality of fish products for export.

As of late 2016, the first phase of the WARFP in Cabo Verde, Guinea-Bissau, Liberia, Senegal and Sierra Leone has achieved the largest volume of outputs and expected impact from these countries’ efforts to reduce illegal fishing. Although an imperfect measure, the ratio of infractions to vessels observed fishing dropped by roughly 50 percent or more in four of the five countries (though measures in Sierra Leone were not available after 2013), and in the fifth (Senegal) the coastal surveillance activities increased significantly. This decline in the ratio of fishing infractions was accompanied by a number of specific WARFP reforms:

- increased sea patrols in three of the five countries;

- establishment of a satellite-based vessel monitoring system for the industrial fleets operating in four of the five countries (in the fifth, Senegal, such a system was previously in place);

- construction and launch of a new fisheries monitoring center and coastal surveillance station in Guinea-Bissau;

- increased numbers of trained observers on the industrial vessels fishing in Liberia, and increased inspectors conducting fisheries surveillance in Cape Verde (together with surveillance stations on Sal and Maio);

- multi-donor partnerships strengthened or catalyzed in both Liberia and Sierra Leone to support fisheries surveillance, including together with United States Coast Guard and National Oceanic and Atmospheric Administration (NOAA) in Liberia, and the Government of the Isle of Man, the International Military Training and Advisory Team (IMATT) to Sierra Leone, and the Environmental Justice Foundation (EJF); and

- in four of the five countries, WARFP supported the establishment of inter-agency collaboration (e.g. joint committees) to enhance fisheries surveillance, based on formal memoranda of understanding.

These outputs resulted in a significant increase in arrests and fines for fishing infractions in a number of the countries, with a distribution skewed towards the early years of the WARFP, such that over time the detected fishing infractions, fines and arrests decreased in the coastal fisheries in Cabo Verde, Liberia and Sierra Leone – as would be predicted if actual infractions were trending downwards. For example in Liberia, during the first phase of the WARFP the government arrested or fined 48 fishing vessels for a total of over $6.4 million largely in the first three years, while the indicator on the rate of illegal coastal fishing dropped from 83 percent at baseline over time to 30 percent in 2015. Similarly, the high volume of arrests and fines occurred in the first few years of Sierra Leone. According to a number of reports, these efforts have been associated with increased yields for coastal communities, for example large fishing communities in Sierra Leone such as Tombo have subsequently reported a 42 percent increase in catch. Similarly, beginning in 2011 Liberian coastal communities experienced a change in fish availability with the sizes of all fish landed increasing and the overall volumes of fish caught more than double the levels in 2009 when the project began, according to sampling on fish landings carried out by the a citizen science program. World Bank trip reports recorded feedback from communities in Robertsport, Liberia that there as of 2015 there were far fewer incidents of illegal coastal trawling, and fish catch and revenues were increasing. Lastly, in Guinea-Bissau some $522,000 in fines was collected from enhanced surveillance patrolling in 2013 – early 2016.

In terms of outputs from additional efforts to strengthen governance, particularly to change the rules controlling fish harvesting and the organizations administering and monitoring them, the picture is somewhat more mixed.  At the national level, new policy statements were articulated and approved by the state in four of the five countries (and drafted in the fifth, Sierra Leone), and translated into draft laws and regulations in all cases – generally the product of several years of consultations and analysis at a minimum.  Additionally, in Senegal two fishery-specific policies and regulations (fisheries management plans) were completed and approved by the government. State registration of small-scale fishing vessels increased to between 80 to 100 percent in three countries, and in Guinea-Bissau such registration was not part of the targeted reforms (given the relatively small domestic small-scale fleet). Only in Senegal did the registration rate for small-scale vessels decrease, and notably the significant fleet operating outside the country’s waters remains largely unregistered. In total, some 37,000 canoes were registered across Cabo Verde, Liberia, Senegal and Sierra Leone. Registration for new small-scale vessels was frozen in Cabo Verde, and in Senegal efforts to begin to limit access to the small-scale fleet through the use of licenses (‘fishing permits’) have advanced only partially. New biological assessments and bio-economic analyses for the fish stocks and fisheries were conducted in Cabo Verde, Guinea-Bissau and Liberia.  Finally, a regional ‘dashboard’ for public disclosure of information on fishing licenses and public revenues is under construction and expected to be completed in 2016, with a number of countries beginning to publicly disclose this information.

The project’s targets for reduced fishing vessels (as a proxy for effort) via project-financed Government compensation in Cabo Verde and Senegal, were not achieved. Such reductions were not introduced until a new input control was formalized freezing the size of the fleet in 2014 in Cabo Verde (via a freeze in vessel registration), after which some 69 fishers received grants or subsidized loans in order to start new enterprises outside of the fisheries sector.  In Senegal, a rule freezing access to new industrial trawl vessels was in place at the start of the project, however no public ‘buy-backs’ of vessels occurred.

In terms of community management rights, the state recognized communities’ right to manage defined areas or fisheries in two sites in Cabo Verde, one in Liberia and eight in Senegal (while four sites are in progress towards recognition in Sierra Leone, and such pilots are not included in the Guinea-Bissau reform program due to the limited amount of coastal community fishing activity). The outputs from these pilots have been generally discussed as positive and encouraging in World Bank trip reports and monitoring documents, with communities introducing harvesting rule changes in many cases and in some reported evidence of local coastal demersal fish stocks rebuilding. In Senegal where these rights have been exercised over the longest time period, communities have reported a 133 percent increase in catch efficiency.

Lastly, in terms of building local infrastructure and skills to process more of the fish harvest within the region, a majority of the targeted outputs were not realized. No fish landing sites were completed in the first four countries (none were planned in Guinea-Bissau), due to a mix of inadequate planning during the preparation phase, errors in procurement processes for large construction contracts, poor quality of design and oversight work by contractors, and a general hesitancy to advance these activities prior to completion of governance reforms to better control harvesting operations (for fear that efficiencies gained from landing and processing infrastructure might send a price signal to increase harvesting).  However, the small-scale landing site at Robertsport in Liberia is expected to be completed by the end of 2016, provided that additional public funds are secured for budget shortfalls.  In Cabo Verde community freezing facilities are in place and functional in Sal island, and a new auction market at the fishing port has been established and is now operating on the island of Santiago.

In summary, according to the targeted outputs recorded in the project documents, the objective of the first phase of the WARFP in Cabo Verde, Guinea-Bissau, Liberia, Senegal and Sierra Leone has been partially achieved, with efforts to combat and reduce illegal fishing largely successful, and additional governance reforms partially introduced throughout the countries at different rates, while the activities targeted towards increased local processing and value addition to fish products were mostly not completed.

Some lessons learned and future considerations

Based upon the context at the beginning of the WARFP (Chapter III), the types of governance reforms introduced by the program (Chapter IV), and the available measures of WARFP outputs and associated changes in fisheries outcomes (Chapter V), the following five lessons were extracted:

- Tangible progress in combatting illegal fishing in West Africa was achieved as the first step in governance reform, with most of the WARFP’s targets met if not exceeded – though this will still require continued effort and investment to be sustained.

- Many West African states simply lacked the capacity to deliver fisheries governance reform at the spatial scales needed, with institutional frameworks creating/supporting agencies whose incentives may not always have been aligned to reform.

- A mismatch between the spatial scale of the ecological system and the rules governing the interaction with the social system was a key challenge for reform.

- Where these features (i.e. state agency delivery capacity and a spatial match between the ecological and social systems) were combined with inclusive decision-making – such as in community management pilots – harvest rules were changed to limit fishing effort and increase benefits.

- States underinvested in monitoring outcomes, and indicators may not have been designed to adequately measure WARFP objectives.

These lessons focus on the fundamental imperative of strengthened governance over fish harvesting as the basis for enhanced and sustained benefits from the fisheries for West Africa, but not on investments for increased local value addition.  Experiences from phase one suggest that enhancing the size and efficiency of the post-harvest segments of fishery value chains should wait until reforms have sufficiently advanced. The theoretical concern is that increased efficiencies in post-harvest operations would increase profits and send a signal to harvesters to produce more, which in the absence of effective rules would lead to increased fishing effort and potentially overexploitation. The practical experience was that proposed public investments in fish landing infrastructure in the WARFP may not have been justified for inclusion, as key pieces of the preparation (such as environmental impact assessments at the site level) were not completed.  Implementing such investments added to the complexity of the WARFP’s program of reforms and potentially increased the strains on state agencies charged with delivery.

Given these lessons, the focus of the second phase of the WARFP is suggested to be solely on continuing governance reforms (including combating illegal fishing). As such, the following seven steps are proposed for consideration by West African states as they identify and design the next round of fisheries governance reforms:

- Maintain efforts to combat illegal fishing at national and regional spatial scales, leveraging new technologies;

- Build upon the national-scale reforms (e.g. new policy statements, laws) to define the boundaries of the fishery systems to be governed and identify the specific entry points for reform (i.e. the spatial scales and jurisdictions of origin for reform), such as reforms to govern the small pelagic fishery at the regional scale with participating states as jurisdictions of origin, vs. coastal demersal fisheries at the local scale with co-governance between the state and communities;

- Drawing upon bio-economic modeling of potential scenarios or empirical observation, work with stakeholders in each system to identify and develop reforms to limit fishing effort as needed to achieve policy objectives, based upon expected benefits (compared to the counterfactual) – for example scaling up the number of community management pilots for coastal demersal fisheries;

- Ensure these proposed governance reforms are consistent with universally-agreed principles of equity, taking special account of small-scale fisheries;

- Estimate the financial costs of the proposed reforms over time, including compensation for any production expected to be foregone where reforms will reduce fishing effort;

- Carry out a ‘reality check’ or feasibility assessment on the capacity of the responsible state agency(ies) to deliver the reforms, including political feasibility and ‘governability’ from the literature on political economy (and particularly the distribution of the perceived economic costs of reforms); and

- Introduce enhanced monitoring of governance and fishery outcome measures together with the reforms.

In conclusion, WARFP-supported efforts to combat illegal fishing in the first five West African countries have met many of the targets for success, credited as much to the ‘software’ (i.e. the people and institutions) as the ‘hardware’ (e.g. patrol boats, surveillance equipment, monitoring centers, etc.). National-scale governance reforms have set clear principles and new policy objectives for the fisheries, and state agencies have begun to develop basic instruments for policy delivery, such as vessel registries, stock monitoring programs and public data dashboards. Where the spatial scale of the resources to be governed has matched the use patterns of coastal communities, such as in coastal demersal fisheries, pilots in state recognition and support of community management rights have generally met program targets and were considered successful in views reflected in CSRP and World Bank staff reports monitoring progress.

Going forward, the focus would be expected to shift towards defining and delineating specific fisheries for reform to limit access to levels that achieve states’ policy objectives, with access for small-scale fisheries secured as the priority. For nearshore sedentary fisheries such as those based on coastal demersal species, with state recognition and support communities have proven willing and able to manage the resources, though in some cases with need of transition assistance in the form of startup grants or micro-finance to pursue alternative livelihoods if fishing effort is reduced (or potentially conditional cash transfers). For all of these efforts, the key determinant will be the entry point to reform within the WARFP: the capability of the state agencies responsible for delivering the policies. Strengthening these agencies through internal reform and restructuring, external partnerships, and a shift towards a modus operandi of inclusive decision-making, will likely determine the success of subsequent phases of the WARFP.

# I. Introduction and Objectives of the Paper

## 1.1 Introduction: The need for large-scale and context-specific governance reforms in the tropics to meet the SDG 14 target to reduce overfishing in the ocean

The current status of many of the ocean’s fish stocks. The current level of ‘overfishing’ by commercial fleets in the global ocean is considered one of the major environmental problems of our time, notably for coastal and island developing countries (United Nations 2012). For the world’s ocean fish stocks that the United Nations Food and Agriculture Organization (FAO) has assessed since the 1950s, currently some 31 percent are considered as ‘overfished’ (FAO 2016), where the size of the stock is less than 40 percent of the amount that would be present in the ocean in the absence of fishing (Ye et al. 2011), often with significant impacts on wider ecosystems (Worm et al. 2009). This level of ‘overfishing’ has resulted in lost benefits that include an estimated 16.5 million tons of fish per year that could sustainably be added to the world’s food supply (Ye et al. 2013), and an estimated $50 billion per year in profits that could sustainably contribute to economic growth and poverty reduction (World Bank and FAO 2009). Similarly, overfishing threatens the estimated 73.6 to 92.0 million jobs dependent on fishing in the ocean – larger than all other sectors of the ocean economy which combine to support an estimated 31 million jobs (FAO 2012a, 2014; OECD 2016). Overfishing has been increasing the most in the tropical waters of developing countries, for example at a steady rate in African waters after the mid-1970s, and even more so in Asian waters where the number of fishing vessels more than doubled during this time period (Srinivasan et al. 2010). On top of these demands for food fish and fishing livelihoods, the world’s population is expected to grow to 9.6 billion by 2050 (UN DESA 2013).

The Sustainable Development Goal (SDG) to change the status of the ocean’s fish stocks and the benefits that they can sustain by 2020. Overfishing was recognized by states as a global problem during the United Nations Conference on the Environment and Development in 1992 (United Nations 1992). Since that time, states have set goals to end overfishing and rebuild ocean fish stocks, for example during the World Summit on Sustainable Development (WSSD) in 2002 as part of the Johannesburg Plan of Implementation (United Nations 2002), and at the 10th meeting of the Conference of the Parties to the Convention on Biological Diversity in 2010 as part of the Aichi biodiversity targets (Convention on Biological Diversity 2013). Following these precedents, on September 25, 2015 the United Nations General Assembly adopted a resolution setting 17 ‘Sustainable Development Goals’ and a number of more specific targets for progress towards solving selected global problems, including Goal 14 to “conserve and sustainably use the oceans, seas and marine resources for sustainable development”, with a target (14.4) to “effectively regulate harvesting and end overfishing, illegal, unreported and unregulated fishing and destructive fishing practices and implement science-based management plans, in order to restore fish stocks in the shortest time feasible, at least to levels that can produce maximum sustainable yield as determined by their biological characteristics” by 2020 (United Nations General Assembly, 2015).

Governance reform to change fishing behavior and subsequently the status of the ocean’s fish stocks, in order to achieve SDG 14. There is general scientific consensus that human fishing activity is the single biggest determinant of the biological status of ocean fish stocks, rather than fluctuations in ecological characteristics (Beddington et al, 2007, Worm et al., 2009). Global models have suggested that achieving targets such as those included in the Sustainable Development Goal (SDG) to ‘end overfishing’ and ‘restore fish stocks…to levels that can produce maximum sustainable yield’ will require a change in fishing behavior to reduce the amount of fishing effort by 36 to 43 percent from 2008 levels (Ye et al, 2013). While there is no single determinant of human behavior such as fishing, social scientists have increasingly characterized this type of complex interaction between humans and the natural environment as a socio-ecological system (SES) which includes: (i) ecological systems and their biophysical characteristics  in a given context, (ii) social systems and their characteristics, and (iii) governance institutions (i.e. the rules, norms and shared strategies in use) that regulate these interactions (Berkes et al., 2003; Ostrom, 2005; Lui et al, 2007; Levin and Clark, 2010; Perry et al., 2010; Ommer et al., 2011). Of these three types of sub-systems within a larger SES such as a given fishery, the governance institutions may be the most feasible to change (Ostrom, 2005), and hence a wide body of literature has identified failures in governance as the primary reason for current levels of overfishing (Garcia, 2005; Cochrane, 2009), and the key determinant of changes to these levels (Grafton et al, 2008).

Figure 1. Simplified Ocean Fishery Socio-Ecological System (SES)

Ecological Unit

Fish stock(s)

Processing Sub-System

Individuals, groups, companies

Harvest Sub-System

Fishing Fleets, Families, Communities

Wholesale & Retail Sub-System

Distributors, groups, companies

Consumer Sub-System

Consumer preferences

Ecological System

Social System

Fishing Effort

Yield

Governance

Filter

Source: Adapted from Charles, 2001; Ommer et al., 2011

The spatial scale of governance changes to influence fishing behavior. Fisheries throughout the ocean are not monolithic, but are as diverse as the different types of ecosystems and fish stocks that support them (Kooiman et al, 2005).  The international framework for governance of ocean fisheries, the United Nations Convention on the Law of the Sea (UNCLOS) Treaty, accommodates (partially) this diversity by providing states with the jurisdiction to make rules governing fishing activity in the coastal area of the sea where most of the world’s fisheries are located (Wang, 1992).  Given the diversity of ocean fisheries and the state-based institutional framework provided by UNCLOS, changes in governance to help achieve the SDG target for fisheries will be very context-specific on a case-by-case basis, within or between states. Perhaps in an ideal world a single global policy solution would be possible within the framework of UNCLOS, but ocean fisheries are far too heterogenous, including a wide range of different supply chains based upon very different types of fish resources (e.g. open ocean migrating species versus coastal bottom-dwelling species, etc.) and supporting ecosystems, such that individual fisheries are often defined at sub-national, national or regional scales (Charles, 2001). For this reason, policy solutions will need to be defined at the local and regional scale based on the biophysical characteristics of the ecosystems, and then aggregated in order to meet the SDG target.

Case studies in fisheries governance changes at the spatial scale of nation states, in the world’s tropical regions. Spatial mismatches between scales of governance and ecosystems are common (Crowder et al. 2008). The above paragraphs suggest the utility of empirical analysis to understand the types of governance reforms that could support progress towards the SDG target for fisheries in different contexts and at different scales. For many economic sectors, such as agriculture for example, there is a well-developed body of empirical analysis on governance reforms at the spatial scale of the state, but relatively little work in documenting large-scale fisheries governance reform (OECD, 2011). Alternatively, a wide body of literature exists on efforts at the level of specific fisheries, and a growing body on national-scale reforms in developed countries with temperate waters such as Iceland, New Zealand, Norway and the U.S. for example (FAO, 2000a; Cunningham et al, 2005; OECD, 2011). Overfishing actually first occurred in the temperate waters of developed countries (Srinivasan et al, 2010), and with notable exceptions many have reformed fisheries governance and reduced overfishing as a result (Worm et al., 2009). In contrast, relatively few cases of national or large-scale fisheries governance reform efforts have been documented in tropical developing countries, where the trends in overfishing are growing.  If the international community is to meet the SDG target, efforts to reform governance of fisheries in the tropics will need to occur at much larger spatial scales, supported by a greater body of empirical analysis. This paper aims to document the experiences with one of the largest tropical fisheries governance reform efforts to date in Africa, to help fill the knowledge gap in the empirical literature on large-scale initiatives to reduce tropical overfishing, where efforts may well need to be concentrated and prioritized in the coming year if the overfishing target under SDG 14 is to be met.

## 1.2 Objectives

This paper aims to fill a knowledge gap in the literature documenting experiences with governance reforms at a large spatial scale that have successfully reduced overfishing in the tropics, by synthesizing the observations and accounts from periodic monitoring and reporting by the World Bank and development partners over the first five years of the West Africa Regional Fisheries Program (WARFP).  This program is arguably one of the largest-scale fisheries governance reform efforts undertaken in Africa and perhaps all of the tropics to date, and the completion of the first of multiple phases of implementation after five years provides a useful opportunity to compare the outputs achieved to what was envisaged, and suggest some lessons learned and ways forward.

# II. Methodology

Following standard methods for qualitative analysis summarized by Miles and Huberman (1994), the paper begins by defining the scope of the overfishing problem in West Africa in 2009, in terms of the interacting ecological, social and governance systems throughout the region and the outcomes associated with this interaction over time, as the context for the introduction of the West Africa Regional Fisheries Program (WARFP) – Chapter III. Of course a full description of the ecological, social and governance systems comprising the region’s fisheries in 2009 would be beyond the scope of the paper, the intention is rather to provide the minimum context necessary to understand the rationale for the governance reforms taken at the time. With this context, Chapter IV of the paper describes in detail the components of the governance reforms that states and their agents committed to introduce with the support of WARFP financing, drawing large from the project document prepared by the World Bank, in order to change the outcomes associated with the fisheries and reduce overfishing.

Chapter V the paper draws upon reviews of periodic monitoring and trip reports prepared by staff of the Sub-Regional Fisheries Commission (CSRP) and the World Bank to provide a historical description of the events that were documented during the first phase of the WARFP, and syntheses of available data on outputs attributed to these events. Admittedly, this describes the events from the perspective of the CSRP and the World Bank, however these reflections were periodically documented and form the largest available data set to understand what took place.

To the extent possible, drawing upon syntheses of available date on outputs attributed to the events described previously, Chapter VI of the paper aims to derive conclusions on the outcomes potentially associated with the reform efforts undertaken to date with the support of the WARFP, and some key considerations and recommendations for the design of the reforms to be supported by the next phase.  Of course care must be taken in drawing conclusions from the series of events in West Africa during the first phase of the WARFP and the historical explanation given to make connections between them, with assumptions explicit (Miles and Huberman, 1994).  Even greater care must be taken in generalizing the conclusions from a case study such as the WARFP to other contexts (Agrawal, 2001), as the generalizability of explanations increases with the number of cases and comparative analysis across them (Miles and Huberman, 1994).

Scope of the Problem: The Context for the WARFP in 2009

- Ecological Systems (e.g. fish stocks)

- Social Systems (e.g. fish harvesters)

- Governance System (e.g. harvesting rules)

- Associated Outcomes

Figure 2. Roadmap to the Report

Response: Detailed Description of Fisheries Governance Reforms to be Supported by the WARFP

- Policy changes, rule changes and organizational changes

Summary of WARFP Experiences Supporting these Reforms

- Trip reports

- Monitoring data

Changes in Outcomes Associated with these Experiences

Some Lessons Learned

# III. The Context for the WARFP in 2009

## 3.1 The Ecological Systems of West Africa’s Fisheries in 2009

Box 1. Geographic Scope of the West Africa Regional Fisheries Program

Source: World Bank 2009

The West Africa Regional Fisheries Program (WARFP) includes 9 countries from Mauritania down to Ghana, spanning two large marine ecosystems (LMEs): the Canary Current LME beginning from the northern boundary of Morocco and extending down to Guinea-Bissau, and then the Guinea Current LME extending from this northern boundary down to the northern boundary of Angola.  Notably, the geographic scope of the WARFP was not defined in direct correspondence to these ecological boundaries, but rather based on the institutions for governance and the pattern of demand expressed by states. Thus, the term ‘West Africa’ is used in this report to cover the resources under the jurisdiction of coastal countries from Mauritania down to Ghana, inclusive.

Ecosystems. As described by Pauly and Christensen (1995), primary production in marine ecosystems can be related to the carrying capacity of an ecosystem for supporting fish resources. The marine ecosystems encompassed in the national waters of many coastal countries in West Africa, most notably Mauritania, Senegal, the Gambia and Guinea-Bissau (and to a lesser extent Guinea and Sierra Leone), due to exceptional ecological and climatic conditions have relatively high levels of phytoplankton production, which serves as the base of the diet of many marine animals, and provides the region with some of the richest fishing grounds in the world (MRAG 2005; OECD 2008; Sambe et al. 2016). These conditions include a seasonal upwelling that brings cold and nutrient-rich waters from depths of the Atlantic to the surface between the months of November and June, the presence of canyons that enhance its effect, relatively large continental shelves with rich rocky habitats, high volumes of freshwater inputs of nutrients, and numerous estuaries and mangroves that provide natural refuges and spawning grounds, among others (MRAG 2005; OECD 2008; Heileman and Tandstad 2008; Sambe et al. 2016).

Based on differences in these ecological conditions, the region could be divided into four sub-regions:

- Mauritania, Senegal, the Gambia and Guinea-Bissau:  This area receives the bulk of the effects of the seasonal upwelling from the Canary Current over the period from November to June, while beginning in June the Guinea Current causes an accumulation of warm water along the coasts, which combined with the amount of alluvium carried by the Senegal and Gambia rivers results in rich and varied marine fauna that make these waters considered as some of the world’s richest fishing grounds;

- Guinea and northern Sierra Leone: This area is characterized by the interface of the Senegal-Mauritanian and Gulf of Guinea hydrodynamic systems and benefits from the descent of nutrient-rich waters from the Canary Islands during the dry season (November to June), and the influx of nutrients from a number of coastal rivers during the rainy season, covering the widest continental shelf area in West Africa and dense mangrove forests;

- Southern Sierra Leone and Liberia (the grain coast): without the influence of upwelling this area is characterized by warmer waters year-round; and

- Cape Verde archipelago: includes islands of volcanic origin with a narrow continental shelf and much deeper waters, and without the influence of the Canary Current upwelling, such that productivity to support fisheries is lower (OECD 2008).

Fish Stocks. While there is a large range of fish species (including mollusks and crustaceans) harvested in the national waters of the coastal West African countries, the following species groups are most commonly harvested for commercial fisheries (see FAO 2011 and Heileman and Tandstad 2008):

- Tuna (Katsuwonis pelamis, Thunnus albacares, Thunnus obesus)

- Small pelagics, such as:

  - Sardine (Sardina pilchardus)

  - Sardinella (Sardinella aurita, Sardinella maderensis)

  - Anchovy (Engraulis encrasicolus)

  - Chub mackerel (Scomber japonicas)

  - Horse mackerel (Trachus spp.)

  - Bonga shad (Ethmalosa fimbriata)

- Coastal migratory pelagic finfish such as hakes (Merluccius merluccius, M. senegalensis, M. poli)

- Demersal finfish (incl. Pagellus belloti, Pseudotolithus spp., Dentex canariensis, Galeoides decadactylus, Brachydeuteris auritus, Lutjanus fulgus, etc.)

- Cephalopods (Octopus vulgaris, Sepia spp., Loligo vulgaris)

- Shrimps (Parapenaeus longirostris, Penaeus notalis)

Many of the stocks of these species groups are shared between two or more West African countries, notably the small and large pelagics such as sardines, anchovies and tuna.  Measures of the biomass of the region’s commercially-targeted fish stocks were rarely available, however for the five countries that served as the initial focus of the West Africa Regional Fisheries Program (Cape Verde, Guinea-Bissau, Liberia, Senegal and Sierra Leone), a number of estimates had been generated in the years preceding 2009 to support projections of maximum sustainable yield (MSY) – often given as the potential annual yield, and summarized in Table 1 below.  World Bank documents highlighted that the characteristics of the ecological systems supporting the region’s fisheries (notably the biomass of the targeted fish stocks) was difficult to assess in 2009, due to a dearth of data available (World Bank 2009).

Table 1. Summary of Most Recent Estimates Available in 2009 for MSY (mt/year) of Species Groups Supporting Key Commercial Fisheries in West Africa

|  | Cape Verde* | Guinea-Bissau** | Liberia*** | Senegal**** | Sierra Leone **** |
| --- | --- | --- | --- | --- | --- |
| Demersal Fish (bony fishes) | 3,790 – 9,425 | 59,000 | 8,303 – 22,484 | 100,000 – 130,000 | 18,000 |
| Cephalopods |  | 12,000 |  |  | N/A |
| Crustaceans |  | 3,600 |  |  | 2,600 |
| Small Pelagics | 7,500 – 9,300 | 105,000 | N/A | 200,000 – 450,000 | 116,860 |
| Tuna | 25,000 | N/A | N/A | 15,000 – 20,000 | 15,000 |
| Total | 36,290 – 43,725 | 179,600 | 8,303 – 22,484 | 450,000 | 152,460 |

Sources: Van Santen and Stobberup (2007); Guinea-Bissau Secretary of State for Fisheries (2010); Macfadyen, G. (2007); Mees, C. (2011); Van Santen et al. (2004); DFID, World Bank and FAO (2007) and Van Santen and Kamara (2006).

*The authors give a synthesis of existing estimates as of 2007, but note that these seemed to be generated on optimistic assumptions, and sustainable yields likely to be far lower in reality.

**Government estimates based on research campaigns conducted prior to the 1998-1999 Civil War, and subsequently in 2004 and for demersal species in 2008.

***Estimates given in 2011, based on 2007 biomass data generated from a survey by the Fridjof Nansen vessel, and catch data no later than 2010, but does not include small-scale ringnet fishery.

****Synthesis of data from 2002, noting that the small pelagic stocks are shared, spanning from the Bijagos in Guinea-Bissau to the border of Mauritania and Morocco, and hence this yield would be shared between those countries well.  Additionally, a sustainable yield of 20,000 mt/yr of deepwater demersals (e.g. prawns and hakes) was given.

****Synthesis of existing estimates, small pelagics estimate includes 70,000 mt/yr for ‘industrial small pelagics’, and assumes entire sustainable yield for ‘artisanal fisheries’ of 46,480 mt/yr consists of small pelagics.  Also does not include 10,000 mt/yr listed as ‘other industrial’ catch.  Previous assessments by FAO and USSR in the 1980s suggested a MSY of small pelagics on the order of 70,000 to 120,000 mt/yr; a MSY for cephalopods of 10,000 mt/yr, and a MSY for demersal fish of 18,000 to 45,000 mt/yr (later revised to 55,000 mt/yr and 33,000 mt/yr by the Institute for Marine Biology and Oceanography and the Ministry of Fisheries and Marine Resources respectively, in 2000).

While of course these estimates were based on limited data and indicative only, they suggested a magnitude for maximum sustainable yields from the waters under the jurisdiction of these five countries, on the order of:

- Coastal demersal species: 207,293 – 257,109 mt/yr,

- Small pelagic species: 429,360 mt/yr (with caveats above that this includes catch beyond these countries’ borders), and

- Tuna species: 55,000  - 60,000 mt/yr (again from transboundary stocks).

## 3.2 The Social Systems of West Africa’s Fisheries in 2009

As shown in Figure 1, the social systems interacting with the ecological systems in the waters of West Africa include the harvesting segment of the fisheries, the processing segment, the wholesale/retail segment and the consumers – all in a number discrete fishery systems and sub-systems.  In 2009, many of the fish resources harvested from West African waters were destined for foreign consumption – either overseas or inland within the continent.  The diversity of fleets harvesting the resources, households and companies processing and marketing them, and final markets for consumption were (and remain) poorly understood.

The harvesting segment. The fleets of fishing vessels operating in the waters of West Africa are diverse and form a spectrum from artisanal to industrial: from small dugout canoes without motors, to larger motorized canoes that carry ice boxes for storage and travel long distances, to large industrial trawl and tuna fleets that are often foreign and move between countries (FAO 2011). European fishing fleets have fished the West African coasts for several centuries and some even maintained a continuous presence since colonization (OECD 2008).  Given the productivity of the waters and the abundance of species with high commercial value, in the decades after independence the region integrated rapidly into international markets with high growth in fish production and exports from harvesting.  This period was characterized by rapid increases in harvests throughout West and Central Africa, from less than 300,000 mt in 1960 to almost 1.5 million mt in 2000 for all ECOWAS members plus Mauritania (Senegal, Mauritania and Ghana lone represented some 75 percent of the fishing effort) (OECD 2008).  By 2009 some 1.2 million mt of fish was harvested annually from West Africa’s waters according to data submitted to FAO, with small pelagics constituting the largest percentage of the total volume of production (FAO 2011).  World Bank estimates at the time placed the total West African harvest at roughly 1.6 million mt (World Bank 2009).

Figure 3. FAO Data on Marine Fisheries Production from West Africa’s Waters (1950 – 2009)

*Note: Does not include FAO categories of 'diadromous fishes' and 'miscellaneous aquatic animals'

Source: FAO Fishery Statistical Collections: Global Capture Production. http://www.fao.org/fishery/statistics/global-capture-production/en

As shown in Figure 3 above, FAO’s data showed a growing trend in production from the harvesting segment of West Africa’s fisheries systems since 2050.  Given that this data was recorded by the country where the fish was landed, according to the national flag on the vessel, this reflects largely domestic fleets (and particularly large small-scale fleets in Ghana and Senegal).  However, foreign fleets have been active in the region’s waters over this time period, for example a number of West African countries signed fishing access agreements with foreign fleets and governments, some of which may not have been captured in the FAO data (Zeller and Pauly 2015).  For this reason, the University of British Columbia’s Sea Around Us Project attempts to measure all of the catches in a country’s national waters (Exclusive Economic Zone or EEZ) by building off of the FAO data and including additional data sets from national and regional agencies, as well as estimates or literature on illegal, unreported and unregulated fishing (Zeller and Pauly 2015). As shown in Figure 4, these estimates are almost an order of magnitude higher, reflecting in particular the estimates of catches by foreign fleets in West African waters (Sea Around Us Project 2015).

Figure 4. Sea Around Us Project Data on Marine Fisheries Production from West Africa’s Waters (1950 – 2009)

Source: http://www.seaaroundus.org/data/#/eez

Small-scale fishing. Although no universally-agreed definition exists, the term small-scale fishing refers here to the dynamic and evolving sub-system of fisheries employing labor-intensive harvesting, processing and distribution technologies to exploit marine fishery resources, often targeted to supplying fish or fishery products to local and domestic markets (though increasingly as of 2009 supporting export markets in some cases) (FAO 2004).  In some countries, small-scale fisheries reflect centuries of tradition and practice in coastal communities, for example in Senegal – the region’s oldest fishing nation - where canoe fisheries steadily motorized beginning in the late 1940s and increasingly adopted foreign-imported gears such as monofilament nets (OECD 2008; Fontana and Samba 2013). While these cultures and traditions vary enormously along the coast of West Africa, some common techniques and technologies have proliferated, including hand lines, hook and line, set or drifting gillnets, and ring or circling nets, among others (see Table 2 below for examples from Liberia and Sierra Leone). In countries such as Ghana and Senegal these fisheries have grown dramatically over time with technological advances, for example in Senegal the canoe fleet (‘pirogues’) grew from 2,500 in 1947 to 3,700 in 1953, to 5,600 in 1972 and 12,000 in 2007 (Fontana and Samba 2013).

Table 2. Small-Scale Fishing Technologies in Liberia and Sierra Leone in 2009

| Country | Vessel | Propulsion | Length (m) | Gears | Crew (# persons) | Range (miles from shore) | Species |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Liberia | Kru canoe | Paddle or sail | Up to 7 | Gill net, hook & line, traps | 1 – 3 | 1 - 3 | Coastal demersals, Barracudas |
|  | Fanti canoe (or Ghana canoe) | Motor (side-mounted outboard engines of 10-15 hp) | Up to 20 | Gill net, ring net, set net, hook & line, beach seine |  | Up to 5 | Sardinella, Barracudas, Croakers, Sharks and Ilisha africana |
| Sierra Leone | Kru canoe | Paddle or long pole | Up to 6 | Hand line, hook & line, cast net, gill net | 1 | N/A | Barracudas, Coastal demersals |
|  | Standard 1–3 canoe | Paddle or sail | 6 - 8 | Hook & line, set net, drift net | 3 | N/A |  |
|  | Standard 3–5 canoe | Paddle or sail | 7 - 8 |  | 5 | N/A |  |
|  | Standard 5-10 canoe | Motor (25-40 hp outboard engines) |  | Ring net, bottom and drift gillnets, surface drift gillnet | Up to 10 | N/A | Barracudas, Coastal demersals, Small pelagics (herring, bonga, mackerel, etc.) |
|  | Ghana canoe | Motor (40 hp outboard engine | 15 - 20 | Ring net | 15 - 25 | N/A | Small pelagics (bonga, herring, etc.) |

Sources:  Mees (2011), MFMR (2010)

Table 3. Number of Small-Scale Fishing Vessels Operational in Most Recent Year Data Available in 2009*

| Country (Year) | Motorized Vessels | Non-Motorized Vessels | Total |
| --- | --- | --- | --- |
| Cape Verde (2006) | 756 | 280 | 1,036 |
| Guinea-Bissau (2011) | 246 | 1,274 | 1,520 |
| Liberia (2008) | 280 | 3,400 | 3,680 |
| Senegal (2004) | Approx. 12,000 |  | 12,000 |
| Sierra Leone (2006) | 1,650 | 9,350 | 11,000 |
| Total |  |  | 29,236 |

*Data for Guinea-Bissau given in 2011, the year for which the West Africa Regional Fisheries Program commenced there.

Sources: Van Santen et al. (2004); World Bank (2009); Guinea-Bissau Secretary of State for Fisheries (2013);

Industrial fishing. Foreign interest in fishing West African waters with industrial vessels has been high for decades, stretching back to the period just after World War Two (OECD 2008).  Throughout the region, foreign industrial vessels have typically migrated throughout countries’ waters, while joint ventures and domestic companies developed in the three main producers: Ghana, Mauritania and Senegal (for example in Senegal in 2000, 167 out of 201 licensed trawl vessels were registered nationally) (Van Santen et al 2004). Additionally, per requirements in the laws of many of the countries in the region, foreign companies wishing to apply for a license to fish from the government must use a local ‘fishing agent’ who will make the application to the government on behalf of the company (Interpol 2014).  As a result, a number of local companies have functioned as fishing agents for foreign companies to facilitate access foreign industrial vessels, e.g. in Liberia and Sierra Leone.

Both foreign and subsequently domestic industrial harvesting operations have typically differed and developed around three types:

- Bottom-trawling on the continental shelf for high-value coastal demersal finfish, crustaceans and cephalopods – using different gears and methods when trawling for finfish as compared to shrimp;

- Mid-water trawling for small pelagics in deeper waters, notably in the north where the stocks range from Guinea-Bissau to the northern border of Mauritania; and

- Tuna vessels such as purse seiners or longliners that follow the tuna stocks as they migrate across national borders and in the high seas.

In the five countries that served as the initial focus of the West Africa Regional Fisheries Program (Cape Verde, Guinea-Bissau, Liberia, Senegal and Sierra Leone), the total number of industrial vessels officially operating in years prior to 2009 for which data was available was on the order of 490 (though some or many of these may have been the same vessels operating in the waters of multiple countries) – in comparison to an estimated small-scale fleet on the order of more than 29,000 canoes (see Table 3 above) (OECD 2008; Mees 2011).

The harvesting segment in the five countries of Cape Verde, Guinea-Bissau, Liberia, Senegal and Sierra Leone produced almost 600,000 mt per year based on the most recent estimates available in 2009, as shown in Table 4.  In some cases, such as Senegal, the majority of this harvest was taken by small-scale fisheries, whereas in Guinea-Bissau the industrial fisheries predominated. In other cases, this dynamic had shifted as a result of exogenous shocks to the sector: for example in Sierra Leone the industrial fisheries produced a high of some 180,000 mt/yr in the early 1990s, declining to roughly 30,000 by 2009 as a result of the civil war and the exit of the Soviet fleet – while the small-scale annual harvest more than doubled after the year 2000 (Kaindeneh 2009).

Table 4. Summary of Most Recent Estimates Available in 2009 for Annual Harvest (mt) of Species Groups Supporting Key Commercial Fisheries in West Africa

|  | Cape Verde* | Guinea-Bissau** | Liberia*** | Senegal**** | Sierra Leone **** |
| --- | --- | --- | --- | --- | --- |
| Demersal Fish (bony fishes) | 1,222 | 17,626 | 15,000 (50% SSF; 50% Industrial) | 100,000 | 35,000 (77% SSF; 23% Industrial) |
| Cephalopods | N/A | 3,364 |  |  | 1,000 (Industrial) |
| Crustaceans | 30 | 1,241 |  |  | 1,400 (Industrial) |
| Small Pelagics | 2,860 (approx.. 50% SSF; 50% industrial) | 36,652 |  | 260,000 | 111,000 (76% SSF; 24% Industrial) |
| Tuna | 6,000 | 4,390 | N/A | 20,000 | N/A |
| Total | 10,112 | 67,641 (Industrial) | 15,000 | 380,000 (89% SSF; 11% Industrial) | 121,400 |

Note: SSF = Small-Scale Fisheries

Sources: Van Santen and Stobberup (2007); Guinea-Bissau Secretary of State for Fisheries (2013); Macfadyen, G. (2007); Van Santen et al. (2004); DFID, World Bank and FAO (2007) and Sesay (2009).

*Mean 1997 – 2001; **Data for the year 2008, for industrial vessel harvest only; ***Estimates for the year 2004; ****Landings in the year 2000; ****Estimates based on the year 2006.

The processing segment. Processing occurred at various stages in each of the five different countries, but a common feature of the different fishery systems and the value chains they formed, was the low level of harvest from the industrial fishing vessels that was actually landed within the region and processed locally – given that most of these vessels were foreign-registered (World Bank 2009). Hence with some exceptions, the majority of the harvest taken by industrial trawlers (both bottom and mid-water) was often transshipped at sea or in port to carrier vessels that often landed the fish in Europe (World Bank 2009).  Small-scale vessels alternatively, landed their catch within the region (though not always within the same country from whose waters the harvest was taken). This catch was often dried and smoked for local or regional consumption, for example in Sierra Leone by well-established systems of women processors working directly with fishing vessels (Kaindeneh 2009). For this reason the World Bank estimated that the small-scale harvests generated more than twice as much local value added to West Africa in 2009 as the foreign industrial harvest, even though the volume of the foreign industrial harvest was estimated to be more than two and half times larger than the volume of the small-scale harvest – essentially over 60% of the reported foreign industrial harvest was estimated to be landed overseas (World Bank 2009). Nonetheless, the processing systems and subsequent supply chains for small-scale fishery systems in West Africa were little studied in 2009, and those examinations that did take place, such as in Sierra Leone by Kaindeneh (2009), highlighted the fragmented nature of the small-scale value chains, notably the lack of postharvest facilities for proper handling of fishery products, as well as long supply lines.  In some cases, small-scale fisheries supplied high-value coastal demersal fish products for the European export market, essentially ensuring catch was preserved with ice and shipped via flights from Dakar (Van Santen et al. 2004).

The retail and consumption segment. Following on from the processing segment of the value chains emerging from West African fishery systems, the retail market and consumers for many of the products from the industrial harvesting segment were located in Europe – notably for fresh, high-value coastal demersal species – or in Asia, with Las Palmas a transit point (World Bank 2009).  Alternatively, the retail and consumption segments of the small-scale fisheries value chains were as complex as these systems themselves, often with distribution networks far inland or to other countries throughout the continent – for example fish imports from Guinea to Sierra Leone increased during the civil war (Kaindeneh 2009).

Box 2. Profile of Small-Scale Fish Processing in Sierra Leone in 2009

In 2009, Kaindeneh surveyed two different categories of fish trading operations in Sierra Leone: (i) frozen fish supplied by industrial vessels landing in Freetown, and (ii) smoked fish supplied from coastal communities – in this case Shenge, Tombo, Goderich and Yeliboya.  Returns from surveys of both in 2009 are given below:

The results above showed that the profitability of the frozen fish trade originating from industrial landings and processing in Freetown is much higher than the smoked fish trade based upon small-scale landings.  At the same time, there were very few people involved in the frozen fish trade, due largely to high initial investments required and the high risks given the lack of functioning refrigeration trucks to transport products from Freetown to inland markets where the demand was highest.

Source: Kaindeneh (2009)

In summary, to focus again on the example of Sierra Leone, the social system of the fisheries could be summarized in 2009 as shown in Table 5 below.

| Species Group (MSY in mt) | Harvesting |  |  | Processing | Retail/ Markets |
| --- | --- | --- | --- | --- | --- |
|  | Type | Catch (mt) | Vessels (Number) |  |  |
| Small Pelagics (116,860) | Small-Scale (Canoe) | 84,000 | 8,000 | Generally dried and smoked | Local or regional |
| Demersal Fish (18,000) |  | 27,000 |  |  |  |
|  | Industrial Bottom Trawl (fish) | 8,000 | 32 | At least 40 to 70% transshipped at sea or near Freetown for export; Remainder sold in Freetown market fresh |  |
| Cephalopods (N/A) |  | 1,000 |  |  |  |
| Crustaceans (2,600) | Industrial Bottom Trawl (shrimp) | 1,400 |  | 95% transshipped for export |  |

Table 5. Social System of Sierra Leone’s Fisheries in 2006

Sources: Sesay (2009); DFID, World Bank and FAO (2007) and Van Santen and Kamara (2006).

## 3.3 The Governance Systems for West Africa’s Fisheries in 2009

As indicated previously in Figure 1, governance was considered as the filter through which social and ecological systems interact. Definitions of governance as a concept, and its application to fisheries, vary from narrow to broader: for example the World Bank (2004) defined fisheries governance as an institutional framework including the policies, rules and organizations that provide a set of social prescriptions and procedures that control fishing activity (both formal and informal), while Kooiman et al. (2005) defined governance as the whole of public as well as private interactions taken to solve societal problems and create societal opportunities, which includes the formulation and application of principles guiding those interactions and care for institutions that enable them.  Here fisheries governance is defined as “a systemic concept relating to the exercise of control or influence over fishing activity by political, economic and social institutions, and the organizations emerging from them and articulating policies to implement or change them or establish new rules.”  Further, this concept can be deconstructed into three components: the policies (i.e. principals and objectives), rules and organizations.  While it would be beyond the scope of the paper to fully describe the status of these three components of governance in all of West Africa’s fishery systems in 2009, Table 6 below provides a brief overview of these key components for the first five countries to participate in the WARFP:

Table 6. Governance Framework for West Africa’s Fisheries in 2009

| Spatial Scale | Policy Statements | Rules | Organizations |
| --- | --- | --- | --- |
| Regional | Sub-Regional Fisheries Commission (CSRP) Strategic Action Plan 2002 – 2010 Focused on: - strengthened fish resource management - increased surveillance and enforcement to enhance compliance with national rules | Convention establishing the CSRP – March 29, 1985; with a mandate to harmonize fisheries policy in the region; governed by a board of Ministers of from the fisheries agency of each member county | CSRP A secretariat based in Dakar, Senegal Member states include: Cape Verde, Gambia, Guinea-Bissau, Guinea, Mauritania, Senegal and Sierra Leone |
| National Cape Verde Guinea-Bissau Liberia Senegal Sierra Leone | 2004 – 2014 Fisheries Management Plan | 1987 Fisheries Law (Law Decree nº17/87) | Fisheries Department, within the Ministry of Environment, Agriculture and Fisheries |
|  | 1996 Fisheries Management Plan (financed by USAID) | 1986 Fisheries Law | Secretary of State for Fisheries |
|  | N/A | 2009 Fisheries Regulation (draft) | Bureau of National Fisheries |
|  | 2008 Fisheries Sector Letter of Policy (LPS) | 1998 Fisheries Law and its Application Degree | Ministry of Fisheries and Maritime Economy |
|  | 2007 Fisheries Sector Strategy Paper (financed by DfID) | 1994 Fisheries Management and Development Act | Ministry of Fisheries and Marine Resources |
| Local | Site and context-specific |  |  |

Sources: Van Santen et al. (2003); Van Santen and Stobberup (2007); World Bank (2009)

Table 6 of course captures instruments of governance at the national or regional scale, but of course does not capture the wide range of governance influencing West Africa’s fisheries at other scales, such as at a local scale via formal government or through community and stakeholder institutions and organizations.  In terms of the rules that were in use for harvesting operations as a result of this governance framework, the World Bank assessed in 2009 that generally throughout the region (though certainly not in all cases):

- access for small-scale fishing operators was de jure and de facto open access, as in many cases access for these vessels was not regulated by the state (though in many cases was governed by customary rules); and

- access for industrial operators was regulated by the state via short-term, non-transferable licenses often accompanied by terms and conditions for the type of fishing that could take place.

## 3.4 Outcomes from West Africa’s Fishery Systems in 2009

Outcomes from the interaction of the ecological and social systems comprising West Africa’s fisheries were assessed in 2009 based on the limited data available.  While a diversity of indicators for the outcomes from these systems have been used in different contexts, typically monitored indicators of ecological outcomes include: (i) the biomass of the targeted stock(s) and (ii) the diversity of animal species and ecological structures; and for social outcomes include among others: (i) efficiency of harvesting operations as measured according to economic benefits and (ii) equity measures which are often context-specific.  In 2009, many of these outcome measures were incomplete or missing in West Africa.

| Box 3. Example of Overcapacity: Trends in Senegal’s Ocean Fishery Systems from 1960- 2000 |  |
| --- | --- |
| 1960s | Small-scale fleet supplies local and regional market First industrial shrimp trawlers start to operate |
| 1970s | Industrial fleet focuses on low value small pelagics; first industrial trawlers arrive and target cephalopods. The adoption of new techniques allows small-scale fisheries to target small pelagics. |
| 1980s | Industrial fisheries abandon small pelagics and starts exploiting high value demersal fish. Large numbers of trawlers of Korean origin start fishing for octopus (Octopus vulgaris), after local stocks expand. Export market surges following appearance of refrigerated containers. Small-scale fisheries recaptures market for small pelagics. |
| 1990s | Foreign fisheries operate under cover of fisheries agreements. Artisanal fisheries gradually increase efforts on coastal demersal fish for export. Overall catches of demersal fish – increasingly caught in waters of neighboring countries - surged until 1997, but decreased since then. |

Source: Van Santen et al. (2004)

Ecological outcomes.  In terms of the biomass of targeted West African fish stocks, very little information was available in 2009. Even though production levels had been steadily increasing, at the time most of the commercially important stocks in West Africa were considered as fully or overexploited (i.e. at a biomass lower than necessary to support the maximum sustainable yield), with the demersal fish in the northern countries the most severely overexploited, as shown in Table 7 (World Bank, 2009). For example, according to studies by the University of British Columbia, fishing activity along the West African coast tripled between the mid-1970s and mid-2000s, and by 2002 biomass of the high-value coastal sedentary stocks in the region had been reduced to a quarter of their levels in 1950 (World Bank, 2009). Levels of overexploitation were subsequently confirmed at a series of FAO working groups from 2008 to 2011 to assess the state of the region’s major fish resources (FAO, 2011).  Even the fast-growing sardine stock in the northern countries was considered overexploited (FAO, 2011).  Similarly, a number of fully exploited stocks were at risk of over-exploitation, given the trends in increasing production.

Table 7. West African Fish Stocks Considered Fully or Over-Exploited in 2009, according to FAO*

*English translation of common names

Source: World Bank, 2009

In addition to information on the biomass of targeted fish stocks, measurements of the diversity of animal species and ecological structures were not widely available in West Africa in 2009, e.g. levels of by-catch in bottom-trawl harvests or rates of mangrove forest loss among others.  However individual cases pointed to significant changes in ecological structures and animal species diversity, for example in Sierra Leone the composition of the harvest of shrimp trawlers was estimated in 2005 to consist of only some 15 percent shrimp species with the remainder as by-catch (Mees 2011).

Social Outcomes. While there are a range of measures of social outcomes, including the size and distribution of economic benefits (including between present and future generations) as well as cultural and religious values and benefits among others, the available data collected focused on the economic benefits that could contribute to poverty reduction.  In terms of the economic benefits, the analyses conducted by the World Bank prior to 2009 showed a consistent pattern of increasing fleets and costs, even as the resource base was fully or overexploited and often catch rates were declining (e.g. in small-scale fisheries in Cape Verde (Van Santen Stobberup 2007; World Bank 2009).  More detailed economic analysis of costs and revenues for domestic small-scale fleets in Senegal for example, showed declining profit margins to the extent that many fleets were operating at the ‘break-even’ point, suggesting fishing effort in the system at a level that costs were equivalent to gross revenues (i.e. ‘the bio-economic equilibrium’) (World Bank 2009).

For example as part of the assessments of West Africa’s fisheries during this period, the World Bank drew upon the most recent fish catch, effort and price data available to estimate the profitability of the coastal demersal fisheries in Senegal (excluding the region south of the Gambia), looking at the annual net economic benefits to the country from the fleet in three different measures: (i) excluding depreciation and costs of capital (actual cashflow generated); (ii) including depreciation and costs of capital (full economic benefits); and (iii) excluding returns to labor, if labor was given as a cost (assuming full opportunity cost to labor).  In both the small-scale and industrial fishing operations, the data available showed an overall declining trend in profitability since 2002, with cashflow below break-even for the small-scale operations (though fuel subsidies were not included) and relatively low for the industrial operations, per Figures 5 and 6 below:

Figure 5. Annual Net Economic Benefits from Small-Scale Harvests of Coastal Demersal Fish Species in Senegal (in US$)

(15,000,000)

(10,000,000)

(5,000,000)

-

5,000,000

10,000,000

15,000,000

20,000,000

25,000,000

30,000,000

35,000,000

2002

2003

2004

2005

2006

2007

Annual net benefits to economy from entire fleet (excluding depreciation & opportunity cost of capital)

Annual net benefits to economy from entire fleet (including depreciation & opportunity cost of capital)

Annual net benefits to economy from entire fleet (excluding returns to labor)

Source: World Bank estimates in 2009

Figure 6. Annual Net Economic Benefits from Industrial Harvests of Coastal Demersal Fish Species in Senegal (in US$)

Source: World Bank estimates in 2009

Despite declining profitability in many harvesting operations, employment throughout the region’s fishery systems remained high, in many cases expected to be pure economic benefits to the countries with little or no opportunity cost to labor (rather than included as a cost in profit estimates as shown in Figures 5 and 6 above). While the annual wholesale value of the harvest taken from the region’s waters was estimated by the World Bank to be on the order of some $2.5 billion annually, given that many fishery systems were considered to be operating near the bio-economic equilibrium, the economic benefits to the region from the harvesting segment were likely far below what they might have been at different levels of fish stock biomass, effort and incomes (World Bank 2009).  Similarly, the economic benefits to the region from the processing segment was also considered to be far lower than the potential, given the high levels of harvest – notably by the foreign industrial vessels – that was landed and processed outside of West Africa.

Nonetheless, given the economic stress observed in the harvesting segment of many of the region’s fishery systems, and the non-existence of a local processing segment in many cases, the World Bank characterized significant social outcomes to West Africa in 2009 from the fisheries, as shown in Table 8 below:

Table 8. Snapshot of Social Outcomes from West Africa’s Fisheries in 2009

| Country | Annual Reported Fish Catch (tons) | Contribution to GDP (%) | Employment (direct & indirect) | Contribution to Gov. Revenues (%) | Contribution to Total Export Revenues (%) | Contribution to Animal Protein Intake (%) |
| --- | --- | --- | --- | --- | --- | --- |
| Mauritania | 680,000 | 6.0 | 39,000 | 27 | 33 | N/A |
| Senegal | 368,000 | 4.9 | 600,000 | N/A | 37 | 70 |
| Gambia | 33,000 | 4.0 | 6,000 | 7 | N/A | 40 – 50 |
| Guinea-Bissau | N/A | 7 - 10 | 15,000 | 40 | N/A | N/A |
| Guinea | 94,000 | 6.0 | 112,000 | N/A | 10 - 30 | 40 |
| Cape Verde | 10,000 | 4.0 | 18,000 | N/A | N/A | N/A |
| Sierra Leone | 134,000 | 9.4 | 230,000 | N/A | N/A | 80 |
| Liberia | 15,000 | 3.2 | 33,000 | N/A | N/A | N/A |
| Ghana | 290,000 | 4.5 | 2,200,000 | N/A | N/A | 60 |
| TOTAL | 1,624,000 |  | 3,253,000 |  |  |  |

Sources: World Bank (2009)

Within the fishery systems of West Africa, Table 9 below highlights just how important the small-scale harvesting operations were to the social outcomes at the time, e.g. for both jobs and contribution to the economy.

Table 9. Examples of the contribution of small-scale fisheries to West Africa's economy in 2010

| Country | Fishers & Dependents as a % of the Labor Force (%) | Economic Impact – in GDP equivalent (%)* |
| --- | --- | --- |
| Cape Verde | <1 | 24 |
| Gambia | <1 | 20 |
| Ghana | 39 | 3 |
| Liberia | 3 | 10 |
| Mauritania | 8 | 12 |
| Senegal | 9 | 3 |
| Sierra Leone | 9 | 38 |

*Economic impact based on 4.3 additional dollars injected into the economy for every 1 dollar produced by small-scale fisheries

Source: Belhabib et al, 2015

At the same time that profitability in many of the fisheries was declining, with particular concern for the small-scale fisheries given the central role that they played in jobs and incomes for so many coastal communities, another prevalent though harder to measure outcome was the high levels of resources lost to illegal activities (FAO 2011). At the time, some West African countries were estimated to experience illegal harvests in their waters equivalent to 30 percent of the value of the legal harvests (World Bank 2009). Throughout the region, an estimated 18 percent of the total harvest was taken via illegal, unregulated or unreported methods (MRAG 2005), or the World Bank estimated this rate to be equivalent to 277,000 mt per year with a wholesale value of $457 million (World Bank 2009).

In conclusion, an assessment by the World Bank of the outcomes from the interaction of the ecological and social systems in West Africa’s fisheries, as controlled by the filter of governance, suggested some of the following key features among the diversity of different fishery systems in the region:

- A complex and diverse set of fishery systems, where the resources were often shared across borders, targeted jointly by large industrialized foreign fleets (some of whom were fishing under explicit foreign access agreements with West African Governments) and tens of thousands of small-scale vessels (canoes often fishing with outboard motors and ice boxes) from countries such as Ghana and Senegal, traveling long distances up and down the coast and generally targeting multiple species at a time.

- Lack of information on the ecological systems, in terms of the biomass of targeted stocks based on fisheries dependent and independent data, and in terms of the diversity of animal species and ecological structures which collectively contribute to fish resource productivity, and on othe social systems, notably in terms of how the fisheries performed economically and for whom.  In particular, estimates of sustainable yields from commercially valuable fish stocks were outdated at best, as well as fisheries-independent assessments of stock abundance (compared to unfished states).

- Weak or poorly defined governance institutions for management of the fisheries at almost all levels, together with organizations incapacitated to act as agents for the state, particularly to monitor the fisheries and enforce compliance with laws and regulations.  The scale of illegal fishing underway at the time was estimated to be at a volume almost as high as the amount of fish caught legally in some countries (in some cases by domestic small-scale fleets fishing in neighbouring waters), for example in Guinea (and likely Liberia, although no data existed). Similarly, the illegal catch in Guinea-Bissau was estimated to be equivalent to roughly 40 percent of the legal catch, and 35 percent in Sierra Leone (World Bank 2009). In some cases this led to direct conflicts, such as in nearshore waters (often less than 6 miles from the coast) where industrial trawling was prohibited yet frequently occurring – together with small-scale fishing vessels (Interpol 2014).

- Many countries lacked the basic fish landing and food safety control infrastructure and investment climate needed to attract local investment in fish processing, wholesaling and retailing activities, or to be competitive with equally accessible destinations such as Las Palmas. For example, Guinea-Bissau, Guinea, Sierra Leone and Liberia all lacked the basic port infrastructure to support significant industrial vessels to land their fish, and almost all countries in the region lacked the adequate infrastructure to provide the necessary support to small-scale fish landings (either to process landed fish for local consumption or for exports). Furthermore, at least one third of the nine participating countries did not have a sanitary authority certified to export to the European markets in 2009 (World Bank, 2009). The World Bank hypothesized at the time that the weakness in governance institutions likely constrained private investment in local value addition in a number of countries – indeed the IFC indicated at the time that the risk was too high in order to invest due in part to concerns over sustainability of supply in the current context (World Bank 2009).

In the context of these constraints, all available measures suggested increased fishing effort and rising yields throughout the majority of West Africa’s fishery systems, associated with declining trends in ecological and social outcomes (as measured by the decreasing biomass of targeted fish stocks and decreasing net economic benefits to the region, respectively).  The one countervailing social outcome for many countries was the increasing provision of labor in the small-scale fish harvesting operations, though this was accompanied in some cases by a decrease in incomes (potentially reflecting declining catch rates per vessel, as effort may have been increasing faster than harvests, or at rates beyond the maximum harvest the stocks could sustain).  Figure 7 provides a simple illustration of these trends to fishery systems in West Africa.

Ecological Unit

Fish stock(s)

Processing Sub-System

Individuals, groups, companies

Harvest Sub-System

Fishing Fleets, Families, Communities

Wholesale & Retail Sub-System

Distributors, groups, companies

Consumer Sub-System

Consumer preferences

Ecological System

Biomass of targeted stocks decreasing

Social System

Net economic benefits to West Africa decreasing (e.g. incomes), labor increasing

Fishing Effort

Increasing

Regulated Yield Increasing

Illegal and Unregulated Yield Increasing

Governance

Filter

Processing & Retail of Industrial Harvest largely outside of West Africa

* Key Trends added in Green

Figure 7. Simplified Ocean Fishery Socio-Ecological System (SES) with Key Trends in West Africa in 2009*

## IV. The Fisheries Governance Reforms Introduced through the WARFP

Given the context described in Chapter III and specifically the indications of resource overexploitation and declining benefits synthesized in the World Bank’s country-specific fisheries analyses conducted between 2003 and 2007, governments and the World Bank began discussions in 2007 on possible governance reforms to improve outcomes and help implement the region’s Strategic Action Plan 2002 – 2010, facilitated by the CSRP.  These discussions broadened to include a wide range of stakeholders and resulted in the identification of a program of reform with financing from the World Bank, titled the West Africa Regional Fisheries Program (WARFP), which was endorsed by the CSRP members at meetings in October 2007 and December 2008.  Subsequently, as observers to the CSRP, both Liberia and Ghana expressed interest to participate in the program, notably given the presence of some of the same industrial trawl fleets in their waters (World Bank, 2009).

The CSRP member countries had some experience working together on region-wide fisheries governance reforms, such as through collaborative surveillance missions, but on a much smaller scale than envisaged in the WARFP.  At the same time, World Bank had relatively little experience financing countries efforts to reform fisheries governance when the first discussions began in 2007. While the Bank had extensive experience in supporting fisheries development in preceding decades until the 1980s, it was only in 2004 that the institution formally re-engaged in supporting the sector after a long absence, with a new focus on sustainable fisheries management (World Bank, 2004).  Shifting from a development focus to a resource management focus, the Bank had begun to support investments to reform or strengthen fisheries governance, for example in the Indonesia Coral Reef Rehabilitation and Management Program (COREMAP), the Tanzania Marine and Coastal Environmental Management Project (MACEMP, and the Senegal Integrated Coastal and Maritime Resource Management Project (GIRMaC), among others. However, the Senegal and Tanzania efforts were still underway at the time, and the Indonesia program had shifted significantly in 2004 with the second phase, so there was not a wealth of experience throughout the organization in efforts to reform tropical fisheries governance at a large spatial scale.  Similarly, many of the examples cited in the approach paper that led to the 2004 re-engagement were from vastly different contexts in the developing world, such as Iceland, New Zealand, Norway or the United States, and had typically occurred over a time period on the order of 10 to 20 years (World Bank 2004).  Hence, the WARFP would be one of the World Bank’s earliest and largest pilots in supporting countries to rebuild tropical fish resources, with a design based on ‘learning by doing’ rather than any fixed blueprint.

## 4.1 Entry points for proposed governance reforms

The governance reforms proposed in the WARFP emerged from the discussions between the governments in the region, a range of stakeholders and the World Bank, such that the state was the jurisdiction of origin for reform with financing support from the Bank. The CSRP secretariat played a fundamental role in facilitating and supporting the development and implementation of a common reform program, but the decisions taken, and the reforms themselves, originated at the state level with governments. The spatial scale of the reforms was determined by opportunity as much as ecology, with CSRP members sharing fish resources in some cases, and/or resource users (e.g. mobile fleets, including those fishing illegally as shown in Box 4), as well as simply the opportunity to capture economies of scale in reforms in some instances. The large area included multiple and overlapping fishery systems, for example where a small pelagic stock and fleet might span several nations, while coastal demersal stocks would be more sedentary on the shelf though often exploited by mobile fleets.  The zone of reform, from Mauritania down to Ghana, exceeded

Box 4. Estimated Flow of Illegal Fishing in West Africa in 2009

Source: MRAG (2009)

the boundaries of any one ecosystem (e.g. including both the Canary Current and Guinea Current large marine ecosystems) and any one governing body (e.g. including Ghana and Liberia in addition to the CSRP).

Within this large area of West Africa, the reforms initially targeted the region’s coastal demersal fishery systems, with the government of each participating country envisaging to introduce governance reforms at essentially two common spatial scales:

- at the national scale, in order to develop or articulate new policy principles and objectives, and/or to significantly enhance the capacity of organizations to deliver policies (e.g. enhanced surveillance and enforcement of existing rules such as the ban on bottom trawling within 6 miles of the coast, or increased registration of fishing canoes, new resource assessments, etc.); and/or

- at the local scale, through establishment of co-governance partnerships between the government and user groups in order to create community management rights over defined ocean areas, together with ongoing support from state agencies and surveillance and enforcement of new rules formulated by communities.

The costs of implementing the reforms would be financed by the World Bank via a series of grants and concessional loans directly to the governments of each participating country, in each case for two phases of five years (reflecting the understanding of the long time period needed) (World Bank 2009).  The WARFP was structured such that countries could begin when ready and participate on a rolling basis, rather than all countries having to initiate the effort at the same time. This financing instrument also had the benefit of allowing West African governments with relatively small allocations of concessionary pools of finance from the World Bank, to access an additional ‘window’ of concessionary lending available only for such regional programs as an incentive for multi-country cooperation and integration (World Bank 2009). Hence the first five countries to begin the program were Cape Verde, Liberia, Senegal and Sierra Leone after the financing was approved by the World Bank in late 2009, and subsequently Guinea-Bissau in 2011.  Given that a number of West Africa countries had relatively small populations (and concessional financing from the Bank was allocated at least in part based on population), such financing was already scarce and this provided an additional incentive for Ministries of Finance to prioritize the sector.

## 4.2 Description of the fisheries governance reforms to be financed by the WARFP

With a long-term financing commitment from the World Bank possible, the discussions among governments and stakeholders in 2007 focused initially on the loss of economic value due to high levels of illegal fishing and insufficient government agency resources to conduct surveillance operations (World Bank 2009). As mentioned previously, a 2005 (MRAG) study indicated that fish with an estimated wholesale value on the order of $450 million were harvested each year from West Africa’s waters via illegal, unreported or unregulated (IUU) fishing activity. During the WARFP preparation period from 2007 to 2009, the World Bank funded an updated assessment of IUU fishing in West Africa estimating consistently high losses due to illegal fishing in a number of countries, notably Guinea-Bissau, Guinea and Sierra Leone, among others (MRAG, 2009). Given that many of the users and likely illegal fishers were foreign fleets migrating across national boundaries (analogous to Olson’s (1993) as ‘roving bandits’), a number of stakeholder consultations indicated coastal communities’ unwillingness to participate in reforms before the existing laws were enforced – notably the exclusion of industrial trawling from the near-shore waters in Liberia and Sierra Leone. With the level of illegal fishing in these two countries, as well as Guinea and Guinea-Bissau, enhancing the capacity of agencies to enforce compliance with the existing rules was seen as a pre-requisite to any further reform. Hence, one of the early priorities of the WARFP was a focus on clearing out the illegal fishing under the institutional frameworks currently in place in 2009, to create the space for discussions and work on wider governance reform and strengthening.

Box 5.  A Natural Capital Approach in Fisheries

The design of the WARFP reflected a perspective on fish stocks as natural capital assets of the countries, which could provide significantly more economic returns for shared growth and subsequently poverty reduction, if the region’s fisheries governance institutions were reformed or strengthened in order to limit fishing effort as needed to maintain or rebuild the fish stocks to levels that could support the MSY. This natural capital accounting perspective drew from the World Bank (2006) publication entitled ‘Where is the wealth of nations?’, to describe stocks of natural resources as part of a country’s portfolio of assets, i.e. an item of economic value or able to produce a flow of benefits such as income. A country’s total wealth was considered as comprised of three types of assets: (i) natural capital such as fish stocks in the ocean, (ii) produced capital (machinery and structures, urban land), and (iii) intangible capital (skills, expertise, etc. with which labor is applied) (World Bank, 2006).  A country’s gross domestic product (GDP) was considered as essentially the economic returns on its total capital or wealth, which could be measured as the present value of future consumption, and economic growth would be achieved by increasing a country’s total wealth, i.e. the total value of its different assets (i.e. by investing the surplus benefits from a country’s assets into growing the future value of those or other assets – saving and investing) (World Bank, 2006). Shared economic growth in a country, where the increasing flow of benefits from the assets is shared widely among the population, was then considered the most successful way to reduce poverty (World Bank, 2006).

The economic benefits of fisheries governance reform was illustrated at the global scale in a study conducted jointly by the World Bank and FAO entitled ‘The Sunken Billions: the Economic Justification for Fishing Reform’ (World Bank and FAO, 2009), which showed significant efficiency gains from reducing fishing effort to restore biomass levels.  The economic justification for the World Bank’s investment in West African fisheries rested on the need for financing of transition costs of governance reforms to reduce fishing effort and rebuild fish stocks (and the stream of benefits from harvesting them) (World Bank, 2009).

At the outset in late 2007, the WARFP was conceived only to this point: as a regional reform program to reduce illegal fishing in the waters of West African countries, and thereby enhance the contribution of the fisheries to economic growth.  However, during the design phase the focus shifted quickly to ensuring that the governance institutions would be in place to safeguard the gains made from reducing illegal fishing, and regulate fishing activity more sustainably. WARFP preparation efforts during this period included the preparation of a study by FAO (2009) on fisheries governance, which proposed institutional reforms at the scale of the coastal fishery systems in the waters above the shelf in the countries. According to the WARFP project document, the institutions for access to the region’s coastal fisheries could be changed in context-specific ways to limit fishing effort to levels that would rebuild or maintain the fish stocks to sizes that could support harvests comparable to a maximum sustainable yield, while enhancing the property rights characteristics of access to increase the economic benefits generated for West Africa (World Bank 2009).

Where governance reforms and enhanced limits on fishing effort might be expected to reduce catches and returns for West African fishers during a transition phase until the stocks recovered, the WARFP included mechanisms aimed at providing compensation or alternative livelihood opportunities – consistent with the World Bank’s social safeguard policy requirements on involuntary resettlement and restriction of access to resources by traditional users (World Bank 2009). Finally, governments were eager to capitalize on the perceived benefits of governance reforms and expected stock recovery, by investing in fish landing infrastructure and local skills development in order to encourage more processing in West Africa of the fish caught in the region’s waters, and thereby increase economic returns and local employment along the value chain (World Bank, 2009).

As the scope of the reforms widened – from strengthening compliance with the existing institutional framework to reforming it in order to better govern fishing activities – a remaining issue gained attention.  Even if the institutional framework is reformed and greater benefits generated from the fisheries, West African countries argued that all too often these benefits were leaving the region.   For this reason, a third pillar to the program was developed: to develop the local skills, equipment and infrastructure needed  to support greater local value added to fish products and higher levels of fish exports, to help bring some of the fisheries economy onshore.

In summary, through the analyses, discussions and collaborations between government agencies in West Africa, stakeholders in the fisheries and the World Bank, the WARFP’s objective was articulated as a reform program to “sustainably increase the overall wealth generated by the exploitation of marine fisheries resources of West Africa, and the proportion of that wealth captured by West African countries” (World Bank 2009).  The target for this increase over a ten-year period would subsequently be set as “the initial recovery of at least 7 overexploited fisheries in the region” and “at least a 25% increase in the net economic benefits to the region from the fisheries targeted by the program” (World Bank 2009).

In summary, the preparation phase of the WARFP had produced a ‘clear-hold-build’ approach to fisheries governance reform for the region’s coastal fishery systems:

- Clear out illegal fishing by providing immediate support to West African countries to eliminate illegal fishing activities in their waters, stop the loss of products and economic returns as well as its contribution to overfishing;

- Hold these gains through governance reforms to reduce fishing effort to levels sufficient to allow the stocks to recover to sizes capable of supporting the maximum sustainable yield; and

- Build the infrastructure necessary to capture the benefits of reform locally through increased the domestic value added to the fish captured in the region’s waters at the processing, wholesaling and retail stages (World Bank, 2009).

With this overall approach, the first phase of financing was approved by the World Bank for Cape Verde, Liberia, Senegal and Sierra Leone at the end of 2009 for a period of five years, with at least a second phase of another five years of financing envisaged for each (with potentially a third phase as needed), as well as a grant to the CSRP to support the countries (World Bank 2009; World Bank 2011). Subsequently, the first phase of funding for Guinea-Bissau was approved in early 2011, also for five years with a second phase of five years envisaged (World Bank 2011b). The objective of the first round of WARFP-financed reforms was to strengthen the capacity of each country to govern and manage targeted fisheries (principally the coastal demersal fisheries), reduce illegal fishing and increase local value added to fish products – though admittedly each country introduced these reforms into a different and specific context (World Bank 2009; World Bank 2011b).  In the final project documents and plans, the three components of the first phase of the program and its financing in these five countries were listed as:

- Good governance and sustainable management of the fisheries,

- Reduction of illegal fishing, and

- Increasing the contribution of the marine fish resources to the local economies.

More specifically, these three components of reform translated into the following menu of activities financed by the WARFP in each of the five countries during the first phase:

Component one focused on institutions for good governance, including:

- Strengthening or reform of state-level institutions for fisheries governance, beginning with:

  - articulation of new statements of each country’s policy objectives for the fisheries,

  - revision of the legal frameworks and public agencies for carrying it out,

  - the preparation of fishery-specific regulations (e.g. management plans), and

  - enhanced capacity of state agencies to deliver on the policy, including:

    - nation-wide registration of all fishing vessels,

    - enhanced transparency in fishing licenses, and

    - expanded monitoring to increase the information base required for reform – particularly on the biological and economic status of the fisheries;

- The establishment of co-governance partnerships with communities to manage sedentary fish resources in adjacent and defined coastal areas, often in the form of territorial use rights fisheries (TURFs);

- For targeted overexploited fisheries where regulations are introduced to reduce fishing activity to help rebuild the resource stock, the provision of transition assistance to those adversely impacted (e.g. training and small grants); and

- Government communication of the objectives and status of the reform process, to raise awareness and participation (World Bank 2009).

Notably in this component, a common thread to governance reforms was a change to access rules in order for the state to recognize resource management rights for communities over demersal fisheries in adjacent waters, based on extension efforts by state fisheries agencies (World Bank 2009).  Additionally, as indicated above a significant focus of the reforms supported was to enhance the capacity and activities of national agencies to administer rules for access to the resources, including enhanced transparency in the licensing of access for industrial vessels, increased communication and dialogue with resource users and communities, and increased registration of fishing vessels (World Bank, 2009). Additionally, changes to state fisheries agencies included increased fisheries, research, assessment and monitoring in order to expand the information base required for reform, including stock assessments for coastal demersal species (World Bank, 2009).

Component two focused on reducing illegal fishing, included:

- Support for operational planning by state agencies to conduct fisheries surveillance, including coordination between various agencies (in the form of multiple-agency coordinating committees in some cases);

- Expanding aerial and sea patrols for fisheries surveillance, including procurement and/or lease of vessels and project financing of their operating costs, in order to increase the number of patrol days at sea; and

- Establishment or expansion of a satellite-based fishing vessel monitoring systems, together with fisheries monitoring centers for state agencies to track fishing activity and plan surveillance patrols and activities.

Component three focused on investments for greater value added locally, included:

- Public investments in infrastructure for fish landing site clusters, including private partners to provide small processing hubs; and

- Strengthened capacity for state agencies designated as competent authorities to regulate food quality of fish products, to be able to meet requirements for exports to the European market.

Table 10 below summarizes the characteristics of the specific governance reforms agreed in the project document and approved by the Governments.

Table 10. Summary of the types of fisheries governance reforms proposed in WARFP Phase I

| Country | Entry Points | Governance Changes |  |  |
| --- | --- | --- | --- | --- |
|  |  | Policy | Rules | Organizations |
| Cabo Verde | Spatial scale: National Jurisdiction of origin: State | Articulation of a new national policy statement for ocean fishery systems, specifically a mid-term evaluation of the implementation of the Fisheries Sector Management Plan 2004 – 2014, and then development of any necessary revisions to the Plan | N/A | Enhanced national agency capacity and activities for administration of rules for access, including enhanced transparency in the licensing of access for industrial vessels, increased communication and dialogue with resource users and communities, increased registration of fishing vessels Increased research, assessment and monitoring in order to expand the information base required for reform, including stock assessments for coastal demersal species Enhanced national agency surveillance and enforcement of existing rules (including expanded sea and aerial patrols, increased training, construction of two surveillance outposts) |
|  | Spatial scale: Local Jurisdiction of origin: Co-Governance | N/A | Community management rights over adjacent areas of the sea (expected to result in the introduction of a range of technical measures, including gear restrictions, closed areas, etc.) in two pilot areas | Extension by national fisheries agency |
| Guinea-Bissau | Spatial scale: National Jurisdiction of origin: State | Review of the delivery capacity needs for the existing draft national policy statement (National Fisheries Strategy) | Revision of the general fisheries law and introduction of new regulations, with a focus on incentives for industrial harvesting operations to land catch locally Development of new regulations (management plans) for coastal demersal fisheries | Enhanced national agency capacity and activities for administration of rules for access, including enhanced transparency in the licensing of access for industrial vessels, increased communication and dialogue with resource users and communities, increased registration of fishing vessels Increased research, assessment and monitoring in order to expand the information base required for reform, including working with a university to build a research program and conduct resource assessments Enhanced national agency surveillance and enforcement of existing rules (including expanded sea and aerial patrols, increased training, observers on industrial vessels, establishment of a satellite-based fishing vessel monitoring system, linked to a fisheries monitoring center, two surveillance stations) |
| Liberia | Spatial scale: National Jurisdiction of origin: State | Articulation of a new national policy statement for ocean fishery systems, together with a new law to formalize principles and objectives Development of new policy objectives for the coastal demersal fisheries | Input controls for industrial vessels | Enhanced national agency capacity and activities for administration of rules for access, including enhanced transparency in the licensing of access for industrial vessels, increased communication and dialogue with resource users and communities, increased registration of fishing vessels Increased research, assessment and monitoring in order to expand the information base required for reform, including working with a university to build a research program and conduct resource assessments Enhanced national agency surveillance and enforcement of existing rules (including expanded sea and aerial patrols, increased training, observers on industrial vessels, establishment of a satellite-based fishing vessel monitoring system, linked to a fisheries monitoring center, two surveillance stations) |
|  | Spatial scale: Local Jurisdiction of origin: Co-Governance | N/A | Community management rights over adjacent areas of the sea in 1 to 2 pilot areas (resulting in the introduction of a range of tech. measures, including gear restrictions, closed areas, etc.) | Extension by national fisheries agency, linkage to national surveillance support |
| Senegal | Spatial scale: National Jurisdiction of origin: State | Development of new policy objectives (and accompanying regulations) for coastal demersal fish stocks | N/A | Enhanced national agency capacity and activities for administration of rules for tenure, including enhanced transparency in the licensing of access for industrial vessels, increased communication and dialogue with resource users and communities, increased registration of fishing vessels Increased research, assessment and monitoring in order to expand the information base required for reform, including working with the oceanic research center (CRODT) to synthesize data on stock status Enhanced national agency surveillance and enforcement of existing rules (coastal surveillance stations) |
|  | Spatial scale: Local Jurisdiction of origin: Co-Governance | N/A | Community management rights over adjacent areas of the sea (expected to result in the introduction of a range of technical measures, including gear restrictions, closed areas, etc.) in 12 pilot sites | National agency extension Local government surveillance support to communities |
| Sierra Leone | Spatial scale: National Jurisdiction of origin: State | Finalize articulation of a national policy review | Development of regulations for input controls for industrial trawl fisheries (outsides the 6-mile coastal zone) | Enhanced national agency capacity and activities for administration of rules for tenure, including enhanced transparency in the licensing of access for industrial vessels, increased communication and dialogue with resource users and communities, increased registration of fishing vessels Increased research, assessment and monitoring in order to expand the information base required for reform, including training and technical assistance in analysis of key fisheries statistics Enhanced national agency surveillance and enforcement of existing rules (including expanded sea and aerial patrols, increased training, observers on industrial vessels, establishment of a satellite-based fishing vessel monitoring system, linked to a fisheries monitoring center, two surveillance stations) |
|  | Spatial scale: Local Jurisdiction of origin: Co-Governance | N/A | Community management rights in four pilot areas | National agency extension |

Sources: World Bank (2009); World Bank (2011b)

Summary of expected financial costs of the WARFP.  The total financial costs of the first phase of the WARFP in each of the initial five countries was some $75 million over five years, from the World Bank’s concessional lending arm, the International Development Association (IDA), the Global Environment Facility (GEF) and the Africa Catalytic Growth Fund (ACGF) housed at the World Bank, as shown in Table 11 below.

Table 11. WARFP Phase One Financing by Source (US$ Million)

| Country | IDA (Credit/Grant) | GEF (Grant) | Africa Catalytic Growth Fund | Total amount |
| --- | --- | --- | --- | --- |
| Cape Verde | 6.0 | 2 .0 |  | 8.0 |
| Guinea-Bissau | 6.0 | 2.0 |  | 8.0 |
| Liberia | 9.0 | 3.0 | 2.0 | 14.0 |
| Senegal | 15.0 | - |  | 15.0 |
| Sierra Leone | 15.0 | 5.0 | 8.0 | 28.0 |
| CSRP | 2.0 | - |  | 2.0 |
| TOTAL | 53.0 | 12.0 | 10.0 | 75.0 |

* Reflects funds committed directly to countries and/or the CSRP.  Of the funds committed directly to the five countries, each on-granted a portion of the funds to the CSRP for regional coordination – some $3.5 million in total – in addition to a $2.0 million regional grant directly to the CSRP.

Sources: World Bank (2009); World Bank (2011); World Bank (2011b)

Additionally, Table 12 provides a summary of the break-down of financial costs of each component of the program in each of the five countries.

Table 12. WARFP Phase One Financing by Project Component (US$ Million)

| Component | Cabo Verde | Guinea-Bissau | Liberia | Senegal | Sierra Leone | CSRP |
| --- | --- | --- | --- | --- | --- | --- |
| 1. Strengthened Governance | 2.8 | 2 .0 | 2.2 | 8.4 | 4.8 | 2.2 |
| 2. Reduced Illegal Fishing | 1.8 | 4.7 | 5.4 | 2.2 | 7.9 | 0.3 |
| 3. Increased Local Value Added | 2.0 | 0.4 | 3.9 | 2.3 | 13.0 | 0.2 |
| 4. Program Management | 0.9 | 0.6 | 1.7 | 1.3 | 1.2 | 2.8 |
| TOTAL | 7.5 | 7.7 | 13.2 | 14.2 | 26.9 | 5.5 |

Sources: World Bank (2009); World Bank (2011); World Bank (2011b)

Excluding the costs of increased local value addition and overall program management in components three and four, the financial costs of the governance reforms in components two and three can be more precisely categorized and classified, as shown in Table 13 below.

Table 13. Break-down of financial costs of fisheries governance reform in Phase One of the WARFP*

|  | Cape Verde | Guinea-Bissau | Liberia | Senegal | Sierra Leone | CSRP | TOTAL |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Costs of formulating and enacting changes to institutions and organizations |  |  |  |  |  |  |  |
| Policy formulation/ reform | 0.4 | 0.4 | 0.5 | N/A | 0.3 | N/A | 1.6 |
| Development and enactment of rule changes or new rules | 0.5 | 0.3 | 0.8 | 2.3 | 1.4 | N/A | 5.3 |
| Organizational costs to administer, monitor and enforce rule changes | 2.5 | 6.0 | 6.3 | 3.8 | 9.6 | 2.5 | 30.7 |
| Costs of changes in fishing effort and subsequently yield |  |  |  |  |  |  |  |
| Compensation for profits foregone | 1.2 | N/A | N/A | 4.5 | 1.4 | N/A | 7.1 |
| TOTAL | 4.6 | 6.7 | 7.6 | 10.6 | 12.7 | 2.5 | 44.7 |

* Amounts given in US$ millions, as total costs over the duration of the project; Source: World Bank (2009); World Bank (2011); World Bank (2011b)

As shown in the above tables, of the $75 million in financial costs estimated for implementation of the WARFP in the first five countries, together with CSRP support, some $44.7 million focused specifically on financing governance reforms, another $21.8 million focused on infrastructure and skills development for increasing local value added to fish products, and finally $8.5 million covered the costs of program management (e.g. audits, additional staff, etc.).  Of the funds targeted specifically to governance reforms, per Table 13 the types of expenditures could be characterized as:

- Policy formulation/reform: 3 percent

- Development and enactment of rule changes or new rules: 12 percent

- Organizational costs to administer, monitor and enforce rule changes: 69 percent

- Compensation for foregone profits (i.e. from reduced fishing effort): 16 percent.

This break-down reflects the significant costs in enhancing the capability of state agencies to administer, monitor and enforce the rules governing targeted fisheries, notably the costs of surveillance.  This may also reflect a fairly low baseline of expenditures on the operations of these agencies at the outset of the WARFP. Additionally, only in Cape Verde and Senegal were voluntary fishing effort reductions in the small-scale fisheries envisaged, with funding targeted to support or compensate fishing households in the transition.  In the other three countries effort in the small-scale fisheries was not expected to be reduced, as opposed to industrial effort and notably illegal industrial fishing.

Summary of expected economic benefits to the five countries from the first phase of the WARFP. The expected economic returns to the region from the reform program were significant. As a starting point at the beginning of the preparation phase in 2007, the World Bank prepared some very simple back-of-the-envelope estimates based on a value-added model of the region’s fisheries, in order to give an indication of the potential benefits to the region from the types of reforms proposed.  A simple scenario was considered where more effective fisheries governance combined with enhanced local infrastructure could: (i) reduce the total catch by illegal or ‘pirate’ vessels by 50 percent; (ii) reduce the total catch of fish in West African waters on the order of 25 percent; and (iii) reduce the percentage of the total catch taken by legal foreign industrial vessels on the order of 20 to 25 percent; and (iv) increase the percentage of the total catch taken by local small-scale vessels on the order of 20 to 55 percent. Essentially this would reduce illegal losses, reduce industrial fishing effort to help rebuild stocks and enhance productivity, and shift a larger proportion of the catch to small-scale harvesting operations.  Such a scenario was expected to result in: (i) an increase in the fish stocks and decrease in the costs of catching them, i.e. the percentage of the gross value of the catch considered as value added for an average industrial and small-scale fishing operation would increase, and (ii) an increase in the average landed price for many of the major fish species groups in region.  This scenario resulted in an annual increase of the value added to the region from the fisheries on the order of $300 million, as an indication of the scale of benefits that could be achieved.

By the time the program was initially prepared in mid-2009, the phase one reforms in Cape Verde, Liberia, Senegal and Sierra Leone were costed at some $56 million, to be financed by World Bank concessional loans and grants, and GEF grants (World Bank 2009). The World Bank developed a basic economic model of the coastal demersal fisheries in the four countries, to estimate the direct benefits captured in the marketplace and therefore quantifiable.  These benefits were measured at first sale after landing the fish catch, and so did not capture enhanced benefits throughout the entire value chain (World Bank 2009).  The World Bank estimated the benefits from a scenario with the proposed reforms in the four countries, compared to a ‘business-as-usual’ scenario.  The baseline was essentially declining or marginally profitable fisheries, with negative profitability in Cape Verde and Senegal, profits just above zero in Liberia, and only in Sierra Leone were profits still positive (at roughly 5 percent of gross revenues from first sale) (World Bank 2009). From that baseline, the model included a number of assumptions for the impacts of the investments, including: (i) a 33 percent reduction in small-scale fishing effort in Cape Verde; (ii) a full reduction in bottom trawling within 6 miles of the coast in Liberia and Sierra Leone (in the latter case coupled with a one to two-year closure of the shrimp fishery); and (iii) in Senegal a 50 percent reduction in coastal trawling effort and a freeze on small-scale fishing effort. These impacts, coupled with increased community management rights for the fisheries, were expected to lead to increased profitability in the coastal fisheries on the order of $39 million over the 5-year period from 2010 through 2014 (see Table 14 below) (World Bank, 2009).  Adding in the returns to labor, the transfers to support alternative livelihoods to fishing, and increased value added from fish landing site infrastructure, the total net economic benefits from the program’s investments in phase one in these four countries were estimated to be approximately $75 million over the five year period, for an economic internal rate of return of 16 percent (World Bank 2009).  These estimates did not include the additional $10 million in financing provided for fish landing site infrastructure in Liberia and Sierra Leone, nor the additional $2 million grant to CSRP, both agreed in 2011 (World Bank 2011).

Table 14. Estimated net present value (NPV) of changes in economic benefits in first four countries between 2010 and 2015 as a result of WARFP governance reforms (US$ millions)

|  | Cape Verde | Liberia | Senegal | Sierra Leone | Total |
| --- | --- | --- | --- | --- | --- |
| NPV of economic benefits* | 5.0*** | 13.4 | 8.6 | 28.8 | 55.8 |
| NPV of economic benefits** | 2.8 | 9.0 | 8.3 | 18.5 | 38.6 |
| Total | 2.8 – 5.0 | 9.0 – 13.4 | 8.3 – 8.6 | 18.5 – 28.8 | 38.6 – 55.8 |

* Considers no opportunity cost to labor, wages fully included in economic benefits; ** Considers wages to labor as a cost, not included in economic benefits; *** Includes rent from small pelagic systems; Source: World Bank (2009); Assumptions:

- Does not include transfers for compensation of foregone resource rents

- Measured at first sale after landing fish catch, do not include enhanced benefits throughout the entire value chain

- The baseline rents estimated for coastal demersal fisheries systems were negative in Cape Verde and Senegal, just above zero in Liberia, and positive in Sierra Leone (at roughly 5% of gross revenues from first sale) (World Bank, 2009).

- Ex-ante estimates assumed: (i) a 33% reduction in small-scale fishing effort in Cape Verde; (ii) a full reduction in trawling within 6 miles of the coast in Liberia and Sierra Leone (in the latter case coupled with a one to two-year closure of the shrimp fishery); and (iii) in Senegal a 50% reduction in coastal trawling activity and a freeze on small-scale coastal demersal fishing effort.

# V. Experiences with Fisheries Governance Reforms Supported by the WARFP

Table 15 below indicates the timeline for the World Bank financing to become available to the first five countries in order to support the reforms introduced through the WARFP, in each case with a duration of five years.  A critical caveat is that each of these five countries introduced the WARFP into a very specific and different context or starting point.

Table 15. Start date for World Bank financing to the first five countries in the WARFP

| Country | Start Date |
| --- | --- |
| Cabo Verde | 30 April 2010 |
| Guinea-Bissau | N/A - 2011 |
| Liberia | 19 April 2010 |
| Senegal | 22 June 2010 |
| Sierra Leone | 17 Aug. 2010 |

## 5.1 Cabo Verde

WARFP-supported activities actually began in Cabo Verde in April 2010 (World Bank and CSRP, 2011a).  At the time, while illegal fishing was considered a constraint on the benefits from the fisheries given the large area of the country’s waters, the key challenge identified for the coastal demersal fishery system was the expanding small-scale fleet and accompanying decline of sedentary coastal fish resources on the relatively narrow shelf area (World Bank, 2009). However, the first year of reform implementation began slowly and soon fell behind schedule (World Bank and CSRP 2011a). Subsequently, a World Bank team noted considerable delays in December 2012, and during the March 2013 mid-term review, the project was ‘restructured,’ whereby the government and the World Bank agreed to change the terms of the financing to add, change or reduce planned activities and objectives (World Bank 2014a).  The restructuring focused WARFP support on those activities where objectives were considered as most likely to be achieved by the end of the project in 2015, with a reduction in funding for activities considered as unlikely to reach their goal (e.g. small grants and training for diversified livelihoods in fishing communities in order to compensate for foregone resource rent resulting from changes in harvesting rules) (World Bank, 2014a).

In terms of national-scale efforts to change articulated policy statements for the fisheries, after a slower than expected start in year one, the Fisheries Department (DGP) began to work with international experts to conduct bio-economic modeling and assessments of the fishery systems in order to prepare a new policy for the sector (World Bank and CSRP, 2011a).  The policy statement was drafted in 2012, entitled the ‘Strategic Fisheries Development Plan,’ and further revised in 2013 as a government ‘letter of sector policy’, before being adopted by the Government in 2015 and further analysis begun in order to implement the policy’, including drafting of revisions to the national law and regulations, with the former including recognition of community rights to manage defined coastal fisheries (World Bank and CSRP, 2015b; World Bank and CSRP 2016).  The revisions to the law and new regulations were completing final review as of early 2016 (World Bank and CSRP 2016).

To enhance national agency capacity to administer harvesting rules, the project included support for the Fisheries Department (DGP) to complete a full registration of the canoe fleet (World Bank, 2009). The registration program implemented by DGP was considered a model for the region by the World Bank, and achieved 100 percent registration of canoes by December 2013, with a full database of the fleet stored in the cloud, accessible by smart phone and available to the public (World Bank, 2014a). Additionally to support policy objectives and administration of  harvesting rules, the biological status of key fish stocks in the country’s waters was assessed, beginning with a survey of small pelagics in 2010 and continuing in 2012, leading DGP to propose new input control rules to freeze the registration of new small-scale vessels in March 2015, with the objective of transitioning to an output control rule based on establishment of a total allowable catch limit for small pelagic species towards the end of 2015 (World Bank and CSRP, 2015b).  Drawing from the information provided by these assessments and monitoring, as well as enhanced capacity of the state agency, licensing coverage of small-scale and semi-industrial fishing vessels increased over the course of the WARFP, with licenses issued for these types of vessels recorded as follows: 105 vessels in 2012, 476 vessels in 2013, 780 in 2014 and 605 in 2015, with reported catches from these fleets increasing to 12,100 mt and 14,300 mt in 2013 and 2014 respectively (World Bank and CSRP 2016).

Two pilot projects were envisaged for introduction of state recognition of community management rights over defined coastal fisheries, though the sites were not selected until 2011 (World Bank and CSRP 2011a).  As of early 2013, the World Bank reported that progress remained slow, and DGP had approached the Government of Senegal to facilitate an exchange of expertise and learning based on the latter’s experiences in co-management (World Bank 2014a). Funding for this activity was increased as a result of the restructuring, and progress reported as subsequently accelerated (World Bank 2014a).  As of 2015, four fishers’ associations had formed at the two sites (Sal and Maio), with a facilitator from DGP supporting each (World Bank and CSRP 2015b). Each association had reportedly worked with the facilitators to conduct a rapid assessment of the coastal demersal fisheries, and developed new rules for state recognition (World Bank and CSRP 2015b; World Bank and CSRP 2016).  The associations were subsequently legally established with internal governance structures (a general assembly, a board and technical committees) and their rules were expected to be recognized by the state as regulations in early 2016 (World Bank and CSRP 2015b; World Bank and CSRP 2016).  According to an early 2016 report, the communities had embraced state recognition of management rights, utilizing the opportunity to develop new rules for the fisheries, with dues collected from members in order to help sustainably fund the organizations’ operating costs (World Bank and CSRP 2016).  In early 2016 the government indicated an interest to support the establishment of similar associations on the islands of Boa Vista, Santiago and Santo Antao (World Bank and CSRP 2016).

Additionally, although delayed and funding reduced compared to what was envisaged in the project document, the WARFP has financed small-scale fishers interested to exit the small pelagic fishery system, after DGP passed a rule freezing registration of new vessels. With the rule in place, DGP considered the funding for incentives to diversify out of fisheries to be more likely to reduce overall fishing effort in the small pelagic system.  As of mid-2015, some 69 fishers had received grants or subsidized loans in order to start new enterprises outside of the fisheries sector (World Bank and CSRP, 2015b).

In terms of enhancing state agency capacity for surveillance and enforcement of harvesting rules, DGP and the country’s Coastal and Marine Secretariat (COSMAR) signed an agreement to collaborate, the latter being established with United States Government support (World Bank 2014a). This collaboration eventually led to the establishment of a new agency (an ‘authority’ - ACOPESCA), designated to carry out surveillance operations to combat IUU fishing (World Bank and CSRP 2016). The WARFP supported construction of two fisheries control stations on the islands of Sal and Maio, where 10 of 22 trained fisheries inspectors would be deployed (World Bank 2014a; World Bank and CSRP 2016). A satellite-based vessel monitoring system was installed early in the project, and subsequently a national fisheries surveillance plan completed in 2012 (World Bank, 2014a).  By May 2015 approximately 60 percent of licensed industrial fishing vessels had transponders sending signals to a vessel monitoring system used by the state (World Bank and CSRP 2015b). In addition a fisheries observer program was instituted, in order to record fish catches on industrial vessels (World Bank 2014a).  A review by the European Union (EU) of the country’s efforts to fight IUU fishing was considered positive, ensuring continued access to EU markets for Cape Verde fish products (World Bank 2014a). Additionally, DGP linked the registry of small-scale vessels and the satellite-based vessel monitoring system of industrial vessels, to smart phones of fisheries inspectors, in order to enhance the efficiency of fisheries surveillance (World Bank and CSRP, 2015b). By 2016, the rate of fishing infractions as a percentage of all observed fishing was measured at 27 percent according to World Bank reports, below the target set for the WARFP (World Bank and CSRP 2016).  The government’s budgetary allocations by 2016 also included funding for the additional 22 inspectors recruited through the WARFP, as well as additional monitoring staff and the facilitators for the CMAs (World Bank and CSRP 2016).

In addition to governance reforms, the WARFP provided support for infrastructure to increase local value added to fish harvested in the country’s waters.  However, the original infrastructure investments envisaged were heavily delayed, and at restructuring significantly reduced (World Bank 2014). Rather than an additional landing site, the government and the World Banka agreed that the WARFP would support the construction of an ice-making factory in the Port of Palmeira on Sal Island. By early 2016 the construction was completed, with trials of 15 tons of ice produced (World Bank and CSRP 2016). Additionally, the project has supported the rehabilitation of the Port of Praia on Santiago Island (electricity grid, potable water and sanitation), with work on the development of an auction system scheduled to be completed by the end of 2015.

## 5.2 Guinea-Bissau

The Government had undertaken collaborations with a number of development partners to enhance fisheries policy delivery and generate greater benefits from the country’s resources, including budget support incorporated into fishing access agreements with the EU, and initial fish landing site infrastructure financed by the African Development Bank. Given the dearth of data on the status of the country’s fish stocks or natural capital asset base during the preparation phase, as well as limited governance over fishing activities, the WARFP focused on supporting reforms to national-scale institutions for fisheries governance, and particularly increased sea patrols and the introduction of satellite-based monitoring of fishing vessels in order to enhance compliance (World Bank 2011b). Essentially, the WARFP was aimed at supporting the minimum governance reforms and capacity needed to control fishing effort and help make access to the Guinea-Bissau’s fishing grounds more valuable, such that the terms of access for foreign industrial fleets would become more favorable and sustainable.

Although the financing was agreed by late 2011, WARFP-supported activities were significantly delayed in starting, as a coup in 2012 led to a nine-month suspension of disbursements for all World Bank projects. Subsequently, after funds became available again in 2013, progress was slow in restarting (World Bank and CSRP 2015).  Beginning in early 2013, the WARFP financed: (i) national-scale governance reforms, including technical assistance for policy and regulatory reform, the 2014 assessment of demersal fish stocks, and pilots in community management of near-shore coastal fishing grounds; (ii) increased surveillance of the fisheries, including equipping a fisheries monitoring center with FISCAP that is linked to fleets by satellite, constructing or rehabilitating functioning coastal surveillance stations, increased sea patrols, including training of crew; and technical assistance to estimate annual operating costs for surveillance and identify sustainable sources of revenue; and (iii) small investments in a future transition of the offshore fisheries economy onshore, by establishing a competent authority to regulate food quality of fish products to meet requirements for exports to the European market; and training for local fishers to improve the quality of fish products post-harvest (World Bank 2011b).

By January 2014, only 11 percent of funds had been disbursed, and as a result the Government developed a plan to accelerate implementation, together with the World Bank (World Bank and CSRP 2015).  In February 2014, the government agency implementing the project, the Secretary of State for Fisheries, agreed to sign a MOU with the compliance arm of the agency, FISCAP, and the Coast Guard, in order to strengthen coordination for delivery of fisheries monitoring and surveillance to enforce compliance with regulations. Shortly thereafter FISCAP and the Coast Guard began to increase sea patrols through a short-term leasing arrangement with the Government of Senegal for patrol vessel, as well as rehabilitation of two small coastal patrol vessels, together with a larger 20-meter coastal patrol vessel financed by the EU and scheduled to be available in 2016 (World Bank and CSRP 2015; World Bank and CSRP 2015b). By October 2014 WARFP funds disbursement had increased to 19 percent, but still well short of the 50 percent projected for this time (World Bank and CSRP 2015).  By early 2015, the Bank’s mid-term review noted that the agency had made progress in delivering the reforms financed by the project, and implementation pace had accelerated. However, by this stage, the World Bank reported that the original targets for project success could not be achieved, while the data used for the baselines was incorrect. A restructuring was recommended, together with a one-year extension of the closing date (World Bank and CSRP 2015).

As of late June 2015, some 31 percent of funds had been disbursed, as a proxy for the pace of implementation of WARFP reforms (World Bank and CSRP 2015b).  The Government had begun to make some adjustments, continuing to pursue short-term leases of a patrol boat from the Government of Senegal, instead of a longer-term lease of a patrol boat as originally envisaged at appraisal.  In late 2014 and throughout 2015 the project financed international technical assistance to strengthen fisheries surveillance. Over time the project implementation unit within the Secretary of State for Fisheries began to build the partnerships and delivery capability needed at FISCAP and to a lesser extent the Coast Guard, for increased surveillance.  However, delivering enhanced surveillance would be a continuing challenge throughout the project, with progress reported as slow (World Bank and CSRP 2015).

In conclusion, the WARFP supported the development and introduction of several national-scale fisheries governance reforms, including articulation of a new policy vision in 2014, together with a draft law (Fisheries Act) and accompanying regulations for the state which were under review as of 2016 (with the exception of a regulation requiring VMS which was enacted), as well as an action plan for delivery in 2015. At the same time, the project financed some of the basic infrastructure, partnerships and training to begin to increase fisheries surveillance.  This included the renovation of a monitoring center at FISCAP, equipped with a satellite-based VMS (tracking 100 percent of the licensed trawl fleet by 2016, or some 99 trawlers), radar, an Automatic Identifier System (AIS) and a short and long-range radio, as well as renovation of a coastal surveillance station at Caravela equipped with radio and radar (World Bank and CSRP 2015; World Bank and CSRP 2016).

The outputs of increased patrols and arrests were clearly measured (see Table 16), though surveillance occurred through sporadic missions of a rented foreign patrol vessel – leaving an open question as to how much of the fishing grounds were patrolled and during how much of the fishing season.  Nonetheless, basic sea patrol capacity was reportedly in place by mid-2015, together with a working vessel monitoring system (VMS) covering the industrial trawl fleet for the first time, and a decrease in the percentage of observed vessels that were committing an infraction (World Bank and CSRP 2016).

A next step envisaged by the Secretary of State for Fisheries is to develop fishery-specific rules that control or reduce effort, and begin to generate increased economic benefits. Towards this end, fishery management plans have been envisaged, drawing upon bio-economic models to be developed. The lack of such models was reported as an impediment, as the Government was not able to track levels of economic rent generated from key commercial fisheries, nor fishing effort and catch rates (World Bank and CSRP 2016).  Finally, a building was constructed to house a competent authority and laboratory for regulation of fish product quality and food safety, together with laboratory equipment, inspection protocols and traceability standards, with the process launched towards an eventual accreditation by the EU for certification of fish exports to the European market (World Bank and CSRP 2016).

Table 16. Increased Fisheries Surveillance Patrols financed by the WARFP

|  | Total Patrol Days* | Fishing Vessels Sighted | Fishing Vessels Inspected | Number of Infractions | Type of Infractions | Amount of Fines Collected |
| --- | --- | --- | --- | --- | --- | --- |
| 2013 | 23 | N/A | N/A | N/A | N/A | N/A |
| 2014 | 46** | N/A | N/A | N/A | N/A | N/A |
| 2015*** | 99**** | N/A | 202 industrial 239 canoes | 14 trawlers 59 canoes | 3 trawlers for gear violations; 3 for by-catch violations; Canoes – fishing w/o a license | 10 m F CFA from one trawler committing gear violation, collected via sale of confiscated fish |
| 2016 – Q1 | 22***** | 103 trawlers | 89 trawlers | 2 trawlers | 1 trawler for capture of juveniles |  |
| TOTAL | 190i | N/A | 475 trawlersii | 30 trawlersii | N/A | 306 m F CFAiii |

* Represents a total of 16 patrol missions over the period from 2013 to March 2016.

**At least 10 of these patrol days were conducted on 2 missions of the Senegalese patrol boat rented with funds from WARFP

*** From June 2015 to Feb. 2016 no patrols took place (Gov. notes difficulties to receive Bank non-objection to rent patrol vessel)

****Rate of sighting for use of Senegalese patrol vessel appears to have been high – 3 missions (May 23, May 29 and June 18) of a total of 8 hours sighted 110 trawlers.

*****4 missions from: February 12 – 16; February 19 – 23; March 4 – 9; March 7 – 11.

i The 2016 Aide Memoire also results a total number of patrol days for this period as 211.

ii Totals available in 2016 Aide Memoire, but not broken down for all years.

iii Breakdown as follows: 235 m F CFA from fines to trawlers, 15 m F CFA from canoes and 56 m F CFA from sale of confiscated catch.

Sources: World Bank and CSRP (2015); World Bank and CSRP (2015b); World Bank and CSRP (2016)

## 5.3 Liberia

WARFP-supported activities actually began in Liberia in April 2010, and the coordinator arrived in May to begin work at the Bureau for National Fisheries (BNF) (World Bank, 2012a). At that time operations by the national fisheries agency (i.e. BNF) were considered to be fairly limited, and trawling activity in the coastal demersal fishery system included an estimated 42 licensed vessels providing a total of $88,000 in public revenues to the state in 2008, and many more vessels observed fishing illegally without licenses (World Bank and CSRP, 2015b). This coastal trawling resulted in many reported incidents of conflict with Liberian artisanal fishermen, high rates of artisanal fishing gear losses and risks of collision with industrial trawl vessels, and low artisanal catch rates (World Bank, 2012c). Indeed, during preparation of the project, members of fishing communities near Robertsport had stated that reducing coastal trawling was a precondition for any co-governance partnership with the state (World Bank and CSRP, 2015c).

As a first step to allow for regulation of fishing effort in the country’s waters, a new national fisheries regulation was enacted by BNF in 2010 – based on the regulatory authority established in the original 1953 Act – while the government began to prepare a new long-term policy vision for the sector and a new fisheries act to help implement that vision (World Bank 2012c; World Bank and CSRP 2016).  These regulations included a prohibition on bottom trawling within 6 miles of the coast to avoid damaging essential fish habitats, higher fines for illegal fishing activity and links between actual harvest value and license fees (World Bank and CSRP 2015c; World Bank and CSRP 2016). A ‘stock-take’ was conducted in 2010 of the status of key commercial fisheries, and input controls for a fixed number of licenses for industrial vessels introduced (World Bank 2012c).  For the first time, these licenses were made public as an annex to an August 2011 trip ‘Aide Memoire’, i.e. trip report, from the World Bank (World Bank and CSRP 2011b). That disclosure led to the discovery of previously unreported industrial tuna fishing in the country’s waters, when representatives of the foreign companies contacted the government to ask why their vessels were not listed, leading to a government investigation revealing that past payments by the foreign companies to their local agents for fishing licenses had never been received by the government, and subsequently retroactive payments and fines of over $3 million were paid by the companies to the treasury by the end of 2012 (World Bank, 2012c). By 2015, the level of transparency in fisheries governance had reportedly improved to the point that the list of licensed fishing vessels and revenue generated were periodically published on BNF’s website, together with frequent radio discussion programs (World Bank and CSRP 2015c).

To enhance BNF’s capacity to administer harvesting rules, in 2011 and 2012 the project supported a first registration of the country’s canoes, including marking and registering 4,087 canoes into a database (of whom 3,626 were considered active), with a unique identification number carved into the hull (World Bank 2012c; World Bank and CSRP 2016). This register was maintained and expanded in the subsequent years, with BNF collaborating with the Liberia Artisanal Fishermen’s Association (LAFA) (World Bank and CSRP 2014a). Together with increased data collection at small-scale fish landing sites, BNF has preliminarily estimated that annual harvests landed could be on the order of 60,000 mt, significantly more than the 9,000 mt reported by Liberia to FAO in previous years (World Bank and CSRP 2016).  In terms of rules for the industrial fisheries, the WARFP has supported assessments to propose precautionary limits on industrial harvests (total allowable catches) (World Bank and CSRP 2016).

In 2011 BNF began to develop a new policy vision for the country’s fisheries, which establishes national objectives and a strategy to 2030 (World Bank and CSRP 2016).  The policy was completed and in 2015 approved by the Cabinet, while a new Fisheries Act and accompanying regulations were drafted to implement the policy, and the Act is scheduled to be submitted to Parliament in 2016 (World Bank and CSRP 2014a; World Bank and CSRP 2016). In May 2015 the government concluded an access agreement with the EU, providing access for 34 European tuna vessels (28 purse seiners and 6 long-line vessels), in return for 650,000 euros per year to the state for the next five years – half of which will be earmarked to support fisheries management costs (European Commission 2015).

A planned investment in a new headquarters for BNF was postponed until the policy statement influencing the future functions of the agency was completed, and eventually the project would opt for an interim solution of a pre-fabricated building in 2014, as the full cost of a new building was under-budgeted during preparation (World Bank and CSRP, 2014a). The uncertainty regarding a facility for BNF staff, and temporary solutions that resulted in scattering BNF staff and particularly project contractors across different locations, were considered a continuing constraint to reform throughout the project, and poor quality of contracting and design for the temporary facility led to persisting delays (World Bank and CSRP 2014a; World Bank and CSRP 2016). State resources for BNF operations were reported to be $44,000 per year, sufficient to pay the salaries of the 30 staff and 18 contractors but with little provision for operating costs (World Bank, 2012c). A number of BNF functions, including surveillance operations, were financed largely by the World Bank during the project, but were considered to be significantly reduced in the absence of this source of financing, with alternatives not available from state appropriations as of early 2016 (World Bank and CSRP 2015c; World Bank and CSRP 2016).

With assistance from BNF facilitators financed by the project, a number of communities around Robertsport collectively and informally established a Co-Management Association (CMA) with by-laws as a pilot for community management rights in the coastal demersal fishery system. In 2013, the CMA created a sub-committee of members on fisheries surveillance, to partner with state in order to reduce illegal fishing in the coastal waters (World Bank and CSRP, 2014a). An independent review of the Robertsport CMA process in November 2013 concluded that the CMA’s constitution and by-laws needed to be clarified and formally recognized by the state, the CMA’s work plan needed to be strengthened together with a budget, a stronger information basis for the CMA to exercise management rights was needed, and the question of the distribution of benefits from anticipated government-financed construction of a fish landing site was raised (World Bank and CSRP, 2014a). By mid-2014, the Ministry of Agriculture recognized the Roberstport CMA as an autonomous entity authorized to manage coastal fisheries (World Bank and CSRP, 2014a). In early 2015 the Bank assessed that the CMA was “a young yet functioning organization,” acknowledged by at least some local communities as helping to reduce illegal trawling (World Bank and CSRP, 2015c). At the same time, the World Bank reviews suggested that the by-laws needed to be simplified and better communicated (e.g. the voting rules and governing structure), particularly reports that the CMA was exercising exclusion rights not yet formalized or transparent (World Bank and CSRP, 2015c). As of early 2015, concerns were raised in World Bank reports about the representation of the CMA, as membership is mixed with government representatives, and decision-making was perceived by community representatives as being influenced by board members picked by the national agency (World Bank and CSRP, 2015c).  A 2016 report considered the legitimacy of the CMA as partial, given that only 215 of the approximately 1,000 fishers living in the Robertsport area are members (World Bank and CSRP 2016).  The report suggests that rebuilding trust between the CMA and fishers will be a priority (World Bank and CSRP 2016).

In terms of enhanced agency capacity to enforce harvesting rules, incidence of illegal fishing was estimated to be at 83 percent in the coastal fisheries at the beginning of the project (World Bank, 2009). As a first step in 2010, an inter-agency fisheries monitoring, control and surveillance coordinating committee (MCSCC) was established by memorandum of understanding, and a functioning fisheries monitoring center opened at the Liberia Maritime Agency (one of the MCSCC members), with staff recruited and trained, and equipped with radio and computer communications and a satellite-based fishing vessel monitoring system (VMS) receiving reports from the licensed industrial vessels equipped with transponders (World Bank, 2012c).  Under direction from staff at this monitoring center, the Liberian Coast Guard began to launch sea patrols in the coastal waters together with officers of BNF with support from the United States Coast Guard, as well as aerial patrols through collaboration with the United Nations Mission in Liberia (UNMIL) (World Bank, 2012c). These efforts resulted in the arrest of five trawl vessels for non-compliance with the new regulation, as well as collaboration with the Ministry of Fisheries and Marine Resources (MFMR) in Sierra Leone to arrest a Portuguese-flagged vessel in Freetown for violations of harvesting rules in Liberia’s waters (World Bank, 2012c). By the end of 2012, BNF would prosecute infractions by 39 industrial vessels, resulting in $3.7 million in fines (World Bank, 2014a). The U.S. government’s National Oceanic and Atmospheric Administration (NOAA) provided training to a team of fisheries observers recruited by BNF through the project, to begin to record fish catch data on all licensed industrial vessels, for entry in a newly-established database for licenses, revenues and fishing catch and effort at BNF (World Bank, 2012c).

By October 2012 the World Bank reported that illegal trawling in coastal waters (within 6 miles of the coast) had been significantly reduced, with the exception of some incursions by unlicensed vessels in the far south near Harper (World Bank, 2012c). According to the report (World Bank, 2012c), “with this illegal trawling removed from the inshore waters, local artisanal fishers no longer compete with industrial trawl vessels, and environmental externalities on the habitats supporting healthier fish stocks have been reduced. Stock recovery among all coastal demersal species in these inshore waters, and particularly the valuable shrimp fishery, can be expected as a result, although data collection to verify this has not been completed.  Anecdotal claims by communities suggest fish landings are increasing.” By 2013 coastal communities at West Point and Robertsport reported increased level of coastal demersal catches, which the World Bank report suggests could be at least partially attributed to the reduction in illegal fishing (World Bank and CSRP, 2014a). These enhanced surveillance operations continued throughout 2013, when 103 patrol days were conducted (88 sea patrol and 15 aerial patrols) (World Bank and CSRP, 2014a). By the end of 2013, the occurrence of illegal fishing in Liberia’s coastal waters was reported to have been reduced from the 83% baseline to 57% (World Bank and CSRP, 2014a).  Throughout this period, the project actively invested in strengthening the fisheries monitoring center, with ongoing international technical assistance provided to the staff (World Bank and CSRP, 2014a).

By 2015, the project’s support for enhanced surveillance and enforcement, including through introduction of a satellite-based VMS and on-board observers, had resulted in several arrests and fines that were reported in the media and considered to have galvanized significant public attention and critical support (World Bank and CSRP, 2015c). In total 14 air patrols and 30 sea patrols were conducted in 2015 (World Bank and CSRP 2016). In parallel, public disclosure of fishing licenses beginning in late 2011 reportedly deterred national agents and boat owners from trading forged licenses (World Bank and CSRP, 2015c).  Total arrests and fines over the life of the project by the government reached over $6.4 million (World Bank and CSRP, 2015c).  A 2016 review by the CSRP and World Bank reported that IUU activities by foreign vessels in the waters near the previously open southern and northern borders were considered to be minimal (World Bank and CSRP 2016).

Table 17. Liberia fisheries judicial and administrative penalties imposed from 2010 - 2013

| Year | Vessel Name(s) (Flag State) | Company / Association | Violations | Penalty/Compensation Imposed US$ |
| --- | --- | --- | --- | --- |
| 2011 | F/V SETA 70 (South Korea) | Inter-Burgo Industrial Co. | Various (fishing in the IEZ, others) | USD 125,000 |
|  | F/V LIAO ZHUANG-YU 15011 (China) F/V LIAO ZHUANG-YU 15012 (China) F/V LIAO ZHUANG-YU 15031 (China) F/V LIAO ZHUANG-YU 15032 (China) |  | Various (Fishing without a license, fishing in the IEZ, pair trawling) | USD 60,000 (USD 15,000 per vessel) |
|  | F/V SETA 70 (South Korea) | Inter-Burgo Industrial Co. | Failure to carry an observer, failure to report | USD 25,000 |
|  | F/V SETA 70 (South Korea) | Inter-Burgo Industrial Co. | Various (fishing in the IEZ, others) | USD 150,000 + 6 month license suspension |
| 2012 | F/V DONIENE (Spain) | ANABAC | Licensing Irregularities, Unreported fishing activities | USD 350,000 + 1 year license ban |
|  | F/V TXORI URDIN (Spain) F/V EGALUZE (Spain) F/V ALBONIGA (Spain) F/V JUAN RAMON EGANA (Spain) F/V TXIRINNE (Spain) F/V PLAYA DE AZKORRI (Belize) | ANABAC | Licensing Irregularities, Unreported fishing activities | USD 150,000 USD 150,000 USD 150,000 USD 150,000 USD 150,000 USD 150,000 |
|  | F/V AVEL VOR (France) F/V CAP BOJADOR (France) F/V GUERIDEN (France) F/V VIA EUROS(France) F/V VIA HARMATTAN (France) | ORTHONGEL | Licensing Irregularities, Unreported fishing activities | USD 150,000 USD 150,000 USD 150,000 USD 150,000 USD 150,000 |
|  | F/V GALERNA (Panama) F/V KURTZIO (Spain) F/V MATXI KORTA (Spain) F/V MAR DE SERGIO (Spain) F/V ALBACORA QUINCE (Panama) F/V MONTECELO (St. Vincent and the Grenadines) F/V MONTEFRISA NUEVE F/V ALBACORA NUEVE (Curacao) F/V ALBACORA CARIBE (Panama) F/V ALBACORA DIEZ (Panama) F/V KOOSHA II (now ALBACORA SEIS) F/V SANT YAGO UNO (Guatemala) | OPAGAC | Licensing Irregularities, Unreported fishing activities | USD 150,000 USD 50,000 USD 50,000 USD 50,000 USD 50,000 USD 50,000 USD 50,000 USD 50,000 USD 50,000 USD 50,000 USD 50,000 USD 50,000 |
|  | F/V CAP FINISTERE F/V CAP VERGA F/V CAP COZ | MW Brands | Licensing Irregularities, Unreported fishing activities | USD 150,000 USD 150,000 USD 150,000 |
|  | F/V ZUBEROA (Spain) | ANABAC | Fishing without a license | Two year licensing ban (2013 & 2014) |
|  | F/V PANOFI DISCOVERER (Ghana) M/V VOLTA VICTORY (Ghana) M/V VOLTA GLORY (Ghana) | Panofi Fisheries Co. | Various (Fishing without a license, illegal transhipment at sea. Others) | USD 300,000 USD 100,000 USD 100,000 |
| 2013 |  |  |  |  |
|  | F/V PREMIER (South Korea) F/V SOLEVANT (Ivory Coast) | Dongwon Industries | Various (Fishing without a license, forged license, others) | USD 1,000,000 USD 1,000,000 |
|  | F/V SETA 60 (South Korea ) F/V SETA 62 (South Korea) F/V SETA 70 (South Korea) M/V SETA No.73 (Panama) | Inter-Burgo Industries Co. | Various (Fishing without a license, illegal transhipment at sea, forged licenses, others) | Case charged but not yet settled |
|  | HAE JEONG 3 (South Korea) HAE JEONG 7 (South Korea) | HaeJeong Co. Ltd. HaeJeong Co. Ltd. | Fishing inside the Inshore Exclusion Zone | USD 100,000 USD 100,000 |
| 2014 | M/V JINYUN |  | Reefer failure to get authorisation to land fish | USD 3000 |
|  | M/V GABU REEFER |  | Reefer failure to get authorisation to land fish | USD 2000 |
|  |  |  | Total Fines | USD 6,215,000 |

Source: World Bank and CSRP (2014a)

In addition to governance reforms, the WARFP provide support for fish landing infrastructure. The small-scale landing site to accompany the community-based resource management institution at Robertsport advanced in 2010 and 2011– with the land confirmed, deed and resettlement plan completed, and funding for compensation committed by the Government.  In 2014 construction of the landing site was inaugurated and began (World Bank, 2014).  However, given this late start, as of early 2016 construction had not been completed, and additional government funds were requested by BNF in order to fill budget gaps (World Bank and CSRP 2015b; World Bank and CSRP 2016). With the CMA operational the demand for this infrastructure grew, though as of March 2015 construction was still on hold after the recent ebola outbreak (World Bank and CSRP 2015b).

The larger landing site planned at Mesurado did not advance in the early years of the project.  Even as late as October 2012 the terms of the lease for the pier where the construction and operation would take place, were not finalized with the Ports Authority (World Bank, 2012a). By the time of the mid-term review, the lease from the Ports Authority to BNF had been signed in a manner sufficient to allow for the landing site and adjacent fish packaging center that was envisaged in the WARFP to advance (World Bank, 2014).  Difficulties with the company recruited to prepare the detailed designs further delayed progress in 2013 and into 2014 (World Bank, 2014).  As of 2016 construction had just begun (World Bank and CSRP 2016).

## 5.4 Senegal

WARFP-supported activities actually began in June 2010, in addition to ongoing World Bank-financed activities by the government to articulate a new policy statement and national law, to register all fishing canoes, and to support pilots in community management rights for coastal demersal fisheries, in the Integrated Management of Coastal and Maritime Resources Project (GIRMaC) and the Sustainable Management of Fish Resources Project (GDRH) (World Bank, 2012d). Progress in completing these reforms was reported to have been affected early by weak administration of the project, as a number of expenses deemed ineligible for World Bank financing according to the terms of the agreement with the government were incurred by the Ministry of Fisheries and Maritime Economy (MPEM) for all three Bank-financed projects in the sector: the GIRMaC, GDRH and WARFP, starting in August 2011 (World Bank, 2012d).  At the same time, implementation progress was reported to have decreased markedly (World Bank, 2012d). In April 2012 a new government was elected and the staffing of MPEM changed, with a new coordinator responsible for administering the WARFP financing named in June, 2012 (World Bank and CSRP, 2015d). Subsequently, the WARFP project was restructured by December 2012 to reduce the scope of activities planned for constructing fish landing infrastructure at Kafountine, and to continue financing the costs of state support to the community management pilots begun under the GIRMaC and GDRH (which had ended) (World Bank, 2012d). The stated objective of the project restructuring was to sharpen the focus to support the government’s policy objective of rebuilding the coastal demersal resource base for increased economic benefits (World Bank, 2012d).

Project finance to support governance reforms included: development of input controls for all canoes fishing in the EEZ via registration and licensing; compensation for foregone rents by industrial trawl vessels via a proposed ‘buy-back’ of  vessels and re-training programs for crew; expansion of pilots for community management rights in defined coastal demersal fisheries; enhanced administration of rules for tenure via increased transparency in state issuance of fishing licenses and research and assessment of fish resources (World Bank and CSRP, 2011c).  Progress in the financing and implementation of these reforms reportedly slowed considerably beginning in late 2011 as a result of reviews of possible ineligible expenditures with World Bank funds, the turnover of staff in MPEM in early 2012 and the project restructuring process completed in late 2012 (World Bank, 2014a). By mid-2014, state recognition of community management rights (via a new law) was in preparation, and the canoe registration program had identified 21,693 canoes, 77% of whom had been physically marked (World Bank, 2014a).  The growth in the canoe fleet over the recent decades has been exponential – in 2004 estimated suggested 12,000 canoes operating (World Bank, 2004b), whereas by mid-2014 the registration suggested over 21,000 (World Bank, 2014b). As of 2016, some 19,001 canoes were counted and only 61 percent registered, of which the number with a physical marking of the registration was unknown (World Bank and CSRP 2016). Despite repeated external support efforts prior to and through the WARFP, the registration process still has yet to be institutionalized and operationalized within the government and in society more broadly (World Bank and CSRP 2016). At various points, MPEM was reportedly considering a national regulation requiring registration of fishing canoes and possession of a fishing license in order to obtain the registration card for government fuel subsidies for fishing canoes (World Bank and CSRP, 2015d).  By 2016, the new fisheries law was passed (enacted by the legislature in June 2015), after more than eight years of development and revision, which directs the Ministry to prepare a regulation requiring small-scale vessel registration (World Bank and CSRP 2016).

Similarly to small-scale vessel registration, the process of licensing access for canoes has been required by regulation for almost a decade, but roughly 40 percent of vessels have obtained them (World Bank and CSRP 2016).  The capacity of the state agency to issue small-scale licenses has been assessed as lacking, and similarly the agreement and understanding by small-scale owners to purchase such licenses has always been questionable (World Bank and CSRP 2016).  As of 2016, a debate over reforming small-scale fishing licenses continued, with differences of opinion amongst fishers using different ports and landing sites (World Bank and CSRP 2016).

In terms of regulations for specific fishery systems, the WARFP supported the preparation of two fishery management plans (for cymbium and for shrimp fisheries), together with plans for the deepwater shrimp, octopus (with support from the EU) and sardinella (with support from the United States Agency for International Development) fisheries respectively, as well as two management plans prepared jointly with Mauritania for shared small pelagic fisheries (World Bank and CSRP 2016).  Of these seven management plans which include specific regulations for fishing activity targeting these species groups, only the regulations for the deepwater shrimp fishery had been adopted by the government as of early 2016 (World Bank and CSRP 2016).

In terms of project financing for the government to ‘buy back’ industrial trawl vessels and reduce the size of the fleet (and overall fishing effort), this activity failed to materialize (World Bank, 2014a).  Since 2006 the Government has maintained a freeze on new licenses for industrial trawl vessels, resulting in a 35% reduction in the fleet through attrition by 2014 (World Bank, 2014a).  However, the buy-out program only began in 2013, and ultimately failed to purchase any vessels (World Bank 2014a).  The design of this reform did not include modeling or surveys of the scale of payments that would provide sufficient incentives for vessel owners to take the ‘buy-out’, and in practice the proposed prices were too low to attract participants (World Bank 2014a).

At the local scale, the project continued to support the four pilots in community management rights for coastal fisheries that were initiated through the GIRMaC project, as well as another eight that were initiated under the GDRH (World Bank, 2014a).  The communities and the coastal demersal fishery systems for whom management rights were recognized by the state (four initially through the GIRMaC and then the remaining eight by 2016), and for which the actual areas were demarcated for community management, are as follows (World Bank and CSRP 2015d; World Bank and CSRP 2016):

Saloum river delta:

- Betenty: coastal shrimp (Penaeus notialis)

- Foundiougne: coastal shrimp (Penaeus notialis)

- Fimela: coastal shrimp (Penaeus notialis)

The ‘petite-cote’:

- Ngaparou: lobster (Panilurus regius) and other sedentary species (notably Cymbium and octopus)

- Mballing: lobster (Panilurus regius) and other sedentary species (notably Cymbium and octopus)

- Nianing: lobster (Panilurus regius) and other sedentary species (notably Cymbium and octopus)

- Point Sarene: lobster (Panilurus regius) and other sedentary species (notably Cymbium and octopus)

- Mbodienne: lobster (Panilurus regius) and other sedentary species (notably Cymbium and octopus)

Cap Vert Peninsula:

- Yenne: lobster (Panilurus regius) and other sedentary species (notably groupers)

- Bargny: lobster (Panilurus regius) and other sedentary species (notably groupers)

- Soumbedioune: lobster (Panilurus regius) and other sedentary species (notably groupers)

- Oukam: lobster (Panilurus regius) and other sedentary species (notably groupers)

A number of the associations in these sites focused on introducing artificial reefs to help increase targeted stocks, while several others introduced protected areas and no-take reserves, gear restrictions (e.g. minimum mesh sizes on nets), closed seasons for fishing, or some combination of rule changes (World Bank and CSRP 2016). For example the associations in the sites of Soumbédioune, Yenne and Fimela-Ndangane established a closed season in the month of June starting in 2015, for the Thiof (species of group: Epinephelus geneus), while the associations in Fimela-Ndangane, Foundiougne et Bétenty established a closed season in August 2015 for coastal shrimp (Peneus notialis) (World Bank and CSRP 2016).

According to World Bank trip reports the rules introduced by the fishing association in Ngaparou have likely yielded the biggest changes to date, with the introduction of technical measures in the adjacent sea area 3 kilometers wide and 12 kilometers long, which included introducing a closed area over roughly one third of the total managed area, gear restrictions and closed seasons in another roughly one third of the total managed area, and open access maintained in the remaining one third of the area (World Bank and CSRP, 2015d).  From 2005 when this effort began in Ngaparou to 2010, the average weight of lobsters caught in the managed area increased 72%, from 295 grams to 420 grams, with catch rates more than doubling from 1.5 kilograms per trip in 2006 to 3.5 kilograms in 2010 (World Bank and CSRP, 2015d).  Demersal fish species (and overall species diversity and abundance) are reported by fishers and government staff to have gradually reappeared in the area, though sampling or structured data collection has not occurred (World Bank and CSRP, 2015d).  At the same time, despite voluntary surveillance patrols by association members, conflict has reportedly increased as the growing catch rates in the area have attracted new entrants from neighboring communities and waters (World Bank and CSRP, 2015d). In total, fishers’ associations in 8 of the 12 sites had been legally recognized by the state as of mid-2015, (World Bank and CSRP, 2015d).

In conjunction with the introduction of community management rights, after restructuring the project increasingly supported fishers in targeted communities to undertake alternative livelihoods to fishing, via directed lines of commercial micro-finance as well as block grants for public infrastructure and/or startup of enterprises by the associations (World Bank and CSRP, 2015d).  Through this model, MPEM provided a guarantee with project financing to a local micro-finance institution (Credit Mutuelle Senegal - CMS), to establish a commercial line of credit for fishers (World Bank and CSRP, 2015d). By 2016 some 405 micro-loans were issued for a total of 259.06 million F CFA, with a repayment rate of 92 percent and 94 percent of the activities showing profitability (World Bank and CSRP 2016). MPEM’s consultations with recipients indicated a positive link with a reduction in fishing activity (World Bank and CSRP, 2015d). However the World Bank’s June 2015 trip report noted that broader implementation of this mechanism in advance of limited access for the canoe fleet at the national scale could be less effective in reducing overall fishing effort beyond the scale of the targeted communities (World Bank and CSRP, 2015d). The report highlighted another challenge that the required repayment period of 3 years was considered too short to satisfy the demand of all the fishers (World Bank and CSRP, 2015d).

The project’s support for enhanced fisheries surveillance operations by state agencies aimed to build upon existing efforts and capacity in place with MPEM (World Bank, 2009).  After the restructuring, progress in implementing these activities reportedly accelerated, particularly surveillance of operations by coastal industrial fishing vessels (World Bank, 2014a). The project supported the rehabilitation, equipping and furnishing of coastal surveillance stations, leading to inspections of 423 industrial vessels and 3,711 canoes in 2013 (World Bank, 2014a).  That same year a national strategy to combat IUU fishing was developed by MPEM (World Bank, 2014a).  In 2015, 751 coastal patrols were conducted, leading to inspections of 287 industrial vessels and 7,395 canoes, with arrests of two of the industrial vessels and 449 canoes for infractions (World Bank and CSRP 2016).

## 5.5 Sierra Leone

WARFP-supported activities actually began in Sierra Leone towards the end of 2010, providing support the Ministry of Fisheries and Marine Resources (MFMR) to articulate a new policy vision (5-year plan) and any accompanying law and regulations (World Bank and CSRP, 2015a). By March 2014 the policy statement was not completed and considered behind schedule (World Bank and CSRP, 2015a), and since that time a draft (including a range of background papers) was prepared, but not agreed by the government as of mid-2015 (World Bank and CSRP, 2015a). In addition, the project included financing to support the government to articulate policy objectives and new harvest rules for industrial vessels operating in specific coastal demersal fisheries, such as the shrimp fishery (World Bank, 2009). This was delayed until completion of the updated policy statement, though in 2013 and 2014 the project financed the costs to MFMR to synthesize the information on fish stocks available and to inform potential input controls (World Bank and CSRP, 2015a). At the same time, the government completed registration of 100 percent of the canoe fleet with project financing by March 2014, (though World Bank reports note that the painted used by MFMR to mark the canoes was not durable, so a transition to using metal registration plates was undertaken) (World Bank and CSRP, 2015a).

The project included finance for the introduction of management rights for defined ocean areas adjacent to the coast, in four pilot sites where co-management associations (CMAs) of fishers were envisaged to be established (World Bank, 2009). In 2011 MFMR staff (i.e. extension agents) began working with communities around these four areas to form CMAs, and identify new harvesting rules (World Bank and CSRP, 2014b).  By the end of 2013, 31 CMAs had been established and 15 legally recognized by the state (i.e. registered with District Councils) (World Bank and CSRP, 2014b). At this time, an independent analysis of progress was carried out by MFMR via project financing, via interviews with the extension agents and with community focus groups (World Bank and CSRP, 2014b).  According to that assessment, the creation of four zones where communities through CMAs could exercise management rights had given greater voice to residents and shown ‘encouraging trends’ for the governance of these fisheries (World Bank and CSRP, 2014b). The report cited one case in Bonthe as an example, where a CMA proposed a gear restriction, i.e. a minimum mesh size for fishing nets allowed for use in the waters under CMA management, resulting in the confiscation and destruction of illegal nets (World Bank and CSRP, 2014b).  At the same time, in early 2014 the demarcation of the zones for CMA management was not yet agreed with all communities and completed (World Bank and CSRP, 2014b).

In terms of efforts to enhance agency capacity for surveillance and enforcement, project-financed activities focused on compliance with the rule in the 1994 Fisheries Act prohibiting trawling in the coastal waters within 6 miles of the coast (World Bank, 2009).  During preparation, the Government introduced a new organizational structure to deliver surveillance operations for the fisheries, an inter-agency committee formed via a memorandum of understanding, the Joint Maritime Committee (JMC), which included MFMR, the Maritime Wing and the President’s Office of National Security, among others (World Bank, 2009). In late 2010 after project funds started to flow, the JMC helped coordinate increased sea patrols using existing equipment, and began to record a number of arrests, reporting a drop in illegal trawling in the coastal zone (World Bank and CSRP, 2014b).  According to World Bank reports, in the second half of 2011 the JMC conducted 10 patrols leading to 5 arrests for a total of $383,000 in fines paid to the Government (World Bank and CSRP, 2012).

In early 2012 the Government of the Isle of Man donated a patrol vessel to the government’s Maritime Wing to support JMC fisheries surveillance operations (World Bank and CSRP, 2014b).  The Government of the Isle of Man also supported MFMR to subsidize the purchase of 60 satellite transponders for all licensed industrial vessels, so that a functioning, satellite-based vessel monitoring system (VMS) was in place for all industrial vessels, and tracked at the JMC (World Bank and CSRP, 2014b). By the mid-term review in early 2013, the World Bank documented reports of increased artisanal fish catch and fishing effort in the communities of Goderich, Konakree dee and Tombo, and suggested a causal connection with the reduction in illegal trawling in the coastal fishing grounds (World Bank and CSRP, 2013).  The World Bank trip reports record discussions held with community members stating that they no longer feared damage to fishing nets and gear as a result of collisions with industrial trawl vessels in the coastal waters, and that they had seen an increase in their fish catch (World Bank and CSRP, 2013).

At the same time, although the Government of the United Kingdom provided hands-on training to JMC staff early in the project, training needs continued throughout the project and in some cases were reportedly not filled (World Bank and CSRP, 2014b). The project continued to finance investments to enhance the JMC’s fisheries monitoring center, for example in expanded internet access (World Bank and CSRP, 2014b).  In July 2014, reports indicated that MFMR had issued six licenses permitting trawling in the prohibited coastal zone, in contradiction to the 1994 Act (CSRP, 2015).

In addition to governance reforms, WARFP support was envisaged for fish landing infrastructure, including a small-scale fish landing site, and an industrial fish landing site in Freetown.  While this landing site was identified at Kissy Dockyard on MFMR property in the preparation of the WARFP, after approval of the additional financing for this site in 2011 the World Bank reported significant numbers of squatters’ settlements on the property.  A resettlement action plan was launched, but in February, 2012 the Minister of MFMR informed the Bank of the Government’s intention to move the landing site, to a location in Murray Town near the JMC fisheries monitoring center (World Bank and CSRP, 2012).  In 2013 the Government and the World Bank confirmed that the proposed landing site is in a Ramsar Wetland of International Importance and a detailed environmental and social impact assessment (ESIA) was required (World Bank and CSRP, 2013).  However, by 2014 the ESIA had not been completed, and the contract canceled with the firm recruited due to a failure by the government to comply with the World Bank’s procurement guidelines (World Bank and CSRP, 2014b). Subsequently, the funding for this landing site was cancelled.

Additionally, a small-scale fishing landing site was envisaged at Konakree dee, together with improvement of the road to Lungi airport, to support increased exports of high value fish (World Bank, 2009).  ).  Furthermore, a sanitary competent authority certified to EU standards was planned (World Bank, 2009).  As with the industrial landing site at Murray Town, the implementation of the small-scale site at Konakreedee was significantly delayed (World Bank and CSRP, 2014b).  In 2012 the Ministry recruited a consulting firm with Government resources, with terms of reference to provide a sanitary competent authority certified for export to EU markets (World Bank and CSRP, 2014b). As such, the Ministry did not take this activity forward with WARFP support, but the status as of mid-2015 was still uncertain.

Throughout phase one, the delivery capacity of MFMR was reported as a challenge, beginning with reports after just the first year (World Bank et al., 2011). A project implementation unit was established under MFMR, but housed outside the Ministry when office space agreed during appraisal was no longer available after the start date. By 2013 a review noted that a number of WARFP reforms had been delayed because of disagreements between MFMR focal points and the project coordinator at the implementation unit (World Bank, 2013).

In conclusion, the impact of the Ebola outbreak in Sierra Leone in May 2014 (as well as Liberia) must be highlighted.  In July 2014 the President of Sierra Leone declared a national emergency, and the World Health Organization declared a Public Health Emergency for the country on August 8th, 2014. The outbreak peaked in Sierra Leone between October and December 2014, with general restrictions on travel and a ban on public gatherings.

## 5.6 Regional – Sub-Regional Fisheries Commission (CSRP)

As mentioned previously, the focus of WARFP activities in the first phase was largely on national-level implementation of regionally-shared objectives, with the CSRP playing a coordinating and supporting role to national government agencies (e.g. monitoring and evaluating progress, helping to train implementation teams as needed, etc.).  The project document for the first phase envisaged a gradual shift in the level of implementation towards regional over the lifetime of the program and reform process, as national agencies strengthened the minimum frameworks and capacity needed to effectively collaborate at the regional level.

Beginning in 2010 with the initial countries, the CSRP established a Regional Coordination Unit housed at the Commission’s secretariat in Dakar, to provide support to countries.

Perhaps the largest effort at the regional scale was the work to enhance transparency in governance of the region’s fisheries, by establishing a ‘dashboard’ of key fisheries data and socio-economic indicators, such as fishing licenses issued, infractions and fines collected, etc. that would be housed on a website at the CSRP, drawing from data collected and submitted at the national level in each country.  This proved to be a significant undertaking, beginning with consultations and planning in each country on the current and future data that would be available, and existing legal frameworks for information-sharing, among others. This process to build consensus took longer than was envisaged, but resulted in agreement amongst countries on the parameters of the dashboard and information-sharing (CSRP 2016).

Development of the actual web-based tool was delayed due to performance issues with the first contractor, but as of 2016 the tool was completed and stored on the CSRP’s server, with windows and access for each country.  Throughout the process, countries began to disclose (e.g. on their own web sites) lists of licensed fishing vessels for the first time, significantly enhancing the transparency of governance of the harvesting sub-sector (CSRP 2016).  The dashboard was ready for launch in 2016, with the key challenge of ensuring that the agencies in each country are providing data into the tool on a timely basis, to begin to form a better public picture of the region’s fisheries.

In terms of supporting regional-scale efforts to combat illegal fishing, the CSRP began work on a regional registry of industrial fishing vessels, as well as helped coordinate collaboration between countries, e.g. supporting communication between the relevant national agencies to ensure that a vessel identified as fishing illegally in Liberia was inspected upon landing in Senegal, or assisting the agencies in Guinea-Bissau to rent a patrol boat from the Government in Senegal for periodic fisheries surveillance patrols (CSRP 2016).

Crucially, a key concern in the design of the WARFP was to ensure that fisheries surveillance patrols financed by the program would be carried out in accordance with international law, such as provisions in UNCLOS that forbid detaining crew members upon arrest of a foreign vessel fishing illegally (World Bank 2009).  As part of the WARFP, the CSRP carried out audits of the surveillance activities financed through the program in each country, to ensure compliance with the relevant provisions of international law – which were also highlighted as part of the agreements between the governments and the World Bank for the financing (CSRP 2016).

Additional activities carried out at the regional level beyond coordination and support to the countries, included the establishment of a network of journalists in the region to communicate more broadly on the status and issues in the fisheries (and their relevance to the daily lives of so many coastal residents), which culminated in a regional training workshop in Ghana in early 2016 (CSRP 2016).

Going forward, while the activities carried out at the regional level were relatively few compared to those financed at the national level in the first phase, as progress with reform continues to occur in the countries, more and more opportunities for collaboration and capture of economies of scale would be expected, via implementation by the CSRP.  The dashboard of indicators and data in particular would be expected to become a critical tool for public engagement in fisheries governance as well as supporting national and regional decision-making.

# VI. Outcomes from Reforms and Some Key Lessons Learned

Data on outcome indicators such as changes in biomass of targeted fish stocks and net economic benefits to West Africa from the fishery systems that they support (see section 3.4) have been sporadically collected at best during the first phase of the WARFP, so it is difficult to accurately characterize change since the beginning of the program (when baseline measures were taken) – for example carrying out an ex-poste economic evaluation of the reforms nor establish clear causality based on an impact evaluation using counterfactuals of what the outcome measures would have been in the absence of the reforms.  That said, the CSRP collected data from each of the governments on the specific outputs linked to WARFP reforms, which give an indication of the direction that outcome measures might be expected to take as a result.  These outputs are described in detail here, as well as any information available on changes to measures of outcomes in the ecological and social systems of West Africa’s fisheries (see Appendix 1 for the specific output measures from each of the five countries).

## 6.1 Outputs

The outputs from the WARFP follow the general approach to the design of the reforms, beginning with efforts to clear out illegal fishing in coastal waters, then to hold onto these gains through strengthening governance institutions for the harvesting segment of coastal fisheries value chains, and finally building local infrastructure and skills to process more of that harvest within the region. The largest volume of outputs and expected impact was achieved in this first priority – increasing surveillance to reduce illegal fishing.  Although the ratio is an imperfect measure, observed infractions dropped by roughly 50 percent or more in four of the five countries (though measures in Sierra Leone were not available after 2013), and in the fifth (Senegal) the coastal surveillance activities increased significantly.

Figure 8. % of known industrial fishing vessels operating in Liberia and Sierra Leone's waters, sighted as committing a rule infraction (trawling < 6 miles from shore)

Source: CSRP (2015)

This decline in the ratio of fishing infractions was accompanied by a number of specific WARFP reforms:

- increased sea patrols in three of the five countries;

- establishment of an functional VMS for the industrial fleets operating in four of the five countries (in the fifth, Senegal, such a system was previously in place);

- construction and launch of a new fisheries monitoring center and coastal surveillance station in Guinea-Bissau;

- increased numbers of trained observers on the industrial vessels fishing in Liberia, and increased inspectors conducting fisheries surveillance in Cape Verde (together with surveillance stations on Sal and Maio);

- multi-donor partnerships strengthened or catalyzed in both Liberia and Sierra Leone to support fisheries surveillance, including together with United States Coast Guard and National Oceanic and Atmospheric Administration (NOAA) in Liberia, and the Government of the Isle of Man, the International Military Training and Advisory Team (IMATT) to Sierra Leone, and the Environmental Justice Foundation (EJF);

- In the case of Cabo Verde the VMS was linked to smart phones for fisheries inspectors, while Liberia trialed smart phone applications to photograph illegal trawling (CSRP 2015). In four of the five countries, WARFP supported the establishment of inter-agency collaboration (e.g. joint committees) to enhance fisheries surveillance, based on formal memoranda of understanding.

Box 6. Outputs by early 2016 from WARFP reforms to enhance fisheries surveillance in Guinea-Bissau

- Patrol missions were conducted sporadically starting in 2013 (see Table 1), by renting a Senegalese patrol vessel from the Government (Department of Fisheries Surveillance – DPSP).  Patrols increased in 2015, and fines collected from vessels arrested were agreed to be published in local papers for transparency.

- The headquarters of FISCAP was refurbished as a surveillance center by early 2015, and equipped with a satellite-based vessel monitoring system (VMS), radar, an Automatic Identifier System (AIS), and short and long-range radio.  The center is operational and by 2016 the VMS was also operational and tracking 100% of the trawl fleet licensed at the time (99 trawlers).

- Two small coastal patrol vessels rehabilitated by WARFP and staff being trained in maintenance and repair, also a larger 20-meter coastal patrol vessel financed by the EU and available by March 2016.   Two other small coastal patrol vessels were expected.

- By 2016 a coastal surveillance station on Caravela was refurbished and equipped with radios and radar, and operational.

- A registration system for all vessels fishing in the country’s waters has been designed, allowing for the transfer of data on licensed vessels easily to FISCAP for surveillance.

- A study of sustainable financing of surveillance was conducted.

These outputs resulted in a significant increase in arrests and fines for fishing infractions in a number of the countries, with a distribution skewed towards the early years of the WARFP, such that over time the detected fishing infractions, fines and arrests decreased in the coastal fisheries in Cabo Verde, Liberia and Sierra Leone – as would be predicted if actual infractions were trending downwards (CSRP, 2015). For example in Liberia, during the first phase of the WARFP the government arrested or fined 48 fishing vessels for a total of over $6.4 million largely in the first three years, while the indicator on the rate of illegal coastal fishing dropped from 83 percent at baseline over time to 30 percent in 2015. Similarly, the high volume of arrests and fines occurred in the first few years of Sierra Leone. According to a number of reports, these efforts have been associated with increased yields for coastal communities, for example large fishing communities in Sierra Leone such as Tombo have subsequently reported a 42% increase in catch (World Bank, 2014a). Similarly, the Bank team noted that beginning in 2011, Liberian coastal communities experienced a change in fish availability with the sizes of all fish landed increasing and the overall volumes of fish caught more than double the levels in 2009 when the project began, according to sampling on fish landings carried out by the Community Sciences Program (World Bank and CSRP, 2015b).  The team was also given a clear message by the Co-Management Association in Robertsport and members of nearby communities: there are today far fewer incidents of illegal coastal trawling, and fish catch and revenues were increasing (World Bank and CSRP, 2015b).  Additionally, in 2014 the EU carried out an independent and positive assessment of Cabo Verde’s capacity to combat illegal fishing, building upon significant support to the Coast Guard from the U.S. Government, which permitted the country’s fish products to maintain access to European markets (World Bank, 2014).  Lastly, in Guinea-Bissau some $522,000 in fines was collected from enhanced surveillance patrolling in 2013 – early 2016.

In terms of outputs from additional efforts to strengthen governance, particularly to change the rules controlling fish harvesting and the organizations administering and monitoring them, the picture is somewhat more mixed.  At the national level, new policy statements were articulated and approved by the state in four of the five countries (and drafted in the fifth, Sierra Leone), and translated into draft laws and regulations in all cases – generally the product of several years of consultations and analysis at a minimum.  Additionally, in Senegal two fishery-specific policies and regulations (fisheries management plans) were completed and approved by the government.  State registration of small-scale fishing vessels increased to between 80 to 100 percent in three countries, and in Guinea-Bissau such registration was not part of the targeted reforms (given the relatively small domestic small-scale fleet). Only in Senegal did the registration rate for small-scale vessels decrease, and notably the significant fleet operating outside the country’s waters remains largely unregistered.  In total, some 37,000 canoes were registered across Cabo Verde, Liberia, Senegal and Sierra Leone (CSRP 2015). Registration for new small-scale vessels was frozen in Cabo Verde, and in Senegal efforts to begin to control access by the small-scale fleet through the use of licenses (‘fishing permits’) have advanced only partially. New biological assessments and bio-economic analyses for the fish stocks and fisheries were conducted in Cabo Verde, Guinea-Bissau and Liberia. Finally, a regional ‘dashboard’ for public disclosure of information on fishing licenses and public revenues is under construction and expected to be completed in 2016, with a number of countries beginning to publicly disclose this information.

The project’s targets for reduced fishing vessels (as a proxy for effort) via project-financed Government compensation in Cape Verde and Senegal, were not achieved (CSRP 2015). Such reductions were not introduced until a new input control was formalized freezing the size of the fleet in 2014 in Cape Verde (via a freeze in vessel registration), after which some 69 fishers received grants or subsidized loans in order to start new enterprises outside of the fisheries sector (World Bank and CSRP 2015b).  In Senegal, a rule freezing access to new industrial trawl vessels was in place at the start of the project, however no public ‘buy-backs’ of vessels occurred (World Bank and CSRP 2015d).

In terms of community management rights, the state has recognized communities’ right to manage defined areas or fisheries in two sites in Cabo Verde, one in Liberia and eight in Senegal (while four sites are in progress towards recognition in Sierra Leone, and such pilots are not included in the Guinea-Bissau reform program due to the limited amount of coastal community fishing activity).  The outputs from these pilots have been generally discussed as positive and encouraging in the trip reports and monitoring documents, with communities introducing harvesting rule changes in many cases and in some reported evidence of local coastal demersal fish stocks rebuilding. In Senegal where these rights have been exercised over the longest time period, communities have reported a 133% increase in catch efficiency (World Bank, 2012b).

Lastly, in terms of building local infrastructure and skills to process more of the fish harvest within the region, a majority of the targeted outputs were not realized. No fish landing sites were completed in the first four countries (none were planned in Guinea-Bissau), due to a mix of inadequate planning during the preparation phase, errors in procurement processes for large construction contracts, poor quality of design and oversight work by contractors, and a general hesitancy to advance these activities prior to completion of governance reforms to better control harvesting operations (for fear that efficiencies gained from landing and processing infrastructure might send a price signal to increase harvesting).  However, the small-scale landing site at Robertsport in Liberia is expected to be completed by the end of 2016, provided that additional public funds are secured for budget shortfalls.  In Cabo Verde community freezing facilities are in place and functional in Sal island, and a new auction market at the fishing port has been established and is now operating on the island of Santiago.

In conclusion, according to the targeted outputs recorded in the project documents, the objective of the first phase of the WARFP in Cabo Verde, Guinea-Bissau, Liberia, Senegal and Sierra Leone has been partially achieved, with efforts to combat and reduce illegal fishing largely successful, and additional governance reforms partially introduced throughout the countries at different rates, while the activities targeted towards increased local processing and value addition to fish products were mostly not completed (CSRP 2015).

## 6.2 Outcomes

The WARFP’s ecological and social outcome indicators were established on the time-scale of the program, rather than the first phase, i.e. some ten years (World Bank 2009).  These outcome indicators included:

- Ecological indicator: increased fish catch per unit of fishing effort, as a fisheries-dependent indicator of the size of the stock (i.e. increasing catch rates for the same level of fishing were taken as a proxy for biomass);

- Social indicators:

  - increase in net economic benefits from targeted fisheries to participating countries; and

  - empowerment of communities with management rights.

In terms of measuring the change in these indicators since the baseline at the start of phase one, the data simply was not systematically collected in the targeted coastal fisheries in order to permit such an assessment. For the ecological indicators, updated measures of catch-per-unit-fishing effort are not available in most targeted coastal fisheries, nor a time series of fisheries-independent data on stocks such as biomass measures.  Similarly for the social indicator of net economic benefits, the data were not collected after the baseline (e.g. on current costs, yields and estimated profits for the fleets operating in the coastal fisheries in each country), in order to permit an ex-poste economic analysis for example.

In terms of measures of the interaction between the ecological and social systems in the targeted fisheries, such as fishing effort and yield, data is generally available for the industrial fisheries, though much less so for the small-scale.

En lieu of data providing measures of some of these key indicators, it is difficult to say with the confidence the outcomes generated by the WARFP. Certainly the project has had significant success in supporting the countries to reduce high volumes of illegal fishing, often with quick and tangible positive impacts for nearby coastal communities (World Bank, 2014). An argument could be made that illegal fishing activity was as prevalent in West Africa at the time of appraisal as anywhere in the world, and the success in particular of Liberia and Sierra Leone has been highlighted in the news media (e.g. NEPAD, 2011). Similarly, while slower and less consistent across the four countries, tangible outputs for state-level fisheries governance reform were achieved (CSRP, 2015).  However, the project’s objective to simultaneously strengthen sector governance including compliance, and to capture more of the value chain locally via improved landing and processing infrastructure, proved too ambitious for the five-year time frame. Most if not all of the intended outcomes for increased local value added were not met, particularly in terms of increased exports and the infrastructure outputs to attain them (CSRP, 2015).

## 6.3 Some Lessons Learned

Based upon the context at the beginning of the WARFP (Chapter III), the types of governance reforms introduced by the program (Chapter IV), and the available measures of WARFP outputs and associated changes in fisheries outcomes, some of the following five lessons have been extracted:

- Tangible progress in combatting illegal fishing in West Africa was achieved as the first step in governance reform, with most of the WARFP’s targets met if not exceeded – though this will still require continued effort and investment to be sustained.

- Many West African states simply lacked the capacity to deliver fisheries governance reform at the spatial scales needed, with institutional frameworks creating/supporting agencies whose incentives may not always have been aligned to reform;

- A mismatch between the spatial scale of the ecological system and the rules governing the interaction with the social system was a key challenge for reform;

- Where these features (i.e. state agency delivery capacity and a spatial match between the ecological and social systems) were combined with inclusive decision-making – such as in community management pilots – harvest rules were changed to limit fishing effort and increase benefits.

- States underinvested in monitoring outcomes, and indicators may not have been designed to adequately measure WARFP objectives.

(i) Tangible progress in combatting illegal fishing in West Africa was achieved as the first step in governance reform, with most of the WARFP’s targets met if not exceeded – though this will still require continued effort and investment to be sustained.  As might be expected, there was no blueprint or single instrument that can be isolated as the cause, but rather a combination of a number of factors (some perhaps unrelated to the WARFP), including among others:

- Pooling of resources and government commitment via inter-agency groups formally organized (e.g. through a memorandum of understanding) around a clear mandate to enforce fish harvesting rules;

- Equipping such inter-agency groups, or responsible agencies, with the resources needed for minimum surveillance of fishing grounds, including a fisheries monitoring center, increased staff with enhanced training and protocols, and greater access to sea patrol vessels (which in many cases were not new or relatively costly, but rather were adapted to the climate and supported by engineers and sufficient operation and maintenance);

- Use of greater monitoring via requirement that all industrial vessels participate in a satellite-based vessel monitoring system (VMS) accessible to government authorities;

- Sufficient penalties to serve as a deterrence to illegal fishing activities, and increased training and capability to quickly and efficiently prosecute fishing infractions in a manner consistent with international law;

- Stakeholder engagement and monitoring, e.g. through information-sharing such as with smart phones and applications for photographing illegal vessels; and

- A committed and well-trained core of state agents, supported by the government to enforce compliance, and collaborating with international partners for transfer of skills and technology.

However, given the progress made to date, many of the enhanced agency operations to combat illegal fishing remain dependent upon both a committed, well-trained and well-supported core of state agents, as well as external financing to supplement public allocations.

(ii) Many West African states lack the capacity to deliver further fisheries governance reform at the spatial scales needed. Although progress in combatting illegal fishing likely helped build a consensus for the introduction of further governance reforms to limit fishing effort to levels that would rebuild or maintain fish stocks and supporting ecosystems, progress was slower and more mixed. A number of resource users pointed to illegal fishing as an obstacle to discussing potential reforms at the start of the WARFP.  However, in anticipation of removing this obstacle, the processes for policy reform and delivery, particularly at the national (if not regional) scale, were slower than envisaged in the likely over-ambitious design of the WARFP. Carrying out reforms to control fishing effort in a context of poverty and in a manner consistent with internationally-agreed principles of equity, even while demand, overfishing and resource scarcity grow, is an incredibly complex task for which there are few examples of success at a large spatial scale in the tropics.

A common theme emerging in the review of trip and monitoring reports, was that many state agencies were simply not up to this task of initiating governance reforms that simultaneously enhanced ecological and social outcomes, without compromising internationally-agreed principles of equity. State agencies reviewed in the case studies consistently displayed weak capacity to administer, monitor and enforce reforms, as many had been organized in the past around objectives of fisheries production where the incentives may not have been aligned to the reforms proposed. Such agencies were the entry points for reform given the large spatial scale targeted, but struggled to carry out large-scale extension efforts or diffuse monitoring and surveillance of fisheries. In the aggregate, the cases evoke Hilborn’s (2007) suggestion that actors focus on minimum reforms to ensure limited access while simultaneously working to enhance inclusion in governance institutions–in order to allow stakeholders to work through the governance process to find mutually agreed solutions over time. Such a suggestion seems particularly relevant for West Africa’s fisheries given their complexity and the emerging analyses of the challenges involved in fisheries governability (Kooiman and Bavinck, 2013).  The takeaway may well be that states should invest in greater inclusion in fisheries decision-making, and increased ecological and social benefits will follow.

An open question remains if state agencies in many West African countries lack the capacity to support the introduction of far-ranging and complex governance reforms, is this because they are the product of an institutional framework that consistently leads to such outcomes, or renders them particularly weak? What are the incentive structures and functions of effective state agencies for fisheries governance in the context of West Africa, notably to enforce compliance with rules and to provide the services needed to limit access at a large spatial scale?

(iii) A mismatch between the spatial scale of the ecological system and the rules governing the interaction with the social system was a key challenge for reform. The boundaries of ecological systems supporting commercial fisheries are rarely well defined, and as with many natural resources spatial mismatches between scales of governance and ecosystems are common (Crowder et al. 2008).  West Africa is no exception, with diverse (and relatively sedentary) coastal demersal fishery systems overlapping with migratory small pelagic fishery systems, and offshore tuna fisheries, etc., such that often the line is blurred between one ecological system and the next (for example defining all coastal demersal fish stocks on the continental shelf as one unit targeted for governance reforms, as was the case in the first phase of the WARFP). At the same time, the social systems are extremely complex, with large numbers of highly mobile resource users, targeting multiple species using a range of gear types.

As an initial step in reforming governance of these complex systems, the WARFP supported state agencies to lead the development of new national policy statements for all of the fishery systems in countries’ waters, together with the preparation of new national laws to support the realization of these policies, as well as registration of all fishing vessels.  However, the first phase of the WARFP largely did not focus on applying these instruments to develop fishery-specific rules that might directly affect fishing effort and hence ecological systems, fishing yields and the social benefits that they can provide.  Throughout the coastal fisheries in the first five countries, harvesting rule changes were generally only developed at the site-specific level in community management pilots, generally only covering small-scale fishing operations.  With some exceptions (e.g. the introduction of pre-cautionary total allowable catch limits for the industrial coastal fleet in Liberia, and the freeze on the registration of new small-scale vessels in Cabo Verde), fishery-specific harvesting rules changes have not yet been developed in order to limit fishing effort to levels that would maintain or rebuild the stocks to achieve states’ policy objectives.

Even where community management pilots were introduced and fishery-specific rules developed, the match of spatial scales was a critical factor. For example in Senegal, the application of pilots was ‘patchy’, such that waters neighboring community-managed areas were governed only by the state or de facto open access. In the case of Ngaparou, increased catch rates resulting from the rules introduced in the community-managed area attracted new and external entrants from neighboring waters, and created potential conflicts.

(iv) Where state agencies developed delivery capacity, where the spatial scale of the ecological and social systems were aligned, and where resource users were included in the decision-making – such as in community management pilots – harvest rules were changed to limit fishing effort. These factors combined in the community management pilots:

- state agency delivery capacity (e.g. through enhanced extension and facilitation, as well as surveillance to enforce rule changes),

- spatial match between ecological and social systems (e.g. delineation of ocean areas and/or specific fisheries to be governed, where the unit delineated is sufficient to elicit a bioecological response from any behavior changes in fishers associated with rule changes), and

- inclusive decision-making (e.g. state recognition of stakeholders right to manage the areas/resources delineated previously, and support as needed to do so – via delivery capacity referenced above).

This is not an exhaustive list nor a blueprint by any means, and certainly a small portion of the common features or characteristics of successful self-governance models that may apply (Ostrom 2005). However, in the experiences to date with the first phase of West Africa, these features appear to be present in few cases where fish harvesting rules were changed and actually associated with measures of increased benefits. In almost all sites in Senegal for example, user associations empowered with resource management rights introduced harvesting rules changes, often in the form of technical measures such as gear restrictions, closed seasons and areas. Where measurements were available, World Bank and CSRP reports characterized productivity increases and enhanced benefits for communities.

However, throughout the countries the first point above on state agency delivery capacity remained a challenge, as community pilots took longer than envisaged, e.g. with only one site introduced in Liberia compared to two planned, or 8 in Senegal compared to 20 planned, etc. Unsurprisingly, such efforts by the state to establish co-governance partnerships with resource users were labor-intensive and required significant investment in extension (as well as monitoring and surveillance to enforce compliance with user-articulated rules).

(v) States underinvested in monitoring outcomes, and indicators may not have been designed to adequately measure WARFP objectives. In the context of West Africa – though different in each country – a common feature was the scarcity of public resources invested in monitoring changes in the indicators of outcomes from the fisheries, or even those indicators of the interactions between the social and ecological systems (i.e. fishing effort and yield). Going forward, investing in much greater monitoring of changes in fishing catch and effort in targeted SES, as well as sampling of biomass and ecological indicators, and the size and distribution of the resource rents generated, together with counterfactuals, would provide much greater indications of the benefits associated with reforms.

A useful tool to assist states to monitor outcomes with scarce resources may be the recently developed ‘fisheries performance indicators’ (FPIs), a rapid assessment tool to provide an aggregate measure of outcomes from fisheries, following the three dimensions of the sustainable development concept: ecological sustainability, economic sustainability and social sustainability (Anderson et al 2015). The FPIs include 68 different measures of outcomes across these three components or dimensions of sustainable development, including:

- Ecological outcomes, such as stock status, by-catch of other species and protection of critical habitats;

- Economic outcomes, such as trends in harvest volumes and values, levels of risk (volatility of harvests and revenues), returns along the value chain and total wealth; and

- Social outcomes, such as returns to labor, health care and education access and facilities for workers and the percentage of assets locally owned (Anderson et al., 2015).

The authors note that the indicators are aggregated among the three dimensions, but not across them, and as of 2015 had been tested in 61 ocean fishery systems around the world as case studies that build an empirical body of knowledge (Anderson et al., 2015).

Additionally, while allocation of resources to data collection and monitoring of outcome indicators was insufficient in the first phase of the WARFP, the selection of indicators was reportedly not always the most appropriate measure of progress towards meeting policy objectives, leading to frequent revisions (World Bank and CSRP 2015d).  For example, measures of a reduction in fishing infractions were general, when more specificity on the types of infractions targeted would have been more meaningful, e.g. a reduction of infractions against the prohibition on industrial fishing within a certain distance such as 6 – 12 miles from the coast in several countries (Guinea-Bissau, Liberia and Sierra Leone).  Similarly, indicators of policy reforms were broad and not focused on specific reforms such as the recognition of community rights to manage defined areas of the sea or fisheries.

Ultimately, the objective would be to more precisely categorize governance reforms (i.e. changes to policies, rules or organizations governing the fisheries), in order to associate them to changes in outcomes to the ecological and social systems of the fisheries.  While a diversity of indicators can be used depending upon the context, and the FPIs for example provides a menu for rapid assessment, Table 18 below suggests some basic indicators on the various components of the fisheries that may be a useful starting point for monitoring changes in outcomes for West African countries, including indicators for the ecological systems, the social systems and the interactions between the two, as well as the governance systems that influence these interactions.

Table 18. Sample of Indicators for Fishery Systems and Outcomes

| Ecological System | Governance System | Social System |
| --- | --- | --- |
| - Clarity and size of system boundaries (based on spatial distribution of targeted fish stocks) - Productivity - Number and diversity of targeted fish stocks - Growth rate(s) of targeted fish stock(s) | Policies - Changes in policy objectives - Changes in targeted outcomes Rules - Changes in entry point (spatial and/or jurisdiction of origin) - Changes in intention (technical measures, inputs controls, output controls, rights around controls) Organizations - Changes in administration of harvesting rules - Changes in research, assessment and monitoring - Changes in enforcement Costs over time of formulating and enacting changes to institutions and organizations - Policy formulation/reform - Development and enactment of rule changes or new rules - Organizational costs to administer, monitor and enforce rules changes | - Number of fishers - Number and type of fishing vessels (fleets) - Fishing gear type used - Socio-economic attributes of fishers - History of use - Dependence on resource - Leadership/ entrepreneurship - Norms/social capital - Location |
| Interactions - Fishing effort (by fleet) - Fish catch (by targeted stocks) |  |  |
| Outcomes - Ecological: biomass of targeted stock(s) - Ecological: diversity of animal species and ecological structures - Social: efficiency of harvesting operations as measured by the PV of net economic benefits - Social: context-specific equity measures (e.g. distribution of net economic benefits) |  |  |

Incorporating monitoring and measurement of these indicators in future reform efforts could help associate fisheries governance reforms with changes in fisheries outcome measures (compared with the counter-factual).  Regardless of the types of indicators though, in the future much more investment would be expected in the collection of data on fishing effort changes (e.g. catch per unit of fishing effort in a given fishery), and in the changes in ecological and social outcomes.  The aim would be to correlate governance reforms to changes in fishing effort and ecological and social outcomes.

# VII. Considerations for the Future

This Chapter proposes some key considerations for the future of the WARFP, based upon the lessons extracted from Chapter VI:

- Tangible progress in combatting illegal fishing in West Africa was achieved as the first step in governance reform, with most of the WARFP’s targets met if not exceeded – though this will still require continued effort and investment to be sustained.

- Beyond these efforts to combat illegal fishing, many West African states simply lacked the capacity to deliver further fisheries governance reform at the spatial scales needed, with institutional frameworks creating/supporting agencies whose incentives may not always have been aligned to reform;

- Matching the spatial scale of the ecological system to the rules governing the interaction with the social system was a key challenge for reform;

- Where these features (i.e. state agency delivery capacity and a spatial match between the ecological and social systems) were combined with inclusive decision-making – such as in community management pilots – harvest rules were changed to limit fishing effort and increase benefits.

- States underinvested in monitoring outcomes, and indicators may not have been designed to adequately measure WARFP objectives.

These lessons focus on the fundamental imperative of strengthened governance over fish harvesting as the basis for enhanced and sustained benefits from the fisheries for West Africa, but not on investments for increased local value addition.  Experiences from phase one suggest that enhancing the size and efficiency of the post-harvest segments of fishery value chains should wait until reforms have sufficiently advanced. The theoretical concern that increased efficiencies in post-harvest operations would increase profits and send a signal to harvesters to produce more, which in the absence of effective rules would lead to increased fishing effort and potentially overexploitation. The practical experience was that proposed public investments in fish landing infrastructure in the WARFP may not have been justified for inclusion, as key pieces of the preparation (such as environmental impact assessments at the site level) were not completed.  Implementing such investments added to the complexity of the WARFP’s program of reforms and potentially increased the strains on state agencies charged with delivery.

Given these lessons, the focus of the second phase of the WARFP is suggested to be solely on continuing governance reforms (including combating illegal fishing). As such, the following seven steps are proposed for consideration by West African states as they identify and design the next round of fisheries governance reforms:

- Maintain efforts to combat illegal fishing at national and regional spatial scales, leveraging new technologies.

- Build upon the national-scale reforms (e.g. new policy statements, laws) to define the boundaries of the fishery systems to be governed and identify the specific entry points for reform (i.e. spatial scales and jurisdictions of origin – such as reforms to govern the small pelagic fishery at the regional scale with participating states as jurisdictions of origin, vs. coastal demersal fisheries at the local scale with co-governance between the state and communities);

- Drawing upon modeling of potential scenarios or empirical observation, work with stakeholders in each system to identify and develop reforms to limit fishing effort, based upon expected benefits (compared to the counterfactual) – for example scaling up community management pilots for coastal demersal fisheries;

- Ensure these proposed governance reforms are consistent with universally-agreed principles of equity, taking special account of small-scale fisheries;

- Estimate the financial costs of the proposed reforms over time, including compensation for foregone production where reforms will reduce fishing effort;

- Carry out a ‘reality check’ or feasibility assessment on the capacity of the responsible agency to deliver the reforms, including political feasibility and ‘governability’ from the literature on political economy (and particularly the distribution of the perceived economic costs of reforms); and

- Introduce enhanced monitoring of governance and fishery system outcome measures together with the reforms.

Each of these steps is discussed in further detail below:

(i) Continue to combat illegal fishing, leveraging new technologies and economies of scale.  States would be expected to need a minimum investment in prevention and surveillance to enforce compliance with fishing rules, even after the progress that has been made.  Even with the successes, most countries have at best partially completed a long-term fisheries governance reform process, with demand threats expected to continue into the near future.  Globally, with the population projected to reach 9.6 billion by 2050, seafood consumption is expected to rise (Waite et al. 2014) and hence demand placed upon ocean fisheries (World Bank 2013). Hence, interest in West African fisheries could be expected to remain high, as well as the potential for infractions. At the same time, even when and where reforms have been completed, though

Box 7. Ostrom’s ‘design principles’ for effective institutions for self-governance of shared resources such as fisheries

- The boundaries of the resource itself and of the set of fishery users are clearly defined,

- Operational (use) rules in the fishery are in keeping with local conditions,

- Those affected by operational (use) rules can participate in modifying those rules,

- Effective monitoring of the resource and fishing activity is carried out by, or is accountable to, the fishery users,

- Sanctions for violations of operational rules are ‘graduated’, based on the seriousness and context of the offence, and are issued collectively by the fishery user themselves, or by officials accountable to the users,

- Mechanisms for rapid, low-cost local-level conflict resolution are available,

- The institution’s right to exist and operate is accepted by government authorities, and

- Appropriate management rules are established at each spatial and/or organizational scale of the system, with these arrangements being ‘nested’ in an effective manner.

Source: Ostrom (2005)

assessments are limited and dated, the costs of fisheries enforcement remains significant – for example on the order of two percent of the landed value of the catch in OECD member waters in 1997 (Wallis and Flaaten 2000).  Given an estimate of the order of magnitude of the first sale value of fish caught in West African waters of some $1.5 billion per year, this would imply total expenditures for surveillance and enforcement of at least $30 million annually – though the OECD case applied to a very different context and the types of fisheries in West Africa may likely have higher surveillance costs.  Essentially, countries may expect expenditure levels comparable to those under the WARFP for surveillance, in order to ensure compliance with the ‘rules of the game’.

Of course, there are growing opportunities for efficiency gains in surveillance, from partnerships with stakeholders and users to raise awareness of the rules and prevent infractions, to utilization of advancing technologies for electronic monitoring of industrial and eventually small-scale fleets, to enhanced collaboration and reciprocal agreements that capture economies of scale (e.g. the agreement between Guinea-Bissau and Senegal to rent the latter’s patrol vessel periodically). However, experiences in phase one of the WARFP have shown that the crucial determinant for continued success will be a committed and well-trained core of state agents, supported across the government to enforce compliance, and collaborating with international partners for transfer of skills and technology.   Essentially, the ‘software’ of fisheries surveillance and enforcement will likely be more determinant of success than the ‘hardware’.

(ii) Build upon new national policies and laws to define the boundaries for fishery-specific reforms. The first phase of the WARFP supported the articulation of new national policy statements for the fisheries, and draft laws to advance these policies.  Building upon this foundation at the national-scale, and conscious of frequent mis-matches between the spatial scale of governance and ecological systems, phase two may support the definition of boundaries for specific fisheries to be governed and the entry points for reform, i.e. the spatial scale and the jurisdiction of origin. Ostrom (1990) suggested that effective, robust institutions governing the use of shared resources such as fish stocks tend to be characterized by a number of design principles, the first of which was that the boundaries of the resource itself and the set of users are clearly defined.  This principle has been applied in the case of fisheries as the concept of ‘management unit’, for which it is possible to make predictions, particularly about responses to changes in fishing activity and mortality (Sparre and Willmann, 2001).  In tropical fisheries such as those in West Africa, where multiple species could be targeted from a number of different stocks, a challenge is often to define the management units to ensure that corresponding institutions govern the behavior affecting a minimum amount of the resource to change its status (World Bank, 2011).  Fish stocks interact to such a degree that it is almost impossible to separate them, and so in many cases it is necessary to define resource management units, and then sub-units that take into account local conditions and for which predictions can still be made (e.g. a shrimp management unit defined nationally, comprised of local sub-units). For example, reforms to govern the small pelagic fishery would be expected to take place at a regional scale that matches the distribution of the stocks, where the jurisdiction of origin for reforms is the states that share the resource. Alternatively, coastal demersal fisheries that are more sedentary with smaller ranges of movement may be governed at a local scale with co-governance partnerships between communities and states as the jurisdiction of origin for reform.

A number of experiences in the first phase of the program reiterated the importance of scaling governance institutions to the ecological systems. For example, in Robertsport in Liberia, scaling the co-management association to the ecological system was an early challenge, as users of the adjacent coastal sedentary resources on the shelf migrated from a wide range of communities along the coast, and the resources targeted covered a wide range of the shelf (such that it was a challenge to change behavior affecting one part of the resource without covering the remainder).  Similarly, in Senegal the pilots have only affected a relatively small portion of the users – such that neighboring fishers have been increasingly drawn by the prospect of profits from the greater productivity of the resources within the communities’ management zone (World Bank and CSRP, 2015c).

(iii) Developing inclusive rules to limit fishing effort, at spatial scales that match the ecological systems.

For defined and bounded fisheries targeted for further reform, states may wish to invest in inclusive-decision making, which draws upon potential reform scenarios developed through bio-economic modeling and/or empirical observation, in order to facilitate and support stakeholders in each fishery to identify and develop reforms to limit fishing effort.  Based on policy objectives, these limits would aim to ensure that the stocks are maintained or rebuilt to sizes capable of supporting the maximum sustainable yield, and perhaps higher. Additionally, translating these limits into access rights that mimic some of the characteristics of property rights may align economic incentives with fishing limits, where such incentives are a key driver of fishing behavior (Bromley and Cernea, 1989; Ostrom and Schlager, 1996; Ostrom, 2005).  However the types of rules limiting fishing effort and the rights that they confer would be fishery and context-specific, dependent upon countries’ policy objectives and on the inclusion of stakeholders in the design process.  Investment in inclusion may take time for states, but as the case of Senegal has illustrated – can determine the success of rules. Several years ago the government introduced a rule requiring all small-scale fishers to purchase access rights, i.e. fishing permits, yet compliance remains below 50 percent (World Bank and CSRP 2016). General trends of fishing effort and overexploitation have continued throughout much of Senegal’s waters, and while awareness and acceptance by fishers of the need to limit access via licensing is growing, some coastal communities still prefer to keep access to the fisheries open (World Bank and CSRP 2016).

One of the examples where the first phase supported governments to introduce-fishery specific rules developed through an inclusive process was the community management pilots for coastal demersal fisheries.  Given the general success of these pilots in the first phase (and significant time commitments required), scaling up these efforts to govern more of the coastal demersal fisheries under such partnerships would seem an opportunity for West African states to achieve some of their fisheries policy objectives, though would likely be a challenging effort. In Senegal for example, such rights have been discussed as a pre-cursor to full concessions to coastal communities, which would add the right of exclusion to the bundle of community rights recognized by the state (World Bank and CSRP 2016). Yet in Senegal as well as the other countries, a key question will be: do the various agencies of the state have the resources and training to play a partnership and supporting role in governing the coastal demersal fisheries?  For example, can they mobilize much larger extension efforts to collaborate on the ground with communities and facilitate co-governance partnerships?  Are the agencies even organized to deliver such support, and are young professionals trained to work in this mode?  The skill set to build co-governance partnerships is different from typical extension efforts such as seen in Sierra Leone, where the co-management associations were initially seen to be extensions of the state rather than inclusive institutions for exercising community management rights (Macphail 2013). Similarly in Liberia, because the co-management association was implementing administrative tasks for the Bureau for National Fisheries (such as collecting fees for canoe registration and licenses) and because of the prominent role of the Board of Directors nominated by the Ministry of Agriculture, the association was for a time considered as an extension of the national government (Macphail, 2013). At the time in 2013, these associations’ constitution differed from the structured of the community fishers’ associations in Senegal and Cabo Verde, where the associations are fully owned and driven by stakeholders (Macphail, 2013).

Equally important to these questions will be the level of organization among resource users and communities: if the state is going to partner in the governance of coastal demersal fisheries in West Africa, with whom will it partner? How are fishing communities and user groups organized along the value chain; are partners representative of the diversity of users?  Here again the question of scale will be crucial: are the management rights defined over a spatial scale that matches approximately with the ecological system? More specifically, are communities are recognized for rights to manage an area of the sea or a defined fish harvesting unit that matches closely enough with the biological and ecological characteristics of the targeted fish species and species groups, in order to see the stocks responding to harvesting rules and the fishing behavior changes that they aim to encourage)?

(iv) Ensure these proposed governance reforms are consistent with universally-agreed principles of equity, taking special account of small-scale fisheries. In 2015, FAO facilitated agreement of its member states on voluntary guidelines for governance of small-scale fisheries in support of the Code of Conduct for Responsible Fisheries. The ‘small-scale fisheries guidelines’ emphasize the relevance for small-scale fisheries of a number of internationally-agreed principles, including: (i) respect for human rights and dignity; (ii) equity in fisheries, including respect of cultures, non-discrimination, gender equality and equity, and social responsibility; (iii) equity to future generations by emphasizing sustainable development; and (iv) inclusive, sustainable and fair governance processes, including consultation and participation, rule of law, transparency, accountability, holistic and integrated approaches (FAO, 2015). Essentially, the guidelines promote an approach to fisheries governance focused on small-scale fishers that keeps the principle of respect for human rights at the forefront, and particularly poverty eradication and food security (FAO, 2015).  These guidelines provide a new tool to West African states in the development of fishery-specific governance reforms as described above, and in particular provide principles that can guide the introduction of any rules that limit fishing – with a priority on securing traditional access for small-scale fishers (as several countries have aimed to do through rules prohibiting industrial fishing within specific distances of the coast).

The small-scale fisheries guidelines also provide another tool for governments to include resource users in decision-making and development of fishing rules, such as through the community management pilots trialed in the first phase of the WARFP.  Of course even in these cases, fishing communities will be different in each context and heterogenous, so creation of community management rights by the state can still be prone to elite capture within communities (Davis and Ruddle, 2012), and fail to meet principles for equity such as in the small-scale fisheries guidelines.

(v) Estimate the financial costs of proposed reforms over time, including compensation for foregone production where reforms will reduce fishing effort. Even with financing from the World Bank, the financial costs and duration of the fisheries governance reform process in West Africa have shown to be significant.  In particular, where fishing effort is reduced as a result of reform, particularly in small-scale fisheries, the FAO small-scale fisheries guidelines (as well as the World Bank’s social safeguard policies for reforms financed by the Bank) imply that users are compensated for foregone production.  The documents summarizing progress with phase one of the WARFP did not indicate any formal reports of involuntary loss of access by small-scale fishers as a result of state recognition of community management rights.  In Senegal and Cabo Verde mechanisms for compensation were established and utilized to ensure consistency with World Bank social safeguards, providing micro-finance opportunities on a voluntary basis, as well as block grants to help start enterprises.  Nonetheless, given historically high levels of fishing effort and overexploitation in a number of small-scale fisheries, countries in phase two will likely need to scale up mechanisms and effort to provide compensation and alternative livelihoods for any foregone production in small-scale fisheries.

Where small-scale production is foregone, the World Bank’s experiences with conditional cash transfers in other continents and sectors may be applicable. Such conditional cash transfers are public programs that transfer cash, generally to poor households, on the condition that those households make pre-specified investments in the human capital of their children (Fiszbein and Schady 2009). In the context of West African fisheries, the state could provide cash transfers to fishing households where community rights have been recognized, on the condition that community fishing rules to limit effort are followed.

(vi) Carry out a ‘reality check’ on agency capacity to deliver proposed reforms, e.g. through a feasibility assessment of the agency(ies) capacity, including political feasibility (and particularly the distribution of the perceived economic costs of reforms). As various groups compare the expected benefit streams under a proposed governance change to the status quo, a key to consensus and collective action is actually the distribution and who will bear the costs (Libecap 1994).  Resistance to change often favors the status quo and reflects perceived unequal distribution in the potential gains and losses from proposed changes, uncertainty about who wins and loses from the proposed changes, among others (OECD 2011). Political science models of the process by which consensus is reached on proposed reforms emphasize the importance of the distribution of potential costs and benefits – or ‘wins and losses’ – which can form additional ‘hidden costs’ in the introduction of reforms (see Table 19) (Gupta 2010).  Particularly in shared resources such as fisheries where various groups are heterogeneous, the challenge of reaching consensus on reforms becomes even greater (Libecap 1994). This is frequently the case with fisheries governance reforms, where the costs are generally highly concentrated in specific groups while the benefits are diffuse across the community as a whole (OECD 2011).  As such, the reductions in fishing effort achieved in phase one of the WARFP through combatting illegal fishing, could theoretically have been the most likely reforms to gain consensus – given that the specific groups where costs were concentrated, were often foreign (and hence had less bargaining power in the reform process).

Table 19. Simple illustration of likelihood of achieving consensus on proposed fisheries governance reforms, based on the distribution of potential economic costs and benefits

| Costs (those who might ‘lose’) | Benefits (those who might ‘gain’) |  |
| --- | --- | --- |
|  | Diffuse | Concentrated |
| Diffuse | Inaction | Consensus likely reached |
| Concentrated | Consensus likely rejected | Conflict |

Source: adapted from Gupta (2010)

In summary, the distribution of perceived costs and benefits of potential governance reforms in a given fishery can significantly influence the political feasibility of such reforms (Libecap, 1994; Gupta, 2010).

(vii) Introduce enhanced monitoring of outcome measures together with reforms. Perhaps some of the most important data gaps in correlating governance reforms to outcomes in West Africa’s fisheries are on the interactions between the social and ecological systems, in terms of fishing effort and yield, as well as the indicators of system outcomes such as the size and distribution of economic benefits, and the biomass of targeted and associated fish stocks, as well as the status of ecological structures supporting targeted stocks. For example, Table 18 in Chapter Six suggests some key indicators that could be monitored in order to assess the impacts of governance reforms in a given fishery, focusing on the ecological, social and governance systems. In particular, changes in measures of fishing effort (or catch per unit of fishing effort) and of economic benefits, may be instructive in the correlation of governance reforms to outcomes.

References

Anderson, J.L., Anderson, C.M., Chu, J., Meredith, J., Asche, F., Sylvia, G., Smith, M.D., Anggraeni, D., Arthur, R., Guttormsen, A., McCluney, J.K., Ward, T., Akpalu, W., Eggert, H., Flores, J., Freeman, M.A., Holland, D.S., Knapp, G., Kobayashi, M., Larkin, S., MacLauchlin, K., Schneir, K., Soboil, M., Tveteras, S., Uchida, H., and Valderrama, D. (2015) The Fishery Performance Indicators: A Management Tool for Triple Bottom Line Outcomes. PLoS ONE, 10(5).

Anderson, L.G. and Seijo, J.C. (2010) Bioeconomics of fisheries management. Ames, Iowa. Wiley-Blackwell Publishing.

Beddington, J.R., Agnew, D.J., and Clark, C.J. (2007) Current Problems in the Management of Marine Fisheries. Science 316 (5832): 1713-1716.

Belhabib, D., Sumaila, U.R., and D. Pauly (2015) Feeding the poor: contribution of West African fisheries to employment and food security. Ocean & Coastal Management 111: 72 – 81.

Christy, F. T. Jr. (1992) Territorial use rights in marine fisheries: definitions and conditions. FAO Fisheries Technical Paper No. 227. Rome, FAO.

Convention on Biological Diversity (2013, February) Quick Guides to the Aichi Biodiversity Targets. Version 2. Retrieved from https://www.cbd.int/doc/strategic-plan/targets/compilation-quick-guide-en.pdf

CSRP (2015) West Africa Regional Fisheries Program Annual Report 2014. Regional Coordination Unit, Dakar, CSRP.

CSRP (2016). WARFP Activities implemented by the CSRP.  Regional Coordination Unit, Dakar, CSRP.

DFID, World Bank and FAO (2007) Sierra Leone: A proposed Fisheries Sector Strategy Paper (FSSP). Prepared by Neiland, A.E., Arbuckle, M., Bodiguel, C., Bostock, T., Campbell, J., Gronnevet, L., Kaindaneh, P., Seisay, M., and Williams, L.O. London: UK Department for International Development (DFID), Washington, D.C: World Bank, and Rome: FAO.

EDF, International Sustainability Unit, 50-in-10 (2014) Towards investment in sustainable fisheries: a framework for financing the transition.  Discussion document. Accessed at: http://www.pcfisu.org/wp-content/uploads/2014/07/Towards-Investment-in-Sustainable-Fisheries.pdf on June 10.

EDF (2015) The Potential for Global Fish Recovery: How Effective Fisheries Management can increase Abundance, Yield and Value.  Accessed at: http://www.edf.org/sites/default/files/content/upside-model-report-summary.pdf on June 9.

European Commission (2015) EU and Liberia initial a new sustainable Fisheries Partnership Agreement.  Accessed at: http://ec.europa.eu/newsroom/mare/itemdetail.cfm?item_id=23850&subweb=343&lang=en on June 11.

FAO (1997) Fisheries Management.  FAO Technical Guidelines for Responsible Fisheries No. 4.  Rome, FAO

FAO (2009) Bonne gestion et gouvernance durable des peches au sein de la CSRP – PRAO composante 1. Background paper prepared for the World Bank, Rome, FAO.

FAO (2011) Review of the state of world marine fishery resources. FAO Fisheries and Aquaculture Technical Paper No. 569. Rome, FAO.

FAO (2012a) State of the World’s Fisheries and Aquaculture. Rome: FAO.

FAO (2012b) Voluntary Guidelines on the Responsible Governance of Tenure of Land, Fisheries and Forests in the Context of National Food Security.  Rome: FAO.

FAO (2014) State of the World’s Fisheries and Aquaculture. Rome: FAO.

FAO (2015) Voluntary Guidelines for Securing Sustainable Small Scale Fisheries in the Context of Food Security and Poverty Eradication. Rome, FAO.

FAO (2015b) Marine capture fisheries production. FIGIS Database.

FAO (2016) State of the World Fisheries and Aquaculture. Rome: FAO.

FAO Coordinating Working Party on Atlantic Fishery Statistics (1990) Handbook of fishery statistics.  Accessed at http://www.fao.org/fishery/cwp/handbook/A/en on June 7, 2015. Rome, FAO.

Fiszbein, A. and Schady, N., with Ferreira, F.H.G., Grosh, M., Kelleher, N., Olinto, P. and Skoufias, E. (2009) Conditional Cash Transfers: Reducing Present and Future Poverty. Washington, D.C: World Bank.

Fontana, A. and Samba, A. eds (2013) Artisans de la mer: une histoire de la peche maritime senegalaise. Dakar: La Rochette.

Grafton et al. (2007) Economics of Overexploitation Revisited. Science, Vol. 318, December 7, 2007.

Heileman, S. and Tandstad (2008) Canary Current LME, pp. 131–14. In The UNEP Large Marine Ecosystem Report: A perspective on changing conditions in LMEs of the world's Regional Seas. Rapport et études des mers regionals no 182. Nairobi, PNUE. K. Sherman and G, Hemphel, eds.

Interpol (2014) Study on Fisheries Crime in the West African Coastal Region. Environmental Security Sub-Directorate.  Project Scale. Lyon: Interpol.

Kaindeneh, P. (2009) Technical Support to Sierra Leone Fish Marketing.  Background Report to the West Africa Regional Fisheries Program.

Macfadyen, G. (2007) Liberia: Diagnostic Trade Integration Study – Fisheries. Integrated Framework for Trade-Related Technical Assistance to the Least Developed Countries. Washington, D.C: World Bank.

Macphail, B. (2013) Consultancy report for clear road mapping of the development of Co-Management Associations (CMA) and Territorial Use Right Fishery (TURF) in the West Africa Regional Fisheries Program (WARFP) in Sierra Leone and Liberia: Sierra Leone Report.  Prepared for the World Bank.

Mees, C. (2011) Liberia Fisheries Assessment No. WARFP/CS/7/10. London: MRAG.

MFMR (2010) Training Manual for Local Council. Freetown: Sierra Leone Ministry of Fisheries and Marine Resources.

MRAG (2005) Review of Impacts of Illegal, Unreported and Unregulated Fishing on Developing Countries. London, MRAG.

MRAG (2009) Illegal fishing in West Africa.  Background paper prepared for the World Bank, London, MRAG.

OECD (2008) Fishing for Coherence in West Africa: Policy Coherence in the Fisheries Sector in Seven West African Countries. Paris: OECD.

OECD (2016) The Future of The Ocean Economy: Exploring the prospects for emerging ocean industries to 2030. Paris: OECD.

Ostrom, E. (1990) Governing the commons: the evolution of institutions for collective action.  Cambridge University, New York, Cambridge University Press.

Ostrom, E. (2005) Understanding Institutional Diversity. Princeton, NJ: Princeton University Press.

Pauly, D. and V. Christensen (1995) Primary production required to sustain global fisheries. Nature 374: 255 – 257.

Sambe, B., Tandstad, M., Caramelo, A.M., and B. Brown (2016) Variations in productivity of the Canary Current Large Marine Ecosystem and their effects on small pelagic fish stocks.  Environmental Development 17: 105 – 117.

Sea Around Us Project (2015) Capture fisheries production.  Accessed at: http://www.seaaroundus.org/data/#/eez on June 8, 2015. University of British Columbia.

Secretary of State for Fisheries and Maritime Economy. 2013. Strategic Plan for Fisheries Development in Guinea-Bissau: 2013 – 2017. Secretary of State for Fisheries and Maritime Economy: Bissau.

Sesay, M. (2009) Sierra Leone Fisheries.  Background paper to the preparation of the West Africa Regional Fisheries Program.

Sewell, B., Atkinson, S., Newman, D., and Suatoni, L. (2013) Bringing back the fish: an evaluation of U.S. fisheries rebuilding under the Magnuson-Stevens Fishery Conservation and Management Act.  NRDC Report. Washington, D.C., NRDC.

Sherman, K. and A. Duda (1999) An Ecosystem Approach to Global Assessment and Management of Coastal Waters. Marine Ecology Progress Series 190:271-287.

Sparre, P. and Willmann, R. (2001) Bioeconomic Analytical Model No. 5.  XIII EAFE Conference, Salerno, 18 – 20 April, 2001.

Srinivasan, U.T., Cheung, W.W.L., Watson, R., and Sumaila, U.R. (2010) Food security implications of global marine catch losses due to overfishing. Journal of Bioeconomics, 12:183–200.

United Nations (1992) Rio Declaration on Environment and Development. United Nations, New York. Retrieved from http://www.unesco.org/education/nfsunesco/pdf/RIO_E.PDF

United Nations (2002) Johannesburg Declaration on Sustainable Development. Retrieved from http://www.un-documents.net/jburgdec.htm

United Nations (2012) The Future We Want: Outcome Document of the United Nations Conference on Sustainable Development. Retrieved ffrom https://sustainabledevelopment.un.org/content/documents/733FutureWeWant.pdf

United Nations Department of Economic and Social Affairs (UN DESA) 2013. World Population Prospects: The 2012 Revision, Key Findings and Advance Tables [online]. Working Paper No. ESA/P/WP.227. Retrieved ffrom  http://esa.un.org/wpp/Documentation/pdf/WPP2012_%20KEY%20FINDINGS.pdf

United Nations General Assembly (2015) Resolution adopted by the General Assembly on 25 September 2015, Transforming our world: the 2030 agenda for sustainable development. A/Res/70/1.  United Nations, New York. Retrieved from http://www.un.org/ga/search/view_doc.asp?symbol=A/RES/70/1&Lang=E

Van Santen, G., Lo., M. and Virdin, J. (2004) Republic of Senegal: Fishery Sector Strategy. Washington, D.C: World Bank.

Van Santen, G. and Kamara, A. (2006) Sierra Leone: Diagnostic Trade Integration Study – Fisheries. Integrated Framework for Trade-Related Technical Assistance to the Least Developed Countries. Washington, D.C: World Bank.

Van Santen, G. and Stobberup, K. (2007) Republic of Cape Verde: World Bank Fisheries Sector Strategy Assessment. Washington, D.C: World Bank.

Wallis, P. and Flaaten, O. (2000) Fisheries Management Costs: Concepts and Studies. Paris: OECD. http://www.oecd.org/greengrowth/fisheries/1917868.pdf

World Bank (2004) Saving fish and fishers: towards sustainable and equitable governance of the global fishing sector. Report No. 29090-GLB. Washington, D.C., World Bank.

World Bank (2005) Project Appraisal Document for a Senegal Integrated Marine and Coastal Resource Management Project. Washington, D.C., World Bank.

World Bank (2006) Where is the wealth of nations? Measuring capital for the 21st century. Washington, D.C., World Bank.

World Bank (2009) Project Appraisal Document: West Africa Regional Fisheries Program.  Washington, D.C., World Bank.

World Bank (2011) Project Appraisal Document: West Africa Regional Fisheries Program in Ghana. Washington, D.C., World Bank.

World Bank (2012a) Aide Memoire: West Africa Regional Fisheries Program in Liberia. October 17 – 21, Monrovia, Liberia, World Bank.

World Bank (2012b) Restructuring Paper: West Africa Regional Fisheries Program.  Report No. 74617. Washington, D.C., World Bank.

World Bank (2012c) Implementation Completion and Results Report: Senegal Integrated Marine and Coastal Resource Management Project. Report No. ICR2377. Washington, D.C., World Bank.

World Bank (2014) Implementation Status Report: West Africa Regional Fisheries Program.  July 6, 2014. Washington, D.C., World Bank.

World Bank (2015) Implementation Status Report: West Africa Regional Fisheries Program.  February 25, 2015. Washington, D.C., World Bank.

World Bank and CSRP (2011a) Aide Memoire: West Africa Regional Fisheries Program in Cape Verde. December 1 – 8, Praia, Cape Verde, World Bank.

World Bank and CSRP (2011b) Aide Memoire: West Africa Regional Fisheries Program in Liberia. August 6 – 12, Monrovia, Liberia, World Bank.

World Bank and CSRP (2011c) Aide Memoire: West Africa Regional Fisheries Program in Senegal. March 4 – April 1, May 24 – 27, Dakar, Senegal, World Bank.

World Bank and CSRP (2012) Aide Memoire: West Africa Regional Fisheries Program in Sierra Leone.  February 6 – 10, Freetown, Sierra Leone, World Bank.

World Bank and CSRP (2013) Aide Memoire: West Africa Regional Fisheries Program in Sierra Leone.  Mid-Term Review, March 11 – 15, Freetown, Sierra Leone, World Bank.

World Bank and CSRP (2014a) Aide Memoire: West Africa Regional Fisheries Program in Liberia. February 17 – 22, March 12 – 18, Monrovia, Liberia, World Bank.

World Bank and CSRP (2014b) Aide Memoire: West Africa Regional Fisheries Program in Sierra Leone.  February 9 – 16, March 18 – 27, Freetown, Sierra Leone, World Bank.

World Bank and CSRP (2015a) Aide Memoire from Mid-Term Review. February 4 – 5, 2015; October 27 – 31, 2014; Washington, D.C, World Bank

World Bank and CSRP (2015b) Aide Memoire: West Africa Regional Fisheries Program in Cabo Verde. June 15 – 19, Praia, Cape Verde, World Bank.

World Bank and CSRP (2015c) Aide Memoire: West Africa Regional Fisheries Program in Guinea-Bissau. July 28 – 30, 2015. Washington, D.C, World Bank.

World Bank and CSRP (2015d) Aide Memoire: West Africa Regional Fisheries Program in Liberia. April 16 – 22, Monrovia, Liberia, World Bank.

World Bank and CSRP (2015e) Aide Memoire: West Africa Regional Fisheries Program in Senegal. June 8 – 12, Dakar, Senegal, World Bank.

World Bank and CSRP (2015f) Aide Memoire: West Africa Regional Fisheries Program in Sierra Leone. February 9 – 16 and March 18 – 27, Freetown, Sierra Leone, World Bank.

World Bank and CSRP (2016a) Aide Memoire: West Africa Regional Fisheries Program in Cabo Verde. January 11 – 16, 2016.  Washington, D.C.: World Bank.

World Bank and CSRP (2016b) Aide Memoire: West Africa Regional Fisheries Program in Guinea-Bissau. April 11 – 14, 2016. Washington, D.C: World Bank.

World Bank and CSRP (2016c) Aide Memoire: West Africa Regional Fisheries Program in Liberia.  January 25-31, 2015. Washington, D.C: World Bank.

World Bank and CSRP (2016d) Aide Memoire: West Africa Regional Fisheries Program in Senegal. January 18 – 22. Washington, D.C.: World Bank.

World Bank and FAO (2009) The Sunken Billions. The Economic Justification for Fisheries Reform. Washington, DC, World Bank.

World Bank, NEPAD and CSRP (2011) Aide Memoire: West Africa Regional Fisheries Program in Sierra Leone. August 1 – 5, Freetown, Sierra Leone, World Bank.

Worm, B., Hilborn, R., Baum, J.K., Branch, T.A., Collie, J.S., Costello, C., Fogary, M.J., Fulton, E.A., Hutchings, J.A., Jennings, S., Jensen, O.P., Lotze, H.K., Mace, P.M., McClanahan, T.R., Minto, C., Palumbi, S.R., Parma, A.M., Ricard, D., Rosenberg, A.A., Watson, R., Zeller, D. (2009) Rebuilding Global Fisheries.  Science, 325:578-585.

Ye, Y. and Cochrane, K. (2011) Global overview of marine fishery resources. In FAO (2011) Review of the state of world marine fishery resources.  FAO Fisheries and Aquaculture Technical Paper No. 569.  Rome: FAO.

Ye, Y., Cochrane, K., Bianchi, G., Willmann, R., Majkowski, J., Tandstad, M. & Carocci, F. 2013. Rebuilding global fisheries: the World Summit Goal, costs and benefits. Fish and Fisheries, 14 (2): 174–185.

Zeller, D. and Pauly, D. (2015) Reconstructing marine fisheries catch data. Accessed at http://www.seaaroundus.org/doc/Methods/CatchReconstructionMethod/Methods-Catch-tab-June-8-2015.pdf on June 8, 2015.  Sea Around Us Project, University of British Columbia.

| APL-A1 Outcome Indicators | # Appendix I. WARFP Phase One Targets and Outputs Country | Baseline in 2009 | Target for End of Phase I | Measured Value at Beginning of 2016 |
| --- | --- | --- | --- | --- |
| Improved Governance Indicator: Territorial Use Rights Fisheries (TURFs) legally established for coastal fisheries (number) | Cape Verde | 0 | At least 2 | 2 |
|  | Guinea-Bissau |  | N/A | N/A |
|  | Liberia |  | At least 1 | 1 |
|  | Senegal |  | At least 8 | 8 |
|  | Sierra Leone |  | At least 4 | 0 |
| Reduction of Illegal Fishing Indicator: Fishing vessels observed by aerial/surface patrol or by radar and satellite monitoring, that are committing a serious infraction (% of total number of vessels known/observed) | Cape Verde | 42% | 20 | 25% total: 3% (Semi-industrial), 29% (Canoes) |
|  | Guinea-Bissau | Small scale = 20% Industrial = 25% | Small scale = 10% Industrial = 10% | Small-scale = 7% Industrial = 2% |
|  | Liberia (% of all known industrial vessels targeting the coastal demersal & shrimp fisheries observed fishing without a license) | 83% | 33% | 30 |
|  | Senegal (% of all known small-scale vessels fishing without a permit) | 70% | 5% | 60% |
|  | Sierra Leone (% of all licensed industrial vessels observed fishing within 6-mile IEZ) | 88% | 44% | N/A for years 2015 and 2014, but values for 2012 and 2013 were 33% and 24% respectively |
| Increased Local Value Added Indicators: Increase or stabilization in the volume of exports from targeted fisheries (USD - % increase) | Cape Verde | Coastal demersal fish = 12 tons Lobsters = 17 tons | 15% | N/A |
|  | Guinea-Bissau | N/A | N/A | N/A |
|  | Liberia | Coastal demersals = 0 tons Shrimp = 0 tons | 1,000 | N/A |
|  | Senegal (coastal demersals) | 69,000 tons | 0% | 20,000 mt of annual exports – not attributable to WARFP reforms |
|  | Sierra Leone | Coastal demersals = 9,000 tons Shrimp = 1,400 tons | 10% | N/A |
| Proportion of fish and fish products destined for export tested for sanitary and hygiene conditions in a quality control and inspection laboratory (%) | Guinea-Bissau | 0 | 10% | 0 - The laboratory is now equipped with relevant fish quality testing equipment and operational; Personnel have been trained, Samples of fish products destined for export are tested at the laboratory and certificate for export issued. |
| Intermediate Outcome Indicators | Country | Baseline in 2009 | Target for the End Phase 1 | Measured Value at the Beginning of 2016 |
| Clear principles and policies are established to increase the wealth from fisheries through strengthened rights and equitable allocation of these rights which balances economic efficiency and social benefits. (Yes / No) | Cape Verde | 0 | Policies adopted in each country | Yes: Policy approved; Legal framework under revision |
|  | Guinea-Bissau |  |  | Yes, policy approved in 2014 (Strategic Plan); revised law and regulations under review |
|  | Liberia |  |  | Yes: Policy developed and approved |
|  | Senegal |  |  | Yes: Fisheries Code passed by General Assembly into Law |
|  | Sierra Leone |  |  | No: Draft documents under consultation |
| Small-scale fishing vessels in targeted fisheries that are registered (% of total) | Cape Verde | 50% | 100% | 100% |
|  | Liberia | 0% | 100% | 80% |
|  | Senegal | 60% | 100% | 43% |
|  | Sierra Leone | 0% | 100% | 100% |
| Registered small-scale fishing vessels that are allocated a defined access right (current fishing permit) (% of total) | Senegal | N/A | 50% | 40% Licensing of fishing canoes is ongoing but at a very slow pace. The number of patrol days effected is increasing but the rate of compliance in acquiring license is still below 45% since the start of project. Awaremenss-raising among fishermen and the communities is however ongoing. |
| Communities that are allocated fishing rights (number) | Cape Verde | 0 | 4 | 0 |
|  | Liberia |  | 2 | 1 |
|  | Senegal |  | 12 | 8 |
|  | Sierra Leone |  | 15 | 10? |
| Vessels reduced in targeted fisheries that are overexploited (number per year) | Cape Verde (small-scale vessels – or reduction in number of fishers equivalent to targets for vessels) | 0 | 50 | 0 |
|  | Liberia | N/A | N/A | N/A |
|  | Senegal (licensed industrial trawlers) | 0 | 10 | 0 |
|  | Sierra Leone | N/A | N/A | N/A |
| Percentage of alternative livelihoods undertaken by artisanal fishers and members of crew from industrial vessel receiving micro finance access and small-enterprise training from the project, sustained profitably | Senegal | N/A | 40% | 70 |
| Fisheries Management Plans prepared for targeted fisheries and set levels of sustainable exploitation for these targeted fisheries, and create rights and allocation mechanism for those fisheries | Guinea-Bissau | 0 | 1 | The management plan not yet updated and adopted. Recent stock assessment data on targeted demersal fish stock is now available to be used to update the management plan for the 3 target fisheries (demersal fish, shrimps and cephalopods). |
|  | Senegal | N/A | 2 | 2. Plans for coastal shrimp, Penaeus notialis and Cymbium spp have been finalized and approved by the National Consultative counsel for Marine Fisheries (CNCPM) in November 2015. |
| Two assessment of Fisheries Performance Indicators are carried out and reports available (1 in 2015 and another in 2017) | Guinea-Bissau | 0 | 2 | This is a new activity that will be implemented in 2016. A budget line for this activity has been incorporated in the project budget. |
| A biological and economic assessment of the health of targeted fish stocks is conducted | Guinea-Bissau | No | Yes | Yes for the biological evaluation:Two stock assessments of key demersal fish stocks have been conducted; The ToR for the assessment of targeted fish stocks using simple economic and biological models has been approved. 60% completed |
| Total patrol days at sea per year in targeted fisheries (number of total patrol days/year) | Cape Verde | 70 | 150 | 100 |
|  | Guinea-Bissau | 132 | 150 | 99 days A total of 202 fishing vessels and 239 fishing canoes were inspected; 14 fishing trawler were arrested for committing infractions and 59 canoes were arrested for fishing without license; Within the framework of the Fisheries Partnership Agreement, the EU has bought a new 20-meter coastal patrol boat. In addition, two coastal speedboats Balai III and IV have been repaired and operational. It is expected the no. of patrol days will increase by end 2016. |
|  | Liberia | 0 | 100 | 47 |
|  | Senegal (# total patrol days/yr in coastal waters) | 200 | 400 | 751 patrol days |
|  | Sierra Leone | 348 | 696 | 200 sea patrol days |
| A satellite-based fishing vessel monitoring system (VMS) is in place and functioning (Yes / No) | Cape Verde | No | Yes | Yes |
|  | Guinea-Bissau | No | Yes | Yes. 100% of trawl fleet reporting on VMS by 2016 |
|  | Liberia | No | Yes | Yes |
|  | Senegal | Yes, but without link to AIS | Yes | Yes with no link to AIS |
|  | Sierra Leone | No | Yes | Yes |
| A fisheries monitoring center is equipped and functional | Guinea-Bissau | No | Yes | Yes. The fisheries monitoring centre at the FISCAP has been established and functioning. It is equipped with satellite-based vessel monitoring system (VMS), radar, AIS and short and long-range radio equipment. The Coastal station in the Island of Caravela is refurbished, equipped with radios and radar and it is operational. All licensed industrial fishing vessels have VMS transponders and are monitored from the monitoring centre. |
| Pilot integrated fish landing site clusters established by the Program and operating (number) | Cape Verde (Santiago) | 0 | 1 | 0 |
|  | Liberia (Robertsport) |  | 1 | 0 |
|  | Senegal (Kafountine) |  | 1 | 0 |
|  | Sierra Leone (Konakree Dee) |  | 1 | 0 |
| A competent sanitary authority (CA) is accredited for certification of exports to the European Union, in each country (Yes/No) | Guinea-Bissau | No |  | Yes - The building that houses the Laboratory and the Competent Authority has been constructed and equipped with relevant testing equipment. A Consultant has developed protocols for quality assurance and traceability standards for the laboratory and has prepared a road map for action to be taken in obtaining accreditation from the EU. The Competent Authority has requested DG SANCO / EU to conduct an appraisal mission to Guinea Bissau for accreditation for fish export to the EU. |
|  | Liberia | No | Yes | No |
|  | Sierra Leone | No |  | No |
| Regional database and ‘dashboard’ of key environmental, economic and social fisheries statistics established at CSRP (Yes/No) | CSRP | No | Yes | No. A new firm called Business & Decision has developed the database system for the Dashboard and its installation at the CSRP is ongoing; Training for the Dashboard users and administrators is scheduled to take place in February 2016 in Dakar; The CSRP has acquired licences from the IBM for an application, Cognos to be used in the Dashboard; The SRFC has acquired list of equipment with specification approved by Business & Decision and they are being installed at the SRFC. |
| Annual M&E reports with all data on results indicators and M&E plan completed (Yes / No) | All | No | Yes | Yes (CV, GB, LB) |
| Annual work programs, budgets and procurement plans completed (Yes / No) | All | No | Yes | Yes (CV, GB, LB) |
| Community monitoring of local site conditions (environmental conditions, in-shore hygiene, water quality and possible climate change assessments) underway in TURFs (Yes / No) | All | No | Yes | No |

Cabo Verde, Gambia, Guinea, Guinea-Bissau, Mauritania, Senegal and Sierra Leone.

See for example paragraph 168 of the ‘Future We Want’ outcome document of the United Nations Conference on Sustainable Development (‘Rio+20’).

FAO (2014) estimates some 18.4 million capture fishers operating in the global ocean. FAO (2012) estimates 3 to 4 related jobs are generated in secondary activities for every person directly engaged in fisheries production.  Hence the estimate reflects = 18.4 million marine capture fishers + 3(18.4 million) or 18.4 million marine capture fishers + 4(18.4 million).

Assessing causality is inherently difficult when it comes to human behavior, and the causes of any particular event are always multiple (Miles and Huberman, 1994), hence given limited data the paper focuses on associations rather than causes.

Large Marine Ecosystems (LMEs) are relatively large areas of ocean space of approximately 200,000 km² or greater, adjacent to the continents in coastal waters where primary productivity is generally higher than in open ocean areas.  These areas have been considered as ecologically distinct, and defined into 64 LMEs globally (Sherman and Duda 1999).

Upwelling is an oceanographic phenomenon that occurs when strong sea winds (generally seasonal winds) drive ocean surface water, leaving an empty space into which deep waters can rise and with them a considerable amount of nutrients. These nutrients combine with light to support high levels of phytoplankton production, as the base of the food chain in ocean waters (OECD 2008; Heileman and Tandstad 2008; Sambe et al. 2016).

Benin, Burkina Faso, Côte d'Ivoire, Gambia, Ghana, Guinea, Guinea-Bissau, Liberia, Mali, Niger, Nigeria, Senegal, Sierra Leone and Togo.

This figure excludes data from the small-scale coastal demersal fisheries south of the Gambia.

The finance instrument was named a horizontal and vertical adaptable program loan (APL) in the World Bank’s terminology.

Ghana (2011), Guinea and Mauritania (2015) would join as well.

The project document states that review and compliance with the World Bank’s involuntary resettlement policy (Operational Policy 4.12) would be required for all WARFP-supported reforms, given “the potential for involuntary restrictions on access to the fish resources as a result of …[the] transition away from open access to more regulated fisheries.” The document notes that activities associated with WARFP-supported reforms would be required to follow an inclusive and consultative process in the development of new rules for fishing, as well as provide compensation for any restrictions on resource access (World Bank, 2009).

Additional financing approved in 2011.

Final document entitled: Carta de Politica para o sector das Pescas, CPP, 2013-2018.

Regulations drafted include specific instruments for research, surveillance, small-scale fisheries management, industrial fisheries management, and human resource development within the Secretary of State for Fisheries.

This percentage represents the estimated percentage of total fishing vessels that were unlicensed.  In 2007, there were 50 licensed vessels, and close to 250 different vessels were observed fishing without a license by UNMIL flights, in the coastal zone. Total known industrial fishing vessels was thus 300, at least 250 of which were fishing without a license, for a minimum value of 83% serious infractions observed per every known industrial fishing vessel (inclusion of infraction to the Inshore Exclusion Zone would increase this value).

http://www.stopillegalfishing.com/sifnews_article.php?ID=71  accessed on December 14, 2015.

Equivalent to roughly $442,000 according to August 2016 exchange rates.

$80,000 from US Coast Guard arrests, $125,000 Ocean 3, $10,000 from Poyu 616, $158,000 Marampa

The ratio of infractions to total observed vessels can be misleading in cases where the absolute values for both infractions and observed vessels fall significantly such as in Liberia – though the ratio may remain relatively high, the total number of infractions may fall drastically.

See: http://www.communitysciences.org/

Figure based on a conversion rate of 586.2 F CFA per U.S. dollar.

Personal communication from Stephen Akester: “Largest effect on reducing illegals fishing was international attention made possible by WARFP. Asiatic governments were embarrassed into making changes, the Korean industry based in Las Palmas realized the previous business model had run its course. The nature of IUU changed, agents became desperate for new business models, increasing transparency by WARFP reduced rent seeking opportunities by Gov staff. Anti corruption agendas in SL and Li though only partial also helped.”

http://www.stopillegalfishing.com/sifnews_article.php?ID=71

See for example FAO’s Small-Scale Fisheries Guidelines.

Four pilot communities have been identified in Sal and Miao Islands; Diagnostic analysis of the communities has been conducted and validated by the communities; Co-management associations have been formed; and stakeholders in Maio and Sal are being trained on co-management. The associations have develoepd management regulations approved at the level of users, and under review for legal recognition at the end of 2015.

One TURF has been established constituting a cluster of 15 coastal communities in the Cape Mount County; Implementation was derailed due to the Ebola crisis. CMA Work plan and budget for 2014/2015 has been approved by the National Assembly of the Robertsport CMA; The Robertsport CMA now collects registration and licence fees from the fishermen onbehalf of the BNF; The PIU has acquired legal fishing netting material for the net exchange program;  the exchange is scheduled in some time in 2015.

CLPAs given legal jurisdiction over the fisheries in an area of the sea

By end of 2014/early 2015 TURF management has been legally established in eight (8) co-management sites by Ministrial Orders and their management areas  have been demarcated (Ouakam, Ngaparu, Foundioune, Betenty, Soumbédioune, Bargny, Yenne and Fimela); Implementation of Co-management work plans or strategy to render these communities an effective and sustainable TURFs is underway.

Four MPA sites (Yawry Bay, Sherbro River, Scarcies Rivers and Sierra Leone River) have been declared in 2012; No TURF has been established, however, 14 Co-management Associations (9 in the Sherbro River Estuary and 5 in the Yawry Bay) have been legally registered with local and central government and co-management areas demarcated; CMA members with MFMR outstation personnel have conducted study tour in co-management sites in Senegal for experience sharing;

Using 2000 EU reporting data.

12 Semi-industrials vessels committed infraction out of 403 registered; 543 canoes were found committing infraction out of 1862 canoes registered; Two coastal surveillance stations have been constructed and equipped with communication devices in Maio and Sal Islands.

As at December 2015, 59 small-scale fishing canoes were observed committing infractions (fishing without license), a total of 833 small-scale canoes have license to fish.

As at April 2016, 142 industrial fishing vessels have license and 3 industrial vessels were observed committing infractions

For last data year available, 2007, there were 50 licensed vessels, and close to 250 different vessels were observed fishing without a license by UNMIL flights, in the coastal zone. Total known industrial fishing vessels was thus 300, at least 250 of which were fishing without a license, for a minimum value of 83% serious infractions observed per every known industrial fishing vessel (inclusion of infraction to the Inshore Exclusion Zone would increase this value).

As of 2012, the Government had allocated fishing permits to small-scale fishermen but without any specification about the targeted species, fishing area, and fishing period. So the first step towards the allocation of clear fishing rights (via specified fishing license) was considered to be to allocate the current fishing permits to all the fishermen in the fleet and then the next step was considered to be the replacement of this permits with the introduction and allocation of specified and legally recognized fishing license for small-scale fisheries as form of clear fishing rights. The objective was to allocate clear, specified, long-term fishing rights through this more specified fishing license to limit the access to the fisheries.

For last year data available, 2001, there were 35 zone infractions recorded, with a total of 40 licensed industrial vessels.

33% measure based on the available data for 2012, where 7 industrial fishing vessels were arrested for committing infractions; plus 33 VMS violations (Vessels that put-off their transponders for 24 hours) were recorded with a total of 120 licensed industrial vessels. 24% measure based on 2013 surveillance report from JMC, 16 IEZ infractions were recorded, with a total of 68 licensed industrial vessels targeting demersal resources. In July 2014, the Ministry of Fisheries and Marine Resources authorized six industrial fishing vessels to fish in the inshore zone prohibited for trawling, and data was not collected.

Based on 2003 data, last year available.  Exports have likely risen since this time.

Tons of total exports of coastal demersal fish and shrimp – absolute values are given instead of percentage for Liberia, since the baseline is zero.

Only one industrial vessel was licensed in 2014; Effective data collection system is not established yet. The University of Iceland/MRAG is setting up the data collection system. NOAA is also assisting.

Based on most recent year data available – 2005 – with total export volume of 83,104 tons, of which 83% estimated to originate from coastal demersal fisheries.

Policy has been approved; Key fish stocks of small pelagic, demersal and red lobsters have been evaluated in 2012 and updated in 2014. Key fish stock have also been evaluated using bioeconomic model in 2015; Fisheries management plan (2004 - 2014) has been revised, the Plan for 2016-2020 is under preparation and  it is due to complete  by Sept. 2015; Strategic Development Plan for the fisheries sector has been developed, approved and its implementation is underway; The Legal, Management and Institutional frameworks is under review and it is scheduled to complete in Sept. 2015. The Legislation will take into account co-management and right fishing.

The Fisheries and Aquaculture Policy has been developed, awaiting approval by the Cabinet in June sitting; Draft Fisheries Act has been prepared and reviewed by the Bank, BNF/WARFP and the Law reform Commission. NFDS consultancy to complete the draft Act by July 2015. MRAG is conducting stock assessment of key fish stocks in Liberia. A second round of data collection on catch and effort, length frequency was completed in August 2014. Analysis is on going by  MRAG.

Management and Functional Review (MFR) has been approved by Cabinet; The Ministry (MFMR) technical committee has aligned the draft Fisheries and Aquaculture Bill with the MFR recommendations; The Fisheries Policy and Strategy documents produced by a consultancy firm,  IDDRA, has been updated and submitted to NEPAD Governance working group to finalize; Fisheries Regulation revised waiting to be enacted; Technical report of MFMR on the Fisheries Bill has been submitted to IDDRA to finalize it.

Registration and marking of all industrial/semi-industrial vessels and small-scale fishing canoes has been completed and records stored in a Web-based Database (Registry). A total of 1,588 small scale canoes and 146 semi industrial vessels have been recorded in the database . It should be noted that this figures have increased by 34% since 2013 when the total registered vessels was 1,136 small canoes and 80 semi-industrial.

4,073  artisanal and semi-industrial fishing vessels have been registered and embossed and data stored in the National Registry (Database for Vessel Registration Database). Liberia Artisanal Fishermen Association (LAFA) participated in the embossement exercise of registered vessels in some communities.

The National Database for Vessel Registration (PNI) has shown inconsistent records, and a new strategy for vessel registration was adopted in 2015 and is currently being implemented.  Similarly, a new database for registration of vessels has been developed.  As of December 15, 2015, a total 19,009 canoes have been counted, which include 11, 625 canoes already registered and 7,384 canoes never registered, while a total of 13,676 canoes have been inputed into the database.

All small-scale vessels (10,500) have been registered and records stored in the database for vessel registration; A total 22,000 plastic number plates have been procured to mark the vessel. The marking exercise did not go ahead due to the Ebola crisis.

As per footnote above, this indicator was added at restructuring, to record if specified and legally recognized fishing licenses had been substituted for the current fishing permits in order to allocate clear fishing rights to fishermen/communities.

Four pilot communities have been identified in Sal and Miao Islands and diagnostic analysis  has been conducted; Co-management Associations have officially been created, and community members in Sal and Maio Islands have conducted a study tour to co-management sites  in Dakar to share experience; Community leaders have been identified and trained on co-mangement concept. With the guidiance of the consultant, the   community animators and the community leaders have embarked on massive community sensitization on co-management processes; Preparation of Co-management Agreements for the pilot communities was scheduled for Sept/Oct. 2015.

A Co-Management Association (CMA) has been established in Robertsport that comprises a cluster of 15 fishing villages; The Robertsport CMA has signed Co-Management Agreement with the Ministry of Agriculture to operate right-based fishing management. The CMA has collected an amount of LD$323,250 onbehalf of BNF as registration and licensing fees for semi-industrial and artisanal fishing canoes. The CMAs General Assembly has approved the 2014/2015 Work Plan and Budget.  Legal fishing nets and accessories have been procured and delivered to Robertsport for the CMA net exchange program. The construction of the Robertsport Community Fisheries Centre is more than 30% complete now. This activity was significantly delayed by the Ebola crisis, as contractors left the site for few months.

Targets revised at restructuring.

A local fisher committee has  been legally established in eight (8) Co-management sites (Ouakam, Ngaparu, Foundiougne, Bétenty, Soumbédioune, Bargny, Yenne, Fimela-Ndangane); the State has allocated management rights to these associations for defined management areas; Strategic plans to implement the TURF in order to render the management effective and sustainable are underway; A closed season has been observed for demersal species such as grouper species, coastal shrimp species, sea urchins, etc. in Soumbediounne, Yenee, Fimela-Ngangane and Foundiougne.

5. Construction of seven "Fisherman's Houses" in Bargny, Yenne, Mballing, Nianing, Pointe-Sarene, and Mbodiène Fimela-Ndangane has completed.

Four (4) MPA sites (Yawry Bay, sherbro River, Scarcies Rivers and Sierra Leone River) have been declared in 2012. 31 CMAs with elected executives have been established, 15 of the CMAs have constitutions and byelaws and have legally registered with their Local Councils; Some CMAs have legally registered with Ministry of Social Welfare. GIS experts has delineated the co-management areas in the MPA sites;Capacity building of stakeholders on co-management concept is ongoing. Members of CMAs and Outstation Fisheries Officers has conducted study tour to Co-management sites in Senegal.

Based on estimates of roughly 3 fishers per small-scale vessel, i.e. a total of 4,000 small-scale fishers and roughly 1,250 small-scale vessels for most recent data available.

A Ministrial Order  was issued in January 2015 to  regulate the number of authorized vessels to be registered according to type of fishing gear and per island ; it is being implemented since March 2015; 23 fishing units constituting 60 fishermen from Sal and Maio fishing communities have opted to leave fishing for alternative activities outside the fisheries sector; With technical assistance from the national enterprise, SIDEL Consulting, 23 micro-projects have been submitted by owners of small-scale boats in Sal and Maio; With No Objection from the World Bank, a total of US$300,000 Micro-Credit Fund will be in effect from June 2015 to finance the 23 projects. Professional training program that was previously developed was scheduled to be implemented in June 2015.

Targets revised at restructuring.

By 2014, ten industrial vessels should have moved out from the fisheries. No fishing vessel has left the targeted fisheries. Independent auditors identified two fishing vessels in 2013 and the negotiation for buy-back was faced with some roadblock, as the proposed cost for the two vessels is much higher than the current values of the vessels.  The vessels are dilapidated/write-off.

Indicator added at Restructuring.

Micro-projects with block grants for infrastructure and starter grants to help association members diversify outsdie of fishing include poulty farms in Nianing and Mbodiene, farms for beef fattening in Point Sarene and Mballing, and astores for maritime hardware, and infrastructure for existing enterprises was strengtheend in Ouakam, Soumbedioune and Foundiougne (poultry farm and store for maritime hardware).

Indicator added at restructuring.

A period of transition to the authority ACOPESCA was underway, which reduced the number of annual patrol days in 2015.  In the islands of Sal and Maio where pilots in community management rights were underway, surveillance teams includeing a fisher from the association, a fisheries inspector from the government agency and an officer of the Coast Guard conducted patrols.

As at December 2015, a total of 99-patrol days/year covering both industrial and artisanal fisheries were conducted in coastal waters of Guinea Bissau. The number of patrol day/year conducted in 2015 was below the baseline, this is due to the delay in finalizing the hiring agreement of the Senegalese naval patrol boat.

Includes surveillance of both industrial and small-scale fisheries.

In 2015, a total of 751 patrol days have been conducted; 7,395 canoes and 287 industrial vessels were inspected. 449 canoes and 2 industrial vessels were arrested.

Limited sea patrols were conducted at the forward operating bases (FOB); Community surveillance has not started yet Construction of new fisheries patrol boat has been completed awaiting to be delivered.

VMS system has been established and operational with 80% coverage (60 industrial vessels now have  VMS transponders); the Coastal surveillance stations in Maio and Sal Islands have been completed, and operational, including two speed boats that will be used for participatory surveillance in the co-management sites.

The MCS center is established, equipped with communication gadgets including VMS and AIS.

Automatic Identification System

The VMS and the AIS are functioning well now.

The MCS center is established, equipped with communication instruments; VMS transponders installed on all licensed industrial fishing vessels.

A discrete additional landing site infrastructure was not completed, but rather the Government is in the final phase of the construction of an ice-making factory in Port of Palmeira, Sal Island. A prefab 20 ft. ice-making container has been installed but not operational; some civil works, electrical and water supply are still need to be completed.  Additionally, the first phase of the rehabilitation of the Port of Praia, Santiago Island has been concluded (electricity grid, portable water and sanitation); the second phase is on-going (development of an auction system) and forecast to complete by December 2015. This activity saw significant delays due to the death of the contractor. Of note: the ice-making machine is not well sheltered; there will be a need to cover it with canopy to maintain temperature.

Environmental Protection Agency (EPA) gave construction permit for the landing site; Construction of the landing site has begun and general progress of work is about 30% before the contractors left due to Ebola; One contractor, Phoenicia Construction Ltd. has resumed work and they have plastered most of the structures. The other contractor, Top International Ltd has still not resumed work. Feasibility study for the enterprise development for the Robertsport fish landing site clusters has completed and validation of the feasibility and management plan has been conducted. This activity was delayed due to the Ebola crisis.

This indicator was dropped at restructuring.

The contract of the first consultant for the ESIA study was stopped due to sub-standard work. ToR for the proposed harbour site and the 12km road from Konakridee to Lungi Internal Airport was revised and re-launched. Evaluation report of the Technical proposal was submitted to the World Bank for no objection since September 2014 but no response until close of project.

Accreditation process has not started yet; CA is established but institutional role needs to be defined; Fish health Consultant has prepared draft of the following documents: MOU for collaboration, food safety policy, regulation on HACCP and best practices, regulation on specific rules for quality control as well as additives; For the establishment of Competent Laboratory, the consultant has listed equipment and material needed; Relevant personnel have trained on fish sanitary and quality control and how to establish competent laboratory; Design for the Competent Laboratory has been prepared.

Competent Authority is in place but not accredited for certification of fish product; Laboratories for heavy metal analysis have not been accredited; A Dutch firm, PRECON is working with relevant institutions on accreditation process.

Established but not all data are available in on time; catch and effort data are most times delayed by one year or more. Data collection of relevant information at national level is still a challenge; Some target values were over-estimated as indicated by some countries.

The Robertsport CMA in Liberia is conducting community monitoring of local sites through a community science program; The other participating countries are now begining to the monitoring program.