United Nations Development Programme

Country: Samoa

PROJECT DOCUMENT

Project Title:  Capacity for Implementing Rio Conventions in Samoa

UNDAF Outcome 1:  By 2017, the most vulnerable communities across the Pacific Island Countries and Territories are more resilient and select government agencies, civil society organizations and communities have enhanced capacity to apply integrated approaches to environmental management, climate change adaptation/mitigation, and disaster risk management.

UNDP Strategic Plan: Outcome 5: Countries are able to reduce the likelihood of conflict, and lower the risk of natural disasters, including from climate change

UNDAF Results Matrix

Output 3.1.1:	Strengthened capacity to formulate, ratify and report on International Conventions and Treaties, World Heritage Convention, CBD and Kyoto Protocol

Output 3.1.2:	Strengthened national capacity to develop and upgrade the national environmental policy

Output 3.1.3:	Increased involvement of youth in the implementation of international Conventions and Treaties and their participation in regional events such as Youth Forum of World Heritage site managers, Youth NGOs and festivals.

Output 3.2.1:	Increased government capacity to more effectively meet obligations of the CCD, Biodiversity Convention and FCCC.

Executing Entity/Implementing Partner: Ministry of Natural Resources and Environment (MNRE)

Implementing Entity/Responsible Partners: UNDP

Programme Period:		2014 - 2017

Atlas Award ID:			00078841

Project ID:			00088926

PIMS #				4938

Start date:			Sept 2014

End Date			Sept 2017

Management Arrangements	NIM

PAC Meeting Date	              2/5/2014

Total resources required           	US$ 1,000,000

Total allocated resources:		US$ 1,000,000

  - GEF TF (Grant)		US$ 500,000

  - Government (In-kind) 	US$ 400,000

  - UNDP (Grant)			US$ 100,000

Brief Description: This project will assist the Government of Samoa to meet its obligations under the three Rio Conventions by catalyzing better decisions for the global environment.  This will be achieved through the mainstreaming and promotion of the Rio Conventions into national development plans, and the strengthening of inter-ministerial cooperation and participatory approaches.  As appropriate, the strengthening of legislative and regulatory instruments will help further institutionalize capacities developed under the project.  The project will help improve public awareness to strengthen the understanding of Samoa on the important linkages between national sustainable development priorities.

| Agreed by: |  |  |
| --- | --- | --- |
| (Government) | _____________________________________ | _______________ |
|  | (Name Title) | Date/Month/Year |
| Agreed by: |  |  |
| (Executing Entity/Implementing Partner) | _____________________________________ | ______________ |
|  | (Name Title) | Date/Month/Year |
| Agreed by: |  |  |
| United Nations Development Programme | ______________________________________ | ______________ |
|  | Name Title | Date/Month/Year |

Table of Contents

Acronyms and Abbreviations	4

PART I - PROJECT	5

A Project Summary	5

A.1	Project Rationale, Objectives, Outcomes/Outputs, and Activities	5

A.2	Key Indicators, Assumptions, and Risks	6

B	Country ownership	7

B.1	Country Eligibility	7

B.2	Country Driven-ness	7

B.2.a	National Capacity Self-Assessment	9

B.2.b	Sustainable Development Context	10

B.2.c	Policy and Legislative Context	13

B.2.d	Institutional Context	13

B.2.e	Barriers to Achieving Global Environmental Objectives	18

C.	Programme and policy conformity	20

C.1	GEF Programme Designation and Conformity	20

C.1.a	Guidance from the Rio Conventions	23

C.2 Project Design:  GEF Alternative	24

C.2.a	Project Rationale	24

C.2.b	Project Goal and Objectives	25

C.2.c	Expected Outcomes	26

C.2.d	Project Components, Outputs, and Activities	27

C.3	Sustainability, Replicability, and Lessons Learned	33

C.3.a	Sustainability	33

C.3.b	Replicability and Lessons Learned	34

C.3	Stakeholder Involvement	35

C.4	Monitoring and Evaluation	36

D.	Financing	42

D.1	Financing Plan	42

D.2	Cost Effectiveness	43

D.3	Co-financing	44

D.4	Total GEF Work Plan and Budget	45

E.	Institutional Coordination and Support	49

E.1	Core Commitments and Linkages	49

E.2	Implementation and Execution Arrangements	50

F.  Legal context	53

PART II:	ANNEXES	55

Annex 1:	Capacity Development Scorecard	56

Annex 2:	Logical Framework	66

Annex 3:	Outcome Budget (GEF Contribution and Co-Financing)	75

Annex 4:	Provisional Work Plan	77

Annex 5:	Terms of Reference	89

Annex 7:	Environmental and Social Review Criteria	95

Annex 8:	Draft Letter of Agreement (LoA)	104

PART III:	GEF Letters of Endorsement and Co-Financing	108

## Acronyms and Abbreviations

ACD 		Aid Coordination Division

ACEO		Assistant Chief Executive Officer

ACM		Adaptive Collaborative Management

APR		Annual Project Report

AWP		Annual Work Programme

CCCD		Cross Cutting Capacity Development

CBD		Convention on Biological Diversity

CCCPIR		Coping with Climate Change in the Pacific Region

CCD		Convention to Combat Desertification and Drought

CEO		Chief Executive Officer

CIF		Climate Investment Fund

CLEWS		Climate Early Warning Systems

CoC		Chamber of Commerce

CPEIR		Climate Public Expenditure and Institutional Review

CSD		Corporate Service Division

DKIF		Data, Knowledge & Information Facility

EPPD		Economic, Policy and Planning Division

FCCC		Framework Convention on Climate Change

GDP 		Gross Domestic Product

GEF 		Global Environment Facility

GHG 		Green House Gas

LDC 		Least Developed Country

MAF 		Ministry of Agriculture and Fisheries

MJCA 		Ministry of Justice, Courts and Administration

MEAs 		Multilateral Environment Agreements

MESC 		Ministry of Education, Sports and Culture

MFAT 		Ministry of Foreign Affairs and Trade

MNRE 		Ministry of Natural Resources, Environment and Meteorology

MOF		Ministry of Finance

MTEF		Medium Term Expenditure Framework

MWCSD 	Ministry of Women, Community, and Social Development

MWTI 		Ministry of Works, Transport and Infrastructure

NAP 		National Action Plan

NPD		National Project Director

NBSAP 		National Biodiversity Strategy and Action Plan

NCCCT		National Climate Change Coordinating Team

NCSA 		National Capacity Self-Assessment

NEMS 		National Environmental Management Strategy

NESP		National Environment Sector Plan

NESPAC	National Environment Sector Plan Advisory Committee

NGOs 		Non-governmental Organizations

PCBO		Principal Capacity Building Officer

PIR		Project Implementation Review

PMU 		Project Management Unit

PPCR		Pilot Project on Climate Resilience

PUMA 		Planning and Urban Management Agency

SACEP		Samoa Agriculture Competitiveness Project

SBS 		Samoa Bureau of Statistics

SDS 		Strategy for the Development of Samoa

SNAP		Samoa National Action Plan for Disaster Risk Management

SPC		Secretariat of the Pacific Community

SPREP		Secretariat of the Pacific Regional Environment Programme

TWG		Technical Working Group

# PART I - PROJECT

# A Project Summary

## A.1	Project Rationale, Objectives, Outcomes/Outputs, and Activities

- Samoa completed its National Capacity Self-Assessment (NCSA) in 2007, the final report of which included a prioritization of capacity development needs that cut across the three Rio Conventions.  In particular, part of the assessment included the development of a National Environmental Capacity Strategy and Action Plan that provided recommendations on strategies for national capacity development.  The NCSA also provided the basis for interventions on capacity development and environmental concerns.  Priority recommended activities were to improve national policy, legislative and institutional frameworks for better compliance to the requirements of sustainable development, in particular to the three Rio Conventions.  Other key activities included the strengthening of cross-sectoral cooperation and participatory approach in the implementation of environmental programmes; strengthening and enforcement of policies and legal frameworks; establishment of adequate data and information management systems and mechanism and; strengthening communication tools and strategies to improve public awareness and advocacy roles of local communities.

- In addition to the three Rio Conventions and other MEAs, Samoa has adopted a number of environmental legislation and strategic frameworks that reflect the broad range of critical environmental priorities.  These include the National Environmental Sector Plan 2013-2017 (replaces National Environment Management Strategy (NEMS)) designed to provide broad strategic direction for sub-sector plans such as the National Water Resources Management Strategy 2007-2017; Protection of Wildlife Regulations 2004; National Waste Management Strategy 2000-2010; National Biodiversity Strategies and Action Plan (NBSAP); National Adaptation Plan of Action (NAPA); the National Communications, Samoa National Action Plan for Disaster Risk Management (SNAP); and Water for Life “Framework for Actions” 2012-2016.  These plans provide the detailed action plans of specific activities within Samoa’s environment priorities.

- Fulfilling commitments as a Party under the three Rio Conventions and other MEAs contributed significantly to keeping the environment momentum at the national level, with the adoption of corresponding legislations and policies and action plans for implementing national obligations.  This is evident in the changes reflected in the Strategy for Development of Samoa (SDS) 2012-2016 that includes Environment as a Priority Focus area as compared to the SDS 2005-2007 where environment was not mentioned at all except as a cross cutting issue within three strategic areas; agriculture, health and tourism development.  However, despite these policies and institutional steps, Samoa continues to face many challenges in fulfilling its obligations under the Rio Conventions.

- The rationale for this project stems from the NCSA findings that there a great number of environment laws, strategies, frameworks and policies that generate much confusion, impeding Samoa’s  ability to effectively comply with Convention objectives.  As a result, these legal instruments are not effectively implemented or enforced, and in certain cases work against each other.  This is further exacerbated by decision-makers and planners not being adequately versed on the legislation and issues inherent.  This is due to a variety of reasons including staff changes and insufficient training.

- This project is in line with CCCD Programme Framework 2, which calls for countries to improve decision-making for the global environment through improved generation, access and use of information and knowledge.  The project will also contribute to CCCD Programme Framework 4, which calls for countries to strengthen capacities for developing policy and legislative frameworks.  Through a learn-by-doing process, this project will increase the ability of stakeholders to diagnose, understand and transform information and knowledge into local actions.  The project will help institutionalize these capacities through the implementation of selected recommendations reinforcing improved compliance with Rio Conventions.

- This project is innovative in its design as it will target capacity development activities to key partners, decision-makers, planners and their respective staff, on how to better implement (and amend where appropriate) the current set of environmental legal instruments, tools and mechanisms to meet both national and global environmental priorities.  This will necessitate the improvement of coordination mechanism and data and knowledge management tools to equip the MNRE (as the key environment organization) better drive and encourage coordinated efforts at mainstreaming three Rio Conventions into the planning stages of national programmes and priorities.

- The objectives of this targeted cross-cutting capacity development project are to strengthen technical and institutional capacities for more effective implementation of the three Rio Conventions.  This objective will be met by three interlinked components: Component 1 sets out to assess and strengthen existing legal instruments, tools and mechanisms to integrate Rio Convention provisions as well as strengthen the basis upon which the Rio Conventions can be implemented.  Component 2 is to strengthen the institutional and individual capacities of the key implementing agencies to support the implementation of the Rio Conventions.  This component is crucial as it comprises a broader set of capacity development activities that serve to reinforce the resilience and institutional sustainability of project outcomes.  This includes the strengthening of data, information and knowledge management systems and processes which will contribute to the design and implementation of a comprehensive training programme and public awareness campaign targeting technical staff, parliamentarians, legal officers, community authorities as well as a range of other stakeholders.  Component three sets the basis upon which the development of monitoring and evaluation tools will be developed through a participatory process as well as a set of learning by doing activities, to integrate Rio Convention obligations into national development plans and sector plans.

- The project will take an adaptive collaborative management (ACM) approach to implementation, which calls for stakeholders to take an early and proactive role in the mainstreaming exercises, as well as to help identify and solve unexpected implementation barriers and challenges.  By taking an ACM approach, project activities and outputs can be more legitimately modified and adapted to maintain timely and cost-effective project performance and delivery.

## A.2	Key Indicators, Assumptions, and Risks

- There are a number of substantive risks and assumptions associated with the design of this project.    These risks include the continued commitment of key agencies and authorities to the formulation and implementation of a consolidated environmental monitoring programme across the sectors as well as genuine commitment and active participation of community authorities in the project.  Another low risk is that associated with the perception within some sectors of the government that environment should take a back seat to more important issues, such as the economy, health care and education resulting in sector agencies non-committal to mainstreaming Rio Conventions into their respective plans.

- Other low risks are those associated with key agencies and authorities not agreeing to share data and information towards the establishment of a centralized Data, Knowledge & Information Facility (DKIF) or the provision of poor quality or wrong information that would illegitimate decision-making and misinform Rio Convention reporting obligations.  Another low risk is the respondents to surveys conducted not providing true answers that could also damage the integrity of data and information collected for monitoring and reporting on Rio Convention implementation.

- An important risk is the staff turnover in government ministries, in particular the MNRE.  This is a medium risk to the project in that investments in training could be lost.  This is minimized by the project involving as many staff as possible in the training activities, as well as stakeholders and other individuals who would likely replace departing staff.

- There are some inherent key indicators of the project that will help raise the implementation level of Rio Convention obligations in Samoa.  Some key outcome indicators see the Rio Convention obligations becoming an integral part of Samoa’s key overarching development plan, Samoa’s Sustainable Development Strategy (SDS) and that the Government and a wide range of stakeholders will systematically review natural resource and environmental policies in a holistic manner in line with Rio Conventions.  Central to the successful achievements of outcomes previously mentioned, the biggest achievement of this project will be the building and strengthening of key capacities to drive the implementation of the Rio Conventions on a national level.  The introduction of targeted workshops to build the capacity and understanding of parliamentarians is another key indicator in the process of integrating Rio Convention provisions and obligations into legal instruments, national plans, strategies and policies.

# B	Country ownership

## B.1	Country Eligibility

- Samoa is eligible to receive technical assistance from UNDP, and is thus eligible for support under the Global Environment Facility (GEF).  Samoa ratified the Convention on Biological Diversity (CBD) on 2 September 1994, acceded to the Convention to Combat Desertification and Drought (CCD) on 21 August 1998, and ratified the Framework Convention on Climate Change (FCCC) on 29 November 1994.  Samoa ratified important protocols under the Rio Conventions in later years, namely:

  - The Cartagena Protocol on Biological Safety on9 November 2003 to protect biodiversity from the potential risks posed by genetically modified organisms that are the product of biotechnology.

  - The Kyoto Protocol on 27 November 2000, committing to stabilize greenhouse gas emissions for the period 2008-2012 at the 1990 level.

  - The Montreal Protocol on Substances that deplete the Ozone Layer on 21 December 1992 (Accession) with later Acceptance on 4 October 2001.

- In addition to the Rio Conventions, Samoa is committed to a number of other multilateral environmental agreements (MEAs), having acceded to or ratified several other international and regional treaties and protocols that call for the protection and sustainable use of natural resources, such as the Convention on Persistent Organic Pollutants (Stockholm Convention); World Heritage Convention, Ramsar Convention on Wetlands; and Convention on International Trade in Endangered Species.

- Fit with the GEF-5 CCCD Strategy:  The GEF strategy for Cross-Cutting Capacity Development projects serves to provide resources for reducing, if not eliminating, the institutional bottlenecks and barriers to the synergistic implementation of the Rio Conventions.  This particular project is in line with CCCD Programme Framework 2, which calls for countries to improve decision-making for the global environment through improved generation, access and use of information and knowledge.  The project will also contribute to CCCD Programme Framework 4, which calls for countries to strengthen capacities for developing policy and legislative frameworks.  Through a learn-by-doing process, this project will increase the ability of stakeholders to diagnose, understand and transform information and knowledge into local actions.  The project will help institutionalize these capacities through the implementation of selected recommendations reinforcing improved compliance with Rio Conventions.

## B.2	Country Driven-ness

- Samoa is one of the 14 Pacific Island Countries and Territories covered under the United Nations Development Assistance Framework (UNDAF) for the Pacific Sub-Region.  The five year strategic programme framework outlines the collective responses of the UN system to development challenges and national priorities of these 14 Pacific Island Countries and Territories for the period 2013-2017.  Its overarching ambition is to promote sustainable development and inclusive economic growth to address the social, economic and environmental vulnerabilities affecting society at all levels and to ensure human security in the Pacific, with a focus on the most vulnerable groups.

- The UNDAF Multi-Country Action Plan complements the outcome level UNDAF and represents the common operational plan for implementing 14 individual UNDAF Country Results Matrices to address the specific priorities and circumstances of each Pacific island country.  The UNDAF 2013-2017 for the Pacific highlighted challenges such as physical isolation, small economies of scale, limited natural resources, impact and variability of climate change, natural hazard risk and the vulnerability to economic shock.  The UN system in the Pacific will focus its programming and advocacy efforts on five inter-related outcome areas: Environmental management, climate and disaster risk management; Gender equality; Poverty reduction and inclusive economic growth; Basic services (health & education) and; governance and human rights.

- There are four inter-related outcomes areas within Samoa’s Country Results Matrix that the UN system and Samoa have agreed to cooperate on.  Poverty reduction and inclusive economic growth (aligned with National Priority Area 1 – Economic Sector); gender equality; basic services (health & education) (aligned with National Priority Area 2 – Social Policies); and environmental management, CC & DRM (aligned with National Priority Area 4 – Environment).

- Samoa’s key overarching guiding document is the Strategy for the Development of Samoa (SDS).  The Government of Samoa is committed to ensuring environmental sustainability and is reflected in the inclusion of Priority Area 4 with Key Outcomes 13: Environment Sustainability and 14: Climate and Disaster Resilience in the SDS 2012-2016.  The SDS recognizes that this work is a priority focal area and is underpinned by the development and implementation of appropriate legislative frameworks and policies to guide sustainable development and management of natural resources.  The SDS further states that the environment will feature prominently as a cross-cutting issue in all development initiatives.  The National Environment Sector Plan (NESP) reflects the overall vision and goal of the SDS and clarifies how the national goal and vision will be achieved in the qualities of the natural environment that the NESP represents and is responsible for.

- The National Environment Sector Plan (NESP) 2013-2017 is intricately linked to and flow from the macro-level goals and priorities defined in the SDS 2012-2016.  The NESP reaffirmed the Principles of the Rio Declaration 1992 underpinning the notion of equitable and sustainable development.  Specifically, The NESP lists 10 high level outcomes that will help Samoa achieve environmental sustainability: habitats and species within protected areas, sanctuaries and KBAs protected and maintained in natural (pristine) condition; degraded habitats and threatened species of economic and conservation importance restored to healthy states and viable populations; rural and urban built environment is sustainable and resilient against extreme climate included events and longer term climate induced changes; environmental resources such as forests land, water and fisheries are managed sustainably; knowledge for Samoa’s biodiversity and natural resource enhanced and kept up to date through science based assessments and ongoing monitoring; strengthened stakeholder engagement and involvement (in decision making) in environmental management; improved sector coordination of environmental initiatives through a robust and effective management framework; strengthened enabling environment that promotes sustainable financing and partnerships; strengthened institutional framework with improved governance and capacity at all levels to promote integrated decision making, exchange of information and provision of expertise; effective policy and legal frameworks that regulate activities, improve monitoring and enforcement (State of Environment, strategic environmental assessments).

- The NESP took into consideration the strategic areas definite in the SDS 2012-2016 and added key indicators so it is inclusive of impacts on the environment that stem from activities of other economic sectors including agriculture, water and sanitation, infrastructure and energy.  Likewise some of its strategies call on remedial measures within these sectors, cognizant of the fact that the same goal of environmental sustainability and disaster risk reduction are shared by all sectors.  In this way, the NESP complements economic sector outcomes for agriculture and tourism under SDS Priority Area 1 and 3, as well as Key Outcomes 9 (Sustainable Access to Safe Drinking Water and Basic Sanitation), 10 (Efficient Safe and Sustainable Transport System and Networks) and 12 (Sustainable Energy Supply) under Priority Area 3 Infrastructure Sector.

- The social and economic development priorities for the period 2013-2017 of the UNDAF Samoa Results Matrix correspond to the government’s priorities under the SDS Priority Area 4 that also achieve Millennium Development Goals (MDGs).  These include addressing climate change and the sustainable use of the natural resources in line with national priorities.

- In addition to the three Rio Conventions and other MEAs, Samoa has adopted a number of strategic frameworks that reflect the broad range of critical environmental priorities.  These include the National Environmental Sector Plan 2013-2017 (replaces National Environment Management Strategy (NEMS)) designed to provide broad strategic direction for sub-sector plans such as the National Water Resources Management Strategy 2007-2017; Protection of Wildlife Regulations 2004; National Waste Management Strategy 2000-2010; National Biodiversity Strategies and Action Plan (NBSAP); National Adaptation Plan of Action (NAPA); the National Communication, Samoa National Action Plan for Disaster Risk Management (SNAP); Water for Life “Framework for Actions” 2012-2016.  These ‘sub-sector’ plans provide the detailed action plans of specific activities within each focal area of the environment.

### B.2.a	National Capacity Self-Assessment

- Funded by the GEF through UNDP, the Samoa National Capacity Self-Assessment (NCSA) undertook a participatory approach from both the local and community level and national level.  Completed in 2007, the NCSA was implemented in five phases: the inception phase that required the establishment of a project management unit and the National Steering Committee.  The second phase consisted of taking stock of Samoa’s national implementation of the three conventions.  The third phase focused on a thematic assessment, while the fourth focused on an assessment of the cross-cutting interactions of convention implementation, including an assessment of stakeholder capacities.  The final phase included the development of the National Environmental Capacity Strategy and Action Plan that provided recommendations on strategies for national capacity development.  It also provided the basis for interventions on capacity development and environmental concerns.  The problems related to global environmental management are rooted in an overall institutional weakness of governance, including environmental governance, in Samoa.  The NCSA identified the following major shortfalls.

- Weak coordination and collaborative systems across sectors

- Ineffective implementation, enforcement and monitoring of legal frameworks at the systemic and individual levels impacting on the effective implementation of convention obligations

- Weak institutional arrangements for the implementation of the Conventions

- Poor financing and lack of appropriate human resources in governmental institutions.

- Lack of consistency and insufficient sharing of information between key stakeholders.  There is currently little communication across the ministry responsible for the Conventions in Samoa.  This is linked to low commitment to follow up on identified priorities, and to the lack of a strong policy framework and political commitment to implementation

- Nonexistent frameworks and strategies to communicate issues to the wider community and to raise public awareness of the Rio Conventions

- The weak capacity of the government to carry out strategic planning that reflects an integration of international objectives into local and national action plans.  This is primarily related to two factors: first, the lack of up-to-date social, economic and environmental data to support the strategic planning process; and second, lack of communication and coherent regulations establishing the framework for preparing and implementing integrated sustainable planning.

- Based on these challenges, the NCSA's main recommendation was to improve national policy, legislative, and institutional frameworks for better compliance to the requirements of sustainable development, in particular to the three Rio Conventions.  This included:

- Promote and strengthen cross-sectoral cooperation and participatory approach in the implementation of environmental programmes and initiatives at the national and local levels;

- Strengthening and enforcement of policies and legal frameworks at the systemic and individual levels;

- Establish adequate institutional data and information management and dissemination mechanism; and

- Strengthen communication tools and strategies to improve public awareness to facilitate the participation of local populations in national efforts

### B.2.b	Sustainable Development Context

- Samoa is an island nation with a total area of 2,820 km2, (43% of arable land) and a population of 187,820 recorded in Samoa’s national census of 2011.  76% in Upolu, 20% in the urban area of the capital city, Apia.  Its size, remoteness from major global markets and vulnerability to natural disasters and the impacts of climate change are major constraints to its development.  Its small economy is dependent on tourism, agriculture, fisheries, remittances and external development assistance.  Economic growth is driven by commerce, transport and communications and construction sectors that are both supported by tourism; with the major exports being fresh fish, coconut oil, coconut cream and noni juice.  The main imports are food items, petroleum and manufactured goods.

- Samoa’s economy is relatively small with aggregate 2011 GDP of 1.546 billion Samoan Tala (or approximately US$ 505 million) implying a per capita annual income of SAT$8233 (US$ 2693), approximate average of 18.2% coming from remittances.  Samoa is classified as a Small Island Developing State (SID) mainly because of its vulnerability to natural disasters and its vulnerability to external economic context.  Samoa’s economic performance is constrained by distance to global markets, a small local market, and a low skill base population and vulnerability to natural disasters (particularly cyclones).  For example, Apia experiences 10 tropical cyclones per decade on average, usually between November and April.  The impact of the September 2009 tsunami and 2011 cyclones also affected Samoa’s economy negatively.  Samoa's current Human Development Index (HDI) is 0.688, which gives the country a global rank of 99 out of 187 countries assessed.

- Samoa’s economy still largely depends on its natural resources.  Despite a decline in agricultural sector’s contribution to the GDP, the 2009 Agricultural Survey has identified an increase in households engaged in this sector.  In 2006 around 75% of the households were engaged in agricultural activities, but it increased to 84% of households in 2009(accounting for the increase in numbers of households between 2006 and 2009).  Agriculture continues to be the major contributor to household subsistence, particularly in rural areas.  The 2009 Agriculture Census showed that 34% of the households mainly practiced mostly “subsistence” agriculture, whilst 31%, were engaged “mainly for home consumption”.  Only 3% of households practiced mainly commercial agriculture.  Notably, many wage-earning households were also engaged in supplementary subsistence production.

- Pollution and the growing volumes of solid and hazardous wastes are serious threats to Samoa’s environment and to its sustainable development.  Waste proliferation continues to accelerate with population growth, improved living standards, urbanization and increasing participation in international trade.  High levels of emission gases (GHG) is polluting Samoa’s atmosphere and affecting both the quality of the air, and contributing to climate change and climate variability.

- Samoa’s environmental challenges are significant and presently one of the most complex areas for the country to address given the pressures of rapid economic growth and social transition.  Being of small islands, the coastal zone assumes a disproportionately large role in its biogeography, and the interface between the coastal area and the marine environment a prominent feature.  Add to this a high human population and infrastructure concentrated along the coast, the result is a highly active zone where coastal habitats and species are under ongoing pressures from land-based pollution, exploitation and other stresses.  This is further compounded by the impacts of climate change.  Despite considerable progress achieved in the past years, Samoa’s environment still remains in a critical state.  Environmental governance is not effective, due largely to insufficient political commitment, unrealistic and unclear objectives, inadequate financing, weak technical and institutional capacities, and poor monitoring and evaluation.

- Samoa’s upland habitats are largely intact and undisturbed by human activities with a high percentage of forest cover (99%) for both Upolu and Savaii.  The nature and quality of forests in the uplands of the two islands are now significantly different.  For Savaii, 91% of the upland forest area is dominated by native species.  For Upolu, non-natives dominate 99% of the upland area.  The impact of the invasive vine Merremia is the main threat with recent estimates suggesting 24% of all forests affected including upland forests.  The increasing dominance of non-native species in the Upolu upland areas is largely the result of cyclones compounded by impact of cultivation and invasive species.  The existence of access tracks including vehicle access roads makes this easier.

- The loss of bird population from hunting is largely anecdotal with no recent studies of bird populations to indicate how serious this impact may be.  The BioRAP concentrated on ascertaining the status of two critically threatened species one of which appeared to have become extinct, and did not gather extensive data on other more common species.  Other invasive species of concern are myna birds, other vine species including Mikaniaspp and tree species including Albizziaspp.

- Land and water resources are constantly under threat from several pressures.  Beyond the degradation inflicted on corals and coral reefs, there is reported degradation of inshore habitats as a result of the impacts of land-based pollution.  A combination of land based activities are contributing factors including unsustainable land use practices including cultivation including within catchment areas, high level of siltation from surface run-off in areas denuded of vegetation cover, inferior sanitation facilities and solid waste management, waste dumping either into the sea or in mangrove areas and coastal dredging activities.  Some villages also continue to use traditional fishing methods that are unsustainable and are largely taboo in some villages.

- The degradation and fragmentation of forests is likely to continue as a result of cyclones, agro-deforestation, and settlements.  The rate of agro-deforestation is likely to increase.  This is the anticipated result of a Government objective of expanding both subsistence and commercial agriculture as set forth in the Samoa Development Strategy (SDS) 2008-2012.  The use of incentives such as the removal of import tariffs on agricultural related imports and the expansive network of access roads already built will facilitate the commercial expansion of agriculture.  Expanding agriculture has also led to the destruction of water shed management areas, an issue calling for urgent attention.  However the expansion of agriculture has also resulted in increased food security as well as the declining percentage of people living below the food poverty line.

- Sources of major air pollutants are of human induced activities.  These include cars, electricity and manufacturing products.  The most prevalent air pollutants come from carbon monoxide from motor vehicle exhaust and sulphur dioxide from power plants.  Cases in Samoa that have been brought to the attention of the government include a diesel generator for electricity with complaints against the noise and fumes emission as well as an old bitumen plant that pumps out particulate emissions from its chimney.

- Demand for energy has increased in Samoa over the last decade, thus reliable, affordable and environmentally sound energy services and supply is crucial to meeting this demand.  In 2010 petroleum consumption totaled at 90.9 million litres, seeing an increase of 5.9 % from 2009 (88.2 million litres).  The Transport sector accounted for 66.6% of total petroleum consumption in 2010 compared to 70.2% in 2009.  The Electricity sector takes 20.8% of total consumption and the rest of the 12.5% to commercial, agriculture, forestry, and residential sectors.  Average retail prices in 2010 increased by 8.3% and 7.8% for unleaded petrol and diesel respectively compared to 2009.  Total fuel imports show an increase of 3.7% from 88.2 million litres in 2009 to 91.5 million litres in 2010.

- Petroleum consumption in the Transport sector has decreased by 1.2% from 61.3 million litres in 2009 to 60.6 million litres in 2010.  This decrease in consumption is reflected from the air and marine transport that showed decreases of 8.9% and 27.1% respectively.  Land transport recorded an increase in consumption by 6.4% that is reflected by the increased number of registered vehicles in 2010.  Around 39% of total electricity production in Samoa is generated from hydro, 6% from Solar and the rest from diesel.  This percentage varies during the wet and dry seasons.  Electricity generation, transmission and distribution are exclusively under the authority of the Electric Power Corporation that is a government state owned enterprise.  The 2006 Population Census identified that 96% of the whole population in Samoa is electrified.

- The Samoan economy did not achieve its macroeconomic targets in the Strategy for the Development of Samoa (SDS) 2008 – 2012.  The SDS target for Gross Domestic Product (GDP) growth was 3 - 4% per annum.  However, over the four years of the SDS period, aggregate GDP showed zero real growth.  This implies that per capita GDP declined by an average of about 0.7% per annum.  The economy was adversely impacted by exogenous shocks such as the Tsunami in September 2009 that significantly affected tourism) and global economic volatility, notably the food and fuel price rises in 2007/08 and the economic and financial crisis that followed.

- Nevertheless, the government’s continuing economic goal is to rebuild macro-economic resilience and encourage inclusive growth, generate opportunities from global and regional integration as well as build resilience against natural disasters and climate change.  In this regard, the government will continue to ensure that it will progressively reduce the fiscal deficit and rebuild reserves as a cushion for future shocks, possibly through the use of budget support provided by the international community to enhance macro-economic resilience; including building cash balances and, potentially, improve the structure of its debt portfolio.

- Samoa‘s external position has been stable and remains comfortable.  Export revenues went up by 13.8 percent in 2009 while imports decreased by 17.8 percent over 2008.  Remittances more than doubled in the 8 years from 2002 to 2009, increasing by more than $180 million.  Net foreign reserves, at year end amounted to $339.7 million, a notable increase of 55.9 percent over 2008 and equivalent to 7.5 months’ worth of import cover was well above the Central Bank‘s target of 4 months.  On public finance, overall fiscal balance has been well maintained below the fiscal target of 3.5 percent of GDP throughout the years 2002/03 to 2007/08.  Financial year 2008/09 (provisional) was exceptional to record an overall deficit of $59.0 million (4.1% of GDP), however this was lower compared to the budgeted deficit of $84 million.

- In view of the recent economic performance, and Samoa’s vulnerability to external factors and natural disasters as recently experienced, the outlook for the medium term remains a challenge.  Hence, Samoa is committed to put in place prudent and responsible measures that would provide stimulus for sustained economic performance.  The impacts of climate change will continue to threaten environmental sustainability efforts in the medium term hence building national resilience will be accorded high priority.

### B.2.c	Policy and Legislative Context

- Since the last NCSA, the following legislation associated with the three Rio Conventions have been produced and are being implemented: Forestry Act 2011 (under review); Disaster & Emergency Management Act 2007; Land Registration Act 2008; Water Resources Management Act 2008; Unit Titles Act 2009; Waste Management Act 2010; Spatial Information Agency Act 2010.  The MNRE is also in the process of drafting an Environment Management & Conservation Bill as well as a Natural Resource Management Bill.  Related Regulations such as the PUMA (EIA) Regulation 2007; PUMA (Development Consent Application & Fees) Regulation 2008; Marine Wildlife Protection Regulation 2009; Aufaga Water Resources Bylaws 2011; Survey Regulation 2011 and Water Licensing Regulation 2011 have also been implemented.

- Added to these legislation and regulations are environmental policies, strategies and plans such as the NBSAP, National Communications, NAPA, NIP, NISAB, NWRM Strategy; CIM plans and others.  These policies, strategies and plans are implemented cognizant of other related sector policies and plans such as the Agriculture, Tourism, Energy, Disaster Reduction and Health Sector Plans.

- Fulfilling commitments as a Party under these various conventions contributed significantly to keeping the environment momentum at the national level, with the adoption of corresponding legislations and policies and action plans for implementing national obligations.  This is evident in the changes reflected in the Strategy for Development of Samoa (SDS) 2012-2016 that includes Environment as a Priority Focus area as compared to the SDS 2005-2007 where environment was not mentioned at all except as a cross cutting issue within three strategic areas; agriculture, health and tourism development.  The elevation of environmental sustainability alongside the economic and social pillars that previously were the focus of Samoa’s national planning framework also brought it in line with Samoa’s MDG goals.  The integration of environmental sustainability is observed in sector and sub-sector plans in all economic sectors including agriculture, fisheries, energy, infrastructure, and tourism.

### B.2.d	Institutional Context

- The Ministry of Natural Resources & Environment (MNRE) is the main implementing agency that oversees the formulation, coordination, and implementation of all of Samoa’s environmental policies.  As such, the MNRE is the focal point institution for the three Rio Conventions and responsible for reporting on their national implementation to the respective secretariats.  It houses multiple separate divisions dedicated primarily to meteorology, land, water and environmental planning and management.  The MNRE being the key ministry implementing national and global environmental obligations, has the largest repository of knowledge and experience on climate and natural resources in the country, with a number of highly trained staff in areas from hydrology to land registry and management to urban planning and climate sciences.  MNRE is also the ministry responsible for producing the key policy documents that guide climate change programming for the country, including the National Policy Statement on Climate Change and the NAPA.  It is the designated secretariat for the National Climate Change Country Team (NCCCT), members of which include the CEOs of relevant ministries, which has served as the key coordination mechanism for national response to climate change initiatives in the past.

- The Ministry of Agriculture and Fisheries (MAF) is another important line ministry that is responsible for the management of inshore and offshore fisheries, crop and livestock production and management practices as well as research to improve and increase subsistence and commercial farm production.  The MAF is a key partner agency of projects such as the GEF/UNDP Integrating Climate Change Risks in the Agriculture and Health Sectors in Samoa (ICCRAS&HSS) and Samoa Agriculture Competitiveness Project (SACEP) that aims to help local produce capture a larger proportion of the domestic food market and increase rural household incomes.  Part of this project is looking at impact of disasters and climate change on agricultural products that affects food security.

- The Ministry of Women, Social & Community Development (MWCSD) as the primary government institution for women’s issues as well as village governance, cooperation and development, is the entity through which all other government and non-government entities are required to pass for any work involving the local communities.  As such, it maintains the closest government ties to the village mayors, village women’s leaders and key local development actors.  Samoa operates on and advocates strongly, participatory approach and the use of consultative process.  The MNRE works in partnership with the MWCSD as well as the Samoa Umbrella of Non-Governmental Organizations (SUNGO), in ensuring the communities and civil society are included and consulted on all environmental matters and issues.  The MNRE has integrated and planning frameworks in all its divisions focusing on increasing awareness and providing support to communities and NGOs so they are involved throughout the whole environmental planning and management process.  An example of a community involvement in environmental management is the Community Forestry Program; and the implementation of Coastal Infrastructure Management (CIM) plan as the vast majority of the population living on the coastal fringes of Upolu and Savaii may experience an increase in coastal erosion, and are most likely to be affected more by storm surges, cyclones, hurricanes and other natural disasters.

- The MWCSD also warehouses the most extensive data and information on Samoa’s nearly 200 villages, much of which has recently been compiled in the MWCSD publication Samoan Village Profiles 2013.  Because of its extensive connection with the villages and its official mandate in the areas of social and community development and gender, MWCSD is also the ministry with the most expertise and experience in local development, productivity and vulnerable populations.  It is the ministry in charge of paying each village mayor and women’s representative and tends to be among the first official entities involved and consulted in any disaster situation, local governance issue or development assessment.  MWCSD has a small community development coordination unit that serves to represent the sector in the bimonthly sector coordination meetings and track progress on village sustainable development plans.

- The Ministry of Works & Transport Infrastructure (MWTI) is another major ministry, in charge of developing, disseminating and monitoring specifications for the national building code, which has been revamped to accommodate the country’s objectives in connection with climate change, disaster risk management and “building back better” philosophy.

- The Ministry of Finance (MoF) is the central agency in charge of the centralized database of donor assistance, which comprises close to 20% of GDP annually and through which all external development financing must pass prior to allocation.  Direct access to this data, in conjunction with the information compiled on national productivity by the Samoan Bureau of Statistics, provides MoF with the most comprehensive view of national expenditures.  This allows for more widespread analysis of cross-sector expenditures, such as those related to issues like CC and DRM.  Additionally, MoF was the principal government agency working with UNDP and other international partners on the national Climate Public Expenditure and Institutional Review (CPEIR) project, providing it with extensive background in the concepts of CC fiscal management.  MoF, through its Economic Policy and Planning Division (EPPD) is also responsible for the coordination of the country’s 14 sectors that contribute to the national development strategy and programme objectives in line with a relatively recently adopted sector-wide approach to development.  These sectors include finance; agriculture; education; tourism; trade, commerce and manufacturing; health, law and justice; community development; public administration; water; communication; transport; energy; and environment.

- At the regional level, Samoa is a member of several regional organizations and mechanisms such as the Secretariat of the Pacific Regional Environment Programme (SPREP), Secretariat of the Pacific Community (SPC), Pacific Islands Forum Secretariat (PIFS) and others.  SPREP plays a key role in providing technical advice on regional and global environmental programmes on thematic areas including biodiversity, climate change, environmental monitoring and governance, and waste management.  The MNRE works in close collaboration with SPREP on all these thematic areas.  Samoa being a Pacific island country, works closely with PIFS in the areas of climate change expenditure and climate change financing, to meet the critical climate change challenges in the Pacific region.  This is consistent with the call by Forum Leaders for PIFS to pursue the Copenhagen Accord announced at the 15th FCCC Conference of the Parties in 2009.

- Procedures and mechanisms to enable effective coordination between ministries/sector on environmental issues and to ensure mainstreaming and integration of the Rio Conventions into the SDS and various national and sectoral legal frameworks include establishment of various coordination bodies and committees such as the National Climate Change Country Team that include the CEOs of relevant ministries.  The NCCCT has served as the key coordination mechanism for national response to climate change initiatives in the past.  The NCCCT, first established in the early 1990swas effective in supervising the formulation of the National Climate Policy 2007 and in managing the NAPA.  Its ToR states that it is to meet 2-3 times a year or more frequently if necessary.  However, the NCCCT in recent years has not seen the need to meet given the number of cross-sectoral and inter-ministerial coordination mechanisms that have sprung up (as detailed in the following sections) and have effectively taken over the role of the NCCCT.  Its mandate is also quite limited and was set up as a working group since it was not established by any legislation or regulation.

- From the economic planning and budgeting perspective, the Economic Policy & Planning Sector Coordination is led by the Ministry of Finance (MOF).  This brings together the 14 sectors, including environment, who all contribute to the SDS and programme objectives in line with a relatively recently adopted sector-wide approach to development.

- The NESP Advisory Committee (NESPAC) was established with the approval of the Cabinet in 2013.  Chaired by the MNRE CEO, membership is 27 comprised of representatives from Government Ministries, Corporations, Universities and Research Organizations, Private Sector, Regional organizations and NGOs.  This committee was first established under the NEMS in 1993 but has since been reactivated during the review of the NEMS, SOE and the development of the NESP in 2013.  The NESPAC is a multi-sector/agency coordination mechanism set up to oversee and coordinate the implementation of the NESP.  The NESP provides broad strategic directions recognizing that sub-sector plans such as NAPA, NBSAP, SNAP, Biosafety, NIP, KBA, National Communications and Water for Life provide the detailed action plans of specific activities within each focal areas of MNRE.  This coordination mechanism brings together all relevant stakeholders to review environmental monitoring activities and identify ways for encouraging coordination and integration; facilitate the harmonization and compatibility of data gathering methods, protocols and indicators and; ensure environmental monitoring is integrated into agencies annual work plans as ongoing activities.

- The Environment Coordinating Unit is based within the MNRE and headed by an Environment Sector Coordinator.  Its setup is similar to the Water Sector Coordination Unit and supports the work of all three Rio Conventions Focal Points.  The Samoa Bureau of Statistics (SBS) works closely with this unit to ensure data for baselines, including numeric indicators are used in future national environmental strategies, policies and plans.  These mechanisms serve to support and further enhance the coordination, and further improve implementation of the Rio Conventions in Samoa.

- As an open economy with a narrow export base, Samoa faces a persistent sizeable trade deficit.  Samoa, in association with its development partners provides support and incentives to the private sector under various schemes and facilities such as the Private Sector Support Fund, Duty Concession scheme and Code 121.  The MNRE works closely with the private sector through the Chamber of Commerce (CoC) in developing national strategies in alliance with the private sector.  For example, the MNRE works closely with the Women in Business Development Inc who has a unique role of being an NGO but provides and empowers communities and families with knowledge and skills, opportunities and access to finance and markets for locally produced products.  This organization serves a client base of more than 1,300 rural Samoa families in 187 villages and their products (for national commercial clients or exportation) range includes dried bananas, fetau oil (medicinal and commercial value), fine mats, virgin coconut oil, handicrafts

Table 1: Samoa’s ministries as of March 2014

| Ministry of Agriculture (MAF) | Fisheries; Crops; Livestock; Quarantine; Research |
| --- | --- |
| Ministry of Commerce, Industry & Labor (MCIL) | Industrial relations; OSH; Fair Trading & CODES; Apprenticeships; Investment Promotion; Industry development |
| Ministry of Communications & Technology (MCIT) | National Radio; Telecommunications & Postal Service; Rural connectivity programme; MDG LED Screen |
| Ministry of Education, Sports & Culture (MESC) | Education, Sport & Culture (museum and archives) |
| Ministry of Foreign Affairs & Trade (MFAT) | Foreign Services; Scholarships; Political Focal Point for all Conventions & Treaties |
| Ministry of Justice and Courts Administration (MJCA) | Courts; Correction & Enforcements; Legal, Policy & Censorship; Mediation & Registration |
| Ministry of Natural Resources and Environment (MNRE) | Disaster Management; Environment & Conservation; Forestry; GEF Advisory Services; Land Management; Meteorology; Planning & Urban Management; Renewable Energy; Water Resources; Technical services |
| Ministry of Finance (MOF) | Economy; Budget; Procurement; Aid Coordination & Debt Management; State Owned Enterprises; Climate Resilience Investment Coordination |
| Ministry of Health | Health professionals & Enforcement Service; National hospitals |
| Ministry of Revenue | Revenue |
| Ministry of the Prime Minister & Cabinet (MPMC) | Prime Minister, Cabinet; Immigration; Transnational Crimes Unit; Policy Implementation & Monitoring Unit |
| Ministry of Women, Community & Social Development (MWCSD) | Women, Internal Affairs; Youth |
| Ministry of Works & Transport Infrastructure (MWTI) | Civil aviation; maritime; land & transport; asset management & building; policy &planning |

- The MNRE works closely with the Ministry of Education, Sports & Culture (MESC) in the integration of environmental issues into national curricula.  The National University of Samoa is piloting a Renewable Energy project in partnership with the MNRE.  The education sector is also one of the representatives on the various committees and coordination mechanisms established mentioned in earlier sections.  The Scientific Research Organization of Samoa (SROS) is a major partner of the MNRE in terms of conducting research on issues such as biogas, assessments or pre-feasibility studies for the identified viable sources and RE technologies, identification of potential projects for Clean Development Mechanism

- Samoa’s institutional structure in the area of environmental management is heavily sectoral and centralized.  While the line ministries' sectoral approach to the implementation of their strategies, plans and programmes conform within the boundaries of their institutional mandates and legislative authorities, this also makes it difficult to integrate the Rio Conventions provisions into their programme of work.  All ministries struggle with project management for donor driven initiatives.  Because donor funding can seldom be incorporated into existing national programmes or budgets, these projects often entail duplication of staffing, reporting and implementation effort—but with different corresponding parameters and requirements, which further complicates the issue.  Given Samoa’s small population and labor force, international project management ends up being a capacity problem for all government entities.  Additionally, results based management principles (working with baseline indicators, tracking of output, and documentation of concrete results) are relatively new to public sector work in Samoa and not yet fully comprehended or mainstreamed into operational practice.

- Rio Conventions are not explicitly integrated in the various ministries’ objectives and current works of these different Ministries also do not explicitly attempt to maximize global environmental values – including global biodiversity conservation and greenhouse gas emission reduction.  Thus, Rio Conventions promotion is hindered by limited institutional coordination capacities, but additionally there are also issues of systemic and staff capacities.

- There has been an extremely limited attempt to capture lessons from relevant programmes and projects into a national environment information database that is readily available for local communities or government agencies.  Thus, such experiences have been lost and not been widely replicated.  Past efforts at strengthening national capacities have been ad-hoc, with training, workshops and other events organized based on short term projects and programmes that are not strategic.

- Although different national level manuals and technical documents have been developed, they are not being used by all relevant agencies.  For example, the MNRE has developed a Soil Resources Interpretative Manual (SRIM 2010), which identifies different soil types and their suitability to various types of crops and trees.  However, such manuals are neither widely available nor used as such manuals have not been designed with local land holders/ farmers as target groups.  In addition, they are also not available in the local language.

- Fulfilling commitments as a Party under the three Rio Conventions and other MEAs contributed significantly to keeping the environment momentum at the national level, with the adoption of corresponding legislations and policies and action plans for implementing national obligations.  This is evident in the changes reflected in the Strategy for Development of Samoa (SDS) 2012-2016 that includes Environment as a Priority Focus area as compared to the SDS 2005-2007 where environment was not mentioned at all except as a cross cutting issue within three strategic areas; agriculture, health and tourism development.  The elevation of environmental sustainability alongside the economic and social pillars that previously were the focus of Samoa’s national planning framework also brought it in line with Samoa’s MDG goals.  The integration of environmental sustainability is observed in sector and sub-sector plans in all economic sectors including agriculture, fisheries, energy, infrastructure, and tourism.

- Despite these policies and institutional steps, Samoa continues to face many challenges in fulfilling its obligations under the Rio Conventions.  The Samoa National Capacity Self-Assessment (NCSA) completed in 2007 identified gaps in capacity at the systemic, institutional and individual levels as being the primary barrier to effective management of global environment commitments and limits Samoa’s ability to realize full implementation of the three Rio Conventions.  The National Environmental Capacity Strategy and Action Plan that followed in the same year provided recommendations on strategies for national capacity development.  It also provided the basis for interventions on capacity development and environmental concerns.

- Samoa has attempted to address these issues through the establishment of various coordination mechanisms such as steering committees, task forces and various other mechanisms.  These coordination mechanisms mentioned in an earlier section would be normally tasked with establishing procedures for cross-sectoral coordination towards the integration of environmental conservation principles in the development of socio-economic programmes and projects.  However, while the process and mechanisms are there, there is scope for enhancing these existing mechanisms to become more efficient and effective.

- Mainstreaming of Rio Conventions into the SDS to Sector levels needs to be developed further and requires cascading programmes and activities into Corporate Plans as they are crucial to the economic and development planning cycle.  Corporate Plans are also directly linked to Performance Budgeting.  This issue was also raised in studies undertaken under PPCR Phase 1.  Samoa’s recurring experience with natural disasters such as cyclones and the 2009 tsunami has raised recognition of climate resilience as a development issue.  This has in a roundabout way significantly contributed to progressing implementation and obligations to the three Rio Conventions.  It has catapulted the integration of climate change, climate resilience and disaster risk reduction into the national planning process with the majority of the sector plans making reference to, or including climate related activities.

### B.2.e	Barriers to Achieving Global Environmental Objectives

- The barriers to achieving global environmental objectives are in large part a reflection of the challenge Samoa faces in pursuing environmentally sound and sustainable development while keeping a fine balance on its socio-economic development.  The main barriers identified during the NCSA process were:

Systemic

- Non-existent or weak and ineffective coordination and networking systems

- Weak enforcement of policies and legal frameworks for the effective implementation of the Conventions;

- Lack of a comprehensive approach to the strategic implementation of the Rio Conventions and creation of synergies; and

- Non-compliance of MEAs obligations

Institutional

- Non-existent centralized information database/system for efficient data management and environmental monitoring,

- Inadequate mechanisms for enforcing the fulfillment of Samoa’s obligations under multilateral environmental agreements;

- Weak organizational capacity and lack of effective coordination and management at all levels (national and sectoral level) to support Rio Convention implementation;

- Inadequate consideration of environmental impacts during the development of sectoral regulation;

- Inadequate indicators to assess Rio Convention implementation; and

- Lack of or weak public awareness on the Rio Conventions; and

- No strategic and logical approach to communicating Rio Conventions and environmental issues in a simpler manner

Individual

- Lack of or weak awareness on national, sectoral and general public with regard to Samoa’s obligations under the Rio Conventions; and

- No strategic and logical approach to communicating Rio Conventions and environmental issues in a simpler manner for awareness-raising.

- All three Rio Convention Focal Areas have their own specific databases that feed into the Centralized Information & Data unit (for instance the CBD has Marine, Terrestrial and National Parks and Reserves databases; the FCCC has CLEWS, CLIDE& CCD has Land Management databases; GIS; SamFris).  To meet global obligations of the FCCC and to raise awareness most especially in climate change and related issues (CCA, DRR/DRM), the MNRE climate section is developing user friendly climate information for the Agriculture and Health sectors through the CLEWS.  The MNRE being the key ministry implementing national and global environmental obligations, has the largest repository of knowledge and experience on climate and natural resources in the country, with a number of highly trained staff in areas from hydrology to land registry and management to urban planning and climate sciences.  Various Communication Strategies developed by different projects exist and help coordinate efforts at raising awareness of environmental issues in Samoa.

- However, findings of the capacity scoping of the GEF LDCF Economy-wide Integration of CCA and DRM/DRR to Reduce Climate Vulnerability of Communities in Samoa capacity, NEMS review, compilation of the SOE and the NESP, and other relevant evaluation reports note that while there is a tremendous amount of databases, data and information, knowledge management and data sharing is most often the hindrance to meeting reporting obligations of the three Rio Conventions.  Baselines and indicators do not exist in some instances and in cases where they do exist, are not kept or stored in an easily accessible manner.

- Synergies exist in other projects such as the GEF/UNDP Integrating Climate Change Risks in the Agriculture and Health Sectors in Samoa (ICCRAS&HSS) and Samoa Agriculture Competitiveness Project (SACEP) that aims to help local produce capture a larger proportion of the domestic food market and increase rural household incomes.  Part of this project is looking at impact of disasters and climate change on agricultural products that affects food security.  While the SDS 2012-2016 include revised priorities and indicators for Environment Sustainability, the SBS in collaboration with the MNRE will look at reviewing indicators in the SOE to align with the SDS 2012-2016.  However, it requires strengthening of coordination mechanisms so they are more efficient and effective to translate from just policy level to implementation level so all three Rio Conventions are mainstreamed into the SDS indicators that by default will also achieve MDG indicators.

- Rio Conventions obligations and implementation are seen as environment-specific, so while plans and work is already underway to mainstream the Rio Conventions into the SDS and all sector levels, the actual implementation and reporting of the Convention obligations is handled at the Corporate Plan level and most often, are not seen as a priority and not allocated resources (people and financing) as they are not cascaded into the implementation level.  Corporate Plans are crucial to the economic and development planning cycle as they are directly linked to Performance Budgeting.  This issue was also raised in studies undertaken under PPCR Phase 1.  Samoa’s recurring experience with natural disasters such as cyclones and the 2009 tsunami has raised recognition of climate resilience as a development issue.  This has in a roundabout way significantly contributed to progressing implementation and obligations to the three Rio Conventions, including the recognition to review budgetary allocations to increase the implementation of the Rio Conventions and its obligations.

- Most of the barriers to achieving global environmental objectives in Samoa are largely the result of lack of awareness and understanding of the Rio Conventions’ value to the nation, and is further exacerbated by fragmented policies, legislation and outdated legal frameworks on both the national and sectoral levels in Samoa.

# C.	Programme and policy conformity

## C.1	GEF Programme Designation and Conformity

- This project conforms to the GEF-5 Cross-Cutting Capacity Development (CCCD) Strategy, CCCD Programme Framework 2, which calls for countries to improve decision-making for the global environment through improved generation, access and use of information and knowledge.  The project will improve the decision making process through the strengthening of information and knowledge management systems.  In line with the strengthening of institutional capacities will be improved procedures for accessing, analyzing and sharing data and information pertinent to the implementation of the Rio Conventions.  This will also reduce associated transaction costs.  The project will also target key legislative and regulatory instruments necessary to underpin the institutional structures and mechanisms that make up the Data, Knowledge and Information Facility (DKIF).  Training and awareness-raising will be provided to strengthen stakeholders and other social actors’ understanding and value of the DKIF and other capacity development activities under the project.  Through a learn-by-doing process, this project will increase the ability of stakeholders to diagnose, understand and transform information and knowledge into local actions.  The project will help institutionalize these capacities through the implementation of selected recommendations reinforcing improved compliance with Rio Conventions.  More precisely, this CCCD framework provides the vision for CCCD projects to institutionalize and strengthen these capacities for improved implementation, management, reporting and compliance.

- This project will implement capacity development activities through a collaborative management approach to engage key stakeholders as partners and collaborators in the design and implementation of project activities.  The design will take into account unintended consequences arising from policy interventions.  The project is consistent with programmatic objectives of three GEF thematic focal areas of biodiversity, climate change and land degradation, the achievement and sustainability of which is dependent on the cross-cutting capacity development challenges and barriers assessed in the NCSA and outlined in sections B.2.a National Capacity Self-Assessment and B.2.e.  Barriers to Achieving Global Environmental Objectives. Underpinning

- As a targeted CCCD medium-size project, the project activities will focus on setting up a centralized information and knowledge management system for data management and environmental monitoring.  This system will be integrated with other relevant and existing databases and information systems that complement the implementation of the Rio Conventions and other MEAs.  In the process of establishing the DKIF, the project will by default necessitate the review and synergizing of necessary legal instruments and policies to strengthen the effective implementation of the Rio Conventions.  Training will be provided for all relevant and targeted stakeholders on the revised environmental legal instruments as well as the centralized information and knowledge system.  The project will work to institutionalize the centralized information & knowledge management system, and work with the Samoa Bureau of Statistics (SBS) to develop protocols and parameters to analyze data, coordinate and share information across departments, agencies and other organizations.  This by default will strengthen the coordination mechanisms critical to catalyzing effective mainstreaming of Rio obligations into Samoa’s overarching national development framework.

- Through the successful implementation of this project, outcomes will have resulted in a set of improved capacities to better implement, meet and sustain global environmental outcomes.  This is in line with the shared obligations under the three Rio Conventions that call for countries to strengthen their national capacities for effective national environmental management.  Table 2 summarizes the project's conformity with the 11 operational principles of capacity development identified in the GEF Strategic Approach to Capacity Building.

Table 2:  Conformity with GEF Capacity Development Operational Principles

| Capacity Development Operational Principle | Project Conformity |
| --- | --- |
| Ensure national ownership and leadership | The development of the present project benefitted from consultations with relevant cross-sector stakeholders including private, inter-faith/religious groups, civil society, research & academic institutions, government agencies, and laboratories among others. These consultations resulted in a consensus on the capacity development needs and the entry points for interventions this project will focus on. |
| Ensure multi-stakeholder consultations and decision-making | Preliminary consultations have already identified the major stakeholders and partners, inclusive coordination mechanism, who will be involved. Each with their own particular comparative advantages, to ensure a holistic approach to the integration of global environmental priorities into national development frameworks. This includes contributing to the identification and development of strategic policy and programmatic gaps to meet Rio Convention objectives, as well as to both deliver and receive training to better understand and operationalize integrated global/national environmental and development strategies, programmes and plans. The further narrowing of the targeted groups and their representatives will be undertaken through an open consultative process to re-affirm and strengthen their commitment to project objectives and goals |
| Base capacity building efforts in self-needs assessment | Building on the existing capacities and those developed as part of the NCSA consultative process, the project will strengthen a process to catalyze effective mainstreaming of Rio Convention obligations into Samoa’s overarching national development framework. This project will strengthen capacities of the MNRE, and relevant coordination mechanisms (which includes a wide spectrum of stakeholders) to effectively coordinate the policy decisions and catalyze implementation pertaining to the three Rio Conventions, as was identified as a top cross-cutting capacity priority in the Samoa NCSA. |
| Adopt a holistic approach to capacity building | The project recognizes and takes into account the need for proper balance between individual, institutional and overall policy framework in which individuals and organizations operates and interacts with the external environment. The project will focus on institutionalizing a holistic approach to policy coordination, and strengthening associated human capacities and necessary infrastructure, to operate and manage this process. It will focus on the MNRE and other (MOF, MFAT, MAF) central and line ministries that govern environmental and socio-economic issues for Samoa. It will seek to address the priority barriers within MNRE and other agencies, to effectively implement the three conventions. Particularly by strengthening cooperation among the various governmental units to develop policies, programmes and implement legislation that reduce the fragmented implementation of biodiversity, climate change, and land degradation programmes |
| Integrate capacity building in wider sustainable development efforts | The project recognizes that developing capacities for global environmental action is closely related and interlinked to Samoa’s on-going initiatives to enhance capacities for environmental management and sustainable development efforts in general. By effectively mainstreaming and integrating Rio Convention provisions into Samoa’s overarching socio-economic plan (SDS and associated sector plans), the project will catalyze capacity building activities for Samoa (e.g., learning-by-doing; training on data, information & knowledge management) that will meet both national and global environmental benefits. |
| Promote partnerships | This project calls for the strengthening of institutional, systemic and individual capacities, promoting and strengthening existing coordination mechanisms (task forces, steering committees), partnerships and commitments. By doing so, improved coordination and collaboration should reduce overlap and duplication of activities, catalyze the effective and efficient exchange of information, and improve the country’s implementation of the Rio Conventions. Also, by raising public awareness, building partnerships, and promoting policy dialogue, the project will seek to promote an enabling environment within its government ministries and agencies, as well as with the civil society, academic and research institutes, NGOs and the private sector, for achieving sustainable development and addressing global environmental issues. |
| Accommodate the dynamic nature of capacity building | The project's implementation arrangements include the coordination among different initiatives that will be managed through the MNRE, through its Corporate Services Division, support of the National Focal Points to the Rio Conventions and the inter-sectoral monitoring of the GEF Division (Focal Point). Furthermore, bi-monthly meetings with project coordinators working on related initiatives will be held in order to analyze synergy opportunities, challenges and lessons learnt. A Project Board (NESP Advisory Committee) that includes MNRE, MFAT, MOF and other stakeholders as identified in earlier sections, will convene regularly (once every four months and as needed) to oversee the performance of capacity development activities, manage risks, and to approve appropriate modifications to the project activities |
| Adopt a learn-by-doing approach | The key capacity development activities of the project involve a variety of tools and methodologies ranging from traditional methods to capacity building (e.g., workshops, in-service technical training) to wider scope ones such as multi-stakeholder project steering committees, shared project management responsibilities and the learn-by-doing approach. Government representatives and other stakeholders will be involved in the collaborative review, analysis for formulation of recommendations of the various national and sector analyses to implement solutions. The learn-by-doing approach will also be instituted through the implementation of selected recommended policy reforms of the respective sectoral analyses. |
| Combine programmatic and project-based approaches | This project takes both a bottom-up and top-down approach to mainstreaming Rio Conventions that effectively mirrors the NCSA bottom up approach. Using the existing five (5) environmental legal instruments and Rio Conventions as the analytic framework for the national and sectoral analyses, recommendations will be made to strengthen relevant national and sectoral policies to better deliver global environmental outcomes. These would be integrated into Samoa’s SDS that will provide a programmatic framework for the holistic pursuit of Rio Convention outcomes and sustainable development. |
| Combine process as well as product-based approaches | This project will follow the process of applying adaptive collaborative management to allow project activities to be flexible to changing circumstances while maintain consistency to agree project objectives. It will ensure that representatives from all stakeholder groups are represented early in the decision making process. This process effectively began with the NCSA and will continue, and wherever appropriate, ensure that stakeholders receive an equitable share of benefits (e.g., data, information and knowledge) to sustain their interest, commitment and accountability of project activities, outputs, and outcomes. Since the NCSA phase, this project has involved many multi-stakeholder representatives, and it will continue to engage champions that will play a leading role in the present phase in order to implement national and sectoral policy recommendations and actions. |
| Promote regional approaches | This project will test recommendations for reforms and amendments at the regional level. Contextualizing issues from the regional level will allow for trialing and ground-proofing recommendations, and informing modifications of national and sectoral plans. This project will work with complementary programmes and projects of regional organizations such as the Secretariat of the Pacific Regional Environment Programme (SPREP) through its climate, biodiversity, environmental governance & monitoring as well as others such as the, Pacific Islands Forum Secretariat (PIFS climate programmes) and Secretariat of the Pacific Community (SPC land, agriculture programme). |

### C.1.a	Guidance from the Rio Conventions

- This project will address the shared obligations under the three Rio Conventions that call for countries to strengthen their national capacities for effective national environmental management.  Samoa is fully committed to meets its obligations under the Conventions and other MEAs and the proposed project is intended to facilitate an important step towards strengthening capacities for an effective national environmental management framework.  The project will address a set of Rio Convention articles (see Table 3) that will strengthen Samoa’s environmental governance for the global environment by targeting capacity development towards institutionalizing, reconciling, and harmonizing environmental legal instruments for a better understanding of how to strategically and effectively implement national environmental legislation to support global objectives.  It will build upon the 11 GEF Capacity Development Operational Principles (Table 2) in its implementation arrangements to deliver technical and institutional capacities.

Table 3:  Capacity Development Requirements of the Rio Conventions

| Type of Capacity | Convention Requirements | FCCC | CBD | CCD |
| --- | --- | --- | --- | --- |
| Stakeholder Engagement | Capacities of relevant individuals and organizations (resource users, owners, consumers, community and political leaders, private and public sector managers and experts) to engage proactively and constructively with one another to manage a global environmental issue. | Article 4 Article 6 | Article 10 Article 13 | Article 5 Article 9 Article 10 Article 19 |
| Organizational Capacities | Capacities of individuals and organizations to plan and develop effective environmental policy and legislation, related strategies, and plans based on informed decision-making processes for global environmental management. | Article 4 Article 6 | Article 8 Article 9 Article 16 Article 17 | Article 4 Article 5 Article 13 Article 17 Article 18 Article 19 |
| Environmental Governance | Capacities of individuals and organizations to enact environmental policies or regulatory decisions, as well as plan and execute relevant sustainable global environmental management actions and solutions. | Article 4 | Article 6 Article 14 Article 19 Article 22 | Article 4 Article 5 Article 8 Article 9 Article 10 |
| Information Management and Knowledge | Capacities of individuals and organizations to research, acquire, communicate, educate and make use of pertinent information to be able to diagnose and understand global environmental problems and potential solutions | Article 4 Article 5 Article 12 | Article 12 Article 14 Article 17 Article 26 | Article 9 Article 10 Article 16 |
| Monitoring and Evaluation | Capacities in individuals and organizations to effectively monitor and evaluate project and/or programme achievements against expected results and to provide feedback for learning, adaptive management and suggesting adjustments to the course of action if necessary to conserve and preserve the global environment | Article 6 | Article 7 |  |

## C.2 Project Design:  GEF Alternative

- This project takes an incremental approach from a GEF construct towards strengthening Samoa’s environmental governance to meet Rio Convention objectives.  In the absence of this project, Samoa would continue to govern its environment through existing set of legislation, policy and development planning documents with mixed results.  While these results would provide global environmental benefits, they would do so at a higher transaction cost than through the proposed GEF Alternative.  Government staff and the general public would remain insufficiently knowledgeable about how to fully understand the implications of global environmental directives under the conferences of the parties on national environmental and development policies, and how these directives can be strategically implemented through existing national environmental legislation and legal frameworks on both the national and sectoral levels.  The barriers to meeting and sustaining global environmental outcomes are described in section B.2.e.

### C.2.a	Project Rationale

- The rationale for this project stems from the NCSA findings mentioned in B.2.a and subsequent recommendations which asked for the improvement of national policy, legislative and institutional frameworks for better compliance and implementation of the three Rio Conventions.  This would include the establishment of adequate institutional data and information management and dissemination mechanism to assist improve public awareness, to facilitate their participation in national efforts at meeting global issues.  It also calls for strengthening and enforcement of policies and legal frameworks at the systemic and individual levels.  There are in existence a great number of environment laws, strategies, frameworks and policies that generate much confusion, impeding Samoa’s  ability to effectively comply with Convention objectives.  As a result, these legal instruments are not effectively implemented or enforced, and in certain cases work against each other.  This is further exacerbated by decision-makers and planners not being adequately versed on the legislation and issues inherent.  This is due to a variety of reasons including staff changes and insufficient training.

- This project is innovative in its design as it will target capacity development activities to key partners, decision-makers, planners and their respective staff, on how to better implement (and amend where appropriate) the current set of environmental legal instruments, tools and mechanisms to meet both national and global environmental priorities.  It will work in close parallel with other government initiatives which compliment and/or strengthen Samoa’s capacity to implement Rio Convention obligations.  This will necessitate the improvement of coordination mechanism and data and knowledge management tools to equip the MNRE (as the key environment organization) better drive and encourage coordinated efforts at mainstreaming the three Rio Conventions into the planning stages of national programmes and priorities.

- This project is in line with CCCD Programme Framework 2, which calls for countries to improve decision-making for the global environment through improved generation, access and use of information and knowledge.  Through the generation and use of knowledge and information, the project will also contribute to CCCD Programme Framework 4, which calls for countries to strengthen capacities for developing and implementing policy and legislative frameworks.  Through a learning-by-doing process, this project will increase the ability of stakeholders to diagnose, understand and transform information and knowledge into local actions.

- The allocation of the GEF increment and co-financing to each activity is a best estimate of how much of the GEF increment is needed to complement the baseline and co-financing that was leveraged to implement the project.  The GEF will partner with the Government of Samoa and UNDP’s technical assistance programmes to provide incremental support to strengthen tools and mechanisms to mainstream global environmental provisions under the three Rio Conventions.  This project will also coordinate with the GEF/UNDP Samoa LDCF parallel outputs such as Output 1 on mainstreaming CCA into development plans and sectoral strategies, and Outputs 3.1 and 3.2 on development of knowledge management and establishment of an M&E system to strengthen institutional coordination.  These two complementary projects will contribute to the overall effective implementation, reporting and monitoring of the Rio Conventions and other MEAs.

### C.2.b	Project Goal and Objectives

- The goal of this project is to address the capacity gaps and needs that are vital to the enhancement of Samoa’s ability to meet its obligations under the Conventions.  To this end, the objective of this targeted cross-cutting capacity development project is to strengthen technical and institutional capacities for more effective implementation of the three Rio Conventions.  This objective will be met by three closely interlinked components:

- Component 1 focuses on strengthening developing more effective tools and mechanisms to meet Rio Convention obligations, including strengthening targeted legal instruments to ensure long-term legitimacy of project results.  Building on the capacities developed under Component 1, Component 2 will strengthen the institutional and individual capacities of the key implementing agencies to support the implementation of the Rio Conventions.  This component is crucial as it comprises a broad set of capacity development activities that serve to reinforce the resilience and institutional sustainability of project outcomes.  It includes the design and implementation of a centralized knowledge and information management and sharing system, policies and processes which will feed into the design of comprehensive training programmes and public awareness campaign, targeted for technical staff, parliamentarians, legal officers, community authorities as well as a range of other stakeholders.

- Through a learn-by-doing, collaborative and participatory set of exercises and building upon the tools developed in component 1, Component 3will engage stakeholders in the mainstreaming of Rio Convention obligations, criteria, and indicators into a select set of national development plans and sector plans.

- The objective of this project is in line with the CCCD strategy of strengthening capacities for policy and legislation development for achieving global benefits and generation, access and use of information and knowledge to capture and share environmental development baseline as a strategic approach to institutionalize national efforts that deliver global environmental benefits.  Annex 2 provides a logical framework of the project that details project objectives, outputs and activities.

- The project will take an adaptive collaborative management (ACM) approach to implementation, which calls for stakeholders to take an early and proactive role in the mainstreaming exercises, as well as to help identify and solve unexpected implementation barriers and challenges.  By taking an ACM approach, project activities and outputs can be more legitimately modified and adapted to maintain timely and cost-effective project performance and delivery.

Mainstreaming of Rio Conventions

- SDS 2017-2021 with operational focus on Rio Conventions

- Rio Convention obligations mainstreamed into NESP, and other sector plans

- Streamlined monitoring & implementation of Rio Convention & other MEAs global obligations across sectors

Information Management and Sharing

- Assessment of institutional structure & mechanisms for managing, collecting and sharing data and information

- Design, procure & establish centralized Data, Information and Knowledge Management Facility (DIKF)

- Develop policies, protocols & parameters for identification, collection, storage, access and info sharing

Effective Tools and Mechanisms to Implement Rio Conventions

- Rio Convention tools defined and revised

- Consolidated multi-agency/multi-sector environmental programme designed and implemented

- Coordination mechanisms  (inclusive financial) strengthened

- Revised environmental legislation, policies and frameworks

3

2

1

- Targeted Trainings (complete with training plans, pre & post-training questionnaires, and training objectives & expected learning outcomes)

- Consultations

- Policy dialogues

- Workshops

- Public Awareness Campaign

Figure 1:  Project design

### C.2.c	Expected Outcomes

- At the end of the project, activities will have resulted in a set of improved capacities to better meet and sustain global environmental outcomes as framed by the Rio Convention objectives and other MEAs that Samoa has ratified.  This project will have strengthened and institutionalized commitments under the Rio Conventions through mainstreaming of the Rio Conventions into key national and sectoral development programmes, plans and policies to better implement, monitor, and enforce national environmental legislation and frameworks that contribute to achieving Rio Convention obligations.  Another project outcome will be strengthened coordination mechanisms, tools and infrastructure to improve data, information and knowledge management and sharing, to support a more harmonized approach to collecting baselines and data for monitoring and enforcing of Convention obligations as well as national programmes and priorities.  This outcome will also raise public support, through improved awareness of, and participation in, the implementation of the Rio Conventions.  This outcome will provide data and information required to support the mainstreaming, monitoring and evaluation aspects (M&E) of the conventions into national and sectoral plans.  All outcomes will notably achieve Convention objectives through the development of the environment sector.

- Through its learning-by-doing approach and,  supported by data and information generated through project activities, the project will strengthen the technical capacities of government agencies on their understanding of the various environment-related legislation, their overlap, conflicts, synergies, and how to reconcile these to better meet Rio Convention priorities and obligations.  The project will institutionalize a process that will strengthen inter-agency and sectoral coordination and information sharing, to better sustain long-term actions required to effectively implement Rio Convention obligations on a nation-wide basis.

### C.2.d	Project Components, Outputs, and Activities

Component 1:  Strengthened tools and mechanisms for implementing Rio Conventions

Outcome 1:	The Rio Conventions are more effectively implemented through national planning frameworks that are supported by best practice tools and institutional arrangements

- This component focuses on strengthening organizational and individual capacities to understand how new and improved tools and mechanisms can more effectively contribute to meeting Rio Convention obligations.  It will achieve its outcome through the development of a multi-sector, multi-agency consolidated environmental monitoring programme and the provision of targeted trainings and workshops.  The strengthening of mechanisms will see an improved coordination of monitoring of the global environment outcomes, and achieve Samoa’s national development priorities.  This component will also focus on strengthening environmental legislation, policies and frameworks to guide the implementation of the Rio Conventions.  The outcome can only be achieved by building and strengthening existing technical capacities to diagnose, understand and transform the complex dynamic nature of global environmental problems and develop local solutions.  Component 1 focuses particularly on strengthening the capacities of the MNRE as the Focal Points for all three Rio Conventions and as well, the key organisation driving the integration and mainstreaming of environment and sustainable development into all other related sectors.

Output 1.1:	Effective tools and mechanisms for implementing Rio Conventions

- This output will include a number of activities to strengthen environmental instruments and associated policies and frameworks that will drive the effective implementation, monitoring and compliance at the institutional and national level, of the Rio Conventions obligations.  Tools and mechanisms are already in place however, requires either strengthening or updating in order for a coordinated approach at proper implementation, monitoring and reporting across the three Rio Conventions, most specifically from a strategic perspective.

Activities:

1.1.1:	Conduct desk review of NBSAP, NAP, NAPA and National Communications to identify cross-cutting tools and policies that require strengthening or updating.

Target indicator:	Matrix indicating status of each tool/mechanism used completed by month 6

1.1.2:	Prepare definitions of different tools and key reporting components (Reporting, Monitoring, Assessment, Data collection & Analysis tools) and identify weaknesses and strengths for each based on findings from 1.1.1.

Target indicator:	(i) Specific definitions for each tool developed and weaknesses and strengths identified by month 6

(ii) Matrix indicating key mechanisms in place and specific components that will be strengthened to support obligations completed by month 6.

1.1.3:	Convene 3 workshops on identified tools, gaps & weaknesses for at least 60 participants on all Rio Convention Focal Points and relevant stakeholders, inclusive key implementing agencies.

Target indicator:	Rio Convention Focal Points and stakeholders awareness raised on specific weaknesses (and strengths) of tools and areas that require strengthening to inform the design of a consolidated environmental monitoring programme completed by month 8.

1.1.4:	Design a multi-sector & multi-agency monitoring programme that consolidates all environmental monitoring under different MNRE divisions, Rio Convention Focal Points and other agencies.

Target indicator:	Operational multi-sector/multi-agency monitoring programme (M&E Framework components) for Rio Convention Focal Points and relevant agencies completed by month 12

1.1.5:	Convene a validation workshop for 1.1.4 and policy dialogues with relevant sector agencies (i.e., water and sanitation, infrastructure and energy, agriculture, and tourism) to promote and facilitate institutionalization of consolidated multi-sector/multi-agency environmental monitoring programme.

Target indicator:	(i) Targeted workshop questionnaire show raised awareness of Rio Convention Focal Points and stakeholders on how to implement consolidated monitoring programme for Rio Convention implementation, monitoring and reporting completed by month 11

(ii) At least 2 sector agency work programmes show integration of consolidated environmental monitoring programme by month 14

Output 1.2:	Training on best practice approaches to implement Rio Conventions

- This output focuses on strengthening technical capacities and capabilities of individuals within key ministries and agencies but specifically the MNRE which leads the implementation of the three Rio Conventions and other relevant MEAs.

- Activities:

1.2.1:	Develop training plan (to be linked to MNRE Capacity Needs 2013) with targeted objectives and learning outcomes for different stakeholders.  This activity is to be undertaken in parallel with Activities 1.1.3 and 1.1.5.

Target indicator: 	Strategic training plan(s) building on existing MNRE Capacity Needs 2013, listing specific learning outcomes for each required training & workshop completed by month 8

1.2.2:	Conduct trainings for MNRE staff including Rio Convention Focal Points on consolidated environmental monitoring programme developed in Activity 1.1.4.

Target indicator:	At least three (3) in-house trainings for 60 participants (20 staff @ from Rio Convention FP sections, per training) of the MNRE on how to implement the consolidated environmental monitoring programme completed by month 12

1.2.3:	Conduct national training for all Rio Convention implementing agencies and communities as follow-on from Activity 1.2.2.

Target indicator:	At least three (2) trainings for 60 participants of the Rio Convention implementing agencies and communities completed by month 24

1.2.4:	Produce training and workshop reports (information from pre & post questionnaires used as baseline data).

Target indicator:	Reports of trainings and workshops undertaken under Outputs 1.1 – 1.3 completed by month 24

Output 1.3:	Strengthened environmental legal instruments & associated policies and legal frameworks

- Activities included in this output include a review of five (5) existing environmental legislation related to the Rio Conventions, and six (6) related policies and frameworks to ascertain which that require updating and or new ones developed to accommodate for the effective implementation of Rio Convention and other MEAs.  These activities are undertaken in parallel with, and in close collaboration with, other GEF projects (LDCF Economy Wide project; GEF/UNDP Strengthening Multi-sectoral Management of Critical Landscapes (SMSMCL) project) with similar initiatives and activities.  This component will require identification of gaps in the existing environmental legislation, policies and legal frameworks to identify areas of weakness and facilitate appraisal and approval of revisions by Government.

Activities:

1.3.1:	Undertake an in-depth SWOT and gap analysis of existing legal instruments and policies to meeting and sustaining Rio Convention obligations.   This activity will be undertaken in parallel with activities 1.1.1-1.1.2

Target indicator:	In-depth analysis of legal instruments drafted by month 6 and completed by month 8

Target indicator:	Independent peer review of the analysis by ten (10) independent peer reviewers completed by month 7

1.3.2:	Convene consultation workshops within MNRE and relevant stakeholders to present analyses and findings. Activity undertaken in parallel with Activities 1.1.3 - 1.1.5 as well as Activities 1.2.2 and 1.2.3

Target indicator:	(i) 3 workshops targeting 90 participants from MNRE and enforcement/legal authorities (Police, MAF, MJCA) completed by month 24

(ii) 3 workshops targeting 90 Village Council Chiefs from both Savaii and

Upolu completed by month 24

(iii) Workshop questionnaire analysis show awareness of MNRE and enforcement/legal authorities (Police, MAF, and MJCA) and community enforcement authorities of specific legislation, frameworks and policies relevant to the Rio Conventions is improved by month 24

1.3.3:	Revise (or enact new) legal instruments and policies according to guidance from Activities 1.3.4 and in collaboration with Activities 1.1.2, 1.1.4 – 1.1.5.

Target indicator:	(i) No less than two (2) legal instruments submitted to government/parliament for consideration by month 30.

(ii) Approved, revised and/or new legislation, frameworks and policies by month 33.

(iii) Publication of Convention Laws – Rio Conventions by month 24.

Component 2:  Public Awareness-raising and Information Management

Outcome 2:	Raised public support and understanding of Rio Conventions

- This component will develop and implement a broad-based public awareness campaign to raise the level of public support to the goal and objectives of the project, focusing on promoting an understanding of Rio Convention issues and the roles the communities play in the effective implementation of the Rio Conventions.  It will also establish a centralized data and information management system upon which Components 1 and 3 will be extracting data and information from to guide the development of interventions required on the national level, to understand, mainstream and integrate Rio Conventions obligations.

Output 2.1:	Centralized knowledge & information facility established (Data, Knowledge & Information Facility – DKIF) to collect, manage, share and disseminate knowledge and information on Rio Conventions

- This output will include a number of activities to strengthen the existing data and information management system, much of which are scattered around the 12 divisions of the MNRE.  A database for each Rio Convention area exists however, there is no centralized system, policies nor protocols that can extract and analyze data required for baselines and indicators to meet Rio Convention and other MEA obligations.  The fragmentation of data requires this output to integrate existing databases into an improved centralized data management facility to better coordinate identification, collection, storage and sharing of information on the Rio Conventions.  The centralized proposed DKIF also contributes to the empowerment of the MNRE to effectively monitor and comply with Rio Convention obligations.

Activities:

2.1.1:	Identify and secure national knowledge management and communications, data and statistical experts (in partnership with SBS).

Target indicator:	 National knowledge management and communications and statistical data experts (2) identified and procured completed by month 4.

2.1.2:	Conduct assessment of existing information management system and processes to identify synergies, gaps, and overlaps.  Identify key information gaps (e.g. indicators) in SOE required to feed into monitoring of implementation of Rio Conventions & other MEAs.  Activity undertaken in parallel with 1.1 – 1.5

Target indicator:	(i) Assessment report detailing institutional structure, systems and mechanisms for managing data, information & knowledge as well as recommendations on priority capacity development activities at the systemic, institutional and technical levels completed by month 6.

(ii)  Gaps in SOE identified and appropriate recommendations completed by month 6

2.1.3:	Convene workshops for MNRE (Rio Convention Focal Points and division staff) and other Rio Convention implementing agencies to present findings and recommendations for feedback, guidance and validation.

Target indicator:	2 Workshops for at least 60 participants completed by month 7.  Workshops conducted to present findings and recommendations specifically focusing on Rio Convention Focal Points and MNRE.

2.1.4:	Design integrated, synergized, centralized DKIF based on analysis & feedback from workshops (including technological hardware & software requirements).

Target indicator:	Design (including ‘architectural’ drawing of system network etc.) of fully dynamic DKIF (including technological infrastructure, hardware and software) for peer review by month 8, approved by month 10 for implementation by month 12.

2.1.5:	Develop manuals, policies, protocols and parameters for DKIF, MNRE and other relevant stakeholders on data gathering, analysis, collection, sharing

Target indicator:	DKIF operational manuals, policies, protocols and parameters produced for peer review by month 14, approved by month 16 for implementation by month 18

2.1.6:	Procure and install hardware & software for DKIF based on trials, feedback.

Target indicator:	Equipment, hardware and software purchased and installed by month 14.  Centralized integrated database & system fully operational by month 18

2.1.7:	Conduct training for MNRE (Rio Convention Focal Points) and divisional staff, implementing agencies (Environmental Focal Contacts), communities and stakeholders on use of DKIF for environmental monitoring, reporting and data sharing

Target indicator:	(i) Intensive targeted training for 5 MNRE data entry personnel completed by month 14.

(ii) Intensive targeted training for at least 30 relevant stakeholders (data owners, creators, keepers) via Ministries/Corporations completed by month 15

2.1.8:	Initiate collection of information &knowledge for DKIF (from Components 1-3) and create link to MNRE Website (searchable online) and other relevant implementing and partner agencies (national, regional and/or international)

Target indicator:	Targeted platforms showing analyzed and integrated reports of Samoa’s Rio Convention obligations by month 24.  Improved MNRE website hosting relevant Rio Convention information from CBD, CCD and FCCC Focal Points by month 30

Output 2.2:	Raised public awareness and support through national campaign on Rio Conventions

- Components 1 and 3 will be complemented by this output that will include a number of activities targeted towards raising awareness and support of the public through a broad-based awareness campaign.  The activities target not just members of the community but as well partner government agencies and include workshops and seminars (undertaken in Components 1 and 3), printed media, and roadshows.

Activities:

2.2.1:	Develop an integrated campaign plan in line with Outputs 1 and 3

Target indicator:	Integrated campaign plan completed by month 6 and at least two (2) sector plans identified in 1.1.5 show coordinated approach to implementing Rio Conventions through raised awareness (through national workshops, trainings  undertaken in 1.2.3, 1.3.4) by month 30

2.2.2:	Develop simple fact sheets/brochures (bilingual) explaining importance of meeting Rio obligations and make available through 2.1.8 as well as 2.2.3.

Target indicator:	Targeted survey results show at least 20% (from a baseline of 0) rise in understanding of local communities of importance of meeting Rio Convention obligations.  Survey completed by month 26, and released for publishing and sharing by month 30.

2.2.3:	Conduct national roadshow involving Rio Convention Focal Points and implementing agencies (MESC) targeting schools and communities contributing to the implementation of Rio Convention obligations.

Target indicator:	(i) At least four (4) roadshows (2xSavaii, 2xUpolu) completed by month 24

(ii) National quiz competitions show at least 40% (from a baseline of 0) rise in understanding of Rio Convention obligations by month 30.

(iii) Annual school environment debates show at least 40% (from a baseline of 0) increase in understanding of Rio Convention obligations by month 30

Component 3:  Mainstreaming Rio Conventions into Development Sectors

Outcome 3:  Development plans and programmes address implementation of Rio Conventions at national and sectoral level

- While Component 1 focused effectively on building and strengthening capacities of the ministry responsible for the three Rio Conventions (all relevant staff, not just the Focal Point person), the final component focuses on strengthening and improving opportunities to address the implementation of Rio Conventions on the national level through sector plans and programmes, as well as the national development strategy, programmes and plans.  The SDS 2012-2016 already shows environment as a priority area, however, this output and activities will look at further mainstreaming Rio Conventions so they are contained within national and sectoral plans from an operational perspective.  This component will drive the cascading of Rio Conventions into the corporate plan level as this is the actual level tied to Samoa’s economic and development planning cycle, and directly linked to Performance Budgeting.

Output 3.1:	Integration of Rio Conventions in the Samoa SDS 2017-2021 and in other national strategic frameworks

Activities:

3.1.1:	Identification of national priorities to support the Rio Conventions and mainstreamed to coincide with mid-term review of SDS and sector plans.  This activity will be undertaken in collaboration with Output 1.3, Activities 1.1.6, 1.2.2, and 2.2.3.

Target indicator:	 Economic Policy & Planning (MOF EPPD), mid-term review of national and sector plans show consideration by month 24 and integration of Rio Conventions by month 33

3.1.2:	Develop links in the national MTEF and institutional arrangements for implementation of Rio Conventions

Target indicator:	Revised MTEF showing operational and financial arrangements integrated into the current system for the implementation of Rio Conventions by month 33

3.1.3:	Convene targeted workshop for central agencies (MOF), line ministries (MAF, MOH, STA, MWCSD, and MESC), corporations (LTA, MWTI), private sector and communities on mainstreaming Rio Conventions.

Target indicator:	Workshop for partner/implementing agencies completed by month 12.  At least four (4) agency work programmes integrating Rio Convention obligations by month 24

Output 3.2:	Identified and addressed capacity gaps for mainstreaming Rio Conventions in four relevant sectors

Activities:

3.2.1:	Conduct an in-depth review of status of Rio Convention implementation for all relevant sectors (including community) identified in NESP.

Target indicator:	Desk review completed by month 16 and at least four (4) relevant sectors shows improved implementation status of Rio Conventions by month 33.

3.2.2:	Address identified gaps in four relevant sector plans, using knowledge gained from Activities 1.1.4-1.1.5, 1.2.2, 1.3.1 and 3.2.1.  This activity will involve the convening of workshops and working group meetings, structured as learn-by-doing exercises, with widespread participation of government staff from across various planning agencies involved in the drafting of sectoral development plans.

Target indicator:	Rio Convention obligations integrated into four (4) sector plans by month 30.

Output 3.3:	Strengthened National & Sectoral capacity on monitoring and reporting obligations of Rio Conventions and other MEAs

Activities:

3.3.1:	Identify and secure an M&E expert for Rio Conventions (to work across Outcomes 1 and 3).

Target indicator:	 National independent M&E specialist identified and procured completed by month 6.

3.3.2:	Develop a monitoring framework to track progress of Rio Conventions & other MEAs.  Activity undertaken in parallel with Outputs 1.2 and 1.3.

Target indicator:	Integrated M&E framework developed by month 7, peer review completed by month 9, approved by month 10 and trialed during 1.2.2, 1.2.3, 1.3.2-1.3.3 for implementation by month 12.

3.3.3:	Organize and conduct targeted training on monitoring & evaluation and reporting obligations (tools) of Rio Conventions and other MEA for relevant stakeholders.  Activity to feed into collaborating activities 3.2.1 and 3.2.2).

Target indicator:	At least four (4) trainings conducted on integrated approach towards monitoring and reporting obligations completed by month 20.

3.3.4:	Prepare reports of all trainings conducted and make available through Outcome 2

Target indicator:	All reports produced by Output 3 available online through MNRE website and other relevant national, regional and international platforms

## C.3	Sustainability, Replicability, and Lessons Learned

### C.3.a	Sustainability

- The project builds primarily upon existing institutional structure and mandates of the government agencies and as per expressed policies of the government.  This is expected to be sustainable as long as participants find the analysis and trainings informative, practical and applicable to their respective roles in the implementation of the Rio Convention obligations.  Hence the critical need to ensure the main driving organization’s capacities (institutional, systemic and individual) are strengthened to better service and raise awareness of all stakeholders, on Rio Conventions and other relevant MEAs.  No extra investments are envisaged to maintain the institutional structures by the government post project completion.  The capacity building of government staff and others are expected to be institutionalized within the MNRE and continued with the government’s funds.  Securing the institutional sustainability of the project’s impacts will be promoted by developing the technical capacities at relevant levels, in all the participating institutions.

- The sustainability of the project will also be strengthened not only by the Project Board, but also by the involvement of the NESP Advisory Committee (NESPAC) that will provide close follow-up to how the Rio Convention obligations are effectively implemented through existing environmental legislation, and provide the high-level oversight to facilitating the appropriate reforms to ensure long-term implementation.  The NESPAC is indeed a critical feature of this project’s sustainability, as it represents the best opportunity for mobilizing political commitment to sustain the project’s momentum after project closure.  Project sustainability will also require the long-term support of project champions, as well as ensuring that a sufficient critical mass of stakeholders remains committed and supportive of the project’s strategy.

- A third critical feature of the project’s sustainability lies in the project’s cost-effective strategy.  By seeking to use existing government structures, staff and environment and related natural resource management legislation to implement Rio Convention obligations, by targeting current weaknesses in their monitoring and compliance, this project builds upon an existing strong baseline of legislation and national institutional capacities.

### C.3.b	Replicability and Lessons Learned

- The project has been designed to ensure that its actions can be widely replicated within Samoa.  The cost-effectiveness, as well as institutional, social and environment sustainability inherent in the design of the project, is expected to contribute to the replication of the project’s approaches.

- As a medium-size project, this intervention has certain limitations, namely in being able to reconcile and undertake all the necessary legislative reforms identified as needed during project implementation.  Instead, this project serves as catalyst of a more long-term approach to Rio Convention implementation by creating a set of institutional arrangements, negotiating improvements to the existing procedures of environmental legislation monitoring and compliance, and building up a strong baseline of technical capacities.  Part of the catalytic role of the project is to demonstrate the value of this approach.

- During early project implementation, the Project Board (Steering Committee) will approve the selection of a targeted set of environmental and natural resource management legislation to be tested.  It will also approve a selected set of recommendations to be piloted.  These specific activities will be constructed as a set of technical workshops, regional and stakeholder consultations, policy dialogues and negotiating meetings, and drafting of appropriate legislative and institutional reforms.  Together, they aim to remove contradictions among the multiple sets of legislation, reduce, if not remove, counter-productive institutional authorities and responsibilities, and undertake targeted trainings and awareness-raising activities.

- The replication of project activities is further strengthened by the project implementation arrangements, which will involve numerous stakeholder representatives.  The involvement of NGOs and the private sector and others in the project activities and through the coordination mechanisms is also expected to lead to further replication of the project’s actions in Samoa.  Research and academic institutions are also playing a leading role in identifying new and innovative interpretations and policy responses to improve environmental management.

- Replication will also be supported by raising the awareness of the project throughout Samoa.  The series of public and awareness dialogues with stakeholders is central to ensuring that lessons are actually learned, and that the country as a whole moves forward with incremental improvements on meeting Rio Convention obligations within the framework of national sustainable development.  As more and more people understand the critical linkages between the global environment and local actions, they will be able to take more informed decisions and thereby popularizing the project with the public, generating greater support and demand for replication activities.

- In addition, the close links the project will have with the GEF LDCF Economy-wide project, the GEF SMSMCL project, and other Pacific regional programmes through SPREP, PIFS, SPC and others will also facilitate sharing of lessons between the participating Pacific countries, allowing possible replication of approaches to other neighboring Pacific island countries.

## C.3	Stakeholder Involvement

- This project was developed on the basis of consultations with a number of stakeholder representatives, both during the development of the PIF and the development of the present project document.  The preliminary consultations identified the major stakeholders and partners, inclusive coordination mechanisms, who will be involved.  These identified stakeholders, each with their own particular comparative advantage, will ensure a holistic approach to the integration of global environmental priorities into national development frameworks.  Taking an adaptive and collaborative management approach to execution, the project will ensure that key stakeholders are involved early and throughout project execution as partners for development.  This includes contributing to the identification and development of strategic policy and programmatic gaps to meet Rio Convention objectives, as well as to both deliver and receive training to better understand and operationalise integrated global/national environmental and development strategies, programmes and plans.  It also includes participation in the Project Board (Steering Committee) as well as the Technical Working Groups, review of project outputs such as recommendations for amendments to policies, plans, programmes and legislation, as well as participation in monitoring activities.

- Given the project strategy, the key project stakeholders are government ministries (central and line ministries) and state owned enterprises (corporations) who play a critical role and are mandated to oversee and guide implementation and compliance with key environmental legislation.  These stakeholder representatives will participate in activities to negotiate the improved interpretation of environmental and natural resource legislation, which is structured as learn-by-doing exercises.  The sector coordination committees will also be involved in the mainstreaming of Rio Conventions into Samoa’s SDS.  In addition to these governmental stakeholders, there are state owned enterprises from academia, the private sector, civil society organizations and community-based organizations.  During the establishment of technical working groups on the three Rio Conventions, these non-state organizations will also be invited in the project activities to share their comparative expertise, but also to undertake selected project activities.

- In addition to the above, a key group of stakeholders are the parliamentarians that make policy decisions and who will be responsible for approving integrated environmental legislation.  The project will carry out structured awareness-raising dialogues to raise and strengthen the support of parliamentarians to the concept and strategy of integrated approach to meeting global environment (Rio Conventions) and national socio-economic development priorities.

- Particular attention will be given to address issues of gender equality, and will be guided by the GEF’s Policy on Gender Mainstreaming.  Gender issues will also be reviewed as part of UNDP’s Environmental and Social Screening Checklist.  A criterion of stakeholder participation in project activities will be to explain the extent to which efforts were made and realized to ensure gender balance, and will be specifically reported as part of the Quarterly Operational Reporting procedures, as well as in the annual Project Implementation Review that is reported to the GEF Secretariat.

- Participants of the validation workshop further strengthened the intervention points identified during the development of the PIF and the project document in terms of the crucial need for institutional strengthening through a centralized DKIF.  The DKIF would provide for proper inventorying, management, extraction and analysis of data which will contribute to awareness-raising activities of the project.  The DKIF will also play a vital role in validating data which will be utilized by all project components to better inform national and sectoral policies and plans, in the implementation of the Rio Conventions across the nation.   In order for this project to be implemented successfully, the stakeholders further affirmed the need for parliamentarians to be fully conversant on Rio Conventions and other international conventions Samoa is a party to.  This would be achieved through the proposed awareness-raising dialogues, trainings and workshops specifically targeting parliament committees on environment and international conventions.

- Key stakeholders include: Ministry of Foreign Affairs & Trade, Ministry of Finance, Ministry of Natural Resources & Environment, Ministry of Agriculture & Fisheries, Ministry of Communication, Information & Technology, Ministry of Education, Sports & Culture, Ministry of Health, Ministry of Women, Social & Community Development, Samoa Water Authority, Samoa Tourism Authority, Scientific Research Organization of Samoa (SROS), Electric Power Corporation (EPC), Fire & Emergency Services Authority, National University of Samoa, and University of the South Pacific (USP).  Section B.2.d above outlined the roles and responsibilities of key stakeholder institutions.

## C.4	Monitoring and Evaluation

- Project monitoring and evaluation will be conducted in accordance with established UNDP and GEF procedures.  The project team and the UNDP Multi-Country Office (UNDP MCO) will undertake monitoring and evaluation activities, with support from UNDP/GEF, including by independent evaluators in the case of the final evaluation.  The logical framework matrix in Annex 2 provides a logical structure for monitoring project performance and delivery using SMART indicators during project implementation.  The output budget and the work plan in the UNDP project document provide additional information for the allocation of funds, both the GEF and co-financing, for expected project deliverables and the timing of project activities to produce these deliverables.  Annex 3 provides a breakdown of the total GEF budget by outcome, project management costs, and allocated disbursements on a per year basis.  A GEF tracking tool for CCCD will be used as part of monitoring and evaluation activities to assess project delivery.  The work plan is provisional, and is to be reviewed during the first project board and endorsed at the project inception workshop.

- The project’s monitoring and evaluation approach will be discussed during the project’s initiation meeting so as to fine-tune indicators and means of verification, as well as an explanation and full definition of project staff M&E responsibilities.

- A project inception workshop will be conducted within the first 2 months of project start with the full project team, National Project Director, relevant government counterparts, co-financing partners, the UNDP MCO, with representation from the UNDP/GEF Regional Coordinating Unit as appropriate.  Non-governmental stakeholders will also be represented at this workshop.

- A fundamental objective of this inception workshop will be to further instill understanding and ownership of the project’s goals and objectives among the project team, government and other stakeholder groups.  The workshop also serves to finalize preparation of the project’s first annual work plan on the basis of the project’s log-frame matrix.  This will include reviewing the log frame (indicators, means of verification, assumptions), imparting additional detail as needed, and on the basis of this exercise, finalize the Annual Work Plan (AWP) with precise and measurable programme, output, and process indicators, and in a manner consistent with the expected outcomes for the project.

- Specifically, the project inception workshop will: (i) introduce project staff to the UNDP/GEF expanded team that will support the project during its implementation, namely the CO and responsible Project Management Unit (PMU) staff; (ii) detail the roles, support services and complementary responsibilities of UNDP MCO and PMU staff with respect to the project team; (iii) provide a detailed overview of UNDP/GEF reporting and monitoring and evaluation (M&E) requirements, with particular emphasis on the combined Annual Project Reports - Project Implementation Reviews (APR/PIRs), Project Board meetings, as well as final evaluation.  The inception workshop will also provide an opportunity to inform the project team on UNDP project-related budgetary planning, budget reviews, and mandatory budget re-phasing.

- The inception workshop will also provide an opportunity for all parties to understand their roles, functions, and responsibilities within the project’s decision-making structures, including reporting and communication lines, and conflict resolution mechanisms.  A Terms of Reference for PMU staff and associated decision-making structures will be discussed, in order to clarify for all, each party’s responsibilities during the project’s implementation phase.

- The inception workshop will present a schedule of M&E-related meetings and reports.  The Project Manager in consultation with UNDP will develop this schedule, and will include: (i) tentative time frames for Project Board meetings, and the timing of near-term project activities, such as the in-depth review of environment legal instruments, policies and frameworks; and (ii) project-related monitoring and evaluation activities.  The provisional work plan will be approved in the first meeting of the Project Board.

- A project initiation report will be prepared immediately following the inception workshop.  This report will include a detailed First Year Work Plan divided in quarterly time-frames as well as detailed activities and performance indicators that will guide project implementation (over the course of the first year).  This Work Plan will include the proposed dates for any visits and/or support missions from the UNDP MCO, the UNDP/GEF Regional Coordinating Unit, or consultants, as well as time-frames for meetings of the project decision-making structures (e.g., Project Board).  The report will also include the detailed project budget for the first full year of implementation, prepared on the basis of the Annual Work Plan, and including any monitoring and evaluation requirements to effectively measure project performance during the targeted 12 months’ time-frame.

- The initiation report will include a more detailed narrative on the institutional roles, responsibilities, coordinating actions and feedback mechanisms of project related partners.  In addition, a section will be included on progress to date on project establishment and start-up activities and an update of any changed external conditions that may affect project implementation, including any unforeseen or newly arisen constraints.  When finalized, the report will be circulated to project counterparts who will be given a period of one calendar month in that to respond with comments or queries.

- Quarterly Progress Reports are short reports outlining the main updates in project performance, and are to be provided quarterly to the UNDP MCO. The MCO will provide guidelines for the preparation of these reports, which will be shared with the UNDP/GEF RCU.

- Progress made shall be monitored in the UNDP Enhanced Results Based Management Platform.

- Based on the initial risk analysis submitted, the risk log shall be regularly updated in ATLAS.  Risks become critical when the impact and probability are high.  Note that for UNDP GEF projects, all financial risks associated with financial instruments such as revolving funds, microfinance schemes, or capitalization of Energy Service Corporations are automatically classified as critical on the basis of their innovative nature (high impact and uncertainty due to no previous experience justifies classification as critical).

- Based on the information recorded in Atlas, a Project Progress Reports (PPR) can be generated in the Executive Snapshot.

- Other ATLAS logs can be used to monitor issues, lessons learned.  The use of these functions is a key indicator in the UNDP Executive Balanced Scorecard.

- Monitoring will occur through Project Board meetings. This is the highest policy-level meeting of the parties directly involved in the implementation of a project.  The project will be subject to Project Board meetings at least twice per year. The first such meeting will be held within the first twelve months following the inception workshop.  For each year-end meeting of the Project Board, the Project Manager will prepare harmonized Annual Project Report / Project Implementation Reviews (APR/PIR) and submit it to UNDP MCO, the UNDP/GEF Regional Coordination Unit, and all Project Board members at least two weeks prior to the meeting for review and comments.

- The APR/PIR will be used as one of the basic documents for discussions in the Project Board year-end meeting.  The Project Manager will present the APR/PIR to the Project Board members, highlighting policy issues and recommendations for the decision of the Committee participants.  The Project Manager will also inform the participants of any agreement(s) reached by stakeholders during the APR/PIR preparation, on how to resolve operational issues.  Separate reviews of each project output may also be conducted, as necessary.  Details regarding the requirements and conduct of the APR and Project Board meetings are contained with the M&E Information Kit available through UNDP/GEF.

- The combined Annual Project Report (APR) and Project Implementation Review (PIR) is a UNDP requirement and part of UNDP’s Country Office central oversight, monitoring and project management.  As a self-assessment report by project management to the Country Office, the APR/PIR is a key input to the year-end Project Board meetings.  The PIR is an annual monitoring process mandated by the GEF.  It has become an essential management and monitoring tool for project managers and offers the main vehicle for extracting lessons from on-going projects.  These two reporting requirements are very similar in input, purpose and timing that they have now been amalgamated into a single APR/PIR Report.

- An APR/PIR is to be prepared on an annual basis by June, but well in advance (at least one month) in order to be considered at the Project Board meeting.  The purpose of the APR/PIR is to reflect progress achieved in meeting the project’s Annual Work Plan and assess performance of the project in contributing to intended outcomes through outputs and partnership work.  The APR/PIR is discussed by the Project Board, so that the resultant report represents a document that has been agreed upon by all of the key stakeholders.

- A standard format/template for the APR/PIR is provided by UNDP/GEF.  This includes the following:

- Progress made toward project objective and project outcomes - each with indicators, baseline data and end-of-project targets (cumulative)

- Project outputs delivered per project outcome (annual).

- Lesson learned/good practice.

- AWP and other expenditure reports

- Risk and adaptive management

- ATLAS QPR

- Portfolio level indicators (i.e., GEF focal area tracking tools) are used by most focal areas on an annual basis as well.

- UNDP will analyze the individual APR/PIRs by focal area, theme and region for common issues/results and lessons.  The APR/PIRs are also valuable for the independent evaluators who can utilize them to identify any changes in the project’s structure, indicators, work plan, among others, and view a past history of delivery and assessment.

- Day-to-day monitoring of implementation progress will be the responsibility of the Project Manager based on the project’s Annual Work Plan and its indicators.  The Project Manager will inform the UNDP MCO of any delays or difficulties faced during implementation so that the appropriate support or corrective measures can be adopted in a timely and remedial fashion.

- The Project Manager will fine-tune outcome and performance indicators in consultation with the full project team at the inception workshop, with support from UNDP MCO and assisted by the UNDP/GEF.  Specific targets for the first year implementation performance indicators, together with their means of verification, will be developed at the inception workshop.  These will be used to assess whether implementation is proceeding at the intended pace and in the right direction and will form part of the Annual Work Plan.  Targets and indicators for subsequent years would be defined annually as part of the internal evaluation and planning processes undertaken by the Project Team, and agreed with the Executing Agency (MNRE), among other key project partners sitting on the Project Board.

- Periodic monitoring of implementation progress will be undertaken by the UNDP MCO through the provision of quarterly reports from the Project Manager.  Furthermore, specific meetings may be scheduled between the PMU, the UNDP MCO and other pertinent stakeholders as deemed appropriate and relevant (particularly the Project Board members).  Such meetings will allow parties to take stock and to troubleshoot any problems pertaining to the project in a timely fashion to ensure smooth implementation of project activities.

- An independent final evaluation will take place three months prior to the terminal tripartite review meeting, and will focus on: a) the cost-effectiveness, efficiency and timeliness of project implementation and performance; b) highlight issues requiring decisions and actions; and c) present initial lessons learned about project design, implementation and management.  Findings of this evaluation will be incorporated as lessons learned, and recommendations for improvement addressed to ensure the institutional sustainability of project outputs, particular for the replication of project activities.  The final evaluation will also look at project outcomes and their sustainability.  The final evaluation should also provide recommendations for follow-up activities, as appropriate.  The terms of reference for the final evaluation will be prepared by the UNDP MCO based on guidance from the UNDP/GEF Regional Coordinating Unit, in consultation with the MNRE.

- During the last three months of the project, the PMU will prepare the Project Terminal Report.  This comprehensive report will summarize all activities, achievements and outputs of the project, lessons learned, the extent to which objectives have been met, structures and mechanisms implemented, capacities developed, among others.  Together with the independent final evaluation, the project terminal report is one of two definitive statements of the project’s activities during its lifetime.  The project terminal report will also recommend further steps, if necessary, in order to ensure sustainability and replicability of the project outcomes and outputs.

- The terminal review meeting is held by the Project Board, with invitation to other relevant Government and municipal stakeholders as necessary, in the last month of project operations.  The Project Manager is responsible for preparing the terminal review report and submitting it to UNDP MCO, the UNDP/GEF Regional Coordinating Unit, and all participants of the terminal review meeting.  The terminal review report will be drafted at least one month in advance of the terminal review meeting, in order to allow for timely review and to serve as the basis for discussion.  The terminal review report considers the implementation of the project as a whole, paying particular attention to whether the project has achieved its stated objectives and contributed to the broader environmental objective.  The report also decides whether any actions remain necessary, particularly in relation to the sustainability of project outputs and outcomes, and acts as a vehicle through that lessons learned can be captured to feed into other projects under implementation or formulation.  The terminal review meeting should refer to the independent final evaluation report, conclusions and recommendations as appropriate.

- The UNDP MCO, in consultation with the UNDP/GEF Regional Coordinator and members of the Project Board, has the authority to suspend disbursement if project performance benchmarks are not met as per delivery rates, and qualitative assessments of achievements of outputs.

Audit:

- The Project Manager will provide the UNDP Resident Representative with certified periodic financial statements and an annual audit of the financial statements relating to the status of UNDP (including GEF) funds according to the established procedures set out in UNDP’s Programming and Finance manuals.  The audit on project will be conducted according to UNDP financial regulations and rules and applicable audit policies.  The audit will be conducted by the legally recognized auditor of UNDP Samoa.

- Learning and knowledge sharing will be enhanced through the dissemination of project results within and beyond the project intervention zone through existing information sharing networks and forums.  The project will identify and participate, as relevant and appropriate, in scientific, policy-based and/or any other networks, which may be of benefit to project implementation though lessons learned.  The project will identify, analyze, and share lessons learned that might be beneficial in the design and implementation of similar future projects.  Finally, there will be a two-way flow of information between this project and other projects of a similar focus.

- Communications and visibility requirements: Full compliance is required with UNDP’s Branding Guidelines.  These can be accessed at http://intra.undp.org/coa/branding.shtml, and specific guidelines on UNDP logo use can be accessed at: http://intra.undp.org/branding/useOfLogo.html.  Amongst other things, these guidelines describe when and how the UNDP logo needs to be used, as well as how the logos of donors to UNDP projects needs to be used.  For the avoidance of any doubt, when logo use is required, the UNDP logo needs to be used alongside the GEF and SPREP logos.  The GEF logo can be accessed at: http://www.thegef.org/gef/GEF_logo.  The UNDP logo can be accessed at: http://intra.undp.org/coa/branding.shtml.

- Full compliance is also required with the GEF’s Communication and Visibility Guidelines (the “GEF Guidelines”).  The GEF Guidelines describe when and how the GEF logo needs to be used in project publications, vehicles, supplies and other project equipment.  The GEF Guidelines also describe other GEF promotional requirements regarding press releases, press conferences, press visits, visits by Government officials, productions and other promotional items.  Where other agencies and project partners have provided support through co-financing, their branding policies and requirements should be similarly applied.  The GEF Guidelines can be accessed at:

http://www.thegef.org/gef/sites/thegef.org/files/documents/C.40.08_Branding_the_GEF%20final_0.pdf.

Table 4:  M& E Work Plan and Budget

| Type of M&E activity | Responsible Parties | Budget US$ Excluding project team staff time | Time frame |
| --- | --- | --- | --- |
| Inception Workshop and Report | - Project Manager - UNDP Multi-Country Office - UNDP GEF | Indicative cost: 10,000 | Within first two months of project start up |
| Measurement of Means of Verification of project results. | - UNDP GEF RTA/Project Manager will oversee the hiring of specific studies and institutions, and delegate responsibilities to relevant team members. | To be finalized in Inception Phase and Workshop. | Start, mid and end of project (during evaluation cycle) and annually when required. |
| Measurement of Means of Verification for Project Progress on output and implementation | - Oversight by Project Manager - Project team | To be determined as part of the Annual Work Plan's preparation. | Annually prior to APR/PIR and to the definition of annual work plans |
| APR/PIR | - Project manager and team - UNDP Multi-Country Office - UNDP Regional Technical Advisor - UNDP Energy & Environment Group | None | Annually |
| Periodic status/ progress reports | - Project manager and team | None | Quarterly |
| Mid-term Evaluation | - Project manager and team - UNDP Multi-Country Office - UNDP Regional Coordinating Unit - External Consultants (i.e., evaluation team) |  | At the mid-point of project implementation. Not required for Medium Sized projects. |
| Final Evaluation | - Project manager and team, - UNDP Multi-Country Office - UNDP Regional Coordinating - External Consultants (i.e., evaluation team) | Indicative cost: 20,000 | At least three months before the end of project implementation |
| Project Terminal Report | - Project manager and team - UNDP Multi-Country Office - Local consultant | 0 | At least three months before the end of the project |
| Audit | - UNDP Multi-Country Office - Project manager and team | Indicative cost: 5,000 | At the end of the project |
| Visits to field sites | - UNDP Multi-Country Office - UNDP RCU (as appropriate) - Government representatives | For GEF supported projects, paid from IA fees and operational budget | Yearly |
| TOTAL indicative COST Excluding project team staff time and UNDP staff and travel expenses |  | US$ 35,000 (+/- 7% of total budget) |  |

# D.	Financing

## D.1	Financing Plan

- The financing of this project will be provided by the GEF, with co-financing from the UNDP TRAC.  The Government of Samoa is also providing substantial co-financing through in-kind assistance.  The allocation of these sources of finances is structured by the three main project components, as described in section C.2.b above.  Table 5 below details this allocation.

Table 5:  Project Costs (US$)

| Total Project Budget by Component | GEF ($) | Co-Financing ($) | Project Total ($) |
| --- | --- | --- | --- |
| Component 1: | 100,000 | 50,000 | 150,000 |
| Component 2: | 250,000 | 100,000 | 350,000 |
| Component 3: | 100,000 | 124,000 | 224,000 |
| Project Management | 50,000 | 226,000 | 276,000 |
| Total project costs | 500,000 | 500,000 | 1,000,000 |

| Project Management | Estimated Staff weeks | GEF ($) | Co-Financing UNDP ($) | Co-Financing Gov't ($) | Project Total ($) |
| --- | --- | --- | --- | --- | --- |
| Project Manager | 90 | 0 | 0 | 90,000 | 90,000 |
| Environmental Sector Coordinator | 80 | 0 | 0 | 45,000 | 45,000 |
| Monitoring and Evaluation Specialist | 65 | 0 | 50,000 | 0 | 50,000 |
| Internationally Evaluation Specialist | 3 | 20,000 | 0 | 5,000 | 25,000 |
| Office facilities and communications |  | 5,000 | 0 | 36,000 | 41,000 |
| Travel |  | 5,000 | 0 | 0 | 5,000 |
| Audit |  | 5,000 | 0 | 0 | 5,000 |
| Miscellaneous expenses, including cost recovery for UNDP support services |  | 15,000 | 0 | 0 | 15,000 |
| Total project management cost |  | 50,000 | 50,000 | 176,000 | 276,000 |

- An internationally recruited consultant will be contracted to undertake the independent final evaluation towards the end of the project.  Co-financing is mainly from in-kind assistance for staff that will be assisting the international consultant, as well as vehicle expenses (e.g., petrol).  The international consultant budget line includes the costs of airfares, DSA and fees for the international consultant.

Table 6:  Consultants for technical assistance components (estimated for entire project)

| Technical Assistance | Estimated Staff weeks | GEF ($) | Co-Financing ($) | Project Total ($) |
| --- | --- | --- | --- | --- |
| Environmental Lawyer (CBD) | 45 | 30,000 | 7,500 | 37,500 |
| Environmental Lawyer (CCD) | 40 | 30,000 | 7,500 | 37,500 |
| Environmental Lawyer (FCCC) | 45 | 35,000 | 10,000 | 45,000 |
| Data & Statistician Expert | 60 | 45,000 | 25,000 | 70,000 |
| KM & IT Communications Expert | 60 | 0 | 60,000 | 60,000 |
| Total | 250 | 140,000 | 110,000 | 250,000 |

## D.2	Cost Effectiveness

- The cost-effectiveness of this project lies largely in its design.  It does this by building upon a significant baseline and leveraged commitment and a legislative framework government environmental and natural resource management.  Mainstreaming Rio Conventions into national and sectoral policies, as well as strengthening of mechanisms and tools activities of the project will be implemented in parallel with other GEF and UNDP projects with similar interventions and activities.  It is cost-effective primarily through the project’s strategic and holistic approach at mainstreaming Rio Conventions within the sustainable development baseline of strengthening sectoral policies to meet socio-economic development priorities.  The financing of this project is also cost-effective in that the GEF contribution has leveraged an equal amount of resources as co-financing.

- The cost-effectiveness of the project also arises by the nature of the leveraging.  The Government of Samoa is providing significant co-financing in the order of US$ 400,000 towards project implementation, management, monitoring and evaluation.  Although all in-kind, a significant portion of this contribution is considered real financial resources, taking into account the significant investment of government staff to actively implement, manage and participate in project activities.  The project will be mainstreamed into daily operations of the MNRE through the use of a Project Director, Project Manager, project assistants and other staff, from within the existing, government approved structure of the MNRE.  These positions are ‘funded’ through Samoa’s in-kind assistance and are positions that will be maintained over the 3-year timeframe of the project. Samoa’s programmatic approach at managing this project ensures the project’s outputs and outcomes are sustained post-project, and that all activities are implemented in close parallel with, and or in partnership with other GEF projects currently being implemented in Samoa.  This approach makes for a streamlined and cost-efficient approach to sustainable development.  This process of mainstreaming from legislation to national to sectoral plans to corporate implementation plans and all the way into building the capacity of its people through community programmes shows the genuine commitment of the Government of Samoa towards implementing this project from a long-term, cost-effective perspective.  Table 7 below is an estimate of government staff contribution over the three years of project implementation.

Table 7:  In-kind contribution of government staff time to project activities

| Government Staff Contribution | Estimated Staff Weeks | Government in-kind (US$) |  |
| --- | --- | --- | --- |
| Project Manager | 90 | 90,000 |
| Environment Sector Coordinator | 80 | 45,000 |
| Principal Capacity Building Officer | 80 | 45,000 |
| Knowledge Management & IT Communications Expert | 60 | 60,000 |
| IT Officer | 80 | 40,000 |
| Total |  | 280,000 |

Table 8:  Project Costs (%age)

| Project Budget Component by Contribution type | Contribution (US$) | Percentage (%) |
| --- | --- | --- |
| Component 1: GEF | 100,000 | 10 |
| Component 1: Co-Financing | 50,000 | 5 |
| Component 2: GEF | 250,000 | 25 |
| Component 2: Co-Financing | 100,000 | 10 |
| Component 3: GEF | 100,000 | 10 |
| Component : Co-Financing | 124,000 | 12 |
| Project Management: GEF | 50,000 | 5 |
| Project Management: Co-Financing | 226,000 | 23 |
| Total | 1,000,000 | 100 |

## D.3	Co-financing

- The co-financing to this project is estimated at US$ 500,000, of which US$ 400,000 is in-kind assistance provided by the Government of Samoa.  The in-kind assistance from the Government of Samoa is considered co-financing as these funds represent real funds that are paid by the government to the Project Manager and other technical staff required for project implementation (US$ 280,000 over the three-year project, as estimated on table 7), as well as funds to pay for office costs such as transportation, electricity, servers, internet and venues for workshops and public awareness activities of the project (estimated as US$ 40,000 per year). UNDP is providing significant cash co-financing in the amount of US$ 100,000 to cover some of the project implementation costs.

Table 9:  Co-financing Sources

| Name of Co-financier | Classification | Type | Amount |  |
| --- | --- | --- | --- | --- |
|  |  |  | Confirmed (US$) | Unconfirmed (US$) |
| MNRE/Government of Samoa | Government | In-kind | 400,000 | 0 |
| UNDP TRAC | GEF Implementing Agency | Grant | 100,000 | 0 |
| Total Co-financing |  |  | 500,000 | 0 |

## D.4	Total GEF Work Plan and Budget

| Award ID: | 00078841 | Project ID: | 00088926 |
| --- | --- | --- | --- |
| Award Title: | Capacity for Implementing Rio Conventions in Samoa |  |  |
| Business Unit: | WSM10 |  |  |
| Project Title: | Capacity for Implementing Rio Conventions in Samoa |  |  |
| PIMS no: | 4938 |  |  |
| Implementing Partner (Executing Agency) | Ministry of Natural Resources and Environment (MNRE) |  |  |

| GEF Outcome/Atlas Activity | Responsible Party/ Implementing Agent | Fund ID | Donor Name | Atlas Budgetary Account Code | ATLAS Budget Description | Amount Year 1 (USD) | Amount Year 2 (USD) | Amount Year 3 (USD) | Total (USD) | Budget Notes |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| OUTCOME 1 The Rio Conventions are more effectively implemented through national planning frameworks that are supported by best practice tools and institutional arrangements | UNDP | 62000 | GEF | 71300 | Local Consultants | 30,500 | 19,500 | 0 | 50,000 | 1 |
|  |  |  |  | 75700 | Trainings, workshops and conferences | 15,000 | 15,000 | 20,000 | 50,000 | 2 |
|  |  |  |  |  | Sub-total GEF | 45,500 | 34,500 | 20,000 | 100,000 |  |
|  |  | 04000 | UNDP | 71300 | Local Consultants | 5,000 | 5,000 | 5,000 | 15,000 | 3 |
|  |  |  |  |  | Sub-total UNDP | 5,000 | 5,000 | 5,000 | 15,000 |  |
|  |  |  |  |  | Total Outcome 1 | 50,500 | 39,500 | 25,000 | 115,000 |  |
| OUTCOME 2 Raised public support and understanding of Rio Conventions | MNRE | 62000 | GEF | 71300 | Local Consultants | 76,000 | 24,000 | 0 | 100,000 | 1 |
|  |  |  |  | 72100 | Contractual services: Companies | 100,000 | 50,000 | 0 | 150,000 | 4 |
|  |  |  |  |  | Sub-total GEF | 176,000 | 74,000 | 0 | 250,000 |  |
|  |  | 04000 | UNDP | 71300 | Local Consultants | 6,000 | 6,000 | 6,000 | 18,000 | 3 |
|  |  |  |  |  | Sub-total UNDP | 6,000 | 6,000 | 6,000 | 18,000 |  |
|  |  |  |  |  | Total Outcome 2 | 182,000 | 80,000 | 6,000 | 268,000 |  |
| OUTCOME 3 Development plans and programmes address implementation of Rio Conventions at national and sectoral level | MNRE | 62000 | GEF | 71300 | Local Consultants | 26,000 | 23,000 | 11,000 | 60,000 | 1 |
|  |  |  |  | 75700 | Trainings, workshops and conferences | 10,000 | 10,000 | 0 | 20,000 | 2 |
|  |  |  |  | 74200 | Printing and publishing | 10,000 | 5,000 | 5,000 | 20,000 | 5 |
|  |  |  |  |  | Sub-total GEF | 46,000 | 38,000 | 16,000 | 100,000 |  |
|  |  | 04000 | UNDP | 71300 | Local Consultants | 6,000 | 6,000 | 5,000 | 17,000 | 3 |
|  |  |  |  |  | Sub-total UNDP | 6,000 | 6,000 | 5,000 | 17,000 |  |
|  |  |  |  |  | Total Outcome 3 | 52,000 | 44,000 | 21,000 | 117,000 |  |
| Project Management | MNRE | 62000 | GEF | 71200 | International consultants | 0 | 0 | 20,000 | 20,000 | 6 |
|  |  |  |  | 71300 | Local consultants | 2,000 | 1,500 | 1,500 | 5,000 | 11 |
|  |  |  |  | 71600 | Travel | 0 | 0 | 5,000 | 5,000 | 7 |
|  |  |  |  | 74100 | Professional Services | 0 | 0 | 5,000 | 5,000 | 8 |
|  |  |  |  | 74599 | UNDP cost recovery chrgs-Bills | 5,500 | 4,500 | 5,000 | 15,000 | 9 |
|  |  |  |  |  | Sub-total GEF | 7,500 | 6,000 | 36,500 | 50,000 |  |
|  |  | 04000 | UNDP | 71300 | Local Consultants | 15,000 | 20,000 | 15,000 | 50,000 | 10 |
|  |  |  |  |  | Sub-total UNDP | 15,000 | 20,000 | 15,000 | 50,000 |  |
|  |  |  |  |  | Total Project Management | 22,500 | 26,000 | 51,500 | 100,000 |  |
| Total GEF funds |  |  |  |  |  | 275,000 | 152,500 | 72,500 | 500,000 |  |
| Total UNDP Funds |  |  |  |  |  | 32,000 | 37,000 | 31,000 | 100,000 |  |
| Project total |  |  |  |  |  | 307,000 | 189,500 | 103,500 | 600,000 |  |

| Source of funds | Amount Year 1 (USD) | Amount Year 2 (USD) | Amount Year 3 (USD) | Total (USD) |
| --- | --- | --- | --- | --- |
| GEF | 275,000 | 152,500 | 72,500 | 500,000 |
| UNDP | 32,000 | 37,000 | 31,000 | 100,000 |
| Government of Samoa | 125,000 | 125,000 | 150,000 | 400,000 |
| Total | 432,000 | 314,500 | 253,500 | 1,000,000 |

Budget Notes:

1	GEF financing for three (3) local specialists

2	GEF financing for workshop, training and conferences expenses

3	UNDP will finance local consultant on data and statistical management

4	Activities in Outcome 2 may require the support of a company to design the DKIF

5	GEF financing for printing and publishing activities related to workshops, trainings or other activities

6	GEF will finance the cost of an international consultant to conduct terminal evaluation

7	Travel cost

8	Audit fees

9	This may include, among other things, communications and/or cost recovery for support services, if required by the IP, as per UNDP and GEF policies. DPCs will be charged according to LoA (Annex 8).

10	UNDP will finance Local Consultants including M&E Specialist under Project Management

11	Communication and/or other support services

# E.	Institutional Coordination and Support

## E.1	Core Commitments and Linkages

E.1.a	Linkages to other activities and programmes

- The key initiatives that this project will coordinate activities with include a number of development projects underway in Samoa, a few of which are directly relevant and complementary to this project.  Some of these key initiatives include GEF and LDCF funded initiatives.

- UNDP is currently implementing a number of projects that complement this Rio Convention Mainstreaming project, and with which activities will be closely coordinated to ensure no overlap or duplication, as well as to foster synergies, as appropriate.  For example, a number of these projects include workshops and seminars where many of the participants would be the same as those likely to be invited to the workshops and seminars under the Rio Convention Mainstreaming project.  The majority of these projects also fall under the same or similar project implementation and management arrangements as detailed in Section E.  In such instances, the project will explore options of convening workshops back-to-back with these other complementary projects and maximize the benefit of having the same or similar coordination mechanisms under which these projects are implemented and managed.  Such opportunities would be explored on a case-by-case basis.  The key projects include:

- The UNDP-LDCF Integrating Climate Change Risks into the Forestry Sector in Samoa is supporting the Government of Samoa (GoS) to strengthen institutional capacities to systematically identify and address the climate change-driven risks for the management of native forests and agroforestry areas, in order to increase the resilience of rural communities and protect their livelihoods from dynamic climate-related damage.  The activities of this project also have strong links with the UNEP-GEF regional project on invasive species management and the GEF-FAO multi-country project on Forestry and Protected Area Management in the Pacific.

- The UNDP-LDCF Economy-wide Integration of CC Adaptation and DRM/DRR to Reduce Climate Vulnerability of Communities in Samoa will also be running in parallel with this project.  This project will establish an economy-wide approach to climate change adaptation in Samoa, aimed for efficient integration and management of adaptation and DRR/DRM into national development planning and programming and enhancing the resilience of communities’ physical assets and livelihoods across Samoa, to CC and natural disasters.

- The GEF/UNDP Integrating Climate Change Risks in the Agriculture and Health Sectors in Samoa (ICCRAS&HSS).  Under this initiative, the MNRE is developing a Climate Early Warning System (CLEWS) to enable improved climate services to agriculture, to help maintain economic and secure food supplies, and build resilience in the agriculture sector.  In the health sector, the MNRE will work closely to improve the well-being and livelihood of communities by setting up an early- warning surveillance system program (through the CLEWS) that will enable communities to better prepare for potential outbreaks of diseases relating to changes in climate.  The ICCRAS&HSS project works in close collaboration with the World Bank funded Samoa Agriculture Competitiveness Project (SACEP) implemented by the MAF that aims to help local produce capture a larger proportion of the domestic food market and increase rural household incomes.  Part of this project is looking at impact of disasters and climate change on agricultural products that affects food security

- The GEF-UNDP Small Grants projects building capacity of local communities in Samoa

- The JICA funded Forest Monitoring Project in four National Parks and Reserves on Upolu and Savaii

- The AusAid funded NAPA 4 Climate Change Adaptation Project, “Samoa Agroforestry and Tree Farming Project”

- Aside from the Samoa specific implemented UNDP/GEF projects mentioned above, there are also other Pacific wide UNDP/GEF initiatives as well as other development partner projects that will enhance the capacity building activities of this project.  Such projects include:

- The GEF-UNDP regional “Pacific Adaptation to Climate Change” (PACC) Project where Samoa is implementing coastal adaptation measures.  The PACC project aims to strengthen technical capacities to support appropriate adaptation-centric policies, demonstrate cost-effective adaptation techniques in key sectors, and promote regional cooperation.  It is designed to lay the framework for effective and efficient future investment on climate change adaptation in the Pacific.

- The Pilot Programme for Climate Resilience (PPCR) is one of the programmes under the Strategic Climate Fund (SCF) of the Climate Investment Funds (CIF).  The PPCR is designed to pilot and demonstrate ways to integrate climate risk and resilience into core development policies, planning and budgeting processes at national and regional level through increased capacity and scaled-up investments.  Samoa is one of the 14 selected countries under the Country Track programme and as well is involved in the PPCR Pacific Regional Track programme.  The PPCR Country Track programme builds on the NAPAs and helps fund public and private sector investments identified in climate resilient development plans.

- The Coping with Climate Change in the Pacific Island Region (CCCPIR) is a SPC/GIZ project being implemented in Samoa and seven other Pacific island nations, the aim; to strengthen the capacities of Pacific member countries to cope with the impacts of climate change.  Samoa specific activities include work on promoting adaptation to climate change and strategies for emission reduction through private partnerships with larger operators and supporting community based tourism initiatives.  The same project also targets national education ministries, vocational training institutions and teacher training institutions to integrate climate change into existing curricula and training programmes.

## E.2	Implementation and Execution Arrangements

- UNDP is the GEF Implementing Agency for this project, with the UNDP Multi-Country Office responsible for transparent practices, appropriate conduct and professional auditing.  The Executing Agency is the Ministry of Natural Resources and Environment (MNRE), which will assign a National Project Director (NPD) and provide its staff and network of experts as support to Project Management Unit (as part of government co-financing).

- Samoa is one of the 14 Pacific Island Countries and Territories covered under the UNDAF Multi-Country Action Plan that complements and represents a common operational plan for implementing 14 individual UNDAF Country Results Matrices.  Samoa’s Country Results Matrix that the UN system and Samoa have agreed to, has four interrelated outcome areas that are aligned with Samoa’s key overarching guiding document.  This project falls under the UNDAF outcome area environmental management, climate change and disaster risk management that is aligned with Samoa’s SDS 2012-2016 Priority Area 4, Key Outcome 13; Environment Sustainability and Key Outcome 14; Climate and Disaster Resilience.  The priority areas in the SDS will also achieve Samoa’s MDGs.

- The project will be implemented in line with established and agreed Government of Samoa and UNDP procedures.  MNRE will take overall responsibility for implementation of the project, and for the project success.  It will establish the necessary planning and management mechanisms to oversee project inputs, activities and outputs.  The UNDP Multi-Country Office will support the Ministry as requested and as necessary.  The basic implementation and execution framework is depicted in Figure 2.

Figure 2:  Project execution

Programme and Project Organization Structure

Cabinet Development Committee

- Prime Minister (Chair)

- Cabinet Ministers

- Associate Ministers

- All CEOs and ACEOs

Project Board

Executive

MNRE

Senior Suppliers

- UNDP

Senior Beneficiaries

- MNRE

- MOF

Project Assurance

UNDP

Project Director (CEO MNRE)

Project Manager (ACEO CSD)

Technical Working Group

Government Private sector NGO other experts as needed

Project Management Unit

- Principal Capacity Building Officer (PCBO)

- Environment Sector Coordinator

- Project Assistants (CSD staff)

CCD TWG

Government Private Sector NGO

Other experts as needed

FCCC TWG Government Private sector NGO

Other experts as needed

CBD TWG

Government Private Sector NGO

Other experts as needed

Experts and Consultants

- Project Board:  The Project Board will be chaired by the MNRE CEO (Operational Focal Point for the CBD, CCD and FCCC) assisted by the Project Manager and Environment Sector Coordinator.  Membership of the Project Board will be UNDP, CEOs and representatives of seven (7) government agencies and 2 representatives from the Private and NGO/CSO sectors.  The Project Board will provide management oversight of project activities, review progress and evaluation reports and approve programmatic modifications to project execution as appropriate, and in accordance with UNDP procedures.  It is the authority that will sign off on completion of quarterly reports and authorize the start of the next quarterly plan.  It will ensure required resources are committed and arbitrate on any conflicts within the project or negotiates a solution to any problem between the project and external bodies.  In addition, it will make the final decision on appointments of consultants required for the technical implementation of the project.  Policy and legal instrument recommendations will be discussed and recommended for consideration by the Cabinet Development Committee.  The Project Board will meet at a minimum three (3) times per year.

- The MNRE and MOF are the Senior Beneficiaries of the project on the basis that the project will be strengthening and integrating Rio Convention provisions into the SDS and relevant sectoral plans, legislation, policies and institutional mandates where necessary.  UNDP will be the Senior Supplier, providing Project Assurance through technical guidance and support for the cost-effective procurement and implementation of project services and activities, including project implementation oversight through regular monitoring and reporting

- Project Assurance: UNDP will ensure the application of UNDP administrative and financial procedures for the use of funds. UNDP will ensure project monitoring and evaluation according to an agreed schedule and in line with UNDP and GEF requirements. UNDP will assist in compiling lessons learned and sharing project experiences on a national, regional and international basis.

- Project Director:  The MNRE CEO will be designated as the Project Director, and will be responsible for management and oversight of the project.  In the fulfillment of his responsibilities, the Project Director will be supported by the Project Board, Program Manager and GEF Advisor (GA).

- Project Management Unit:  The Project Management Unit (PMU) will be managed by the Project Manager (ACEO Corporate Service Division (CSD)).  He will be responsible to the Project Director for the overall administration, management, coordination, implementation, monitoring and reporting.  He will head the PMU, supported by the Environmental Sector Coordinator, Principal Capacity Building Officer (PCBO), Rio Convention Focal Points TWGs and Project Technical Working Group (TWG).  The Project Manager may act as the Executive of the Project Board in the absence of the MNRE CEO.

- MNRE/GEF Corporate Services:  The MNRE/GEF Services provides advice to all three Rio Convention Focal Points and because of GEF funding modality requirements, alternates for the GEF Focal Point in the absence of the MNRE CEO.

- National Consultants:  The project will contract four (4) national experts as consultants to (i) undertake reviews of legal instruments, tools and policies relevant to the Rio Conventions that require strengthening or updating and synergizing these tools to align with inter-linked and related sector plans as well as the SDS; (ii) design and install an integrated, centralized Data, Knowledge & Information Facility (DKIF) linked to existing Rio Convention related databases (e.g., CBD has Marine, Terrestrial and National Parks & Reserves database; FCCC has CLEWS, CLIDE and CCD has Land Management databases, GIS, SamFris) as well as the MNRE website for easier access; develop policies, protocols and parameters for the DKIF on data gathering, analysis, collection; (iii) develop fully strategic training plans and programmes including a strategic campaign plan to raise awareness of stakeholders involved in the implementation of the Rio Convention and other MEAs; and (iv) develop a monitoring framework that can track the progress of the Rio Conventions.  The M&E Framework will also take into consideration the MTEF and institutional arrangements for implementation of the Rio Conventions, to feed into the national planning process.

- Technical Working Groups (TWGs):  There will be 4TWGs.  The TWG, comprised of Assistant Chief Executive Officers (ACEOs) and representatives from the 12 technical divisions of the MNRE, three of which are Focal Points for the Rio Convention; UNDP, independent experts (where necessary), as well as representatives from stakeholder groups, will discuss and deliberate on the revised legal instruments and strategic implementation of environmental implementation, design and establishment of the centralized Data, Knowledge &Information Facility (DKIF), analysis of sectoral mainstreaming of Rio Conventions and other outputs as required of the project.  The TWGs will be drawn from a pool of approximately 20-30 experts from within the technical divisions as well as relevant stakeholder groups as needed.  The three specific Rio Convention TWGs will discuss and deliberate on each specific Rio Convention obligation and feed into the work of the project TWG as well as the PMU.

- Stakeholder Consultations:  These consultations will focus on the active participation of stakeholders in the training and awareness-raising activities.  Specifically, consultations will focus on the various impacted groups (MNRE Rio Convention Focal Points and implementing agencies, communities, academic, private and civil society groups) involved in the implementation of the Rio Conventions.  Consultations will be led by the Deputy Project Director, supported by the Environmental Sector Coordinator, PCBO, Rio Convention Focal Points (where necessary) to secure their interest and commitment to participating actively in the project activities.  Stakeholders from the private sector may also be contracted to provide services or equipment required by the project.  NGO and community participation is vital as they deliver and implement some of the project activities.

- Capacity Development Activities:  The project will take an adaptive collaborative management (ACM) approach to implementation.  That is, UNDP and MNRE will manage project activities in order that stakeholders are involved early and throughout project implementation, providing regular input of the performance of project activities.  This will help signal unforeseen risks and contribute to the timely modification and realignment of activities within the boundaries of the project's goal and objectives.

# F.  Legal context

- This Project Document shall be the instrument referred to as such in Article I of the Standard Basic Assistance Agreement (SBAA) between the GoS and UNDP, signed by the parties on 5 September 2008.  Samoa’s IA shall, for the purpose of the SBAA, be referred to as the Government Co-operating Agency as described in that SBAA.

- Consistent with the Article III of the Standard Basic Assistance Agreement, the responsibility for the safety and security of the implementing partner and its personnel and property, and of UNDP’s property in the implementing partner’s custody, rests with the implementing partner.

- The implementing partner shall put in place an appropriate security plan and maintain the security plan, taking into account the security situation in the country where the project is being carried; as well as assume all risks and liabilities related to the implementing partner’s security, and the full implementation of the security plan.

- UNDP reserves the right to verify whether such a plan is in place, and to suggest modifications to the plan when necessary.  Failure to maintain and implement an appropriate security plan as required hereunder shall be deemed a breach of this agreement.

- The implementing partner agrees to undertake all reasonable efforts to ensure that none of the UNDP funds received pursuant to the Project Document are used to provide support to individuals or entities associated with terrorism and that the recipients of any amounts provided by UNDP hereunder do not appear on the list maintained by the Security Council Committee established pursuant to resolution 1267 (1999).  The list can be accessed viahttp://www.un.org/sc/committees/1267/aq_sanctions_list.shtml.  This provision must be included in all sub-contracts or sub-agreements entered into under this Project Document.

- This project forms part of an overall programmatic framework under which several separate associated country level activities will be implemented.  When assistance and support services are provided from this Project to the associated country level activities, this document shall be the “Project Document” instrument referred to in: (i) the respective signed SBAAs for the specific countries; or (ii) in the Supplemental Provisions attached to the Project Document in cases where the recipient country has not signed an SBAA with UNDP, attached hereto and forming an integral part hereof.

- This project will be implemented by the agency MNRE (“Implementing Partner”) in accordance with its financial regulations, rules, practices and procedures only to the extent that they do not contravene the principles of the Financial Regulations and Rules of UNDP.  Where the financial governance of an Implementing Partner does not provide the required guidance to ensure best value for money, fairness, integrity, transparency, and effective international competition, the financial governance of UNDP shall apply.

- The responsibility for the safety and security of the Implementing Partner and its personnel and property, and of UNDP’s property in the Implementing Partner’s custody, rests with the Implementing Partner.  The Implementing Partner shall: (a) put in place an appropriate security plan and maintain the security plan, taking into account the security situation in the country where the project is being carried; (b) assume all risks and liabilities related to the Implementing Partner’s security, and the full implementation of the security plan.  UNDP reserves the right to verify whether such a plan is in place, and to suggest modifications to the plan when necessary.  Failure to maintain and implement an appropriate security plan as required hereunder shall be deemed a breach of this agreement.

- The Implementing Partner agrees to undertake all reasonable efforts to ensure that none of the UNDP funds received pursuant to the Project Document are used to provide support to individuals or entities associated with terrorism and that the recipients of any amounts provided by UNDP hereunder do not appear on the list maintained by the Security Council Committee established pursuant to resolution 1267 (1999).  The list can be accessed via http://www.un.org/Docs/sc/committees/1267/1267ListEng.htm.  This provision must be included in all sub-contracts or sub-agreements entered into under this Project Document.

# PART II:	ANNEXES

Annex 1:	Capacity Development Scorecard	56

Annex 2:	Logical Framework	66

Annex 3:	Outcome Budget (GEF contribution and co-financing)	75

Annex 4:	Provisional Work Plan	77

Annex 5:	Terms Of References	89

Annex 6:	PPG Status Report	94

Annex 7:	Environmental and Social Review Criteria	95

Annex 8:     Draft Letter of Agreement (LoA)                                                                                           104

## Annex 1:	Capacity Development Scorecard

Project/Programme Name:	Capacity for implementing Rio Conventions in Samoa

Project/Programme Cycle Phase:	Project preparation 		Date:	March 2014

| Capacity Result / Indicator | Staged Indicators | Rating | Score | Comments | Next Steps | Contribution to which Outcome |
| --- | --- | --- | --- | --- | --- | --- |
| CR 1: Capacities for engagement |  |  |  |  |  |  |
| Indicator 1 – Degree of legitimacy/mandate of lead environmental organizations | Institutional responsibilities for environmental management are not clearly defined | 0 |  | The Executing Agency (MNRE) is the legally mandated authority responsible for environmental management. It is responsible for producing key environmental legislation, policies and action plans for implementing national obligations. Samoa’s key overarching document is the Strategy for Development of Samoa (SDS) that guides the development of the country as a whole and identifies its priority areas every four (4) years. The 2012-2016 SDS includes Environment as a Priority Focus area. The integration of environmental sustainability is observed in sector and sub-sector plans in all economic sectors including agriculture, fisheries, energy, infrastructure, and tourism and the MNRE was instrumental in the integration of environment within a document that previously (2005-2007) did not mention environment at all except in the form of three strategic areas (agriculture, health and tourism development). The MNRE is the Operational Focal Point, in partnership with the Ministry of Foreign Affairs (Political Focal Point), for all Multi-lateral Environmental Agreements (MEAs) Samoa has ratified that in essence, mandates the development and implementation of environment related policies and activities undertaken within Samoa. | MNRE’s capacity will be strengthened to coordinate environmental management in such a way that it will create synergies for the national implementation, monitoring and reporting of the Rio Conventions. MNRE will have strengthened its legal mandate and leading capacities to integrate global environmental priorities into national development plans, sector plans, strategies and planning frameworks that have an impact on the environment sector | Project Outcome 1 and 3 |
|  | Institutional responsibilities for environmental management are identified | 1 |  |  |  |  |
|  | Authority and legitimacy of all lead organizations responsible for environmental management are partially recognized by stakeholders | 2 |  |  |  |  |
|  | Authority and legitimacy of all lead organizations responsible for environmental management recognized by stakeholders | 3 | 3 |  |  |  |
| Indicator 2 – Existence of operational co-management mechanisms | No co-management mechanisms are in place | 0 |  | There are existing mechanisms but the project calls for strengthening of these mechanisms to enable better coordination and implementation of Rio Convention obligations. The NESP was formally established and approved by the Cabinet in 2013 and is now the highest legal environmental co-management mechanism in existence. The highest national legal entity from the policy and development side is the Cabinet Development Committee whose function is to review all new proposals, approve policy frameworks and monitor progress of implementation of all programmes and projects. The ICCRAS&HSS, SACEP, PPCR, CCCPIR projects in particular have good operational co-management mechanisms where agencies are ‘allotted’ technical areas of focus and implementation. However, the PPCR Situational Analysis undertaken in 2012 showed that where partnerships and linkages are mentioned in the implementation of inter-agency projects & programmes, only lead or implementing agencies show programmes and activities incorporated into Corp Plans and Management Plans. Corp Plans are crucial to the economic and development planning cycle as they are directly linked to Performance Budgeting. Corporate Plans are also the operational mechanisms upon which programmes and projects are implemented on a nationwide basis. | The official establishment of the NESP will strengthen and reinvigorate the capacity of the existing agencies responsible for Rio Convention implementation. The ability to monitor, negotiate and facilitate cooperative agreements among the members will be strengthened. Also by improving existing consultation and coordination mechanisms, and promoting information and data sharing with all Rio implementing agencies, the decisions made in relation to the global environment will become more inclusive, legitimate, resilient and robust. There is also an opportunity to strengthen or establish counterparts within these individual agencies to make for an effective network of people working towards one common goal | Project Outcome 1 |
|  | Some co-management mechanisms are in place and operational | 1 |  |  |  |  |
|  | Some co-management mechanisms are formally established through agreements, MOUs, etc. | 2 | 2 |  |  |  |
|  | Comprehensive co-management mechanisms are formally established and are operational/functional | 3 |  |  |  |  |
| Indicator 3 – Existence of cooperation with stakeholder groups | Identification of stakeholders and their participation/involvement in decision-making is poor | 0 |  | Institutional frameworks, structures, coordination mechanisms and the like exist, but despite these, Samoa continues to face many challenges in fulfilling its obligations under the Rio Conventions. Samoa prides itself on the use of participatory and consultative processes in the development, management and implementation of its environmental programmes and projects. Relevant stakeholders are mapped out before the start of any project and participation of stakeholders is maintained throughout the life of such projects. However, the need is for better communication between all stakeholders involved in the implementation of environmental programmes. | During the life of the project, stakeholders will be actively involved through workshops, consultations and trainings (as a learning by doing exercise) in the review of tools and mechanisms to better deliver the Rio Convention obligations. Stakeholders will also be involved in the review of environmental legal instruments, policies and frameworks (through workshops and learning by doing approaches) to mainstream Rio Conventions into mandated national and sector plans and strategies. Targeted training for technical innovations (DKIF) as well as the proposed national roadshows will strengthen the awareness and cooperation of stakeholders | Project Outcome 1, 2 and 3 |
|  | Stakeholders are identified but their participation in decision-making is limited | 1 |  |  |  |  |
|  | Stakeholders are identified and regular consultations mechanisms are established | 2 | 2 |  |  |  |
|  | Stakeholders are identified and they actively contribute to established participative decision-making processes | 3 |  |  |  |  |
| CR 2: Capacities to generate, access and use information and knowledge |  |  |  |  |  |  |
| Indicator 4 – Degree of environmental awareness of stakeholders | Stakeholders are not aware about global environmental issues and their related possible solutions (MEAs) | 0 |  | Samoa is lauded as one of the top countries at the forefront in incorporating international and regional issues into national planning frameworks. Samoa informs its policies and strategies through comprehensive and participatory consultations with all relevant stakeholders. This includes the community at large. However, consultations show there is limited knowledge in some sectors on MEAs and their operational linkages to their respective sectors. The MOF being the central agency responsible for the development of the SDS, usually undertakes the role of incorporating environmental (specifically climate and climate related) issues into sector plans that had not considered it during the planning and development phases. For instance, the Transport Sector is a critical part of the national economy upon which a multitude of industries and sectors rely. Although identified as a critical player in the national economy, it has yet to develop a Sector Plan and is not well informed of international obligations (Rio Conventions & other MEAs) and related activities on the national level and how they inter-link with their various programmes and activities. | Targeted training and learning by doing exercises within the project design (over a 3yr span) will ensure stakeholders understanding and commitment to the Rio Conventions will be improved. In addition to the Rio Conventions, this project will respond to Samoa’s commitments to the global environmental through other MEAs. The broad-based campaign will be implemented on the inter-agency, sector, and national levels. The involvement of the TWG and NESPAC will also improve awareness of stakeholders and ensure their active participation in the implementation of solutions | Project Outcome 2 and 3 |
|  | Stakeholders are aware about global environmental issues but not about the possible solutions (MEAs) | 1 |  |  |  |  |
|  | Stakeholders are aware about global environmental issues and the possible solutions but do not know how to participate | 2 | 2 |  |  |  |
|  | Stakeholders are aware about global environmental issues and are actively participating in the implementation of related solutions | 3 |  |  |  |  |
| Indicator 5 – Access and sharing of environmental information by stakeholders | The environmental information needs are not identified and the information management infrastructure is inadequate | 0 |  | The recent NESP and SOE compilation showed lack of up-to-date quality data and information and time series data as major constraints hindering the preparation of the reports. Data deficiency affected the choice of indicators and how metrics were defined and in some cases, eliminated the possibility of detecting trends or changes over time. The 2nd Communication, NBSAP review and other environment related reviews (e.g., LDCF consultation) identified this also as a problem and attributed it to several reasons including proprietary mentality, limited resources and capacity and lack of internal knowledge management systems. The data, knowledge and information deficiency is not from the absence of information but rather from the absence of, or inadequate information management infrastructure. Coupled with this is the fragmented data collection and information management inherent in the majority of ministries and agencies involved in the implementation of the Rio and other MEAs. This is the biggest and most formidable problem that needs to be fixed in order to inform the stakeholders, and in effectively implementing, monitoring and reporting the Rio Conventions obligations. The rest of the project (and every other projects complementary or parallel to), being implemented by MNRE and other line ministries) is dependent on this focal area | The project will significantly contribute to the effective monitoring, reporting and information sharing of the Rio Conventions and other MEAs through the establishment of a centralized DKIF to collect up to date quality data and information. The development of policies, protocols and parameters will also improve coordination and collaboration in the effective implementation of the Rio Conventions & other MEAs. The creation of the system and linking to the existing MNRE website for more visibility of Rio Convention obligations will ensure public access and raise awareness. It also promotes international and regional partnerships through creating links to relevant platforms. Targeted training on collection, synthesis and data analysis will also significantly reduce the problem of fragmented and outdated information required to meet the global environmental management and sustainable development obligations that also achieves Samoa’s national priorities | Project Outcome 2 |
|  | The environmental information needs are identified but the information management infrastructure is inadequate | 1 | 1 |  |  |  |
|  | The environmental information is partially available and shared among stakeholders but is not covering all focal areas and/or the information management infrastructure to manage and give information access to the public is limited | 2 |  |  |  |  |
|  | Comprehensive environmental information is available and shared through an adequate information management infrastructure | 3 |  |  |  |  |
| Indicator 6 – Existence of environmental education programmes | No environmental education programmes are in place | 0 |  | Samoa holds a lot of environmental education and awareness activities (annual debates, battle of the mind quizzes, climate change competitions etc.). The primary, secondary and tertiary curricula also have sections on the environment. However, these are done through project “lenses” that means they are not strategically developed and delivered (i.e., integrated environmental education programmes) targeting specific linkages to the Rio Conventions and other MEAs. | There are financial limitations to the project in undertaking a full-scale educational programme specifically targeting the Rio Convention. However, the project will conduct four (4) national roadshows, which will showcase global environmental issues and their relation and impact as linked to communities. The roadshows will be in the Samoan language specifically but will also provide simplified bilingual brochures (bilingual) for dissemination to schools and communities. | Project Outcome 2 |
|  | Environmental education programmes are partially developed and partially delivered | 1 |  |  |  |  |
|  | Environmental education programmes are fully developed but partially delivered | 2 | 2 |  |  |  |
|  | Comprehensive environmental education programmes exist and are being delivered | 3 |  |  |  |  |
| Indicator 7 – Extent of the linkage between environmental research/science and policy development | No linkage exist between environmental policy development and science/research strategies and programmes | 0 |  | The MNRE Renewable Energy Division works closely with the SROS in research projects for alternative biofuels; the Water Resources Division regularly monitors rivers and streams for physical parameters including flow/discharge rates, temperature, turbidity etc., the MNRE works with the USP on soil suitability, etc. Results of research are then subsumed into relevant policies. However, there are limited resources to fully expand such scientific research to cover all areas under the Rio Convention, not only for policy development but as well, for informed decision making. | The project will strengthen information sharing agreements with academic and research institutions through their involvement in coordination mechanisms (including the NESPAC). This area will not be a main focus of this project. | Project Outcome 1 and 2 |
|  | Research needs for environmental policy development are identified but are not translated into relevant research strategies and programmes | 1 |  |  |  |  |
|  | Relevant research strategies and programmes for environmental policy development exist but the research information is not responding fully to the policy research needs | 2 | 2 |  |  |  |
|  | Relevant research results are available for environmental policy development | 3 |  |  |  |  |
| Indicator 8 – Extent of inclusion/use of traditional knowledge in environmental decision-making | Traditional knowledge is ignored and not taken into account into relevant participative decision-making processes | 0 |  | The MNRE Meteorology Division collects traditional knowledge on weather patterns; climatic conditions etc. and incorporate these into research to ascertain linkages of climatic changes to health issues, etc. However, translating traditional knowledge into scientific data for decision-making purposes is limited. There is also an element of IPR involved that makes it difficult for traditional knowledge to be systematically shared for effective decision making. Information is also collected through the various consultations undertaken in other Rio related projects (e.g., land management, climate and biodiversity) however, morphing traditional knowledge into numeric indicators (from the scientific perspective) is difficult to achieve | The project will strengthen existing coordination mechanisms that include the participation of NGOs and civil societies in the review of legal instruments, policies and frameworks. It will also enhance and support compliance of communities with Rio Conventions and MEAs through better understanding of global issues through their involvement in the TWG and NESPAC as well as through their participation in targeted workshops and trainings. The brochure on Rio Conventions will be available in Samoan that will encourage participation of the wider community and NGOs. | Project Outcome 2 and 3 |
|  | Traditional knowledge is identified and recognized as important but is not collected and used in relevant participative decision-making processes | 1 |  |  |  |  |
|  | Traditional knowledge is collected but is not used systematically into relevant participative decision-making processes | 2 | 2 |  |  |  |
|  | Traditional knowledge is collected, used and shared for effective participative decision-making processes | 3 |  |  |  |  |
| CR 3: Capacities for strategy, policy and legislation development |  |  |  |  |  |  |
| Indicator 9 – Extend of the environmental planning and strategy development process | The environmental planning and strategy development process is not coordinated and does not produce adequate environmental plans and strategies | 0 |  | Fulfilling commitments as a Party under the Rio Conventions and other MEAs contributed significantly to keeping the environment momentum at the national level, with the adoption of corresponding legislations and policies and action plans for implementing national obligations. This is evident in the changes reflected in the Strategy for Development of Samoa (SDS) 2012-2016 that includes Environment as a Priority Focus area. The integration of national environmental concerns is achieved through incorporation into its economic and development planning cycle that is made up of four main components (i) SDS (ii) Sector Plan (iii) Programme/Project Planning and (iv) Performance Budgeting. The elevation of environmental sustainability alongside the economic and social pillars that previously were the focus of Samoa’s national planning framework also brought it in line with Samoa’s MDG goals. However, the Rio Convention obligations are not fully mainstreamed into the SDS (operational focus) as well as other related Sector plans. | The aim of this project is to integrate global environmental objectives into national and sector policy and planning frameworks. It will also strengthen legal instruments, policies and frameworks that will guide the mainstreaming of Rio Conventions into key national development plans. The development of a coordinated environmental monitoring programme across sectors will track the implementation status of Rio Convention on both the national and sector levels. | Project Outcome 1 and 3 |
|  | The environmental planning and strategy development process does produce adequate environmental plans and strategies but there are not implemented/used | 1 |  |  |  |  |
|  | Adequate environmental plans and strategies are produced but there are only partially implemented because of funding constraints and/or other problems | 2 | 2 |  |  |  |
|  | The environmental planning and strategy development process is well coordinated by the lead environmental organizations and produces the required environmental plans and strategies; which are being implemented | 3 |  |  |  |  |
| Indicator 10 – Existence of an adequate environmental policy and regulatory frameworks | The environmental policy and regulatory frameworks are insufficient; they do not provide an enabling environment | 0 |  | Samoa has a large number of environmental policies and legislation under the overarching jurisdiction of the MNRE. Various legal instruments and policies exist; each Rio Convention has a national policy as well as several tools for monitoring and reporting purposes. The general feeling is that these policies need to go further and reviews are being recommended for almost all. There are relatively new issues of the Rio Convention obligations that need to be legislated. MNRE acknowledges the existence of so many policies and are interested in strategizing on how these policies could be pulled together into one effective law. The concern is that turning all environment related policies into a law would require a strong enforcement component. In retrospect, there are also shortcomings in the enforcement of legislation. For example, the Environment Impact Assessment (EIA) requirements prescribed under the PUMA Act 2004 have not always been adhered to, but most certainly through no fault of the Act or the Agency. | One of the major outcomes of this project is directed at policy and legislative strengthening to integrate Rio Convention provisions. Policy and legislative amendments where required will focus on strengthening the implementation, monitoring and enforcement of Rio and other MEA obligations on a national level. This will encourage and forge stronger commitment to reduce overlap and duplication of activities, and catalyze the effective and efficient exchange of information, and improve Samoa’s implementation of the three Rio Conventions. Furthermore, by raising public awareness, building partnerships and promoting policy dialogue, the project will seek to promote an enabling environment within government agencies and ministries, as well as with other sectors (private, community) for achieving sustainable development and addressing global environmental issues | Project Outcome 1 |
|  | Some relevant environmental policies and laws exist but few are implemented and enforced | 1 |  |  |  |  |
|  | Adequate environmental policy and legislation frameworks exist but there are problems in implementing and enforcing them | 2 | 2 |  |  |  |
|  | Adequate policy and legislation frameworks are implemented and provide an adequate enabling environment; a compliance and enforcement mechanism is established and functions | 3 |  |  |  |  |
| Indicator 11 – Adequacy of the environmental information available for decision-making | The availability of environmental information for decision-making is lacking | 0 |  | Decision-making is not always based on the best available scientific information. Added to this is the problem of non-existent or inadequate knowledge management systems that keeps a ‘trail’ of baseline and indicators for informed decision-making. The absence of a “proactive” centralized knowledge management system that outlasts the life of projects exacerbates the problem. Projects have end dates and information & knowledge is lost when projects end. Staff turnover also contributes to this problem | The project will design and establish a proactive, centralized information management system (DKIF) to enable easier access to, adequate recording of, and effective dissemination of information and knowledge on the Rio Conventions and other MEAs. It will strengthen existing mechanisms through the establishment of policies, protocols and parameters of data, information & knowledge management and sharing to encourage informed decision-making. The project will also strengthen the capacity of MNRE to meet the monitoring and reporting obligations of the Rio Conventions and other MEAs. | Project Outcome 2 |
|  | Some environmental information exists but it is not sufficient to support environmental decision-making processes | 1 |  |  |  |  |
|  | Relevant environmental information is made available to environmental decision-makers but the process to update this information is not functioning properly | 2 | 2 |  |  |  |
|  | Political and administrative decision-makers obtain and use updated environmental information to make environmental decisions | 3 |  |  |  |  |
| CR 4: Capacities for management and implementation |  |  |  |  |  |  |
| Indicator 12 – Existence and mobilization of resources | The environmental organizations don’t have adequate resources for their programmes and projects and the requirements have not been assessed | 0 |  | Financial resources to enact some of the environmental policies (and the three Rio Conventions) are generally available. However, in most cases, there is a fragmented approach in the identification and implementation of resource requirements. This sometimes results in overlapping activities and programmes being implemented within one ministry/agency. This is exacerbated by the demand of the donor for accountability, probity and transparency and forces the creation of extra layers within one ministry. There is a ‘disconnect’ between the planning and implementation levels that makes it difficult to approach donors and development partners from a strategic perspective. There are also serious difficulties in government ministries to implement projects and programmes due to lack of personnel, technical resources and equipment. | The project will mainstream global environmental obligations into the national and sector development plans and strategies. By strengthening the linkages of the national development plans to the Rio Conventions, MNRE will also effectively encourage donor and development partners’ ‘buy in’ into nationally drive initiatives that further strengthens the implementation of Rio Convention obligations. Discussions with donors show that they are very conscious of Samoa’s national priorities and that they use the SDS as their guiding document for financing priority areas. The development partners buy into the government programmes rather than the other way – hence importance of Rio Conventions being mainstreamed into the SDS and other sector plans. The inclusion of an M&E framework to monitor and track the progress of the Rio Conventions will also be another part of this project | Project Outcome 3 |
|  | The resource requirements are known but are not being addressed | 1 |  |  |  |  |
|  | The funding sources for these resource requirements are partially identified and the resource requirements are partially addressed | 2 | 2 |  |  |  |
|  | Adequate resources are mobilized and available for the functioning of the lead environmental organizations | 3 |  |  |  |  |
| Indicator 13 – Availability of required technical skills and technology transfer | The necessary required skills and technology are not available and the needs are not identified | 0 |  | While some of the required skills may be available within the ministry or on a national level, there are at times too many other national projects and programmes running concurrently that puts unnecessary strain on the available expertise. There is heavy reliance on foreign sources for technical and financial assistance to undertake work required. In some cases, stakeholders know what they want but do not have the finances readily available to undertake required technological innovations. Some training is provided to government ministries through short-term attachments, and more development partners are coming onboard to finance skills development for the workforce. However, there is no systematic training provided on how to mainstream Rio Convention provisions into sectoral and national planning. | This project will involve a lot of trainings, workshops and learning by doing exercises, which will build the capacity of stakeholders in implementing Rio Convention obligations in a strategic way. Their involvement from the start until end of the project will ensure adherence and involvement of all concerned stakeholders not only from the planning and implementation levels, but as well will be actively involved in the monitoring and reporting phases of the project. | Project Outcome 1-3 |
|  | The required skills and technologies needs are identified as well as their sources | 1 |  |  |  |  |
|  | The required skills and technologies are obtained but their access depend on foreign sources | 2 | 2 |  |  |  |
|  | The required skills and technologies are available and there is a national-based mechanism for updating the required skills and for upgrading the technologies | 3 |  |  |  |  |
| CR 5: Capacities to monitor and evaluate |  |  |  |  |  |  |
| Indicator 14 – Adequacy of the project/programme monitoring process | Irregular project monitoring is being done without an adequate monitoring framework detailing what and how to monitor the particular project or programme | 0 |  | The Ministry does this as a whole through various monitoring tools (corporate documents, project documents, implementation or action plans). Whilst M & E frameworks are integrated into project documents, these are undertaken primarily for projects but not from a systematic and national approach. Generally much of the effort is focused on project design and implementation but little effort is made in monitoring and in using lessons learnt. An MTEF exists however there is a ‘disconnect’ between the MTEF and M&E of the Rio Conventions on both national and sector levels. | The project will involve not only a review of existing tools and mechanisms for the effective implementation of the Rio Convention obligations, it will also establish an M & E framework to track and monitoring the progress of implementation at all levels (national, sector and inter-agency). The project will also strengthen the monitoring aspect of MNRE through the development of a consolidated monitoring programme to be used by all Rio Convention Focal Points and implementing agencies. The NESPAC will provide for a vigorous monitoring mechanism to gauge the progress and effectiveness of Rio obligations and its implementation on a nation-wide perspective | Project Outcome 3 |
|  | An adequate resourced monitoring framework is in place but project monitoring is irregularly conducted | 1 |  |  |  |  |
|  | Regular participative monitoring of results in being conducted but this information is only partially used by the project/programme implementation team | 2 | 2 |  |  |  |
|  | Monitoring information is produced timely and accurately and is used by the implementation team to learn and possibly to change the course of action | 3 |  |  |  |  |
| Indicator 15 – Adequacy of the project/programme monitoring and evaluation process | None or ineffective evaluations are being conducted without an adequate evaluation plan; including the necessary resources | 0 |  | M & E is undertaken as part of the fiduciary arrangements between Samoa and her development partners. However, these M&Es are not subsumed into corporate plans and management plans, with clearly identified budgetary allocations, KPIs and M & E frameworks not only to measure the implementation of Rio Conventions and other MEAs but also to make sure resources are optimised and activities synergised at all levels. | The project will strengthen existing legal environmental instruments and during the lifetime of the project, specific measure will be undertaken to promote the exchange of information for a coordinated approach at the effective implementation and mainstreaming of Rio Convention obligations into national and sector plans. By integrating MEAs into an approved strategy (i.e., SDS) it will also lead to the development of sector policies that will effectively watch over sustainable use of natural resources. he inclusion | Project Outcome 1 and 3 |
|  | An adequate evaluation plan is in place but evaluation activities are irregularly conducted | 1 |  |  |  |  |
|  | Evaluations are being conducted as per an adequate evaluation plan but the evaluation results are only partially used by the project/programme implementation team | 2 | 2 |  |  |  |
|  | Effective evaluations are conducted timely and accurately and are used by the implementation team and the Agencies and GEF Staff to correct the course of action if needed and to learn for further planning activities | 3 |  |  |  |  |

## Annex 2:	Logical Framework

General comments

| Project Strategy | Objectively verifiable indicators |  |  | Sources of verification | Risks and Assumptions |
| --- | --- | --- | --- | --- | --- |
|  | Indicator | Baseline value | Target value and date |  |  |
| Long-term goal: To strengthen the technical and institutional capacities that will catalyze Samoa’s mainstreaming of the three Rio Conventions and provide for a more effective implementation of the Rio Conventions |  |  |  |  |  |
| Project objectives: A. To strengthen key institutional and individual capacities to implement policies, plans, and programmes that deliver global environmental benefits B. To mainstream and integrate obligations of the three Rio Conventions into Samoa’s national policy framework | Outcome indicators: - Rio Convention obligations are an integral part of Samoa’s Sustainable Development Strategy - SDS is an overarching plan of action for the environmental and sectoral action plans - The Government of Samoa and a wide range of stakeholders systematically review natural resource and environmental policies in a holistic manner in line with Rio Conventions requirements. - Key necessary capacities are built and/or strengthened for a more streamlined implementation of global obligations | - There is no overarching policy that links the Rio Conventions within the framework of national sustainable development - Requirements of the Rio Conventions are not effectively integrated into sectoral plans and policies - There is little inter-ministerial coordination on the implementation and enforcement of natural resource and environmental policies. - Policy interventions often result in overlap, duplication of effort, and weak implementation. - There is fragmented data and information to undertake a streamlined and coordinated effort at achieving Rio Convention monitoring and reporting obligations. | By the end of the project: - The 2017-2021 Sustainable Development Strategy has been approved by the Cabinet of Ministers and ready for Parliamentary consideration for adoption - There is a minimum of 20% increase in the understanding of the Rio Convention mainstreaming among key government agencies and staff - There is a minimum of 15% increase in the understanding of the Rio Conventions among the communities, schools and general public | - Meeting Minutes - Technical Working Group meeting reports - UNDP quarterly progress reports - Independent final evaluation report - Rio Convention national reports and communications - GoS and Parliament bodies decisions - GEF Cross-Cutting Capacity Development Scorecard - Statistical analyses of surveys carried out | - Central and line government ministries and authorities maintain political commitment to the formulation and implementation of the Sustainable Development Strategy - The project will be executed in a transparent, holistic, adaptive, and collaborative manner - Non-state stakeholder representatives, in particular community representatives (Village Council), remain active participants in the project - Policy and institutional reforms and modifications recommended by the project and the SDS are politically, technically, and financially feasible |
| Project Strategy | Objectively verifiable indicators |  |  | Sources of verification | Risks and Assumptions |
|  | Indicator | Baseline value | Target value and date |  |  |

| Outcome 1: The Rio Conventions are more effectively implemented through national planning frameworks that are supported by best practice tools and institutional arrangements |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Output 1.1 Effective tools and mechanisms for implementing Rio Conventions | - Review of NBSAP, NAP, NAPA, SNAP tools & mechanisms completed by month 6 - Specific definitions for each tool developed and specific components requiring strengthening to support Rio Convention obligations completed by month 6 - At least 3 workshop conducted on gaps and weaknesses of tools and mechanisms - At least two (2) workshops conducted on the design and development (and validation) of the consolidated environmental monitoring programme - Operational multi-sector, multi-agency monitoring programme (M & E components) designed and trialed through workshops - At least 2 sector agency work plans show integration of consolidated EMP by month 14 - Reports on policy dialogues undertaken, on institutionalization of consolidated environmental monitoring programme | - Rio Convention tools and mechanisms exist however monitoring & reporting not streamlined across the Focal Points and implementing agencies - Weak inter-linkages between three Rio Convention reporting obligations - Non-existent consolidated environmental monitoring programme - Steering committees and TWG exist however strategic approach to implementation of Rio Conventions very weak | - Review of tools & mechanisms, and definitions of tools completed by month 6 - Training and workshop learning outcomes shows at least 50% improvement in awareness of Rio Convention Focal Points and stakeholders on how to implement consolidated monitoring programme for Rio Convention implementation, monitoring and reporting by month 11 - Consolidated environmental monitoring programme (M & E components) integrated into relevant sector agency work programmes by month 14 | - Analytic matrix and reports - Training &Workshop reports - Learning outcomes pre & post- training questionnaires - Sector agency reports and work plans - Pre & Post questionnaires |  | - Analyses are deemed legitimate, relevant, and valid among all key stakeholder representatives - Sector agencies remain committed to undertaking an integrated approach to monitoring and reporting |  |  |
| Project Strategy | Objectively verifiable indicators |  |  | Sources of verification |  | Risks and Assumptions |  |  |
|  | Indicator | Baseline value | Target value and date |  |  |  |  |  |
| Output 1.2: Training on best practice approaches to implement Rio Conventions | - Training plans designed, peer reviewed and published - At least 5 trainings conducted for MNRE, Rio Convention Focal Points, implementing agencies and communities - Reports of trainings and workshops ‘published’ and available via MNRE& other relevant platforms & website | - Level of understanding of Although the technical qualifications of staff on the Rio Conventions by technical staff is high, this is not the case for the partner implementing agencies | - Training and workshop learning outcomes shows at least 50% improvement in awareness of Rio Convention Focal Points and stakeholders on how to implement consolidated monitoring programme for Rio Convention implementation, monitoring and reporting by month 11 - Strategic training plans listing specific learning outcomes for each required training & workshop completed by month 6 - All training, workshop reports available for downloading on MNRE & other relevant platforms & website by month 24 | - Training plan - Workshop & training reports - Website and other targeted platforms - Sector agency reports - Pre & Post questionnaires |  | - Trainings are utilized and knowledge sustained - Continued commitment and interest of stakeholders maintained |  |  |
| Project Strategy | Objectively verifiable indicators |  |  |  | Sources of verification |  | Risks and Assumptions |
|  | Indicator | Baseline value | Target value and date |  |  |  |  |
| Output 1.3: Strengthened environmental legal instruments and associated policies and legal frameworks | - Independent evaluation of outdated legislation and frameworks and policies completed by month 6 - No less than 2 legal instrument revised and submitted to parliament for consideration by month 30 - At least 6 workshops conducted with all relevant enforcement legal officers and community enforcement authorities on legislation, frameworks and policies relevant to the Rio Conventions - At least one (1) workshop conducted with parliamentary environment steering committee on legislation, frameworks and policies relevant to the Rio Conventions - Convention Laws – Rio Conventions published by month 24 | - Environmental legislation is extensive but not cohesive and sometimes conflict with other legislation - Rio Conventions obligations are not effectively integrated within national legislation - Commitment to Rio Convention provisions are not evident in sectors and national development plans | - Legal enforcement officers, community enforcement authorities and parliamentarians awareness of legislation, frameworks and policies relevant to Rio conventions improved by at least 50% by month 24 - New and/or revised legal instrument approved by relevant authorities by month 36 - Convention Laws – Rio Convention published by month 24 and made available through DKIF by month 26 |  | - Evaluation report - Workshop & Training reports - Pre & Post questionnaires - Revised/new legal instrument - Faatonuga a le Kapeneta (FK) - Parliament Environment Steering Committee report - Published Convention Laws - Website and DKIF |  | - Ministries and Parliament consider policy and legislative recommendations to mainstream Rio Conventions as a priority - Delays in approval of revised legislation - Not all parliamentarians agree with recommended legislation |
| Project Strategy | Objectively verifiable indicators |  |  |  | Sources of verification |  | Risks and Assumptions |
|  | Indicator | Baseline value | Target value and date |  |  |  |  |
| Outcome 2: Raised public support and understanding of Rio Conventions |  |  |  |  |  |  |  |  |
| Output 2.1: Centralized knowledge & information facility established (DKIF) to collect, manage, share and disseminate knowledge and information on Rio Conventions | - Assessment report of institutional structure, systems and mechanisms for managing data, knowledge and information completed by month 6 - At least 2 workshops targeting 60 participants conducted for MNRE, Rio Convention Focal Points, implementing agencies to present findings, recommendations and design of DKIF - High quality DKIF design peer reviewed by relevant knowledge management, communications and data experts by month 14 for implementation by month 18 - Policies, protocols and parameters for DKIF completed by month 12 - Hardware, software procured and database designed and operational by month 24 - At least four (4) national trainings conducted for 90 participants MNRE, Rio Convention Focal Points, implementing agencies, and other stakeholders on data entry, managing, sharing and extraction for environmental monitoring and reporting of Rio Convention obligations | - There is no systematic approach or institutional procedures to collect, synthesize, manage, share and analyze data collected by the three Rio Convention implementing agencies - Inadequate data, knowledge & information management systems, policies and procedures in place - There is limited coordination among agencies and ministries to reconcile design and implement data and knowledge sharing to achieve Rio Convention obligations - Databases exist for three Rio Conventions however, storage of information is fragmented and access is very minimal – mostly restricted to Rio Convention Focal Points - Inadequate hardware & software to capture, store, manage, extract and analyze data for Rio Convention monitoring & reporting purposes | - Intensive targeted training for MNRE, Rio Convention Focal Points and implementing agencies completed by month 14 - Centralized DKIF operational by month 18 - Targeted surveys on knowledge and information management and sharing shows improvement by at least 50% - MNRE website includes new webpage on Rio Convention Laws and information published by implementing agencies by month 26 - Targeted platforms & websites shows analyzed and integrated reports of Samoa’s Rio Convention obligations by month 24 - Rio Convention reporting obligations improved through use of data stored within DKIF by month 24 |  | - Assessment report - Training & Workshop reports - Operational DKIF with report of design - DKIF Policies, manual and procedures - Hardware & software - MNRE Website - Targeted platforms - Survey analysis/report - Pre & Post questionnaires |  | - Sustainability of DKIF - Ministries and agencies agree to share data and information - Data not analyzed properly resulting in wrong data and information released - Knowledge acquired through trainings applied in-house |

| Project Strategy | Objectively verifiable indicators |  |  | Sources of verification | Risks and Assumptions |
| --- | --- | --- | --- | --- | --- |
|  | Indicator | Baseline value | Target value and date |  |  |

| Output 2.2: Raised public awareness and support through national campaign on Rio Conventions | - Campaign plan developed and peer reviewed by month 6 - Simplified and bilingual factsheets/ brochures explaining importance of meeting Rio obligations completed and disseminated by month 30 - At least 4 (2xSavaii, 2xUpolu) national roadshows involving Rio Convention Focal Points and implementing agencies for both Upolu & Savaii completed by month 24 - Quiz competition shows at least 40% increase in understanding of Rio Conventions (pre & post questionnaires) - Annual school debates show at least 40% increase in understanding of Rio Convention obligations (pre & post questionnaires) | - Some understanding of Rio Convention exists within implementing agencies and general public however, knowledge not translated to ‘grassroots’ level - Enforcement undertaken at community level however understanding of Rio Convention very basic | - At least four (4) sector plans show coordinated approach to implementing Rio Conventions through raised awareness, by month 24 - At least 10 colleges, 10 primary schools on both Savaii & Upolu show improved understanding of Rio Conventions and Samoa’s obligations under the Conventions - Targeted survey to determine whether campaign improved awareness of schools and relevant stakeholders completed by month 30 | - Campaign plan - Factsheets (bilingual) - Brochures (bilingual) - Awareness reports - Newspaper articles - MNRE Website - DKIF - Survey report/analysis - Sector plans |  |  | - Roadshow will raise public awareness - Campaign ambitious resulting in failure to achieve set targets and dates |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Outcome 3: Development plans and programmes address implementation of Rio Conventions at national and sectoral level |  |  |  |  |  |  |  |  |  |
| Project Strategy | Objectively verifiable indicators |  |  |  | Sources of verification |  |  | Risks and Assumptions |  |
|  | Indicator | Baseline value | Target value and date |  |  |  |  |  |  |
| Output 3.1: Integration of Rio Conventions in the Samoa SDS 2017-2021 and in other national strategic frameworks | - Reports of policy dialogues undertaken with MOF EPPD during mid-term review of SDS and sector plans completed - Revised MTEF showing links and institutional arrangements for implementation of Rio Conventions by month 33 - At least 2 workshops targeting at least 60 participants for central agencies and implementing agencies conducted in collaboration with MOF, on mainstreaming Rio Conventions into SDS | - SDS exists, but does not fully integrate Rio Convention provisions - National MTEF exists but does not show linkages for institutional arrangements for implementation of Rio Conventions - General understanding of Rio Convention obligations in agencies that collaborate with MNRE but knowledge does not extend to operational level of Rio Conventions | - MOF EPPD review of SDS and sector plans show consideration of mainstreaming Rio Conventions by month 24 and integration by month 36 - MTEF operational and utilized by MNRE to monitor operational and financial arrangements for implementation of Rio Conventions by month 30 - At least four (4) sector agency work programmes show Rio Convention obligations mainstreamed by month 24 - Improved awareness and understanding of the value of mainstreaming Rio Conventions within sectoral policies, plans, programmes and legislation |  | - Report of dialogues - MTEF - SDS - Training & Workshop reports - Mid-Term review report (MOF EPPD) - Sector plans - Pre & Post questionnaires |  |  | - MOF and sector agencies committed to mainstream Rio Conventions into national development plans and sector plans - Workshops conducive to learning outcome required to fully implement Rio Conventions - Delays in mainstreaming Rio Conventions into SDS due to competing priorities - Sector agencies committed to mainstreaming Rio Conventions into their respective plans |  |
| Project Strategy | Objectively verifiable indicators |  |  |  |  | Sources of verification |  |  | Risks and Assumptions |  |
|  | Indicator | Baseline value | Target value and date |  |  |  |  |  |  |  |
| Output 3.2: Identified and addressed capacity gaps for mainstreaming Rio Conventions in four relevant sectors | - Four (4) sector plans integrate Rio Convention obligations by month 24 | - No M & E framework exists to monitor implementation status of Rio Convention (for MNRE & relevant sectors) - Monitoring and reporting of Rio Convention obligations not systematic | - Survey conducted to assess coordinated monitoring and reporting of global and national priorities by month 30 - At least four (4) relevant sectors show improved implementation status of Rio Convention by month 36 |  |  | - Survey instrument - Survey responses - Integrated M & E Framework - Sector agency reports and plans |  |  | - Survey respondents contribute their honest attitudes and values - Changes in awareness and understanding of Rio Convention mainstreaming can be largely attributed to project activities (survey questionnaire can address this issue) |  |
| Project Strategy | Objectively verifiable indicators |  |  |  |  | Sources of verification |  |  | Risks and Assumptions |  |
|  | Indicator | Baseline value | Target value and date |  |  |  |  |  |  |  |
| Output 3.3: Strengthened National & Sectoral capacity on monitoring and reporting obligations of Rio Conventions and other MEAs | - Integrated Monitoring & Evaluation (M & E) Framework developed and trialed by month 10 for implementation by month 12 - At least four (4) trainings on M & E framework and reporting obligations (tools) of Rio Conventions and other relevant MEAs - At least 4 reports published on MNRE website & relevant platforms | - No integrated M & E framework exists - Monitoring and reporting of Rio Convention obligations not systematic - Databases scattered and information non-qualitative | - MNRE, Conventional Focal Points, implementing agencies & communities (MOF, MAF, Police,) utilizing M & E framework to monitor and report on Rio Convention obligations by month 24 - Awareness and understanding of all relevant agencies and stakeholders on inter-linkages of Rio Convention and other MEAs and reporting obligations become more streamlined by month 24 |  |  | - Integrated M & E framework - Sector agency reports - Rio Convention reports - Workshops & Training reports - Pre & Post questionnaires |  |  | - Sector agencies committed to utilizing M & E framework - Legal and community authorities awareness raised - Databases operational and contains right data |  |

## Annex 3:	Outcome Budget (GEF Contribution and Co-Financing)

|  |  | Year 1 | Year 2 | Year 3 | GEF | CO-FIN | TOTAL |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Description |  |  |  |  |  |  |
|  | Total | 432,000 | 315,000 | 253,000 | 500,000 | 500,000 | 1,000,000 |
| Outcome 1:The Rio Conventions are more effectively implemented through national planning frameworks that are supported by best practice tools and institutional arrangements |  | 157,500 | 88,000 | 42,000 | 19,000 | 100,000 | 50,000 |
| Output 1.1 | Effective tools and mechanisms for implementing Rio Conventions | 23,000 | 16,000 | 5,000 | 27,000 | 18,000 | 44,000 |
| Output 1.2 | Training on best practice approaches to implement Rio Conventions | 24,000 | 16,000 | 8,000 | 31,000 | 18,000 | 49,000 |
| Output 1.3 | Strengthened environmental legal instruments & associated policies and legal frameworks | 41,000 | 10,000 | 6,000 | 43,000 | 14,000 | 57,000 |
| Outcome 2: Raised public support and understanding of Rio Conventions |  | 98,000 | 137,000 | 140,000 | 73,000 | 250,000 | 100,000 |
| Output 2.1 | Centralized knowledge & information facility established (Data, Knowledge & Information Facility – DKIF) to collect, manage, share and disseminate knowledge and information on Rio Conventions | 114,000 | 114,000 | 57,000 | 208,000 | 77,000 | 285,000 |
| Output 2.2 | Raised public awareness and support through national campaign on Rio Conventions | 23,000 | 26,000 | 16,000 | 42,000 | 23,000 | 65,000 |
| Outcome 3: Development plans and programmes address implementation of Rio Conventions at national and sectoral level |  | 154,000 | 90,000 | 69,000 | 65,000 | 100,000 | 124,000 |
| Output 3.1 | Integration of Rio Conventions in the Samoa SDS 2017-2021 and in other national strategic frameworks | 15,000 | 25,000 | 21,000 | 20,000 | 41,000 | 61,000 |
| Output 3.2 | Identified and addressed capacity gaps for mainstreaming Rio Conventions in four relevant sectors | 45,000 | 23,000 | 17,000 | 50,000 | 34,000 | 84,000 |
| Output 3.3 | Strengthened National & Sectoral capacity on monitoring and reporting obligations of Rio Conventions and other MEAs | 29,000 | 22,000 | 27,000 | 30,000 | 48,000 | 78,000 |
| Project Management |  | 23,500 | 116,000 | 63,000 | 96,000 | 50,000 | 226,000 |
| A | International consultants | 0 | 0 | 20,000 | 20,000 | 0 | 20,000 |
| B | Local Consultants | 111,000 | 59,000 | 61,000 | 5,000 | 226,000 | 231,000 |
| C | Travel | 0 | 0 | 5,000 | 5,000 | 0 | 5,000 |
| D | Miscellaneous expenses | 6,000 | 5,000 | 5,000 | 15,000 | 0 | 15,000 |
| E | Professional Services | 0 | 0 | 5,000 | 5,000 | 0 | 5,000 |

## Annex 4:	Provisional Work Plan

| Year 1 |  | Month |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Activity | Description | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 |
|  | Project start-up: Organize project team and review work plan |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Project Steering Committee meetings |  |  |  |  |  |  |  |  |  |  |  |  |
|  | International Consultant (Terminal Evaluation) |  |  |  |  |  |  |  |  |  |  |  |  |
| Component 1: Tools and mechanisms for implementing Rio Conventions |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 1.1 | Effective tools and mechanisms for implementing Rio Conventions |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.1.1 | Conduct desk review of NBSAP (CBD); NAP (CCD) and NAPA, SNAP (FCCC) to identify tools and policies that require strengthening or updating |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.1.2 | Prepare definitions of different tools and key reporting components (Reporting, Monitoring, Assessment, Data collection & Analysis tools etc.) and identify weaknesses and strengths for each based on findings from 1.1.1 |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.1.3 | Convene 3 workshops on identified tools, gaps & weaknesses for at least 60 participants on all Rio Convention Focal Points and relevant stakeholders, inclusive key implementing agencies. |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.1.4 | Design a multi-sector & multi-agency monitoring programme that consolidates all environmental monitoring under different MNRE divisions, Rio Convention Focal Points and other agencies. |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.1.5 | Convene a validation workshop for 1.1.4 and policy dialogues with relevant sector agencies (i.e., water and sanitation, infrastructure and energy, agriculture, and tourism) to promote and facilitate institutionalization of consolidated multi-sector/multi-agency environmental monitoring programme. |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 1.2 | Training on best practice approaches to implement Rio Conventions |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.2.1 | Develop training plan (to be linked to MNRE Capacity Needs 2013) with targeted objectives and learning outcomes for different stakeholders. This activity is to be undertaken in parallel with Activities 1.1.3 and 1.1.5. |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.2.2 | Conduct trainings for MNRE staff including Rio Convention Focal Points on consolidated environmental monitoring programme developed in Activity 1.1.4. |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.2.3 | Conduct national training for all Rio Convention implementing agencies and communities as follow-on from Activity 1.2.2. |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.2.4 | Produce training and workshop reports (information from pre & post questionnaires used as baseline data) |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 1.3 | Strengthened environmental legal instruments & associated policies and legal frameworks |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.3.1 | Undertake an in-depth SWOT and gap analysis of existing legal instruments and policies to meeting and sustaining Rio Convention obligations. This activity will be undertaken in parallel with activities 1.1.1-1.1.2 |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.3.2 | Convene consultation workshops within MNRE and relevant stakeholders to present analyses and findings. Activity undertaken in parallel with Activities 1.1.3 - 1.1.5 as well as Activities 1.2.2 and 1.2.3 |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.3.3 | Revise (or enact new) legal instruments and policies according to guidance from Activities 1.3.4 and in collaboration with Activities 1.1.2, 1.1.4 – 1.1.5. |  |  |  |  |  |  |  |  |  |  |  |  |
| Component 2: Public Awareness-raising & Information Management |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 2.1 | Centralized knowledge & information facility established (Data, Knowledge & Information Facility – DKIF) to collect, manage, share and disseminate knowledge and information on Rio Conventions |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.1.1 | Identify and secure national knowledge management and communications, data and statistical experts (in partnership with SBS) |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.1.2 | Conduct assessment of existing information management system and processes to identify synergies, gaps, and overlaps. Identify key information gaps (e.g. indicators) in SOE required to feed into monitoring of implementation of Rio Conventions & other MEAs. Activity undertaken in parallel with 1.1 – 1.5 |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.1.3 | Convene workshops for MNRE (Rio Convention Focal Points and division staff) and other Rio Convention implementing agencies to present findings and recommendations for feedback, guidance and validation. |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.1.4 | Design integrated, synergized, centralized DKIF based on analysis & feedback from workshops (including technological hardware & software requirements) |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.1.5 | Develop manuals, policies, protocols and parameters for DKIF, MNRE and other relevant stakeholders on data gathering, analysis, collection, sharing |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.1.6 | Procure and install hardware & software for DKIF based on trials, feedback. |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.1.7 | Conduct training for MNRE (Rio Convention Focal Points) and divisional staff, implementing agencies (Environmental Focal Contacts), communities and stakeholders on use of DKIF for environmental monitoring, reporting and data sharing |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.1.8 | Initiate collection of information &knowledge for DKIF (from Components 1-3) and create link to MNRE Website (searchable online) and other relevant implementing and partner agencies (national, regional and/or international) |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 2.2 | Raised public awareness and support through national campaign on Rio Conventions |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.2.1 | Develop an integrated campaign plan in line with Outputs 1 and 3 |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.2.2 | Develop simple fact sheets/brochures (bilingual) explaining importance of meeting Rio obligations and make available through 2.1.8 as well as 2.2.3. |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.2.3 | Conduct national roadshow involving Rio Convention Focal Points and implementing agencies (MESC) targeting schools and communities contributing to the implementation of Rio Convention obligations. |  |  |  |  |  |  |  |  |  |  |  |  |
| Component 3: Mainstreaming Rio Conventions into Development Sectors |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 3.1 | Integration of Rio Conventions in the Samoa SDS 2017-2021 and in other national strategic frameworks |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.1.1 | Identification of national priorities to support the Rio Conventions and mainstreamed to coincide with mid-term review of SDS and sector plans. This activity will be undertaken in collaboration with Output 1.3, Activities 1.1.6, 1.2.2, and 2.2.3. |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.1.2 | Develop links in the national MTEF and institutional arrangements for implementation of Rio Conventions |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.1.3 | Convene targeted workshop for central agencies (MOF), line ministries (MAF, MOH, STA, MWCSD, and MESC), corporations (LTA, MWTI), private sector and communities on mainstreaming Rio Conventions. |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 3.2 | Identified and addressed capacity gaps for mainstreaming Rio Conventions in four relevant sectors |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.2.1 | Conduct an in-depth review of status of Rio Convention implementation for all relevant sectors (including community) identified in NESP |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.2.2 | Address identified gaps in four relevant sector plans, using knowledge gained from Activities 1.1.4-1.1.5, 1.2.2, 1.3.1 and 3.2.1. This activity will involve the convening of workshops and working group meetings, structured as learn-by-doing exercises, with widespread participation of government staff from across various planning agencies involved in the drafting of sectoral development plans. |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 3.3 | Strengthened National & Sectoral capacity on monitoring and reporting obligations of Rio Conventions and other MEAs |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.3.1 | Identify and secure an M&E expert for Rio Conventions (to work across Outcomes 1 and 3) |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.3.2 | Develop a monitoring framework to track progress of Rio Conventions & other MEAs. Activity undertaken in parallel with Outputs 1.2 and 1.3. |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.3.3 | Organize and conduct targeted training on monitoring & evaluation and reporting obligations (tools) of Rio Conventions and other MEA for relevant stakeholders. Activity to feed into collaborating activities 3.2.1 and 3.2.2). |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.3.4 | Prepare reports of all trainings conducted and make available through Outcome 2 |  |  |  |  |  |  |  |  |  |  |  |  |

| YEAR 2 |  | MONTH |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Activity | Description | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 |  | 24 |
| A | Project start-up: Organize project team and review work plan |  |  |  |  |  |  |  |  |  |  |  |  |  |
| B | Project Steering Committee meetings |  |  |  |  |  |  |  |  |  |  |  |  |  |
| C | International Consultant (Terminal Evaluation) |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Component 1: Tools and mechanisms for implementing Rio Conventions |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 1.1 | Effective tools and mechanisms for implementing Rio Conventions |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.1.1 | Conduct desk review of NBSAP (CBD); NAP (CCD) and NAPA, SNAP (FCCC) to identify tools and policies that require strengthening or updating |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.1.2 | Prepare definitions of different tools and key reporting components (Reporting, Monitoring, Assessment, Data collection & Analysis tools etc.) and identify weaknesses and strengths for each based on findings from 1.1.1 |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.1.3 | Convene workshop on identified tools; gaps, weaknesses & strengths for all Rio Convention Focal Points and relevant stakeholders |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.1.4 | Design a multi-sector & multi-agency monitoring programme that consolidates all environmental monitoring under different MNRE divisions, Rio Convention Focal Points and other agencies |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.1.5 | Convene a validation workshop for 1.1.4 and policy dialogues with relevant sector agencies (i.e., water and sanitation, infrastructure and energy, agriculture, and tourism) to promote and facilitate institutionalization of consolidated multi-sector/multi-agency environmental monitoring programme. |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 1.2 | Training on best practice approaches to implement Rio Conventions |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.2.1 | Develop training plan (to be linked to MNRE Capacity Needs 2013) with targeted objectives and learning outcomes for different stakeholders. This activity is to be undertaken in parallel with Activities 1.1.3 and 1.1.5. |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.2.2 | Conduct trainings for MNRE staff including Rio Convention Focal Points on consolidated environmental monitoring programme developed in Activity 1.1.4. |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.2.3 | Conduct national training for all Rio Convention implementing agencies and communities as follow-on from Activity 1.2.2. |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.2.4 | Produce training and workshop reports (information from pre & post questionnaires used as baseline data). |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 1.3 | Strengthened environmental legal instruments & associated policies and legal frameworks |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.3.1 | Undertake an in-depth SWOT and gap analysis of existing legal instruments and policies to meeting and sustaining Rio Convention obligations. This activity will be undertaken in parallel with activities 1.1.1-1.1.2 |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.3.2 | Convene consultation workshops within MNRE and relevant stakeholders to present analyses and findings. Activity undertaken in parallel with Activities 1.1.3 - 1.1.5 as well as Activities 1.2.2 and 1.2.3 |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.3.3 | Revise (or enact new) legal instruments and policies according to guidance from Activities 1.3.4 and in collaboration with Activities 1.1.2, 1.1.4 – 1.1.5. |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Component 2: Public Awareness-raising & Information Management |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 2.1 | Centralized knowledge & information facility established (Data, Knowledge & Information Facility – DKIF) to collect, manage, share and disseminate knowledge and information on Rio Conventions |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.1.1 | Identify and secure national knowledge management and communications, data and statistical experts (in partnership with SBS). |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.1.2 | Conduct assessment of existing information management system and processes to identify synergies, gaps, and overlaps. Identify key information gaps (e.g. indicators) in SOE required to feed into monitoring of implementation of Rio Conventions & other MEAs. Activity undertaken in parallel with 1.1 – 1.5 |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.1.3 | Convene workshops for MNRE (Rio Convention Focal Points and division staff) and other Rio Convention implementing agencies to present findings and recommendations for feedback, guidance and validation. |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.1.4 | Design integrated, synergized, centralized DKIF based on analysis & feedback from workshops (including technological hardware & software requirements). |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.1.5 | Develop manuals, policies, protocols and parameters for DKIF, MNRE and other relevant stakeholders on data gathering, analysis, collection, sharing |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.1.6 | Procure and install hardware & software for DKIF based on trials, feedback |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.1.7 | Conduct training for MNRE (Rio Convention Focal Points) and divisional staff, implementing agencies (Environmental Focal Contacts), communities and stakeholders on use of DKIF for environmental monitoring, reporting and data sharing |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.1.8 | Initiate collection of information &knowledge for DKIF (from Components 1-3) and create link to MNRE Website (searchable online) and other relevant implementing and partner agencies (national, regional and/or international) |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 2.2 | Raised public awareness and support through national campaign on Rio Conventions |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.2.1 | Develop an integrated campaign plan in line with Outputs 1 and 3 |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.2.2 | Develop simple fact sheets/brochures (bilingual) explaining importance of meeting Rio obligations and make available through 2.1.8 as well as 2.2.3. |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.2.3 | Conduct national roadshow involving Rio Convention Focal Points and implementing agencies (MESC) targeting schools and communities contributing to the implementation of Rio Convention obligations. |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Component 3: Mainstreaming Rio Conventions into Development Sectors |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 3.1 | Integration of Rio Conventions in the Samoa SDS 2017-2021 and in other national strategic frameworks |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.1.1 | Identification of national priorities to support the Rio Conventions and mainstreamed to coincide with mid-term review of SDS and sector plans. This activity will be undertaken in collaboration with Output 1.3, Activities 1.1.6, 1.2.2, and 2.2.3. |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.1.2 | Develop links in the national MTEF and institutional arrangements for implementation of Rio Conventions |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.1.3 | Convene targeted workshop for central agencies (MOF), line ministries (MAF, MOH, STA, MWCSD, and MESC), corporations (LTA, MWTI), private sector and communities on mainstreaming Rio Conventions. |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 3.2 | Identified and addressed capacity gaps for mainstreaming Rio Conventions in four relevant sectors |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.2.1 | Conduct an in-depth review of status of Rio Convention implementation for all relevant sectors (including community) identified in NESP. |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.2.2 | Address identified gaps in four relevant sector plans, using knowledge gained from Activities 1.1.4-1.1.5, 1.2.2, 1.3.1 and 3.2.1. This activity will involve the convening of workshops and working group meetings, structured as learn-by-doing exercises, with widespread participation of government staff from across various planning agencies involved in the drafting of sectoral development plans. |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 3.3 | Strengthened National & Sectoral capacity on monitoring and reporting obligations of Rio Conventions and other MEAs |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.3.1 | Identify and secure an M&E expert for Rio Conventions (to work across Outcomes 1 and 3). |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.3.2 | Develop a monitoring framework to track progress of Rio Conventions & other MEAs. Activity undertaken in parallel with Outputs 1.2 and 1.3. |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.3.3 | Organize and conduct targeted training on monitoring & evaluation and reporting obligations (tools) of Rio Conventions and other MEA for relevant stakeholders. Activity to feed into collaborating activities 3.2.1 and 3.2.2). |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.3.4 | Prepare reports of all trainings conducted and make available through Outcome 2 |  |  |  |  |  |  |  |  |  |  |  |  |  |

| YEAR 3 |  | MONTH |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Activity | Description | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 |  | 36 |
| A | Project start-up: Organize project team and review work plan |  |  |  |  |  |  |  |  |  |  |  |  |  |
| B | Project Steering Committee meetings |  |  |  |  |  |  |  |  |  |  |  |  |  |
| C | International Consultant (Terminal Evaluation) |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Component 1: Tools and mechanisms for implementing Rio Conventions |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 1.1 | Effective tools and mechanisms for implementing Rio Conventions |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.1.1 | Conduct desk review of NBSAP (CBD); NAP (CCD) and NAPA, SNAP (FCCC) to identify tools and policies that require strengthening or updating |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.1.2 | Prepare definitions of different tools and key reporting components (Reporting, Monitoring, Assessment, Data collection & Analysis tools etc.) and identify weaknesses and strengths for each based on findings from 1.1.1 |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.1.3 | Convene workshop on identified tools; gaps, weaknesses & strengths for all Rio Convention Focal Points and relevant stakeholders |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.1.4 | Design a multi-sector & multi-agency monitoring programme that consolidates all environmental monitoring under different MNRE divisions, Rio Convention Focal Points and other agencies |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.1.5 | Convene a validation workshop for 1.1.4 and policy dialogues with relevant sector agencies (i.e., water and sanitation, infrastructure and energy, agriculture, and tourism) to promote and facilitate institutionalization of consolidated multi-sector/multi-agency environmental monitoring programme. |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 1.2 | Training on best practice approaches to implement Rio Conventions |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.2.1 | Develop training plan (to be linked to MNRE Capacity Needs 2013) with targeted objectives and learning outcomes for different stakeholders. This activity is to be undertaken in parallel with Activities 1.1.3 and 1.1.5. |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.2.2 | Conduct trainings for MNRE staff including Rio Convention Focal Points on consolidated environmental monitoring programme developed in Activity 1.1.4. |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.2.3 | Conduct national training for all Rio Convention implementing agencies and communities as follow-on from Activity 1.2.2. |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.2.4 | Produce training and workshop reports (information from pre & post questionnaires used as baseline data). |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 1.3 | Strengthened environmental legal instruments & associated policies and legal frameworks |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.3.1 | Undertake an in-depth SWOT and gap analysis of existing legal instruments and policies to meeting and sustaining Rio Convention obligations. This activity will be undertaken in parallel with activities 1.1.1-1.1.2 |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.3.2 | Convene consultation workshops within MNRE and relevant stakeholders to present analyses and findings. Activity undertaken in parallel with Activities 1.1.3 - 1.1.5 as well as Activities 1.2.2 and 1.2.3 |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.3.3 | Revise (or enact new) legal instruments and policies according to guidance from Activities 1.3.4 and in collaboration with Activities 1.1.2, 1.1.4 – 1.1.5. |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Component 2: Public Awareness-raising & Information Management |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 2.1 | Centralized knowledge & information facility established (Data, Knowledge & Information Facility – DKIF) to collect, manage, share and disseminate knowledge and information on Rio Conventions |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.1.1 | Identify and secure national knowledge management and communications, data and statistical experts (in partnership with SBS). |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.1.2 | Conduct assessment of existing information management system and processes to identify synergies, gaps, and overlaps. Identify key information gaps (e.g. indicators) in SOE required to feed into monitoring of implementation of Rio Conventions & other MEAs. Activity undertaken in parallel with 1.1 – 1.5 |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.1.3 | Convene workshops for MNRE (Rio Convention Focal Points and division staff) and other Rio Convention implementing agencies to present findings and recommendations for feedback, guidance and validation. |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.1.4 | Design integrated, synergized, centralized DKIF based on analysis & feedback from workshops (including technological hardware & software requirements). |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.1.5 | Develop manuals, policies, protocols and parameters for DKIF, MNRE and other relevant stakeholders on data gathering, analysis, collection, sharing |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.1.6 | Procure and install hardware & software for DKIF based on trials, feedback |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.1.7 | Conduct training for MNRE (Rio Convention Focal Points) and divisional staff, implementing agencies (Environmental Focal Contacts), communities and stakeholders on use of DKIF for environmental monitoring, reporting and data sharing |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.1.8 | Initiate collection of information &knowledge for DKIF (from Components 1-3) and create link to MNRE Website (searchable online) and other relevant implementing and partner agencies (national, regional and/or international) |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 2.2 | Raised public awareness and support through national campaign on Rio Conventions |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.2.1 | Develop an integrated campaign plan in line with Outputs 1 and 3 |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.2.2 | Develop simple fact sheets/brochures (bilingual) explaining importance of meeting Rio obligations and make available through 2.1.8 as well as 2.2.3. |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.2.3 | Conduct national roadshow involving Rio Convention Focal Points and implementing agencies (MESC) targeting schools and communities contributing to the implementation of Rio Convention obligations. |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Component 3: Mainstreaming Rio Conventions into Development Sectors |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 3.1 | Integration of Rio Conventions in the Samoa SDS 2017-2021 and in other national strategic frameworks |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.1.1 | Identification of national priorities to support the Rio Conventions and mainstreamed to coincide with mid-term review of SDS and sector plans. This activity will be undertaken in collaboration with Output 1.3, Activities 1.1.6, 1.2.2, and 2.2.3. |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.1.2 | Develop links in the national MTEF and institutional arrangements for implementation of Rio Conventions |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.1.3 | Convene targeted workshop for central agencies (MOF), line ministries (MAF, MOH, STA, MWCSD, and MESC), corporations (LTA, MWTI), private sector and communities on mainstreaming Rio Conventions. |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 3.2 | Identified and addressed capacity gaps for mainstreaming Rio Conventions in four relevant sectors |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.2.1 | Conduct an in-depth review of status of Rio Convention implementation for all relevant sectors (including community) identified in NESP. |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.2.2 | Address identified gaps in four relevant sector plans, using knowledge gained from Activities 1.1.4-1.1.5, 1.2.2, 1.3.1 and 3.2.1. This activity will involve the convening of workshops and working group meetings, structured as learn-by-doing exercises, with widespread participation of government staff from across various planning agencies involved in the drafting of sectoral development plans. |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 3.3 | Strengthened National & Sectoral capacity on monitoring and reporting obligations of Rio Conventions and other MEAs |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.3.1 | Identify and secure an M&E expert for Rio Conventions (to work across Outcomes 1 and 3). |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.3.2 | Develop a monitoring framework to track progress of Rio Conventions & other MEAs. Activity undertaken in parallel with Outputs 1.2 and 1.3. |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.3.3 | Organize and conduct targeted training on monitoring & evaluation and reporting obligations (tools) of Rio Conventions and other MEA for relevant stakeholders. Activity to feed into collaborating activities 3.2.1 and 3.2.2). |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.3.4 | Prepare reports of all trainings conducted and make available through Outcome 2 |  |  |  |  |  |  |  |  |  |  |  |  |  |

## Annex 5:	Terms of Reference

The following Terms of Reference outlines the general responsibilities to be carried out by consultants contracted under the project.  These will be developed in further detailed during the inception phase of the project.

Background

This project is grounded in Samoa's National Capacity Self-Assessment (NCSA), which was completed in 2007.  As with many other countries, Samoa's challenge in meeting global environmental priorities is rooted in a real priority to meet national socio-economic priorities, lack of awareness on the national benefits of Rio Convention implementation, weak institutional capacities to implement the Rio Conventions, and limited financial resources of government institutions, among other challenges and barriers.  Under the NCSA, Samoa prepared their National Environmental Capacity Strategy and Action Plan, which strategized improving national capacity development.  Recommended activities were designed to achieve improved compliance with the three Rio Conventions.

Project Goal and Objectives

The goal of this project is to address the capacity gaps and needs that are vital to the enhancement of Samoa’s ability to meet its obligations under the Conventions.  To this end, the project will focus on mainstreaming Rio Convention provisions into Samoa's broader national development framework and strengthening related capacities to implement this framework through three complementary objectives.  The objectives of the project will be to create and strengthen mechanisms and tools to identify, collect, manage and synergize environmental baselines and catalyze mainstreaming of Rio Conventions and other MEAs into national and sectoral policy, management, financial and legislative frameworks.  It will also strengthen coordination mechanisms and raise public awareness to enable full participation and support of the implementation of the Rio Conventions and other relevant MEAs.  The objectives will be implemented through a learn-by-doing approach.  The active participation of stakeholder representatives in the full project life cycle serves to facilitate the strategic adaptation of project activities in keeping with project objectives.  The critical role of non-state stakeholders will contribute to the adaptive collaborative management of project implementation.

Project Strategy

Sustainable development has never been only about meeting national priorities.  Because of the pressing social and economic needs that more visibly affect people’s daily lives, the environmental component has traditionally been interpreted as managing the environment to the extent that it supports national social and economic priorities.

This project will be among the set of innovative and transformative projects under the Global Environmental Facility (GEF) that will demonstrate the pursuit of sustainable development through sectoral policies that help better deliver global environmental benefits as well as meeting their national socio-economic objectives.  At the end of the project, a key set of foundational capacities through improved sectoral policies, programmes, plans and legislation as well as training of government staff and other stakeholders will have been strengthened that facilitates the delivery and sustainability of global environmental outcomes.

The project will take an adaptive collaborative management (ACM) approach to implementation, which calls for stakeholders to take an early and proactive role in the mainstreaming exercises, as well as to help identify and solve unexpected implementation barriers and challenges.  By taking an ACM approach, project activities and outputs can be more legitimately modified and adapted to maintain timely and cost-effective project performance and delivery.

Project Outcomes and Components

At the end of the project, activities will have resulted in a set of improved capacities to meet and sustain Rio Convention objectives.  This project will have strengthened and helped institutionalize commitments under the Rio Conventions within the framework of national sustainable development policy.  In this way, the project will have lowered the transaction costs in terms of political will and resources (human and financial).  To this end, the project will have produced a national Sustainable Development Strategy (SDS) that fully reflects articles of the three Rio Conventions and decisions of their respective Conference of the Parties.  The project will have also strengthened the institutional arrangements necessary for the cost-effective implementation of the SDS by demonstrating regional SDS implementation and extensive training and public awareness on the critical links between environment and development.

This project will be implemented in three linked components:

- Samoa has effective tools and mechanisms for implementing Rio Conventions

- Samoa implementing tools and mechanisms to improve data, information and knowledge management and sharing

- Development plans and programmes address implementation of Rio Conventions

Responsibilities

National Project Director (NPD)

The Government of Samoa must appoint a national director for this UNDP-supported project.  The National Project Director supports the project and acts as a focal point on the part of the Government.  This responsibility normally entails ensuring effective communication between partners and monitoring of progress towards expected results.

The National Project Director is the party that represents the Government’s ownership and authority over the project, responsibility for achieving project objectives and the accountability to the Government and UNDP for the use of project resources.

In consultation with UNDP, Ministry of Natural Resources and Environment (MNRE), as the concerned ministry, will designate the National Project Director from among its staff at not lower than the Chief Executive Officer (CEO) level.  The National Project Director (NPD) will be supported by a full-time National Project Manager (NPM).

Duties and Responsibilities of the NPD

- The NPD will have the following duties and responsibilities:

- Assume overall responsibility for the successful execution and implementation of the project, accountability to the Government and UNDP for the proper and effective use of project resources)

- Serve as a focal point for the coordination of projects with other Government agencies, UNDP and outside implementing agencies;

- Ensure that all Government inputs committed to the project are made available;

- Supervise the work of the National Project Manager and ensure that the National Project Manager is empowered to effectively manage the project and other project staff to perform their duties effectively;

- Select and arrange, in close collaboration with UNDP, for the appointment of the National Project Manager (in cases where the NPM has not yet been appointed);

- Supervise the preparation of project work plans, updating, clearance and approval, in consultation with UNDP and other stakeholders and ensure the timely request of inputs according to the project work plans;

- Represent the Government institution (national counterpart) at the tripartite review project meetings, and other stakeholder meetings.

Remuneration and entitlements:

The National Project Director may not receive monetary compensation from project funds for the discharge of his/her functions.

Project Manager

A Project Manager will be chosen from among MNRE staff but at not lower than the Assistant Chief Executive Officer (ACEO) level to oversee the project implementation under the guidance of the NPD, the Project Advisory Board, and with the support of UNDP Samoa.  The position of the Project Manager is financed by the in-kind contribution of the Government of Samoa.  In addition to overseeing the implementation of the project’s capacity development activities, the project manager will carry out the monitoring and evaluation procedures per UNDP agreed policies and procedures.  These include:

- Oversee the day-to-day monitoring of project implementation

- In consultation with stakeholders, recommend modifications to project management to maintain project’s cost-effectiveness, timeliness, and quality project deliverables (adaptive collaborative management) to be approved by the Project Advisory Board

- Prepare all required progress and management reports, e.g., APR/PIR and project initiation report

- Support all meetings of the Project Advisory Board

- Maintain effective communication with project partners and stakeholders to disseminate project results, as well as to facilitate input from stakeholder representatives as project partners

- Support the independent terminal evaluation

- Ensure full compliance with the UNDP and GEF branding policy

Environment Sector Coordinator

The Environment Sector Coordinator will support the Project Manager in the carrying out of his/her duties, which will include:

- Organizational and logistical issues related to project execution per UNDP guidelines and procedures

- Record keeping of project documents, including financial in accordance with audit requirements

- Ensure all logistical arrangements are carried out smoothly

- Assist Project Manager in preparation and update of project work plans in collaboration with the UNDP MCOUNDP Multi-Country Office

- Facilitate timely preparation and submission of financial reports and settlement of advances, including progress reports and other substantial reports

- Organise and conduct trainings and workshops in collaboration with consultants

- Report to the Project Manager and UNDP Programme Officer on a regular basis

- Identification and resolution of logistical and organizational problems, under the guidance of the Project Manager

He/she will have at least five (5) years’ experience in supporting the implementation of UNDP implemented projects, in particular environment and natural resource management projects.  This position will be financed by the Government of Samoa.

Environmental Lawyer

Three environmental lawyers will be recruited as a national consultant to undertake an in-depth analysis of Samoa’s environmental legislation, frameworks and policies for review and or updating.  Each will facilitate negotiations among line ministries on cooperative agreements facilitate targeted consultations and negotiations to implement Inter-Ministerial Council decisions as well as select monitoring and compliance.  In collaboration with other national consultants, he/she will, in collaboration with other national consultants, prepare a comprehensive training programme and targeted training modules to contribute to the preparation of the public awareness implementation plan and contribute to the preparation of articles on legislative responses for Rio Convention implementation.

Each Environmental Lawyer will have a post-graduate degree in law, with a specialization on environmental law, in particular the three Rio Conventions.  He/she will have a minimum of ten (10) years’ experience in progressively responsible and substantive areas in environmental and natural resource governance programming and planning.  Each of the selected individuals will have at participated substantively in the negotiations under either the FCCC, CBD, and CCD, and thus three separate environmental lawyers will be recruited under this TORs.  These three positions will be financed by the GEF grant, with additional co-financing from UNDP.

Knowledge Management and IT Communications Specialist

A knowledge management and IT communications specialist will be recruited to oversee the technical design of the Data, Knowledge and Information Facility (DKIF), including the procurement of the technological hardware and software for its installation.  Under the supervision of the Project Manager, he/she will work with the Data and Statistician Specialist as well as with the relevant information technology managers in the different departments to network the DKIF with their information systems.  The specialist will apply technical expertise to the implementation, monitoring, and maintenance of the DKIF.  With at least five (5) years’ of work experience, the specialist will have at least a Master’s degree in information technology, including network analysis, system administration, security and information assurance, IT audit, database administration, and web administration.

This position will be financed by the Government of Samoa.

International Evaluation Specialist

The international evaluation specialist will be an independent contractor with no conflict of interest in the performance of his or her duties, and will be contracted to assess the extent to which the project has met project objectives as stated in the project document and produced cost-effective deliverables.  The specialist will also rate capacities developed under the project using the Capacity Development Scorecard.

The Terms of Reference for the project evaluation specialist will follow the UNDP/GEF policies and procedures, and together with the final agenda will be agreed upon by the UNDP/GEF RCU, UNDP Multi-Country Office and the Project Team.  The final report will be cleared and accepted by UNDP (Country Office and Regional Coordination Unit) before being made public.

Data and Statistician Expert

A data and statistician specialist will be recruited to oversee the technical design of the DKIF, including the procurement of the technological hardware and software for its installation.  Under the supervision of the Project Manager, he/she will work with the Knowledge Management and IT Communications Specialist, as well as with the relevant data and information technology managers in the different departments to network the DKIF with their information systems.  The specialist will apply technical expertise to the implementation, monitoring, and maintenance of the DKIF.  With at least five (5) years’ of work experience, the specialist will have at least a Master’s degree in statistical analysis technology, including software analysis, database and system administration, security and information assurance, IT audit, database administration, and web administration.  This position will be financed by the GEF grant with additional co-financing from UNDP.

Monitoring and Evaluation Specialist

A monitoring and evaluation specialist will be recruited to ensure project compliance with corporate programme and project management requirements (including planning, M & E and reporting), as well as effectively monitor and report on the country programme and related project in support of partnership-building and resource mobilization.  He/she will design and implement a Medium-Term Expenditure Framework to align with government budgetary systems and will manage audit and evaluation policies, strategies and processes, and build and share knowledge regarding monitoring and evaluation across all relevant sectors and the community.  This project management position will be financed by UNDP.

With at least five (5) years of experience in Business Administration, Public Administration, Economics, Political Sciences, Social Sciences or a related field, the specialist will have at least a Master’s degree or bachelor’s degree with 7 years of experience.  Five (5) years of post-Master’s relevant experience at the national or international level in monitoring and evaluation, including hands-on experience in design, monitoring and evaluation or development projects and creating relationships with partners; experience with computers and office software, experience in handling web based-management systems.

Annex 6:	PDF/PPG Status Report

status of implementation of project preparation activities and the use of funds

provide detailed funding amount of the ppg activities financing status in the table below:

The activities undertaken within the framework of PPG were directed towards the design and development of the medium size project “Capacity for Implementing Rio Conventions in Samoa”.

The project preparation stage envisioned the preparation of background assessments on the institutional context associated with managing data and information for decision-making on environmental issues, with a particular focus on the Rio Conventions.  Consultations were held with various stakeholders to compare and contrast challenges and barriers to data and information management for decision-making.

The validation workshop was a particular useful exercise. It has been well-attended by a good cross-section of stakeholders, who vetted project activities.  All of these consultations and background assessments contributed to the drafting of the project document by national consultant under the guidance of an international consultant, in consultation with the Government of Samoa.

These outputs were funded by GEF resources, with the table below specifying how much of PPG funds were disbursed at the time of submission for approval.

A.1:  describe findings that might affect the project design or any concerns on project implementation, if any:

The findings obtained during the preparatory phase confirmed that the approach identified during the PIF stage remains valid.  Participants at the validation workshop reaffirmed their interest and commitment to the project.

| PPG Grant approved at PIF: |  |  |  |
| --- | --- | --- | --- |
| Project Preparation Activities Implemented | GEF Amount ($) |  |  |
|  | Budgeted Amount ($) | Amount Spent to date($) | Amount Committed ($) |
| Background analysis of Rio conventions tools and mechanisms | 7,500 | 4,113 | 3,387 |
| Background analysis of mainstreaming Rio conventions into key nationals and environmental plans and strategies | 7,500 | 4,113 | 3,387 |
| Project strategy, detailed budget, work plan, and logical framework: costs will be basically one international expert for five weeks | 5,000 | 0 | 5,000 |
| PPG Management: costs will be basically one national expert for four months, plus one validation workshop, plus communications, printing (all activities) | 5,000 | 1,178 | 3,822 |
| Total | 25,000 | 9,404 | 15,596 |

## Annex 7:	Environmental and Social Review Criteria

QUESTION 1:

Has a combined environmental and social assessment/review that covers the proposed project already been completed by implementing partners or donor(s)? Select answer below and follow instructions: NO Continue to Question 2 (do not fill out Table 1.1) - YES No further environmental and social review is required if the existing documentation meets UNDP’s quality assurance standards, and environmental and social management recommendations are integrated into the project. Therefore, you should undertake the following steps to complete the screening process: 1. Use Table 1.1 below to assess existing documentation. (It is recommended that this assessment be undertaken jointly by the Project Developer and other relevant Focal Points in the office or Bureau). 2. Ensure that the Project Document incorporates the recommendations made in the implementing partner’s environmental and social review. 3. Summarize the relevant information contained in the implementing partner’s environmental and social review in Annex A.2 of this Screening Template, selecting Category 1. 4. Submit Annex A to the PAC, along with other relevant documentation.

| TABLE 1.1: CHECKLIST FOR APPRAISING QUALITY ASSURANCE OF EXISTING ENVIRONMENTAL AND SOCIAL ASSESSMENT | Yes/No |
| --- | --- |
| 1. Does the assessment/review meet its terms of reference, both procedurally and substantively? | N/A |
| 2. Does the assessment/review provide a satisfactory assessment of the proposed project? | N/A |
| 3. Does the assessment/review contain the information required for decision-making? | N/A |
| 4. Does the assessment/review describe specific environmental and social management measures (e.g., mitigation, monitoring, advocacy, and capacity development measures)? | N/A |
| 5. Does the assessment/review identify capacity needs of the institutions responsible for implementing environmental and social management issues? | N/A |
| 6. Was the assessment/review developed through a consultative process with strong stakeholder engagement, including the view of men and women? | N/A |
| 7. Does the assessment/review assess the adequacy of the cost of and financing arrangements for environmental and social management issues? | N/A |
| Table 1.1 (continued) For any “no” answers, describe below how the issue has been or will be resolved (e.g., amendments made or supplemental review conducted). |  |
| N/A |  |

QUESTION 2:

Do all outputs and activities described in the Project Document fall within the following categories? - Procurement (in which case UNDP’s Procurement Ethics and Environmental Procurement Guide need to be complied with) - Report preparation - Training - Event/workshop/meeting/conference (refer to Green Meeting Guide) - Communication and dissemination of results Select answer below and follow instructions: NO Continue to Question 3 - YES No further environmental and social review required. Complete Annex A.2, selecting Category 1, and submit the completed template (Annex A) to the PAC.

QUESTION 3:

Does the proposed project include activities and outputs that support upstream planning processes that potentially pose environmental and social impacts or are vulnerable to environmental and social change (refer to Table 3.1 for examples)? (Note that upstream planning processes can occur at global, regional, national, local and sectoral levels) Select the appropriate answer and follow instructions: - NO Continue to Question 4. YES Conduct the following steps to complete the screening process: 1. Adjust the project design as needed to incorporate UNDP support to the country(ies), to ensure that environmental and social issues are appropriately considered during the upstream planning process. Refer to Section 7 of this Guidance for elaboration of environmental and social mainstreaming services, tools, guidance and approaches that may be used. 2. Summarize environmental and social mainstreaming support in Annex A.2, Section C of the Screening Template and select ”Category 2”. 3. If the proposed project ONLY includes upstream planning processes then screening is complete, and you should submit the completed Environmental and Social Screening Template (Annex A) to the PAC. If downstream implementation activities are also included in the project then continue to Question 4.

| TABLE 3. 1 EXAMPLES OF UPSTREAM PLANNING PROCESSES WITH POTENTIAL DOWNSTREAM ENVIRONMENTAL AND SOCIAL IMPACTS | Check appropriate box(es) below |
| --- | --- |
| - Support for the elaboration or revision of global-level strategies, policies, plans, and programmes. For example, capacity development and support related to international negotiations and agreements. Other examples might include a global water governance project or a global MDG project. |  |
| - Support for the elaboration or revision of regional-level strategies, policies and plans, and programmes. For example, capacity development and support related to transboundary programmes and planning (river basin management, migration, international waters, energy development and access, climate change adaptation etc.). |  |
| 3. Support for the elaboration or revision of national-level strategies, policies, plans and programmes. For example, capacity development and support related to national development policies, plans, strategies and budgets, MDG-based plans and strategies (e.g., PRS/PRSPs, NAMAs), sector plans. | √ |
| 4. Support for the elaboration or revision of sub-national/local-level strategies, polices, plans and programmes. For example, capacity development and support for district and local level development plans and regulatory frameworks, urban plans, land use development plans, sector plans, provincial development plans, provision of services, investment funds, technical guidelines and methods, stakeholder engagement. | √ |

QUESTION 4:

Does the proposed project include the implementation of downstream activities that potentially pose environmental and social impacts or are vulnerable to environmental and social change? To answer this question, you should first complete Table 4.1 by selecting appropriate answers. If you answer “No” or “Not Applicable” to all questions in Table 4.1 then the answer to Question 4 is “NO.” If you answer “Yes” to any questions in Table 4.1 (even one “Yes” can indicated a significant issue that needs to be addressed through further review and management) then the answer to Question 4 is “YES”: NO No further environmental and social review and management required for downstream activities. Complete Annex A.2 by selecting “Category 1”, and submit the Environmental and Social Screening Template to the PAC. YES Conduct the following steps to complete the screening process: 1. Consult Section 8 of this Guidance, to determine the extent of further environmental and social review and management that might be required for the project. 2. Revise the Project Document to incorporate environmental and social management measures. Where further environmental and social review and management activity cannot be undertaken prior to the PAC, a plan for undertaking such review and management activity within an acceptable period of time, post-PAC approval (e.g., as the first phase of the project) should be outlined in Annex A.2. 3. Select “Category 3” in Annex A.2, and submit the completed Environmental and Social Screening Template (Annex A) and relevant documentation to the PAC.

| TABLE 4.1: ADDITIONAL SCREENING QUESTIONS TO DETERMINE THE NEED AND POSSIBLE EXTENT OF FURTHER ENVIRONMENTAL AND SOCIAL REVIEW AND MANAGEMENT |  |
| --- | --- |
| 1. Biodiversity and Natural Resources | Answer (Yes/No/ Not Applicable) |
| 1.1 Would the proposed project result in the conversion or degradation of modified habitat, natural habitat or critical habitat? | No |
| 1.2 Are any development activities proposed within a legally protected area (e.g., natural reserve, national park) for the protection or conservation of biodiversity? | No |
| 1.3 Would the proposed project pose a risk of introducing invasive alien species? | No |
| 1.4 Does the project involve natural forest harvesting or plantation development without an independent forest certification system for sustainable forest management (e.g., PEFC, the Forest Stewardship Council certification systems, or processes established or accepted by the relevant National Environmental Authority)? | No |
| 1.5 Does the project involve the production and harvesting of fish populations or other aquatic species without an accepted system of independent certification to ensure sustainability (e.g., the Marine Stewardship Council certification system, certifications, standards, or processes established or accepted by the relevant National Environmental Authority)? | No |
| 1.6 Does the project involve significant extraction, diversion or containment of surface or ground water? For example, construction of dams, reservoirs, river basin developments, groundwater extraction. | No |
| 1.7 Does the project pose a risk of degrading soils? | No |
| 2. Pollution | Answer (Yes/No/ Not Applicable) |
| 2.1 Would the proposed project result in the release of pollutants to the environment due to routine or non-routine circumstances with the potential for adverse local, regional, and transboundary impacts? | No |
| 2.2 Would the proposed project result in the generation of waste that cannot be recovered, reused, or disposed of in an environmentally and socially sound manner? | No |
| 2.3 Will the propose project involve the manufacture, trade, release, and/or use of chemicals and hazardous materials subject to international action bans or phase-outs? For example, DDT, PCBs and other chemicals listed in international conventions such as the Stockholm Convention on Persistent Organic Pollutants, or the Montreal Protocol. | No |
| 2.4 Is there a potential for the release, in the environment, of hazardous materials resulting from their production, transportation, handling, storage and use for project activities? | No |
| 2.5 Will the proposed project involve the application of pesticides that have a known negative effect on the environment or human health? | No |
| 3. Climate Change |  |
| 3.1 Will the proposed project result in significant greenhouse gas emissions? Annex E provides additional guidance for answering this question. | No |
| 3.2 Is the proposed project likely to directly or indirectly increase environmental and social vulnerability to climate change now or in the future (also known as maladaptive practices)? You can refer to the additional guidance in Annex C to help you answer this question. For example, a project that would involve indirectly removing mangroves from coastal zones or encouraging land use plans that would suggest building houses on floodplains could increase the surrounding population’s vulnerability to climate change, specifically flooding. | No |
| 4. Social Equity and Equality | Answer (Yes/No/ Not Applicable) |
| 4.1 Would the proposed project have environmental and social impacts that could affect indigenous people or other vulnerable groups? | No |
| 4.2 Is the project likely to significantly impact gender equality and women’s empowerment? | No |
| 4.3 Is the proposed project likely to directly or indirectly increase social inequalities now or in the future? | No |
| 4.4 Will the proposed project have variable impacts on women and men, different ethnic groups, social classes? | No |
| 4.5 Have there been challenges in engaging women and other certain key groups of stakeholders in the project design process? | No |
| 4.6 Will the project have specific human rights implications for vulnerable groups? | No |
| 5. Demographics | No |
| 5.1 Is the project likely to result in a substantial influx of people into the affected community(ies)? | No |
| 5.2 Would the proposed project result in substantial voluntary or involuntary resettlement of populations? For example, projects with environmental and social benefits (e.g., protected areas, climate change adaptation) that impact human settlements, and certain disadvantaged groups within these settlements in particular. | No |
| 5.3 Would the proposed project lead to significant population density increase that could affect the environmental and social sustainability of the project? For example, a project aiming at financing tourism infrastructure in a specific area (e.g., coastal zone, mountain) could lead to significant population density increase that could have serious environmental and social impacts (e.g., destruction of the area’s ecology, noise pollution, waste management problems, greater work burden on women). | No |
| - Culture |  |
| 6.1 Is the project likely to significantly affect the cultural traditions of affected communities, including gender-based roles? | No |
| 6.2 Will the proposed project result in physical interventions (during construction or implementation) that would affect areas that have known physical or cultural significance to indigenous groups and other communities with settled recognized cultural claims? | No |
| 6.3 Would the proposed project produce a physical “splintering” of a community? For example, through the construction of a road, power line, or dam that divides a community. | No |
| - Health and Safety |  |
| 7.1 Would the proposed project be susceptible to or lead to increased vulnerability to earthquakes, subsidence, landslides, erosion, flooding or extreme climatic conditions? For example, development projects located within a floodplain or landslide prone area. | No |
| 7.2 Will the project result in increased health risks as a result of a change in living and working conditions? In particular, will it have the potential to lead to an increase in HIV/AIDS infection? | No |
| 7.3 Will the proposed project require additional health services including testing? | No |
| - Socio-Economics |  |
| 8.1 Is the proposed project likely to have impacts that could affect women’s and men’s ability to use, develop and protect natural resources and other natural capital assets? For example, activities that could lead to natural resources degradation or depletion in communities who depend on these resources for their development, livelihoods, and well-being? | No |
| 8.2 Is the proposed project likely to significantly affect land tenure arrangements and/or traditional cultural ownership patterns? | No |
| 8.3 Is the proposed project likely to negatively affect the income levels or employment opportunities of vulnerable groups? | No |
| 9. Cumulative and/or Secondary Impacts | Answer (Yes/No/ Not Applicable) |
| 9.1 Is the proposed project location subject to currently approved land use plans (e.g., roads, settlements), which could affect the environmental and social sustainability of the project? For example, future plans for urban growth, industrial development, transportation infrastructure, etc. | No |
| 9.2 Would the proposed project result in secondary or consequential development that could lead to environmental and social effects, or would it have potential to generate cumulative impacts with other known existing or planned activities in the area? For example, a new road through forested land will generate direct environmental and social impacts through the cutting of forest and earthworks associated with construction and potential relocation of inhabitants. These are direct impacts. In addition, however, the new road would likely also bring new commercial and domestic development (houses, shops, businesses). In turn, these will generate indirect impacts. (Sometimes these are termed “secondary” or “consequential” impacts). Or if there are similar developments planned in the same forested area then cumulative impacts need to be considered. | No |

ANNEX A.2:  ENVIRONMENTAL AND SOCIAL SCREENING SUMMARY

(To be filled in after Annex A.1 has been completed)

Name of Proposed Project:	Capacity for Implementing Rio Conventions in Samoa

A.  Environmental and Social Screening Outcome

Select from the following:

- Category 1.  No further action is needed

- Category 2.  Further review and management is needed.  There are possible environmental and social benefits, impacts, and/or risks associated with the project (or specific project component), but these are predominantly indirect or very long-term and so extremely difficult or impossible to directly identify and assess.

- Category 3.  Further review and management is needed, and it is possible to identify these with a reasonable degree of certainty.  If Category 3, select one or more of the following sub-categories:

- Category 3a: Impacts and risks are limited in scale and can be identified with a reasonable degree of certainty and can often be handled through application of standard best practice, but require some minimal or targeted further review and assessment to identify and evaluate whether there is a need for a full environmental and social assessment (in which case the project would move to Category 3b).

- Category 3b: Impacts and risks may well be significant, and so full environmental and social assessment is required.  In these cases, a scoping exercise will need to be conducted to identify the level and approach of assessment that is most appropriate.

B.  Environmental and Social Issues (for projects requiring further environmental and social review and management)

In this section, you should list the key potential environmental and social issues raised by this project.  This might include both environmental and social opportunities that could be seized on to strengthen the project, as well as risks that need to be managed.  You should use the answers you provided in Table 4.1 as the basis for this summary, as well as any further review and management that is conducted.

There are no real negative social impacts of this project, which is largely about facilitating a broad engagement of stakeholders from key government departments, corporations, as well as civil society and the wider communities to agree on the collection, analysis and sharing of data and information.  The project also attempts to build the capacity of decision makers through the use of policy dialogues and targeted trainings so parliamentarians are more conducive to mainstreaming environment into the national socio-economic and development priorities.   The project will provide technical training on good/best practices to collect and manage data, and most importantly undertake learn-by-doing exercises to encourage critical thinking on the use of data and information in the assessment and monitoring of development policies and plans from a stronger global environmental perspective.  Women will be encouraged to participate in the training workshops and learn-by-doing exercises.

C.  Next Steps (for projects requiring further environmental and social review and management):

In this section, you should summarize actions that will be taken to deal with the above-listed issues.  If your project has Category 2 or 3 components, then appropriate next steps will likely involve further environmental and social review and management, and the outcomes of this work should also be summarized here.  Relevant guidance should be obtained from Section 7 for Category 2, and Section 8 for Category 3.

Further environmental and social review and management is recommended to ensure that the project is being adaptively and collaboratively managed, as this is critical to project success.  The fragmentation of data and systems upon which information is collected, managed and shared is a key underlying barrier to the proper monitoring, assessment and implementation of global obligations in Samoa.  This project therefore targets the strengthening of a centralized information, knowledge management and sharing unit that will help provide for better implementation, reporting and monitoring of Rio Convention obligations.

The risk to this project is that stakeholders do not have strong environmental values and may become disinterested.  The project will manage this risk by convening a mixture of specialized trainings and general awareness-raising meetings and workshops, among other means to actively engage stakeholders.

The project’s design also sets out to shorten the divide between protecting the environment and socio-economic priorities.  This is to be achieved through mainstreaming.  The integration of global issues and benefits into Samoa’s development plan would ensure Samoa pursues priority socio-economic development that also achieves global environmental priorities.  The use of policy dialogues, parliamentary-focused workshops and trainings, learn-by-doing exercises that stakeholders will ensure the various affected stakeholders will know how to reconcile priority socio-economic priorities with global environmental obligations.

The project will take an adaptive collaborative management approach to ensure that project activities remain appropriate to meeting long-term objectives.  This approach is designed to strengthen the legitimacy of project activities throughout its implementation with stakeholders.

D.  Sign Off

Project Manager:  Ms. Anne Trevor                     Date: 13/5/2014

PAC: Mr. Jaime De Aguinaga	                                Date: 2/5/2014

Programme Manager: Mr. Jaime De Aguinaga   Date: 13/5/2014

## Annex 8:	Draft Letter of Agreement (LoA)

STANDARD LETTER OF AGREEMENT (LOA) BETWEEN UNDP AND THE GOVERNMENT OF SAMOA FOR THE PROVISION OF SUPPORT SERVICES FOR THE RIO PLUS ENABLING ACTIVITY “CAPACITY FOR IMPLEMENTING RIO CONVENTIONS IN SAMOA”

Mr. Aiono Mose Pouvi Sua,

1.	Reference is made to consultations between officials of the Government of Samoa (hereinafter referred to as “the Government”) and officials of UNDP with respect to the provision of support services by the UNDP country office for nationally managed programmes and projects.  UNDP and the Government hereby agree that the UNDP Multi-Country Office may provide such support services at the request of the Government through its institution designated in the relevant programme support document or project document, as described below.

2.	The UNDP country office may provide support services for assistance with reporting requirements and direct payment.  In providing such support services, the UNDP country office shall ensure that the capacity of the Government-designated institution is strengthened to enable it to carry out such activities directly.  The costs incurred by the UNDP country office in providing such support services shall be recovered from the administrative budget of the office.

3.	The UNDP country office may provide, at the request of the designated institution, the following support services for the activities of the programme/project:

(a)	Identification and/or recruitment of project and programme personnel;

(b)	Identification and facilitation of training activities;

(c)	Procurement of goods and services;

4.	The procurement of goods and services and the recruitment of project and programme personnel by the UNDP country office shall be in accordance with the UNDP regulations, rules, policies and procedures.  Support services described in paragraph 3 above shall be detailed in an annex to the programme support document or project document, in the form provided in the Attachment hereto.  If the requirements for support services by the country office change during the life of a programme or project,

_____________________

Aiono Mose Pouvi Sua

Chief Executive Officer

Ministry of Foreign Affairs and Trade

08 April 2014

the annex to the programme support document or project document is revised with the mutual agreement of the UNDP resident representative and the designated institution.

5.	The relevant provisions of the Standard Basic Assistance Agreement from the 5th of September 2008 (the “SBAA”), including the provisions on liability and privileges and immunities, shall apply to the provision of such support services. The Government shall retain overall responsibility for the nationally managed programme or project through its designated institution.  The responsibility of the UNDP country office for the provision of the support services described herein shall be limited to the provision of such support services detailed in the annex to the programme support document or project document.

6.	Any claim or dispute arising under or in connection with the provision of support services by the UNDP country office in accordance with this letter shall be handled pursuant to the relevant provisions of the SBAA.

7.	The manner and method of cost-recovery by the UNDP country office in providing the support services described in paragraph 3 above shall be specified in the annex to the programme support document or project document.

8.	The UNDP country office shall submit progress reports on the support services provided and shall report on the costs reimbursed in providing such services, as may be required.

9.	Any modification of the present arrangements shall be effected by mutual written agreement of the parties hereto.

10.	If you are in agreement with the provisions set forth above, please sign and return to this office two signed copies of this letter.  Upon your signature, this letter shall constitute an agreement between your Government and UNDP on the terms and conditions for the provision of support services by the UNDP country office for nationally managed programmes and projects.

Yours sincerely,

________________________

Signed on behalf of UNDP

Lizbeth Cullity

UN Resident Coordinator and UNDP Resident Representative

for Cook Islands, Niue, Samoa and Tokelau

_____________________

Aiono Mose Pouvi Sua

Chief Executive Officer

Ministry of Foreign Affairs and Trade

08 April 2014

Attachment to the LoA

DESCRIPTION OF UNDP COUNTRY OFFICE SUPPORT SERVICES

1.	Reference is made to consultations between the Ministry of Natural Resources and Environment, the institution designated by the Government of Samoa and officials of UNDP with respect to the provision of support services by the UNDP country office for the nationally managed programme: “Capacity for implementing Rio Conventions in Samoa”

2.	In accordance with the provisions of the letter of agreement signed on the 07th of April 2014 and the project document the UNDP country office shall provide support services for the Programme as described below.

3.	Support services to be provided:

The Government may request Implementation Support Services (ISS) from UNDP.  These are services provided by UNDP Country Offices in the implementation of regular and other resource-funded programmes and projects and include:

- Support to the preparation and submission of project proposals, revisions and related tasks

- Payments, disbursements and other financial transactions

- Recruitment of staff, project personnel, and consultants contracting and trainings, as needed

- Procurement of services and goods, including disposal

- Organization of training activities, conferences, and workshops, including fellowships

- Travel authorization, visa requests, support ticketing, and travel arrangements and transportation

- Shipment, custom clearance, vehicle registration, and accreditation

- Support to the preparation, documentation and response to NIM audits and UNDP or other donor required audits

- Support to the preparation, documentation and response to evaluations

- Support for the organization of missions into the country

- Support to the preparation of financial transactions (Financial Authorization and Certificate of Expenditures - FACE FORM), provision of specific finance transactions requested by the implemented partner and external access to ATLAS.

- Other similar implementation support services requested by the Implementing Partner.

Recovery of costs for such services will be calculated based on actual costs, in accordance with UNDP’s Cost Recovery Policy. When determining actual costs is not possible, the Universal Price List / Local Price List will be applied. The Annual Work Plans may specify in more detail the requested services and their associated cost on a yearly basis. In addition, the Implementing Partner may also request those services on ad hoc basis.

4.         Description of functions and responsibilities of the parties involved:

The Project will be implemented through UNDP’s National implementation Modality (NIM), with the Ministry of Natural Resources (MNRE) as the designated national executing agency (“Implementing Partner”) of the project. MNRE will have the technical and administrative responsibility for applying Global Environment Facility (GEF) inputs in order to reach the expected Outcomes/Outputs as defined in this project document. MNRE is responsible for the timely delivery of project inputs and outputs, and in this context, for the coordination of all other responsible parties, including other line ministries, local government authorities and/or UN agencies.

Upon the request of the Government of the Samoa, UNDP will serve as the Multilateral Implementing Agency (MIE) for this project. Services that UNDP will provide to the Implementing Partner in support of achieving project Outcomes will be provided by staff in the UNDP Multi-Country Office in Samoa, UNDP Pacific Centre in Suva, UNDP Asia Pacific Regional Centre in Bangkok (with a Regional Technical Advisor on Adaptation out-posted in Samoa) as well as UNDP Headquarters  in New York.

Additional Support Services to the Programme will be provided ONLY upon request to UNDP from the Implementing partner based on this LoA.

# PART III:	GEF Letters of Endorsement and Co-Financing

A.  Endorsement letter of PFO GEF; endorsement letters by convention focal points

B.  Letters of co-financing: each of the organizations will write a letter intending to fund a part of the project, either in-kind or in cash.

Letters are attached in a separate attachment.

MNRE (2013).  National Environment Sector Plan, Apia, Samoa

Ibid

GoS (2010).  Millennium Development Goals: Second progress report, Apia, Samoa

MNRE.  2013.  State of Environment Report, Apia, Samoa

Ibid

MNRE, 2013.  National Environment Sector Plan, Apia, Samoa

Ibid

MOF.  2010.  Energy review report, Apia, Samoa

GoS.  2012.  Strategy for the Development of Samoa 2012-2016, Apia, Samoa

Ibid

MNRE.  2013.  Summary review of the 1993 NEMS

These divisions include the following: Corporate Services, Disaster Management, Environment and Conservation, Global Environmental Facility (GEF), Forestry, Land Management, Legal Services, Meteorology, Planning of Urban Management Agency (PUMA), Renewable Energy, Technical Services, and Water Resources.

See World Bank Data, World Development Indicators: http://data.worldbank.org.

PIFS. 2013.  Climate finance: Strengthening capacity in the Pacific in Commonwealth Governance Handbook 2013-2014

See list of partner ministries/agencies in Table 1

UNDP/GEF/GoS.  [2010].  ICCRIFS : project document, Annex 1

Summary review of the 1993 NEMS, MNRE, 2013

Women in Business Development Inc.  [2012].  Annual report 2010-2011, Apia, Samoa

UNDP/MNRE. 2013.  Strengthening Multi-sectoral Management of Critical Landscapes : project document

MNRE.  2013.  Summary review of the 1993 NEMS

PPCR Situation Analysis, MOF, 2012

MNRE.  2013.  Status of communication outputs for the ICCRIFS Project.  Technical Report; no.5

MOF/World Bank.  2012.  PPCR Situation Analysis, Apia, Samoa

See GEF (2012), GEF Policy on Gender Mainstreaming, PL/SD/02, 7pp and (GEF (2014)Mainstreaming Gender at the GEF, 58pp, http://www.thegef.org/gef/gender

See http://www.undp.org/content/undp/en/home/librarypage/operations1/environmental-and-social-screening-procedure-for-UNDP-projects.html

The Project Management Unit (PMU) will be an administrative extension of the MNRE Corporate Services Division, with technical support from the Environment Sector Coordinator, Legal and Rio Convention Focal Points.

Includes Environmental Lawyer, Environment Sector Coordinator, Rio Convention Focal Points

GEF/UNDP/NIWA.  [2014].  Climate services to agriculture through the Climate Early Warning System (CLEWS) : [draft brochure]

MNRE/NHS/MOH.  [2014].  GEF/UNDP Integrating Climate Change Risks in the Agriculture and Health Sectors in Samoa (ICCRAS&HSS): [Discussion sheet; draft2]

Meeting minutes includes records of key meetings such as the Project Board, TWG and national consultations regarding inputs on the design and implementation of the relevant output and associated activities.  Meetings may be individual or group meetings, with government officials, non-state actors, private and community representatives

Information acquired through pre & post questionnaires of workshops and trainings conducted

Targeting data owners, creators, keepers etc. of Rio Convention implementing agencies

Through targeted national survey

Targeted mainly through pre & post questionnaires of workshops and trainings conducted on mainstreaming Rio Conventions

Significant corresponds to CO2 emissions greater than 100,000 tons per year (from both direct and indirect sources).  Annex E provides additional guidance on calculating potential amounts of CO2 emissions.

Women are often more vulnerable than men to environmental degradation and resource scarcity.  They typically have weaker and insecure rights to the resources they manage (especially land), and spend longer hours on collection of water, firewood, etc.  (OECD, 2006).  Women are also more often excluded from other social, economic, and political development processes.