request for project preparation grant (PPG)

Project Type: FULL- SIZED PROJECT

the GEF Trust Fund

Submission date:  November 10, 2009

Re-submission date:   November 11, 2009

2nd re-submission date:   February 16, 2010

GEFSEC Project ID: 4080

GEF AGENCY PROJECT ID:  4313

COUNTRY (ies): Senegal

Project Title: SPWA - Participatory Conservation of Biodiversity and Low Carbon Development of Pilot Ecovillages Adjacent to Protected Areas in Senegal.

GEF Agency (ies): UNDP

Other Executing partner(s): National Ecovillages Agency (ANEV)

GEF Focal Area(s): Biodiversity & Climate Change

GEF-4 Strategic program(s): BDSP4-SFM3-CC

name of parent/program/umbrella project:  GEF Strategic Program for West Africa

a.   Project preparation Timeframe

| Start date | Mar-2010 |
| --- | --- |
| Completion date | Nov-2010 |

- Past project preparation activities ($)

n/a

- proposed project preparation activities ($)

Describe the PPG activities and justifications: The PPG process will focus on all the activities that are necessary for producing the information that will feed into the UNDP Project Document and the GEF CEO Endorsement Request for the Full-Size Project (FSP) SPWA - Participatory Conservation of Biodiversity and Low Carbon Development of Pilot Ecovillages at the Vicinity of Protected Areas in Senegal. Those will be submitted to the GEF at the end of the process, following due technical and financial clearance by the UNDP, and will be accompanied by co-financing confirmation letters. The PPG Team will take into consideration in project design any comments received from the GEF Secretariat, the GEF Council, STAP or any other relevant partner, and will be preparing a due response to those as part of the FSP for submission. The PPG activities during the preparatory phase will consolidate and supplement the existing information on the biophysical, technical and economic aspects of the Ecovillages’ concept. The project’s technical feasibility and economic viability will be assessed as well as the risks associated with the development of this new and innovative concept of sustainable rural development and participatory global environment conservation. The PPG activities include: 1. Pilot Site Selection, Socio-economic Analysis and Community Engagement Strategy Development In the approved PIF, it is suggested that seven project zones, within or adjacent to the territory (terroir) of some 35 villages, would be the object of gazettal through the category Community Natural Reserves (CNR). The zones would be selected for their ecological value (e.g. the Manatee Marsh in the Senegal River Valley which is an essential habitat for the manatees, the Niayes ecosystem harbouring several endemic plant species). These zones will be indicatively located in areas adjacent to three important protected areas (PAs) in Senegal: the Niokolo Koba National Park, the Saloum Delta Biosphere Reserve and the Ferlo Biome Reserve. Those villages are expected to form part of the group of Pilot Ecovillages, upon which the GEF project will concentrate. The PPG activities on site selection will contribute to: - Completing a national geographically-based Ecovillage database of existing and potential Ecovillages. The list will necessarily include the approximately 40 Ecovillages accredited by the national branch of the Global Ecovillage Network, GENSEN, as well as the Ecovillages where the National Ecovillage Agency (ANEV) is currently developing activities. The database will build on existing information on demographics and socio-economic data and generate new data through the field work to be carried out under this PPG. - A suitable set of criteria will be developed for the selection of Pilot Ecovillages for the project. These will necessarily include the sites’ potential to generate global environmental benefits with respect to biodiversity conservation and low-carbon local development plus other criteria as applicable. This is a very important element viz. the project’s overall feasibility, particularly in light of GEF Council comments received with respect to CNRs (given the current difficulties met by the Senegalese State to even manage core protected areas such as Niokolo-Koba), the alternative sources of energy that the project proposes and the risks of the project contributing to impoverishment of rural poor. - In a consultative and participatory fashion, the PPG Team will reach agreement with key stakeholders on the final selection of sites to be covered by the project (Pilot Ecovillages). The total number of proposed sites (35 at PIF stage) may be reconsidered as part of the task of scoping the project’s intervention with a view to its overall feasibility. The possibility of including ‘primary’ and ‘secondary’ sites, where the interventions differ in intensity, will be evaluated in this context. This is also to be carried out bearing in mind the mentioned critical comments received from the GEF Council. - Carry out the Ecovillages Survey. Selected sites will be surveyed on the ground for key socio-economic features and mapped. The assessment work will also serve to carry out consultations at the local level. - Initial proposals for the location, polygons and surface coverage for the CNRs and for alternative livelihoods activities (Jatropha curcas agrofuel development; mangrove regeneration; development of arboreta and massive afforestation) will be made. - Proposed CNRs will be named, in full consultation with resident communities, and the PA Management Effectiveness Tracking Tool (METT) will be completed for the proposed sites slated for PA gazettal. The PPG team will decide whether it is applicable or not to also include in ‘SO1 Tracking Tool’ the PA Financial Sustainability Scorecard, given the potentially limited contribution of CNRs to PA finance. Due justification will be provided. - The PPG team will equally assess the implications of considering CNRs (or some of them), and the co-management models to be engineered by the project, under the special PA category Indigenous Community Conservation Areas (ICCA). Special guidance from UNDP and the Convention on Biological Diversity applies in that case. 2. Baseline Data Collection and Information Gap Analysis The baseline data that will be collected, as well as other information to be researched and collated for the preparation of the FSP to the GEF can be subdivided into two major groups: (1) the ‘Biodiversity Baseline’ and (2) the ‘Energy, and Carbon baseline’. Yet, the Ecovillage model builds on an integrated approach to sustainable use of natural resources, biodiversity conservation, and efficient use of available sources of renewable energy in rural areas of Senegal. The distinction between these two groups is purely methodological and aimed mostly at organising the work of defining the baseline. The data collected and gap analysis will corroborate in an integrated manner to the conceptualisation of the project strategy. Biodiversity baseline: The biodiversity baseline will contribute to: (1) articulating the global biodiversity significance in the project; (2) analysing Senegal’s Protected Area System (ecosystem and surface coverage, management modalities) and identifying the gaps in it, as well as how the project proposes to contribute to the improvement of this system; (3) analysing the threats to biodiversity, the root causes and impacts; and (4) determining the conservation outcome of the project (i.e. the ecological indicators). More specifically, baseline studies will be conducted to: - Identify the current state of ecosystems and status of biological resources in the target PAs (i.e. the core parks and reserves) and in their buffer zones. - Identify direct threats to biodiversity, describing the impacts, and the root causes to the degradation of biological resources. Applicable threats will need to be grouped as belonging to the following categories: (i) Habitat / land use change; (ii) Overexploitation; (iii) Invasive Alien Species; (iv) Pollution; and/or (v) Climate Change. - Identify threatened species, with particular focus on population, distribution. - Propose a few but highly central ecological indicators for the project (e.g. deforestation trends, the local conservation status of keystone species), establish the baseline for these indicators and the targets by end of project (conservation outcome) which are to be achieved as a result of project the intervention. - Propose a functional, feasible and continual biodiversity monitoring system for Ecovillages: Establish the basis for a biodiversity monitoring system specifically tailored to the needs of CNRs, including the provision of baseline data for the targeted sites. An outline of TOR for the development of the full system during project implementation will be provided by the PPG Team. - Baseline mapping studies will be carried out to identify the boundaries of the target CNRs. The data will be presented in GIS mapping format and include information on the current state of land use and clearance (as determined by remote monitoring), water resources, land usage (including agriculture pasture, settlements), fauna and transhumance migration routes, types of vegetation, etc. This study will include analysis and mapping of existing rainfall data to assist with project climate change planning; - Baseline studies will be conducted on resource use, ownership, socio-economic conditions and trends in the target CNRs using rapid assessment methodologies. Particular attention will be paid to unsustainable resource use and potential alternative livelihood options for various Ecovillages as proposed in the PIF (e.g. Jatropha curcas agrofuel development, mangrove regeneration, development of arboreta and massive afforestation); and - Collection of baseline information for determining, during project implementation, the ecological carrying capacities and feasibility of the CNRs for ecotourism, hunting, fishing and harvesting of forest resources will be gathered and analysed. Energy and Carbon Baseline A preliminary assessment of energy and carbon, including current emissions patterns and the potential for emissions’ avoidance and carbon sequestration, will be carried out in selected and representative Pilot Ecovillages. More specifically this will entail: - Determine the energy profile and associated GHG emissions of a typical Ecovillage (typically using carbon assessment tool such as “Bilan Carbone”); - Assess the potential for a low carbon local development at the local level based on the energy and emissions profiles. Special attention to assess wood use for cooking and possible options to promote improved cookstove techniques.On the basis of vegetation maps and existing data on biocarbon sequestration, assess the potential of certain proposed alternative livelihoods activities to sequester carbon, in particular mangrove regeneration, development of arboreta and massive afforestation; - Based on the mapping exercise, which will indicate the total and potential land available for the development of Jatropha curcas agrofuel within Ecovillages’ territory, carry out a preliminary feasibility exercise for the activity as it is expected to be piloted by the project. This will be primarily based on existing economic and agronomic data for such agrofuel projects. The analysis will necessarily consider the implications of Jatropha curcas plantations to biodiversity and to food-security - Analyse low carbon options for energy efficiency services (solar, solar/wind grids, agrofuel, mini or micro-hydro, agrofuels). 3. Analyses of Policy and Legal Frameworks and Capacity Gaps - Current and proposed legal, policy and fiscal frameworks relevant for the development and implementation of the Ecovillage model in Senegal will be analysed, in particular as they either support or represent a barrier to achieving global environmental benefits through the model. These frameworks may refer to CNRs (as a PA category), as well as energy use, forestry agriculture, water or any other relevant sector. The legal, policy and fiscal frameworks will be reviewed to identify any gaps requiring additional work during the project. Particular attention will be paid to determining legislation required to implement the proposed changes to community management, land tenure, land usage, zoning or conservation enforcement required to establish effective community conservation areas, but equally to fiscal regulations that are relevant for the implementation of a low carbon development path at the local level and to carbon ownership (with respect to the prospects on generating local benefits from biocarbon). - The current institutional framework will be assessed. ANEV will be in the centre of the assessment, but it will equally focus on ANEV’s ability to engage with other government bodies (national and local), NGOs / CSO and, not least also, the private sector, for promoting the Ecovillage model and mobilising finance to it. Gaps in capacity will be identified and any changes in structure required may be recommended. - The roles and responsibilities of different stakeholders relevant to the Ecovillage model will be analysed. In particular, the capacity of local committees, village cooperatives, traditional leaders and other stakeholders (traders, NGOs, research centres, etc.) operating in Pilot Ecovillages will be analysed to determine any support needed for these actors to contribute to the project objective. - Co-financing and support letters will be pledged from several project partners. - The UNDP’s Capacity Development Scorecard and other relevant scorecards to measure civil society organisations’ capacity will be completed to establish a framework for measuring capacity and financial performance in community management of the selected Pilot Ecovillages, including the biodiversity aspects, as well as the low carbon development path and the biocarbon components. 4. Consolidation of the Ecovillage Model and Industry Engagement Strategy According to the approved PIF, the project’s global environment benefits that will arise from the removal of barriers to the effective application of an integrated approach to sustainable use of natural resources, biodiversity conservation, and efficient use of available sources of renewable energy in rural areas of Senegal through the Ecovillage model. However, this will need to be properly articulated in the project, at least through incremental reasoning and the inclusion of both the demonstration and replication potential of pilot sites as a criteria for their choice. Furthermore, Components 3 and 4 of the PIF have been specifically conceived to build on solid private sector investments, whereas the GEF will complement the increment. Still, much of the potential co-financing from the private sector remains to be leveraged. It is assumed that the involvement of the private sector will be facilitated, if the activities that private investors may be willing to finance are well designed and “fit” well with the overall project strategy. This PPG Activity will hence concentrate exactly on making the case for the GEF and for the private sector to finance the project as follows: - The strategy and key concepts underpinning the State-sponsored Ecovillage model will be formulated into a ‘Strategy Paper’ to be validated by a wide range of stakeholders. These concepts include e.g. the community PA co-management model to be operationalised through the CRNs, low carbon development path, energy self-sufficiency, among others. This brief and strategic paper will be also used to show how the private sector can find investment niches in the implementation of the model, in particular in Pilot Ecovillages. - Identify the niche for the GEF through the clear articulation of the incremental reasoning and the cost-effectiveness of the project. This will entail first and foremost the identification of an array of related projects, programmes and initiatives that compose the projects’ “baseline” and an analysis of the “business-as-usual” scenario. The key question to be answered is: “What would happen without the GEF?” Secondly, and based on the consolidated project strategy, the national and global benefits of the project will be outlined and distinguished. Finally, and considering the fit with the GEF’s Focal Area Strategy (which had already been considered at PIF stage), the cost-effectiveness approach will be analysed, by answering the question: “Would the project provide better value-for-money if done differently?” - Mobilise private-sector co-financing to the project by defining the niche and/or the economic case for private sector investment/involvement in the Ecovillage model, scoping and costing activities, where private sector investment/involvement can enlarge the scale and make a difference in terms of sustainable development in rural Senegal. This will be achieved through the preparation of brief feasibility analyses on the range of activities that were initially envisaged at PIF stage for public-private partnerships. These include the following and will, where applicable and to the extent possible, explore possibilities of developing Payment for Ecosystems Services (PES): - Tourism concessions - Carbon trading in the voluntary market - Briquetting or pelletizing process for non-woody biomass resources; and/or use of commercially available non-woody biomass fuel briquettes/pellets - Development of pilot “energy hubs” - Production, development and promotion of use of locally produced agrofuel from Jatropha curcas - Massive afforestation and the development of arboretums for indigenous and endemic species of global importance - Organic agriculture 5. Project Costing, Risk Assessment and M&E Planning Based on the above steps, project costs and risks will be assess and an M&E plan will be outlined, which will include analysis and identification of: - Summary of the local, national and global biodiversity benefits of the project; - A thorough analysis of the barriers to achieving the following project outcomes: - The governance framework for generating global environmental benefits from the implementation of the Ecovillage model - The establishment of demonstration activities through the gazettal and operationalisation of CNRs in Pilot Ecovillages adjacent to important PAs (including PA management effectiveness, livelihoods improvements, and removal of threats to globally significant biodiversity) - The systematic reduction of greenhouse gas emissions in key end-uses and strategy towards energy self-sufficiency in Pilot Ecovillages - The Strengthening capacities for carbon sequestration, integrated ecosystem management and nature-based climate change adaptation in territories adjacent to Ecovillages - Appropriate scoping of the project, based on the conceptual elements outlined in the PIF and the results of the PPG studies, where comments from GEF Council and GEF Secretariat will be specifically taken into account; - Identification of lead implementing partners and implementation arrangements, and a complementary strategy for partnerships and co-funding; - A learning (adaptive management) plan, including potential lessons and knowledge products; - A replication plan to ensure that project interventions are geared towards ensuring replication, following the removal of barriers; - An analysis of project risks and risk mitigation measures, including climate change associated risks; - A cost effectiveness analysis to identify the most effective project alternatives; - Analysis of the social, institutional, economic and financial sustainability of proposed project activities; and - An overall project Monitoring and Evaluation Plan, with recommendations on how to track the project’s progress and effectiveness, and the baseline and target values on indicators.

| ### List of Proposed Project Preparation Activities | ### Output of the PPG Activities | Project Preparation Amount ($) (a) | Co-financing ($) (b) * | Total c = a + b |
| --- | --- | --- | --- | --- |
| 1. Pilot Site Selection, Socio-economic Analysis and Community Engagement Strategy Development | Pilot Ecovillages determined and appropriately described | 43,000 | 41,200 | 84,200 |
| 2. Baseline Data Collection and Information Gap Analysis | Baseline and targets established for biodiversity, energy and carbon | 40,000 | 13,000 | 53,000 |
| 3. Analyses of Policy and Legal Frameworks and Capacity Gaps | Capacity of project partners is confirmed and gaps identified; policy, fiscal and regulatory frameworks for implementing the Ecovillages model are thoroughly described and analysed | 4,000 | 0 | 4,000 |
| 4. Consolidation of the Ecovillage Model and Industry Engagement Strategy | Consensus reached on project’s strategy and mechanisms for industry engagement | 25,000 | 16,000 | 41,000 |
| 5. Project Costing, Risk Assessment and M&E Planning | Full Project scoped and costed | 8,000 | 113,000 | 121,000 |
| Total Project Preparation Financing |  | 120,000 | 183,200 | 303,200 |

Note: * Of which $33,200 is the government’s and communities’ in-kind contribution and $150,000 is an in-cash contribution from UNDP to be managed directly in conjunction with GEF funds.

- Financing plan summary for project preparation grant: ($)

|  | Project Preparation | Agency Fee |
| --- | --- | --- |
| GEF financing | 120,000 | 12,000 |
| Co-financing | 183,200 |  |
| Total | 303,200 | 12,000 |

- PPG  requested by agency(ies), focal area(s) and country(ies)

| GEF Agency | Focal Area | Country Name/ Global | (in $) |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  |  | PPG (a) | Agency Fee (b) | Total c = a + b |
| UNDP | Biodiversity | Senegal | 80,000 | 8,000 | 88,000 |
| UNDP | Climate Change | Senegal | 40,000 | 4,000 | 44,000 |
| Total PPG Requested |  |  | 120,000 | 12,000 | 132,000 |

- PPG Budget Request

|  | Total Estimated Person Weeks (PW) - GEF only ** | GEF ($) | Co-financing ($)*** | Total ($) |
| --- | --- | --- | --- | --- |
| Local consultants* | 31 | 31,000 | 36,556 | 67,556 |
| International consultants* | 16 | 48,000 | 30,000 | 78,000 |
| Consultations: local and national |  | 0 | 10,000 | 10,000 |
| Supplies: Satellite images, datasets GIS equipment |  | 9,000 | 7,444 | 16,444 |
| Professional Services: translation and audit, but may also include publications, webdesign |  | 8,000 | 5,000 | 13,000 |
| Travel |  | 24,000 | 26,000 | 50,000 |
| Project vehicle |  | 0 | 35,000 | 35,000 |
| Other (Government's and communities' in-kind contribution) |  | 0 | 33,200 | 33,200 |
| Total PPG Budget |  | 120,000 | 183,200 | 303,200 |

Notes:

*   Additional information regarding consultants is provided in Annex A.

** Consultants’ rates in this proposal have been budgeted for at the higher end of the rates’ scale to better reflect, on the one hand, the scarcity of qualified local consultants and, on the other, the relative low value of the USD vis-a-vis the local currency CFA, which is pegged to the Euro. Split between local and International consultants is indicative and subject to procurement guidelines of Agencies and Governments. Consultants will be hired in line with UNDP rates. Also, in accordance with both UNDP and GEF policies, no GEF project resources will be used to pay any government, agency, or NGO staff personnel.

** * UNDP core funds will be managed in conjunction with GEF funds under the same budgetary award.

- GEF Agency (ies) Certification

This request has been prepared in accordance with GEF policies and procedures and meets the GEF criteria for project identification and preparation.

| Agency Coordinator, Agency name | Signature | Date | Project Contact Person | Telephone | Email Address |
| --- | --- | --- | --- | --- | --- |
| Yannick Glemarec UNDP/GEF Executive Coordinator |  | February 16, 2010 | For Biodiversity: Fabiana Issler, Regional Technical Advisor | + 27 12 354 8128 | fabiana.issler@undp.org |
|  |  |  | For Climate Change Mitigation: Benoît Lebot, Regional Technical Advisor | + 221 33 869 06 76 | benoit.lebot@undp.org |

Annex A

Consultants Financed by the Project Preparation Grant (PPG)

| Position / Titles | $/ Person week1 | Estimated # of weeks | Tasks to be performed |
| --- | --- | --- | --- |
| Local |  |  |  |
| Mapping Expert | 1,000 | 8.0 Financed by GEF | The consultant will lead in the production of the following PPG deliverables: - Developing a national geographically-based Ecovillage database and populating it with baseline data - Detailed mapping of Pilot Ecovillages, including proposals for the location, size and polygon for CNRs In addition, the consultant will: (1) Assist in Defining a suitable set of criteria the choice will be developed for the selection of Pilot Ecovillages for the project (2) Complete baseline mapping of Ecovillages, including the boundaries of target sites and Community Natural Reserves (CNR), and establish procedures for boundary identification and demarcation to be carried out under the project; and (3) Ensure that key information from the Ecovillage Mapping, Survey and Assessment is captured in GIS (4) Produce key maps of Sacred Forests in Benin in applicable scales for use by the project |
| Biodiversity Expert | 1,000 | 4.0 Financed by GEF | The consultant will co-lead, in close collaboration with the international Protected Areas & Alternative Livelihoods Specialist, in the production of the following PPG deliverables: - Application of the Protected Area Management Effectiveness Tracking Tool (METT) for the Community Natural Reserves (CNR), to be targeted by the project - Biodiversity threat analysis - Development of ecological indicators and definition of baseline and targets - Design of TOR for the development and implementation of a BD monitoring system to be managed by the National Ecovillages Agency (ANEV) - Development of brief feasibility analyses on the range of activities that were initially envisaged at PIF stage for public-private partnerships (refer to PPG paragraph 14). In addition, the consultant will: (1) Play a key role in all of the baseline studies for what biodiversity aspects are concerned, namely the articulation of threats and global benefits and an analysis of Senegal’s Protected Area System (2) On the threats’ assessment, identify and produce lists threatened species (both flora and fauna) for population studies in the target sites; (3) Make recommendations for relevant project activities and their costing |
| Energy Expert | 1,000 | 4.0 Financed by GEF | The consultant will co-lead, in close collaboration with the international Climate Change Mitigation & Carbon Specialist, in the production of the following PPG deliverables: - Development of energy profiles for typical Ecovillages - Determine the potential for a low carbon development path at the local level - Feasibility analysis and project costing for the development of Jathropha curcas plantations, of low carbon energy services and for the development of endemics' arboreta and massive afforestation - Development of brief feasibility analyses on the range of activities that were initially envisaged at PIF stage for public-private partnerships (refer to PPG paragraph 14). In addition, the consultant will: (1) Review and summarize existing policies, legislative and regulatory frameworks for the adoption of low carbon energy solution for rural communities; (2) Provide analysis on the level of investments needed for the installation of clean energy solution (3) Contribute to Ecovillages project strategic framing; (4) Identify potential zones for solar/wind/hydro/agrofuel production; (5) Facilitate discussion with private sector and industrial business groups interested in partnering with the project |
| Forestry Expert | 1,000 | 3.0 Financed by GEF | The consultant will make a specific and technical contribution to the production of the following PPG deliverables from a forestry point of view: - Feasibility analysis and project costing for development of endemics' arboreta and massive afforestation activities - Development of brief feasibility analyses on the range of activities that were initially envisaged at PIF stage for public-private partnerships (refer to PPG paragraph 14). Detailed calculations are expected to be provided, as well as recommendations for the use of appropriate species with due consideration for environmental, biodiversity and GHG emissions’ impacts. The consultant will work together with the following national and international experts/specialists in the fulfilment of the above task: (i) Mapping Expert; (ii) Biodiversity Expert; (iii) Energy Expert; (iv) Agronomist; (v) Socio-Economist; (vi) Intl. Protected Areas & Alternative Livelihoods Specialist; and (vii) Environment Economist |
| Agronomist | 1,000 | 3.0 Financed by GEF | The consultant will make a specific and technical contribution to the production of the following PPG deliverables from a forestry point of view: - Feasibility analysis and project costing for the development of Jathropha curcas plantations - Development of brief feasibility analyses on the range of activities that were initially envisaged at PIF stage for public-private partnerships (refer to PPG paragraph 14). Detailed calculations are expected to be provided, as well as recommendations for the use of appropriate cultivars with due consideration for environmental, biodiversity and GHG emissions’ impacts. The consultant will work together with the following national and international experts/specialists in the fulfilment of the above task: (i) Mapping Expert; (ii) Biodiversity Expert; (iii) Energy Expert; (iv) Agronomist; (v) Socio-Economist; (vi) Intl. Climate Change Mitigation & Carbon Specialist; and (vii) Environment Economist |
| Socio-Economist | 1,000 | 5.0 Financed by GEF | The consultant will provide a substantive contribution in the production of the following PPG deliverables: - Developing a national geographically-based Ecovillage database and populating it with baseline data - Defining a suitable set of criteria the choice will be developed for the selection of Pilot Ecovillages for the project - Determine the potential for a low carbon development path at the local level - Feasibility analysis and project costing for the development of Jathropha curcas plantations, of low carbon energy services and for the development of endemics' arboreta and massive afforestation - Development of Ecovillage Concept Paper - Development of brief feasibility analyses on the range of activities that were initially envisaged at PIF stage for public-private partnerships (refer to PPG paragraph 14). In addition, the consultant will: (1) Work together with the remainder PPG experts/ specialists to develop partnership agreements with specialized research centers (national and international) in connection with the ecological monitoring, the forestry and agricultural components and the energy/low carbon components of the project (2) Contribute to the analysis of fiscal aspects of the legal and policy frameworks that will be analysed in the context of the PPG (3) Assess, in consultation with the Policy, Legal & Institutional Expert and other PPG experts/specialists, any relevant legal and fiscal issues (e.g. ownership, including land and carbon ownership, responsibility for maintenance, insurance etc.) that might negatively affect implementation of the following project activities: development of Jathropha curcas plantations, of low carbon energy services and for the development of endemics' arboreta and massive (4) Make recommendations for relevant project activities and their costing (5) Be the lead focal point in the ground surveying of Ecovillages |
| Policy, Legal & Institutional Expert | 1,000 | 4.0 Financed by GEF | The consultant will lead in the production of the following PPG deliverables: - Policy, legal and institutional assessment - Capacity gap analysis of project's implementation stakeholders (incl. application of scorecards) In addition, the consultant will: (1) Current and proposed legal, policy and fiscal frameworks pertaining to either Ecovillages, protected areas, decentralized NRM or energy (including energy use), forestry agriculture, water or any other relevant sector, will be reviewed to assess whether support or represent a barrier to achieving global environmental benefits through the Ecovillages model (2) Identify any gaps requiring additional work during the project in order to establish legal recognition of Community Natural Reserves (CNR) (2) Determine the legislation required to implement the proposed changes to natural resources, energy use, community co-management, land tenure, land usage, and zoning or conservation enforcement required to establish effective demonstration Ecovillages in Pilot Sites. (5) Assess, in consultation with the Socio-economist and other PPG experts/specialists, any relevant legal and fiscal issues (e.g. ownership, including land and carbon ownership, responsibility for maintenance, insurance etc.) that might negatively affect implementation of the following project activities: development of Jathropha curcas plantations, of low carbon energy services and for the development of endemics' arboreta and massive afforestation (4) Assist in designing the Ecovillages Survey and Assessment (5) Make recommendations for relevant project activities, their costing and in particular the project’s management arrangements, as per requirements in a UNDP PRODOC. |
| Stakeholder Engagement Expert / Activity Coordinator (co-financing) | 700 | 27.0 Financed by UNDP Core Funds (TRAC) | Functioning as the national activity coordinator, the incumbent will: (1) Analyze current and completed projects to determine lessons learned and identify areas that can be replicated in the current project; (2) Conduct stakeholder analysis for the development of the Ecovillages model; (3) Indentify capacity barriers and capacity building needs; (4) Recommendations for coordinated national, regional and local management of Ecovillages (5) Identify opportunities for public-private partnerships; (6) Assist in the mobilization of co-financing; and (7) Develop stakeholder participation and engagement plans for project (8) Play a key role in developing the partnership agreement with specialized research centers (national and international) in connection with the ecological monitoring, the forestry and agricultural components and the energy/low carbon components of the project (9) Assist in designing the Ecovillages Survey and Assessment (10) Make recommendations for relevant project activities and their costing |
| Logistical support / Admin assistance (co-financing) | 400 | 27.0 Financed by UNDP Core Funds (TRAC) | Functioning as the key logistical, clerical and administrative focal point and support to national activity coordinator, the incumbent will: (1) Ensure that PPG logistics are well organized, including travel, consultations, contracts and various payments. (2) Ensure that PPG finance is well managed and appropriately reported on, in compliance with UNDP Rules and Procedures. |
| International |  |  |  |
| Protected Areas & Alternative Livelihoods Specialist | 3,000 | 8.0 Financed by GEF | The consultant will lead, in close collaboration with the national Biodiversity Expert, in the production of the following PPG deliverables: - Application of the Protected Area Management Effectiveness Tracking Tool (METT) for the Community Natural Reserves (CNR), to be targeted by the project - Biodiversity threat analysis - Development of ecological indicators and definition of baseline and targets - Design of TOR for the development and implementation of a BD monitoring system to be managed by the National Ecovillages Agency (ANEV) - Development of brief feasibility analyses on the range of activities that were initially envisaged at PIF stage for public-private partnerships (refer to PPG paragraph 14). Generally, a key task for the specialist is to provide quality assurance on the different PPG products pertaining to the biodiversity component, as well as guiding national consultants in the preparation of their products. In addition, the consultant will: (1) Play a key role in designing the Ecovillages Survey and Assessment (2) Analyze and inventory relevant data from current and past projects to aid research work during the current project; (3) Review existing datasets on the ecological status of key biological resources in Ecovillages and make recommendations for the site selection and inclusion of ecological indicators in the project’s SRF; (4) Design the TOR for the biodiversity monitoring system specifically tailored to the needs of Ecovillages conservation and community co-management (through CNRs) including the provision of baseline data for the targeted sites; (4) Assess, based on existing studies, long term climate change planning for PA design to be carried out under the project; (5) Summarize proposals for the institutional framework for the management of Ecovillages at the local level, in collaboration with the remainder team members; (6) The PA Management Effectiveness Tracking Tool (METT), the UNDP Capacity Development scorecard and the UNDP Financial Sustainability scorecard (the latter only if applicable) will be completed to establish a framework for measuring capacity and financial performance in community management of the selected CRNs / Ecovillages and related PAs. |
| Climate Change Mitigation & Carbon Specialist | 3,000 | 8.0 Financed by GEF | The consultant will lead, in close collaboration with the national Energy specialist, in the production of the following PPG deliverables: - Development of energy profiles for typical Ecovillages - Determine the potential for a low carbon development path at the local level - Feasibility analysis and project costing for the development of Jathropha curcas plantations, of low carbon energy services and for the development of endemics' arboreta and massive afforestation - Development of brief feasibility analyses on the range of activities that were initially envisaged at PIF stage for public-private partnerships (refer to PPG paragraph 14). Generally, a key task for the specialist is to provide quality assurance on the different PPG products pertaining to the climate change and carbon components of the project, as well as guiding national consultants in the preparation of their products. In addition, the consultant will: (1) Using the tool “Bilan Carbone”, perform a preliminary assessment of carbon emission of a selection of Ecovillages,in terms of energy uses, land use and deforestation; (2) Set the baseline situation on energy services (3) Analyse the potential for low carbon options for energy services (solar, solar/wind grids, agrofuel, mini or micro-hydro) (4) List barriers to the promotion and adoption of low carbon options for energy services |
| Environment Economist (co-financing) | 3,000 | 10.0 Financed by UNDP Core Funds (TRAC) | The consultant will function as the technical team leader and will lead in the production of the following PPG deliverables: - Consolidation of the Ecovillage Model through the preparation and validation of the Ecovillages’ Strategy Paper - Assessment of the GEF Increment and conceptualization of the project strategy, also including cost-effectiveness considerations - Industry Engagement Strategy to aide in the moblisation of private-sector co-financing to the project; this will be done on the basis of brief feasibility analyses. More specifically, the feasibility analyses will have as key topics the range of activities that were initially envisaged at PIF stage for public-private partnerships. These include the following: - Tourism concessions - Carbon trading in the voluntary market - Briquetting or pelletizing process for non-woody biomass resources; and/or use of commercially available non-woody biomass fuel briquettes/pellets - Development of pilot “energy hubs” (refer to PIF for more information) - Production, development and promotion of use of locally produced agrofuel from Jatropha curcas - Massive afforestation and the development of arboretums for indigenous species of global importance - Organic agriculture The consultant will play a pivotal role in project development by guiding, coaching and assisting other consultants in the production of their deliverables, ensuring the alignment of the project with the best practices in GEF project design. This will include working closely with the Activity Coordinator in structuring and planning PPG implementation, and taking lead responsibility for the drafting of the required documents, namely the UNDP PRODOC and the GEF CEO Endorsement Request, for review by both the UNDP Country Office and the Regional Technical Advisor (RTA) responsible for the project at the UNDP Environment and Energy Group (EEG). The consultant wills equally advice the National Stakeholder Engagement Expert / Activity Coordinator in the tasks of mobilising co-financing for the project, participating in negotiations if needed. Finally, the consultant will ensure that: (1) The project is properly scoped, costed (with a thorough and complete Total Budget and Workplan), that risks have been considered, assessed and that a suitable risk mitigation strategy has been proposed; (2) A thorough analysis of the barriers to achieving the proposed project outcomes is in line with the several PPG findings and duly informs the composition of the Strategic Results Framework; (3) Sound management and implementation arrangements will contribute to project success and sustainability; (4) A learning (adaptive management) plan, as well as a replication plan, have been included in the project; (5) The project contains an overall project Monitoring and Evaluation Plan, with recommendations on how to track the project’s progress and effectiveness, and the baseline and target values on indicators. |

During PIF preparation there were several discussions between UNDP and the Senegalese government on a key opportunity cost of this project with respect to PAs. The current project is proposing to develop and operationalise on a  pilot basis  CNRs as part and parcel of the Ecovillage model. The project further proposes to do that in the vicinity of important core PAs. Yet, it is patent that there visible are gaps in terms of core PA management that will not be addressed by the project. The argument for addressing threats to PAs by developing alternative livelihoods in the buffer zone of these areas is that much of these threats come exactly from degrading and unsustainable activities carried out by communities living in buffer zones. Other threats to PAs are linked to insufficient and ineffective management from the part of park authorities. These will need to be addressed by a complementary and comprehensive initiative. The government committed to seeking solutions to the issue of core PA management in collaboration with its partners.

That is: an assessment of ongoing and planned activities in the absence of the GEF and the expected/projected loss of global environmental benefits if left unattended.

The ideal length of a feasibility analysis would five pages. As a minimum these studies will include: (i) description of activities and potential locations; (ii) technology, know-how and inputs needed; (iii) estimated costs per unit and according to desired scale; (iv) benefits. The idea is that brief feasibility analyses will be used to show in a preliminary fashion that certain activities are feasible and under which conditions. If business interest is leveraged, the private sector will be in charge of carrying out more detailed business plans for these activities.

An ‘energy hub’ in an Ecovillage produces sufficient electricity to satisfy the following needs: (1) collective public services (schools, dispensaries); (2) artificial lighting for public spaces; (3) artificial lighting for homes; (4) power supply for telecommunication (cellular phones); (5) access to water.